2021 Work Plan | 117432947 | Not Scheduled | T2 DI SMRTVLL-CMP FR WST 14/272 RMV STRW | 43852549 | SMARTVILLE-CAMP FAR WEST | 014/272 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-06-06 | 2024-06-06 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.307871 | 39.0325 | ETL.7970 | 40673317 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117433130 | Feb | T2NT DI ORL-TT-TBL MT#1 002/009 INS MRKS | 43932169 | MTN #1(CDWR) | 002/009 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-06-06 | 2021-06-06 |  |  | 2021-02-20 | 2021-02-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.512072 | 39.5465 | ETL.6621 | 42580632 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117433133 | Q2 | T2 DI CSCD-BNTN-DSCHTES 2/57 INS GYWW | 43690811 | CASCADE-BENTON-DESCHUTES | 002/057 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-06-07 | 2020-06-07 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.322291 | 40.6194 | ETL.6310 | 40600665 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117433135 | Q2 | T2 DI CSCD-BNTN-DSCHTES 2/57 RPR SPLW | 43690811 | CASCADE-BENTON-DESCHUTES | 002/057 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-07 | 2020-06-07 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.322291 | 40.6194 | ETL.6310 | 40600665 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117433163 | Q2 | T2 DI FLTN-MOLNO-COTATI 16/309 INS BOND | 43920595 | FULTON-MOLINO-COTATI | 016/309 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-06-07 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.732804 | 38.3098 | ETL.6910 | 40877338 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-05 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117433194 | Not Scheduled | T2 DI MALIN-RND MTN #2 66/331 CANCEL | 44305271 | MALIN-ROUND MTN #2 | 066/331 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-05 | 2023-06-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.719174 | 41.1398 | ETL.6020 | 40586427 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117433382 | Q2 | T2 DI LOWER LAKE-HOMESTAKE 3/11 INS HRDW | 43865623 | LOWER LAKE-HOMESTAKE TAP | 003/011 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-06-07 | 2021-05-31 | 2021-05-12 | 2021-05-12 | 2021-05-12 | 2021-05-12 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.566579 | 38.8991 | ETL.1481 | 44401312 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-02 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117433446 | Q2 | T2 DI KONOCTI-MIDDLETOWN 24/5 RPL STRW | 31490901 | KONOCTI-MIDDLETOWN | 024/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-05 | 2021-05-31 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.708489 | 38.9205 | ETL.6380 | 40747632 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-26 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117433580 | Not Scheduled | DI TRACY-LOS BANOS 008/045 RPR GYWS | 43851678 | TRACY-LOS BANOS | 008/045 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-06 | 2020-06-06 | [6 empty] | Tower guy |  | LATE | Central | WSIP | [6 empty] | '-121.526956 | 37.6901 | ETL.6130 | 40753747 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117433617 | Q2 | T2 DI TULE-SPRINGVILLE 20/9 INST GYWW | 44323689 | TULE-SPRINGVILLE | 020/009 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-06-06 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-118.804742 | 36.137 | ETL.9040 | 40873006 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117433951 | Not Scheduled | T2 DI DRUM-SUMMIT#2 19/236 INS MRKW | 43947609 | DRUM-SUMMIT #2 | 019/236 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-06 | 2020-04-15 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.453362 | 39.3182 | ETL.1450 | 44558995 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117434241 | Not Scheduled | T2 DI RND MTN-CTTNWOOD#3 43/371 PNT STRS | 43755801 | ROUND MTN-COTTONWOOD #3 | 043/371 | ICQ | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-06 | 2021-06-06 | [6 empty] | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [6 empty] | '-122.104095 | 40.5933 | ETL.5650 | 40595049 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117434309 | Q2 | T2 DI KONOCTI-MIDDLETOWN 24/3 RPR GYWS | 43908958 | KONOCTI-MIDDLETOWN | 024/003 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-05 | 2021-05-31 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.712219 | 38.9215 | ETL.6380 | 44244869 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117434640 | Not Scheduled | T2 DI IGN ALT SAU #2 16/114 GRND WSH INS | 43919392 | IGNACIO-ALTO-SAUSALITO #2 | 016/114 | ICD | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-06 | 2020-06-06 | 2020-09-01 | 2020-09-01 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.502237 | 37.8598 | ETL.7170 | 40740661 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  | 2019-07-12 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117434748 | Q2 | DI CASCADE-BNTN-DSCHTS A5/110 RPR INSW | 43690811 | CASCADE-BENTON-DESCHUTES | A005/110 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-07 | 2020-06-07 |  |  | 2021-04-30 | 2021-04-12 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.296814 | 40.5886 | ETL.6310 | 40759477 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117434993 | Q2 | T3 DI DRUM-HIGGINS 2/24L RPL PL | 31509929 | DRUM-HIGGINS | 002/024 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-08 | 2019-12-08 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.790597 | 39.2305 | ETL.4393 | 44172164 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-09-24 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117434995 | Q2 | T3 DI DRUM-HIGGINS 2/24R RPL PL | 31509929 | DRUM-HIGGINS | 002/024 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-08 | 2019-12-08 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.790597 | 39.2305 | ETL.4393 | 44172165 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-09-24 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117435035 | Not Scheduled | T2 DI COLGATE-PALERMO 010/201 RPR GYWW | 43878561 | COLGATE-PALERMO | 010/201 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-07 | 2020-06-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.363655 | 39.3656 | ETL.6500 | 40767115 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117435170 | Feb | T2 DI EL DRD-MSSR FLT #1 10/084 RPR GYWW | 43748116 | ELDORADO-MISSOURI FLAT #1 | 010/084 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-05 | 2020-06-05 |  |  | 2021-02-21 | 2021-02-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.77909 | 38.7399 | ETL.1530 | 40760877 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117435306 | Not Scheduled | T2 DI SPAULDING-SUMMIT 002/108 RPL POLE | 31453471 | SPAULDING-SUMMIT | 002/108 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-08 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.59853 | 39.3138 | ETL.8060 | 40618288 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117435564 | Q2 | T2 DI CTTNWOD-RED BLUFF014/290 RPR STRW | 43939201 | COTTONWOOD-RED BLUFF | 014/290 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-06 | 2020-06-06 |  |  | 2021-04-01 | 2020-09-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.254537 | 40.217 | ETL.6660 | 40909626 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117435772 | Feb | T3 DI KILARC-CDR CRK 13/285 RPL PL | 31459424 | KILARC-CEDAR CREEK | 013/285 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-30 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.937812 | 40.7911 | ETL.7290 | 40810437 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-08-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117435865 | Not Scheduled | T2NT DI MLN-RND MTN#2 079/403 CANCEL | 43621093 | MALIN-ROUND MTN #2 | 079/403 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-05 | 2021-06-05 | [6 empty] | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.893136 | 41.0108 | ETL.6020 | 40650409 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117436101 | Not Scheduled | T2 DI SPAULDING-SUMMIT 001/074 INST GMKW | 43923456 | SPAULDING-SUMMIT | 001/074 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-11 | 2021-06-11 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.615578 | 39.3106 | ETL.8060 | 40652032 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117436102 | Not Scheduled | T2 DI SPAULDING-SUMMIT 001/074 INST MRKW | 43923456 | SPAULDING-SUMMIT | 001/074 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-11 | 2021-06-11 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.615578 | 39.3106 | ETL.8060 | 40652032 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117436509 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/10 INS MRKW | 43923456 | SPAULDING-SUMMIT | 000/010 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-10 | 2021-06-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.640687 | 39.3238 | ETL.8060 | 40589998 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117436556 | Feb | T2 EI TRINITY-MAPLE CRK 014/004 RPL INSW | 31472111 | TRINITY-MAPLE CREEK | 014/004 | 93I | E | Pre-2020_(2) High fire spread TD |  | 2019-06-10 | 2021-05-31 | 2020-12-13 | 2020-12-15 | 2021-02-27 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Weather | AT RISK - weather impacts | '-123.306668 | 40.7074 | ETL.8170 | 40781218 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  | 2019-10-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-10-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117436625 | Not Scheduled | DI CARIBOU-PALERMO 1/12 RPR STRT | 43932153 | CARIBOU-PALERMO | 001/012 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-04 | 2020-06-04 | [8 empty] | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.541011 | 39.4665 | ETL.3190 | 40674849 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117436626 | Q2 | T2 DI KONOCTI-MIDDLETON 20/0 RPR GYWW | 43919877 | KONOCTI-MIDDLETOWN | 020/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-06 | 2020-06-06 | 2021-04-19 | 2021-04-23 | 2021-04-19 | 2021-04-19 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.586176 | 38.8518 | ETL.6380 | 40615071 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117436967 | Not Scheduled | T2NT DI SPAULDING-SMMT 000/035 INST MRKW | 43923456 | SPAULDING-SUMMIT | 000/035 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-10 | 2021-06-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.628119 | 39.3213 | ETL.8060 | 40746162 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117437029 | Q2 | T2 DI SBRNT-GRZZLY-CLRMT#1 0/10 RPR FOND | 43752388 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 000/010 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-07 | 2020-06-07 |  |  | 2021-05-31 | 2021-05-24 |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.204643 | 37.9015 | ETL.3740 | 40770752 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-13 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117437064 | Not Scheduled | T2 EI IGNCO-ALTO-SSLTO #1 11/80 RMV VEGN |  | IGNACIO-ALTO-SAUSALITO #1 | 011/080 | HNA | E | Pre-2020_(9a) Other ignition related | Budget Owner (Veg/Land/Road) | 2019-06-11 | 2021-05-31 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.516967 | 37.9081 | ETL.7160 | 40754844 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117437105 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/34 INST MRKW | 43923456 | SPAULDING-SUMMIT | 000/034 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-10 | 2021-06-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.628689 | 39.3214 | ETL.8060 | 40751892 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117437273 | Q2 | T2 DI TULE-SPRINGVILLE 013/009 WASH INSW | 44637082 | TULE-SPRINGVILLE | 013/009 | ICD | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-10 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.907348 | 36.1098 | ETL.9040 | 40872985 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117437393 | Not Scheduled | T2NT DI SPLDNG-SMMT 002/079 INST MRKW | 43923456 | SPAULDING-SUMMIT | 002/079 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-10 | 2021-06-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.613407 | 39.311 | ETL.8060 | 40603894 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117437417 | Not Scheduled | T2 DI SPAULDING-SUMMIT 10/351 RPL STRW | 31495368 | SPAULDING-SUMMIT | 010/351 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-10 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.473081 | 39.3179 | ETL.8060 | 44224995 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117437984 | Q2 | T2 DI TULE-SPRINGVILLE 018/010 WASH INSW | 44637082 | TULE-SPRINGVILLE | 018/010 | ICD | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-10 | 2020-06-10 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.828597 | 36.1185 | ETL.9040 | 40586429 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117438076 | Not Scheduled | T2 DI TGR CRK-VLY SPRNG 015/126 RPR FOND | 43852924 | TIGER CREEK-VALLEY SPRINGS | 015/126 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-10 | 2024-06-10 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.684586 | 38.3064 | ETL.5790 | 40765491 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 10 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117438192 | Q2 | T2 DI LAYTNVLLE-WLLTS 016/004 RPL POLE | 31490917 | LAYTONVILLE-WILLITS | 016/004 | 70Y | F | Pre-2020_(4) TD tag on high spread line |  | 2019-06-08 | 2022-06-08 | 2021-05-26 | 2021-05-28 | 2021-05-26 | 2021-05-26 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.453977 | 39.5991 | ETL.8360 | 44356041 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-27 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117438308 | Q2 | T2 DI TULE-SPRINGVILLE 026/009 RPR SPLS | 44323595 | TULE-SPRINGVILLE | 026/009 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-10 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.712372 | 36.1612 | ETL.9040 | 43604137 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117438445 | Not Scheduled | DI DRUM-SUMMIT#2 17/211L RPL PL | 31521949 | DRUM-SUMMIT #2 | 017/211 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-08 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.489779 | 39.3159 | ETL.1450 | 44549869 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117438525 | Not Scheduled | DI DRUM-SUMMIT#2 17/211R REPL PL | 31521949 | DRUM-SUMMIT #2 | 017/211 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-08 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.489779 | 39.3159 | ETL.1450 | 44549967 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117438541 | Not Scheduled | DI DRUM-SUMMIT#2 17/211C REPL PL | 31521949 | DRUM-SUMMIT #2 | 017/211 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-08 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.489779 | 39.3159 | ETL.1450 | 44549943 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117438582 | Feb | T3 DI KLARC-CDR CRK 9/210 RPR STRW | 43685209 | KILARC-CEDAR CREEK | 009/210 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-07 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.977905 | 40.7441 | ETL.7290 | 40868041 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2020-02-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117438587 | Q2 | T2 DI CNTRVL-TBL MTN-RVLL 10/198 INS MRK | 43903760 | CENTERVILLE-TABLE MTN-OROVILLE | 010/198 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-06-10 | 2021-06-10 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.634085 | 39.6481 | ETL.6330 | 40675499 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117438633 | Q2 | T2 DI TULE-SPRINGVILLE 013/007 WASH INSW | 44637082 | TULE-SPRINGVILLE | 013/007 | ICD | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-07 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.909662 | 36.1097 | ETL.9040 | 40807680 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117439085 | Q2 | T2 DI HAT CREEK #1-W WD 20/385 RPR STRW | 43736798 | HAT CREEK #1-WESTWOOD | 020/385 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-10 | 2020-06-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.274675 | 40.742 | ETL.7030 | 40592092 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117439504 | Not Scheduled | T2 DI COLGT-PALRM 10/200 RPL STRW | 31517754 | COLGATE-PALERMO | 010/200 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-10 | 2020-06-10 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.362776 | 39.3652 | ETL.6500 | 40664525 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117439540 | Not Scheduled | T2 DI DRUM-SUMMIT#1 22/269 RPL POLE | 31498145 | DRUM-SUMMIT #1 | 022/269 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-07 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.402117 | 39.3104 | ETL.1440 | 40597039 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117439601 | Q3 | T2 DI TDEWATER-SOBRANTE 022/104 RPR FOND | 44509425 | TIDEWATER-SOBRANTE | 022/104 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-11 | 2020-06-11 |  |  | 2021-07-30 | 2021-07-26 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.203201 | 37.9169 | ETL.5770 | 40745891 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2 | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117439727 | Q2 | T2 DI TUL SPR 20/14 RPR GYWW | 44323693 | TULE-SPRINGVILLE | 020/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-30 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.801146 | 36.1375 | ETL.9040 | 40749767 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117439768 | Q2 | DI KONOCTI-MIDDLETOWN 28/4 RPR STRW | 43919877 | KONOCTI-MIDDLETOWN | 028/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-08 | 2020-06-08 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235471 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117439795 | Q2 | DI KONOCTI-MIDDLETOWN 28/4 RPR STRW | 43919877 | KONOCTI-MIDDLETOWN | 028/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-08 | 2020-06-08 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235473 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117439810 | Q2 | T2 DI TUL SPR 20/14 RPR SPLW | 44323697 | TULE-SPRINGVILLE | 020/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-30 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.801146 | 36.1375 | ETL.9040 | 40749767 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117439880 | Q2 | DI KONOCTI-MIDDLETOWN 28/4 RPR GYWW | 43919877 | KONOCTI-MIDDLETOWN | 028/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-08 | 2020-06-08 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235471 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117439916 | Q2 | DI KONOCTI-MIDDLETOWN 28/4 RPR GYWW | 43919877 | KONOCTI-MIDDLETOWN | 028/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-08 | 2020-06-08 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235472 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117439934 | Q2 | DI KONOCTI-MIDDLETOWN 28/4 RPR GYWW | 43919877 | KONOCTI-MIDDLETOWN | 028/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-08 | 2020-06-08 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235473 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117439935 | Q2 | DI KONOCTI-MIDDLETOWN 28/4 GRD WSH INSU | 43919388 | KONOCTI-MIDDLETOWN | 028/004 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-08 | 2020-06-08 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235471 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117440045 | Q2 | DI KONOCTI-MIDDLETOWN 28/4 GRD WSH INSU | 43919388 | KONOCTI-MIDDLETOWN | 028/004 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-08 | 2020-06-08 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235472 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117440178 | Mar | T2 DI MNDCN-WLLTS-FRT BRGG 20/4 RPR GYWW | 43891087 | MENDOCINO-WILLITS-FORT BRAGG | 020/004 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-06-07 | 2021-05-31 |  |  | 2021-03-18 | 2021-03-15 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.456285 | 39.3933 | ETL.7550 | 40769233 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117440834 | Not Scheduled | T2 DI COLLINS PN TAP 000/027 RPR GYWW | 43919591 | COLLINS PINE TAP | 000/027 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-10 | 2020-06-10 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.242703 | 40.2994 | ETL.7001 | 42623475 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117440925 | Not Scheduled | T2 SPAULDING-SUMMIT 000/011 RPL INSW | 31463883 | SPAULDING-SUMMIT | 000/011 | 93I | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-12 | 2020-06-12 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.640432 | 39.3237 | ETL.8060 | 40610596 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117441193 | Not Scheduled | T2NT DI COLGATE-PALMO 004/078 INST MRKW | 43910642 | COLGATE-PALERMO | 004/078 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-11 | 2021-06-11 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.264242 | 39.333 | ETL.6500 | 40874639 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117441565 | Not Scheduled | DI VALLEY SPRINGS-CLAY 14/194 RPR STRW | 43853795 | VALLEY SPRINGS-CLAY | 014/194 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-11 | 2020-06-11 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.911201 | 38.2945 | ETL.8264 | 40904795 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117442542 | Not Scheduled | DI JEFFERSON-STNFRD 2/67 RPL PL | 31434138 | JEFFERSON-STANFORD (NO FLY) | 002/067 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-11 | 2020-06-11 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-122.246559 | 37.4654 | ETL.7220 | 40694682 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117442609 | Mar | DI CLEAR LAKE-HOPLAND 1/7 RPL PL | 31488229 | CLEAR LAKE-HOPLAND | 001/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-10 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-24 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.055913 | 38.9663 | ETL.6390 | 40808130 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117442699 | Feb | T2 DI WINTU TAP 001/038 RPR GYWW | 43760225 | WINTU TAP | 001/038 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-10 | 2020-06-10 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.368724 | 40.5928 | ETL.6311 | 40828032 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117442866 | Not Scheduled | T2 DI MAL RND MTN #2 64/323 CANCEL | 43939115 | MALIN-ROUND MTN #2 | 064/323 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-05 | 2023-06-05 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.700588 | 41.1545 | ETL.6020 | 40651401 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117442940 | Not Scheduled | T2 DI JEFFERSON-STANFORD 1/42 RPR GYWW | 43877613 | JEFFERSON-STANFORD (NO FLY) | 001/042 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-11 | 2020-06-11 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.259654 | 37.4634 | ETL.7220 | 40612104 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117443014 | Q2 | T2 DI DRUM-SPAULDING 07/188 RPL STRW | 31502001 | DRUM-SPAULDING | 007/188 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2021-05-31 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.664223 | 39.3093 | ETL.6770 | 40825229 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117443137 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 1/40 INST MRKW | 43923456 | SPAULDING-SUMMIT | 001/040 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-10 | 2021-06-10 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.62615 | 39.3202 | ETL.8060 | 40650035 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117443276 | Q2 | T2 DI DRUM-SPAULDING 08/218 RPL POLE | 31502001 | DRUM-SPAULDING | 008/218 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2021-05-31 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.649472 | 39.3174 | ETL.6770 | 40869678 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117443376 | Not Scheduled | T2 DRUM-SUMMIT #2 023/276L RPL STRW | 31451466 | DRUM-SUMMIT #2 | 023/276 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-13 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.390765 | 39.3292 | ETL.1450 | 44557732 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117443385 | Q2 | T3 DI GOLD HILL #1 25/368 RPL STRW | 31502809 | GOLD HILL #1 | 025/368 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2019-12-12 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.847953 | 38.5749 | ETL.6950 | 40768907 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-03-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117443546 | Not Scheduled | T2 DI COLGATE-PALERMO 3/56 RPL PL | 31457073 | COLGATE-PALERMO | 003/056 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2020-06-12 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.250392 | 39.3241 | ETL.6500 | 40814347 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117443558 | Q2 | T3 DI FRNCH MDWS-MDL FRK 4/82 RPL POLE | 31504550 | FRENCH MEADOWS-MIDDLE FORK | 004/082 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-06-10 | 2021-05-31 |  |  | 2021-05-23 | 2021-05-17 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | 2021 - Rock hole was not deep enough to set the pole | '-120.466787 | 39.0446 | ETL.6870 | 40751842 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2020-09-21 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117443655 | Not Scheduled | T2 DI JEFFERSON-STANFORD 2/59 RPR GYWW | 43877613 | JEFFERSON-STANFORD (NO FLY) | 002/059 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-11 | 2020-06-11 | 2020-08-12 | 2020-08-21 | [5 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.251859 | 37.4643 | ETL.7220 | 40767836 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31 | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117443659 | Not Scheduled | DI PITTSBURG-MARTINEZ#1 003/020 RPR FOND | 44238519 | PITTSBURG-MARTINEZ #1 | 003/020 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-11 | 2020-06-11 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.915192 | 37.9986 | ETL.3320 | 40581782 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117444561 | Not Scheduled | T3 DI FRE MEA MID FRK 4/79 RMV VEG |  | FRENCH MEADOWS-MIDDLE FORK | 004/079 | HNA | F | Pre-2020_(9a) Other ignition related |  | 2019-06-10 | 2022-12-10 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.46371 | 39.0448 | ETL.6870 | 40693729 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | HNA | Not Scheduled |  |  | 2020-05-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117445449 | Not Scheduled | T3 DI DRUM-HIGGINS 010/094 RPL HRDT | 43903301 | DRUM-HIGGINS | 010/094 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-06-10 | 2019-12-10 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.890562 | 39.1778 | ETL.4393 | 40586122 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117445504 | Mar | T2 DI KNCTI-MDDLTWN 015/000 RPR GYWW | 43919877 | KONOCTI-MIDDLETOWN | 015/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-11 | 2020-06-11 | 2021-03-01 | 2021-03-04 | 2021-03-02 | 2021-03-02 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.574752 | 38.7821 | ETL.6380 | 44370573 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117445660 | Not Scheduled | T2 DI SPAULDING-SUMMIT 011/372 RPL STRW | 31495368 | SPAULDING-SUMMIT | 011/372 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-10 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.460245 | 39.3189 | ETL.8060 | 40761663 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117445747 | Not Scheduled | T2NT DI TGR CRK-VLY SPRG 010/078 REPAINT | 43852921 | TIGER CREEK-VALLEY SPRINGS | 010/078 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-12 | 2021-06-12 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.639514 | 38.376 | ETL.5790 | 40858394 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117445806 | Mar | T2 DI PLCR-DL MR 5/110 RPR STRW | 43912223 | PLACER-DEL MAR | 005/110 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-10 | 2020-06-10 |  |  | 2021-03-31 | 2021-03-27 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.15477 | 38.8523 | ETL.7800 | 40763994 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117446814 | Not Scheduled | T2 DI COLGATE-PALERMO 010/202 RPR SPLW | 43878561 | COLGATE-PALERMO | 010/202 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-10 | 2020-06-10 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.364245 | 39.3661 | ETL.6500 | 40766515 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117447047 | Not Scheduled | T2NT DI PIT #5 RND MTN #1 8/81 PNT TWR | 44322478 | PIT #5-ROUND MTN #1 | 008/081 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-11 | 2021-06-11 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.92994 | 40.8824 | ETL.5420 | 40680602 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117447351 | Mar | T2 DI CLEAR LAKE-HPLND 1/2 RPL POLE | 31501313 | CLEAR LAKE-HOPLAND | 001/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-11 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-24 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.061092 | 38.9693 | ETL.6390 | 40699068 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117447352 | Not Scheduled | SAN MIGUEL-PASO ROBLES 9/150 RPL POLE | 31454632 | SAN MIGUEL-PASO ROBLES | 009/150 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | 2018-03-30 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.680402 | 35.6251 | ETL.9390 | 40754894 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117447450 | Not Scheduled | T2 DI SPAULDING-SUMMIT 015/491 INS MRKW | 43923456 | SPAULDING-SUMMIT | 015/491 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-12 | 2021-06-12 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.383007 | 39.3283 | ETL.8060 | 40650067 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117447486 | Q2 | T3 DI DRUM-HIGGINS 2/27R REPL PL | 31423108 | DRUM-HIGGINS | 002/027 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2019-12-12 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.795057 | 39.2286 | ETL.4393 | 44172274 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117447779 | Not Scheduled | T2NT DI DRM SUM #2 28/333 RPR GYWW | 43947611 | DRUM-SUMMIT #2 | 028/333 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-10 | 2020-06-10 | [7 empty] | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1450 | 44420820 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117447947 | Not Scheduled | T2 DI SPAULDING-SUMMIT 001/045 INST GMKW | 43923456 | SPAULDING-SUMMIT | 001/045 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-13 | 2021-06-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.625174 | 39.3189 | ETL.8060 | 40878046 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117447995 | Not Scheduled | T2 DI BRCBRG JCT-MRPSA TAP 5/14 RPR STRW | 43825046 | BRICEBURG JCT-MARIPOSA TAP | 005/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-10 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.986086 | 37.521 | ETL.8651 | 40748193 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-06-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117448209 | Not Scheduled | T3NT DI MORAGA-SAN LEAND #3 4/32 PNT TWR | 43728142 | MORAGA-SAN LEANDRO #3 | 004/032 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-12 | 2023-06-12 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.127777 | 37.7936 | ETL.2790 | 40657111 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117448341 | Q2 | DI HAT CREEK #1-WESTWOOD 49/952 RPL POLE | 31454829 | HAT CREEK #1-WESTWOOD | 049/952 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2020-06-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.016208 | 40.384 | ETL.7030 | 40868255 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117448508 | Q2 | T2 DI OLEUM-G #1 000/007 REPR STRT | 44229259 | OLEUM-G #1 | 000/007 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.243946 | 38.0399 | ETL.3150 | 40804762 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117448554 | Q2 | T2 DI HAT CREEK#1 WSTWOOD 2/61 RPR GYWW | 43939287 | HAT CREEK #1-WESTWOOD | 002/061 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2020-06-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.487518 | 40.9194 | ETL.7030 | 41198412 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117448570 | Not Scheduled | T2 DI OLEUM-G #1 000/007 PAINT STRS | 44586166 | OLEUM-G #1 | 000/007 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-13 | 2020-06-13 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.243946 | 38.0399 | ETL.3150 | 40804762 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117448578 | Not Scheduled | T2 DI SPAULDING-SUMMIT 001/043 REPL POLE | 31415019 | SPAULDING-SUMMIT | 001/043 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-10 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.625593 | 39.3195 | ETL.8060 | 40828117 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-03-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117448832 | Not Scheduled | T3 DI FRNCH MDWS-MDL FRK 8/158 RPR GYWW | 43870412 | FRENCH MEADOWS-MIDDLE FORK | 008/158 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-06-11 | 2019-12-11 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.539137 | 39.0231 | ETL.6870 | 40611462 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117449068 | Feb | T2 DI SMTVLE-NICUS #2 0/3 GRD WASH INSS | 43938536 | SMARTVILLE-NICOLAUS #2 | 000/003 | ICD | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-13 | 2020-06-13 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.303105 | 39.2076 | ETL.8000 | 44177579 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117449644 | Q2 | T2 DI HAT CRK#1 WESTWOOD 8/166 REPL PL | 31456189 | HAT CREEK #1-WESTWOOD | 008/166 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.411245 | 40.8709 | ETL.7030 | 40601695 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2020-06-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117450658 | Feb | DI TRINITY-MAPLE CREEK 0/9 RPL STRW | 31471999 | TRINITY-MAPLE CREEK | 000/009 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-22 |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.938732 | 40.7229 | ETL.8170 | 40906228 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-04-14 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2020-04-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117450667 | Q2 | T2 DI HAT-CREEK #1-WSTWOOD 0/20 RPL PL | 31456189 | HAT CREEK #1-WESTWOOD | 000/020 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2020-06-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.527695 | 40.9256 | ETL.7030 | 40815030 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117450687 | Q2 | T2 EI TULE-SPRVILLE 026/007 RPL POLE | 31455758 | TULE-SPRINGVILLE | 026/007 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-17 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.71499 | 36.1606 | ETL.9040 | 40807817 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117450762 | Not Scheduled | T3 DI FULTON-IGNACIO 1/9 CANCEL | 43761412 | FULTON-IGNACIO #1 | 001/009 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-06-11 | 2019-12-11 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.736555 | 38.4975 | ETL.4680 | 40863245 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117450983 | Not Scheduled | T2NT DI COLGATE-CHALLENGE 0/14 INS MRKW | 43910648 | COLGATE-CHALLENGE | 000/014 | ICS | F | 2020_(1a) PSPS |  | 2019-06-13 | 2023-06-13 | [6 empty] | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [6 empty] | '-121.190891 | 39.3398 | ETL.6480 | 42549793 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117450987 | Not Scheduled | T2NT DI PITTSBURG-TESLA#1 4/19 PNT TWR | 44586176 | PITTSBURG-TESLA #1 | 004/019 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-12 | 2021-06-12 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-121.908272 | 37.9831 | ETL.5510 | 40862418 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117451220 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/31 RPR STRW | 43923456 | SPAULDING-SUMMIT | 000/031 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-14 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.630442 | 39.3217 | ETL.8060 | 40581014 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117451430 | Not Scheduled | T2 DI HAAS-MCCALL 3/24 RPR SPLS | 43863061 | HAAS-MCCALL | 003/024 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2020-06-12 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-119.06837 | 36.9061 | ETL.4850 | 40761914 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117451477 | Q2 | T2 DI HAAS-MCCALL 3/29 RPR STRT | 44140314 | HAAS-MCCALL | 003/029 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2021-05-31 |  |  | 2021-06-15 | 2021-06-02 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.079558 | 36.9103 | ETL.4850 | 40858142 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-06-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117452457 | Not Scheduled | DI VALLEY SPRINGS #1 005/091 REPR STRW | 43853790 | VALLEY SPRINGS #1 | 005/091 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.832255 | 38.1766 | ETL.8210 | 40905506 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117452498 | Q3 | T2 DI HAAS-MCCLL 5/37 RPR FOND | 43863061 | HAAS-MCCALL | 005/037 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-12 | 2024-06-12 |  |  | 2021-08-15 | 2021-07-02 |  |  | Likely MAT error - delink to correct | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.106287 | 36.905 | ETL.4850 | 40813914 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2019-06-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117452687 | Q2 | T3 DI DRUM SPAULD 1/39 BOND HRDW | 43921229 | DRUM-SPAULDING | 001/039 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-06-12 | 2019-12-12 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.743018 | 39.258 | ETL.6770 | 40809630 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117452727 | Not Scheduled | T2 DI HAAS-MC CALL 001/013 RPR INSS | 43863061 | HAAS-MCCALL | 001/013 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2020-06-12 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-119.044071 | 36.9127 | ETL.4850 | 40689789 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117453156 | Q3 | T2 DI DELTA-MTN GT JCT 15/187 INST HRDW | 43866636 | DELTA-MOUNTAIN GATE JCT | 015/187 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-06-12 | 2021-05-31 |  |  | 2021-07-30 | 2021-07-27 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.308376 | 40.7443 | ETL.6750 | 44564933 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117453201 | Q3 | T2 DI DELTA-MTN GT JCT 15/187R INST HRDW | 43866636 | DELTA-MOUNTAIN GATE JCT | 015/187 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-06-12 | 2021-05-31 |  |  | 2021-07-30 | 2021-07-27 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.308376 | 40.7443 | ETL.6750 | 44564934 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117455368 | Not Scheduled | T2 DI SPAULDING-SUMMIT 00/25 INST MRKW | 43923458 | SPAULDING-SUMMIT | 000/025 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-14 | 2021-06-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.633724 | 39.3223 | ETL.8060 | 40751891 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117455699 | Mar | T2 DI MTN QRS 2/27A RPR STRS | 43869988 | MTN QUARRIES TAP | 002/027A | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-12 | 2020-06-12 |  |  | 2021-03-15 | 2021-03-15 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.027394 | 38.9127 | ETL.6991 | 44191124 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117455820 | Not Scheduled | T2 DI COLGATE-CHALLENGE 1/23 RPR STRW | 43910648 | COLGATE-CHALLENGE | 001/023 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.189466 | 39.3444 | ETL.6480 | 40594206 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117455826 | Not Scheduled | T2 DI PITTSBURG-TESLA#1 7/34 RPR STRT | 43753186 | PITTSBURG-TESLA #1 | 007/034 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-11 | 2020-06-11 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.859374 | 37.9467 | ETL.5510 | 40752491 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-21 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117455848 | Q2 | T2 DI HT CRK #1 WW 36/702 RPL PL | 31456280 | HAT CREEK #1-WESTWOOD | 036/702 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.066967 | 40.5614 | ETL.7030 | 40601708 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | In Review | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117455991 | Not Scheduled | T2 DI SPAULDING-SUMMIT 15/498 RPR GYWW | 43923458 | SPAULDING-SUMMIT | 015/498 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-12 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.379556 | 39.3244 | ETL.8060 | 40618286 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117456059 | Q2 | DI IGNACIO-ALTO 15/151 RPL PL | 31471947 | IGNACIO-ALTO | 015/151 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-12 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | WSIP | [6 empty] | '-122.513036 | 37.921 | ETL.7150 | 40876331 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2020-07-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117456158 | Not Scheduled | DI DRUM-SUMMIT #1 017/205L INST MRKW | 43910104 | DRUM-SUMMIT #1 | 017/205 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-10 | 2021-06-10 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.490905 | 39.3154 | ETL.1440 | 44769591 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117456170 | Not Scheduled | T3 DI COLGATE-CHALLENGE 1/27 RPR STRW | 43910648 | COLGATE-CHALLENGE | 001/027 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.186917 | 39.3464 | ETL.6480 | 40767123 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117456191 | Q3 | T2 DI TESLA-NEWARK #2 012/085 RPR FOND |  | TESLA-NEWARK #2 | 012/085 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-10 | 2020-06-10 |  |  | 2021-07-23 | 2021-07-19 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.772939 | 37.6358 | ETL.5354 | 41152630 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-10-01 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117456289 | Q2 | T2 DI COLGATE-PALRMO 19/380 GRD WSH INSU | 43878259 | COLGATE-PALERMO | 019/380 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2020-06-12 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.463647 | 39.4466 | ETL.6500 | 40664457 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117456429 | Q2 | T2 DI VOLTA-DESCHUTES 19/436 RPR STRW | 43939089 | VOLTA-DESCHUTES | 019/436 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2021-05-31 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.220937 | 40.5506 | ETL.8290 | 40877249 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117456493 | Q2 | T2 DI HT CRK #1 WW 25/488 RPL PL | 31456280 | HAT CREEK #1-WESTWOOD | 025/488 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.206318 | 40.6821 | ETL.7030 | 40876190 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117456522 | Q2 | T2 DI HAAS-MCL 5/34 RPR STRT | 44140314 | HAAS-MCCALL | 005/034 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2021-05-31 |  |  | 2021-06-15 | 2021-06-02 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.097322 | 36.9073 | ETL.4850 | 40746545 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-06-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117456574 | Q2 | DI HAT CRK#1-WESTWOOD 47/907 RPL STRW | 31456189 | HAT CREEK #1-WESTWOOD | 047/907 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-06-10 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 7/2020 | '-121.021968 | 40.4177 | ETL.7030 | 40667988 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117456576 | Not Scheduled | T2NT DI RND MTN CTTNWD R002/19 PNT STRS | 43755801 | ROUND MTN-COTTONWOOD #3 | R002/019 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-06-11 | 2021-06-11 | [6 empty] | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [6 empty] | '-121.93736 | 40.7945 | ETL.5650 | 40857973 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117456604 | Q2 | T2 DI HT CRK #1 WW 24/467 REPL PL | 31456280 | HAT CREEK #1-WESTWOOD | 024/467 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.219798 | 40.6945 | ETL.7030 | 40825679 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2020-06-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117456726 | Not Scheduled | T2NT DI CTTNWD-DLVN#2 67/596 PNT TWR | 44305184 | COTTONWOOD-DELEVAN #2 | 067/596 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-11 | 2021-06-11 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.267777 | 40.2787 | ETL.4580 | 40822896 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117456785 | Mar | T2 HUMBOLDT-TRINITY 057/1R REMV BUTT | 44311174 | HUMBOLDT-TRINITY | 057/001 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-22 | 2024-05-22 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.119316 | 40.7687 | ETL.1820 | 44562713 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117456834 | Mar | T2 HUMBOLDT-TRINITY 52/004R REMV BUTT | 44311174 | HUMBOLDT-TRINITY | 052/004 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-20 | 2024-05-20 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.054248 | 40.7434 | ETL.1820 | 44557692 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117456876 | Q2 | T2 DI FORT BRAGG-ELK 12/2 RPR GYWW | 43877649 | FORT BRAGG-ELK | 012/002 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-06-12 | 2020-06-12 |  |  | 2021-05-04 | 2021-05-04 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.784752 | 39.283 | ETL.2060 | 40697824 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117456927 | Q2 | DI HAT CRK#1-WESTWOOD 47/906 RPR STRW | 43939293 | HAT CREEK #1-WESTWOOD | 047/906 | ICW | E | Pre-2020_(2) High fire spread TD |  | 2019-06-10 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.022087 | 40.4185 | ETL.7030 | 40675741 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117457044 | Feb | T2 DI TRI MPLE CRK 16/11 RPR GYWW | 43749708 | TRINITY-MAPLE CREEK | 016/011 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2021-05-31 | 2021-02-22 | 2021-02-27 | 2021-02-22 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.207492 | 40.741 | ETL.8170 | 44628450 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117457071 | Q2 | T2 DI HAT CREEK #1-WSTWD 2/44 RPR GYWW | 43736795 | HAT CREEK #1-WESTWOOD | 002/044 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.50444 | 40.922 | ETL.7030 | 40596892 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117457075 | Q2 | T2 DI HAT CREEK #1-WESTWOD 3/77 RPL STRW | 31504344 | HAT CREEK #1-WESTWOOD | 003/077 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.471672 | 40.9169 | ETL.7030 | 40770080 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117457798 | Q2 | T2 DI HAT CREEK #1-WSTWD 11/213 RPL STRW | 31504344 | HAT CREEK #1-WESTWOOD | 011/213 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.389475 | 40.8397 | ETL.7030 | 40701209 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458003 | Q2 | T2 DI HAT CRK#1-WESTWOOD 20/400 RPR PL | 43939287 | HAT CREEK #1-WESTWOOD | 020/400 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-11 | 2020-06-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.264272 | 40.7336 | ETL.7030 | 40827479 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458007 | Q2 | T2 DI HAT CRK#1-WESTWOOD 20/400 RPL HRDD | 43939292 | HAT CREEK #1-WESTWOOD | 020/400 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-11 | 2020-06-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.264272 | 40.7336 | ETL.7030 | 40827479 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458142 | Q2 | T2 DI HT CRK #1 WW 2/49 RPL PL | 31504344 | HAT CREEK #1-WESTWOOD | 002/049 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2020-06-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.499562 | 40.9212 | ETL.7030 | 40814026 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458144 | Q2 | T2 DI HAT CRK#1-WESTWD 19/373 RPL PL | 31505374 | HAT CREEK #1-WESTWOOD | 019/373 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.282277 | 40.7482 | ETL.7030 | 40877585 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458163 | Not Scheduled | T2NT DI STNL-MLNS-MNTC#1 002/016 PAINT | 43852843 | STANISLAUS-MELONES SS-MANTECA #1+ | 002/016 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-06-11 | 2021-06-11 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.41139 | 38.1258 | ETL.3830 | 40804662 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458269 | Not Scheduled | T3 DI CEN TAB MTN 2/41 RPR STRW | 43724253 | CENTERVILLE-TABLE MTN | 002/041 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-12 | 2019-12-12 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.681033 | 39.7575 | ETL.6320 | 40822423 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458343 | Not Scheduled | T2 DI DUNLAP TAP 015/014 RPR PL | 43709736 | DUNLAP TAP | 015/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-11 | 2020-06-11 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-119.031207 | 36.7075 | ETL.9061 | 40747119 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458400 | Not Scheduled | DI CAYUCOS-CAMBRIA 13/84 RPL INSW | 31502978 | CAYUCOS-CAMBRIA | 013/084 | 93I | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [7 empty] | ETL.8560 | 44271584 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458497 | Q2 | T2 DI CBRY SW ST-RD MTN 21/168 INST MRKS | 43897848 | CARBERRY SW STA-ROUND MTN | 021/168 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-11 | 2021-06-11 |  |  | 2021-05-07 | 2021-05-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.82031 | 40.8241 | ETL.5410 | 40868794 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458600 | Not Scheduled | T2 DI SPLDNG-SMMT 1/48 INS MRKW | 43923458 | SPAULDING-SUMMIT | 001/048 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-13 | 2021-06-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624686 | 39.3183 | ETL.8060 | 40586118 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458658 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/3 RPR GYWW | 43923458 | SPAULDING-SUMMIT | 000/003 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-14 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.643808 | 39.3247 | ETL.8060 | 40652035 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458784 | Q2 | T2 DI HAT CREEK 1-WESTWOOD 0/13 RPL PL | 31504344 | HAT CREEK #1-WESTWOOD | 000/013 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-11 | 2020-06-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.534698 | 40.9267 | ETL.7030 | 40616826 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-09-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458805 | Not Scheduled | T2 DI PIT#1 COTTNWOOD 21/170 PNT STRS | 44586171 | PIT #1-COTTONWOOD | 021/170 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-13 | 2021-06-13 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.823958 | 40.8233 | ETL.5390 | 40580083 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458833 | Not Scheduled | DI COLGATE-CHALLANGE 0/2 RPR GYWS | 43910648 | COLGATE-CHALLENGE | 000/002 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-14 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.189756 | 39.3323 | ETL.6480 | 44695457 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458921 | Q2 | T2 DI HAT CREEK #1-WSTWD 20/395 RPL STRW | 31456280 | HAT CREEK #1-WESTWOOD | 020/395 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.267768 | 40.7364 | ETL.7030 | 40592094 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117458949 | Not Scheduled | DI VLLY SPRNGS#1 12/246 RPR GYWW | 43857861 | VALLEY SPRINGS #1 | 012/246 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.923895 | 38.1021 | ETL.8210 | 40904221 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117459024 | Q2 | T2 DI HAT CREEK #1-WSTWD 20/402 RPR PL | 43939292 | HAT CREEK #1-WESTWOOD | 020/402 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2020-06-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.262903 | 40.7325 | ETL.7030 | 40877481 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117459228 | Q3 | T2 DI MONTA VSTA-LOS GATS 8/167 RMV VEG |  | MONTA VISTA-LOS GATOS | 008/167 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-06-14 | 2021-05-31 |  |  | 2021-08-15 | 2021-08-01 |  |  |  | TR2 | LATE | Central | WSIP | FSRP |  |  |  |  | [REDACTED] - applying for Cal Trans District 4 scenic highway permmit; eta 8/15/2020 | '-122.004522 | 37.2419 | ETL.7610 | 40766368 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117459267 | Q2 | T2 DI HAT CREEK #1-WSTWD 28/542 RPL STRW | 31456280 | HAT CREEK #1-WESTWOOD | 028/542 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.173778 | 40.6515 | ETL.7030 | 40770751 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117459325 | Q2 | T2 DI HAT CRK#1-WESTWOOD 25/494 RPR HRDW | 43939292 | HAT CREEK #1-WESTWOOD | 025/494 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.20251 | 40.6786 | ETL.7030 | 40759033 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117459539 | Q2 | T2 TULUCAY-NAPA #1 006/014 REPL POLE | 31471954 | TULUCAY-NAPA #1 | 006/014 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2021-05-31 | 2020-09-28 | 2020-10-01 | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.200994 | 38.2605 | ETL.8180 | 40751190 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-08-09 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-09 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117459567 | Q2 | T2 DI SOB STA OIL SW S#1 7/42 RPR FOND |  | SOBRANTE-STANDARD OIL SW STA #2 | 007/042 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2020-06-12 |  |  | 2021-05-15 | 2021-05-10 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.230683 | 37.9967 | ETL.3800 | 40681223 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-22 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117459569 | Not Scheduled | T2NT DI SOB STA OIL SW S#1 7/42 REPAINT | 44586185 | SOBRANTE-STANDARD OIL SW STA #2 | 007/042 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-12 | 2021-06-12 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-122.230683 | 37.9967 | ETL.3800 | 40681223 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117459855 | Q2 | T2 DI HAT CRK#1 23/443 RPR STRW | 43939292 | HAT CREEK #1-WESTWOOD | 023/443 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.235233 | 40.7086 | ETL.7030 | 40676328 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117459860 | Q2 | T2 DI HT CRK #1 WW 6/130 RPL POLE | 31504344 | HAT CREEK #1-WESTWOOD | 006/130 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.428357 | 40.8953 | ETL.7030 | 40658523 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117460065 | Not Scheduled | T2 DI VAL SPR CLA 16/226 RPR GYWW | 43857873 | VALLEY SPRINGS-CLAY | 016/226 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2020-06-12 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.926816 | 38.3232 | ETL.8264 | 40904822 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117460384 | Mar | T2 HUMBOLDT-TRINITY 90/4 RMV POLE BUTT | 44311171 | HUMBOLDT-TRINITY | 090/004 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-29 | 2024-05-29 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.689461 | 40.7396 | ETL.1820 | 44562640 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117460477 | Mar | T2 HUMBOLDT-TRINITY 89/7 RMV PL BUTTS | 44311171 | HUMBOLDT-TRINITY | 089/007 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-29 | 2024-05-29 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.675507 | 40.7306 | ETL.1820 | 44560497 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117460489 | Mar | T2 HUMBOLDT-TRINITY 89/6 RMV POLE BUTTS | 44285711 | HUMBOLDT-TRINITY | 089/006A | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-29 | 2022-05-29 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.674455 | 40.7302 | ETL.1820 | 44553939 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117460615 | Mar | T2 HUMBOLDT-TRINITY 88/4 RMV DEBRIS | 43729541 | HUMBOLDT-TRINITY | 088/004 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-29 | 2024-05-29 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.664978 | 40.728 | ETL.1820 | 44560494 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117460715 | Q2 | T2 DI HATCRK#1 WSTWD 10/209 RPL STRW | 31495723 | HAT CREEK #1-WESTWOOD | 010/209 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.391318 | 40.8423 | ETL.7030 | 40877575 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117460739 | Mar | T2 HUMBOLDT-TRINITY 88/2 RMV DEBR | 43729541 | HUMBOLDT-TRINITY | 088/002 | ICW | F | Pre-2020_(3) On high spread structure |  | 2019-05-29 | 2024-05-29 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.658695 | 40.7266 | ETL.1820 | 44562193 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-04 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117460942 | Not Scheduled | DI VAL SPR CLA 13/193 RPL INSS | 31433173 | VALLEY SPRINGS-CLAY | 013/193 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2020-06-12 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.910789 | 38.2936 | ETL.8264 | 40906858 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117460944 | Not Scheduled | T2NT DI CHRISTIE-SOBRANTE 010/058 PAINT | 43751914 | CHRISTIE-SOBRANTE | 010/058 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-12 | 2021-06-12 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-122.198532 | 37.9922 | ETL.1260 | 40869614 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117461030 | Mar | T2 HUMBOLDT-TRINITY 88/1 RMV DEBR | 43729541 | HUMBOLDT-TRINITY | 088/001 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-05-29 | 2024-05-29 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.653024 | 40.7253 | ETL.1820 | 44562990 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-04 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117461155 | Q2 | T2 DI HATCRK#1 WSTWD #1 14/280 RPLC POLE | 31456189 | HAT CREEK #1-WESTWOOD | 014/280 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.34681 | 40.8002 | ETL.7030 | 40701333 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117461377 | Not Scheduled | T2 DI SPAULDING-SUMMIT 000/005 RPL HRDD | 43923458 | SPAULDING-SUMMIT | 000/005 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-17 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.643267 | 39.3247 | ETL.8060 | 40770692 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117461582 | Q2 | T2 DI HATCRK#1 WSTWD 13/256 RPL STRW | 31505374 | HAT CREEK #1-WESTWOOD | 013/256 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.36344 | 40.8137 | ETL.7030 | 40701219 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117461595 | Q2 | T2 DI HAT CRK#1 WSTWD 24/460 RPR STRW | 43736795 | HAT CREEK #1-WESTWOOD | 024/460 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.224298 | 40.6986 | ETL.7030 | 40600226 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117461693 | Not Scheduled | T2 DI SPAULDING-SUMMIT 000/019 INS MRKW | 43923458 | SPAULDING-SUMMIT | 000/019 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-14 | 2021-06-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.637176 | 39.3229 | ETL.8060 | 40861966 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117461766 | Not Scheduled | T2 DI VLLY SPRNGS-CLAY 13/173 RPR STRW | 43857873 | VALLEY SPRINGS-CLAY | 013/173 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.898455 | 38.2822 | ETL.8264 | 40904779 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117461796 | Not Scheduled | T2 DI COLGATE-PALERMO 0/2 RPL STRW | 31457073 | COLGATE-PALERMO | 000/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2020-06-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.19024 | 39.3316 | ETL.6500 | 40672039 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117462118 | Not Scheduled | T2 DI STA MEL SW STA MA 15/95 RPR STRS | 43852841 | STANISLAUS-MELONES SS-MANTECA #1+ | 015/095 | ICS | F | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2023-06-13 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.602914 | 38.0179 | ETL.3830 | 40751416 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117462325 | Not Scheduled | T2 DI VALLEY SPRNGS-CLAY 12/164 RPR STRW | 43857873 | VALLEY SPRINGS-CLAY | 012/164 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2020-06-12 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.890535 | 38.2778 | ETL.8264 | 40904774 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117462326 | Not Scheduled | T2 DI VALLEY SPRNGS-CLAY 12/164 RPR GYWW | 43857873 | VALLEY SPRINGS-CLAY | 012/164 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-12 | 2020-06-12 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.890535 | 38.2778 | ETL.8264 | 40904774 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117462460 | Q2 | T2 DI HAT CRK#1 WSTWD :15/300 RPR STRW | 43939287 | HAT CREEK #1-WESTWOOD | 015/300 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.332935 | 40.7891 | ETL.7030 | 40701335 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117462488 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 1/68 INST MRKW | 43923458 | SPAULDING-SUMMIT | 001/068 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-14 | 2021-06-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.618417 | 39.3114 | ETL.8060 | 40811570 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117462640 | Before Feb | DI MERCED FALLS-EXCH 6/14 RPR RUST MBER | 44300717 | MERCED FALLS-EXCHEQUER | 006/014 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-14 | 2020-06-14 | 2020-09-01 | 2020-10-31 | 2020-10-31 | 2020-09-01 |  |  |  |  | LATE | South | WSIP | [6 empty] | '-120.274276 | 37.5845 | ETL.8990 | 40748143 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117463317 | Q2 | T2 DI HATCRK#1 -WSTD 15/294 RPR HOLE | 43736796 | HAT CREEK #1-WESTWOOD | 015/294 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.337078 | 40.7924 | ETL.7030 | 40616868 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117463448 | Not Scheduled | T3 DI COLGATE-CHALLENGE 1/29 RPR STRW | 43910648 | COLGATE-CHALLENGE | 001/029 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.18562 | 39.3473 | ETL.6480 | 40824182 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117463796 | Q2 | T2 DI HATCRK#1 -WSTD 17/327 RPL STRW | 31495723 | HAT CREEK #1-WESTWOOD | 017/327 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.314315 | 40.774 | ETL.7030 | 40617050 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117463857 | Q2 | T2 DI MORAGA-LAKEWOOD 010/080 RPR SPLS | 43877251 | MORAGA-LAKEWOOD | 010/080 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-13 | 2020-06-13 |  |  | 2021-04-06 | 2021-04-05 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.138722 | 37.8632 | ETL.3741 | 40604203 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117464721 | Not Scheduled | T2NT DI MALIN-RND MTN#2 70/353 CANCEL | 43621093 | MALIN-ROUND MTN #2 | 070/353 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-14 | 2021-06-14 | [6 empty] | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.772887 | 41.0973 | ETL.6020 | 40660399 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117464805 | Not Scheduled | T2NT DI VACA-LAKEVILL #1 13/66 INST MRKS | 43908800 | VACA-LAKEVILLE #1 | 013/066 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-13 | 2021-06-13 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.103094 | 38.3111 | ETL.5840 | 40816985 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117464833 | Not Scheduled | T2 DI MALIN-RND MTN#2 67/340 CANCEL | 43621093 | MALIN-ROUND MTN #2 | 067/340 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-14 | 2023-06-14 | [6 empty] | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.740654 | 41.1228 | ETL.6020 | 40605579 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117465244 | Q2 | T2 DI HATCRK#1 -WSTD 33/637 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 033/637 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-14 | 2020-06-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.104343 | 40.6017 | ETL.7030 | 40759225 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117465312 | Not Scheduled | T2 DI STANISLAUS-MNTCA #2 BENT STEEL | 44460416 | STANISLAUS-MANTECA #2 | 019/114 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.656686 | 37.9763 | ETL.3820 | 40744470 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117465372 | Q2 | T2 DI HAT CRK #1-WSTWOOD 21/414 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 021/414 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.2546 | 40.7258 | ETL.7030 | 40601696 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117465390 | Q4 | T2 DI SLNS-LRLS A12/268 RMV VEG |  | SALINAS-LAURELES | A012/268 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-06-14 | 2021-05-31 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | LATE | South | WSIP | [5 empty] | Per Cal Trans District 5, unless the trees are dead, the removal of the trees as a scenic resource will require Coastal Development Permit or some other kind of locally driven approval that complies with CEQA. | '-121.771939 | 36.5701 | ETL.7930 | 40768981 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117465399 | Q2 | T2 DI HATCRK#1 -WSTD 22/424 RPR STRW | 43939292 | HAT CREEK #1-WESTWOOD | 022/424 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.247742 | 40.7201 | ETL.7030 | 40676320 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117465425 | Q2 | T2 DI HAT CRK #1-WSTWOOD 21/418 RPL POLE | 31456280 | HAT CREEK #1-WESTWOOD | 021/418 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-14 | 2020-06-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.251847 | 40.7235 | ETL.7030 | 40769954 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | In Review | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117465458 | Q2 | T2 DI HAT CREK #1 WESTWD 15/296 RPL POLE | 31505374 | HAT CREEK #1-WESTWOOD | 015/296 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.33568 | 40.7913 | ETL.7030 | 40759180 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117465583 | Q2 | T2 DI HATCRK#1 -WSTD 19/368 RPL STRW | 31456280 | HAT CREEK #1-WESTWOOD | 019/368 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.285798 | 40.7509 | ETL.7030 | 40656881 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117465690 | Q2 | T2 DI HT CRK #1 WW 14/287 RPR STRW | 43939287 | HAT CREEK #1-WESTWOOD | 014/287 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.341957 | 40.7964 | ETL.7030 | 40827468 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117466312 | Q2 | T2 DI HAT CRK #1-WSTWOOD 22/440 INST HV | 43904280 | HAT CREEK #1-WESTWOOD | 022/440 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-13 | 2021-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.237517 | 40.7106 | ETL.7030 | 40877483 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117466445 | Q2 | T2 DI HT CRK #1 WW 22/438 RPR STRW | 43939292 | HAT CREEK #1-WESTWOOD | 022/438 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.238727 | 40.7118 | ETL.7030 | 40827483 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117466502 | Not Scheduled | T2 DI MALIN-RND MTN#2 68/345 CANCEL | 43621093 | MALIN-ROUND MTN #2 | 068/345 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-14 | 2023-06-14 | [6 empty] | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.752349 | 41.1135 | ETL.6020 | 40764368 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117466510 | Q2 | T2 DI HT CRK #1 WW 29/565 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 029/565 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.155908 | 40.6403 | ETL.7030 | 40868488 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117466513 | Q2 | T2 DI HT CRK #1 WESTWD 27/519 RPL POLE | 31504344 | HAT CREEK #1-WESTWOOD | 027/519 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.188762 | 40.6641 | ETL.7030 | 40617071 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117466780 | Q2 | T2 DI HAT CRK #1-WSTWOOD 23/450 RPR POLE | 43939292 | HAT CREEK #1-WESTWOOD | 023/450 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.230683 | 40.7044 | ETL.7030 | 40876274 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117467341 | Q2 | T2 DI HAT CRK #1-WSTWOOD 27/529 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 027/529 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.18311 | 40.6579 | ETL.7030 | 40600238 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117467451 | Q2 | T2 DI HAT CRK #1-WSTWOD 29/559 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 029/559 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.16055 | 40.6433 | ETL.7030 | 40701230 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117467513 | Q2 | T2 DI HAT CRK #1-WSTWD 31/607 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 031/607 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.122963 | 40.6197 | ETL.7030 | 40676370 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117467676 | Q2 | T2 DI HAT CRK #1-WESTWD 18/349 REPL STRW | 31505374 | HAT CREEK #1-WESTWOOD | 018/349 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.298903 | 40.7616 | ETL.7030 | 40816128 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117467683 | Q4 | T2 DI SLNS-LRLS A12/261 RMV VEGN |  | SALINAS-LAURELES | A012/261 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-06-17 | 2021-05-31 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.765932 | 36.5705 | ETL.7930 | 40812151 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117467745 | Not Scheduled | EI DRUM-SUMMIT #1 017/205R INST MRKW | 43910102 | DRUM-SUMMIT #1 | 017/205 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-10 | 2021-06-10 | [8 empty] | WECC | North Valley | Non-WSIP | [6 empty] | '-120.490905 | 39.3154 | ETL.1440 | 44769592 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117467835 | Q2 | T2 DI HAT CRK #1-WESTWD 32/618 RPL INSW | 31474040 | HAT CREEK #1-WESTWOOD | 032/618 | 93I | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.115338 | 40.6136 | ETL.7030 | 44144300 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-04-07 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117467913 | Q2 | T2 DI HT CRK #1 WW 32/620 RPR STRW | 43939292 | HAT CREEK #1-WESTWOOD | 032/620 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.11417 | 40.6123 | ETL.7030 | 40817143 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117467970 | Q2 | T2 DI MLN-RND MTN #2 70/354 INS GMKS | 44305271 | MALIN-ROUND MTN #2 | 070/354 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-14 | 2022-06-14 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.774762 | 41.0958 | ETL.6020 | 40753370 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117468057 | Q2 | T2 DI HAT CRK #1-WSTWOOD 24/472 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 024/472 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.216593 | 40.6915 | ETL.7030 | 40676335 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2020-06-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117468059 | Q2 | T2 DI HAT CRK #1-WSTWOOD 24/472 RPL INSW | 31456189 | HAT CREEK #1-WESTWOOD | 024/472 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.216593 | 40.6915 | ETL.7030 | 40721586 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 508 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117468069 | Mar | DI PALERMO-OROVILLE #2 000/004 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | 000/004 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2020-06-18 |  |  | 2021-03-04 | 2021-03-04 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.519202 | 39.4546 | ETL.7740 | 41123116 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117468116 | Q2 | T2 DI HAT CRK 1-WESTWOOD 38/744 RPL STRW | 31456280 | HAT CREEK #1-WESTWOOD | 038/744 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.042957 | 40.5355 | ETL.7030 | 40769987 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117470128 | Q2 | T2 EI BALCH-SANGER 05/31 RPL CONN | 43862937 | BALCH-SANGER | 005/031 | ICM | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-14 | 2020-05-14 | 2021-04-12 | 2021-04-15 | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.156996 | 36.8885 | ETL.1050 | 40583101 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Fresno |  | Y - Prog USFS |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117470133 | Not Scheduled | T2NT DI SPAULDNG-SUMMT 001/049 INS MRKW | 43923458 | SPAULDING-SUMMIT | 001/049 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-19 | 2021-06-19 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624547 | 39.3181 | ETL.8060 | 40660203 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117470327 | Q2 | T2 DI HT CRK #1-WSTWD 15/289 RPR POLE | 43736796 | HAT CREEK #1-WESTWOOD | 015/289 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.34057 | 40.7952 | ETL.7030 | 40616865 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117470386 | Q2 | DI STA NEW #1 84/558 EXPOSE STB | 44505634 | STANISLAUS-NEWARK #1 (12KV) | 084/558 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2020-06-17 |  |  | 2021-06-05 | 2021-06-01 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.749736 | 37.6512 | ETL.3850 | 41195978 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117470434 | Q2 | DI STA NEW #1 84/558 RPR STRT | 44505634 | STANISLAUS-NEWARK #1 (12KV) | 084/558 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2020-06-17 |  |  | 2021-06-05 | 2021-06-01 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.749736 | 37.6512 | ETL.3850 | 41195978 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117470436 | Q2 | T2 DI HT CRK #1-WSTWD 31/600 RPR PL | 43939292 | HAT CREEK #1-WESTWOOD | 031/600 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-14 | 2020-06-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.128433 | 40.6232 | ETL.7030 | 40759041 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117470591 | Q2 | T2 DI PLRM-RVILLE #2 A007/93 RPR STRW | 43724470 | PALERMO-OROVILLE #2 | A007/093 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-14 | 2020-06-14 |  |  | 2021-04-01 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.493617 | 39.5304 | ETL.7740 | 41123124 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-17 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117470599 | Not Scheduled | T2 DI COLGATE-PALERMO 7/135 RMV VEGN |  | COLGATE-PALERMO | 007/135 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-06-14 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.307753 | 39.3463 | ETL.6500 | 40873598 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | HNA | Not Scheduled |  |  | 2019-09-13 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117470632 | Q2 | DI COTTNWD-DELVN #2 000/001 RPR SPLS | 44305184 | COTTONWOOD-DELEVAN #2 | 000/001 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2020-06-18 |  |  | 2021-04-02 | 2021-03-30 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.263005 | 40.3968 | ETL.4580 | 40651417 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117470636 | Mar | DI CLEAR LAKE-HPLND 1/8 RPL STRW | 31483756 | CLEAR LAKE-HOPLAND | 001/008 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2021-05-31 | 2021-03-30 | 2021-04-02 | 2021-03-24 | 2021-03-24 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.054987 | 38.9664 | ETL.6390 | 40860806 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117470852 | Not Scheduled | DI JFFRSON-STANFORD 0/1 RPR GYWW | 43877613 | JEFFERSON-STANFORD (NO FLY) | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2020-06-18 | 2020-08-26 | [7 empty] | LATE | Central | WSIP | [6 empty] | '-122.285318 | 37.4558 | ETL.7220 | 40588805 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117470907 | Q2 | T3 DI DRUM-HIGGINS 4/48 RPR GYWW | 43903303 | DRUM-HIGGINS | 004/048 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2019-12-17 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.831684 | 39.2144 | ETL.4393 | 44172173 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117470909 | Mar | T2 DI VOLTA-SOUTH 2/48 RPR PL | 44309960 | VOLTA-SOUTH | 002/048 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-17 | 2020-06-17 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871635 | 40.4316 | ETL.8300 | 40615862 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117470951 | Not Scheduled | DI TESLA NEWARK #2 13/89 PAINT COATING | 43753285 | TESLA-NEWARK #2 | 013/089 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-17 | 2021-06-17 | [9 empty] | Central | WSIP | [6 empty] | '-121.783442 | 37.6301 | ETL.5354 | 41152634 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117470971 | Q2 | T2 DI HAT CRK #1-WSTWD 25/486 RPL STRW | 31456280 | HAT CREEK #1-WESTWOOD | 025/486 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2020-06-13 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.207628 | 40.6832 | ETL.7030 | 40825586 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117471106 | Not Scheduled | DI PALERMO-WYANDTT 000/000B RPR GYWW | 43952543 | PALERMO-WYANDOTTE | 000/000B | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2020-06-18 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.519468 | 39.4548 | ETL.4315 | 44190800 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117471108 | Not Scheduled | DI PALERMO-WYANDOTTE 000/000B RPR STRW | 43952543 | PALERMO-WYANDOTTE | 000/000B | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2020-06-18 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.519468 | 39.4548 | ETL.4315 | 44190800 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117471197 | Not Scheduled | T2 DI CENTERVLL-TBL MTN 004/075 RPR SPLW | 43792089 | CENTERVILLE-TABLE MTN | 004/075 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2020-06-18 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.705885 | 39.7329 | ETL.6320 | 40867505 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117471319 | Not Scheduled | T2 DI CNTRVLL-TBL MTN 6/106 RPR INSS | 31457914 | CENTERVILLE-TABLE MTN | 006/106 | 93I | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-17 | 2020-06-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.712818 | 39.7012 | ETL.6320 | 44417895 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-02-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117471491 | Q3 | T2 DI MONTA VST-LS GATOS 9/182 RMV VEGN |  | MONTA VISTA-LOS GATOS | 009/182 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-06-17 | 2021-05-31 |  |  | 2021-08-15 | 2021-08-01 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.991958 | 37.2363 | ETL.7610 | 40597933 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117471525 | Not Scheduled | T3 DI COLGATE-CHALLENGE 7/135 RPL STRW | 31462967 | COLGATE-CHALLENGE | 007/135 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.195678 | 39.4181 | ETL.6480 | 40611341 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-07-27 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117471743 | Q3 | T2 DI CARIBOU-WSTWD 7/140C RPL STRW | 31473384 | CARIBOU-WESTWOOD | 007/140C | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2021-05-31 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  | REJECT: Crew reported they were unable to complete work. Scope of work has been changed. Pleae resubmit once new scope of work has been completed. |  |  | '-121.087819 | 40.1717 | ETL.6300 | 42624247 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  | Reject | 2019-09-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117472003 | Not Scheduled | DI SPAULDING-SUMMIT 004/159 RPL STRW | 31495368 | SPAULDING-SUMMIT | 004/159 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-18 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.571981 | 39.3064 | ETL.8060 | 40602304 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117472047 | Not Scheduled | DI HELMS-GREGG #1 5/40 REM NEST | 44301795 | HELMS-GREGG #1 | 005/040A | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-06-18 | 2021-05-31 | [8 empty] | LATE | South | WSIP | FSRP | [5 empty] | '-119.03554 | 37.0007 | ETL.4870 | 40576885 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117472283 | Not Scheduled | T2 DI CARIBOU-PALERMO :18/147 RMV DEBRIS |  | CARIBOU-PALERMO | :018/147 | ICW | F | Pre-2020_(3) On high spread structure |  | 2019-06-18 | 2021-06-18 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.329026 | 39.9139 | ETL.3190 | 44549940 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117472284 | Q2 | T2 DI HAT CREEK #1-WSTWD 31/601 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 031/601 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-14 | 2020-06-14 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.127653 | 40.6227 | ETL.7030 | 40827493 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117472296 | Q4 | T2 DI SLNS-LRLS A12/269 RMV VEGN |  | SALINAS-LAURELES | A012/269 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-06-17 | 2021-05-31 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.772494 | 36.5698 | ETL.7930 | 40754673 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117472396 | Not Scheduled | T2 DI JFFRSN-HILLSDALE JCT 7/41 INS MRKS | 43877609 | JEFFERSON-HILLSDALE JCT | 007/041 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-06-18 | 2021-06-18 | 2020-07-13 | 2020-07-17 | [5 empty] | TR2 |  | Central | WSIP | [6 empty] | '-122.363099 | 37.5387 | ETL.7190 | 44384035 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi | SFPUC (4) | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117472671 | Not Scheduled | T3NT DI CAR PAL :31/256B INST MRKS |  | CARIBOU-PALERMO | :031/256B | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-18 | 2021-06-18 | [7 empty] | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations | reprioritization of work - noncritical facility | '-121.467788 | 39.7593 | ETL.3190 | 44374355 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117473386 | Q2 | T2 DI HT CRK#1-WSTWD 007/142 RPR GYWW | 43939287 | HAT CREEK #1-WESTWOOD | 007/142 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-15 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.422642 | 40.8872 | ETL.7030 | 40758997 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117473595 | Q2 | DI TASSAJARA NWRK 23/108 RPL DAMS | 43900133 | TASSAJARA-NEWARK | 023/108 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2020-06-18 |  |  | 2021-05-20 | 2021-05-19 |  | Structure Number incorrect |  |  | LATE | Central | WSIP | [6 empty] | '-121.877409 | 37.5668 | ETL.5920 | 40923052 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 1 | SFPUC | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-05-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117473612 | Not Scheduled | DI TESLA-LS BNS#1 2/13 RPR GYWS | 43866683 | TESLA-LOS BANOS #1 | 002/013 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2020-06-18 | [6 empty] | Tower guy |  | LATE | Central | WSIP | [6 empty] | '-121.526971 | 37.6897 | ETL.6100 | 40651778 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117473728 | Mar | DI PARADISE-BUTTE 009/094A RPR GYWS | 43881381 | PARADISE-BUTTE | 009/094A | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2020-06-18 |  |  | 2021-03-19 | 2021-03-09 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.737332 | 39.7094 | ETL.4396 | 43249546 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117473946 | Q2 | T2 DI COLGATE-PALERMO 019/377 RPR PL | 43878561 | COLGATE-PALERMO | 019/377 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-14 | 2020-06-14 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.460948 | 39.4465 | ETL.6500 | 40599632 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117474078 | Mar | DI PALERMO-OROVILLE #2 000/001 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2020-06-18 |  |  | 2021-03-04 | 2021-03-04 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.517922 | 39.4551 | ETL.7740 | 41123113 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117474312 | Q3 | DI CARIBOU-PLUMAS JCT 14/6 RPR GYWW | 43920793 | CARIBOU-PLUMAS JCT | 014/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2020-06-18 |  |  | 2021-08-20 | 2021-08-02 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.954807 | 39.9576 | ETL.6290 | 40810058 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117474387 | Q4 | T2 DI KESWICK-TRINITY 015/190 REPR STRW | 43939188 | KESWICK-TRINITY | 015/190 | ICW | E | Pre-2020_(2) High fire spread TD |  | 2019-06-17 | 2021-05-31 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - FSR 12/2020 | '-122.672176 | 40.7145 | ETL.7270 | 40668396 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q4 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117474570 | Mar | T3 DI CLOVER CREEK TAP A5/128 RPR GYWW | 43901760 | CLOVER CREEK TAP | A005/128 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-14 | 2019-12-14 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [5 empty] | reprioritization of work - E/F tags pushed to 2020 | '-121.972443 | 40.7083 | ETL.7291 | 42712147 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117474750 | Not Scheduled | T2 DI CRBOU-PLRMO :01/10 RPR FOND | 44062862 | CARIBOU-PALERMO | :001/010 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-18 | 2020-06-18 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.164829 | 40.0739 | ETL.3190 | 40910257 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117474816 | Mar | T2 DI VOLTA-SOUTH 1/37 RPR STRW | 43827513 | VOLTA-SOUTH | 001/037 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2020-06-18 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.872648 | 40.4384 | ETL.8300 | 40667419 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117475108 | Q2 | T2 DI CORDELIA #2 TAP 3/68 RPR GYWW | 43901135 | CORDELIA #2 TAP | 003/068 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2020-06-18 |  |  | 2021-05-04 | 2021-04-26 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.154799 | 38.2509 | ETL.8184 | 40695236 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117476381 | Not Scheduled | T2 DI VALLEY SPRINGS #1 9/176 RPR GYWW | 43863111 | VALLEY SPRINGS #1 | 009/176 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2020-06-18 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.874433 | 38.1291 | ETL.8210 | 40908259 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117476382 | Not Scheduled | T2 DI VALLEY SPRINGS #1 9/184 RPR GYWW | 43863113 | VALLEY SPRINGS #1 | 009/184 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2020-06-18 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.878384 | 38.1244 | ETL.8210 | 40908269 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117476383 | Feb | T2 DI COLGATE-PALERMO 011/210 RPL POLE | 31457073 | COLGATE-PALERMO | 011/210 | 70Y | E | 2020_(1a) PSPS |  | 2019-06-18 | 2020-06-18 |  |  | 2021-02-10 | 2021-01-28 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.368872 | 39.3701 | ETL.6500 | 40692901 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-09-02 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117476541 | Not Scheduled | T2 DI COLGATE-PALERMO 8/159 RPL PL | 31506096 | COLGATE-PALERMO | 008/159 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2020-06-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.330109 | 39.352 | ETL.6500 | 40664523 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117476785 | Q2 | T2 DI CRESTA-RIO OSO 30/243 RPL HRDT | 43708739 | CRESTA-RIO OSO | 030/243 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-15 | 2020-06-15 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.535087 | 39.5443 | ETL.4590 | 41083103 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117476817 | Q2 | T2 DI NEWARK-LIVERMORE 16/96 RPR STRW | 43877617 | NEWARK-LIVERMORE | 016/096 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2021-05-31 |  |  | 2021-05-12 | 2021-05-10 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.776232 | 37.6342 | ETL.7660 | 40580690 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117476869 | Not Scheduled | T2 DI VALLEY SPRINGS #1 8/167 RPR PL | 43863106 | VALLEY SPRINGS #1 | 008/167 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.869751 | 38.1343 | ETL.8210 | 40908250 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117476879 | Not Scheduled | T2 DI SPAULDING-SUMMIT 13/453 RPR PL |  | SPAULDING-SUMMIT | 013/453 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-17 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.411649 | 39.3283 | ETL.8060 | 40603905 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117476935 | Q2 | T2 DI LAYTONVILLE-WILL 17/9 RPL POLE | 31490917 | LAYTONVILLE-WILLITS | 017/009 | 70Y | F | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2022-06-17 | 2021-05-26 | 2021-05-28 | 2021-05-26 | 2021-05-26 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.46341 | 39.6176 | ETL.8360 | 40860923 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-09-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117476952 | Q4 | T2 DI SALINAS-LAURELES A017/359 RMV VEGN |  | SALINAS-LAURELES | A017/359 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-06-15 | 2021-05-31 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | LATE | South | WSIP | [5 empty] | Per Cal Trans District 5, unless the trees are dead, the removal of the trees as a scenic resource will require Coastal Development Permit or some other kind of locally driven approval that complies with CEQA. | '-121.842795 | 36.582 | ETL.7930 | 40600163 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117476962 | Not Scheduled | T3NT DI DRUM-RIO OSO #1 004/047 PAINT | 43908283 | DRUM-RIO OSO #1 | 004/047 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-18 | 2022-06-18 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.83335 | 39.228 | ETL.1420 | 40819129 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117477116 | Not Scheduled | T2 DI IGNACIO-ALTO 15/155 RPL STRW | 31492618 | IGNACIO-ALTO | 015/155 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2020-06-18 | [7 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.51466 | 37.918 | ETL.7150 | 40668130 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117477177 | Not Scheduled | T2 DI VALLEY SPRINGS #1 8/165 RPR PL | 43863105 | VALLEY SPRINGS #1 | 008/165 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.868789 | 38.1355 | ETL.8210 | 40908248 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117477263 | Q2 | DI STANISLAUS-NEW #1 83/552 RPR FOND |  | STANISLAUS-NEWARK #1 (12KV) | 083/552 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2020-06-18 |  |  | 2021-06-05 | 2021-06-01 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.73798 | 37.6571 | ETL.3850 | 41196042 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117477264 | Not Scheduled | T2 DI SPAULDING-SUMMIT 16/503 INS MRKW | 43923458 | SPAULDING-SUMMIT | 016/503 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-19 | 2021-06-19 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.379091 | 39.3215 | ETL.8060 | 40603910 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117477265 | Q2 | DI STANISLAUS-NEW #1 83/552 RPR STRT |  | STANISLAUS-NEWARK #1 (12KV) | 083/552 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2020-06-18 |  |  | 2021-06-05 | 2021-06-01 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.73798 | 37.6571 | ETL.3850 | 41196042 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-02 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117477755 | Q2 | T2 DI HT CRK #1-WESTWOOD 37/716 RPL PL | 31456280 | HAT CREEK #1-WESTWOOD | 037/716 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-06-14 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.059193 | 40.5531 | ETL.7030 | 40816880 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  |  | In Review | Complete | Awaiting ERTC |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117478052 | Q2 | DI STANISLAUS-NEWARK #1 84/556 RPR STRT |  | STANISLAUS-NEWARK #1 (12KV) | 084/556 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2020-06-17 |  |  | 2021-06-05 | 2021-06-01 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.746267 | 37.653 | ETL.3850 | 41195974 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-02 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117478053 | Q2 | DI STA NEW #1 83/553 RPR STUBS |  | STANISLAUS-NEWARK #1 (12KV) | 083/553 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-18 | 2020-06-18 |  |  | 2021-06-05 | 2021-06-01 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.739502 | 37.6564 | ETL.3850 | 41196044 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-02 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117478197 | Not Scheduled | DI POE RIO OSO 32/217 PAINT | 43875009 | POE-RIO OSO | 032/217 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-18 | 2021-06-18 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.536853 | 39.5214 | ETL.5540 | 40814851 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117478595 | Q2 | DI VOLTA-DESCHUTES 20/464 RPL POLE | 31453473 | VOLTA-DESCHUTES | 020/464 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2021-05-31 |  |  | 2021-04-09 | 2021-04-05 |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.239761 | 40.5556 | ETL.8290 | 42607768 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117478638 | Mar | DI POE RIO OSO 32/216 RPR HRDS | 43875009 | POE-RIO OSO | 032/216 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2020-06-18 |  |  | 2021-03-26 | 2021-03-22 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.536684 | 39.524 | ETL.5540 | 40815733 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117478826 | Feb | DI RND MTN-CTTNWD#3 51/458 INS MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 051/458 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-18 | 2021-06-18 |  |  | 2021-02-19 | 2021-02-15 | [5 empty] | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-122.186793 | 40.4936 | ETL.5650 | 40862659 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117478838 | Q2 | DI IGNC SN RFL #3 1/26 RPR GYWW | 43919193 | IGNACIO-SAN RAFAEL #3 NF | 001/026 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-06-17 | 2021-05-31 |  |  | 2021-05-31 | [5 empty] | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.532067 | 38.0594 | ETL.1860 | 44680761 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117478950 | Not Scheduled | T2 DI DRUM-RIO OSO#1 30/219 RPL EYE-PLAT | 43908283 | DRUM-RIO OSO #1 | 030/219 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2020-06-18 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.248194 | 39.0445 | ETL.1420 | 40864699 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117478952 | Not Scheduled | DI POE-RIO OSO 33/220 INS HRDT | 43854765 | POE-RIO OSO | 033/220 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-06-18 | 2024-06-18 | [8 empty] | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.536481 | 39.5156 | ETL.5540 | 40605303 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117479219 | Not Scheduled | DI STANISLAUS-NEWARK#2 88/579 RPR FOND |  | STANISLAUS-NEWARK #2 (12KV) | 088/579 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-06-18 | 2020-06-18 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.80416 | 37.6219 | ETL.3860 | 44188781 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117479452 | Q2 | T2 DI SMA MAR 2/48 REFRAME | 31499716 | SMARTVILLE-MARYSVILLE | 002/048 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2020-06-17 |  |  | 2021-04-13 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.343103 | 39.2009 | ETL.7980 | 40602028 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117480449 | Mar | T3 DI VOLTA-SOUTH 000/020 REPL SPLW | 43827513 | VOLTA-SOUTH | 000/020 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-19 | 2019-12-19 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [5 empty] | reprioritization of work - E/F tags pushed to 2020 | '-121.867703 | 40.4494 | ETL.8300 | 40615951 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117480549 | Q2 | T3 EI DRUM-HIGGINS 02/27 RPL POLE | 31423108 | DRUM-HIGGINS | 002/027 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-21 | 2019-12-21 |  |  | 2021-04-03 | 2021-03-22 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.795057 | 39.2286 | ETL.4393 | 44172273 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117480559 | Q3 | T2 DI HMLTON BRNCH-CHSTR 9/194 REPL STRW | 31439198 | HAMILTON BRANCH-CHESTER | 009/194 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-19 | 2020-06-19 |  |  | 2021-08-31 | 2021-08-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.18056 | 40.3124 | ETL.7000 | 40770669 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2019-07-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117480600 | Q3 | T2 DI HMLTON BRNCH-CHSTR 7/168 REPR GYWW | 43879596 | HAMILTON BRANCH-CHESTER | 007/168 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2020-06-18 |  |  | 2021-08-31 | 2021-08-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.160822 | 40.3029 | ETL.7000 | 40815860 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117480752 | Not Scheduled | T2 EI SPAULDING-SUMMIT 003/126 RPL POLE | 31453471 | SPAULDING-SUMMIT | 003/126 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-22 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.58706 | 39.3141 | ETL.8060 | 40809649 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117480756 | Not Scheduled | EI FULTON-IGNACIO #1 1/8 RPR FOND | 44310541 | FULTON-IGNACIO #1 | 001/008 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-06-22 | 2021-06-22 | [9 empty] | North Coast | Non-WSIP | [6 empty] | '-122.739923 | 38.4975 | ETL.4680 | 40863589 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117480833 | Not Scheduled | T2NT EI SPAULDING-SUMMIT 3/123 RMV SIGN | 43923458 | SPAULDING-SUMMIT | 003/123 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-22 | 2021-06-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.589626 | 39.3135 | ETL.8060 | 40771495 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117480857 | Not Scheduled | T2 EI SPAULDING-SUMMIT 3/121 RMV VEGN | 43923458 | SPAULDING-SUMMIT | 003/121 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-22 | 2020-06-22 | [6 empty] | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.591299 | 39.3131 | ETL.8060 | 40701997 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117480870 | Not Scheduled | T2NT DI VACA-LAKEVILLE #1 8/40 INST MRKS | 43908800 | VACA-LAKEVILLE #1 | 008/040 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-19 | 2021-06-19 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.034111 | 38.3684 | ETL.5840 | 40598949 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117481009 | Not Scheduled | T2 EI SPAULDING-SUMMIT 2/111 RPL PL | 31453471 | SPAULDING-SUMMIT | 002/111 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-22 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.597406 | 39.3134 | ETL.8060 | 40668658 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117481014 | Not Scheduled | T2 EI SPAULDING-SUMMIT 2/112 RMV VEGN | 43923458 | SPAULDING-SUMMIT | 002/112 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-22 | 2020-06-22 | [6 empty] | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.596911 | 39.3132 | ETL.8060 | 40771550 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117481124 | Q4 | T2 DI SALINAS-LAURELES A016/353 RMV VEGN |  | SALINAS-LAURELES | A016/353 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-06-15 | 2021-05-31 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | LATE | South | WSIP | [5 empty] | Per Cal Trans District 5, unless the trees are dead, the removal of the trees as a scenic resource will require Coastal Development Permit or some other kind of locally driven approval that complies with CEQA. | '-121.837614 | 36.5808 | ETL.7930 | 40876152 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117481197 | Not Scheduled | T2 EI SPAULDING-SUMMIT 003/130 INST MRKW | 43923458 | SPAULDING-SUMMIT | 003/130 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-22 | 2021-06-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.585377 | 39.3106 | ETL.8060 | 40602286 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117481230 | Q4 | T2 DI SALINAS-LAURELES A16/350 RMV VEGN |  | SALINAS-LAURELES | A016/350 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-06-15 | 2021-05-31 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | LATE | South | WSIP | [5 empty] | Per Cal Trans District 5, unless the trees are dead, the removal of the trees as a scenic resource will require Coastal Development Permit or some other kind of locally driven approval that complies with CEQA. | '-121.834939 | 36.581 | ETL.7930 | 40754679 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117481239 | Q2 | DI VOLTA-DESCHUTES 020/459 REPR GYWW | 43939089 | VOLTA-DESCHUTES | 020/459 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2021-05-31 |  |  | 2021-04-09 | 2021-04-05 |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.238568 | 40.555 | ETL.8290 | 40816205 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117481269 | Q4 | T2 DI MIDDLE FRK-GLD HILL 26/207L RPL PL | 31471246 | MIDDLE FORK-GOLD HILL | 026/207 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-19 | 2019-12-21 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.945506 | 38.8126 | ETL.5140 | 44558401 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117481787 | Not Scheduled | DI NEWARK-VALLECITOS 93/607 RPR FOND |  | NEWARK-VALLECITOS | 093/607 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-06-21 | 2020-06-21 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.869978 | 37.5863 | ETL.7670 | 44883851 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-03 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117481788 | Not Scheduled | T2 DI VALLEY SPRINGS #1 A01/30 RPR STRW | 43865295 | VALLEY SPRINGS #1 | A001/030 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-20 | 2020-06-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.741193 | 38.2051 | ETL.8210 | 40907087 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117481810 | Not Scheduled | T2 DI VALLEY SPRINGS #1 A01/35 RPR STRW | 43865298 | VALLEY SPRINGS #1 | A001/035 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-20 | 2020-06-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.736974 | 38.2039 | ETL.8210 | 40907092 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117481861 | Feb | T2 DI STNSLS-MELNS SS-MNTC 8/49 RPR FOND | 44460417 | STANISLAUS-MELONES SS-MANTECA #1+ | 008/049 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2020-06-18 |  |  | 2021-02-10 | 2021-02-10 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.492825 | 38.0808 | ETL.3830 | 40857653 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117481929 | Not Scheduled | DI VALLEY SPRINGS #1 010/210 RPR GYWW | 43857861 | VALLEY SPRINGS #1 | 010/210 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-20 | 2020-06-18 | [8 empty] | LATE | Central | WSIP |  |  |  |  | Clearance Denied by GCC | Clearance denied due to heat, Tman checked structure and feels it is safe to perform work in Nov under new clearance. TCY2 | '-120.897144 | 38.1152 | ETL.8210 | 40908295 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117482468 | Not Scheduled | T2 DI STLS-MLS SS-MTC #1 25/159 REPAINT | 43878406 | STANISLAUS-MELONES SS-MANTECA #1+ | 025/159 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-20 | 2021-06-20 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.745475 | 37.9304 | ETL.3830 | 40803332 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117482471 | Not Scheduled | T2 DI STSLS-MLS SS-MTC #1 :6/35 PNT STRS | 43878406 | STANISLAUS-MELONES SS-MANTECA #1+ | :006/035 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-06-21 | 2024-06-21 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.624725 | 37.9743 | ETL.3830 | 40744455 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117482645 | Mar | DI PALERMO-OROVILLE 0/3 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | 000/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2020-06-18 |  |  | 2021-03-04 | 2021-03-04 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.519024 | 39.455 | ETL.7740 | 41123115 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117482855 | Not Scheduled | T3 DI RND MTN-CTTNWD 033/280 RMV VEGN |  | ROUND MTN-COTTONWOOD #2 | 033/280 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-06-18 | 2019-12-18 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-122.149449 | 40.5658 | ETL.5640 | 40598925 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2019-09-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117483039 | Q2 | T3 DI PARADISE-TBL MTN 016/134C RPR POLE | 43724325 | PARADISE-TABLE MTN | 016/134 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2019-12-18 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [5 empty] | reprioritization of work - E/F tags pushed to 2020 | '-121.499399 | 39.6792 | ETL.4316 | 44552318 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117483096 | Q2 | T3 DI PARADISE-TBL MTN 016/134R RPR POLE | 43724325 | PARADISE-TABLE MTN | 016/134 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2019-12-18 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [5 empty] | reprioritization of work - E/F tags pushed to 2020 | '-121.499399 | 39.6792 | ETL.4316 | 44552501 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117483192 | Not Scheduled | DI LAS POSITAS-NEWARK 014/090 PAINT STRT | 43753291 | LAS POSITAS-NEWARK | 014/090 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-18 | 2021-06-18 | [9 empty] | Central | WSIP | [6 empty] | '-121.890686 | 37.549 | ETL.4980 | 40870183 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117483210 | Not Scheduled | T2 DI VLY SPRNGS-CLY 12/165 RPR WP HOLES | 43866744 | VALLEY SPRINGS-CLAY | 012/165 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-19 | 2020-06-19 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.890851 | 38.278 | ETL.8264 | 40911614 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117483215 | Q2 | T2 DI NEWARK-LIVERMORE 016/101 RPL POLE | 31455746 | NEWARK-LIVERMORE | 016/101 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2021-05-31 |  |  | 2021-05-12 | 2021-05-10 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.77932 | 37.6379 | ETL.7660 | 40804524 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 9 | Sycamore Grove Park | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2020-05-15 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117483384 | Feb | T2 DI TRINITY-MAPLE CRK 10/17R RPR GYWW | 43749708 | TRINITY-MAPLE CREEK | 010/017 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | WSIP | [8 empty] | ETL.8170 | 44420597 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-10-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117483592 | Not Scheduled | DI STA MEL SW SRA MAN 26/169 PNT STRS | 43878406 | STANISLAUS-MELONES SS-MANTECA #1+ | 026/169 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-19 | 2021-06-19 | [9 empty] | Central | WSIP | [6 empty] | '-120.773529 | 37.922 | ETL.3830 | 40803334 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117483865 | Not Scheduled | T2 DI COL CHA 0/19 RPR GYWW | 43910648 | COLGATE-CHALLENGE | 000/019 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-19 | 2021-05-31 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.19143 | 39.3421 | ETL.6480 | 40866889 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117484173 | Q2 | T2 DI HT CRK #1 WW 32/625 RPR PL | 43736798 | HAT CREEK #1-WESTWOOD | 032/625 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-19 | 2020-06-19 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.111218 | 40.6092 | ETL.7030 | 40592108 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117484197 | Not Scheduled | T2 DI VALLEY SPRINGS A002/043 RPR STRW | 43865299 | VALLEY SPRINGS #1 | A002/043 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2020-06-18 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.730492 | 38.2018 | ETL.8210 | 40907100 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117484400 | Feb | T2 DI ORVLLE-TERLO-TBLE#3 2/11 INST MRKS | 43933021 | MTN #3 (CDWR) | 002/011 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-06-18 | 2021-06-18 |  |  | 2021-02-22 | 2021-02-22 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.522945 | 39.5464 | ETL.6622 | 42580956 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117484494 | Not Scheduled | T2 DI STA MEL SW STA 0/1 PNT STRS | 43878406 | STANISLAUS-MELONES SS-MANTECA #1+ | 000/001 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-19 | 2021-06-19 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.373847 | 38.1395 | ETL.3830 | 40579566 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-12-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117484515 | Feb | T3 DI KLRC-CEDAR CRK 11/245 RPR STRW | 43724328 | KILARC-CEDAR CREEK | 011/245 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [5 empty] | reprioritization of work - E/F tags pushed to 2020 | '-121.960302 | 40.7653 | ETL.7290 | 40650325 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117484544 | Not Scheduled | T2 DI SPAULDING-SUMMIT 000/021 RPR GYWW | 43923459 | SPAULDING-SUMMIT | 000/021 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-18 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.636447 | 39.3228 | ETL.8060 | 40586116 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117484573 | Not Scheduled | DI RND MTN-COTTONWD #3 55/496 REPAINT | 43755801 | ROUND MTN-COTTONWOOD #3 | 055/496 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-06-18 | 2022-06-18 | [6 empty] | Likely MAT error - delink to correct |  |  | North Valley | WSIP | [6 empty] | '-122.223248 | 40.4495 | ETL.5650 | 40817529 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117484596 | Feb | T2NT DI ORVL-TRT-TBL MT 002/011 INS MRKS | 43932169 | MTN #1(CDWR) | 002/011 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-06-18 | 2021-06-18 |  |  | 2021-02-20 | 2021-02-02 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.522911 | 39.5466 | ETL.6621 | 42580634 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117484674 | Not Scheduled | T2 DI SPAULDING-SUMMIT 015/483 RPR STRW | 43923459 | SPAULDING-SUMMIT | 015/483 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-18 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.389485 | 39.3289 | ETL.8060 | 40770708 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117484750 | Feb | T2 DI ORVL-TRTO-TBE MTN#3 2/10 INST MRKS | 43933021 | MTN #3 (CDWR) | 002/010 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-06-18 | 2021-06-18 |  |  | 2021-02-22 | 2021-02-22 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.519462 | 39.5464 | ETL.6622 | 42580955 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117484900 | Not Scheduled | T2 EI DRUM-SUMMIT #2 18/214L REPL PL | 31521949 | DRUM-SUMMIT #2 | 018/214 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-24 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.483627 | 39.3171 | ETL.1450 | 44552369 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117485040 | Not Scheduled | T2 DI PITTSBRG-SN MTEO 006/028 RPR FOND | 44238800 | PITTSBURG-SAN MATEO | 006/028 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2020-06-18 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.892903 | 37.9538 | ETL.5463 | 40644625 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117485042 | Not Scheduled | DI VAC-VACAVILLE-CORDELIA 3/26 RPR SPLS | 43910119 | VACA-VACAVILLE-CORDELIA | 003/026 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2020-06-17 | [8 empty] | LATE | North Valley | WSIP |  |  |  | REJECT: Notification has been updated to correct circuit. Please resubmit once work has been completed for updated notification. |  |  | '-121.981896 | 38.4049 | ETL.4090 | 40841249 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  | Reject | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117485181 | Not Scheduled | T2 EI DRUM-SUMMIT #2 18/214 REPL PL | 31521949 | DRUM-SUMMIT #2 | 018/214 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-24 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.483627 | 39.3171 | ETL.1450 | 44552495 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117485291 | Not Scheduled | T2 EI DRUM-SUMMIT #2 18/217 INSTL GMKW | 43947607 | DRUM-SUMMIT #2 | 018/217 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-24 | 2021-06-24 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.480702 | 39.3174 | ETL.1450 | 44552421 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117485389 | Not Scheduled | NT EI OLEUM-NRTH TWR-CHRIST 0/6 PNT TWR | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 000/006 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-06-24 | 2021-06-24 | [9 empty] | Central | WSIP | [6 empty] | '-122.24671 | 38.0407 | ETL.3180 | 40804798 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117485598 | Not Scheduled | NT EI OLEUM-NRTH TWR-CHRIST 0/4 PNT TWR | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 000/004 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-06-24 | 2021-06-24 | [9 empty] | Central | WSIP | [6 empty] | '-122.251731 | 38.0418 | ETL.3180 | 40746018 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117486289 | Feb | T2 EI RND MTN-COTTNWD #3 R1/16L RPR STRW | 43946912 | ROUND MTN-COTTONWOOD #3 | R001/016 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-24 | 2020-06-24 |  |  | 2021-02-19 | 2021-02-15 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.935935 | 40.7985 | ETL.5650 | 44765641 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117486867 | Not Scheduled | DI NEWARK-LIVERMORE 008/052 PAINT STRS | 43752137 | NEWARK-LIVERMORE | 008/052 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-20 | 2025-06-20 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.868233 | 37.5732 | ETL.7660 | 40645722 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117487171 | Mar | T2 HUMBOLDT-TRINITY 67/0 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 067/000 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-06-24 | 2024-06-24 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.279785 | 40.7163 | ETL.1820 | 44562262 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117487179 | Mar | T2 HUMBOLDT-TRINITY 069/005 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 069/005 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-06-24 | 2024-06-24 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.328789 | 40.7053 | ETL.1820 | 44562218 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117487649 | Not Scheduled | T2 DRUM-SUMMIT #2 023/276R REPL STRW | 31451466 | DRUM-SUMMIT #2 | 023/276 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-13 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.390804 | 39.3292 | ETL.1450 | 44557684 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117487732 | Not Scheduled | T2 DI MADISON-VACA 50/312 RMV NEST | 43910328 | MADISON-VACA | 050/312 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-22 | 2020-06-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.98933 | 38.4183 | ETL.2170 | 40643367 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117487865 | Not Scheduled | T2 DI SPAULDING-SUMMIT 3/120 RPL STRW | 31453471 | SPAULDING-SUMMIT | 003/120 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-19 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.592151 | 39.3129 | ETL.8060 | 40586083 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117488204 | Q2 | T2 DI HT CRK #1-WSTWD 024/466 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 024/466 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-13 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.220435 | 40.6951 | ETL.7030 | 40817129 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117488269 | Not Scheduled | T2NT DI MAL RD MT #2 70/357 CANCEL | 44305271 | MALIN-ROUND MTN #2 | 070/357 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-21 | 2021-06-21 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.781686 | 41.0903 | ETL.6020 | 40819380 | Guy Wire Mark /Indic-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117488292 | Not Scheduled | T2 DI SPALDNG-SUMMIT 10/344 RPL PL | 31495368 | SPAULDING-SUMMIT | 010/344 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-25 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.476602 | 39.3175 | ETL.8060 | 40809667 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117488375 | Q2 | T2NT DI MLIN-RND MTN #2 71/359 INST GMKS | 43621093 | MALIN-ROUND MTN #2 | 071/359 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-20 | 2021-06-20 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.788067 | 41.0852 | ETL.6020 | 40858177 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117488402 | Q2 | T2 DI SNTH LN-PCFCA 004/050R RPL ANCW | 31488021 | SNEATH LANE-PACIFICA | 004/050 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-19 | 2020-06-19 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR2 | LATE | Central | WSIP | [8 empty] | ETL.7575 | 44384744 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117488415 | Q2 | T2NT DI MAL RD MT #2 68/342 INST GMKS | 43621093 | MALIN-ROUND MTN #2 | 068/342 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-21 | 2023-06-21 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.744196 | 41.12 | ETL.6020 | 40660987 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117488541 | Not Scheduled | T2 EI SPAULDING-SUMMIT 010/347 RPL POLE | 31453471 | SPAULDING-SUMMIT | 010/347 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-25 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.475127 | 39.3177 | ETL.8060 | 40618206 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117488625 | Not Scheduled | EI OLEUM-G #1 003/022 REPAINT | 44586166 | OLEUM-G #1 | 003/022 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-25 | 2021-06-25 | [9 empty] | Central | Non-WSIP | [6 empty] | '-122.234184 | 38.0152 | ETL.3150 | 40646292 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117488632 | Q2 | EI OLEUM-G #1 003/022 INST HRDT |  | OLEUM-G #1 | 003/022 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-06-25 | 2021-05-31 |  |  | 2021-04-02 | 2021-03-29 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.234184 | 38.0152 | ETL.3150 | 40646292 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-02 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117488912 | Q2 | DI COLGATE-PALERMO 022/445 RPL POLE | 31501100 | COLGATE-PALERMO | 022/445 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2020-06-18 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.518207 | 39.4555 | ETL.6500 | 40822466 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117489149 | Not Scheduled | EI OLEUM-G #1 002/021 REPAINT | 44586166 | OLEUM-G #1 | 002/021 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-25 | 2025-06-25 | [9 empty] | Central | Non-WSIP | [6 empty] | '-122.234171 | 38.0172 | ETL.3150 | 40580895 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117489216 | Not Scheduled | T2 EI SPAULDING-SUMMIT 010/353 RPL POLE | 31453471 | SPAULDING-SUMMIT | 010/353 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-25 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.472145 | 39.318 | ETL.8060 | 40828144 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117489532 | Not Scheduled | T2 DI VALLEY SPRINGS#1 5/94 RPL POLE | 31455760 | VALLEY SPRINGS #1 | 005/094 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-19 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833891 | 38.1748 | ETL.8210 | 40905509 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117489608 | Not Scheduled | DI CONTRA COSTA-LS POSITAS 7/49 CANCEL | 44587767 | CONTRA COSTA-LAS POSITAS | 007/049 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-06-20 | 2021-06-20 | [6 empty] | CANCEL/CNCL |  |  | Central | WSIP | [6 empty] | '-121.745519 | 37.9105 | ETL.4510 | 40872899 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117489715 | Q2 | DI MORAGA-LAKEWOOD 009/073 RPR SPLS | 43877251 | MORAGA-LAKEWOOD | 009/073 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-19 | 2020-06-19 |  |  | 2021-04-06 | 2021-04-05 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.12562 | 37.8701 | ETL.3741 | 40644192 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117489745 | Not Scheduled | EI MORAGA-SAN LEANDRO #1 09/67 REPAINT | 43708450 | MORAGA-SAN LEANDRO #1 | 009/067 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-06-25 | 2020-06-25 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.135162 | 37.7234 | ETL.2770 | 40804658 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117489817 | Not Scheduled | EI SOBRANTE-STNDD OL SW #1 7/46 RPR JUMS | 43877550 | SOBRANTE-STANDARD OIL SW STA #2 | 007/046 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-25 | 2020-06-25 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.23903 | 37.9999 | ETL.3800 | 40810740 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117489828 | Not Scheduled | T2NT DI COT DEL #1 7/48 PNT STRS | 44305035 | COTTONWOOD-DELEVAN #1 | 007/048 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-19 | 2021-06-19 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.268088 | 40.2948 | ETL.4550 | 40869183 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117490001 | Not Scheduled | T2 DI SPAULDING-SUMMIT 11/370 RPL STRW | 31495368 | SPAULDING-SUMMIT | 011/370 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-19 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.461299 | 39.3189 | ETL.8060 | 40702059 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117490304 | Q2 | DI NEWARK-LIVERMORE 006/043 RPL INSS | 31479060 | NEWARK-LIVERMORE | 006/043 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-20 | 2021-05-31 |  |  | 2021-05-12 | 2021-05-10 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.890098 | 37.5486 | ETL.7660 | 40671135 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117490533 | Not Scheduled | EI MORAGA-SAN LEANDRO #1 9/69 REPAINT | 43708450 | MORAGA-SAN LEANDRO #1 | 009/069 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-25 | 2020-06-25 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.136011 | 37.7222 | ETL.2770 | 40861002 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117490656 | Q2 | DI CORDELLA #2 2/50 RPL POLE | 31454608 | CORDELIA #2 TAP | 002/050 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-21 | 2020-06-21 |  |  | 2021-05-04 | 2021-04-26 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.144643 | 38.2348 | ETL.8184 | 40595149 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117490668 | Not Scheduled | T2 DI VALLEY SPRINGS #1 009/177 RPR STRW | 43863112 | VALLEY SPRINGS #1 | 009/177 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-18 | 2020-06-18 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.874985 | 38.1285 | ETL.8210 | 40908262 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117490726 | Not Scheduled | T2 EI SPAULDING-SUMMIT 010/360 RPL INSW | 31463883 | SPAULDING-SUMMIT | 010/360 | 93I | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-25 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.4665911 | 39.319 | ETL.8060 | 40678214 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117490728 | Not Scheduled | T2 DI STNISLS-MNTCA #2 12/73 RPR FOND |  | STANISLAUS-MANTECA #2 | 012/073 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-06-19 | 2024-06-19 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.567115 | 38.0418 | ETL.3820 | 40642813 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 27 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2018-10-14 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117490754 | Not Scheduled | T2 DI STNISLS-MNTCA #2 004/025 RPR FOND |  | STANISLAUS-MANTECA #2 | 004/025 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-06-19 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.43658 | 38.1117 | ETL.3820 | 40750233 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117490815 | Not Scheduled | T2 DI CHR SOB 10/56 RPR CONDS | 43877470 | CHRISTIE-SOBRANTE | 010/056 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-19 | 2020-06-19 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.198877 | 37.9972 | ETL.1260 | 40819643 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Land |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117490953 | Not Scheduled | EI MORAGA-SAN LEANDRO #1 09/70 REPAINT | 43708450 | MORAGA-SAN LEANDRO #1 | 009/070 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-06-25 | 2020-06-25 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.136636 | 37.7212 | ETL.2770 | 40581580 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117491002 | Mar | DI TGR CRK-VLLEY SPRINGS 23/185 RMV NEST | 43878409 | TIGER CREEK-VALLEY SPRINGS | 023/185 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-06-19 | 2021-05-31 |  |  | 2021-03-09 | 2021-03-08 |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-120.766409 | 38.2194 | ETL.5790 | 40906780 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 11 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117491273 | Not Scheduled | EI SOBRANTE-G #1 5/40 REPAINT | 44586182 | SOBRANTE-"G" #1 | 005/040 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-25 | 2021-06-25 | [9 empty] | Central | Non-WSIP | [6 empty] | '-122.300432 | 37.9169 | ETL.3720 | 40607984 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117491321 | Not Scheduled | DI NEWARK-LIVERMORE 8/51 REPAINT | 43752137 | NEWARK-LIVERMORE | 008/051 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-20 | 2022-06-20 | [9 empty] | Central | WSIP | [6 empty] | '-121.871832 | 37.5692 | ETL.7660 | 40599751 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117491327 | Not Scheduled | T2 DI VALLEY SPRINGS#1 9/192 RPR STRW | 43866693 | VALLEY SPRINGS #1 | 009/192 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-19 | 2020-06-19 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.883575 | 38.1194 | ETL.8210 | 40908277 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117491969 | Q2 | T2 PALERMO-OROVILLE #2 A6/077 REPL INSW | 31431545 | PALERMO-OROVILLE #2 | A006/077 | 93I | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-25 | 2020-06-25 |  |  | 2021-04-01 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.502618 | 39.512 | ETL.7740 | 41123111 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117491970 | Mar | EI PLACER-DEL MAR 000/002 RPL POLE | 31485413 | PLACER-DEL MAR | 000/002 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-25 | 2020-06-25 |  |  | 2021-03-31 | 2021-03-27 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.086567 | 38.9006 | ETL.7800 | 40872008 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-07-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117492782 | Not Scheduled | T2 DI CLAY-MARTTEL 22/316 RPR STRW | 43865457 | CLAY-MARTEL | 022/316 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-19 | 2020-06-19 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.847056 | 38.3496 | ETL.8250 | 40666544 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117492945 | Mar | DI GLENN #2 026/486 RPR GYWW | 43939404 | GLENN #2 | 026/486 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-19 | 2020-06-19 |  |  | 2021-03-10 | 2021-03-08 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.012339 | 39.5284 | ETL.6930 | 44421367 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117492956 | Not Scheduled | T3NT DI TGR CRK-VLLY SPRNGS 4/37 REPAINT | 43878409 | TIGER CREEK-VALLEY SPRINGS | 004/037 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-20 | 2021-06-20 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-120.57122 | 38.4269 | ETL.5790 | 40863675 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117492984 | Not Scheduled | T2NT DI TIG CRK VAL SPR 11/89 RPR FOND |  | TIGER CREEK-VALLEY SPRINGS | 011/089 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-06-19 | 2021-06-19 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.652116 | 38.3583 | ETL.5790 | 40582765 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Released |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117493044 | Not Scheduled | T3 DI CARIBOU-PALERMO :031/256C RPR GYWS | 44304491 | CARIBOU-PALERMO | :031/256C | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-19 | 2019-12-19 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467814 | 39.7593 | ETL.3190 | 44374356 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117493045 | Not Scheduled | T3NT DI CRBU-PALERMO :031/256C INST MRKS |  | CARIBOU-PALERMO | :031/256C | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-19 | 2021-06-19 | [7 empty] | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations | reprioritization of work - noncritical facility | '-121.467814 | 39.7593 | ETL.3190 | 44374356 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117493053 | Not Scheduled | T2NT DI SPAULDING-SUMMT 17/530 INST MRKW | 43923459 | SPAULDING-SUMMIT | 017/530 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-18 | 2021-06-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.368198 | 39.3101 | ETL.8060 | 40771535 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117493378 | Feb | DI HALSEY-PLACER 004/098 RPL STRW | 31404619 | HALSEY-PLACER | 004/098 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-20 | 2020-06-20 |  |  | 2021-02-11 | 2021-02-11 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.082619 | 38.9046 | ETL.6990 | 40858683 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-10-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117493584 | Q2 | DI STANISLAUS-NEWARK #1 090/599 RPR STRT |  | STANISLAUS-NEWARK #1 (12KV) | 090/599 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-19 | 2020-06-19 |  |  | 2021-06-05 | 2021-06-01 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.843614 | 37.5973 | ETL.3850 | 41196133 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-02 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117493731 | Not Scheduled | DI STANISLAUS-NEWARK #2 084/549 PNT STRS | 44586189 | STANISLAUS-NEWARK #2 (12KV) | 084/549 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-19 | 2021-06-19 | [9 empty] | Central | WSIP | [6 empty] | '-121.736048 | 37.6576 | ETL.3860 | 41196037 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117493753 | Not Scheduled | T2 DI VALLEY SPRINGS #1 004/086 RPR GYWW | 43862279 | VALLEY SPRINGS #1 | 004/086 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-20 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.829894 | 38.1801 | ETL.8210 | 40903817 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117493759 | Mar | T2 HUMBOLDT-TRINITY 070/002 RMV PL BUTT | 44311174 | HUMBOLDT-TRINITY | 070/002 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-06-24 | 2024-06-24 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.337232 | 40.7056 | ETL.1820 | 44562220 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117493770 | Mar | T2 HUMBOLDT-TRINITY 070/004 RMV BUTT | 44311174 | HUMBOLDT-TRINITY | 070/004 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-06-24 | 2024-06-24 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.344548 | 40.7057 | ETL.1820 | 44559976 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117493775 | Mar | T2 HUMBOLDT-TRINITY 070/006 RMV VEG |  | HUMBOLDT-TRINITY | 070/006 | HNA | F | Pre-2020_(9a) Other ignition related | Budget Owner (Veg/Land/Road) | 2019-06-24 | 2024-06-24 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.348875 | 40.7049 | ETL.1820 | 44562315 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | HNA | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117493777 | Mar | T2 HUMBOLDT-TRINITY 070/006 RMV PL BUTT | 44311174 | HUMBOLDT-TRINITY | 070/006 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-06-24 | 2024-06-24 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.348875 | 40.7049 | ETL.1820 | 44562315 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117493870 | Not Scheduled | T2 DI PARKWAY-MORAGA 007/041 RPL HRDS | 43877573 | PARKWAY-MORAGA | 007/041 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-20 | 2020-06-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233527 | 38.0404 | ETL.5930 | 40811223 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117493874 | Not Scheduled | T2 DI PARKWAY-MORAGA 007/041 RPR SPLS | 43877573 | PARKWAY-MORAGA | 007/041 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-20 | 2020-06-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233527 | 38.0404 | ETL.5930 | 40811223 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117494040 | Not Scheduled | T2 EI SPAULDING-SUMMIT 011/369 RPL POLE | 31453471 | SPAULDING-SUMMIT | 011/369 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-26 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.461854 | 39.3189 | ETL.8060 | 40594097 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117494126 | Mar | T2 HUMBOLDT-TRINITY 71/002B COMPLETE | 44311173 | HUMBOLDT-TRINITY | 071/002B | CHS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-24 | 2020-06-24 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.362283 | 40.7038 | ETL.1820 | 44562953 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117494177 | Mar | T2 HUMBOLDT-TRINITY 70/5 RMV POLE BUTTS | 44311174 | HUMBOLDT-TRINITY | 070/005 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-06-24 | 2024-06-24 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.346627 | 40.7054 | ETL.1820 | 44560626 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117494184 | Not Scheduled | NT DI NEWARK-VALLECITOS 91/596 PNT TWR | 44586165 | NEWARK-VALLECITOS | 091/596 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-18 | 2023-06-18 | [9 empty] | Central | WSIP | [6 empty] | '-121.843542 | 37.5972 | ETL.7670 | 40825462 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117494228 | Mar | T2 HUMBOLDT-TRINITY 066/004 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 066/004 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-06-24 | 2024-06-24 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.277202 | 40.7175 | ETL.1820 | 44560480 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117494231 | Mar | T2 HUMBOLDT-TRINITY 67/005 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 067/005 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-06-24 | 2024-06-24 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.293287 | 40.7093 | ETL.1820 | 44560642 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117494273 | Not Scheduled | EI PITTSBURG-COLMBA STEEL 02/17 REPAINT | 44586174 | PITTSBURG-COLUMBIA STEEL | 002/017 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-06-26 | 2020-06-26 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.907031 | 37.9976 | ETL.3300 | 40804805 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117494281 | Q2 | DI GREEN VALLEY-LLAGAS :009/064 RPR FOND | 44140504 | GREEN VALLEY-LLAGAS | :009/064 | ICQ | F | Pre-2020_(5) TD tag on other lines |  | 2019-06-19 | 2021-06-19 |  |  | 2021-05-21 | 2021-05-03 | [5 empty] | South | WSIP | [6 empty] | '-121.656829 | 37.1203 | ETL.1720 | 40761140 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117494493 | Not Scheduled | EI PITTSBURG-COLUMBIA STEEL 2/16 REPAINT | 44586174 | PITTSBURG-COLUMBIA STEEL | 002/016 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-26 | 2024-06-26 | [8 empty] | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.907 | 38.0015 | ETL.3300 | 40804817 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117494496 | Not Scheduled | EI PITTSBURG-COLUMBIA STL 2/16 RPL BOLT | 43877546 | PITTSBURG-COLUMBIA STEEL | 002/016 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-26 | 2024-06-26 | [6 empty] | Likely MAT error - delink to correct |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.907 | 38.0015 | ETL.3300 | 40804817 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117494647 | Not Scheduled | EI PITTSBURG-CLAYTON #1 2/18 REPAINT | 44586173 | PITTSBURG-CLAYTON #1 | 002/018 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-06-26 | 2020-06-26 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.907414 | 38.0018 | ETL.3280 | 40870490 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117494908 | Q2 | T2 DI TASSAJARA-NEWARK 21/97 RPL INSS | 31484762 | TASSAJARA-NEWARK | 021/097 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-19 | 2020-06-19 |  |  | 2021-05-20 | 2021-05-19 |  | Need to separate out Hanger Tag |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.916547 | 37.586 | ETL.5920 | 40633240 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117495300 | Not Scheduled | DI COR #2 TAP 2/44 RMV STRS | 43901134 | CORDELIA #2 TAP | 002/044 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-06-20 | 2020-06-20 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-122.142331 | 38.2315 | ETL.8184 | 40825086 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117495336 | Not Scheduled | DI PITTSBURG-TESLA #1 3/16 PAINT STRS | 44586176 | PITTSBURG-TESLA #1 | 003/016 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-19 | 2021-06-19 | [9 empty] | Central | WSIP | [6 empty] | '-121.909028 | 37.9969 | ETL.5510 | 40819981 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117495421 | Not Scheduled | T2 DI SPA SUM 3/119 INST MRKW | 43923459 | SPAULDING-SUMMIT | 003/119 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-18 | 2021-06-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.592894 | 39.3128 | ETL.8060 | 40618180 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117495701 | Q3 | DI TESLA-NEWARK#1 12/68 RPR FOND |  | TESLA-NEWARK #1 | 012/068 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-06-20 | 2021-06-20 |  |  | 2021-07-17 | 2021-07-12 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-121.76556 | 37.6393 | ETL.5720 | 40862796 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117495792 | Not Scheduled | DI LOS ESTEROS-METCALF 00/002 PAINT STRS | 43753289 | LOS ESTEROS-METCALF | 000/002 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-06-20 | 2020-06-20 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.741128 | 37.227 | ETL.5353 | 40662696 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117495939 | Not Scheduled | T2 DI PIT #1-COTTONWOD 39/337 RMV VEG |  | PIT #1-COTTONWOOD | 039/337 | HNA | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-20 | 2020-06-20 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.060957 | 40.6449 | ETL.5390 | 40817903 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2020-05-28 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117496029 | Q2 | T2 DI FORT ROSS-GUALALA 30/10 REPL GRD | 43908953 | GUALALA-MONTE RIO | 030/010 | ICB | F | Pre-2020_(9a) Other ignition related |  | 2019-06-22 | 2021-06-22 | 2021-06-15 | 2021-06-18 | 2021-06-17 | 2021-06-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.249438 | 38.5508 | ETL.6980 | 40587345 | Raptor Guard-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117496726 | Q3 | EI HELMS-GREGG #2 003/030B RPR FOND | 44104288 | HELMS-GREGG #2 | 003/030B | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-06-26 | 2021-05-31 |  |  | 2021-08-15 | 2021-07-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.015864 | 37.0132 | ETL.4880 | 40740049 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117497091 | Mar | T2 HUMBOLDT-TRINITY 073/2B RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 073/002B | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-06-22 | 2022-06-22 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.395038 | 40.7056 | ETL.1820 | 40642991 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117497093 | Mar | T2 HUMBOLDT-TRINITY 72/004 RPR ROAD | 44311173 | HUMBOLDT-TRINITY | 072/004 | CHS | F | Pre-2020_(3) On high spread structure | Budget Owner (Veg/Land/Road) | 2019-06-22 | 2022-06-22 |  |  | 2021-03-28 | 2021-03-20 |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Program | 2021 - ROADS | '-123.386005 | 40.7051 | ETL.1820 | 44562210 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | CH | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117497715 | Not Scheduled | T2 DI SANTA YNEZ TAP 002/022 RPR STRW | 44371037 | SANTA YNEZ TAP | 002/022 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-21 | 2020-06-21 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-120.145584 | 34.6349 | ETL.3701 | 40751451 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117497952 | Not Scheduled | DI SOBRANT-STD OIL SWS#1 7/47 PAINT STRS | 44586185 | SOBRANTE-STANDARD OIL SW STA #2 | 007/047 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-20 | 2021-06-20 | [9 empty] | Central | WSIP | [6 empty] | '-122.240676 | 37.9992 | ETL.3800 | 40804898 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117498003 | Not Scheduled | DI ELECTRA-BELLOTA 020/141 RPR FOND | 44460411 | ELECTRA-BELLOTA | 020/141 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-20 | 2020-06-20 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.905515 | 38.1071 | ETL.4670 | 40818353 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117498005 | Not Scheduled | DI ELECTRA-BELLOTA 020/141 PAINT STRS | 43878408 | ELECTRA-BELLOTA | 020/141 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-06-20 | 2021-06-20 | [9 empty] | Central | WSIP | [6 empty] | '-120.905515 | 38.1071 | ETL.4670 | 40818353 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117498174 | Mar | DI PALERMO-OROVILLE #2 000/002 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | 000/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-21 | 2020-06-21 |  |  | 2021-03-04 | 2021-03-04 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.51857 | 39.4553 | ETL.7740 | 41123114 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117498219 | Not Scheduled | DI NEWARK-JARVIS #1 005/037 RPR INSS | 43877252 | NEWARK-JARVIS #1 | 005/037 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-21 | 2020-06-21 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.902169 | 37.5354 | ETL.3020 | 44361554 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117498793 | Not Scheduled | T2 DI CARIBOU-PALERMO :5/45 BURIED STUB | 44059014 | CARIBOU-PALERMO | :005/045 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-21 | 2020-06-21 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.218992 | 40.0312 | ETL.3190 | 40910287 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117498880 | Not Scheduled | T2 DI SPAULDING-SUMMIT 000/012 RPR GYWW | 43923459 | SPAULDING-SUMMIT | 000/012 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-21 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.640116 | 39.3235 | ETL.8060 | 40660103 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117498925 | Not Scheduled | T2 EI SPAULDING-SUMMIT 011/392 INS MRKW | 43923459 | SPAULDING-SUMMIT | 011/392 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-27 | 2023-06-27 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.450839 | 39.3177 | ETL.8060 | 44156122 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117499113 | Not Scheduled | EI SOBRNTE-GRIZY-CLRMNT #2 02/20 REPAINT | 44586183 | SOBRANTE-GRIZLY-CLARMNT #2+ | 002/020 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-27 | 2020-06-27 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.188205 | 37.882 | ETL.3750 | 40810738 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117499147 | Not Scheduled | DI ELECTRA-BELLOTA 019/139 RPL HRDS | 43865530 | ELECTRA-BELLOTA | 019/139 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-21 | 2020-06-21 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.902842 | 38.1102 | ETL.4670 | 40752910 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117499170 | Q2 | T2 DI FRT RSS GUA 44/7 RPR GYWW | 43920743 | GUALALA-MONTE RIO | 044/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.331007 | 38.7016 | ETL.6980 | 40808302 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117499279 | Mar | DI SOBRANTE-GRIZ-CLARE #2 2/23 REPL INSS | 31492386 | SOBRANTE-GRIZLY-CLARMNT #2+ | 002/023 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-27 | 2020-06-27 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.1836763 | 37.8769 | ETL.3750 | 40896427 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117499291 | Not Scheduled | DI ELECTRA-BELLOTA 019/139 REPAINT | 43878408 | ELECTRA-BELLOTA | 019/139 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-06-21 | 2021-06-21 | [9 empty] | Central | WSIP | [6 empty] | '-120.902842 | 38.1102 | ETL.4670 | 40752910 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 2 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117499550 | Not Scheduled | T3 DI CARIBOU-PALERMO :32/263 BURID STUB | 44056495 | CARIBOU-PALERMO | :032/263 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-21 | 2019-12-21 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | Circuit Based Scheduling | '-121.475573 | 39.7491 | ETL.3190 | 40656367 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117499682 | Q2 | DI MEN PHI JCT HOP 14/8 RMV VEGN |  | MENDOCINO-PHILO JCT-HOPLAND | 014/008 | HNA | E | Pre-2020_(9a) Other ignition related | Budget Owner (Veg/Land/Road) | 2019-06-24 | 2021-05-31 |  |  | 2021-05-14 | 2021-05-11 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.143457 | 39.0649 | ETL.7520 | 40871979 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | HNA | Q2 |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117500113 | Q3 | T2 DI CARIBOU-PLUMAS JCT 14/16 RPR GYWW | 43920793 | CARIBOU-PLUMAS JCT | 014/016 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-20 | 2021-05-31 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.94371 | 39.9571 | ETL.6290 | 40810060 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117500274 | Not Scheduled | T2 DI SPAULDING-SUMMIT 011/406 RPL POLE | 31453471 | SPAULDING-SUMMIT | 011/406 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-21 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.444875 | 39.3184 | ETL.8060 | 40862170 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117500693 | Feb | 5 POINTS SW STA-HURON-GATES 15/1 RPLC PL | 31455753 | SCHINDLER-HURON-GATES | 015/001 | 70Y | B | 2020_(0) A and B Tags |  | 2019-03-29 | 2021-02-18 | 2021-02-15 | 2021-02-15 | 2021-02-15 | 2021-02-15 | [5 empty] | South | Non-WSIP | [6 empty] | '-120.121315 | 36.1966 | ETL.9160 | 40582725 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 3 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2021-02-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 117501263 | Not Scheduled | T2 EI VALLEY SPRNGS #1 A0/21A C RPR GYWW | 43878410 | VALLEY SPRINGS #1 | A000/021A | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-27 | 2020-06-27 | [7 empty] | TR2 | LATE | Central | WSIP | [8 empty] | ETL.8210 | 44291411 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117501751 | Q3 | T2 DI CARIBOU#2 20/15 INST MRKW | 43854201 | CARIBOU #2 | 020/015 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-21 | 2021-06-21 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.021227 | 40.0301 | ETL.6280 | 40768829 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117501816 | Not Scheduled | T2 DI SPAULDING-SUMMT 11/397 INST MRKW | 43923459 | SPAULDING-SUMMIT | 011/397 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-20 | 2023-06-20 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.448486 | 39.3175 | ETL.8060 | 40876698 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117501819 | Q3 | T2 DI TESLA-METCALF 32/133 RPR FOND |  | TESLA-METCALF | 032/133 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-24 | 2020-06-24 |  |  | 2021-07-10 | 2021-07-05 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.726393 | 37.2656 | ETL.6110 | 40651772 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Multi Prog |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117501851 | Not Scheduled | T2 DI BLACK TAP 000/002 REPAINT | 44304021 | BLACK TAP | 000/002 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-06-20 | 2020-06-20 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.976527 | 40.9899 | ETL.5431 | 44188818 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117501977 | Not Scheduled | T2 DI VALLEY SPRINGS #1 10/197 RPR GYWW | 43875774 | VALLEY SPRINGS #1 | 010/197 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-24 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.88683 | 38.1173 | ETL.8210 | 40908282 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Not Released | CalTrans | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117502396 | Not Scheduled | T2 EI CARIBOU-PALERMO 15/123 RPR STRT | 44069597 | CARIBOU-PALERMO | 015/123 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-21 | 2020-06-21 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.501865 | 39.6662 | ETL.3190 | 40913205 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117502430 | Not Scheduled | T2 DI CARIBOU-PALERMO 15/123 RPL INSS |  | CARIBOU-PALERMO | 015/123 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-21 | 2020-06-21 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.501865 | 39.6662 | ETL.3190 | 40913205 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117502488 | Q2 | T2 DI MLN-RND MTN #2 68/344 INS MRKS | 43621093 | MALIN-ROUND MTN #2 | 068/344 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-22 | 2021-06-22 |  |  | 2021-06-15 | 2021-05-01 |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.748645 | 41.1165 | ETL.6020 | 40759865 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117502527 | Not Scheduled | DI BEL PLA 1/16 RMV VEGN |  | BELL-PLACER | 001/016 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-06-18 | 2020-06-18 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.05913 | 38.9368 | ETL.4395 | 40577450 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2019-01-24 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117502947 | Not Scheduled | T2NT DI SPAULDING-SUMMT 16/512 INST MRKW | 43923459 | SPAULDING-SUMMIT | 016/512 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-20 | 2021-06-20 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.378387 | 39.3163 | ETL.8060 | 40878079 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117503278 | Q2 | EI KONOCTI-MIDDLETOWN ;24/6 RPR GYWW | 43919877 | KONOCTI-MIDDLETOWN | ;024/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-28 | 2021-05-31 | 2021-04-19 | 2021-04-23 | 2021-04-20 | 2021-04-20 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.61734 | 38.9073 | ETL.6380 | 44667817 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117503425 | Not Scheduled | T3NT DI ROUND MTN-TBL MT#2 4/24 REPAINT | 44586179 | ROUND MTN-TABLE MTN #2 | 004/024 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-20 | 2021-06-20 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.93821 | 40.7493 | ETL.6070 | 40762873 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117504021 | Not Scheduled | DI NEWARK-LAW LAB 006/042 RPL INSS | 31455147 | NEWARK-LAWRENCE LAB | 006/042 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-20 | 2021-05-31 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.891898 | 37.5466 | ETL.3060 | 40732589 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold srdy |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117504069 | Feb | DI RND MTN-COTTNWD #3 57/523 INST MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 057/523 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-25 | 2021-06-25 |  |  | 2021-02-19 | 2021-02-15 | [5 empty] | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-122.248626 | 40.4188 | ETL.5650 | 40657352 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117504146 | Not Scheduled | DI NEWARK-JARVIS #1 5/39 RPR GYWS | 43877252 | NEWARK-JARVIS #1 | 005/039 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-21 | 2020-06-21 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.89713 | 37.5411 | ETL.3020 | 40857702 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117504207 | Not Scheduled | T2NT DI RND MNTN-TBL MNTN 44/197 PNT TWR | 44586179 | ROUND MTN-TABLE MTN #2 | 044/197 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-25 | 2021-06-25 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.919231 | 40.1677 | ETL.6070 | 40816753 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117504453 | Q2 | T2NT DI RND MTN-TBL MTN 64/269 INST GMKS | 44305720 | ROUND MTN-TABLE MTN #2 | 064/269 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-25 | 2021-06-25 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.814772 | 39.8898 | ETL.6070 | 40872477 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117504459 | Q2 | T2 DI PARDSE-TBL MTN 6/55AB (L) RPR GYWW | 43724325 | PARADISE-TABLE MTN | 006/055AB | ICW | E | 2020_(1a) PSPS |  | 2019-06-21 | 2020-06-21 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4316 | 44383158 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117504551 | Q2 | T2 DI PARDSE-TBL MTN 6/55AB (C) RPR GYWW | 43724325 | PARADISE-TABLE MTN | 006/055AB | ICW | E | 2020_(1a) PSPS |  | 2019-06-21 | 2020-06-21 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4316 | 44383159 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117504555 | Q2 | T2 DI PARDSE-TBL MTN 6/55AB (R) RPR GYWW | 43724325 | PARADISE-TABLE MTN | 006/055AB | ICW | E | 2020_(1a) PSPS |  | 2019-06-21 | 2020-06-21 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4316 | 44383160 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117504556 | Q2 | T2 DI PARDSE-TBL MTN 6/55AB (C) RPR PL | 43724325 | PARADISE-TABLE MTN | 006/055AB | ICW | E | 2020_(1a) PSPS |  | 2019-06-21 | 2020-06-21 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4316 | 44383159 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117504647 | Not Scheduled | T2 CAYUCOS-CAMBRIA 016/119 REPL INSW | 31456903 | CAYUCOS-CAMBRIA | 016/119 | 93I | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-28 | 2021-05-31 | [7 empty] | TR2 | LATE | South | Non-WSIP | [6 empty] | '-121.087555 | 35.5891 | ETL.8560 | 40846544 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 2 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-08-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117505062 | Q3 | EI HELMS-GREGG #2 3/26B RPR FOND | 44104289 | HELMS-GREGG #2 | 003/026B | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-06-28 | 2021-05-31 |  |  | 2021-08-15 | 2021-07-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.008252 | 37.0181 | ETL.4880 | 40740443 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117506189 | Not Scheduled | T3 DI GRIZZLY TAP 0/13 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-27 | 2019-10-16 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.284071 | 39.8978 | ETL.2395 | 44549881 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117506410 | Not Scheduled | T3 DI GRIZZLY TAP 1/3 REM VEGN |  | TAP (CITY OF SANTA CLARA) | 001/003 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-06-27 | 2019-12-27 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.28805 | 39.8998 | ETL.2395 | 44550803 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117506415 | Not Scheduled | T3 DI GRIZZLY TAP 1/3 REM VEGN |  | TAP (CITY OF SANTA CLARA) | 001/003 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-06-27 | 2019-12-27 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.28805 | 39.8998 | ETL.2395 | 44550737 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117506473 | Q2 | T2 DI RNDMTN-TBLMTN 64/270 INST GMKS | 44305720 | ROUND MTN-TABLE MTN #2 | 064/270 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-25 | 2021-06-25 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.813862 | 39.8876 | ETL.6070 | 40596118 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117506640 | Not Scheduled | T2NT DI MALIN-RND MTN#2 69/349 CANCEL | 44305271 | MALIN-ROUND MTN #2 | 069/349 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-21 | 2021-06-21 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.762555 | 41.1055 | ETL.6020 | 40870333 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117506750 | Q3 | EI HELMS-GREGG #1 000/007A INST HRDT | 43908764 | HELMS-GREGG #1 | 000/007A | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-06-29 | 2022-06-29 |  |  | 2021-08-15 | 2021-07-02 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-118.977902 | 37.0362 | ETL.4870 | 40576731 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117506825 | Not Scheduled | EI IGNCO-ALTO-SASLTO #1 10/072 PNT STRT | 44585959 | IGNACIO-ALTO-SAUSALITO #1 | 010/072 | ICX | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-06-29 | 2021-06-29 | [6 empty] | Likely MAT error - delink to correct |  |  | North Coast | Non-WSIP | [6 empty] | '-122.509311 | 37.926 | ETL.7160 | 40827698 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117507284 | Not Scheduled | EI PITTSBURG-COLUMBIA STL :0/1A RPR GYWS | 43886420 | PITTSBURG-COLUMBIA STEEL | :000/001A | ICS | F | Pre-2020_(5) TD tag on other lines |  | 2019-06-29 | 2021-06-29 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.872831 | 37.9873 | ETL.3300 | 40576381 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117507407 | Not Scheduled | EI PTSBRG-CLMBA STL :0/1A INSTL CLMB GRD | 31494704 | PITTSBURG-COLUMBIA STEEL | :000/001A | 93A | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-06-29 | 2021-06-29 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.872831 | 37.9873 | ETL.3300 | 40576381 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117544824 | Not Scheduled | T3 DI GRIZZLY TAP 1/6L RPR PL | 43760153 | TAP (CITY OF SANTA CLARA) | 001/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-29 | 2019-12-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.290928 | 39.8991 | ETL.2395 | 44550759 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117545138 | Not Scheduled | DI NEWARK-JARVIS #1 5/35 RMV NEST | 43877252 | NEWARK-JARVIS #1 | 005/035 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-06-28 | 2020-06-28 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.906426 | 37.5321 | ETL.3020 | 40745974 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117545273 | Mar | T2 HUMBOLDT-TRINITY 073/003 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 073/003 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-06-22 | 2022-06-22 |  |  | 2021-03-27 | 2021-03-01 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.399021 | 40.7035 | ETL.1820 | 44562968 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117545278 | Mar | T2 HUMBOLDT-TRINITY 62/0 RMV BUTT | 44298745 | HUMBOLDT-TRINITY | 062/000 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-02 | 2024-06-02 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.196663 | 40.7375 | ETL.1820 | 44560488 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117545351 | Mar | DI PLACER-DEL MAR 000/003 RPR PL | 43912223 | PLACER-DEL MAR | 000/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-28 | 2020-06-28 |  |  | 2021-03-31 | 2021-03-27 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.087149 | 38.9 | ETL.7800 | 40867079 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117545463 | Not Scheduled | T2 DI HEL GREG #2 9/70B RMV NEST | 43825465 | HELMS-GREGG #2 | 009/070B | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-06-29 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.111955 | 36.9887 | ETL.4880 | 40740538 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117545492 | Not Scheduled | T3 DI GRIZZLY TAP 0/6 INST HRDW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/006 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-06-27 | 2019-12-27 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.278706 | 39.8937 | ETL.2395 | 44549956 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117545516 | Not Scheduled | EI BRDGVLLE-CTTNWOOD 000/003 REMV VEGN |  | BRIDGEVILLE-COTTONWOOD | 000/003 | HNA | E | Pre-2020_(9a) Other ignition related | Budget Owner (Veg/Land/Road) | 2019-06-18 | 2020-06-18 | [8 empty] | LATE | North Valley | Non-WSIP | [8 empty] | ETL.1110 | 44423422 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117545714 | Not Scheduled | T3 DI GRIZZLY TAP 003/001 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-29 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.320267 | 39.8983 | ETL.2395 | 44551382 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117545838 | Not Scheduled | T2NT DI STNSLS-MNTCA #2 018/105 REPAINT | 43878405 | STANISLAUS-MANTECA #2 | 018/105 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-26 | 2021-06-26 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.637983 | 37.9901 | ETL.3820 | 40744467 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117545955 | Not Scheduled | T3 DI GRIZ TAP 3/4R RMV DEBRIS | 43760153 | TAP (CITY OF SANTA CLARA) | 003/004 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-06-28 | 2022-12-28 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.320922 | 39.901 | ETL.2395 | 44551436 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117545958 | Not Scheduled | T3 DI GRIZ TAP 3/4 RMV DEBRIS | 43760153 | TAP (CITY OF SANTA CLARA) | 003/004 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-06-28 | 2022-12-28 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.320922 | 39.901 | ETL.2395 | 44551415 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117546891 | Q3 | T2 DI CARIBOU #2 017/028 RPR GYWW | 43742132 | CARIBOU #2 | 017/028 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-27 | 2020-06-27 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.061832 | 40.0205 | ETL.6280 | 40862055 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-22 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117547621 | Q3 | T2 DI CARIBOU #2 024/628 INS MRKS | 43854201 | CARIBOU #2 | 024/628 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-26 | 2021-06-26 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-120.965067 | 40.0393 | ETL.6280 | 44259148 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117548732 | Not Scheduled | EI IGNACIO-ALTO 000/001 RPR GYWW | 43920745 | IGNACIO-ALTO | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-01 | 2020-07-01 | [8 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-122.540334 | 38.0755 | ETL.7150 | 44574866 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117554026 | Not Scheduled | T2 DI DRM-GRSS VLLY-WMR B16/380 REPL PL | 31500646 | DRUM-GRASS VALLEY-WEIMAR | B016/380 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-20 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  | REJECT: Could not complete work due to a clearance, materials or access issue. |  |  | '-120.962544 | 39.1283 | ETL.6760 | 40590232 | Structure-Wood | No Good/Out of Stdrd | Replace | DOCC | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  | Reject | 2019-08-07 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117554128 | Q2 | T2 DI RND MTN-TBL MTN 74/305 INST GMKS | 44305720 | ROUND MTN-TABLE MTN #2 | 074/305 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-06-25 | 2021-06-25 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.74984 | 39.7443 | ETL.6070 | 40765376 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117554303 | Not Scheduled | T2 DI VALLEY SPRNGS #1 A001/033 RPR POLE |  | VALLEY SPRINGS #1 | A001/033 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-20 | 2020-06-20 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.73895 | 38.2044 | ETL.8210 | 40907090 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117554352 | Not Scheduled | T2 DI MALIN-RND MTN #2 078/398 CANCEL | 43621093 | MALIN-ROUND MTN #2 | 078/398 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-06-24 | 2021-06-24 | [6 empty] | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.890488 | 41.0279 | ETL.6020 | 40868976 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117554417 | Mar | EI CLEAR LAKE-HOPLAND 02/009 RPR GYWW | 43919879 | CLEAR LAKE-HOPLAND | 002/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-02 | 2021-05-31 |  |  | 2021-03-26 | 2021-03-24 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.6390 | 44224595 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117554425 | Not Scheduled | T2 DI DRUM-SUMMIT #2 27/326A CANCEL | 43947611 | DRUM-SUMMIT #2 | 027/326A | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-26 | 2021-05-31 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.33228 | 39.3122 | ETL.1450 | 40752050 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117554663 | Not Scheduled | T2 DI DRUM-SUMMIT #2 27/326C RPR GYWW | 43947611 | DRUM-SUMMIT #2 | 027/326C | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-26 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.332213 | 39.3121 | ETL.1450 | 42572857 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117555078 | Not Scheduled | T2 DI CNTERVILLE-TBL MTN 4/76 REPR SPLW | 43939207 | CENTERVILLE-TABLE MTN | 004/076 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-29 | 2020-06-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.705945 | 39.7319 | ETL.6320 | 44384785 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117555081 | Feb | T2 DI RND MTN-CTNWD #3 R001/15L RPR STRW | 43946912 | ROUND MTN-COTTONWOOD #3 | R001/015 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-25 | 2020-06-25 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.935829 | 40.7997 | ETL.5650 | 44737543 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117555082 | Feb | T2 DI RND MTN-CTWD #3 R001/15R RPR STRW | 43946912 | ROUND MTN-COTTONWOOD #3 | R001/015 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-25 | 2020-06-25 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.935829 | 40.7997 | ETL.5650 | 44737544 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117555692 | Not Scheduled | T2NT DI MLN-RND MTN #2 064/320 CANCEL | 43621093 | MALIN-ROUND MTN #2 | 064/320 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-01 | 2023-07-01 | [6 empty] | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.694345 | 41.1595 | ETL.6020 | 40601164 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117555697 | Not Scheduled | T2NT DI MLN-RND MTN #2 062/312 CANCEL | 44305271 | MALIN-ROUND MTN #2 | 062/312 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-01 | 2024-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.676937 | 41.1784 | ETL.6020 | 40660983 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117555751 | Q2 | T2 DI FORT ROSS-GUALALA 058/000 RPR GYWW | 43920743 | GUALALA-MONTE RIO | 058/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-02 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.514432 | 38.7749 | ETL.6980 | 40606947 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117556001 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 026/317 INS GMKW | 43947608 | DRUM-SUMMIT #2 | 026/317 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.345206 | 39.3088 | ETL.1450 | 44557479 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117556002 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 026/317 INS GMKW | 43947608 | DRUM-SUMMIT #2 | 026/317 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.345206 | 39.3088 | ETL.1450 | 44557784 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117556003 | Not Scheduled | T2NT DI DRUM-SUMMIT #2 026/317 INS GMKW | 43947608 | DRUM-SUMMIT #2 | 026/317 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.345206 | 39.3088 | ETL.1450 | 44557646 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117556006 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 024/290C INS GMKW | 43910101 | DRUM-SUMMIT #1 | 024/290C | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.370392 | 39.3104 | ETL.1440 | 42572726 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117556007 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 024/290C INS MRKW | 43910101 | DRUM-SUMMIT #1 | 024/290C | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.370392 | 39.3104 | ETL.1440 | 42572726 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117556548 | Not Scheduled | T2NT DI DRM-SUMMIT #1 023/274B INST GMKW | 43910102 | DRUM-SUMMIT #1 | 023/274B | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.394185 | 39.3112 | ETL.1440 | 42572723 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117556831 | Not Scheduled | T2 DI CARIBOU-PALERMO :15/122 REPR STUBS | 44069583 | CARIBOU-PALERMO | :015/122 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-07-01 | 2020-07-01 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.308374 | 39.9421 | ETL.3190 | 40738347 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117558205 | Q2 | T2 DI TULE-SPRINGVILLE 13/16 RPR GYWW | 44323707 | TULE-SPRINGVILLE | 013/016 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-28 | 2020-06-28 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.899482 | 36.1099 | ETL.9040 | 40823413 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-12-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117558329 | Not Scheduled | T2 DI BCKS CK-RCK CRK-CRST 2/25 PNT STRS | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | 002/025 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) | 2019-07-02 | 2021-07-02 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-121.37416 | 39.8811 | ETL.4430 | 40758269 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117559046 | Q2 | T2 DI CSCDE-BNTN-DSCHTS 4/90 RPR GYWS | 44370533 | CASCADE-BENTON-DESCHUTES | 004/090 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-28 | 2020-06-28 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.310589 | 40.5951 | ETL.6310 | 40817322 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117559050 | Not Scheduled | EI NT IGNCI-ALT-SSLT #1 000/007 CANCEL | 44310665 | IGNACIO-ALTO-SAUSALITO #1 | 000/007 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-03 | 2021-07-03 | [6 empty] | CANCEL/CNCL |  |  | North Coast | Non-WSIP | [6 empty] | '-122.535807 | 38.0749 | ETL.7160 | 40701499 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117559505 | Not Scheduled | EI NT IGNC-ALT-SSLT #1 000/06 STRT PAINT | 44310665 | IGNACIO-ALTO-SAUSALITO #1 | 000/006 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-03 | 2021-07-03 | [9 empty] | North Coast | Non-WSIP | [6 empty] | '-122.537918 | 38.0762 | ETL.7160 | 40588462 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117559986 | Not Scheduled | EI STNISLAUS-NWARK #2 84/548 PAINT STRT | 44586189 | STANISLAUS-NEWARK #2 (12KV) | 084/548 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-03 | 2021-07-03 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.733988 | 37.6581 | ETL.3860 | 41196036 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560068 | Not Scheduled | DI ELECTRA-BELLOTA 20/140 RPR FOND | 44460410 | ELECTRA-BELLOTA | 020/140 | ICQ | F | Pre-2020_(5) TD tag on other lines |  | 2019-06-28 | 2021-06-28 | [9 empty] | Central | WSIP | [6 empty] | '-120.904178 | 38.1087 | ETL.4670 | 40819257 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560134 | Mar | T2 DI TEJON-LEBEC 011/184 RMV VEGN |  | TEJON-LEBEC | 011/184 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-06-28 | 2021-05-31 |  |  | 2021-03-15 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-118.895745 | 34.8765 | ETL.9250 | 40662630 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | HNA | Mar |  |  | 2019-08-14 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560177 | Not Scheduled | T2 MORRO BAY-SLO#2 3/020 RPR INSS |  | MORRO BAY-SAN LUIS OBISPO #2 | 003/020 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-03 | 2021-05-31 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.806646 | 35.3537 | ETL.2820 | 40638126 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-10-02 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560197 | Q2 | EI STNISLUS-NEWARK #2 84/549 RPL HRDT |  | STANISLAUS-NEWARK #2 (12KV) | 084/549 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-03 | 2020-07-03 |  |  | 2021-06-19 | 2021-06-14 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.736048 | 37.6576 | ETL.3860 | 41196037 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560210 | Q2 | EI STNISLUS-NEWARK #2 84/549 RPR STRT |  | STANISLAUS-NEWARK #2 (12KV) | 084/549 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-03 | 2020-07-03 |  |  | 2021-06-19 | 2021-06-14 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.736048 | 37.6576 | ETL.3860 | 41196037 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-24 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560377 | Q2 | EI STANISLAUS-NEWARK #1 83/5 INS ANTCLMB | 31493857 | STANISLAUS-NEWARK #1 (12KV) | 083/551 | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-03 | 2021-07-03 |  |  | 2021-06-05 | 2021-06-01 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.736104 | 37.6577 | ETL.3850 | 41196040 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560379 | Not Scheduled | EI STANISLAUS-NEWARK #1 83/5 PAINT STRT |  | STANISLAUS-NEWARK #1 (12KV) | 083/551 |  | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-03 | 2021-07-03 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.736104 | 37.6577 | ETL.3850 | 41196040 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560424 | Q2 | EI STANISLAUS-NEWARK #1 83/5 RPL HRDT |  | STANISLAUS-NEWARK #1 (12KV) | 083/551 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-03 | 2020-07-03 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.736104 | 37.6577 | ETL.3850 | 41196040 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560599 | Not Scheduled | EI STNISLUS-NWARK #2 84/550 PAINT STRT | 44586189 | STANISLAUS-NEWARK #2 (12KV) | 084/550 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-03 | 2021-07-03 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.737918 | 37.657 | ETL.3860 | 41196038 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560691 | Q2 | EI STNISLUS-NWARK #2 84/550 RPL HRDT |  | STANISLAUS-NEWARK #2 (12KV) | 084/550 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-03 | 2020-07-03 |  |  | 2021-06-19 | 2021-06-14 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.737918 | 37.657 | ETL.3860 | 41196038 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560696 | Q2 | EI STNISLUS-NWARK #2 84/550 RPL BENT MEM |  | STANISLAUS-NEWARK #2 (12KV) | 084/550 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-03 | 2020-07-03 |  |  | 2021-06-19 | 2021-06-14 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.737918 | 37.657 | ETL.3860 | 41196038 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560818 | Q2 | EI STANISLAUS-NWRK #1 83/552 INS ANTCLMB | 31493857 | STANISLAUS-NEWARK #1 (12KV) | 083/552 | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-03 | 2021-07-03 |  |  | 2021-06-05 | 2021-06-01 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.73798 | 37.6571 | ETL.3850 | 41196042 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560819 | Q2 | EI STANISLAUS-NEWARK #1 83/552 RPL HRDT |  | STANISLAUS-NEWARK #1 (12KV) | 083/552 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-03 | 2020-07-03 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.73798 | 37.6571 | ETL.3850 | 41196042 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560872 | Feb | T2 MRR-BY SN LUS OBSP #2 05/029 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 005/029 | 93K | F | Pre-2020_(5) TD tag on other lines |  | 2019-07-03 | 2024-07-03 | 2021-02-16 | 2021-02-19 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.783413 | 35.3365 | ETL.2820 | 40884613 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-10-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560931 | Not Scheduled | EI STANISLAUS-NWRK #2 84/551 PAINT STRT | 44586189 | STANISLAUS-NEWARK #2 (12KV) | 084/551 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-03 | 2021-07-03 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.739423 | 37.6562 | ETL.3860 | 41196039 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560936 | Q2 | EI STANISLUS-NWRK #2 84/551 RPL BENT MEM |  | STANISLAUS-NEWARK #2 (12KV) | 084/551 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-03 | 2020-07-03 |  |  | 2021-06-19 | 2021-06-14 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.739423 | 37.6562 | ETL.3860 | 41196039 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117560989 | Q2 | EI STANISLAUS-NWRK #2 84/551 RPL HRDT |  | STANISLAUS-NEWARK #2 (12KV) | 084/551 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-03 | 2020-07-03 |  |  | 2021-06-19 | 2021-06-14 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.739423 | 37.6562 | ETL.3860 | 41196039 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117561078 | Feb | T2 MORRO BAY-SLO #2 5/31 REPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 005/031 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-03 | 2021-05-31 | 2021-02-16 | 2021-02-19 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.777633 | 35.3322 | ETL.2820 | 40611534 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-10-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117561102 | Not Scheduled | EI STANISLAUS-NEWARK #1 83/552 STR PAINT | 44586188 | STANISLAUS-NEWARK #1 (12KV) | 083/552 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-03 | 2021-07-03 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.73798 | 37.6571 | ETL.3850 | 41196042 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117561106 | Q2 | EI STANISLAUS-NEWARK #1 83/553 RPL HRDT | 43877551 | STANISLAUS-NEWARK #1 (12KV) | 083/553 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-03 | 2020-07-03 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.739502 | 37.6564 | ETL.3850 | 41196044 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117561109 | Not Scheduled | EI STANISLAUS-NEWARK #1 83/553 STR PAINT | 44586188 | STANISLAUS-NEWARK #1 (12KV) | 083/553 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-03 | 2021-07-03 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.739502 | 37.6564 | ETL.3850 | 41196044 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117561114 | Q2 | EI STANISLAUS-NWRK #1 83/553 INS ANTCLMB | 31493857 | STANISLAUS-NEWARK #1 (12KV) | 083/553 | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-03 | 2021-07-03 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.739502 | 37.6564 | ETL.3850 | 41196044 | GO95 / Anti Climb | Ground / Clearance | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117561183 | Feb | T2 MRR BY-SN LUIS OBSP #2 06/34 RPL HRDS |  | MORRO BAY-SAN LUIS OBISPO #2 | 006/034 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-03 | 2021-05-31 | 2021-02-16 | 2021-02-19 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.770526 | 35.327 | ETL.2820 | 40781930 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-10-02 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117562157 | Not Scheduled | T3NT EI GYSRS #16 TAP 000/003 PAINT STRT | 44310547 | GEYSERS #16 TAP | 000/003 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-03 | 2021-07-03 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.715252 | 38.7649 | ETL.4760 | 40659179 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117562799 | Not Scheduled | EI STNSLAUS-NEWRK #2 084/552 PAINT TOWER | 44586189 | STANISLAUS-NEWARK #2 (12KV) | 084/552 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-04 | 2021-07-04 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.741173 | 37.6554 | ETL.3860 | 41196041 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117562852 | Q2 | EI STANISLAUS-NEWARK #2 084/552 RPL HRDT |  | STANISLAUS-NEWARK #2 (12KV) | 084/552 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-04 | 2020-07-04 |  |  | 2021-06-19 | 2021-06-14 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.741173 | 37.6554 | ETL.3860 | 41196041 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117562857 | Not Scheduled | EI STANSLUS-NEWARK #1 83/554 PAINT TOWER | 44586188 | STANISLAUS-NEWARK #1 (12KV) | 083/554 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-04 | 2021-07-04 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.741256 | 37.6555 | ETL.3850 | 41196046 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117562862 | Q2 | EI STANISLUS-NEWARK #1 83/554 ANTI-CLIMB | 31493857 | STANISLAUS-NEWARK #1 (12KV) | 083/554 | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-04 | 2021-07-04 |  |  | 2021-06-05 | 2021-06-01 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.741256 | 37.6555 | ETL.3850 | 41196046 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-07-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117562865 | Q2 | EI STANISLAUS-NEWARK #1 83/554 RPL HRDT |  | STANISLAUS-NEWARK #1 (12KV) | 083/554 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-04 | 2020-07-04 |  |  | 2021-06-05 | 2021-06-01 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.741256 | 37.6555 | ETL.3850 | 41196046 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117562934 | Q2 | EI STANISLAUS-NEWARK #2 084/552 RPR STRT |  | STANISLAUS-NEWARK #2 (12KV) | 084/552 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-04 | 2020-07-04 |  |  | 2021-06-19 | 2021-06-14 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.741173 | 37.6554 | ETL.3860 | 41196041 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-24 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117562936 | Not Scheduled | NT EI STANISLAUS-NWK #2 85/554 PNT TWR | 44586189 | STANISLAUS-NEWARK #2 (12KV) | 085/554 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-04 | 2021-07-04 | [9 empty] | Central | WSIP | [6 empty] | '-121.746183 | 37.6529 | ETL.3860 | 41196045 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117562938 | Q2 | NT EI STANISLAUS-NWK #2 85/554 INST ACG |  | STANISLAUS-NEWARK #2 (12KV) | 085/554 | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-04 | 2021-07-04 |  |  | 2021-06-19 | 2021-06-14 | [5 empty] | Central | WSIP | [6 empty] | '-121.746183 | 37.6529 | ETL.3860 | 41196045 | Structure-Tower | Anti-Climbing Guard | Install |  |  |  |  | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117562951 | Q2 | EI STANISLAUS-NWK #2 85/554 RPL HRDT |  | STANISLAUS-NEWARK #2 (12KV) | 085/554 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-04 | 2020-07-04 |  |  | 2021-06-19 | 2021-06-14 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.746183 | 37.6529 | ETL.3860 | 41196045 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117562954 | Q2 | EI STANISLAUS-NEWARK #1 84/556 RPR FOND |  | STANISLAUS-NEWARK #1 (12KV) | 084/556 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-04 | 2020-07-04 |  |  | 2021-06-12 | 2021-06-07 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.746267 | 37.653 | ETL.3850 | 41195974 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117562956 | Q2 | EI STANISLAUS-NEWARK #1 84/556 CLMB GRD | 31493857 | STANISLAUS-NEWARK #1 (12KV) | 084/556 | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-04 | 2021-07-04 |  |  | 2021-06-05 | 2021-06-01 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.746267 | 37.653 | ETL.3850 | 41195974 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117563001 | Q2 | EI STANISLAUS-NEWARK #2 85/555 RPR STRT |  | STANISLAUS-NEWARK #2 (12KV) | 085/555 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-04 | 2020-07-04 |  |  | 2021-06-19 | 2021-06-14 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.748168 | 37.6519 | ETL.3860 | 41195973 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-24 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117563007 | Not Scheduled | EI STANISLAUS-NEWARK #2 85/556 RPR FOND |  | STANISLAUS-NEWARK #2 (12KV) | 085/556 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-07-04 | 2020-07-04 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.749562 | 37.6511 | ETL.3860 | 41195975 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117563032 | Q2 | EI STANISLAUS-NEWARK #1 84/558 CLMB GRD | 31493857 | STANISLAUS-NEWARK #1 (12KV) | 084/558 | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-04 | 2021-07-04 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.749736 | 37.6512 | ETL.3850 | 41195978 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117563784 | Feb | T2 TRINITY-MAPLE CREEK 15/2 RPL POLE | 31490924 | TRINITY-MAPLE CREEK | 015/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-07-03 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.177053 | 40.7465 | ETL.8170 | 40660828 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-11-14 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117563785 | Feb | T2 TRINITY-MAPLE CREEK 15/001 RPL POLE | 31490924 | TRINITY-MAPLE CREEK | 015/001 | 70Y | E | 2020_(2) High fire spread TD |  | 2019-07-03 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.176107 | 40.7469 | ETL.8170 | 40579624 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-11-14 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117563802 | Feb | T2 TRINITY-MAPLE CREEK 14/9 RPL POLE | 31490924 | TRINITY-MAPLE CREEK | 014/009 | 70Y | F | 2020_(2) High fire spread TD |  | 2019-07-03 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.172152 | 40.7486 | ETL.8170 | 40862185 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-11-14 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117564607 | Not Scheduled | EI JEFFERSON-HILLSDALE JCT 00/0 RPL POLE | 31456783 | JEFFERSON-HILLSDALE JCT | 000/000 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-05 | 2020-07-05 | 2020-07-13 | 2020-07-17 | [6 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.285275 | 37.4559 | ETL.7190 | 40594770 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 5 | SMCPD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  | Not Released | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117565276 | Mar | T2 HUMBOLDT-TRINITY 59/3 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 059/003 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-07-03 | 2024-07-03 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.160155 | 40.7536 | ETL.1820 | 44562699 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117565321 | Mar | T2 HUMBOLDT-TRINITY 91/0 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 091/000 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-05 | 2024-07-05 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.699446 | 40.746 | ETL.1820 | 44562981 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117565323 | Mar | T2 HUMBOLDT-TRINITY 091/003 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 091/003 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-05 | 2024-07-05 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.705149 | 40.7479 | ETL.1820 | 44565445 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117565324 | Mar | T2 HUMBOLDT-TRINITY 091/004 REPL ANCW | 31472098 | HUMBOLDT-TRINITY | 091/004 | 93E | E | Pre-2020_(2) High fire spread TD |  | 2019-07-05 | 2021-05-31 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.70711 | 40.7485 | ETL.1820 | 44560505 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117565332 | Mar | T2 HUMBOLDT-TRINITY 090/010 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 090/010 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-05 | 2024-07-05 |  |  | 2021-03-27 | 2021-03-01 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.697578 | 40.7453 | ETL.1820 | 44395233 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117566100 | Not Scheduled | EI MONTA VISTA-PERMANENTE 0/9 RPL CRSW | 31457590 | MONTA VISTA-PERMANENTE | 000/009 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-06 | 2020-07-06 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.086618 | 37.3148 | ETL.7620 | 40612246 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117567103 | Not Scheduled | T3 DI GRIZZLY TAP 0/10 RPR GYWW (L) |  | TAP (CITY OF SANTA CLARA) | 000/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-01 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.294599 | 39.8956 | ETL.2395 | 44550777 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117567104 | Not Scheduled | T3 DI GRIZZLY TAP 000/010 RPR GYWW (C) |  | TAP (CITY OF SANTA CLARA) | 000/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-01 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.294599 | 39.8956 | ETL.2395 | 44550761 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117567105 | Not Scheduled | T3 DI GRIZZLY TAP 000/010 RPR GYWW (R) |  | TAP (CITY OF SANTA CLARA) | 000/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-01 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.294599 | 39.8956 | ETL.2395 | 44550760 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117567137 | Not Scheduled | T2 DI SPA SUM 0/2 RPR GYWW | 43923459 | SPAULDING-SUMMIT | 000/002 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-01 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.644199 | 39.3246 | ETL.8060 | 40660099 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117567655 | Not Scheduled | T3 DI GRI TAO 0/11 RPR GYWW (L) |  | TAP (CITY OF SANTA CLARA) | 000/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-02 | 2020-01-02 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.279468 | 39.8976 | ETL.2395 | 44549959 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117567657 | Not Scheduled | T3 DI GRI TAO 0/11 RPR GYWW (C) |  | TAP (CITY OF SANTA CLARA) | 000/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-02 | 2020-01-02 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.279468 | 39.8976 | ETL.2395 | 44550035 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117567795 | Q3 | MONTA VISTA-LOS GATOS 010/201 TRM VEGN |  | MONTA VISTA-LOS GATOS | 010/201 | HNA | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2019-07-03 | 2020-07-03 |  |  | 2021-08-15 | 2021-08-01 |  |  |  |  | LATE | Central | Non-WSIP | [5 empty] | [REDACTED]- Need for Hwy 9 permit; inquiry w/ Cal Trans District 4 on 6/11/20; s4r5 - applying for Cal Trans District 4 scenic highway permit; eta 8/15/2020 | '-121.977472 | 37.2276 | ETL.7610 | 40694893 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117567955 | Not Scheduled | T2 DI COLGATE-PALERMO 009/167 RPL STRW | 31457073 | COLGATE-PALERMO | 009/167 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-03 | 2020-07-03 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.336983 | 39.3546 | ETL.6500 | 40598473 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117567968 | Not Scheduled | T2 EI SPAULDING-SUMMIT 014/464 REFRAME | 43923459 | SPAULDING-SUMMIT | 014/464 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-08 | 2021-05-31 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.403677 | 39.3286 | ETL.8060 | 40878098 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117567991 | Not Scheduled | T2 EI DRUM-SUMMIT #2 21/260 RPL POLE | 31471241 | DRUM-SUMMIT #2 | 021/260 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-08 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.4168094 | 39.3283 | ETL.1450 | 44558923 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117568219 | Feb | T2 DI RD MT CTNWD #3 R1/18 RPR STRW (R) | 43946912 | ROUND MTN-COTTONWOOD #3 | R001/018 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-03 | 2020-07-03 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.936725 | 40.7957 | ETL.5650 | 44737546 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117568370 | Feb | T2 DI RDMT CTNWD #3 R1/18 RPR STRW (L) | 43946912 | ROUND MTN-COTTONWOOD #3 | R001/018 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-03 | 2020-07-03 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.936725 | 40.7957 | ETL.5650 | 44737545 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117568461 | Not Scheduled | T2 EI SPAULDING-SUMMIT 014/459 RPR STRW | 43923459 | SPAULDING-SUMMIT | 014/459 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-08 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.407944 | 39.3284 | ETL.8060 | 40650061 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117568584 | Not Scheduled | T2 EI SPLDING-SMMIT 014/470 RPL STRW | 31495368 | SPAULDING-SUMMIT | 014/470 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-08 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.398613 | 39.3287 | ETL.8060 | 40751873 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117568758 | Not Scheduled | T2 DI DRUM-SUMMIT #2 021/253L RPL POLE | 31471241 | DRUM-SUMMIT #2 | 021/253 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-25 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.428125 | 39.3265 | ETL.1450 | 44557473 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117568759 | Q2 | T2 DI SNEATH LANE-PACIFICA 4/52 RPR GYWW | 43877619 | SNEATH LANE-PACIFICA | 004/052 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-08 | 2020-07-08 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.456143 | 37.6142 | ETL.7575 | 40864576 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117568793 | Not Scheduled | T2 DI DRUM-SUMMIT #2 021/253R RPL POLE | 31471241 | DRUM-SUMMIT #2 | 021/253 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-06-25 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.428125 | 39.3265 | ETL.1450 | 44557671 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117568853 | Q2 | DI NEWARK-VALLECITOS 94/616 BENT MBR | 43753293 | NEWARK-VALLECITOS | 094/616 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-08 | 2020-07-08 |  |  | 2021-04-02 | 2021-03-29 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.885566 | 37.5728 | ETL.7670 | 40825455 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117568856 | Q2 | DI NEWARK-VALLECITOS 94/616 GRDWASH INSS | 43753293 | NEWARK-VALLECITOS | 094/616 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-08 | 2020-07-08 |  |  | 2021-04-02 | 2021-03-29 |  |  | Likely MAT error - delink to correct |  | LATE | Central | WSIP | [6 empty] | '-121.885566 | 37.5728 | ETL.7670 | 40854583 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 622 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117568897 | Not Scheduled | T2 EI DRUM-SUMMIT #2 23/274R RPR GYWW | 43947611 | DRUM-SUMMIT #2 | 023/274 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-08 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.3939853 | 39.3291 | ETL.1450 | 44552299 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117569010 | Not Scheduled | T2 EI DRUM-SUMMIT #2 23/274C RPL STRW | 31497848 | DRUM-SUMMIT #2 | 023/274 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-08 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.3939853 | 39.3291 | ETL.1450 | 44552298 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117570049 | Not Scheduled | T2 DI CAR PAL :20/160 RPL HRDT | 44069454 | CARIBOU-PALERMO | :020/160 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-07-02 | 2020-07-02 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.353207 | 39.9056 | ETL.3190 | 40642284 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117570097 | Not Scheduled | T2NT DI CAR PAL 20/160 RPL INSS |  | CARIBOU-PALERMO | :020/160 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-02 | 2020-07-02 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.353207 | 39.9056 | ETL.3190 | 40642431 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117572217 | Q2 | T2 DI FT RSS GUA 49/9 BOND GYWW HRDD | 43920743 | GUALALA-MONTE RIO | 049/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-02 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.402144 | 38.722 | ETL.6980 | 40876078 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117572583 | Not Scheduled | T2NT EI SPALDNG-SMMT 015/492 REMV VEG |  | SPAULDING-SUMMIT | 015/492 | HNA | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-09 | 2021-07-09 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.381998 | 39.328 | ETL.8060 | 40771521 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2019-09-13 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117572628 | Not Scheduled | T2 DI CARIBOU-PALERMO :6/048 RPR FOND | 44059014 | CARIBOU-PALERMO | :006/048 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-07-08 | 2020-07-08 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.219155 | 40.0264 | ETL.3190 | 40910290 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117572775 | Not Scheduled | EI T2NT SPLDING-SUMMIT 15/479 RPR INSW | 43924041 | SPAULDING-SUMMIT | 015/479 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-09 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.392076 | 39.3289 | ETL.8060 | 40602263 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117572800 | Not Scheduled | T2NT EI DRUM-SUMMIT #1 21/252 INS STR ID | 43910103 | DRUM-SUMMIT #1 | 021/252 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-09 | 2021-07-09 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4264296 | 39.3159 | ETL.1440 | 44338240 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117572822 | Not Scheduled | EI NT NWARK - LIVERMORE 008/050 REPAINT | 43752137 | NEWARK-LIVERMORE | 008/050 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-09 | 2021-07-09 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.874509 | 37.5661 | ETL.7660 | 40613235 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117572996 | Not Scheduled | T2NT EI SPLDNG-SMMIT 015/493 INST MRKW | 43924041 | SPAULDING-SUMMIT | 015/493 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-09 | 2021-07-09 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.380982 | 39.3277 | ETL.8060 | 40770700 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117573568 | Not Scheduled | T2 SPAULDING-SUMMIT 015/487 RPL ANCW | 31463885 | SPAULDING-SUMMIT | 015/487 | 93E | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-09 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.386916 | 39.3286 | ETL.8060 | 44349562 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-08-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117573615 | Not Scheduled | EI NT NEWRK - LIVERMORE 005/037 REPAINT | 43752137 | NEWARK-LIVERMORE | 005/037 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-09 | 2021-07-09 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.901972 | 37.5353 | ETL.7660 | 40804508 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117573760 | Not Scheduled | MIDWAY-WHEELER RIDGE #1 19/89 INS SHIELD | 31462807 | MIDWAY-WHEELER RIDGE #1 | 019/089 | 70S | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-07-09 | 2021-07-09 | [9 empty] | South | Non-WSIP | [6 empty] | '-119.359772 | 35.1945 | ETL.5190 | 40860421 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 426 | Midway |  |  | DWR | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117573859 | Feb | T2 MORRO BAY-SLO#2 010/058 REPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 010/058 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-09 | 2021-05-31 | 2021-02-16 | 2021-02-19 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.705446 | 35.2872 | ETL.2820 | 40884352 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117574043 | Not Scheduled | EI NEWARK-LIVERMORE 005/039 CANCEL | 43752137 | NEWARK-LIVERMORE | 005/039 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-09 | 2021-07-09 | [6 empty] | CANCEL/CNCL |  |  | Central | Non-WSIP | [6 empty] | '-121.89639 | 37.5416 | ETL.7660 | 40857512 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117574069 | Q2 | DI STANISLAUS-NWK #2 85/554 RPR FOND |  | STANISLAUS-NEWARK #2 (12KV) | 085/554 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-03 | 2020-07-03 |  |  | 2021-06-19 | 2021-06-14 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.746183 | 37.6529 | ETL.3860 | 41196045 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117574143 | Feb | T2 MRR BY-SN LUS OBSP #2 10/57 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 010/057 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-09 | 2021-05-31 | 2021-02-16 | 2021-02-19 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.707306 | 35.2891 | ETL.2820 | 40835299 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117574220 | Q2 | DI STANISLAUS-NWK #2 85/554 BENT MBR |  | STANISLAUS-NEWARK #2 (12KV) | 085/554 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-03 | 2020-07-03 |  |  | 2021-06-19 | 2021-06-14 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.746183 | 37.6529 | ETL.3860 | 41196045 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117574409 | Feb | T2 MRR BY-SN LUS OBSP #2 10/55 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 010/055 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-09 | 2021-05-31 | 2021-02-16 | 2021-02-19 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.711131 | 35.2928 | ETL.2820 | 40778639 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117574441 | Not Scheduled | T2 EI DRUM-SUMMIT #2 26/311A REPL PL | 31521951 | DRUM-SUMMIT #2 | 026/311A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-09 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.355394 | 39.3095 | ETL.1450 | 40590181 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117574525 | Feb | T2 MORRO BAY-SLO#2 9/52 REPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 009/052 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-09 | 2021-05-31 | 2021-02-16 | 2021-02-19 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.717714 | 35.297 | ETL.2820 | 40713610 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117574546 | Not Scheduled | T2 EI DRUM-SUMMIT #2 26/311B REPL PL | 31521951 | DRUM-SUMMIT #2 | 026/311B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-09 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.355409 | 39.3095 | ETL.1450 | 42572851 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117574668 | Feb | T2 MRR BY-SN LUS OBSP #2 09/051 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 009/051 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-09 | 2021-05-31 | 2021-02-16 | 2021-02-19 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.720181 | 35.2982 | ETL.2820 | 40609263 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117574814 | Not Scheduled | T2 EI DRUM-SUMMIT #2 26/311C REPL PL | 31521951 | DRUM-SUMMIT #2 | 026/311C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-09 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.355434 | 39.3094 | ETL.1450 | 42572852 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117575033 | Feb | T2 MORRO BAY-SLO #2 8/43 REPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 008/043 | 93K | F | Pre-2020_(5) TD tag on other lines |  | 2019-07-09 | 2024-07-09 | 2021-02-16 | 2021-02-19 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.739234 | 35.3078 | ETL.2820 | 40676695 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117575107 | Before Feb | EI HELMS-GREGG #2 0/1B REPAINT TOWER | 44300721 | HELMS-GREGG #2 | 000/001B | ICX | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-09 | 2021-07-09 |  |  | 2020-04-30 | 2020-04-06 |  |  | Likely MAT error - delink to correct |  |  | South | Non-WSIP | [6 empty] | '-118.964024 | 37.0388 | ETL.4880 | 40740028 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Fresno |  | Y - 12 | Released | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2020-02-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117575225 | Not Scheduled | T2 SNETH LNE-HLF MN BY ?011/05 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/005 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-01 | 2021-07-01 | [7 empty] | TR2 |  | Central | Non-WSIP | [6 empty] | '-122.420738 | 37.4734 | ETL.7212 | 40875342 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117575226 | Not Scheduled | T2 SNEATH LANE-HLF MN BY ?11/4 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/004 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-01 | 2021-07-01 | [7 empty] | TR2 |  | Central | Non-WSIP | [6 empty] | '-122.420313 | 37.4744 | ETL.7212 | 40823350 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117575230 | Not Scheduled | SNEATH LANE-HALF MN BY ?11/14 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/014 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-06-26 | 2021-06-26 | [9 empty] | Central | Non-WSIP | [6 empty] | '-122.429996 | 37.4693 | ETL.7212 | 40823354 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117575231 | Not Scheduled | SNEATH LANE-HLF MN BY ?011/012 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/012 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-26 | 2021-06-26 | [9 empty] | Central | Non-WSIP | [6 empty] | '-122.429256 | 37.4703 | ETL.7212 | 40813440 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117575232 | Not Scheduled | SNEATH LANE-HALF MOON BAY ?11/11 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/011 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-26 | 2021-06-26 | [9 empty] | Central | Non-WSIP | [6 empty] | '-122.428389 | 37.4705 | ETL.7212 | 43250631 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117575236 | Not Scheduled | SNEATH LANE-HLF MN BY ?11/10 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/010 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-06-26 | 2021-06-26 | [9 empty] | Central | Non-WSIP | [6 empty] | '-122.427063 | 37.4709 | ETL.7212 | 40656255 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117575238 | Not Scheduled | T2 SNEATH LNE-HLF MN BY ?11/01 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/001 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-01 | 2021-07-01 | [7 empty] | TR2 |  | Central | Non-WSIP | [6 empty] | '-122.418584 | 37.4788 | ETL.7212 | 40768024 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117583170 | Not Scheduled | EI HELMS-GREGG #2 0/001B RPR CONS | 43825465 | HELMS-GREGG #2 | 000/001B | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-09 | 2020-07-09 | [8 empty] | LATE | South | WSIP | [6 empty] | '-118.964024 | 37.0388 | ETL.4880 | 40740028 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117583755 | Feb | T2 MRR BY-SN LUS OBSP #2 12/68 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 012/068 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-10 | 2021-05-31 | 2021-02-16 | 2021-02-19 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.684904 | 35.2676 | ETL.2820 | 40884355 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-09-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117583822 | Feb | T2 MORRO BAY-SLO #2 12/067 REPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 012/067 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-10 | 2021-05-31 | 2021-02-16 | 2021-02-19 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.68678 | 35.2693 | ETL.2820 | 40835303 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-09-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117583835 | Mar | T2 EI DRUM-SUMMIT #2 27/323 INS ANTCLMB | 31462463 | DRUM-SUMMIT #2 | 027/323 | 93A | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-10 | 2021-07-10 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.338006 | 39.3108 | ETL.1450 | 40671557 | Structure-Steel | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117583873 | Feb | T2 MRR BY-SN LUS OBSP #2 12/66 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 012/066 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-10 | 2021-05-31 | 2021-02-16 | 2021-02-19 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.68856 | 35.271 | ETL.2820 | 40838024 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-09-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117583893 | Q2 | T2 TRINITY-MAPLE CREEK 15/7 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 015/007 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-09 | 2024-07-09 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [8 empty] | ETL.8170 | 44370545 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117583921 | Not Scheduled | T2 MRR BY-SN LS OBSP #1 12/68 RPR ROAD | 44635170 | MORRO BAY-SAN LUIS OBISPO #1 | 012/068 | CHS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-10 | 2021-07-10 |  |  |  | 2021-05-15 |  |  |  | TR2 |  | South | Non-WSIP | [6 empty] | '-120.685057 | 35.2675 | ETL.2810 | 40861171 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117583936 | Not Scheduled | T3 SNEATH LANE-HALF MN BY ?10/2 CLR ROAD |  | SNEATH LANE-HALF MOON BAY | ?010/002 | CHS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Veg/Land/Road) | 2019-07-03 | 2021-07-03 |  |  |  | 2020-08-12 |  |  |  | TR3 |  | Central | Non-WSIP | [6 empty] | '-122.424481 | 37.4906 | ETL.7212 | 40695077 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117583963 | Q2 | T2 TRINITY-MAPLE CREEK 17/014 RMV BUTTS | 43749708 | TRINITY-MAPLE CREEK | 017/014 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-07-06 | 2025-07-06 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.223948 | 40.7396 | ETL.8170 | 40744513 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117584020 | Mar | T2NT EI DRM-SUMMIT #2 27/322 INS ANTCLMB | 31462463 | DRUM-SUMMIT #2 | 027/322 | 93A | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-10 | 2021-07-10 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.338353 | 39.3107 | ETL.1450 | 40590184 | Structure-Steel | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117584038 | Feb | T2 TRINITY-MAPLE CREEK 18/3 RPL POLE | 31472080 | TRINITY-MAPLE CREEK | 018/003B | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-07-06 | 2021-05-31 |  |  | 2021-02-20 | 2021-02-19 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.230054 | 40.7365 | ETL.8170 | 40650354 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-11-14 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117584327 | Feb | T2 TRINITY-MAPLE CREEK 018/004 RPL POLE | 31472080 | TRINITY-MAPLE CREEK | 018/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-07-06 | 2021-05-31 |  |  | 2021-02-20 | 2021-02-19 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.230526 | 40.7365 | ETL.8170 | 40744515 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-11-14 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117585155 | Feb | T2 TRINITY-MAPLE CREEK 018/5 RPL POLE | 31472080 | TRINITY-MAPLE CREEK | 018/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-07-06 | 2021-05-31 |  |  | 2021-02-20 | 2021-02-19 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.23111 | 40.7365 | ETL.8170 | 40761915 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-11-14 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117585230 | Not Scheduled | T2 HUMBOLDT-TRINITY 062/004 CANCEL |  | HUMBOLDT-TRINITY | 062/004 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-07-06 | 2020-07-06 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.212105 | 40.7436 | ETL.1820 | 44562275 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-30 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117585419 | Q2 | T2 DI HATCRK#1-WSTWD 026/500 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 026/500 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-09 | 2020-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.198738 | 40.6751 | ETL.7030 | 40676346 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117585592 | Feb | T2 MRR BY-SN LUS OBSP #2 15/85 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 015/085 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-10 | 2021-05-31 | 2021-02-16 | 2021-02-19 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.647688 | 35.2542 | ETL.2820 | 40778645 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117585702 | Q2 | EI HUMBOLDT-BRIDGEVILLE 108/1 LFT RPL PL | 31496089 | HUMBOLDT-BRIDGEVILLE | 108/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-10 | 2020-07-10 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.9737185 | 40.7487 | ETL.1810 | 44322586 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117585913 | Not Scheduled | T3 DI CARIBOU-PALERMO :007/056 BENT MEMB | 44057199 | CARIBOU-PALERMO | :007/056 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-07-09 | 2020-01-09 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | Circuit Based Scheduling | '-121.226084 | 40.0084 | ETL.3190 | 40910298 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117586096 | Mar | EI PARADISE-BUTTE 009/093L RPR GYWS | 43881381 | PARADISE-BUTTE | 009/093 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-10 | 2020-07-10 |  |  | 2021-03-19 | 2021-03-09 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.731853 | 39.7086 | ETL.4396 | 44382923 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117586107 | Not Scheduled | DI MTN GATE JCT-CSCD 004/038R CANCEL | 43758388 | MTN GATE JCT-CASCADE | 004/038 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-10 | 2021-05-31 | [6 empty] | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.325896 | 40.6902 | ETL.7640 | 44565420 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117586601 | Feb | T2 MRR BY-SN LUS OBSP #2 07/41 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 007/041 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-10 | 2021-05-31 | 2021-02-16 | 2021-02-19 | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.746952 | 35.3117 | ETL.2820 | 40611537 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117586693 | Q2 | T2 TRINITY-MAPLE CREEK 44/007 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 044/007 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-05 | 2024-07-05 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.703384 | 40.7471 | ETL.8170 | 40808963 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117586730 | Q2 | T2 TRINITY-MAPLE CREEK 044/008 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 044/008 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-05 | 2024-07-05 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.704593 | 40.7475 | ETL.8170 | 40877937 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117586870 | Not Scheduled | T3 DI CARIBOU PALERMO :10/83 RPR FOND | 44057199 | CARIBOU-PALERMO | :010/083 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-07-09 | 2020-01-09 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | Circuit Based Scheduling | '-121.272689 | 39.9931 | ETL.3190 | 40910324 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117588202 | Q2 | T2 DI FRT RSS-GLLA 55/2 RPR GYWW | 43920743 | GUALALA-MONTE RIO | 055/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-03 | 2021-05-31 | 2020-09-16 | 2020-09-19 | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.492903 | 38.7416 | ETL.6980 | 40656424 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117588209 | Not Scheduled | T2 DI FORT ROSS-GUALALA 056/002 CANCEL | 43920743 | GUALALA-MONTE RIO | 056/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-02 | 2020-07-02 | 2020-09-16 | 2020-09-19 |  |  |  |  | CANCEL/CNCL | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.507076 | 38.7502 | ETL.6980 | 40686563 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117588670 | Feb | T2 DI CASCD-BNTN-DSCHTS 004/104 RPR GYWW | 43690811 | CASCADE-BENTON-DESCHUTES | 004/104 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-09 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.311551 | 40.5888 | ETL.6310 | 40759287 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117588672 | Not Scheduled | T2 DI MALIN-ROUND MTN#2 62/310 CANCEL | 44110674 | MALIN-ROUND MTN #2 | 062/310 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.672844 | 41.1834 | ETL.6020 | 40608604 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117588726 | Not Scheduled | T2 EI SPAULDING-SUMMIT 015/497 RMV VEGN | 43924041 | SPAULDING-SUMMIT | 015/497 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-11 | 2020-07-11 | [6 empty] | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.379673 | 39.3248 | ETL.8060 | 40876711 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117588842 | Not Scheduled | T3 DI CARIBOU-PALERMO :009/075 RPR STUBS | 44057199 | CARIBOU-PALERMO | :009/075 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-07-08 | 2020-01-08 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | Priority Bucket 9 | '-121.26518 | 40.0035 | ETL.3190 | 40910317 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117588843 | Not Scheduled | DI COTTONWOOD-DELEVAN#2 72/623 PNT STRS | 44305184 | COTTONWOOD-DELEVAN #2 | 072/623 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-03 | 2021-07-03 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.267023 | 40.2184 | ETL.4580 | 40660417 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117588848 | Q2 | DI CASCADE-BNTN-DSCHTS A007/156 RPR STRW | 43690811 | CASCADE-BENTON-DESCHUTES | A007/156 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-02 | 2020-07-02 |  |  | 2021-04-30 | 2021-04-12 |  |  |  |  | LATE | North Valley | WSIP | [8 empty] | ETL.6310 | 44416908 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117588953 | Not Scheduled | T3 DI CARIBOU PALERMO :10/79 UNBURY MEMB | 44070463 | CARIBOU-PALERMO | :010/079 | ICS | E | Pre-2020_(3) On high spread structure |  | 2019-07-08 | 2020-01-08 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.268442 | 39.9988 | ETL.3190 | 40910320 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117589019 | Not Scheduled | EI NT CSTR VLLY - NWRK 014/073 RPR FOND |  | CASTRO VALLEY-NEWARK | 014/073 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-07-11 | 2021-07-11 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.874511 | 37.5654 | ETL.4450 | 40675940 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-15 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117589525 | Mar | T2 HUMBOLDT-TRINITY 092/000C RPL STRW | 31471992 | HUMBOLDT-TRINITY | 092/000 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-07-08 | 2021-05-31 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.716509 | 40.7504 | ETL.1820 | 44560655 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117589528 | Mar | T2 HUMBOLDT-TRINITY 092/00R RPL STRW | 31471992 | HUMBOLDT-TRINITY | 092/000 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-07-08 | 2021-05-31 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.716509 | 40.7504 | ETL.1820 | 44560462 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117589529 | Mar | T2 HUMBOLDT-TRINITY 92/00L RPL STRW | 31471992 | HUMBOLDT-TRINITY | 092/000 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-07-08 | 2020-07-08 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.716509 | 40.7504 | ETL.1820 | 44560498 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117590020 | Not Scheduled | T2 EI SPALDING-SUMMIT 016/525 RPL STRW | 31495368 | SPAULDING-SUMMIT | 016/525 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-11 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.37069 | 39.3104 | ETL.8060 | 40593593 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-04 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117590346 | Q3 | T2 DI MNTA VSTA-LOS GTOS 8/169 REMV VEG |  | MONTA VISTA-LOS GATOS | 008/169 | HNA | F | Pre-2020_(9a) Other ignition related |  | 2019-07-09 | 2021-07-09 |  |  | 2021-08-15 | 2021-08-01 |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.003495 | 37.2417 | ETL.7610 | 40824938 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117591093 | Mar | DI POE-RIO OSO 029/195 INST MRKS | 43875009 | POE-RIO OSO | 029/195 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-09 | 2021-07-09 |  |  | 2021-03-26 | 2021-03-22 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.532712 | 39.5674 | ETL.5540 | 40757649 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117591143 | Q2 | T2 DI HT CREEK#1-WESTWOOD 0/6 RPR GYWW | 43939287 | HAT CREEK #1-WESTWOOD | 000/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-11 | 2020-07-11 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.541173 | 40.9279 | ETL.7030 | 44190884 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117591695 | Mar | T2 HUMBOLDT-TRINITY 091/004 RMV DEBRIS | 44298757 | HUMBOLDT-TRINITY | 091/004 | ICW | F | Pre-2020_(3) On high spread structure |  | 2019-07-05 | 2022-07-05 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.707111 | 40.7485 | ETL.1820 | 44560531 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117591701 | Not Scheduled | T2 SNEATH LANE-HLF MN BY ?11/06 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/006 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-07-01 | 2021-07-01 | [7 empty] | TR2 |  | Central | Non-WSIP | [6 empty] | '-122.421761 | 37.4729 | ETL.7212 | 40867272 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117591703 | Mar | T2 HUMBOLDT-TRINITY 090/009 RMV DBRS | 44311171 | HUMBOLDT-TRINITY | 090/009 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-05 | 2024-07-05 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.696271 | 40.7444 | ETL.1820 | 44562641 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117591706 | Mar | T2 HUMBOLDT-TRINITY 066/000 RMV BUTTS | 44311174 | HUMBOLDT-TRINITY | 066/000 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-06 | 2024-07-06 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.263163 | 40.7249 | ETL.1820 | 44562918 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117591708 | Mar | T2 HUMBOLDT-TRINITY 066/000 RMV VEGN |  | HUMBOLDT-TRINITY | 066/000 | HNA | F | Pre-2020_(9a) Other ignition related | Budget Owner (Veg/Land/Road) | 2019-07-06 | 2024-07-06 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.263163 | 40.7249 | ETL.1820 | 44562918 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | HNA | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117591830 | Mar | T2 HUMBOLDT-TRINITY 066/001X RMV BUTT | 44311174 | HUMBOLDT-TRINITY | 066/001X | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-06 | 2024-07-06 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.269842 | 40.7206 | ETL.1820 | 44557449 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117591831 | Mar | T2 HUMBOLDT-TRINTY 066/01 RMV POLE BUTTS | 44298750 | HUMBOLDT-TRINITY | 066/001 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-06 | 2022-07-06 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.268289 | 40.7213 | ETL.1820 | 44562899 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117591985 | Q2 | T2 DI HUMBOLT-BRIDGEVILE 112/4L RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 112/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-11 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322682 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-27 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117592028 | Mar | T2 HUMBOLDT-TRINITY 064/001 RMV BUTT | 44311174 | HUMBOLDT-TRINITY | 064/001 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-07-06 | 2025-07-06 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.237982 | 40.7371 | ETL.1820 | 44560554 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117592101 | Mar | T2 HUMBOLDT-TRINITY 065/001 RMV BUTT | 44311174 | HUMBOLDT-TRINITY | 065/001 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-07-06 | 2025-07-06 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.254854 | 40.7316 | ETL.1820 | 44562900 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117592122 | Mar | HUMBOLDT-TRINITY 65/004 RMV POLE BUTTS | 44311174 | HUMBOLDT-TRINITY | 065/004 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-07-06 | 2025-07-06 |  |  | 2021-03-27 | 2021-03-01 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.261915 | 40.726 | ETL.1820 | 44557501 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117592192 | Mar | HUMBOLDT-TRINITY 063/003 RMV PL BUTTS | 44298746 | HUMBOLDT-TRINITY | 063/003 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-06 | 2025-07-06 |  |  | 2021-03-27 | 2021-03-01 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.220224 | 40.7425 | ETL.1820 | 44562915 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117592194 | Mar | T2 HUMBOLDT-TRINITY 061/004 RMV BUTTS | 44311171 | HUMBOLDT-TRINITY | 061/004 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-09 | 2022-07-09 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.190398 | 40.7403 | ETL.1820 | 44560670 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117592196 | Q2 | T2 DI HMBOLDT-BRIDGEVILLE 110/1 RPR DAMW | 43749687 | HUMBOLDT-BRIDGEVILLE | 110/001 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-07-11 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322629 | Damper-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117592200 | Mar | HUMBOLDT-TRINITY 064/000 RPL POLE | 31494734 | HUMBOLDT-TRINITY | 064/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-07-06 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.230802 | 40.7363 | ETL.1820 | 44562406 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2019-10-04 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-10-04 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117592211 | Not Scheduled | HUMBOLDT-TRINITY 063/003 CLR ROAD | 43878519 | HUMBOLDT-TRINITY | 063/003 | CHS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-06 | 2021-07-06 |  |  |  | 2021-06-06 | [5 empty] | North Coast | Non-WSIP | [6 empty] | '-123.220224 | 40.7425 | ETL.1820 | 44562915 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117592964 | Not Scheduled | T3 EI GRIZZLY TAP 000/001 RPL STRW (C) | 31495730 | TAP (CITY OF SANTA CLARA) | 000/001 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-11 | 2020-01-11 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.279937 | 39.8898 | ETL.2395 | 44550027 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117594223 | Q2 | T2 DI HAT CRK#1-WESTWD 034/664 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 034/664 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-10 | 2020-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.088658 | 40.5849 | ETL.7030 | 40701239 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117594541 | Q2 | T2 DI HAT CREEK#1-WESTWD 28/555 RPR STRW | 43939292 | HAT CREEK #1-WESTWOOD | 028/555 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-10 | 2020-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.163668 | 40.6452 | ETL.7030 | 40816147 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-07 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117594545 | Not Scheduled | T3 DI CARIBOU-PALERMO :10/78 BURIED STUB | 44057199 | CARIBOU-PALERMO | :010/078 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-07-08 | 2020-01-08 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | Circuit Based Scheduling | '-121.267244 | 40.0011 | ETL.3190 | 40907020 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117594762 | Q2 | T2 DI HAT CREEK#1-WSTWD 040/777 RPR STRW | 44388736 | HAT CREEK #1-WESTWOOD | 040/777 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-09 | 2020-07-09 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.031802 | 40.5117 | ETL.7030 | 40586012 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117594765 | Q2 | T2 DI HAT CRK#1-WSTWD 027/535 RPLC HRDD | 43939292 | HAT CREEK #1-WESTWOOD | 027/535 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-10 | 2020-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.17898 | 40.6548 | ETL.7030 | 40827594 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117594909 | Mar | T2 DI HUMBOLT-TRINITY 110/2 RPL STRW (L) | 31476190 | HUMBOLDT-TRINITY | 110/002 | 70Y | B | Pre-2020_(0) A and B Tags |  | 2019-07-11 | 2021-03-21 |  |  | 2021-03-21 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-124.051873 | 40.7615 | ETL.1820 | 44562299 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 117595142 | Not Scheduled | EI LAS POSITAS - NEWARK 002/020 RPR STRT |  | LAS POSITAS-NEWARK | 002/020 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-07-12 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.732669 | 37.66 | ETL.4980 | 40870181 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-04-14 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117595251 | Mar | T2 DI HUMBOLT-TRINITY 110/2 RPL STRW (C) | 31476190 | HUMBOLDT-TRINITY | 110/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-11 | 2021-05-21 |  |  | 2021-03-21 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-124.051873 | 40.7615 | ETL.1820 | 44562261 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117595253 | Mar | T2 DI HUMBOLT-TRINITY 110/2 RPL STRW (R) | 31476190 | HUMBOLDT-TRINITY | 110/002 | 70Y | B | Pre-2020_(0) A and B Tags |  | 2019-07-11 | 2021-03-21 |  |  | 2021-03-21 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-124.051873 | 40.7615 | ETL.1820 | 44562178 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 117595407 | Not Scheduled | EI LAS POSITAS - NEWARK 002/021 RPR FOND |  | LAS POSITAS-NEWARK | 002/021 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-07-12 | 2020-07-12 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.73264 | 37.6581 | ETL.4980 | 40590641 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-04-14 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117595427 | Not Scheduled | EI LAS POSITAS-NEWARK 002/021 RPR STRT |  | LAS POSITAS-NEWARK | 002/021 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-07-12 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.73264 | 37.6581 | ETL.4980 | 40590641 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-04-14 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117596032 | Q2 | T2 EI BRIDGVILL-CTTNWD 32/265R RPL PL | 31444708 | BRIDGEVILLE-COTTONWOOD | 032/265 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2018-12-20 | 2019-12-20 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-122.880879 | 40.365 | ETL.1110 | 44423883 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117596447 | Q2 | T2 DI HUMBLT-BRGEVLLE 110/0 RPR GYWW (L) | 43749687 | HUMBOLDT-BRIDGEVILLE | 110/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-10 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322626 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-27 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117596492 | Q2 | T2 DI HUMBLT-BRGEVLLE 110/0 RPR GYWW (R) | 43749687 | HUMBOLDT-BRIDGEVILLE | 110/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-10 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322627 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-27 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117596560 | Not Scheduled | T2 DI COLGATE-CHALLENGE 0/17 RPL STRW | 31462967 | COLGATE-CHALLENGE | 000/017 | 70Y | E | 2020_(1a) PSPS |  | 2019-07-11 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.191419 | 39.3408 | ETL.6480 | 40824180 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-07-27 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 117596883 | Q2 | T2 DI HT CRK #1-WESTWD 023/451 RPR STRT | 43736797 | HAT CREEK #1-WESTWOOD | 023/451 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-10 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.230127 | 40.7039 | ETL.7030 | 40616904 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-08-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117597101 | Q3 | T2 DI HMLTN-BRNCH-CHSTR 009/195 RPR STRW | 43908598 | HAMILTON BRANCH-CHESTER | 009/195 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-10 | 2020-07-10 |  |  | 2021-08-31 | 2021-08-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.181558 | 40.3125 | ETL.7000 | 40758795 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-07-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117597140 | Q2 | T2NT DI MLN-RND MTN # 2 72/366 INST GMKS | 44305271 | MALIN-ROUND MTN #2 | 072/366 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-10 | 2021-07-10 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.80575 | 41.073 | ETL.6020 | 40811608 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117597770 | Not Scheduled | T2NT EI SPLDNG-SMMT 019/603 INST GMKW | 43924041 | SPAULDING-SUMMIT | 019/603 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-13 | 2021-07-13 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.332025 | 39.3118 | ETL.8060 | 40771558 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117597895 | Not Scheduled | EI NT MORRO BAY - MESA 000/005 STRT PNT | 44300723 | MORRO BAY-MESA | 000/005 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-13 | 2021-07-13 | [9 empty] | South | Non-WSIP | [6 empty] | '-120.839561 | 35.3735 | ETL.5290 | 40753053 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117598005 | Not Scheduled | EI NT PALERMO - NICOLS 000/007 STRT PNT | 44586168 | PALERMO-NICOLAUS | 000/007 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-13 | 2021-07-13 | [9 empty] | North Valley | Non-WSIP | [6 empty] | '-121.533677 | 39.4594 | ETL.3210 | 40818313 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117598486 | Q2 | T2 TRINITY-MAPLE CREEK 010/017 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 010/017 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-14 | 2024-07-14 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.108183 | 40.7689 | ETL.8170 | 44420595 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117598487 | Q2 | T2 TRINITY-MAPLE CREEK 11/0 RMV DEBRIS | 43749708 | TRINITY-MAPLE CREEK | 011/000 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-14 | 2024-07-14 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.111874 | 40.768 | ETL.8170 | 40906413 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117599008 | Q2 | T2 DI PLRMO-ORV#2 A7/090 BOND GYWW HRDD | 43724470 | PALERMO-OROVILLE #2 | A007/090 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-10 | 2020-07-10 |  |  | 2021-04-01 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.498408 | 39.5273 | ETL.7740 | 40766680 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117599085 | Not Scheduled | T2NT DI CNTR CST-MRG #1 009/046 REPAINT | 44587769 | CONTRA COSTA-MORAGA #1 | 009/046 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-11 | 2021-07-11 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-121.903407 | 37.9579 | ETL.5452 | 40857837 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117599502 | Not Scheduled | DI DELTA-MTN GATE JCT 004/081 REPAINT | 43708883 | DELTA-MOUNTAIN GATE JCT | 004/081 | ICS | F | Pre-2020_(5) TD tag on other lines |  | 2019-07-10 | 2021-07-10 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.370515 | 40.888 | ETL.6750 | 40602175 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-01-27 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117599539 | Q3 | T2 DI MNT VISTA-LOS GATOS 9/184 RMV VEG |  | MONTA VISTA-LOS GATOS | 009/184 | HNA | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2019-07-10 | 2020-07-10 |  |  | 2021-08-15 | 2021-08-01 |  |  |  | TR2 | LATE | Central | WSIP | [5 empty] | [REDACTED] - applying for Cal Trans District 4 scenic highway permmit; eta 8/15/2020 | '-121.990117 | 37.2348 | ETL.7610 | 40665276 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  | Not Released | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117599836 | Feb | T2 TRINITY-MAPLE CREEK -012/004 RPL STRW | 31471998 | TRINITY-MAPLE CREEK | 012/004 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-07-13 | 2021-05-31 | 2020-12-13 | 2020-12-15 | 2021-02-27 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Weather | AT RISK - weather impacts | '-123.138954 | 40.7656 | ETL.8170 | 40744498 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2020-09-04 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117599945 | Not Scheduled | T3 EI GRIZZLY TAP 002/001L RPR ANCW |  | TAP (CITY OF SANTA CLARA) | 002/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-15 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.302584 | 39.8958 | ETL.2395 | 44550829 | Anchor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117599956 | Not Scheduled | T2 DI SPAULDING-SUMMIT 13/449 REFRAME PL | 43924041 | SPAULDING-SUMMIT | 013/449 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-10 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.414746 | 39.3282 | ETL.8060 | 42571856 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117599961 | Not Scheduled | T2 DI DRUM-SUMMIT #1 021/252 INST MRKS | 43910101 | DRUM-SUMMIT #1 | 021/252 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-09 | 2021-07-09 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.426416 | 39.3159 | ETL.1440 | 44338241 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117599977 | Not Scheduled | EI NT POE-RIO OSO 032/215 STRT PAINT | 43875009 | POE-RIO OSO | 032/215 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-15 | 2021-07-15 | [9 empty] | North Valley | Non-WSIP | [6 empty] | '-121.536562 | 39.5259 | ETL.5540 | 40757659 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117600082 | Mar | EI POE-RIO OSO 032/215 RPR CONS | 43875009 | POE-RIO OSO | 032/215 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-15 | 2020-07-15 |  |  | 2021-03-26 | 2021-03-22 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.536562 | 39.5259 | ETL.5540 | 40757659 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117600136 | Not Scheduled | T3NT EI GRIZZLY TAP 002/007L INST MRKW |  | TAP (CITY OF SANTA CLARA) | 002/007 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-07-02 | 2025-07-02 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.312669 | 39.8973 | ETL.2395 | 44550815 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117600137 | Not Scheduled | T3NT EI GRIZZLY TAP 002/007C INST MRKW |  | TAP (CITY OF SANTA CLARA) | 002/007 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-07-02 | 2025-07-02 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.312669 | 39.8973 | ETL.2395 | 44550837 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117600549 | Q3 | NT EI TESLA-NEWARK #1 011/062 INST ACG | 31451420 | TESLA-NEWARK #1 | 011/062 | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-15 | 2021-07-15 |  |  | 2021-07-17 | 2021-07-12 | [5 empty] | Central | WSIP | [6 empty] | '-121.746129 | 37.6497 | ETL.5720 | 40661746 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117600608 | Mar | EI POE-RIO OSO 32/217 RPR COND | 43875009 | POE-RIO OSO | 032/217 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-15 | 2020-07-15 |  |  | 2021-03-26 | 2021-03-22 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.536853 | 39.5214 | ETL.5540 | 40814851 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117600645 | Not Scheduled | T2 DI MALIN-RND MTN#2 063/317 CANCEL | 44305271 | MALIN-ROUND MTN #2 | 063/317 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-11 | 2023-07-11 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.686599 | 41.1664 | ETL.6020 | 40820723 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117600822 | Not Scheduled | T2 DI MALIN-ROUND MTN 63/308 CANCEL | 44305271 | MALIN-ROUND MTN #2 | 061/308 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-11 | 2021-07-11 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.669095 | 41.188 | ETL.6020 | 40862525 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117601367 | Not Scheduled | T2NT DI MAL-RND MTN #2 61/307 CANCEL | 43621093 | MALIN-ROUND MTN #2 | 061/307 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-11 | 2021-07-11 | [6 empty] | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.66772 | 41.1897 | ETL.6020 | 40816579 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117601381 | Feb | T3 DI DESABLA-CENTERVLL 004/047 RPR GYWW | 43913825 | DESABLA-CENTERVILLE | 004/047 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-07-10 | 2021-05-31 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.646249 | 39.8082 | ETL.6720 | 40770242 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117601455 | Mar | T2NT DI HUMBO-TRINI 61/5 INST MRKS (R) | 43729518 | HUMBOLDT-TRINITY | 061/005 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-01-17 | 2021-01-17 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [8 empty] | ETL.1820 | 44324178 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2019-08-30 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117601587 | Not Scheduled | T2 DI MALIN-ROUND MTN 62/309 STRT PAINT | 44305271 | MALIN-ROUND MTN #2 | 062/309 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-11 | 2021-07-11 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.671008 | 41.1857 | ETL.6020 | 40868281 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117601963 | Not Scheduled | NT EI POE-RIO OSO 33/220 PNT TWR | 43875009 | POE-RIO OSO | 033/220 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-15 | 2021-07-15 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.536481 | 39.5156 | ETL.5540 | 40605303 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117603718 | Q2 | T2 DI HAT CREK #1-WESTWD 1/24 RPL POLE | 31504344 | HAT CREEK #1-WESTWOOD | 001/024 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-12 | 2020-07-12 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.523727 | 40.925 | ETL.7030 | 40668055 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-09-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117604003 | Mar | DI HUMBOLDT-TRINITY 80/0 RMV VEG |  | HUMBOLDT-TRINITY | 080/000 | HNA | F | Pre-2020_(9a) Other ignition related | Budget Owner (Veg/Land/Road) | 2019-07-12 | 2024-07-12 |  |  | 2021-03-27 | 2021-03-01 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.513173 | 40.7039 | ETL.1820 | 44565615 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | HNA | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117604015 | Mar | HUMBOLDT-TRINITY 057/007 RMV POLE BUTTS | 43729541 | HUMBOLDT-TRINITY | 057/007 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-13 | 2020-07-13 |  |  | 2021-03-27 | 2021-03-01 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.135296 | 40.7676 | ETL.1820 | 44560664 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-10-04 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117604123 | Not Scheduled | T2 DI PIT#1-COTTONWOOD 8/73A RPR STRT | 43900587 | PIT #1-COTTONWOOD | 008/073A | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-12 | 2020-07-12 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.638364 | 40.9163 | ETL.5390 | 40576864 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117604167 | Not Scheduled | T2 DI SPAULDING-SUMMIT 1/77 INST MRKW | 43924041 | SPAULDING-SUMMIT | 001/077 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-15 | 2021-07-15 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.614465 | 39.3108 | ETL.8060 | 40810155 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117604453 | Q3 | EI TESLA-NEWARK #2 12/83 RPR FOND |  | TESLA-NEWARK #2 | 012/083 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-16 | 2020-07-16 |  |  | 2021-07-23 | 2021-07-19 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.766193 | 37.6394 | ETL.5354 | 41152628 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117604703 | Not Scheduled | EI NT CLNG #1-SN MGL 014/000 STRT PAINT | 44301011 | COALINGA #1-SAN MIGUEL | 014/000 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-16 | 2021-07-16 | [9 empty] | South | WSIP | [6 empty] | '-120.511294 | 36.0246 | ETL.8580 | 40609549 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117604903 | Not Scheduled | T2 DI SPAULDING-SUMMIT 1/76 INS MRKW | 43924041 | SPAULDING-SUMMIT | 001/076 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-07-15 | 2021-07-15 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.614798 | 39.3108 | ETL.8060 | 40770649 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117604959 | Q2 | T2 DI HUMBOLDT-BRIDGE 111/5L RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 111/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-15 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322669 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-27 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-08-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117605313 | Q2 | T2 TRINITY-MAPLE CREEK 002/000 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 002/000 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-16 | 2022-07-16 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.965366 | 40.7319 | ETL.8170 | 40906262 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117605324 | Q2 | T2 TRINITY-MAPLE CREEK 001/018 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 001/018 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-16 | 2022-07-16 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.964397 | 40.7316 | ETL.8170 | 40906261 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117605404 | Not Scheduled | T2 DI BRIGHTON-CLAYTON#2 51/384 HANGER | 43918839 | BRIGHTON-CLAYTON #2 IDLE | 051/384 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-12 | 2021-05-31 | [5 empty] | TLN/TLQ error | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-121.903186 | 37.9837 | ETL.1130 | 40782188 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117605831 | Not Scheduled | T3 EI GRIZZLY TAP 1/11R RMV VEGN |  | TAP (CITY OF SANTA CLARA) | 001/011 | HNA | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-07-12 | 2020-01-12 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.295465 | 39.8954 | ETL.2395 | 44550727 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117605880 | Not Scheduled | EI NT COLNG #1-SN MIGL 014/001 STR PNT | 44301011 | COALINGA #1-SAN MIGUEL | 014/001 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-16 | 2021-07-16 | [9 empty] | South | WSIP | [6 empty] | '-120.51189 | 36.0228 | ETL.8580 | 40588488 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117606027 | Not Scheduled | EI T2 CLNG #1-SN MGL 014/002 STRT PNT | 44301011 | COALINGA #1-SAN MIGUEL | 014/002 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-16 | 2021-07-16 | [7 empty] | TR2 |  | South | Non-WSIP | [6 empty] | '-120.51245 | 36.0223 | ETL.8580 | 40691147 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117606138 | Not Scheduled | EI T2NT CLNGA #1-SN MGL 015/00 STRT PNT | 44301011 | COALINGA #1-SAN MIGUEL | 015/001 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-16 | 2021-07-16 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.53244 | 36.0109 | ETL.8580 | 40588490 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117606569 | Not Scheduled | EI NT COLINGA #1-SN MGL 015/002 STRT PNT | 44301011 | COALINGA #1-SAN MIGUEL | 015/002 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-16 | 2021-07-16 | [9 empty] | South | Non-WSIP | [6 empty] | '-120.53354 | 36.0104 | ETL.8580 | 40666972 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 15 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117607999 | Q3 | EI TESLA-NEWARK #2 13/088 RPR FOND |  | TESLA-NEWARK #2 | 013/088 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-07-17 | 2021-07-17 |  |  | 2021-07-23 | 2021-07-19 |  |  |  |  | SCHD | Central | Non-WSIP | [6 empty] | '-121.781421 | 37.6312 | ETL.5354 | 41152633 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-10-01 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117608281 | Not Scheduled | T2 DI WEIMAR-HALSEY 5/126 RPL POLE | 31509756 | WEIMAR-HALSEY | 005/126 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-16 | 2020-07-16 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.037119 | 38.963 | ETL.8340 | 40766755 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117609004 | Not Scheduled | EI CARIBOU-PALERMO 001/013 RPR JUMS | 44304488 | CARIBOU-PALERMO | 001/013 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-17 | 2020-07-17 | [8 empty] | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.540308 | 39.4674 | ETL.3190 | 40656294 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117609122 | Not Scheduled | EI NT CLNGA #1-SAN MIGL 015/004 STRT PNT | 44301011 | COALINGA #1-SAN MIGUEL | 015/004 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-16 | 2021-07-16 | [9 empty] | South | WSIP | [6 empty] | '-120.53669 | 36.009 | ETL.8580 | 40754875 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 15 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117609460 | Q3 | EI TESLA-NEWARK #1 12/68 INSTL ACG | 31477901 | TESLA-NEWARK #1 | 012/068 | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-17 | 2021-07-17 |  |  | 2021-07-17 | 2021-07-12 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.76556 | 37.6393 | ETL.5720 | 40862796 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117610631 | Not Scheduled | EI CARIBOU-PALERMO 001/014 BURIED MEMB | 44069801 | CARIBOU-PALERMO | 001/014 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-17 | 2020-07-17 | [8 empty] | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.539763 | 39.4683 | ETL.3190 | 40762749 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117610647 | Not Scheduled | EI CARIBOU-PALERMO 001/014 INST ACG | 31460573 | CARIBOU-PALERMO | 001/014 | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-17 | 2021-07-17 | [9 empty] | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.539763 | 39.4683 | ETL.3190 | 40762749 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117610650 | Not Scheduled | EI CARIBOU-PALERMO 001/014 REPAINT | 44302345 | CARIBOU-PALERMO | 001/014 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-17 | 2021-07-17 | [9 empty] | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.539763 | 39.4683 | ETL.3190 | 40762749 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117610694 | Not Scheduled | EI CARIBOU-PALERMO 001/014 RPL JUMS | 44304488 | CARIBOU-PALERMO | 001/014 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-17 | 2020-07-17 | [8 empty] | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.539763 | 39.4683 | ETL.3190 | 40762749 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117610971 | Q2 | T2 DI BRDGVILLE-COTTNWOD 11/102 RPR PL | 43939216 | BRIDGEVILLE-COTTONWOOD | 011/102 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-22 | 2020-05-22 |  |  | 2021-04-30 | 2021-03-29 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.475337 | 40.389 | ETL.1110 | 44423204 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117611221 | Q3 | EI TESLA-NEWARK #2 13/89 RPR FOND |  | TESLA-NEWARK #2 | 013/089 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-17 | 2020-07-17 |  |  | 2021-07-23 | 2021-07-19 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.783442 | 37.6301 | ETL.5354 | 41152634 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-10-01 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117611367 | Not Scheduled | EI CARIBOU-PALERMO 1/015 INS HRDT | 44069801 | CARIBOU-PALERMO | 001/015 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-07-17 | 2020-07-17 | [8 empty] | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.539783 | 39.4704 | ETL.3190 | 40755505 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117612125 | Q3 | EI TESLA-NEWARK #2 13/090 INSTL ACG | 31477903 | TESLA-NEWARK #2 | 013/090 | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-17 | 2021-07-17 |  |  | 2021-07-23 | 2021-07-19 |  |  |  |  | SCHD | Central | Non-WSIP | [6 empty] | '-121.785374 | 37.6291 | ETL.5354 | 41152635 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2019-10-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117612154 | Q3 | EI TESLA-NEWARK #2 13/090 RPR FOND |  | TESLA-NEWARK #2 | 013/090 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-07-17 | 2021-07-17 |  |  | 2021-07-23 | 2021-07-19 |  |  |  |  | SCHD | Central | Non-WSIP | [6 empty] | '-121.785374 | 37.6291 | ETL.5354 | 41152635 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-10-01 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117613502 | Q2 | T2 CASCADE-BENTN-DSCHTS A9/185 REPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A009/185 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-17 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-122.242295 | 40.5557 | ETL.6310 | 40586277 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117613524 | Not Scheduled | EI CONTRA CST-LS POSITAS 7/48 PNT STRT | 44587767 | CONTRA COSTA-LAS POSITAS | 007/048 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-07-18 | 2021-07-18 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.746603 | 37.9135 | ETL.4510 | 40810026 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117613782 | Mar | T2 VOLTA-SOUTH 003/074 RPL POLE | 31470529 | VOLTA-SOUTH | 003/074 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-18 | 2020-07-18 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.871677 | 40.4168 | ETL.8300 | 40586400 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-06-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117613825 | Q3 | CARIBOU-PLUMAS JCT 015/010 REPL POLE | 31455444 | CARIBOU-PLUMAS JCT | 015/010 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2020-06-17 |  |  | 2021-08-20 | 2021-08-02 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-120.931812 | 39.956 | ETL.6290 | 40599541 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117613863 | Not Scheduled | EI CARIBOU-PALERMO 008/068 REPAINT | 44302345 | CARIBOU-PALERMO | 008/068 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2021-07-18 | [9 empty] | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.53181 | 39.568 | ETL.3190 | 40865370 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117613868 | Not Scheduled | T2 CENTERVILLE-TABLE MTN 6/93 RPR POLE | 43939208 | CENTERVILLE-TABLE MTN | 006/093 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-06-18 | 2020-06-18 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.70821 | 39.7125 | ETL.6320 | 40675330 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117614221 | Mar | T2 TRINITY-MAPLE CREEK 2/11 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 002/011 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2020-07-18 |  |  | 2021-03-24 | 2021-03-24 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.974642 | 40.7347 | ETL.8170 | 40906273 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-10-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117614466 | Not Scheduled | T2 DI CRTNA-MNOCNO #1 36/171 INST HRDT | 44306522 | CORTINA-MENDOCINO #1 | 036/171 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-07-17 | 2020-07-17 | [6 empty] | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.799896 | 39.1069 | ETL.1330 | 40584925 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117614558 | Mar | T2 TRINITY-MAPLE CREEK 003/003 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/003 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2024-07-18 |  |  | 2021-03-23 | 2021-03-23 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.985621 | 40.7319 | ETL.8170 | 40906283 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117614562 | Not Scheduled | T2NT DI WEIMAR-HALSEY 2/60 RMV STRW | 43938294 | WEIMAR-HALSEY | 002/060 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-17 | 2021-07-17 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.004307 | 38.9991 | ETL.8340 | 40758131 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117614652 | Q2 | T3 EI CRESTA-RIO OSO 15/127 RPL INSS | 31435732 | CRESTA-RIO OSO | 015/127 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-18 | 2020-01-18 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.47636 | 39.7473 | ETL.4590 | 40910145 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117614843 | Feb | T2 TRINITY-MAPLE CREEK 003/006 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/006 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2024-07-18 | 2021-02-22 | 2021-02-27 | 2021-02-26 | 2021-02-26 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.988451 | 40.7317 | ETL.8170 | 40906286 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117614844 | Mar | T2 TRINITY-MAPLE CREEK 3/8 RMV POLE BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/008 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2024-07-18 |  |  | 2021-03-25 | 2021-03-25 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.989807 | 40.7311 | ETL.8170 | 40906288 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117614871 | Q2 | T2 TRINITY-MAPLE CREEK 003/009 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/009 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2024-07-18 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.990322 | 40.7309 | ETL.8170 | 40906289 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117614980 | Q2 | T2 TRINITY-MAPLE CREEK 003/012 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/012 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2024-07-18 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.993108 | 40.7303 | ETL.8170 | 40906291 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117615012 | Q2 | T2 TRINITY-MAPLE CREEK 3/14 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/014 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2022-07-18 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.994751 | 40.7307 | ETL.8170 | 40906293 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117615015 | Q2 | T2 TRINITY-MAPLE CREEK 003/015 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/015 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2024-07-18 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.995333 | 40.7309 | ETL.8170 | 40906294 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117615168 | Q2 | T2 TRINITY-MAPLE CREEK 3/10 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/010 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2024-07-18 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.991412 | 40.7304 | ETL.8170 | 40906290 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117615246 | Not Scheduled | T2 EI CNTR CST-LS PSTS 10/70 PNT STRT | 43899985 | CONTRA COSTA-LAS POSITAS | 010/070 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2021-07-18 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-121.726121 | 37.8514 | ETL.4510 | 40857287 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117615735 | Mar | T2 TRINITY-MAPLE CREEK 3/0 RMV POLE BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/000 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2024-07-18 |  |  | 2021-03-23 | 2021-03-23 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.983195 | 40.733 | ETL.8170 | 40906280 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117616066 | Q2 | T2 TRINITY-MAPLE CREEK 4/4A RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 004/004A | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2024-07-18 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.008531 | 40.7348 | ETL.8170 | 40906305 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117616432 | Q2 | T2 TRINITY-MAPLE CREEK 4/1 RMV POLE BUTT | 43749708 | TRINITY-MAPLE CREEK | 004/001 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2024-07-18 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.004666 | 40.7336 | ETL.8170 | 40906301 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117616511 | Q2 | T2 TRINITY-MAPLE CREEK 004/002 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 004/002 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2024-07-18 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.005132 | 40.7337 | ETL.8170 | 40906302 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117617232 | Not Scheduled | T2 EI CNTR CSTA-LS PSTS 10/72 INST HRDT |  | CONTRA COSTA-LAS POSITAS | 010/072 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2020-07-18 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.727463 | 37.8418 | ETL.4510 | 40593917 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-28 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117617288 | Q2 | T3 EI CRESTA-RIO OSO 15/127 RPR CONS | 43947257 | CRESTA-RIO OSO | 015/127 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-18 | 2020-01-18 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.47636 | 39.7473 | ETL.4590 | 40910145 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117617666 | Not Scheduled | EI CARIBOU-PALERMO 4/39 INS ANTCLMB | 31460573 | CARIBOU-PALERMO | 004/039 | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-18 | 2021-07-18 | [9 empty] | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.54005 | 39.5163 | ETL.3190 | 40867350 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117617693 | Not Scheduled | EI CARIBOU-PALERMO 4/39 PAINT STRT | 44302345 | CARIBOU-PALERMO | 004/039 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-18 | 2021-07-18 | [6 empty] | Check FDA |  |  | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.54005 | 39.5163 | ETL.3190 | 40867350 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117617696 | Not Scheduled | CARIBOU-PALERMO 4/039 RMV WOOD PLANKS | 44070463 | CARIBOU-PALERMO | 004/039 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-18 | 2020-07-18 | [8 empty] | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.54005 | 39.5163 | ETL.3190 | 40867350 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117617697 | Not Scheduled | EI CARIBOU-PALERMO 4/39 RPL SPLICES | 44304488 | CARIBOU-PALERMO | 004/039 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-18 | 2020-07-18 | [8 empty] | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.54005 | 39.5163 | ETL.3190 | 40867350 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117617788 | Not Scheduled | EI CARIBOU-PALERMO 4/39 RPR HRDT | 44069801 | CARIBOU-PALERMO | 004/039 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-18 | 2020-07-18 | [8 empty] | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.54005 | 39.5163 | ETL.3190 | 40867350 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117619175 | Not Scheduled | NT EI BELL-PLACER 1/16 PNT TWR | 44303813 | BELL-PLACER | 001/016 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-19 | 2021-07-19 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.05913 | 38.9368 | ETL.4395 | 40577450 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117619628 | Not Scheduled | T2 EI CNTR CST-LS PSTS 10/71 PNT STRT | 43899985 | CONTRA COSTA-LAS POSITAS | 010/071 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-19 | 2021-07-19 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-121.727017 | 37.845 | ETL.4510 | 40590628 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | LVW | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117619882 | Not Scheduled | EI TESLA-SALADO #1 59/259 INST HRDT | 44460801 | TESLA-SALADO #1 | 059/259 | ICQ | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-07-19 | 2020-07-19 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.192974 | 37.4463 | ETL.3990 | 41136336 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117620259 | Q2 | T2 TRINITY-MAPLE CREEK 1/14 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 001/014 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-19 | 2024-07-19 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.961111 | 40.7304 | ETL.8170 | 44356510 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117620302 | Q2 | T2 TRINITY-MAPLE CREEK 001/015 RMV DBRIS | 43749708 | TRINITY-MAPLE CREEK | 001/015 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-19 | 2024-07-19 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.961474 | 40.7307 | ETL.8170 | 40906258 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117620470 | Not Scheduled | T2 EI CNTR CST-LS POSITAS 10/73 PNT STRT | 44587767 | CONTRA COSTA-LAS POSITAS | 010/073 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-19 | 2021-07-19 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-121.723992 | 37.8393 | ETL.4510 | 40911563 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117620779 | Q2 | T2 TRINITY-MAPLE CREEK 004/010 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 004/010 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-19 | 2022-07-19 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.013497 | 40.7347 | ETL.8170 | 40906311 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117620803 | Q2 | T2 TRINITY-MAPLE CREEK 4/5 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 004/005 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-19 | 2024-07-19 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.009752 | 40.7352 | ETL.8170 | 40906306 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117620979 | Q2 | T2 TRINITY-MAPLE CREEK 004/015 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 004/015 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-19 | 2024-07-19 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.018614 | 40.7341 | ETL.8170 | 44420579 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117621989 | Feb | EI MORAGA-OAKLAND #3 005/037 RPR HRDT | 44293744 | MORAGA-OAKLAND #3 | 005/037 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-20 | 2020-07-20 |  |  | 2021-02-27 | 2021-02-22 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.226863 | 37.8069 | ETL.2740 | 40804643 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117622980 | Not Scheduled | EI MORAGA-OAKLAND #3 005/038 RPR FOND |  | MORAGA-OAKLAND #3 | 005/038 |  | E | Pre-2020_(9a) Other ignition related |  | 2019-07-20 | 2020-07-20 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-122.229105 | 37.8058 | ETL.2740 | 40857643 | Structure-Tower | Soil | Remove |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade |  | Not Scheduled |  |  | 2019-11-04 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117622981 | Not Scheduled | EI MORAGA-OAKLAND #3 005/038 INST HRDT |  | MORAGA-OAKLAND #3 | 005/038 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-07-20 | 2020-07-20 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-122.229105 | 37.8058 | ETL.2740 | 40857643 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-04 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117623854 | Not Scheduled | T2NT EI CNTR CST-LS PSTS 11/80 PNT TWR | 43899985 | CONTRA COSTA-LAS POSITAS | 011/080 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-07-20 | 2021-07-20 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-121.713182 | 37.8196 | ETL.4510 | 40911564 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117623912 | Not Scheduled | T2NT EI CNTR CST-LS PSTS 12/83 PNT TWR | 43899985 | CONTRA COSTA-LAS POSITAS | 012/083 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-20 | 2021-07-20 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-121.70943 | 37.8092 | ETL.4510 | 40681623 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117625163 | Feb | T2 TRINITY-MAPLE CREEK 004/014 RPL POLE | 31471998 | TRINITY-MAPLE CREEK | 004/014 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-19 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.017932 | 40.7342 | ETL.8170 | 40906315 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-10-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-10-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117625194 | Mar | T2 TRINITY-MAPLE CREEK 3/5 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/005 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2024-07-18 |  |  | 2021-03-25 | 2021-03-25 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.987254 | 40.7318 | ETL.8170 | 40906285 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117625230 | Q2 | T2 TRINITY-MAPLE CREEK 3/20 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/020 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-18 | 2024-07-18 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [8 empty] | ETL.8170 | 44420575 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117626523 | Q2 | T2 EI SBRT-GRZZY-CLRMNT #1 6/54 RPR FOND | 43752388 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 006/054 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-19 | 2020-07-19 |  |  | 2021-05-31 | 2021-05-24 |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.228018 | 37.8479 | ETL.3740 | 40580980 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117626759 | Not Scheduled | NT EI CASTRO VALLEY-NEWARK 2/16 PNT TWR | 44585912 | CASTRO VALLEY-NEWARK | 002/016 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-22 | 2021-07-22 | [9 empty] | Central | WSIP | [6 empty] | '-122.036043 | 37.6797 | ETL.4450 | 40866263 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117627229 | Not Scheduled | T2 DI WEIMAR-HALSEY 1/39 RPL STRW | 31454601 | WEIMAR-HALSEY | 001/039 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-17 | 2020-07-17 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.997127 | 39.009 | ETL.8340 | 40873791 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117627429 | Q2 | T2 DI SBRT-GRZY-CLMNT #1 A0/2 WASH INSS | 43752388 | SOBRNTE-GRIZZLY-CLARMNT #1+ | A000/002 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-19 | 2020-07-19 |  |  | 2021-05-31 | 2021-05-24 |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.212805 | 37.9041 | ETL.3740 | 40577689 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 626 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117627507 | Feb | EI MORAGA-OAKLAND #1 5/36 RPR FOND | 44392608 | MORAGA-OAKLAND #1 | 005/036 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-22 | 2020-07-22 |  |  | 2021-02-27 | 2021-02-22 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.229135 | 37.8059 | ETL.2720 | 40804646 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-09-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117627603 | Feb | EI MORAGA-OAKLAND #1 5/36 RPR STRT | 44392608 | MORAGA-OAKLAND #1 | 005/036 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-22 | 2020-07-22 |  |  | 2021-02-27 | 2021-02-22 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.229135 | 37.8059 | ETL.2720 | 40804646 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-09-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117627609 | Feb | EI MORAGA-OAKLAND #1 5/36 RPL HRDT | 44392608 | MORAGA-OAKLAND #1 | 005/036 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-22 | 2020-07-22 |  |  | 2021-02-27 | 2021-02-22 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.229135 | 37.8059 | ETL.2720 | 40804646 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-09-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117628165 | Not Scheduled | DI NT MORAGA-OAKLAND #3 5/39 RPR FOND |  | MORAGA-OAKLAND #3 | 005/039 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-07-22 | 2020-07-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-122.230287 | 37.8058 | ETL.2740 | 41196337 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-04 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117629694 | Not Scheduled | DI MORAGA-OAKLAND #1 4/34 RMV DEBRIS | 44598133 | MORAGA-OAKLAND #1 | 004/034 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-07-22 | 2020-07-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-122.224179 | 37.8094 | ETL.2720 | 40745869 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117629859 | Not Scheduled | EI MORAGA-OAKLAND #1 4/34 RPR FOND |  | MORAGA-OAKLAND #1 | 004/034 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-07-22 | 2020-07-22 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-122.224179 | 37.8094 | ETL.2720 | 40745869 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-07-29 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117629900 | Mar | EI MORAGA-OAKLAND #2 4/33 RPR CONS | 43909784 | MORAGA-OAKLAND #2 | 004/033 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-22 | 2020-07-22 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.221382 | 37.8113 | ETL.2730 | 44668643 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi | 2019-07-31 | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-07-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117631802 | Not Scheduled | T2 EI CHOWCHILLA-KERCKHOFF 2/1 RMV BUTTS | 43912702 | CHOWCHILLA-KERCKHOFF | 002/001 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-06-19 | 2024-06-19 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.586009 | 37.0905 | ETL.1250 | 44191704 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 21 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117632537 | Mar | T2 SOBRANTE-GRZLY-CLRMNT#2 A0/1 RPR CONS | 43914263 | SOBRANTE-GRIZLY-CLARMNT #2+ | A000/001 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-23 | 2021-05-31 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.210483 | 37.9054 | ETL.3750 | 44359726 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-07-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117633025 | Q2 | DI HUMBOLDT-BRIDGEVILLE 114/5 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 114/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-23 | 2021-05-31 | 2021-05-03 | 2021-05-22 | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322747 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-07-29 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117634305 | Not Scheduled | T3 DI GRIZZLY TAP (SVP) 4/2 RPR STRT | 43930737 | GRIZZLY TAP (SVP) | 004/002 | ICQ | E | Pre-2020_(2) High fire spread TD |  | 2019-07-23 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | 2021 | '-121.327512 | 39.9113 | ETL.1231 | 44188701 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117635491 | Mar | T2 SOBRNT-GRZZLY-CLRMNT#1 02/23 RPL INSS | 31484739 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 002/023 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-24 | 2020-07-24 | 2021-03-17 | 2021-03-17 | 2021-03-17 | 2021-03-17 |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-122.186646 | 37.8798 | ETL.3740 | 40898589 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117635619 | Mar | T2 SOBRANTE-GRZLY-CLRMNT#1 2/24 REPL INS | 31484739 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 002/024 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-24 | 2020-07-24 | 2021-03-17 | 2021-03-17 | 2021-03-17 | 2021-03-17 |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-122.185476 | 37.8783 | ETL.3740 | 40884326 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 13 | CalTrans | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117636475 | Q2 | DI HUMBOLDT-BRIDGEVILLE 114/5 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 114/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-24 | 2021-05-31 | 2021-05-03 | 2021-05-22 | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322749 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-27 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117636478 | Q2 | DI HUMBOLDT-BRIDGEVILLE 114/5 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 114/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-24 | 2021-05-31 | 2021-05-03 | 2021-05-22 | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322748 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-27 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117636501 | Q2 | DI HUMBOLDT-BRIDGEVILLE 114/5 RPL INSW | 31472113 | HUMBOLDT-BRIDGEVILLE | 114/005 | 93I | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-24 | 2021-05-31 | 2021-05-03 |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322749 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-08-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117639163 | Not Scheduled | T2 DI PIT #1-COTTONWOOD 038/328 RPR FOND | 43637398 | PIT #1-COTTONWOOD | 038/328 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-24 | 2020-07-24 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.044765 | 40.6643 | ETL.5390 | 40871584 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117639169 | Not Scheduled | T2 DI PIT #3-PIT #1 001/012 REPL SPLS | 43877630 | PIT #3-PIT #1 | 001/012 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-24 | 2020-07-24 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.515038 | 40.9767 | ETL.5400 | 40668278 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117639528 | Not Scheduled | T2 DI FULTON-HOPLAND 017/002 RPL STRW | 31478308 | FULTON-HOPLAND | 017/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-24 | 2020-07-24 | 2020-08-17 | 2020-08-23 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.865708 | 38.7062 | ETL.6890 | 40692939 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-08-15 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-08-15 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117640648 | Mar | T2 DI EL DRDO-MSSR FLT#2 12/112 RPL INSS | 31462723 | ELDORADO-MISSOURI FLAT #2 | 012/112 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-25 | 2020-07-25 |  |  | 2021-03-29 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.804806 | 38.7147 | ETL.1540 | 40724797 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117640834 | Q2 | T2 DI TULE-SPRINGVILLE 14/1 RPR GYWW | 44323713 | TULE-SPRINGVILLE | 014/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-25 | 2020-07-25 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.899227 | 36.1099 | ETL.9040 | 40584057 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-12-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117645216 | Feb | DI RND MTN-COTTONWOOD #3 35/302 RPR SPLS | 43755803 | ROUND MTN-COTTONWOOD #3 | 035/302 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-26 | 2020-07-26 |  |  | 2021-02-19 | 2021-02-15 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.019568 | 40.6948 | ETL.5650 | 40675852 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117646483 | Not Scheduled | DI TESLA-LOS BNS #1 28/126 INST ZENA | 43939159 | TESLA-LOS BANOS #1 | 028/126 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-07-26 | 2024-07-26 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-121.192398 | 37.4432 | ETL.6100 | 40811974 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117646634 | Not Scheduled | DI TESLA-LOS BANOS #1 28/126 WASH INSS | 44598406 | TESLA-LOS BANOS #1 | 028/126 | ICI | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-26 | 2020-07-26 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.192398 | 37.4432 | ETL.6100 | 40839391 | Insulator | Contaminated | Helicopter Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 626 | Victor |  | None |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117647940 | Q2 | T2 TRINITY-MAPLE CREEK 47/12 RMV PL BUTT | 43683558 | TRINITY-MAPLE CREEK | 047/012 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-06 | 2023-07-06 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.758649 | 40.7506 | ETL.8170 | 40701836 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117648492 | Q2 | T2 TRINITY-MAPLE CREEK 42/0 RMV PL BUTT | 43683558 | TRINITY-MAPLE CREEK | 042/000 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-07 | 2024-07-07 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.663121 | 40.7284 | ETL.8170 | 40617900 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-11-14 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-11-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117649423 | Q2 | T2 TRINITY-MAPLE CRK 41/11A RMV PL BUTT | 43683558 | TRINITY-MAPLE CREEK | 041/011A | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-07 | 2024-07-07 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.660398 | 40.7278 | ETL.8170 | 44948556 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-11-14 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-11-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117649880 | Not Scheduled | T2 DI GRIZZLY TAP 2/4L RPR PL |  | TAP (CITY OF SANTA CLARA) | 002/004 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-26 | 2020-07-26 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.308071 | 39.8967 | ETL.2395 | 44550057 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117654249 | Not Scheduled | T2 DRUM-SUMMIT #2 24/296B REPL POLE | 31521951 | DRUM-SUMMIT #2 | 024/296B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-27 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.377716 | 39.3155 | ETL.1450 | 42572847 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117654284 | Not Scheduled | T2 DRUM-SUMMIT #2 25/302A REPL POLE | 31521951 | DRUM-SUMMIT #2 | 025/302A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-27 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.370508 | 39.3106 | ETL.1450 | 40756991 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117654296 | Not Scheduled | T2 DRUM-SUMMIT #2 24/296C REPL POLE | 31521951 | DRUM-SUMMIT #2 | 024/296C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-27 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.377675 | 39.3155 | ETL.1450 | 42572848 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117654297 | Not Scheduled | T2 DRUM-SUMMIT #2 25/302B REPL POLE | 31521951 | DRUM-SUMMIT #2 | 025/302B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-27 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.370536 | 39.3106 | ETL.1450 | 42572849 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117654301 | Not Scheduled | T2 DRUM-SUMMIT #2 24/296A REPL POLE | 31521951 | DRUM-SUMMIT #2 | 024/296A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-27 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.377795 | 39.3154 | ETL.1450 | 40594971 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117654302 | Not Scheduled | T2 DRUM-SUMMIT #2 25/302C REPL POLE | 31521951 | DRUM-SUMMIT #2 | 025/302C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-27 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.370575 | 39.3105 | ETL.1450 | 42572850 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117654685 | Not Scheduled | T2 SPAULDING-SUMMIT 12/429 REPL POLE | 31453471 | SPAULDING-SUMMIT | 012/429 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-28 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.430958 | 39.3253 | ETL.8060 | 40586101 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-03-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117654686 | Not Scheduled | T2 SPAULDING-SUMMIT 15/481 REFRAME | 31463885 | SPAULDING-SUMMIT | 015/481 | 93E | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-28 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.390725 | 39.329 | ETL.8060 | 40650064 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-08-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117655702 | Mar | DI TABLE MTN-PALERMO 5/27 INST MRKS | 44154424 | TABLE MTN-PALERMO | 005/027 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-07-26 | 2021-07-26 |  |  | 2021-03-17 | 2021-03-17 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.543912 | 39.5456 | ETL.5690 | 40814381 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-08-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117657953 | Not Scheduled | DRUM-SUMMIT #2 15/176L REPL POLE | 31521945 | DRUM-SUMMIT #2 | 015/176 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-27 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | [6 empty] | '-120.537147 | 39.3098 | ETL.1450 | 44559040 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117657954 | Not Scheduled | DRUM-SUMMIT #2 17/204 REPL POLE | 31521949 | DRUM-SUMMIT #2 | 017/204 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-27 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | [6 empty] | '-120.498895 | 39.3143 | ETL.1450 | 44557615 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117658094 | Not Scheduled | DRUM-SUMMIT #2 14/164R REPL POLE | 31521945 | DRUM-SUMMIT #2 | 014/164 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-27 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | [6 empty] | '-120.550965 | 39.318 | ETL.1450 | 44561431 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117658230 | Not Scheduled | DRUM-SUMMIT #2 13/155L REPL POLE | 31498154 | DRUM-SUMMIT #2 | 013/155 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-27 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | [6 empty] | '-120.563451 | 39.3252 | ETL.1450 | 44561321 | Structure-Wood | Rotten | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-05-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117665794 | Q2 | T3 DRUM-HIGGINS 0/3 RPR CONW | 43918680 | DRUM-HIGGINS | 000/003 | ICW | E | Pre-2020_(2) High fire spread TD |  | 2019-07-15 | 2021-05-31 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Denied by GCC | 2021 - Clearance denied due to work on the Drum powerhouse. | '-120.766933 | 39.2541 | ETL.4393 | 44552302 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117665982 | Not Scheduled | T3NT EI MORAGA-OAKLAND#3 0/8 PAINT STRS | 43725286 | MORAGA-OAKLAND #3 | 000/008 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-07-29 | 2021-07-29 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.176756 | 37.8441 | ETL.2740 | 40872587 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117666210 | Mar | T3 DI MRAGA-OKLND#2 000/002 RPL INSS | 31461003 | MORAGA-OAKLAND #2 | 000/002 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-26 | 2020-01-26 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.166133 | 37.8478 | ETL.2730 | 40728506 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117666219 | Mar | T3 DI MORAGA-OAKLAND #4 001/009 RPL INSS | 31461002 | MORAGA-OAKLAND #4 | 001/009 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-29 | 2021-05-31 | 2021-03-28 | 2021-03-30 | 2021-03-30 | 2021-03-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.177789 | 37.8431 | ETL.2750 | 40878740 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2019-09-17 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117666328 | Mar | T3 SOBRANTE-GRZLY-CLRMNT#2 A1/9 RPR JUMS | 44221597 | SOBRANTE-GRIZLY-CLARMNT #2+ | A001/009 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-30 | 2021-05-31 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 |  |  |  | TR3 | LATE | Central | Non-WSIP | [6 empty] | '-122.224573 | 37.8895 | ETL.3750 | 40878965 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-09-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117667063 | Not Scheduled | T2 DI TESLA-METCALF 011/045 INST HRDT |  | TESLA-METCALF | 011/045 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-07-29 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.605177 | 37.551 | ETL.6110 | 40764502 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117667313 | Q4 | T2 SNEATH LANE-HALF MN BY ;0/8 RMV VEGN |  | SNEATH LANE-HALF MOON BAY | ;000/008 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-07-30 | 2021-05-31 |  |  | 2021-11-30 | 2021-10-31 |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.455446 | 37.6145 | ETL.7212 | 40875330 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117667376 | Q4 | T2 SNEATH LANE-HLF MN BY ;1/13 RMV VEGN |  | SNEATH LANE-HALF MOON BAY | ;001/013 | HNA | E | Pre-2020_(3) On high spread structure |  | 2019-07-30 | 2020-07-30 |  |  | 2021-11-30 | 2021-10-31 |  |  |  | TR2 | LATE | Central | Non-WSIP |  |  |  |  | Access Issues | 2021 - Access issues | '-122.456784 | 37.6077 | ETL.7212 | 40695033 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117667383 | Q4 | T2 SNEATH LANE-HALF MN BY ;1/14 RMV VEGN |  | SNEATH LANE-HALF MOON BAY | ;001/014 | HNA | E | Pre-2020_(3) On high spread structure |  | 2019-07-30 | 2020-07-30 |  |  | 2021-11-30 | 2021-10-31 |  |  |  | TR2 | LATE | Central | Non-WSIP |  |  |  |  | Access Issues | 2021 - Access issues | '-122.457322 | 37.6069 | ETL.7212 | 40665322 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117668498 | Mar | T3 EI MORAGA-OAKLAND #4 1/10 RPL INSS | 31461002 | MORAGA-OAKLAND #4 | 001/010 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-30 | 2020-01-30 | 2021-03-28 | 2021-03-30 | 2021-03-30 | 2021-03-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.181803 | 37.8409 | ETL.2750 | 40621986 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-09-17 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117668751 | Feb | T3 EI MORAGA-OAKLAND #3 2/20 RPR STRT | 44293744 | MORAGA-OAKLAND #3 | 002/020 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-30 | 2020-01-30 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.201996 | 37.8297 | ETL.2740 | 40581560 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-08-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117669359 | Q2 | T2 TRINITY-MAPLE CREEK 49/6 RMV PL BUTT | 44167431 | TRINITY-MAPLE CREEK | 049/006 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-07-05 | 2021-05-31 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.78975 | 40.7572 | ETL.8170 | 40809442 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117671064 | Mar | T3 EI MORAGA-OAKLAND#3 2/24 RPL INSS | 31461014 | MORAGA-OAKLAND #3 | 002/024 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-30 | 2020-01-30 | 2021-03-28 | 2021-03-30 | 2021-03-30 | 2021-03-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.203794 | 37.823 | ETL.2740 | 40775600 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117671140 | Mar | T3 DI MORAGA-OAKLAND#4 2/24 RPL INSS | 31461002 | MORAGA-OAKLAND #4 | 002/024 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-30 | 2020-01-30 | 2021-03-28 | 2021-03-30 | 2021-03-30 | 2021-03-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.203794 | 37.823 | ETL.2750 | 40775602 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-09-17 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117671391 | Q2 | T2 DI TULE-SPRINGVILLE 23/17 RPR STRW | 44323716 | TULE-SPRINGVILLE | 023/017 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-30 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.754825 | 36.1479 | ETL.9040 | 40821821 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-12-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117671611 | Q2 | T2 TRINITY-MAPLE CREEK 5/5 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 005/005 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-31 | 2024-07-31 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.030801 | 40.7332 | ETL.8170 | 40906322 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117671814 | Not Scheduled | DRUM-SUMMIT#2 13/155R RPL POLE | 31498154 | DRUM-SUMMIT #2 | 013/155 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-30 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.563451 | 39.3252 | ETL.1450 | 44561486 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  | Yes |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-05-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117671816 | Not Scheduled | DRUM-SUMMIT#2 15/176 RPL POLE | 31521945 | DRUM-SUMMIT #2 | 015/176 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-30 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.537147 | 39.3098 | ETL.1450 | 44558996 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117672055 | Not Scheduled | DRUM-SUMMIT#2 13/155C RPL POLE | 31498154 | DRUM-SUMMIT #2 | 013/155 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-30 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.563451 | 39.3252 | ETL.1450 | 44561342 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  | Yes |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-05-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117672056 | Not Scheduled | DRUM-SUMMIT#2 14/164 RPL POLE | 31521945 | DRUM-SUMMIT #2 | 014/164 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-30 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.550965 | 39.318 | ETL.1450 | 44561377 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117672440 | Not Scheduled | DRUM-SUMMIT#2 15/176 RPL POLE | 31521945 | DRUM-SUMMIT #2 | 015/176 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-30 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.537147 | 39.3098 | ETL.1450 | 44558938 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117672474 | Mar | EI MORAGA-OAKLAND 5-37 RPR INSS | 44371832 | MORAGA-OAKLAND #3 | 005/037 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-07-31 | 2021-05-31 | 2021-03-28 | 2021-03-30 | 2021-03-30 | 2021-03-28 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.226863 | 37.8069 | ETL.2740 | 40828536 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-09-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117672477 | Not Scheduled | T3 EI MORAGA-OAKLAND #2 0/2 RPL HRDs | 44303393 | MORAGA-OAKLAND #2 | 000/002 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-26 | 2020-01-26 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | Central | WSIP | [6 empty] | '-122.166133 | 37.8478 | ETL.2730 | 40728506 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117673090 | Not Scheduled | DRUM-SUMMIT#2 17/204 RPL POLE | 31521949 | DRUM-SUMMIT #2 | 017/204 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-07-30 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.498895 | 39.3143 | ETL.1450 | 44557737 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2019-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117673232 | Q2 | T3 PARADISE TABLE MTN 16/134L RPL POLE | 31461179 | PARADISE-TABLE MTN | 016/134 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-07-08 | 2020-01-08 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.499399 | 39.6792 | ETL.4316 | 44552419 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117697271 | Q2 | T2 TRINITY-MAPLE CRK 20/8 RMV POLE BUTT | 44299848 | TRINITY-MAPLE CREEK | 020/008 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-07-31 | 2022-07-31 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.276437 | 40.7169 | ETL.8170 | 40873263 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-11-14 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-11-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117697715 | Not Scheduled | NT EI LAS POSITAS-NEWARK 12/81 PNT TWR | 43753291 | LAS POSITAS-NEWARK | 012/081 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-08-01 | 2021-08-01 | [9 empty] | Central | WSIP | [6 empty] | '-121.868653 | 37.5734 | ETL.4980 | 40604725 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117697719 | Not Scheduled | NT EI TESLA-NEWARK #2 19/128 PNT TWR | 43753285 | TESLA-NEWARK #2 | 019/128 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-08-01 | 2021-08-01 | [9 empty] | Central | WSIP | [6 empty] | '-121.868441 | 37.5733 | ETL.5354 | 41152674 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117698565 | Q2 | T2 TRINITY-MAPLE CREEK 10/6 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 010/006 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-08-01 | 2024-08-01 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.097229 | 40.7669 | ETL.8170 | 40906400 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117700453 | Q2 | T2 TRINITY-MAPLE CREEK 16/6 REPL POLE | 31471998 | TRINITY-MAPLE CREEK | 016/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-01 | 2020-08-01 | 2021-06-07 | 2021-06-12 | 2021-06-08 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.202233 | 40.7399 | ETL.8170 | 40810476 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-11-14 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117700495 | Q2 | T2 TRINITY-MAPLE CREEK 9/004 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 009/004 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-08-01 | 2024-08-01 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.076825 | 40.7661 | ETL.8170 | 40906382 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-23 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117707071 | Before Feb | T2 Eagle Rock/Redbud 026/125 RPL SWTCH |  | MENDOCINO-REDBUD | 026/125 | 93S | E | Pre-2020_(2) High fire spread TD |  | 2019-08-02 | 2020-08-02 |  |  | 2021-01-31 | 2020-12-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.661419 | 39.0292 | ETL.2410 | 41119845 | Switch-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 435 | Lakeville |  |  | 2019-09-13 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Before Feb |  |  | 2019-09-12 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117708697 | Not Scheduled | EI LAS POSITAS-NEWARK 12/83 REPAINT | 43753291 | LAS POSITAS-NEWARK | 012/083 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-08-02 | 2021-08-02 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.875144 | 37.5661 | ETL.4980 | 40661097 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117709065 | Not Scheduled | EI GREEN VALLEY-LLAGAS :010/070 REPAINT | 43766025 | GREEN VALLEY-LLAGAS | :010/070 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-08-02 | 2021-08-02 | [9 empty] | South | Non-WSIP | [6 empty] | '-121.651331 | 37.1038 | ETL.1720 | 40589047 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-20 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117710060 | Not Scheduled | EI DIABLO-GATES #1 7/33 PNT TWR | 43756059 | DIABLO-GATES #1 | 007/033 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-08-02 | 2024-08-02 | [9 empty] | South | WSIP | [6 empty] | '-120.80207 | 35.298 | ETL.5960 | 40651918 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-08-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117710837 | Not Scheduled | NT EI METCALF-MOSS LND #1 26/111 PNT TWR | 43910751 | METCALF-MOSS LANDING #1 | 026/111 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-08-03 | 2021-08-03 | [9 empty] | South | WSIP | [6 empty] | '-121.737849 | 37.2255 | ETL.5100 | 40587029 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117712709 | Q4 | T3 EI MIDDLE FORK-GLD HLL 2/027 RPL STRW | 31454603 | MIDDLE FORK-GOLD HILL | 002/027 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-08-03 | 2021-05-31 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | 2021 - Due to Long lead material delay | '-120.6282 | 39.0004 | ETL.5140 | 44552528 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117713813 | Not Scheduled | EI COALINGA #1-SAN MIGUL 15/5 REPNT MEMB | 44301011 | COALINGA #1-SAN MIGUEL | 015/005 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-08-05 | 2020-08-05 | [8 empty] | LATE | South | WSIP | [6 empty] | '-120.53864 | 36.0081 | ETL.8580 | 40754810 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 15 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-08-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117714165 | Not Scheduled | EI LAS POSITAS-NEWARK 14/091 PAINT STRT | 43753291 | LAS POSITAS-NEWARK | 014/091 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-08-05 | 2021-08-05 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.891631 | 37.548 | ETL.4980 | 40590657 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117715706 | Q2 | T3 EI SNEATH LANE-HMB ?010/2 WASH INSW | 44645175 | SNEATH LANE-HALF MOON BAY | ?010/002 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-05 | 2020-02-05 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.424481 | 37.4906 | ETL.7212 | 40695077 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 29 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-10-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117715707 | Q2 | T3 DI SNTH LN-HMB ?010/3 GRND WASH INSW | 44645175 | SNEATH LANE-HALF MOON BAY | ?010/003 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-05 | 2020-02-05 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.423577 | 37.4891 | ETL.7212 | 40656253 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 29 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-10-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117715761 | Q2 | T2 EI MELONES-CURTIS 9/4 RPR POLE | 44392489 | MELONES-CURTIS | 009/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-05 | 2020-08-05 |  |  | 2021-04-02 | 2021-03-02 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.401446 | 37.944 | ETL.2390 | 44391167 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117715766 | Q2 | T2 EI MELONES-CURTIS 10/6 RPL POLE | 31462761 | MELONES-CURTIS | 010/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-05 | 2020-08-05 |  |  | 2021-04-02 | 2021-03-02 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.384587 | 37.953 | ETL.2390 | 44391219 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-09-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117715783 | Q2 | T2 EI MELONES-CURTIS 9/5 RPL POLE | 31462760 | MELONES-CURTIS | 009/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-05 | 2020-08-05 |  |  | 2021-04-02 | 2021-03-02 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.399508 | 37.945 | ETL.2390 | 44391192 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-09-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117715786 | Q2 | T2 EI MELONES-CURTIS 13/6 RPL POLE | 31462763 | MELONES-CURTIS | 013/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-05 | 2020-08-05 |  |  | 2021-04-02 | 2021-03-02 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.337952 | 37.9698 | ETL.2390 | 44391226 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-09-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117715789 | Q2 | T2 EI MELONES-CURTIS 12/1 RPL POLE | 31462762 | MELONES-CURTIS | 012/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-05 | 2020-08-05 |  |  | 2021-04-02 | 2021-03-02 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.362702 | 37.9622 | ETL.2390 | 44391034 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-09-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117715797 | Q2 | T2 DI HAT CREEK #1 WSTWD 7/140 RPL STRW | 31471016 | HAT CREEK #1-WESTWOOD | 007/140 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-02 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.423578 | 40.8886 | ETL.7030 | 40668057 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2019-08-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117715920 | Q3 | T2 CARIBOU #2 014/011 RPL POLE | 31519914 | CARIBOU #2 | 014/011 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-06-21 | 2021-05-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Access Issues | 2021 - Tag was created to stub pole and location was inaccessible for stubbing equp. Tag converted from GAR to 70Y. FSR 12/2020 | '-121.122393 | 40.0266 | ETL.6280 | 40600614 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2020-02-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117717945 | Q3 | EI TESLA-NEWARK #2 22/142 INST HRDT |  | TESLA-NEWARK #2 | 022/142 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-08-06 | 2020-08-06 |  |  | 2021-07-23 | 2021-07-19 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.895011 | 37.5411 | ETL.5354 | 40870328 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-10-01 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117721321 | Mar | T3 DRUM-RIO OSO #2 005/059A INST LADDERS | 43937827 | DRUM-RIO OSO #2 | 005/059A | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-08-06 | 2024-08-06 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.850634 | 39.216 | ETL.1430 | 40576825 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117721358 | Q2 | T2 EI CLAY-MARTEL 32/492 RPL POLE | 31461360 | CLAY-MARTEL | 032/492 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-06 | 2020-08-06 |  |  | 2021-05-01 | 2021-04-26 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.842849 | 38.4595 | ETL.8250 | 40904096 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-08-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117722378 | Not Scheduled | T2 DI CARIBOU-PALERMO :20/170 RPR FOND | 44069454 | CARIBOU-PALERMO | :020/170 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-08-05 | 2020-08-05 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.363578 | 39.8908 | ETL.3190 | 40642282 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117722443 | Not Scheduled | T2 DI CARIBOU-PALERMO :14/118 RMV SOIL |  | CARIBOU-PALERMO | :014/118 | ICS | E | Pre-2020_(3) On high spread structure |  | 2019-08-05 | 2020-08-05 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.304514 | 39.949 | ETL.3190 | 40738823 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117723283 | Not Scheduled | DI PALERMO-WYANDOTTE 1/14 RMV DEBRIS | 43952544 | PALERMO-WYANDOTTE | 001/014 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-08-06 | 2020-08-06 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.539627 | 39.4704 | ETL.4315 | 40757545 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117723286 | Not Scheduled | DI PALERMO-WYANDOTTE 1/14 INST MRKS | 43952544 | PALERMO-WYANDOTTE | 001/014 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-08-06 | 2021-08-06 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.539627 | 39.4704 | ETL.4315 | 40757545 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117723288 | Not Scheduled | DI PALERMO-WYANDOTTE 1/14 RPL INSS | 31462731 | PALERMO-WYANDOTTE | 001/014 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-06 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.539638 | 39.4678 | ETL.4315 | 40787574 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-09-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117723827 | Q2 | T2 EI MELONES-CURTIS 12/5 RPL POLE | 31462766 | MELONES-CURTIS | 012/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-07 | 2020-08-07 |  |  | 2021-04-02 | 2021-03-02 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.355756 | 37.9652 | ETL.2390 | 44391175 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-09-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117723837 | Q2 | T2EI MELONES-CURTIS 12/2 RPL POLE | 31462765 | MELONES-CURTIS | 012/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-07 | 2020-08-07 |  |  | 2021-04-02 | 2021-03-02 |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-120.360319 | 37.9632 | ETL.2390 | 44391080 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-09-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117724468 | Q2 | T2 EI MELONES-CURTIS 11/0 REFRAME | 31483848 | MELONES-CURTIS | 011/000 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-07 | 2020-08-07 |  |  | 2021-04-02 | 2021-03-02 |  |  |  | TR2 | LATE | Central | WSIP | [8 empty] | ETL.2390 | 44391007 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117725507 | Q2 | T2 OCNO-CALLNDR SW ST 020/132 RPR GYWW | 44391517 | OCEANO-CALLENDAR SW STA | 020/132 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-07 | 2021-05-31 | 2021-04-24 | 2021-04-25 | 2021-04-25 | 2021-04-24 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.57673 | 35.0964 | ETL.2394 | 40652046 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-08-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117725787 | Q2 | T2 COBURN-PANOCHE 041/176 RPR FOND | 43930664 | COBURN-PANOCHE | 041/176 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-07 | 2020-08-07 |  |  | 2021-05-21 | 2021-05-03 |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-121.0742767 | 36.6654 | ETL.4460 | 40959338 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117727313 | Mar | EI PEASE-HARTER A014/308 RPR ANCW | 43932090 | PEASE-HARTER | A014/308 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-06 | 2020-08-06 |  |  | 2021-03-02 | 2021-03-02 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.907684 | 39.145 | ETL.7760 | 40874304 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117728905 | Mar | T2 DI BLLT-RVRBK-MLNS SWS :09/1 RPL STRW | 31509462 | BELLOTA-RIVERBANK-MELONES SW STA | :009/001 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-08 | 2020-08-08 |  |  | 2021-03-05 | 2021-03-04 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.639239 | 37.8769 | ETL.1070 | 40580431 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-09-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117730044 | Not Scheduled | T2 DI HAAS-MCCALL 000/006 RPL INSS | 44299317 | HAAS-MCCALL | 000/006 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-08 | 2020-08-08 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-119.0313 | 36.9224 | ETL.4850 | 40805256 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-12-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117730290 | Q4 | T3 MIDDLE FORK-GOLD HILL 0/6L RPL POLE | 31454603 | MIDDLE FORK-GOLD HILL | 000/006 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-08-08 | 2021-05-31 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | Non-WSIP |  |  |  |  | Material & Equipment | 2021 - Due to Long lead material delay | '-120.598509 | 39.018 | ETL.5140 | 44552438 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q4 |  |  | 2020-10-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117732227 | Mar | T2 DI VOLTA-SOUTH 4/106 RPR GYWW | 44309963 | VOLTA-SOUTH | 004/106 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-08 | 2020-08-08 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.878408 | 40.3955 | ETL.8300 | 40868025 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117732252 | Mar | T2 DI VOLTA-SOUTH 4/106 RPR STRW | 44309963 | VOLTA-SOUTH | 004/106 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-08 | 2020-08-08 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.878408 | 40.3955 | ETL.8300 | 40868025 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117732287 | Not Scheduled | EI PITTSBURG-SAN RAMON 002/015 REPAINT | 44586175 | PITTSBURG-SAN RAMON | 002/015 | ICX | F | Pre-2020_(9a) Other ignition related |  | 2019-08-09 | 2021-08-09 | [6 empty] | Likely MAT error - delink to correct |  |  | Central | Non-WSIP | [6 empty] | '-121.908141 | 38.0019 | ETL.5490 | 40761606 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117733042 | Not Scheduled | EI PITTSBURG-TESLA #1 017/077 RPR FOND | 43753186 | PITTSBURG-TESLA #1 | 017/077 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-09 | 2020-08-09 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.711114 | 37.8826 | ETL.5510 | 40810220 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117733057 | Not Scheduled | EI PITTSBURG-TESLA #1 017/077 INS ACLG | 31494705 | PITTSBURG-TESLA #1 | 017/077 | 93A | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-08-09 | 2021-08-09 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.711114 | 37.8826 | ETL.5510 | 40810220 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117733132 | Not Scheduled | T3 MORAGA-OAKLAND #3 000/005 RPL STRT | 31484160 | MORAGA-OAKLAND #3 | 000/005 | 70S | E | Pre-2020_(2) High fire spread TD |  | 2019-08-09 | 2020-02-09 | [7 empty] | TR3 | LATE | Central | Non-WSIP |  |  |  | REJECT: Long text calls for Tower Replacement, Field notes from crew state they inspected tower, This notification is for replacing the tower. Please resubmit once tower has been replaced. | Project | 2021- Late due to project not being funded for 2020 | '-122.170315 | 37.8466 | ETL.2740 | 40764476 | Structure-Tower | No Good/Out of Stdrd | Replace | POST | POST | POST Estimate | Not Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  | Reject | 2019-11-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117733163 | Q2 | T2 DI CSCD-BNTN-DSCHUTS A007/148 RPR PL | 43690811 | CASCADE-BENTON-DESCHUTES | A007/148 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-09 | 2020-08-09 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.266714 | 40.5699 | ETL.6310 | 40759470 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-10-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117733166 | Q2 | T2 DI CSCD-BNTN-DSCHUTS A008/163 RPR PL | 43962090 | CASCADE-BENTON-DESCHUTES | A008/163 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-09 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.26014 | 40.5605 | ETL.6310 | 40810350 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117733314 | Not Scheduled | EI T2 DRM-SMMT #2_023/279 RPL GYM TAPE | 43947604 | DRUM-SUMMIT #2 | 023/279 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-08-09 | 2021-08-09 | [7 empty] | TR2 | WECC | North Valley | Non-WSIP | [6 empty] | '-120.386811 | 39.3284 | ETL.1450 | 44565808 | Guy Wire Mark /Indic-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117743508 | Not Scheduled | EI SBRNT-GRZL-CLRMNT #1 3/33 PNT STRT | 44586187 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 003/033 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-08-10 | 2021-08-10 | [9 empty] | Central | Non-WSIP | [6 empty] | '-122.176491 | 37.8649 | ETL.3740 | 40607957 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117745284 | Not Scheduled | T3 DI CARIBOU-PALERMO :007/058 RPR INSS | 44304495 | CARIBOU-PALERMO | :007/058 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-08-12 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.227908 | 40.0074 | ETL.3190 | 44399888 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117745286 | Not Scheduled | T3 DI CARIBOU-PALERMO :007/058 RPR STUBS | 44059014 | CARIBOU-PALERMO | :007/058 | ICQ | E | Pre-2020_(3) On high spread structure |  | 2019-08-12 | 2020-02-12 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | Circuit Based Scheduling | '-121.227908 | 40.0074 | ETL.3190 | 40910300 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117745288 | Not Scheduled | T3 DI CARIBOU-PALERMO :07/058 RMV DEBRIS | 44070463 | CARIBOU-PALERMO | :007/058 | ICS | E | Pre-2020_(3) On high spread structure |  | 2019-08-12 | 2020-02-12 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.227908 | 40.0074 | ETL.3190 | 40910300 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117745312 | Q2 | T2 EI PARADISE-TABLE MTN 20/160 RPL ANCS | 31519801 | PARADISE-TABLE MTN | 020/160 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-12 | 2020-08-12 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.564124 | 39.6878 | ETL.4316 | 44712240 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117745313 | Q2 | T2 EI PARADISE-TABLE MTN 20/160 RPL ANCS | 31519801 | PARADISE-TABLE MTN | 020/160 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-12 | 2020-08-12 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.564124 | 39.6878 | ETL.4316 | 44712241 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117745363 | Not Scheduled | T3NT DI CARIBOU-PALERMO :07/57 INST HRDS | 44304825 | CARIBOU-PALERMO | :007/057 | ICS | F | Pre-2020_(3) On high spread structure |  | 2019-08-12 | 2021-08-12 | [7 empty] | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.226794 | 40.0078 | ETL.3190 | 40910299 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117745874 | Not Scheduled | EI SOBRANTE-MORAGA 001/015 REPAINT | 44586184 | SOBRANTE-MORAGA | 001/015 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-08-12 | 2021-08-12 | [9 empty] | Central | Non-WSIP | [6 empty] | '-122.189352 | 37.8874 | ETL.3742 | 41135458 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117745972 | Not Scheduled | T2 DI CARIBOU-PALERMO :026/212 RPR FOND | 44069454 | CARIBOU-PALERMO | :026/212 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-12 | 2020-08-12 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.42118 | 39.8307 | ETL.3190 | 40674984 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117745978 | Q2 | T3 EI PARADISE-TABLE MTN 22/173 RPL ANCS | 31519801 | PARADISE-TABLE MTN | 022/173 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-12 | 2020-02-12 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.606593 | 39.6948 | ETL.4316 | 44712233 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117746323 | Q2 | T3 EI PARADISE-TABLE MTN 21/167 RPL GYWS | 43939113 | PARADISE-TABLE MTN | 021/167 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-12 | 2020-02-12 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.591285 | 39.6921 | ETL.4316 | 44712237 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117746324 | Q2 | T2 DI VOLTA-DESCHUTES 019/430 RPR GYWW | 43939089 | VOLTA-DESCHUTES | 019/430 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-12 | 2021-05-31 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.216505 | 40.5497 | ETL.8290 | 40667427 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117746944 | Not Scheduled | T3 EI PARADISE-TABLE MTN 22/173 CANCEL | 31519801 | PARADISE-TABLE MTN | 022/173 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-12 | 2020-02-12 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.606593 | 39.6948 | ETL.4316 | 44712231 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-09-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117747655 | Q2 | T3 EI PARADISE-TABLE MTN 21/167 RPL GYWS | 43939113 | PARADISE-TABLE MTN | 021/167 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-12 | 2020-02-12 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.591285 | 39.6921 | ETL.4316 | 44712238 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117747756 | Q2 | T3 EI PARADISE-TABLE MTN 21/167 RPL GYWS | 43939113 | PARADISE-TABLE MTN | 021/167 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-12 | 2020-02-12 |  |  | 2021-04-30 | 2021-03-30 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.591285 | 39.6921 | ETL.4316 | 44712236 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117751614 | Not Scheduled | T3 DI CARIBOU-PALERMO :7/59 RPR FOND | 44059014 | CARIBOU-PALERMO | :007/059 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-08-12 | 2020-02-12 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | Priority Bucket 9 | '-121.230422 | 40.0064 | ETL.3190 | 40910301 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117752587 | Mar | T2 DI MNCN-WLLTS-FRT BRG 37/4 RPR JUMW | 44283900 | MENDOCINO-WILLITS-FORT BRAGG | 037/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-12 | 2020-08-12 | 2020-09-07 | 2020-09-10 | 2021-03-17 | 2021-03-17 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.718406 | 39.4012 | ETL.7550 | 40769239 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-09-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117754468 | Q2 | DI ROUND MTN-TBL MTN #2 73/300 INST GMKS | 44305720 | ROUND MTN-TABLE MTN #2 | 073/300 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-08-13 | 2021-08-13 |  |  | 2021-04-08 | 2021-01-12 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.757757 | 39.7589 | ETL.6070 | 40602996 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-03-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117755301 | Not Scheduled | T2 FORT BRAGG-ELK 14/8A RPL INSS | 31490902 | FORT BRAGG-ELK | 014/008A | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-14 | 2020-08-14 | 2020-07-13 | 2020-07-13 | [5 empty] | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.786747 | 39.311 | ETL.2060 | 40577238 | Insulator-Steel | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-01-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117761621 | Not Scheduled | LOS BANOS-MIDWAY #2 072/304 RPR SPLS | 43974863 | LOS BANOS-MIDWAY #2 | 072/304 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-08-15 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.209626 | 36.2458 | ETL.6010 | 40753988 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117762000 | Mar | T2 DI BLT-RVRBNK-MLNS SS :5/2 RMV NEST | 43938937 | BELLOTA-RIVERBANK-MELONES SW STA | :005/002 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-08-15 | 2021-05-31 |  |  | 2021-03-05 | 2021-03-04 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.569427 | 37.8874 | ETL.1070 | 44727555 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-09-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117768126 | Feb | T3 KILARC-CEDAR CREEK 6/138 RPR SPLW | 43939119 | KILARC-CEDAR CREEK | 006/138 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-16 | 2020-02-16 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.98035 | 40.7109 | ETL.7290 | 40617662 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117769455 | Q2 | LOS BANOS-MIDWAY#2 51/214 BENT STL | 44300848 | LOS BANOS-MIDWAY #2 | 051/214 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-08-16 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.462157 | 36.4793 | ETL.6010 | 40753976 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117769901 | Not Scheduled | T2 DI ST-ML SW ST-MN #1 10/63 PNT STRT | 43939154 | STANISLAUS-MELONES SS-MANTECA #1+ | 010/063 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-08-15 | 2021-08-15 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.528849 | 38.0615 | ETL.3830 | 40654276 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117770100 | Q4 | MAPLE CREEK-HOOPA 27/011 RMV VEGN | 44311201 | MAPLE CREEK-HOOPA | 027/011 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-08-16 | 2020-08-16 |  |  | 2021-10-02 | 2021-07-26 |  |  | Likely veg |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.67229 | 41.0436 | ETL.7490 | 40586872 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117773530 | Not Scheduled | EI VASONA-METCALF 6/29 INSTL ACG |  | VASONA-METCALF | 006/029 | 93A | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-08-17 | 2021-08-17 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.853873 | 37.2294 | ETL.5932 | 40862837 | Structure-Tower | Anti-Climbing Guard | Install |  |  |  |  | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117773558 | Not Scheduled | EI VASONA-METCALF 6/029 RPR STRT |  | VASONA-METCALF | 006/029 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-17 | 2020-08-17 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.853873 | 37.2294 | ETL.5932 | 40862837 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117773752 | Q4 | T3 MIDDLE FORK-GOLD HILL 7/63A REPL PL | 31454603 | MIDDLE FORK-GOLD HILL | 007/063A | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-08-17 | 2021-05-31 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | Non-WSIP |  |  |  |  | Material & Equipment | 2021 - Due to Long lead material delay | '-120.716065 | 39.0032 | ETL.5140 | 40656767 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q4 |  |  | 2020-10-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117773761 | Q4 | T3 MIDDLE FORK-GOLD HILL 7/63B REPL PL | 31454603 | MIDDLE FORK-GOLD HILL | 007/063B | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-08-17 | 2021-05-31 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | Non-WSIP |  |  |  |  | Material & Equipment | 2021 - Due to Long lead material delay | '-120.716038 | 39.0033 | ETL.5140 | 42569829 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q4 |  |  | 2020-10-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117773762 | Q4 | T3 MIDDLE FORK-GOLD HILL 7/63C REPL PL | 31454603 | MIDDLE FORK-GOLD HILL | 007/063C | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-08-17 | 2021-05-31 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | Non-WSIP |  |  |  |  | Material & Equipment | 2021 - Due to Long lead material delay | '-120.716011 | 39.0033 | ETL.5140 | 42569831 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q4 |  |  | 2020-10-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117780020 | Q2 | LOS BANOS-MIDWAY#2 081/343 RPR STRT | 44300848 | LOS BANOS-MIDWAY #2 | 081/343 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-08-19 | 2022-08-19 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.11652 | 36.1329 | ETL.6010 | 40651958 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117780538 | Not Scheduled | T2 PARKWAY-MORAGA 7/040 RPR OPGW | 43974750 | PARKWAY-MORAGA | 007/040 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-20 | 2020-08-20 | [7 empty] | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-122.233506 | 38.0434 | ETL.5930 | 40752935 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117780714 | Not Scheduled | T2 JEFFERSON-HILLSDALE JCT 6/37 CLR RD |  | JEFFERSON-HILLSDALE JCT | 006/037 | CHS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2019-08-20 | 2021-08-20 | [7 empty] | TR2 |  | Central | Non-WSIP | [6 empty] | '-122.357579 | 37.5278 | ETL.7190 | 40804838 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Bay |  |  | SFWL | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117782645 | Mar | T2 DI POE-RIO OSO 029/191 INS MRKS |  | POE-RIO OSO | 029/191 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-08-20 | 2021-08-20 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.530297 | 39.575 | ETL.5540 | 40590790 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-09-25 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117785007 | Not Scheduled | T2 DI RND MTN-TBL MTN#2 66/275 RPR STRT | 44156941 | ROUND MTN-TABLE MTN #2 | 066/275 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-21 | 2020-08-21 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.80417 | 39.8647 | ETL.6070 | 40756153 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117785181 | Not Scheduled | SAN MATEO-MARTIN #6 0/3 RPL INSS | 31475502 | SAN MATEO-MARTIN #6 | 000/003 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-21 | 2020-08-21 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-122.2414 | 37.3721 | ETL.3590 | 40840835 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117786680 | Not Scheduled | T2 DI STNL-MLN SST-MNTC#1 12/72 RPR FOND | 44460419 | STANISLAUS-MELONES SS-MANTECA #1+ | 012/072 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-21 | 2020-08-21 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.560497 | 38.046 | ETL.3830 | 40642829 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-01-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117786945 | Not Scheduled | CALLENDAR SS-MESA 1/21 RECONDUCT | 31470273 | CALLENDAR SW STA-MESA | 001/021 | 93C | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-13 | 2020-08-13 | [8 empty] | LATE | South | Non-WSIP | [6 empty] | '-120.570748 | 35.051 | ETL.1210 | 40618576 | Conductor-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-05-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117787255 | Not Scheduled | LOS BANOS-MIDWAY#2 42/176 ZENA GUARD | 43848355 | LOS BANOS-MIDWAY #2 | 042/176 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-08-21 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.576372 | 36.5656 | ETL.6010 | 40817172 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117788588 | Before Feb | T3 EAGLE RK-FULTON-SLVRD 6/29 RPL JUMS | 44074003 | GEYSERS #17-FULTON | 006/029 | IBE | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-22 | 2020-02-22 | 2021-01-18 | 2021-01-21 | 2021-01-21 | 2021-01-18 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.79012 | 38.7576 | ETL.4770 | 40888471 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IB | Before Feb |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117788593 | Not Scheduled | T3 DI CENTERVLLE-TABLE MTN 2/43 RPR PL | 44408859 | CENTERVILLE-TABLE MTN | 002/043 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-22 | 2020-02-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.682223 | 39.7555 | ETL.6320 | 40867501 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117789338 | Not Scheduled | T2 EI DRUM-SUMMIT #2 27/326A REPL POLE | 31471241 | DRUM-SUMMIT #2 | 027/326A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-08-22 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.33228 | 39.3122 | ETL.1450 | 40752050 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-04-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117789766 | Not Scheduled | T2 EI DRUM-SUMMIT #2 27/326C RPL PL | 31471241 | DRUM-SUMMIT #2 | 027/326C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-08-22 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.332213 | 39.3121 | ETL.1450 | 42572857 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-04-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117794063 | Q2 | LOS BANOS-MIDWAY #2 30/129 INST ACG | 31469966 | LOS BANOS-MIDWAY #2 | 030/129 | 93A | F | Pre-2020_(1b) Lines with special commitments |  | 2019-08-23 | 2021-08-23 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.696705 | 36.7039 | ETL.6010 | 40863645 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117794325 | Q4 | T3 MAPLE CREEK-HOOPA 22/011 RMV PL BUTT | 44311201 | MAPLE CREEK-HOOPA | 022/011 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-08-23 | 2023-08-23 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.640275 | 40.986 | ETL.7490 | 44660734 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q4 | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117794331 | Not Scheduled | T2 DI DRUM-SUMMIT#2 27/326B RPL PL | 31471241 | DRUM-SUMMIT #2 | 027/326B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-08-23 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.332239 | 39.3121 | ETL.1450 | 42572856 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-04-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117794382 | Q4 | T3 MAPLE CREEK-HOOPA 021/011 RMV DBR | 44311201 | MAPLE CREEK-HOOPA | 021/011 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-08-23 | 2022-02-23 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.641365 | 40.9725 | ETL.7490 | 40586862 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q4 | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117794653 | Q4 | T3 MAPLE CREEK-HOOPA 021/009 RMV DEBRIS | 44311201 | MAPLE CREEK-HOOPA | 021/009 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-08-23 | 2020-02-23 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.642194 | 40.9694 | ETL.7490 | 44429888 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117794994 | Q2 | T2 DI PIT #1-COTTONWOOD 5/45 RMV NEST | 43879413 | PIT #1-COTTONWOOD | 005/045 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-08-23 | 2020-08-23 |  |  | 2021-05-31 | 2021-05-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.579854 | 40.9459 | ETL.5390 | 40759512 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-05-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117795642 | Not Scheduled | T2 VALLEY SPRINGS #1 000/012 RPL POLE | 31469727 | VALLEY SPRINGS #1 | 000/012 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-23 | 2020-08-23 | [7 empty] | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-120.769068 | 38.2081 | ETL.8210 | 40904188 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117808329 | Q2 | LOS BNS-MDWY#2 035/147 INST HRDS | 43848355 | LOS BANOS-MIDWAY #2 | 035/147 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-08-23 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.660518 | 36.644 | ETL.6010 | 40811493 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117808519 | Q2 | T2 DI PIT#1 COTTONWOOD 012/097 RMV NEST | 43879413 | PIT #1-COTTONWOOD | 012/097 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-08-26 | 2021-05-31 |  |  | 2021-05-31 | 2021-05-17 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.689241 | 40.8905 | ETL.5390 | 40803635 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-05-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117808604 | Not Scheduled | DI FULTON-PUEBLO 012/058 GRD WAS INSS | 44306538 | FULTON-PUEBLO | 012/058 | ICD | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-23 | 2020-08-23 | [8 empty] | LATE | North Coast | WSIP | [6 empty] | '-122.205231 | 38.5097 | ETL.1600 | 40862869 | Insulator | Contaminated | Helicopter Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 626 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-04-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117809120 | Q2 | T2 DI PIT#1 COTTONWOOD 5/46 RMV NEST | 43879413 | PIT #1-COTTONWOOD | 005/046 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-08-26 | 2020-08-26 |  |  | 2021-05-31 | 2021-05-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.581665 | 40.945 | ETL.5390 | 40803648 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-05-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117809127 | Mar | T3 DI VOLTA-SOUTH 0/3 RPR PL | 43827513 | VOLTA-SOUTH | 000/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-26 | 2020-02-26 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.866115 | 40.4583 | ETL.8300 | 40667465 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-10-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117813218 | Not Scheduled | T3 EI DRUM-RIO OSO#2 1/17 INST ANCS | 31471216 | DRUM-RIO OSO #2 | 001/017 | 93Z | E | Pre-2020_(9a) Other ignition related |  | 2019-08-27 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-120.798755 | 39.256 | ETL.1430 | 40814408 | Anchor-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117813491 | Not Scheduled | T3 EI DRUM-RIO OSO#1 1/17 INST ANCS | 31497813 | DRUM-RIO OSO #1 | 001/017 | 93E | E | Pre-2020_(9a) Other ignition related |  | 2019-08-27 | 2021-05-31 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-120.798822 | 39.2562 | ETL.1420 | 40811218 | Anchor-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Sacramento |  |  | Yes | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117814368 | Not Scheduled | T2 VALLEY SPRINGS-CLAY 6/92 INST RPTR PL | 31471034 | VALLEY SPRINGS-CLAY | 006/092 | 93B | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-08-27 | 2020-08-27 | [7 empty] | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-120.835735 | 38.2184 | ETL.8264 | 40905035 | Raptor Guard-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 672 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-09-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117814584 | Not Scheduled | T3 POE-RIO OSO 19/127 CANCEL | 43737421 | POE-RIO OSO | 019/127 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-06 | 2020-02-06 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.48118 | 39.7202 | ETL.5540 | 44383620 | Hardware-Steel | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-09-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117814895 | Not Scheduled | T2 DRUM-SUMMIT #1 18/218A RPL PL | 31453338 | DRUM-SUMMIT #1 | 018/218A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-08-27 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.471139 | 39.3184 | ETL.1440 | 40595348 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-04-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117814896 | Not Scheduled | T2 DRUM-SUMMIT #1 18/218B RPL PL | 31453338 | DRUM-SUMMIT #1 | 018/218B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-08-27 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.47111 | 39.3183 | ETL.1440 | 42572702 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-04-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117814909 | Not Scheduled | T2 DRUM-SUMMIT #1 18/218C RPL PL | 31453338 | DRUM-SUMMIT #1 | 018/218C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  | 2019-08-27 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.471096 | 39.3183 | ETL.1440 | 42572703 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-04-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117816180 | Not Scheduled | T2 DI BRCBURG JCT-MARIPOSA 4/15 RPL HRDD | 44301835 | BRICEBURG JCT-MARIPOSA TAP | 004/015 | ICW | F | Pre-2020_(5) TD tag on other lines |  | 2019-08-27 | 2022-08-27 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.985828 | 37.534 | ETL.8651 | 40748170 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-01-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117816289 | Q2 | LOS BANOS-MIDWAY #2 045/190 RPL HRDT | 44300848 | LOS BANOS-MIDWAY #2 | 045/190 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-08-27 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.529588 | 36.5358 | ETL.6010 | 40600326 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117817298 | Mar | T3 DI VOLTA-SOUTH 0/3 RPL CRSW | 31471616 | VOLTA-SOUTH | 000/003 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-27 | 2020-02-27 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.866115 | 40.4583 | ETL.8300 | 40667465 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-10-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117817507 | Q2 | LOS BNS-GATES#1 46/195 INST CLMBG GUARD | 31480609 | LOS BANOS-GATES #1 | 046/195 | 93A | F | Pre-2020_(1b) Lines with special commitments |  | 2019-08-27 | 2021-08-27 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.514911 | 36.5242 | ETL.6000 | 40758969 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-23 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117817610 | Not Scheduled | T2 DI PALERMO-COLGATE C001/008 INS MRKS | 43978676 | PALERMO-COLGATE | C001/008 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-08-28 | 2021-08-28 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.221242 | 39.3196 | ETL.5360 | 40871483 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117818503 | Q2 | LOS BANOS-MIDWAY#2 45/191 INST HRDT | 44300848 | LOS BANOS-MIDWAY #2 | 045/191 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-08-28 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.525311 | 36.5328 | ETL.6010 | 40587749 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117820552 | Q4 | T3 MAPLE CREEK-HOOPA 19/10 RMV BUTT | 44311201 | MAPLE CREEK-HOOPA | 019/010 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-08-29 | 2020-02-29 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.644742 | 40.9475 | ETL.7490 | 40617823 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117820602 | Q4 | T3 MAPLE CREEK-HOOPA 19/9 RMV BUTT | 44311201 | MAPLE CREEK-HOOPA | 019/009 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-08-29 | 2020-02-29 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.645365 | 40.9476 | ETL.7490 | 44963391 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117821397 | Not Scheduled | T2 DI PIT#1-CTTNWD 42/362 RMV VEGN |  | PIT #1-COTTONWOOD | 042/362 | HNA | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-08-29 | 2020-08-29 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.093226 | 40.6061 | ETL.5390 | 40689979 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2020-05-28 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117821633 | Q2 | LOS BANOS-MIDWAY#2 138/567 REPL INSS | 74008748 | LOS BANOS-MIDWAY #2 | 138/567 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-08-29 | 2021-05-31 | 2021-05-11 | 2021-05-28 | 2021-05-28 | 2021-05-11 |  | DLFL once tag is confirmed complete PM |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.519143 | 35.4829 | ETL.6010 | 40811546 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 26 | CDFW | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-17 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117822093 | Q2 | LOS BANOS-MIDWAY #2 044/187 INS HRDT | 44300848 | LOS BANOS-MIDWAY #2 | 044/187 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-08-29 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.540226 | 36.5428 | ETL.6010 | 40818982 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117822288 | Q4 | T3 MAPLE CREEK-HOOPA 16/001 RMV BUTT | 44311201 | MAPLE CREEK-HOOPA | 016/001 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-08-29 | 2023-08-29 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.699263 | 40.9199 | ETL.7490 | 40602068 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q4 | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117824932 | Not Scheduled | T2 Fulton Calistoga 010/004 RPR SWTCH WD | 43944406 | FULTON-CALISTOGA | 010/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-29 | 2020-08-29 | 2020-05-12 | 2020-05-19 | [5 empty] | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.578187 | 38.5923 | ETL.6880 | 43242522 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117825720 | Q4 | T3 MAPLE CREEK-HOOPA 10/12 RMV BUTT | 44311201 | MAPLE CREEK-HOOPA | 010/012 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-08-30 | 2020-02-29 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.771116 | 40.8935 | ETL.7490 | 40662154 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117825971 | Not Scheduled | EI STNSLS-MNTECA #2 12/71 INST CLMB GRD | 31471073 | STANISLAUS-MANTECA #2 | 012/071 | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-08-30 | 2021-08-30 | [9 empty] | Central | Non-WSIP | [6 empty] | '-120.560399 | 38.0459 | ETL.3820 | 40597023 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Victor |  | Y - 14 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2018-10-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117825982 | Not Scheduled | EI STANISLAUS-MANTECA #2 12/71 RPR FOND | 44460413 | STANISLAUS-MANTECA #2 | 012/071 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-30 | 2020-08-30 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-120.560399 | 38.0459 | ETL.3820 | 40597023 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 14 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2018-10-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117835623 | Q2 | T2 EI BALCH-SANGER 003/025 INS HRDT | 44190547 | BALCH-SANGER | 003/025 | ICQ | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-08-31 | 2020-08-31 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.138379 | 36.8798 | ETL.1050 | 40765310 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 16 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117835624 | Q2 | T2 EI BALCH-SANGER 003/025 RPR STRT | 44139817 | BALCH-SANGER | 003/025 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-08-31 | 2020-08-31 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.138379 | 36.8798 | ETL.1050 | 40765310 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 16 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117837462 | Q4 | T2 DI LOS ESTERS-METCLF 22/99 RMV VEGN |  | LOS ESTEROS-METCALF | 022/099 | HNA | F | Pre-2020_(9a) Other ignition related |  | 2019-08-30 | 2024-08-30 |  |  | 2021-11-30 | 2021-10-31 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.855545 | 37.5229 | ETL.5353 | 40862410 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q4 | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117837472 | Q4 | T2 DI LOS ESTRS-MTCLF 25/107 RMV VEGN |  | LOS ESTEROS-METCALF | 025/107 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-08-30 | 2021-05-31 |  |  | 2021-11-30 | 2021-10-31 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.868393 | 37.5521 | ETL.5353 | 40810199 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117837522 | Q4 | T2 DI LOS ESTRS-METCLF 23/101 RMV VEGN |  | LOS ESTEROS-METCALF | 023/101 | HNA | E | Pre-2020_(9a) Other ignition related |  | 2019-08-30 | 2021-05-31 |  |  | 2021-11-30 | 2021-10-31 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.858978 | 37.5307 | ETL.5353 | 40586608 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117837987 | Not Scheduled | T2 DI LOS ESTERS-METCLAF 23/100 RPR FOND |  | LOS ESTEROS-METCALF | 023/100 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-09-03 | 2021-09-03 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-121.856964 | 37.5261 | ETL.5353 | 40590872 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-12-11 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117838191 | Not Scheduled | T2 DI CARIBOU-PALERMO :20/168 RPL INSS |  | CARIBOU-PALERMO | :020/168 | 93K | E | Pre-2020_(2) High fire spread TD |  | 2019-08-30 | 2020-08-30 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.361944 | 39.8926 | ETL.3190 | 40858943 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-09-25 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117838457 | Not Scheduled | T2 DI EXCHEQUER-YOSEMITE 16/59 REPAINT | 44585956 | EXCHEQUER-YOSEMITE | 016/059 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-09-03 | 2021-09-03 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.087221 | 37.5865 | ETL.8650 | 40871684 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 42 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117838814 | Q2 | T2 DI IGNCO-ALTO-SSLT #1 16/114 RPR GYWW | 44310666 | IGNACIO-ALTO-SAUSALITO #1 | 016/114 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-03 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.503941 | 37.8577 | ETL.7160 | 40576349 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117838819 | Q2 | T2 DI IGNCO-ALTO-SSLT #1 16/114 WSH INSW | 44310668 | IGNACIO-ALTO-SAUSALITO #1 | 016/114 | ICD | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-03 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.503941 | 37.8577 | ETL.7160 | 40576349 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-08-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117840288 | Not Scheduled | T2 FULTON-CALISTOGA 10/4 S19 RPR SWITCH | 43944407 | FULTON-CALISTOGA | 010/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-03 | 2020-09-03 | 2020-05-12 | 2020-05-19 | [5 empty] | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.578072 | 38.5923 | ETL.6880 | 40743693 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117843402 | Q4 | T3 MAPLE CREEK-HOOPA 015/001 RMV DBR | 44311201 | MAPLE CREEK-HOOPA | 015/001 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-09-04 | 2022-09-04 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.708747 | 40.9091 | ETL.7490 | 40586852 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q4 | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117844626 | Mar | TABLE MTN-PALERMO 010/048 RPR CONS | 44154429 | TABLE MTN-PALERMO | 010/048 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-04 | 2020-09-04 |  |  | 2021-03-17 | 2021-03-17 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.502309 | 39.5069 | ETL.5690 | 40871778 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117844892 | Q2 | T2 KONOCTI-MIDDLETOWN 25/7 RPL POLE | 31471948 | KONOCTI-MIDDLETOWN | 025/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-04 | 2020-05-04 | 2021-04-19 | 2021-04-23 | 2021-04-22 | 2021-04-22 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.685926 | 38.9138 | ETL.6380 | 40808153 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-09-19 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117845880 | Feb | T2 OLEUM-MARTINEZ 5/034 CHANGE INSULAT | 31484429 | OLEUM-MARTINEZ | 005/034 | 93K | E | Pre-2020_(5) TD tag on other lines | Clearance restriction (circuit efficiency) | 2019-09-04 | 2020-09-04 |  |  | 2021-02-23 | 2021-02-23 |  | Please verify if work was completed uner LC 116802249 |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-122.171788 | 38.0136 | ETL.3170 | 40623126 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117851982 | Q2 | T2 MALIN-ROUND MTN #2 93/474 RPL INSS | 31475177 | MALIN-ROUND MTN #2 | 093/474 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-09-05 | 2020-09-05 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.918783 | 40.8233 | ETL.6020 | 40657568 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117854771 | Q4 | T3 MAPLE CREEK-HOOPA 11/1 RMV DBRS | 44311201 | MAPLE CREEK-HOOPA | 011/001 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-09-09 | 2020-03-09 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7711518 | 40.8981 | ETL.7490 | 44815580 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117854988 | Q2 | T2 EI CHOWCHILLA-KERCKHOFF 0/3 RPR FOND | 43958150 | CHOWCHILLA-KERCKHOFF | 000/003 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-09 | 2021-05-31 |  |  | 2021-06-05 | 2021-06-01 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.558441 | 37.0916 | ETL.1250 | 40646739 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 | BLM | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-10-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117855073 | Not Scheduled | MORRO BAY-MESA 0/1 REPAINT | 44300723 | MORRO BAY-MESA | 000/001 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-09-09 | 2021-09-09 | [9 empty] | South | Non-WSIP | [6 empty] | '-120.853705 | 35.3744 | ETL.5290 | 40587100 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117855435 | Not Scheduled | T3 MAPLE CREEK-HOOPA 12/005 BTT CNCL | 44311201 | MAPLE CREEK-HOOPA | 012/005 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-09-09 | 2020-03-09 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.75827 | 40.9067 | ETL.7490 | 40770516 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117855863 | Not Scheduled | T3 MORAGA-OAKLAND #1 1/9 INS RETAIN WALL |  | MORAGA-OAKLAND #1 | 001/009 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-09-09 | 2020-03-09 | [7 empty] | TR3 | LATE | Central | Non-WSIP | [6 empty] | '-122.182487 | 37.841 | ETL.2720 | 40857632 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 15 | SVRPR | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117855868 | Q4 | T3 MAPLE CREEK-HOOPA 12/11 RMV BUTT | 44311201 | MAPLE CREEK-HOOPA | 012/011 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-09-09 | 2024-09-09 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.751572 | 40.9074 | ETL.7490 | 40602067 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q4 | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117856562 | Q4 | T2 MAPLE CREEK-HOOPA 16/005 RMV DEBRIS | 44311201 | MAPLE CREEK-HOOPA | 016/005 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-09-09 | 2022-09-09 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.690788 | 40.9239 | ETL.7490 | 40770464 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q4 | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117857008 | Q4 | T3 MAPLE CREEK-HOOPA 10/13 RMV BUTT | 44311201 | MAPLE CREEK-HOOPA | 010/013 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-09-09 | 2024-09-09 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.770896 | 40.895 | ETL.7490 | 44769635 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q4 | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117866035 | Q2 | T2 DI CTTNWD-PANORAMA 000/004 RPR GRWW | 43881008 | COTTONWOOD-PANORAMA | 000/004 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-09 | 2020-09-09 |  |  | 2021-04-24 | 2021-04-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267097 | 40.4029 | ETL.1340 | 40758209 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117866766 | Not Scheduled | T2 DI CARIBOU-PALERMO :0/2 RPR STRS |  | CARIBOU-PALERMO | :000/002 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-10 | 2020-09-10 | [7 empty] | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.149439 | 40.0846 | ETL.3190 | 44188832 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117868111 | Q2 | T2 DI TULE-SPRINGVILLE 021/002 RPL PL | 31471491 | TULE-SPRINGVILLE | 021/002 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-10 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.795542 | 36.1365 | ETL.9040 | 40655107 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2019-12-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117870598 | Q2 | GATES-MIDWAY 006/025 RPL INSS | 31473303 | GATES-MIDWAY | 006/025 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-11 | 2020-09-11 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | WSIP | [6 empty] | '-120.066072 | 36.0729 | ETL.5990 | 40691195 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117870951 | Not Scheduled | T3NT DIABLO-MESA X0/1 INS MKBLS | 31514438 | DIABLO-MESA | X000/001 | 93P | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-11 | 2021-05-31 | [7 empty] | TR3 | LATE | South | Non-WSIP | [6 empty] | '-120.851119 | 35.2175 | ETL.4620 | 40587023 | FAA Lighting-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 671 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-09-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117871038 | Q2 | T2 EI CHOWCHILLA-KERCKHOFF 1/2 RPR FOND | 44140481 | CHOWCHILLA-KERCKHOFF | 001/002 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-11 | 2021-05-31 |  |  | 2021-06-05 | 2021-06-01 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.572565 | 37.091 | ETL.1250 | 40652120 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-10-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117871139 | Q2 | T2 EI CHOWCHILLA-KERCKHOFF 1/1 RPR FOND | 44140481 | CHOWCHILLA-KERCKHOFF | 001/001 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-11 | 2021-05-31 |  |  | 2021-06-05 | 2021-06-01 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.570722 | 37.0911 | ETL.1250 | 44327115 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2019-10-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117871277 | Not Scheduled | T2 PARKWAY-MORAGA 10/059 INSTL ACG | 43683430 | PARKWAY-MORAGA | 010/059 | ICQ | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-09-11 | 2021-09-11 | [6 empty] | Likely MAT error - delink to correct | TR2 |  | Central | Non-WSIP | [6 empty] | '-122.23148 | 37.9973 | ETL.5930 | 40763001 | Structure-Tower | Anti-Climbing Guard | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 988 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-04-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117871908 | Not Scheduled | T3 MORRO BAY-DIABLO X4/20 RPR CNDS |  | MORRO BAY-DIABLO | X004/020 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-11 | 2020-03-11 | [7 empty] | TR3 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.8068035 | 35.2479 | ETL.5260 | 44330047 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-09-17 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117872019 | Not Scheduled | T3 MORRO BAY-DIABLO X3/19 RPR CNDS |  | MORRO BAY-DIABLO | X003/019 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-11 | 2020-03-11 | [7 empty] | TR3 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.806356 | 35.2443 | ETL.5260 | 44767309 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-09-17 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117872382 | Not Scheduled | T3 MORRO BAY-DIABLO X4/21 RPR CNDS | 44498739 | MORRO BAY-DIABLO | X004/021 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-11 | 2020-03-11 | [7 empty] | TR3 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.8073602 | 35.252 | ETL.5260 | 40611783 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | IC | Not Scheduled |  |  | 2019-09-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117872557 | Not Scheduled | T3 DIABLO-MESA X5/23 RPL INSS | 31479418 | DIABLO-MESA | X005/023 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-11 | 2020-03-11 | [7 empty] | TR3 | LATE | South | Non-WSIP | [6 empty] | '-120.8083999 | 35.2596 | ETL.4620 | 40686660 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-09-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117872597 | Not Scheduled | T2 DIABLO-MESA X5/24 RPL INSS | 31479418 | DIABLO-MESA | X005/024 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-11 | 2020-09-11 | [7 empty] | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.8099962 | 35.2653 | ETL.4620 | 40782272 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-09-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117873529 | Q2 | LOS BANOS-MIDWAY#2 119/488 INST HRDT | 44284322 | LOS BANOS-MIDWAY #2 | 119/488 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-09-11 | 2024-09-11 |  |  | 2021-06-14 | 2021-06-01 |  |  |  |  | LATE | South | WSIP | FSRP | [5 empty] | '-119.714568 | 35.7182 | ETL.6010 | 40870076 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  | Y - 26 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117874306 | Feb | T3 KILARC-CEDAR CREEK 010/226 REFRAME | 31471799 | KILARC-CEDAR CREEK | 010/226 | 93E | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-12 | 2020-03-12 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.970125 | 40.7535 | ETL.7290 | 40759581 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-02-18 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117874872 | Not Scheduled | T2 DIABLO-MESA X007/032 RPL INSS | 31479418 | DIABLO-MESA | X007/032 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-12 | 2020-09-12 | [7 empty] | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.80426 | 35.2934 | ETL.4620 | 40725429 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-09-17 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117874948 | Q2 | LOS BANOS-MIDWAY #2 093/388 RPR STRT | 44300848 | LOS BANOS-MIDWAY #2 | 093/388 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-09-12 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.983152 | 36.015 | ETL.6010 | 40864000 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117875667 | Not Scheduled | LOS BANOS-MIDWAY #2 088/372 INS DAMS | 43848355 | LOS BANOS-MIDWAY #2 | 088/372 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-09-12 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.042592 | 36.0526 | ETL.6010 | 40664842 | Damper-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117876261 | Not Scheduled | T2NT DI PIT #3-PIT #1 0/0A PAINT TWR | 44586172 | PIT #3-PIT #1 | 000/000A | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-09-12 | 2021-09-12 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.498029 | 40.9917 | ETL.5400 | 41184137 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117879845 | Q2 | DI COTTONWOOD-BENTON#2 0/2 RPR GYWW | 43939217 | COTTONWOOD-BENTON #2 | 000/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-12 | 2020-09-12 |  |  | 2021-06-25 | 2021-06-24 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.266115 | 40.3973 | ETL.6650 | 41147732 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-03-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117879952 | Mar | T3 DI VOLTA-SOUTH 0/1 RPR GYWW | 43827513 | VOLTA-SOUTH | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-12 | 2020-03-12 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.866227 | 40.4594 | ETL.8300 | 40592377 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117879972 | Q2 | T2 DI CLAY-MARTEL 032/489 RPL POLE | 31461360 | CLAY-MARTEL | 032/489 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-13 | 2020-09-13 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.841814 | 38.4572 | ETL.8250 | 40904099 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 | BLM | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-10-04 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117880051 | Mar | T3 DI VOLTA-SOUTH 0/1 RPR INSW | 43827513 | VOLTA-SOUTH | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-12 | 2021-05-31 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.866292 | 40.4594 | ETL.8300 | 40618010 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117880085 | Q2 | LOS BANOS-MIDWAY#2 097/408 RPLC INSS |  | LOS BANOS-MIDWAY #2 | 097/408 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-09-13 | 2020-09-13 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.926875 | 35.9629 | ETL.6010 | 40871735 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 24 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117880148 | Q2 | LOS BANOS-MIDWAY#2 110/455 RPL INSS | 31527043 | LOS BANOS-MIDWAY #2 | 110/455 | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-09-13 | 2021-09-13 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.795882 | 35.822 | ETL.6010 | 40764995 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-11-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117880361 | Q2 | LOS BANOS-MIDWAY#2 117/484 RPL INSS |  | LOS BANOS-MIDWAY #2 | 117/484 | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-09-13 | 2022-09-13 | 2021-05-11 | 2021-05-28 | 2021-05-28 | 2021-05-11 |  | DLFL once tag is confirmed complete PM |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.72383 | 35.7306 | ETL.6010 | 40793250 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 26 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117880616 | Q2 | GATES-MIDWAY 020/085 RPL INSS | 31473303 | GATES-MIDWAY | 020/085 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-13 | 2020-09-13 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | WSIP | [6 empty] | '-119.88914 | 35.9205 | ETL.5990 | 40688341 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117880617 | Not Scheduled | GATES-MIDWAY 020/085 TRIM VEGN |  | GATES-MIDWAY | 020/085 | HNA | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-09-13 | 2020-09-13 | [8 empty] | LATE | South | Non-WSIP | [6 empty] | '-119.88914 | 35.9205 | ETL.5990 | 40658397 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2019-10-03 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117880936 | Not Scheduled | T2 HAT CREEK #1-PIT #1 4/46 CANCEL | 31472892 | HAT CREEK #1-PIT #1 | 004/046 | 93E | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-13 | 2020-09-13 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.550796 | 40.9507 | ETL.7020 | 40600855 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-06-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117880947 | Q2 | LOS BANOS-MIDWAY #2 100/418 RPLC INSS |  | LOS BANOS-MIDWAY #2 | 100/418 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-09-13 | 2020-09-13 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.902909 | 35.9359 | ETL.6010 | 40894409 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 24 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-25 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117881763 | Q2 | T2 EI CORDELIA #2 TAP 004/095 RPL PL | 31472910 | CORDELIA #2 TAP | 004/095 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-13 | 2020-09-13 |  |  | 2021-05-04 | 2021-04-26 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.174453 | 38.2527 | ETL.8184 | 40665400 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-05-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117882687 | Not Scheduled | T2 HELMS-GREGG #1 29/178 INST RPT GUARD | 44301794 | HELMS-GREGG #1 | 029/178 | ICB | F | Pre-2020_(9a) Other ignition related |  | 2019-09-14 | 2024-09-14 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.451899 | 36.9428 | ETL.4870 | 40869772 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117883960 | Not Scheduled | EI DIVIDE-CABRILLO #1 011/136 RPL INSW | 31472118 | DIVIDE-CABRILLO #1 | 011/136 | 93I | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-15 | 2020-09-15 | [8 empty] | LATE | South | WSIP | [6 empty] | '-120.45284 | 34.6732 | ETL.1380 | 42574031 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-09-20 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117884417 | Q2 | LOS BANOS-MIDWAY#2 102/426 RPL INSS |  | LOS BANOS-MIDWAY #2 | 102/426 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-09-13 | 2020-09-13 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.880844 | 35.9122 | ETL.6010 | 40839600 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 24 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117885327 | Q2 | LOS BANOS-MIDWAY #2 102/425B RPR GYWS | 44301006 | LOS BANOS-MIDWAY #2 | 102/425B | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-09-16 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  | Tower guy |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.882017 | 35.9139 | ETL.6010 | 40740439 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117886611 | Q2 | LOS BANOS-GATES #1 050/213 RPR FOND | 44300852 | LOS BANOS-GATES #1 | 050/213 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-09-16 | 2021-09-16 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.464786 | 36.4813 | ETL.6000 | 40656821 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2019-09-27 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117887835 | Q2 | EI CORDELIA #2 TAP 004/078 RPL POLE | 31472910 | CORDELIA #2 TAP | 004/078 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-16 | 2020-09-16 |  |  | 2021-05-04 | 2021-04-26 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.161449 | 38.2535 | ETL.8184 | 40823386 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-05-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117888472 | Not Scheduled | T2 EI STNSLS-MLNS SWST-MNTC #1 :3/20 PNT |  | STANISLAUS-MELONES SS-MANTECA #1+ | :003/020 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-09-17 | 2021-09-17 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.584325 | 37.9569 | ETL.3830 | 40612628 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117889129 | Not Scheduled | T2 EI STNSLS-MLNS SS-MNTC #1 17/108_PNT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 017/108 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-09-17 | 2021-09-17 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.634408 | 37.9929 | ETL.3830 | 40856462 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117889282 | Not Scheduled | EI STNSL-MLNS SS-MNTC 1 - 19/122 RPR FND | 44460800 | STANISLAUS-MELONES SS-MANTECA #1+ | 019/122 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  | 2019-09-17 | 2021-09-17 | [9 empty] | Central | Non-WSIP | [6 empty] | '-120.659151 | 37.9746 | ETL.3830 | 40579574 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117890163 | Feb | T3 KILARC-CEDAR CREEK 008/180 RPL POLE | 31475774 | KILARC-CEDAR CREEK | 008/180 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-17 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.992672 | 40.7265 | ETL.7290 | 40617747 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-09-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117890643 | Not Scheduled | DI IGNACIO-SAN RFL #1 0/1 GRND WASH INSU | 44304493 | IGNACIO-SAN RAFAEL #1 | 000/001 | ICD | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-17 | 2020-09-16 | [8 empty] | LATE | North Coast | WSIP | [6 empty] | '-122.54015 | 38.0761 | ETL.1850 | 40597447 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-04-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117892757 | Not Scheduled | T2 PALERMO PEASE 1/10 RPR JUMS | 44103306 | CARIBOU-PALERMO | 001/010 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-29 | 2020-08-29 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.542374 | 39.4642 | ETL.3190 | 40599223 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117893957 | Q2 | LOS BANOS-MIDWAY #2 105/437 RPR GYWS | 43848355 | LOS BANOS-MIDWAY #2 | 105/437 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-09-18 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  | Tower guy |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.848334 | 35.8781 | ETL.6010 | 40818987 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117894167 | Not Scheduled | T2 EI SPAULDING-SUMMIT 14/466 REFRAME | 31453006 | SPAULDING-SUMMIT | 014/466 | 93E | E | Pre-2020_(1b) Lines with special commitments |  | 2019-09-11 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.4019 | 39.3286 | ETL.8060 | 40590032 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-09-25 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117894274 | Not Scheduled | T2 FLTN-CLSTGA 10/4 SWITCH 19 REPL SWTCH | 31472157 | FULTON-CALISTOGA | 010/004 | 93S | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-18 | 2020-09-18 | [7 empty] | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.578072 | 38.5923 | ETL.6880 | 40743693 | Switch-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 435 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117894361 | Not Scheduled | T2 FLTN-CLSTGA 10/4 SWITCH 17 REPL SWTCH | 31472157 | FULTON-CALISTOGA | 010/004 | 93S | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-18 | 2020-09-18 | [7 empty] | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.578187 | 38.5923 | ETL.6880 | 43242522 | Switch-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 435 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117897551 | Q2 | LOS BANOS-GATES#1 50/209 RPR GYWS | 44301004 | LOS BANOS-GATES #1 | 050/209 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-09-18 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  | Tower guy |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4757 | 36.4912 | ETL.6000 | 40872601 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-27 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117899355 | Mar | T2 EI HUMBOLDT-MAPLE CRK 85/0 REPL ANCW | 31472098 | HUMBOLDT-TRINITY | 085/000 | 93E | E | Pre-2020_(2) High fire spread TD |  | 2019-07-28 | 2020-07-28 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.596672 | 40.7118 | ETL.1820 | 44562970 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117899435 | Not Scheduled | T2 EI TESLA-NEWARK #2 20/134 RMV NEST | 44598167 | TESLA-NEWARK #2 | 020/134 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-09-19 | 2024-09-19 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.875165 | 37.5635 | ETL.5354 | 41152680 | Conductor-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117899617 | Feb | T2 RIO DELL JCT-BRDIGEVILLE 29/2 RPL PL | 31472992 | RIO DELL JCT-BRIDGEVILLE | 029/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-10 | 2020-08-10 |  |  | 2021-02-27 | 2021-02-15 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.960114 | 40.4765 | ETL.7850 | 40733677 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-12-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-15 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117899618 | Feb | T2 DI BRIDGEVLE-COTNWD 83/583L REPL POLE | 31473704 | BRIDGEVILLE-COTTONWOOD | 083/583 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-08-09 | 2021-05-31 | 2020-10-26 | 2020-10-29 | 2021-02-28 | 2021-02-28 |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Weather | AT RISK - weather impacts | '-123.728935 | 40.484 | ETL.1110 | 44424588 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2020-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117900444 | Q2 | LOS BANOS-GATES #1 058/245 RPR STRT | 44300852 | LOS BANOS-GATES #1 | 058/245 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-09-19 | 2022-09-19 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.386038 | 36.3962 | ETL.6000 | 40757866 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117900445 | Q2 | LOS BANOS-MIDWAY #2 100/419 RPL INSS |  | LOS BANOS-MIDWAY #2 | 100/419 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-09-19 | 2020-09-19 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.900484 | 35.9332 | ETL.6010 | 40886147 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 24 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117901510 | Feb | T2 EI BRDGVILLE-CTTNWD 083/583R RPL STRW | 31473704 | BRIDGEVILLE-COTTONWOOD | 083/583 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-09-20 | 2021-05-31 | 2020-10-26 | 2020-10-29 | 2021-02-28 | 2021-02-28 |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Weather | AT RISK - weather impacts | '-123.728935 | 40.484 | ETL.1110 | 44424589 | Structure-Wood | Rotten | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2020-06-03 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117901674 | Q2 | LOS BANOS-GATES#1 70/296 BENT MEMB | 44300852 | LOS BANOS-GATES #1 | 070/296 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-09-19 | 2022-09-18 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.234813 | 36.2647 | ETL.6000 | 40815939 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-09-27 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117902879 | Mar | T2 DI KILARC-DESCHUTES A025/532 INS MRKW | 43930440 | KILARC-DESCHUTES | A025/532 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-09-20 | 2021-09-20 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.286894 | 40.5711 | ETL.7300 | 40772210 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117903693 | Q3 | T2 DI KILARC-DESCHUTES A025/533 INS MRKW | 43930440 | KILARC-DESCHUTES | A025/533 | ICW | F | Pre-2020_(1b) Lines with special commitments |  | 2019-09-20 | 2021-09-20 |  |  | 2021-07-18 | 2021-06-28 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.28782 | 40.5711 | ETL.7300 | 44825413 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2019-09-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117905171 | Not Scheduled | T3NT EI TGR CRK-VLLY SPRNGS 0/2 RPT STRT | 43878409 | TIGER CREEK-VALLEY SPRINGS | 000/002 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-09-21 | 2020-09-21 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.493319 | 38.4516 | ETL.5790 | 40664027 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 11 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117906871 | Q2 | LOS BANOS-MIDWAY #2 102/425B RPL INSS | 31527043 | LOS BANOS-MIDWAY #2 | 102/425B | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-09-17 | 2021-09-17 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.882142 | 35.9133 | ETL.6010 | 40741309 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117907168 | Not Scheduled | T2 EI METCALF-EDNVLE #1 003/017 INS MRKS | 44598166 | METCALF-EDENVALE #1 | 003/017 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-09-23 | 2021-09-23 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-121.794216 | 37.2212 | ETL.2480 | 40819260 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117907451 | Q3 | T2 DI SOBRANTE-R #1 004/031 RMV VEGN |  | SOBRANTE-R #1 | 004/031 | HNA | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Veg/Land/Road) | 2019-09-20 | 2020-09-20 |  |  | 2021-08-30 | 2021-08-15 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.286632 | 37.9192 | ETL.3770 | 40581013 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117907504 | Not Scheduled | T2 EI METCLF-EDNVLE #1 003/017D RPL HRDS |  | METCALF-EDENVALE #1 | 003/017D | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-09-23 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.803579 | 37.2225 | ETL.2480 | 40742457 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-02-03 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117908366 | Q2 | T2 DI MOSS LANDING-METCLF 12/59 RPR FOND | 44113810 | MOSS LANDING-METCALF | 012/059 | ICQ | F | Pre-2020_(9a) Other ignition related |  | 2019-09-23 | 2024-09-23 |  |  | 2021-05-21 | 2021-05-03 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.652183 | 36.9302 | ETL.6050 | 40863484 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117908367 | Q2 | T2 DI MSS LNDNG-METCLF 12/59 RPR ANC FND | 44113810 | MOSS LANDING-METCALF | 012/059 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-09-23 | 2021-05-31 |  |  | 2021-05-21 | 2021-05-03 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.652183 | 36.9302 | ETL.6050 | 40863484 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117908447 | Not Scheduled | T2NT DI RND MT-CTNWD#3 41/345 PAINT STRS | 43755801 | ROUND MTN-COTTONWOOD #3 | 041/345 | ICQ | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-09-23 | 2021-09-23 | [6 empty] | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [6 empty] | '-122.078079 | 40.6246 | ETL.5650 | 40758852 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117908449 | Feb | T2 DI ROUND MTN-CTNWD #3 41/345 RPL INSS | 31454792 | ROUND MTN-COTTONWOOD #3 | 041/345 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-23 | 2020-09-23 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.078079 | 40.6246 | ETL.5650 | 40788172 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-07-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117908857 | Not Scheduled | T2 DIABLO-MESA 009/041 RPL INSS | 31479418 | DIABLO-MESA | 009/041 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-23 | 2021-05-31 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.7353612 | 35.2932 | ETL.4620 | 40623551 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117909233 | Mar | T2 HUMBOLDT-TRINITY 074/002 INS DAMW | 44311171 | HUMBOLDT-TRINITY | 074/002 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-09-23 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.417097 | 40.6994 | ETL.1820 | 44562663 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117911202 | Q2 | T2 DI CLAY-MARTEL 33/504 RPL POLE | 31461360 | CLAY-MARTEL | 033/504 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-23 | 2020-09-23 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.845788 | 38.4699 | ETL.8250 | 40912847 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-10-11 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117911238 | Feb | T3 DI KILARC-CEDAR CREEK 5/130 RPR STRW | 44406464 | KILARC-CEDAR CREEK | 005/130 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-23 | 2020-03-23 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.974468 | 40.7092 | ETL.7290 | 40759371 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-02-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117911339 | Q2 | T2NT DI PIT#1-COTTONWOOD 11/93 INST MRKS | 43879413 | PIT #1-COTTONWOOD | 011/093 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-09-23 | 2021-09-23 |  |  | 2021-05-31 | 2021-05-17 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.681045 | 40.8947 | ETL.5390 | 40657385 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-05-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117911403 | Mar | T2 HUMBOLDT-TRINITY 088/002 RPL ANCW | 31473759 | HUMBOLDT-TRINITY | 088/002 | 93E | E | Pre-2020_(2) High fire spread TD |  | 2019-09-24 | 2021-05-31 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.658695 | 40.7266 | ETL.1820 | 44562229 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  | 2020-05-27 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2020-05-27 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117911629 | Mar | T2 HUMBOLDT-TRINITY 074/002 INST DAMW | 44311171 | HUMBOLDT-TRINITY | 074/002 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-09-24 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.417097 | 40.6994 | ETL.1820 | 44562889 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117912010 | Mar | T2 HUMBOLDT-TRINITY 074/002 INST DAMW | 44311171 | HUMBOLDT-TRINITY | 074/002 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-09-24 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.417097 | 40.6994 | ETL.1820 | 44562664 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117912540 | Not Scheduled | T2 DIABLO-MESA 012/053 RPL INSS | 31479418 | DIABLO-MESA | 012/053 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-24 | 2021-05-31 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.7092547 | 35.2603 | ETL.4620 | 40679735 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2020-01-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117913029 | Not Scheduled | T2 DIABLO-MESA 013/058 RPL INSS | 31479418 | DIABLO-MESA | 013/058 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-24 | 2021-05-31 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.695995 | 35.2449 | ETL.4620 | 40895395 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2020-01-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117913057 | Not Scheduled | T2 DIABLO-MESA 012/057 RPL INSS | 31479418 | DIABLO-MESA | 012/057 | 93K | F | Pre-2020_(4) TD tag on high spread line |  | 2019-09-24 | 2024-09-24 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.6973473 | 35.2466 | ETL.4620 | 40835733 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2020-01-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117913118 | Not Scheduled | T2 DIABLO-MESA 013/059 RPL INSS | 31479418 | DIABLO-MESA | 013/059 | 93K | F | Pre-2020_(4) TD tag on high spread line |  | 2019-09-24 | 2024-09-24 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.6945523 | 35.2432 | ETL.4620 | 40885002 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2020-01-06 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117913245 | Not Scheduled | T2NT DI ELECTRA-BELLOTA 2/019 INST MRKS | 44631102 | ELECTRA-BELLOTA | 002/019 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-09-24 | 2021-09-24 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.687829 | 38.304 | ETL.4670 | 40811165 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117913696 | Not Scheduled | T2 DIABLO-MESA 013/061 RPL INSS | 31479418 | DIABLO-MESA | 013/061 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-24 | 2021-05-31 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.6870284 | 35.2368 | ETL.4620 | 40614927 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117913997 | Q2 | T3 DI SBNT-GRZL-CLMNT#1 04/041 RPR FOND | 43752388 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 004/041 | ICS | F | Pre-2020_(4) TD tag on high spread line |  | 2019-09-24 | 2022-09-24 |  |  | 2021-05-31 | 2021-05-24 |  |  | Likely MAT error - delink to correct | TR3 | LATE | Central | WSIP | [6 empty] | '-122.198441 | 37.8612 | ETL.3740 | 40764494 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-21 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117914044 | Not Scheduled | T3NT DI SBNT-GRZL-CLNT#1 04/041 REPAINT | 44586187 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 004/041 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-09-24 | 2023-09-24 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.198441 | 37.8612 | ETL.3740 | 40764494 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117917093 | Q2 | T2 DI MOSS LANDING-METCLF 12/61 RPR GYWS | 44190551 | MOSS LANDING-METCALF | 012/061 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-24 | 2021-05-31 |  |  | 2021-05-21 | 2021-05-03 |  |  | Tower guy | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.651656 | 36.9349 | ETL.6050 | 40597456 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  | Y - 6 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117917371 | Not Scheduled | T2 DI OLEUM-N-TWR-CHRST A03/24 RPR STRT | 43752227 | OLEUM-NORTH TOWER-CHRISTIE | A03/024 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-24 | 2020-09-24 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.203463 | 38.0271 | ETL.3180 | 40745842 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-01-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117917676 | Not Scheduled | T3 DI CARIBOU-PALERMO :35/283 BENT MEMB | 44069801 | CARIBOU-PALERMO | :035/283 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-24 | 2020-03-24 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.481438 | 39.7126 | ETL.3190 | 40656368 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117917740 | Q2 | T2 DI HT CRK #1 WSTWD 19/376 RPR STRW | 43904280 | HAT CREEK #1-WESTWOOD | 019/376 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-24 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.280287 | 40.7465 | ETL.7030 | 40601612 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2020-06-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117917819 | Not Scheduled | DI BRIONES TAP 001/026 WASH INSU |  | BRIONES TAP | 001/026 | ICD | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-24 | 2021-05-31 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-121.742222 | 37.9083 | ETL.7055 | 40850931 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-01-31 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117917906 | Q2 | T2 DI HT CRK #1-WSTWD 8/163 RPR GYWW | 43904280 | HAT CREEK #1-WESTWOOD | 008/163 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-25 | 2020-09-25 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.412648 | 40.8729 | ETL.7030 | 40868428 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117917941 | Mar | T2 DI KILARC-DESCHUTES 007/148 REGRADE | 43930440 | KILARC-DESCHUTES | 007/148 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-09-25 | 2022-09-25 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.964289 | 40.6073 | ETL.7300 | 40771289 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117918335 | Q2 | T2 DI MSS LNDING-LOS BNS 37/163 RPL GYWS | 44190496 | MOSS LANDING-LOS BANOS | 037/163 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-24 | 2021-05-31 |  |  | 2021-05-21 | 2021-05-03 |  |  | Tower guy | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.197632 | 36.9139 | ETL.6040 | 40658768 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  | Y - 8 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117918580 | Not Scheduled | T2 MORRO BAY-MESA 034/153 RPL INSS | 31479415 | MORRO BAY-MESA | 034/153 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-25 | 2020-09-25 | [7 empty] | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.4479419 | 35.0179 | ETL.5290 | 44330044 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-10-02 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117918682 | Not Scheduled | T2 DIABLO-MESA 034/152 RPL INSLS | 31479418 | DIABLO-MESA | 034/152 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-25 | 2021-05-31 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4483778 | 35.0202 | ETL.4620 | 40724300 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117918839 | Not Scheduled | T2 DIABLO-MESA 033/147 RPL INSS | 31479418 | DIABLO-MESA | 033/147 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-25 | 2021-05-31 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4550119 | 35.0309 | ETL.4620 | 40845445 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117918854 | Not Scheduled | T2 EI MORAGA-LAKEWOOD 011/082 INS HRDT |  | MORAGA-LAKEWOOD | 011/082 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-09-25 | 2021-05-31 | [7 empty] | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.143622 | 37.8606 | ETL.3741 | 44376928 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-04-03 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117918874 | Not Scheduled | T2 DI CHRISTIE-SOBRANTE 11/64 PNT STRS | 43751914 | CHRISTIE-SOBRANTE | 011/064 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-09-24 | 2021-09-24 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-122.194183 | 37.9814 | ETL.1260 | 40760658 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117918924 | Not Scheduled | T2 DI VALLEY SPRINGS #1 A000/013 RPR STR | 44290817 | VALLEY SPRINGS #1 | A000/013 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-24 | 2020-09-24 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.756422 | 38.2094 | ETL.8210 | 40911570 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-01-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117918929 | Not Scheduled | T2 DI VALLEY SPRINGS #1 001/030 RPR STRW | 44290818 | VALLEY SPRINGS #1 | 001/030 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-24 | 2020-09-24 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.787994 | 38.2053 | ETL.8210 | 40904197 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-01-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117918970 | Not Scheduled | T2 DIABLO-MESA 033/146 RPL INSS | 31479418 | DIABLO-MESA | 033/146 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-25 | 2021-05-31 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4567713 | 35.0333 | ETL.4620 | 40838488 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117919107 | Not Scheduled | T3NT EI ROCK CREEK-POE 012/085 PNT STRT | 44586178 | ROCK CREEK-POE | 012/085 | ICX | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-09-25 | 2021-09-25 | [6 empty] | Likely MAT error - delink to correct | TR3 |  | North Valley | WSIP | [6 empty] | '-121.457984 | 39.7724 | ETL.5630 | 40757655 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117919382 | Not Scheduled | T2 DIABLO-MESA 033/145 RPL INSS | 31479418 | DIABLO-MESA | 033/145 | 93K | F | Pre-2020_(4) TD tag on high spread line |  | 2019-09-25 | 2024-09-25 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4588826 | 35.0362 | ETL.4620 | 40781634 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117919687 | Q2 | T2 KERCKHOFF-CLVS-SNGR #1 0/7 RPL TOWER | 31473355 | KERCKHOFF-CLOVIS-SANGER #1 | 000/007 | 70S | F | Pre-2020_(4) TD tag on high spread line |  | 2019-09-25 | 2021-09-25 |  |  | 2021-04-15 | 2020-12-20 |  |  |  | TR2 |  | South | Non-WSIP | [6 empty] | '-119.565054 | 37.053 | ETL.1890 | 40806738 | Structure-Tower | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Fresno |  |  | Project | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117919732 | Not Scheduled | T2 DIABLO-MESA 022/098 RPL INSS | 31479418 | DIABLO-MESA | 022/098 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-25 | 2021-05-31 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.573342 | 35.1585 | ETL.4620 | 40899410 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117921552 | Not Scheduled | T2 DI OLEUM-MARTINEZ 004/033 RPL HRDs | 44326132 | OLEUM-MARTINEZ | 004/033 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-25 | 2020-09-25 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.17407 | 38.0147 | ETL.3170 | 40645947 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117921555 | Feb | T2 DI OLEUM-MARTINEZ 004/033 RPL INSS | 31457825 | OLEUM-MARTINEZ | 004/033 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-25 | 2020-09-25 |  |  | 2021-02-23 | 2021-02-23 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.17407 | 38.0147 | ETL.3170 | 40704788 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-03-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117921594 | Not Scheduled | T2 DI OLEUM-MARTINEZ 004/033 REPAINT | 44586167 | OLEUM-MARTINEZ | 004/033 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-09-25 | 2021-09-25 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-122.17407 | 38.0147 | ETL.3170 | 40645947 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117921598 | Not Scheduled | T2 DI CARIBOU-PALERMO 008/070 RPL INSS |  | CARIBOU-PALERMO | 008/070 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-25 | 2020-09-25 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.529001 | 39.5781 | ETL.3190 | 40634312 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117922191 | Mar | T2 DI NARROWS#1 TAP 0/9 RPL POLE | 31505367 | NARROWS #1 TAP | 000/009 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-25 | 2020-09-25 |  |  | 2021-03-02 | 2021-03-02 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.291809 | 39.2144 | ETL.6511 | 40757183 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-04-27 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117922910 | Q2 | EI VACA-PARKWAY 024/133 RPL SHLS | 44299272 | VACA-PARKWAY | 024/133 | ICS | E | Pre-2020_(2) High fire spread TD |  | 2019-09-25 | 2021-05-31 |  |  | 2021-06-04 | 2021-06-01 |  |  |  |  | LATE | North Coast | Non-WSIP |  |  |  |  | Field Operations | Cannot complete without Line support out of Lakeville | '-122.198202 | 38.1687 | ETL.5850 | 40783264 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q2 |  |  | 2020-05-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117925479 | Not Scheduled | T2 DI VALLEY SPRINGS #1 008/170 RPR STRW | 44292020 | VALLEY SPRINGS #1 | 008/170 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-27 | 2020-09-27 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.871035 | 38.1328 | ETL.8210 | 40908253 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-01-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117926336 | Not Scheduled | T3NT DI SOBRANTE-R-#1 1/12 REPAINT | 43727737 | SOBRANTE-R #1 | 001/012 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-09-26 | 2021-09-26 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.240263 | 37.908 | ETL.3770 | 40646639 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117926600 | Q3 | T2 DI TIDEWATER-SOBRANTE 22/105 RPR FOND |  | TIDEWATER-SOBRANTE | 022/105 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-26 | 2020-09-26 |  |  | 2021-07-30 | 2021-07-26 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.204163 | 37.912 | ETL.5770 | 40752591 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2 | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-14 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117926730 | Q2 | T3 DI SBT-GRZLY-CLRMNT#1 04/040 RPR FOND | 43752388 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 004/040 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-26 | 2021-05-31 |  |  | 2021-05-31 | 2021-05-24 |  |  | Likely MAT error - delink to correct | TR3 | LATE | Central | WSIP | [6 empty] | '-122.195233 | 37.8618 | ETL.3740 | 40761864 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-10-13 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117927234 | Feb | T3 KILARC-CEDAR CREEK 7/166 RPL POLE | 31473906 | KILARC-CEDAR CREEK | 007/166 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-27 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.99944 | 40.7185 | ETL.7290 | 40809931 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2020-02-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117927460 | Not Scheduled | T2 DIABLO-MESA 023/103 RPL INSS | 31479418 | DIABLO-MESA | 023/103 | 93K | F | Pre-2020_(4) TD tag on high spread line |  | 2019-09-27 | 2024-09-27 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.558845 | 35.1462 | ETL.4620 | 40691295 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117927463 | Not Scheduled | T2 DIABLO-MESA 023/104 RPL INSS | 31479418 | DIABLO-MESA | 023/104 | 93K | F | Pre-2020_(4) TD tag on high spread line |  | 2019-09-27 | 2024-09-27 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.5567449 | 35.1443 | ETL.4620 | 40797208 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-01 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117931109 | Feb | RND MTN-CTTNWD #3 035/304 RPL INSS | 31478747 | ROUND MTN-COTTONWOOD #3 | 035/304 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-21 | 2020-09-21 |  |  | 2021-02-19 | 2021-02-15 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.0215326 | 40.6925 | ETL.5650 | 40789061 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-07-14 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117931257 | Not Scheduled | T2NT DI STLS-MLNS-SS-MTC 17/110 REPAINT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 017/110 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-09-27 | 2021-09-27 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.636639 | 37.9913 | ETL.3830 | 40579611 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-12-31 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117931300 | Not Scheduled | T2 DI STNNLS-MNTCA #2 019/110 RPR STRT | 44460415 | STANISLAUS-MANTECA #2 | 019/110 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-27 | 2020-09-27 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-120.648263 | 37.9825 | ETL.3820 | 40579645 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 14 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117931431 | Not Scheduled | T2 PALERMO-COLGATE C003/016 RPL INSS | 31473816 | PALERMO-COLGATE | C003/016 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-30 | 2020-09-30 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.253743 | 39.3089 | ETL.5360 | 40847730 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-05-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117931610 | Not Scheduled | T2 EI LOS ESTROS-MTCALF 17/78 PAINT STRT | 43753289 | LOS ESTEROS-METCALF | 017/078 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-09-30 | 2021-09-30 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-121.82071 | 37.4494 | ETL.5353 | 40863120 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | SFWL | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117931678 | Mar | T2 PARADISE-BUTTE 4/46 RPL INSS | 31478630 | PARADISE-BUTTE | 004/046 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-30 | 2021-05-31 |  |  | 2021-03-19 | 2021-03-09 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.6569745 | 39.7258 | ETL.4396 | 41127313 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117931731 | Not Scheduled | T2 MORRO BAY-MESA 23/105 RPL INSS | 31479418 | DIABLO-MESA | 023/105 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-27 | 2021-05-31 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.5529869 | 35.1411 | ETL.4620 | 40792450 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117931736 | Not Scheduled | T2 DIABLO-MESA 24/106 RPL INSS | 31479418 | DIABLO-MESA | 024/106 | 93K | F | Pre-2020_(4) TD tag on high spread line |  | 2019-09-27 | 2024-09-27 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.5496043 | 35.1382 | ETL.4620 | 40838476 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117931737 | Not Scheduled | T3 DIABLO-MESA 25/109 RPL INSS | 31479418 | DIABLO-MESA | 025/109 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-27 | 2021-05-31 | [7 empty] | TR3 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.5378851 | 35.1278 | ETL.4620 | 40893972 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117931751 | Not Scheduled | EI COALINGA #1-SAN MIGUEL 16/2 PNT STRS | 44301011 | COALINGA #1-SAN MIGUEL | 016/002 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-09-27 | 2021-09-27 | [9 empty] | South | Non-WSIP | [6 empty] | '-120.54436 | 36.0065 | ETL.8580 | 40690794 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117931755 | Not Scheduled | EI VACA-PARKWAY 003/022 REPAINT STRS | 43978210 | VACA-PARKWAY | 003/022 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-09-27 | 2024-09-27 | [8 empty] | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.985702 | 38.4107 | ETL.5850 | 40681095 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117931756 | Not Scheduled | EI COALINGA #1-SAN MIGUEL 16/1 PNT STRS | 44301011 | COALINGA #1-SAN MIGUEL | 016/001 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-09-27 | 2021-09-27 | [9 empty] | South | Non-WSIP | [6 empty] | '-120.54101 | 36.0071 | ETL.8580 | 40597831 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117931843 | Not Scheduled | T3 DIABLO-MESA 26/113 RPL INSS | 31479418 | DIABLO-MESA | 026/113 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-30 | 2021-05-31 | [7 empty] | TR3 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.5236248 | 35.1156 | ETL.4620 | 40672027 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117931994 | Not Scheduled | T3 DIABLO-MESA 27/117 RPL INSS | 31479418 | DIABLO-MESA | 027/117 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-30 | 2021-05-31 | [7 empty] | TR3 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.512393 | 35.1059 | ETL.4620 | 40835745 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117932222 | Not Scheduled | T2 DI PTTSBRG-TESLA #1 008/038 RPL HRDT | 43753186 | PITTSBURG-TESLA #1 | 008/038 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-27 | 2020-09-27 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-121.846949 | 37.9365 | ETL.5510 | 40873706 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117932412 | Not Scheduled | T2 DIABLO-MESA 28/124 RPL INSS | 31479418 | DIABLO-MESA | 028/124 | 93K | F | Pre-2020_(4) TD tag on high spread line |  | 2019-09-30 | 2024-09-30 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4945118 | 35.0871 | ETL.4620 | 40782425 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117932548 | Not Scheduled | T2 DIABLO-MESA 29/128 RPL INSS | 31479418 | DIABLO-MESA | 029/128 | 93K | F | Pre-2020_(4) TD tag on high spread line |  | 2019-09-30 | 2024-09-30 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4877866 | 35.0759 | ETL.4620 | 40895401 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117932673 | Not Scheduled | DRUM PH #2 TAP 0/TERM1 RPR INSS | 43976856 | DRUM PH #2 TAP | 000/001C | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-09-30 | 2020-03-30 | [7 empty] | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.766333 | 39.2571 | ETL.6375 | 43196977 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117932908 | Mar | T2 DI HIGGINS-BELL 31/234 RPR INSS | 43978209 | HIGGINS-BELL | 031/234 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-30 | 2020-09-30 |  |  | 2021-03-17 | 2021-03-14 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.05851 | 38.9955 | ETL.1412 | 40899328 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117935388 | Not Scheduled | T2NT EI SOBRANTE-MRGA 00/01A RPR GYWS | 44621660 | SOBRANTE-MORAGA | 000/001A | ICS | F | Pre-2020_(5) TD tag on other lines |  | 2019-10-01 | 2021-10-01 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-122.162935 | 37.8489 | ETL.3742 | 40575706 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117935399 | Not Scheduled | T2 EI SOBRANTE-MORAGA 00/001A RPL ANCS | 31475815 | SOBRANTE-MORAGA | 000/001A | 93Z | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-01 | 2020-10-01 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.162935 | 37.8489 | ETL.3742 | 40575706 | Anchor-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-11-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117935776 | Mar | T2 EI MARTINEZ-SOBRANTE 5/32 RPL INSS | 31453033 | MARTINEZ-SOBRANTE | 005/032 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-27 | 2020-09-27 |  |  | 2021-03-30 | 2021-03-30 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.173567 | 38.0144 | ETL.2270 | 40704790 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - OM3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-03-10 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117937333 | Mar | T2 TEJON-LEBEC 11/196 RPL CONN | 44226977 | TEJON-LEBEC | 011/196 | ICM | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-01 | 2021-05-31 |  |  | 2021-03-07 | 2021-03-06 |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-118.888407 | 34.8715 | ETL.9250 | 40749552 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Midway |  | Y - 10 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-11-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117941074 | Q2 | LOS BANOS-MIDWAY #2 144/594 RPL INSS | 74008748 | LOS BANOS-MIDWAY #2 | 144/594 | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-01 | 2021-10-01 | 2021-05-11 | 2021-05-28 | 2021-05-28 | 2021-05-11 |  | DLFL once tag is confirmed complete PM |  |  | WECC | South | Non-WSIP | [6 empty] | '-119.45614 | 35.4056 | ETL.6010 | 40797042 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 26 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-15 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117941338 | Q2 | DI PIT#7 TAP 0/7L RPL STRW | 31501365 | PIT #7 TAP | 000/007 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-01 | 2020-10-01 |  |  | 2021-06-26 | 2021-06-23 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.980088 | 40.8407 | ETL.5442 | 44553612 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117941350 | Q2 | DI PIT#7 TAP 0/7R RPL STRW | 31501365 | PIT #7 TAP | 000/007 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-01 | 2020-10-01 |  |  | 2021-06-26 | 2021-06-23 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.980088 | 40.8407 | ETL.5442 | 44553592 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117941672 | Not Scheduled | DI SMARTVILLE-NICOLAS #1 20/410 RPR SPLW | 43983792 | SMARTVILLE-NICOLAUS #1 | 020/410 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-01 | 2020-10-01 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-121.428751 | 38.9554 | ETL.7990 | 40909207 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117942122 | Mar | T2 TEJON-LEBEC 12/204 RPL CONNECTORS | 44226979 | TEJON-LEBEC | 012/204 | ICM | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-02 | 2020-10-02 |  |  | 2021-03-07 | 2021-03-06 |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-118.886676 | 34.8684 | ETL.9250 | 40654747 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Midway |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-11-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117942163 | Not Scheduled | T3 DI DRM-GRSS VLY-WMR B017/387 RPR SPLW | 43983614 | DRUM-GRASS VALLEY-WEIMAR | B017/387 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-02 | 2020-04-02 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.965608 | 39.1333 | ETL.6760 | 40874781 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117942281 | Not Scheduled | T2 DI DBLO-MDWY #3 013/051 REMV DEBRIS |  | DIABLO-MIDWAY #3 | 013/051 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-10-02 | 2021-05-31 | [7 empty] | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.623079 | 35.1706 | ETL.5980 | 40593641 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117942438 | Not Scheduled | T2 DIABLO-MESA 028/121 RPL INSS | 31479418 | DIABLO-MESA | 028/121 | 93K | F | Pre-2020_(4) TD tag on high spread line |  | 2019-09-30 | 2024-09-30 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4992223 | 35.0937 | ETL.4620 | 40611915 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-10-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117942620 | Not Scheduled | T3 DI CARIBOU-PALERMO :036/293 RPR FOND | 44069455 | CARIBOU-PALERMO | :036/293 | ICQ | F | Pre-2020_(2) High fire spread TD |  | 2019-10-02 | 2021-10-02 | [7 empty] | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.484237 | 39.6955 | ETL.3190 | 40656370 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117943182 | Not Scheduled | PALERMO-WYANDOTTE 004/037 RPL INSS | 31478468 | PALERMO-WYANDOTTE | 004/037 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-09-06 | 2021-05-31 | [8 empty] | LATE | North Valley | Non-WSIP | [6 empty] | '-121.539795 | 39.5145 | ETL.4315 | 40841302 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117955088 | Q2 | LOS BANOS-MIDWAY #2 133/549 RPL INSS | 74008748 | LOS BANOS-MIDWAY #2 | 133/549 | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-02 | 2021-10-02 | 2021-05-11 | 2021-05-28 | 2021-05-28 | 2021-05-11 |  | DLFL once tag is confirmed complete PM |  |  | WECC | South | Non-WSIP | [6 empty] | '-119.562198 | 35.5358 | ETL.6010 | 40886169 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 26 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-15 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117955455 | Feb | T2 EI RIO DELL JCT-BRDGVL 25/13 RPL COND | 31475455 | RIO DELL JCT-BRIDGEVILLE | 025/013 | 93C | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-03 | 2020-01-24 | 2021-02-15 | 2021-02-27 | 2021-02-25 | 2021-02-25 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.987331 | 40.5108 | ETL.7850 | 40648543 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Eureka |  |  | 2019-12-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2019-12-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117955786 | Mar | T3 DIABLO-MIDWAY #2 026/107 RPR GYWS | 44571720 | DIABLO-MIDWAY #2 | 026/107 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-10-03 | 2021-05-31 |  |  | 2021-03-31 | 2021-03-03 |  |  | Tower guy | TR3 | LATE | South | Non-WSIP | [6 empty] | '-120.395742 | 35.1633 | ETL.5970 | 40818969 | Guy Wire-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 19 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  | 2019-10-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117955810 | Mar | T3 DIABLO-MIDWAY #3 026/106 RPR GYWS | 44571721 | DIABLO-MIDWAY #3 | 026/106 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-10-03 | 2020-04-03 |  |  | 2021-03-31 | 2021-03-03 |  |  | Tower guy | TR3 | LATE | South | Non-WSIP | [6 empty] | '-120.398713 | 35.1636 | ETL.5980 | 40818892 | Guy Wire-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 15 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Mar |  |  | 2019-10-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117956027 | Not Scheduled | T3NT DI TGR CRK-VLY SPRNGS 5/44 REPAINT | 43878409 | TIGER CREEK-VALLEY SPRINGS | 005/044 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-10-02 | 2021-10-02 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-120.58546 | 38.4234 | ETL.5790 | 40756083 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 11 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117956041 | Feb | T3 EI BRUNSWICK #1 TAP 000/003 RPL INSS | 31474523 | BRUNSWICK #1 TAP | 000/003 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-03 | 2020-04-03 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.008695 | 39.1443 | ETL.1422 | 40650072 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-01-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117956601 | Q2 | DI WASTONVILLE-SALINAS 5/76 RPL POLE | 31511435 | WATSONVILLE-SALINAS | 005/076 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-04-05 | 2020-04-05 | 2021-06-21 | 2021-06-22 | 2021-06-22 | 2021-06-21 |  |  |  |  | LATE | South | WSIP | [6 empty] | '-121.68963 | 36.8782 | ETL.8310 | 40645486 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2019-10-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117957244 | Feb | T2 DI RIO DELL JCT-BRDGVL 38/2 RPL PL(R) | 31475456 | RIO DELL JCT-BRIDGEVILLE | 038/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-03 | 2020-01-28 |  |  | 2021-02-27 | 2021-02-15 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.8216277 | 40.4691 | ETL.7850 | 44403585 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2019-12-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-12-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117957264 | Q2 | LOS BANOS-MIDWAY #2 123/507A RPL INSS | 74008748 | LOS BANOS-MIDWAY #2 | 123/507A | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-03 | 2021-10-03 | 2021-05-11 | 2021-05-28 | 2021-05-28 | 2021-05-11 |  | DLFL once tag is confirmed complete PM |  |  | WECC | South | Non-WSIP | [6 empty] | '-119.663856 | 35.6612 | ETL.6010 | 40578867 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 26 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-15 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117957426 | Q2 | T2 DI RND MTN-TBL MTN#2 73/299 INST GMKS | 44305720 | ROUND MTN-TABLE MTN #2 | 073/299 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-03 | 2021-10-03 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.759893 | 39.7628 | ETL.6070 | 40865419 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-03-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117959262 | Q2 | LOS BANOS-MIDWAY #2 111/460 RPL INSS | 31527048 | LOS BANOS-MIDWAY #2 | 111/460 | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-03 | 2021-10-03 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.781842 | 35.8061 | ETL.6010 | 40635851 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-11-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117959344 | Q2 | T2 EI BALCH-SANGER 012/065B RPR ANC FOND | 44589311 | BALCH-SANGER | 012/065B | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-10-04 | 2020-10-04 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.267889 | 36.8413 | ETL.1050 | 44191341 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 | USFS | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-23 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117959348 | Not Scheduled | LOS BANOS-MIDWAY#2 126/521 PNT STRS | 44284331 | LOS BANOS-MIDWAY #2 | 126/521 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-03 | 2023-10-03 | [8 empty] | WECC | South | Non-WSIP | [6 empty] | '-119.63008 | 35.62 | ETL.6010 | 40593354 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Midway |  | Y - 26 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117959461 | Q2 | LOS BANOS-MIDWAY#2 123/507B RPL INSS | 74008748 | LOS BANOS-MIDWAY #2 | 123/507B | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-03 | 2021-10-03 | 2021-05-11 | 2021-05-28 | 2021-05-28 | 2021-05-11 |  | DLFL once tag is confirmed complete PM |  |  | WECC | South | Non-WSIP | [6 empty] | '-119.663606 | 35.6613 | ETL.6010 | 41132665 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 26 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-11-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117959466 | Before Feb | LOS BANOS-GATES #1 027/115A CANCEL | 31527294 | LOS BANOS-GATES #1 | 027/115A | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-03 | 2021-10-03 | 2020-07-06 | 2020-08-19 | 2020-09-16 | 2020-08-01 |  | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.721685 | 36.748 | ETL.6000 | 40578881 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Before Feb |  |  | 2019-10-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117959652 | Before Feb | LOS BANOS-GATES #1 027/115B CANCEL | 31527294 | LOS BANOS-GATES #1 | 027/115B | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-03 | 2021-10-03 | 2020-07-06 | 2020-08-19 | 2020-09-16 | 2020-08-01 |  | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.721952 | 36.7478 | ETL.6000 | 40740401 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Before Feb |  |  | 2019-10-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117959854 | Q2 | T2 DI DUNLAP TAP 03/001 RPR FOND | 44301877 | DUNLAP TAP | 003/001 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-03 | 2020-10-03 |  |  | 2021-06-15 | 2021-06-02 |  |  | Likely MAT error - delink to correct | TR2 | LATE | South | WSIP | [6 empty] | '-119.213701 | 36.5965 | ETL.9061 | 44669787 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 543 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117960064 | Q2 | T2 DI WISHN-COPPERMINE 5/038 INST MRKS | 44278154 | WISHON-COPPERMINE | 005/038 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-03 | 2021-10-03 |  |  | 2021-06-15 | 2021-06-02 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.53096 | 37.077 | ETL.9330 | 40868036 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE crdy |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 12 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-10 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117960590 | Q2 | DI HT CRK #1 WSTWD 49/955 RPR STRW | 43904280 | HAT CREEK #1-WESTWOOD | 049/955 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-04 | 2020-10-04 |  |  | 2021-06-25 | 2021-05-03 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.015807 | 40.3816 | ETL.7030 | 40601694 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117961327 | Before Feb | LOS BANOS-GATES #1 033/141 CANCEL | 31527294 | LOS BANOS-GATES #1 | 033/141 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-10-04 | 2020-10-04 | 2020-07-06 | 2020-08-19 | 2020-08-19 | 2020-07-06 |  | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.67428 | 36.6618 | ETL.6000 | 40617621 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 16 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | No | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Before Feb |  |  | 2019-10-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117961341 | Not Scheduled | T3 DI GRIZZLY TAP 3/9L RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 003/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-04 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.321883 | 39.9052 | ETL.2395 | 44551401 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117961392 | Not Scheduled | T3 GRIZZLY TAP 003/009 RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 003/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-04 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.321883 | 39.9052 | ETL.2395 | 44551438 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117961396 | Not Scheduled | T3 GRIZZLY TAP 3/9 RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 003/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-04 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.321883 | 39.9052 | ETL.2395 | 44551468 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117961843 | Q2 | T2 EI BALCH-SANGER 007/045 INS ATCG | 31431430 | BALCH-SANGER | 007/045 | 93A | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-10-04 | 2021-10-04 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.187861 | 36.8774 | ETL.1050 | 40751518 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Fresno |  | Y - 16 | USFS | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-01-23 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117966587 | Q2 | T2 CRESTA-RIO OSO 008/067 RPL CONN | 43844645 | CRESTA-RIO OSO | 008/067 | ICM | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-02 | 2020-10-02 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.412336 | 39.8281 | ETL.4590 | 40815415 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117966680 | Q2 | T2 CRESTA-RIO OSO 008/071 RPL CONN | 43844645 | CRESTA-RIO OSO | 008/071 | ICM | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-02 | 2020-10-02 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.421164 | 39.8293 | ETL.4590 | 40591398 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117966783 | Q2 | T3 CRESTA-RIO OSO 014/117 RPL INSS | 31475914 | CRESTA-RIO OSO | 014/117 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-02 | 2021-05-31 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.478503 | 39.7336 | ETL.4590 | 40919877 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2020-02-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117966829 | Q2 | LOS BANOS-MIDWAY #2 108/449 RPL INSS | 31527048 | LOS BANOS-MIDWAY #2 | 108/449 | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-04 | 2021-10-04 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.813134 | 35.8413 | ETL.6010 | 40886153 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-11-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117967357 | Feb | T2 DI RIO DL JCT-BRDGVL 38/2 RPL POLE(L) | 31475456 | RIO DELL JCT-BRIDGEVILLE | 038/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-03 | 2020-10-03 |  |  | 2021-02-27 | 2021-02-15 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.7850 | 44403583 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-12-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-12-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117967410 | Feb | DI RIO DL JCT-BRDGVL 38/2 RPLC POLE(C) | 31475456 | RIO DELL JCT-BRIDGEVILLE | 038/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-03 | 2020-01-28 |  |  | 2021-02-27 | 2021-02-15 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.7850 | 44403584 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-12-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2019-12-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117969898 | Not Scheduled | EI DEL MONTE-FORT ORD #1 3/52 REPNT | 44585954 | DEL MONTE-FORT ORD #1 (NO FLY) | 003/052 | ICX | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-10-08 | 2021-10-08 | [6 empty] | Likely MAT error - delink to correct |  |  | South | Non-WSIP | [6 empty] | '-121.817637 | 36.6217 | ETL.8400 | 40754623 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Moss Landing |  | Y - 4 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117970378 | Q3 | T2 CARIBOU #2 :0/011 RPL POLE UNMAPPED | 31474479 | CARIBOU #2 | 000/011 | 70Y | F | Pre-2020_(4) TD tag on high spread line |  | 2019-08-27 | 2020-08-27 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.149185 | 40.0849 | ETL.6280 | 40600559 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-03-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117970897 | Not Scheduled | LOS BANOS-MIDWAY#2 7/34 ZENA GUARD | 43848355 | LOS BANOS-MIDWAY #2 | 007/034 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-08 | 2022-10-08 | [8 empty] | WECC | South | Non-WSIP | [6 empty] | '-120.954813 | 36.958 | ETL.6010 | 40753952 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-11-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117971048 | Q2 | LOS BANOS-MIDWAY#2 106/441 RPL INSS | 31527047 | LOS BANOS-MIDWAY #2 | 106/441 | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-08 | 2021-10-08 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.836638 | 35.8662 | ETL.6010 | 40619485 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117973505 | Q2 | LOS BANOS-GATES #1 036/150 RPR STRT | 44300852 | LOS BANOS-GATES #1 | 036/150 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-09-24 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.652417 | 36.6342 | ETL.6000 | 40600078 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117973641 | Q2 | LOS BANOS-MIDWAY #2 103/431 RPLC INSS |  | LOS BANOS-MIDWAY #2 | 103/431 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-10-08 | 2020-10-08 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.866001 | 35.8968 | ETL.6010 | 40612813 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-11-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117973838 | Feb | T2 DI RIO-DL JCT-BRDVL 27/5 RPR STRW | 43749702 | RIO DELL JCT-BRIDGEVILLE | 027/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-09 | 2020-10-09 |  |  | 2021-02-27 | 2021-02-15 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.982194 | 40.493 | ETL.7850 | 40750366 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-12-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2019-12-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117973867 | Not Scheduled | T3 DIABLO-MIDWAY #2 008/032 RPL INSS | 31487951 | DIABLO-MIDWAY #2 | 008/032 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-07 | 2020-04-07 | [7 empty] | TR3 | LATE | South | Non-WSIP | [6 empty] | '-120.6993804 | 35.2011 | ETL.5970 | 40726391 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 19 | CalTrans | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-02-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117973868 | Not Scheduled | T3 DIABLO-MIDWAY #2 009/033 RPL INSS | 31487951 | DIABLO-MIDWAY #2 | 009/033 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-07 | 2020-04-07 | [7 empty] | TR3 | LATE | South | Non-WSIP | [6 empty] | '-120.6933401 | 35.2006 | ETL.5970 | 40680766 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 19 | CalTrans | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-02-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117974030 | Not Scheduled | T2 EI TGR CRK-VLLY SPRGS 14/116 REPAINT | 43878409 | TIGER CREEK-VALLEY SPRINGS | 014/116 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-10-09 | 2021-10-09 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.669473 | 38.3207 | ETL.5790 | 40765241 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 11 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117974367 | Q2 | LOS BANOS-MIDWAY #2 102/425A RPLC INSS | 31527047 | LOS BANOS-MIDWAY #2 | 102/425A | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-08 | 2021-10-08 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.882252 | 35.9137 | ETL.6010 | 40578712 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117974402 | Q2 | LOS BANOS-MIDWAY #2 103/432 RPL INSS | 31527047 | LOS BANOS-MIDWAY #2 | 103/432 | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-08 | 2021-10-08 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.86307 | 35.8936 | ETL.6010 | 40715362 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117974403 | Q2 | LOS BANOS-MIDWAY #2 104/435 RPL INSS | 31527047 | LOS BANOS-MIDWAY #2 | 104/435 | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-08 | 2021-10-08 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.854424 | 35.8845 | ETL.6010 | 40795590 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117974405 | Q2 | LOS BANOS-MIDWAY #2 105/438 RPL INSS |  | LOS BANOS-MIDWAY #2 | 105/438 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-10-08 | 2020-10-08 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.845447 | 35.8752 | ETL.6010 | 40888001 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-11-19 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117974474 | Q2 | LOS BANOS-MIDWAY#2 99/415 RPL INSS | 31527048 | LOS BANOS-MIDWAY #2 | 099/415 | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-09 | 2021-10-09 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.910686 | 35.9442 | ETL.6010 | 40790433 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117974514 | Q2 | LOS BANOS-MIDWAY #2 107/446 RPLC INSS | 31527047 | LOS BANOS-MIDWAY #2 | 107/446 | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-08 | 2021-10-08 | 2021-06-01 | 2021-06-30 | 2021-06-30 | 2021-06-01 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.822384 | 35.8507 | ETL.6010 | 40839605 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-11-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117975285 | Q3 | T2 CARIBOU #2 002/108 REPLACE P | 31474479 | CARIBOU #2 | ;002/017 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-08-07 | 2021-05-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.95132 | 39.9959 | ETL.6280 | 44172015 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  | Yes |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2020-03-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117975289 | Before Feb | LOS BANOS-MIDWAY #2 064/268 CANCEL |  | LOS BANOS-GATES #1 | 064/268 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-10-09 | 2020-10-09 |  |  | 2020-08-19 | 2020-07-06 |  | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.315381 | 36.3318 | ETL.6000 | 40891892 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | No | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Before Feb |  |  | 2019-10-23 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117975441 | Not Scheduled | T2 DI CC-LAS POS 008/056 RPLC RPTS | 44609769 | CONTRA COSTA-LAS POSITAS | 008/056 | ICB | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-10-09 | 2021-10-09 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-121.73819 | 37.8905 | ETL.4510 | 40762775 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117975671 | Q2 | LOS BANOS-MIDWAY #2 045/188 RPR FOND | 44300848 | LOS BANOS-MIDWAY #2 | 045/188 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-09 | 2024-10-09 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.536008 | 36.54 | ETL.6010 | 40863976 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-11-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117975994 | Q3 | T2 CARIBOU #2 007/017 RPLC POLE | 31474479 | CARIBOU #2 | 007/017 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2019-08-15 | 2021-05-31 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Denied by GCC | 2021 - Per FLS, Bucks 1102 needs to be out to replace pole. 230kv needs to be out | '-121.223427 | 40.0161 | ETL.6280 | 40815734 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2020-02-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 117984295 | Not Scheduled | LOS BANOS-MIDWAY #2 011/051 RPL INSS | 31527048 | LOS BANOS-MIDWAY #2 | 011/051 | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-09 | 2021-10-09 | [8 empty] | WECC | South | Non-WSIP | [6 empty] | '-120.909839 | 36.9054 | ETL.6010 | 40612775 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - LBG17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-10-23 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117984326 | Q2 | T2 DI PIT#1-COTTONWOOD 4/42 RMV NEST | 43879413 | PIT #1-COTTONWOOD | 004/042 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-09 | 2020-10-09 |  |  | 2021-05-31 | 2021-05-17 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5736 | 40.949 | ETL.5390 | 40677448 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-02-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117984626 | Q2 | T3 CRESTA-RIO OSO 017/145 RPL INSS | 31475914 | CRESTA-RIO OSO | 017/145 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-03 | 2021-05-31 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.496592 | 39.6722 | ETL.4590 | 40919899 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2020-02-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117984690 | Mar | T2 DIABLO-MIDWAY #2 038/156 RPL INSS | 31487951 | DIABLO-MIDWAY #2 | 038/156 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-10 | 2020-10-10 | 2021-03-08 | 2021-03-10 | 2021-03-10 | 2021-03-08 |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.1832063 | 35.1851 | ETL.5970 | 40839495 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 19 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2019-12-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117985082 | Q2 | T3 DRUM-HIGGINS 001/023L RPL LDSP | 31509929 | DRUM-HIGGINS | 001/023 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-10 | 2020-04-10 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.787451 | 39.2317 | ETL.4393 | 44172117 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-04-07 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117985729 | Not Scheduled | LOS BANOS-MIDWAY#2 023/101 PAINT STRS | 44301828 | LOS BANOS-MIDWAY #2 | 023/101 | ICS | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-09 | 2021-10-09 | [8 empty] | WECC | South | Non-WSIP | [6 empty] | '-120.770143 | 36.7779 | ETL.6010 | 40587740 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117986529 | Not Scheduled | T2 CARIBOU-TABLE MTN 20/139A INS ATCG | 31462236 | CARIBOU-TABLE MTN | 020/139A | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-10 | 2021-10-10 | [7 empty] | TR2 |  | North Valley | Non-WSIP | [6 empty] | '-121.27706 | 39.9655 | ETL.4440 | 40867202 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-05-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117991656 | Not Scheduled | T2 EI TULUCAY-NAPA #1 008/011 RPL POL | 31475457 | TULUCAY-NAPA #1 | 008/011 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-04 | 2020-10-04 | 2020-09-28 | 2020-10-01 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.227287 | 38.2806 | ETL.8180 | 40602331 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-03-30 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117992852 | Q2 | T2 HUMBOLDT-BRIDGEVILLE 114/003 RPR INSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 114/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-12 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0860955 | 40.7753 | ETL.1810 | 44378065 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117992944 | Feb | T2 EI PITTSB-KRKR-COL STL 4/24 RPR INSS | 44379346 | PITTSBRG-KIRKER-COLUMBIA STEEL | 004/024 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-05-21 | 2020-10-12 |  |  | 2021-02-17 | 2021-02-17 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.884568 | 37.9878 | ETL.3310 | 44705831 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-04-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117992963 | Q2 | T2 HUMBOLDT-BRIDGEVILLE 113/002 RPR INSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 113/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-12 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0651527 | 40.7677 | ETL.1810 | 43691653 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117992966 | Q2 | T2 HUMBOLDT-BRIDGEVILLE 113/000 RPL INSW | 44107184 | HUMBOLDT-BRIDGEVILLE | 113/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-12 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0627207 | 40.7658 | ETL.1810 | 43691652 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117992995 | Q2 | T2 HUMBOLDT-BRIDGEVILLE 112/006 RPR INSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 112/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-12 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.056485 | 40.7627 | ETL.1810 | 44322688 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117993030 | Q2 | T2 HUMBOLDT-BRIDGEVILLE 112/001 RPR INSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 112/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-12 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0478205 | 40.7611 | ETL.1810 | 43691647 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117993773 | Feb | T2 EI ROCK CREEK-POE 010/074 INST MRKS |  | ROCK CREEK-POE | 010/074 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-12 | 2021-10-12 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.45337 | 39.7977 | ETL.5630 | 40762731 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117995154 | Q2 | LOS BANOS-MIDWAY #2 028/122 RPR GYWS | 44301006 | LOS BANOS-MIDWAY #2 | 028/122 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-10-14 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  | Tower guy |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.709873 | 36.7281 | ETL.6010 | 40664769 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 117995204 | Q2 | T2 HUMBOLDT-BRIDGEVILLE 111/3 RPR STRW | 43749687 | HUMBOLDT-BRIDGEVILLE | 111/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-14 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0323913 | 40.7609 | ETL.1810 | 44322664 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117995207 | Q2 | T2 HUMBLDT-BRIDGVLLE 110/8 RPR INSS | 44228080 | HUMBOLDT-BRIDGEVILLE | 110/008 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-14 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0243664 | 40.7609 | ETL.1810 | 43691645 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117995285 | Q2 | T2 HUMBOLDT-BRIDGEVILLE 110/7 RPR INSS | 44208366 | HUMBOLDT-BRIDGEVILLE | 110/007 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-14 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0220046 | 40.7609 | ETL.1810 | 43691644 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117995801 | Q2 | T2 HUMBOLDT-BRIDGEVILLE 110/3 RPR INSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 110/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-14 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0137893 | 40.7607 | ETL.1810 | 43691640 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117995861 | Q2 | T2 HMBLDT-BRIDGEVILLE 109/8 RPR INSW | 43749687 | HUMBOLDT-BRIDGEVILLE | 109/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-14 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0035206 | 40.7586 | ETL.1810 | 43691639 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117996513 | Q2 | T2 HUMBOLDT-BRIDGEVILLE 108/5 RPR INSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 108/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-14 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.982845 | 40.7519 | ETL.1810 | 40802245 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117997183 | Q2 | T3 DRUM-HIGGINS 001/023R RPL POLE | 31509929 | DRUM-HIGGINS | 001/023 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-10 | 2020-04-10 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.787451 | 39.2317 | ETL.4393 | 44172118 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-04-07 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117997580 | Q2 | T2 CRESTA-RIO OSO 28/231 rpl inss | 31475914 | CRESTA-RIO OSO | 028/231 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-14 | 2021-05-31 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.533148 | 39.5647 | ETL.4590 | 41140701 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2020-02-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 117997882 | Not Scheduled | COLLINS PINE TAP 000/005 STUB POLE | 44155694 | COLLINS PINE TAP | 000/005 | GAR | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-06-29 | 2020-06-29 | [8 empty] | LATE | North Valley | Non-WSIP | [6 empty] | '-121.228734 | 40.3014 | ETL.7001 | 42623453 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 586 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118000753 | Q2 | HUMBOLDT-BRIDGEVILLE 095/005 RMV DEBRIS | 43749687 | HUMBOLDT-BRIDGEVILLE | 095/005 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-10-13 | 2020-10-13 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322361 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118000754 | Q2 | HUMBOLDT-BRIDGEVILLE 095/001 RMV DEBRIS | 43749687 | HUMBOLDT-BRIDGEVILLE | 095/001 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-10-13 | 2020-10-13 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322348 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118000755 | Q2 | HUMBOLDT-BRIDGEVILLE 095/000 RMV DEBRIS | 43749687 | HUMBOLDT-BRIDGEVILLE | 095/000 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-10-13 | 2024-10-13 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.854368 | 40.5948 | ETL.1810 | 44322344 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118003309 | Q2 | HUMBOLDT-BRIDGEVILLE 089/000 RMV DEBRIS | 43749687 | HUMBOLDT-BRIDGEVILLE | 089/000 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-10-15 | 2020-10-15 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322253 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118004148 | Q2 | HUMBOLDT-BRIDGEVILLE 090/002 RMV DEBRIS | 43749687 | HUMBOLDT-BRIDGEVILLE | 090/002 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-10-15 | 2020-10-15 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322276 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118005746 | Q2 | HUMBOLDT-BRIDGEVILLE 091/003 RMV DEBRIS | 43749687 | HUMBOLDT-BRIDGEVILLE | 091/003 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-10-15 | 2020-10-15 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322300 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118008063 | Not Scheduled | DI CARIBOU #2 ;005/016 CANCEL | 31475564 | CARIBOU #2 | ;005/016 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-15 | 2020-10-15 | [6 empty] | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.954754 | 39.9577 | ETL.6280 | 40813525 | Structure-Wood | No Good/Out of Stdrd | Replace | MAPP srdy | MAPP | Constructed and mapped | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | 70 | Not Scheduled |  |  | 2020-03-12 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118008456 | Q2 | LOS BANOS-MIDWAY #2 054/231A RPL INSS | 31527141 | LOS BANOS-MIDWAY #2 | 054/231A | 93K | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-15 | 2021-10-15 | 2021-05-11 | 2021-05-28 | 2021-05-28 | 2021-05-11 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.420863 | 36.4355 | ETL.6010 | 40578217 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-11-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118008458 | Q2 | LOS BANOS-MIDWAY #2 054/231B RPL INSS | 31527041 | LOS BANOS-MIDWAY #2 | 054/231B | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-10-15 | 2021-07-16 | 2021-05-11 | 2021-05-28 | 2021-05-28 | 2021-05-11 |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.421441 | 36.4352 | ETL.6010 | 40741133 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-11-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118008703 | Mar | MARTIN-MILLBRAE#1 1/15 RPR BENT MEMBERS | 44273546 | MARTIN-MILLBRAE #1 | 001/015 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-14 | 2021-05-31 |  |  | 2021-03-13 | 2021-03-08 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.40837 | 37.6771 | ETL.2230 | 40755337 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 1 | SMCPD | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | IC | Mar |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118009204 | Q2 | SAN MATEO-MARTIN#3 9/74 RPR FOND | 44483397 | SAN MATEO-MARTIN #3 | 009/074 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-14 | 2020-10-14 |  |  | 2021-04-24 | 2021-04-19 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.408463 | 37.6767 | ETL.3580 | 40755309 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 | SMCPD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  |  | Not Released | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118010598 | Q2 | T2 HUMBOLDT-BRIDGEVILL 112/004R RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 112/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-07-11 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.1810 | 44322683 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118010697 | Q2 | T2 HUMBOLDT-BRIDGLE 111/005R RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 111/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-16 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.1810 | 44322670 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118010755 | Not Scheduled | LOS BANOS-GATES#1 69/290 RPL INSS |  | LOS BANOS-GATES #1 | 069/290 | 93K | E | Pre-2020_(1b) Lines with special commitments |  | 2019-10-15 | 2020-10-15 | [5 empty] | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.254091 | 36.2788 | ETL.6000 | 40633994 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-10-24 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118011030 | Q2 | LOS BANOS-MIDWAY#2 48/201 RPL HRDT | 44300848 | LOS BANOS-MIDWAY #2 | 048/201 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-10-15 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.498212 | 36.5121 | ETL.6010 | 40587751 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-11-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118011326 | Q2 | HUMBOLDT-BRIDGEVILLE 110/8 PAINT CRSM | 44107184 | HUMBOLDT-BRIDGEVILLE | 110/008 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-15 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.024353 | 40.7609 | ETL.1810 | 44322650 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118011415 | Q2 | EI HUMBOLDT-BRIDGEVILLE 112/006 PNT STRW | 44107184 | HUMBOLDT-BRIDGEVILLE | 112/006 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-15 | 2020-10-15 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322689 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118011416 | Q2 | HUMBOLDT-BRIDGEVILLE 110/7 PAINT STRS | 44208367 | HUMBOLDT-BRIDGEVILLE | 110/007 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-15 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.021991 | 40.7609 | ETL.1810 | 44322647 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118011419 | Q2 | HUMBOLDT-BRIDGEVILLE 112/001 PNT CRSAM | 44107184 | HUMBOLDT-BRIDGEVILLE | 112/001 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-15 | 2020-10-15 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322672 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118011453 | Q2 | HUMBOLDT-BRIDGEVILLE 88/001 PAINT STRS | 44208367 | HUMBOLDT-BRIDGEVILLE | 088/001 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-10-15 | 2020-10-15 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-123.811986 | 40.5032 | ETL.1810 | 44322238 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118011457 | Q2 | HUMBOLDT-BRIDGEVILLE 113/000 PNT STR | 44107184 | HUMBOLDT-BRIDGEVILLE | 113/000 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-15 | 2020-10-15 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322701 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118011561 | Q2 | HUMBOLDT-BRIDGEVILLE 115/001 PNT STRS | 44311169 | HUMBOLDT-BRIDGEVILLE | 115/001 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-10-12 | 2020-10-12 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-124.09794 | 40.7788 | ETL.1810 | 43691598 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118011564 | Q2 | HUMBOLDT-BRIDGEVILLE 113/002 PNT STRS | 44107184 | HUMBOLDT-BRIDGEVILLE | 113/002 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-15 | 2020-10-15 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322709 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118014089 | Feb | T2 EI PITTSBURG-CLMBIA STL 4/24 RPR INSS | 44379347 | PITTSBURG-COLUMBIA STEEL | 004/024 | ICS | E | Pre-2020_(5) TD tag on other lines |  | 2019-10-16 | 2020-10-16 |  |  | 2021-02-17 | 2021-02-17 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.884568 | 37.9878 | ETL.3300 | 44761258 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-04-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118016814 | Feb | GLENN #5 005/112 RPL POLE | 31475727 | GLENN #5 | 005/112 | 70Y | B | Pre-2020_(0) A and B Tags |  | 2019-10-17 | 2021-03-14 |  |  | 2021-02-19 | 2021-02-18 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.197462 | 39.7421 | ETL.8427 | 40738645 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2021-02-08 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 118017378 | Q2 | T2 BUTTE VALLEY-CARIBOU 7/053A RPL L PL | 31479584 | BUTT VALLEY-CARIBOU | 007/053A | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-17 | 2020-10-17 |  |  | 2021-06-11 | 2021-06-08 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [8 empty] | ETL.1180 | 44399493 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | In Review | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118026607 | Not Scheduled | T2 TULUCAY-NAPA #1 007/005 RPR POLE | 44310753 | TULUCAY-NAPA #1 | 007/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-19 | 2020-10-19 | 2020-09-28 | 2020-10-01 | [5 empty] | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.206774 | 38.268 | ETL.8180 | 40751173 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118057983 | Q2 | HUMBOLDT-BRIDGEVILLE 107/002 RPR WP HOLE | 43749687 | HUMBOLDT-BRIDGEVILLE | 107/002 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-21 | 2020-10-21 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322575 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118057985 | Q2 | HUMBOLDT-BRIDGEVILLE 107/002 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 107/002 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-21 | 2020-10-21 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322575 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118057992 | Q2 | HUMBOLDT-BRIDGEVILLE 107/002 RPL HRDD | 43749687 | HUMBOLDT-BRIDGEVILLE | 107/002 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-21 | 2020-10-21 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322576 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118058011 | Q2 | HUMBOLDT-BRIDGEVILLE 107/002 RPL INSW | 31498302 | HUMBOLDT-BRIDGEVILLE | 107/002 | 93I | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-21 | 2020-10-21 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.964884 | 40.7452 | ETL.1810 | 40720047 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118058083 | Q2 | HUMBOLDT-BRIDGEVILLE 107/001R RPL POLE | 31404623 | HUMBOLDT-BRIDGEVILLE | 107/001 | 70Y | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-21 | 2020-10-21 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322573 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118058602 | Q2 | HUMBOLDT-BRIDGEVILLE 105/002 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 105/002 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-21 | 2020-10-21 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322544 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118060048 | Q2 | HUMBOLDT-BRIDGEVILLE 096/004 RMV DEBRIS | 44378879 | HUMBOLDT-BRIDGEVILLE | 096/004 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-10-21 | 2020-10-21 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.863309 | 40.6183 | ETL.1810 | 44324153 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118060261 | Q2 | HUMBOLDT-BRIDGEVILLE 096/003 RMV DEBRIS | 44378879 | HUMBOLDT-BRIDGEVILLE | 096/003 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-10-21 | 2020-10-21 |  |  | 2021-05-22 | 2021-05-03 |  |  | Likely MAT error - delink to correct |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.861664 | 40.6165 | ETL.1810 | 44324147 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118060521 | Q2 | HUMBOLDT-BRIDGEVILLE 98/1L REPL POLE |  | HUMBOLDT-BRIDGEVILLE | 098/001 | 70Y | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-21 | 2020-10-21 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322385 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-01-16 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118069310 | Not Scheduled | CLAY MARTEL 31/12 RPR SWITCH | 44073627 | CLAY-MARTEL | 031/012 | ICE | E | Pre-2020_(9a) Other ignition related |  | 2019-10-22 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-120.845487 | 38.4828 | ETL.8250 | 40744160 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Victor |  | Y - 39 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2019-10-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118069451 | Q2 | T2 DI COLGATE-PALERMO 022/440 RPR STRW | 43728969 | COLGATE-PALERMO | 022/440 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-22 | 2020-10-22 |  |  | 2021-05-22 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.516851 | 39.458 | ETL.6500 | 40692851 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-02-05 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118069464 | Q2 | LOS BANOS-GATES #1 80/339 RPR GYWS | 43848347 | LOS BANOS-GATES #1 | 080/338A | ICS | E | Pre-2020_(1b) Lines with special commitments | Director approved | 2019-10-22 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  | Tower guy |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.129484 | 36.1454 | ETL.6000 | 40576536 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | CLSD | CLSD | Closed | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-31 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118075840 | Q2 | LOS BANOS-GATES #1 79/332 RPR STRT | 44300852 | LOS BANOS-GATES #1 | 079/332 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-10-22 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.14335 | 36.1637 | ETL.6000 | 40673627 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118083452 | Q2 | HUMBOLDT-BRIDGEVILLE 105/2 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 105/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-22 | 2020-10-22 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322546 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118084193 | Q2 | HUMBOLDT-BRIDGEVILLE 98/1C REPL POLE |  | HUMBOLDT-BRIDGEVILLE | 098/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-22 | 2020-10-22 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322386 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-01-16 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118084195 | Q2 | HUMBOLDT-BRIDGEVILLE 98/1R REPL POLE |  | HUMBOLDT-BRIDGEVILLE | 098/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-22 | 2020-10-22 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322387 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-01-16 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118084196 | Q2 | HUMBOLDT-BRIDGEVILLE 105/002 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 105/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-22 | 2020-10-22 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322545 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118084407 | Q2 | T2 EI FORT BRAGG-ELK 13/8 RPL COND | 31482836 | FORT BRAGG-ELK | 013/008 | 93C | E | Pre-2020_(5) TD tag on other lines |  | 2019-01-22 | 2021-05-31 |  |  | 2021-05-04 | 2021-05-04 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.78927 | 39.3052 | ETL.2060 | 40860782 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2020-01-09 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118084828 | Q2 | HUMBOLDT-BRIDGEVILLE 107/2 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 107/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-22 | 2020-10-22 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322576 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118084829 | Q2 | HUMBOLDT-BRIDGEVILLE 107/2 RPR WP HOLE | 43749687 | HUMBOLDT-BRIDGEVILLE | 107/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-22 | 2020-10-22 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322577 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118085072 | Q2 | HUMBOLDT-BRIDGEVILLE 108/005 PNT STRS | 44107184 | HUMBOLDT-BRIDGEVILLE | 108/005 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-15 | 2025-10-15 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.982845 | 40.7519 | ETL.1810 | 44324318 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118085073 | Q2 | HUMBOLDT-BRIDGEVILLE 109/008 PNT CRSM | 44107184 | HUMBOLDT-BRIDGEVILLE | 109/008 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-15 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.003507 | 40.7586 | ETL.1810 | 44322623 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118085074 | Q2 | HUMBOLDT-BRIDGEVILLE 110/003 PNT CRSM | 44107184 | HUMBOLDT-BRIDGEVILLE | 110/003 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-15 | 2021-05-31 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.013775 | 40.7607 | ETL.1810 | 44322635 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118085664 | Q2 | HUMBOLDT-BRIDGEVILLE 099/008 RMV DEBRIS | 43749687 | HUMBOLDT-BRIDGEVILLE | 099/008 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-10-22 | 2020-10-22 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322429 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118085859 | Q2 | HMBLDT-BRDGVL 107/002 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 107/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-22 | 2020-10-22 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322577 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118085991 | Not Scheduled | LOS BANOS-GATES #1 77/326 RPR INSS | 44301827 | LOS BANOS-GATES #1 | 077/326 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | 2019-10-22 | 2020-10-22 | [5 empty] | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.158573 | 36.1815 | ETL.6000 | 40820405 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118086072 | Q2 | HUMBOLDT-BRIDGEVILLE 107/001C RPL POLE | 31404623 | HUMBOLDT-BRIDGEVILLE | 107/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-22 | 2020-10-22 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322572 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118086075 | Q2 | HUMBOLDT-BRIDGEVILLE 107/002 RPR WP HOLE | 43749687 | HUMBOLDT-BRIDGEVILLE | 107/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-22 | 2020-10-22 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322576 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118090554 | Q2 | LOS BANOS-GATES #1 75/317 RPR STRT | 44300852 | LOS BANOS-GATES #1 | 075/317 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-23 | 2022-10-23 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.179424 | 36.2074 | ETL.6000 | 40817423 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-10-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118090993 | Q2 | HUMBOLDT-BRIDGEVILL 100/003L RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 100/003 | 70Y | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-23 | 2020-10-23 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322441 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118092122 | Q3 | T2 WISHON-COPPERMINE 07/056 REGRADE | 44300844 | WISHON-COPPERMINE | 007/056 | ICQ | E | Pre-2020_(9a) Other ignition related |  | 2019-10-23 | 2021-05-31 |  |  | 2021-08-15 | 2021-07-02 |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.55012 | 37.047 | ETL.9330 | 40816710 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 12 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | IC | Q3 |  |  | 2020-01-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118092358 | Q2 | HUMBOLDT-BRIDGEVILLE 102/001L RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 102/001 | 70Y | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-23 | 2020-10-23 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322484 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118092846 | Not Scheduled | T2NT ARCO-PLNIO PSS PP 15/256 RMV DBRIS | 44609889 | ARCO-POLONIO PASS PP | 015/256 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-10-23 | 2021-10-23 | [7 empty] | TR2 |  | South | Non-WSIP | [6 empty] | '-120.113399 | 35.7083 | ETL.8450 | 41148788 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-12-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118098389 | Not Scheduled | T3 EI MDL FRK-GOLD HILL 33/241 PNT STRS | 44082912 | MIDDLE FORK-GOLD HILL | 033/241 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-24 | 2021-05-31 | [8 empty] | LATE | North Valley | WSIP | [6 empty] | '-120.995025 | 38.7311 | ETL.5140 | 44377466 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118098415 | Q2 | HMBLDT-BRDGVL 102/001R RPL STRW | 31497841 | HUMBOLDT-BRIDGEVILLE | 102/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-23 | 2020-10-23 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322485 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118098461 | Q2 | HMBLDT-BRDGVL 100/003R RPLC STRW | 31497841 | HUMBOLDT-BRIDGEVILLE | 100/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-23 | 2020-10-23 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322443 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118098464 | Q2 | HMBLDT-BRDGVL 100/003C RPLC STRW | 31497841 | HUMBOLDT-BRIDGEVILLE | 100/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-23 | 2020-10-23 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322442 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118104065 | Q2 | HMBLDT-BRDGVILLE 114/003 PAINT CRSARM | 44107184 | HUMBOLDT-BRIDGEVILLE | 114/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-25 | 2025-10-25 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.1810 | 44322742 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118104377 | Feb | T2 COALINGA #1-SAN MIGUEL 22/1 RPR STRT | 44140483 | COALINGA #1-SAN MIGUEL | 022/001 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-25 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-15 |  |  | Likely MAT error - delink to correct | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.63573 | 35.9682 | ETL.8580 | 40597797 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 15 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2019-10-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118106502 | Q2 | T2 CHRISTIE-WILLOW PASS 3/37 INS DAMW | 44221598 | CHRISTIE-WILLOW PASS | 003/037 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-10-25 | 2021-05-31 |  |  | 2021-04-10 | 2021-04-09 |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.156699 | 38.0185 | ETL.6370 | 40825343 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  | CSRS | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118106551 | Q2 | T2 CHRISTIE-WILLOW PASS 2/029 INS DAMW | 44221598 | CHRISTIE-WILLOW PASS | 002/029 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-10-25 | 2021-05-31 |  |  | 2021-04-10 | 2021-04-09 |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.163387 | 38.0206 | ETL.6370 | 40599510 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  | CSRS | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118106651 | Not Scheduled | T2 HASS-MCCALL 014/080 INST INSS | 31480611 | HAAS-MCCALL | 014/080 | 93K | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-25 | 2021-05-31 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.2495056 | 36.8627 | ETL.4850 | 40633389 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  |  |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2020-03-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118107045 | Not Scheduled | T2 CAYUCOS-CAMBRIA 11/073 INSTL DAMW | 43753055 | CAYUCOS-CAMBRIA | 011/073 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-10-25 | 2020-10-25 | [7 empty] | TR2 | LATE | South | Non-WSIP | [6 empty] | '-121.015154 | 35.5451 | ETL.8560 | 40754943 | Damper-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118107112 | Not Scheduled | T2 CAYUCOS-CAMBRIA 12/082 INSTL DAMW | 43753055 | CAYUCOS-CAMBRIA | 012/082 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-10-25 | 2020-10-25 | [7 empty] | TR2 | LATE | South | Non-WSIP | [6 empty] | '-121.031851 | 35.5562 | ETL.8560 | 40812347 | Damper-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-10-30 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118115376 | Q2 | LOS BANOS-GATES #1 055/234 INST ACG | 31480609 | LOS BANOS-GATES #1 | 055/234 | 93A | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-28 | 2021-10-28 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.415851 | 36.4288 | ETL.6000 | 40757937 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-11-07 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118116425 | Q2 | LOS BANOS-GATES #1 054/229 INST HRDT | 44300852 | LOS BANOS-GATES #1 | 054/229 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-10-28 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.427434 | 36.4416 | ETL.6000 | 40866820 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-11-07 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118117045 | Not Scheduled | T2 BRIDGEVILLE-COTTONWOO 13/124A STUB P | 44143774 | BRIDGEVILLE-COTTONWOOD | 013/124 | GAR | E | Pre-2020_(4) TD tag on high spread line |  | 2019-05-15 | 2020-05-15 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-122.520412 | 40.3946 | ETL.1110 | 44424060 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 586 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  | 2020-01-27 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118118571 | Mar | CNTRVLLE-TBLE MTN-ORVLLE 9/190 RPL PL | 31478313 | CENTERVILLE-TABLE MTN-OROVILLE | 009/190 | 70Y | F | Pre-2020_(5) TD tag on other lines |  | 2019-09-17 | 2021-09-17 |  |  | 2021-03-05 | 2021-03-05 | [5 empty] | North Valley | Non-WSIP | [6 empty] | '-121.635677 | 39.6535 | ETL.6330 | 40758836 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-02-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118118847 | Not Scheduled | TRACY-LOS BANOS 50/227 INST RPTS | 44651145 | TRACY-LOS BANOS | 050/227 | ICB | E | Pre-2020_(9a) Other ignition related |  | 2019-10-25 | 2021-05-31 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-121.106254 | 37.2127 | ETL.6130 | 40811400 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-01-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118118890 | Not Scheduled | TRACY-LOS BANOS 42/191 INST RPTS | 44651144 | TRACY-LOS BANOS | 042/191 | ICB | F | Pre-2020_(9a) Other ignition related |  | 2019-10-25 | 2022-10-25 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-121.145839 | 37.3314 | ETL.6130 | 40587649 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-01-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118118891 | Not Scheduled | TRACY-LOS BANOS 38/178 INST RPTS | 44651143 | TRACY-LOS BANOS | 038/178 | ICB | E | Pre-2020_(9a) Other ignition related |  | 2019-10-25 | 2021-05-31 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-121.162545 | 37.3813 | ETL.6130 | 40863863 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-01-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118119027 | Not Scheduled | TRACY-LOS BANOS 021/103 INST RPTS | 44651141 | TRACY-LOS BANOS | 021/103 | ICB | E | Pre-2020_(9a) Other ignition related |  | 2019-10-25 | 2021-05-31 | [8 empty] | LATE | Central | WSIP | FSRP | [5 empty] | '-121.333564 | 37.5775 | ETL.6130 | 40662852 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-01-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118123322 | Not Scheduled | DRM-GRSS VLLY-WIMR B16/361 INS GMKW | 44090176 | DRUM-GRASS VALLEY-WEIMAR | B016/361 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-10-30 | 2021-10-30 | [9 empty] | North Valley | Non-WSIP | [6 empty] | '-120.955831 | 39.118 | ETL.6760 | 40822707 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-02-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118124179 | Mar | HUMBOLDT-TRINITY 076/000LFT RPL POLE | 31497850 | HUMBOLDT-TRINITY | 076/000 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2018-10-19 | 2021-05-31 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  |  | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.442836 | 40.6977 | ETL.1820 | 44565478 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2020-05-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 118124411 | Mar | HUMBOLDT-TRINITY 076/000CNTR RPL POLE | 31497850 | HUMBOLDT-TRINITY | 076/000 | 70Y | E | Pre-2020_(2) High fire spread TD |  | 2018-10-19 | 2021-05-31 | 2020-11-03 | 2020-11-14 | 2021-03-27 | 2021-03-01 |  |  |  |  | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.442836 | 40.6977 | ETL.1820 | 44565611 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2020-05-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 118126037 | Q2 | LOS BANOS-GATES #1 035/147 BENT MEMB | 44300852 | LOS BANOS-GATES #1 | 035/147 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-10-31 | 2022-10-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.660935 | 36.6438 | ETL.6000 | 40816033 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-11-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118126552 | Q2 | LOS BANOS-GATES #1 033/142 BENT MEMB | 44300852 | LOS BANOS-GATES #1 | 033/142 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-10-31 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.672518 | 36.6586 | ETL.6000 | 40680385 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-11-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118134718 | Not Scheduled | TULUCAY-NAPA #1 9/2 RPR STRW | 44310753 | TULUCAY-NAPA #1 | 009/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-11-03 | 2020-11-03 | 2020-09-28 | 2020-10-01 | [6 empty] | LATE | North Coast | Non-WSIP | [6 empty] | '-122.227382 | 38.2844 | ETL.8180 | 40658491 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118134767 | Not Scheduled | TULUCAY-NAPA #1 9/2 INST GATE |  | TULUCAY-NAPA #1 | 009/002 | 71Y | F | Pre-2020_(4b) On structure in bucket 4 |  | 2019-11-03 | 2021-11-03 | [9 empty] | North Coast | Non-WSIP | [6 empty] | '-122.227382 | 38.2844 | ETL.8180 | 40658491 | Fence / Gate | Missing | Install |  |  |  |  | PEND | LC | TLR | Roads | Capital | 374 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  | 2020-03-30 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118138629 | Q2 | LOS BANOS-GATES #1 31/132 RPR FOND | 44300852 | LOS BANOS-GATES #1 | 031/132 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-11-04 | 2022-11-04 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.691267 | 36.6929 | ETL.6000 | 40676067 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118138697 | Q2 | LOS BANOS-GATES #1 31/131 RPR STRT | 44300852 | LOS BANOS-GATES #1 | 031/131 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  | 2019-11-04 | 2021-05-31 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.693225 | 36.6965 | ETL.6000 | 40592015 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118139036 | Q2 | LOS BANOS-GATES #1 29/124 RPR STRT | 44300852 | LOS BANOS-GATES #1 | 029/124 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-11-04 | 2022-11-04 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.70645 | 36.7208 | ETL.6000 | 40759096 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118139534 | Q2 | LOS BANOS-GATES #1 28/120 RPR STRT | 44300852 | LOS BANOS-GATES #1 | 028/120 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  | 2019-11-04 | 2022-11-04 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.713992 | 36.7346 | ETL.6000 | 40600075 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2019-12-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118165078 | Not Scheduled | WEBER-FRENCH CAMP #1 001/026 RPL ANCW | 44595064 | WEBER #1 | 001/026 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  | 2019-11-12 | 2020-11-12 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.255521 | 37.9122 | ETL.8320 | 40804098 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 4 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-12-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118165702 | Not Scheduled | WEBER-FRENCH CAMP #1 002/045 INS MRKW | 44595065 | WEBER #1 | 002/045 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  | 2019-11-12 | 2021-11-12 | [9 empty] | Central | Non-WSIP | [6 empty] | '-121.27385 | 37.9063 | ETL.8320 | 40857166 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 4 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-12-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118165943 | Not Scheduled | T2 EI TULUCAY-NAPA #1 7/6 INST HRDW | 44310753 | TULUCAY-NAPA #1 | 007/006 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-08-30 | 2020-08-30 | 2020-09-28 | 2020-10-01 | [5 empty] | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.207683 | 38.2692 | ETL.8180 | 40821522 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118167074 | Not Scheduled | WEBER-FRENCH CAMP #1 001/026 RPR GYWW | 44631075 | WEBER #1 | 001/026 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-11-12 | 2020-11-12 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-121.255521 | 37.9122 | ETL.8320 | 40804098 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 4 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-12-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118176637 | Q2 | T2 BUTTE VALLEY-CARIBOU 7/53A C RPL POLE | 31479584 | BUTT VALLEY-CARIBOU | 007/053A | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-17 | 2020-10-17 |  |  | 2021-06-11 | 2021-06-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1180 | 44399494 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | In Review | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118176639 | Q2 | T2 BUTTE VALLEY-CARIBOU 7/53A RPL R POLE | 31479584 | BUTT VALLEY-CARIBOU | 007/053A | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-17 | 2020-10-17 |  |  | 2021-06-11 | 2021-06-08 |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1180 | 44399495 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | In Review | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118177783 | Q3 | T2 BRIDGEVILLE-CTTNWD 66/481 RMV DEBRIS | 44143776 | BRIDGEVILLE-COTTONWOOD | 066/481 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-11-15 | 2024-11-15 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.465033 | 40.4234 | ETL.1110 | 44424646 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118178177 | Q2 | CORDELIA #2 TAP 03/064 RPL POLE | 31472910 | CORDELIA #2 TAP | 003/064 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-11-15 | 2020-11-15 |  |  | 2021-05-04 | 2021-04-26 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.151767 | 38.2491 | ETL.8184 | 40576417 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-05-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118179195 | Q3 | T2 BRIDGEVILLE-CTTNWD 079/561 RMV DEBRIS | 44106807 | BRIDGEVILLE-COTTONWOOD | 079/561 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-11-16 | 2024-11-16 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.65761 | 40.4784 | ETL.1110 | 44512081 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-17 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2020-01-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118185065 | Q3 | BRIDGEVILLE-COTTONWOOD 76/545 RMV BUTT | 44299811 | BRIDGEVILLE-COTTONWOOD | 076/545 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-11-19 | 2024-11-19 |  |  | 2021-07-17 | 2021-06-21 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-120.11496 | 36.8181 | ETL.1110 | 44424608 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2020-01-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118185921 | Q3 | T2 BRIDGEVILLE-CTTNWD 73/530 RMV BUTT | 44310757 | BRIDGEVILLE-COTTONWOOD | 073/530 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-11-19 | 2024-11-19 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.566011 | 40.4804 | ETL.1110 | 44744836 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-17 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2020-01-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118185922 | Q3 | T2 BRIDGEVLLE-CTTNWD 73/531 RMV BUTT | 44310757 | BRIDGEVILLE-COTTONWOOD | 073/531 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-11-19 | 2024-11-19 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.568275 | 40.4815 | ETL.1110 | 44553105 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-17 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2020-01-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118186213 | Q2 | HUMBOLDT-BRIDGEVILLE 99/7 RPR INSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 099/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-11-19 | 2020-11-19 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-120.117321 | 36.0931 | ETL.1810 | 43691636 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118186218 | Q3 | T2 BRIDGEVILLE-CTTNWD 73/528 RMV BUTT | 44299811 | BRIDGEVILLE-COTTONWOOD | 073/528 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-19 | 2024-11-19 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5595578 | 40.4772 | ETL.1110 | 44423942 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118186266 | Q3 | T2 BRIDGEVILLE-CTTNWD 73/527 RMV BUTT | 44143777 | BRIDGEVILLE-COTTONWOOD | 073/527 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-19 | 2024-11-19 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5574395 | 40.4762 | ETL.1110 | 44423352 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118186305 | Q3 | T2 BRIDGEVILLE-CTTNWD 72/525 RMV BUTT | 44143777 | BRIDGEVILLE-COTTONWOOD | 072/525 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-11-19 | 2024-11-19 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5525556 | 40.4738 | ETL.1110 | 44740684 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2020-10-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118186334 | Q3 | T2 BRIDGEVILLE-CTTNWD 72/524 RMV DEBRIS | 44143777 | BRIDGEVILLE-COTTONWOOD | 072/524 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-19 | 2024-11-19 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5511086 | 40.4731 | ETL.1110 | 44424508 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2020-10-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118186385 | Q3 | T2 BRIDGEVILLE-CTTNWD 72/523 RMV DBRIS | 44299811 | BRIDGEVILLE-COTTONWOOD | 072/523 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-19 | 2024-11-19 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5485371 | 40.4718 | ETL.1110 | 44424376 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2020-01-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118186695 | Q2 | HAT CREEK #1-WESTWOOD 26/508 RPL POLE | 31504249 | HAT CREEK #1-WESTWOOD | 026/508 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-10-04 | 2021-05-31 |  |  | 2021-06-25 | 2021-05-03 |  |  | Likely MAT error - delink to correct |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.194835 | 40.6708 | ETL.7030 | 40616910 | Structure-Wood | Rotten | Stub | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118186698 | Not Scheduled | T2 PARADISE-TABLE MTN 6/56AB STUB POLE |  | PARADISE-TABLE MTN | 006/055AB | GAR | E | 2020_(1a) PSPS |  | 2019-09-12 | 2020-09-12 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.537939 | 39.5476 | ETL.4316 | 44383157 | Structure-Wood | Rotten | Stub |  |  |  |  | PEND | LC | TLX | Contract | Expense | 586 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 118187329 | Q2 | HUMBOLDT-BRIDGEVILLE 99/02C INST IBWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 099/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-11-19 | 2020-11-19 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.8932644 | 40.6441 | ETL.1810 | 44322410 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118187369 | Q2 | HUMBOLDT-BRIDGEVILLE 99/02C RPR WP HOLE | 43749687 | HUMBOLDT-BRIDGEVILLE | 099/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-11-19 | 2020-11-19 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.8932644 | 40.6441 | ETL.1810 | 44322410 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118187390 | Q2 | HUMBOLDT-BRIDGEVILLE 99/02L RPR JUMW | 43749687 | HUMBOLDT-BRIDGEVILLE | 099/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-11-19 | 2020-11-19 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.8932644 | 40.6441 | ETL.1810 | 44322409 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118187763 | Q2 | HUMBOLDT-BRIDGEVILLE 96/04 INST DAMS | 44107184 | HUMBOLDT-BRIDGEVILLE | 096/004 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-19 | 2020-11-19 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.863309 | 40.6183 | ETL.1810 | 44324153 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118187929 | Q2 | HUMBOLDT-BRIDGEVILLE 099/007 PNT CRSM | 44107184 | HUMBOLDT-BRIDGEVILLE | 099/007 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  | 2019-11-19 | 2020-11-19 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.901921 | 40.6479 | ETL.1810 | 44322426 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118188951 | Q3 | T2 BRIDGEVILLE-CTTNWD 71/515 RMV DEBRIS | 44143776 | BRIDGEVILLE-COTTONWOOD | 071/515 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-11-20 | 2024-11-20 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.528872 | 40.4681 | ETL.1110 | 44814455 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2020-10-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118189071 | Q2 | T2 BRIDGEVILLE-CTTNWD 03/29L RPL POLE | 31485141 | BRIDGEVILLE-COTTONWOOD | 003/029 | 70Y | E | 2020_(1a) PSPS |  | 2019-11-20 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-122.325294 | 40.391 | ETL.1110 | 44423198 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2020-01-27 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 118190056 | Q3 | T2 BRIDGEVILLE-CTTNWD 69/501 RMV BUTT | 44299811 | BRIDGEVILLE-COTTONWOOD | 069/501 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-11-20 | 2022-11-20 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.498437 | 40.4519 | ETL.1110 | 44510516 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2020-01-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118190143 | Q3 | T2 BRIDGEVILLE-CTTNWD 69/498 RMV BUTT | 44299811 | BRIDGEVILLE-COTTONWOOD | 069/498 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-20 | 2020-11-20 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.494471 | 40.4487 | ETL.1110 | 44510553 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-01-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118190241 | Q3 | T2 BRIDGEVILLE-CTNWD 69/497 RMV BUTT | 44299811 | BRIDGEVILLE-COTTONWOOD | 069/497 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-20 | 2020-11-20 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.493193 | 40.4476 | ETL.1110 | 44510624 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-01-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118195339 | Q2 | BRIDGEVILLE-COTTONWOOD 03/29R RPL POLE | 31485141 | BRIDGEVILLE-COTTONWOOD | 003/029 | 70Y | E | 2020_(1a) PSPS |  | 2019-11-19 | 2021-05-31 |  |  | 2021-04-30 | 2021-03-29 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.325294 | 40.391 | ETL.1110 | 44423199 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  | 2020-01-27 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 118195719 | Q2 | HUMBOLDT-BRIDGEVILLE 99/2R RPR JUMW | 43749687 | HUMBOLDT-BRIDGEVILLE | 099/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-11-19 | 2020-11-19 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.842729 | 40.5606 | ETL.1810 | 44322411 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118195881 | Q2 | HUMBOLDT-BRIDGEVILLE 99/2C RPR JUMW | 43749687 | HUMBOLDT-BRIDGEVILLE | 099/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-11-19 | 2020-11-19 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322410 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-01-16 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118196173 | Not Scheduled | T2 SMARTVILLE-CAMP FR WST A1/18 RPL POLE | 31479591 | SMARTVILLE-CAMP FAR WEST | A001/018 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-11-22 | 2020-11-22 | [7 empty] | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.301809 | 39.0412 | ETL.7970 | 40666683 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-02-24 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118199811 | Not Scheduled | IGNCIO-ALTO-SUSLITO #1 12/82 PAINT STRT | 44586160 | IGNACIO-ALTO-SAUSALITO #1 | 012/082 | ICX | E | Pre-2020_(9a) Other ignition related |  | 2019-11-23 | 2020-11-23 | [6 empty] | Likely MAT error - delink to correct |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.519722 | 37.9017 | ETL.7160 | 40812969 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118199814 | Q3 | T2 BRIDGEVILLE-CTNWD 70/505 RMV DEBRIS | 44299811 | BRIDGEVILLE-COTTONWOOD | 070/505 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-23 | 2024-11-23 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5076161 | 40.4592 | ETL.1110 | 44510576 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2020-01-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118199818 | Q3 | T2 BRIDGEVILLE-CTNWD 70/504 RMV BUTT | 44299811 | BRIDGEVILLE-COTTONWOOD | 070/504 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-23 | 2024-11-23 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5062419 | 40.4581 | ETL.1110 | 44423343 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2020-01-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118199861 | Q3 | T2 BRIDGEVILLE-CTNWD 70/510 RMV BUTT | 44299811 | BRIDGEVILLE-COTTONWOOD | 070/510 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-23 | 2024-11-23 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5156462 | 40.4657 | ETL.1110 | 44510621 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2020-01-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118199874 | Q3 | T2 BRIDGEVILLE-CTNWD 70/506 RMV DEBRIS | 44299811 | BRIDGEVILLE-COTTONWOOD | 070/506 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-23 | 2024-11-23 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5107748 | 40.4618 | ETL.1110 | 44510607 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  | 2020-01-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118200367 | Not Scheduled | T2 BRIDGEVILLE-CTTNWD 82/575 CANCEL |  | BRIDGEVILLE-COTTONWOOD | 082/575 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-11-23 | 2020-11-23 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7081052 | 40.478 | ETL.1110 | 44425587 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118200431 | Q3 | T2 BRIDGEVILLE-CTNWD 82/578 RMV BUTT | 44143776 | BRIDGEVILLE-COTTONWOOD | 082/578 | ICS | F | Pre-2020_(9a) Other ignition related |  | 2019-11-24 | 2024-11-24 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7164328 | 40.4804 | ETL.1110 | 44425590 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118200480 | Feb | T2 BRIDGEVILLE-CTNWD 83/583 RMV BUTT | 44143777 | BRIDGEVILLE-COTTONWOOD | 083/583 | ICW | E | Pre-2020_(3) On high spread structure |  | 2019-11-24 | 2024-11-24 | 2020-10-26 | 2020-10-29 | 2021-02-28 | 2021-02-28 |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Weather | AT RISK - weather impacts | '-123.7289484 | 40.484 | ETL.1110 | 44424588 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2020-06-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-03-31
2021 Work Plan | 118200675 | Q3 | T2 DI CARIBOU-WSTWD 7/140A RPL STRW | 31473384 | CARIBOU-WESTWOOD | 007/140A | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2021-05-31 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.087797 | 40.1717 | ETL.6300 | 40873904 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2020-06-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118201058 | Q3 | T2 DI CARIBOU-WSTWD 7/140B RPL STRW | 31473384 | CARIBOU-WESTWOOD | 007/140 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-06-17 | 2020-06-17 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.08781 | 40.1717 | ETL.6300 | 42624246 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-06-22 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118202022 | Q3 | T2 BRIDGEVILLE-COTTONWD 83/586 RMV DEBRS | 44143777 | BRIDGEVILLE-COTTONWOOD | 083/586 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-25 | 2020-11-25 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7398388 | 40.4866 | ETL.1110 | 44424000 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118202203 | Feb | T2 BRIDGEVILLE-COTTONWD 84/588 RMV DEBRS | 44143777 | BRIDGEVILLE-COTTONWOOD | 084/588 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-25 | 2021-05-31 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7447937 | 40.4869 | ETL.1110 | 44424569 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118202242 | Feb | T2 BRIDGEVILLE-CTNWD 84/593 RMV DEBRIS | 44143777 | BRIDGEVILLE-COTTONWOOD | 084/593 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-25 | 2021-05-31 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7558897 | 40.4862 | ETL.1110 | 44424554 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2021-01-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118202273 | Feb | T2 BRIDGEVILLE-CTNWD 84/591 RMV DEBRIS | 44143777 | BRIDGEVILLE-COTTONWOOD | 084/591 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-25 | 2021-05-31 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.751597 | 40.4864 | ETL.1110 | 44424575 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2021-01-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118202461 | Feb | T2 BRIDGEVLLE-CTNWD 84/590 RMV DEBRIS | 44143777 | BRIDGEVILLE-COTTONWOOD | 084/590 | ICW | E | Pre-2020_(9a) Other ignition related |  | 2019-11-25 | 2021-05-31 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7495506 | 40.4866 | ETL.1110 | 44424572 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | IC | Feb |  |  | 2021-01-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118202543 | Q3 | T3 BRIDGEVILLE-COTTOND 85/598 RMV DEBRIS | 44143777 | BRIDGEVILLE-COTTONWOOD | 085/598 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-11-25 | 2024-11-25 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.766643 | 40.4843 | ETL.1110 | 44424563 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q3 | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118202924 | Q2 | T2 HAT CREEK #1-WESTWOOD 26/509 RPLC P | 31495723 | HAT CREEK #1-WESTWOOD | 026/509 | 70Y | F | Pre-2020_(4) TD tag on high spread line |  | 2019-10-04 | 2021-10-04 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | Non-WSIP | [6 empty] | '-121.194428 | 40.6704 | ETL.7030 | 40601697 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-23 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118207765 | Mar | T2 KILARC-DESCHUTES 5/108 RPL POLE | 31482714 | KILARC-DESCHUTES | 005/108 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-11-27 | 2020-11-27 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.929089 | 40.6182 | ETL.7300 | 40759294 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118220134 | Not Scheduled | T2 WV SNG-SMIT 0/013 BOND GUY HRDW | 44111976 | SPAULDING-SUMMIT | 000/013 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-12-02 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.639723 | 39.3233 | ETL.8060 | 40650034 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-03-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118223348 | Not Scheduled | SAN BRUNO TAP 000/001 RPR SWIW | 44588133 | SAN BRUNO TAP | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-12-03 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.439223 | 37.6159 | ETL.7572 | 40588793 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-03-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118223985 | Not Scheduled | T2 CALNDER SW STA-MESA 015/068 RPL INSS | 31481083 | CALLENDAR SW STA-MESA | 015/068 | 93K | E | Pre-2020_(5) TD tag on other lines |  | 2019-12-03 | 2021-05-31 | [7 empty] | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.495546 | 35.0895 | ETL.1210 | 41178097 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  | 2019-12-10 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118224339 | Feb | T2 EL DORADO-MSRI FLAT #1 9/76 RPL POLE | 31482715 | ELDORADO-MISSOURI FLAT #1 | 009/076 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  | 2019-12-03 | 2020-12-03 |  |  | 2021-02-21 | 2021-02-16 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.771565 | 38.7464 | ETL.1530 | 40818661 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-02-18 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118224398 | Not Scheduled | T2 CHRISTIE-SOBRANTE 000/003 REPAINT | 43751914 | CHRISTIE-SOBRANTE | 000/003 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) | 2019-12-03 | 2021-12-03 | [7 empty] | TR2 |  | Central | Non-WSIP | [6 empty] | '-122.205649 | 38.0025 | ETL.1260 | 41146800 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118238966 | Not Scheduled | CALLENDER SW STA-MESA 4/70 RMV IDLE | 44226578 | CALLENDAR SW STA-MESA | 004/070 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-12-05 | 2021-12-05 | [7 empty] | TR2 |  | South | Non-WSIP | [6 empty] | '-120.515695 | 35.0527 | ETL.1210 | 40736121 | Conductor-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-12-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118239340 | Not Scheduled | T2 DI BELE AFB (WAPA) 2 TAP 0/1 RPR GYWW | 44119803 | BEALE AFB (WAPA) #2 TAP | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-12-05 | 2020-12-05 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.332321 | 39.1139 | ETL.7971 | 40741836 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118239486 | Q2 | T2 FULTON-CALISTOGA 32/8 RPR STRW | 44305659 | FULTON-CALISTOGA | 032/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  | 2019-12-05 | 2021-05-31 | 2020-09-21 | 2020-09-25 | 2021-04-30 | 2021-04-26 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.447606 | 38.5084 | ETL.6880 | 40905814 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-05-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118241771 | Not Scheduled | T2 DI BEALE AFB (WAPA) #1 INST HRDS | 44119801 | BEALE AFB (WAPA) #1 TAP | 000/002 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-12-05 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.332562 | 39.1136 | ETL.8001 | 40740418 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118241960 | Not Scheduled | DI OLEUM-NRTH TWR-CHRSTE 0/5 PAINT STRS | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 000/005 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) | 2019-12-05 | 2021-12-05 | [9 empty] | Central | WSIP | [6 empty] | '-122.249236 | 38.0412 | ETL.3180 | 40746026 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(5b) On structure in bucket 5 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118241964 | Not Scheduled | DI OLEUM-NRTH TWR-CHRSTE 0/5 RPL HRDT | 44323369 | OLEUM-NORTH TOWER-CHRISTIE | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-12-05 | 2020-12-05 | [6 empty] | Likely MAT error - delink to correct |  | LATE | Central | WSIP | [6 empty] | '-122.249236 | 38.0412 | ETL.3180 | 40746026 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 630 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-01-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118241968 | Not Scheduled | T2 DI BEALE AFB (WAPA)#2 0/2 RMV NEST | 44119801 | BEALE AFB (WAPA) #2 TAP | 000/002 | ICS | E | Pre-2020_(9a) Other ignition related |  | 2019-12-05 | 2020-12-05 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.33242 | 39.1137 | ETL.7971 | 40576711 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118242213 | Q2 | T2 DI BRDGVLLE-COTTNWD 31/260 RMV DEBRIS | 43939216 | BRIDGEVILLE-COTTONWOOD | 031/260 | ICW | F | Pre-2020_(9a) Other ignition related |  | 2019-12-05 | 2021-12-05 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.855024 | 40.3636 | ETL.1110 | 44423926 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118242536 | Not Scheduled | T2 DI OLM-NO TWR-CHRST 0/8 RPR STRT | 43752227 | OLEUM-NORTH TOWER-CHRISTIE | 000/008 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | 2019-12-05 | 2020-12-05 | [7 empty] | TR2 | LATE | Central | WSIP | [6 empty] | '-122.241671 | 38.0396 | ETL.3180 | 40857755 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-01-06 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118242641 | Q3 | DI T2 SURF TAP 10/175 RMV VEGN |  | SURF TAP | 010/175 | HNA | F | Pre-2020_(9a) Other ignition related |  | 2019-12-03 | 2021-12-03 |  |  | 2021-08-15 | 2021-08-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.586005 | 34.6843 | ETL.1381 | 40864675 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9a) Other ignition related | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118243901 | Feb | T2 DI SMRTVL-NICOLAUS#2 6/135 RPR GYWW | 44123655 | SMARTVILLE-NICOLAUS #2 | 006/135 | ICW | E | Pre-2020_(5) TD tag on other lines |  | 2019-12-05 | 2020-12-05 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.331823 | 39.1136 | ETL.8000 | 40912141 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118247801 | Not Scheduled | AGNEW TAP 0/11 RPR GYWW | 44303608 | AGNEW TAP | 000/011 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | 2019-12-09 | 2021-05-31 | [8 empty] | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.941618 | 37.4345 | ETL.3122 | 40585505 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-04-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118248218 | Q2 | T2 PIT #7 TAP 2/17R RPL POLE | 31432828 | PIT #7 TAP | 002/017 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-12-09 | 2020-12-09 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.956949 | 40.8326 | ETL.5442 | 44553739 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118248223 | Q2 | T2 PIT #7 TAP 2/17L RPL POLE | 31432828 | PIT #7 TAP | 002/017 | 70Y | E | Pre-2020_(5) TD tag on other lines |  | 2019-12-09 | 2020-12-09 |  |  | 2021-06-26 | 2021-06-23 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.956949 | 40.8326 | ETL.5442 | 44553553 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-12 | Released-Standard | Complete | Ready for Construction |  | Pre-2020_(5) TD tag on other lines | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118260498 | Q2 | T3 FULTON-CALISTOGA -13/4 RPR PL | 44305659 | FULTON-CALISTOGA | '-013/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2019-12-11 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.515425 | 38.4197 | ETL.6880 | 40751147 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | IC | Q2 |  |  | 2020-05-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118263098 | Mar | T2 HUMBOLDT-TRINITY 91/4L RPL STRW | 31497850 | HUMBOLDT-TRINITY | 091/004 | 70Y | E | 2020_(2) High fire spread TD |  | 2019-12-11 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7071239 | 40.7486 | ETL.1820 | 44560531 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2020-05-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118264284 | Before Feb | T3 GEYSERS #12-FULTON 1/6 RPR STRT | 44239025 | GEYSERS #12-FULTON | 001/006 | ICQ | E | 2020_(2) High fire spread TD |  | 2019-11-13 | 2020-05-13 | 2021-01-25 | 2021-01-28 | 2021-01-28 | 2021-01-25 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.767206 | 38.7958 | ETL.4750 | 41129171 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2020-05-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118264643 | Feb | T2 RIO DELL JCT-BRIDGEVILL 32/5L RPL PL | 31423103 | RIO DELL JCT-BRIDGEVILLE | 032/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2019-12-12 | 2020-12-12 |  |  | 2021-02-27 | 2021-02-15 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.913305 | 40.4881 | ETL.7850 | 44779574 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-01-09 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118266568 | Q2 | T3 FULTON-CALISTOGA -014/004 RPL POLE | 31482772 | FULTON-CALISTOGA | '-014/004 | 93E | E | 2020_(2) High fire spread TD |  | 2019-12-12 | 2020-06-12 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.505863 | 38.4335 | ETL.6880 | 40751149 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-05-04 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118266611 | Q2 | T3 FULTON-CALISTOGA -015/001 RPR STRW |  | FULTON-CALISTOGA | '-015/001 | ICW | E | 2020_(2) High fire spread TD |  | 2019-12-12 | 2020-06-12 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.495961 | 38.4394 | ETL.6880 | 40585421 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-05-27 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118267516 | Feb | EI RIO DELL JCT-BRIDGEVLE 32/5C RPL STRW | 31423103 | RIO DELL JCT-BRIDGEVILLE | 032/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2019-12-12 | 2020-12-12 |  |  | 2021-02-27 | 2021-02-15 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.913305 | 40.4881 | ETL.7850 | 44779575 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-01-09 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118267610 | Feb | EI RIO DELL JCT-BRIDGEVLE 32/5R RPL STRW | 31423103 | RIO DELL JCT-BRIDGEVILLE | 032/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2019-12-12 | 2020-12-12 |  |  | 2021-02-27 | 2021-02-15 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.913305 | 40.4881 | ETL.7850 | 44779576 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-09 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-01-09 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118268097 | Mar | T2 EI HMBLDT-TRNTY 91/04C RPL STRW | 31497849 | HUMBOLDT-TRINITY | 091/004 | 70Y | E | 2020_(2) High fire spread TD |  | 2019-12-11 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.70711 | 40.7485 | ETL.1820 | 44560505 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2020-05-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118268375 | Mar | T2 EI HMBLDT-TRNTY 91/04R RPL STRW | 31497849 | HUMBOLDT-TRINITY | 091/004 | 70Y | E | 2020_(2) High fire spread TD |  | 2019-12-11 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.70711 | 40.7485 | ETL.1820 | 44560532 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2020-05-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118268916 | Not Scheduled | T3 DRUM-RIO OSO #2 010/100 RMV VEG |  | DRUM-RIO OSO #2 | 010/100 | HNA | E | 2020_(3) On high spread structure |  | 2019-12-13 | 2020-06-13 | [7 empty] | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.919028 | 39.1756 | ETL.1430 | 40608843 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118269745 | Q3 | T2 CARIBOU #2 ;002/010 RPR STRS | 44144219 | CARIBOU #2 | ;002/010 | ICS | E | 2020_(4) TD tag on high spread line |  | 2019-12-13 | 2020-12-13 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.954713 | 39.9989 | ETL.6280 | 44688355 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-02-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118278684 | Not Scheduled | T2 BELDEN TAP 0/1A CANCEL | 44170043 | BELDEN TAP | 000/001A | ICQ | E | 2020_(2) High fire spread TD |  | 2019-12-16 | 2020-12-16 | [6 empty] | CANCEL/CNCL | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.250817 | 40.0077 | ETL.4441 | 43198032 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118279869 | Q3 | T2 DI CARIBOU-PLUMAS JCT 0/1 RPL POLE | 31498402 | CARIBOU-PLUMAS JCT | 000/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-12-12 | 2020-12-12 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.14748 | 40.0855 | ETL.6290 | 40600690 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-06-24 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118280663 | Q2 | T2 DI HUMBOLDT-MAPLE CRK 13/5C RPL STRW | 31485371 | HUMBOLDT-MAPLE CREEK | 013/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-04-30 | 2020-04-30 |  |  | 2021-06-19 | 2021-06-14 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.8853558 | 40.7679 | ETL.7130 | 44859705 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-01-29 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118280672 | Q2 | T2 DI HUMBOLDT-MAPLE CRK 13/5R RPL STRW | 31485371 | HUMBOLDT-MAPLE CREEK | 013/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-04-30 | 2020-04-30 |  |  | 2021-06-19 | 2021-06-14 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.8853558 | 40.7679 | ETL.7130 | 44859706 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-29 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-01-29 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118284857 | Not Scheduled | T2 EI CARIBOU-TABLE MTN 7/056 RPR ANCHOR |  | CARIBOU-TABLE MTN | 007/056 | ICS | E | 2020_(4) TD tag on high spread line |  | 2019-12-18 | 2020-12-18 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.149342 | 40.0851 | ETL.4440 | 40815780 | Anchor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-10 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118316604 | Not Scheduled | T2 DI COLGATE-SMARTVIL#2 3/36 BOND GUY | 44135957 | COLGATE-SMARTVILLE #2 | 003/036 | ICW | E | 2020_(4) TD tag on high spread line |  | 2019-12-19 | 2020-06-05 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.237627 | 39.3101 | ETL.6520 | 40602842 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118369993 | Feb | T2 EI TRINITY-MAPLE CREEK 7/8 REFRAME | 31489366 | TRINITY-MAPLE CREEK | 007/008 | 93E | E | 2020_(2) High fire spread TD |  | 2019-12-30 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.056467 | 40.7467 | ETL.8170 | 40906351 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  | 2020-04-14 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2020-04-14 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118388637 | Q2 | T2 EI CASTRO VALLEY-NWRK 05/033 RPL DAMS | 44144892 | CASTRO VALLEY-NEWARK | 005/033 | ICS | E | 2020_(2) High fire spread TD |  | 2020-01-02 | 2021-01-02 | 2020-08-15 | 2020-08-16 | 2021-05-18 | 2021-05-17 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | 121.9918 | 37.6408 | ETL.4450 | 40788240 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-02-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118388683 | Q2 | T2 EI CSTRO VLY-NWRK 5/33 INST JUMS INSS | 31529998 | CASTRO VALLEY-NEWARK | 005/033 | 93K | E | 2020_(2) High fire spread TD |  | 2020-01-02 | 2021-01-02 | 2020-08-15 | 2020-08-16 | 2021-05-18 | 2021-05-17 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | 121.9918 | 37.6408 | ETL.4450 | 40788240 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-02-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118388885 | Mar | T3 EI BRUNSWICK #2 TAP 0/3 RPL INSS | 31433277 | BRUNSWICK #2 TAP | 000/003 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-01-02 | 2020-07-02 |  |  | 2021-03-16 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.008684 | 39.1445 | ETL.1431 | 40678233 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118390408 | Not Scheduled | T2 EI DRUM-RIO OSO #1 31/224 BENT MEMB | 44144912 | DRUM-RIO OSO #1 | 031/224 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-01-02 | 2021-01-02 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.262626 | 39.0386 | ETL.1420 | 40746096 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118395911 | Q4 | EI SALINAS-LAURELES A018/383 RMV VEGN |  | SALINAS-LAURELES | A018/383 | HNA | E | 2020_(4b) On structure in bucket 4 | Budget Owner (Veg/Land/Road) | 2019-12-26 | 2020-12-26 |  |  | 2021-12-31 | 2021-12-01 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-121.862366 | 36.5857 | ETL.7930 | 40680327 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118395982 | Not Scheduled | DI SALINAS-LAURELES A017/374 REPL POLE | 31478032 | SALINAS-LAURELES | A017/374 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-12-26 | 2020-12-26 | [8 empty] | LATE | South | WSIP | [6 empty] | '-121.854788 | 36.5833 | ETL.7930 | 40825953 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  |  | Caltrans (DSDD) | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118396324 | Q2 | DI SALINAS-LAURELES A16/348 TIGHTEN BOLT | 44391519 | SALINAS-LAURELES | A016/348 | ICW | E | 2020_(4) TD tag on high spread line |  | 2019-12-26 | 2020-12-26 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-10 |  |  |  |  | LATE | South | WSIP | [6 empty] | '-121.833233 | 36.5815 | ETL.7930 | 40658683 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-02-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118399557 | Not Scheduled | T2 SPAULDING-SUMMIT 0/006 RPR GYWW | 44146289 | SPAULDING-SUMMIT | 000/006 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-01-07 | 2021-01-07 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.642656 | 39.3248 | ETL.8060 | 40810153 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118400020 | Mar | T2 HUMBOLDT-TRINITY 64/0 REPL GYWW | 44298747 | HUMBOLDT-TRINITY | 064/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-01-07 | 2020-05-10 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.230802 | 40.7363 | ETL.1820 | 44562748 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-05-27 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-05-27 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118428982 | Not Scheduled | T3NT FULTON-CALISTOGA :0/8 INSTL MRKS | 31487688 | FULTON-CALISTOGA | :000/008 | 93C | F | 2020_(4b) On structure in bucket 4 |  | 2020-01-14 | 2022-01-14 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.58119 | 38.6037 | ETL.6880 | 44647598 | Marker (i.e. signs)-Steel | Missing | Install | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 531 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118437940 | Q2 | HUMBOLDT-BRIDGEVILLE 92/6 RPL PL LEFT | 31486487 | HUMBOLDT-BRIDGEVILLE | 092/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-01-16 | 2021-01-15 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322322 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-03-23 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-03-23 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118440911 | Not Scheduled | GEYSERS #7-EAGLE ROCK 1/10 REPL CROSSING | 31487105 | GEYSERS #7-EAGLE ROCK | 001/010 | 71Y | F | 2020_(3) On high spread structure |  | 2020-01-16 | 2022-01-16 |  |  |  | 2021-08-01 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.811077 | 38.8232 | ETL.1680 | 40588203 | Road | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118447822 | Q2 | EI HUMBOLDT-BRIDGEVILLE 92/6R RPL STRW | 31486487 | HUMBOLDT-BRIDGEVILLE | 092/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-01-21 | 2021-01-21 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322323 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-03-23 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-03-23 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118453527 | Not Scheduled | T2 SNEATH LANE-PFCA 4/50 TST POLE CMPLTD | 44162132 | SNEATH LANE-PACIFICA | 004/050 | ICH | E | 2020_(4) TD tag on high spread line |  | 2020-01-22 | 2021-01-22 | [6 empty] | CANCEL/CNCL | TR2 | LATE | Central | WSIP | [6 empty] | '-122.4549992 | 37.615 | ETL.7575 | 44384746 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118454334 | Feb | T2 DI TRINITY-MAPLE CREEK 02/10 RPL ANCW | 31488022 | TRINITY-MAPLE CREEK | 002/010 | 93E | E | 2020_(2) High fire spread TD |  | 2020-01-23 | 2021-01-23 | 2021-02-22 | 2021-02-27 | 2021-02-24 | 2021-02-24 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.973681 | 40.7346 | ETL.8170 | 40906272 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  | 2020-04-14 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-04-14 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118455543 | Feb | T3 EGLE RCK-FLTN-SLVDO 3/16A RPL INSS | 31485176 | EAGLE ROCK-FULTON-SILVERADO | 003/016A | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-01-23 | 2020-07-23 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.802181 | 38.8015 | ETL.4392 | 40578874 | Insulator-Steel | No Good/Out of Stdrd | Replace | POST | POST | POST Estimate | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-02-27 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118477236 | Q2 | T2 LAKEVILLE-SOBRANTE #2 44/211 RPL INSS | 31431937 | LAKEVILLE-SOBRANTE #2 | 044/211 | 93K | E | 2020_(2) High fire spread TD |  | 2020-01-29 | 2021-01-29 | 2020-07-13 | 2020-07-17 | 2021-06-05 | 2021-06-04 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.2039344 | 37.9529 | ETL.4960 | 40618899 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-12-07 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118484703 | Q2 | T2 NEWARK-LIVERMORE 16/99 RPL PL | 31489034 | NEWARK-LIVERMORE | 016/099 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-01-31 | 2021-01-31 |  |  | 2021-05-12 | 2021-05-10 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.77775 | 37.636 | ETL.7660 | 40745742 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118486847 | Q2 | MELONES-CURTIS 5/6 RPR GYWW | 44623079 | MELONES-CURTIS | 005/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-01-31 | 2021-01-31 |  |  | 2021-04-02 | 2021-03-02 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.4567661 | 37.9131 | ETL.2390 | 44195243 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 18 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-03-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118499120 | Q2 | OLEUM-G #1 0/6 RPR FOND |  | OLEUM-G #1 | 000/006 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-02-05 | 2021-02-05 |  |  | 2021-04-02 | 2021-03-29 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.246756 | 38.0405 | ETL.3150 | 40804781 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-15 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118499883 | Not Scheduled | T2 DIVIDE-VANDENBERG #2 5/42 RPL ANCW | 31490364 | DIVIDE-VANDENBERG #2 | 005/042 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-02-05 | 2021-02-05 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-120.510648 | 34.7691 | ETL.8630 | 40754920 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-03-05 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118500086 | Q2 | MELONES-CURTIS 5/6 RPR GYWW | 44623200 | MELONES-CURTIS | 005/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-02-05 | 2021-02-05 |  |  | 2021-04-02 | 2021-03-02 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.4567697 | 37.9131 | ETL.2390 | 44195244 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 18 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-03-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118502119 | Not Scheduled | T2 HAAS-MCCALL 15/085 RPR JUMS | 44301790 | HAAS-MCCALL | 015/085 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-02-06 | 2021-02-06 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-119.266507 | 36.8466 | ETL.4850 | 40762656 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-03-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118505099 | Q2 | EI T3NT ROSSMOOR #1 TAP 0/003 RPR FOND |  | ROSSMOOR #1 TAP | 000/003 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-02-07 | 2022-02-07 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.07906 | 37.86 | ETL.5451 | 40659428 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118506108 | Q2 | T2 HAT CREEK #1-WESTWOOD 44/863 REFRAME | 31469738 | HAT CREEK #1-WESTWOOD | 044/863 | 93E | E | 2020_(2) High fire spread TD |  | 2020-02-07 | 2021-02-07 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.022952 | 40.4504 | ETL.7030 | 40877507 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-06-02 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118506297 | Feb | T2 VACA-SUISUN-JAMESON 5/40 RPL INSS | 31457373 | VACA-SUISUN-JAMESON | 005/040 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-02-04 | 2021-02-04 |  |  | 2021-02-13 | 2021-02-11 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.9959972 | 38.3818 | ETL.4080 | 40632749 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118506415 | Feb | T2 CORTINA-MENDOCINO #1 28/137 RPR FOND | 44302218 | CORTINA-MENDOCINO #1 | 028/137 | ICS | E | 2020_(2) High fire spread TD |  | 2020-02-07 | 2021-02-07 |  |  | 2021-02-19 | 2021-02-16 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.708607 | 39.0337 | ETL.1330 | 40808527 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118506416 | Feb | T2 CORTINA-MENDOCINO #1 23/107 RPR FOND | 44302218 | CORTINA-MENDOCINO #1 | 023/107 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-02-07 | 2021-02-07 |  |  | 2021-02-19 | 2021-02-16 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607196 | 39.011 | ETL.1330 | 40813110 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118506419 | Feb | T2 CORTINA-MENDOCINO #1 15/72 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 015/072 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-02-07 | 2021-02-07 |  |  | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.469953 | 39.0228 | ETL.1330 | 40657040 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118519948 | Q2 | T2 SALINAS-LAURELES A012/270 RPR STRW | 44294541 | SALINAS-LAURELES | A012/270 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-01-29 | 2021-01-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.773189 | 36.5693 | ETL.7930 | 40825940 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118521765 | Feb | T2 CORTINA-MENDOCINO #1 20/96 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 020/096 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-02-10 | 2021-02-10 |  |  | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.563714 | 39.0039 | ETL.1330 | 40808919 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118522125 | Not Scheduled | T2 EI NEWARK-LIVMORE 009/056 CANCEL | 44621454 | NEWARK-LIVERMORE | 009/056 | ICS | E | 2020_(2) High fire spread TD |  | 2020-02-05 | 2021-02-05 | [6 empty] | CANCEL/CNCL | TR2 | LATE | Central | WSIP | [6 empty] | '-121.860387 | 37.582 | ETL.7660 | 40830360 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | SFWL | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118522380 | Feb | T2 CORTINA-MENDOCINO #1 51/252 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 051/252 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-02-10 | 2021-02-10 |  |  | 2021-02-19 | 2021-02-16 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.041805 | 39.207 | ETL.1330 | 40657091 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118524639 | Mar | T2 CLEAR LAKE-HOPLAND 2/0 RPL POLE | 31488229 | CLEAR LAKE-HOPLAND | 002/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-02-11 | 2021-02-11 | 2021-01-01 | 2021-12-31 | 2021-03-26 | 2021-03-24 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.046297 | 38.9673 | ETL.6390 | 40587019 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-04-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118527459 | Q2 | T3 EI SNEATH LANE-HMB ?10/5 RPL ANCW | 31490660 | SNEATH LANE-HALF MOON BAY | ?010/005 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-02-12 | 2020-08-12 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.422274 | 37.4871 | ETL.7212 | 40758359 | Anchor-Wood | No Good/Out of Stdrd | Replace | MAPP srdy | MAPP | Constructed and mapped | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118529067 | Not Scheduled | T2 DIABLO-MIDWAY #3 21/088A RPL INSS | 31500490 | DIABLO-MIDWAY #3 | 021/088A | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-02-12 | 2021-02-12 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-120.477877 | 35.1638 | ETL.5980 | 40577051 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-02-19 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118532302 | Q2 | T3 EI SNEATH LANE-HMB ;2/21 RPL ANCW | 31490660 | SNEATH LANE-HALF MOON BAY | ;002/021 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-02-13 | 2020-08-13 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.469905 | 37.6016 | ETL.7212 | 40599236 | Anchor-Wood | No Good/Out of Stdrd | Replace | MAPP srdy | MAPP | Constructed and mapped | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118532589 | Q2 | T3 EI SNEATH LANE-HMB ?9/4 RPL ANCW | 31490660 | SNEATH LANE-HALF MOON BAY | ?009/004 | 93E | E | 2020_(2) High fire spread TD |  | 2020-02-13 | 2020-08-13 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.42395 | 37.503 | ETL.7212 | 40768020 | Anchor-Wood | No Good/Out of Stdrd | Replace | MAPP srdy | MAPP | Constructed and mapped | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118537816 | Q3 | T2 BRDEVLLE-CTTNWD 72/522L RPL POLE | 31497846 | BRIDGEVILLE-COTTONWOOD | 072/522 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-02-14 | 2021-02-14 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.545146 | 40.4703 | ETL.1110 | 44512064 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-06-03 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118537866 | Q2 | TRINITY-MAPLE CREEK 50/8 RPL ANCW | 31492622 | TRINITY-MAPLE CREEK | 050/008 | 93E | E | 2020_(2) High fire spread TD |  | 2020-02-14 | 2021-02-14 |  |  | 2021-04-17 | 2021-04-05 |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-123.8123315 | 40.7617 | ETL.8170 | 44752436 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  | 2020-04-23 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-04-23 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118543518 | Feb | T2 CORTINA-MENDOCINO #1 51/248 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 051/248 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-02-17 | 2021-02-17 |  |  | 2021-02-19 | 2021-02-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.031889 | 39.2075 | ETL.1330 | 40870938 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118543556 | Feb | T2 CORTINA-MENDOCINO #1 34/165 RPR FOND | 44302218 | CORTINA-MENDOCINO #1 | 034/165 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-02-17 | 2021-02-17 |  |  | 2021-02-19 | 2021-02-16 |  |  | Likely MAT error - delink to correct | TR2 |  | North Coast | WSIP | [6 empty] | '-122.775849 | 39.0916 | ETL.1330 | 40750579 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118544026 | Q3 | BRIDGEVILE-COTTONWOOD 72/522R RPL POLE | 31497846 | BRIDGEVILLE-COTTONWOOD | 072/522 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-02-14 | 2021-02-14 |  |  | 2021-07-17 | 2021-06-21 |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-123.545146 | 40.4703 | ETL.1110 | 44512065 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-06-03 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118545246 | Q2 | HUMBOLDT-MAPLE CREEK 11/006 RPL PL | 31492615 | HUMBOLDT-MAPLE CREEK | 011/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-02-18 | 2021-02-18 |  |  | 2021-06-19 | 2021-06-14 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.918768 | 40.7613 | ETL.7130 | 40809422 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-08-06 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118546043 | Q2 | EI HUMBOLDT-BRIDGEVILE 108/1 RGT RPL PL | 31496089 | HUMBOLDT-BRIDGEVILLE | 108/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-07-10 | 2020-07-10 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-118.863225 | 35.2965 | ETL.1810 | 44322587 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-03-23 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-03-23 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118551837 | Feb | T2 JOLON TAP 3/37 RPR STRW FENCE | 44575318 | JOLON TAP | 003/037 | ICW | E | 2020_(2) High fire spread TD |  | 2020-02-20 | 2021-02-20 | 2021-02-22 | 2021-02-23 | 2021-02-23 | 2021-02-22 |  |  |  | TR2 | SCHD | South | WSIP | [6 empty] | '-121.171572 | 36.1679 | ETL.7321 | 40649734 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-03-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118552444 | Q2 | T2 TRINITY-MAPLE CREEK 6/13 RPL POLE | 31492616 | TRINITY-MAPLE CREEK | 006/013 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-02-20 | 2021-02-20 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.053455 | 40.7384 | ETL.8170 | 40906340 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-04-14 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-04-14 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118558637 | Mar | BLLT-RVRBNK-MLNS SW ST :15/8 RPL POLE | 31492502 | BELLOTA-RIVERBANK-MELONES SW STA | :015/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-02-21 | 2021-02-21 |  |  | 2021-03-05 | 2021-03-04 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.760854 | 37.8701 | ETL.1070 | 40857288 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 13 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-08-04 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118558695 | Not Scheduled | T2 DI MNDOCINO-RDBD #1 59/293 RPL INSS | 31530110 | MENDOCINO-REDBUD | 059/293 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-02-21 | 2021-02-21 | [7 empty] | TR2 | <15D | North Coast | WSIP | [6 empty] | '-123.181329 | 39.2418 | ETL.2410 | 40690028 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118559044 | Not Scheduled | T3 MONTE RIO-FULTON 10/0 RPL INSS | 31492628 | MONTE RIO-FULTON | 010/000 | 93I | E | 2020_(2) High fire spread TD |  | 2020-02-21 | 2020-08-21 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.9391902 | 38.4872 | ETL.7630 | 40628712 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-03-31 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118575868 | Mar | T2 PARKWAY-MORAGA 011/064 RPL HRDT |  | PARKWAY-MORAGA | 011/064 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-02-25 | 2021-02-25 |  |  | 2021-03-27 | 2021-03-22 |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.22211 | 37.9854 | ETL.5930 | 44768968 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118575961 | Feb | T2 BAHIA-MORAGA 14/82 RPLC HRDT | 43683410 | BAHIA-MORAGA | 014/082 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-02-25 | 2021-02-25 |  |  | 2021-02-24 | 2021-02-23 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.217859 | 37.9801 | ETL.4340 | 40611761 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118575962 | Mar | T2 PARKWAY-MORAGA 11/66 RPLC HRDT |  | PARKWAY-MORAGA | 011/066 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-02-25 | 2021-02-25 |  |  | 2021-03-27 | 2021-03-22 |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.217859 | 37.9801 | ETL.5930 | 40611760 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118575964 | Mar | T2 BAHIA-MORAGA 14/82 RPR SHLS/OPGW | 44245153 | BAHIA-MORAGA | 014/082 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-02-25 | 2021-02-25 | 2021-03-01 | 2021-03-05 | 2021-03-05 | 2021-03-01 |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.217859 | 37.9801 | ETL.4340 | 40611761 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118575990 | Not Scheduled | T2 PARKWAY-MORAGA 011/064 RPR SHLS | 44245151 | PARKWAY-MORAGA | 011/064 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-02-25 | 2021-02-25 | [7 empty] | TR2 | <15D | Central | WSIP | [6 empty] | '-122.22211 | 37.9854 | ETL.5930 | 44768968 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118576042 | Not Scheduled | T2 PARKWAY-MORAGA 011/064 INSTL DAMS | 44609773 | PARKWAY-MORAGA | 011/064 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-02-25 | 2021-02-25 | [7 empty] | TR2 | <15D | Central | WSIP | [6 empty] | '-122.22211 | 37.9854 | ETL.5930 | 44768968 | Damper-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118576241 | Mar | T2 BAHIA-MORAGA 14/82 RPLC DAMS | 44621442 | BAHIA-MORAGA | 014/082 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-02-25 | 2021-02-25 | 2021-03-01 | 2021-03-05 | 2021-03-05 | 2021-03-01 |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.217859 | 37.9801 | ETL.4340 | 40611761 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118576242 | Not Scheduled | T2 PARKWAY-MORAGA 11/66 RPLC DAMS | 44332287 | PARKWAY-MORAGA | 011/066 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-02-25 | 2021-02-25 | [7 empty] | TR2 | <15D | Central | WSIP | [6 empty] | '-122.217859 | 37.9801 | ETL.5930 | 40611760 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118576243 | Mar | T2 PARKWAY-MORAGA 11/67 RPLC HRDT |  | PARKWAY-MORAGA | 011/067 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-02-25 | 2021-02-25 |  |  | 2021-03-27 | 2021-03-22 |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.216207 | 37.978 | ETL.5930 | 40713873 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118576244 | Feb | T2 BAHIA-MORAGA 14/83 RPLC HRDT | 43683410 | BAHIA-MORAGA | 014/083 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-02-25 | 2021-02-25 |  |  | 2021-02-24 | 2021-02-23 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.216207 | 37.978 | ETL.4340 | 40713875 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118576245 | Mar | T2 PARKWAY-MORAGA 14/84 RPL HRDT | 44298735 | PARKWAY-MORAGA | 014/084 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-02-25 | 2021-02-25 |  |  | 2021-03-12 |  |  |  |  | TR2 | <15D | Central | WSIP | [6 empty] | '-122.205301 | 37.943 | ETL.5930 | 40890767 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-05-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118576248 | Not Scheduled | T2 PARKWAY-MORAGA 14/84 RPR SHLS | 44245151 | PARKWAY-MORAGA | 014/084 | ICS | E | 2020_(2) High fire spread TD |  | 2020-02-25 | 2021-02-25 | [7 empty] | TR2 | <15D | Central | WSIP | [6 empty] | '-122.205301 | 37.943 | ETL.5930 | 40890767 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118576596 | Mar | T2 BAHIA-MORAGA 14/83 RPR SHLS/OPGW | 44245153 | BAHIA-MORAGA | 014/083 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-02-25 | 2021-02-25 | 2021-03-01 | 2021-03-05 | 2021-03-05 | 2021-03-01 |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.216207 | 37.978 | ETL.4340 | 40713875 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118576900 | Mar | T2 BAHIA-MORAGA 14/83 RPLC DAMS | 44645362 | BAHIA-MORAGA | 014/083 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-02-25 | 2021-02-25 | 2021-03-01 | 2021-03-05 | 2021-03-05 | 2021-03-01 |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.216353 | 37.9782 | ETL.4340 | 45000991 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118581796 | Feb | T2 DRUM-RIO OSO # 212/114 RPR INSS | 44228282 | DRUM-RIO OSO #2 | 012/114 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-02-26 | 2021-02-26 |  |  | 2021-02-23 | 2020-12-14 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.957397 | 39.1609 | ETL.1430 | 40786138 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118585608 | Mar | T2 CNTRA CSTA-MORAGA#1 023/110 RPL INSS | 31526487 | CONTRA COSTA-MORAGA #1 | 023/110 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-02-27 | 2021-02-27 |  |  | 2021-03-23 | 2021-03-23 |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.113779 | 37.8585 | ETL.5452 | 44291683 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118585758 | Q2 | T2 ROND MTN-TABLE MTN #2 55/236 RPR SPLS | 44305720 | ROUND MTN-TABLE MTN #2 | 055/236 | ICS | E | 2020_(2) High fire spread TD |  | 2020-02-13 | 2021-02-13 |  |  | 2021-04-08 | 2021-01-12 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.866989 | 40.013 | ETL.6070 | 40820562 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-03-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118590002 | Feb | T2 JOLON TAP 2/026 RPL GYWW | 44650481 | JOLON TAP | 002/026 | ICW | E | 2020_(2) High fire spread TD |  | 2020-02-28 | 2021-02-28 | 2021-02-22 | 2021-02-23 | 2021-02-23 | 2021-02-22 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.172475 | 36.1874 | ETL.7321 | 40585799 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-03-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118593945 | Q2 | T2 DI PIT#1-COTTONWOOD 11/94 RPR CONS | 43879413 | PIT #1-COTTONWOOD | 011/094 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-02-28 | 2021-02-28 |  |  | 2021-05-31 | 2021-05-17 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.684753 | 40.8928 | ETL.5390 | 40762844 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-05-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118598941 | Not Scheduled | T3 DI MIDDLE FORK #1 9/126 RPLC INSW | 31493812 | MIDDLE FORK #1 | 009/126 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-03-02 | 2020-09-02 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.737811 | 39.0039 | ETL.8405 | 44650051 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  | Yes | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-03-10 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118600451 | Mar | T3 EI MORAGA-OAKLAND #2 00/07 RPL INSS | 31506692 | MORAGA-OAKLAND #2 | 000/007 | 93K | E | 2020_(2) High fire spread TD |  | 2020-03-03 | 2020-09-03 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.1768427 | 37.8442 | ETL.2730 | 40828515 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-26 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118600509 | Mar | T3 EI MORAGA-OAKLAND #4 0/8 REPL INSS | 31508630 | MORAGA-OAKLAND #4 | 000/008 | 93K | E | 2020_(2) High fire spread TD |  | 2020-03-03 | 2020-09-03 | 2021-03-28 | 2021-03-30 | 2021-03-30 | 2021-03-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.176291 | 37.844 | ETL.2750 | 40898131 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y- 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-26 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118600893 | Mar | T3 EI MORAGA-OAKLAND #3 1/9 REPL INSS | 31504796 | MORAGA-OAKLAND #3 | 001/009 | 93K | E | 2020_(2) High fire spread TD |  | 2020-03-03 | 2021-05-31 | 2021-03-28 | 2021-03-30 | 2021-03-30 | 2021-03-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.177789 | 37.8431 | ETL.2740 | 40878738 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 12 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | 93 | Mar |  |  | 2020-06-26 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118601460 | Not Scheduled | T2 COLGATE-SMARTVILLE #2 08/100 RPL POLE | 31493813 | COLGATE-SMARTVILLE #2 | 008/100 | 70Y | E | 2020_(1a) PSPS |  | 2020-03-03 | 2021-03-03 | [7 empty] | TR2 | <15D | North Valley | WSIP | [6 empty] | '-121.295814 | 39.2389 | ETL.6520 | 40594280 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-22 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 118602344 | Not Scheduled | T3 EI MORAGA-OAKLAND #3 1/9 REPAINT | 43725286 | MORAGA-OAKLAND #3 | 001/009 | ICS | F | 2020_(3) On high spread structure |  | 2020-03-03 | 2022-09-03 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.178464 | 37.8431 | ETL.2740 | 40857636 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118602558 | Q4 | T2 KESWICK-TRINITY 15/183A REPL ANCHOR | 31494691 | KESWICK-TRINITY | 015/183A | 93E | E | 2020_(2) High fire spread TD |  | 2020-03-04 | 2021-03-04 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.67028 | 40.7103 | ETL.7270 | 40827887 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-07-24 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118602596 | Q4 | T2 KESWICK-TRINITY 15/193 REPL ANCHOR | 31494691 | KESWICK-TRINITY | 015/193 | 93E | E | 2020_(2) High fire spread TD |  | 2020-03-04 | 2021-03-04 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.673623 | 40.7154 | ETL.7270 | 40827889 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-07-24 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118602997 | Not Scheduled | EI T3NT MORAGA-OAKLAND #1 001/008 REPAIN | 43744382 | MORAGA-OAKLAND #1 | 001/008 | ICS | F | 2020_(3) On high spread structure |  | 2020-03-03 | 2022-03-03 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.178678 | 37.8431 | ETL.2720 | 40870714 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118603025 | Mar | T3 EI MORAGA-OAKLAND #1 001/008 RPL INSS | 31504785 | MORAGA-OAKLAND #1 | 001/008 | 93K | E | 2020_(2) High fire spread TD |  | 2020-03-03 | 2021-05-31 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.178195 | 37.8435 | ETL.2720 | 40895764 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | 93 | Mar |  |  | 2020-06-26 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118603242 | Not Scheduled | T2 SAN LUIS OBISPO-CAYUCOS 5/33 REPL PL | 31494257 | SAN LUIS OBISPO-CAYUCOS | 005/033 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-03-04 | 2021-03-04 | [7 empty] | TR2 | <30D | South | WSIP | [6 empty] | '-120.654282 | 35.3142 | ETL.9090 | 44565351 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-03-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118603403 | Not Scheduled | EI T3NT MORAGA-OAKLAND #1 001/010 REPAIN | 43744382 | MORAGA-OAKLAND #1 | 001/010 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-03-04 | 2022-03-04 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.187276 | 37.8382 | ETL.2720 | 40581554 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118603454 | Not Scheduled | T2 SAN LUIS OBISPO-CYCS 5/37 REPL POLE | 31494257 | SAN LUIS OBISPO-CAYUCOS | 005/037 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-03-04 | 2021-03-04 | [7 empty] | TR2 | <30D | South | WSIP | [6 empty] | '-120.658954 | 35.3161 | ETL.9090 | 44565337 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-03-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118603530 | Q3 | T3 DONNELLS-MI-WUK 018/003L RPL POLE | 31494673 | DONNELLS-CURTIS | 018/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-03-04 | 2020-09-04 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.21401 | 38.0548 | ETL.1400 | 44774113 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor |  | Y - 40 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-06-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118604143 | Q3 | T2 CARIBOU #2 15/016 REPL ANCW | 31494689 | CARIBOU #2 | 015/016 | 93E | E | 2020_(2) High fire spread TD |  | 2020-03-04 | 2021-03-04 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.103577 | 40.0194 | ETL.6280 | 40826420 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-04-01 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118604263 | Not Scheduled | T2 SAN LUIS OBISPO-CYCS 5/37 REPL POLE | 31494257 | SAN LUIS OBISPO-CAYUCOS | 005/037 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-03-04 | 2021-03-04 | [7 empty] | TR2 | <30D | South | WSIP | [6 empty] | '-120.658954 | 35.3161 | ETL.9090 | 44565369 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-03-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118604906 | Before Feb | LOS BANOS-GATES #1 68/285 REPL DAMPS | 44301827 | LOS BANOS-GATES #1 | 068/285 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-03-04 | 2021-03-04 | 2020-07-06 | 2020-08-19 | 2020-08-19 | 2020-07-06 |  | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | WECC | South | WSIP | [6 empty] | '-120.268235 | 36.2892 | ETL.6000 | 40765394 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Before Feb | Found in 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2020-06-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118604994 | Not Scheduled | T2 CAYUCOS-CAMBRIA 11/070 BOND GUYS |  | CAYUCOS-CAMBRIA | 011/070 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-03-04 | 2021-05-31 | [7 empty] | TR2 | <30D | South | WSIP | [6 empty] | '-121.009485 | 35.5409 | ETL.8560 | 40588563 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-03-12 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118605416 | Q3 | T3 DONNELLS-MI-WUK 11/00L RPL POLE | 31494253 | DONNELLS-CURTIS | 011/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-03-04 | 2020-09-04 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.125168 | 38.1249 | ETL.1400 | 44770788 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 40 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-04-23 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118605706 | Q3 | DONNELLS-MI-WUK 018/003R RPLC STRW | 31494673 | DONNELLS-CURTIS | 018/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-03-04 | 2021-03-04 |  |  | 2021-09-07 | 2021-08-07 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.21401 | 38.0548 | ETL.1400 | 44774119 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 40 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-06-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118605707 | Mar | T3 MORAGA-OAKLAND#2 1/8 RPLC INSS | 31506692 | MORAGA-OAKLAND #2 | 001/008 | 93K | E | 2020_(2) High fire spread TD |  | 2020-03-03 | 2021-05-31 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.178195 | 37.8435 | ETL.2730 | 40895766 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | 93 | Mar |  |  | 2020-06-26 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118606093 | Not Scheduled | T2 SAN LUIS OBISPO-CAYUCOS 5/33 REPL PL | 31494257 | SAN LUIS OBISPO-CAYUCOS | 005/033 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-03-04 | 2021-03-04 | [7 empty] | TR2 | <30D | South | WSIP | [6 empty] | '-120.654282 | 35.3142 | ETL.9090 | 44565529 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-03-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118615220 | Feb | IGNACIO-MARE ISLAND #1 10/77 RPR BAYW | 44176145 | IGNACIO-MARE ISLAND #1 | 010/077 | ICJ | B | 2020_(0) A and B Tags |  | 2020-03-05 | 2021-01-21 |  |  | 2021-02-28 | 2021-02-08 | [5 empty] | North Coast | WSIP |  |  |  |  | Readiness | ENV Restrictions review; Must have Bio Monitor onsite | '-122.380093 | 38.1526 | ETL.1830 | 43249843 | Bay Water-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 510 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Already Past Due | IC | Feb |  |  | 2020-08-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 118640162 | Q3 | T3 DONNELLS-MI-WUK 11/00L RPL POLE | 31494253 | DONNELLS-CURTIS | 011/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-03-04 | 2020-09-04 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.125168 | 38.1249 | ETL.1400 | 44770789 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 40 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-04-23 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118676332 | Q2 | T2 GARBERVILLE-LAYTONVILLE 25/7 RPR STRW | 44311204 | GARBERVILLE-LAYTONVILLE | 025/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-03-10 | 2021-03-10 |  |  | 2021-05-17 | 2021-04-19 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.492136 | 39.7247 | ETL.8365 | 40808444 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-03-12 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-03-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118676861 | Not Scheduled | `2 ROUND MTN-TABLE MTN #1 17/93 RPR FOND | 43848514 | ROUND MTN-TABLE MTN #1 | 017/093 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-03-10 | 2021-03-10 | [7 empty] | TR2 | <30D | North Valley | WSIP | [6 empty] | '-121.944379 | 40.5511 | ETL.6060 | 40663121 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118677432 | Q2 | T2 MELONES-CURTIS 9/3 RPR GYWW | 44623201 | MELONES-CURTIS | 009/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-03-10 | 2021-03-10 |  |  | 2021-04-02 | 2021-03-02 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.403585 | 37.9428 | ETL.2390 | 44391058 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 18 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-03-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118679100 | Mar | HUMBOLDT-TRINITY 064/000 RPL POLE | 31494734 | HUMBOLDT-TRINITY | 064/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-07-06 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.230802 | 40.7363 | ETL.1820 | 44562888 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-27 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2020-05-27 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118679102 | Mar | HUMBOLDT-TRINITY 064/000 RPL POLE | 31494734 | HUMBOLDT-TRINITY | 064/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-07-06 | 2021-05-31 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.230802 | 40.7363 | ETL.1820 | 44562936 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-27 | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Mar | 70 | Mar |  |  | 2020-05-27 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118679805 | Mar | T3 EAGLE ROCK-CORTINA :7/40 RPL INSS | 31479500 | EAGLE ROCK-CORTINA | :007/040 | 93K | E | 2020_(2) High fire spread TD |  | 2020-03-11 | 2020-09-11 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7128763 | 38.8816 | ETL.1470 | 40629623 | Insulator-Steel | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118679828 | Mar | T3 EAGLE ROCK-CORTINA :7/42 RPL INSS | 31479500 | EAGLE ROCK-CORTINA | :007/042 | 93K | E | 2020_(2) High fire spread TD |  | 2020-03-11 | 2020-09-11 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7072807 | 38.8815 | ETL.1470 | 40716617 | Insulator-Steel | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118679877 | Feb | T2 ROCK CREEK-POE 5/042 RPL INSS | 31454863 | ROCK CREEK-POE | 005/042 | 93K | E | 2020_(2) High fire spread TD |  | 2020-03-11 | 2021-03-11 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.402278 | 39.8516 | ETL.5630 | 40671054 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118681268 | Not Scheduled | T3 MIDDLE FORK #1 2/043B RPR GYWW | 44261830 | MIDDLE FORK #1 | 002/043B | ICW | E | 2020_(2) High fire spread TD |  | 2020-03-11 | 2020-09-11 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.625071 | 39.0014 | ETL.8405 | 42569704 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118681295 | Not Scheduled | T3 MIDDLE FORK #1 2/43A RPR GYWW | 44261830 | MIDDLE FORK #1 | 002/043A | ICW | E | 2020_(2) High fire spread TD |  | 2020-03-11 | 2020-09-11 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.625074 | 39.0014 | ETL.8405 | 40822833 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118681702 | Q2 | T3 SNEATH LANE-HMB ?7/1 RPL ANCW | 31475188 | SNEATH LANE-HALF MOON BAY | ?007/001 | 93E | E | 2020_(2) High fire spread TD |  | 2020-03-11 | 2020-09-11 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.436739 | 37.5331 | ETL.7212 | 40599243 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  |  | Scarper Ridge | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118682727 | Feb | T2 RIO DELL JCT-BRIDGEVILL 33/7 RPR STRW | 44261478 | RIO DELL JCT-BRIDGEVILLE | 033/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-03-12 | 2021-03-12 |  |  | 2021-02-27 | 2021-02-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.895707 | 40.4842 | ETL.7850 | 40808358 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118715724 | Q2 | T3 OLEUM-G #1 8/55 RPL INSS | 31503752 | OLEUM-G #1 | 008/055 | 93K | E | 2020_(2) High fire spread TD |  | 2020-03-17 | 2020-09-17 | 2021-05-13 | 2021-05-14 | 2021-05-14 | 2021-05-13 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.2717968 | 37.9449 | ETL.3150 | 40774775 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-06-15 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118715784 | Not Scheduled | T2 KESWICK-TRINITY 17/223 CANCEL | 31422860 | KESWICK-TRINITY | 017/223 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-03-17 | 2021-05-31 | [7 empty] | TR2 | <30D | North Valley | WSIP | [6 empty] | '-122.697592 | 40.7214 | ETL.7270 | 40770390 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-06-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118724076 | Q2 | T2 SNEATH LANE-PACIFICA 4/52 REPL POLE | 31497878 | SNEATH LANE-PACIFICA | 004/052 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-03-19 | 2021-03-19 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.456143 | 37.6142 | ETL.7575 | 40864576 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118725649 | Not Scheduled | EI T3NT SNEATH LANE-PACFCA 5/60 RMV VEGN |  | SNEATH LANE-PACIFICA | 005/060 | CHS | F | 2020_(3) On high spread structure |  | 2020-03-19 | 2022-03-19 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.460381 | 37.6047 | ETL.7575 | 40825064 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118734897 | Q3 | DONNELLS-CURTIS 7/6 RPR GYWW | 44303617 | DONNELLS-CURTIS | 007/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-03-23 | 2021-03-23 |  |  | 2021-09-07 | 2021-08-07 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.100016 | 38.1685 | ETL.1400 | 44402507 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-06-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118735041 | Q3 | DONNELLS-CURTIS 7/6 RPR GYWW | 44303617 | DONNELLS-CURTIS | 007/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-03-23 | 2021-03-23 |  |  | 2021-09-07 | 2021-08-07 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.100016 | 38.1685 | ETL.1400 | 44560756 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-06-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118736659 | Not Scheduled | T2 SPAULDING-SUMMIT 1/47 REFRAME | 31498188 | SPAULDING-SUMMIT | 001/047 | 93E | E | 2020_(1b) Lines with special commitments |  | 2020-03-24 | 2021-03-24 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624789 | 39.3184 | ETL.8060 | 40618280 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118738216 | Not Scheduled | T2 DIABLO-MIDWAY #2 40/163 RPL INSS | 31500466 | DIABLO-MIDWAY #2 | 040/163 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-03-20 | 2021-03-20 | [7 empty] | TR2 | <60D | South | WSIP | [6 empty] | '-120.155834 | 35.1958 | ETL.5970 | 40694500 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 19 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-04-06 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118738521 | Q2 | T3 EI SNEATH LANE-HMB ?9/1 RPL STRW | 31498311 | SNEATH LANE-HALF MOON BAY | ?009/001 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-03-24 | 2020-09-24 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.424373 | 37.5067 | ETL.7212 | 40599265 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 29 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-24 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118742291 | Not Scheduled | DI MORAGA-OAKLAND #3 004/033 RPLC HRDT |  | MORAGA-OAKLAND #3 | 004/033 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-03-24 | 2021-03-24 | [8 empty] | <60D | Central | WSIP | [6 empty] | '-122.218923 | 37.8128 | ETL.2740 | 40645288 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-08 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118743451 | Q2 | T3 SNEATH LANE-HMB ?9/0 RPL ANCW | 31498312 | SNEATH LANE-HALF MOON BAY | ?009/000 | 93E | E | 2020_(2) High fire spread TD |  | 2020-03-25 | 2020-09-25 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [8 empty] | ETL.7212 | 44384379 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  | Y - 29 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-06-24 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118743554 | Q2 | T3 SNEATH LANE-HMB ?9/0 RPL ANCW | 31498312 | SNEATH LANE-HALF MOON BAY | ?009/000 | 93E | E | 2020_(2) High fire spread TD |  | 2020-03-25 | 2020-09-25 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [8 empty] | ETL.7212 | 44384377 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  | Y - 29 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-06-24 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118743556 | Q2 | T3 SNEATH LANE-HMB ?9/0 RPL ANCW | 31498312 | SNEATH LANE-HALF MOON BAY | ?009/000 | 93E | E | 2020_(2) High fire spread TD |  | 2020-03-25 | 2020-09-25 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [8 empty] | ETL.7212 | 44384378 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  | Y - 29 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-06-24 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118744621 | Q2 | T3 EI CRESTA-RIO OSO 15/123 RPL INSS | 31500129 | CRESTA-RIO OSO | 015/123 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-03-25 | 2020-09-25 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.475167 | 39.7551 | ETL.4590 | 40910142 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118744622 | Feb | T3 EI ROCK CREEK-POE 13/095 RPL CONN |  | ROCK CREEK-POE | 013/095 | ICM | E | 2020_(4) TD tag on high spread line |  | 2020-03-25 | 2020-09-25 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.475511 | 39.7552 | ETL.5630 | 40762419 | Connector | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | GDP | Maintenance | Expense | 534 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118745474 | Not Scheduled | T2 PIT #1-COTTONWOOD 42/360 RPR INSS | 43879413 | PIT #1-COTTONWOOD | 042/360 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-03-25 | 2021-03-25 | [7 empty] | TR2 | <60D | North Valley | WSIP | [6 empty] | '-122.0909851 | 40.6088 | ETL.5390 | 40636928 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118745996 | Q2 | HUMBOLDT-BRIDGEVILLE 99/5L RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 099/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-03-25 | 2021-03-25 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-119.777778 | 36.7846 | ETL.1810 | 44322419 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-11 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118747283 | Not Scheduled | T3 EI ROCK CREEK-POE 14/97 RPR SOIL |  | ROCK CREEK-POE | 014/097 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-03-26 | 2020-09-26 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.476379 | 39.7492 | ETL.5630 | 40815393 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118747750 | Q2 | T2 HAT CREEK #1-WESTWOOD 4/96 RPR HRDW | 43904280 | HAT CREEK #1-WESTWOOD | 004/096 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-03-26 | 2021-03-26 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.453323 | 40.9126 | ETL.7030 | 40815933 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118747950 | Q2 | T2 HAT CREEK #1-WESTWOOD 0/4 RPR POLE | 43904280 | HAT CREEK #1-WESTWOOD | 000/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-03-26 | 2021-03-26 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.542565 | 40.9283 | ETL.7030 | 44741489 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118748010 | Q2 | T3 GEYSERS #17-FULTON 13/056 RPL INSS | 31505661 | GEYSERS #17-FULTON | 013/056 | 93K | E | 2020_(2) High fire spread TD |  | 2020-03-26 | 2020-09-26 | 2021-01-18 | 2021-01-21 | 2021-05-08 | 2021-05-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.760611 | 38.6653 | ETL.4770 | 44859240 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118748366 | Q2 | HUMBOLDT-BRIDGEVILLE 099/005R RPL STRW | 31497841 | HUMBOLDT-BRIDGEVILLE | 099/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-03-24 | 2021-03-24 |  |  | 2021-05-22 | 2021-05-03 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-122.224337 | 38.0042 | ETL.1810 | 44322420 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-11 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118748701 | Q2 | T3 EI CRESTA-RIO OSO 16/130 RPL INSS | 31500129 | CRESTA-RIO OSO | 016/130 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-03-26 | 2020-09-26 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.477186 | 39.7418 | ETL.4590 | 40910147 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118753236 | Q2 | T3 FULTON-PUEBLO 31/153 RPR FOND | 44306536 | FULTON-PUEBLO | 031/153 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-03-27 | 2020-09-27 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.552458 | 38.4861 | ETL.1600 | 40648677 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118755973 | Q2 | T3 EI CRESTA-RIO OSO 17/140 RPR CNDS | 44305195 | CRESTA-RIO OSO | 017/140 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-03-30 | 2020-09-30 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.48005 | 39.7241 | ETL.4590 | 40910156 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118756013 | Feb | T3 EI ROCK CREEK-POE 15/107 RPL INSS | 31500380 | ROCK CREEK-POE | 015/107 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-03-30 | 2020-09-30 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.480524 | 39.7234 | ETL.5630 | 40821648 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-02-12 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118758386 | Not Scheduled | T2 TGER CRK-VLLY SPRINGS 11/90 RPR STRS | 44631103 | TIGER CREEK-VALLEY SPRINGS | 011/090 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-03-31 | 2021-03-31 | [7 empty] | TR2 | <60D | Central | WSIP | [6 empty] | '-120.653421 | 38.3568 | ETL.5790 | 40585747 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 11 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-04-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118761449 | Q2 | T3NT TIGER CREEK-ELECTRA 6/50 RPR FOND |  | TIGER CREEK-ELECTRA | 006/050 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-03-31 | 2022-03-30 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.595035 | 38.4179 | ETL.5780 | 40604806 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-04-10 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118763749 | Not Scheduled | T2 WEST POINT-VLY SPRINGS 9/107 RPL STRW | 31498708 | WEST POINT-VALLEY SPRINGS | 009/107 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-01 | 2021-04-01 | [7 empty] | TR2 | <60D | Central | WSIP | [6 empty] | '-120.662012 | 38.3464 | ETL.8350 | 44907040 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-14 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118764774 | Q2 | T3 EI CRESTA-RIO OSO 14/121 RPR CNDS | 44305195 | CRESTA-RIO OSO | 014/121 | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-01 | 2020-10-01 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.471118 | 39.7587 | ETL.4590 | 40910140 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118767180 | Not Scheduled | T2 WEST POINT-VLLY SPRNGS 5/65C RPL POLE | 31498708 | WEST POINT-VALLEY SPRINGS | 005/065C | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-01 | 2021-04-01 | [7 empty] | TR2 | <60D | Central | WSIP | [6 empty] | '-120.633879 | 38.3896 | ETL.8350 | 42833791 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-28 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118767184 | Mar | T2 BLTA-RIVERBANK-MLNS SS :2/6 RPR STRW | 44303610 | BELLOTA-RIVERBANK-MELONES SW STA | :002/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-01 | 2021-04-01 |  |  | 2021-03-05 | 2021-03-04 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.533318 | 37.9089 | ETL.1070 | 40822207 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 15 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118767331 | Q2 | T3 MORAGA-SAN LEANDRO #2 0/6 RPL INSS | 31505512 | MORAGA-SAN LEANDRO #2 | 000/006 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-01 | 2020-10-01 |  |  | 2021-05-27 | 2021-05-26 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.1644898 | 37.8361 | ETL.2780 | 40850662 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118770952 | Q2 | T3 DI CASTRO VALLEY-NEWARK 5/29 RPL INSS | 31504845 | CASTRO VALLEY-NEWARK | 005/029 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-02 | 2020-10-02 |  |  | 2021-05-18 | 2021-05-17 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.97615 | 37.01 | ETL.4450 | 44394311 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-06 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118771614 | Q2 | T2 SNEATH LANE-HMB ?11/4 RPL INSS |  | SNEATH LANE-HALF MOON BAY | ?011/004 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-02 | 2021-04-02 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.4203129 | 37.4744 | ETL.7212 | 40850594 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 29 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-06-24 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118771916 | Mar | CORTINA-VACA 17/113 RPL LADDER | 44295441 | CORTINA-VACA | 017/113 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-04-02 | 2021-04-02 |  |  | 2021-03-18 | 2021-03-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.079737 | 38.8878 | ETL.4540 | 40865836 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118773113 | Not Scheduled | T3NT DI TGR CRK-VLY SPNGS 8/063 RPR FOND |  | TIGER CREEK-VALLEY SPRINGS | 008/063 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-01 | 2022-04-01 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-120.621343 | 38.3988 | ETL.5790 | 40753070 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-04-29 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118775137 | Q2 | PIT #1-COTTONWOOD 50/447 RPL TOWER | 31474087 | PIT #1-COTTONWOOD | 050/447 | 70S | E | 2020_(2) High fire spread TD |  | 2020-04-03 | 2021-04-03 |  |  | 2021-05-13 | 2021-04-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.175877 | 40.5065 | ETL.5390 | 40816480 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-05-28 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118775787 | Q2 | T3 EI CRESTA-RIO OSO 14/116 RPL INSS | 31500129 | CRESTA-RIO OSO | 014/116 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-03 | 2020-10-03 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.465144 | 39.7629 | ETL.4590 | 40910137 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118778522 | Mar | T3 DI MRAGA-SAN LEANDRO #3 3/29 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 003/029 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-03 | 2022-10-03 |  |  | 2021-03-13 | 2021-03-08 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.130327 | 37.802 | ETL.2790 | 40861007 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118778524 | Mar | T3 DI MRAGA-SAN LEANDRO #3 3/29 INS HRDT |  | MORAGA-SAN LEANDRO #3 | 003/029 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-04-03 | 2020-10-03 |  |  | 2021-03-13 | 2021-03-08 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.130327 | 37.802 | ETL.2790 | 40861007 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118778932 | Not Scheduled | T3 DI TIGER CRK 8/064 RPR STRT |  | TIGER CREEK-ELECTRA | 008/064 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-06 | 2020-10-06 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.621524 | 38.3989 | ETL.5780 | 40752893 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-05 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118779405 | Not Scheduled | T3 FULTON-CALISTOGA :6/7 RPR GYWW | 44305659 | FULTON-CALISTOGA | :006/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-06 | 2020-10-06 | 2020-06-07 | 2020-06-16 | [5 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.589498 | 38.6794 | ETL.6880 | 40912477 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118779421 | Not Scheduled | T3 FULTON-CALISTOGA :6/3 RPR GYWW | 44305659 | FULTON-CALISTOGA | :006/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-06 | 2020-10-06 | 2020-06-07 | 2020-06-16 | [5 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.587414 | 38.6737 | ETL.6880 | 40912473 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118780058 | Feb | T2 DRUM-RIO OSO #1 20/161 INST JMPS | 44295442 | DRUM-RIO OSO #1 | 020/161 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-04-06 | 2021-04-06 |  |  | 2021-02-23 | 2020-12-14 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.093121 | 39.1071 | ETL.1420 | 40594933 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118781666 | Mar | T3 DI MORAGA-OAKLAND #1 2/16 RPR SPLS | 44621662 | MORAGA-OAKLAND #1 | 002/016 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-04-06 | 2020-10-06 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.198084 | 37.832 | ETL.2720 | 40822215 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118781667 | Feb | T3 DI MORAGA-OAKLAND #1 2/16 RPR STRS |  | MORAGA-OAKLAND #1 | 002/016 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-04-06 | 2020-10-06 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.198084 | 37.832 | ETL.2720 | 40822215 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-08 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118782271 | Q4 | T3 EI KESWICK-TRINITY 3/57 RPR STRW | 43939188 | KESWICK-TRINITY | 003/057 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-07 | 2020-10-07 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.520258 | 40.6163 | ETL.7270 | 40770362 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118782304 | Mar | T3 DI MORAGA-OAKLAND #1 1/9 RPL INSS | 31504785 | MORAGA-OAKLAND #1 | 001/009 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-07 | 2020-10-07 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.182487 | 37.841 | ETL.2720 | 40878730 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-26 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118782507 | Q4 | T3 EI KESWICK-TRINITY 2/46 REFRAME | 31499732 | KESWICK-TRINITY | 002/046 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-04-07 | 2020-10-07 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.504841 | 40.6163 | ETL.7270 | 40741744 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-06-08 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118782579 | Q2 | T3 DI TASSAJARA-NEWARK 18/87 RPL INSS | 31484762 | TASSAJARA-NEWARK | 018/087 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-07 | 2020-10-07 |  |  | 2021-05-20 | 2021-05-19 |  | Structure Number incorrect |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.952408 | 37.61 | ETL.5920 | 40634572 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118782732 | Q2 | DI CASTRO VALLEY-NEWARK 015/080 RPR INSS | 44144893 | CASTRO VALLEY-NEWARK | 015/080 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-04-06 | 2021-04-06 |  |  | 2021-05-18 | 2021-05-17 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-121.891078 | 37.5459 | ETL.4450 | 40870674 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118782793 | Q4 | T3 EI KESWICK-TRINITY 2/43 RPL CRSW | 31499732 | KESWICK-TRINITY | 002/043 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-04-07 | 2020-10-07 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.50221 | 40.6165 | ETL.7270 | 40752197 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-07-24 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118786797 | Q2 | T3 DI MORAGA-SAN LEANDRO #3 0/3 RPL INSS | 31504873 | MORAGA-SAN LEANDRO #3 | 000/003 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-07 | 2020-10-07 | 2021-04-01 |  | 2021-04-02 | 2021-04-01 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.162805 | 37.8426 | ETL.2790 | 40671359 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118786798 | Mar | T3 DI MORAGA-OAKLAND ""J"" 0/3 RPL INSS | 31511127 | MORAGA-OAKLAND "J" | 000/003 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-07 | 2020-10-07 |  |  | 2021-03-31 | 2021-03-31 |  | Split Tag - Hanger and Insulator |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.162805 | 37.8426 | ETL.2760 | 40671361 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118795568 | Q2 | T2 DI TSSJR-NWRK 20/92 RPLC CONN | 44621453 | TASSAJARA-NEWARK | 020/092 | ICM | E | 2020_(4) TD tag on high spread line |  | 2020-04-07 | 2021-04-07 |  |  | 2021-05-20 | 2021-05-19 |  | Work calls for different Structure number |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-121.926362 | 37.5934 | ETL.5920 | 40791096 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Bay |  |  | SFWL | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118795593 | Not Scheduled | T3NT DI MORAGA-SAN LENDR #1 0/3 PNT STRS | 43708450 | MORAGA-SAN LEANDRO #1 | 000/003 | ICS | F | 2020_(3) On high spread structure |  | 2020-04-07 | 2022-04-07 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.163595 | 37.8423 | ETL.2770 | 40644205 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118796372 | Q4 | T3 EI KESWICK-TRINITY 0/1 RPL CRSW | 31499718 | KESWICK-TRINITY | 000/001 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-04-08 | 2020-10-08 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.462303 | 40.6239 | ETL.7270 | 40586337 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-06-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118796470 | Q4 | T3 EI KESWICK-TRINITY 0/12 RPL STRW | 31499719 | KESWICK-TRINITY | 000/012 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-08 | 2020-10-08 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.464214 | 40.6191 | ETL.7270 | 40867097 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-06-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118796892 | Q2 | T2 BRIDGEVILLE-COTTONWOOD 22/195L RPL PL | 31499714 | BRIDGEVILLE-COTTONWOOD | 022/195 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-08 | 2021-04-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.685083 | 40.3748 | ETL.1110 | 44423403 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118796899 | Q4 | T3 EI KESWICK-TRINITY 1/26 RPL PL | 31499719 | KESWICK-TRINITY | 001/026 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-08 | 2020-10-08 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.478112 | 40.6185 | ETL.7270 | 40668374 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-06-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118797383 | Q2 | T2 GARBERVILLE-LYTNVL 32/0 RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 032/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-08 | 2021-04-08 |  |  | 2021-05-17 | 2021-04-19 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.542347 | 39.801 | ETL.8365 | 40587729 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118900119 | Feb | T3 EI EAGLE ROCK-FULTON-SLVRD 1/10 RPR S | 44310477 | EAGLE ROCK-FULTON-SILVERADO | 001/010 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-04-09 | 2020-10-09 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.800903 | 38.8166 | ETL.4392 | 40605188 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118909625 | Not Scheduled | T2 BELDEN TAP 0/1A RPL STRT | 31500088 | BELDEN TAP | 000/001A | 70S | F | 2020_(2) High fire spread TD |  | 2020-04-10 | 2022-04-10 |  |  |  | 2021-03-24 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.250817 | 40.0077 | ETL.4441 | 43198032 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118911013 | Not Scheduled | T3 EI COLGATE-ALLEGHANY A5/134 RPL POLE | 31509242 | COLGATE-ALLEGHANY | A005/134 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-10 | 2020-10-10 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.101517 | 39.3319 | ETL.6470 | 42568584 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118911578 | Q2 | T3 DI MORAGA-SN LNDRO#1 01/11 RPR CONS | 44621664 | MORAGA-SAN LEANDRO #1 | 001/011 | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-10 | 2020-10-10 |  |  | 2021-05-25 | 2021-05-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.155406 | 37.8289 | ETL.2770 | 40594276 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118911727 | Q2 | GARBERVILLE-LAYTONVILLE 39/8 RPL STRW | 31500085 | GARBERVILLE-LAYTONVILLE | 039/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-10 | 2021-04-10 |  |  | 2021-05-17 | 2021-04-19 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.580915 | 39.8901 | ETL.8365 | 40906634 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118912485 | Q2 | T3 EI CRESTA-RIO OSO 20/167 RPL INSS | 31500129 | CRESTA-RIO OSO | 020/167 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-11 | 2020-10-11 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.494387 | 39.674 | ETL.4590 | 40910178 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118912486 | Q2 | T3 EI CRESTA-RIO OSO 20/167 RMV NEST | 44305195 | CRESTA-RIO OSO | 020/167 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-04-11 | 2020-10-11 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.494387 | 39.674 | ETL.4590 | 40910178 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118913232 | Not Scheduled | DRUM-SUMMIT #2 16/194A RPL POLE | 31451466 | DRUM-SUMMIT #2 | 016/194A | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-04-08 | 2021-04-08 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.516404 | 39.3147 | ETL.1450 | 40822544 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118913261 | Not Scheduled | DRUM-SUMMIT #2 14/169A RPL POLE | 31521945 | DRUM-SUMMIT #2 | 014/169A | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-04-08 | 2021-04-08 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.544928 | 39.3145 | ETL.1450 | 40878359 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118913262 | Not Scheduled | DRUM-SUMMIT #2 14/169B RPL POLE | 31521945 | DRUM-SUMMIT #2 | 014/169B | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-04-08 | 2021-04-08 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.54497 | 39.3144 | ETL.1450 | 42572802 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118913263 | Not Scheduled | DRUM-SUMMIT #2 14/169C RPL POLE | 31521945 | DRUM-SUMMIT #2 | 014/169C | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-04-08 | 2021-04-08 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.545019 | 39.3144 | ETL.1450 | 42572803 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118913264 | Not Scheduled | DRUM-SUMMIT #2 16/194B RPL STRW | 31451466 | DRUM-SUMMIT #2 | 016/194B | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-04-08 | 2021-04-08 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.516427 | 39.3147 | ETL.1450 | 42572822 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118913265 | Not Scheduled | DRUM-SUMMIT #2 16/194C RPL STRW | 31451466 | DRUM-SUMMIT #2 | 016/194C | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-04-13 | 2021-04-13 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.516471 | 39.3148 | ETL.1450 | 42572823 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118913773 | Not Scheduled | T2 MNT RIO-FRT RSS 25/3 RPL ANCW | 31500206 | ETL.6979.POLE.WOOD | 025/003 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-04-13 | 2021-04-13 | [7 empty] | TR2 | <60D | North Coast | WSIP | [6 empty] | '-123.181729 | 38.4936 | ETL.6979 | 40648464 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118914363 | Mar | T3 MONTA VISTA-JFFRSN #1 15/61 RPL INSS | 31529798 | MONTA VISTA-JEFFERSON #1 | 015/061 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-13 | 2020-10-13 |  |  | 2021-03-05 | 2021-02-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | 122.2175 | 37.3239 | ETL.5220 | 40619159 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 10 | RROSP | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-13 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118914525 | Q3 | T3 EI BRIDGEVILLE-GARBERVILLE 9/17 RPR J | 44300097 | BRIDGEVILLE-GARBERVILLE | 009/017 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-13 | 2020-10-13 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.731007 | 40.3669 | ETL.6220 | 40810333 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118914526 | Q3 | T3 EI BRIDGEVILLE-GARBERVILLE 9/17 RPR S | 44299806 | BRIDGEVILLE-GARBERVILLE | 009/017 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-13 | 2020-10-13 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.731007 | 40.3669 | ETL.6220 | 40810333 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118914527 | Q3 | EI T3NT BRIDGEVILLE-GRBRVLE 9/17 RMV DEB | 44299809 | BRIDGEVILLE-GARBERVILLE | 009/017 | ICW | F | 2020_(3) On high spread structure |  | 2020-04-13 | 2022-04-13 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.731007 | 40.3669 | ETL.6220 | 40810333 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118914829 | Feb | T3 DI MORAGA-CASTR VLY 10/43 INST HRDT | 44623422 | MORAGA-CASTRO VALLEY | 010/043 | ICQ | E | 2020_(3) On high spread structure |  | 2020-04-13 | 2020-10-13 |  |  | 2021-02-20 | 2021-02-15 |  |  |  | TR3 | LATE | Central | WSIP |  |  |  | REJECT: Missing bolts at second cross arm (see before photos) are needed per 40365 TYPE 3N tower. Please also provide pictures for repaired loose bolt at the peak. |  |  | '-122.068756 | 37.7381 | ETL.5250 | 40654421 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  | Reject | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118914941 | Not Scheduled | T2 DI MENDOCINO-REDBUD 53/264 RPL INSS | 31530110 | MENDOCINO-REDBUD | 053/264 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-13 | 2021-04-13 | [7 empty] | TR2 | <60D | North Coast | WSIP | [6 empty] | '-123.076535 | 39.217 | ETL.2410 | 40797178 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118915571 | Q2 | PITTSBURG-SAN RAMON 16/064 RPR FOND |  | PITTSBURG-SAN RAMON | 016/064 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-13 | 2021-04-13 |  |  | 2021-04-30 | 2021-04-26 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-121.902887 | 37.8174 | ETL.5490 | 40746315 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118915975 | Feb | T2 DI CORTIN-MNDCNO #1 54/266 RPR STRT | 44302218 | CORTINA-MENDOCINO #1 | 054/266 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-04-13 | 2021-04-13 |  |  | 2021-02-19 | 2021-02-16 |  |  | Likely MAT error - delink to correct | TR2 |  | North Coast | WSIP | [6 empty] | '-123.081093 | 39.2201 | ETL.1330 | 40808943 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118916842 | Q2 | T2 LOWER LAKE-HOMESTAKE 4/6 RPR STRW | 44306528 | LOWER LAKE-HOMESTAKE TAP | 004/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-11 | 2021-04-11 | 2021-05-12 | 2021-05-12 | 2021-05-12 | 2021-05-12 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-122.554064 | 38.8966 | ETL.1481 | 40809121 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118917010 | Q2 | T3 DI SOBRANTE-""R"" #1 1/12 RPR STRT | 44624391 | SOBRANTE-R #1 | 001/012 | ICQ | E | 2020_(3) On high spread structure |  | 2020-04-14 | 2020-10-14 |  |  | 2021-05-15 | 2021-05-10 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.240263 | 37.908 | ETL.3770 | 40646639 | Structure-Steel | Anti-Climbing Guard | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 12 | EBMUD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118917339 | Mar | T2 COALINGA #1-SAN MIGUEL 26/0A RPL STRW | 31455598 | COALINGA #1-SAN MIGUEL | 026/000A | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-14 | 2021-04-14 | 2021-03-15 | 2021-03-18 | 2021-03-18 | 2021-03-15 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.640835 | 35.915 | ETL.8580 | 44190887 | Structure-Wood | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-06-01 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118917409 | Not Scheduled | T2 MONTE RIO-FORT ROSS 27/4C RPR GYWW | 44310654 | ETL.6979.POLE.WOOD | 027/004C | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-14 | 2021-04-14 | [7 empty] | TR2 | <60D | North Coast | WSIP | [6 empty] | '-123.204031 | 38.5202 | ETL.6979 | 40741910 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118917521 | Q4 | T3 EI MAPLE CREEK-HOOPA 10/5 RPR GYWS | 44178090 | MAPLE CREEK-HOOPA | 010/005 | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-14 | 2020-10-14 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.771942 | 40.8863 | ETL.7490 | 44735733 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-06-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118917698 | Q2 | T3 DI FULTON-PUEBLO 33/167 RPR STRT | 44306536 | FULTON-PUEBLO | 033/167 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-04-14 | 2020-10-14 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.593966 | 38.495 | ETL.1600 | 40808453 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118918356 | Q4 | T3 MAPLE CREEK-HOOPA 10/0 RPR GYWW | 44178090 | MAPLE CREEK-HOOPA | 010/000 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-04-14 | 2020-10-14 |  |  | 2021-10-02 | 2021-07-26 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.779061 | 40.8803 | ETL.7490 | 44324520 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-06-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118918358 | Q4 | T3 MAPLE CREEK-HOOPA 10/0 RMV BUTT | 31504608 | MAPLE CREEK-HOOPA | 010/000 | 93J | F | 2020_(4) TD tag on high spread line |  | 2020-04-14 | 2022-04-14 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.779061 | 40.8803 | ETL.7490 | 44324520 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-06-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118918390 | Q4 | EI T3NT MAPLE CREEK-HOOPA 9/10 RMV BUTT | 44311200 | MAPLE CREEK-HOOPA | 009/010 | ICW | F | 2020_(3) On high spread structure |  | 2020-04-14 | 2022-04-14 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.779855 | 40.8799 | ETL.7490 | 40617814 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118920723 | Feb | T3 DI PITTSBURG-SAN MATEO 11/45 RPL INSS | 31504797 | PITTSBURG-SAN MATEO | 011/045 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-15 | 2020-10-15 |  |  | 2021-02-16 | 2021-02-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.879024 | 37.8838 | ETL.5463 | 40582079 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-06-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118921552 | Not Scheduled | T3 DI MONTE RIO-FORT ROSS 20/3 RPR CNDW | 44310656 | ETL.6979.POLE.WOOD | 020/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-14 | 2020-10-14 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.103783 | 38.4818 | ETL.6979 | 40648460 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118921769 | Q4 | T3 EI KESWICK-TRINITY 5/72 RPL ANCW | 31500438 | KESWICK-TRINITY | 005/072 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-04-15 | 2020-10-15 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.545832 | 40.6308 | ETL.7270 | 40617597 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118921855 | Q2 | T2 DI LAKEVILLE #1 009/005 RPR GYWW | 44310740 | LAKEVILLE #1 | 009/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-14 | 2021-04-14 | 2020-08-10 | 2020-08-14 | 2021-06-01 | 2021-05-28 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-122.542543 | 38.3739 | ETL.7360 | 40751124 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118922133 | Feb | T3 DI MNT VST-JFRSN #1 18/79 RPR STRT |  | MONTA VISTA-JEFFERSON #1 | 018/079 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-13 | 2020-10-13 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.294628 | 37.4457 | ETL.5220 | 40869051 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | Huddart Park | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118922208 | Mar | T3 DI MNT VST-JFRSN #1 18/79 RPLC INSS | 31507365 | MONTA VISTA-JEFFERSON #1 | 018/079 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-13 | 2021-05-31 |  |  | 2021-03-05 | 2021-02-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | 122.2177 | 37.4268 | ETL.5220 | 40892241 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | Huddart Park | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | 93 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118923337 | Q2 | T2 DI FULTON-IGNACIO #1 21/107 RPR FOND | 44310479 | FULTON-IGNACIO #1 | 021/107 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-14 | 2022-04-14 |  |  | 2021-04-23 | 2021-04-19 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.591582 | 38.3119 | ETL.4680 | 40811146 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118923807 | Not Scheduled | T2 DI MENDOCINO-REDBUD 53/262 RPLC INSS | 31530110 | MENDOCINO-REDBUD | 053/262 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-13 | 2021-04-13 | [7 empty] | TR2 | <60D | North Coast | WSIP | [6 empty] | '-123.07556 | 39.2154 | ETL.2410 | 40726475 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118925341 | Q2 | DI METCALF-GREEN VALLEY 9/65 INST MRKW |  | METCALF-GREEN VALLEY | 009/065 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-04-15 | 2022-04-15 |  |  | 2021-05-21 | 2021-05-03 |  |  | Likely MAT error - delink to correct |  |  | South | WSIP | [6 empty] | '-121.654254 | 37.1218 | ETL.2540 | 40751284 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 630 | Moss Landing |  | Y - 2 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-05-20 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118925780 | Mar | T3NT DI MORAGA-SAN LNDR #3 2/20 RPR FOND | 44303862 | MORAGA-SAN LEANDRO #3 | 002/020 | ICQ | F | 2020_(3) On high spread structure |  | 2020-04-14 | 2022-04-14 |  |  | 2021-03-13 | 2021-03-08 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.139234 | 37.8158 | ETL.2790 | 40587930 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118925984 | Q2 | T3 EI ROCK CREEK-POE :2/15 RPR FOND |  | ROCK CREEK-POE | :002/015 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-04-16 | 2020-10-16 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.281704 | 39.9881 | ETL.5630 | 40905953 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118926078 | Not Scheduled | T3 EI CARIBOU-TABLE MTN 18/132 RPR FOND |  | CARIBOU-TABLE MTN | 018/132 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-16 | 2020-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.279929 | 39.983 | ETL.4440 | 40674583 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118926143 | Q2 | DI SOBRANTE-""""G"""" #1"" 5/40 RPR STRT |  | SOBRANTE-"G" #1 | 005/040 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-15 | 2021-04-15 |  |  | 2021-04-30 | 2021-04-26 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-122.300432 | 37.9169 | ETL.3720 | 40607984 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-21 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118926761 | Q2 | T3 EI SNEATH LANE-HMB ?8/5 RPL INSW | 31500745 | SNEATH LANE-HALF MOON BAY | ?008/005 | 93I | E | 2020_(2) High fire spread TD |  | 2020-04-13 | 2020-10-13 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.425079 | 37.5152 | ETL.7212 | 44384387 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Bay |  | Y - 29 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-06-24 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118927308 | Q2 | T3 DI MORAGA-SAN LEANDRO#1 3/22 RPL INSS | 31504872 | MORAGA-SAN LEANDRO #1 | 003/022 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-16 | 2020-10-16 |  |  | 2021-05-25 | 2021-05-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.137432 | 37.8128 | ETL.2770 | 40704861 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118927335 | Mar | T2 HUMBOLDT-TRINITY 112/2 RPL POLE | 31500770 | HUMBOLDT-TRINITY | 112/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-16 | 2021-04-16 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-124.078645 | 40.7734 | ETL.1820 | 44560679 | Structure-Wood | Rotten | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-05-21 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118927805 | Q2 | T2 CLEAR LAKE-KONOCTI 19/5 RPR GYWW | 44310559 | CLEAR LAKE-KONOCTI | 019/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-16 | 2021-04-16 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-122.789985 | 38.948 | ETL.6852 | 40747630 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118927834 | Not Scheduled | T3 DRM-GRS VLY-WEIMR B022/491 RPL PL | 31500477 | DRUM-GRASS VALLEY-WEIMAR | B022/491 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-16 | 2020-10-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.01182 | 39.1908 | ETL.6760 | 40815106 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | County | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-15 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118927854 | Q2 | T2 BRIDGEVILLE-COTTONWD 22/195R RPL POLE | 31499714 | BRIDGEVILLE-COTTONWOOD | 022/195 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-08 | 2021-04-08 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.685083 | 40.3748 | ETL.1110 | 44423404 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118927878 | Q3 | T2 CARIBOU #2 2/22 RPR GYWW |  | CARIBOU #2 | ;002/022 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-16 | 2021-04-16 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.948522 | 39.9941 | ETL.6280 | 40698759 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118928838 | Mar | T2 HUMBOLDT-TRINITY 112/2 RPL POLE | 31500770 | HUMBOLDT-TRINITY | 112/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-16 | 2021-04-16 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-124.078645 | 40.7734 | ETL.1820 | 44560641 | Structure-Wood | Rotten | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-05-21 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118928839 | Mar | T2 HUMBOLDT-TRINITY 112/2 RPL POLE | 31500770 | HUMBOLDT-TRINITY | 112/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-16 | 2021-04-16 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-124.078645 | 40.7734 | ETL.1820 | 44560612 | Structure-Wood | Rotten | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21 | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-05-21 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118929251 | Q2 | T3 EI SANTA FE GEOTHERMAL TAP 0/1 RPR FO | 44310549 | SANTA FE GEOTHERMAL TAP | 000/001 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-17 | 2020-10-17 |  |  | 2021-06-04 | 2021-06-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.743451 | 38.7878 | ETL.4782 | 40584987 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118930189 | Not Scheduled | T2 COALINGA #1-SAN MIGUEL 32/0 RPL HRDS |  | COALINGA #1-SAN MIGUEL | 032/000 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-04-17 | 2021-04-17 | [7 empty] | TR2 | <60D | South | WSIP | [6 empty] | '-120.636155 | 35.8293 | ETL.8580 | 40601112 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-04-22 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118930321 | Q2 | T3 EI SNEATH LANE-HMB ?3/7 RPL POLE | 31500744 | SNEATH LANE-HALF MOON BAY | ?003/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-17 | 2020-10-17 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.477939 | 37.5569 | ETL.7212 | 43249686 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  |  | RCDT | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118933116 | Q3 | T2 CARIBOU-PLUMAS JCT 0/6 INST DAMW | 44304459 | CARIBOU-PLUMAS JCT | 000/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-20 | 2021-04-20 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.140699 | 40.0839 | ETL.6290 | 40826471 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-06-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118933190 | Mar | T3 DRUM-RIO OSO #2 5/063 RPR JUMPER | 44300640 | DRUM-RIO OSO #2 | 005/063 | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-20 | 2020-10-20 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.855862 | 39.213 | ETL.1430 | 40655122 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118933234 | Q3 | T2 CARIBOU #2 0/017 REFRAME | 31500636 | CARIBOU #2 | ;000/017 | 93E | E | 2020_(2) High fire spread TD |  | 2020-04-20 | 2021-04-20 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.962288 | 40.0205 | ETL.6280 | 40824669 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118933422 | Not Scheduled | T2 WEST POINT-VALLY SPRNGS 5/68 RPL POLE | 31498708 | WEST POINT-VALLEY SPRINGS | 005/068 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-20 | 2021-04-20 | [7 empty] | TR2 | <90D | Central | WSIP | [6 empty] | '-120.63505 | 38.3866 | ETL.8350 | 40580256 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-14 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118933579 | Q2 | T3 EI FULTON-PUEBLO 27/130 RPR FOND | 44306536 | FULTON-PUEBLO | 027/130 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-20 | 2020-10-20 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.475879 | 38.4904 | ETL.1600 | 40582771 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118933594 | Not Scheduled | T3 EAGLE ROCK-FULTN-SLVRD 4/23 RPR JUMS | 44310477 | EAGLE ROCK-FULTON-SILVERADO | 004/023 | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-20 | 2020-10-20 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.798086 | 38.7769 | ETL.4392 | 40660132 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118936241 | Q2 | T3 OLEUM-G #1 9/060 RPL INSS | 31503752 | OLEUM-G #1 | 009/060 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-21 | 2020-10-21 | 2021-05-13 | 2021-05-14 | 2021-05-14 | 2021-05-13 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.362728 | 38.0283 | ETL.3150 | 43601234 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 8 | EBRPD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-05-05 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118937286 | Q3 | IGNACIO-MARE ISLAND#1 13/93 REPL TOWER |  | IGNACIO-MARE ISLAND #1 | 013/093 | 70S | B | 2020_(0) A and B Tags |  | 2020-04-21 | 2021-01-26 |  |  | 2021-07-23 | 2021-01-26 | [5 empty] | North Coast | WSIP |  |  |  |  | System Inspection | Tower did not FSR this structure; upgraded by SI; in project to replace. | '-122.337826 | 38.1525 | ETL.1830 | 40760246 | Bay Water-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Pole Program | Capital | 426 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Already Past Due | 70 | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 118937557 | Mar | T3 DI SOBRANTE-""""R"""" #2 2/16 RPL INSS | 31510378 | SOBRANTE-R #2 | 002/016 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-20 | 2020-10-20 |  |  | 2021-03-22 | 2021-03-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.249227 | 37.9104 | ETL.3780 | 40830934 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-05-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118937817 | Q3 | T3 EI BRIDGEVILLE-GARBERVI 11/5 RPR WDPK | 44299806 | BRIDGEVILLE-GARBERVILLE | 011/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-21 | 2020-10-21 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.71576 | 40.3508 | ETL.6220 | 40752659 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118937891 | Q3 | T3 EI BRIDGEVILLE-GARBERVILL 10/17 RPR C | 44300097 | BRIDGEVILLE-GARBERVILLE | 010/017 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-21 | 2020-10-21 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.719665 | 40.3566 | ETL.6220 | 40810335 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118937892 | Mar | T3 EI BRIDGEVILLE-GRBRVILL 10/17 RMV DEB | 31504607 | BRIDGEVILLE-GARBERVILLE | 010/017 | 93J | E | 2020_(2) High fire spread TD |  | 2020-04-21 | 2020-10-21 |  |  | 2021-03-22 | 2021-03-22 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.719665 | 40.3566 | ETL.6220 | 40810335 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118937899 | Q3 | T3 EI BRIDGEVILLE-GARBERVILLE 11/5 RPL S | 44300097 | BRIDGEVILLE-GARBERVILLE | 011/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-21 | 2020-10-21 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.71576 | 40.3508 | ETL.6220 | 40752659 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118937901 | Q3 | T3 EI BRIDGEVILLE-GARBERVILL 10/13 RPL P | 31500972 | BRIDGEVILLE-GARBERVILLE | 010/013 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-21 | 2020-10-21 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.721445 | 40.3592 | ETL.6220 | 40650758 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118938516 | Not Scheduled | T2 DI DRUM-SUMMIT#1 25/299B RPL POLE | 31498145 | DRUM-SUMMIT #1 | 025/299B | 70Y | E | 2020_(1b) Lines with special commitments |  | 2019-05-14 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.355483 | 39.3093 | ETL.1440 | 42572727 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-05-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118938517 | Not Scheduled | T2 DI DRUM-SUMMIT#1 25/299C RPL POLE | 31498145 | DRUM-SUMMIT #1 | 025/299C | 70Y | E | 2020_(1b) Lines with special commitments |  | 2019-05-14 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.355498 | 39.3093 | ETL.1440 | 42572728 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  | 2020-05-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118939606 | Mar | T3 DI SOBRANTE ""R"" #2 1/13 REPL INSS | 31510378 | SOBRANTE-R #2 | 001/013 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-20 | 2020-10-20 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.244409 | 37.9091 | ETL.3780 | 44396595 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 2 | EBMUD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-02-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118940192 | Mar | T3 DI SOBRANTE-""G"" #2"" 2/15 RPL INSS |  | SOBRANTE-"G" #2 | 002/015 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-22 | 2020-10-22 |  |  | 2021-03-20 | 2021-03-20 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.248716 | 37.9108 | ETL.3730 | 40773243 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y -3 | EBMUD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-02-08 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118940222 | Q2 | ROUND MTN-COTTONWD #3 49/433 RPR FOND | 43932111 | ROUND MTN-COTTONWOOD #3 | 049/433 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-04-22 | 2021-04-22 |  |  | 2021-05-13 | 2021-04-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.162628 | 40.5228 | ETL.5650 | 40657340 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118940787 | Q3 | T3 EI BRIDGEVILLE-GARBRVILL 9/5 RPR STRW | 44299806 | BRIDGEVILLE-GARBERVILLE | 009/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-22 | 2020-10-22 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.738576 | 40.3741 | ETL.6220 | 40752655 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118940794 | Q3 | T3 EI BRIDGEVILLE-GARBERVLE 9/15 RPR JUM | 44300097 | BRIDGEVILLE-GARBERVILLE | 009/015 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-22 | 2020-10-22 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.733536 | 40.3687 | ETL.6220 | 40768709 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118940795 | Q3 | T3 EI BRIDGEVILLE-GARBERVLE 9/15 RPR PL | 44299806 | BRIDGEVILLE-GARBERVILLE | 009/015 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-22 | 2020-10-22 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.733536 | 40.3687 | ETL.6220 | 40768709 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118940803 | Q2 | T3 EI GEYSERS #12 - FULTON 3/14A RPR STR | 44631264 | GEYSERS #12-FULTON | 003/014A | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-22 | 2020-10-22 |  |  | 2021-05-14 | 2021-05-10 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.761708 | 38.7679 | ETL.4750 | 44469284 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118940882 | Q2 | T3 EI GEYSERS #12-FULTON 3/14B RPR STRS | 44631264 | GEYSERS #12-FULTON | 003/014B | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-22 | 2020-10-22 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.761772 | 38.7678 | ETL.4750 | 44468539 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118941208 | Mar | T3 EI BRIDGEVILLE-GARBRVILL 10/7 RMV DEB | 31504607 | BRIDGEVILLE-GARBERVILLE | 010/007 | 93J | E | 2020_(2) High fire spread TD |  | 2020-04-22 | 2020-10-22 |  |  | 2021-03-22 | 2021-03-22 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.725967 | 40.363 | ETL.6220 | 44814412 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118941962 | Not Scheduled | T2 CORTINA-MENDOCINO #1 54/266 RPL ROAD | 31516303 | CORTINA-MENDOCINO #1 | 054/266 | 71Y | E | 2020_(4b) On structure in bucket 4 |  | 2020-04-23 | 2021-04-23 |  |  |  | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.081093 | 39.2201 | ETL.1330 | 40808943 | Road | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118942751 | Mar | T3 DI MRAGA-SN LNDRO #1 4/32 RPR STRT | 44303861 | MORAGA-SAN LEANDRO #1 | 004/032 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-04-22 | 2020-10-22 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.1285 | 37.7953 | ETL.2770 | 40657121 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-05-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118942979 | Not Scheduled | EI T3NT CARIBOU-TABLE MTN 40/295 RPR FON |  | CARIBOU-TABLE MTN | 040/295 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2022-04-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.497857 | 39.7439 | ETL.4440 | 40758293 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-10 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118943649 | Q2 | T3 DI FULTON-CALISTOGA ;8/1 RPL HRDT | 44306735 | FULTON-CALISTOGA | ;008/001 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-04-22 | 2020-10-22 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.6019 | 38.4965 | ETL.6880 | 40593317 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118944195 | Q2 | T3 DI FULTON-CALISTOGA ;5/7 RPR INSS |  | FULTON-CALISTOGA | ;005/007 | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-22 | 2021-05-31 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.645247 | 38.497 | ETL.6880 | 40825316 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118946262 | Not Scheduled | T3 MONTE RIO-FULTON 13/1 RPL POLE | 31501349 | MONTE RIO-FULTON | 013/001 | 70Y | E | 2020_(4b) On structure in bucket 4 |  | 2020-04-24 | 2020-10-24 | [7 empty] | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.7630 | 44315964 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-11-05 | Released-Standard | Complete | Ready for Construction |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118946338 | Q2 | T3 DI SLT SPRGS-TGR CRK 16/127 RPLC INSS | 31502542 | SALT SPRINGS-TIGER CREEK | 016/127 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-22 | 2020-10-22 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.492046 | 38.4481 | ETL.3500 | 40827321 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-06 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118946429 | Mar | T3 DI SAN RAMON-MORAGA 5/22 RPLC INSS | 31504799 | SAN RAMON-MORAGA | 005/022 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-20 | 2020-10-20 |  |  | 2021-03-18 | 2021-03-18 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.002386 | 37.7013 | ETL.5660 | 40852159 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118946523 | Q2 | T2 DI SLT SPRNGS-TGR CRK 7/60 RPR INSS | 44631104 | SALT SPRINGS-TIGER CREEK | 007/060 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2021-04-23 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.335805 | 38.4767 | ETL.3500 | 40620104 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-05-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118946601 | Not Scheduled | T3 MONTE RIO-FULTON 13/1L REPL POLE | 31501349 | MONTE RIO-FULTON | 013/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2020-10-24 | [7 empty] | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.7630 | 44315962 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-11-05 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118946994 | Q2 | T2 VOLTA-DESCHUTES 15/328 REFRAME | 31416186 | VOLTA-DESCHUTES | 015/328 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2021-04-24 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.14629 | 40.5334 | ETL.8290 | 40592140 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-04-30 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118947031 | Q2 | T2 VOLTA-DESCHUTES 14/302 REFRAME | 31416186 | VOLTA-DESCHUTES | 014/302 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2021-04-24 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.124928 | 40.5254 | ETL.8290 | 40817183 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-04-30 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118947138 | Q2 | T3 VOLTA-DESCHUTES 003/084 REFRAME | 31416186 | VOLTA-DESCHUTES | 003/084 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2021-05-31 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.937202 | 40.4772 | ETL.8290 | 40868506 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | 93 | Q2 |  |  | 2020-04-30 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118947140 | Q2 | T3 VOLTA-DESCHUTES 3/083 REFRAME | 31416186 | VOLTA-DESCHUTES | 003/083 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2021-05-31 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.936385 | 40.477 | ETL.8290 | 40825124 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | 93 | Q2 |  |  | 2020-04-30 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118947143 | Q2 | T3 VOLTA-DESCHUTES 1/036 REFRAME | 31416186 | VOLTA-DESCHUTES | 001/036 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2021-05-31 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.896662 | 40.4672 | ETL.8290 | 40656909 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | 93 | Q2 |  |  | 2020-04-30 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118947144 | Q2 | T3 VOLTA-DESCHUTES 0/020 REFRAME | 31416186 | VOLTA-DESCHUTES | 000/020 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2020-10-24 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.882562 | 40.4637 | ETL.8290 | 40868500 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-04-30 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118947152 | Q2 | T3 VOLTA-DESCHUTES 0/016 REFRAME | 31416186 | VOLTA-DESCHUTES | 000/016 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2021-05-31 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.879192 | 40.4629 | ETL.8290 | 40759234 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | 93 | Q2 |  |  | 2020-04-30 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118947264 | Not Scheduled | T3NT DI SAN RAMON-MORAGA 3/18 PNT STRS | 44586180 | SAN RAMON-MORAGA | 003/018 | ICS | F | 2020_(3) On high spread structure |  | 2020-04-23 | 2022-04-23 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-121.990765 | 37.7098 | ETL.5660 | 40644606 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118947644 | Q2 | T3 EI GEYSERS #7-EAGLE ROCK 0/8 RPR FOND | 44306736 | GEYSERS #7-EAGLE ROCK | 000/008 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2020-10-24 |  |  | 2021-05-28 | 2021-05-24 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.810963 | 38.8191 | ETL.1680 | 40861322 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118947777 | Mar | T3 DI MORAGA-CSTR VALLEY 9/40 RPLC INSS | 44609775 | MORAGA-CASTRO VALLEY | 009/040 | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-20 | 2020-10-20 |  |  | 2021-03-09 | 2021-03-09 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.072319 | 37.7479 | ETL.5250 | 40596226 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 9 | EBMUD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118947800 | Q2 | T3 DI WSHN-SN JOAQUIN #3 1/14 REPL PL | 31501721 | WISHON-SAN JOAQUIN #3 | 001/014 | 70Y | E | 2020_(1a) PSPS |  | 2020-04-23 | 2020-10-23 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-19 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.502722 | 37.2312 | ETL.9340 | 40748452 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  |  | USFS | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-17 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 118947848 | Not Scheduled | T3 FULTON-HOPLAND 27/012 REPLACE POLE | 31478309 | FULTON-HOPLAND | 027/012 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2020-10-24 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.998643 | 38.8228 | ETL.6890 | 40700692 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118948201 | Q3 | T3 EI BRIDGEVILLE-GARBERVILLE 9/3 REFRAM | 31501358 | BRIDGEVILLE-GARBERVILLE | 009/003 | 93E | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2020-10-24 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.739792 | 40.3756 | ETL.6220 | 40666708 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118948207 | Not Scheduled | EI T3NT EAGL RCK-FLTN-SLVRD :0/1 PNT STR | 44304081 | EAGLE ROCK-FULTON-SILVERADO | :000/001 | ICQ | F | 2020_(4b) On structure in bucket 4 |  | 2020-04-24 | 2022-04-24 | [6 empty] | Likely MAT error - delink to correct | TR3 |  | North Coast | WSIP | [6 empty] | '-122.761291 | 38.7405 | ETL.4392 | 41129397 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118948274 | Q3 | T3 EI BRIDGEVILLE-GARBERVILLE 8/17 RPR G | 44300097 | BRIDGEVILLE-GARBERVILLE | 008/017 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2020-10-24 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.741361 | 40.3803 | ETL.6220 | 44813261 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118948275 | Q3 | T3 EI BRIDGEVILLE-GARBERVILLE 8/8 RPR IN | 44300097 | BRIDGEVILLE-GARBERVILLE | 008/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2020-10-24 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.742444 | 40.3862 | ETL.6220 | 40876486 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118948278 | Q3 | T3 EI BRIDGEVILLE-GARBERVILLE 8/10 REPL | 44300097 | BRIDGEVILLE-GARBERVILLE | 008/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2020-10-24 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.742211 | 40.3847 | ETL.6220 | 40591068 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118948305 | Q3 | T3 EI BRIDGEVILLE-GARBERVILLE 8/4 REPL S | 44300097 | BRIDGEVILLE-GARBERVILLE | 008/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2020-10-24 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.742729 | 40.3894 | ETL.6220 | 40769368 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118948306 | Feb | T3 EI BRIDGEVILLE-GARBERVILL 7/4 RMV PL | 44299809 | BRIDGEVILLE-GARBERVILLE | 007/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-04-24 | 2024-04-24 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.743556 | 40.403 | ETL.6220 | 40769379 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | IC | Feb |  |  | 2021-01-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118948307 | Feb | T3 EI BRIDGEVILLE-GARBERVILLE 7/4 RPL ST | 31522167 | BRIDGEVILLE-GARBERVILLE | 007/004 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.743556 | 40.403 | ETL.6220 | 40769379 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | 70 | Feb |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118948380 | Q3 | T3 EI BRIDGEVILLE-GARBERVILL 7/5 RMV PL | 44299809 | BRIDGEVILLE-GARBERVILLE | 007/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-04-24 | 2024-04-24 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.743198 | 40.4022 | ETL.6220 | 40752653 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Q3 | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118948384 | Q3 | T3 EI BRIDGEVILLE-GARBERVILL 7/6 RMV PL | 31504607 | BRIDGEVILLE-GARBERVILLE | 007/006 | 93J | F | 2020_(3) On high spread structure |  | 2020-04-24 | 2024-04-24 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.742725 | 40.4012 | ETL.6220 | 40826273 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Q3 | 93 | Q3 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118948407 | Feb | T3 EI BRIDGEVILLE-GARBERVILL 7/7 RPR JUM | 44300097 | BRIDGEVILLE-GARBERVILLE | 007/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.7421734 | 40.3999 | ETL.6220 | 40835203 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118948412 | Q3 | T3 EI BRIDGEVILLE-GARBERVILL 7/9 RMV PL | 31504607 | BRIDGEVILLE-GARBERVILLE | 007/009 | 93J | F | 2020_(3) On high spread structure |  | 2020-04-24 | 2024-04-24 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.741214 | 40.3978 | ETL.6220 | 40862511 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Q3 | 93 | Q3 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118948416 | Q3 | T3 EI BRIDGEVILLE-GARBERVL 7/12 RMV PL B | 44299809 | BRIDGEVILLE-GARBERVILLE | 007/012 | ICW | F | 2020_(3) On high spread structure |  | 2020-04-24 | 2024-04-24 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.74209 | 40.3949 | ETL.6220 | 40698417 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Q3 | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118948450 | Q3 | EI T3NT BRIDGEVILLE-GARBERVL 7/14 INST V | 44300097 | BRIDGEVILLE-GARBERVILLE | 007/014 | ICW | F | 2020_(3) On high spread structure |  | 2020-04-24 | 2022-04-24 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.742608 | 40.3932 | ETL.6220 | 40752608 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118948452 | Feb | T3 EI BRIDGEVILLE-GARBERVILLE 8/0 RPR GY | 44300097 | BRIDGEVILLE-GARBERVILLE | 008/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.742979 | 40.392 | ETL.6220 | 40614599 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118949765 | Not Scheduled | T3 EI EAGL RCK-FLTN-SLVRD :3/15 RMV NEST | 44310477 | EAGLE ROCK-FULTON-SILVERADO | :003/015 | ICS | E | 2020_(3) On high spread structure |  | 2020-04-26 | 2020-10-26 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.766466 | 38.6857 | ETL.4392 | 41129318 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118949767 | Mar | T3 EI EAGL RCK-FLTN-SLVRD :3/13 RPR FOND | 44304081 | EAGLE ROCK-FULTON-SILVERADO | :003/013 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-04-26 | 2020-10-26 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.76376 | 38.6931 | ETL.4392 | 41129316 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-05-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118949768 | Not Scheduled | EI T3NT EAGL RCK-FLTN-SLVRD :3/15 PNT ST | 43730698 | EAGLE ROCK-FULTON-SILVERADO | :003/015 | ICS | F | 2020_(3) On high spread structure |  | 2020-04-26 | 2022-04-26 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.766466 | 38.6857 | ETL.4392 | 41129318 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118950503 | Q2 | T3 DI FULTON-CALISTOGA ;007/1 BENT STL | 44306735 | FULTON-CALISTOGA | ;007/001 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-04-23 | 2020-10-23 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.619841 | 38.4971 | ETL.6880 | 40593315 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118950870 | Q2 | T2 EI DORADO-MISSR FLT#2 5/42 RMV DRBRIS | 44310642 | ELDORADO-MISSOURI FLAT #2 | 005/042 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-04-27 | 2021-04-27 |  |  | 2021-04-01 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.711813 | 38.7584 | ETL.1540 | 40712536 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-05-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118950973 | Not Scheduled | T3 DIMONTE RIO-FULTON 14/14 RPLC SPLW |  | MONTE RIO-FULTON | 014/014 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2020-10-23 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.011995 | 38.4716 | ETL.7630 | 44401983 | Splice-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118951405 | Q2 | T3 EI GEYSERS #17-FULTON 10/46 RPR INSS | 44630990 | GEYSERS #17-FULTON | 010/046 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-04-27 | 2020-10-27 | 2021-01-18 | 2021-01-21 | 2021-05-08 | 2021-05-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.76156 | 38.7052 | ETL.4770 | 40842350 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118951891 | Q4 | T2 MAPLE CREEK-HPA 8/5 REVIEW POLE DEPTH | 44497905 | MAPLE CREEK-HOOPA | 008/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-27 | 2021-04-27 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.801362 | 40.8638 | ETL.7490 | 44707296 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-06-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118952421 | Not Scheduled | T2 DI MENDOCINO-REDBUD 26/126 RPL INSS | 31530110 | MENDOCINO-REDBUD | 026/126 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2021-04-23 | [7 empty] | TR2 | <90D | North Coast | WSIP | [6 empty] | '-122.664634 | 39.0293 | ETL.2410 | 40835492 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118952480 | Q2 | T3NT DI SBRNT-GRZLY-CLNT #1 5/48 RPR FND |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 005/048 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2025-04-23 |  |  | 2021-05-31 | 2021-05-24 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.214609 | 37.8494 | ETL.3740 | 40646528 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | IC | Q2 |  |  | 2020-05-20 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118952863 | Mar | T3 DI GEYSERS#3-CLVRDLE 8/98 RPR POLE | 44580896 | GEYSERS #3-CLOVERDALE | 008/098 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2020-10-23 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.956213 | 38.7974 | ETL.1650 | 40818244 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118952923 | Feb | T2 DI CORTINA-MNDCNO#1 41/197 RPR FOND |  | CORTINA-MENDOCINO #1 | 041/197 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2022-04-23 |  |  | 2021-02-19 | 2021-02-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.880086 | 39.1435 | ETL.1330 | 40809331 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118953078 | Not Scheduled | T2 SPAULDING-SUMMIT 15/485 RPR GYWW | 44310649 | SPAULDING-SUMMIT | 015/485 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-04-27 | 2021-04-27 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.387676 | 39.3284 | ETL.8060 | 40826237 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118953080 | Feb | T2 DI CORTINA-MNDCNO#1 36/174 BENT STL |  | CORTINA-MENDOCINO #1 | 036/174 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2021-04-23 |  |  | 2021-02-19 | 2021-02-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.80641 | 39.1103 | ETL.1330 | 40762063 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118953081 | Feb | T2 DI CORTINA-MNDCNO#1 36/174 RPR FOND |  | CORTINA-MENDOCINO #1 | 036/174 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2022-04-23 |  |  | 2021-02-19 | 2021-02-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.80641 | 39.1103 | ETL.1330 | 40762063 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118953082 | Feb | T2 DI CORTINA-MNDCNO#1 34/164 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 034/164 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-04-23 | 2022-04-23 |  |  | 2021-02-19 | 2021-02-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.773948 | 39.0901 | ETL.1330 | 40762061 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118953120 | Q3 | T3 DI DONNELLS-MI-WUK 18/1 REPL POLE | 31501612 | DONNELLS-CURTIS | 018/001 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-23 | 2020-10-23 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.210896 | 38.0558 | ETL.1400 | 40579920 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 40 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-06-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118954291 | Not Scheduled | T2 SALMON CREEK TAP 7/8 RPR GYWW |  | SALMON CREEK TAP | 007/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-28 | 2021-04-28 | [7 empty] | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.070343 | 38.378 | ETL.6981 | 40860986 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118954686 | Q2 | T3 EI YANKE (NORTH FORK) TAP 0/3 RPR GYW | 44321420 | YANKE (NORTH FORK) TAP (IDLE) | 000/003 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-04-28 | 2020-10-28 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  | DLFL upon completion of 30878389 |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.499698 | 37.2312 | ETL.9341 | 40646693 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118955392 | Mar | T3 WEST POINT-VLLY SPRINGS 0/13 RPR GYWW | 44631105 | WEST POINT-VALLEY SPRINGS | 000/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-28 | 2020-10-28 |  |  | 2021-03-27 | 2021-03-23 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.563855 | 38.4253 | ETL.8350 | 40643809 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-05-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118955469 | Mar | T3 DI GEYSERS #3-CLOVERDALE RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 005/068 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2020-10-24 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.91411 | 38.815 | ETL.1650 | 40603859 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118955472 | Not Scheduled | T3 MIDDLE FORK #1 4/64 REFRAME | 31471244 | MIDDLE FORK #1 | 004/064 | 93E | E | 2020_(2) High fire spread TD |  | 2020-04-28 | 2020-10-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.652003 | 38.9981 | ETL.8405 | 40649998 | Crossarm-Wood | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118955743 | Mar | T2 DI EAGLE ROCK-CORTINA 15/74 RPL INSS | 31505513 | EAGLE ROCK-CORTINA | 015/074 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2021-04-24 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.1470 | 40792690 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118956550 | Q3 | T3 SPRING GAP TAP 1/5A RPL POLE | 31501619 | SPRING GAP TAP | 001/005A | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-28 | 2020-10-28 |  |  | 2021-09-08 | 2021-08-08 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.103043 | 38.1679 | ETL.1402 | 44550064 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-09-17 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118956576 | Q3 | T3 SPRING GAP TAP 1/5B RPL POLE | 31501619 | SPRING GAP TAP | 001/005B | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-28 | 2020-10-28 |  |  | 2021-09-08 | 2021-08-08 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.103072 | 38.1678 | ETL.1402 | 44549850 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-09-17 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118956666 | Q3 | T3 SPRING GAP TAP 1/5C RPL POLE | 31501619 | SPRING GAP TAP | 001/005C | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-28 | 2020-10-28 |  |  | 2021-09-08 | 2021-08-08 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.103016 | 38.1679 | ETL.1402 | 44549849 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-09-17 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118956825 | Feb | T3 EI BRIDGEVILLE-GARBERVILL 5/11 INST I | 31501770 | BRIDGEVILLE-GARBERVILLE | 005/011 | 93I | E | 2020_(2) High fire spread TD |  | 2020-04-28 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.7617139 | 40.4226 | ETL.6220 | 40611404 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | 93 | Feb |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118956862 | Feb | T3 EI BRIDGEVILLE-GARBERVILLE 5/2 RPR ST | 44299806 | BRIDGEVILLE-GARBERVILLE | 005/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-28 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.763432 | 40.4282 | ETL.6220 | 40698435 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | IC | Feb |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118956964 | Feb | T3 EI BRIDGEVILLE-GARBERVILLE 5/19 JUMPW | 44300097 | BRIDGEVILLE-GARBERVILLE | 005/019 | ICW | F | 2020_(2) High fire spread TD |  | 2020-04-28 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.7599506 | 40.4165 | ETL.6220 | 40899732 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118956976 | Mar | T3 DI GEYSERS#3-CLVRDL 9/109 RPL POLE | 31501745 | GEYSERS #3-CLOVERDALE | 009/109 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-23 | 2020-10-23 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.970607 | 38.8007 | ETL.1650 | 40761633 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-15 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118957031 | Not Scheduled | T3 DI SALMON CREEK TAP 0/8 RPR POLE |  | SALMON CREEK TAP | 000/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2020-10-24 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.12086 | 38.4681 | ETL.6981 | 40872229 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118957082 | Feb | T3 EI EAGLE ROCK-FLTN-SLVRD 6/23 RMV NES | 44310477 | EAGLE ROCK-FULTON-SILVERADO | 006/023 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-04-28 | 2020-10-28 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.757907 | 38.6543 | ETL.4392 | 41129326 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118957102 | Q3 | T3 EI BRIDGEVILLE-GARBVLE 5/13 RMV PL BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 005/013 | ICW | F | 2020_(3) On high spread structure |  | 2020-04-28 | 2024-04-28 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.761394 | 40.4211 | ETL.6220 | 40666716 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Q3 | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118957142 | Q2 | T2 DI FORT ROSS-GUALALA 35/6 RPR POLE |  | GUALALA-MONTE RIO | 035/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-27 | 2021-04-27 | 2021-06-15 | 2021-06-18 | 2021-06-16 | 2021-06-16 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.301782 | 38.5932 | ETL.6980 | 40827357 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118957182 | Q2 | T2 DI FORT ROSS-GUALALAN 35/3 RPR POLE |  | GUALALA-MONTE RIO | 035/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-27 | 2021-04-27 | 2021-06-15 | 2021-06-18 | 2021-06-16 | 2021-06-16 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.302714 | 38.5894 | ETL.6980 | 40648473 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118957189 | Q2 | T2 DI FORT ROSS-GUALALA 34/7 REPL POLE | 31501748 | GUALALA-MONTE RIO | 034/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-27 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.295014 | 38.5839 | ETL.6980 | 40808290 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118957190 | Q3 | T3 EI BRIDGEVILLE-GRBRVLL 5/8 RMV PL BUT | 31504607 | BRIDGEVILLE-GARBERVILLE | 005/008 | 93J | F | 2020_(3) On high spread structure |  | 2020-04-28 | 2024-04-28 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.762225 | 40.4244 | ETL.6220 | 40862826 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Q3 | 93 | Q3 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118957235 | Feb | T2 DI CORTINA-MENDCNO #1 32/153 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 032/153 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-04-27 | 2022-04-27 |  |  | 2021-02-19 | 2021-02-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.751365 | 39.0693 | ETL.1330 | 40659078 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118957394 | Not Scheduled | T2 DI FULTON-HOPLAND 30/11 RPR POLE | 44579280 | FULTON-HOPLAND | 030/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-27 | 2021-04-27 | [7 empty] | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.030567 | 38.8553 | ETL.6890 | 40601400 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118957442 | Feb | T2 DI CORTINA-MNDCNO#1 15/72 INST HRDT | 44238817 | CORTINA-MENDOCINO #1 | 015/072 | ICQ | E | 2020_(3) On high spread structure |  | 2020-04-23 | 2021-04-23 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.469953 | 39.0228 | ETL.1330 | 40657040 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118957451 | Not Scheduled | T2 DI FULTON-HOPLAND 30/11 TIGHTN HRDW | 44579280 | FULTON-HOPLAND | 030/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-27 | 2021-04-27 | [7 empty] | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.030567 | 38.8553 | ETL.6890 | 40601400 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118957452 | Not Scheduled | T2 DI FULTON-HOPLAND 30/11 RMV PL BUTT | 44579280 | FULTON-HOPLAND | 030/011 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-04-27 | 2021-04-27 | [7 empty] | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.030567 | 38.8553 | ETL.6890 | 40601400 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118958220 | Q2 | T2 DI FRT RSS-GUALALA 31/11 RPL INSW | 31501747 | GUALALA-MONTE RIO | 031/011 | 93I | E | 2020_(2) High fire spread TD |  | 2020-04-27 | 2021-04-27 | 2021-06-15 | 2021-06-18 | 2021-06-17 | 2021-06-17 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.26558 | 38.5556 | ETL.6980 | 40596034 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118959097 | Feb | T2 DI CORTINA-MNDCNO #1 59/289 RPL INSS | 31518808 | CORTINA-MENDOCINO #1 | 059/289 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-27 | 2021-04-27 |  |  | 2021-02-17 | 2021-02-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.174529 | 39.2398 | ETL.1330 | 40860995 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118959099 | Not Scheduled | T2 DI MENDOCINO-REDBUD 59/289 RPL INSS | 31530110 | MENDOCINO-REDBUD | 059/289 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-27 | 2021-04-27 | [7 empty] | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.175263 | 39.2397 | ETL.2410 | 40882695 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118959203 | Feb | T2 DI CORTINA-MNDCNO #1 59/289 RPR HRDT |  | CORTINA-MENDOCINO #1 | 059/289 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-27 | 2021-04-27 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.174529 | 39.2398 | ETL.1330 | 40860995 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118959209 | Q2 | T2 DI FORT ROSS-GUALALA 37/3 RPR POLE | 44589099 | GUALALA-MONTE RIO | 037/003 | ICW | E | 2020_(1a) PSPS |  | 2020-04-27 | 2021-04-27 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.291245 | 38.6156 | ETL.6980 | 40667852 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 118959342 | Q2 | T2 DI FORT ROSS-GUALALA 37/3 RPR GYWW | 44589099 | GUALALA-MONTE RIO | 037/003 | ICW | E | 2020_(1a) PSPS |  | 2020-04-27 | 2021-04-27 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.291245 | 38.6156 | ETL.6980 | 40667852 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 118959417 | Not Scheduled | T3 MIDDLE FORK #1 1/024 REFRAME | 31471244 | MIDDLE FORK #1 | 001/024 | 93E | E | 2020_(2) High fire spread TD |  | 2020-04-29 | 2020-10-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.603124 | 39.0062 | ETL.8405 | 40824458 | Crossarm-Wood | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118959828 | Feb | T2 DI CRTNA-MNDCNO#1 56/277 RPR STRT |  | CORTINA-MENDOCINO #1 | 056/277 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2021-04-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.12171 | 39.2311 | ETL.1330 | 40808541 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118960040 | Feb | T2 DI CRTNA-MNDCNO#1 46/225 RPR FOND |  | CORTINA-MENDOCINO #1 | 046/225 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2022-04-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.949414 | 39.1853 | ETL.1330 | 40750591 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118960062 | Q2 | DI SNTH LN-HLF MN BY ?11/14 RPL INSS |  | SNEATH LANE-HALF MOON BAY | ?011/014 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-27 | 2021-04-27 |  |  | 2021-05-13 | 2021-04-16 | [5 empty] | Central | WSIP | [6 empty] | '-122.429996 | 37.4693 | ETL.7212 | 40823354 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 29 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-06-24 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118960135 | Q2 | T3 EI SNEATH LANE-HALF MN BAY ?5/0 REPL | 31501618 | SNEATH LANE-HALF MOON BAY | ?005/000 | 93E | E | 2020_(2) High fire spread TD |  | 2020-04-20 | 2020-10-20 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.463429 | 37.5509 | ETL.7212 | 40601801 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  |  | RCDT | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118960394 | Feb | T3 EI EAGLE ROCK-FULTON-SLVRD 6/27 RMV N | 44310477 | EAGLE ROCK-FULTON-SILVERADO | 006/027 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-04-29 | 2020-10-29 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.758519 | 38.6423 | ETL.4392 | 41129330 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118960668 | Q2 | T3 DI WEST PNT-VLY SPRNGS 5/63A RPR GYWW | 44631077 | WEST POINT-VALLEY SPRINGS | 005/063A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-28 | 2020-10-28 |  |  | 2021-04-10 | 2021-04-05 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.62912 | 38.393 | ETL.8350 | 40768204 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118960724 | Feb | T2 DI CRTNA-MNDCNO#1 34/163 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 034/163 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-04-24 | 2022-04-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.772383 | 39.0889 | ETL.1330 | 40659706 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118960726 | Q2 | T3 DI SNTH LN-HLF MN BY ?6/9 RPR PL | 44621672 | SNEATH LANE-HALF MOON BAY | ?006/009 | ICW | E | 2020_(2) High fire spread TD |  | 2019-04-27 | 2019-10-27 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.441814 | 37.5374 | ETL.7212 | 40874256 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  | Scarper Ridge | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118960788 | Q3 | T2 CARIBOU #2 4/5 RPL POLE | 31489363 | CARIBOU #2 | ;004/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-29 | 2021-04-29 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.94644 | 39.975 | ETL.6280 | 40751776 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118960793 | Q2 | T3 DI SNTH LN-HF MN BY ?9/4 BOND GUY | 44621667 | SNEATH LANE-HALF MOON BAY | ?009/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-27 | 2020-10-27 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.42395 | 37.503 | ETL.7212 | 40768020 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 29 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118960795 | Mar | T3NT DI EAGL RCK-FLTN-SLD :3/14 RPR FOND | 44326457 | EAGLE ROCK-FULTON-SILVERADO | :003/014 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-03-27 | 2022-04-27 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.764599 | 38.6908 | ETL.4392 | 41129317 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118960879 | Feb | T2 DI CRTNA-MNDCNO#1 33/162 INST HRDT | 44238817 | CORTINA-MENDOCINO #1 | 033/162 | ICQ | E | 2020_(3) On high spread structure |  | 2020-04-24 | 2021-04-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.768955 | 39.0862 | ETL.1330 | 40689169 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118960992 | Feb | T2 DI CRTNA-MNDCNO#1 33/162 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 033/162 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-04-24 | 2022-04-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.768955 | 39.0862 | ETL.1330 | 40689169 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118961065 | Q2 | T2 DI FORT ROSS-GUALALAN 36/0 BOND GUY |  | GUALALA-MONTE RIO | 036/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-28 | 2021-04-28 | 2021-06-15 | 2021-06-18 | 2021-06-18 | 2021-06-16 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.301436 | 38.5992 | ETL.6980 | 40606896 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118961069 | Q2 | T3 DI TGR CRK-VLY SPRNGS 2/22 RPR STRT |  | TIGER CREEK-VALLEY SPRINGS | 002/022 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-04-28 | 2020-10-28 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.538898 | 38.4352 | ETL.5790 | 40651656 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118961073 | Feb | T3 EI BRIDGEVILLE-GARBERVILLE 6/0 RPL PO | 31501746 | BRIDGEVILLE-GARBERVILLE | 006/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-29 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.759736 | 40.4158 | ETL.6220 | 40614612 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | 70 | Feb |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118961074 | Q3 | T3 EI BRIDGEVILLE-GARBERVLL 6/2 RMV PL B | 31504607 | BRIDGEVILLE-GARBERVILLE | 006/002 | 93J | E | 2020_(2) High fire spread TD |  | 2020-04-29 | 2020-10-29 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.759331 | 40.4146 | ETL.6220 | 40661824 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118961076 | Q3 | T3 EI BRIDGEVILLE-GARBERVILLE 6/0 RMV VE | 44311404 | BRIDGEVILLE-GARBERVILLE | 006/000 | CHS | F | 2020_(3) On high spread structure |  | 2020-04-29 | 2022-04-29 |  |  | 2021-08-31 | 2121-08-01 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.759736 | 40.4158 | ETL.6220 | 40614612 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | CH | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118961111 | Q2 | T3 DI TGR CRK-VLY SPRNGS 2/22 INST HRDT |  | TIGER CREEK-VALLEY SPRINGS | 002/022 | ICQ | E | 2020_(3) On high spread structure |  | 2020-04-28 | 2020-10-28 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.538898 | 38.4352 | ETL.5790 | 40651656 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118961211 | Q2 | T3 DI MI-WUK-CURTIS 22/05 RPL POLE | 31501637 | ETL.1073.POLE.WOOD | 022/005B | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2020-10-23 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.261518 | 38.0128 | ETL.1073 | 40744856 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118961214 | Feb | DI CORTINA-MNDCN#1 4/25 RPL INSS | 31502267 | CORTINA-MENDOCINO #1 | 004/025 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2021-04-24 |  |  | 2021-02-20 | 2021-02-18 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.306158 | 39.111 | ETL.1330 | 40757308 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118961221 | Feb | T3 EI BRIDGEVILLE-GARBERVILLE 06/03 RPL | 31501746 | BRIDGEVILLE-GARBERVILLE | 006/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-29 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.758161 | 40.4138 | ETL.6220 | 40666732 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | 70 | Feb |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118961228 | Feb | T3 EI BRIDGEVILLE-GARBERVILLE 6/6 INST J | 31501770 | BRIDGEVILLE-GARBERVILLE | 006/006 | 93I | E | 2020_(2) High fire spread TD |  | 2020-04-29 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.754982 | 40.4117 | ETL.6220 | 40810915 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | 93 | Feb |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118961263 | Q3 | T3 EI BRIDGEVILLE-GARBERVLL 6/9 RMV PL B | 31504607 | BRIDGEVILLE-GARBERVILLE | 006/009 | 93J | F | 2020_(3) On high spread structure |  | 2020-04-29 | 2024-04-29 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.752625 | 40.4102 | ETL.6220 | 40875285 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Q3 | 93 | Q3 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118961266 | Feb | T3 EI BRIDGEVILLE-GARBRVLL 6/10 RMV PL B | 31504607 | BRIDGEVILLE-GARBERVILLE | 006/010 | 93J | F | 2020_(3) On high spread structure |  | 2020-04-29 | 2024-04-29 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.751232 | 40.4092 | ETL.6220 | 40614602 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | 93 | Feb |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118961268 | Feb | T3 EI BRIDGEVILLE-GARBRVLL 6/10 RPR STRW | 44299806 | BRIDGEVILLE-GARBERVILLE | 006/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-29 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.751232 | 40.4092 | ETL.6220 | 40614602 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | IC | Feb |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118961269 | Feb | T3 EI BRIDGEVILLE-GARBERVILL 6/11 INST I | 31501770 | BRIDGEVILLE-GARBERVILLE | 006/011 | 93I | E | 2020_(2) High fire spread TD |  | 2020-04-29 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.7504177 | 40.4087 | ETL.6220 | 40611405 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | 93 | Feb |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118961307 | Feb | T3 EI BRIDGEVILLE-GARBERVILL 7/0 RPL POL | 31501746 | BRIDGEVILLE-GARBERVILLE | 007/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-29 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.745763 | 40.4056 | ETL.6220 | 40591061 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | 70 | Feb |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118962320 | Not Scheduled | T3 DI SALMON CREEK TAP 0/7 RPR POLE |  | SALMON CREEK TAP | 000/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-28 | 2020-10-28 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.121415 | 38.4694 | ETL.6981 | 40808321 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118962529 | Q3 | T3 EI BRIDGEVILLE-GARBERVLL 6/1 RMV PL B | 31504607 | BRIDGEVILLE-GARBERVILLE | 006/001 | 93J | E | 2020_(2) High fire spread TD |  | 2020-04-29 | 2020-10-29 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.75954 | 40.4153 | ETL.6220 | 40600515 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118963034 | Not Scheduled | DI SALMON CREEK TAP 1/9 RPR GYWW |  | SALMON CREEK TAP | 001/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-28 | 2021-04-28 | [8 empty] | <90D | North Coast | WSIP | [6 empty] | '-123.113506 | 38.4536 | ETL.6981 | 40876106 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118963250 | Q2 | T3 DI SNTH LN-HLF MN BY ?6/0 RPR POLE | 44621672 | SNEATH LANE-HALF MOON BAY | ?006/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-28 | 2020-10-28 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.448776 | 37.5454 | ETL.7212 | 40601798 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  | Scarper Ridge | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118963274 | Q2 | T3NT DI GEYSERS#7-EGL RCK 1/10 RPR FOND | 44306736 | GEYSERS #7-EAGLE ROCK | 001/010 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-04-24 | 2022-04-24 |  |  | 2021-05-28 | 2021-05-24 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.811077 | 38.8232 | ETL.1680 | 40588203 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118963297 | Q2 | IGNACIO-MARE ISLAND #1 13/94 RPL TOWER |  | IGNACIO-MARE ISLAND #1 | 013/094 | 70S | B | 2020_(0) A and B Tags |  | 2020-04-22 | 2021-02-14 |  |  | 2021-05-21 | 2021-03-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.335038 | 38.1526 | ETL.1830 | 40752805 | Bay Water-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Pole Program | Capital | 426 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Already Past Due | 70 | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 118963308 | Not Scheduled | T3 DI GEYSERS#3-EGL RCK 1/10 RPLC INSS | 31506602 | GEYSERS #3-EAGLE ROCK | 001/010 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2020-10-24 | [7 empty] | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.1660 | 44298581 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118963854 | Q2 | T3NT TIGER CREEK-VALLEY 3/026 RPR FOND |  | TIGER CREEK-VALLEY SPRINGS | 003/026 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-04-28 | 2022-04-28 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.546224 | 38.4331 | ETL.5790 | 40818343 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118964152 | Q2 | T3 MI-WUK-CURTIS 22/7R RPL POLE | 31501639 | ETL.1073.POLE.WDPS | 022/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-30 | 2020-10-30 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.26501 | 38.0094 | ETL.1073 | 44774783 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118964239 | Not Scheduled | T2 FULTON-HOPLAND 34/12 RPL POLE | 31501771 | FULTON-HOPLAND | 034/012 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-30 | 2021-04-30 | [7 empty] | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.053797 | 38.9089 | ETL.6890 | 44203655 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118964377 | Q2 | T2 DI FT ROSS-GUALALA 35/7 RPR GYWW |  | GUALALA-MONTE RIO | 035/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2021-04-24 | 2021-06-15 | 2021-06-18 | 2021-06-16 | 2021-06-16 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.301886 | 38.5945 | ETL.6980 | 40808292 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118964381 | Feb | T2 RIO DELL JCT-BRIDGEVLE 38/8 RMV STEP | 44311233 | RIO DELL JCT-BRIDGEVILLE | 038/008 | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-30 | 2021-04-30 |  |  | 2021-02-27 | 2021-02-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.811502 | 40.4702 | ETL.7850 | 40876500 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118964508 | Q3 | T3 EI BRIDGEVLL-GRBRVLL 4/15 RMV PL BUTT | 44572647 | BRIDGEVILLE-GARBERVILLE | 004/015 | ICW | F | 2020_(3) On high spread structure |  | 2020-04-30 | 2022-04-30 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.764972 | 40.4334 | ETL.6220 | 40752644 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Q3 | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118964509 | Q3 | T3 EI BRIDGEVILL-GRBRVLL 4/15 INST INSW | 44300097 | BRIDGEVILLE-GARBERVILLE | 004/015 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-30 | 2020-10-30 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.764972 | 40.4334 | ETL.6220 | 40752644 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118964580 | Q3 | T3 EI BRIDGEVILLE-GARBRVLL 4/17 RMV PL B | 31504607 | BRIDGEVILLE-GARBERVILLE | 004/017 | 93J | F | 2020_(3) On high spread structure |  | 2020-04-30 | 2024-04-30 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.764562 | 40.432 | ETL.6220 | 40810324 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Q3 | 93 | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118964581 | Q3 | T3 EI BRIDGEVILLE-GRBRVLL 4/17 INST INSW | 44300097 | BRIDGEVILLE-GARBERVILLE | 004/017 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-30 | 2020-10-30 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.764562 | 40.432 | ETL.6220 | 40810324 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118964587 | Mar | T3 DRUM-RIO OSO #2 6/64 INST INSS | 31471215 | DRUM-RIO OSO #2 | 006/064 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-30 | 2020-10-30 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8572323 | 39.2121 | ETL.1430 | 44319605 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118964641 | Feb | T3 EAGLE ROCK-FLTN-SLVRD 4/24 INST DMPS |  | EAGLE ROCK-FULTON-SILVERADO | 004/024 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-04-30 | 2020-10-30 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7975192 | 38.7748 | ETL.4392 | 40786528 | Damper-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118964671 | Feb | T2 DI CORTINA-MNDCN#1 35/167 RPR FOND |  | CORTINA-MENDOCINO #1 | 035/167 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2022-04-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.785776 | 39.0993 | ETL.1330 | 40808529 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118964674 | Feb | T2 DI CORTINA-MNDCN#1 36/175 RPLC HRDT |  | CORTINA-MENDOCINO #1 | 036/175 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2021-04-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.812717 | 39.1135 | ETL.1330 | 40750581 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118964882 | Q2 | T3 DI KONOCTI-EGL RCK 5/5 RPR GYWW | 44610613 | KONOCTI-EAGLE ROCK | 005/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2020-10-24 |  |  | 2021-05-06 | 2021-05-06 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.785935 | 38.8888 | ETL.6861 | 40750936 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118964887 | Not Scheduled | T3 DI MONTE RIO-FORT ROSS 20/0C RPL POLE | 31437439 | ETL.6979.POLE.WOOD | 020/000C | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-27 | 2020-10-27 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.094753 | 38.4844 | ETL.6979 | 40741868 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118965020 | Q2 | T3 DI UKH-HPLN-CLVR 16/7 RPR GYWW | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 016/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2021-05-31 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.034138 | 38.8801 | ETL.4050 | 40808567 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118966234 | Not Scheduled | T2 DI TGR CREEK-ELCTR 9/72 RPR FOND |  | TIGER CREEK-ELECTRA | 009/072 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-27 | 2022-04-27 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.635156 | 38.3877 | ETL.5780 | 40662450 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118966235 | Q2 | T3 DI SNTH LN-HLF MN BAY 10/3 BOND GUY | 44621667 | SNEATH LANE-HALF MOON BAY | ?010/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-27 | 2020-10-27 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.423577 | 37.4891 | ETL.7212 | 40656253 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 29 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118966441 | Q2 | T3 DI EGL RCK-REDBUD 9/51 RPR FOND |  | EAGLE ROCK-REDBUD | :009/051 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-27 | 2020-10-27 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.674745 | 38.8878 | ETL.1480 | 40585029 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118966444 | Not Scheduled | T2 DI VLY SPRNGS-MRTL#1 11/4 REPL POLE | 31502070 | VALLEY SPRINGS-MARTELL #1 | 011/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-28 | 2021-04-28 | [7 empty] | TR2 | <90D | Central | WSIP | [6 empty] | '-120.785084 | 38.3504 | ETL.8240 | 40758493 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-05-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118966446 | Mar | T3 DI EAGLE RCK-FLTN-SLVRD :4/16 RPR FND | 44326454 | EAGLE ROCK-FULTON-SILVERADO | :004/016 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-04-30 | 2020-10-30 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.766287 | 38.6808 | ETL.4392 | 41129319 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118967135 | Q2 | DI SNTH LN-HLF MN BY ?/14 RPR SPLW | 44645176 | SNEATH LANE-HALF MOON BAY | ?000/014 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-30 | 2021-04-29 |  |  | 2021-05-13 | 2021-04-16 | [5 empty] | Central | WSIP | [6 empty] | '-122.494372 | 37.5882 | ETL.7212 | 40758495 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 29 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118967518 | Not Scheduled | T2 DI VLY SPRNGS-MRTL#1 6/5 RPR SPLW | 44631106 | VALLEY SPRINGS-MARTELL #1 | 006/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-28 | 2021-04-28 | [7 empty] | TR2 | <90D | Central | WSIP | [6 empty] | '-120.756577 | 38.2786 | ETL.8240 | 40768196 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118968201 | Q2 | T3 DI SANTA FE GTHRML TP 0/2 RPR FOND |  | SANTA FE GEOTHERMAL TAP | 000/002 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-30 | 2020-10-30 |  |  | 2021-06-04 | 2021-06-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.745884 | 38.7875 | ETL.4782 | 40681309 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118969167 | Mar | DI GEYSERS#3-CLOVERDALE 9/114 RPR SPLW | 44580896 | GEYSERS #3-CLOVERDALE | 009/114 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-28 | 2021-04-27 |  |  | 2021-03-27 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.976162 | 38.8007 | ETL.1650 | 44258747 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118969168 | Q2 | T3NT DI SANTA FE GEOTHERMAL 0/6 RPR FOND | 44310549 | SANTA FE GEOTHERMAL TAP | 000/006 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-04-30 | 2022-04-30 |  |  | 2021-06-04 | 2021-06-01 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.750111 | 38.7837 | ETL.4782 | 40809008 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118971594 | Q2 | T3 DI MNDOCNO-WLLITS 7/13 BOND GUY | 44610679 | MENDOCINO-WILLITS | 007/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-30 | 2020-10-30 | 2021-04-28 | 2021-04-30 | 2021-04-28 | 2021-04-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.294351 | 39.3147 | ETL.7540 | 41113148 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118971739 | Not Scheduled | T2 EI MONTA VISTA-BURNS 4/038 RPR POLE |  | MONTA VISTA-BURNS | 004/038 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-01 | 2021-05-01 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-122.111076 | 37.2734 | ETL.7590 | 40581859 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118971836 | Q2 | T3 DI KONOCTI-EAGLE ROCK 7/006 REPL GYPL | 31502700 | KONOCTI-EAGLE ROCK | 007/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-30 | 2021-05-31 |  |  | 2021-05-07 | 2021-05-07 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.765993 | 38.9101 | ETL.6861 | 40809250 | Guy Pole-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118971895 | Not Scheduled | T2 DI VLY SPRNGS-MRTL#1 12/9 REPL POLE | 31502070 | VALLEY SPRINGS-MARTELL #1 | 012/009 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-28 | 2021-04-28 | [7 empty] | TR2 | <90D | Central | WSIP | [6 empty] | '-120.794515 | 38.3661 | ETL.8240 | 40874927 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-08-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118971993 | Q2 | T3NT DI SANTA FE GTHRML TAP 0/8 RPR FOND | 44310549 | SANTA FE GEOTHERMAL TAP | 000/008 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-04-30 | 2022-04-30 |  |  | 2021-06-04 | 2021-06-01 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.751249 | 38.78 | ETL.4782 | 40870523 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118971994 | Q2 | DI KONOCTI-EAGLE ROCK 0/1 INST MRKW | 44610613 | KONOCTI-EAGLE ROCK | 001/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-04-30 | 2022-04-30 |  |  | 2021-05-05 | 2021-05-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.795393 | 38.8358 | ETL.6861 | 44679459 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118971999 | Q2 | DI SAN RAMON-MORAGA 0/7 RPR FOND |  | SAN RAMON-MORAGA | 000/007 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-30 | 2021-04-30 |  |  | 2021-04-30 | 2021-04-26 | [5 empty] | Central | WSIP | [6 empty] | '-121.950425 | 37.7378 | ETL.5660 | 40664048 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118972150 | Q2 | T2 DI FORT ROSS-GUALALA 52/10 RPR SPLW |  | GUALALA-MONTE RIO | 052/010 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-30 | 2021-04-30 | 2021-06-07 | 2021-06-14 | 2021-06-09 | 2021-06-09 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.450963 | 38.7387 | ETL.6980 | 40616647 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118972217 | Before Feb | T3 EI GEYSERS #12-FULTON 017/071 REPL IN | 31505663 | GEYSERS #12-FULTON | 017/071 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-01 | 2020-11-01 | 2021-01-25 | 2021-01-28 | 2021-01-28 | 2021-01-25 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.74122 | 38.6203 | ETL.4750 | 40620228 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Before Feb |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118972247 | Feb | T2 DI CRTINA-MNDCINO#1 59/292 RPR FOND |  | CORTINA-MENDOCINO #1 | 059/292 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2022-04-23 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.178026 | 39.2409 | ETL.1330 | 40657103 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118975651 | Mar | T3 DI MENDOCINO-WILLITS 9/5L RPR POLE | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 009/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-30 | 2020-10-30 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.7550 | 44211126 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118975739 | Q2 | T2 DI FORT ROSS-GUALALA 47/03 BOND GUY |  | GUALALA-MONTE RIO | 047/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-30 | 2021-04-30 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.364316 | 38.7171 | ETL.6980 | 40648489 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118975813 | Feb | T2 DI CTRA CSTA-MRGA #1 26/121 RPL HRDT | 44640347 | CONTRA COSTA-MORAGA #1 | 026/121 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-27 | 2021-04-27 |  |  | 2021-02-20 | 2021-02-15 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.149228 | 37.8574 | ETL.5452 | 40746203 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118975864 | Feb | T2 DI CORTINA-MNDOCINO#1 25/119 INS HRDT |  | CORTINA-MENDOCINO #1 | 025/119 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-04-23 | 2021-04-23 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.64441 | 39.0272 | ETL.1330 | 40870083 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118975865 | Feb | T2 DI CORTINA-MNDOCINO#1 25/119 RPR FOND |  | CORTINA-MENDOCINO #1 | 025/119 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2022-04-23 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.64441 | 39.0272 | ETL.1330 | 40870083 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118975957 | Feb | T2 DI CORTINA-MENDO #1 33/158 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 033/158 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-04-24 | 2022-04-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.760214 | 39.0794 | ETL.1330 | 40861155 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118975983 | Feb | T2 DI CRTNA-MDCNO #1-TWR 39/191 RPR FOND |  | CORTINA-MENDOCINO #1 | 039/191 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2022-04-23 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.862113 | 39.1374 | ETL.1330 | 40593956 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118975986 | Q2 | T2 DI FORT ROSS-GUALALA 36/03 REPR GYWW |  | GUALALA-MONTE RIO | 036/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2021-04-24 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.297975 | 38.6031 | ETL.6980 | 40661457 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118976411 | Q2 | T3 DI EAGLE ROCK-REDBUD 8/47 RPR FOND | 44637023 | EAGLE ROCK-REDBUD | :008/047 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-01 | 2020-11-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.687963 | 38.8866 | ETL.1480 | 40812433 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118976421 | Q3 | DI GATES MSTANG SW STA #1 5/24 RPR FOND | 44321035 | SPARE T-LINE RECORD | 005/024 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-05-01 | 2022-05-01 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.040001 | 36.1733 | ETL.2604 | 40761924 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-05-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118976605 | Q3 | DI GTS-MSTNG SW STA #1 5/25 REPR FOND | 44321035 | SPARE T-LINE RECORD | 005/025 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-05-01 | 2022-05-01 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.035996 | 36.1753 | ETL.2604 | 40752363 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-06-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118976831 | Mar | T3 EI EAGLE ROCK-FLTN-SLVRD 19/83 RPR FO | 44326454 | EAGLE ROCK-FULTON-SILVERADO | 019/083 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-02 | 2020-11-02 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.616154 | 38.5119 | ETL.4392 | 41129385 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118976832 | Mar | EI T3NT EAGLE RCK-FLTN-SLVRD 19/81 RPR F | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 019/081 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-02 | 2020-11-02 |  |  | 2021-03-31 | 2021-03-29 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.62029 | 38.5149 | ETL.4392 | 41129383 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977248 | Not Scheduled | DI MONTE RIO-FORT ROSS 23/2C BOND GUY |  | ETL.6979.POLE.WDPS | 023/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-28 | 2021-04-28 | [8 empty] | <90D | North Coast | WSIP | [8 empty] | ETL.6979 | 44312236 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977358 | Q3 | T3 EI BRIDGEVILLE-GARBERVLE 03/12 INST I | 31502608 | BRIDGEVILLE-GARBERVILLE | 003/012 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-03 | 2020-11-03 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.779721 | 40.4427 | ETL.6220 | 40698471 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977359 | Q3 | EI T3NT BRIDGEVILLE-GARBERVLL 3/12 RMV B | 44299809 | BRIDGEVILLE-GARBERVILLE | 003/012 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-03 | 2022-05-03 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.779721 | 40.4427 | ETL.6220 | 40698471 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977360 | Q3 | EI T3NT BRIDGEVILLE-GARBERVIL 3/11 RMV B | 44299809 | BRIDGEVILLE-GARBERVILLE | 003/011 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-03 | 2022-05-03 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.780372 | 40.4431 | ETL.6220 | 40600517 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977369 | Q3 | T3 EI BRIDGEVILLE-GARBERVLE 03/07 INST I | 31502608 | BRIDGEVILLE-GARBERVILLE | 003/007 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-03 | 2020-11-03 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.784318 | 40.4455 | ETL.6220 | 40824514 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977370 | Q3 | T3 EI BRIDGEVILLE-GARBERVLE 03/07 RPR PO | 44299806 | BRIDGEVILLE-GARBERVILLE | 003/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-03 | 2020-11-03 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.784318 | 40.4455 | ETL.6220 | 40824514 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977378 | Q3 | T3 EI BRIDGEVILLE-GARBERVLE 3/4 INST INS | 31502608 | BRIDGEVILLE-GARBERVILLE | 003/004 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-03 | 2020-11-03 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.787035 | 40.4471 | ETL.6220 | 40769398 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977379 | Q3 | T3 EI BRIDGEVILLE-GARBERVLE 03/04 RPR CO | 44300097 | BRIDGEVILLE-GARBERVILLE | 003/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-03 | 2020-11-03 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.787035 | 40.4471 | ETL.6220 | 40769398 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977392 | Q3 | T3 EI BRIDGEVILLE-GARBERVLE 03/03 INST I | 31502608 | BRIDGEVILLE-GARBERVILLE | 003/003 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-03 | 2020-11-03 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.788371 | 40.4478 | ETL.6220 | 40666741 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977397 | Q3 | EI T3NT BRIDGEVILLE-GARBERVLL 3/13 RMV B | 44299809 | BRIDGEVILLE-GARBERVILLE | 003/013 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-03 | 2022-05-03 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.778624 | 40.4423 | ETL.6220 | 40650748 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977399 | Q3 | EI T3NT BRIDGEVILLE-GARBERVIL 3/14 RMV B | 44299809 | BRIDGEVILLE-GARBERVILLE | 003/014 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-03 | 2022-05-03 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.777473 | 40.442 | ETL.6220 | 40769396 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977410 | Q3 | T3 EI BRIDGEVILLE-GARBERVLE 03/14 INST I | 31502608 | BRIDGEVILLE-GARBERVILLE | 003/014 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-03 | 2020-11-03 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.777473 | 40.442 | ETL.6220 | 40769396 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977412 | Q3 | T3 EI BRIDGEVILLE-GARBERVLE 03/15 INST I | 31502608 | BRIDGEVILLE-GARBERVILLE | 003/015 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-03 | 2020-11-03 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.775959 | 40.4415 | ETL.6220 | 40752640 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977416 | Q3 | EI T3NT BRIDGEVILLE-GARBERVIL 4/1 RMV BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 004/001 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-03 | 2022-05-03 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.773857 | 40.4409 | ETL.6220 | 40600519 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977426 | Q3 | EI T3NT BRIDGEVILLE-GARBERVIL 4/4 RMV BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 004/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-03 | 2022-05-03 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.772392 | 40.4399 | ETL.6220 | 40769394 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977436 | Q3 | EI T3NT BRIDGEVILLE-GARBERVIL 4/9 RMV BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 004/009 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-03 | 2022-05-03 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.769526 | 40.4376 | ETL.6220 | 40862507 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977705 | Q2 | T2 TRINITY-MAPLE CREEK 36/4 REPL POLE | 31471998 | TRINITY-MAPLE CREEK | 036/004 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-04 | 2021-05-04 | 2021-04-05 | 2021-04-11 | 2021-04-11 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.564376 | 40.7207 | ETL.8170 | 40771342 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118977707 | Q2 | T2 TRINITY-MAPLE CREEK 34/002 REPL POLE | 31471998 | TRINITY-MAPLE CREEK | 034/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2021-05-04 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.528055 | 40.7115 | ETL.8170 | 40701884 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118978719 | Not Scheduled | T2 DI VLY SPRNGS-MRTLL #1 12/7 RPR SPLW |  | VALLEY SPRINGS-MARTELL #1 | 012/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-28 | 2021-04-28 | [7 empty] | TR2 | <90D | Central | WSIP | [6 empty] | '-120.793805 | 38.3643 | ETL.8240 | 40805044 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-06 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118978959 | Not Scheduled | T2 UKIAH-HOPLAND-CLOVERDL 10/92 RPL POLE | 31490866 | UKIAH-HOPLAND-CLOVERDALE | 010/092 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2021-05-04 | [7 empty] | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.125452 | 39.0458 | ETL.4050 | 40755571 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118979053 | Not Scheduled | DI STNSLS-MLNS SS-MTC #1 25/163 RPR STRT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 025/163 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-28 | 2021-04-27 | [8 empty] | <90D | Central | WSIP | [6 empty] | '-120.756719 | 37.927 | ETL.3830 | 40579579 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-05 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118979300 | Q3 | T3 EI BRIDGEVILLE-GARBERVIL 1/5 JUMP INS | 31502608 | BRIDGEVILLE-GARBERVILLE | 001/005 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-04 | 2020-11-04 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.801234 | 40.4661 | ETL.6220 | 40752634 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118979416 | Q3 | EI T3NT BRIDGEVILLE-GARBERVIL 1/10 RMV B | 44299809 | BRIDGEVILLE-GARBERVILLE | 001/010 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-04 | 2022-05-04 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.801697 | 40.4622 | ETL.6220 | 40591052 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118979419 | Q3 | T3 EI BRIDGEVILLE-GARBERVIL 1/10 RPR GYW | 44300097 | BRIDGEVILLE-GARBERVILLE | 001/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-04 | 2020-11-04 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.801697 | 40.4622 | ETL.6220 | 40591052 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118979606 | Q3 | T3 EI BRIDGEVILLE-GARBERVIL 2/2 JUMP SUP | 31502608 | BRIDGEVILLE-GARBERVILLE | 002/002 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-04 | 2020-11-04 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.800513 | 40.4576 | ETL.6220 | 40661797 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118979607 | Q3 | EI T3NT BRIDGEVILLE-GARBERVIL 2/2 RMV BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 002/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-04 | 2022-05-04 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.800513 | 40.4576 | ETL.6220 | 40661797 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118979699 | Q3 | T3 EI BRIDGEVILLE-GARBERVIL 2/4 JMPR INS | 31502608 | BRIDGEVILLE-GARBERVILLE | 002/004 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-04 | 2020-11-04 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.799065 | 40.4563 | ETL.6220 | 40752604 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118979762 | Q3 | T3 EI BRIDGEVILLE-GARBERVIL 2/7 JMPR INS | 31504243 | BRIDGEVILLE-GARBERVILLE | 002/007 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-04 | 2020-11-04 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.794955 | 40.4526 | ETL.6220 | 40810322 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118979763 | Q3 | EI T3NT BRIDGEVILLE-GARBERVIL 2/7 RMV BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 002/007 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-04 | 2022-05-04 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.794955 | 40.4526 | ETL.6220 | 40810322 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118979788 | Q3 | T3 EI BRIDGEVILLE-GARBERVILLE 2/8 RPR PO | 44321287 | BRIDGEVILLE-GARBERVILLE | 002/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2020-11-04 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.794134 | 40.4518 | ETL.6220 | 44650667 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118979835 | Q3 | EI T3NT BRIDGEVILLE-GARBERVIL 2/9 RMV BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 002/009 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-04 | 2022-05-04 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.79362 | 40.4513 | ETL.6220 | 40875306 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118979913 | Q3 | T3 EI BRIDGEVILLE-GARBERVIL 2/11 JMPR IN | 31504243 | BRIDGEVILLE-GARBERVILLE | 002/011 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2020-11-04 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.792487 | 40.4503 | ETL.6220 | 40586717 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118979983 | Q3 | EI T3NT BRIDGEVILLE-GARBERVIL 3/0 RMV BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 003/000 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-04 | 2022-05-04 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.790644 | 40.4492 | ETL.6220 | 40614661 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118980508 | Q2 | T2 DI FORT ROSS-GUALALA 38/6 BOND GUY |  | GUALALA-MONTE RIO | 038/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2021-04-24 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.309053 | 38.6265 | ETL.6980 | 40821470 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118980617 | Q2 | T3 DI KONOCTI-EGL ROCK 4/14 RPR STRW | 44610613 | KONOCTI-EAGLE ROCK | 004/014 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2020-10-24 |  |  | 2021-05-06 | 2021-05-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.784463 | 38.8832 | ETL.6861 | 40750917 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118980717 | Mar | DI MORAGA-SAN LEANDRO #1 9/66 REPR FOND |  | MORAGA-SAN LEANDRO #1 | 009/066 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2022-05-04 |  |  | 2021-03-06 | 2021-03-01 | [5 empty] | Central | WSIP | [6 empty] | '-122.133961 | 37.7252 | ETL.2770 | 40804657 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118980719 | Q3 | DI GATES-MUSTANG SW STA #1 7/33 RPR FOND | 44321035 | SPARE T-LINE RECORD | 007/033 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-05-01 | 2022-05-01 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.004224 | 36.1906 | ETL.2604 | 40650482 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-06-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118981593 | Feb | T2 DI CRTINA-MNDOCINO #1 34/166 INS HRDT | 44238817 | CORTINA-MENDOCINO #1 | 034/166 | ICQ | E | 2020_(3) On high spread structure |  | 2020-04-24 | 2021-04-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.78187 | 39.0962 | ETL.1330 | 40808931 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118981597 | Feb | T2 DI CRTINA-MNDOCINO #1 34/166 RPR STRS | 44610540 | CORTINA-MENDOCINO #1 | 034/166 | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2021-04-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.78187 | 39.0962 | ETL.1330 | 40808931 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118981599 | Not Scheduled | T2 DI CRTINA-MNDOCINO #1 34/166 RPR SPLS | 44610540 | MENDOCINO-REDBUD | 034/166 | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2021-04-24 | [7 empty] | TR2 | <90D | North Coast | WSIP | [6 empty] | '-122.78187 | 39.0962 | ETL.2410 | 40835508 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118981678 | Q2 | T3 EI FULTON-PUEBLO 030/143 RMV HRDT | 44310479 | FULTON-PUEBLO | 030/143 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-04 | 2020-11-04 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.52288 | 38.4918 | ETL.1600 | 40650803 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118981679 | Q2 | T3 EI FULTON-PUEBLO 029/141 RMV HRDT |  | FULTON-PUEBLO | 029/141 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2020-11-04 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.516951 | 38.4931 | ETL.1600 | 40586782 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-30 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118981720 | Feb | T2 DI CRTINA-MNDOCINO #1 34/166 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 034/166 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-04-24 | 2022-04-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.78187 | 39.0962 | ETL.1330 | 40808931 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118981741 | Q2 | T3 EI FULTON-PUEBLO 030/144 RMV HRDT | 44310479 | FULTON-PUEBLO | 030/144 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-04 | 2020-11-04 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.526891 | 38.4906 | ETL.1600 | 40746839 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118981807 | Q2 | T3NT DI PTTSBRG-SAN MATO 11/146 RPR FOND |  | PITTSBURG-SAN RAMON | 011/046 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-27 | 2022-04-27 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.880363 | 37.8816 | ETL.5490 | 40805062 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118981998 | Q3 | EI GATES-MUSTANG SW STA #2 4/22B RPR FON | 44331648 | ETL.2605.TOWR | 004/022B | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-04 | 2021-05-04 |  |  | 2021-08-03 | 2021-08-01 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-120.047735 | 36.1704 | ETL.2605 | 40740272 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-06-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118982218 | Q2 | T2 TRINITY-MAPLE CREEK 12/005 RPL POLE | 31471998 | TRINITY-MAPLE CREEK | 012/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-05 | 2021-05-05 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.139367 | 40.7654 | ETL.8170 | 40752252 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118983818 | Q4 | T3 EI MAPLE CREEK-HOOPA 11/005 RMV PLE B | 44301081 | MAPLE CREEK-HOOPA | 011/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-05 | 2022-11-05 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.770848 | 40.9011 | ETL.7490 | 40770458 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-06-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118983847 | Q3 | DI GATES-GREGG 3/18 INST HRDT | 44321035 | SPARE T-LINE RECORD | 003/018 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-04 | 2021-05-04 |  |  | 2021-08-01 | 2021-06-02 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-120.064615 | 36.1641 | ETL.2604 | 40858294 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-05-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118983896 | Q4 | T3 EI MAPLE CREEK-HPA 11/3 INS JMPR | 44178090 | MAPLE CREEK-HOOPA | 011/003 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-05 | 2020-11-05 |  |  | 2021-10-02 | 2021-07-26 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.771222 | 40.9001 | ETL.7490 | 40668473 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-06-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118983915 | Not Scheduled | T2 EI DIVIDE-VNDNBRG #1 003/024 RPR GYWW |  | DIVIDE-VANDENBERG #1 | 003/024 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-05 | 2021-05-05 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-120.487918 | 34.7917 | ETL.8620 | 40667198 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-26 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118984169 | Not Scheduled | T3 DI MORRO BAY-TEMPLETON 8/37 RPR OPGW |  | MORRO BAY-TEMPLETON | 008/037 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-04 | 2020-11-04 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.749602 | 35.4613 | ETL.5933 | 40810829 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-18 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118984297 | Not Scheduled | T2 WEST POINT-VALLEY SPRNG 6/076 RPL POL | 31504956 | WEST POINT-VALLEY SPRINGS | 006/076 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-05 | 2021-05-05 | [7 empty] | TR2 | <90D | Central | WSIP | [6 empty] | '-120.639628 | 38.3753 | ETL.8350 | 40876055 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118985369 | Not Scheduled | T2 WEST POINT-VALLEY SPRINGS 8/97 RPL PL | 31504957 | WEST POINT-VALLEY SPRINGS | 008/097 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-05 | 2021-05-05 | [7 empty] | TR2 | <90D | Central | WSIP | [6 empty] | '-120.654212 | 38.3556 | ETL.8350 | 40825790 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118988217 | Mar | T3 DI GYSRS#3-CLVERDL 9/106C RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 009/106C | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2020-10-23 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.965766 | 38.7962 | ETL.1650 | 44298419 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118988322 | Q2 | T2 DRUM-SPAULDING 8/219 RPL POLE | 31503704 | DRUM-SPAULDING | 008/219 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2021-05-06 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.649263 | 39.3178 | ETL.6770 | 40616092 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118988981 | Mar | T3 DI MENDONCINO-WILLETS 7/9 RPR GYWW | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 007/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-04 | 2020-11-04 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.29421 | 39.3148 | ETL.7550 | 40875210 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118989050 | Mar | T3 DI SOBRANTE-""R"" #1-TWR 2/16 RPL INSS | 31503751 | SOBRANTE-R #1 | 002/016 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-21 | 2020-10-21 | 2021-03-21 | 2021-03-21 | 2021-03-21 | 2021-03-21 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.249227 | 37.9104 | ETL.3770 | 40830932 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | Tilden RP | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118989320 | Q2 | T3NT DI EAGLE ROCK-REDBUD 7/41 RPR FOND | 44637023 | EAGLE ROCK-REDBUD | :007/041 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-04-27 | 2022-04-27 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.710229 | 38.8816 | ETL.1480 | 40585028 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118990112 | Q2 | DI HUMBOLDT #1 8/6 REPL INSS | 31503644 | HUMBOLDT #1 | 008/006 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-04 | 2021-05-02 |  |  | 2021-04-17 | 2021-04-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-124.055902 | 40.8762 | ETL.7113 | 40809330 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118990485 | Mar | T3 DI PTTBRGH-SANMATEO 11/46 REPL INSS | 31504797 | PITTSBURG-SAN MATEO | 011/046 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-14 | 2020-10-14 |  |  | 2021-03-16 | 2021-03-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.880119 | 37.8815 | ETL.5463 | 40618853 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118990592 | Not Scheduled | NT DI MORRO BAY-TEMPLETON 0/5 RPNT STRS | 44586162 | MORRO BAY-TEMPLETON | 000/005 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-01 | 2022-05-01 | [9 empty] | South | WSIP | [6 empty] | '-120.842897 | 35.3763 | ETL.5933 | 40753139 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118991021 | Q4 | T3 EI MAPLE CREEK-HOOPA 9/3 INST JUMPR I | 31504242 | MAPLE CREEK-HOOPA | 009/003 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-06 | 2020-11-06 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.788591 | 40.8747 | ETL.7490 | 40650870 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-06-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118991419 | Mar | T3 DI SOBRANTE R #1 02/14 RPL SPLS | 44614167 | SOBRANTE-R #1 | 002/014 | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-20 | 2020-10-20 | 2021-03-21 | 2021-03-21 | 2021-03-21 | 2021-03-21 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.24587 | 37.9095 | ETL.3770 | 40746169 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 12 | EBMUD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118991435 | Q2 | T2 DI FORT ROSS-GUALALA 47/3 RPR POLE |  | GUALALA-MONTE RIO | 047/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-30 | 2021-04-30 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.364316 | 38.7171 | ETL.6980 | 40648489 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118991488 | Q3 | DI GATES-MSTNG SW STA#1 3/38 RPR FOND | 44321035 | SPARE T-LINE RECORD | 008/038 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-05-04 | 2022-05-04 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-119.984413 | 36.2001 | ETL.2604 | 40862579 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-06-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118992043 | Mar | T3 DI MORAGA-OAKLAND #1 2/15 RPR SPLS | 44621662 | MORAGA-OAKLAND #1 | 002/015 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2020-11-04 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.195719 | 37.8334 | ETL.2720 | 40745884 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118992051 | Q2 | T3NT DI TGR CRK-VLLY SPRGS 2/16 RPR FOND |  | TIGER CREEK-VALLEY SPRINGS | 002/016 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-04-27 | 2022-04-27 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.525765 | 38.44 | ETL.5790 | 40811205 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118993036 | Not Scheduled | T3 EI COLGATE-ALLEGHANY 15/400 INST SPLT | 44339048 | COLGATE-ALLEGHANY | 015/400 | ICW | E | 2020_(3) On high spread structure |  | 2020-05-05 | 2020-11-05 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.995281 | 39.4428 | ETL.6470 | 40590441 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118993080 | Mar | T3 DI EAGLE ROCK-CORTINA 15/71 RPL INSS | 31505513 | EAGLE ROCK-CORTINA | 015/071 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2020-10-23 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.1470 | 40609219 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118993094 | Not Scheduled | T2 SPAULDING-SUMMIT 10/350 RPL POLE | 31495368 | SPAULDING-SUMMIT | 010/350 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-05-06 | 2021-05-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.473431 | 39.3179 | ETL.8060 | 40668705 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118993324 | Mar | T3 DI MNT VST-JFFERSON #2 16/69 RPL INSS | 31503450 | MONTA VISTA-JEFFERSON #2 | 016/069 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-13 | 2021-05-31 |  |  | 2021-03-05 | 2021-02-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.300736 | 37.4217 | ETL.5230 | 40884747 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 3 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | 93 | Mar |  |  | 2020-06-04 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118993325 | Feb | T3 DI CORTINA-MENDOCNO #1 17/83 RPL INSS | 44610540 | CORTINA-MENDOCINO #1 | 017/083 | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2020-10-24 |  |  | 2021-02-18 | 2021-02-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.505736 | 39.0087 | ETL.1330 | 40648755 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118993326 | Q2 | T3 DI MUR FLT-GLD HLL #1 17/151 RPL INSS | 31502729 | MISSOURI FLAT-GOLD HILL #1 | 017/151 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-29 | 2020-10-29 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.867462 | 38.6708 | ETL.2660 | 40913117 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118993362 | Mar | T3 DI EAGLE ROCK-CORTINA 20/94 RPL INSS | 31505513 | EAGLE ROCK-CORTINA | 020/094 | 93K | E | 2020_(2) High fire spread TD |  | 2020-04-23 | 2020-10-23 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.1470 | 40792694 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118993541 | Q2 | T3NT DI SBRNT-GZLY-CLMT #2 7/48 RPR FOND |  | SOBRANTE-GRIZLY-CLARMNT #2+ | 007/048 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2022-05-04 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.221725 | 37.8476 | ETL.3750 | 40746130 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-26 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118993630 | Q3 | DI GATES-MUSTANG SW STA #1 1/7 BENT STL | 44331647 | SPARE T-LINE RECORD | 001/007 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-04 | 2021-05-04 |  |  | 2021-08-01 | 2021-06-02 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-120.108956 | 36.1479 | ETL.2604 | 40805347 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-06-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118993749 | Mar | T3 DI MORAGA-CLAREMT #1 3/24 RPLC CONCTR | 44621661 | MORAGA-CLAREMONT #1 | 003/024 | ICM | E | 2020_(2) High fire spread TD |  | 2020-05-05 | 2021-05-31 |  |  | 2021-03-22 | 2021-03-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.209114 | 37.8509 | ETL.2700 | 40745853 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | IC | Mar |  |  | 2021-01-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118993773 | Feb | T3 DI CRTNA-MNDCINO#1 17/83 INST HRDT | 44238817 | CORTINA-MENDOCINO #1 | 017/083 | ICQ | E | 2020_(3) On high spread structure |  | 2020-04-24 | 2020-10-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.505736 | 39.0087 | ETL.1330 | 40648755 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118993836 | Q2 | T3NT DI PARKWAY-MORAGA 20/113 RPR FOND | 44298735 | PARKWAY-MORAGA | 020/113 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-04 | 2022-05-04 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.19896 | 37.8762 | ETL.5930 | 40868391 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y -1 3 | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118993843 | Not Scheduled | T2 DI SAN LS OBSPO-CYCS 11/105 RPLC CRSW | 31505054 | SAN LUIS OBISPO-CAYUCOS | 011/105 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-05-05 | 2021-05-05 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-120.752372 | 35.3149 | ETL.9090 | 40589825 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-05-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118995077 | Q2 | T3 DI PITTSBURGûSAN MATEO 10/40 RPR FOND | 44623139 | PITTSBURG-SAN MATEO | 010/040 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-05 | 2022-11-05 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.880704 | 37.8997 | ETL.5463 | 40746309 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | MDSP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118995441 | Q3 | DI GATES-MUSTANG SW STA #1 5/23 RPR FOND | 44321035 | SPARE T-LINE RECORD | 005/023 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-05-05 | 2022-05-05 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.043543 | 36.1718 | ETL.2604 | 40644918 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-05-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118995444 | Q3 | DI GATES-MUSTANG SW STA #1 5/23 BENT STL | 44321035 | SPARE T-LINE RECORD | 005/023 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-05 | 2021-05-03 |  |  | 2021-08-01 | 2021-06-02 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-120.043543 | 36.1718 | ETL.2604 | 40644918 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-05-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118995447 | Mar | T3 DI SBRNTûGRZLYûCLRMT#1 3/34 RPR SPLS | 44621665 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 003/034 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-05 | 2020-11-05 | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-03-18 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.174892 | 37.862 | ETL.3740 | 40861013 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118995448 | Q3 | DI GATES-MUSTAND SW STA#1 3/17 RPR FOND | 44341601 | SPARE T-LINE RECORD | 003/017 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-05 | 2021-05-05 |  |  | 2021-08-01 | 2021-06-02 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-120.068815 | 36.1626 | ETL.2604 | 40805349 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-06-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118996319 | Q2 | T3 DI SRMNT-GRZLY-CLRMT#1 3/35 RPR STRS | 44624393 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 003/035 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-04 | 2020-11-04 |  |  | 2021-05-31 | 2021-05-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.173894 | 37.8601 | ETL.3740 | 40857621 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118997052 | Feb | T3 DI EL DRD-MISSOU FLT #1 2/22 RPR STRS | 44332237 | ELDORADO-MISSOURI FLAT #1 | 002/022 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-01 | 2020-11-01 |  |  | 2021-02-22 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.65948 | 38.7681 | ETL.1530 | 44722642 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118997476 | Not Scheduled | LOS BANOS-MIDWAY #2 125/517 RMV DEBRIS | 44637107 | LOS BANOS-MIDWAY #2 | 125/517 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-05-07 | 2021-05-07 | [6 empty] | Tower guy |  | WECC | South | WSIP | [6 empty] | '-119.639999 | 35.6321 | ETL.6010 | 40811544 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - 26 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 118997954 | Not Scheduled | T2 DI SAN LS OBSPO-CYCS 14/136C RPR STRW |  | SAN LUIS OBISPO-CAYUCOS | 014/136 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-05 | 2021-05-05 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-120.802772 | 35.3511 | ETL.9090 | 44565321 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-18 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118999616 | Mar | T3 DI MORAGA-OAKLAND #3 2/17 RPLC INSS | 31504796 | MORAGA-OAKLAND #3 | 002/017 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-01 | 2020-11-01 | 2021-03-28 | 2021-03-30 | 2021-03-30 | 2021-03-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.19539 | 37.8331 | ETL.2740 | 40828528 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-08 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 118999617 | Mar | T3 DI MORAGA-OAKLAND #4 2/17 RPLC INSS | 31508629 | MORAGA-OAKLAND #4 | 002/017 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-01 | 2020-11-01 | 2021-03-28 | 2021-03-30 | 2021-03-30 | 2021-03-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.19539 | 37.8331 | ETL.2750 | 40828530 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 2 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-08 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119000339 | Mar | T3 DI MORAGA-OAKLAND #1 2/14 RPLC INSS | 31504785 | MORAGA-OAKLAND #1 | 002/014 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-01 | 2020-11-01 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.194 | 37.8345 | ETL.2720 | 40775596 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-08 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119000428 | Mar | T3 DI DRUM-RIO OSO#2 3/31 REPL INSS | 31502784 | DRUM-RIO OSO #2 | 003/031 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-06 | 2020-11-06 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.817735 | 39.2434 | ETL.1430 | 40594983 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119000451 | Mar | T3 DI MORAGA-OAKLAND #2 2/14 RPLC INSS | 31461003 | MORAGA-OAKLAND #2 | 002/014 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-01 | 2020-11-01 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.194 | 37.8345 | ETL.2730 | 40775598 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 2 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-08 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119001057 | Not Scheduled | T3 DI ATASCADERO-CAYUCOS 3/32 REPL POLE | 31502804 | ATASCADERO-CAYUCOS | 003/032 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2020-11-06 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.729454 | 35.4645 | ETL.8480 | 40760575 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-27 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119001877 | Q2 | DI HUMBOLDT#1 9/006 RPLC INSS | 31503644 | HUMBOLDT #1 | 009/006 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-07 | 2021-05-05 |  |  | 2021-04-17 | 2021-04-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-124.054634 | 40.8916 | ETL.7113 | 40809332 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119002581 | Not Scheduled | T2 DI SAN LS OBISPO-CYCS 6/39 RPR GYWW |  | SAN LUIS OBISPO-CAYUCOS | 006/039 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2021-05-06 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-120.663511 | 35.3133 | ETL.9090 | 40602151 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-18 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119002584 | Mar | T3 DI SAN RAMON-MORAGA 6/27 RPLC INSS | 31504799 | SAN RAMON-MORAGA | 006/027 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-05 | 2020-11-05 |  |  | 2021-03-18 | 2021-03-18 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.018436 | 37.6879 | ETL.5660 | 40605001 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119003006 | Not Scheduled | T3 DI SN LS OBIS-SNT MAR 13/236 RMV BUTT |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/236 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-05-06 | 2022-05-06 | [7 empty] | TR3 |  | South | WSIP | [6 empty] | '-120.510879 | 35.1255 | ETL.9100 | 44191949 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119003116 | Mar | T3 DI PARKWAY-MORAGA 020/110 REPL INSS | 31503747 | PARKWAY-MORAGA | 020/110 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-04 | 2020-11-04 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.203444 | 37.8788 | ETL.5930 | 40788335 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119003303 | Q2 | T2 DI ELK-GUALALA 62/004 RPLC INSW | 31502611 | ELK-GUALALA | 062/004 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-05 | 2021-05-05 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.561674 | 38.831 | ETL.8410 | 40763065 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119003306 | Not Scheduled | DI BEARDSLEY TAP 2/1 RPLC INSW | 31502805 | BEARDSLEY TAP | 002/001 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-01 | 2021-04-30 | [8 empty] | <90D | Central | WSIP | [6 empty] | '-120.060335 | 38.1826 | ETL.1401 | 44390868 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - 15 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-05-13 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119003619 | Q3 | DI GATES-MUSTANG SW STA#1 9/42 INS HRDT | 44321500 | SPARE T-LINE RECORD | 009/042 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-05 | 2021-05-05 |  |  | 2021-08-01 | 2021-06-02 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-119.968562 | 36.2078 | ETL.2604 | 40647633 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-05-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119004448 | Q3 | DI GATES-MSTNG SW STA #1 6/27 RPR FOND | 44322513 | SPARE T-LINE RECORD | 006/027 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-05-01 | 2022-05-01 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.02802 | 36.1791 | ETL.2604 | 40810057 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-06-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119004507 | Q2 | T3 DI SBRNTE-GRZLY-CLRMNT 6/41 RPL HRDT | 44326313 | SOBRANTE-GRIZLY-CLARMNT #2+ | 006/041 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-06 | 2020-11-06 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.203615 | 37.8567 | ETL.3750 | 40818449 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119004560 | Q3 | DI GATES-MUSTANG SW STA#1 9/42 RPR FOND | 44321500 | SPARE T-LINE RECORD | 009/042 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-05 | 2021-05-05 |  |  | 2021-08-01 | 2021-06-02 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-119.968562 | 36.2078 | ETL.2604 | 40647633 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-05-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119004605 | Q2 | T3 DI PITTSBURG-SAN MATEO 10/41 RPR FOND |  | PITTSBURG-SAN MATEO | 010/041 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2020-11-06 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.879973 | 37.8978 | ETL.5463 | 40819140 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | MDSP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119004607 | Feb | T3 DI MORAGA-OAKLAND #1 1/12 BENT STL |  | MORAGA-OAKLAND #1 | 001/012 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2020-11-04 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.189143 | 37.8371 | ETL.2720 | 40648544 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-05-15 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119004609 | Mar | T3 DI MORAGA-OAKLAND #1 1/12 RPL SPLS | 44621662 | MORAGA-OAKLAND #1 | 001/012 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2020-11-04 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.189143 | 37.8371 | ETL.2720 | 40648544 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 8 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119004730 | Mar | T3 DI MORAGA-OAKLAND #3 1/12 RPLC INSS | 31504796 | MORAGA-OAKLAND #3 | 001/012 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2020-11-04 | 2021-03-28 | 2021-03-30 | 2021-03-30 | 2021-03-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.18779 | 37.8378 | ETL.2740 | 40704844 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-05-15 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119004836 | Not Scheduled | T2 DI DIABLO-MESA 20/91 REPL INSS | 31503711 | DIABLO-MESA | 020/091 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2021-05-06 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-120.592536 | 35.1733 | ETL.4620 | 40611912 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-06-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119004847 | Q3 | DI GATES-MSTNG SW STA #1 7/32 RPR FOND | 44331647 | SPARE T-LINE RECORD | 007/032 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-04 | 2021-05-04 |  |  | 2021-08-01 | 2021-06-02 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-120.008201 | 36.1887 | ETL.2604 | 40647629 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-06-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119004875 | Q2 | T3 EI DRUM-SPAULDING 1/33 RPL POLE | 31504201 | DRUM-SPAULDING | 001/033 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-09 | 2020-11-09 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.745074 | 39.2545 | ETL.6770 | 40586058 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119004885 | Not Scheduled | T3 DI ATASCADERO-CAYUCOS 7/61 RPR GYWW | 44392212 | ATASCADERO-CAYUCOS | 007/061 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-05 | 2020-11-05 | [8 empty] | LATE | South | WSIP | [8 empty] | ETL.8480 | 44319828 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119004888 | Not Scheduled | T3 DI ATASCADERO-CAYUCOS 7/61 RPR GYWW | 44392211 | ATASCADERO-CAYUCOS | 007/061 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-05 | 2020-11-05 | [8 empty] | LATE | South | WSIP | [8 empty] | ETL.8480 | 44319829 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119004889 | Not Scheduled | T3 DI ATASCADERO-CAYUCOS 7/61 RPR GYWW | 44392217 | ATASCADERO-CAYUCOS | 007/061 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-05 | 2020-11-05 | [8 empty] | LATE | South | WSIP | [8 empty] | ETL.8480 | 44319830 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119004902 | Q2 | T3 DI PARKWAY-MORAGA 020/112 INST BOLT | 44298735 | PARKWAY-MORAGA | 020/112 | ICQ | E | 2020_(3) On high spread structure |  | 2020-05-01 | 2020-11-01 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.201294 | 37.8781 | ETL.5930 | 40816009 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119004903 | Q2 | T3NT DI PARKWAY-MORAGA 020/111 REPR FOND | 44298735 | PARKWAY-MORAGA | 020/111 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-04 | 2022-05-04 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.202125 | 37.8784 | ETL.5930 | 40819377 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119004909 | Not Scheduled | T3 DI MNTE RIO-FORT ROSS 19/004 RPR STRW |  | ETL.6979.POLE.WOOD | 019/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2020-11-06 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.086718 | 38.4826 | ETL.6979 | 40770580 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119004981 | Mar | T3 DI DRUM-RIO OSO #2 2/29 RPLC INSS | 31502784 | DRUM-RIO OSO #2 | 002/029 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-06 | 2021-05-31 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.81607 | 39.2451 | ETL.1430 | 40896820 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119004989 | Mar | T3 DI MORAGA-OAKLAND #1 0/6 RPR SPLS | 44621662 | MORAGA-OAKLAND #1 | 000/006 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-06 | 2020-11-06 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.174207 | 37.8454 | ETL.2720 | 40830509 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119005003 | Q3 | DI GATES-MSTNG SW STA#1 8/37 RPR FOND | 44331647 | SPARE T-LINE RECORD | 008/037 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-04 | 2021-05-04 |  |  | 2021-08-01 | 2021-06-02 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-119.988362 | 36.1982 | ETL.2604 | 40805351 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-06-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119005128 | Mar | T3 DI POTTER VALLEY-WILLITS 9/0 RPR POLE | 44610689 | POTTER VALLEY-WILLITS | 009/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-30 | 2020-10-30 |  |  | 2021-03-08 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.2749 | 39.3733 | ETL.7820 | 40587664 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119005135 | Feb | T2 DI PHILO JCT-ELK 031/006 RPL ANCW | 31504605 | PHILO JCT-ELK | 031/006 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2021-05-06 |  |  | 2021-02-10 | 2021-02-10 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.622913 | 39.1289 | ETL.7780 | 40826087 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-07-23 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119005169 | Not Scheduled | DI SAN LUIS OBSPO-CYCOS 15/138 RPR STRW |  | SAN LUIS OBISPO-CAYUCOS | 015/138 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2021-05-04 | [8 empty] | <90D | South | WSIP | [6 empty] | '-120.811272 | 35.3574 | ETL.9090 | 40597749 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119005193 | Feb | T3 DI MORAGA-CLAREMONT #1 3/22 RPR FOND | 44631266 | MORAGA-CLAREMONT #1 | 003/022 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-06 | 2021-05-31 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.203444 | 37.8566 | ETL.2700 | 40645976 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | IC | Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119005199 | Feb | T3 DI ELDORADO-MIS FLT #1 1/10 RPR SPLS | 44339704 | ELDORADO-MISSOURI FLAT #1 | 001/010 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-06 | 2020-11-06 |  |  | 2021-02-22 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.636483 | 38.7824 | ETL.1530 | 40590079 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119005245 | Q3 | DI GATES-MSTNG SW STA#1 10/46 RPR FOND | 44323385 | SPARE T-LINE RECORD | 010/046 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-05-04 | 2022-05-04 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-119.95275 | 36.2154 | ETL.2604 | 40805362 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-06-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119005264 | Feb | T3 DI DRUM-RIO OSO #1 2/21 RPR STRS | 44326627 | DRUM-RIO OSO #1 | 002/021 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-06 | 2020-11-06 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.804424 | 39.2526 | ETL.1420 | 40589593 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119005372 | Q2 | T3 EI DRUM-SPAULDING 1/36 RPL POLE | 31504201 | DRUM-SPAULDING | 001/036 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-09 | 2020-11-09 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.744002 | 39.2564 | ETL.6770 | 40751829 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119005736 | Not Scheduled | DI GATES-MUSTANG SW STA #1 0/3 INS MRKS | 44323214 | SPARE T-LINE RECORD | 000/003 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-05-05 | 2022-05-05 | [9 empty] | South | WSIP | [6 empty] | '-120.12269 | 36.1428 | ETL.2604 | 40662283 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119005833 | Feb | T2 DI CRTNA-MNDCINO#1 33/159 INST HRDT | 44238817 | CORTINA-MENDOCINO #1 | 033/159 | ICQ | E | 2020_(3) On high spread structure |  | 2020-04-24 | 2021-04-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.761358 | 39.0803 | ETL.1330 | 40870087 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119005902 | Not Scheduled | T2NT DI EXCHEQUER-INDIN FLT 1/9 PNT STRT | 44341671 | EXCHEQUER-YOSEMITE | 001/009 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-04 | 2022-05-04 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.253778 | 37.5758 | ETL.8650 | 40859233 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 42 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-15 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119013664 | Feb | T2 DI CORTINA-MENDO#1 59/287 INST HRDT |  | CORTINA-MENDOCINO #1 | 059/287 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-04-24 | 2021-04-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.168048 | 39.2418 | ETL.1330 | 40808543 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119013685 | Q2 | T3NT DI FULTON-IGNACIO #1 1/10 RPR FOND | 44310479 | FULTON-IGNACIO #1 | 001/010 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2022-05-06 |  |  | 2021-04-23 | 2021-04-19 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.733963 | 38.4975 | ETL.4680 | 40592327 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119014465 | Mar | T2 DI CORTNA-MENDOCNO #1 35/168 RPR FOND |  | CORTINA-MENDOCINO #1 | 035/168 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2021-04-24 |  |  | 2021-03-05 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.787096 | 39.1 | ETL.1330 | 40861157 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119014589 | Q2 | T3 DI EAGLE ROCK-REDBUD :1/6 RPR FOND | 44637023 | EAGLE ROCK-REDBUD | :001/006 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-05 | 2020-11-05 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.795296 | 38.8357 | ETL.1480 | 40809066 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119014640 | Mar | T2 DI CORTNA-MENDOCNO #1 36/171 RPR STRT |  | CORTINA-MENDOCINO #1 | 036/171 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2021-04-23 |  |  | 2021-03-05 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.799896 | 39.1069 | ETL.1330 | 40584925 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119015279 | Not Scheduled | T3 DI MISSOURI FLAT-GLD HL#1 RPR FOND | 44339849 | MISSOURI FLAT-GOLD HILL #1 | 019/161 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2020-11-06 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.902231 | 38.6625 | ETL.2660 | 40586140 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119015476 | Q3 | DI GATES-GREGG 7/34 RPR STRT | 44341601 | SPARE T-LINE RECORD | 007/034 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-05 | 2021-05-05 |  |  | 2021-08-01 | 2021-06-02 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-120.000248 | 36.1925 | ETL.2604 | 40746628 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-06-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119015591 | Q3 | DI GATES-GREGG 7/34 RPR FOND | 44341601 | SPARE T-LINE RECORD | 007/034 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-05 | 2021-05-05 |  |  | 2021-08-01 | 2021-06-02 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-120.000248 | 36.1925 | ETL.2604 | 40746628 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-06-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119016121 | Feb | DI RIO DELL JCT-BRIDGEVLLE 37/4 RPL POLE | 31503085 | RIO DELL JCT-BRIDGEVILLE | 037/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-07 | 2021-05-07 |  |  | 2021-02-27 | 2021-02-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.836218 | 40.4665 | ETL.7850 | 40769400 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-08-21 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119016211 | Q2 | T3 DI EAGLE ROCK-REDBUD :9/53 RPR FOND | 44637023 | EAGLE ROCK-REDBUD | :009/053 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-05 | 2020-11-05 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.66868 | 38.8881 | ETL.1480 | 40648896 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119016272 | Not Scheduled | T2 DI SAN LS OBISPO-CYCS 9/67 RPR SPLW |  | SAN LUIS OBISPO-CAYUCOS | 009/067 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2021-05-06 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-120.693562 | 35.3166 | ETL.9090 | 40760560 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-15 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119016315 | Q2 | T2 DI FORT ROSS-GUALALA 038/008 RPR GYWW |  | GUALALA-MONTE RIO | 038/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2021-04-24 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.31194 | 38.6258 | ETL.6980 | 40860960 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119016549 | Q2 | T2 DI FORT ROSS-GUALALA 51/000 REPR GYWW |  | GUALALA-MONTE RIO | 051/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-07 | 2021-05-07 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.4223 | 38.7298 | ETL.6980 | 40606927 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119016620 | Mar | T2 DI CORTNA-MENDOCNO #1 40/196 RPR FOND |  | CORTINA-MENDOCINO #1 | 040/196 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-23 | 2022-04-23 |  |  | 2021-03-05 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.876013 | 39.1421 | ETL.1330 | 40822489 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119016680 | Q2 | T2 DI FORT ROSS-GUALALA 51/000 REPL INSW | 31502792 | GUALALA-MONTE RIO | 051/000 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-05-07 | 2021-05-07 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.422878 | 38.73 | ETL.6980 | 40637492 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119016688 | Feb | DI RIO DLL JCT-BRDGVLE 39/04 RMV BUTT | 44326491 | RIO DELL JCT-BRIDGEVILLE | 039/004 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-06 | 2022-05-06 |  |  | 2021-02-27 | 2021-02-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.801747 | 40.4704 | ETL.7850 | 40750417 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119016690 | Q2 | T3 EAGLE RCK-FLTN-SLVRDO 11/45 RPR SLEEV |  | EAGLE ROCK-FULTON-SILVERADO | 011/045 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-11 | 2020-11-11 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.727002 | 38.595 | ETL.4392 | 41129347 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119016734 | Q2 | DI FORT ROSS-GUALALA 042/000 RPR GYWW |  | GUALALA-MONTE RIO | 042/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2021-05-06 | 2021-06-15 | 2021-06-18 | 2021-06-18 | 2021-06-15 |  |  |  |  | SCHD | North Coast | WSIP | [8 empty] | ETL.6980 | 44312229 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119016735 | Q2 | T2 PHILO JCT ELK 011/000 REPAIR POLEW | 44610684 | PHILO JCT-ELK | 011/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-08 | 2021-05-08 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.311373 | 39.0274 | ETL.7780 | 44799552 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119016736 | Q2 | DI FORT ROSS-GUALALA 042/000 BOND GUY |  | GUALALA-MONTE RIO | 042/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2021-05-06 | 2021-06-15 | 2021-06-18 | 2021-06-18 | 2021-06-15 |  |  |  |  | SCHD | North Coast | WSIP | [8 empty] | ETL.6980 | 44312228 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119016750 | Q3 | DI GATES-MSTNG SW STA#1 10/45 RPR STRT | 44571491 | SPARE T-LINE RECORD | 010/045 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-04 | 2021-05-04 |  |  | 2021-08-01 | 2021-06-02 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-119.95683 | 36.2134 | ETL.2604 | 40746598 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-05-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119016752 | Q3 | DI GATES-MSTNG SW STA#1 10/45 INST HRDT | 44328897 | SPARE T-LINE RECORD | 010/045 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-04 | 2021-05-04 |  |  | 2021-08-01 | 2021-06-02 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-119.95683 | 36.2134 | ETL.2604 | 40746598 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-05-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119016775 | Q2 | T3 DI FULTON-LAKEVILLE 027/121 REPL INSS | 31506378 | FULTON-LAKEVILLE | 027/121 | 93K | E | 2020_(1a) PSPS |  | 2020-05-08 | 2020-11-08 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.592944 | 38.4655 | ETL.4950 | 41130060 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119016778 | Mar | T3 DI DRUM-RIO OSO #2 2/28 RPR STRT | 44326630 | DRUM-RIO OSO #2 | 002/028 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-06 | 2020-11-06 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.815381 | 39.2455 | ETL.1430 | 40866872 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119017125 | Mar | T2NT DI CORTNA-MNDCNO #1 48/234 RPR FOND |  | CORTINA-MENDOCINO #1 | 048/234 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2022-04-24 |  |  | 2021-03-05 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.976271 | 39.2013 | ETL.1330 | 40750610 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119017159 | Q2 | DI ELK-GUALALA 052/001 REPL INSW | 31504606 | ELK-GUALALA | 052/001 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2021-05-06 | 2021-05-20 | 2021-05-21 | 2021-05-21 | 2021-05-20 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.6763 | 38.9269 | ETL.8410 | 40621651 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119019640 | Mar | T2 EAGLE ROCK-CORTINA 13/062 RPL HANGER | 44346063 | EAGLE ROCK-CORTINA | 013/062 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2021-05-12 |  |  | 2021-03-24 | 2021-03-24 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.437368 | 39.0383 | ETL.1470 | 44941620 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119019649 | Mar | T2 EAGLE ROCK-CORTINA 11/056 RPL HANGER | 44346063 | EAGLE ROCK-CORTINA | 011/056 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-12 | 2021-05-12 |  |  | 2021-03-24 | 2021-03-24 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.412288 | 39.0525 | ETL.1470 | 44941619 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119019697 | Mar | T2 SOBRNTE-GRZLY-CLRMNT #2 A0/1 RPR SWTC | 44621458 | SOBRANTE-GRIZLY-CLARMNT #2+ | A000/001 | ICE | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-12 | 2021-05-12 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.21048 | 37.9048 | ETL.3750 | 40705186 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Bay |  | Y - 14 | EBMUD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-05 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119019961 | Q2 | T3 DI OLEUM-G #2 8/55 RPLC INSS |  | OLEUM-G #2 | 008/055 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-11 | 2020-11-11 | 2021-05-15 | 2021-05-15 | 2021-05-15 | 2021-05-15 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.271784 | 37.9449 | ETL.3160 | 40774777 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | WCRP | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119020768 | Not Scheduled | DRUM-GRASS VLLY-WMR B025/567 REWORK | 31454660 | DRUM-GRASS VALLEY-WEIMAR | B025/567 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2021-05-12 | [8 empty] | <90D | North Valley | WSIP | [6 empty] | '-121.061376 | 39.2042 | ETL.6760 | 40866687 | Crossarm-Wood | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119021013 | Not Scheduled | T3 DI ATASCADERO-CAYUCOS 6/59 REFRAME | 31504190 | ATASCADERO-CAYUCOS | 006/059 | 93E | E | 2020_(2) High fire spread TD |  | 2020-05-07 | 2020-11-07 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.784285 | 35.4603 | ETL.8480 | 40872891 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119021662 | Not Scheduled | T2 DI SAN LUIS OBSPO-CYCS 14/127 RPR PL |  | SAN LUIS OBISPO-CAYUCOS | 014/127 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2021-05-04 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-120.788506 | 35.3404 | ETL.9090 | 40596531 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-15 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119021667 | Not Scheduled | T2 DI SLO-CAYUCOS 14/128 RPR GUY HRDD |  | SAN LUIS OBISPO-CAYUCOS | 014/128 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2021-05-04 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-120.790368 | 35.3418 | ETL.9090 | 40597794 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-15 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119022412 | Not Scheduled | T2 DI SLO-CAYUCOS 14/128 RPR STRW |  | SAN LUIS OBISPO-CAYUCOS | 014/128 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2021-05-04 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-120.790368 | 35.3418 | ETL.9090 | 40597794 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-15 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119023441 | Not Scheduled | T2 DI SAN LS OBISPO-CYCS 7/49 RPR INSW |  | SAN LUIS OBISPO-CAYUCOS | 007/049 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2021-05-06 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-120.676223 | 35.3161 | ETL.9090 | 40717170 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-15 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119024393 | Not Scheduled | T2 DI SAN LS OBISPO-CYCS 7/51 RPLC SPLW |  | SAN LUIS OBISPO-CAYUCOS | 007/051 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2021-05-06 | [7 empty] | TR2 | <90D | South | WSIP | [8 empty] | ETL.9090 | 44376815 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119024972 | Mar | T3 DI EAGLE RK-FLTN-SLVRDO 7/36 RPR STRT | 44326454 | EAGLE ROCK-FULTON-SILVERADO | 007/036 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-11 | 2020-11-11 |  |  | 2021-03-31 | 2021-03-29 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.76483 | 38.7442 | ETL.4392 | 40814652 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119026416 | Mar | T3 DI MORAGA-SN LEANDRO #1 3/29 RPR FOND |  | MORAGA-SAN LEANDRO #1 | 003/029 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-11 | 2020-11-11 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.130524 | 37.802 | ETL.2770 | 40870097 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119026447 | Not Scheduled | T3 DI TIGR CRK-VLLY SPGS 8/65 REPL INSS | 31512319 | TIGER CREEK-VALLEY SPRINGS | 008/065 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-27 | 2020-10-27 | [8 empty] | LATE | Central | WSIP | [6 empty] | '-120.624676 | 38.3964 | ETL.5790 | 40718480 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119026564 | Q2 | T2 DI ELK-GUALALA 055/008 RPR GYWW |  | ELK-GUALALA | 055/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-07 | 2021-05-31 | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-19 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.637946 | 38.9031 | ETL.8410 | 40871841 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119026673 | Q2 | T3 DI FULTON-PUEBLO 029/141 REPR FOND |  | FULTON-PUEBLO | 029/141 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2020-11-12 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.516951 | 38.4931 | ETL.1600 | 40586782 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119026754 | Q2 | DI WEST PONT-VLY SPRNGS 4/55 RMV PL BUTT |  | WEST POINT-VALLEY SPRINGS | 004/055 | GAR | F | 2020_(4) TD tag on high spread line |  | 2020-05-11 | 2022-05-11 |  |  | 2021-04-10 | 2021-04-05 | [5 empty] | Central | WSIP | [8 empty] | ETL.8350 | 44405873 | Structure-Wood | Rotten | Stub |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 586 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | GAR | Q2 |  |  | 2020-05-14 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119026758 | Mar | T2 DI MONTA VSTA-JFFRSN #1 6/25 RPL HRDT |  | MONTA VISTA-JEFFERSON #1 | 006/025 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-11 | 2021-05-11 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.180639 | 37.3299 | ETL.5220 | 40760553 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 12 | LTOSP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119026759 | Mar | T2NT DI MNT VSTA-JFFRSN #1 6/25 RPR FOND |  | MONTA VISTA-JEFFERSON #1 | 006/025 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-11 | 2022-05-11 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.180639 | 37.3299 | ETL.5220 | 40760553 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 | LTOSP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119027090 | Not Scheduled | T2 DI VLY SPRNGS-MRTL#1 10/14 RPR STRW |  | VALLEY SPRINGS-MARTELL #1 | 010/014 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-11 | 2021-05-11 | [7 empty] | TR2 | <90D | Central | WSIP | [6 empty] | '-120.783152 | 38.3432 | ETL.8240 | 40768889 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-17 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119027252 | Q2 | DI MUSTANG SW STA-GRGG X056/238 RPR FOND | 44346364 | GATES-GREGG | X056/238 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-08 | 2021-05-08 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.900693 | 36.8259 | ETL.4700 | 40858326 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119027258 | Q2 | DI MUSTANG SW STA-GRGG X055/236 RPR STRT | 44342028 | GATES-GREGG | X055/236 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-07 | 2021-05-07 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.900705 | 36.8198 | ETL.4700 | 40805390 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119027344 | Q2 | DI MUSTANG SW STA-GRGG X055/236 RPR FOND | 44342028 | GATES-GREGG | X055/236 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-07 | 2021-05-07 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.900705 | 36.8198 | ETL.4700 | 40805390 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119027349 | Not Scheduled | DI MUSTNG SW STA-GRGG X49/206 RMV DEBRIS | 44341661 | GATES-GREGG | X049/206 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-05-05 | 2021-05-05 | [8 empty] | WECC | South | WSIP | [6 empty] | '-119.897204 | 36.7298 | ETL.4700 | 40815319 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119028433 | Q2 | DI SNEATH LN-HALF MOON BY ?0/2 RPR INSW | 31503553 | SNEATH LANE-HALF MOON BAY | ?000/002 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2021-05-10 |  |  | 2021-05-13 | 2021-04-16 | [5 empty] | Central | WSIP | [6 empty] | 122.4893 | 37.5942 | ETL.7212 | 40714078 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Bay |  | Y - 29 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-06-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119028435 | Mar | T3 DI MORAGA-OAKLAND #4 1/12 RPLC INSS | 31508629 | MORAGA-OAKLAND #4 | 001/012 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-04 | 2020-11-04 | 2021-03-28 | 2021-03-30 | 2021-03-30 | 2021-03-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.187282 | 37.8378 | ETL.2750 | 40704846 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 2 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-08 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119029024 | Not Scheduled | T3 EI MIDDLE FORK #1 7/105 RPR GWSW | 44339848 | MIDDLE FORK #1 | 007/105 | ICK | E | 2020_(2) High fire spread TD |  | 2020-05-14 | 2020-11-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.711017 | 39.0029 | ETL.8405 | 40810143 | Auto Guy Wire Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 515 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119029025 | Not Scheduled | T3 EI MIDDLE FORK #1 7/105 RPR ANCW | 44339029 | MIDDLE FORK #1 | 007/105 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-14 | 2020-11-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.711017 | 39.0029 | ETL.8405 | 40810143 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119029026 | Not Scheduled | T3 EI MIDDLE FORK #1 7/105 RMV VEGN |  | MIDDLE FORK #1 | 007/105 | HNA | E | 2020_(3) On high spread structure |  | 2020-05-14 | 2020-11-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.711017 | 39.0029 | ETL.8405 | 40810143 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119029112 | Feb | T2 ROUND MTN-COTTNWD #3 46/399 RPL INSS | 31504993 | ROUND MTN-COTTONWOOD #3 | 046/399 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-14 | 2021-05-14 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.1314537 | 40.5604 | ETL.5650 | 40884291 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-07-14 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119029325 | Not Scheduled | T3 EI MIDDLE FORK #1 7/107 RPR ANCW | 44339029 | MIDDLE FORK #1 | 007/107 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-14 | 2020-11-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.713808 | 39.003 | ETL.8405 | 40874900 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119029389 | Not Scheduled | T3 EI MIDDLE FORK #1 7/106 BOND GUY | 44339029 | MIDDLE FORK #1 | 007/106 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-14 | 2020-11-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.712705 | 39.003 | ETL.8405 | 40822815 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119029406 | Feb | T3 EI ORO FINO TAP - 60 kV_000/012 RPR S | 43758390 | ORO FINO TAP | 000/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-14 | 2020-11-14 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.620065 | 39.8688 | ETL.6721 | 40700244 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119029671 | Q2 | T3 LAURELES-OTTER 013/013 RPR STRW | 31475444 | LAURELES-OTTER | 013/013 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-05-14 | 2020-11-14 | 2021-06-01 | 2021-06-04 | 2021-06-04 | 2021-06-01 |  |  | Likely MAT error - delink to correct | TR3 | LATE | South | WSIP | [6 empty] | '-121.868232 | 36.3862 | ETL.7380 | 40668280 | Structure-Wood | No Good/Out of Stdrd | Repair | POST | POST | POST Estimate | Not Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Moss Landing |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-06-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119029767 | Not Scheduled | T2 VLY SPRGS-MARTELL #1 003/019 RPL PL T | 31503164 | VALLEY SPRINGS-MARTELL #1 | 003/019 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-07 | 2021-04-07 | [7 empty] | TR2 | <60D | Central | WSIP | [6 empty] | '-120.772185 | 38.2556 | ETL.8240 | 40874931 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-06-17 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119030082 | Q2 | T2 PHILO JCT-ELK 007/000 RPR CONDW | 44610684 | PHILO JCT-ELK | 007/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-14 | 2021-05-14 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.24797 | 39.0515 | ETL.7780 | 40614234 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119030163 | Feb | T2 DI CORTINA-MENDCINO #1 13/63 RPL INSS | 31502267 | CORTINA-MENDOCINO #1 | 013/063 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-13 | 2021-05-13 |  |  | 2021-02-20 | 2021-02-18 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.441222 | 39.0362 | ETL.1330 | 40655208 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-11 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119030178 | Mar | T3 WEST POINT-VLY SPRGS 2/31 RPL POLE - | 31502979 | WEST POINT-VALLEY SPRINGS | 002/031 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-04-01 | 2020-10-01 |  |  | 2021-03-27 | 2021-03-23 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.589974 | 38.421 | ETL.8350 | 40825786 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119030244 | Q2 | T2 DI 10245 OLEUM-G #1 10/68 RPL INSS |  | OLEUM-G #1 | 010/068 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-14 | 2021-05-13 |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.288972 | 37.9192 | ETL.3150 | 40857750 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-06-15 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119030320 | Q3 | T2 DI 10245 OLEUM-G #1 10/68 RMV VEG |  | OLEUM-G #1 | 010/068 | HNA | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-12 | 2022-05-12 |  |  | 2021-08-15 | 2021-08-01 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.288972 | 37.9192 | ETL.3150 | 40857750 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119030323 | Q2 | T2 DI 10245 OLEUM-G #2 010/066 RPR SPLS | 44621444 | OLEUM-G #2 | 010/066 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2021-05-12 | 2021-05-15 | 2021-05-15 | 2021-05-15 | 2021-05-15 |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.284407 | 37.92 | ETL.3160 | 44377341 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-15 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119030324 | Q2 | DI SOBRANTE-GRLY-CLRMNT #2 3/27 RPR STRT |  | SOBRANTE-GRIZLY-CLARMNT #2+ | 003/027 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-12 | 2021-05-10 |  |  | 2021-05-08 | 2021-05-03 | [5 empty] | Central | WSIP | [6 empty] | '-122.178209 | 37.8681 | ETL.3750 | 40659418 | Structure-Tower | Anti-Climbing Guard | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-26 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119030327 | Q2 | DI SOBRANTE-GRLY-CLRMNT #2 3/27 RPR FOND |  | SOBRANTE-GRIZLY-CLARMNT #2+ | 003/027 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2021-05-12 |  |  | 2021-05-08 | 2021-05-03 | [5 empty] | Central | WSIP | [6 empty] | '-122.178209 | 37.8681 | ETL.3750 | 40659418 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-26 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119030365 | Q2 | T2 LOWER LKE-HMSTAKE 10/9 REFRAME STRS |  | LOWER LAKE-HOMESTAKE TAP | 010/009 |  | E | 2020_(2) High fire spread TD |  | 2020-05-14 | 2021-05-14 |  |  | 2021-05-28 | 2021-05-24 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-122.457499 | 38.8846 | ETL.1481 | 44917331 | Crossarm-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade |  | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119030458 | Q2 | T3 EAGLE ROCK-REDBUD :004/023 RPL INSS | 31506377 | EAGLE ROCK-REDBUD | :004/023 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2020-11-12 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.1480 | 40739312 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119030586 | Q2 | T2 DI FORT ROSS-GUALALA 050/006 RPR GYWW |  | GUALALA-MONTE RIO | 050/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-07 | 2021-05-07 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.414692 | 38.7259 | ETL.6980 | 40821495 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119031184 | Q2 | T2 DI ELK-GUALALA 65/0 RPL POLE | 31504604 | ELK-GUALALA | 065/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2021-05-06 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.531802 | 38.8014 | ETL.8410 | 40605939 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119033840 | Not Scheduled | T3 EI MIDDLE FORK #1 1/019 RPR GYWW | 44339029 | MIDDLE FORK #1 | 001/019 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2020-11-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.600028 | 39.0092 | ETL.8405 | 40598765 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119033944 | Not Scheduled | T3 EI MIDDLE FORK #1 7/105 BOND GUY | 44339029 | MIDDLE FORK #1 | 007/105 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2020-11-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.711017 | 39.0029 | ETL.8405 | 40810143 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119033961 | Q2 | DI WST PNT-VLY SPRG 4/54C RPL STRW | 31503556 | WEST POINT-VALLEY SPRINGS | 004/054 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2021-05-12 |  |  | 2021-04-03 | 2021-03-29 | [5 empty] | Central | WSIP | [8 empty] | ETL.8350 | 44405860 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119033980 | Not Scheduled | T3 EI MIDDLE FORK #1 7/105 INST DAMPER | 44339029 | MIDDLE FORK #1 | 007/105 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2020-11-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.711017 | 39.0029 | ETL.8405 | 40810143 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119034175 | Q2 | DI WST PNT-VLY SPRG 4/54L RPL POLE | 31503556 | WEST POINT-VALLEY SPRINGS | 004/054 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2021-05-12 |  |  | 2021-04-03 | 2021-03-29 | [5 empty] | Central | WSIP | [8 empty] | ETL.8350 | 44405861 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119034245 | Q2 | DI WST PNT-VLY SPRG 4/54R RPL POLE | 31503556 | WEST POINT-VALLEY SPRINGS | 004/054 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2021-05-12 |  |  | 2021-04-03 | 2021-03-29 | [5 empty] | Central | WSIP | [8 empty] | ETL.8350 | 44405862 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119035354 | Not Scheduled | T2 DI STNSLS-MLNS-MNTC 22/137 BENT STL |  | STANISLAUS-MELONES SS-MANTECA #1+ | 022/137 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-13 | 2021-05-13 | [7 empty] | TR2 | <90D | Central | WSIP | [6 empty] | '-120.688977 | 37.9524 | ETL.3830 | 40803333 | Structure-Tower | Anti-Climbing Guard | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119035414 | Not Scheduled | T2 DI STNSLS-MLNS-MNTC 22/137 RPR FOND |  | STANISLAUS-MELONES SS-MANTECA #1+ | 022/137 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-13 | 2021-05-13 | [7 empty] | TR2 | <90D | Central | WSIP | [6 empty] | '-120.688977 | 37.9524 | ETL.3830 | 40803333 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119035416 | Not Scheduled | T2 DI STNSLS-MLNS-MNTC 22/137 INST BOLT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 022/137 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-13 | 2021-05-13 | [7 empty] | TR2 | <90D | Central | WSIP | [6 empty] | '-120.688977 | 37.9524 | ETL.3830 | 40803333 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119035575 | Q2 | T3 DI GYSRS#3-CLVRDL 8/94 RPR POLE | 44580896 | GEYSERS #3-CLOVERDALE | 008/094 | ICW | E | 2020_(1a) PSPS |  | 2020-05-11 | 2020-11-11 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.951033 | 38.7998 | ETL.1650 | 40659189 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119035578 | Q2 | T3 DI GYSRS#3-CLVRDL 8/94 BOND GUY | 44580896 | GEYSERS #3-CLOVERDALE | 008/094 | ICW | E | 2020_(1a) PSPS |  | 2020-05-11 | 2020-11-11 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.951033 | 38.7998 | ETL.1650 | 40659189 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119035719 | Not Scheduled | T3 DI GEYSERS#9-LAKVLLE 01/07 RPR INSS |  | GEYSERS #9-LAKEVILLE | 001/007 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-08 | 2020-11-08 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.76768 | 38.7909 | ETL.4780 | 40710885 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119036191 | Feb | T3NT DI MORAGA-CLRMNT #1 3/23 RPR FOND | 44631266 | MORAGA-CLAREMONT #1 | 003/023 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-06 | 2022-05-06 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.207804 | 37.852 | ETL.2700 | 40644184 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119036192 | Not Scheduled | T3NT DI MORAGA-CLAREMNT #1 3/23 PNT STRS | 44586161 | MORAGA-CLAREMONT #1 | 003/023 | ICS | F | 2020_(3) On high spread structure |  | 2020-05-06 | 2022-05-06 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.207804 | 37.852 | ETL.2700 | 40644184 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119036207 | Not Scheduled | T3 DI FULTON-HOPLAND :027/003 RPR POLE | 44579280 | FULTON-HOPLAND | :027/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2020-11-12 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.988001 | 38.8012 | ETL.6890 | 40664531 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119036216 | Not Scheduled | T3 DI FULTON-PUEBLO 18/86 RPL INSS | 31505500 | FULTON-PUEBLO | 018/086 | 92E | E | 2020_(2) High fire spread TD |  | 2020-05-12 | 2020-11-12 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.327374 | 38.5023 | ETL.1600 | 40831855 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-10-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119036237 | Not Scheduled | T3 FULTON-CALISTOGA_:003/000 REFRAME | 31505209 | FULTON-CALISTOGA | :003/000 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-05-13 | 2020-11-13 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.595056 | 38.6326 | ETL.6880 | 40912430 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119036275 | Mar | T2 DI CRTNA-MENDOCINO #1 57/281 RPR FOND |  | CORTINA-MENDOCINO #1 | 057/281 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-13 | 2022-05-13 |  |  | 2021-03-05 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.133708 | 39.2342 | ETL.1330 | 40584934 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119036276 | Mar | T2 DI CRTNA-MNDOCINO #1 57/281 INST HRDT |  | CORTINA-MENDOCINO #1 | 057/281 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-13 | 2021-05-13 |  |  | 2021-03-05 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.133708 | 39.2342 | ETL.1330 | 40584934 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119036337 | Q2 | T2 DI ELK-GUALALA 59/3 RPLC INSW | 31503233 | ELK-GUALALA | 059/003 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2021-05-15 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.590581 | 38.8685 | ETL.8410 | 40699290 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119036551 | Mar | T2 DI CLEAR LAKE-HOPLAND 01/03 RMV BUTT | 44610498 | CLEAR LAKE-HOPLAND | 001/003 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-14 | 2021-05-14 |  |  | 2021-03-26 | 2021-03-24 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.059435 | 38.9693 | ETL.6390 | 40667033 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119036773 | Q2 | T2 DI ELK-GUALALA 39/8 RPR GYWW | 44610591 | ELK-GUALALA | 039/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2021-05-15 | 2021-05-20 | 2021-05-22 | 2021-05-20 | 2021-05-20 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.698251 | 39.0922 | ETL.8410 | 40877405 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119036828 | Q3 | DI GATES-MUSTANGS SS #1 11/048 REPR FOND | 44326364 | SPARE T-LINE RECORD | 011/048 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-05-01 | 2022-05-01 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-119.944735 | 36.2192 | ETL.2604 | 40858298 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119036996 | Not Scheduled | T3 EI DRUM-SUMMIT #1 001/021 RPL STRW | 31508705 | DRUM-SUMMIT #1 | 001/021 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-05-15 | 2020-11-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.740703 | 39.2612 | ETL.1440 | 44765187 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119038110 | Not Scheduled | DI MUSTANG SW STA-GREGG 19/83 RMV DEBRIS | 44342033 | GATES-GREGG | 019/083 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-05-07 | 2021-05-07 | [8 empty] | WECC | South | WSIP | [6 empty] | '-119.879357 | 36.2955 | ETL.4700 | 40659466 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119038118 | Q2 | DI PARKWAY-MORAGA 021/119 RPR FOND |  | PARKWAY-MORAGA | 021/119 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2022-05-12 |  |  | 2021-04-17 | 2021-04-12 | [5 empty] | Central | WSIP | [6 empty] | '-122.180554 | 37.8657 | ETL.5930 | 40759114 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119038128 | Q2 | T3 DI PITTSBURG-SAN MATEO 22/90 RPR FOND |  | PITTSBURG-SAN MATEO | 022/090 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-11 | 2020-11-11 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.95457 | 37.7359 | ETL.5463 | 40764506 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-22 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119038695 | Q2 | T3 SBTE-GRZLY-CLRMNT #2 6/40 RPL ARMS | 44326313 | SOBRANTE-GRIZLY-CLARMNT #2+ | 006/040 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-18 | 2020-11-18 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.200555 | 37.8595 | ETL.3750 | 40804897 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | SVRPR | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119038776 | Not Scheduled | T3 MONTE RIO-FULTON 13/1C REPL POLE | 31501349 | MONTE RIO-FULTON | 013/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2020-10-24 | [8 empty] | LATE | North Coast | WSIP | [8 empty] | ETL.7630 | 44315963 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-11-05 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119038864 | Q2 | DI LAKEVILLE#1 10/6 GRD WSH INSW |  | LAKEVILLE #1 | 010/006 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2021-05-12 |  |  | 2021-06-01 | 2021-05-28 |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-122.527872 | 38.3826 | ETL.7360 | 40836118 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-27 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119039186 | Not Scheduled | T3 EI MIDDLE FORK #1 0/004 CTTR KEY | 44332282 | MIDDLE FORK #1 | 000/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-16 | 2020-11-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.597476 | 39.0218 | ETL.8405 | 40767429 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119039187 | Not Scheduled | T3 EI MIDDLE FORK #1 000/004 ARMR ROD | 44332282 | MIDDLE FORK #1 | 000/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-16 | 2020-11-16 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.597476 | 39.0218 | ETL.8405 | 40767429 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119039200 | Not Scheduled | T2 EI DIABLO-GATES #1 023/095 RPL INST | 31526479 | DIABLO-GATES #1 | 023/095 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-18 | 2021-05-18 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.7175886 | 35.5145 | ETL.5960 | 40792242 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119039479 | Not Scheduled | T2 EI DIABLO-GATES #1 023/096 RPL INST | 31526479 | DIABLO-GATES #1 | 023/096 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-18 | 2021-05-18 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.7151653 | 35.5175 | ETL.5960 | 40839529 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119039521 | Not Scheduled | EI T2NT DIABLO-GATES #1 023/096 RMV DEBR | 44298383 | DIABLO-GATES #1 | 023/096 | CHS | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-18 | 2022-05-18 |  |  |  | 2021-04-15 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.715153 | 35.5175 | ETL.5960 | 40812113 | Road | Encroachment | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 931 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119039645 | Q2 | DI EAGLE ROCK-REDBUD :12/73 RPR FOND |  | EAGLE ROCK-REDBUD | :012/073 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-05 | 2021-05-05 |  |  | 2021-04-16 | 2021-04-12 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.619932 | 38.9102 | ETL.1480 | 40659642 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119039807 | Q2 | T2 DI ELK-GUALALA 053/000 RPL INSS | 31528733 | ELK-GUALALA | 053/000 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2021-05-15 | 2021-05-22 | 2021-05-22 | 2021-05-22 | 2021-05-22 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.680323 | 38.9137 | ETL.8410 | 40616755 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119039817 | Q2 | T3 MISSRI FLT-GLD HLL #1 17/148 RPL INSS | 31504275 | MISSOURI FLAT-GOLD HILL #1 | 017/148 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2020-11-15 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8602221 | 38.6752 | ETL.2660 | 40898939 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119039867 | Q2 | T2 DI ELK-GUALALA 053/000 RPR FOND |  | ELK-GUALALA | 053/000 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2021-05-15 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.680323 | 38.9137 | ETL.8410 | 40616755 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119040036 | Not Scheduled | T2 EI DIABLO-GATES #1 022/091 RPL INSS | 31526479 | DIABLO-GATES #1 | 022/091 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-18 | 2021-05-18 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.7269204 | 35.503 | ETL.5960 | 40614760 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119040150 | Not Scheduled | T2 DI SN LS OBSP-SNT MRA 11/195 RPL GYWW |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 011/195 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-05-15 | 2021-05-15 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-120.530481 | 35.1434 | ETL.9100 | 44191360 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119040158 | Not Scheduled | T2 DI SN LS OBSP-SNT MRA 11/195 RPR SPLW |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 011/195 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-05-15 | 2021-05-15 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-120.530481 | 35.1434 | ETL.9100 | 44191360 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119040276 | Not Scheduled | T3 MONTE RIO-FORT ROSS 15/004 RPR GYWW |  | ETL.6979.POLE.WOOD | 015/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-18 | 2020-11-18 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.01231 | 38.4779 | ETL.6979 | 40750316 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119040460 | Not Scheduled | T3 FULTON-PUEBLO 038/197 INS INSS | 31505500 | FULTON-PUEBLO | 038/197 | 92E | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-18 | 2020-11-18 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.68717 | 38.4965 | ETL.1600 | 40818390 | Emergency | Fire | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 437 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119041041 | Mar | T2 DI EAGLE RCK-CORTINA 11/54 REPL INS | 31503642 | EAGLE ROCK-CORTINA | 011/054 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-14 | 2021-05-14 |  |  | 2021-03-24 | 2021-03-24 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.664351 | 38.8885 | ETL.1470 | 40796412 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119041215 | Q2 | T3NT DI PARKWAY-MORAGA 19/109 RPR FOND | 44298735 | PARKWAY-MORAGA | 019/109 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-05 | 2022-05-05 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.205925 | 37.8796 | ETL.5930 | 40762788 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119041217 | Not Scheduled | DI STNS-MLNS SWSTA-MN#1 19/121 RPLC HRDT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 019/121 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-13 | 2021-05-13 | [8 empty] | <90D | Central | WSIP | [6 empty] | '-120.657175 | 37.9761 | ETL.3830 | 41136914 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-23 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119041252 | Not Scheduled | T2 EI DIABLO-GATES #1 022/090 RPL INSS | 31526479 | DIABLO-GATES #1 | 022/090 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-18 | 2021-05-18 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.7298248 | 35.4994 | ETL.5960 | 40631779 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119041352 | Q2 | T2 DI FORT ROSS-GUALALA 039/012 RPL SPLW |  | GUALALA-MONTE RIO | 039/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2021-05-15 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.314846 | 38.6402 | ETL.6980 | 40656371 | Splice-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119041430 | Feb | DI BRIGHTON-DAVIS 23/238 RPR GWYS | 44332239 | BRIGHTON-DAVIS | 023/238 | ICS | B | 2020_(0) A and B Tags |  | 2020-05-18 | 2021-04-05 |  |  | 2021-02-20 | 2021-02-20 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.695352 | 38.5155 | ETL.1140 | 40862318 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | IC | Feb |  |  | 2021-01-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 119041518 | Not Scheduled | DI STNS-MLNS SWSTA-MN#1 19/121 RPR STRT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 019/121 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-13 | 2021-05-13 | [8 empty] | <90D | Central | WSIP | [6 empty] | '-120.657175 | 37.9761 | ETL.3830 | 41136914 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-23 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119041519 | Not Scheduled | DI STNS-MLNS SWSTA-MN#1 19/121 STRS RPNT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 019/121 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-13 | 2022-05-13 | [9 empty] | Central | WSIP | [6 empty] | '-120.657175 | 37.9761 | ETL.3830 | 41136914 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 22 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-23 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119043946 | Mar | T3 DI DRUM-RIO OSO #2 004/049 RPL INSS | 31503652 | DRUM-RIO OSO #2 | 004/049 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2021-05-31 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.834864 | 39.2256 | ETL.1430 | 40889166 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119044022 | Mar | T3 DI DRUM-RIO OSO #2 10/107 RPL INSS | 31503652 | DRUM-RIO OSO #2 | 010/107 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.934059 | 39.1694 | ETL.1430 | 40829297 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119044080 | Q2 | T3 DI SBRNT-GRZLY-CLRMT #1 1/18 RPR FOND |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 001/018 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2020-11-12 |  |  | 2021-05-31 | 2021-05-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.194661 | 37.8882 | ETL.3740 | 40644699 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119044733 | Mar | T3 DI SAN RAMON-MORAGA 6/30 RPLC INSS | 31504799 | SAN RAMON-MORAGA | 006/030 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-13 | 2020-11-13 |  |  | 2021-03-18 | 2021-03-18 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.0255 | 37.6852 | ETL.5660 | 40782564 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | GRP | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119044736 | Mar | T3 DI TIGER CREEK-ELECTRA 6/47 RPL HRDS |  | TIGER CREEK-ELECTRA | 006/047 | ICS | F | 2020_(2) High fire spread TD |  | 2020-05-11 | 2022-05-11 |  |  | 2021-03-09 | 2021-03-08 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.589632 | 38.4217 | ETL.5780 | 40819485 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 11 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119045503 | Mar | T3 DI DRUM-RIO OSO #2 008/083 RPR SPLS | 44332280 | DRUM-RIO OSO #2 | 008/083 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.880357 | 39.1909 | ETL.1430 | 40655211 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119045596 | Mar | T3NT DI MORAGA-SAN LNDRO #1 7/52 RPR FND |  | MORAGA-SAN LEANDRO #1 | 007/052 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-11 | 2022-05-11 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.114006 | 37.7494 | ETL.2770 | 40646049 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119045799 | Q2 | T3 DI SBRNT-GRZLY-CLRMT #1 4/40 RPL STEP |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 004/040 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-11 | 2021-05-31 |  |  | 2021-05-31 | 2021-05-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.195233 | 37.8618 | ETL.3740 | 40761864 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119045830 | Not Scheduled | T3 DI MONTE RIO-FULTON 14/5 RPL POLE | 31428882 | MONTE RIO-FULTON | 014/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2020-11-12 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.00761 | 38.4779 | ETL.7630 | 40750287 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-11-05 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119045862 | Not Scheduled | T3 DI FULTON-CALISTOGA 7/1 RPLC STRW | 31504258 | FULTON-CALISTOGA | 007/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-18 | 2020-11-18 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.519836 | 38.5774 | ETL.6880 | 40585443 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-02-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119045884 | Q2 | T2 DI BRDGVLL-CTTNWD 11/106 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 011/106 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-19 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.482862 | 40.389 | ETL.1110 | 44424030 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119045885 | Q2 | T2 DI BRDGVLL-CTTNWD 11/106 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 011/106 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-19 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.482862 | 40.389 | ETL.1110 | 44424031 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119045888 | Q2 | T2 DI BRDGVLL-CTTNWD 11/106 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 011/106 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-19 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.482862 | 40.389 | ETL.1110 | 44424032 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119046302 | Q2 | T2 DI PARKWAY-MORAGA 21/116 RMV HRDT |  | PARKWAY-MORAGA | 021/116 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2021-05-12 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.188459 | 37.8703 | ETL.5930 | 40597321 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119046303 | Not Scheduled | T2 DI PARKWAY-MORAGA 21/116 REPAINT | 44586170 | PARKWAY-MORAGA | 021/116 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-12 | 2022-05-12 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-122.188459 | 37.8703 | ETL.5930 | 40597321 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119046630 | Mar | T2 DI MRGA-SAN LEANDRO #1 8/58 RPR FOND |  | MORAGA-SAN LEANDRO #1 | 008/058 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2021-05-12 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.11931 | 37.7372 | ETL.2770 | 40857652 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119046631 | Q2 | T3 DI FULTON-CALISTOGA -17/4 BOND GUY |  | FULTON-CALISTOGA | '-017/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-12 | 2020-11-12 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.478148 | 38.4674 | ETL.6880 | 44140231 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119046750 | Feb | T3 DI ROUND MTN-CTWND #3 28/234 RPL INSS | 31529415 | ROUND MTN-COTTONWOOD #3 | 028/234 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2020-11-19 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.950635 | 40.7775 | ETL.5650 | 40785142 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-07-14 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119047101 | Mar | T2NT DI MRG-SN LNDR #1 8/57 RPR FOND |  | MORAGA-SAN LEANDRO #1 | 008/057 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2022-05-12 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.117419 | 37.7394 | ETL.2770 | 40804655 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119047321 | Mar | DI MORAGA-SAN LEANDRO #1 10/67 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 010/067 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2022-05-12 |  |  | 2021-03-13 | 2021-03-08 | [5 empty] | Central | WSIP | [6 empty] | '-122.136471 | 37.7212 | ETL.2790 | 40818439 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119047328 | Mar | DI MORAGA-SAN LEANDRO #3 9/65 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 009/065 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2022-05-12 |  |  | 2021-03-13 | 2021-03-08 | [5 empty] | Central | WSIP | [6 empty] | '-122.134982 | 37.7233 | ETL.2790 | 40745921 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119047357 | Mar | T3 DI DRUM-RIO OSO #2 5/59 RPLC INSS | 31503652 | DRUM-RIO OSO #2 | 005/059 | 93K | E | 2020_(1a) PSPS |  | 2020-05-19 | 2020-11-19 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.850964 | 39.2154 | ETL.1430 | 40894424 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119047571 | Mar | T2 DI FULTON-HOPLAND 013/003 RPL POLE | 31503986 | FULTON-HOPLAND | 013/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-04-28 | 2021-04-28 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.854065 | 38.6572 | ETL.6890 | 40648705 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119047693 | Not Scheduled | T3 DI ROUND MTN-CTWD #3 29/241 RPR FOND | 43932111 | ROUND MTN-COTTONWOOD #3 | 029/241 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2020-11-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.959149 | 40.7672 | ETL.5650 | 40588925 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119047990 | Q2 | T3 DI GEYSERS #12-FULTON 15/66 RPR FOND | 44631264 | GEYSERS #12-FULTON | 015/066 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-14 | 2020-11-14 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.752571 | 38.6312 | ETL.4750 | 40814644 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119048211 | Mar | T3 DI EAGLE ROCK-CORTINA 18/88 RPL INSS | 31505513 | EAGLE ROCK-CORTINA | 018/088 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2020-11-15 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.1470 | 40884304 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119049439 | Not Scheduled | T3 EI DIABLO-GATES #1 22/089 RPR ROAD | 44298383 | DIABLO-GATES #1 | 022/089 | CHS | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-20 | 2021-05-20 |  |  |  | 2021-05-20 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.732485 | 35.4961 | ETL.5960 | 40869355 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119049470 | Not Scheduled | T3 EI DIABLO-GATES #1 22/89 RPL INSS | 31526471 | DIABLO-GATES #1 | 022/089 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-20 | 2020-11-20 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.732485 | 35.4961 | ETL.5960 | 40869355 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119049540 | Mar | T3 DI DRUM-RIO OSO #2 8/84 RPR SPLS | 44332280 | DRUM-RIO OSO #2 | 008/084 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.881811 | 39.1903 | ETL.1430 | 40761902 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119049747 | Q2 | DI PIT #1-COTTONWOOD 11/90 RPL SPLS | 43879413 | PIT #1-COTTONWOOD | 011/090 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-20 | 2021-05-20 |  |  | 2021-05-31 | 2021-05-17 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.673215 | 40.8987 | ETL.5390 | 40607833 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119049832 | Q2 | T2 EI FORT ROSS-GUALALA 48/08 RPL POLE | 31492553 | GUALALA-MONTE RIO | 048/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2019-01-03 | 2020-01-03 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.387318 | 38.7183 | ETL.6980 | 40872364 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119049834 | Q2 | T2 EI FORT ROSS-GUALALA 56/02 RPL POLE | 31492553 | GUALALA-MONTE RIO | 056/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2019-01-03 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.507076 | 38.7502 | ETL.6980 | 40686563 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119051704 | Q4 | T3 DI MIDDLE FORK-GLD HILL 6/53 RPR SHLW | 44332286 | MIDDLE FORK-GOLD HILL | 006/053 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-20 | 2020-11-18 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.692485 | 39.0025 | ETL.5140 | 44552279 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119051964 | Feb | T2 EI MIDWAY-WHIRLWIND 052/213 RMV NEST | 44516056 | MIDWAY-WHIRLWIND | 052/213 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-05-21 | 2021-05-21 |  |  | 2021-02-11 | 2021-02-08 |  |  |  | TR2 | WECC | South | WSIP | [6 empty] | '-118.691465 | 35.0698 | ETL.6030 | 40648048 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119051965 | Feb | T2 EI MIDWAY-WHIRLWIND 052/214 RPLC INSS | 31514956 | MIDWAY-WHIRLWIND | 052/214 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-05-21 | 2021-05-21 |  |  | 2021-02-11 | 2021-02-08 |  |  |  | TR2 | WECC | South | WSIP | [6 empty] | '-118.6893721 | 35.0674 | ETL.6030 | 40794031 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-12-08 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119052816 | Not Scheduled | T3 EI DIABLO-GATES #1 21/88 REPL INSS | 31526471 | DIABLO-GATES #1 | 021/088 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-21 | 2020-11-21 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.7361866 | 35.4914 | ETL.5960 | 40899077 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119054538 | Q2 | T3 SNEATH LANE-HMB ?2/4 RPR INSS | 44621946 | SNEATH LANE-HALF MOON BAY | ?002/004 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-21 | 2020-11-21 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.494878 | 37.5682 | ETL.7212 | 44384390 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | MSB | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119054869 | Q2 | T2 DI BRDGVL-CTNWD 10/93 RPR OPGW | 43939216 | BRIDGEVILLE-COTTONWOOD | 010/093 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-19 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.456683 | 40.389 | ETL.1110 | 44423223 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119056348 | Not Scheduled | T2 DI PARKWAY-MORAGA 10/59 RPLC DAMS | 44245151 | PARKWAY-MORAGA | 010/059 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-21 | 2021-05-21 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-122.23148 | 37.9973 | ETL.5930 | 40763001 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | JMLT | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119057076 | Feb | T2 DI EAGLE ROCK-REDBUD :14/20 RPLC INSW | 31503989 | EAGLE ROCK-REDBUD | :014/020 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-05-21 | 2021-05-21 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.608891 | 38.9362 | ETL.1480 | 40629651 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119057301 | Q2 | T2 DI WEIMAR #1 0/17 RPLC HRDD | 44362372 | WEIMAR #1 | 000/017 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-19 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.977205 | 39.034 | ETL.7560 | 40923014 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119057307 | Q2 | T2 DI WEIMAR #1 0/17 REPULL GUY | 44332294 | WEIMAR #1 | 000/017 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-19 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.977205 | 39.034 | ETL.7560 | 40913169 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119059348 | Mar | T3 EI SBRNT-GRZZLY-CLRMNT #2 6/43 WSH IN | 44645178 | SOBRANTE-GRIZLY-CLARMNT #2+ | 006/043 | ICD | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2020-11-22 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.209237 | 37.851 | ETL.3750 | 40857800 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119059370 | Not Scheduled | T3 DRUM-GRASS VLLY-WMR B21/465 RPL POLE | 31504330 | DRUM-GRASS VALLEY-WEIMAR | B021/465 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2020-11-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.998654 | 39.1775 | ETL.6760 | 40913019 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119059471 | Q2 | T3 DI GEYSERS #12-FULTON 24/99 RPR FOND |  | GEYSERS #12-FULTON | 024/099 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-14 | 2020-11-14 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.753242 | 38.5199 | ETL.4750 | 40870878 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119059474 | Not Scheduled | DI STLS-MLN SW ST-MCA #1 25/160 RPR STRT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 025/160 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-11 | 2021-05-11 | [8 empty] | <90D | Central | WSIP | [6 empty] | '-120.748795 | 37.9294 | ETL.3830 | 40856466 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-23 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119059477 | Not Scheduled | DI STLS-MLN SW ST-MCA #1 25/162 RPR STRT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 025/162 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-13 | 2021-05-13 | [8 empty] | <90D | Central | WSIP | [6 empty] | '-120.753763 | 37.9279 | ETL.3830 | 40596056 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-23 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119059996 | Mar | T3 DI DRUM-RIO OSO #1 7/75 RPR FOND | 44339678 | DRUM-RIO OSO #1 | 007/075 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.870217 | 39.198 | ETL.1420 | 40756207 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119060141 | Q2 | T2 DI ELK-GUALALA 41/09 RPL INSW | 31506140 | ELK-GUALALA | 041/009 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-05-13 | 2021-05-13 |  |  | 2021-05-20 | 2021-05-20 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.685355 | 39.067 | ETL.8410 | 40900605 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119060225 | Mar | T3 DI EGL RCK-FLTN-SLVRDO 9/37 RPR FOND |  | EAGLE ROCK-FULTON-SILVERADO | 009/037 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-14 | 2020-11-14 |  |  | 2021-03-31 | 2021-03-29 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.741752 | 38.6162 | ETL.4392 | 41129339 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119060227 | Mar | T3 DI EGL RCK-FLTN-SLVRDO :0/1 RPR FOND |  | EAGLE ROCK-FULTON-SILVERADO | :000/001 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2020-11-15 |  |  | 2021-03-31 | 2021-03-29 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.761291 | 38.7405 | ETL.4392 | 41129397 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119060607 | Q2 | T2 DI EAGLE ROCK-CORTINA :14/2 REPL POLE | 31503965 | EAGLE ROCK-CORTINA | :014/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-21 | 2021-05-21 | 2021-04-27 | 2021-04-30 | 2021-04-30 | 2021-04-27 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.607624 | 38.9249 | ETL.1470 | 41176305 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119060678 | Not Scheduled | T3NT DI DRUM-SUMMIT #1 000/006 INST MRKW | 44345829 | DRUM-SUMMIT #1 | 000/006 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-05-19 | 2022-05-19 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.761918 | 39.2548 | ETL.1440 | 44338092 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119060852 | Not Scheduled | T3NT DI DRUM-RIO OSO #2 00/09 REGRADE | 44356575 | DRUM-RIO OSO #2 | 000/009 | ICQ | F | 2020_(1a) PSPS |  | 2020-05-19 | 2022-05-19 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.784973 | 39.2565 | ETL.1430 | 40866282 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119060905 | Q2 | T3 DI SBRNT-GRZLY-CLRMT #2 6/39 RPR FOND | 44326313 | SOBRANTE-GRIZLY-CLARMNT #2+ | 006/039 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-12 | 2020-11-12 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.199539 | 37.8609 | ETL.3750 | 40746118 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | SVRPR | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119061030 | Q2 | T3NT DI TGR CRK-VLY SPRNGS 5/46 RPR FOND |  | TIGER CREEK-VALLEY SPRINGS | 005/046 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-12 | 2022-05-12 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.589465 | 38.4216 | ETL.5790 | 40811207 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119061031 | Not Scheduled | DI DIVIDE-CABRILLO #1 011/136 RPR GYWW |  | DIVIDE-CABRILLO #1 | 011/136 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-21 | 2021-05-21 |  | 2021-01-05 | [7 empty] | South | WSIP | [8 empty] | ETL.1380 | 44283834 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-03 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119061032 | Q2 | T2NT DI SBRT-GRZLY-CLRMT#1 2/23 RPR FOND |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 002/023 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2022-05-12 |  |  | 2021-05-31 | 2021-05-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.186631 | 37.8798 | ETL.3740 | 40872983 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119061035 | Q2 | T3 DI TIGER CREEK-ELECTRA 5/46 RMV STEP |  | TIGER CREEK-ELECTRA | 005/046 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-12 | 2020-11-12 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.587925 | 38.423 | ETL.5780 | 40811161 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-18 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119061079 | Mar | T3 EI SBRNT-GRZZLY-CLRMNT #2 6/42 WSH IN | 44645177 | SOBRANTE-GRIZLY-CLARMNT #2+ | 006/042 | ICD | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2020-11-22 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.208075 | 37.852 | ETL.3750 | 40857842 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  |  | SVRPR | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119061232 | Mar | T3 DI DRUM-RIO OSO #2 004/053 RPL INSS | 31503652 | DRUM-RIO OSO #2 | 004/053 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2021-05-31 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.840426 | 39.2214 | ETL.1430 | 40690865 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119061233 | Mar | T3 DI DRUM-RIO OSO #2 006/070 RPL INSS | 31503652 | DRUM-RIO OSO #2 | 006/070 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.864024 | 39.2041 | ETL.1430 | 40633685 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119061712 | Q2 | T2 EI WEIMAR #1 000/017 RPLC POLE | 31506502 | WEIMAR #1 | 000/017 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-25 | 2021-05-25 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.977205 | 39.034 | ETL.7560 | 40913169 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119061768 | Q2 | T2 EI WEIMAR #1 001/022 RPLC POLE | 31506502 | WEIMAR #1 | 001/022 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-25 | 2021-05-25 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.973471 | 39.0313 | ETL.7560 | 40824441 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119061842 | Q2 | T2 EI WEIMAR #1 001/025 RPR STRW | 44362373 | WEIMAR #1 | 001/025 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-25 | 2021-05-25 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.97133 | 39.0304 | ETL.7560 | 40650014 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119061870 | Q2 | T2 EI WEIMAR #1 001/027 RPL INSS | 31506503 | WEIMAR #1 | 001/027 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-05-25 | 2021-05-25 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.9696774 | 39.0297 | ETL.7560 | 40610576 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119061871 | Q2 | T2 EI WEIMAR #1 001/027 INS DAMPER | 44362373 | WEIMAR #1 | 001/027 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-25 | 2021-05-25 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.969664 | 39.0297 | ETL.7560 | 40586055 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119062818 | Q2 | T3 DI IGNCIO-BOLINS #1 10/114 RPR CRSW | 31504329 | IGNACIO-BOLINAS #1 | 010/114 | 93E | E | 2020_(2) High fire spread TD |  | 2020-05-20 | 2020-11-20 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.662603 | 37.9709 | ETL.7140 | 40750704 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-11 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119063050 | Q2 | T3 DI IGNCIO-BOLINS #1 10/114 RMV DEBRIS | 44640733 | IGNACIO-BOLINAS #1 | 010/114 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-20 | 2022-05-20 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.662603 | 37.9709 | ETL.7140 | 40750704 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119063069 | Mar | T3 DI DRUM-RIO OSO #2 007/079 RPL INSS | 31503652 | DRUM-RIO OSO #2 | 007/079 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2020-11-19 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.1430 | 44308041 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119064030 | Q2 | T3 DI TIGER CRK-VLY SPRNGS 5/45 RPR FOND |  | TIGER CREEK-VALLEY SPRINGS | 005/045 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-12 | 2020-11-12 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.587791 | 38.4228 | ETL.5790 | 40805570 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119064040 | Not Scheduled | T3 MONTE RIO-FORT ROSS 20/0B REPL PL | 31437439 | ETL.6979.POLE.WOOD | 020/000B | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-26 | 2020-11-26 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.094753 | 38.4843 | ETL.6979 | 44225239 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119065773 | Q2 | DI GATES-PANOCHE #1 2/12 RPR FOND | 44341603 | GATES-PANOCHE #1 | 002/012 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-26 | 2021-05-26 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.146013 | 36.1682 | ETL.4720 | 40663918 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-05-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119066694 | Mar | T3 DI EGL RCK-FLTN-SLVRD :000/4 RPR FOND |  | EAGLE ROCK-FULTON-SILVERADO | :000/004 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2020-11-15 |  |  | 2021-03-31 | 2021-03-29 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.759729 | 38.7298 | ETL.4392 | 40750668 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119067461 | Mar | T2 DI PARKWAY-MORAGA 11/66 REPL INSS | 31503747 | PARKWAY-MORAGA | 011/066 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-26 | 2021-05-26 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.217859 | 37.9801 | ETL.5930 | 40611760 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119067641 | Q2 | T2 DI PARKWAY-MORAGA 11/67 RPR FOND |  | PARKWAY-MORAGA | 011/067 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-26 | 2022-05-26 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.216353 | 37.9782 | ETL.5930 | 40662572 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119067873 | Q3 | DI GATES-MUSTANG #1 6/30 RPR FOND | 44341601 | SPARE T-LINE RECORD | 006/030 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-26 | 2021-05-26 |  |  | 2021-08-01 | 2021-06-02 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-120.016122 | 36.1848 | ETL.2604 | 40582480 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-05-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119068463 | Mar | T3 DI EAGLE RCK-FLTN-SLVRD 1/9 RPR FOND | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 001/009 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-20 | 2020-11-20 |  |  | 2021-03-31 | 2021-03-29 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.802166 | 38.8199 | ETL.4392 | 40869826 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119068861 | Not Scheduled | T3 DI SANTA FE GHRML TAP 0/1 RPLC INSS | 31506603 | SANTA FE GEOTHERMAL TAP | 000/001 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-22 | 2020-11-22 | [7 empty] | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.4782 | 40609331 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119069021 | Q2 | T2 UKIAH-HOPLAND-CLVRDLE 13/12 RPR COND | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 013/127 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2021-05-27 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.101489 | 39.0073 | ETL.4050 | 40669327 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119069691 | Not Scheduled | DI STNSLS-MLNS MNTCA #1 26/169 RPR STRS |  | STANISLAUS-MELONES SS-MANTECA #1+ | 026/169 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-11 | 2021-05-11 | [5 empty] | Not TLN - Move to TLQ |  |  | <90D | Central | WSIP | [6 empty] | '-120.773529 | 37.922 | ETL.3830 | 40803334 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 22 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119069693 | Feb | DI STNSLS-MLNS MNTCA #1 26/169 RPL SPLS | 44566007 | STANISLAUS-MELONES SS-MANTECA #1+ | 026/169 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-11 | 2021-05-11 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | Central | WSIP | [6 empty] | '-120.773529 | 37.922 | ETL.3830 | 40803334 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 22 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119070232 | Not Scheduled | T3 DI MIDDLE FORK #1 3/54C RPLC HRDW | 44339029 | MIDDLE FORK #1 | 003/054C | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-11 | 2020-11-11 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.638812 | 38.9959 | ETL.8405 | 42569707 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119070251 | Not Scheduled | T3 DI DRUM-RIO OSO #1 007/076 INST STEP | 44339678 | DRUM-RIO OSO #1 | 007/076 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2020-11-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.871402 | 39.1966 | ETL.1420 | 40820316 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119070474 | Q2 | DI SBRNT-GRZLY-CLRMNT #2 3/30 RPR STRT |  | SOBRANTE-GRIZLY-CLARMNT #2+ | 003/030 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2021-05-12 |  |  | 2021-05-08 | 2021-05-03 | [5 empty] | Central | WSIP | [6 empty] | '-122.176264 | 37.8649 | ETL.3750 | 40608060 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 14 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-05 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119070840 | Feb | T2 VACA-SUISUN 9/71 RPR CRST | 44339850 | VACA-SUISUN | 009/071 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2021-05-27 |  |  | 2021-02-15 | 2021-02-15 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.043055 | 38.3221 | ETL.4070 | 40597218 | Crossarm-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119070846 | Feb | T2 VACA-SUISUN-JAMESON 9/71 RPL INSS | 31499779 | VACA-SUISUN-JAMESON | 009/071 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2021-05-27 |  |  | 2021-02-13 | 2021-02-11 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.0430679 | 38.3221 | ETL.4080 | 40623721 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119073187 | Before Feb | T3 DI GEYSERS #12-FULTN 009/040 RPR INSS | 44630990 | GEYSERS #12-FULTON | 009/040 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-26 | 2020-11-26 | 2021-01-25 | 2021-01-28 | 2021-01-28 | 2021-01-25 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.75988 | 38.7297 | ETL.4750 | 40637090 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119074322 | Not Scheduled | DI GATES-PANOCHE #1 0/3 RPR INSS | 44341662 | GATES-PANOCHE #1 | 000/003 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-05-26 | 2021-05-26 | [8 empty] | WECC | South | WSIP | [8 empty] | ETL.4720 | 44402020 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119074484 | Q2 | DI GATES-PANOCHE #1 0/3 RPR FOND | 44341603 | GATES-PANOCHE #1 | 000/003 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-26 | 2021-05-26 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.126384 | 36.1451 | ETL.4720 | 40651593 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119074800 | Q2 | DI GATES-PANOCHE #1 0/3 RPR STRT | 44341603 | GATES-PANOCHE #1 | 000/003 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-26 | 2021-05-26 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.126384 | 36.1451 | ETL.4720 | 40651593 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119075662 | Q2 | DI GATES-PANOCHE #1 1/6 RPR FOND | 44341603 | GATES-PANOCHE #1 | 001/006 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-26 | 2021-05-26 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.132941 | 36.1528 | ETL.4720 | 40814247 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119076057 | Not Scheduled | DI ATASCADERO-CAYUCOS 009/076 RPR GYWW | 44392213 | ATASCADERO-CAYUCOS | 009/076 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-22 | 2021-05-20 | [9 empty] | South | WSIP | [8 empty] | ETL.8480 | 44319783 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119076058 | Not Scheduled | DI ATASCADERO-CAYUCOS 009/076 RPR GYWW | 44392218 | ATASCADERO-CAYUCOS | 009/076 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-22 | 2021-05-20 | [9 empty] | South | WSIP | [8 empty] | ETL.8480 | 44319784 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119076059 | Not Scheduled | DI ATASCADERO-CAYUCOS 009/076 RPR GYWW | 44392284 | ATASCADERO-CAYUCOS | 009/076 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-22 | 2021-05-20 | [9 empty] | South | WSIP | [8 empty] | ETL.8480 | 44319785 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119076280 | Not Scheduled | DI ATASCADERO-CAYUCOS 009/076 RPL CRSW | 31504668 | ATASCADERO-CAYUCOS | 009/076 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-05-22 | 2021-05-22 | [9 empty] | South | WSIP | [8 empty] | ETL.8480 | 44319784 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119077871 | Not Scheduled | T3 DI EAGLE RCK-FLTN-SLVRD 5/26 RPL INSS | 31505662 | EAGLE ROCK-FULTON-SILVERADO | 005/026 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.79536 | 37.7692 | ETL.4392 | 40842372 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119077873 | Mar | T3 DI EAGLE RCK-FLTN-SLVRD 5/26 RPR FOND | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 005/026 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-03-31 | 2021-03-29 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.795407 | 38.7692 | ETL.4392 | 40814650 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119080148 | Mar | T3 DI DRUM-GRS VLY-WMR 0/7 RMV BUTT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 000/007 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-27 | 2022-05-27 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.761669 | 39.2563 | ETL.6760 | 44809295 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119080149 | Mar | T3 DI DRUM-GRS VLY-WMR 0/7 RPR SPLW | 44339676 | DRUM-GRASS VALLEY-WEIMAR | 000/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.761669 | 39.2563 | ETL.6760 | 44809295 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119080990 | Q2 | T3 WEST POINT-VALLEY SPRINGS 5/59 RPL PL | 31506822 | WEST POINT-VALLEY SPRINGS | 005/059 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-04-10 | 2021-04-05 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.624538 | 38.3963 | ETL.8350 | 40579954 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119081013 | Mar | T2 DI PARKWAY-MORAGA 011/064 RPL INSS | 31526488 | PARKWAY-MORAGA | 011/064 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2021-05-29 |  |  | 2021-03-16 | 2021-03-16 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.22211 | 37.9854 | ETL.5930 | 44768968 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 13 | EBMUD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-02-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119081112 | Mar | T3 WEST POINT-VALLEY SPRINGS 1/21 RPL PL | 31506820 | WEST POINT-VALLEY SPRINGS | 001/021 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-03-27 | 2021-03-23 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.576977 | 38.4253 | ETL.8350 | 40803750 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-06-19 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119081209 | Q3 | T3 DI DONNELLS-MI-WUK 4/3 RPLC INSW | 31504671 | DONNELLS-CURTIS | 004/003 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-26 | 2020-11-26 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.044861 | 38.1865 | ETL.1400 | 40670178 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119081253 | Mar | T3 DI DRUM-GRASS VLY-WMR 2/46 RPR SPLW | 44339676 | DRUM-GRASS VALLEY-WEIMAR | 002/046 | ICW | E | 2020_(1a) PSPS |  | 2020-05-28 | 2021-05-31 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.771911 | 39.2394 | ETL.6760 | 40693316 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119081265 | Q2 | T3 DI EGL RCK-FLTN-SILVRD 19/81 RPL HRDT | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 019/081 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-26 | 2020-11-26 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.62029 | 38.5149 | ETL.4392 | 41129383 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119081266 | Feb | T3 DI EGL RCK-FLTN-SLVRD 19/81 RPL INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 019/081 | 92E | E | 2020_(2) High fire spread TD |  | 2020-05-26 | 2020-11-26 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.62037 | 38.5148 | ETL.4392 | 41129275 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Feb |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119081290 | Not Scheduled | T3 DI MIDDLE FORK #1 1/21 RPR POLE | 44365338 | MIDDLE FORK #1 | 001/021 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.601286 | 39.0079 | ETL.8405 | 40664820 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119081294 | Mar | T3 DI DUM-GRS VLY-WMR 2/49 RPLC POLE | 31518244 | DRUM-GRASS VALLEY-WEIMAR | 002/049 | 70Y | E | 2020_(1a) PSPS |  | 2020-05-27 | 2021-05-31 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.773734 | 39.2377 | ETL.6760 | 40756128 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | 70 | Mar |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119081383 | Q2 | T3 DI FULTON-PUEBLO 036/183 RPR FOND | 44306536 | FULTON-PUEBLO | 036/183 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-05-07 | 2021-05-03 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.644933 | 38.4972 | ETL.1600 | 40645131 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119081477 | Mar | T3 DI WST PNT-VLY SPRNGS 1/26 REPL INSW | 31504741 | WEST POINT-VALLEY SPRINGS | 001/026 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-03-27 | 2021-03-23 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.584597 | 38.4229 | ETL.8350 | 40603542 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-19 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119081478 | Not Scheduled | DI MORRO BAY-DIABLO X7/033 RPLC INSS | 31507782 | MORRO BAY-DIABLO | X007/033 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-26 | 2021-05-24 | [9 empty] | South | WSIP | [6 empty] | '-120.801552 | 35.2982 | ETL.5260 | 40679556 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-17 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119081489 | Not Scheduled | T3NT DI FULTON-PUEBLO 031/152 RMV DEBRIS |  | FULTON-PUEBLO | 031/152 | ICS | F | 2020_(3) On high spread structure |  | 2020-05-27 | 2022-05-27 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.5503 | 38.4856 | ETL.1600 | 40656848 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119081572 | Mar | T3 DI DRUM-GRS VLY-WMR 1/25 RPR SPLW | 44339676 | DRUM-GRASS VALLEY-WEIMAR | 001/025 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.758432 | 39.2485 | ETL.6760 | 40693452 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119081774 | Mar | T3 DI DEER CREEK-DRUM 004/106 RPR STRW | 44339658 | DEER CREEK-DRUM | 004/106 | ICW | E | 2020_(1a) PSPS |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.797361 | 39.2564 | ETL.6690 | 40822856 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119081866 | Mar | T3NT DI DRM-GRS VLY-WMR 7/181 RMV PL BUT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 007/181 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-28 | 2022-05-28 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.84619 | 39.1931 | ETL.6760 | 40664750 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119082157 | Mar | T3 DI DRM GRS VLL WEI 006/150 RPR SPLW | 44345839 | DRUM-GRASS VALLEY-WEIMAR | 006/150 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.830137 | 39.2076 | ETL.6760 | 40767243 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119082160 | Not Scheduled | DI DONNELLS-MI-WUK 0/1 RPLC SPLS |  | DONNELLS-CURTIS | 000/001 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-26 | 2021-05-24 | [9 empty] | Central | WSIP | [6 empty] | '-120.034255 | 38.2458 | ETL.1400 | 44379625 | Splice-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 40 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-02 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119082167 | Q2 | T2 DI SN LS OBSPO-SNT MR 10/176 RPL POLE | 31506798 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 010/176 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-05-22 | 2021-05-22 |  |  | 2021-04-30 | 2021-04-30 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.527107 | 35.1577 | ETL.9100 | 44191865 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 5 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119082168 | Not Scheduled | T2 DI SLO-SNT MAR 10/176 RMV PL BUTT |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 010/176 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-05-22 | 2021-05-22 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.527107 | 35.1577 | ETL.9100 | 44191865 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 5 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-17 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119082250 | Mar | T3 DI DRM GRASS-VLL WEI 006/163 RPL SPLW | 44345839 | DRUM-GRASS VALLEY-WEIMAR | 006/163 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.837226 | 39.2012 | ETL.6760 | 40822654 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119082514 | Q2 | T2 DI FRT RSS-GLA-GLA 57/3 RPR GYWW |  | GUALALA-MONTE RIO | 057/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2021-05-15 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-07 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.515304 | 38.765 | ETL.6980 | 40661492 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119082735 | Q2 | T2 DI FRT RSS-GLALA-GLALA 41/6 RPR GYWW |  | GUALALA-MONTE RIO | 041/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2021-05-15 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.308692 | 38.6623 | ETL.6980 | 40821477 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119082765 | Mar | T3NT DI DRM-GRS VLY-WMR 8/209 RMV PL BUT | 44364845 | DRUM-GRASS VALLEY-WEIMAR | 008/209 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-28 | 2022-05-28 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.860133 | 39.1808 | ETL.6760 | 40824298 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119082766 | Mar | T3 DI DRM-GRSS VLLY-WMR 8/209 RPR INSW | 44345839 | DRUM-GRASS VALLEY-WEIMAR | 008/209 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2021-05-31 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.860138 | 39.1808 | ETL.6760 | 40853538 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119082769 | Mar | T3 DI DRM-GRSS VLLY-WEI 9/215 RPR GYWW | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 009/215 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.864528 | 39.1766 | ETL.6760 | 44178361 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119082809 | Mar | T3 DI MRGA-SN LNDRO #1 6/44 RPR FOND |  | MORAGA-SAN LEANDRO #1 | 006/044 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2020-11-15 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.117688 | 37.7663 | ETL.2770 | 40745881 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119082971 | Not Scheduled | T3 DI CRESTA-RIO OSO 19/156 RPR FOND |  | CRESTA-RIO OSO | 019/156 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.484984 | 39.6938 | ETL.4590 | 40910169 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119082974 | Mar | T3 DI DRM-GRS VLY-WMR 2/50 RPLS SPLW | 44345839 | DRUM-GRASS VALLEY-WEIMAR | 002/050 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2021-05-31 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.774035 | 39.2375 | ETL.6760 | 40853527 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083011 | Q2 | T2 DI ELK-GUALALA 53/6 RPR GROUND WIREW | 44610591 | ELK-GUALALA | 053/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2021-05-15 | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-19 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.674224 | 38.9098 | ETL.8410 | 40820744 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083075 | Mar | T2 DI CRTNA-MNDCN#1 47/229 RPR FOUND |  | CORTINA-MENDOCINO #1 | 047/229 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2021-05-15 |  |  | 2021-03-05 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.958405 | 39.1934 | ETL.1330 | 40870093 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083129 | Q2 | T2 DI ELK-GUALALA 59/2 COMPLETED | 31506142 | ELK-GUALALA | 059/002 | 93E | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2021-05-15 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.591298 | 38.869 | ETL.8410 | 40684541 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083161 | Feb | T3 DI KILARC-CEDAR CREEK 8/196 RPLS SPLW | 43939119 | KILARC-CEDAR CREEK | 008/196 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.984632 | 40.7361 | ETL.7290 | 40845369 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083174 | Q2 | T2 DI FRT RSS-GLALA-GLALA 49/0 RPR GYWW |  | GUALALA-MONTE RIO | 049/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2021-05-15 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.393641 | 38.72 | ETL.6980 | 40587389 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083182 | Q2 | T3 DI PTTSBRG-SAN MATEO 12/51 RPR FOUND | 44623139 | PITTSBURG-SAN MATEO | 012/051 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-18 | 2022-05-18 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.886554 | 37.864 | ETL.5463 | 40819688 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083188 | Q2 | T2 DI FRT RSS-GLALA-GLALA 48/13 PRP GYWW |  | GUALALA-MONTE RIO | 048/013 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2021-05-15 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.393053 | 38.7182 | ETL.6980 | 40648493 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083221 | Not Scheduled | T2 DI FULTON-PUEBLO 38/194 RPLC INSS | 31430878 | FULTON-PUEBLO | 038/194 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2021-05-27 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.675248 | 38.4967 | ETL.1600 | 40779344 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083222 | Not Scheduled | T2 DI EGL RCK-FLTN-SLVD 38/194 RPLC INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 038/194 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2021-05-27 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.67503 | 38.497 | ETL.4392 | 40779346 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083223 | Q2 | T2 DI FULTON-PUEBLO 38/194 RPR FOND |  | FULTON-PUEBLO | 038/194 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-27 | 2021-05-27 |  |  | 2021-05-07 | 2021-05-03 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.67506 | 38.497 | ETL.1600 | 40750539 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083250 | Mar | T3 DI DEER CREEK-DRUM 1/23 BOND HARDWARE | 44345900 | DEER CREEK-DRUM | 001/023 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.839196 | 39.2856 | ETL.6690 | 40590222 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083255 | Q2 | T3 DI IGNACIO-BOLINAS #1 004/04 RPR SPLW | 44640733 | IGNACIO-BOLINAS #1 | 004/044 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.598813 | 38.0483 | ETL.7140 | 40657316 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083257 | Mar | T3 DI DRM-GRSS VLLY-WEI 009/232 RPL SPLW | 44345839 | DRUM-GRASS VALLEY-WEIMAR | 009/232 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.874621 | 39.1666 | ETL.6760 | 40822662 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083311 | Mar | T3 DI DEER CREEK-DRUM 2/67 RMV POLE BUTT | 44345900 | DEER CREEK-DRUM | 002/067 | ICW | E | 2020_(1a) PSPS |  | 2020-05-29 | 2020-11-29 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.823692 | 39.2634 | ETL.6690 | 40597182 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119083472 | Feb | T3 DI KILARC-CEDAR CREEK 11/247 RPR SPLW | 43939119 | KILARC-CEDAR CREEK | 011/247 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.959539 | 40.7661 | ETL.7290 | 44175308 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083473 | Feb | T3 DI KILARC-CEDAR CRK 11/247 RMV DEBRIS | 43939119 | KILARC-CEDAR CREEK | 011/247 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2022-05-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.959539 | 40.7661 | ETL.7290 | 44175308 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083477 | Feb | T3 DI KILARC-CEDAR CRK 11/251 RPR POLE | 43939119 | KILARC-CEDAR CREEK | 011/251 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.95717 | 40.7689 | ETL.7290 | 40600840 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083478 | Feb | T3 DI KILARC-CEDAR CRK 11/251 RMV BUTT | 43939119 | KILARC-CEDAR CREEK | 011/251 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.95717 | 40.7689 | ETL.7290 | 40600840 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083479 | Feb | T3 DI KILARC-CEDAR CRK 11/251 RPR SPLW | 43939119 | KILARC-CEDAR CREEK | 011/251 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.95717 | 40.7689 | ETL.7290 | 40600840 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083602 | Mar | T3 DI DRM-GRSS VLY-WEI 11/256 REFRAME | 31504765 | DRUM-GRASS VALLEY-WEIMAR | 011/256 | 93E | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.892147 | 39.1537 | ETL.6760 | 40853610 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083603 | Not Scheduled | T3 DI DRM-GRSS VLY-WEI 11/256 RMV VEGN |  | DRUM-GRASS VALLEY-WEIMAR | 011/256 | HNA | E | 2020_(3) On high spread structure |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.89217 | 39.1538 | ETL.6760 | 40824368 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083648 | Not Scheduled | T3 DI RND MTN-CTTNWD #3 331/264 RPL HRWT | 43932111 | ROUND MTN-COTTONWOOD #3 | 031/264 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.980338 | 40.7418 | ETL.5650 | 40755441 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083652 | Feb | T3 DI RND MTN-CTTNWD #3 331/264 RPL INSS | 31504993 | ROUND MTN-COTTONWOOD #3 | 031/264 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.98013 | 40.7419 | ETL.5650 | 40785134 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-07-14 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083662 | Not Scheduled | T3 DI FULTON-PUEBLO 34/174 RPL INSS | 31505500 | FULTON-PUEBLO | 034/174 | 92E | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.613722 | 38.4972 | ETL.1600 | 40796382 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083664 | Not Scheduled | T3 DI EGL RCK-FLTN-SLVDO 34/174 RPL INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 034/174 | 92E | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 | [6 empty] | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.61378 | 38.4972 | ETL.4392 | 40796384 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083788 | Q2 | T2 DI FT RSS-GLA-GLA 58/5 RPR GYWW |  | GUALALA-MONTE RIO | 058/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2021-05-31 |  |  | 2021-05-31 |  |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.514383 | 38.7801 | ETL.6980 | 40750323 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083796 | Not Scheduled | T3 DI FRCH MDWS-MDDL FRK 12/220 RPR POLE | 44345881 | FRENCH MEADOWS-MIDDLE FORK | 012/220 | ICW | E | 2020_(1a) PSPS |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.59986 | 39.0093 | ETL.6870 | 40603361 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119083797 | Not Scheduled | T3NT DI FRH MDS-ML FRK 12/220 RMV PL BUT | 44365647 | FRENCH MEADOWS-MIDDLE FORK | 012/220 | ICW | F | 2020_(1a) PSPS |  | 2020-05-28 | 2022-05-28 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.59986 | 39.0093 | ETL.6870 | 40603361 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119083823 | Q2 | T2 DI FT RSS-GLA-GLA 41/000 RPR GYWW |  | GUALALA-MONTE RIO | 041/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2021-05-15 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.311665 | 38.6556 | ETL.6980 | 40587370 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119083825 | Q2 | T2 DI PHILO JCT-ELK-ELK 5/6 RPR STRW | 44610684 | PHILO JCT-ELK | 005/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2021-05-15 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.232137 | 39.0626 | ETL.7780 | 40826126 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084502 | Q3 | T3 DI DONNELLS-MI-WUK 5/5 RPR INSW | 44623205 | DONNELLS-CURTIS | 005/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.060762 | 38.1793 | ETL.1400 | 40794327 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084504 | Q3 | T3 DI DONNELLS-MI-WUK 5/5 RMV PLE BUTT | 44623206 | DONNELLS-CURTIS | 005/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-27 | 2022-05-27 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.060762 | 38.1793 | ETL.1400 | 40763958 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  | FERC | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084508 | Q2 | T3 DI TIGR CRK-ELCTRA 0/1 RPR FOND | 44467326 | TIGER CREEK-ELECTRA | 000/001 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.493042 | 38.4514 | ETL.5780 | 40594677 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 12 | BLM | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-26 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084516 | Q3 | T3 DI DONNELLS-MI-WUK 6/3 RPL INSW | 31506059 | DONNELLS-CURTIS | 006/003 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2020-11-22 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.077285 | 38.173 | ETL.1400 | 40670182 | Insulator-Wood | No Good/Out of Stdrd | Replace | APPR | APPR | Awaiting Supervisor Approval | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084518 | Q3 | T3 DI DONNELLS-MI-WUK 6/3 RMV DEBRIS | 44623208 | DONNELLS-CURTIS | 006/003 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-22 | 2022-05-22 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.077853 | 38.1729 | ETL.1400 | 40643189 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  | FERC | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084535 | Not Scheduled | DISTRIBUTION SLO-SM RPL STRW |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 008/157 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-05-22 | 2021-05-22 | [9 empty] | South | WSIP | [6 empty] | '-120.528655 | 35.1725 | ETL.9100 | 44191321 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 5 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-17 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119084544 | Q2 | T2 DI OLEUM G #1 5/34 BURIED STUB | 44621447 | OLEUM-G #1 | 005/034 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-22 | 2021-05-22 | 2021-05-13 | 2021-05-14 | 2021-05-14 | 2021-05-13 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.24541 | 37.9899 | ETL.3150 | 40761781 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084546 | Not Scheduled | T3 DI MIDDLEFORK #1 8/125 BOND GUY | 44365338 | MIDDLE FORK #1 | 008/125 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.736021 | 39.0036 | ETL.8405 | 40669382 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084547 | Not Scheduled | T3 DI MIDDLEFORK #1 8/125 RMV DEBRIS | 44365334 | MIDDLE FORK #1 | 008/125 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-28 | 2022-05-28 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.736021 | 39.0036 | ETL.8405 | 40669382 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084563 | Mar | T3 DI DRM-GRSS VLY-WMAR 3/89 RPL POLE | 31506387 | DRUM-GRASS VALLEY-WEIMAR | 003/089 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.798286 | 39.2251 | ETL.6760 | 40669964 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084577 | Mar | T3 DI DRM-GRSS VLY-WMAR 0/8 BOND GUY | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 000/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.760374 | 39.2554 | ETL.6760 | 40874723 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084610 | Feb | T3 DI KILARC-CEDAR CREEK 3/78 RMV STUB | 43939119 | KILARC-CEDAR CREEK | 003/078 | ICW | E | 2020_(3) On high spread structure |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.935372 | 40.6975 | ETL.7290 | 40876497 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084611 | Feb | T3 DI KILARC-CEDAR CREEK 3/78 RPR SPLW | 43939119 | KILARC-CEDAR CREEK | 003/078 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.935372 | 40.6975 | ETL.7290 | 40876497 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084614 | Mar | T3 DI GYSRS #3-CLOVERDALE 8/92 RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 008/092 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.948579 | 38.8009 | ETL.1650 | 40594505 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084648 | Feb | T2 DI DIABLO-MSA 19/86 RPL INSS | 31503711 | DIABLO-MESA | 019/086 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-26 | 2021-05-26 | 2021-02-08 | 2021-02-11 | 2021-02-11 | 2021-02-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.606856 | 35.1832 | ETL.4620 | 40838471 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-06-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084653 | Mar | T3 DI SRNTE-GZLY-CLRMT#2 A1/10 RPL INSS | 31511124 | SOBRANTE-GRIZLY-CLARMNT #2+ | A001/010 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2020-11-22 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.226721 | 37.8863 | ETL.3750 | 40622389 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | Tilden RP | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084656 | Q2 | T3NT DI SRNTE-GLY-CLT T#1 A1/10 RPR FOND | 44624393 | SOBRNTE-GRIZZLY-CLARMNT #1+ | A001/010 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-22 | 2022-05-22 |  |  | 2021-05-31 | 2021-05-24 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.226805 | 37.8862 | ETL.3740 | 40581836 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084734 | Not Scheduled | T3 DI DRM-GRSS VLY-WMAR B17/386 RPL STRW | 31506387 | DRUM-GRASS VALLEY-WEIMAR | B017/386 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.9653 | 39.1328 | ETL.6760 | 40814230 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084803 | Not Scheduled | T3 DI CRESTA-RIO OSO 18/149 RPR FOND |  | CRESTA-RIO OSO | 018/149 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.483116 | 39.7053 | ETL.4590 | 40910164 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084804 | Q2 | T3 DI CRESTA-RIO OSO 18/149 RPL INSS | 31500129 | CRESTA-RIO OSO | 018/149 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.504838 | 39.6623 | ETL.4590 | 40919903 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119084969 | Mar | T3 DI DEER CREEK-DRUM 0/1 RMV BUTT | 44345900 | DEER CREEK-DRUM | 000/001 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-28 | 2022-05-28 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.843824 | 39.2983 | ETL.6690 | 40590220 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119085060 | Mar | T3 DI DEER CREEK-DRUM 0/1 RPR INSW | 44345900 | DEER CREEK-DRUM | 000/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.843881 | 39.2982 | ETL.6690 | 40615660 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119085113 | Mar | T2 DI ELK-GUALALA 56/8 RPR GYWW | 44644113 | ELK-GUALALA | 056/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2021-05-15 |  |  | 2021-03-23 | 2021-01-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.625267 | 38.8934 | ETL.8410 | 40871843 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119085120 | Not Scheduled | T3 DI MIDDLEFORK #1 1/20 REMV BUTT | 44361892 | MIDDLE FORK #1 | 001/020 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-28 | 2022-05-28 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.600654 | 39.0086 | ETL.8405 | 40660027 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119085121 | Not Scheduled | T3 DI MIDDLEFORK #1 1/20 CANCEL | 44361892 | MIDDLE FORK #1 | 001/020 | ICW | F | 2020_(2) High fire spread TD |  | 2020-05-28 | 2022-05-28 | [6 empty] | CANCEL/CNCL | TR3 |  | North Valley | WSIP | [6 empty] | '-120.600654 | 39.0086 | ETL.8405 | 40660027 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119085129 | Feb | T3 DI DESABL-CENTERVI 3/37A RPR STRW | 44356201 | DESABLA-CENTERVILLE | 003/037A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.641054 | 39.8229 | ETL.6720 | 40700256 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119085250 | Q2 | T2 DI FORT ROSS-GUALALA 47/6 RPR GYWW |  | GUALALA-MONTE RIO | 047/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2021-05-15 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.368614 | 38.7191 | ETL.6980 | 40821493 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119085325 | Not Scheduled | T3 DI DIABLO-MESA 26/114 RPLC INSS | 31510098 | DIABLO-MESA | 026/114 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2020-11-15 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.520641 | 35.1138 | ETL.4620 | 40792007 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-01 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119085435 | Q2 | T3 DI SOBRANTE R #1 3/25 RPR FOND | 44624391 | SOBRANTE-R #1 | 003/025 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-18 | 2020-11-18 |  |  | 2021-05-15 | 2021-05-10 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.272951 | 37.9171 | ETL.3770 | 40746157 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | Tilden RP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119085451 | Not Scheduled | T3NT DI DRM-GSS VLY-WEI 4/92 RMV PL BUTT | 44371581 | DRUM-GRASS VALLEY-WEIMAR | 004/092 | GAR | F | 2020_(2) High fire spread TD |  | 2020-05-28 | 2022-05-28 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.799606 | 39.2233 | ETL.6760 | 40589534 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119085677 | Feb | T3 DI DESABLA-CNTRVLLE 003/040B RPR GYWW | 44356201 | DESABLA-CENTERVILLE | 003/040 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2021-05-31 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.64257 | 39.8187 | ETL.6720 | 42578833 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119086150 | Feb | T3NT DI DESABLA-CNTRVILLE 3/40B RMV BUTT |  | DESABLA-CENTERVILLE | 003/040 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-27 | 2022-05-27 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.64257 | 39.8187 | ETL.6720 | 42578833 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-31 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119086214 | Mar | T2NT DI CRTN-MENDCINO #1 52/256 RPR FOND |  | CORTINA-MENDOCINO #1 | 052/256 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2022-05-15 |  |  | 2021-03-05 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.060306 | 39.2042 | ETL.1330 | 40819332 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119086574 | Q3 | T3 DI DONNELLS-MI-WUK 005/007 RPL POLE | 31506668 | DONNELLS-CURTIS | 005/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.065563 | 38.1776 | ETL.1400 | 44922055 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 40 | USFS | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119086657 | Feb | T3 DI DESABLA-CENTERVILLE 3/40C RPR GYWW | 44356201 | DESABLA-CENTERVILLE | 003/040C | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.642608 | 39.8187 | ETL.6720 | 42578834 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119086716 | Feb | T3NT DI DESABLA-CNTERVLLE 3/40C RMV BUTT |  | DESABLA-CENTERVILLE | 003/040C | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-27 | 2022-05-27 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.642608 | 39.8187 | ETL.6720 | 42578834 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-31 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119086719 | Feb | T3 DI DESABLA-CNTERVLLE 3/40C RPR STRW | 44356201 | DESABLA-CENTERVILLE | 003/040C | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2021-05-31 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.642608 | 39.8187 | ETL.6720 | 42578834 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | IC | Feb |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119086864 | Q3 | T3 DI DONNELLS-MI-WUK 005/007 RPL POLE | 31506668 | DONNELLS-CURTIS | 005/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.065563 | 38.1776 | ETL.1400 | 44922056 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 40 | USFS | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119087047 | Not Scheduled | T3 DI ATASCADERO-CAYUCOS 3/34 RPL POLE | 31505562 | ATASCADERO-CAYUCOS | 003/034 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-18 | 2020-11-18 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.732339 | 35.4645 | ETL.8480 | 40820812 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-27 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119087084 | Q2 | T2 DI FORT ROSS-GUALALA 49/8 RPR GYWW |  | GUALALA-MONTE RIO | 049/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2021-05-15 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.400986 | 38.7214 | ETL.6980 | 40860968 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119087274 | Q2 | T2 DI FORT ROSS-GUALALA 31/9 RPR GYWW |  | GUALALA-MONTE RIO | 031/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2021-05-15 | 2021-06-15 | 2021-06-18 | 2021-06-17 | 2021-06-17 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.263887 | 38.5549 | ETL.6980 | 40876070 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119087548 | Mar | T3 DI KILARC-DESCHUTES 0/11 RMV DEBRIS | 43930440 | KILARC-DESCHUTES | 000/011 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2022-05-29 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.874123 | 40.6709 | ETL.7300 | 40676461 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119087572 | Feb | T3 DI DESABLA-CENTERVILLE 000/2 RPL SPLW | 44356201 | DESABLA-CENTERVILLE | 000/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.630873 | 39.8674 | ETL.6720 | 40659712 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119087603 | Feb | T3 DI DESABLA-CENTERVILLE 0/2 RMV BUTT | 44356201 | DESABLA-CENTERVILLE | 000/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-28 | 2022-05-28 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.630873 | 39.8674 | ETL.6720 | 40659712 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119087623 | Mar | T3 DI KILARC-DESCHUTES 0/11 REPL CRSW | 31504926 | KILARC-DESCHUTES | 000/011 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.874123 | 40.6709 | ETL.7300 | 40676461 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119087890 | Q2 | T2 DI KONOCTI-MIDDLETOWN 13/3 RPR GYWW | 44610651 | KONOCTI-MIDDLETOWN | 013/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-14 | 2021-05-14 | 2021-04-19 | 2021-04-23 | 2021-04-20 | 2021-04-20 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.591673 | 38.7654 | ETL.6380 | 40666996 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119087897 | Q2 | T2 DI KONOCTI-MIDDLETOWN 13/3 RPR STRW | 44610651 | KONOCTI-MIDDLETOWN | 013/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-14 | 2021-05-14 | 2021-04-19 | 2021-04-23 | 2021-04-20 | 2021-04-20 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.591673 | 38.7654 | ETL.6380 | 40666996 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119087930 | Q2 | T2 DI KONOCTI-MIDDLETOWN 13/3 RPLC HRDW | 44610651 | KONOCTI-MIDDLETOWN | 013/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-14 | 2021-05-14 | 2021-04-19 | 2021-04-23 | 2021-04-20 | 2021-04-20 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.591673 | 38.7654 | ETL.6380 | 40666996 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088059 | Feb | T3 DI DESABLA-CNTRVLL 4/57 RPR SPLW | 44356201 | DESABLA-CENTERVILLE | 004/057 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2021-05-31 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.650768 | 39.8002 | ETL.6720 | 44324212 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088152 | Not Scheduled | T3 DI FULTON-PUEBLO 027/129 RPL INSS | 31505500 | FULTON-PUEBLO | 027/129 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-05-12 | 2020-11-12 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.473851 | 38.4908 | ETL.1600 | 40884574 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088468 | Q2 | T3 DI SOBRANTE- ""G"" #1 3/21 RPR FOND | 44624390 | SOBRANTE-"G" #1 | 003/021 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-15 | 2022-05-15 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.265319 | 37.9153 | ETL.3720 | 40581007 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088469 | Not Scheduled | T3 DI TMBLR-SLO 45/255 RPR SPLS |  | TEMBLOR-SAN LUIS OBISPO | 045/255 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2020-11-15 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.461633 | 35.3653 | ETL.3960 | 40744735 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-27 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088482 | Q2 | T3 DI TMBLR-SLO 54/301 RPR FOND | 44346363 | TEMBLOR-SAN LUIS OBISPO | 054/301 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2020-11-15 |  |  | 2021-04-15 | 2021-04-01 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.58198 | 35.283 | ETL.3960 | 40585669 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088581 | Feb | T3 DI MORAGA-OAKLAND #1 3/22 RPL INSS | 31504785 | MORAGA-OAKLAND #1 | 003/022 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-18 | 2020-11-18 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.204736 | 37.8227 | ETL.2720 | 40727887 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-21 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088588 | Mar | T3 DI MRAGA-SAN LEANDRO #1 5/40 RMV STEP |  | MORAGA-SAN LEANDRO #1 | 005/040 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2020-11-15 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.124378 | 37.7785 | ETL.2770 | 40609137 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088660 | Not Scheduled | T3NT DI FULTON-CALSTGA 8/7 RMV PL BUTT | 44597303 | FULTON-CALISTOGA | :008/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-27 | 2022-05-27 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.604341 | 38.7085 | ETL.6880 | 40905734 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088667 | Not Scheduled | T3 DI DRUM-GRSS VLY-WMR B17/383 RPL POLE | 31506387 | DRUM-GRASS VALLEY-WEIMAR | B017/383 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.964024 | 39.1307 | ETL.6760 | 40757030 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088678 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 5/146 REPL POLE | 31507442 | COLGATE-ALLEGHANY | 005/146 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.093931 | 39.3363 | ETL.6470 | 40817333 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-06-12 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088712 | Q2 | T2 DI ELK-GLALA 54/009 INS GROUND WASH | 44610595 | ELK-GUALALA | 054/009 | ICD | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2021-05-15 | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-19 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.653609 | 38.9058 | ETL.8410 | 40894863 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088716 | Q2 | T3 DI SANTA FE GEOTHERMAL 000/3 RPR FOND |  | SANTA FE GEOTHERMAL TAP | 000/003 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2022-05-15 |  |  | 2021-06-04 | 2021-06-01 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.746969 | 38.7871 | ETL.4782 | 40659183 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088820 | Q2 | T3 DI PTTSBRG-SAN MATEO 12/50 RPR FOND | 44623139 | PITTSBURG-SAN MATEO | 012/050 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-19 | 2022-05-19 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.886021 | 37.8655 | ETL.5463 | 40760262 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088825 | Q2 | T2 DI ELK-GUALALA 054/008 GRD WAS INSU | 44610595 | ELK-GUALALA | 054/008 | ICD | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2021-05-15 | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-19 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.654891 | 38.9055 | ETL.8410 | 40897367 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088860 | Mar | T3 DI MRGA-SN LNDRO #1 6/49 RPR FOND |  | MORAGA-SAN LEANDRO #1 | 006/049 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2020-11-15 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.113987 | 37.7576 | ETL.2770 | 40861001 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088891 | Q2 | T2 DI ELK-GUALALA 056/010 RPL INSW | 31506140 | ELK-GUALALA | 056/010 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2021-05-15 | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-19 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.623769 | 38.8924 | ETL.8410 | 40641076 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088957 | Q2 | T3 DI IGNACIO-BOLINAS #1 2/32 RPR POLE | 44640733 | IGNACIO-BOLINAS #1 | 002/032 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-18 | 2020-11-18 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.583547 | 38.0691 | ETL.7140 | 40762994 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119088959 | Not Scheduled | DI DIVIDE-CABRILLO #2 006/076 RPR STRW |  | DIVIDE-CABRILLO #2 | 006/076 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-18 | 2021-05-18 | [9 empty] | South | WSIP | [8 empty] | ETL.1370 | 44283610 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119091224 | Q2 | T2NT DI PHILO JCT-ELK 010/000 INS MRKW |  | PHILO JCT-ELK | 010/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-18 | 2022-05-18 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.293795 | 39.0272 | ETL.7780 | 40614228 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119091225 | Q2 | T2 DI PHILO JCT-ELK 010/000 RPR STRW | 44610684 | PHILO JCT-ELK | 010/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2021-05-15 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.293795 | 39.0272 | ETL.7780 | 40614228 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119091884 | Q2 | T3 DI SOBRANTE-""G"" #1 2/18 RPR FOND | 44624390 | SOBRANTE-"G" #1 | 002/018 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-18 | 2022-05-18 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.258275 | 37.9134 | ETL.3720 | 40857867 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119091999 | Q2 | T3 DI MORRO BY-SLR STA #1 21/91 RPR FOND | 44346367 | MORRO BAY-SOLAR SW STA #1 | 021/091 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-18 | 2022-05-18 |  |  | 2021-04-15 | 2021-04-01 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.477886 | 35.3557 | ETL.5300 | 40587537 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119092245 | Not Scheduled | T3 DI TMBLR-SLO 51/287 RPLC INSS | 31514502 | TEMBLOR-SAN LUIS OBISPO | 051/287 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-18 | 2020-11-18 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.297619 | 35.3696 | ETL.3960 | 40833915 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-09 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119093764 | Not Scheduled | T3 DI FULTON-CALISTOGA :6/9 RPR SHLW | 44597303 | FULTON-CALISTOGA | :006/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.59049 | 38.6807 | ETL.6880 | 44922946 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119093826 | Not Scheduled | T3NT DI FULTON-CALISTOGA :6/9 RMV DEBRIS | 44597303 | FULTON-CALISTOGA | :006/009 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-19 | 2022-05-19 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.59049 | 38.6807 | ETL.6880 | 44922946 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119094029 | Q2 | DI GATES-PANOCHE #1 001/008 INST HRDT | 44361571 | GATES-PANOCHE #1 | 001/008 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-26 | 2021-05-26 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.137272 | 36.1579 | ETL.4720 | 40863626 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119094122 | Q2 | T2 DI FORT ROSS-GUALAL 56/11 INST DAMPRS |  | GUALALA-MONTE RIO | 056/011 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-15 | 2021-05-15 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-07 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.51306 | 38.7601 | ETL.6980 | 40584669 | Damper-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119094123 | Not Scheduled | T3 DI TMBLR-SN LS OBISPO 41/239 RPR SPLS |  | TEMBLOR-SAN LUIS OBISPO | 041/239 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2020-11-15 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.406668 | 35.3677 | ETL.3960 | 40856781 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-27 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119094125 | Not Scheduled | T3 DI TMBLR-SN LS OBISPO 41/239 RPL INSS | 31514502 | TEMBLOR-SAN LUIS OBISPO | 041/239 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2020-11-15 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.134823 | 35.3846 | ETL.3960 | 40877812 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119094280 | Not Scheduled | T3 DI FULTON-CALISTOGA 1/5 RPLC HRDW |  | FULTON-CALISTOGA | 001/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-18 | 2020-11-18 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.462797 | 38.5225 | ETL.6880 | 40751150 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119094300 | Not Scheduled | T3 DI PIT #1-COTTONWOOD 30/255 RPR FOND | 44051409 | PIT #1-COTTONWOOD | 030/255 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-19 | 2020-11-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.971856 | 40.7516 | ETL.5390 | 40744731 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119094332 | Not Scheduled | T3 DI PIT #1-COTTONWOOD 30/255 BENT STL | 43879413 | PIT #1-COTTONWOOD | 030/255 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2020-11-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.971856 | 40.7516 | ETL.5390 | 40744731 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119094684 | Feb | T3NT DI MORAGA-CASTRO VALL 6/27 RPR FOND |  | MORAGA-CASTRO VALLEY | 006/027 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2022-05-27 |  |  | 2021-02-24 | 2021-02-23 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.095526 | 37.7927 | ETL.5250 | 40813796 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119094752 | Mar | T2 EI KILARC-DESCHUTES 021/454 INST MRK | 43930440 | KILARC-DESCHUTES | 021/454 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-02 | 2022-06-02 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.222322 | 40.564 | ETL.7300 | 40617679 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119094782 | Mar | T2 EI KILARC-DESCHUTES 022/455 RPL ANCHO | 31510881 | KILARC-DESCHUTES | 022/455 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.222974 | 40.5638 | ETL.7300 | 40600426 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119094930 | Q2 | T3 DI VOLTA-DESCHUTES 2/57 RPR SPLW | 43939089 | VOLTA-DESCHUTES | 002/057 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.914102 | 40.4715 | ETL.8290 | 42607771 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119094932 | Q2 | T3 T2 DI VOLTA-DESCHUTES 2/56 REFRAME | 31504879 | VOLTA-DESCHUTES | 002/056 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.913358 | 40.4713 | ETL.8290 | 40601159 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119095027 | Q2 | T3 DI VOLTA-DESCHUTES 4/87 RPR SPLW | 43939089 | VOLTA-DESCHUTES | 004/087 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.939948 | 40.4779 | ETL.8290 | 40615924 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119095053 | Q2 | T3 DI VOLTA-DESCHUTES 7/149 RPR SPLW | 43939089 | VOLTA-DESCHUTES | 007/149 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.993258 | 40.4911 | ETL.8290 | 40600298 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119095055 | Q2 | T3 DI VOLTA-DESCHUTES 7/149 REPL POLE | 31504923 | VOLTA-DESCHUTES | 007/149 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.993258 | 40.4911 | ETL.8290 | 40600298 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119095225 | Q2 | T3 DI VOLTA-DESCHUTES 6/136 RPLC POLE | 31504923 | VOLTA-DESCHUTES | 006/136 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.982465 | 40.4886 | ETL.8290 | 40868514 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119095241 | Feb | T3 DI KILARC-CEDAR CREEK 3/68 REFRAME | 31505020 | KILARC-CEDAR CREEK | 003/068 | 93E | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.926527 | 40.6949 | ETL.7290 | 40617668 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-06-05 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119095246 | Feb | T3NT DI KILARC-CDR CRK 3/68 RMV PL BUTT | 43939119 | KILARC-CEDAR CREEK | 003/068 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-29 | 2022-05-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.926527 | 40.6949 | ETL.7290 | 40617668 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119095585 | Q2 | T2 DI ELK-GUALALA 47/9 RPL HRDW | 44610591 | ELK-GUALALA | 047/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2021-05-15 | 2021-05-20 | 2021-05-22 | 2021-05-20 | 2021-05-20 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.679365 | 38.9859 | ETL.8410 | 40894857 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119095636 | Not Scheduled | T2 EI SPAULDING-SUMMIT 12/428 RPL POLE | 31507079 | SPAULDING-SUMMIT | 012/428 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-06-01 | 2021-06-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.431857 | 39.325 | ETL.8060 | 40618259 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119095755 | Not Scheduled | T3 DI MIDDLE FORK #1 3/54A RPL HRDD | 44356683 | MIDDLE FORK #1 | 003/054A | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.638821 | 38.9959 | ETL.8405 | 40810139 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119095862 | Not Scheduled | T3 DI MIDDLE FORK #1 3/54B RPL HRDD | 44356683 | MIDDLE FORK #1 | 003/054B | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.638818 | 38.9959 | ETL.8405 | 42569706 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119095867 | Not Scheduled | T3 DI DRUM-RIO OSO#1 16/135 RPLC HRDT | 44345989 | DRUM-RIO OSO #1 | 016/135 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2020-11-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.01754 | 39.137 | ETL.1420 | 40765091 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096105 | Q2 | DI IGNACIO-BOLINAS#2 24/269R BOND GYWW | 44640732 | IGNACIO-BOLINAS #2 | 024/269 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-19 |  |  | 2021-04-23 | 2021-04-16 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.7180 | 44360930 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096109 | Q2 | DI IGNACIO-BOLINAS#2 24/269L BOND GYWW | 44640732 | IGNACIO-BOLINAS #2 | 024/269 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-19 |  |  | 2021-04-23 | 2021-04-16 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.7180 | 44360929 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096119 | Not Scheduled | T3 DI DRUM-GRAS VALLE-WEI 6/155 RMV STUB | 44361670 | DRUM-GRASS VALLEY-WEIMAR | 006/155 | GAR | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.833218 | 39.2048 | ETL.6760 | 40865385 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096197 | Q2 | T3 DI VOLTA-DESCHUTES 2/58 RPR SPLW | 43939089 | VOLTA-DESCHUTES | 002/058 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.914993 | 40.4717 | ETL.8290 | 40650371 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096215 | Q2 | T3 DI VOLTA-DESCHUTES 5/115 RPR SPLW | 43939089 | VOLTA-DESCHUTES | 005/115 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.96353 | 40.4838 | ETL.8290 | 40825144 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096301 | Q2 | T3 FULTON-CALISTOGA -019/000 RPL STRW | 31507073 | FULTON-CALISTOGA | '-019/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2020-12-02 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.476947 | 38.4896 | ETL.6880 | 40588871 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-02-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096489 | Mar | T3 DI DRUM-RIO OSO #2 5/59A RPL INSW | 31506135 | DRUM-RIO OSO #2 | 005/59A | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.851765 | 39.215 | ETL.1430 | 40578817 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096490 | Q2 | T2 DRUM-SPAULDING 7/183 RPL POLE | 31502001 | DRUM-SPAULDING | 007/183 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.667594 | 39.3077 | ETL.6770 | 40660095 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096512 | Q2 | T2 DRUM-SPAULDING 7/186 RPL POLE | 31502001 | DRUM-SPAULDING | 007/186 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.66539 | 39.3088 | ETL.6770 | 40751884 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096558 | Not Scheduled | T2 DI VLY SPRGS-MTL #1 10/10 RMV PL BUTT |  | VALLEY SPRINGS-MARTELL #1 | 010/010 | ICW | F | 2020_(1a) PSPS |  | 2020-06-01 | 2022-06-01 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.781872 | 38.3412 | ETL.8240 | 40599122 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-17 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119096571 | Q2 | T2 DRUM-SPAULDING 7/185 RPL POLE | 31502001 | DRUM-SPAULDING | 007/185 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.666126 | 39.3084 | ETL.6770 | 40751837 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096610 | Mar | T3 DI DRUM-RIO OSO #2 5/59A RPR STRW | 44356578 | DRUM-RIO OSO #2 | 005/059A | ICW | F | 2020_(2) High fire spread TD |  | 2020-05-19 | 2022-05-19 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.850634 | 39.216 | ETL.1430 | 40576825 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096615 | Q2 | T3 DI FULTON-CALISTOGA :5/2 RPR STRW | 44597303 | FULTON-CALISTOGA | :005/002 | ICW | E | 2020_(1a) PSPS |  | 2020-05-18 | 2020-11-18 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.591305 | 38.6621 | ETL.6880 | 40912459 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119096616 | Q2 | T3 DI FULTON-CALISTOGA :5/2 RMV PL BUTT | 44597303 | FULTON-CALISTOGA | :005/002 | ICW | F | 2020_(1a) PSPS |  | 2020-05-18 | 2022-05-18 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.591305 | 38.6621 | ETL.6880 | 40912459 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119096618 | Mar | T3 DI SAN RAMON-MORAGA 14/64 RPL INSS | 31504799 | SAN RAMON-MORAGA | 014/064 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2020-11-22 |  |  | 2021-03-18 | 2021-03-18 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.085837 | 37.7678 | ETL.5660 | 40786486 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096635 | Not Scheduled | T2 FULTON-HOPLAND 35/8 RPL POLE | 31478309 | FULTON-HOPLAND | 035/008 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.053247 | 38.9219 | ETL.6890 | 40877330 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096694 | Not Scheduled | T2 DI VLY SPRGS-MTL #1 10/10 RPL POLE | 31505055 | VALLEY SPRINGS-MARTELL #1 | 010/010 | 70Y | E | 2020_(1a) PSPS |  | 2020-06-02 | 2021-06-02 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.781872 | 38.3412 | ETL.8240 | 40599122 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-06-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119096714 | Q2 | T3 IGNACIO-BOLINAS #1 001/027 RPL PL | 31488037 | IGNACIO-BOLINAS #1 | 001/027 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-02 | 2020-12-02 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.57555 | 38.0737 | ETL.7140 | 40617116 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-11 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096822 | Mar | T3 DI MORAGA-CASTRO VALLE 7/34 RPL INSS | 31511128 | MORAGA-CASTRO VALLEY | 007/034 | 93K | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2020-11-22 |  |  | 2021-03-09 | 2021-03-09 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.085837 | 37.7678 | ETL.5250 | 40786488 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 | EBMUD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096828 | Mar | T3 DI DRUM-RIO OSO #2 1/13 RPR INSS | 44356576 | DRUM-RIO OSO #2 | 001/013 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.791625 | 39.2555 | ETL.1430 | 40684600 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096830 | Q2 | T2 CLEAR LAKE-KONOCTI 020/001 RPL PL | 31490846 | CLEAR LAKE-KONOCTI | 020/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.779208 | 38.9453 | ETL.6852 | 40584516 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096898 | Q2 | T3 DI VOLTA-DESCHUTES 0/6 RPLC POLE | 31504923 | VOLTA-DESCHUTES | 000/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.871087 | 40.4606 | ETL.8290 | 40759232 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096920 | Mar | T3NT DI GEYS#3-CLDLE 8/93 RMV PL BUTT | 44580896 | GEYSERS #3-CLOVERDALE | 008/093 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-27 | 2022-05-27 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.949468 | 38.8005 | ETL.1650 | 40657192 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096921 | Mar | T3 DI DRUM-RIO OSO #2 1/13 RPLC HRDT | 44356575 | DRUM-RIO OSO #2 | 001/013 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.791034 | 39.2563 | ETL.1430 | 40655126 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096922 | Q3 | DI TESLA-NEWARK #2 17/117 RMV HRDT | 44226389 | TESLA-NEWARK #2 | 017/117 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2021-05-19 |  |  | 2021-07-23 | 2021-07-19 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-121.845963 | 37.5934 | ETL.5354 | 41152663 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y-15 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096923 | Mar | T3 DI GEYSERS#3-CLOVERDALE 8/93 RPR SPLW | 44580896 | GEYSERS #3-CLOVERDALE | 008/093 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.949468 | 38.8005 | ETL.1650 | 40657192 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119096926 | Q2 | T3 DI VOLTA-DESCHUTES 2/52 RPR SPLW | 43939089 | VOLTA-DESCHUTES | 002/052 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2020-12-02 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.909583 | 40.4704 | ETL.8290 | 40816161 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097018 | Q2 | T2 DI TRINITY-MAPLE CREEK 9/3 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 009/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-02 | 2021-06-02 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.076219 | 40.7659 | ETL.8170 | 40906381 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097064 | Feb | T2 VACA-SUISUN 009/071 RPL INSS | 31507028 | VACA-SUISUN | 009/071 | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-02 | 2021-06-02 |  |  | 2021-02-15 | 2021-02-15 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.0430682 | 38.3221 | ETL.4070 | 40623720 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097074 | Not Scheduled | T3NT DI DRUM-RIO OSO #1 10/102 RMV FOUND |  | DRUM-RIO OSO #1 | 010/102 | ICQ | F | 2020_(3) On high spread structure |  | 2020-05-19 | 2022-05-19 | [7 empty] | TR3 |  | North Valley | WSIP | [8 empty] | ETL.1420 | 44337068 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097076 | Not Scheduled | T3 DI DRUM-RIO OSO #1 10/102 REPL XARM | 31505601 | DRUM-RIO OSO #1 | 010/102 | 93Z | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.1420 | 44337148 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097093 | Q2 | T2 DI TRINITY-MAPLE CREEK 9/3 RPR SPLW | 44273074 | TRINITY-MAPLE CREEK | 009/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-02 | 2021-06-02 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.076219 | 40.7659 | ETL.8170 | 40906381 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097154 | Not Scheduled | T3NT DI DRM-GRS VLY-WMR 8/193 RMV PL BUT | 44361669 | DRUM-GRASS VALLEY-WEIMAR | 008/193 | GAR | F | 2020_(1a) PSPS |  | 2020-05-28 | 2022-05-28 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.851925 | 39.1881 | ETL.6760 | 40611224 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119097155 | Q3 | DI TESLA-NEWARK #2 12/105B RPR FONDT | 44226389 | TESLA-NEWARK #2 | 015/105B | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-19 | 2022-05-19 |  |  | 2021-07-23 | 2021-07-19 | [5 empty] | Central | WSIP | [6 empty] | '-121.819481 | 37.6093 | ETL.5354 | 41152651 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y-15 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097162 | Q4 | T3 DI MDLE FORK-GOLD HILL 5/47 RPR GRWW | 44356684 | MIDDLE FORK-GOLD HILL | 005/047 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.678791 | 39.0021 | ETL.5140 | 44551683 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097167 | Mar | T3 DI DRUM-RIO OSO #2 9/98 RPR FOND | 44356575 | DRUM-RIO OSO #2 | 009/098 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-19 | 2022-05-19 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.915529 | 39.177 | ETL.1430 | 40871471 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097246 | Not Scheduled | DI ATASCADERO-CAYUCOS 0/3 RPR STRW |  | ATASCADERO-CAYUCOS | 000/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-18 | 2021-05-18 | [9 empty] | South | WSIP | [6 empty] | '-120.67346 | 35.4661 | ETL.8480 | 40669485 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097266 | Mar | T3 DI DRUM-RIO OSO#2 9/92 RPR FOND | 44356575 | DRUM-RIO OSO #2 | 009/092 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-19 | 2022-05-19 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.904248 | 39.1815 | ETL.1430 | 40672397 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097277 | Q2 | T3 DI SOBRANTE-""G"" #1 3/19 RPR FOND | 44624390 | SOBRANTE-"G" #1 | 003/019 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-18 | 2022-05-18 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.259485 | 37.9137 | ETL.3720 | 40857649 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097279 | Q4 | T3 DI MIDDLE FRK-GLD HL 9/80 RPLC INSW | 31506134 | MIDDLE FORK-GOLD HILL | 009/080 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.739895 | 38.9874 | ETL.5140 | 40636078 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097460 | Mar | T3NT DI DRUM-RIO OSO#2 6/65 RPR FOND | 44356575 | DRUM-RIO OSO #2 | 006/065 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-19 | 2022-05-19 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.858508 | 39.2109 | ETL.1430 | 40757182 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097463 | Mar | DI DRUM- RIO OSO#2 009/094 RPR FONDT | 44361674 | DRUM-RIO OSO #2 | 009/094 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-19 | 2022-05-19 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.907128 | 39.1803 | ETL.1430 | 40757351 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097486 | Q2 | T3 DI IGNACIO-BOLINAS #1 13/143 RPR INSW | 44640733 | IGNACIO-BOLINAS #1 | 013/143 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-20 | 2020-11-20 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.698253 | 37.9424 | ETL.7140 | 40778792 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097515 | Q2 | T3 DI MTF-GRVLY 16/112 RPR STRW | 44392287 | METCALF-GREEN VALLEY | 016/112 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-20 | 2020-11-20 | 2021-04-26 | 2021-04-26 | 2021-04-26 | 2021-04-26 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.662117 | 37.0351 | ETL.2540 | 44401453 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097568 | Not Scheduled | T2 DI PIT #1-CTNWD 54/489 RPR FOND | 44051409 | PIT #1-COTTONWOOD | 054/489 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-19 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.214369 | 40.46 | ETL.5390 | 40868155 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097570 | Feb | T3 DI DSBLA-CNTRVLLE 1/26A RMV PL BUTT |  | DESABLA-CENTERVILLE | 001/026A | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-19 | 2022-05-19 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.633102 | 39.8452 | ETL.6720 | 40809994 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-31 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097571 | Feb | T3 DI DSBLA-CNTRVLLE 1/26A RPR GYWW | 44356201 | DESABLA-CENTERVILLE | 001/026A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-31 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.633102 | 39.8452 | ETL.6720 | 40809994 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097573 | Mar | T3 DI DRUM-RIO OSO #2 1/10 RPR STRT | 44345992 | DRUM-RIO OSO #2 | 001/010 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.786353 | 39.2564 | ETL.1430 | 40597545 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097576 | Feb | T3 DI RND MTN CTTNWD #3 28/226 RPL INSS | 31504993 | ROUND MTN-COTTONWOOD #3 | 028/226 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2020-11-19 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.942401 | 40.7872 | ETL.5650 | 40813496 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-07-14 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097595 | Not Scheduled | DI PIT #1-COTTONWOOD 13/106 RPR STRT | 44051409 | PIT #1-COTTONWOOD | 013/106 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-20 | 2021-05-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.707815 | 40.8811 | ETL.5390 | 40817578 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097621 | Q2 | T2 DI BRDGVLL-CTTNWD 10/95 RPL HRDW | 43939216 | BRIDGEVILLE-COTTONWOOD | 010/095 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-19 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.460955 | 40.389 | ETL.1110 | 44423873 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097622 | Not Scheduled | DI PIT #1-COTTONWOOD 58/525 RPR STRT | 44051409 | PIT #1-COTTONWOOD | 058/525 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-19 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.250398 | 40.4163 | ETL.5390 | 40759495 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097628 | Q2 | T3 DI WEIMAR #1 11/163 RMV BUTT | 44362375 | WEIMAR #1 | 011/163 | ICW | E | 2020_(1a) PSPS |  | 2020-05-20 | 2020-11-20 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.805138 | 39.0121 | ETL.7560 | 40824475 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119097629 | Q2 | T3 DI WEIMAR #1 11/163 REFRAME | 31506098 | WEIMAR #1 | 011/163 | 93E | E | 2020_(1a) PSPS |  | 2020-05-20 | 2020-11-20 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.805138 | 39.0121 | ETL.7560 | 40824475 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119097848 | Q2 | T3 DI SBRNT-GRZLY-CLRMNT #1 A0/4 RPR FND | 44624393 | SOBRNTE-GRIZZLY-CLARMNT #1+ | A000/004 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-19 | 2022-05-19 |  |  | 2021-05-31 | 2021-05-24 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.213556 | 37.8989 | ETL.3740 | 40765711 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119097849 | Q2 | T3NT DI SBRNT-GRZLY-CLRMNT #1 A0/4 ATCG | 44624393 | SOBRNTE-GRIZZLY-CLARMNT #1+ | A000/004 | ICQ | F | 2020_(3) On high spread structure |  | 2020-05-19 | 2022-05-19 |  |  | 2021-05-31 | 2021-05-24 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.213556 | 37.8989 | ETL.3740 | 40765711 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 988 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119098458 | Not Scheduled | T2 DI COLGATE-SMRTVL #2 9/114 RPLC SPLW | 44345892 | COLGATE-SMARTVILLE #2 | 009/114 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.29803 | 39.2298 | ETL.6520 | 40644594 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119098581 | Q2 | T2 DI BRDGVLL-COTTONWD 30/253 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 030/253 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-19 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.836544 | 40.3641 | ETL.1110 | 44561190 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119098597 | Feb | T3 DI KILARC-CEDAR CREEK 5/131 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 005/131 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.975193 | 40.7093 | ETL.7290 | 44837767 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119098687 | Q4 | T3 DI DRUM-RIO OSO #2 8/86 RPR SPLICE | 44356576 | DRUM-RIO OSO #2 | 008/086 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-12-31 | 2021-04-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.884581 | 39.1892 | ETL.1430 | 40822812 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119098829 | Q2 | T3 DI PITTSBURG-SAN RAMON 13/52 RPR FOND | 44623420 | PITTSBURG-SAN RAMON | 013/052 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-18 | 2022-05-18 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.886824 | 37.864 | ETL.5490 | 40646929 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119099090 | Not Scheduled | T2 DI COLGATE-SMRTVL #2 9/105 RPLC SPLS | 44345893 | COLGATE-SMARTVILLE #2 | 009/105 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.295597 | 39.2355 | ETL.6520 | 40668767 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119099093 | Not Scheduled | T2 DI COLGATE-SMRTVL #2 9/105 RMV BUTT | 44345892 | COLGATE-SMARTVILLE #2 | 009/105 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2021-06-03 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.295597 | 39.2355 | ETL.6520 | 40668767 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119099372 | Not Scheduled | T2 DI COLGATE-SMRTVL #2 7/78 CANCEL | 44345892 | COLGATE-SMARTVILLE #2 | 007/078 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.284506 | 39.2633 | ETL.6520 | 40771603 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119099938 | Q2 | T2 DI BRDGVL-CTNWOOD 31/261 RPR FOND | 43706644 | BRIDGEVILLE-COTTONWOOD | 031/261 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2021-05-19 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.857568 | 40.3637 | ETL.1110 | 40657032 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119100178 | Not Scheduled | T2 DI COLGATE-SMRTVI #2 4/54 RPR SPLW | 44345892 | COLGATE-SMARTVILLE #2 | 004/054 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.256375 | 39.2898 | ETL.6520 | 44231831 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119100627 | Not Scheduled | T3 EAGL RCK-FLTN-SLVD 4/23 INST JMP INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 004/023 | 92E | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2020-12-03 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7980828 | 38.7769 | ETL.4392 | 40690781 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119100725 | Mar | DI GREEN VALLEY-LLAGAS 6/51 RPL CSRW | 31506197 | GREEN VALLEY-LLAGAS | 006/051 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-05-20 | 2021-05-20 | 2021-03-09 | 2021-03-11 | 2021-03-11 | 2021-03-09 | [5 empty] | South | WSIP | [6 empty] | '-121.713752 | 37.034 | ETL.1720 | 44401059 | Crossarm-Wood | No Good/Out of Stdrd | Replace | MAPP srdy | MAPP | Constructed and mapped | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Moss Landing |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-13 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119100763 | Not Scheduled | T3 DI POE-RIO OSO-RIO 19/134 RPL HRDT |  | POE-RIO OSO | 019/134 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2020-12-02 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.484173 | 39.701 | ETL.5540 | 40757242 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119100983 | Not Scheduled | T3 DI CRESTA-RIO OSO-TW 020/166 RPL HRDT |  | CRESTA-RIO OSO | 020/166 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2022-05-28 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.492615 | 39.6754 | ETL.4590 | 40906789 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119101064 | Q2 | T2 TRINITY-MAPLE CREEK 030/003 REFRAME | 31472099 | TRINITY-MAPLE CREEK | 030/003 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.463254 | 40.6926 | ETL.8170 | 40906460 | Crossarm-Wood | No Good/Out of Stdrd | Replace | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119101533 | Q2 | T2 DI WEIMAR #1 4/64 REPL SPLW | 44362373 | WEIMAR #1 | 004/064 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-20 | 2021-05-20 |  |  | 2021-04-08 | 2021-03-22 |  |  | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-120.925046 | 39.0204 | ETL.7560 | 40696105 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119101937 | Not Scheduled | T2 FULTON-HOPLAND 29/9 RPL POLE | 31478309 | FULTON-HOPLAND | 029/009 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.016792 | 38.8449 | ETL.6890 | 40868390 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119101974 | Mar | FULTON-HOPLAND 10/6 RPL POLE | 31478308 | FULTON-HOPLAND | 010/006 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.845103 | 38.6206 | ETL.6890 | 40827228 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119102039 | Not Scheduled | T2 FULTON-HOPLAND 30/7 RPL POLE | 31478309 | FULTON-HOPLAND | 030/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.02736 | 38.852 | ETL.6890 | 40825342 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119102114 | Mar | T3 DI DRUM-RIO OSO #2 1/15 RPR FOND | 44356575 | DRUM-RIO OSO #2 | 001/015 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.794213 | 39.2562 | ETL.1430 | 40765123 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119102208 | Not Scheduled | T2 COLGATE-SMARTVILLE #2 10/117 RPL POLE | 31485386 | COLGATE-SMARTVILLE #2 | 010/117 | 70Y | E | 2020_(1a) PSPS |  | 2020-06-03 | 2021-06-03 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.300744 | 39.2241 | ETL.6520 | 40618357 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119102540 | Q2 | T2 DI BRDGVL-COTTONWOOD 9/91 RPR STRW | 43939216 | BRIDGEVILLE-COTTONWOOD | 009/091 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-19 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.452629 | 40.3891 | ETL.1110 | 44424551 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119102710 | Not Scheduled | T3 DI DIABLO-MESA 26/112 RPLC INSS | 31510098 | DIABLO-MESA | 026/112 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-18 | 2020-11-18 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.525487 | 35.1183 | ETL.4620 | 40714102 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-01 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119102717 | Not Scheduled | T3 DI MORRO BAY-MESA 26/112 RPLC INSS | 31501671 | MORRO BAY-MESA | 026/112 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-18 | 2020-11-18 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.525487 | 35.1183 | ETL.5290 | 40714100 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-01 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119102783 | Q2 | T3NT DI FULTN-PUBLO-TWER 41/210 RPR FOND |  | FULTON-PUEBLO | 041/210 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2022-05-27 |  |  | 2021-05-07 | 2021-05-03 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.723757 | 38.4968 | ETL.1600 | 40587750 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119102914 | Feb | T3 DI RND MTN-CTNWOOD #3 33/280 RPL INSS | 31504993 | ROUND MTN-COTTONWOOD #3 | 033/280 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 |  |  | 2021-02-19 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.997653 | 40.721 | ETL.5650 | 40634534 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-07-14 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119102929 | Q2 | T3 DI WEIMAR #1 7/105 RPR GYWW | 44362375 | WEIMAR #1 | 007/105 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-20 | 2020-11-20 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.86999 | 39.02 | ETL.7560 | 40874873 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119102952 | Q2 | T3 DI VOLTA-DESCHUTES 1/36 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 001/036 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.896662 | 40.4672 | ETL.8290 | 40656909 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119102957 | Not Scheduled | T3 DI COLGATE-ALLEGHNY 9/264 RMV PL BUTT | 44345667 | COLGATE-ALLEGHANY | 009/264 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-29 | 2022-05-29 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.036797 | 39.3781 | ETL.6470 | 40818482 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103032 | Not Scheduled | T3 DI MIDDLE FORK #1 9/129 RPR GYWW | 44365338 | MIDDLE FORK #1 | 009/129 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.740752 | 39.0054 | ETL.8405 | 40653602 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103050 | Not Scheduled | T3 DI FRNCH MEADW-MDLE FORK 0/2 RPR IBWW | 44361677 | FRENCH MEADOWS-MIDDLE FORK | 000/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.407465 | 39.0777 | ETL.6870 | 40693741 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103070 | Q2 | T3 DI VOLTA-DESCHUTES 3/83 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 003/083 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.936385 | 40.477 | ETL.8290 | 40825124 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103080 | Not Scheduled | T3 DI CARIBOU-PALERMO :31/255 RPR INSS |  | CARIBOU-PALERMO | 031/255 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.464758 | 39.7615 | ETL.3190 | 40801850 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103113 | Mar | T3 DI DRM GRS VLY-WMR 2/67 RPR SHLW | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 002/067 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.785792 | 39.2326 | ETL.6760 | 40654108 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103115 | Mar | T3 DI DRM GRS VLY-WMR 2/67 RMV PL BUTT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 002/067 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-28 | 2022-05-28 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.785792 | 39.2326 | ETL.6760 | 40654108 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103144 | Not Scheduled | T2 DI COLGTE-SMARTVLE #2 3/43 RPL POLE | 31507078 | COLGATE-SMARTVILLE #2 | 003/043 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.244787 | 39.3032 | ETL.6520 | 40864694 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-22 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103160 | Q2 | T3 DI IGNACIO-BOLINAS #1 9/104B RMV STUB | 44640733 | IGNACIO-BOLINAS #1 | 009/104 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2020-11-29 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.657464 | 37.9899 | ETL.7140 | 41118222 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103162 | Feb | T3NT DI KLRC-CDR CRK 9/210 RMV DEBRIS | 43939119 | KILARC-CEDAR CREEK | 009/210 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2023-05-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.977905 | 40.7441 | ETL.7290 | 40868041 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | IC | Feb |  |  | 2021-02-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103181 | Q2 | T3 DI SOBRANTE-""""R"""" #1 3/021 RPR FOND | 44624391 | SOBRANTE-R #1 | 003/021 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-15 | 2022-05-15 |  |  | 2021-05-15 | 2021-05-10 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.263779 | 37.9147 | ETL.3770 | 40581011 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | Tilden RP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103267 | Q2 | T3NT DI VOLTA-DESCHUTES 2/64 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 002/064 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-01 | 2022-06-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.920258 | 40.473 | ETL.8290 | 40867824 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103290 | Q2 | T3 DI VOLTA-DESCHUTES 2/64 REFRAME CRSW | 31505200 | VOLTA-DESCHUTES | 002/064 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.920258 | 40.473 | ETL.8290 | 40867824 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103297 | Feb | T3 DI DSBLA-CNTRVLLE 0/12 RPR GYWW | 44356201 | DESABLA-CENTERVILLE | 000/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2020-12-01 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.629187 | 39.8642 | ETL.6720 | 40700298 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103357 | Q2 | T2 DI FT RS-GLA-GLA 32/0 GRND WASH INSW |  | GUALALA-MONTE RIO | 032/000 | ICD | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2021-05-15 | 2021-06-15 | 2021-06-18 | 2021-06-17 | 2021-06-17 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.2676 | 38.5568 | ETL.6980 | 40606887 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103389 | Q2 | T2 DI PHILO JCT-ELK-ELK 5/4 RPR STRW | 44610684 | PHILO JCT-ELK | 005/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-15 | 2021-05-15 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.228235 | 39.0644 | ETL.7780 | 40763009 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103436 | Mar | T3 DI MORAGA-SAN LENDRO #3 6/45 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 006/045 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-15 | 2022-05-15 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.115846 | 37.7634 | ETL.2790 | 40745916 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103754 | Q2 | T3 DI VOLTA-DESCHUTES 6/135 REFRAME | 31505200 | VOLTA-DESCHUTES | 006/135 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.98168 | 40.4883 | ETL.8290 | 40825136 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103759 | Not Scheduled | T2 DI CLGT-SMRTVL #2 7/74 RMV PL BUTT | 44345892 | COLGATE-SMARTVILLE #2 | 007/074 | ICW | E | 2020_(1a) PSPS |  | 2020-06-03 | 2021-06-03 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.283314 | 39.2653 | ETL.6520 | 40618345 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119103812 | Not Scheduled | DI GOLDTREE 001/018 RMV DEBRIS |  | GOLDTREE TAP | 001/018 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-18 | 2022-05-18 | [9 empty] | South | WSIP | [6 empty] | '-120.702442 | 35.3046 | ETL.2821 | 40657975 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103953 | Not Scheduled | T3 DI FULTON-PUEBLO 033/166 RPL INSS | 31505500 | FULTON-PUEBLO | 033/166 | 92E | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.590748 | 38.4943 | ETL.1600 | 40835394 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103972 | Mar | T2 DI KILARC-DESCHUTES 4/90 RPLC SPLW | 43930440 | KILARC-DESCHUTES | 004/090 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.918251 | 40.6274 | ETL.7300 | 40816213 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119103973 | Mar | T2 DI KILARC-DESCHUTES 9/196 RPLC POLE | 31505204 | KILARC-DESCHUTES | 009/196 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.997468 | 40.5865 | ETL.7300 | 40592171 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119104214 | Not Scheduled | T3NT DI MORAGA-CASTRO VALY 4/22 PNT STRS | 43744386 | MORAGA-CASTRO VALLEY | 004/022 | ICS | F | 2020_(3) On high spread structure |  | 2020-05-21 | 2022-05-21 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.106985 | 37.8086 | ETL.5250 | 40670657 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119104420 | Mar | T3 DI DRUM-RIO OSO #2 01/016 RPR SPLS | 44356576 | DRUM-RIO OSO #2 | 001/016 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.796389 | 39.2561 | ETL.1430 | 40820377 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119104428 | Q2 | T2 DI BRIDGVLLE-CTTNWD 10/99L RMV PL BUT | 43939216 | BRIDGEVILLE-COTTONWOOD | 010/099 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-19 | 2022-05-19 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.469683 | 40.389 | ETL.1110 | 44424496 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119104607 | Q2 | T3 DI KONOCTI-MDLTWN 28/3 RPR INSS | 44610651 | KONOCTI-MIDDLETOWN | 028/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-21 | 2020-11-21 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.644696 | 38.909 | ETL.6380 | 44433446 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119104731 | Q4 | T3NT DI DRUM-RIO OSO #2 8/89 RMV DEBRIS | 44345661 | DRUM-RIO OSO #2 | 008/089 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-19 | 2022-05-19 |  |  | 2021-12-31 | 2021-04-01 |  |  | Likely MAT error - delink to correct | TR3 |  | North Valley | WSIP | [8 empty] | ETL.1430 | 44304980 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119104767 | Not Scheduled | DI CAYUCOS-CAMBRIA 7/47 RPR HRDW |  | CAYUCOS-CAMBRIA | 007/047 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-21 | 2021-05-21 | [9 empty] | South | WSIP | [6 empty] | '-120.963397 | 35.5105 | ETL.8560 | 40752359 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119105264 | Not Scheduled | T3NT DI DRUM-SUMMIT#2 0/5L RMV DEBRIS | 44345830 | DRUM-SUMMIT #2 | 000/005 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-05-19 | 2022-05-19 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.761868 | 39.2549 | ETL.1450 | 44549915 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119105267 | Q2 | T2 DI WEIMAR#1 1/27 RMV PL BUTT | 44362374 | WEIMAR #1 | 001/027 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-20 | 2022-05-20 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.969664 | 39.0297 | ETL.7560 | 40586055 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119105302 | Not Scheduled | T2NT DI GARCIA TAP 1/1 INST MRKW |  | GARCIA TAP | 001/001 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-22 | 2022-05-22 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.578937 | 38.8813 | ETL.8411 | 40601539 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119105305 | Not Scheduled | T2 DI GARCIA TAP 1/1 RPR INSW | 44610601 | GARCIA TAP | 001/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2021-05-22 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.578985 | 38.8805 | ETL.8411 | 40628230 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119105307 | Not Scheduled | T2 DI GARCIA TAP 1/1 RPR SPLW | 44610601 | GARCIA TAP | 001/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2021-05-22 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.578937 | 38.8813 | ETL.8411 | 40601539 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119105433 | Q4 | T3 DI MIDDLE FRK-GLD HL 7/60R RPR STRW | 44361893 | MIDDLE FORK-GOLD HILL | 007/060 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-20 | 2020-11-20 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.711104 | 39.0031 | ETL.5140 | 44565762 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119105441 | Q2 | T3 DI PITTSBURG-SAN RAMON 12/51 RPR FOND | 44623420 | PITTSBURG-SAN RAMON | 012/051 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-21 | 2025-05-21 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.886302 | 37.8655 | ETL.5490 | 40581142 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | CCR | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119105772 | Q2 | T3 DI GREEN VALLEY-LLAGAS 3/28 SPLIT BLT | 44392293 | GREEN VALLEY-LLAGAS | 003/028 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-20 | 2020-11-20 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-04-14 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.729801 | 36.9938 | ETL.1720 | 44401072 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119105919 | Mar | T2 DI KILARC-DESCHUTES 021/452 RPL SPLW | 43930440 | KILARC-DESCHUTES | 021/452 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.220619 | 40.5642 | ETL.7300 | 40877870 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119105971 | Mar | T2 DI KILARC-DESCHUTES 4/95 RPL INSW | 31506150 | KILARC-DESCHUTES | 004/095 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.921461 | 40.6246 | ETL.7300 | 40735599 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119106183 | Mar | T2 DI KILARC-DESCHUTES 22/455 RMV BUTT | 43930440 | KILARC-DESCHUTES | 022/455 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.222974 | 40.5638 | ETL.7300 | 40600426 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119106522 | Mar | T2 HUMBOLDT-TRINITY 58/1 RPL INSW | 31509856 | HUMBOLDT-TRINITY | 058/001 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.139448 | 40.7656 | ETL.1820 | 44553876 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119106533 | Feb | T2 DI COLGATE-GRASS VLY 7/180 REFRAME | 31507018 | COLGATE-GRASS VALLEY | 007/180 | 93E | E | 2020_(1a) PSPS |  | 2020-06-03 | 2021-06-03 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.090593 | 39.2704 | ETL.6490 | 40760395 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119106534 | Mar | T2 DI KILARC-DESCHUTES 4/92 RPR SPLW | 43930440 | KILARC-DESCHUTES | 004/092 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.919549 | 40.6263 | ETL.7300 | 40867886 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119106537 | Not Scheduled | T2 DI CLGT-SMRTVL #2 9/104 CANCEL | 44345892 | COLGATE-SMARTVILLE #2 | 009/104 | ICW | E | 2020_(1a) PSPS |  | 2020-06-03 | 2021-06-03 | [6 empty] | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-121.295651 | 39.2364 | ETL.6520 | 40702105 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119106543 | Q2 | T2 DI TRNTY-MPL CRK 024/000 RPR SPLW | 44273074 | TRINITY-MAPLE CREEK | 024/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.335753 | 40.7057 | ETL.8170 | 40590531 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119106822 | Not Scheduled | T2 DI CLGT-SMRTVL #2 9/104 RPLC POLE | 31505202 | COLGATE-SMARTVILLE #2 | 009/104 | 70Y | E | 2020_(1a) PSPS |  | 2020-06-03 | 2021-06-03 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.295651 | 39.2364 | ETL.6520 | 40702105 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-22 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119106863 | Mar | T2 DI KILARC-DESCHUTES 9/200 RMV BUTT | 43930440 | KILARC-DESCHUTES | 009/200 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.000248 | 40.5856 | ETL.7300 | 40759124 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119106865 | Mar | T2 DI KILARC-DESCHUTES 9/200 RPR SPLW | 43930440 | KILARC-DESCHUTES | 009/200 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.000248 | 40.5856 | ETL.7300 | 40759124 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119107011 | Q2 | T2 DI SALINAS-LAURELES 14/298 RPLC POLE | 31505565 | SALINAS-LAURELES | 014/298 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | 2021-05-25 | 2021-05-28 | 2021-05-28 | 2021-05-21 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.746674 | 36.5268 | ETL.7930 | 40697439 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-31 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119107038 | Mar | T2 DI SALINAS-LAURLS 13/283 GRWASH INSU | 44640865 | SALINAS-LAURELES | 013/283 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.753169 | 36.5422 | ETL.7930 | 40630294 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119107141 | Q2 | T2 DI TRINITY-MAPLE CREEK 5/7 BOND GUY | 44273074 | TRINITY-MAPLE CREEK | 005/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 | 2020-09-08 | 2020-09-12 | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.031816 | 40.732 | ETL.8170 | 40906324 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119107311 | Q2 | T3 DI WEIMAR #1 5/80 RPR GYWS | 44362376 | WEIMAR #1 | 005/080 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-20 | 2020-11-20 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.899512 | 39.0191 | ETL.7560 | 40589969 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119107783 | Q2 | T3 DI SOBRANT-GRZZ-CLR #1 5/51 RPR FOND |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 005/051 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-11 | 2025-05-11 |  |  | 2021-05-31 | 2021-05-24 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.221722 | 37.8478 | ETL.3740 | 40746108 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 404 |  | Yes | No | M&C Tag | Yes | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119107833 | Q2 | T3 DI GRN VLY-LLAGAS 5/42L RMV BUTT | 44578798 | GREEN VALLEY-LLAGAS | 005/042 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-20 | 2022-05-20 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-04-14 | [5 empty] | South | WSIP | [6 empty] | '-121.721726 | 37.0221 | ETL.1720 | 44565746 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119107834 | Q2 | T3 DI GRN VLY-LLAGAS 5/42L RPR POLE | 44578798 | GREEN VALLEY-LLAGAS | 005/042 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-20 | 2020-11-20 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-04-14 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.721726 | 37.0221 | ETL.1720 | 44565746 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119107836 | Q2 | T3 DI GRN VLY-LLAGAS 5/42R RPR POLE | 44578798 | GREEN VALLEY-LLAGAS | 005/042 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-20 | 2020-11-20 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-04-14 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.721726 | 37.0221 | ETL.1720 | 44565816 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119107839 | Q2 | T3 DI GRN VLY-LLAGAS 5/42L RPR BOND | 44578798 | GREEN VALLEY-LLAGAS | 005/042 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-20 | 2020-11-20 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-04-14 |  |  |  |  | LATE | South | WSIP | [6 empty] | '-121.721726 | 37.0221 | ETL.1720 | 44565746 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119107984 | Q2 | T3 DI WEIMAR #1 012/170R RPL POLE | 31505365 | WEIMAR #1 | 012/170 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.784859 | 39.0146 | ETL.7560 | 44947129 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | In Review | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119107987 | Q2 | T3 DI WEIMAR #1 012/170L RPL POLE | 31505365 | WEIMAR #1 | 012/170 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.784859 | 39.0146 | ETL.7560 | 44947119 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | In Review | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119108001 | Q3 | T2 DI SN LS OBSP-SNT MAR 10/180 RMV VEG |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 010/180 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-05-22 | 2021-05-22 |  |  | 2021-08-15 | 2021-08-01 |  |  |  | TR2 | SCHD | South | WSIP | [6 empty] | '-120.527967 | 35.1547 | ETL.9100 | 44191884 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119108078 | Mar | T3 DI DRUM-RIO OSO #1 10/100 BENT MEMB | 44356574 | DRUM-RIO OSO #1 | 010/100 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-20 | 2020-11-20 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.919362 | 39.1757 | ETL.1420 | 40588543 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119108139 | Q2 | T3 DI PTSBURG-SAN MTO-TWR 11/43 REP FOND |  | PITTSBURG-SAN MATEO | 011/043 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-06 | 2020-11-06 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.876532 | 37.8891 | ETL.5463 | 40870770 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119108365 | Not Scheduled | T2 DI SN LIS OBSPO-CAYCS 15/137 RPR IBWW |  | SAN LUIS OBISPO-CAYUCOS | 015/137 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-05 | 2021-05-05 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-120.806262 | 35.3536 | ETL.9090 | 44565348 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-15 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119108420 | Not Scheduled | T2 DI SN LIS OBSPO-CAYCS 15/137 RPR IBWW |  | SAN LUIS OBISPO-CAYUCOS | 015/137 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-05 | 2021-05-05 | [7 empty] | TR2 | <90D | South | WSIP | [6 empty] | '-120.806262 | 35.3536 | ETL.9090 | 44565513 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-15 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119108635 | Feb | T3 DI KLRC-CEDAR CREEK 4/109 RPL STRW | 31506712 | KILARC-CEDAR CREEK | 004/109 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.957883 | 40.7042 | ETL.7290 | 42615554 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-06-05 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119108730 | Mar | T3 DI DRUM-GRSS VALY-WEIMR 2/65 RPR STRW | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 002/065 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2021-05-31 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.784317 | 39.2331 | ETL.6760 | 40589537 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | IC | Mar |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119108840 | Mar | T3 DI GEYSRS #3-CLVRDLE 007/081 RPL INSW | 31506240 | GEYSERS #3-CLOVERDALE | 007/081 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.934694 | 38.8063 | ETL.1650 | 40700670 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119108843 | Mar | T3 DI GEYSRS #3-CLVRDLE 007/081 RPL ANCW | 31506241 | GEYSERS #3-CLOVERDALE | 007/081 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.934694 | 38.8063 | ETL.1650 | 40700670 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119108847 | Q4 | T3 DI MIDDL FRK-GLD HL 6/56L RPLC HRDD | 44356684 | MIDDLE FORK-GOLD HILL | 006/056 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.701453 | 39.0028 | ETL.5140 | 44552539 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119108848 | Q2 | T3NT DI MNDOCINO-WILLITS 9/4A RPL POLE | 31514050 | MENDOCINO-WILLITS | 009/004A | 70Y | F | 2020_(2) High fire spread TD |  | 2020-05-21 | 2022-05-21 | 2021-04-28 | 2021-04-30 | 2021-04-28 | 2021-04-28 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.303156 | 39.3367 | ETL.7540 | 40577241 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119108849 | Q4 | T3 DI MIDDL FRK-GLD HL 6/56R RPLC HRDD | 44356684 | MIDDLE FORK-GOLD HILL | 006/056 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.701453 | 39.0028 | ETL.5140 | 44552407 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119108917 | Q2 | T3 DI EAGLE ROCK-REDBUD :8/46 RPR FOND | 44637023 | EAGLE ROCK-REDBUD | :008/046 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-21 | 2022-05-21 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.691637 | 38.8861 | ETL.1480 | 40809073 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119108991 | Q2 | T2 DI ELK-GUALALA 049/001 RPR GYWW | 44610591 | ELK-GUALALA | 049/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-21 | 2021-05-21 | 2021-05-20 | 2021-05-22 | 2021-05-20 | 2021-05-20 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.680698 | 38.9688 | ETL.8410 | 40601575 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119109025 | Feb | T2 DI CLGT-GRSS VLLY 10/246 RPR SPLW | 44371196 | COLGATE-GRASS VALLEY | 010/246 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.079202 | 39.2296 | ETL.6490 | 40760648 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119109251 | Q2 | T2 DI FORT ROSS-GUALALA 49/4 RPR GYWW |  | GUALALA-MONTE RIO | 049/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-21 | 2021-05-21 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.396437 | 38.7223 | ETL.6980 | 40770597 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119109259 | Q2 | T2 DI ELK-GUALALA 063/005 RPR STRW | 44610591 | ELK-GUALALA | 063/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-21 | 2021-05-21 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.549584 | 38.8193 | ETL.8410 | 40762845 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119109292 | Not Scheduled | T3 DI FULTON-CALISTOGA :006/000 BOND GUY | 44597303 | FULTON-CALISTOGA | :006/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-18 | 2020-11-18 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.586577 | 38.6712 | ETL.6880 | 40912470 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119109354 | Not Scheduled | T3 DI MDL FRK-GLD HL 4/41R CANCEL | 44361893 | MIDDLE FORK-GOLD HILL | 004/041 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-20 | 2020-11-20 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.65868 | 38.9995 | ETL.5140 | 44552450 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119109371 | Mar | T3NT DI MORAGA-OAKLND #3 0/1 RPR FOND | 44623421 | MORAGA-OAKLAND #3 | 000/001 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-22 | 2022-05-22 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.16193 | 37.8471 | ETL.2740 | 40580802 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119109376 | Q2 | DI GATES-PANOCHE #1 1/9 INSTALL HRDT | 44361571 | GATES-PANOCHE #1 | 001/009 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-26 | 2021-05-26 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.139353 | 36.1603 | ETL.4720 | 40863280 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119109465 | Not Scheduled | T2 DI VLLY SPRNGS-MRTEL #1 8/5 RPR GYWW |  | VALLEY SPRINGS-MARTELL #1 | 008/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2021-06-01 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.765147 | 38.3082 | ETL.8240 | 40753638 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-18 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119109512 | Not Scheduled | T2 DI CARIBOU-PALERMO 8/69 INST STEPS |  | CARIBOU-PALERMO | 008/069 | ICQ | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2022-06-01 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.53135 | 39.5695 | ETL.3190 | 40867354 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119109517 | Q2 | T3 DI WEIMAR #1 12/170C RPL POLE | 31505365 | WEIMAR #1 | 012/170 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.784859 | 39.0146 | ETL.7560 | 44947120 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  | In Review | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119109574 | Not Scheduled | T2 DI VLLY SPRNGS-MRTL #1 10/5 RPL SPLC |  | VALLEY SPRINGS-MARTELL #1 | 010/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.779866 | 38.338 | ETL.8240 | 40767359 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-18 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119110319 | Not Scheduled | T2 DI COLGATE-GRSS VLLY 9/218 BUTT CNCL | 44365323 | COLGATE-GRASS VALLEY | 009/218 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-02 | 2022-06-02 | [6 empty] | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-121.083132 | 39.2466 | ETL.6490 | 40818423 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119110349 | Not Scheduled | T3 DI FULTON-PUEBLO 36/182 RPL INSS | 31505500 | FULTON-PUEBLO | 036/182 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.641108 | 38.497 | ETL.1600 | 40712064 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119110368 | Q2 | DI SBRNTE-GRZZLY-CLMNT #1 3/033 RPR FOND |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 003/033 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-26 | 2022-05-26 |  |  | 2021-05-31 | 2021-05-24 | [5 empty] | Central | WSIP | [6 empty] | '-122.176491 | 37.8649 | ETL.3740 | 40607957 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119110381 | Not Scheduled | T3 DI EGL RCK-FLTN-SLVDO 36/182 RPL INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 036/182 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.64095 | 38.4971 | ETL.4392 | 40712066 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119110424 | Not Scheduled | T3 DI RND MTN-CTTONWD #3 31/257 RPR FOND | 43932111 | ROUND MTN-COTTONWOOD #3 | 031/257 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2020-11-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.974225 | 40.7491 | ETL.5650 | 40810664 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119110446 | Q3 | T3 DI BEARDSLEY TAP 2/5C RPR GYWW |  | BEARDSLEY TAP | 002/005C | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-26 | 2020-11-26 |  |  | 2021-09-04 | 2021-09-03 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.060421 | 38.1793 | ETL.1401 | 42834637 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119110480 | Not Scheduled | T3 DI EGL RCK-FLTN-SLVRD 38/192 RPL INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 038/192 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.66908 | 38.497 | ETL.4392 | 40724682 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119110483 | Not Scheduled | T3 DI FULTON PUEBLO 38/192 RPL INSS | 31505500 | FULTON-PUEBLO | 038/192 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.669118 | 38.4968 | ETL.1600 | 40724680 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119110545 | Not Scheduled | T3 DI RND MTN-CTTONWD #3 29/240 RPR FOND | 43932111 | ROUND MTN-COTTONWOOD #3 | 029/240 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2022-05-19 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.957067 | 40.7696 | ETL.5650 | 40594999 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119110637 | Q3 | DI BEARDSLEY TAP 000/006 RMV DEBRIS |  | BEARDSLEY TAP | 000/006 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-19 | 2022-05-19 |  |  | 2021-09-04 | 2021-09-03 | [5 empty] | Central | WSIP | [6 empty] | '-120.067372 | 38.2004 | ETL.1401 | 44889239 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119110638 | Q3 | DI BEARDSLEY TAP 000/006 RPL HRDD |  | BEARDSLEY TAP | 000/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2021-05-19 |  |  | 2021-09-04 | 2021-09-03 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.067372 | 38.2004 | ETL.1401 | 44889239 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119110658 | Q2 | T3 DI MI-WUK-CURTIS 19/5R RPL STRW | 31505692 | ETL.1073.POLE.WDPS | 019/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-21 | 2020-11-21 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.2343 | 38.0479 | ETL.1073 | 44837668 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119110768 | Q2 | DI SAN LUIS OBISPO-OCNO 16/79 RPL HRDW |  | SAN LUIS OBISPO-OCEANO | 016/079 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-18 | 2021-05-18 | 2021-03-08 | 2021-03-11 | 2021-04-08 | 2021-04-05 | [5 empty] | South | WSIP | [6 empty] | '-120.521409 | 35.0979 | ETL.3530 | 40810258 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119110864 | Q3 | DI GTS-MSTNG SW STA #1 1/10 RPR FOUND | 44361564 | SPARE T-LINE RECORD | 001/010 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-05-26 | 2022-05-26 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.09719 | 36.1522 | ETL.2604 | 40582474 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119110889 | Q2 | DI MUSTANG SW STA-GREGG 21/91 RPR FOUND | 44361567 | GATES-GREGG | 021/091 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-05-27 | 2022-05-27 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.889514 | 36.3226 | ETL.4700 | 40581133 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119110898 | Q2 | T3 DI WEIMAR #1 9/137 RPLC STRW | 31506097 | WEIMAR #1 | 009/137 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-20 | 2020-11-20 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.835468 | 39.0201 | ETL.7560 | 40913138 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-08-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111137 | Not Scheduled | DI PIT #1-COTTONWOOD 009/078A RPR FOND | 44051409 | PIT #1-COTTONWOOD | 009/078A | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-20 | 2021-05-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.648089 | 40.9114 | ETL.5390 | 40576647 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111138 | Mar | T2 DI KILARC-DESCHUTES A23/494 REFRAME | 31507071 | KILARC-DESCHUTES | A023/494 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.255163 | 40.5639 | ETL.7300 | 40755256 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111255 | Mar | T2 DI KILARC-DESCHUTS A23/494 RMV PL BUT | 43930440 | KILARC-DESCHUTES | A023/494 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.255163 | 40.5639 | ETL.7300 | 40755256 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111295 | Q2 | DI GATES-PANOCHE #1 0/4 RPR STRT | 44361571 | GATES-PANOCHE #1 | 000/004 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-26 | 2021-05-26 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.12857 | 36.1477 | ETL.4720 | 40753571 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119111328 | Not Scheduled | DI GATES-PANOCHE #1 0/4 RPR SHLS | 44361501 | GATES-PANOCHE #1 | 000/004 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-05-26 | 2021-05-26 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.12857 | 36.1477 | ETL.4720 | 40753571 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119111345 | Not Scheduled | T3 DI CARIBOU-PALERMO :010/083 RPR STRT |  | CARIBOU-PALERMO | :010/083 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.272689 | 39.9931 | ETL.3190 | 40910324 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111347 | Not Scheduled | T3 DI CARIBOU-PALERMO :010/083 RPL INSS |  | CARIBOU-PALERMO | :010/083 | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.272689 | 39.9931 | ETL.3190 | 40920063 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111436 | Mar | T3NT DI MIDDLE FRK-GLD HLL 2/20 RPR FOND | 44371599 | MIDDLE FORK-GOLD HILL | 002/020 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-01 | 2022-06-01 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.612675 | 39.0016 | ETL.5140 | 40597516 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111532 | Q2 | T3 DI UKH-HPLND-CLVRDL 13/4 RMV PLE BUTT | 44610700 | UKIAH-HOPLAND-CLOVERDALE | 013/004 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-21 | 2022-05-21 |  |  | 2021-04-16 | 2021-04-13 |  |  | Likely MAT error - delink to correct | TR3 |  | North Coast | WSIP | [6 empty] | '-122.99799 | 38.8444 | ETL.4050 | 44838830 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111541 | Q4 | T3 DI MIDDLE FORK-GOLD HLL 2/20 RPR SHDW | 44371780 | MIDDLE FORK-GOLD HILL | 002/020 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2020-12-01 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.612675 | 39.0016 | ETL.5140 | 40597516 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111603 | Q2 | T2 DI BRDGVLL-CTTONWD 10/100 RMV PL BUT | 43939216 | BRIDGEVILLE-COTTONWOOD | 010/100 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-19 | 2022-05-19 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.471567 | 40.389 | ETL.1110 | 44424541 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111713 | Q2 | T3 DI VOLTA-DESCHUTES 003/070 RPL HRDW | 43939089 | VOLTA-DESCHUTES | 003/070 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.925362 | 40.4743 | ETL.8290 | 40759238 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111785 | Mar | T2 DI VLY SPRGS-MRTL #1 4/4 RPL POLE |  | VALLEY SPRINGS-MARTELL #1 | 004/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2021-06-01 |  |  | 2021-03-12 | 2021-03-09 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.770398 | 38.2579 | ETL.8240 | 40754958 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-07-30 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111810 | Feb | T2 DI CLGATE-GRASS VLY 3/073 RMV PL BUTT | 44365323 | COLGATE-GRASS VALLEY | 003/073 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-02 | 2022-06-02 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.134833 | 39.3212 | ETL.6490 | 40695676 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111821 | Mar | T3 DI DRUM-RIO OSO #2 0/6 BENT MEMB | 44356575 | DRUM-RIO OSO #2 | 000/006 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-05-20 | 2020-11-20 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.780496 | 39.2566 | ETL.1430 | 40815323 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111823 | Not Scheduled | T2 DI VLY SPRGS-MRTL #1 4/4 RPR SPLICE |  | VALLEY SPRINGS-MARTELL #1 | 004/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2021-06-01 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.770398 | 38.2579 | ETL.8240 | 40754958 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111874 | Q2 | 006/013 LIGHT DUTY STEEL POLE | 44610613 | KONOCTI-EAGLE ROCK | 006/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-05 | 2020-12-05 |  |  | 2021-05-06 | 2021-05-06 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.772283 | 38.9058 | ETL.6861 | 44933137 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111953 | Mar | T3 DI DRM-GRS VLY-WMAR 4/109 RPR GYWW | 44364856 | DRUM-GRASS VALLEY-WEIMAR | 004/109 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8033 | 39.2162 | ETL.6760 | 40693324 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119111992 | Mar | T3 DI DRM-GRS VLY-WMR 2/57 RMV BUTT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 002/057 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-27 | 2022-05-27 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.778266 | 39.2355 | ETL.6760 | 40654105 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112003 | Mar | T3NT DI DRM-GRS VLY-WMAR 4/109 RMV DBRIS | 44364845 | DRUM-GRASS VALLEY-WEIMAR | 004/109 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-29 | 2022-05-29 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.8033 | 39.2162 | ETL.6760 | 40693324 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112040 | Not Scheduled | T2 DI VLY SPRNGS-MRTL #1 6/4 RMV PL BUT |  | VALLEY SPRINGS-MARTELL #1 | 006/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-01 | 2022-06-01 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.756621 | 38.2783 | ETL.8240 | 40768897 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-30 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112090 | Mar | T3 DI DRM-GRS VLY-WMR 2/57 RPR POLE | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 002/057 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.778266 | 39.2355 | ETL.6760 | 40654105 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112099 | Not Scheduled | T2 DI VLY SPRINGS-MRTL #1 6/4 RPL SPLICE |  | VALLEY SPRINGS-MARTELL #1 | 006/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2021-06-01 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.756621 | 38.2783 | ETL.8240 | 40768897 | Splice-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-18 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112103 | Not Scheduled | T2NT DI DIVIDE-CABRILLO #2 6/74 RMV STUB |  | DIVIDE-CABRILLO #2 | 006/074 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-26 | 2022-05-26 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.433366 | 34.7434 | ETL.1370 | 40618728 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112109 | Q2 | T2 DI WEIMAR #1 3/45 RPR STRW | 44362373 | WEIMAR #1 | 003/045 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-20 | 2021-05-20 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.95 | 39.0206 | ETL.7560 | 40913164 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112116 | Not Scheduled | T3 ATASCADERO-CAYUCOS 3/035 RPL POLE | 31507005 | ATASCADERO-CAYUCOS | 003/035 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-05 | 2020-12-05 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.732913 | 35.4645 | ETL.8480 | 40817233 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-27 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112251 | Q4 | T2 DI MDDL FRK-GLD HILL 022/177 RPR GYWW | 44361893 | MIDDLE FORK-GOLD HILL | 022/177 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-22 | 2021-05-22 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.904212 | 38.859 | ETL.5140 | 44557467 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112252 | Q4 | T2 DI MDDL FRK-GLD HILL 022/177 RPR GYWW | 44361893 | MIDDLE FORK-GOLD HILL | 022/177 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-22 | 2021-05-22 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.904212 | 38.859 | ETL.5140 | 44557466 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112260 | Feb | T2 DI CLGTE-GRS VLY 6/147 RMV DEBRIS | 44365323 | COLGATE-GRASS VALLEY | 006/147 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-02 | 2022-06-02 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.102287 | 39.294 | ETL.6490 | 40603839 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112363 | Mar | T2 DI KILARC-DESCHUTES 4/99 RPR SPLW | 43930440 | KILARC-DESCHUTES | 004/099 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.923997 | 40.6225 | ETL.7300 | 44809991 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112535 | Q2 | T2 DI ELK-GUALALA 64/1 RPR STRW |  | ELK-GUALALA | 064/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-21 | 2021-05-21 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.542173 | 38.8121 | ETL.8410 | 40601544 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112559 | Q3 | T2 DI CARIBOU-WSTWD 8/159 RMV PL BUTT |  | CARIBOU-WESTWOOD | 008/159 | ICW | F | 2020_(3) On high spread structure | Budget Owner (Veg/Land/Road) | 2020-06-02 | 2022-06-02 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.07989 | 40.181 | ETL.6300 | 40591698 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112576 | Not Scheduled | T3 DI DRUM-SUMMIT#2 004/055A RPR INSW | 44365659 | DRUM-SUMMIT #2 | 004/055A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.704355 | 39.2924 | ETL.1450 | 40893025 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112597 | Mar | T3 DI MORAGA-CLARE #1 2/21 INST HRDS | 44621674 | MORAGA-CLAREMONT #1 | 002/021 | ICS | E | 2020_(3) On high spread structure |  | 2020-05-22 | 2021-05-31 |  |  | 2021-03-22 | 2021-03-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.200386 | 37.8595 | ETL.2700 | 40580781 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | SVRPR | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112614 | Q3 | T2 DI CARIBOU-WESTWOOD 8/159 RPR WDPKR |  | CARIBOU-WESTWOOD | 008/159 | ICW | E | 2020_(2) High fire spread TD | Budget Owner (Veg/Land/Road) | 2020-06-02 | 2021-06-02 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.07989 | 40.181 | ETL.6300 | 40591698 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112659 | Q2 | T3 DI IGNACIO-BOLINAS #1 8/88 RPL POLE | 44640733 | IGNACIO-BOLINAS #1 | 008/088 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.654775 | 38.0115 | ETL.7140 | 40657320 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112717 | Not Scheduled | T2 DI PARKWAY-MORAGA 9/54 RPR SHLS | 44609770 | PARKWAY-MORAGA | 009/054 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-21 | 2021-05-21 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-122.233759 | 38.0065 | ETL.5930 | 40867736 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112761 | Mar | T3 DI MORAGA-CLARE #1 2/21 RPL SPLS | 44621674 | MORAGA-CLAREMONT #1 | 002/021 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2021-05-31 |  |  | 2021-03-22 | 2021-03-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.200386 | 37.8595 | ETL.2700 | 40580781 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | SVRPR | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112821 | Q2 | T3 DI VOLTA-DESCHUTES 5/120 RPR STRW | 43939089 | VOLTA-DESCHUTES | 005/120 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.967662 | 40.4849 | ETL.8290 | 40700143 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112857 | Q4 | T3 MIDDLE FORK-GLD HILL 033/240 RPL INSW | 31506654 | MIDDLE FORK-GOLD HILL | 033/240 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-05-21 | 2021-05-31 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.993412 | 38.7332 | ETL.5140 | 44316300 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Scheduled Past Due | 93 | Q4 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112928 | Not Scheduled | T3 DI MDDLE FRK-GLD HLL 20/160C CANCEL | 31506651 | MIDDLE FORK-GOLD HILL | 020/160C | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.877038 | 38.8846 | ETL.5140 | 42569861 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112930 | Q2 | T3 DI WST PT VLLY SPNGS 4/56 RPL POLE | 31505998 | WEST POINT-VALLEY SPRINGS | 004/056 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 |  |  | 2021-04-10 | 2021-04-05 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.620975 | 38.3988 | ETL.8350 | 40803754 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-06-30 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112931 | Not Scheduled | T3 DI FRNCH MDWS-MDL FRK 12/224 RPR POLE | 44365646 | FRENCH MEADOWS-MIDDLE FORK | 012/224 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.599252 | 39.0124 | ETL.6870 | 40751819 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119112966 | Q3 | DI GTS-MSTNG SW STA #1 4/20 RPR FOUND | 44361564 | SPARE T-LINE RECORD | 004/020 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-05-26 | 2022-05-26 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.056169 | 36.1672 | ETL.2604 | 40582477 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119112991 | Q4 | T3 DI MDLE FRK-GLD HILL 8/67 SHIELD WIRE | 44371780 | MIDDLE FORK-GOLD HILL | 008/067 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.723288 | 39.0018 | ETL.5140 | 40815981 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113140 | Not Scheduled | T3 DI MDLE FRK-GLD HILL 8/67 RPL BOLT | 44371783 | MIDDLE FORK-GOLD HILL | 008/067 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.723288 | 39.0018 | ETL.5140 | 40815981 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113159 | Not Scheduled | DI STANISLAUS-MANTECA #2 26/153 RPR STRT |  | STANISLAUS-MANTECA #2 | 026/153 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-05 | 2021-06-05 | [9 empty] | Central | WSIP | [6 empty] | '-120.751638 | 37.9284 | ETL.3820 | 40651750 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 26 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113184 | Q2 | T2 DI TRINITY-MAPLE CREEK 41/6 RPL INSW | 31507478 | TRINITY-MAPLE CREEK | 041/006 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2021-06-04 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.651528 | 40.7256 | ETL.8170 | 40855869 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113187 | Q2 | T2 DI TRINITY-MPL CREEK 41/6 RMV DEBRIS | 44299848 | TRINITY-MAPLE CREEK | 041/006 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-04 | 2021-06-04 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.652448 | 40.7258 | ETL.8170 | 40827993 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113233 | Mar | T3NT DI MORAGA-SN LEAND #3 5/41 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 005/041 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-22 | 2022-05-22 |  |  | 2021-03-13 | 2021-03-08 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.121509 | 37.7737 | ETL.2790 | 40580825 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113235 | Mar | T3 DI MORAGA-SAN LEAND #3 5/41 RPR STRS |  | MORAGA-SAN LEANDRO #3 | 005/041 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-22 | 2020-11-22 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.121509 | 37.7737 | ETL.2790 | 40580825 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | ACRP | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113292 | Feb | T2 DI COLGATE-GRASS VLY 008/195 REFRAME | 31507018 | COLGATE-GRASS VALLEY | 008/195 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.08744 | 39.2616 | ETL.6490 | 40868932 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113356 | Q3 | T3 DI BEARDSLEY TAP 02/05A RPR GYWW |  | BEARDSLEY TAP | 002/005A | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-26 | 2020-11-26 |  |  | 2021-09-04 | 2021-09-03 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.060358 | 38.1794 | ETL.1401 | 40760580 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113424 | Not Scheduled | T2 DI VLY SPRNGS-MRTL #1 9/15 RMV PL BUT |  | VALLEY SPRINGS-MARTELL #1 | 009/015 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2022-06-01 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.775398 | 38.3284 | ETL.8240 | 40753644 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-18 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113458 | Q2 | T2 DI BDGVL CTTNWD 12/117 RPR ADSS | 43939216 | BRIDGEVILLE-COTTONWOOD | 012/117 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2021-05-27 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.506113 | 40.393 | ETL.1110 | 44424455 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113495 | Not Scheduled | T3 DI DRM-GRSS VLLY-WMR B017/384 BUTT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | B017/384 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-27 | 2022-05-27 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.964434 | 39.1314 | ETL.6760 | 40756938 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113497 | Not Scheduled | T3 DI DRM-GRSS VLLY-WMR B17/384 RPR PL | 44361667 | DRUM-GRASS VALLEY-WEIMAR | B017/384 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.964434 | 39.1314 | ETL.6760 | 40756938 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113517 | Q2 | T3 DI IGNACIO-BOLINAS #1 9/104A RMV STUB | 44640733 | IGNACIO-BOLINAS #1 | 009/104A | ICW | E | 2020_(3) On high spread structure |  | 2020-05-29 | 2020-11-29 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.657499 | 37.9899 | ETL.7140 | 40584912 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113583 | Not Scheduled | T3 DI MDDLFRK #1 1/18 RPL RPR POLE | 44361891 | MIDDLE FORK #1 | 001/018 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.599864 | 39.01 | ETL.8405 | 40589936 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113635 | Mar | T3 DI MORAGA-OAKLAND J 5/41 RPL INSS | 31504873 | MORAGA-OAKLAND "J" | 005/041 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-22 | 2020-11-22 |  |  | 2021-03-31 | 2021-03-31 |  | Split Tag - Hanger and Insulator |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.121509 | 37.7737 | ETL.2760 | 40604525 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | ACRP | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113771 | Mar | T3NT DI DRM-GSS VLY-WEI 4/96 RMV PL BUTT | 31507845 | DRUM-GRASS VALLEY-WEIMAR | 004/096 | 93J | F | 2020_(2) High fire spread TD |  | 2020-05-28 | 2022-05-28 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.800939 | 39.2216 | ETL.6760 | 40756119 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113803 | Mar | T3 DI DRM-GRS VLY-WMAR 001/027A RPR PL | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 001/027A | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.760277 | 39.2478 | ETL.6760 | 40766643 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113861 | Feb | T3 DI DSBLA CNTRVL 3/40A RPR GYWW | 44356201 | DESABLA-CENTERVILLE | 003/040A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2021-05-31 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.64251 | 39.8187 | ETL.6720 | 40751702 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113881 | Feb | T3NT DI DSBLA CNTRVL 3/40A RMV BUTT |  | DESABLA-CENTERVILLE | 003/040A | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-27 | 2022-05-27 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.64251 | 39.8187 | ETL.6720 | 40751702 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-31 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119113975 | Mar | T3 DI DRM-GRSS VLLY-WMAR 1/39 RPL POLE | 31418518 | DRUM-GRASS VALLEY-WEIMAR | 001/039 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.767674 | 39.2432 | ETL.6760 | 40813457 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114033 | Q2 | T3 DI GRN VLY-LLAGAS 5/45L RPR STRW | 44381541 | GREEN VALLEY-LLAGAS | 005/045 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-20 | 2020-11-20 | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-04-14 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.719251 | 37.0266 | ETL.1720 | 44513677 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114036 | Feb | T3NT DI MORAGA-CASTR VLLY 4/20 RPR FOND |  | MORAGA-CASTRO VALLEY | 004/020 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-22 | 2022-05-22 |  |  | 2021-02-24 | 2021-02-23 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.111109 | 37.8173 | ETL.5250 | 40596489 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114069 | Feb | DI KILARC-CEDAR CREEK 12/269 RPR GYWW | 43939119 | KILARC-CEDAR CREEK | 012/269 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2021-05-29 |  |  | 2021-02-26 | 2021-02-22 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.947718 | 40.7803 | ETL.7290 | 44774788 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114079 | Q2 | T3NT DI FULTON-PUEBLO 38/197 RPR FOUND |  | FULTON-PUEBLO | 038/197 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2022-05-27 |  |  | 2021-05-07 | 2021-05-03 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.68717 | 38.4965 | ETL.1600 | 40818390 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114164 | Feb | T3 DI DRUM-RIO OSO #1 07/79 REPL INSS | 31505600 | DRUM-RIO OSO #1 | 007/079 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-31 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.874606 | 39.1945 | ETL.1420 | 40888171 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | 93 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114390 | Feb | T3 DI EGL RCK-REDBUD :8/46 RMV DEBRIS | 44640730 | EAGLE ROCK-REDBUD | :008/046 | ICS | F | 2020_(3) On high spread structure |  | 2020-05-21 | 2022-05-21 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.691637 | 38.8861 | ETL.1480 | 40809073 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114497 | Feb | T3 DI BRDVLLE GRBRVLLE 7/2 RPR GYWW | 44300097 | BRIDGEVILLE-GARBERVILLE | 007/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2021-05-31 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.744254 | 40.4046 | ETL.6220 | 40661833 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | Yes | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114507 | Feb | T3 DI MNTA VSTA-JFFRSN#1 17/73 RPR FOND |  | MONTA VISTA-JEFFERSON #1 | 017/073 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2022-05-19 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.304999 | 37.4307 | ETL.5220 | 40658426 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | Huddart Park | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114510 | Not Scheduled | T3NT DI DRM-GS VL-WMR B17/396 RMV PL BUT | 44364845 | DRUM-GRASS VALLEY-WEIMAR | B017/396 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-28 | 2022-05-28 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.969701 | 39.1378 | ETL.6760 | 40814232 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114530 | Q3 | T3 DI DONNELLS-MI-WUK 0/2 RPR GYWW | 44623211 | DONNELLS-CURTIS | 000/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-26 | 2020-11-26 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.034319 | 38.2449 | ETL.1400 | 44379629 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114547 | Q3 | T3 DI DONNELLS-MI-WUK 3/7 RPL HRDW | 44623212 | DONNELLS-CURTIS | 003/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.038515 | 38.1934 | ETL.1400 | 44922053 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114572 | Not Scheduled | T3 DI FULTON-CALISTOGA 000/009 RPR STRW |  | FULTON-CALISTOGA | 000/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  |  | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.445538 | 38.5144 | ETL.6880 | 40861400 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-02-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114578 | Not Scheduled | T3 DI MIDDLEFORK #1 002/041 CANCEL | 44361891 | MIDDLE FORK #1 | 002/041 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.62107 | 39.0014 | ETL.8405 | 40766809 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114579 | Not Scheduled | T3 DI MIDDLEFORK #1 002/041 REPULL GUY | 44361891 | MIDDLE FORK #1 | 002/041 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.62107 | 39.0014 | ETL.8405 | 40766809 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114604 | Q3 | T3 DI DONNELLS-MI-WUK 3/7 RPR STRW | 44623213 | DONNELLS-CURTIS | 003/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.038515 | 38.1934 | ETL.1400 | 44922053 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 | USFS | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114688 | Feb | T3 DI KILARC-CEDAR CREEK 2/65 RPL STRW | 31506712 | KILARC-CEDAR CREEK | 002/065 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2021-05-31 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.923795 | 40.6941 | ETL.7290 | 40862151 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Feb | 70 | Feb |  |  | 2020-06-24 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114742 | Q2 | T3 DI LAURELES-OTTER 13/11 RPR GYWW | 44392340 | LAURELES-OTTER | 013/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 | 2021-06-01 | 2021-06-04 | 2021-06-04 | 2021-06-01 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.866357 | 36.3866 | ETL.7380 | 40601872 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114756 | Q2 | T2NT DI MORRO BAY-MESA 7/32 RPR FOND | 44361574 | MORRO BAY-MESA | 007/032 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-26 | 2022-05-26 |  |  | 2021-04-15 | 2021-04-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.754699 | 35.3153 | ETL.5290 | 40662879 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - 16 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114760 | Mar | T3 DI ATASCADERO-CAYUCOS 4/38 RPR CONDW |  | ATASCADERO-CAYUCOS | 004/038 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 | 2021-03-29 | 2021-03-31 | 2021-03-31 | 2021-03-29 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.742267 | 35.4644 | ETL.8480 | 40684718 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114766 | Mar | DI LAURELES-OTTER 8/2 RPR WDPKR | 44392348 | LAURELES-OTTER | 008/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2021-05-29 |  |  | 2021-03-25 | 2021-03-25 | [5 empty] | South | WSIP | [6 empty] | '-121.78934 | 36.4182 | ETL.7380 | 40701557 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114772 | Not Scheduled | T3 DI FLTN-CLSTG 6/4 RPR LADDER |  | FULTON-CALISTOGA | 006/004 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-18 | 2020-11-18 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.510496 | 38.5696 | ETL.6880 | 43599322 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114828 | Q2 | T3 DI DRUM-SPAULDING 005/120 RPR STRW | 44364850 | DRUM-SPAULDING | 005/120 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.703647 | 39.2945 | ETL.6770 | 40862144 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114865 | Not Scheduled | T3 DI MDDLFK #1 1/29 RPL POLE | 31506388 | MIDDLE FORK #1 | 001/029 | 70Y | E | 2020_(1a) PSPS |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.606706 | 39.0025 | ETL.8405 | 40586047 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119114872 | Not Scheduled | T3 DI PIT #1-COTTONWOOD 34/286 RPR FOND | 44051409 | PIT #1-COTTONWOOD | 034/286 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.003937 | 40.7132 | ETL.5390 | 40817542 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114892 | Mar | T3 DI DRUM-RIO OSO#2 1/12 RPL INSS | 31528394 | DRUM-RIO OSO #2 | 001/012 | 93K | E | 2020_(1a) PSPS |  | 2020-05-19 | 2020-11-19 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.78987 | 39.2563 | ETL.1430 | 40683652 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119114895 | Q2 | T3 DI FULTON-PUEBLO 021/097 RPR FOND |  | FULTON-PUEBLO | 021/097 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-26 | 2020-11-26 |  |  | 2021-05-07 | 2021-05-03 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.377894 | 38.5012 | ETL.1600 | 40818829 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114898 | Mar | T3 DI DRUM-RIO OSO#2 10/106A RPR SPLS | 44356576 | DRUM-RIO OSO #2 | 010/106A | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-19 | 2020-11-19 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.933276 | 39.17 | ETL.1430 | 40913104 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114900 | Feb | T3 DI DRUM-RIO OSO #1 1/020 RPR SPLS | 44361672 | DRUM-RIO OSO #1 | 001/020 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2020-11-22 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.802754 | 39.2537 | ETL.1420 | 40582451 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114903 | Q2 | T2 DI TRINITY-MAPLE CRK 11/00 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 011/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-02 | 2021-06-02 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.111874 | 40.768 | ETL.8170 | 40906413 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114904 | Not Scheduled | T2 DI GARCIA TAP 0/4 RPR STRW | 44610601 | GARCIA TAP | 000/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-22 | 2021-05-22 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.587777 | 38.8701 | ETL.8411 | 40770611 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114992 | Q3 | T3NT DI DONNELLS-MI-WUK 3/8 RMV PL BUTT |  | DONNELLS-CURTIS | 003/008 | GAR | F | 2020_(2) High fire spread TD |  | 2020-05-27 | 2022-05-27 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.04049 | 38.1913 | ETL.1400 | 40869936 | Structure-Wood | Rotten | Stub |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 586 | Victor |  |  | FERC | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | GAR | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119114997 | Not Scheduled | T3 DI PIT #1-COTTONWOOD 34/288 RPR FOND | 44051409 | PIT #1-COTTONWOOD | 034/288 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.005944 | 40.7108 | ETL.5390 | 40868818 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115009 | Not Scheduled | T3 DI MIDDLE FORK #1 8/121 RPR GYWW | 44365338 | MIDDLE FORK #1 | 008/121 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.728332 | 39.0038 | ETL.8405 | 40873841 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115023 | Not Scheduled | T3 DI MIDDLE FORK #1 8/122B RPR GYWW | 44365338 | MIDDLE FORK #1 | 008/122B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.729369 | 39.0046 | ETL.8405 | 42569712 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115053 | Feb | T3NT DI CLGATE-GRSS VLLY 5/134 RMV BUTT | 44361616 | COLGATE-GRASS VALLEY | 005/134 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-28 | 2022-05-28 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.107078 | 39.301 | ETL.6490 | 40874470 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115056 | Feb | T3NT DI KILARC-CEDAR CRK 6/148 RMV STUB | 43939119 | KILARC-CEDAR CREEK | 006/148 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2022-05-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.987757 | 40.7131 | ETL.7290 | 40600832 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115059 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 006/174 RPR POLE | 44345667 | COLGATE-ALLEGHANY | 006/174 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.078334 | 39.3451 | ETL.6470 | 40905847 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115067 | Q3 | T3 DI BEARDSLEY TAP 001/009 RPL X-BRACE | 31506058 | BEARDSLEY TAP | 001/009 | 93E | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2020-11-22 |  |  | 2021-09-04 | 2021-09-03 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.060243 | 38.1875 | ETL.1401 | 44390917 | Crossarm-Wood | No Good/Out of Stdrd | Replace | MAPP srdy | MAPP | Constructed and mapped | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115084 | Q2 | T2 DI TRINITY-MAPLE CREEK 8/15 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 008/015 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-02 | 2021-06-02 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.070906 | 40.7637 | ETL.8170 | 40906376 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115158 | Feb | T3 DI KILARC-CEDAR CREEK 8/190 RPR SPLW | 43939119 | KILARC-CEDAR CREEK | 008/190 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.987742 | 40.7325 | ETL.7290 | 40611087 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115190 | Mar | T3 DI LAURELES-OTTER 008/000 RPR STRW | 44392342 | LAURELES-OTTER | 008/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-03-25 | 2021-03-25 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.787395 | 36.4188 | ETL.7380 | 40617420 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115192 | Feb | T3NT DI KILARC-CEDAR CRK 8/198 RMV STUB | 43939119 | KILARC-CEDAR CREEK | 008/198 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2022-05-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.983625 | 40.7373 | ETL.7290 | 40877889 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115193 | Feb | T3 DI KILARC-CEDAR CREEK 8/198 RPR GYWW | 43939119 | KILARC-CEDAR CREEK | 008/198 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.983625 | 40.7373 | ETL.7290 | 40877889 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115194 | Mar | T3 DI DRM-GRSS VLLY-WEIMR 8/207 RPR STRW | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 008/207 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.858097 | 39.1826 | ETL.6760 | 40756216 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115199 | Q2 | T3 DI IGNACIO-BOLINAS #1 010/109 RPR SPL | 44640733 | IGNACIO-BOLINAS #1 | 010/109 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.659423 | 37.9785 | ETL.7140 | 40809050 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115240 | Q3 | T2 DI BRDGEVLE-GRBRVLE 21/4 RMV PL BUTT | 44299809 | BRIDGEVILLE-GARBERVILLE | 021/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-02 | 2022-06-02 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.759815 | 40.2279 | ETL.6220 | 40769355 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115267 | Feb | T3 DI KILARC-CEDAR CREEK 10/224 RPR GYWW | 43939119 | KILARC-CEDAR CREEK | 010/224 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.971115 | 40.7523 | ETL.7290 | 40677185 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115466 | Q2 | T3 DI LAURELES-OTTER WASH INSW | 44610149 | LAURELES-OTTER | 013/016 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-04-02 | 2021-03-31 |  |  | Likely MAT error - delink to correct | TR3 | LATE | South | WSIP | [6 empty] | '-121.87131 | 36.386 | ETL.7380 | 40855776 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115673 | Not Scheduled | T3 DI RND MTN-CTNWD #3 34/288 RPR FOND | 43932111 | ROUND MTN-COTTONWOOD #3 | 034/288 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.005991 | 40.7111 | ETL.5650 | 40868288 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115772 | Feb | T3NT DI KILARC-CEDAR CRK 11/252 RMV STUB | 43939119 | KILARC-CEDAR CREEK | 011/252 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2022-05-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.95676 | 40.7695 | ETL.7290 | 40592403 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115774 | Q2 | T3 DI LAURELES-OTTER 014/001 RPR STRW | 44610149 | LAURELES-OTTER | 014/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-04-02 | 2021-03-31 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.873744 | 36.3858 | ETL.7380 | 40601881 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115937 | Q2 | T2 DI WEIMAR #1 000/008 RPR SPLW | 44345834 | WEIMAR #1 | 000/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-19 | 2021-05-19 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.983034 | 39.0355 | ETL.7560 | 44913366 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115992 | Not Scheduled | T3 DI CRESTA-RIO OSO 018/151 RPR FOND |  | CRESTA-RIO OSO | 018/151 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.483761 | 39.7013 | ETL.4590 | 40910166 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119115994 | Q2 | T3 DI CRESTA-RIO OSO 018/151 RPL INSS | 31500129 | CRESTA-RIO OSO | 018/151 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.483761 | 39.7013 | ETL.4590 | 40919905 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116003 | Q2 | DI GATES-PANOCHE #1 1/7 RPR FOND | 44361571 | GATES-PANOCHE #1 | 001/007 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-05-26 | 2021-05-26 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.135091 | 36.1553 | ETL.4720 | 40811166 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119116004 | Q3 | DI GATES-MUSTNG SW STA #1 4/22A RPR FOND | 44361564 | SPARE T-LINE RECORD | 004/022A | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-05-26 | 2022-05-26 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.047671 | 36.1702 | ETL.2604 | 40576158 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119116008 | Q3 | T3 DI BEARDSLEY TAP 002/005B RPR GYWW |  | BEARDSLEY TAP | 002/005B | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-26 | 2020-11-26 |  |  | 2021-09-04 | 2021-09-03 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.060391 | 38.1793 | ETL.1401 | 42834636 | Guy Wire-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116061 | Not Scheduled | T3 DI FULTON-PUEBLO 039/199 REPAIR STRS |  | FULTON-PUEBLO | 039/199 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.693585 | 38.4969 | ETL.1600 | 40872212 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116074 | Q2 | DI MUSTANG SW STA-GREGG 18/80A RPR FOND | 44361567 | GATES-GREGG | 018/080A | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-05-27 | 2022-05-27 |  |  | 2021-06-30 | 2021-06-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.875068 | 36.2854 | ETL.4700 | 40575766 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119116080 | Feb | T2 DI PHILO JCT-ELK-ELK 27/7 RPL INSW | 31506299 | PHILO JCT-ELK | 027/007 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2021-05-22 |  |  | 2021-02-11 | 2021-02-09 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.568018 | 39.0989 | ETL.7780 | 40819527 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116081 | Feb | T2 DI PHILO JCT-ELK-ELK 27/7 RPL XARM | 31506500 | PHILO JCT-ELK | 027/007 | 93E | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2021-05-22 |  |  | 2021-02-11 | 2021-02-09 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.568018 | 39.0989 | ETL.7780 | 40819527 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116116 | Q2 | T3 DI IGNACIO-BOLINAS#1 011/116 RPR GYWW | 44640733 | IGNACIO-BOLINAS #1 | 011/116 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.665735 | 37.9671 | ETL.7140 | 40827632 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116174 | Mar | T3NT DI GYSRS #3 CLVRDL 7/85 RMV DEBRIS | 44580896 | GEYSERS #3-CLOVERDALE | 007/085 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-27 | 2022-05-27 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.940542 | 38.803 | ETL.1650 | 40808559 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116175 | Mar | T3 DI GYSRS #3 CLVRDL 7/85 RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 007/085 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.940542 | 38.803 | ETL.1650 | 40808559 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116194 | Mar | T2 DI CORTINA-MENDCNO #1 57/283 RPR FOND |  | CORTINA-MENDOCINO #1 | 057/283 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-26 | 2021-05-26 |  |  | 2021-03-05 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.141714 | 39.2363 | ETL.1330 | 40648772 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116200 | Q4 | T3 DI MDDLFK GLD HILL 16/135 RPR STRW | 44361894 | MIDDLE FORK-GOLD HILL | 016/135 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.848375 | 38.9152 | ETL.5140 | 40761211 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116223 | Q2 | T3 DI LAURELES-OTTER 12/0 RPR GYWW | 44392343 | LAURELES-OTTER | 012/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 | 2021-06-01 | 2021-06-04 | 2021-06-04 | 2021-06-01 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.843052 | 36.3947 | ETL.7380 | 40617443 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116224 | Feb | T3 DI KILARC-CEDAR CRK 9/204 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 009/204 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.980802 | 40.7407 | ETL.7290 | 40657254 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116225 | Feb | T3 DI KILARC-CEDAR CRK 9/204 RPLC HRDW | 43939119 | KILARC-CEDAR CREEK | 009/204 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.980802 | 40.7407 | ETL.7290 | 40657254 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116226 | Q2 | T3 DI IGNACIO-BOLINAS #1 9/101 RPLC CRSW | 31506711 | IGNACIO-BOLINAS #1 | 009/101 | 93E | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.656368 | 37.9967 | ETL.7140 | 40861143 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-11 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116228 | Q2 | T3 DI DRUM-SPAULDING 4/100 RPL STRW | 31529083 | DRUM-SPAULDING | 004/100 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.71124 | 39.2856 | ETL.6770 | 40616116 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116252 | Mar | T3 DI DRM-GRSS VLY-WR 6/167 REFRAME | 31506292 | DRUM-GRASS VALLEY-WEIMAR | 006/167 | 93E | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.83942 | 39.1992 | ETL.6760 | 40598631 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116258 | Mar | T3NT DI DRM-GRSS VLY-WR 6/167 RMV PL BUT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 006/167 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-28 | 2022-05-28 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.83942 | 39.1992 | ETL.6760 | 40598631 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116270 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 6/161 RPR POLE | 44346134 | COLGATE-ALLEGHANY | 006/161 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.085966 | 39.3408 | ETL.6470 | 40766590 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116272 | Q2 | T3 DI IGNACIO-BOLINAS #1 10/110 RMV STUB | 44640733 | IGNACIO-BOLINAS #1 | 010/110 | ICW | E | 2020_(3) On high spread structure |  | 2020-05-29 | 2020-11-29 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.659548 | 37.9782 | ETL.7140 | 40588059 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116275 | Q2 | T3 DI SLY CREEK TAP 1/10A RPR POLE | 44391954 | SLY CREEK TAP | 001/010A | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.137836 | 39.5697 | ETL.4221 | 40658758 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116298 | Mar | T3 DI KILARC-DESCHUTES 0/1 RMV BUTT | 43930440 | KILARC-DESCHUTES | 000/001 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-28 | 2022-05-28 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.872795 | 40.6778 | ETL.7300 | 40701858 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116312 | Mar | T3 DI DEER CREEK-DRUM 001/030 RPR GRDWW | 44364857 | DEER CREEK-DRUM | 001/030 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.837432 | 39.2812 | ETL.6690 | 40874928 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116317 | Feb | T3 DI KILARC-CEDAR CREEK 9/206 RPLC HRDW | 43939119 | KILARC-CEDAR CREEK | 009/206 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.979987 | 40.7417 | ETL.7290 | 40770427 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116320 | Feb | T3NT DI KILARC-CDR CRK 10/226 RMV PL BUT | 43939119 | KILARC-CEDAR CREEK | 010/226 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2022-05-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.970125 | 40.7535 | ETL.7290 | 40759581 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116340 | Feb | T3 DI KILARC-CEDAR CREEK 9/201 RPR INSW | 43939119 | KILARC-CEDAR CREEK | 009/201 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.9823 | 40.7389 | ETL.7290 | 40641432 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116341 | Feb | T3NT DI KILARC-CEDAR CRK 9/201 RMV BUTT | 44406464 | KILARC-CEDAR CREEK | 009/201 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2022-05-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.9823 | 40.7389 | ETL.7290 | 40617738 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116346 | Mar | T3 DI LAURELES-OTTER 7/5 RPR STRW | 44392344 | LAURELES-OTTER | 007/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-03-24 | 2021-03-24 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.77766 | 36.4231 | ETL.7380 | 40770243 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116349 | Mar | T3 DI GEYSERS #3-CLOVRDALE 7/84 RPR STRW | 44580896 | GEYSERS #3-CLOVERDALE | 007/084 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.939793 | 38.8033 | ETL.1650 | 40819430 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116444 | Mar | T3 DI DRM-GRS VLLY-WMR 8/208 RPR STRW | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 008/208 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.859366 | 39.1815 | ETL.6760 | 40766735 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116468 | Not Scheduled | T3 DI MIDDLE FORK #1 7/110 RPR INSW | 44365338 | MIDDLE FORK #1 | 007/110 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.717933 | 39.0037 | ETL.8405 | 40602856 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116471 | Feb | T3 DI COLGATE-GRSS VALLY 7/167 RPL POLE | 31506254 | COLGATE-GRASS VALLEY | 007/167 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.09406 | 39.2793 | ETL.6490 | 40695701 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116476 | Mar | T3 DI DRM-GRS VLY-WMR 4/104 RPLC POLE | 31506387 | DRUM-GRASS VALLEY-WEIMAR | 004/104 | 70Y | E | 2020_(1a) PSPS |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.802644 | 39.2183 | ETL.6760 | 40654100 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119116477 | Mar | T3 DI DRM-GRS VLY-WMR 4/104 RMV DEBRIS | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 004/104 | ICW | F | 2020_(1a) PSPS |  | 2020-05-28 | 2022-05-28 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.802644 | 39.2183 | ETL.6760 | 40654100 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119116484 | Q4 | T3 DI MAPLE CRK-HOOPA 11/008B RPR GYWW | 44178090 | MAPLE CREEK-HOOPA | 011/008 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-10-02 | 2021-07-26 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.769416 | 40.9017 | ETL.7490 | 44735735 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116507 | Q2 | T3NT DI FULTON-PUEBLO 36/185 RPR FOUND |  | FULTON-PUEBLO | 036/185 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2022-05-27 |  |  | 2021-05-07 | 2021-05-03 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.649733 | 38.4971 | ETL.1600 | 40750505 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116561 | Mar | T3 DI DRM-GRS VLY-WMR 3/75 REFRAME | 31506292 | DRUM-GRASS VALLEY-WEIMAR | 003/075 | 93E | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.791339 | 39.2304 | ETL.6760 | 40900625 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116565 | Not Scheduled | T3 DI FRNCH MDWS-MDL FRK 12/237 RPL HRDW | 44365646 | FRENCH MEADOWS-MIDDLE FORK | 012/237 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.597109 | 39.023 | ETL.6870 | 40826825 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116580 | Mar | T3 DI LAURELES-OTTER 8/3 RPR STRW | 44392345 | LAURELES-OTTER | 008/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-03-25 | 2021-03-25 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.790198 | 36.4177 | ETL.7380 | 40668266 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116651 | Mar | T3NT DI DRM GRS-GRSVLY WMR 0/23 RMV BUTT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 000/023 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-28 | 2022-05-28 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.757064 | 39.2491 | ETL.6760 | 42549841 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116732 | Q4 | T3 DI KESWICK-TRINITY 0/22 RMV PL BUTT | 43661466 | KESWICK-TRINITY | 000/022 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-04 | 2022-06-04 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-122.473438 | 40.6189 | ETL.7270 | 40576552 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-06-22 | Released-Standard | Complete | Ready for Construction |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116739 | Not Scheduled | T3NT DI MIDDLE FORK #1 2/43C INST NUMBR | 44361892 | MIDDLE FORK #1 | 002/043C | ICW | F | 2020_(3) On high spread structure |  | 2020-05-28 | 2022-05-28 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.625059 | 39.0014 | ETL.8405 | 42569705 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116741 | Q2 | T3NT DI PTTSBRG-SAN RMN 10/41 RPR FOUND |  | PITTSBURG-SAN RAMON | 010/041 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-22 | 2022-05-22 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.880246 | 37.8978 | ETL.5490 | 40581140 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116746 | Q3 | T3 DI PTTSBRG-SAN RMN 10/41 RMV VEG |  | PITTSBURG-SAN RAMON | 010/041 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-22 | 2020-11-22 |  |  | 2021-08-31 | 2021-08-01 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.880246 | 37.8978 | ETL.5490 | 40581140 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116763 | Not Scheduled | T3 DI DRM GRS-GRSVY WMR B18/402 RPL POLE | 31515654 | DRUM-GRASS VALLEY-WEIMAR | B018/402 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.971814 | 39.1413 | ETL.6760 | 40664712 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116768 | Q4 | T3 DI MDDL FRK-GLD HILL 6/131A RPR STRW | 44361894 | MIDDLE FORK-GOLD HILL | 016/131A | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.839252 | 38.9202 | ETL.5140 | 40593947 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116794 | Not Scheduled | T3 DI ROND MTN-CTTNWD #3 33/281 RPL HRDT | 43932111 | ROUND MTN-COTTONWOOD #3 | 033/281 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.999325 | 40.7191 | ETL.5650 | 40591930 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116801 | Not Scheduled | T3 DI MIDDLE FORK #1 2/43C CANCEL | 44361891 | MIDDLE FORK #1 | 002/043C | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.625059 | 39.0014 | ETL.8405 | 42569705 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116824 | Q2 | T3NT DI GEYSERS #12-FULTON 0/3 RPR FOND | 44631264 | GEYSERS #12-FULTON | 000/003 | ICS | F | 2020_(2) High fire spread TD |  | 2020-05-27 | 2022-05-27 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.778493 | 38.8017 | ETL.4750 | 41129168 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116861 | Mar | T2 DI KILARC-DESCHUTES 19/406 INST MRKW | 43930440 | KILARC-DESCHUTES | 019/406 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.181682 | 40.5638 | ETL.7300 | 40817238 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116862 | Mar | T2 DI KILARC-DESCHTES 19/406 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 019/406 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.181682 | 40.5638 | ETL.7300 | 40817238 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116863 | Mar | T2 DI KILARC-DESCHUTES 19/406 RPL SPLW | 43930440 | KILARC-DESCHUTES | 019/406 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.181682 | 40.5638 | ETL.7300 | 40817238 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116866 | Q2 | T3 DI VOLTA-DESCHTES 5/119 REFRAME CRSW | 31505200 | VOLTA-DESCHUTES | 005/119 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.966973 | 40.4847 | ETL.8290 | 40592118 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116897 | Q2 | T3 DI VOLTA-DESCHUTES 5/125 REFRAME CRSW | 31505200 | VOLTA-DESCHUTES | 005/125 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.97269 | 40.4861 | ETL.8290 | 40816165 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116915 | Q2 | T3 DI VOLTA-DESCHUTES 0/8 RMV STUB | 43939089 | VOLTA-DESCHUTES | 000/008 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.87309 | 40.4612 | ETL.8290 | 40827011 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116920 | Q2 | T3 DI VOLTA-DESCHUTES 0/8 RPR STRW | 43939089 | VOLTA-DESCHUTES | 000/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.87309 | 40.4612 | ETL.8290 | 40827011 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116937 | Not Scheduled | T3NT DI MDDLE FRK #1 007/107 INST GMKW | 44365334 | MIDDLE FORK #1 | 007/107 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-28 | 2022-05-28 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.713808 | 39.003 | ETL.8405 | 40874900 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116943 | Q2 | DI UKIAH-HPAND-CLOVERDALE 11/9 RPR GYWW | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 011/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2021-06-01 |  |  | 2021-04-16 | 2021-04-13 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.993389 | 38.8192 | ETL.4050 | 44310999 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116945 | Not Scheduled | T3 DI MORRO BAY-MESA 24/108 RPL INSS | 31501671 | MORRO BAY-MESA | 024/108 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.541329 | 35.131 | ETL.5290 | 40886908 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-01 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116947 | Not Scheduled | T3 DI DIABLO-MESA 24/108 RPL INSS | 31510098 | DIABLO-MESA | 024/108 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.541329 | 35.131 | ETL.4620 | 40886910 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-01 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116950 | Q2 | DI UKIAH-HPLND-CLOVERDALE 11/9 INST MRKW |  | UKIAH-HOPLAND-CLOVERDALE | 011/009 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-01 | 2022-06-01 |  |  | 2021-04-16 | 2021-04-13 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.993389 | 38.8192 | ETL.4050 | 44310999 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116990 | Mar | T3 DI DRM-GRSS VLY-WEIMR 000/018 RP GYWW | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 000/018 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.755581 | 39.2504 | ETL.6760 | 40813455 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116991 | Mar | T3NT DI DRM-GRSS VLY-WMR 0/018 RMV DBR | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 000/018 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-28 | 2022-05-28 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.755581 | 39.2504 | ETL.6760 | 40813455 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116992 | Q2 | T3 DI DRUM-SPAULDING 1/37 RMV PL BUTT | 44346133 | DRUM-SPAULDING | 001/037 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-04 | 2022-06-04 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.743482 | 39.2574 | ETL.6770 | 40751870 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116993 | Q2 | T3 DI DRUM-SPAULDING 1/37 RPR SPLW | 44346133 | DRUM-SPAULDING | 001/037 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.743482 | 39.2574 | ETL.6770 | 40751870 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116994 | Q2 | T3 DI VOLTA-DESCHUTES 1/25 RPR GYWW | 43939089 | VOLTA-DESCHUTES | 001/025 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.88842 | 40.4652 | ETL.8290 | 40660881 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119116995 | Q2 | T3NT DI VOLTA-DESCHUTES 1/25 RMV STUB | 43939089 | VOLTA-DESCHUTES | 001/025 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2022-06-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.88842 | 40.4652 | ETL.8290 | 40660881 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117021 | Not Scheduled | T3 DI FULTON-CALISTOGA 0/8 RPR INSS | 44597303 | FULTON-CALISTOGA | :000/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-18 | 2020-11-18 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.58119 | 38.6037 | ETL.6880 | 44860477 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117066 | Mar | T2 DI KILARC-DESCHUTES 2/56 RPL POLE | 31505377 | KILARC-DESCHUTES | 002/056 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.89531 | 40.6446 | ETL.7300 | 40577361 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117092 | Q2 | T3 DI VOLTA DESCHUTES 5/127 RPR STRW | 43939089 | VOLTA-DESCHUTES | 005/127 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.974627 | 40.4866 | ETL.8290 | 40867830 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117118 | Not Scheduled | T3 DI CARIBOU-PALERMO :011/088 RMV STEP |  | CARIBOU-PALERMO | :011/088 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-05 | 2022-06-05 | [7 empty] | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.280178 | 39.9882 | ETL.3190 | 40910328 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117153 | Feb | T3 DI KILARC-CDR CRK 11/246 RPR CNDW | 43939119 | KILARC-CEDAR CREEK | 011/246 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.959958 | 40.7656 | ETL.7290 | 40771266 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117165 | Q2 | T3 DI DRUM-HIGGINS 002/028C RPL STRW | 31508014 | DRUM-HIGGINS | 002/028C | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.79575 | 39.2282 | ETL.4393 | 42550184 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-22 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117175 | Not Scheduled | T3NT DI MIDDLEFORK #1 008/122B RMV STUB | 44365334 | MIDDLE FORK #1 | 008/122B | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2022-05-29 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.729369 | 39.0046 | ETL.8405 | 42569712 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117184 | Feb | T3 DI KILARC-CDR CRK 11/246 RMV DEBRIS | 43939119 | KILARC-CEDAR CREEK | 011/246 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.959958 | 40.7656 | ETL.7290 | 40771266 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117201 | Not Scheduled | T3 DI DRM-GRS VLY-WMAR B17/385 REPL POLE | 31515653 | DRUM-GRASS VALLEY-WEIMAR | B017/385 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.964823 | 39.1321 | ETL.6760 | 40824332 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117216 | Feb | T3NT DI DESABLA-CENTERVLE 0/14 RMV BUTT |  | DESABLA-CENTERVILLE | 000/014 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-01 | 2022-06-01 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.628197 | 39.8623 | ETL.6720 | 40751698 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-31 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117219 | Not Scheduled | T3 DI DRM-GRS VLY-WMAR B17/385 RMV STUB | 44364852 | DRUM-GRASS VALLEY-WEIMAR | B017/385 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2022-05-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.964823 | 39.1321 | ETL.6760 | 40824332 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117226 | Not Scheduled | T3 DI CARIBOU-PALERMO :011/088 RPR SPLS |  | CARIBOU-PALERMO | :011/088 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-05 | 2020-12-05 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.280178 | 39.9882 | ETL.3190 | 40910328 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117234 | Feb | T3 DI DESABLA-CENTERVLE 0/14 RPR STRW |  | DESABLA-CENTERVILLE | 000/014 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2020-12-01 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.628197 | 39.8623 | ETL.6720 | 40751698 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-31 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117243 | Not Scheduled | T3 DI MIDDLEFORK #1 8/122A RPR GYWW | 44365338 | MIDDLE FORK #1 | 008/122A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.729357 | 39.0046 | ETL.8405 | 40595340 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117267 | Feb | T3 DI KILARC-CEDAR CREEK 1/27 RPLC HRDW | 43939119 | KILARC-CEDAR CREEK | 001/027 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.893275 | 40.6852 | ETL.7290 | 44159598 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117268 | Feb | T3 DI DESABLA-CENTERVILLE 4/45 RPR STRW | 44356201 | DESABLA-CENTERVILLE | 004/045 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.646132 | 39.8084 | ETL.6720 | 40700318 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117274 | Q2 | T3 DI VOLTA DESCHUTES 6/146 RPL STRW | 31506865 | VOLTA-DESCHUTES | 006/146 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2021-05-31 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.991033 | 40.4906 | ETL.8290 | 40862488 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117290 | Not Scheduled | T2 BRDGVL-CTTNWD 30/251 RPR FOND | 43706644 | BRIDGEVILLE-COTTONWOOD | 030/251 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2022-06-01 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.830245 | 40.3645 | ETL.1110 | 40600474 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-24 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117299 | Q2 | T3 DI VOLTA DESCHUTES 6/138 REFRAME CRSW | 31505200 | VOLTA-DESCHUTES | 006/138 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.984325 | 40.4889 | ETL.8290 | 40615918 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117318 | Feb | T3 DI KILARC-CEDAR CRK 010/237 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 010/237 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.964302 | 40.7605 | ETL.7290 | 40752215 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117333 | Q3 | DI GATES-MUSTANG SW STA #1 2/21 RPR FOND | 44361564 | SPARE T-LINE RECORD | 002/011 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-05-26 | 2022-05-26 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.093333 | 36.1536 | ETL.2604 | 40581379 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119117380 | Feb | T3 DI KILARC-CEDAR CRK 10/237 RMV STUB | 43939119 | KILARC-CEDAR CREEK | 010/237 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.964302 | 40.7605 | ETL.7290 | 40752215 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117408 | Q2 | T3NT DI PITTSBURG-SN MAT 27/106 RPR FOND | 44623139 | PITTSBURG-SAN MATEO | 027/106 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-05-26 | 2022-05-26 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.00977 | 37.694 | ETL.5463 | 40581165 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117447 | Not Scheduled | T2 DI VLY SPRGS-MARTELL#1 3/18 RPR WDPKR |  | VALLEY SPRINGS-MARTELL #1 | 003/018 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2021-06-01 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.772631 | 38.255 | ETL.8240 | 40876069 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-30 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117522 | Q2 | T3 DI VOLTA-DESCHUTES 3/86 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 003/086 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2021-05-31 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.939017 | 40.4777 | ETL.8290 | 40600280 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117537 | Feb | T3NT DI KILARC-CEDAR CRK 7/179 RMV STUB | 43939119 | KILARC-CEDAR CREEK | 007/179 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2022-05-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.99317 | 40.7259 | ETL.7290 | 40873627 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117538 | Feb | T3 DI KILARC-CEDAR CREEK 007/179 RPR INS | 43939119 | KILARC-CEDAR CREEK | 007/179 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.99317 | 40.7259 | ETL.7290 | 40898034 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117539 | Not Scheduled | T3 DI COLGATE-ALLGHANY 007/192 RPR POLE | 44346106 | COLGATE-ALLEGHANY | 007/192 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.069579 | 39.351 | ETL.6470 | 40868948 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117543 | Q2 | T2NT DI SBNTGRZLYCLRMNT #1 2/24 RPR FOND |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 002/024 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-26 | 2022-05-26 |  |  | 2021-05-31 | 2021-05-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.185475 | 37.8783 | ETL.3740 | 40862369 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117548 | Mar | T3 DI DRUM-GRASS VLLY-WMR 1/44 RPR POLE | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 001/044 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.770683 | 39.2405 | ETL.6760 | 44260558 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117655 | Feb | T3 DI DRUM-RIO OSO #2 016/133 RPL INSS | 31503652 | DRUM-RIO OSO #2 | 016/133 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-26 | 2020-11-26 |  |  | 2021-02-23 | 2020-12-14 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.011487 | 39.1393 | ETL.1430 | 40683428 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117671 | Feb | T3NT DI DSBL-CENTERVILLE 0/8 RMV PL BUTT |  | DESABLA-CENTERVILLE | 000/008 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-01 | 2022-06-01 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.629918 | 39.8655 | ETL.6720 | 40862027 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-12 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117688 | Not Scheduled | T3 DI MIDDLEFORK #1 6/88 REPL HRDW | 44365338 | MIDDLE FORK #1 | 006/088 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.686971 | 39.0022 | ETL.8405 | 40598766 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117691 | Mar | T3NT DI DEER CREEK-DRUM 2/61 RMV PL BUT | 44364857 | DEER CREEK-DRUM | 002/061 | ICW | F | 2020_(1a) PSPS |  | 2020-05-29 | 2022-05-29 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.827108 | 39.2636 | ETL.6690 | 40757020 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119117715 | Q2 | T3 DI VOLTA-DESCHUTES 4/100 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 004/100 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.950823 | 40.4806 | ETL.8290 | 40660889 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117716 | Q2 | T3 DI VOLTA-DESCHUTES 4/100 RPR STRW | 43939089 | VOLTA-DESCHUTES | 004/100 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.950823 | 40.4806 | ETL.8290 | 40660889 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117737 | Q2 | T3NT DI FULTON-IGNAC #1 016/085 RPR FOND | 44310479 | FULTON-IGNACIO #1 | 016/085 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-30 | 2022-05-30 |  |  | 2021-04-23 | 2021-04-19 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592332 | 38.3898 | ETL.4680 | 40765347 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117742 | Mar | T3NT DI MDLE FRK-GLD HILL 5/44 RPR FOND | 44371599 | MIDDLE FORK-GOLD HILL | 005/044 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-01 | 2022-06-01 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.668234 | 39.0011 | ETL.5140 | 40759034 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117766 | Not Scheduled | T3 DI CARIBOU-PALERMO :30/245 REPLC HRDS |  | CARIBOU-PALERMO | :030/245 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452493 | 39.7774 | ETL.3190 | 40787815 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117768 | Not Scheduled | T3 DI CARIBOU-PALERMO :034/276 RPR FOND |  | CARIBOU-PALERMO | :034/276 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.479471 | 39.7247 | ETL.3190 | 40828377 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117790 | Feb | T3 DI DRUM-RIO OSO #1 1/14 RPR SPLS | 44346102 | DRUM-RIO OSO #1 | 001/014 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.793092 | 39.256 | ETL.1420 | 40786128 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117810 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 5/132 RPR POLE | 44346104 | COLGATE-ALLEGHANY | 005/132 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.101984 | 39.3318 | ETL.6470 | 40760699 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117839 | Not Scheduled | T3 DI PIT #1-COTTONWOOD 33/283 RPR FOND | 44051409 | PIT #1-COTTONWOOD | 033/283 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.000886 | 40.7169 | ETL.5390 | 40657358 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117878 | Q2 | T3NT DI VOLTA-DESCHUTES 6/131 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 006/131 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2022-06-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.978162 | 40.4875 | ETL.8290 | 40656917 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117918 | Q2 | T2 DI TRINITY MAPLE CREEK 36/6 RPL SPLW | 44273074 | TRINITY-MAPLE CREEK | 036/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2021-06-04 | 2021-04-05 | 2021-04-11 | 2021-04-11 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.571679 | 40.7183 | ETL.8170 | 40837327 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117921 | Q2 | T2 DI TRINITY MAPLE CRK 36/6 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 036/006 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-04 | 2022-06-04 | 2021-04-05 | 2021-04-11 | 2021-04-11 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.571679 | 40.7183 | ETL.8170 | 40810498 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117949 | Q2 | T2 DI TRINITY MAPLE CRK 36/6 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 036/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2021-06-04 | 2021-04-05 | 2021-04-11 | 2021-04-11 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.571679 | 40.7183 | ETL.8170 | 40810498 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119117958 | Q2 | T3NT DI DRUM HIGGINS A5/51B RMV PL BUTT | 44365656 | DRUM-HIGGINS | A005/051B | ICW | F | 2020_(3) On high spread structure |  | 2020-05-29 | 2022-05-29 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.835753 | 39.2151 | ETL.4393 | 42550227 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118018 | Q4 | T3 DI MDLE FRK-GLD HL 8/66 REPA SHLS | 44371780 | MIDDLE FORK-GOLD HILL | 008/066 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.721857 | 39.0023 | ETL.5140 | 40820687 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118020 | Q4 | T3 DI MDLE FRK-GLD HL 8/66 RPR INSS | 44371780 | MIDDLE FORK-GOLD HILL | 008/066 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.721857 | 39.0023 | ETL.5140 | 40849542 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118026 | Not Scheduled | T2 DI BRIDGEVILLE-CTNWD 31/258 RPR FOND | 43706644 | BRIDGEVILLE-COTTONWOOD | 031/258 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2022-06-02 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.84947 | 40.3633 | ETL.1110 | 40605507 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118052 | Q2 | T3 DI IGNCO-BLINS #1 10/111A RPR GYWW | 44640733 | IGNACIO-BOLINAS #1 | 010/111A | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.660175 | 37.9765 | ETL.7140 | 40585009 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118054 | Q2 | T3 DI IGNCO-BLINS #1 10/111B RPR GYWW | 44640733 | IGNACIO-BOLINAS #1 | 010/111 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.660207 | 37.9765 | ETL.7140 | 41111795 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118147 | Not Scheduled | T3 DI DIABLO-MESA X005/023 RPR JUMPER |  | DIABLO-MESA | X005/023 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.808344 | 35.2595 | ETL.4620 | 40686660 | Jumper-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-01 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118173 | Not Scheduled | T3 DI DIABLO-MESA X005/023 RPR SHLS |  | DIABLO-MESA | X005/023 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2020-12-02 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.808344 | 35.2595 | ETL.4620 | 40656939 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-01 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118191 | Not Scheduled | T3 DI MORRO BAY-DIABL X005/023 RPL INSS | 31507782 | MORRO BAY-DIABLO | X005/023 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2020-12-02 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.808344 | 35.2595 | ETL.5260 | 44690748 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-17 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118206 | Feb | T2 DI CLGATE-GRASS VALEY 3/76 RPR WDPKR | 44365328 | COLGATE-GRASS VALLEY | 003/076 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.132677 | 39.3211 | ETL.6490 | 40760389 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118214 | Not Scheduled | T3 DI CLGTE ALLGHNY 6/175 RPR POLE | 44346079 | COLGATE-ALLEGHANY | 006/175 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.078039 | 39.3453 | ETL.6470 | 40875293 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118240 | Not Scheduled | T3 DI DIABLO-MESA X004/022 RPR OPGW |  | DIABLO-MESA | X004/022 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2021-05-31 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.807354 | 35.2523 | ETL.4620 | 40682852 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-01 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118256 | Not Scheduled | T3NT DI CLGTE ALLGHNY 6/162 RMV STUB | 44356570 | COLGATE-ALLEGHANY | 006/162 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2022-05-29 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.085202 | 39.3412 | ETL.6470 | 40824244 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118261 | Q2 | T2 DI SALINAS-LAURELES 17/323 RPL INSW | 31507341 | SALINAS-LAURELES | 017/323 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-05-06 | 2021-05-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.73109 | 36.4965 | ETL.7930 | 40640126 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Moss Landing |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118262 | Not Scheduled | T3 DI CLGTE ALLGHNY 6/162 RPR POLE | 44346079 | COLGATE-ALLEGHANY | 006/162 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.085202 | 39.3412 | ETL.6470 | 40824244 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118263 | Not Scheduled | T2 DI CLGTE-SMARTVILLE #2 4/47 RPL POLE | 31507078 | COLGATE-SMARTVILLE #2 | 004/047 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.248594 | 39.2987 | ETL.6520 | 40594297 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118265 | Feb | T2 DI CLGT-GRASS VLY 5/125 RPR GYWW | 44365328 | COLGATE-GRASS VALLEY | 005/125 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.110397 | 39.3058 | ETL.6490 | 40603836 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118297 | Feb | T3 DI KILARC-CEDAR CRK 8/199 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 008/199 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.983077 | 40.738 | ETL.7290 | 40868039 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118311 | Feb | T3NT DI KILARC-CEDAR CRK 8/199 RMV STUB | 43939119 | KILARC-CEDAR CREEK | 008/199 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2022-05-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.983077 | 40.738 | ETL.7290 | 40868039 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118332 | Feb | T3 DI COLGATE-GRASS VALLY 5/137 RPL CRSW | 31506252 | COLGATE-GRASS VALLEY | 005/137 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.106155 | 39.2996 | ETL.6490 | 40679384 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118334 | Feb | T3 DI CLGTE-GRSS VLLY 6/163 RPR OPGW | 44361619 | COLGATE-GRASS VALLEY | 006/163 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.094973 | 39.2815 | ETL.6490 | 40825362 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118335 | Q2 | T3NT DI FULTON IGNACI #1 17/86 RPR FOUND | 44310479 | FULTON-IGNACIO #1 | 017/086 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2022-05-29 |  |  | 2021-04-23 | 2021-04-19 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592421 | 38.3835 | ETL.4680 | 40811759 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118424 | Feb | T3NT DI COLGATE-GRSS VLY 6/157 RMV BUTT | 44361616 | COLGATE-GRASS VALLEY | 006/157 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-28 | 2022-05-28 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.096818 | 39.2859 | ETL.6490 | 40612744 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118450 | Feb | T3 DI COLGATE-GRSS VLY 5/142 RPL INSW | 31506253 | COLGATE-GRASS VALLEY | 005/142 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.103753 | 39.2961 | ETL.6490 | 40851085 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118451 | Feb | T3NT DI COLGATE-GRSS VLY 5/142 RMV BUTTS | 44361616 | COLGATE-GRASS VALLEY | 005/142 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-28 | 2022-05-28 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.103753 | 39.2961 | ETL.6490 | 40823818 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118602 | Q2 | T2 DI TRINITY-MAPLE CREEK 4/5 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 004/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.009752 | 40.7352 | ETL.8170 | 40906306 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118607 | Not Scheduled | T2 DI CLGTE-SMARTVILLE #2 4/55 RPR GYWW | 44365320 | COLGATE-SMARTVILLE #2 | 004/055 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.256871 | 39.2892 | ETL.6520 | 40864696 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118608 | Not Scheduled | T2 DI CLGTE-SMARTVILLE #2 7/85 RPR GYWW | 44371197 | COLGATE-SMARTVILLE #2 | 007/085 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.287464 | 39.2569 | ETL.6520 | 40602839 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118623 | Q3 | T3 DI DONNELLS-MI-WUK 7/1 RMV PL BUTT | 44623215 | DONNELLS-CURTIS | 007/001 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-26 | 2022-05-26 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.090118 | 38.1706 | ETL.1400 | 40579646 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  | FERC | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118624 | Q3 | T3 DI DONNELLS-MI-WUK 7/1 RPR INSW | 44623216 | DONNELLS-CURTIS | 007/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-26 | 2020-11-26 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.090118 | 38.1706 | ETL.1400 | 40603180 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118627 | Feb | T2 DI COLGATE-GRASS VLLY 3/84 RPL POLE | 31514628 | COLGATE-GRASS VALLEY | 003/084 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.127437 | 39.3206 | ETL.6490 | 40760678 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-28 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118642 | Not Scheduled | T3NT DI DRUM-SUMMIT #2 4/50A RMV DEBRIS | 44371595 | DRUM-SUMMIT #2 | 004/050A | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-01 | 2022-06-01 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.708729 | 39.2871 | ETL.1450 | 40761541 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118684 | Q3 | T2 DI CARIBOU #2 000/027 RPR GYWW |  | CARIBOU #2 | 000/027 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.156424 | 40.0796 | ETL.6280 | 40815719 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118688 | Not Scheduled | T3 DI COLGATE-ALLGHANY 008/232 RPR POLE | 44356570 | COLGATE-ALLEGHANY | 008/232 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.04869 | 39.3654 | ETL.6470 | 40598545 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118710 | Mar | T2 DI KILARC-DESCHUTES 005/113 RPL POLE | 31507070 | KILARC-DESCHUTES | 005/113 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.933605 | 40.6173 | ETL.7300 | 40876550 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118762 | Mar | T3NT DI LAURELES OTTER 10/0 RMV PL BUTT | 44392350 | LAURELES-OTTER | 010/000 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-29 | 2022-05-29 |  |  | 2021-03-29 | 2021-03-29 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.819478 | 36.415 | ETL.7380 | 44563002 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118766 | Mar | T3 DI LAURELES OTTER 10/0 RMV PL BUTT | 44392351 | LAURELES-OTTER | 010/000 | ICW | E | 2020_(3) On high spread structure |  | 2020-05-29 | 2021-05-29 |  |  | 2021-03-29 | 2021-03-29 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.819478 | 36.415 | ETL.7380 | 44562891 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118769 | Q2 | T3 DI VOLTA-DESCHUTES 7/159 REFRAME CRSW | 31505200 | VOLTA-DESCHUTES | 007/159 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.003277 | 40.4934 | ETL.8290 | 40601160 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118770 | Q2 | T2 DI TRINITY-MAPLE CRK 010/015 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 010/015 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-02 | 2021-06-02 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.105256 | 40.7681 | ETL.8170 | 43950784 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118777 | Not Scheduled | T2 DI CAYUCOS-CAMBRIA 015/110 RPR WDPKR |  | CAYUCOS-CAMBRIA | 015/110 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.074404 | 35.582 | ETL.8560 | 40871956 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-17 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118786 | Q2 | T2 DI TRINITY-MPLE CREEK 8/7 RMV DEBRIS | 44299848 | TRINITY-MAPLE CREEK | 008/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2022-06-03 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.065517 | 40.7569 | ETL.8170 | 40906368 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118797 | Not Scheduled | T2 DI COLGAT-SMTVLL #2 8/99 CANCEL | 44371197 | COLGATE-SMARTVILLE #2 | 008/099 | ICW | E | 2020_(1a) PSPS |  | 2020-06-03 | 2021-06-03 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.29558 | 39.2393 | ETL.6520 | 40876773 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119118801 | Q3 | T2 DI CARIBOU #2 3/26 RPLC INSW | 31505337 | CARIBOU #2 | 003/026 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.20228 | 40.0593 | ETL.6280 | 40855024 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118811 | Feb | T3NT DI KLRC CDR CRK 6/156 RMV PL BUTT | 43939119 | KILARC-CEDAR CREEK | 006/156 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-05-29 | 2022-05-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.994445 | 40.7152 | ETL.7290 | 40877862 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118817 | Mar | T2 DI CRNA MNDCNO 31 27/133 RPR FOUND |  | CORTINA-MENDOCINO #1 | 027/133 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-05 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.692826 | 39.0301 | ETL.1330 | 40648763 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118839 | Not Scheduled | T3 DI ROND MTN-CTTNWD #3 33/285 RPL HRDT | 43932111 | ROUND MTN-COTTONWOOD #3 | 033/285 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.003174 | 40.7145 | ETL.5650 | 40758845 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118853 | Q2 | T2 DI SLNS LRLS LRLS 16/316B RPR POLE |  | SALINAS-LAURELES | 016/316B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | 2021-05-03 | 2021-05-06 | 2021-05-06 | 2021-05-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.744762 | 36.5043 | ETL.7930 | 42564785 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-31 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118877 | Mar | T2 DI KILARC-DESCHUTES 8/169 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 008/169 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2022-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.978156 | 40.5972 | ETL.7300 | 40771367 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118901 | Feb | T2 DI COLGATE-GRASS VLY 3/72 RMV PL BUTT | 44371194 | COLGATE-GRASS VALLEY | 003/072 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2022-06-03 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.135423 | 39.3213 | ETL.6490 | 40590716 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118902 | Q3 | T2 DI CARIBOU #2 4/16 RMV STEP |  | CARIBOU #2 | 004/016 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.20692 | 40.053 | ETL.6280 | 40816768 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118906 | Q2 | T2 DI TRINITY-MAPLE CREK 21/7 RMV PL BUT | 44299848 | TRINITY-MAPLE CREEK | 021/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2022-06-03 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.293377 | 40.7094 | ETL.8170 | 40803410 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118942 | Mar | T2 DI KILARC-DESCHUTES 2/55 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 002/055 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2022-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.895151 | 40.6447 | ETL.7300 | 40656957 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118953 | Feb | T2 DI CLGTE-GRSS VLLY 03/075 RMV PL BUTT | 44365323 | COLGATE-GRASS VALLEY | 003/075 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-02 | 2022-06-02 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.133715 | 39.3211 | ETL.6490 | 40768368 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118955 | Q2 | T3 DI VOLTA-DESCHUTES 003/081 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 003/081 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.93473 | 40.4767 | ETL.8290 | 40769424 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118960 | Q4 | T2 DI KESWICK-TRINITY 025/417 RPR GYWW | 43939188 | KESWICK-TRINITY | 025/417 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-05-31 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.851102 | 40.7024 | ETL.7270 | 40909460 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Scheduled Past Due | IC | Q4 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118961 | Q4 | T2 DI KSWICK-TRINITY 025/417 RMV PL BUTT | 43939188 | KESWICK-TRINITY | 025/417 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-02 | 2022-06-02 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.851102 | 40.7024 | ETL.7270 | 40909460 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119118996 | Feb | T2 DI COLGATE-GRASS VLY 2/61 REFRAME | 31507018 | COLGATE-GRASS VALLEY | 002/061 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.143277 | 39.322 | ETL.6490 | 40818452 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119002 | Mar | T2 DI KLRC DSCHTS 7/151 RPL POLE | 31507070 | KILARC-DESCHUTES | 007/151 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.966776 | 40.6064 | ETL.7300 | 40816220 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119003 | Mar | T2 DI KLRC DSCHTS 7/151 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 007/151 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.966776 | 40.6064 | ETL.7300 | 40816220 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119005 | Mar | T2 DI KLRC DSCHTS A23/493 RPR GYWW | 43930440 | KILARC-DESCHUTES | A023/493 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.253713 | 40.5639 | ETL.7300 | 44141990 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119038 | Q2 | T3 DI VOLTA-DESCHUTES 004/090 RPR STRW | 43939089 | VOLTA-DESCHUTES | 004/090 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.942033 | 40.4784 | ETL.8290 | 40669476 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119050 | Q2 | T2 DI CLGT SMTVLL #2 8/97 RPL POLE | 31511059 | COLGATE-SMARTVILLE #2 | 008/097 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-06-19 | 2021-05-31 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.293653 | 39.2435 | ETL.6520 | 40826284 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119058 | Q2 | T2 DI LAURELES-OTTER 1/4 RPR WDPKR | 44587870 | LAURELES-OTTER | 001/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.713582 | 36.4656 | ETL.7380 | 40769033 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119059 | Feb | T2 DI CLGT GRSS VLLY 0/10 RPL POLE | 31507019 | COLGATE-GRASS VALLEY | 000/010 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.181937 | 39.3278 | ETL.6490 | 40868924 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119078 | Q2 | T2 DI TRINITY-MAPLE CRK 15/1 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 015/001 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-02 | 2022-06-02 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.176107 | 40.7469 | ETL.8170 | 40579624 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119084 | Feb | T2 DI COLGTE-GRSS VLY 004/109 RPR SPLICE | 44365328 | COLGATE-GRASS VALLEY | 004/109 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.114985 | 39.3144 | ETL.6490 | 40696032 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119089 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 004/119 RPR POLE | 44346079 | COLGATE-ALLEGHANY | 004/119 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.108663 | 39.328 | ETL.6470 | 40874807 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119092 | Mar | T3NT DI DRM-GRSS VLY-WIM 8/201 RMV BUTT | 44364845 | DRUM-GRASS VALLEY-WEIMAR | 008/201 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-28 | 2022-05-28 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.855296 | 39.185 | ETL.6760 | 40874779 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119111 | Mar | T3 DI KILARC-DESCHUTES 0/12 REFRAME CRSW | 43930440 | KILARC-DESCHUTES | 000/012 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.87414 | 40.6701 | ETL.7300 | 40656952 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119118 | Q2 | T2 DI LAURELES-OTTER 1/3 RPL INSW | 31507239 | LAURELES-OTTER | 001/003 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.712631 | 36.4665 | ETL.7380 | 40697709 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-06-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119126 | Not Scheduled | T2 DI DIABLO MESA 5/27 RPL INSS | 31510098 | DIABLO-MESA | 005/027 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.772358 | 35.3274 | ETL.4620 | 40835757 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-01 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119132 | Q2 | T3 DI VOLTA-DESCHUTES 006/130 RPL CRSW | 31505200 | VOLTA-DESCHUTES | 006/130 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2020-12-02 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.97745 | 40.4873 | ETL.8290 | 40700066 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119139 | Not Scheduled | T3 DI FULTON-CALISTOGA :8/0 RPR STRW | 44597303 | FULTON-CALISTOGA | :008/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.59817 | 38.6996 | ETL.6880 | 40912490 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119149 | Not Scheduled | T2 DI CAYUCOS-CAMBRIA 18/131 RPR GYWW |  | CAYUCOS-CAMBRIA | 018/131 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.107473 | 35.5977 | ETL.8560 | 40606220 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119162 | Not Scheduled | T3 DI BRUNSWICK #1 TAP 0/6 RPR FOND | 44370736 | BRUNSWICK #1 TAP | 000/006 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2022-06-04 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.012471 | 39.1503 | ETL.1422 | 40822534 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119163 | Q2 | T3NT DI DRUM-SPAULDING 3/82 RMV BUTT | 44364848 | DRUM-SPAULDING | 003/082 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-04 | 2022-06-04 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.724231 | 39.281 | ETL.6770 | 40769530 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119164 | Q2 | T3 DI DRUM-SPAULDING 3/82 RPR STRW | 44364850 | DRUM-SPAULDING | 003/082 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.724231 | 39.281 | ETL.6770 | 40769530 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119184 | Q2 | T3 DI VOLTA DESCHUTES 3/69 RPR STRW | 43939089 | VOLTA-DESCHUTES | 003/069 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.924482 | 40.4741 | ETL.8290 | 40667432 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119186 | Q2 | T2 DI CLGT SMTVLL #2 8/98 RPL POLE | 31511059 | COLGATE-SMARTVILLE #2 | 008/098 | 70Y | E | 2020_(1a) PSPS |  | 2020-06-03 | 2021-06-03 |  |  | 2021-06-19 | 2021-05-31 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.294848 | 39.2409 | ETL.6520 | 40864688 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119119189 | Not Scheduled | T2 DI TRNTY-MPLE CRK 18/5 CANCEL | 44299848 | TRINITY-MAPLE CREEK | 018/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2022-06-03 | [6 empty] | CANCEL/CNCL | TR2 |  | North Coast | WSIP | [6 empty] | '-123.23111 | 40.7365 | ETL.8170 | 40761915 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119210 | Q2 | T3 DI DRUM-SPAULDING 2/65 RPL STRW | 31529083 | DRUM-SPAULDING | 002/065 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.733517 | 39.273 | ETL.6770 | 40616113 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119221 | Not Scheduled | DI CAYUCOS-CAMBRIA 009/057 RPl XARM | 31507414 | CAYUCOS-CAMBRIA | 009/057 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | [9 empty] | South | WSIP | [8 empty] | ETL.8560 | 44171797 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119239 | Mar | T3 DI DRUM-RIO OSO #2 003/032 RMV HRDT | 44361673 | DRUM-RIO OSO #2 | 003/032 | ICS | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2020-11-22 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.818817 | 39.2423 | ETL.1430 | 40672175 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119243 | Q2 | T3 DI VOLTA DESCHUTES 5/122 RPL STRW | 31507067 | VOLTA-DESCHUTES | 005/122 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.969607 | 40.4853 | ETL.8290 | 40770155 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119253 | Mar | T3 DI DRUM-HIGGINS 07/72 RPL INSL | 31506971 | DRUM-HIGGINS | 007/072 | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.85979 | 39.1898 | ETL.4393 | 40725218 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119294 | Mar | T3 DI MORAGA-SN LEANDRO #3 7/50 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 007/050 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2020-12-04 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.113789 | 37.7534 | ETL.2790 | 40587933 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119330 | Q2 | T2 DI TRNTY-MPLE CRK 31/4 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 031/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-03 | 2022-06-03 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.484549 | 40.6899 | ETL.8170 | 40906467 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119333 | Q2 | T3 DI VOLTA DESCHUTES 6/143 RPR STRW | 43939089 | VOLTA-DESCHUTES | 006/143 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.988507 | 40.49 | ETL.8290 | 40769428 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119335 | Q2 | T3 DI VOLTA DESCHUTES 1/35 REFRAME CRSW | 31505200 | VOLTA-DESCHUTES | 001/035 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.895788 | 40.467 | ETL.8290 | 40660885 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119336 | Q2 | T3 DI VOLTA DESCHUTES 1/35 RPR STRW | 43939089 | VOLTA-DESCHUTES | 001/035 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.895788 | 40.467 | ETL.8290 | 40660885 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119358 | Not Scheduled | T2 DI CARIBOU-PALERMO 015/121 RPR STRS |  | CARIBOU-PALERMO | 015/121 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2021-06-04 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119359 | Not Scheduled | T2 DI CARIBOU-PALERMO 015/121 RPLC HRDS |  | CARIBOU-PALERMO | 015/121 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2021-06-04 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119411 | Q3 | T3NT DI DONNELLS-MI-WUK 8/0 RMV BUTT | 44467328 | DONNELLS-CURTIS | 008/000 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-02 | 2022-06-02 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.102319 | 38.1641 | ETL.1400 | 40580189 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119412 | Q3 | T3 DI DONNELLS-MI-WUK 8/0 RPR STRW | 44623218 | DONNELLS-CURTIS | 008/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-02 | 2020-12-02 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.102319 | 38.1641 | ETL.1400 | 40580189 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 | USFS | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119414 | Q2 | T3 DI PIT #1-CTTONWOD 034/293 RMV DEBRIS | 43879413 | PIT #1-COTTONWOOD | 034/293 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2022-06-01 |  |  | 2021-05-31 | 2021-05-17 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-122.01155 | 40.7041 | ETL.5390 | 40657359 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119419 | Feb | T2 DI COLGATE-GRASS VALLY 1/44 RPR WDPKR | 44365328 | COLGATE-GRASS VALLEY | 001/044 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.155927 | 39.3232 | ETL.6490 | 40599479 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119420 | Not Scheduled | T2NT DI CARIBOU-PALRMO 15/121 RMV DEBRIS |  | CARIBOU-PALERMO | 015/121 | ICS | F | 2020_(3) On high spread structure |  | 2020-06-04 | 2022-06-04 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119436 | Not Scheduled | T3NT DI CLGT-ALLGHNY 8/231 RMV BUTT | 44356570 | COLGATE-ALLEGHANY | 008/231 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-01 | 2022-06-01 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.049275 | 39.365 | ETL.6470 | 40602502 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119510 | Not Scheduled | T3NT DI CARIBOU-PLRMO :30/247 RMV DEBRIS |  | CARIBOU-PALERMO | :030/247 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2022-06-01 | [7 empty] | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.454013 | 39.7748 | ETL.3190 | 40826439 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119631 | Q2 | T2 DI TRINITY-MAPLE CREEK 7/7 RPR WDPKER | 44295371 | TRINITY-MAPLE CREEK | 007/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.055824 | 40.746 | ETL.8170 | 40906350 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119672 | Mar | T2 DI KILARC-DESCHUTES 2/51 RPL POLE | 31507070 | KILARC-DESCHUTES | 002/051 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.892542 | 40.6468 | ETL.7300 | 40876595 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119714 | Q2 | T3 DI DRUM-SPAULDING 1/31 RPL STRW | 31529084 | DRUM-SPAULDING | 001/031 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.746034 | 39.2533 | ETL.6770 | 40861931 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119813 | Q2 | T2 DI COLGATE-SMARTVLL #2 7/77 RPL POLE | 31511059 | COLGATE-SMARTVILLE #2 | 007/077 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-06-19 | 2021-05-31 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.284237 | 39.2638 | ETL.6520 | 40668758 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119818 | Q2 | T2 DI SALINAS-LAURELES 008/174 RPR GYWW | 44610150 | SALINAS-LAURELES | 008/174 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | 2021-04-05 | 2021-04-07 | 2021-04-07 | 2021-04-05 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.701152 | 36.5956 | ETL.7930 | 40613943 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 12 | CalTrans | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119819 | Q2 | T2 DI SALINAS-LAURELES 008/174 RPR WDPKR | 44610150 | SALINAS-LAURELES | 008/174 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | 2021-04-05 | 2021-04-07 | 2021-04-07 | 2021-04-05 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.701152 | 36.5956 | ETL.7930 | 40613943 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 12 | CalTrans | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119843 | Q4 | T3NT DI KESWICK-TRINITY 2/39 RMV BUTT | 43939188 | KESWICK-TRINITY | 002/039 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2022-06-04 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-122.495793 | 40.617 | ETL.7270 | 40660731 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119903 | Q4 | T3 DI KESWICK-TRINITY 1/27 RPR GYWW | 43939188 | KESWICK-TRINITY | 001/027 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.479404 | 40.6184 | ETL.7270 | 40771192 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119962 | Q2 | T2 DI LAURELES-OTTER 000/011 RPR GYWW | 44587870 | LAURELES-OTTER | 000/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-04-11 | 2021-04-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.719199 | 36.4757 | ETL.7380 | 40600142 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119964 | Q2 | T2 DI LAURELES-OTTER 000/011 RMV PL BUTT | 44587870 | LAURELES-OTTER | 000/011 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2022-06-03 |  |  | 2021-04-11 | 2021-04-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.719199 | 36.4757 | ETL.7380 | 40600142 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119972 | Q3 | T2 DI KILARC-DESCHUTES 1/28 REFRAME | 31507189 | KILARC-DESCHUTES | 001/028 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-05-31 |  |  | 2021-07-18 | 2021-06-28 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.879428 | 40.6598 | ETL.7300 | 40817199 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Released | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Scheduled Past Due | 93 | Q3 |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119119974 | Mar | T2 DI KILARC-DESCHUTES 1/28 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 001/028 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.879428 | 40.6598 | ETL.7300 | 40817199 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119120007 | Q4 | T3 DI KESWICK-TRINITY 1/27 REMV BUTT | 43939188 | KESWICK-TRINITY | 001/027 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-04 | 2020-12-04 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.479404 | 40.6184 | ETL.7270 | 40771192 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119120028 | Q2 | T2 DI LAURELES-OTTER 2/0 RPR WDPKER | 44587870 | LAURELES-OTTER | 002/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-04-11 | 2021-04-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.709893 | 36.4588 | ETL.7380 | 40589527 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119120045 | Q2 | T2 DI SALINAS-LAURELES 007/154 RPR WDPKR | 44578873 | SALINAS-LAURELES | 007/154 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2021-05-10 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.690779 | 36.609 | ETL.7930 | 40594149 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119120046 | Q2 | T2 DI TRINITY-MAPLE CREK 47/18 RPR WDPKR | 44295371 | TRINITY-MAPLE CREEK | 047/018 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.765662 | 40.7517 | ETL.8170 | 40861543 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119120136 | Mar | T2 DI KILARC-DESCHUTES 3/65 RPR WDPKR | 43930440 | KILARC-DESCHUTES | 003/065 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.901174 | 40.6398 | ETL.7300 | 40676474 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119120369 | Q2 | T2 DI TRINITY-MPL CRK 52/0(C) RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 052/000B | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.838427 | 40.7673 | ETL.8170 | 40588804 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119121210 | Q3 | T2 DI CARIBOU #2 4/21 REMV DEBRIS |  | CARIBOU #2 | 004/021 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2022-06-03 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.2105 | 40.0512 | ETL.6280 | 44738173 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119122053 | Q3 | T2 DI CARIBOU #2 4/21 RMV STEP |  | CARIBOU #2 | 004/021 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.2105 | 40.0512 | ETL.6280 | 44738173 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119122056 | Feb | T3 DI KILARC-CEDAR CRK 4/105 RPR GYWW | 43939119 | KILARC-CEDAR CREEK | 004/105 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.955008 | 40.7033 | ETL.7290 | 40677172 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119122059 | Feb | T3NT DI KILARC-CEDR 4/105 RPL GMKW | 43939119 | KILARC-CEDAR CREEK | 004/105 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-29 | 2022-05-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.955008 | 40.7033 | ETL.7290 | 40677172 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119122094 | Feb | T2 DI COLGATE-GRS VLLY 8/186 RMV PL BUTT | 44365323 | COLGATE-GRASS VALLEY | 008/186 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-02 | 2022-06-02 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.089112 | 39.2665 | ETL.6490 | 40613018 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119122146 | Feb | T2 DI CLGTE-GRSS VLLY 8/201 RMV DEBRIS | 44371194 | COLGATE-GRASS VALLEY | 008/201 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2022-06-03 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.086527 | 39.2584 | ETL.6490 | 40767728 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119122234 | Feb | T3 DI KILARC-CEDAR CREEK 4/105 REMV STUB | 43939119 | KILARC-CEDAR CREEK | 004/105 | ICW | E | 2020_(3) On high spread structure |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.955008 | 40.7033 | ETL.7290 | 40677172 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119122255 | Q2 | T3 MI-WUK-CURTIS 19/005L RPL POLE | 31505692 | ETL.1073.POLE.WDPS | 019/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-08 | 2020-12-08 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.2343 | 38.0479 | ETL.1073 | 44837637 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119122909 | Not Scheduled | DI MORRO BAY-SN LS OBSP #2 0/6 RPL INSS | 31527000 | MORRO BAY-SAN LUIS OBISPO #2 | 000/006 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-06-08 | 2021-06-08 | [9 empty] | South | WSIP | [6 empty] | '-120.844636 | 35.3752 | ETL.2820 | 40838015 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119123959 | Q2 | DI GRBRVLL-LYTNVLLE 52/7B RPL INSW | 31505611 | GARBERVILLE-LAYTONVILLE | 052/007B | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-08 | 2021-06-06 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.639329 | 40.0584 | ETL.8365 | 40922396 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119124061 | Q2 | DI GRBRVLL-LYTNVLLE 52/7B BOND GUY | 44311204 | GARBERVILLE-LAYTONVILLE | 052/007B | ICW | E | 2020_(3) On high spread structure |  | 2020-06-08 | 2021-06-08 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.639329 | 40.0584 | ETL.8365 | 40912587 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119124064 | Q2 | DI GRBRVLL-LYTNVLLE 052/007C RPR CNDW | 44311204 | GARBERVILLE-LAYTONVILLE | 052/007C | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-08 | 2021-06-06 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.639287 | 40.0584 | ETL.8365 | 44404873 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119124066 | Q2 | DI GRBRVLL-LYTNVLLE 052/007C BOND GUY | 44311204 | GARBERVILLE-LAYTONVILLE | 052/007C | ICW | E | 2020_(3) On high spread structure |  | 2020-06-08 | 2021-06-08 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.639287 | 40.0584 | ETL.8365 | 44404873 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119124241 | Mar | T2 DI KILARC-DSCHUTES 10/222 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 010/222 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2022-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.01582 | 40.5777 | ETL.7300 | 40770437 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119124269 | Q2 | DI GRBRVLL-LYTNVLLE 053/009A RPR SPLW | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-08 | 2021-06-06 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650305 | 40.0705 | ETL.8365 | 40912599 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119124411 | Q2 | DI GRBRVLL-LYTNVLLE 053/009A BOND | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009A | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-08 | 2021-06-08 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650305 | 40.0705 | ETL.8365 | 40912599 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119124414 | Q2 | DI GRBRVLL-LYTNVLLE 053/009A RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-08 | 2021-06-08 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650305 | 40.0705 | ETL.8365 | 40912599 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119124873 | Q2 | T2 DI TRINITY-MPLE CREK 27/3 RPR WDPKR | 44295371 | TRINITY-MAPLE CREEK | 027/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.401149 | 40.7025 | ETL.8170 | 40906430 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119124875 | Q2 | T2 DI TRINITY-MPLE CREK 024/003 RPL SWIW | 31507468 | TRINITY-MAPLE CREEK | 024/003 | 93H | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.340098 | 40.7058 | ETL.8170 | 40906416 | Switch-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 427 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125060 | Q2 | T2 TRNTY-MPL CRK 17/1 INST CUTOUT BOX | 44470713 | TRINITY-MAPLE CREEK | 017/001 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-08 | 2021-06-08 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.20901 | 40.7414 | ETL.8170 | 43242519 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125063 | Q2 | T2 TRNTy-MPL CRK 17/1B INST CUTOUT BOX | 44470713 | TRINITY-MAPLE CREEK | 017/001B | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-08 | 2021-06-08 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.209853 | 40.7416 | ETL.8170 | 43242518 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125500 | Mar | T3NT DI DRM-GRS VLY-WMR 8/195 RMV PL BUT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 008/195 | ICW | F | 2020_(1a) PSPS |  | 2020-05-28 | 2022-05-28 |  |  | 2021-03-21 | 2021-03-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.852785 | 39.1873 | ETL.6760 | 40669956 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119125558 | Mar | T2 DI KILARC-DESCHUTES 1/24 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 001/024 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2022-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.877247 | 40.6622 | ETL.7300 | 40676466 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125559 | Mar | T2 DI KILARC-DESCHUTES 1/24 RPR WDPKR | 43930440 | KILARC-DESCHUTES | 001/024 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.877247 | 40.6622 | ETL.7300 | 40676466 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125649 | Mar | T2 DI KLRC-DSCHTS 6/134 RPR WDPKR | 43930440 | KILARC-DESCHUTES | 006/134 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.952508 | 40.6118 | ETL.7300 | 40617779 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125661 | Mar | T2 DI KILARC-DESCHUTES 4/96 REFRAME | 31507071 | KILARC-DESCHUTES | 004/096 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.922205 | 40.624 | ETL.7300 | 40656965 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125680 | Mar | T2 DI KILARC-DESCHUTS A24/512 RMV PL BUT | 43930440 | KILARC-DESCHUTES | A024/512 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.270045 | 40.5687 | ETL.7300 | 42614961 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125681 | Mar | T2 DI KLRC-DSCHTS 6/134 RPR DEBRIS | 43930440 | KILARC-DESCHUTES | 006/134 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.952508 | 40.6118 | ETL.7300 | 40617779 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125697 | Mar | T2 DI KLRC-DSCHTS 19/390 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 019/390 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.166579 | 40.5638 | ETL.7300 | 40617685 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125699 | Mar | T2 DI KLRC-DSCHTS 19/390 RPL POLE | 31507070 | KILARC-DESCHUTES | 019/390 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.166579 | 40.5638 | ETL.7300 | 40617685 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125725 | Not Scheduled | T3NT DI CRBU-PALERMO :031/256C INST GMKW |  | CARIBOU-PALERMO | :031/256C | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2022-06-01 | [7 empty] | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467814 | 39.7593 | ETL.3190 | 44374356 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125753 | Q4 | T3 DI MAPLE CREEK-HOOPA 27/6 RPR CNDW | 44178090 | MAPLE CREEK-HOOPA | 027/006 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-10-02 | 2021-07-26 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.671397 | 41.0387 | ETL.7490 | 44645848 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125770 | Feb | T3 DI KLRC-CEDAR CREEK 8/197 RPL STRW | 31506712 | KILARC-CEDAR CREEK | 008/197 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.984088 | 40.7367 | ETL.7290 | 40816384 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-06-24 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125792 | Mar | T2 DI KILARC-DSCHTS 10/207 RPL POLE | 31507070 | KILARC-DESCHUTES | 010/207 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.005468 | 40.5839 | ETL.7300 | 40600387 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125825 | Q3 | T2 DI CARIBOU #2 001/004 RMV STEPS |  | CARIBOU #2 | 001/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.1632 | 40.0765 | ETL.6280 | 40769460 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125919 | Q2 | T3 DI SLY CREEK TAP A0/7B RPR STRW | 44391954 | SLY CREEK TAP | A000/007B | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.12828 | 39.5725 | ETL.4221 | 44388061 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125933 | Mar | T2 DI KLRC-DSCHTS 7/161 RPR WDPKR | 43930440 | KILARC-DESCHUTES | 007/161 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.97324 | 40.6015 | ETL.7300 | 40816221 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125936 | Mar | T2 DI KLRC-DSCHTS 7/161 INSTALL HRDW | 43930440 | KILARC-DESCHUTES | 007/161 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.97324 | 40.6015 | ETL.7300 | 40816221 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125961 | Mar | T3 DI DEER CREEK-DRUM 002/058 RPR GYWW | 44361664 | DEER CREEK-DRUM | 002/058 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-28 | 2020-11-28 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.829188 | 39.264 | ETL.6690 | 40598802 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125964 | Q3 | T2 DI CARIBOU #2 003/015 RMV STEPS |  | CARIBOU #2 | 003/015 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.197265 | 40.0634 | ETL.6280 | 40768765 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119125965 | Not Scheduled | T3 DI MIDDLEFORK #1 004/067 RPR POLE | 44361891 | MIDDLE FORK #1 | 004/067 | ICW | E | 2020_(1a) PSPS |  | 2020-05-28 | 2020-11-28 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.654916 | 38.9986 | ETL.8405 | 40824479 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119126033 | Q2 | T3 DI LAURELES-OTTER 13/17 WASH INSW | 44610149 | LAURELES-OTTER | 013/017 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-04-02 | 2021-03-31 |  |  | Likely MAT error - delink to correct | TR3 | LATE | South | WSIP | [6 empty] | '-121.871747 | 36.3854 | ETL.7380 | 40853162 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126060 | Q3 | T2 DI CARIBOU #2 RMV STEP |  | CARIBOU #2 | 004/028 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.213725 | 40.0494 | ETL.6280 | 40868117 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126068 | Mar | T2 DI KLRC-DSCHTS 11/230 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 011/230 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.019579 | 40.5739 | ETL.7300 | 40602021 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126082 | Mar | T2 DI KLRC-DSCHTS A25/519 RPR WDPKR | 43930440 | KILARC-DESCHUTES | A025/519 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.276034 | 40.571 | ETL.7300 | 44370512 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126116 | Mar | T2 DI KLRC-DSCHTS A25/525 INSTALL MRKW | 43930440 | KILARC-DESCHUTES | A025/525 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.280805 | 40.5712 | ETL.7300 | 40826839 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126147 | Feb | T2 DI COLGATE-GRASS VLLY 0/4 RMV PL BUTT | 44365323 | COLGATE-GRASS VALLEY | 000/004 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-02 | 2022-06-02 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.187827 | 39.3292 | ETL.6490 | 40655407 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126190 | Mar | T2 DI KLARC-DSCHUTES A025/535 RMV DEBRIS | 43930440 | KILARC-DESCHUTES | A025/535 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.289595 | 40.5711 | ETL.7300 | 41118628 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126191 | Mar | T2 DI KILARC-DSCHUTES A025/535 INST MRKW | 43930440 | KILARC-DESCHUTES | A025/535 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.289595 | 40.5711 | ETL.7300 | 41118628 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126198 | Q2 | T2 DI TRNTY-MPLE CRK 019/012 RPR WDPKR | 44295371 | TRINITY-MAPLE CREEK | 019/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2021-06-04 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.259723 | 40.728 | ETL.8170 | 40660845 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126199 | Q2 | T2 DI TRNTY-MPLE CRK 019/012 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 019/012 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-04 | 2022-06-04 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.259723 | 40.728 | ETL.8170 | 40660845 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126209 | Q2 | T2 DI LAURELES-OTTER 0/15 RMV PL BUTT | 44587870 | LAURELES-OTTER | 000/015 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2022-06-03 |  |  | 2021-04-11 | 2021-04-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.717132 | 36.4721 | ETL.7380 | 40768326 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126221 | Mar | T3NT DI RAGA-SAN LEAND #3 7/53 RPR FOND |  | MORAGA-SAN LEANDRO #1 | 007/053 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-13 | 2021-03-08 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.114008 | 37.7479 | ETL.2770 | 40644212 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126226 | Q2 | T2 DI ELK-GUALALA 42/001 ANTI-SPLIT | 44610591 | ELK-GUALALA | 042/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 | 2021-05-20 | 2021-05-22 | 2021-05-20 | 2021-05-20 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.67961 | 39.0638 | ETL.8410 | 40595299 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126423 | Q2 | DI GARBERVILLE-LAYTNVLLE 53/9C BOND INSW | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009C | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-08 | 2021-06-08 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650266 | 40.0706 | ETL.8365 | 40912601 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126424 | Q2 | DI GARBERVILLE-LAYTNVLLE 53/9C RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009C | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-08 | 2021-06-08 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650266 | 40.0706 | ETL.8365 | 40912601 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126488 | Q2 | T2 PIT #5-ROUND MTN #1 000/002 RPL SPLS | 44345514 | PIT #5-ROUND MTN #1 | 000/002 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-09 | 2021-06-09 |  |  | 2021-06-18 | 2021-06-17 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.973862 | 40.9838 | ETL.5420 | 44148492 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126797 | Q2 | T3 DI VOLTA-DESCHUTES 1/32 REFRAME | 31505200 | VOLTA-DESCHUTES | 001/032 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.89359 | 40.4664 | ETL.8290 | 40875808 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126898 | Not Scheduled | T3 DI CRESTA-RIO OSO 012/100 RPR FOND |  | CRESTA-RIO OSO | 012/100 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2020-12-04 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.451228 | 39.7844 | ETL.4590 | 40910126 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119126985 | Mar | T3 DI BRUNSWICK #2 004/027 RPL INSS | 31506897 | BRUNSWICK #2 TAP | 004/027 | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 |  |  | 2021-03-16 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.033621 | 39.189 | ETL.1431 | 40834399 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119127025 | Not Scheduled | T3NT DI BRUNSWICK #1 001/014 RPR FOND | 44370736 | BRUNSWICK #1 TAP | 001/014 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2022-06-04 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.02581 | 39.1634 | ETL.1422 | 40751877 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119127027 | Mar | T2 DI KILARC-DESCHUTES 5/115 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 005/115 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.935512 | 40.6167 | ETL.7300 | 40602045 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119127395 | Mar | T2 DI KILARC-DSCHUTES 10/226 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 010/226 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2022-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.017692 | 40.5758 | ETL.7300 | 40876516 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  | In Review | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119127396 | Mar | T2 DI KILARC-DESCHUTES 10/226 REFRAME | 31507189 | KILARC-DESCHUTES | 010/226 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.017692 | 40.5758 | ETL.7300 | 40876516 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  | In Review | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119127402 | Mar | T3NT DI DRUM-RIO #2 10/106 INST ACG | 31507030 | DRUM-RIO OSO #2 | 010/106 | 93A | F | 2020_(3) On high spread structure |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.931791 | 39.1706 | ETL.1430 | 40815440 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119127403 | Mar | T3NT DI DRUM-RIO OSO #2 10/106 RPR FOND | 44365329 | DRUM-RIO OSO #2 | 010/106 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.931791 | 39.1706 | ETL.1430 | 40815440 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119127900 | Q2 | DI GARBERVL-LYTNVL 46/9A RPR SPLW | 44311204 | GARBERVILLE-LAYTONVILLE | 046/009A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-08 | 2021-06-06 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.625712 | 39.9779 | ETL.8365 | 40912520 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119127901 | Q2 | DI GARBERVL-LYTNVL 46/9A REPL POLE | 31506024 | GARBERVILLE-LAYTONVILLE | 046/009A | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-08 | 2021-06-06 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.625712 | 39.9779 | ETL.8365 | 40912520 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119127906 | Q2 | DI GARBERVL-LYTNVL 46/9B REPL POLE | 31506024 | GARBERVILLE-LAYTONVILLE | 046/009B | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-08 | 2021-06-08 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.625675 | 39.9778 | ETL.8365 | 40912521 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119127983 | Q2 | DI GARBERVIL-LYTNVL 46/9C REPL POLE | 31506024 | GARBERVILLE-LAYTONVILLE | 046/009C | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-08 | 2021-06-06 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.625644 | 39.9778 | ETL.8365 | 40912522 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119128221 | Not Scheduled | T3NT DI BRUNSWICK #1 TAP 2/15 RPR FOND | 44370736 | BRUNSWICK #1 TAP | 002/015 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-05 | 2022-06-05 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.028432 | 39.1644 | ETL.1422 | 40761881 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119128448 | Feb | T2 PHILO JCT-ELK 33/1 RPL ANCHOR | 31507982 | PHILO JCT-ELK | 033/001 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-09 | 2021-06-09 |  |  | 2021-02-11 | 2021-02-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.646385 | 39.1331 | ETL.7780 | 40595293 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-07-23 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119128506 | Feb | T2 PHILO JCT-ELK 30/8 RPL POLE | 31507793 | PHILO JCT-ELK | 030/008B | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-09 | 2021-06-09 |  |  | 2021-02-10 | 2021-02-10 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.610159 | 39.1238 | ETL.7780 | 40876300 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-07-23 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119128588 | Q2 | T2 LAYTONVILLE-WILLITS 8/0 RPL POLE | 31507792 | LAYTONVILLE-WILLITS | 008/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-09 | 2021-06-09 | 2021-05-26 | 2021-05-28 | 2021-05-28 | 2021-05-28 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.373378 | 39.5027 | ETL.8360 | 40613352 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119128616 | Q2 | T2 HUMBOLDT-MAPLE CREEK 7/7 RPL SWITCH | 31508148 | HUMBOLDT-MAPLE CREEK | 007/007 | 93S | E | 2020_(4) TD tag on high spread line |  | 2020-06-09 | 2021-06-09 |  |  | 2021-06-19 | 2021-06-14 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.989915 | 40.7576 | ETL.7130 | 40825283 | Switch-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 435 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119129092 | Mar | T2 DI KESWICK-CASCADE A025/526 RPL POLE | 31507070 | KILARC-DESCHUTES | A025/526 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.281421 | 40.5712 | ETL.7300 | 40870146 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119129094 | Mar | T2 DI KESWICK-CSCADE A025/526 RMV PL BUT | 43930440 | KILARC-DESCHUTES | A025/526 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.281421 | 40.5712 | ETL.7300 | 40870146 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119129381 | Mar | T3NT DI MRGA-SAN LENDRO #3 7/52 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 007/052 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.113802 | 37.7479 | ETL.2790 | 40646083 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119129384 | Q2 | DI GARBERVILLE-LYTNVLL 45/8 RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 045/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-09 | 2021-06-07 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.617512 | 39.967 | ETL.8365 | 40912509 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119129387 | Q2 | DI GARBERVILLE-LYTNVLL 46/2 RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 046/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-08 | 2021-06-06 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.620364 | 39.9704 | ETL.8365 | 40912512 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119129482 | Not Scheduled | T2 DI CLGT-SMRTVLL#2 7/75 CANCEL | 44356572 | COLGATE-SMARTVILLE #2 | 007/075 | ICW | E | 2020_(1a) PSPS |  | 2020-06-09 | 2021-06-09 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.283702 | 39.265 | ETL.6520 | 40602344 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119129576 | Mar | T2 DI KILARC-DESCHUTES 7/146 REFRAME | 31507071 | KILARC-DESCHUTES | 007/146 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.962545 | 40.608 | ETL.7300 | 40701866 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119129835 | Q2 | T2 TRINITY-MAPLE CREEK 37/10 INST DAMPER | 44273074 | TRINITY-MAPLE CREEK | 037/010 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-09 | 2021-06-09 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.588286 | 40.7115 | ETL.8170 | 40617876 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119129967 | Mar | T2 DI KILARC-DESCHUTS A24/502 RMV PL BUT | 43930440 | KILARC-DESCHUTES | A024/502 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.262354 | 40.5658 | ETL.7300 | 44141993 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119130039 | Feb | T2 DI TRINITY-MPLE CRK 2/12 RPR WDPKR | 44295371 | TRINITY-MAPLE CREEK | 002/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 | 2021-02-22 | 2021-02-27 | 2021-02-24 | 2021-02-24 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.976392 | 40.7347 | ETL.8170 | 40906274 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119130144 | Q4 | T3NT DI KESWICK-TRINITY 2/43 RMV BUTT | 43939188 | KESWICK-TRINITY | 002/043 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2022-06-04 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-122.50221 | 40.6165 | ETL.7270 | 40752197 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119130232 | Q4 | T3 DI KESWICK-TRINITY 2/43 RPR GYWW | 43939188 | KESWICK-TRINITY | 002/043 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2020-12-04 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.50221 | 40.6165 | ETL.7270 | 40752197 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119130276 | Mar | T2 DI KILARC-DESCHUTS A24/511 RMV PL BUT | 43930440 | KILARC-DESCHUTES | A024/511 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.26923 | 40.5684 | ETL.7300 | 40669390 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119130280 | Mar | T2 DI KILARC-DESCHUTES 19/401 RMV PL BUT | 43930440 | KILARC-DESCHUTES | 019/401 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.176237 | 40.5638 | ETL.7300 | 40602004 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119130281 | Mar | T2 DI KILARC-DESCHUTES 19/401 RPR WDPKR | 43930440 | KILARC-DESCHUTES | 019/401 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.176237 | 40.5638 | ETL.7300 | 40602004 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119130344 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 10/131 RPL INS | 31507662 | DIVIDE-CABRILLO #2 | 010/131 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-09 | 2021-06-09 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4365167 | 34.6784 | ETL.1370 | 40901477 | Insulator-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119130433 | Mar | T3 DI DRUM-RIO OSO #1 0/5 RPL HRDT | 44371587 | DRUM-RIO OSO #1 | 000/005 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.778322 | 39.2568 | ETL.1420 | 40756197 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119130529 | Not Scheduled | T2 DI CARIBOU-PALERMO 012/106 RPR SPLS |  | CARIBOU-PALERMO | 012/106 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 | [7 empty] | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.510269 | 39.6405 | ETL.3190 | 40841210 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119130667 | Mar | T2 DI KLRC-DSCHTS A25/521 INS MRKW | 43930440 | KILARC-DESCHUTES | A025/521 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.277172 | 40.5712 | ETL.7300 | 44843914 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119130676 | Not Scheduled | T3 DI CRESTA-RIO OSO 016/138 BURIED STUB |  | CRESTA-RIO OSO | 016/138 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2020-12-04 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.479364 | 39.7282 | ETL.4590 | 40910154 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119130800 | Not Scheduled | T3 DI CRESTA-RIO OSO 016/138 RMV STEPS |  | CRESTA-RIO OSO | 016/138 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2020-12-04 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.479364 | 39.7282 | ETL.4590 | 40910154 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119130951 | Mar | T2 DI KILARC-DESCHUTS A24/504 RMV PL BUT | 43930440 | KILARC-DESCHUTES | A024/504 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.263563 | 40.5663 | ETL.7300 | 44141994 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119131164 | Mar | T2 DI KILARC-DESCHUTS 10/228 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 010/228 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-06 | 2022-06-06 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.018676 | 40.5748 | ETL.7300 | 40602020 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119131349 | Mar | T2 DI KILARC-DESCHUT 18/387 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 018/387 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.163639 | 40.5638 | ETL.7300 | 40868583 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119131404 | Mar | T3 DI SBRNT-GRZLY-CRMT #2 5/35F RPL INSS | 31511124 | SOBRANTE-GRIZLY-CLARMNT #2+ | 005/035F | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-05 | 2020-12-05 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.189586 | 37.8587 | ETL.3750 | 42582067 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132014 | Q2 | T2 MI-WUK-CURTIS 023/001 RPL POLE | 31516010 | ETL.1073.POLE.WDPS | 023/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-09 | 2021-06-09 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.26918 | 38.0053 | ETL.1073 | 44774786 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132043 | Q3 | T2 CRIBU-PLUMS JCT 11/012 RPL ANCHOR | 31507980 | CARIBOU-PLUMAS JCT | 011/012 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-09 | 2021-06-09 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.993768 | 39.9803 | ETL.6290 | 40675220 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132055 | Q2 | DI GRBRVLLE-LYTNVLL 33/000A REPL POLE | 31454647 | GARBERVILLE-LAYTONVILLE | 033/000A | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-09 | 2021-06-07 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.553759 | 39.8113 | ETL.8365 | 40906579 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132074 | Q2 | T3NT DI DRUM-SPAULDING 001/035 RMV BUTT | 44364848 | DRUM-SPAULDING | 001/035 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-04 | 2022-06-04 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.744388 | 39.2557 | ETL.6770 | 40667536 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132075 | Q2 | T3 DI DRUM-SPAULDING 001/035 RPL STRW | 31529083 | DRUM-SPAULDING | 001/035 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.744388 | 39.2557 | ETL.6770 | 40667536 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132076 | Q2 | T2 DI LAURELES-OTTER 2/14 RMV PL BUTT | 44587870 | LAURELES-OTTER | 002/014 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2022-06-03 |  |  | 2021-04-11 | 2021-04-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.715685 | 36.4489 | ETL.7380 | 40758134 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132078 | Feb | T3 DI BRUNSWICK #1 TAP 002/019 RPR INSS | 44370738 | BRUNSWICK #1 TAP | 002/019 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2020-12-04 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.034465 | 39.1705 | ETL.1422 | 40878323 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132079 | Q2 | T3 DI VOLTA-DESCHUTES 2/53 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 002/053 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.910683 | 40.4706 | ETL.8290 | 40877079 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132125 | Q2 | DI GRBRVLLE-LYTNVLL 33/000C REPL POLE | 31454647 | GARBERVILLE-LAYTONVILLE | 033/000C | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-09 | 2021-06-09 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.553734 | 39.8114 | ETL.8365 | 40906581 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132170 | Q2 | T3 DI VOLTA-DESCHUTES 2/53 REFRAME XARM | 31505200 | VOLTA-DESCHUTES | 002/053 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.910683 | 40.4706 | ETL.8290 | 40877079 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132173 | Mar | T2 DI KILARC-DESCHUTES 3/082 RPR WDPKR | 43930440 | KILARC-DESCHUTES | 003/082 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.912913 | 40.6311 | ETL.7300 | 40876560 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132174 | Not Scheduled | T2 DI COLGTE-SMRTVLLE #2 4/48 RMV DEBRIS | 44365321 | COLGATE-SMARTVILLE #2 | 004/048 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-02 | 2022-06-02 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.249613 | 39.2975 | ETL.6520 | 40602850 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132176 | Not Scheduled | T2 DI COLGTE-SMRTVLLE #2 4/48 RPR GYWW | 44365320 | COLGATE-SMARTVILLE #2 | 004/048 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.249613 | 39.2975 | ETL.6520 | 40602850 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132178 | Not Scheduled | T2 DI CLGTE-SMARTVILL #2 4/53 RPR GYWW | 44365320 | COLGATE-SMARTVILLE #2 | 004/053 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.25539 | 39.2909 | ETL.6520 | 40828771 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132301 | Mar | T2 DI KILARC-DESCHUTES 004/101 REFRAME | 31507189 | KILARC-DESCHUTES | 004/101 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.924884 | 40.6218 | ETL.7300 | 40576630 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132309 | Mar | T3 DI SBRNTE-GRZLY-CLRMNT #2 RPL INSS | 31511124 | SOBRANTE-GRIZLY-CLARMNT #2+ | 005/035G | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-05 | 2020-12-05 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.191071 | 37.8599 | ETL.3750 | 42582069 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132424 | Mar | T2 DI KILARC-DSCHUTS A024/505 RMV PL BUT | 43930440 | KILARC-DESCHUTES | A024/505 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.264401 | 40.5666 | ETL.7300 | 44141995 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132427 | Mar | T2 DI KILARC-DESCHUTES 04/102 INS MRKW | 43930440 | KILARC-DESCHUTES | 004/102 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.925319 | 40.6214 | ETL.7300 | 40877898 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132550 | Q2 | T3 DI VOLTA-DESCHTS 5/113 REFRAME CRSW | 31505200 | VOLTA-DESCHUTES | 005/113 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.961882 | 40.4834 | ETL.8290 | 40759051 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132590 | Q2 | T3NT DI DRUM-SPAULDING 5/128 RMV DEBRIS | 44364848 | DRUM-SPAULDING | 005/128 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-04 | 2022-06-04 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.702731 | 39.2971 | ETL.6770 | 40810149 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132592 | Q2 | T3 DI DRUM-SPAULDING 005/128 RPL HRDW | 44364850 | DRUM-SPAULDING | 005/128 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.702731 | 39.2971 | ETL.6770 | 40810149 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119132596 | Feb | T3 DI PITTSBURG-SAN MATEO 11/47 PRL INSS | 31511125 | PITTSBURG-SAN MATEO | 011/047 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2020-12-04 |  |  | 2021-02-16 | 2021-02-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.881233 | 37.8771 | ETL.5463 | 40724040 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119140015 | Q2 | T2 DI TRINITY-MAPLE CREEK 45/1 RPL POLE | 31506143 | TRINITY-MAPLE CREEK | 045/001 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.711755 | 40.749 | ETL.8170 | 40585387 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119140060 | Q2 | T3NT DI FULTON-IGNACIO #1 16/84 RPR FOND | 44310479 | FULTON-IGNACIO #1 | 016/084 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2022-05-29 |  |  | 2021-04-23 | 2021-04-19 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592277 | 38.3936 | ETL.4680 | 40753541 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119140103 | Q2 | T2 DI TRINITY-MAPLE CRK 27/2A RPR GYWW | 44364310 | TRINITY-MAPLE CREEK | 027/002A | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.399461 | 40.7034 | ETL.8170 | 40906429 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119141021 | Q2 | T2 DI TRINITY-MAPLE CREEK 24/7 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 024/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-05 | 2021-06-05 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.348963 | 40.705 | ETL.8170 | 40906418 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119141085 | Q2 | T3NT DI VOLTA-DESCHUTES 3/84 RMV PL BUTT | 43939089 | VOLTA-DESCHUTES | 003/084 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2022-06-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.937202 | 40.4772 | ETL.8290 | 40868506 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119141269 | Q2 | T2 DI TRINITY-MPL CRK 35/2 RPL HRDW | 44273074 | TRINITY-MAPLE CREEK | 035/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.546067 | 40.7204 | ETL.8170 | 40701816 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119141328 | Q2 | GARBERVILLE-LAYTONVILLE 52/005 RPL POLE | 31462488 | GARBERVILLE-LAYTONVILLE | 052/005 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-10 | 2021-06-10 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6394 | 40.0563 | ETL.8365 | 40912585 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119141671 | Q2 | T2DI TRINITY-MAPLE CRK 27/2 REPLACE POLE | 31507467 | TRINITY-MAPLE CREEK | 027/002 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 40913390 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119141811 | Q2 | T2 DI TRINITY-MAPLE CRK 27/2 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 027/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-03 | 2022-06-03 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.398882 | 40.7037 | ETL.8170 | 40903784 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119142129 | Q2 | DI GARBRVILLE-LAYTONVLL 61/5 RMV PL BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 061/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-08 | 2022-06-08 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.767368 | 40.1126 | ETL.8365 | 40912694 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119142479 | Q2 | DI GARBRVILLE-LAYTONVLLE 53/9B RPL HRDW | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009B | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-08 | 2021-06-08 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650284 | 40.0706 | ETL.8365 | 40912600 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119142537 | Q2 | DI GARBRVILLE-LAYTONVLLE 53/9B RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-08 | 2021-06-08 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650284 | 40.0706 | ETL.8365 | 40912600 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119142551 | Not Scheduled | EI T3NT SLO-SANTA MARIA 14/249 IDLE |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 014/249 | 93J | F | 2020_(2) High fire spread TD |  | 2020-06-10 | 2022-06-10 | [5 empty] | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.507827 | 35.1122 | ETL.9100 | 44191390 | Structure-Wood | Idle | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119142774 | Not Scheduled | EI T3NT SLO-SANTA MARIA 14/248 IDLE |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 014/248 | 93J | F | 2020_(2) High fire spread TD |  | 2020-06-10 | 2022-06-10 | [5 empty] | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.508072 | 35.1131 | ETL.9100 | 44191389 | Structure-Wood | Idle | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119142858 | Not Scheduled | DI HUMBOLDT-BRIDGEVILLE 89/1 RPR FOND | 44623121 | HUMBOLDT-BRIDGEVILLE | 089/001 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-05 | 2022-06-05 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.82476 | 40.5127 | ETL.1810 | 44321392 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119142976 | Q2 | DI GARBERVILLE-LAYTONVILLE 34/4 RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 034/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-08 | 2021-06-08 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.570625 | 39.8278 | ETL.8365 | 40761558 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119143033 | Not Scheduled | DI DRUM-GRSS VLLY-WMR B18/412 CANCEL | 44379030 | DRUM-GRASS VALLEY-WEIMAR | B018/412 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-05 | 2021-06-05 | [6 empty] | CANCEL/CNCL |  |  | North Valley | WSIP | [6 empty] | '-120.973599 | 39.1486 | ETL.6760 | 40757033 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119143042 | Not Scheduled | EI T3NT SLO-SANTA MARIA 14/247 IDLE |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 014/247 | 93J | F | 2020_(2) High fire spread TD |  | 2020-06-10 | 2022-06-10 | [5 empty] | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.508518 | 35.1147 | ETL.9100 | 44191392 | Structure-Wood | Idle | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119143912 | Mar | T2 DI CORTINA-MENDO #1 28/137 INST STEP | 44238817 | CORTINA-MENDOCINO #1 | 028/137 | ICQ | E | 2020_(3) On high spread structure |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-05 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.708607 | 39.0337 | ETL.1330 | 40808527 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119144575 | Mar | T2 DI KILARC-DESCHUTES 2/59 RPR WDPKR | 43930440 | KILARC-DESCHUTES | 002/059 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-09 | 2021-06-09 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.897062 | 40.6432 | ETL.7300 | 40828003 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119144644 | Mar | T2 DI KLRC-DESCHUTES A024/501 RPR GYWW | 43930440 | KILARC-DESCHUTES | A024/501 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.261792 | 40.5656 | ETL.7300 | 40651306 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119144673 | Mar | T2 DI KILARC-DESCHUTES A02/487 REFRAME | 31507071 | KILARC-DESCHUTES | A023/487 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.249152 | 40.5638 | ETL.7300 | 40865088 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119144701 | Mar | T2 DI KILARC-DSCHUTES 11/232 CANCEL | 43930440 | KILARC-DESCHUTES | 011/232 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-03 | 2022-06-03 |  |  | 2021-03-26 | 2021-03-01 |  |  | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-122.020382 | 40.5726 | ETL.7300 | 40668435 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119144743 | Q2 | T2 DI TRINITY-MPLE CREEK 19/13 RPR WDPKR | 44295371 | TRINITY-MAPLE CREEK | 019/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.260686 | 40.7273 | ETL.8170 | 40650357 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119144745 | Mar | T2 DI KILARC-DESCHUTS 20/414 RMV PL BUT | 43930440 | KILARC-DESCHUTES | 020/414 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.189564 | 40.5637 | ETL.7300 | 40771242 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119144885 | Q2 | T2 DI CNTRVL TBL MTN ORO 8/158 RPL POLE | 31507074 | CENTERVILLE-TABLE MTN-OROVILLE | 008/158 | 70Y | E | 2020_(1a) PSPS |  | 2020-06-02 | 2021-06-02 |  |  | 2021-05-30 | 2021-05-30 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.636302 | 39.6755 | ETL.6330 | 40664412 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-27 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119144906 | Q2 | DI STANISLAUS-MANTECA %2 27/162 RPR STRT |  | STANISLAUS-MANTECA #2 | 027/162 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-06-09 | 2021-06-09 |  |  | 2021-04-01 | 2021-03-18 | [5 empty] | Central | WSIP | [6 empty] | '-120.776389 | 37.9211 | ETL.3820 | 40683083 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 26 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-01 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119145637 | Q2 | T2 DI TRINITY-MAPLE CRK 5/2 RPL HRDW | 44273074 | TRINITY-MAPLE CREEK | 005/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-03 | 2021-06-03 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.0264 | 40.733 | ETL.8170 | 40906319 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119145936 | Not Scheduled | EI T3NT SLO-SANTA MARIA 14/245 IDLE |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 014/245 | 93J | F | 2020_(2) High fire spread TD |  | 2020-06-11 | 2022-06-11 | [5 empty] | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.509191 | 35.1172 | ETL.9100 | 44191387 | Structure-Wood | Idle | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119146000 | Not Scheduled | EI T3NT SLO-SANTA MARIA 14/246 IDLE |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 014/246 | 93J | F | 2020_(2) High fire spread TD |  | 2020-06-11 | 2022-06-11 | [5 empty] | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.509095 | 35.1169 | ETL.9100 | 44191391 | Structure-Wood | Idle | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119146173 | Not Scheduled | T2 DI SN LUS OBSPO-CYUCS 17/154 RPR GYWW |  | SAN LUIS OBISPO-CAYUCOS | 017/154 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-05 | 2021-06-05 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.819742 | 35.3787 | ETL.9090 | 40597837 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-15 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119146256 | Q2 | DI SALINAS-LAURELES 5/133 RPR GYWW | 44578873 | SALINAS-LAURELES | 005/133 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-05 | 2021-06-05 | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2021-05-10 | [5 empty] | South | WSIP | [6 empty] | '-121.684318 | 36.6233 | ETL.7930 | 40697410 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119146632 | Q2 | T2 DI FORT ROSS-GUALLA 50/6 RMV PLE BUTT |  | GUALALA-MONTE RIO | 050/006 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-07 | 2022-05-07 | 2021-06-07 | 2021-06-14 | 2021-06-11 | 2021-06-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.414692 | 38.7259 | ETL.6980 | 40821495 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119146774 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 6/074 RPL INSW | 31506526 | DIVIDE-CABRILLO #2 | 006/074 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2021-06-11 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4333782 | 34.7434 | ETL.1370 | 40641796 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119146834 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 5/072 RPL INSW | 31506526 | DIVIDE-CABRILLO #2 | 005/072 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2021-06-11 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.43325 | 34.7472 | ETL.1370 | 40828426 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119147087 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 5/071 RPL INSW | 31506526 | DIVIDE-CABRILLO #2 | 005/071 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2021-06-11 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.433227 | 34.748 | ETL.1370 | 40757950 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119147977 | Not Scheduled | EI T3NT SLO-SANTA MARIA 13/234 IDLE |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/234 | 93J | F | 2020_(2) High fire spread TD |  | 2020-06-11 | 2022-06-11 | [5 empty] | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.51055 | 35.1261 | ETL.9100 | 44191937 | Structure-Wood | Idle | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119148118 | Not Scheduled | EI T3NT SLO-SANTA MARIA 13/235 IDLE |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/235 | 93J | F | 2020_(2) High fire spread TD |  | 2020-06-11 | 2022-06-11 | [5 empty] | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.510605 | 35.126 | ETL.9100 | 44772564 | Structure-Wood | Idle | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119148251 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 09/108 RPL POLE | 31508019 | DIVIDE-CABRILLO #2 | 009/108 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2021-06-11 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436466 | 34.6985 | ETL.1370 | 40673885 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119148330 | Not Scheduled | EI T3NT SLO-SANTA MARIA 13/236 IDLE |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/236 | 93J | F | 2020_(2) High fire spread TD |  | 2020-06-11 | 2022-06-11 | [5 empty] | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.510879 | 35.1255 | ETL.9100 | 44191949 | Structure-Wood | Idle | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119148396 | Mar | T2 DI KILARC-DESCHUTES 18/385 RPL POLE | 31507070 | KILARC-DESCHUTES | 018/385 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.161748 | 40.5638 | ETL.7300 | 40817236 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-06-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119148398 | Mar | T2 DI KILARC-DSCHTS 18/385 RMV BUTT CNCL | 43930440 | KILARC-DESCHUTES | 018/385 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2022-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-122.161748 | 40.5638 | ETL.7300 | 40817236 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119148469 | Q2 | T3 DI DRUM-SPAULDING 4/106 RPL STRW | 31529083 | DRUM-SPAULDING | 004/106 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.707529 | 39.2879 | ETL.6770 | 40810147 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119148610 | Not Scheduled | EI T3NT SLO-SANTA MARIA 13/237 IDLE |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/237 | 93J | F | 2020_(2) High fire spread TD |  | 2020-06-11 | 2022-06-11 | [5 empty] | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.51069 | 35.1246 | ETL.9100 | 44191897 | Structure-Wood | Idle | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119148945 | Q2 | T3 EAGL RCK-FLTN-SLVRD 1/10 RPR MEMBER |  | EAGLE ROCK-FULTON-SILVERADO | 001/010 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2020-12-11 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.800903 | 38.8166 | ETL.4392 | 40605188 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119148978 | Not Scheduled | EI T3NT SLO-SANTA MARIA 13/238 IDLE |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/238 | 93J | F | 2020_(2) High fire spread TD |  | 2020-06-11 | 2022-06-11 | [5 empty] | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.510343 | 35.1233 | ETL.9100 | 44191410 | Structure-Wood | Idle | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119149184 | Not Scheduled | EI T3NT SLO-SANTA MARIA 13/239 IDLE |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/239 | 93J | F | 2020_(2) High fire spread TD |  | 2020-06-11 | 2022-06-11 | [5 empty] | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.510261 | 35.1229 | ETL.9100 | 44191403 | Structure-Wood | Idle | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119149213 | Not Scheduled | DI DIVIDE-CABRILLO #2 01/26 RPL POLE | 31507527 | DIVIDE-CABRILLO #2 | 001/026 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-05 | 2021-06-05 | [9 empty] | South | WSIP | [6 empty] | '-120.444748 | 34.8057 | ETL.1370 | 40618677 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119149854 | Feb | DI STNSLS-MEL SS-MNT#1 28/178 RPR SPLS | 44566008 | STANISLAUS-MELONES SS-MANTECA #1+ | 028/178 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-10 | 2021-06-10 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | Central | WSIP | [6 empty] | '-120.796253 | 37.9153 | ETL.3830 | 40803339 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 22 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119149955 | Q2 | T3 DI MORAGA-SAN LEANDR #3 7/52 RPL INSS | 31511126 | MORAGA-SAN LEANDRO #3 | 007/052 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2020-12-04 | 2021-04-01 |  | 2021-04-02 | 2021-04-01 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.113802 | 37.7479 | ETL.2790 | 40704892 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | ACRP | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119149967 | Not Scheduled | T3 EI SLO-SANTA MARIA 13/2 RMV IDLE | 31506239 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/241 | 93J | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2020-12-11 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.510259 | 35.1213 | ETL.9100 | 44191413 | Structure-Wood | Idle | Remove | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119149982 | Q3 | T3 EI SLO-SANTA MARIA 13/2 RMV VEGN |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/241 | HNA | F | 2020_(1b) Lines with special commitments |  | 2020-06-11 | 2022-06-11 |  |  | 2021-08-15 | 2021-08-01 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.510259 | 35.1213 | ETL.9100 | 44191413 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119149985 | Not Scheduled | T3 EI SLO-SANTA MARIA 13/2 REPL POLE | 31506239 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/241 | 93J | E | 2020_(1b) Lines with special commitments |  | 2020-06-11 | 2020-12-11 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.510259 | 35.1213 | ETL.9100 | 44191413 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 372 | Pismo Beach |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119150124 | Not Scheduled | EI T3NT SLO-SANTA MARIA 13/242 IDLE |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/242 | 93J | F | 2020_(2) High fire spread TD |  | 2020-06-11 | 2022-06-11 | [5 empty] | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.510188 | 35.121 | ETL.9100 | 44191411 | Structure-Wood | Idle | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119150267 | Not Scheduled | EI T3NT SLO-SANTA MARIA 13/243 IDLE |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/243 | 93J | F | 2020_(2) High fire spread TD |  | 2020-06-11 | 2022-06-11 | [5 empty] | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.510034 | 35.1203 | ETL.9100 | 44191412 | Structure-Wood | Idle | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119150469 | Not Scheduled | EI T3NT SLO-SANTA MARIA 14/244 IDLE |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 014/244 | 93J | F | 2020_(2) High fire spread TD |  | 2020-06-11 | 2022-06-11 | [5 empty] | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.509424 | 35.1181 | ETL.9100 | 44191388 | Structure-Wood | Idle | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119150581 | Q2 | T2 DI TRINITY-MAPLE CREK 26/6 RMV PL BUT | 44299848 | TRINITY-MAPLE CREEK | 026/006 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-03 | 2022-06-03 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.390041 | 40.7056 | ETL.8170 | 40906426 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119150584 | Q2 | T2 DI TRINITY-MAPLE CREK 31/2 RMV PL BUT | 44299848 | TRINITY-MAPLE CREEK | 031/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-03 | 2022-06-03 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.478088 | 40.6898 | ETL.8170 | 40906465 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119150589 | Not Scheduled | T3NT DI CARIBOU-PLRMO :31/256A INST GMKW |  | CARIBOU-PALERMO | :031/256A | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2022-06-01 | [7 empty] | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467758 | 39.7593 | ETL.3190 | 44374354 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119150826 | Q2 | T2 DI SLNS LRLS LRLS 15/307 RPL POLE | 31507340 | SALINAS-LAURELES | 015/307 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-03 | 2021-06-03 | 2021-05-25 | 2021-05-28 | 2021-05-28 | 2021-05-21 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.737689 | 36.5139 | ETL.7930 | 40649765 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-08-21 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119151050 | Q2 | T3 DI VOLTA-DESCHUTES 2/54 RMV STUBB | 43939089 | VOLTA-DESCHUTES | 002/054 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.911555 | 40.4709 | ETL.8290 | 40875829 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119151051 | Q2 | T3 DI VOLTA-DESCHUTES 2/54 RPL HRDD | 43939089 | VOLTA-DESCHUTES | 002/054 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.911555 | 40.4709 | ETL.8290 | 40875829 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119151056 | Q2 | T3 DI VOLTA-DESCHUTES 6/133 RPL STRW | 31506865 | VOLTA-DESCHUTES | 006/133 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.980092 | 40.4879 | ETL.8290 | 40759053 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119151317 | Not Scheduled | T3 DI CLGT ALLGHNY 10/273 RPR INS | 44365653 | COLGATE-ALLEGHANY | 010/273 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.034708 | 39.3834 | ETL.6470 | 40894335 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119151319 | Not Scheduled | T3 DI CLGT ALLGHNY 5/144 RPR STRW | 44365653 | COLGATE-ALLEGHANY | 005/144 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.095128 | 39.3357 | ETL.6470 | 40766588 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119151375 | Q2 | DI TRINITY-MAPLE CREEK 0/1 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 000/001 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-08 | 2021-06-08 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.934888 | 40.7183 | ETL.8170 | 40906220 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119151600 | Not Scheduled | T3NT DI CLGT ALLGHNY 5/141 RMV BUTT | 44365654 | COLGATE-ALLEGHANY | 005/141 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-01 | 2022-06-01 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.096941 | 39.3346 | ETL.6470 | 40693506 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119151601 | Not Scheduled | T3 DI CLGT ALLGHNY 5/141 RPR STRW | 44365653 | COLGATE-ALLEGHANY | 005/141 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.096941 | 39.3346 | ETL.6470 | 40693506 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119151869 | Not Scheduled | T3 DI DRUM-SUMMIT #2 5/61C RPR GYWW | 44365659 | DRUM-SUMMIT #2 | 005/061C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-01 | 2020-12-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.698813 | 39.2971 | ETL.1450 | 44212211 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-18 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119152261 | Not Scheduled | T3 DI CRESTA-RIO OSO 16/136 BURIED STUB |  | CRESTA-RIO OSO | 016/136 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2020-12-04 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.478996 | 39.7305 | ETL.4590 | 40910152 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119153522 | Feb | T3 DI DRM RIO OSO #1 1/16 RPR BNT MEM | 44371588 | DRUM-RIO OSO #1 | 001/016 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.796441 | 39.2562 | ETL.1420 | 40820312 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119155639 | Feb | DI STANISLAUS-MNTC #2 27/158 RPR SPLS | 44566011 | STANISLAUS-MANTECA #2 | 027/158 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-09 | 2021-06-09 |  |  | 2021-02-27 | 2021-02-27 | [5 empty] | Central | WSIP | [6 empty] | '-120.766736 | 37.9239 | ETL.3820 | 40856504 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 26 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119155641 | Q2 | LOS BANOS-MIDWAY #2 144/591 RPL INSS |  | LOS BANOS-MIDWAY #2 | 144/591 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-06-11 | 2021-06-11 | 2021-05-11 | 2021-05-28 | 2021-05-28 | 2021-05-11 |  | DLFL once tag is confirmed complete PM |  |  | WECC | South | WSIP | [6 empty] | '-119.461368 | 35.4118 | ETL.6010 | 44668392 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 26 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119155834 | Feb | T3 DI DRUM-RIO OSO #1 6/64 RPLC INSS | 31505600 | DRUM-RIO OSO #1 | 006/064 | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.1420 | 44319610 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119155984 | Not Scheduled | T3NT DI POE-RIO OSO 21/141 RPR FOND |  | POE-RIO OSO | 021/141 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-09 | 2022-06-09 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.488993 | 39.6836 | ETL.5540 | 40590427 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119156006 | Mar | DI DRUM-RIO OSO #1 33/241 RPL HANGER | 44380501 | DRUM-RIO OSO #1 | 033/241 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-06-08 | 2021-06-08 |  |  | 2021-03-01 | 2021-01-19 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.302869 | 39.0222 | ETL.1420 | 40597503 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119156013 | Mar | DI HUMBOLDT-TRINITY 102/2 RPLC POLE (R) |  | HUMBOLDT-TRINITY | 102/002 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-10 |  |  | 2021-03-27 | 2021-03-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.905065 | 40.7644 | ETL.1820 | 44562924 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-12-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119156075 | Mar | DI DRUM-RIO OSO #2 33/241 RPL INSS | 31503652 | DRUM-RIO OSO #2 | 033/241 | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-08 | 2021-06-08 |  |  | 2021-03-20 | 2021-03-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.30286 | 39.0221 | ETL.1430 | 40624114 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119156138 | Q2 | DI GARBERVILLE-LAYTONVILLE 60/5 RPR SPLW | 44311204 | GARBERVILLE-LAYTONVILLE | 060/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-08 | 2021-06-06 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.757467 | 40.1153 | ETL.8365 | 40912683 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119156221 | Q2 | T3NT DI SBNT-GRZLY-CLRT #1 A0/5 RPR FOND | 44624393 | SOBRNTE-GRIZZLY-CLARMNT #1+ | A000/005 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-08 | 2022-06-08 |  |  | 2021-05-31 | 2021-05-24 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.213431 | 37.8979 | ETL.3740 | 40746110 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119156754 | Q2 | T2 DI TRNTY-MPL CRK 46/8 REPL PL (RIGHT) | 31506143 | TRINITY-MAPLE CREEK | 046/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-12 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.739655 | 40.7483 | ETL.8170 | 44771070 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119156756 | Q2 | T2 DI TRNTY-MPL CRK 46/8 RPLC STRW (C) | 31506143 | TRINITY-MAPLE CREEK | 046/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-10 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.739655 | 40.7483 | ETL.8170 | 44771071 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119156759 | Q2 | T2 DI TRNTY-MPL CRK 46/8 REPL PL (LEFT) | 31506143 | TRINITY-MAPLE CREEK | 046/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-12 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.739655 | 40.7483 | ETL.8170 | 44771069 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119157523 | Not Scheduled | T3 DI COLGATE-ALLGHANY 9/259 RPR INSW | 31506710 | COLGATE-ALLEGHANY | 009/259 | 93I | E | 2020_(2) High fire spread TD |  | 2020-05-29 | 2020-11-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.03776 | 39.3758 | ETL.6470 | 40619049 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-06-26 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119157552 | Q2 | T2 DI TRINITY-MAPLE CRK 12/2 RPR WP HOLE | 44295371 | TRINITY-MAPLE CREEK | 012/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420607 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119157583 | Not Scheduled | T3NT DI COLG-ALLHNY 9/259 RMV PL BUTT | 44365654 | COLGATE-ALLEGHANY | 009/259 | ICW | F | 2020_(3) On high spread structure |  | 2020-05-29 | 2022-05-29 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.03776 | 39.3758 | ETL.6470 | 40593288 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158050 | Q2 | T2 DI CLGT SMRTVLLE #2 3/41 RPL POLE | 31511059 | COLGATE-SMARTVILLE #2 | 003/041 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 |  |  | 2021-06-19 | 2021-05-31 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.244049 | 39.3039 | ETL.6520 | 40828765 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-22 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158164 | Q2 | T2 EI LAURELES-OTTER 0/012 RPR GYWW | 44587870 | LAURELES-OTTER | 000/012 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.718525 | 36.4747 | ETL.7380 | 40659509 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158215 | Q2 | EI GARBERVILLE-LYTNVL 47/4C RPL POLE | 31506024 | GARBERVILLE-LAYTONVILLE | 047/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.617733 | 39.9881 | ETL.8365 | 44403653 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158217 | Q2 | EI GARBERVILLE-LYTNVL 47/4L RPL POLE | 31506024 | GARBERVILLE-LAYTONVILLE | 047/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.617733 | 39.9881 | ETL.8365 | 44403652 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158234 | Not Scheduled | T3 DI COLGATE-CHALLENGE 5/105 RPR INSW | 44365653 | COLGATE-CHALLENGE | 005/105 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2020-12-11 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.168533 | 39.3982 | ETL.6480 | 40843183 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158356 | Mar | T2 MNDCN-WLLITS-FRT BRGG 6/0 RPR WDPKR | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 006/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-10 | 2021-06-10 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.282843 | 39.2969 | ETL.7550 | 44676880 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158481 | Q2 | EI GARBERVILLE-LYTNVL 47/4R RPL POLE | 31506024 | GARBERVILLE-LAYTONVILLE | 047/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.617733 | 39.9881 | ETL.8365 | 44403654 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158518 | Mar | T2 MNDCN-WLITS-FRT BRG 17/010 RPL POLE | 31508092 | MENDOCINO-WILLITS-FORT BRAGG | 017/010 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-10 | 2021-06-10 |  |  | 2021-03-18 | 2021-03-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.408618 | 39.3916 | ETL.7550 | 40588460 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-12-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158777 | Q2 | T2 DI CNTRVLL TBLMTN ORO 8/172 RPL POLE | 31507074 | CENTERVILLE-TABLE MTN-OROVILLE | 008/172 | 70Y | E | 2020_(1a) PSPS |  | 2020-06-02 | 2021-06-02 |  |  | 2021-05-30 | 2021-05-30 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.636354 | 39.6656 | ETL.6330 | 40822499 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-17 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119158796 | Q2 | T2 DI TRNTY-MPL CRK 13/0 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 013/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-02 | 2021-06-02 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.143431 | 40.7646 | ETL.8170 | 40605815 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158799 | Q2 | T2 DI TRNTY-MPL CRK 13/0 RPR WDPKR | 44299848 | TRINITY-MAPLE CREEK | 013/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-02 | 2021-06-02 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.143431 | 40.7646 | ETL.8170 | 40605815 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158864 | Q2 | T3 DI CRESTA-RIO OSO 15/123 RPR CONNS |  | CRESTA-RIO OSO | 015/123 | ICM | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2020-12-04 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.475167 | 39.7551 | ETL.4590 | 40910142 | Connector | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 534 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158865 | Not Scheduled | T3 DI CRESTA-RIO OSO 15/123 BURIED STUB |  | CRESTA-RIO OSO | 015/123 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2020-12-04 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.475167 | 39.7551 | ETL.4590 | 40910142 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158880 | Q2 | T2 DI TRINITY-MAPLE CREEK 20/6R RPL POLE | 31509757 | TRINITY-MAPLE CREEK | 020/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-06-05 | 2021-05-31 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.27023 | 40.7201 | ETL.8170 | 44761229 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158881 | Q2 | T2 DI TRINITY-MAPLE CREEK 20/6C REPL POL | 31509757 | TRINITY-MAPLE CREEK | 020/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-06-05 | 2021-05-31 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.27023 | 40.7201 | ETL.8170 | 44761230 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158882 | Q2 | T2 DI TRINITY-MAPLE CREEK 20/6L RPL POLE | 31509757 | TRINITY-MAPLE CREEK | 020/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.27023 | 40.7201 | ETL.8170 | 44761228 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119158921 | Q2 | T2 EI LAURELES-OTTER 000/014 RPR GYWW | 44587870 | LAURELES-OTTER | 000/014 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.717479 | 36.4728 | ETL.7380 | 40751601 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119159313 | Mar | T2 DI KILARC-DESCHUTS 10/212 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 010/212 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.009581 | 40.5828 | ETL.7300 | 40759126 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119159315 | Mar | T2 DI KILARC-DESCHUTES 10/212 REFRAME | 31507071 | KILARC-DESCHUTES | 010/212 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2021-06-04 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.009581 | 40.5828 | ETL.7300 | 40759126 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-13 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119159316 | Not Scheduled | DI DRUM-GRASS VALL-WEI B18/411 RMV BUTT | 44379030 | DRUM-GRASS VALLEY-WEIMAR | B018/411 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-05 | 2021-06-05 | [9 empty] | North Valley | WSIP | [6 empty] | '-120.973245 | 39.148 | ETL.6760 | 40664757 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119159317 | Not Scheduled | DI DRUM-GRASS VALL-WEI B18/411 RPR CONW | 44379030 | DRUM-GRASS VALLEY-WEIMAR | B018/411 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-05 | 2021-06-05 | [9 empty] | North Valley | WSIP | [6 empty] | '-120.973245 | 39.148 | ETL.6760 | 40664757 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119160235 | Q2 | T2 DI PHILO JCT-ELK 18/2 RPR CRSW | 31507080 | PHILO JCT-ELK | 018/002 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-02 | 2021-06-02 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.425168 | 39.0607 | ETL.7780 | 40684472 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-23 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119160419 | Q2 | DI GARBERVLL-LAYTONVLLE 050/010 RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 050/010 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-09 | 2021-06-09 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.638632 | 40.0323 | ETL.8365 | 44141971 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119160646 | Q2 | DI HUMBOLDT-BRIDGEVILLE 104/3 RPL DAMW | 44107184 | HUMBOLDT-BRIDGEVILLE | 104/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-10 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322522 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119160647 | Q2 | DI HUMBOLDT-BRIDGEVILLE 104/3 RPR POLE | 44379658 | HUMBOLDT-BRIDGEVILLE | 104/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322523 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119160720 | Q4 | T3 DI MAPLE CRK-HOOPA 19/000R RPL POLE | 31437835 | MAPLE CREEK-HOOPA | 019/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2020-12-10 |  |  | 2021-10-02 | 2021-07-26 |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-123.658724 | 40.9464 | ETL.7490 | 44145868 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy idoc |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119160768 | Not Scheduled | T3NT DI CLGTE ALLGHNY 13/346 RMV BUTT | 44365654 | COLGATE-ALLEGHANY | 013/346 | ICW | F | 2020_(1a) PSPS |  | 2020-06-11 | 2022-06-11 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.010129 | 39.4188 | ETL.6470 | 40760435 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119160898 | Feb | NT DI LYTNVLLE CVLO 8/11 INSTALL MRKW |  | LAYTONVILLE-COVELO | 008/011 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-08 | 2022-06-08 |  |  | 2021-02-23 | 2021-02-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.331813 | 39.7257 | ETL.7390 | 40600467 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119161022 | Not Scheduled | T3 DI CRESTA RIO OSO 17/139 INST STEPS |  | CRESTA-RIO OSO | 017/139 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2020-12-04 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.479492 | 39.7275 | ETL.4590 | 40910155 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119161332 | Q4 | T3 DI MDDL FRK-GLD HLL 1/18 RPL HRDWW | 44365655 | MIDDLE FORK-GOLD HILL | 001/018 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2020-12-01 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.608923 | 39.0023 | ETL.5140 | 40871784 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119161350 | Q4 | T3 DI MDDL FRK-GLD HLL 1/18 RPR STRW | 44365655 | MIDDLE FORK-GOLD HILL | 001/018 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-01 | 2020-12-01 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.608923 | 39.0023 | ETL.5140 | 40871784 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119161451 | Not Scheduled | T3 DI CARIBOU-PALERMO :11/89 RPR GYWW |  | CARIBOU-PALERMO | :011/089 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-04 | 2020-12-04 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.279035 | 39.9862 | ETL.3190 | 40910329 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119161575 | Mar | DI HUMBOLDT-TRINITY 102/2 RPLC POLE (L) |  | HUMBOLDT-TRINITY | 102/002 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-10 |  |  | 2021-03-27 | 2021-03-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.905065 | 40.7644 | ETL.1820 | 44562822 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-12-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119161578 | Mar | DI HUMBOLDT-TRINITY 102/2 RPLC POLE (C) |  | HUMBOLDT-TRINITY | 102/002 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-10 |  |  | 2021-03-27 | 2021-03-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.905065 | 40.7644 | ETL.1820 | 44562872 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-12-09 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119161603 | Not Scheduled | DI HUMBOLDT-BRIDGEVILLE 97/6 RPR FOND | 44623121 | HUMBOLDT-BRIDGEVILLE | 097/006 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-08 | 2022-06-08 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.874134 | 40.6297 | ETL.1810 | 44321411 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119161692 | Mar | T2 DI KILARC-DESCHUTES 014/309 RPR GYWW | 43930440 | KILARC-DESCHUTES | 014/309 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2021-06-11 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.088143 | 40.5642 | ETL.7300 | 40825996 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119161721 | Not Scheduled | T3 DI ROCK CREEK-POE :2/16 INST HRDT |  | ROCK CREEK-POE | :002/016 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2020-12-11 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.279562 | 39.983 | ETL.5630 | 40804249 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119161722 | Q2 | DI GARBRVLLE-LYTNVLLE 61/0A INS MRKW | 44311204 | GARBERVILLE-LAYTONVILLE | 061/000A | ICW | F | 2020_(3) On high spread structure |  | 2020-06-08 | 2022-06-08 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.761084 | 40.1163 | ETL.8365 | 40912687 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162032 | Not Scheduled | T3NT DI CLGT-ALLGHNY 012/314 RMV PL BUTT | 44371190 | COLGATE-ALLEGHANY | 012/314 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-11 | 2022-06-11 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.024112 | 39.4074 | ETL.6470 | 40693206 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162215 | Not Scheduled | T3NT DI COLGATE-ALLGHANY 14/372 RMV BUTT | 44371791 | COLGATE-ALLEGHANY | 014/372 | GAR | F | 2020_(2) High fire spread TD |  | 2020-06-11 | 2022-06-11 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.002667 | 39.4307 | ETL.6470 | 40693234 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162253 | Q3 | DI BRIDGEVILLE-GARBRVILLE 15/8R RPL POLE | 31508168 | BRIDGEVILLE-GARBERVILLE | 015/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2021-06-11 |  |  | 2021-08-21 | 2021-08-02 |  |  |  |  | SCHD | North Coast | WSIP | [8 empty] | ETL.6220 | 44402635 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162257 | Q3 | DI BRIDGEVILLE-GARBRVILLE 15/8C RPL POLE | 31508168 | BRIDGEVILLE-GARBERVILLE | 015/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2021-06-11 |  |  | 2021-08-21 | 2021-08-02 |  |  |  |  | SCHD | North Coast | WSIP | [8 empty] | ETL.6220 | 44402634 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162321 | Q3 | DI BRIDGEVILLE-GARBRVILLE 15/8L RPL POLE | 31508168 | BRIDGEVILLE-GARBERVILLE | 015/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2021-06-11 |  |  | 2021-08-21 | 2021-08-02 |  |  |  |  | SCHD | North Coast | WSIP | [8 empty] | ETL.6220 | 44402633 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162324 | Q3 | DI BRIDGEVLLE-GRBERVILLE 15/8 RMV BUTT | 44299809 | BRIDGEVILLE-GARBERVILLE | 015/008 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-11 | 2022-06-11 |  |  | 2021-08-21 | 2021-08-02 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.6220 | 44402633 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162394 | Q4 | T3 DI MDDLE FORK-GOLD HILL 6/52 RPL DAMS | 44371780 | MIDDLE FORK-GOLD HILL | 006/052 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2020-12-11 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.691027 | 39.0025 | ETL.5140 | 44690646 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162395 | Q2 | T2 DI IGNACIO-BLNS #2 15/176 RMV BUTT | 44640732 | IGNACIO-BOLINAS #2 | 015/176 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-11 | 2021-06-11 |  |  | 2021-04-15 | 2021-04-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.743056 | 38.0483 | ETL.7180 | 40827646 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162397 | Q4 | T3 DI MDDLE FORK-GOLD HILL 6/52 RPR SHLS | 44371780 | MIDDLE FORK-GOLD HILL | 006/052 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2020-12-11 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.691027 | 39.0025 | ETL.5140 | 44690646 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162470 | Q2 | T2 DI TRINITY-MAPLE CRK 54/0 RPL INSW | 31510698 | TRINITY-MAPLE CREEK | 054/000 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.873257 | 40.7679 | ETL.8170 | 40641469 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162549 | Mar | T2 MNT VST-JFFRSN #1 8/3 RPL INSS | 31513842 | MONTA VISTA-JEFFERSON #1 | 008/033 | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-13 | 2021-06-13 |  |  | 2021-03-05 | 2021-02-28 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.21436 | 37.3305 | ETL.5220 | 40658429 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 10 | RROSP | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162576 | Feb | T2 COLGATE-GRASS VALLEY 10/239 RPL POLE | 31506254 | COLGATE-GRASS VALLEY | 010/239 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-13 | 2021-06-13 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.079235 | 39.2332 | ETL.6490 | 40869595 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162622 | Mar | T2 MNDCN-WLLTS-FRT BRGG 38/0 RPL INSW | 31508139 | MENDOCINO-WILLITS-FORT BRAGG | 038/000 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-13 | 2021-06-13 |  |  | 2021-03-17 | 2021-03-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.7262785 | 39.4046 | ETL.7550 | 40629898 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162631 | Q2 | DI HUMBOLDT-BRIDGEVILLE 93/5 RPR GYWW | 44107184 | HUMBOLDT-BRIDGEVILLE | 093/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2021-06-11 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322335 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162632 | Q2 | DI HUMBOLDT-BRIDGEVILLE 93/5 RPR GYWW | 44107184 | HUMBOLDT-BRIDGEVILLE | 093/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2021-06-11 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322336 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162699 | Feb | T2 COLGATE-GRASS VALLEY 10/246 RPR INSW | 44388662 | COLGATE-GRASS VALLEY | 010/246 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-13 | 2021-06-13 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.079202 | 39.2296 | ETL.6490 | 40760648 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162799 | Mar | T2 ATASCADERO-CAYUCOS 2/21 RPL POLE | 31508522 | ATASCADERO-CAYUCOS | 002/021 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-13 | 2021-06-13 | 2021-03-29 | 2021-03-31 | 2021-03-31 | 2021-03-29 |  |  |  | TR2 |  | South | WSIP | [8 empty] | ETL.8480 | 44319815 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-07-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162899 | Q3 | T3NT DI DONNELLS-MI-WUK 14/0L RMV BUTT | 44467328 | DONNELLS-CURTIS | 014/000 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-12 | 2022-06-12 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.151592 | 38.0908 | ETL.1400 | 44776441 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162900 | Feb | T3 KILARC-CEDAR CREEK 001/022 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 001/022 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-13 | 2020-12-13 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.889052 | 40.6837 | ETL.7290 | 40600823 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119162939 | Q2 | DI HUMBOLDT-BRIDGEVILLE 9/3 RPL INSW | 31506838 | HUMBOLDT-BRIDGEVILLE | 090/003 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-12 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.832529 | 40.5294 | ETL.1810 | 40685195 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-09-18 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119163061 | Q2 | DI HUMBOLDT-BRIDGEVLLE 9/3 RPL ADSS BOLT | 44107184 | HUMBOLDT-BRIDGEVILLE | 090/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-12 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322279 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119163180 | Q3 | T3NT DI DONNELLS-MI-WUK 14/0R RMV BUTT | 44467328 | DONNELLS-CURTIS | 014/000 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-12 | 2022-06-12 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.151592 | 38.0908 | ETL.1400 | 44776440 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119163182 | Q3 | T3 DI DONNELLS-MI-WUK 14/0L RPR STRW | 44467328 | DONNELLS-CURTIS | 014/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2020-12-12 |  |  | 2021-09-07 | 2021-08-07 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.151592 | 38.0908 | ETL.1400 | 44776441 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119163258 | Q4 | T3 DI MDL FRK-GLD HLL 6/50 RPR SHLS | 44371780 | MIDDLE FORK-GOLD HILL | 006/050 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2020-12-11 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.684499 | 39.0023 | ETL.5140 | 44690644 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119163263 | Q4 | T3 DI MDL FRK-GLD HLL 6/50 RPR SHLS | 44371780 | MIDDLE FORK-GOLD HILL | 006/050 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2020-12-11 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.684499 | 39.0023 | ETL.5140 | 44690645 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119163487 | Feb | T3 DI DRUM-RIO OSO #1 3/39 RPR SPLS | 44371588 | DRUM-RIO OSO #1 | 003/039 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2020-12-11 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.826141 | 39.2352 | ETL.1420 | 40865466 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119163507 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 13/351 RPR STRW | 44365653 | COLGATE-ALLEGHANY | 013/351 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2020-12-11 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.008723 | 39.421 | ETL.6470 | 40611332 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119163561 | Q2 | T3 DI IGNACIO-BOLINAS #1 11/121 RPR STRW | 44640733 | IGNACIO-BOLINAS #1 | 011/121 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2020-12-11 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.67241 | 37.9592 | ETL.7140 | 40750706 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119163662 | Q2 | DI HUMBOLDT-BRIDGEVILLE 98/2 RPR FIBER | 44356653 | HUMBOLDT-BRIDGEVILLE | 098/002 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322390 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119163671 | Q2 | DI HUMBOLDT-BRIDGEVILLE 090/6 RPR ADSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 099/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2021-06-11 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322423 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119163777 | Q2 | DI HUMBOLDT-BRIDGEVILLE 100/4 RPR GYWS | 44356920 | HUMBOLDT-BRIDGEVILLE | 100/004 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2021-06-11 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322445 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119163796 | Feb | T3 DI KILARC-CEDAR CREEK 4/95 RPR GYWW | 43939119 | KILARC-CEDAR CREEK | 004/095 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2020-12-11 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.94599 | 40.7006 | ETL.7290 | 40677168 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119163799 | Feb | T3NT DI KILARC-CEDAR CREEK 4/95 RMV BUTT | 43939119 | KILARC-CEDAR CREEK | 004/095 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-11 | 2022-06-11 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.94599 | 40.7006 | ETL.7290 | 40677168 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119163866 | Q2 | DI HUMBOLDT-BRDGEVILLE 105/5 RMV PL BUTT | 44398571 | HUMBOLDT-BRIDGEVILLE | 105/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-12 | 2022-06-12 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322554 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119164291 | Mar | T2 MENDO-WLLTS-FT BRAGG 29/11 RPL DAMPER | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 029/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-14 | 2021-06-14 |  |  | 2021-03-16 | 2021-03-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.6016724 | 39.3483 | ETL.7550 | 40627066 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119164310 | Feb | T3 COLGATE-GRASS VALLEY 007/168 CANCEL | 44371196 | COLGATE-GRASS VALLEY | 007/168 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-14 | 2020-12-14 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.093922 | 39.2788 | ETL.6490 | 40665605 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119164320 | Mar | T2 HUMBOLDT-TRINITY 58/001 RPR GYWW | 44299237 | HUMBOLDT-TRINITY | 058/001 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-14 | 2021-06-14 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.139448 | 40.7656 | ETL.1820 | 44553876 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119164323 | Q2 | T2 TRINITY-MAPLE CREEK 44/3 INST DAMPER | 44273074 | TRINITY-MAPLE CREEK | 044/003 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-14 | 2021-06-14 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.697538 | 40.7451 | ETL.8170 | 40699975 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119164324 | Not Scheduled | T3 FRNCH MDWS-MDDLE FORK 9/170 INST DMPW | 44371596 | FRENCH MEADOWS-MIDDLE FORK | 009/170 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-14 | 2020-12-14 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.549678 | 39.0178 | ETL.6870 | 40664828 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119164328 | Not Scheduled | T2 CAYUCOS-CAMBRIA 12/077 RPLC POLE | 31508524 | CAYUCOS-CAMBRIA | 012/077 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-14 | 2021-06-14 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.022758 | 35.5506 | ETL.8560 | 40667163 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119164331 | Q2 | T2 TRINITY-MAPLE CREEK 39/5L RPL POLE | 31509758 | TRINITY-MAPLE CREEK | 039/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-14 | 2021-06-14 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.618915 | 40.7192 | ETL.8170 | 44769576 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119164994 | Feb | T3 DI KILARC-CEDAR CRK 5/135 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 005/135 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2020-12-11 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.978012 | 40.7102 | ETL.7290 | 40617665 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119165285 | Q2 | DI HUMBOLDT-BRIDGEVIL 95/0 RMV PL BUTT | 44378879 | HUMBOLDT-BRIDGEVILLE | 095/000 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-11 | 2021-06-11 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322345 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119165533 | Mar | T3NT DI MORGA-SN LNDRO #3 4/36 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 004/036 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-09 | 2022-06-09 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.125781 | 37.7858 | ETL.2790 | 40804668 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119165615 | Not Scheduled | T3 DI COLGATE-CHALLENGE 8/143 RPLC SPLW | 44361610 | COLGATE-CHALLENGE | 008/143 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2020-12-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.1984 | 39.4255 | ETL.6480 | 40824215 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119165683 | Not Scheduled | T3 DI FULTON-PUEBLO 37/191A RPR SWITCH |  | FULTON-PUEBLO | 037/191A | ICE | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-09 | 2020-12-09 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.66591 | 38.4968 | ETL.1600 | 40743260 | Switch | Out of Adjustment | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 623 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119165684 | Not Scheduled | T3 DI COLGATE-CHALLENGE 7/135 RMV BUTT | 44361612 | COLGATE-CHALLENGE | 007/135 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-15 | 2022-06-15 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.195678 | 39.4181 | ETL.6480 | 40611341 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119165686 | Not Scheduled | T3 DI COLGATE-CHALLENGE 7/135 RPR SPLW | 44361610 | COLGATE-CHALLENGE | 007/135 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-15 | 2020-12-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.195678 | 39.4181 | ETL.6480 | 40611341 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119165687 | Mar | T3 DI LAURELES-OTTER 4/4 RPR GYWW | 44381542 | LAURELES-OTTER | 004/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2020-12-15 |  |  | 2021-03-24 | 2021-03-24 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.735825 | 36.431 | ETL.7380 | 44562656 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119165689 | Mar | T3 DI LAURELES-OTTER 4/4 RPR GYWW | 44381542 | LAURELES-OTTER | 004/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2020-12-15 |  |  | 2021-03-24 | 2021-03-24 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.735825 | 36.431 | ETL.7380 | 44562780 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119165751 | Not Scheduled | T3 DI COLGATE-CHALLENGE 8/143 RPR BOND | 44361610 | COLGATE-CHALLENGE | 008/143 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2020-12-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.1984 | 39.4255 | ETL.6480 | 40824215 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119165910 | Mar | T3 DI LAURELES-OTTER 4/4 RPR GYWW | 44381542 | LAURELES-OTTER | 004/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2020-12-15 |  |  | 2021-03-24 | 2021-03-24 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.735825 | 36.431 | ETL.7380 | 44562832 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119165929 | Mar | T3 DI DEER CREEK-DRUM 3/83 RMV BUTT | 44361665 | DEER CREEK-DRUM | 003/083 | ICW | F | 2020_(1a) PSPS |  | 2020-06-15 | 2022-06-15 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.809966 | 39.2617 | ETL.6690 | 40866658 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119165974 | Mar | T3 DI DEER CREEK-DRUM 3/83 RPR POLE | 44361664 | DEER CREEK-DRUM | 003/083 | ICW | E | 2020_(1a) PSPS |  | 2020-06-15 | 2020-12-15 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.809966 | 39.2617 | ETL.6690 | 40866658 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119166010 | Mar | T3 DI DEER CREEK-DRUM 3/83 RPR SPLW | 44361664 | DEER CREEK-DRUM | 003/083 | ICW | E | 2020_(1a) PSPS |  | 2020-06-15 | 2020-12-15 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.809966 | 39.2617 | ETL.6690 | 40866658 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119166110 | Q2 | T3 DI MORAGA-SAN LEAND #3 5/41 RPL INSS | 31511126 | MORAGA-SAN LEANDRO #3 | 005/041 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-22 | 2020-11-22 | 2021-04-01 |  | 2021-04-02 | 2021-04-01 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.121509 | 37.7737 | ETL.2790 | 40604524 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | ACRP | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166113 | Not Scheduled | T3NT DI COLGATE-CHALLENGE 4/83 RMV BUTT | 44371193 | COLGATE-CHALLENGE | 004/083 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-15 | 2022-06-15 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.162487 | 39.3822 | ETL.6480 | 40655138 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166116 | Not Scheduled | T3NT DI COLGATE-CHALLENGE 2/55 RMV BUTT | 44371193 | COLGATE-CHALLENGE | 002/055 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-15 | 2022-06-15 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.167405 | 39.3629 | ETL.6480 | 40664548 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166126 | Q2 | T3 VOLTA-DESCHUTES 0/5 RPL POLE | 31507081 | VOLTA-DESCHUTES | 000/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2020-12-11 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.87047 | 40.4603 | ETL.8290 | 40656907 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166143 | Q2 | T2 VOLTA-DESCHUTES 11/249 RPLC POLE | 31508171 | VOLTA-DESCHUTES | 011/249 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2021-06-11 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.081207 | 40.5109 | ETL.8290 | 40825156 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166149 | Q2 | T2 VOLTA-DESCHUTES 13/276 RPLC POLE | 31508171 | VOLTA-DESCHUTES | 013/276 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2021-06-11 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.104063 | 40.5176 | ETL.8290 | 40669479 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166161 | Mar | DI HUMBOLDT-TRINITY 045/005A REPL PL | 31506039 | HUMBOLDT-TRINITY | 045/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-10 |  |  | 2021-03-27 | 2021-03-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.937207 | 40.7193 | ETL.1820 | 44560583 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166200 | Mar | T2 KILARC-DESCHUTES 9/203 RPLC POLE | 31507647 | KILARC-DESCHUTES | 009/203 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2021-06-11 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.002473 | 40.5846 | ETL.7300 | 40877958 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-07-13 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166217 | Mar | T2 KILARC-DESCHUTES 2/050 REFRAME | 31510881 | KILARC-DESCHUTES | 002/050 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2021-06-11 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.891824 | 40.6474 | ETL.7300 | 40868553 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-13 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166263 | Mar | T2 KILARC-DESCHUTES 2/48 RPL POLE | 31507647 | KILARC-DESCHUTES | 002/048 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-15 | 2021-06-15 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.890636 | 40.6483 | ETL.7300 | 40817202 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166346 | Mar | T3 KILARC-DESCHUTES 0/5 REFRAME CRSW | 31507069 | KILARC-DESCHUTES | 000/005 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2020-12-11 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.873104 | 40.6752 | ETL.7300 | 40827951 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-13 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166488 | Q2 | T2 TRINITY-MAPLE CREEK 000/00A RPL POLE | 31505649 | TRINITY-MAPLE CREEK | 000/000A | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-15 | 2021-06-15 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.530267 | 40.7126 | ETL.8170 | 44966204 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166503 | Q2 | T2 TRINITY-MAPLE CREEK 000/001 RPL POLE | 31505649 | TRINITY-MAPLE CREEK | 000/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-15 | 2021-06-15 |  |  | 2021-06-12 | 2021-06-07 |  | DLFL | Placeholder notification | TR2 |  | North Coast | WSIP | [6 empty] | '-123.530512 | 40.7124 | ETL.8170 | 44966205 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166530 | Q2 | T2 TRINITY-MAPLE CREEK 000/002 RPL POLE | 31505649 | TRINITY-MAPLE CREEK | 000/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-15 | 2021-06-15 |  |  | 2021-06-12 | 2021-06-07 |  | DLFL | Placeholder notification | TR2 |  | North Coast | WSIP | [6 empty] | '-123.531045 | 40.7122 | ETL.8170 | 44966206 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166584 | Not Scheduled | T3 FULTON-CALISTOGA 3/005 RPL POLE | 31507363 | FULTON-CALISTOGA | 003/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-15 | 2020-12-15 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.485897 | 38.5386 | ETL.6880 | 40769769 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166709 | Q3 | T2 DI CARIBOU#2 ;1/22 RMV PL BUTT |  | CARIBOU #2 | ;001/022 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-15 | 2022-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.960768 | 40.0033 | ETL.6280 | 40659831 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166724 | Q2 | T2 DI TRINITY-MAPLE CRK 45/4 BOND GUY | 44273074 | TRINITY-MAPLE CREEK | 045/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-12 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.716487 | 40.7502 | ETL.8170 | 44565336 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166802 | Q2 | DI BRDGVLL-CTTNWD 0/4 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 000/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2021-06-11 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [8 empty] | ETL.1110 | 44424591 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166809 | Q2 | DI BRDGVLL-CTTNWD 0/4 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 000/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2021-06-11 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [8 empty] | ETL.1110 | 44424592 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166844 | Q2 | DI BRDGVLL-CTTNWD 0/4 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 000/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2021-06-11 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [8 empty] | ETL.1110 | 44424593 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166881 | Q3 | T2 DI CARIBOU #2 ;1/5 RMV PL BUTT |  | CARIBOU #2 | ;001/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-15 | 2022-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.96705 | 40.0099 | ETL.6280 | 40768896 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166894 | Q2 | DI BRDGVLL-CTTNWD 0/4 RPL CRSW | 43939216 | BRIDGEVILLE-COTTONWOOD | 000/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2021-06-11 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.272785 | 40.3994 | ETL.1110 | 44424590 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119166896 | Q2 | DI BRDGVLL-CTTNWD 0/4 RMV PL BUTT | 43939216 | BRIDGEVILLE-COTTONWOOD | 000/004 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-11 | 2022-06-11 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [8 empty] | ETL.1110 | 44424592 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119167128 | Not Scheduled | T2 DRM-GRSS VLLY-WMR B016/366 INST MRKW | 44389587 | DRUM-GRASS VALLEY-WEIMAR | B016/366 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-15 | 2021-06-15 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-120.957249 | 39.1199 | ETL.6760 | 44922916 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119167282 | Q3 | T2 DI CARIBOU #2 :6/2 RPLC SPLW |  | CARIBOU #2 | :006/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2021-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.979528 | 39.9694 | ETL.6280 | 40659889 | Splice-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119167455 | Not Scheduled | T2 DI MORRO BAY-TEMPLETON 5/24 RPR OPGW |  | MORRO BAY-TEMPLETON | 005/024 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-15 | 2021-06-15 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.78575 | 35.4179 | ETL.5933 | 40753216 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-03 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119167813 | Mar | T2 WV HMBLDT-TRNTY 95/12 INS INSW | 31509856 | HUMBOLDT-TRINITY | 095/012 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2021-06-15 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.787614 | 40.7576 | ETL.1820 | 44924629 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119167938 | Q3 | T2 DI CARIBOU #2 ;1/10 REFRAME | 31507060 | CARIBOU #2 | ;001/010 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2021-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.966952 | 40.0079 | ETL.6280 | 40593017 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119167982 | Q2 | LAYTONVILLE-WILLITS 0/8 REPLUMB POLE | 44610677 | LAYTONVILLE-WILLITS | 000/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-15 | 2021-06-15 | 2021-05-26 | 2021-05-28 | 2021-05-28 | 2021-05-28 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.321934 | 39.4108 | ETL.8360 | 40876424 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119168083 | Feb | T3 DI KILARC-CEDAR CREEK 3/87 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 003/087 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2020-12-11 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.940665 | 40.6991 | ETL.7290 | 40577356 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119168092 | Q2 | T2NT DI MI-WUK-CURTIS 25/2 RMV BUTT |  | ETL.1073.POLE.WOOD | 025/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-15 | 2022-06-15 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.294848 | 37.9855 | ETL.1073 | 40643775 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119168096 | Q2 | T2 DI MI-WUK-CURTIS 25/2 RPR GYWW | 44623240 | ETL.1073.POLE.WOOD | 025/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-15 | 2021-06-15 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.294848 | 37.9855 | ETL.1073 | 40643775 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119168124 | Mar | T2 DI KILARC-DESCHUTES 11/244 RMV BUTT | 43930440 | KILARC-DESCHUTES | 011/244 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-11 | 2022-06-11 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.027281 | 40.5697 | ETL.7300 | 40770435 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119168126 | Mar | T2 DI KILARC-DESCHUTES 11/244 RPR GYWW | 43930440 | KILARC-DESCHUTES | 011/244 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-11 | 2021-06-11 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.027281 | 40.5697 | ETL.7300 | 40770435 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119168385 | Not Scheduled | T2 DI TRINITY-MAPLE CRK 5/5A RMV BUTT | 44299848 | TRINITY-MAPLE CREEK | 005/005A | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-15 | 2022-06-15 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.030752 | 40.7331 | ETL.8170 | 44859212 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119168822 | Q2 | DI HUMBOLDT-BRDGVLL 103/1R RMV PL BUTT | 44398571 | HUMBOLDT-BRIDGEVILLE | 103/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-12 | 2022-06-12 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322502 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169335 | Q3 | T2 DI CARIBOU #2 0/17 RMV PL BUTT |  | CARIBOU #2 | ;000/017 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-15 | 2022-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.962288 | 40.0205 | ETL.6280 | 40824669 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169383 | Q3 | T2 DI CARIBOU #2 16/9 RMV PL BUTT |  | CARIBOU #2 | 016/009 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-15 | 2022-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.090562 | 40.0152 | ETL.6280 | 40867537 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169580 | Mar | T2 DI KILARC-DESCHUTS 11/239 RMV PL BUTT | 44406469 | KILARC-DESCHUTES | 011/239 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-15 | 2022-06-15 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.022578 | 40.5709 | ETL.7300 | 40617697 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169584 | Q3 | T2 DI CARIBOU #2 1/14 REFRAME | 31507060 | CARIBOU #2 | ;001/014 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2021-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.964812 | 40.0063 | ETL.6280 | 40751748 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169619 | Q3 | T2 DI CARIBOU #2 1/14 RMV PL BUTT |  | CARIBOU #2 | ;001/014 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-15 | 2022-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.964812 | 40.0063 | ETL.6280 | 40751748 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169743 | Q2 | T2 DI TRINITY-MAPLE CREEK 36/1 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 036/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 | 2021-04-05 | 2021-04-11 | 2021-04-11 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44271138 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169744 | Q2 | T2 DI TRINITY-MAPLE CREEK 36/1 RPL ANCW | 31507467 | TRINITY-MAPLE CREEK | 036/001 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 | 2021-04-05 | 2021-04-11 | 2021-04-11 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44271139 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169800 | Q4 | T2 DI MAPLE CREEK-HOOPA 25/2 RPR WDPKR | 44192340 | MAPLE CREEK-HOOPA | 015/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.700172 | 40.9165 | ETL.7490 | 44145856 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169803 | Q2 | DI HUMBOLDT-TRINITY 103/3 RPL HRDD | 44299237 | HUMBOLDT-TRINITY | 103/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-06-12 | 2021-05-24 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.924835 | 40.7646 | ETL.1820 | 44560559 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169806 | Mar | DI HUMBOLDT-TRINITY 102/000 RPL INSW | 31509856 | HUMBOLDT-TRINITY | 102/000 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-12 |  |  | 2021-03-02 | 2021-03-02 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.898598 | 40.7663 | ETL.1820 | 40630995 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169826 | Q2 | DI HUMBOLDT-BRIDGEVILLE 88/3R RPL STRW | 31508093 | HUMBOLDT-BRIDGEVILLE | 088/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322245 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169829 | Q2 | DI GRBRVLL LYTNVLL 45/6 RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 045/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.613537 | 39.9661 | ETL.8365 | 44403647 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169840 | Q2 | DI GRBRVLL LYTNVLL 45/6 RMV PL BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 045/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-12 | 2022-06-12 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.613537 | 39.9661 | ETL.8365 | 44403647 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169903 | Not Scheduled | T3 DI CLGTE CHLLNGE 5/103 RPL HRDD | 44371192 | COLGATE-CHALLENGE | 005/103 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2020-12-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.165737 | 39.3969 | ETL.6480 | 44695492 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169925 | Feb | DI RIO DELL JCT-BRDGVLL 38/1L RPL STRW | 31508280 | RIO DELL JCT-BRIDGEVILLE | 038/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-02-27 | 2021-02-15 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.7850 | 44403575 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-08-21 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119169929 | Feb | DI RIO DELL JCT-BRDGVLL 38/1 RMV PL BUTT | 44326491 | RIO DELL JCT-BRIDGEVILLE | 038/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-12 | 2022-06-12 |  |  | 2021-02-27 | 2021-02-15 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.7850 | 44403575 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119170000 | Q2 | DI HMBLDT-BRIDGEVILLE 105/7 RPL BRACKET | 44107184 | HUMBOLDT-BRIDGEVILLE | 105/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322562 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119170188 | Not Scheduled | T3 DI COLGATE-CHALLENGE 3/76 RPL POLE | 31506352 | COLGATE-CHALLENGE | 003/076 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2020-12-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.163586 | 39.3777 | ETL.6480 | 40822734 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-08-21 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119170299 | Not Scheduled | T3 DI COLGATE-CHALLENGE 004/093 RPR SPLW | 44361610 | COLGATE-CHALLENGE | 004/093 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2020-12-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.160785 | 39.3892 | ETL.6480 | 44695490 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119170619 | Q2 | T3 DI LAURELES-OTTER 3/5 RPLC HRDW | 44392359 | LAURELES-OTTER | 003/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-05-31 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.722848 | 36.438 | ETL.7380 | 44838826 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119170659 | Not Scheduled | T2 DI SLO-SM 15/66 RPL INSS | 31510359 | SAN LUIS OBISPO-SANTA MARIA | 015/066 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-06-15 | 2021-06-15 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | 120.4982 | 35.0942 | ETL.3540 | 40836331 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119170700 | Q2 | T3 DI LAURELES-OTTER 3/5 RPLC HRDW | 44392360 | LAURELES-OTTER | 003/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-05-31 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.722848 | 36.438 | ETL.7380 | 44838831 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Q2 | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119170703 | Q2 | T2 DI TRINITY-MAPLE CRK 5/0 RPLC HRDW | 44273074 | TRINITY-MAPLE CREEK | 005/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420585 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119170818 | Not Scheduled | T3 DI COLGATE-CHALLENGE 6/14 RPR SPLW | 44361610 | COLGATE-CHALLENGE | 006/114 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2020-12-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.18301 | 39.4004 | ETL.6480 | 40664715 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119171142 | Q3 | T2 DI CARIBOU #2 :6/5 RPLC INSW | 31506251 | CARIBOU #2 | :006/005 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.977264 | 39.968 | ETL.6280 | 40799668 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119171236 | Mar | DI HUMDOLDT-TRINITY 102/3R RPR STRW | 44299237 | HUMBOLDT-TRINITY | 102/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-10 |  |  | 2021-03-03 | 2021-03-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.915197 | 40.7614 | ETL.1820 | 44560443 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119171317 | Q3 | T2 EI BRIDGEVILLE-GARBERVILLE 36/0 RPL P | 31515485 | BRIDGEVILLE-GARBERVILLE | 036/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 | 2021-08-30 | 2021-09-01 | 2021-09-01 | 2021-08-30 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.792536 | 40.103 | ETL.6220 | 40591160 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS hold | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119171365 | Q3 | T2 DI CARIBOU #2 15/22 RPR STRW |  | CARIBOU #2 | 015/022 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2021-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.101143 | 40.0172 | ETL.6280 | 40698677 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119171367 | Q3 | T2 DI CARIBOU #2 15/22 RPR CRSW |  | CARIBOU #2 | 015/022 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2021-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.101143 | 40.0172 | ETL.6280 | 40698677 | Crossarm-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119171534 | Q3 | T2 DI CARIBOU #2 018/000 BOND GUY |  | CARIBOU #2 | 018/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.061181 | 40.0195 | ETL.6280 | 40599711 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119171763 | Q2 | T2 EI BRIDGEVILLE-GARBERVILLE 35/8 RPL P | 31508614 | BRIDGEVILLE-GARBERVILLE | 035/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-16 | 2021-06-16 |  |  | 2021-06-01 | 2021-01-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.788093 | 40.1043 | ETL.6220 | 40862861 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-21 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119171785 | Q2 | T2 EI BRIDGEVILLE-GARBERVILLE 35/7 RPL P | 31508614 | BRIDGEVILLE-GARBERVILLE | 035/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-16 | 2021-06-16 |  |  | 2021-06-01 | 2021-01-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.786773 | 40.1046 | ETL.6220 | 40810360 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-21 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119171813 | Mar | T3NT DI DRUM-RIO OSO #1 9/96 RPR FOND | 44371589 | DRUM-RIO OSO #1 | 009/096 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-12 | 2022-06-12 |  |  | 2021-03-01 | 2021-01-19 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.912623 | 39.1783 | ETL.1420 | 40814354 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119171986 | Q2 | T2 DI TRINITY-MPL CRK 21/1 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 021/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-12 | 2022-06-12 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420623 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119172195 | Q2 | DI HUMBOLDT-BRIDGEVILLE 102/3C RPL STRW | 31508093 | HUMBOLDT-BRIDGEVILLE | 102/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-12 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322491 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119172297 | Not Scheduled | T3 DI COLGATE-ALLGHNY 11/298 RMV BUTT | 44365654 | COLGATE-ALLEGHANY | 011/298 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-11 | 2022-06-11 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.027924 | 39.4002 | ETL.6470 | 40818486 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119172345 | Not Scheduled | T3 DI COLGATE-ALLGHNY 11/298 RPLC HRDD | 44365653 | COLGATE-ALLEGHANY | 011/298 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2020-12-11 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.027924 | 39.4002 | ETL.6470 | 40818486 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119172447 | Q2 | DI HUMBOLDT-BRIDGEVILLE 101/1 RPR STRW | 44379658 | HUMBOLDT-BRIDGEVILLE | 101/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-12 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322466 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119172449 | Q2 | T3 DI IGNACIO-BOLINAS #2 24/270 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 024/270 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2020-12-12 |  |  | 2021-04-23 | 2021-04-16 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.7180 | 44360905 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119172461 | Q2 | T2 EI BRIDGEVILLE-GARBERVILLE 35/5 RPL P | 31508614 | BRIDGEVILLE-GARBERVILLE | 035/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-04 |  |  | 2021-06-01 | 2021-01-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.783442 | 40.1053 | ETL.6220 | 40752680 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119172462 | Q2 | T2 EI BRIDGEVILLE-GARBERVILLE 35/6 RPL P | 31508614 | BRIDGEVILLE-GARBERVILLE | 035/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-06-01 | 2021-01-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.784561 | 40.1051 | ETL.6220 | 41088039 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119172586 | Q2 | T2 DI TRINITY-MAPLE CRK 31/1 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 031/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.474761 | 40.6902 | ETL.8170 | 44565314 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119172587 | Q2 | T2 DI TRINITY-MAPLE CRK 31/1 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 031/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.474761 | 40.6902 | ETL.8170 | 44565602 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119172588 | Q2 | T2 DI TRINITY-MAPLE CRK 31/1 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 031/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.474761 | 40.6902 | ETL.8170 | 44565619 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119172589 | Q2 | T2 DI TRINITY-MAPLE CRK 35/8L RPL POLE | 31506143 | TRINITY-MAPLE CREEK | 035/008 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.556324 | 40.7222 | ETL.8170 | 44565511 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119172701 | Q2 | T2 DI TRINITY-MAPLE CREEK 35/8C RPL POLE | 31506143 | TRINITY-MAPLE CREEK | 035/008 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.556324 | 40.7222 | ETL.8170 | 44565596 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119172702 | Q2 | T2 DI TRINITY-MAPLE CREEK 35/8R RPL POLE | 31506143 | TRINITY-MAPLE CREEK | 035/008 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.556324 | 40.7222 | ETL.8170 | 44565510 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119172885 | Q2 | T2NT DI PTTSBRG-SAN MATEO 21/82 RPR FOND |  | PITTSBURG-SAN MATEO | 021/082 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2022-06-12 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.927405 | 37.7487 | ETL.5463 | 40817953 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119172888 | Q3 | T3 DI DONNELLS-MI-WUK 3/4 RPR STRW | 44623241 | DONNELLS-CURTIS | 003/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2020-12-12 |  |  | 2021-09-07 | 2021-08-07 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.036818 | 38.1959 | ETL.1400 | 44775188 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 | USFS | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119173396 | Feb | T3 DESABLA-CENTERVILLE 0/8 REPLUMB POLE | 44356201 | DESABLA-CENTERVILLE | 000/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-16 | 2020-12-16 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.629918 | 39.8655 | ETL.6720 | 40862027 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119173412 | Q2 | T2 DI BRDGVL-CTNWD 30/253 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 030/253 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2021-05-29 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.836544 | 40.3641 | ETL.1110 | 44561191 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-24 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119173518 | Q4 | T3 DI MAPLE CREEK-HOOPA 12/7 RMV BUTT | 44301081 | MAPLE CREEK-HOOPA | 012/007B | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-15 | 2022-06-15 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.754332 | 40.9086 | ETL.7490 | 40810432 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119173689 | Not Scheduled | T2 EI MDDL FRK-GLD HLL 19/151R CANCEL | 31497889 | MIDDLE FORK-GOLD HILL | 019/151 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2018-12-22 | 2019-12-22 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.869235 | 38.8917 | ETL.5140 | 44557760 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-24 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119173831 | Mar | T2 HUMBOLDT-TRINITY 50/0 RPL INSW | 31509856 | HUMBOLDT-TRINITY | 050/000 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.010925 | 40.7284 | ETL.1820 | 40635182 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-12-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174176 | Mar | T2 DI KILARC-DESCHUTES 012/263 RPL SPLW | 43930440 | KILARC-DESCHUTES | 012/263 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.043839 | 40.5656 | ETL.7300 | 40592179 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-13 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174177 | Mar | T2 DI KILARC-DSCHUTES 011/247 RMV BUTT | 43930440 | KILARC-DESCHUTES | 011/247 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2022-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.030005 | 40.5691 | ETL.7300 | 40868569 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174201 | Mar | T3NT DI LAURELES-OTTER 5/2 RMV BUTTS | 44392361 | LAURELES-OTTER | 005/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-12 | 2022-06-12 |  |  | 2021-03-24 | 2021-03-24 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.745012 | 36.4271 | ETL.7380 | 44562931 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174221 | Not Scheduled | T3 DI COLGATE-CHALLENGE 4/91 RPR STRW | 44361610 | COLGATE-CHALLENGE | 004/091 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2020-12-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.161096 | 39.3878 | ETL.6480 | 40598504 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174320 | Mar | T3 DI LAURELES-OTTER 5/2 RPR HRDW | 44392362 | LAURELES-OTTER | 005/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-05-31 |  |  | 2021-03-24 | 2021-03-24 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.745012 | 36.4271 | ETL.7380 | 44562931 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401 |  | Yes | No | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Mar | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174385 | Q2 | T3 DI PITTSBURG-SAN MATO 23/092 RPR HRDT | 44623139 | PITTSBURG-SAN MATEO | 023/092 | ICQ | E | 2020_(3) On high spread structure |  | 2020-06-16 | 2020-12-16 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.963067 | 37.7326 | ETL.5463 | 40805061 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174593 | Q2 | T2 EXCHEQUER-INDIAN FLAT 20/73 REPL TOWR | 31508860 | EXCHEQUER-YOSEMITE | 020/073 | 70S | E | 2020_(2) High fire spread TD |  | 2020-06-16 | 2021-06-16 |  |  | 2021-06-30 | 2021-06-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.028244 | 37.5843 | ETL.8650 | 40660804 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Fresno |  | y - 50 | BLM | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174669 | Q3 | T2 DI CARIBOU #2 ;001/015 RMV PL BUTT |  | CARIBOU #2 | ;001/015 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-15 | 2022-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.964265 | 40.0058 | ETL.6280 | 40768847 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174726 | Q2 | T2 DI TRINITY-MAPLE CRK 25/1 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 025/001 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-15 | 2022-06-15 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420631 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174727 | Q2 | T2 DI TRINITY-MAPLE CRK 25/1 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 025/001 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-15 | 2022-06-15 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420632 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174728 | Q2 | T2 DI TRINITY-MAPLE CRK 25/1 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 025/001 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-15 | 2022-06-15 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420633 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174824 | Q3 | T3NT DI CARIBOU #2 8/2 RMV POLE BUTT |  | CARIBOU #2 | 008/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-15 | 2022-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.221982 | 40.0135 | ETL.6280 | 40675402 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174891 | Q2 | T2 DI CLNDR SW STA-MESA 19/90 RPL HANGR | 44388365 | SAN LUIS OBISPO-SANTA MARIA | 019/090 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-04-15 | 2021-04-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.458676 | 35.0363 | ETL.3540 | 40636618 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174892 | Not Scheduled | T2 DI SLO-SM 19/90 RPL INSS | 31510359 | SAN LUIS OBISPO-SANTA MARIA | 019/090 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.458676 | 35.0363 | ETL.3540 | 40636618 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174898 | Q2 | T2 DI TRINITY-MAPLE CREEK 12/0 RPLC INSW | 31509759 | TRINITY-MAPLE CREEK | 012/000 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.129279 | 40.77 | ETL.8170 | 40638093 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174913 | Q3 | T2 DI CARIBOU #2 1/7 RMV PL BUTT |  | CARIBOU #2 | ;001/007 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-15 | 2022-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.96714 | 40.0089 | ETL.6280 | 40811553 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174917 | Q3 | T2 DI CARIBOU #2 0/16 RMV PL BUTT |  | CARIBOU #2 | ;000/016 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-15 | 2022-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.962593 | 40.021 | ETL.6280 | 40826432 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174991 | Q2 | DI HUMBOLDT-BRIDGEVILLE 91/3R RPL STRW | 31508093 | HUMBOLDT-BRIDGEVILLE | 091/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-11 | 2021-06-11 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322301 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174994 | Not Scheduled | T2 DI DIVIDE-CABRILLO #2 5/67 INST DAMW |  | DIVIDE-CABRILLO #2 | 005/067 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-05-26 | 2021-05-26 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436737 | 34.756 | ETL.1370 | 44296268 | Damper-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119174998 | Not Scheduled | T3 EI EAGLE RK-FLTN-SLRD 37/187 RPL INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 037/187 | 92E | E | 2020_(4) TD tag on high spread line |  | 2020-05-27 | 2020-11-27 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.65456 | 38.4971 | ETL.4392 | 40832918 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119175041 | Q2 | DI TRINITY-MAPLE CREEK 31/0R RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 031/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-15 | 2021-06-15 |  |  | 2021-06-05 | 2021-05-31 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.8170 | 44420661 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119175070 | Mar | T2 DI KILARC-DESCHUTES 16/337 RPR SPLW | 43930440 | KILARC-DESCHUTES | 016/337 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.115211 | 40.5635 | ETL.7300 | 40770409 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119175071 | Mar | T2 DI KILARC-DESCHUTES 16/337 RMV BUTT | 43930440 | KILARC-DESCHUTES | 016/337 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.115211 | 40.5635 | ETL.7300 | 40770409 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  | In Review | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119175075 | Q2 | T2 DI TRNTY-MAPLE CRK 27/5 RPL DAMW | 44364310 | TRINITY-MAPLE CREEK | 027/005 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-10 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420645 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119175079 | Q2 | T2 DI TRNTY-MAPLE CRK 27/5 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 027/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-12 | 2022-06-12 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420645 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119175138 | Q3 | T2 DI CARIBOU #2 14/5 RMV DEBRIS |  | CARIBOU #2 | 014/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2022-06-16 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.126589 | 40.0284 | ETL.6280 | 40768815 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119176141 | Q3 | T2 DI CARIBOU #2 :7/4 RPR WDPKR |  | CARIBOU #2 | :007/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2021-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.96202 | 39.9602 | ETL.6280 | 40769638 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119176156 | Q3 | T2 DI CARIBOU #2 015/000 RPR GYWW |  | CARIBOU #2 | 015/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.111573 | 40.0239 | ETL.6280 | 40614872 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119176369 | Q2 | T3 DI IGNACIO-BLINS #2 024/269 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 024/269 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2020-12-12 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.722347 | 37.9698 | ETL.7180 | 44360928 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119176429 | Q2 | T2 DI TRINITY-MAPLE CRK 31/3 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 031/003 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-12 | 2022-06-12 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.481094 | 40.6893 | ETL.8170 | 44769573 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119176487 | Mar | T2NT DI CRTINA-MNDCNO #1 56/278 RPR FOND |  | CORTINA-MENDOCINO #1 | 056/278 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2022-04-24 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.126379 | 39.2323 | ETL.1330 | 40861443 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119176695 | Q2 | T3 DI GYSRS #7-EGL RK-TWR 0/7 RPR FOND |  | GEYSERS #7-EAGLE ROCK | 000/007 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2020-12-16 |  |  | 2021-05-28 | 2021-05-24 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.810737 | 38.8173 | ETL.1680 | 40818237 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119176781 | Q2 | T3 DI VOLTA-DESCHUTES 7/151A RPL CRSW | 31507066 | VOLTA-DESCHUTES | 007/151A | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2020-12-12 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.996325 | 40.4918 | ETL.8290 | 43682177 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119176875 | Mar | T2 DI KILARC-DESCHUTES 16/332 RMV BUTT | 43930440 | KILARC-DESCHUTES | 016/332 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.110418 | 40.5635 | ETL.7300 | 40617694 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119176879 | Mar | T2 DI KILARC-DESCHUTES 16/332 RPR SPLW | 43930440 | KILARC-DESCHUTES | 016/332 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.110418 | 40.5635 | ETL.7300 | 40617694 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119176886 | Q2 | T3 DI MORAGA-SAN LEAN #1 1/12 RPR SPLS | 44621663 | MORAGA-SAN LEANDRO #1 | 001/012 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2020-12-15 |  |  | 2021-05-25 | 2021-05-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.153424 | 37.8274 | ETL.2770 | 40704858 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119176981 | Q2 | T2 DI TRINITY-MAPLE CRK 17/12C RPL POLE | 31509757 | TRINITY-MAPLE CREEK | 017/012 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420620 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119177089 | Q3 | T2 DI CARIBOU #2 1/12 RMV BUTT |  | CARIBOU #2 | ;001/012 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-16 | 2022-06-16 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.965895 | 40.0072 | ETL.6280 | 40664906 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119177168 | Q4 | T3 DI KESWICK-TRINITY 0/1 RMV BUTT | 43939188 | KESWICK-TRINITY | 000/001 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-12 | 2020-12-12 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.462303 | 40.6239 | ETL.7270 | 40586337 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119177385 | Mar | T2NT DI KILARC-DESCHUTES 12/252 RMV BUTT | 44406469 | KILARC-DESCHUTES | 012/252 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2022-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.034268 | 40.568 | ETL.7300 | 40617703 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119177602 | Mar | T3 DI CORTINA-MENDOCNO #1 14/69 RPR FOND |  | CORTINA-MENDOCINO #1 | 014/069 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2020-12-16 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.457354 | 39.0282 | ETL.1330 | 40860975 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119177658 | Feb | T3 DI DESABLA-CENTERVILLE 0/13 RPR GYWW | 44356201 | DESABLA-CENTERVILLE | 000/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2020-12-15 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.628393 | 39.8627 | ETL.6720 | 44751924 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119177901 | Mar | T2NT DI CRTN-MNDCINO #1 29/139 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 029/139 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-12 | 2022-06-12 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.718333 | 39.038 | ETL.1330 | 40872726 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119177906 | Not Scheduled | T3 DI BTTLE RCK TAP D.W.R. 0/2 RPR SHLDW |  | BOTTLE ROCK TAP D.W.R. | 000/002 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-16 | 2020-12-16 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.772374 | 38.833 | ETL.4771 | 40661119 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119178161 | Q3 | T2 DI CARIBOU #2 012/001 RPL SPLW |  | CARIBOU #2 | 012/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-17 | 2021-06-17 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.163964 | 40.0234 | ETL.6280 | 40585968 | Splice-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119178165 | Q3 | T2 DI CARIBOU #2 011/013 RPL INSW | 31506251 | CARIBOU #2 | 011/013 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-17 | 2021-06-17 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.166781 | 40.0216 | ETL.6280 | 40698208 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119178273 | Mar | T2 DI KILARC-DESCHUTES 17/353 RMV BUTT | 43930440 | KILARC-DESCHUTES | 017/353 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-17 | 2021-06-17 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.130379 | 40.5636 | ETL.7300 | 40602026 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119178275 | Mar | T2 DI KILARC-DESCHUTES 17/353 RPR SPLW | 43930440 | KILARC-DESCHUTES | 017/353 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-17 | 2021-06-17 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.130379 | 40.5636 | ETL.7300 | 40602026 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119178336 | Q3 | T2 DI CARIBOU #2 017/014 FILL HOLE |  | CARIBOU #2 | 017/014 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-15 | 2021-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.070987 | 40.021 | ETL.6280 | 40769559 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119178424 | Mar | DI LAURELES-OTTER 003/004 WDPKR | 44392379 | LAURELES-OTTER | 003/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-12 |  |  | 2021-03-24 | 2021-03-24 | [5 empty] | South | WSIP | [6 empty] | '-121.718817 | 36.4418 | ETL.7380 | 44562654 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119178427 | Mar | DI LAURELES-OTTER 003/004 WDPKR | 44392380 | LAURELES-OTTER | 003/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-12 |  |  | 2021-03-24 | 2021-03-24 | [5 empty] | South | WSIP | [6 empty] | '-121.718817 | 36.4418 | ETL.7380 | 44562655 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119178552 | Q2 | T3 EI WISHON-SAN JOAQUIN #3 4/5 RPL POLE | 31507342 | WISHON-SAN JOAQUIN #3 | 004/005 | 70Y | E | 2020_(1a) PSPS |  | 2020-06-17 | 2020-12-17 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-19 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.496555 | 37.1976 | ETL.9340 | 40763117 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-06 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119178672 | Q3 | T2NT DI CARIBOU #2 016/018 RMV PL BUTT |  | CARIBOU #2 | 016/018 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-16 | 2022-06-16 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.08645 | 40.0168 | ETL.6280 | 40868139 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119178742 | Q3 | T2 DI CARIBOU #2 016/018 REFRAME CRSW | 31507060 | CARIBOU #2 | 016/018 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-16 | 2021-06-16 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.08645 | 40.0168 | ETL.6280 | 40868139 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119178743 | Q3 | T2NT DI CARIBOU #2 017/028 RMV PL BUTT |  | CARIBOU #2 | 017/028 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2022-06-16 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.061832 | 40.0205 | ETL.6280 | 40862055 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119178748 | Mar | T2NT DI KILARC-DESCHUTS 12/255 RMV DEBRI | 44406469 | KILARC-DESCHUTES | 012/255 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2022-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.037095 | 40.5673 | ETL.7300 | 40656984 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119178749 | Q2 | T2 DI MI-WUK-CURTIS 023/000 RPL POLE | 31508526 | ETL.1073.POLE.WOOD | 023/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.268287 | 38.0062 | ETL.1073 | 40580228 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119178908 | Q2 | T2 DI TRINITY-MAPLE CRK 20/3 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 020/003 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-12 | 2021-06-12 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.264976 | 40.724 | ETL.8170 | 44564200 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119178983 | Mar | T2NT DI KILARC-DSCHUTS 12/266 RMV BUTT | 44406469 | KILARC-DESCHUTES | 012/266 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2022-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.046501 | 40.5649 | ETL.7300 | 40771246 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179064 | Not Scheduled | T2 DI MORRO BAY-TEMPLETON 12/51 RPL INSS | 31527001 | MORRO BAY-TEMPLETON | 012/051 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.716774 | 35.5147 | ETL.5933 | 40612025 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179067 | Q4 | T3 EI MDL FRK-GLD HL 16/131B RPR WDPK | 44361894 | MIDDLE FORK-GOLD HILL | 016/131B | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.839312 | 38.9202 | ETL.5140 | 42569842 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179068 | Q4 | T3 EI MDL FRK-GLD HL 16/131C RPR STRW | 44361894 | MIDDLE FORK-GOLD HILL | 016/131C | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-27 | 2020-11-27 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.839394 | 38.9203 | ETL.5140 | 42569844 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179072 | Mar | T2NT DI KILARC-DESCHUTES 12/266 RPR STRW | 44406469 | KILARC-DESCHUTES | 012/266 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.046501 | 40.5649 | ETL.7300 | 40771246 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179079 | Q3 | T2 DI CARIBOU #2 :002/017 RPR STRW |  | CARIBOU #2 | :002/017 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-16 | 2021-06-16 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.02556 | 39.999 | ETL.6280 | 40809572 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179162 | Q2 | T3 EI WISHON-SAN JOAQUIN #3 4/4 RPL POLE | 31507342 | WISHON-SAN JOAQUIN #3 | 004/004 | 70Y | E | 2020_(1a) PSPS |  | 2020-06-17 | 2020-12-17 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-19 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.496547 | 37.1988 | ETL.9340 | 40764489 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  | Y - 17 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-06 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119179256 | Mar | T2NT DI KILARC-DESCHUTES 17/367 RMV BUTT | 44406469 | KILARC-DESCHUTES | 017/367 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2022-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.145169 | 40.5636 | ETL.7300 | 40827912 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179259 | Mar | T2 DI KILARC-DESCHUTES 17/354 RMV BUTT | 44406469 | KILARC-DESCHUTES | 017/354 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.131304 | 40.5636 | ETL.7300 | 40676539 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179362 | Mar | T2 DI KILARC-DESCHUTES 17/354 RPR STRW | 44406469 | KILARC-DESCHUTES | 017/354 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.131304 | 40.5636 | ETL.7300 | 40676539 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179367 | Mar | T2 DI KILARC-DESCHUTES 16/342 RMV BUTT | 44406469 | KILARC-DESCHUTES | 016/342 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.120023 | 40.5635 | ETL.7300 | 40617715 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179396 | Q2 | T3NT DI DRUM-SPAULDING 01/027 RMV BUTT | 44371592 | DRUM-SPAULDING | 001/027 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-17 | 2022-06-17 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.74982 | 39.2533 | ETL.6770 | 44874802 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179399 | Q2 | T3 DI DRUM-SPAULDING 01/027 RRL INSW | 31507364 | DRUM-SPAULDING | 001/027 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-17 | 2020-12-17 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.74982 | 39.2533 | ETL.6770 | 44874817 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179487 | Mar | T2NT DI KILARC-DESCHUTES 11/246 BTT | 44406469 | KILARC-DESCHUTES | 011/246 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2022-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.029125 | 40.5693 | ETL.7300 | 40816232 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179489 | Mar | T2 DI KILARC-DESCHUTES 15/325 RPR STRW | 44406469 | KILARC-DESCHUTES | 015/325 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.103894 | 40.5636 | ETL.7300 | 40668429 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179600 | Not Scheduled | T3 EI WISHON-SAN JQN #3 004/004 CANCEL | 31521754 | WISHON-SAN JOAQUIN #3 | 004/004 | 71Y | E | 2020_(1a) PSPS |  | 2020-06-17 | 2020-12-17 |  |  |  | 2021-01-04 |  |  | CANCEL/CNCL | TR3 | LATE | South | WSIP | [6 empty] | '-119.496547 | 37.1988 | ETL.9340 | 40764489 | Road | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119179635 | Mar | T3NT DI DEER CREEK-DRUM 3/80 RMV BUTT | 44371580 | DEER CREEK-DRUM | 003/080 | ICW | F | 2020_(1a) PSPS |  | 2020-06-15 | 2022-06-15 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.8133 | 39.2626 | ETL.6690 | 40756928 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119179685 | Not Scheduled | T2 DI MORRO BAY-MESA 019/087 CANCEL |  | MORRO BAY-MESA | 019/087 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.60551 | 35.1823 | ETL.5290 | 40844460 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-07 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179879 | Not Scheduled | T3 DI MORAGA-OAKLND #1 1/13 WAS INSU | 44598173 | MORAGA-OAKLAND #1 | 001/013 | ICD | F | 2020_(4) TD tag on high spread line |  | 2020-06-15 | 2022-06-15 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.19172 | 37.8357 | ETL.2720 | 40689688 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 14 |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179992 | Not Scheduled | T3 DI MORAGA-OAKLND #1 1/13 RMV DEBRIS | 44598172 | MORAGA-OAKLAND #1 | 001/013 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-15 | 2022-06-15 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.19172 | 37.8357 | ETL.2720 | 40659393 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not Scheduled | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119179997 | Mar | T2 DI KILARC-DESCHUTES 15/320 RPR POLE | 43930440 | KILARC-DESCHUTES | 015/320 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-12 | 2021-06-12 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.099207 | 40.5638 | ETL.7300 | 40868575 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180127 | Mar | T2 DI KILARC-DESCHUTES 013/283 RPLC STRW | 31507647 | KILARC-DESCHUTES | 013/283 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.063947 | 40.5645 | ETL.7300 | 40617709 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180185 | Feb | T3 MORAGA-OAKLAND #1 2/017 RPR FOND |  | MORAGA-OAKLAND #1 | 002/017 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-17 | 2020-12-17 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.200509 | 37.8306 | ETL.2720 | 40805690 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180242 | Mar | T2 DI KILARC-DESCHUTES 013/287 RPL STRW | 31507647 | KILARC-DESCHUTES | 013/287 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.067342 | 40.5646 | ETL.7300 | 41118604 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180349 | Mar | T3 PARKWAY-MORAGA 20/112 RPR INSS | 44609779 | PARKWAY-MORAGA | 020/112 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-17 | 2020-12-17 |  |  | 2021-03-16 | 2021-03-16 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.2013071 | 37.8781 | ETL.5930 | 40841800 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180383 | Mar | T2 DI KILARC-DESCHUTES 015/328 RPLC STRW | 31507647 | KILARC-DESCHUTES | 015/328 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.106836 | 40.5635 | ETL.7300 | 40827922 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180387 | Mar | T2 DI KILARC-DESCHUTES 15/328 CANCEL | 44406469 | KILARC-DESCHUTES | 015/328 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-122.106836 | 40.5635 | ETL.7300 | 40827922 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180427 | Mar | T2 DI KILARC-DESCHUTES 16/338 RPL STRW | 31507647 | KILARC-DESCHUTES | 016/338 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.116166 | 40.5635 | ETL.7300 | 40817230 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  | In Review | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180506 | Mar | T2 HUMBOLDT-TRINITY 93/009L RPR STRW | 44356920 | HUMBOLDT-TRINITY | 093/009 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-17 | 2021-06-17 |  |  | 2021-03-17 | 2021-03-17 |  |  | Likely MAT error - delink to correct | TR2 |  | North Coast | WSIP | [6 empty] | '-123.74829 | 40.7493 | ETL.1820 | 44926653 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180552 | Q4 | T3NT DI MAPLE CREEK-HPA 10/11 RMV BUTTS | 44301081 | MAPLE CREEK-HOOPA | 010/011 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-12 | 2022-06-12 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.771278 | 40.8921 | ETL.7490 | 40602127 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180587 | Not Scheduled | T2 DRUM-SUMMIT #1 7/089L INST DAMPERS | 44391347 | DRUM-SUMMIT #1 | 007/089 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-17 | 2021-06-17 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.660649 | 39.3115 | ETL.1440 | 44767650 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180644 | Not Scheduled | T3 EI COLGATE-ALLEGHANY 19/513 REPL SPLW | 44365653 | COLGATE-ALLEGHANY | 019/513 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-17 | 2020-12-17 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.923791 | 39.4532 | ETL.6470 | 40611344 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180647 | Not Scheduled | T3 EI COLGATE-ALLEGHANY 017/481 RPR ADSS | 44371190 | COLGATE-ALLEGHANY | 017/481 | ICW | F | 2020_(2) High fire spread TD |  | 2020-06-17 | 2022-06-17 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.945089 | 39.4509 | ETL.6470 | 40767336 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180726 | Not Scheduled | T3 FULTON-CALISTOGA :008/001 INST DAMPER | 44597303 | FULTON-CALISTOGA | :008/001 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-17 | 2020-12-17 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.599351 | 38.7014 | ETL.6880 | 40912491 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180832 | Mar | T2 DI KILARC-DESCHUTES 15/326 RPR STRW | 44406469 | KILARC-DESCHUTES | 015/326 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.104936 | 40.5636 | ETL.7300 | 40771255 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180899 | Q3 | T2 DI CARIBOU #2 9/6 RMV BUTT |  | CARIBOU #2 | 009/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-17 | 2022-06-17 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.203507 | 40.0136 | ETL.6280 | 40826361 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180900 | Mar | T2NT DI KILARC-DSCHUTS 13/282 RMV DEBRIS | 44406469 | KILARC-DESCHUTES | 013/282 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2022-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.062375 | 40.5644 | ETL.7300 | 40876526 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180908 | Mar | T2 DI KILARC-DESCHUTES 15/327 RMV BUTT | 44406469 | KILARC-DESCHUTES | 015/327 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.10587 | 40.5635 | ETL.7300 | 40770411 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180951 | Mar | T2 DI KILARC-DESCHUTES 15/327 RPR STRW | 44406469 | KILARC-DESCHUTES | 015/327 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.10587 | 40.5635 | ETL.7300 | 40770411 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180968 | Mar | T2 KILARC-DESCHUTES 13/284 RMV BUTT | 44406470 | KILARC-DESCHUTES | 013/284 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2022-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.064963 | 40.5645 | ETL.7300 | 40602027 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180976 | Q3 | T2NT DI CARIBOU #2 14/26 REFRAME | 31507060 | CARIBOU #2 | 014/026 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.11309 | 40.0244 | ETL.6280 | 40816778 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180984 | Not Scheduled | T3 DI COLGATE-CHALLENGE 4/82 RPL STRW | 31515208 | COLGATE-CHALLENGE | 004/082 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2020-12-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.16265 | 39.3815 | ETL.6480 | 40693047 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-08-21 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119180985 | Q2 | T3 DI W. PNT-VLY SPRNGS 3/48 RPL POLE | 31506674 | WEST POINT-VALLEY SPRINGS | 003/048 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2020-12-16 |  |  | 2021-04-03 | 2021-03-29 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.608384 | 38.4078 | ETL.8350 | 40603877 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181022 | Q3 | T2 DI CARIBOU #2 8/19 RMV PL BUTT |  | CARIBOU #2 | 008/019 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-17 | 2022-06-17 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.21292 | 40.0165 | ETL.6280 | 40861853 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181033 | Q3 | T2 DI CARIBOU #2 9/14 RMV BUTT |  | CARIBOU #2 | 009/014 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-17 | 2022-06-17 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.198082 | 40.0137 | ETL.6280 | 40769477 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181045 | Not Scheduled | T2 DI TIGER CREEK-ELECTRA 9/70 RMV STEP |  | TIGER CREEK-ELECTRA | 009/070 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-05-31 | 2021-05-31 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.634276 | 38.3898 | ETL.5780 | 40591468 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 15 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181080 | Q3 | T2 DI CARIBOU #2 9/19 RMV PL BUTT |  | CARIBOU #2 | 009/019 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-17 | 2022-06-17 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.194881 | 40.0133 | ETL.6280 | 44217537 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181081 | Q3 | T2 DI CARIBOU #2 9/19 RPR GYWW |  | CARIBOU #2 | 009/019 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-17 | 2021-06-17 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.194881 | 40.0133 | ETL.6280 | 44217537 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181088 | Q2 | T2 DI MI-WUK-CURTIS 25/1 RPLC STRW | 31508526 | ETL.1073.POLE.WDPS | 025/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-17 | 2021-06-17 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.294459 | 37.9858 | ETL.1073 | 44774791 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181093 | Q3 | T2 DI CARIBOU #2 :4/12 RPL STRW | 31508138 | CARIBOU #2 | :004/012 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-15 | 2021-06-15 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.999276 | 39.9826 | ETL.6280 | 40675658 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181484 | Q3 | T2 DI CARIBOU #2 9/7 RMV PL BUTT |  | CARIBOU #2 | 009/007 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-17 | 2022-06-17 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.202621 | 40.0137 | ETL.6280 | 40824568 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181489 | Q3 | T2 DI CARIBOU #2 9/7 REFRAME | 31507060 | CARIBOU #2 | 009/007 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-17 | 2021-06-17 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.202621 | 40.0137 | ETL.6280 | 40824568 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181504 | Not Scheduled | T3 DI COLGATE-CHALLENGE 4/97 RMV BUTT | 44371192 | COLGATE-CHALLENGE | 004/097 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-15 | 2020-12-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.159607 | 39.3936 | ETL.6480 | 40866891 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181506 | Mar | T3NT DI BRUNSWICK #1 005/041 RPR FOND | 44370736 | BRUNSWICK #1 TAP | 005/041 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-15 | 2022-06-15 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.034153 | 39.2124 | ETL.1422 | 40586112 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181545 | Q3 | T2 DI CARIBOU #2 9/11 RMV PL BUTT |  | CARIBOU #2 | 009/011 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-17 | 2022-06-17 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.200047 | 40.014 | ETL.6280 | 40591750 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181548 | Q3 | T2 DI CARIBOU #2 9/11 REFRAME | 31507060 | CARIBOU #2 | 009/011 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-17 | 2021-06-17 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.200047 | 40.014 | ETL.6280 | 40591750 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181617 | Mar | T2 DI KILARC-DESCHUTES 16/343 RMV BUTT | 44406469 | KILARC-DESCHUTES | 016/343 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.120968 | 40.5635 | ETL.7300 | 40602009 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181671 | Mar | T2 DI KILARC-DESCHUTES 16/343 RPR STRW | 44406469 | KILARC-DESCHUTES | 016/343 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.120968 | 40.5635 | ETL.7300 | 40602009 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181678 | Mar | T2 DI KILARC-DESCHUTES 15/330 RMV BUTT | 44406469 | KILARC-DESCHUTES | 015/330 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.108495 | 40.5635 | ETL.7300 | 40877874 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181757 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 15/407 RPR GYWW | 44371191 | COLGATE-ALLEGHANY | 015/407 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-17 | 2020-12-17 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.9934 | 39.4455 | ETL.6470 | 40874813 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181826 | Q2 | T2 EI FRT RS-GUALALA 30/9 RPLC POLE | 31506296 | GUALALA-MONTE RIO | 030/009 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-18 | 2021-06-18 | 2021-06-15 | 2021-06-17 | 2021-06-17 | 2021-06-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.247692 | 38.5502 | ETL.6980 | 40871392 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181860 | Q2 | T2 DI FORT ROSS-GUALALA 32/5 RPR GYWW |  | GUALALA-MONTE RIO | 032/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-04-24 | 2021-04-24 | 2021-06-15 | 2021-06-18 | 2021-06-17 | 2021-06-17 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.271491 | 38.5616 | ETL.6980 | 40750297 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119181900 | Q2 | T3NT DI GEYSERS #17-FULTON 0/3 RPR FOND | 44637021 | GEYSERS #17-FULTON | 000/003 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-17 | 2022-06-17 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.785374 | 38.824 | ETL.4770 | 40654446 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119182232 | Not Scheduled | T3 DI MORAGA-OAKLND #2 1/13 WAS INSS | 44598173 | MORAGA-OAKLAND #2 | 001/013 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-06-15 | 2020-12-15 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.19172 | 37.8357 | ETL.2730 | 40689689 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119182371 | Q2 | T2 DI FORT ROSS-GUALALA 035/1 RPR GYWW |  | GUALALA-MONTE RIO | 035/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-16 | 2021-06-16 | 2021-06-15 | 2021-06-18 | 2021-06-16 | 2021-06-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.300814 | 38.5879 | ETL.6980 | 40584647 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119182464 | Q2 | T2 DI TRINITY-MAPLE CRK 20/3 RPR STRW | 44273074 | TRINITY-MAPLE CREEK | 020/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-12 | 2021-06-12 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.264976 | 40.724 | ETL.8170 | 44564200 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119182832 | Not Scheduled | T3 DI TGR CRK-ELCTR-TWR 7/61 RMV HRDS |  | TIGER CREEK-ELECTRA | 007/061 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2020-12-16 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.614207 | 38.4042 | ETL.5780 | 40593868 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119182864 | Mar | T2 DI CRTN-MNDCN #1-TWR 16/77 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 016/077 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-16 | 2022-06-16 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.483577 | 39.0169 | ETL.1330 | 40809327 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119182902 | Q2 | T2 DI FORT ROSS-GUALALA 035/9 RPL POLE | 31508619 | GUALALA-MONTE RIO | 035/009 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-16 | 2021-06-16 | 2021-06-15 | 2021-06-18 | 2021-06-16 | 2021-06-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.302503 | 38.597 | ETL.6980 | 40876072 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119183107 | Q2 | T3NT DI PTSBRG-SN RMN-TWR 12/47 RPR FOND |  | PITTSBURG-SAN RAMON | 012/047 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2022-06-16 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.882078 | 37.8769 | ETL.5490 | 40805035 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119183191 | Not Scheduled | MSTNG SW STA-GRGG X52/219 RMV DEBRIS | 44389951 | GATES-GREGG | X052/219 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-06-18 | 2021-06-18 | [8 empty] | WECC | South | WSIP | [6 empty] | '-119.897184 | 36.768 | ETL.4700 | 40866280 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-30 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119183553 | Mar | T3NT DI MRG-SN LNDR #3-TWR 2/16 RPR FOND | 44303862 | MORAGA-SAN LEANDRO #3 | 002/016 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-17 | 2022-06-17 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.146351 | 37.822 | ETL.2790 | 40822221 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119183632 | Q3 | T2 DI CARIBOU #2 17/26 RPR GYWW |  | CARIBOU #2 | 017/026 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.06235 | 40.0214 | ETL.6280 | 40826407 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119183687 | Mar | T3 DI MORAGA-OAKLAND #2 2/17A RPLC INSS |  | MORAGA-OAKLAND #2 | 002/017A | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2020-12-16 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.201135 | 37.8304 | ETL.2730 | 40577583 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119184250 | Q3 | T3 DI DONNELLS-MI-WUK 0/2 RPR GYWW | 44623242 | DONNELLS-CURTIS | 000/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-26 | 2020-11-26 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.034319 | 38.2449 | ETL.1400 | 44379630 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119184252 | Q3 | T3 DI DONNELLS-MI-WUK 0/2 RPR GYWW | 44623243 | DONNELLS-CURTIS | 000/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-26 | 2020-11-26 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.034319 | 38.2449 | ETL.1400 | 44379631 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119184254 | Mar | T2 DI KILARC-DESCHUTES 13/276 RPR STRW | 44406469 | KILARC-DESCHUTES | 013/276 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.055104 | 40.5641 | ETL.7300 | 40668432 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119184469 | Not Scheduled | T3 DI MORAGA-OAKLAND J 1/13 HANGER | 44611129 | MORAGA-OAKLAND "J" | 001/013 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-06-17 | 2020-12-17 | 2021-03-31 | 2021-03-31 | [5 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.151492 | 37.8261 | ETL.2760 | 40676704 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119184574 | Mar | T3 DI MORAGA-OAKLAND ""J"" 1/13 RPL INSS | 31511127 | MORAGA-OAKLAND "J" | 001/013 | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-17 | 2020-12-17 |  |  | 2021-03-31 | 2021-03-31 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.151055 | 37.8265 | ETL.2760 | 40676704 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119184796 | Mar | T2NT DI KILARC-DSCHUTS 11/249 RMV DEBRIS | 44406469 | KILARC-DESCHUTES | 011/249 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2022-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.031697 | 40.5686 | ETL.7300 | 40600393 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119184995 | Mar | T2 DI KILARC-DESCHUTS 17/366A RMV BUTT | 44406469 | KILARC-DESCHUTES | 017/366A | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.144097 | 40.5637 | ETL.7300 | 44416928 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119185025 | Mar | T2 DI KILARC-DESCHUTES 17/352 RPR SPLW | 43930440 | KILARC-DESCHUTES | 017/352 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.129414 | 40.5636 | ETL.7300 | 40590493 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119185070 | Mar | T2 DI KILARC-DESCHUTES 17/352 RMV PL BUT | 43930440 | KILARC-DESCHUTES | 017/352 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.129414 | 40.5636 | ETL.7300 | 40590493 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119185096 | Q2 | T3 DI SOBRANTE""R"" #1+ 0/7 RMV STEP | 44624391 | SOBRANTE-R #1 | 000/007 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-06-16 | 2020-12-16 |  |  | 2021-05-15 | 2021-05-10 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.225265 | 37.904 | ETL.3770 | 40804917 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119185113 | Q2 | T3NT DI EGL RCK-FLTN-SLVRD 6/32 RPR FOND | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 006/032 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-17 | 2022-06-17 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.781832 | 38.7513 | ETL.4392 | 40683484 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119185429 | Not Scheduled | T3 FRNCH MDWS-MDDLE FRK 9/182 INST DAMP | 44371596 | FRENCH MEADOWS-MIDDLE FORK | 009/182 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-18 | 2020-12-18 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.561664 | 39.0162 | ETL.6870 | 40751850 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119185791 | Q2 | DI GATES-PANOCHE #1 3/18 MASTIC | 44389944 | GATES-PANOCHE #1 | 003/018 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-06-18 | 2022-06-18 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.158512 | 36.1828 | ETL.4720 | 40863628 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119185837 | Q2 | T3 DI MNTA VSTA-CYT SS 17/84 RPL INSS | 31507834 | MONTA VISTA-COYOTE SW STA | 017/084 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-04-03 | 2020-12-16 | 2021-05-16 | 2021-05-16 | 2021-05-16 | 2021-05-16 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-122.017352 | 37.2068 | ETL.5090 | 40782451 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Moss Landing |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119185860 | Q2 | T2 DI MI-WUK-CURTIS 26/000 RPR STRW | 44623244 | ETL.1073.POLE.WDPS | 026/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-17 | 2021-06-17 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.307425 | 37.9761 | ETL.1073 | 44770809 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119185862 | Mar | DI FULTON-HOPLAND 10/1 RPR GYWW | 44579280 | FULTON-HOPLAND | 010/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-18 | 2021-06-18 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.843602 | 38.6156 | ETL.6890 | 40601387 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119185866 | Mar | DI FULTON-HOPLAND 10/1 GROUNDWASH | 44592820 | FULTON-HOPLAND | 010/001 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-06-18 | 2021-06-18 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.843602 | 38.6156 | ETL.6890 | 40628076 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119185895 | Mar | T2 DI MORAGA-CSTRO VALLEY 12/55 RPL INSS | 31526489 | MORAGA-CASTRO VALLEY | 012/055 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-06-17 | 2021-06-17 |  |  | 2021-03-09 | 2021-03-09 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.049622 | 37.7084 | ETL.5250 | 40788236 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119185898 | Mar | T2 DI CRTA MDCN #1 54/270 RMV HRDT |  | CORTINA-MENDOCINO #1 | 054/270 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-16 | 2021-06-16 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.094164 | 39.224 | ETL.1330 | 40587921 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119185913 | Q2 | T3 DI GEYSERS #12-FULTON 20/84 RPR FOUND | 44631264 | GEYSERS #12-FULTON | 020/084 | ICS | F | 2020_(2) High fire spread TD |  | 2020-04-09 | 2022-04-09 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.742383 | 38.5727 | ETL.4750 | 40761390 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119185936 | Not Scheduled | DI GATES PANOCHE #1 5/28 RMV DEBRIS | 44389953 | GATES-PANOCHE #1 | 005/028 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-06-18 | 2021-06-18 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.179501 | 36.2089 | ETL.4720 | 40863630 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119185981 | Not Scheduled | T3 DI ORAGA-SAN LEANDRO #1 0/1 WASH INSS | 44598174 | MORAGA-SAN LEANDRO #1 | 000/001 | ICD | E | 2020_(2) High fire spread TD |  | 2020-04-07 | 2020-12-17 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.160858 | 37.8469 | ETL.2770 | 40604490 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 15 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119186030 | Not Scheduled | T3 DI TIGER CREEK-ELECTRA 7/60 RPL INSS | 31511365 | TIGER CREEK-ELECTRA | 007/060 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-05-31 | 2020-11-30 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.613317 | 38.4049 | ETL.5780 | 40631086 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119186031 | Not Scheduled | T3 DI TIGER CREEK-ELECTRA 7/60 RPL HRDS |  | TIGER CREEK-ELECTRA | 007/060 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-05-31 | 2020-11-30 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-120.612794 | 38.4052 | ETL.5780 | 40591465 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-26 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119186816 | Q2 | T3 DI SOBRANTE-""""R"""" #1 1/8 RPR STRT | 44624391 | SOBRANTE-R #1 | 001/008 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-06-17 | 2020-12-17 |  |  | 2021-05-15 | 2021-05-10 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.229863 | 37.9052 | ETL.3770 | 40857873 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 12 | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119186878 | Mar | T3 DI KILARC-CEDAR CREEK 0/1 BOND GUY | 43930440 | KILARC-DESCHUTES | 000/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-05-22 | 2020-11-22 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.872795 | 40.6778 | ETL.7300 | 40701858 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  | In Review | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119186901 | Not Scheduled | DI SLO-SM 17/76B RPLC INSS | 31510359 | SAN LUIS OBISPO-SANTA MARIA | 017/076B | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-06-18 | 2021-06-18 | [9 empty] | South | WSIP | [6 empty] | '-120.480763 | 35.0667 | ETL.3540 | 40741416 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119187190 | Q2 | T3NT DI GYRS #12-FLTN-TWR 23/96 RPR FOND |  | GEYSERS #12-FULTON | 023/096 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-18 | 2022-06-18 |  |  | 2021-05-21 | 2021-05-17 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.7518 | 38.5299 | ETL.4750 | 40814636 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119187191 | Q2 | T3 DI SOBRANTE""G""#1""-TWR 2/16 RPR FOND | 44624390 | SOBRANTE-"G" #1 | 002/016 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-06-18 | 2020-12-18 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.252525 | 37.9116 | ETL.3720 | 40804931 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119187205 | Q2 | T2 PIT #5-ROUND MTN #1 11/112 RPL INSW | 31526971 | PIT #5-ROUND MTN #1 | 011/112 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-19 | 2021-06-19 |  |  | 2021-06-18 | 2021-06-17 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.93282 | 40.8344 | ETL.5420 | 40792848 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119187515 | Q2 | T2 DI CRESTA-RIO OSO 29/235 RPR INSS |  | CRESTA-RIO OSO | 029/235 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-19 | 2021-06-19 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.535578 | 39.5565 | ETL.4590 | 41140730 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119187519 | Not Scheduled | T3NT DI SNTH LN-HLF ;2/21 RMV BUTT | 44621950 | SNEATH LANE-HALF MOON BAY | ;002/021 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-19 | 2022-06-19 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.469905 | 37.6016 | ETL.7212 | 40599236 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119187540 | Q3 | T2 DI CARIBOU #2 016/027 BACKFILL HOLE |  | CARIBOU #2 | 016/027 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-18 | 2021-06-18 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.081523 | 40.0189 | ETL.6280 | 40815753 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119187676 | Q2 | T3 DI FULTON-IGNACIO#1 3/18 RPR FOND | 44310479 | FULTON-IGNACIO #1 | 003/018 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-04-14 | 2022-04-14 |  |  | 2021-04-23 | 2021-04-19 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.705789 | 38.4971 | ETL.4680 | 40863592 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119187803 | Q2 | T3 DI MTCLF-MOSS LNDG 41/181 RMV STEP | 44571497 | METCALF-MOSS LANDING #1 | 041/181 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-04-16 | 2020-12-18 |  |  | 2021-05-21 | 2021-05-03 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.667191 | 37.0394 | ETL.5100 | 40594684 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119187805 | Q3 | T2 DI CARIBOU#2 ;1/16 RMV BUTT |  | CARIBOU #2 | ;001/016 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-19 | 2022-06-19 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.963747 | 40.0055 | ETL.6280 | 40812209 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119188144 | Q2 | T3 DI TIGER CREEK-ELECTRA 2/17 RPR STRT |  | TIGER CREEK-ELECTRA | 002/017 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-06-18 | 2020-12-18 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.5258 | 38.4402 | ETL.5780 | 40821587 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-26 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119188147 | Not Scheduled | T3 DI GEYSERS #9-LAKEVILL :4/23 RPR INSS |  | GEYSERS #9-LAKEVILLE | :004/023 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-18 | 2020-12-18 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.76287 | 38.7431 | ETL.4780 | 40676810 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119188149 | Q3 | T2NT DI CARIBOU#2 ;1/21 RMV BUTT |  | CARIBOU #2 | ;001/021 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-19 | 2022-06-19 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.961303 | 40.0037 | ETL.6280 | 40600644 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119188432 | Q3 | DI GTS-MSTNG SW ST #1 2/14 BENT STL | 44389942 | SPARE T-LINE RECORD | 002/014 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-18 | 2021-06-18 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.081367 | 36.158 | ETL.2604 | 40746626 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119188436 | Q2 | T3NT DI TGR CRK-VLY SPRNGS 5/42 RPR FOND |  | TIGER CREEK-VALLEY SPRINGS | 005/042 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-18 | 2022-06-18 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.581218 | 38.4244 | ETL.5790 | 40645135 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119188449 | Q3 | T2 EI BRIDGEVILLE-GARBERVILLE 22/4 REFRA | 31511889 | BRIDGEVILLE-GARBERVILLE | 022/004 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-19 | 2021-06-19 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.751177 | 40.2152 | ETL.6220 | 40752629 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119188460 | Q3 | EI T2NT BRDGVLLE-GRBRVLLE 22/4 RMV PL BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 022/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-19 | 2022-06-19 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.751177 | 40.2152 | ETL.6220 | 40752629 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119188471 | Q3 | T2 EI BRIDGEVILLE-GARBERVILLE 22/4 RPL A | 31508615 | BRIDGEVILLE-GARBERVILLE | 022/004 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-19 | 2021-06-19 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.751177 | 40.2152 | ETL.6220 | 40752629 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119188478 | Feb | T2 DRUM-RIO OSO #2 22/170 RPR INSLS | 44391340 | DRUM-RIO OSO #2 | 022/170 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-19 | 2021-06-19 |  |  | 2021-02-23 | 2020-12-14 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.120263 | 39.0963 | ETL.1430 | 44934901 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119188623 | Not Scheduled | T2 MONTE RIO-FORT ROSS 26/5 RPL POLE | 31509661 | ETL.6979.POLE.WOOD | 026/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-19 | 2021-06-19 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.195356 | 38.5074 | ETL.6979 | 40750295 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119188626 | Not Scheduled | T2 EI BRIDGEVILLE-GARBERVILLE - CANCEL |  | BRIDGEVILLE-GARBERVILLE | 022/003 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-19 | 2021-06-19 | [6 empty] | CANCEL/CNCL | TR2 |  | North Coast | WSIP | [6 empty] | '-123.751942 | 40.2159 | ETL.6220 | 40650770 | Anchor-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119188665 | Mar | T2 DI CORTIN-MENDOCINO#1 26/123 MASTIC |  | CORTINA-MENDOCINO #1 | 026/123 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-18 | 2022-06-18 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.657504 | 39.0291 | ETL.1330 | 40648761 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119188712 | Not Scheduled | MONTE RIO-FORT ROSS 22/008 INS DAMPER |  | ETL.6979.POLE.WOOD | 022/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-19 | 2021-06-19 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.141168 | 38.4753 | ETL.6979 | 40860942 | Damper-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119188913 | Feb | T2 STANISLAUS-MANTECA #2 9/59 RPR INSLS | 44566009 | STANISLAUS-MANTECA #2 | 009/059 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-19 | 2021-06-19 |  |  | 2021-02-26 | 2021-02-26 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.5221576 | 38.0649 | ETL.3820 | 40883236 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 26 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119188949 | Mar | T2 DI KILARC-DESCHUTES 14/292 RMV BUTT | 44406469 | KILARC-DESCHUTES | 014/292 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-18 | 2022-06-18 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.072216 | 40.5647 | ETL.7300 | 40600402 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119189046 | Q2 | T2 MELONES-CURTIS 9/3 RMV DEBRIS | 44623245 | MELONES-CURTIS | 009/003 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-19 | 2021-06-19 |  |  | 2021-04-02 | 2021-03-02 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.403585 | 37.9428 | ETL.2390 | 44391057 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 18 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119189076 | Not Scheduled | T2 DRUM-SUMMIT #2 7/086 RPR GYWW | 44391349 | DRUM-SUMMIT #2 | 007/086B | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-19 | 2021-06-19 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.662314 | 39.3112 | ETL.1450 | 44159090 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119189097 | Feb | T3 DI CORTINA-MENDOCINO#1 18/89 RPR OPGW | 44610540 | CORTINA-MENDOCINO #1 | 018/089 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-19 | 2020-12-19 |  |  | 2021-02-18 | 2021-02-01 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.533151 | 39.0039 | ETL.1330 | 40860979 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119189101 | Not Scheduled | T3NT DI COLGATE-CHALLENGE 1/29 RMV BUTT | 44371193 | COLGATE-CHALLENGE | 001/029 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-19 | 2022-06-19 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.18562 | 39.3473 | ETL.6480 | 40824182 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119189102 | Not Scheduled | T3 DI COLGATE-CHALLENGE 1/29 RPR SPLW | 44365653 | COLGATE-CHALLENGE | 001/029 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-19 | 2020-12-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.18562 | 39.3473 | ETL.6480 | 40824182 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119189164 | Q3 | T2 EI BRIDGEVILLE-GARBERVLLE 21/12 RPL S | 31508614 | BRIDGEVILLE-GARBERVILLE | 021/012 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-19 | 2021-06-19 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.756258 | 40.2198 | ETL.6220 | 40661882 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119189213 | Q2 | T2 TRNTY-MPL CRK 18/015 RPR CONDUCTOR | 44364310 | TRINITY-MAPLE CREEK | 018/015 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-19 | 2021-06-19 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.242441 | 40.7371 | ETL.8170 | 40752260 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119189513 | Q2 | T3 DI SOBRANTE ""R"" 1/10 RMV STEP | 44624391 | SOBRANTE-R #1 | 001/010 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-04-06 | 2020-12-18 |  |  | 2021-05-15 | 2021-05-10 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.236906 | 37.9071 | ETL.3770 | 40581867 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 12 | EBMUD | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119189637 | Q2 | T2 LAKEVILLE #2 12/257 INS DAMPER |  | LAKEVILLE #2 | 012/257 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-19 | 2021-06-19 |  |  | 2021-05-21 | 2021-05-18 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.697764 | 38.2902 | ETL.7340 | 40825816 | Damper-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119190165 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 9/262 RMV PL BUTT | 44371191 | COLGATE-ALLEGHANY | 009/262 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-19 | 2020-12-19 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.037237 | 39.3772 | ETL.6470 | 40767334 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119190286 | Q2 | T2 TRINITY-MPL CRK 42/002A INST DAMPER | 44364310 | TRINITY-MAPLE CREEK | 042/002A | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-19 | 2021-06-19 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.66822 | 40.7289 | ETL.8170 | 44947102 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119190325 | Feb | T2 VACA-SUISUN 007/059 RPL INSS CMPLT | 31507028 | VACA-SUISUN | 007/059 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-06-19 | 2021-06-19 |  |  | 2021-02-15 | 2021-02-15 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.025925 | 38.3469 | ETL.4070 | 40887573 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119190471 | Mar | T3 EI SBRNTE-GRZZLY-CLRMNT #1 5/46 WSH I | 44645178 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 005/046 | ICD | E | 2020_(2) High fire spread TD |  | 2020-06-19 | 2020-12-19 | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-03-18 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.2093721 | 37.8512 | ETL.3740 | 40638423 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119191490 | Feb | T2 COLGATE-GRASS VALLEY 3/75 REFRAME | 31512499 | COLGATE-GRASS VALLEY | 003/075 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-18 | 2021-06-18 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.133715 | 39.3211 | ETL.6490 | 40768368 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119193758 | Not Scheduled | T3 DI COLGATE-ALLGHNY 20/553 RMV BUTT | 44365654 | COLGATE-ALLEGHANY | 020/553 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.899907 | 39.4628 | ETL.6470 | 40658312 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119193771 | Mar | T3 DI SOBRANTE-""G""#1"" 1/11 RPR INSS | 44645363 | SOBRANTE-"G" #1 | 001/011 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-17 | 2020-12-17 |  |  | 2021-03-19 | 2021-03-19 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.240035 | 37.9081 | ETL.3720 | 44940930 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119193856 | Q2 | T3 DI SOBRANTE-""G""#1""-TWR 0/6 RPR HRDT | 44624390 | SOBRANTE-"G" #1 | 000/006 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-06-18 | 2020-12-18 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.225199 | 37.9042 | ETL.3720 | 40804930 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119194018 | Mar | T3 DI TGR CRK-VLY SPGS TWR 4/35 RPC HRDT |  | TIGER CREEK-VALLEY SPRINGS | 004/035 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-19 | 2020-12-19 |  |  | 2021-03-09 | 2021-03-08 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.568314 | 38.4276 | ETL.5790 | 40811845 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119194025 | Not Scheduled | T3 DI COLGATE-ALLGHNY 20/553 RPLC SPLW | 44365653 | COLGATE-ALLEGHANY | 020/553 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.899907 | 39.4628 | ETL.6470 | 40658312 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119194330 | Not Scheduled | DI GATES-PANOCHE #1 10/49 RPR INSS | 44389952 | GATES-PANOCHE #1 | 010/049 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-06-19 | 2021-06-19 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.221806 | 36.2635 | ETL.4720 | 40885696 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119194332 | Not Scheduled | DI GATES-PANOCHE #2 10/49 RPR INSS | 44389954 | GATES-PANOCHE #2 | 010/049 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-06-19 | 2021-06-19 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.221806 | 36.2635 | ETL.4730 | 40885697 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119194335 | Q2 | DI GATES-PANOCHE #1 10/49 RPR FOND | 44571495 | GATES-PANOCHE #1 | 010/049 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-19 | 2021-06-19 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.222238 | 36.264 | ETL.4720 | 40863288 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119194338 | Q2 | DI GATES-PANOCHE #1 10/49 RPR STRT | 44389944 | GATES-PANOCHE #1 | 010/049 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-19 | 2021-06-19 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.222238 | 36.264 | ETL.4720 | 40863288 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119194422 | Q3 | T2 DI CARIBOU #2 ;0/30 RMV BUTT |  | CARIBOU #2 | ;000/030 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-19 | 2021-06-19 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.965898 | 40.0154 | ETL.6280 | 40614890 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119194432 | Not Scheduled | T3 DI COLGATE-ALLGHNY 16/453 REPL POLE | 31506658 | COLGATE-ALLEGHANY | 016/453 | 70Y | E | 2020_(1a) PSPS |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.962817 | 39.449 | ETL.6470 | 40767328 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119194435 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 16/432 RPLC SPLW | 44365653 | COLGATE-ALLEGHANY | 016/432 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.976701 | 39.4475 | ETL.6470 | 40665267 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119194554 | Not Scheduled | T3NT DI COLGATE-ALLGHNY 17/482 RMV BUTTS | 44374175 | COLGATE-ALLEGHANY | 017/482 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.944581 | 39.451 | ETL.6470 | 44918014 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119194555 | Not Scheduled | T3 DI COLGATE-ALLGHNY 17/482 RPLC INSW | 44365653 | COLGATE-ALLEGHANY | 017/482 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2021-05-31 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.944581 | 39.451 | ETL.6470 | 44918022 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not Scheduled | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119194575 | Not Scheduled | T3NT DI COLGATE-ALLGHANY 23/636 RMV BUTT | 44371190 | COLGATE-ALLEGHANY | 023/636 | ICW | F | 2020_(1a) PSPS |  | 2020-06-19 | 2022-06-19 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.851108 | 39.4769 | ETL.6470 | 40822723 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119194764 | Not Scheduled | T3 DI COLGATE-ALLGHANY 23/651 RPR INSW | 44379091 | COLGATE-ALLEGHANY | 023/651 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.848494 | 39.4716 | ETL.6470 | 40696054 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119194767 | Not Scheduled | T3 DI COLGATE-ALLGHANY 19/525 RPR HRDW | 44379095 | COLGATE-ALLEGHANY | 019/525 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.9159 | 39.4541 | ETL.6470 | 40693271 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119194768 | Not Scheduled | T3NT DI COLGATE-ALLGHANY 19/525 RMV BUTT | 44378839 | COLGATE-ALLEGHANY | 019/525 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.9159 | 39.4541 | ETL.6470 | 40693271 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119194809 | Not Scheduled | T3 DI COLGATE-ALLGHNY 16/432 RMV DEBRIS | 44365654 | COLGATE-ALLEGHANY | 016/432 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.976701 | 39.4475 | ETL.6470 | 40665267 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119194834 | Not Scheduled | T3NT DI COLGTE-ALLGHNY 23/634 RMV BUTT | 44371190 | COLGATE-ALLEGHANY | 023/634 | ICW | F | 2020_(2) High fire spread TD |  | 2020-06-19 | 2022-06-19 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.8515 | 39.4776 | ETL.6470 | 40760458 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119194839 | Not Scheduled | T3 DI COLGATE-ALLGHNY 18/491 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 018/491 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.938863 | 39.4516 | ETL.6470 | 40766624 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119194909 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 23/639 RPR POLE | 44365653 | COLGATE-ALLEGHANY | 023/639 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.850608 | 39.4759 | ETL.6470 | 40611347 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195015 | Not Scheduled | T3 DI COLGATE-ALLGHANY 17/474 REFRAME | 31507062 | COLGATE-ALLEGHANY | 017/474 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.94944 | 39.4504 | ETL.6470 | 40843349 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195020 | Not Scheduled | T3NT DI COLGATE-ALLGHNY 18/491 RMV BUTT | 44378839 | COLGATE-ALLEGHANY | 018/491 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.938863 | 39.4516 | ETL.6470 | 40766624 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195023 | Not Scheduled | T3NT DI COLGATE-ALLGHNY 20/558 RMV BUTT | 44378839 | COLGATE-ALLEGHANY | 020/558 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.89639 | 39.464 | ETL.6470 | 40874718 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195025 | Not Scheduled | T3 DI COLGATE-ALLGHNY 20/558 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 020/558 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.89639 | 39.464 | ETL.6470 | 40874718 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195027 | Not Scheduled | T3NT DI COLGATE-ALLGHNY 20/540 RMV BUTT | 44378839 | COLGATE-ALLEGHANY | 020/540 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.908346 | 39.4599 | ETL.6470 | 40611174 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195028 | Not Scheduled | T3 DI COLGATE-ALLGHNY 20/540 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 020/540 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.908346 | 39.4599 | ETL.6470 | 40611174 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195171 | Not Scheduled | T3 DI COLGATE-ALLGHANY 18/505 RPL STRW | 31507362 | COLGATE-ALLEGHANY | 018/505 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.928714 | 39.4527 | ETL.6470 | 40868967 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195175 | Not Scheduled | T3NT DI COLGATE-ALLGHANY 18/505 RMV BUTT | 44378839 | COLGATE-ALLEGHANY | 018/505 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.928714 | 39.4527 | ETL.6470 | 40868967 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195179 | Not Scheduled | T3 DI COLGATE-ALLGHANY 12/329 RPLC PLE | 31507362 | COLGATE-ALLEGHANY | 012/329 | 70Y | E | 2020_(1a) PSPS |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.017899 | 39.4125 | ETL.6470 | 40817339 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119195356 | Not Scheduled | T3 DI COLGATE-ALLGHANY 24/658 RPR SPLW | 44379097 | COLGATE-ALLEGHANY | 024/658 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.847187 | 39.4693 | ETL.6470 | 40824282 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195364 | Not Scheduled | T3 DI COLGATE-ALLGHNY 17/478 RMV BUTTS | 44378720 | COLGATE-ALLEGHANY | 017/478 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.947012 | 39.4507 | ETL.6470 | 40593293 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195365 | Not Scheduled | T3 DI COLGATE-ALLGHNY 17/478 RPR SHLW | 44378479 | COLGATE-ALLEGHANY | 017/478 | ICW | F | 2020_(2) High fire spread TD |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.947012 | 39.4507 | ETL.6470 | 40593293 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195543 | Not Scheduled | T3 DI COLGATE-ALLGHNY 16/431 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 016/431 | ICW | E | 2020_(1a) PSPS |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.97729 | 39.4474 | ETL.6470 | 40693247 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119195544 | Feb | T3 DI KILARC-CEDAR CRK 12/274 RPLC POLE | 31506712 | KILARC-CEDAR CREEK | 012/274 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-29 | 2020-11-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.943525 | 40.7853 | ETL.7290 | 40816392 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-02-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195549 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 17/468 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 017/468 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.953394 | 39.45 | ETL.6470 | 40598665 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195593 | Not Scheduled | T3 DI COLGATE-ALLGHNY 18/487 RPLC SPLW | 44365653 | COLGATE-ALLEGHANY | 018/487 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.941079 | 39.4513 | ETL.6470 | 40598646 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195596 | Not Scheduled | T3 DI COLGATE-ALLGHNY 18/487 RPR BUTT | 44365654 | COLGATE-ALLEGHANY | 018/487 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.941079 | 39.4513 | ETL.6470 | 40598646 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195734 | Not Scheduled | MONTE RIO-FORT ROSS 23/2 INST DAMPER |  | ETL.6979.INSL.NCER | 023/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-22 | 2021-06-22 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.1487726 | 38.4765 | ETL.6979 | 40741433 | Damper-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195920 | Not Scheduled | T3 DI COLGATE-ALLGHANY 18/489 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 018/489 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.940167 | 39.4515 | ETL.6470 | 40664633 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195921 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 18/489 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 018/489 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.940167 | 39.4515 | ETL.6470 | 40664633 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195923 | Not Scheduled | T3NT DI COLGATE-ALLGHANY 17/481 RMV BUTT | 44378839 | COLGATE-ALLEGHANY | 017/481 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.945089 | 39.4509 | ETL.6470 | 40767336 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195926 | Not Scheduled | T3 DI COLGATE-ALLGHANY 17/481 RPR INSW | 44379091 | COLGATE-ALLEGHANY | 017/481 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.945125 | 39.4509 | ETL.6470 | 40798833 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195927 | Not Scheduled | T3 DI COLGATE-ALLGHANY 16/430 RPR STRW | 44378720 | COLGATE-ALLEGHANY | 016/430 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.978493 | 39.4473 | ETL.6470 | 40590443 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195928 | Not Scheduled | T3NT DI COLGATE-ALLGHANY 16/430 RMV BUTT | 44378479 | COLGATE-ALLEGHANY | 016/430 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.978493 | 39.4473 | ETL.6470 | 40590443 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195929 | Not Scheduled | T3 DI COLGATE-ALLGHANY 19/538 RPR STRW | 44365653 | COLGATE-ALLEGHANY | 019/538 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.909522 | 39.459 | ETL.6470 | 40760451 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195940 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 17/468 RPLC HRDW | 44379095 | COLGATE-ALLEGHANY | 017/468 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.953394 | 39.45 | ETL.6470 | 40598665 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195942 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 17/485 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 017/485 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.94261 | 39.4512 | ETL.6470 | 40874815 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119195943 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 17/485 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 017/485 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.94261 | 39.4512 | ETL.6470 | 40874815 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196152 | Not Scheduled | T3NT DI COLGT-ALLGHANY 19/538 RMV DEBRIS | 44365654 | COLGATE-ALLEGHANY | 019/538 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.909522 | 39.459 | ETL.6470 | 40760451 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196153 | Not Scheduled | T3 DI COLGATE-ALLGHANY 19/538 RPR INSW | 44379091 | COLGATE-ALLEGHANY | 019/538 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.909504 | 39.4589 | ETL.6470 | 40789964 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-26 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196158 | Not Scheduled | T3 DI COLGATE-ALLGHANY 017/464 RPR STRW | 44379301 | COLGATE-ALLEGHANY | 017/464 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.956019 | 39.4498 | ETL.6470 | 40817357 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196210 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 16/436 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 016/436 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.973553 | 39.4478 | ETL.6470 | 40817354 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196212 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 16/436 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 016/436 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.973553 | 39.4478 | ETL.6470 | 40817354 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196213 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 20/548 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 020/548 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.90335 | 39.4622 | ETL.6470 | 40874720 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196215 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 20/548 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 020/548 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.90335 | 39.4622 | ETL.6470 | 40874720 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196218 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 20/547 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 020/547 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.904382 | 39.462 | ETL.6470 | 40817363 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196219 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 20/547 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 020/547 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.904382 | 39.462 | ETL.6470 | 40817363 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196242 | Not Scheduled | EI T3NT SAN LUIS OBPO-OCEANO 13/57 RPR R | 44378910 | SAN LUIS OBISPO-OCEANO | 013/057 | CHS | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-16 | 2022-06-16 |  |  |  | 2021-01-04 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.504774 | 35.121 | ETL.3530 | 40809128 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196360 | Not Scheduled | T3 DI COLGATE-ALLGHANY 019/529 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 019/529 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.914146 | 39.4554 | ETL.6470 | 40824272 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196361 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 19/529 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 019/529 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.914146 | 39.4554 | ETL.6470 | 40824272 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196362 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 20/549 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 020/549 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.902698 | 39.4623 | ETL.6470 | 40873773 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196363 | Not Scheduled | T3 DI COLGATE-ALLGHANY 20/549 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 020/549 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.902698 | 39.4623 | ETL.6470 | 40873773 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196367 | Mar | T3 DI MNDCN-WLLTS-FRT BRGG 10/3 RPR STRW | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 010/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.7550 | 44211132 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196561 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 18/490 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 018/490 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.939619 | 39.4515 | ETL.6470 | 40760735 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196563 | Not Scheduled | T3 DI COLGATE-ALLGHANY 18/490 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 018/490 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.939619 | 39.4515 | ETL.6470 | 40760735 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196664 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 18/488 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 018/488 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.940687 | 39.4514 | ETL.6470 | 40693263 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196665 | Not Scheduled | T3 DI COLGATE-ALLGHNY 18/488 RPLC HRDD | 44378839 | COLGATE-ALLEGHANY | 018/488 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.940687 | 39.4514 | ETL.6470 | 40693263 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196805 | Not Scheduled | T3 DI COLGATE-ALLGHNY 18/493 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 018/493 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.937371 | 39.4517 | ETL.6470 | 40822631 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119196870 | Mar | T2 MNDCN-WLTS-FRT BRG 36/3 RPR GYWW | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 036/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2021-06-22 |  |  | 2021-03-17 | 2021-03-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.704516 | 39.3898 | ETL.7550 | 40669455 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197081 | Not Scheduled | T3 DI COLGATE-ALLGHNY 20/556 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 020/556 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.897851 | 39.4635 | ETL.6470 | 40824276 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197083 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 20/556 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 020/556 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.897851 | 39.4635 | ETL.6470 | 40824276 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197439 | Mar | T2 HUMBOLDT-TRINITY 77/0 RPL ANCHOR |  | HUMBOLDT-TRINITY | 077/000 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2021-06-22 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.461601 | 40.6928 | ETL.1820 | 44554017 | Anchor-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197541 | Q3 | T2 CARIBOU-PLUMAS JCT 07/013 RPL PL | 31508658 | CARIBOU-PLUMAS JCT | 007/013 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2021-06-22 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.057484 | 40.0102 | ETL.6290 | 40656462 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197554 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 15/425 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 015/425 | ICW | E | 2020_(1a) PSPS |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.981287 | 39.4469 | ETL.6470 | 40818495 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119197556 | Q2 | T3 DI MTCLF-GRN VLLY 18/126L REPL POLE | 31506808 | METCALF-GREEN VALLEY | 018/126 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-20 | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-17 |  |  |  |  | LATE | South | WSIP | [6 empty] | '-121.691285 | 37.0146 | ETL.2540 | 44769618 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-07 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197785 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 17/469 RPR SPLW | 44379095 | COLGATE-ALLEGHANY | 017/469 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.952807 | 39.4501 | ETL.6470 | 40693259 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197811 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 17/469 RMV PL BUTT | 44379095 | COLGATE-ALLEGHANY | 017/469 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.952807 | 39.4501 | ETL.6470 | 40693259 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197813 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 17/483 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 017/483 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.944128 | 39.451 | ETL.6470 | 40818503 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197815 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 17/484 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 017/484 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.943136 | 39.4511 | ETL.6470 | 40822630 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197831 | Not Scheduled | T3NT DI CLGTE-ALLEGHANY 19/536 RMV BUTT | 44379095 | COLGATE-ALLEGHANY | 019/536 | ICW | F | 2020_(2) High fire spread TD |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.910532 | 39.4582 | ETL.6470 | 40658308 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197867 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 17/476 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 017/476 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.948167 | 39.4506 | ETL.6470 | 40868966 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197868 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 17/476 RMV PL BUTT | 44379097 | COLGATE-ALLEGHANY | 017/476 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.948167 | 39.4506 | ETL.6470 | 40868966 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197903 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 16/448 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 016/448 | ICW | E | 2020_(1a) PSPS |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.966334 | 39.4486 | ETL.6470 | 40868964 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119197905 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 17/465 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 017/465 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.955344 | 39.4498 | ETL.6470 | 40874710 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197909 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 17/471 RPR INSW | 44379091 | COLGATE-ALLEGHANY | 017/471 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.951562 | 39.4502 | ETL.6470 | 40790973 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197921 | Not Scheduled | T3NT DI COLGATE-ALLEGHNY 17/471 RMV BUTT | 44379095 | COLGATE-ALLEGHANY | 017/471 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.951546 | 39.4502 | ETL.6470 | 40760733 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197926 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 18/499 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 018/499 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.933458 | 39.4522 | ETL.6470 | 40664635 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197927 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 18/499 RMV PL BUTT | 44379095 | COLGATE-ALLEGHANY | 018/499 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.933458 | 39.4522 | ETL.6470 | 40664635 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197969 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 20/541 RPR STRW | 44378720 | COLGATE-ALLEGHANY | 020/541 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.907877 | 39.4602 | ETL.6470 | 40590447 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197980 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 20/541 RMV PL BUTT | 44378479 | COLGATE-ALLEGHANY | 020/541 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.907877 | 39.4602 | ETL.6470 | 40590447 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119197989 | Not Scheduled | T3 DI CLGTE-ALLEGHANY 23/645 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 023/645 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.849519 | 39.4737 | ETL.6470 | 40822738 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198000 | Not Scheduled | T3 DI CLGTE-ALLEGHANY 23/646 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 023/646 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.849336 | 39.4734 | ETL.6470 | 40869677 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198019 | Not Scheduled | T3 DI CLGTE-ALLEGHANY 19/524 RPR STRW | 44378720 | COLGATE-ALLEGHANY | 019/524 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.916426 | 39.454 | ETL.6470 | 40593296 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198031 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 19/524 RMV PL BUTT | 44378479 | COLGATE-ALLEGHANY | 019/524 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.916426 | 39.454 | ETL.6470 | 40593296 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198033 | Not Scheduled | T3NT DI CLGT-ALLGHNY 17/462 RMV PL BUTT | 44371190 | COLGATE-ALLEGHANY | 017/462 | ICW | F | 2020_(1a) PSPS |  | 2020-06-19 | 2022-06-19 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.957324 | 39.4496 | ETL.6470 | 40766725 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119198326 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 20/554 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 020/554 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.899329 | 39.463 | ETL.6470 | 40760743 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198328 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 20/554 RMV PL BUTT | 44379095 | COLGATE-ALLEGHANY | 020/554 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.899329 | 39.463 | ETL.6470 | 40760743 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198513 | Mar | T2 DI KILARC-DESCHUTES 17/356 RMV PL BUT | 44406469 | KILARC-DESCHUTES | 017/356 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-22 | 2021-06-22 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.133522 | 40.5636 | ETL.7300 | 40771273 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198514 | Mar | T2 DI KILARC-DESCHUTES 17/356 RPR STRW | 44406469 | KILARC-DESCHUTES | 017/356 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-22 | 2021-06-22 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.133522 | 40.5636 | ETL.7300 | 40771273 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198551 | Not Scheduled | T3 DI COLGATE-ALLGHANY 24/653 RPR STRW | 44378720 | COLGATE-ALLEGHANY | 024/653 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.848017 | 39.471 | ETL.6470 | 40598570 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198753 | Not Scheduled | T3 DI COLGATE-ALLGHANY 22/600 RPL INSW | 31507063 | COLGATE-ALLEGHANY | 022/600 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.869588 | 39.4722 | ETL.6470 | 40849862 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198818 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 14/394 RMV PL BUTT | 44378479 | COLGATE-ALLEGHANY | 014/394 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-23 | 2022-06-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.995732 | 39.4401 | ETL.6470 | 40767326 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198834 | Not Scheduled | T3 DI COLGATE-ALLGHNY 14/394 RPR STRW | 31507062 | COLGATE-ALLEGHANY | 014/394 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.995732 | 39.4401 | ETL.6470 | 40767326 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198837 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 20/253 RMV PL BUTT | 44378466 | COLGATE-ALLEGHANY | 020/543 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-23 | 2022-06-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.906941 | 39.461 | ETL.6470 | 40658311 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198839 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 20/253 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 020/543 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.906941 | 39.461 | ETL.6470 | 40658311 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198880 | Not Scheduled | T3 DI COLGATE-ALLGHNY 14/395 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 014/395 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.995697 | 39.4405 | ETL.6470 | 40766614 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198881 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 20/253 RPR INSW | 44378808 | COLGATE-ALLEGHANY | 020/543 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.907001 | 39.4608 | ETL.6470 | 40688243 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198882 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 14/395 RMV PL BUTT | 44378466 | COLGATE-ALLEGHANY | 014/395 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-23 | 2022-06-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.995697 | 39.4405 | ETL.6470 | 40766614 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198966 | Not Scheduled | T3NT DI COLGATE-CHLENGE 2/45 RMV PL BUTT | 44379099 | COLGATE-CHALLENGE | 002/045 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.173941 | 39.3564 | ETL.6480 | 40655133 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119198968 | Not Scheduled | T3 DI COLGATE-ALLGHNY 24/665 REPL POLE | 31507362 | COLGATE-ALLEGHANY | 024/665 | 70Y | E | 2020_(1a) PSPS |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.846157 | 39.4671 | ETL.6470 | 40664652 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119199063 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 21/590 RMV PL BUTT | 44378479 | COLGATE-ALLEGHANY | 021/590 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-23 | 2022-06-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.876683 | 39.4713 | ETL.6470 | 40767224 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199067 | Not Scheduled | T3 DI COLGATE-ALLGHNY 21/590 RPR INSW | 44378807 | COLGATE-ALLEGHANY | 021/590 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.876683 | 39.4713 | ETL.6470 | 40798721 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199134 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 22/618 RMV PL BUTT | 44378466 | COLGATE-ALLEGHANY | 022/618 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-23 | 2022-06-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.858726 | 39.4765 | ETL.6470 | 40760456 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199135 | Not Scheduled | T3 DI COLGATE-ALLGHNY 22/618 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 022/618 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.858726 | 39.4765 | ETL.6470 | 40760456 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199199 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 21/577 RPR STRW | 44365653 | COLGATE-ALLEGHANY | 021/577 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.885747 | 39.4699 | ETL.6470 | 40598668 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199320 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 21/577 RPL INSW | 31507063 | COLGATE-ALLEGHANY | 021/577 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.885752 | 39.4699 | ETL.6470 | 40625292 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199323 | Not Scheduled | T3 DI COLGTE-ALLEGHANY 19/513 RMV DEBRIS | 44365654 | COLGATE-ALLEGHANY | 019/513 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.923791 | 39.4532 | ETL.6470 | 40611344 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199325 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 15/409 RPR IBWW | 44365653 | COLGATE-ALLEGHANY | 015/409 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.992785 | 39.4456 | ETL.6470 | 40602523 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199326 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 14/397 RPR SPLW | 44365653 | COLGATE-ALLEGHANY | 014/397 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.99565 | 39.4414 | ETL.6470 | 40817348 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199328 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 23/621 RMV PL BUTT | 44378466 | COLGATE-ALLEGHANY | 023/621 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-23 | 2022-06-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.856994 | 39.4773 | ETL.6470 | 40672230 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199329 | Not Scheduled | T3 DI CLGATE-ALLEGHANY 23/621 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 023/621 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.856994 | 39.4773 | ETL.6470 | 40672230 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199471 | Not Scheduled | T3 DI COLGATE-ALLGHNY 21/583 REPL INSW | 31507063 | COLGATE-ALLEGHANY | 021/583 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.881516 | 39.4707 | ETL.6470 | 40822634 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199512 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 21/583 RMV PL BUTT | 44378479 | COLGATE-ALLEGHANY | 021/583 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-23 | 2022-06-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.881516 | 39.4707 | ETL.6470 | 40822634 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199514 | Not Scheduled | T3 DI COLGATE-ALLGHNY 23/622 RPL SPLW | 44365653 | COLGATE-ALLEGHANY | 023/622 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.856373 | 39.4777 | ETL.6470 | 44686508 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199516 | Q2 | DI GATES-PANOCHE #1 3/14 RPR FOND | 44394839 | GATES-PANOCHE #1 | 003/014 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-06-22 | 2022-06-22 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.150378 | 36.1733 | ETL.4720 | 40753573 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119199541 | Not Scheduled | T3 DI CLGATE-ALLEGHANY 21/592 RPR INSW | 44378807 | COLGATE-ALLEGHANY | 021/592 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.875293 | 39.4715 | ETL.6470 | 40853519 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199545 | Not Scheduled | T3 DI CLGATE-ALLEGHANY 21/580 RPR INSW | 44378807 | COLGATE-ALLEGHANY | 021/580 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.883708 | 39.4704 | ETL.6470 | 40790985 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199546 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 21/580 RMV PL BUT | 44378466 | COLGATE-ALLEGHANY | 021/580 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-23 | 2022-06-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.883743 | 39.4704 | ETL.6470 | 40760745 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199547 | Not Scheduled | T3 DI CLGATE-ALLEGHANY 21/580 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 021/580 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.883743 | 39.4704 | ETL.6470 | 40760745 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199548 | Not Scheduled | T3 DI CLGATE-ALLEGHANY 21/578 RMV BUTT | 44378465 | COLGATE-ALLEGHANY | 021/578 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.885139 | 39.4702 | ETL.6470 | 40679468 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199591 | Not Scheduled | T3 DI COLGATE-ALLGHNY 21/566 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 021/566 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.892165 | 39.4665 | ETL.6470 | 40611189 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199592 | Not Scheduled | T3 DI COLGATE-ALLGHNY 21/566 RPR HRDW | 44378465 | COLGATE-ALLEGHANY | 021/566 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.892165 | 39.4665 | ETL.6470 | 40611189 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199598 | Not Scheduled | T3 DI COLGATE-ALLGHNY 23/648 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 023/648 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.848966 | 39.4727 | ETL.6470 | 40602540 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199841 | Not Scheduled | T3 DI CLGATE-ALLEGHANY 21/578 RPR POLE | 44378465 | COLGATE-ALLEGHANY | 021/578 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.885139 | 39.4702 | ETL.6470 | 40679468 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199884 | Not Scheduled | T3NT DI CLGATE-ALLGHNY 21/575 RMV DEBRIS | 44378479 | COLGATE-ALLEGHANY | 021/575 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-23 | 2022-06-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.886847 | 39.4693 | ETL.6470 | 40868973 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199886 | Not Scheduled | T3 DI COLGATE-ALLGHNY 21/575 RPR INSW | 44378807 | COLGATE-ALLEGHANY | 021/575 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.886881 | 39.4693 | ETL.6470 | 40892148 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119199888 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 22/595 RMV PL BUTT | 44378466 | COLGATE-ALLEGHANY | 022/595 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-23 | 2022-06-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.873134 | 39.4717 | ETL.6470 | 40693300 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200018 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 22/594 RPR POLE | 44378465 | COLGATE-ALLEGHANY | 022/594 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.873829 | 39.4717 | ETL.6470 | 40590450 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200081 | Not Scheduled | T3 DI COLGATE-ALLGHNY 22/595 RPR POLE | 44378465 | COLGATE-ALLEGHANY | 022/595 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.873134 | 39.4717 | ETL.6470 | 40693300 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200087 | Not Scheduled | T3 DI COLGATE-ALLGHNY 20/559 RPR INSW | 44365653 | COLGATE-ALLEGHANY | 020/559 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.896048 | 39.4644 | ETL.6470 | 40892146 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200193 | Not Scheduled | T3 DI COLGATE-ALLGHNY 15/412 RMV BUTT | 44378466 | COLGATE-ALLEGHANY | 015/412 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-23 | 2022-06-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.990618 | 39.4459 | ETL.6470 | 40664628 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200199 | Not Scheduled | T3 DI COLGATE-ALLGHNY 15/412 REPL POLE | 31507362 | COLGATE-ALLEGHANY | 015/412 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.990618 | 39.4459 | ETL.6470 | 40664628 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200211 | Q3 | T2 EI BRIDGEVILLE-GARBERVIL 21/9 RPL ANC | 31508615 | BRIDGEVILLE-GARBERVILLE | 021/009 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2021-06-22 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.757631 | 40.222 | ETL.6220 | 40875290 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200314 | Not Scheduled | T3NT DI COLGATE-ALLGHNY 15/406 INST MRKW | 44378479 | COLGATE-ALLEGHANY | 015/406 | ICW | F | 2020_(1a) PSPS |  | 2020-06-23 | 2022-06-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.993666 | 39.4452 | ETL.6470 | 40817350 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119200315 | Not Scheduled | T3 DI COLGATE-ALLGHNY 20/559 BOND GUY | 44365653 | COLGATE-ALLEGHANY | 020/559 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.896056 | 39.4644 | ETL.6470 | 40868971 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200327 | Not Scheduled | T3 DI CLGATE-ALLEGHANY 22/617 RPR POLE | 44378720 | COLGATE-ALLEGHANY | 022/617 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.859291 | 39.4762 | ETL.6470 | 40767226 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200495 | Not Scheduled | T3 T2 DI COLGATE-ALLEGHANY 22/604 RPR PL | 44378465 | COLGATE-ALLEGHANY | 022/604 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.867098 | 39.4725 | ETL.6470 | 40593302 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200497 | Not Scheduled | T3 DI CLGATE-ALLEGHANY 22/604 RMV DEBRIS | 44378466 | COLGATE-ALLEGHANY | 022/604 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-23 | 2022-06-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.867098 | 39.4725 | ETL.6470 | 40593302 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200662 | Not Scheduled | T3 DI CLGATE-ALLEGHANY 20/546 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 020/546 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-22 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.905058 | 39.4619 | ETL.6470 | 40824274 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200831 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 08/098 RPL JUMP |  | DIVIDE-CABRILLO #2 | 008/098 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4362935 | 34.71 | ETL.1370 | 40685429 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200857 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 08/097 RPL INSW | 31508886 | DIVIDE-CABRILLO #2 | 008/097 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4362902 | 34.7111 | ETL.1370 | 40720300 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200896 | Not Scheduled | T3 DI CLGATE-ALLEGHANY 23/629 RPL HRDD | 44374175 | COLGATE-ALLEGHANY | 023/629 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.852302 | 39.4793 | ETL.6470 | 44684327 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200898 | Not Scheduled | T3NT DI CLGT-ALLGHNY 23/629 RMV PL BUT | 44374175 | COLGATE-ALLEGHANY | 023/629 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-23 | 2022-06-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.852302 | 39.4793 | ETL.6470 | 44684327 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200986 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 08/096 RPL INSW | 31508886 | DIVIDE-CABRILLO #2 | 008/096 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4363033 | 34.7121 | ETL.1370 | 40629304 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-02 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200995 | Q2 | T3NT DI FULTON-LAKEVILLE 33/145 RPR FOND |  | FULTON-LAKEVILLE | 033/145 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2022-06-23 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592176 | 38.3835 | ETL.4950 | 40681705 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119200997 | Not Scheduled | T3 DI COLGATE-ALLGHNY 20/563 RPR POLE | 44378465 | COLGATE-ALLEGHANY | 020/563 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.893733 | 39.4656 | ETL.6470 | 40658314 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119201058 | Not Scheduled | T3 DI CLGATE-ALLEGHANY 15/405 RPR POLE | 44378720 | COLGATE-ALLEGHANY | 015/405 | ICW | E | 2020_(1a) PSPS |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.994007 | 39.4446 | ETL.6470 | 40824270 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119201119 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 07/094 RPL HRD |  | DIVIDE-CABRILLO #2 | 007/094 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436267 | 34.7142 | ETL.1370 | 40702312 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-02 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119201238 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 07/092 RPL INSW | 31508886 | DIVIDE-CABRILLO #2 | 007/092 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2021-06-23 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4362818 | 34.7164 | ETL.1370 | 40634062 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119201271 | Not Scheduled | DI GATES-PANOCHE #1 012/058 RPL INSS | 31514618 | GATES-PANOCHE #1 | 012/058 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-06-23 | 2021-06-21 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.239982 | 36.2868 | ETL.4720 | 40887587 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119201273 | Not Scheduled | DI GATES-PANOCHE #2 012/058 RPL INSS | 31514619 | GATES-PANOCHE #2 | 012/058 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-06-23 | 2021-06-21 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.239982 | 36.2868 | ETL.4730 | 40887589 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119201275 | Q2 | DI GATES-PANOCHE #1 012/058 RPR FOND | 44364838 | GATES-PANOCHE #1 | 012/058 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-06-23 | 2022-06-23 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.240683 | 36.2877 | ETL.4720 | 40863636 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119201342 | Not Scheduled | T3 DI COLGATE-ALLEG 15/420 REFRAME | 31507062 | COLGATE-ALLEGHANY | 015/420 | 93E | E | 2020_(1a) PSPS |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.984493 | 39.4466 | ETL.6470 | 40598662 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119201362 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 007/091 RPL INS | 31508886 | DIVIDE-CABRILLO #2 | 007/091 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2021-06-23 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4362986 | 34.7172 | ETL.1370 | 40889870 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119201415 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 21/589 RPR INSW | 44378462 | COLGATE-ALLEGHANY | 021/589 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.877358 | 39.4712 | ETL.6470 | 40696051 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119201631 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 7/89 RPL INSW | 31508886 | DIVIDE-CABRILLO #2 | 007/089 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4363077 | 34.7195 | ETL.1370 | 40840883 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119201795 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 07/088 RPR GYWW |  | DIVIDE-CABRILLO #2 | 007/088 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436271 | 34.72 | ETL.1370 | 40828430 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119201796 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 07/088 RPR JUMP |  | DIVIDE-CABRILLO #2 | 007/088 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436271 | 34.72 | ETL.1370 | 40828430 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119201797 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 07/088 RPL INSW | 31508886 | DIVIDE-CABRILLO #2 | 007/088 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436284 | 34.72 | ETL.1370 | 40856116 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119202131 | Mar | T2 DI CRTN-MNDCN #1 29/140 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 029/140 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-23 | 2022-06-23 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.722833 | 39.0399 | ETL.1330 | 40587891 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119203305 | Not Scheduled | T2 DI FULTON-HOPLAND 18/9 CANCEL | 31509679 | FULTON-HOPLAND | 018/009 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 | [6 empty] | CANCEL/CNCL | TR2 |  | North Coast | WSIP | [6 empty] | '-122.882493 | 38.7234 | ETL.6890 | 40860943 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119203308 | Q2 | T3 DI MTCLF-GRN VLLY 18/126R REPL POLE | 31506808 | METCALF-GREEN VALLEY | 018/126 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-22 | 2020-12-20 | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-05-17 |  |  |  |  | LATE | South | WSIP | [6 empty] | '-121.691285 | 37.0146 | ETL.2540 | 44769619 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-07 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119203414 | Feb | T3NT DI KILARC-CDAR CRK 5/130 RMV DEBRIS | 43939119 | KILARC-CEDAR CREEK | 005/130 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-22 | 2022-06-22 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.974468 | 40.7092 | ETL.7290 | 40759371 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119204332 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 24/668 RPR POLE | 44378720 | COLGATE-ALLEGHANY | 024/668 | ICW | E | 2020_(1a) PSPS |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.845474 | 39.4658 | ETL.6470 | 40818519 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119204427 | Q2 | DI GATES-PANOCHE#1 4/23 RPR STRT | 44394839 | GATES-PANOCHE #1 | 004/023 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-23 | 2021-06-23 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.169263 | 36.1957 | ETL.4720 | 40658944 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119204461 | Not Scheduled | T3 DI COLGATE-ALLGHNY 21/585 RPR POLE | 44378720 | COLGATE-ALLEGHANY | 021/585 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.880096 | 39.4709 | ETL.6470 | 40873687 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119204465 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 015/415 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 015/415 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-24 | 2020-12-24 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.98812 | 39.4461 | ETL.6470 | 40818493 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119204468 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 015/415 RMV BUTT | 44378465 | COLGATE-ALLEGHANY | 015/415 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-24 | 2020-12-24 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.98812 | 39.4461 | ETL.6470 | 40818493 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119204469 | Q3 | DI GATES-MUSTANG SW STA #1 1/9 RPR FOND | 44389942 | SPARE T-LINE RECORD | 001/009 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-06-23 | 2022-06-23 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.101328 | 36.1507 | ETL.2604 | 40858216 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119204723 | Not Scheduled | T3 DI COLGATE-ALLGHNY 14/393 BOND GUY | 44378465 | COLGATE-ALLEGHANY | 014/393 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.995771 | 39.4395 | ETL.6470 | 40664626 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119204726 | Not Scheduled | T3 DI COLGATE-ALLGHNY 14/393 RMV BUTT | 44378466 | COLGATE-ALLEGHANY | 014/393 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-23 | 2022-06-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.995771 | 39.4395 | ETL.6470 | 40664626 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119204894 | Not Scheduled | DI MONTE RIO-FORT ROSS 16/2 RPR GYWW |  | ETL.6979.POLE.WDPS | 016/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2021-06-23 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.030487 | 38.4803 | ETL.6979 | 44762512 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119204895 | Q2 | DI GATES-PANOCHE #1 007/037 RPR FOND | 44394839 | GATES-PANOCHE #1 | 007/037 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-23 | 2021-06-23 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.19787 | 36.2326 | ETL.4720 | 40811170 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119204897 | Not Scheduled | DI MONTE RIO-FORT ROSS 16/2 RPR GYWW |  | ETL.6979.POLE.WDPS | 016/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2021-06-23 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.030487 | 38.4803 | ETL.6979 | 44762511 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119204898 | Not Scheduled | DI MONTE RIO-FORT ROSS 16/2 RPR GYWW |  | ETL.6979.POLE.WDPS | 016/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2021-06-23 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.030487 | 38.4803 | ETL.6979 | 44762510 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119204945 | Q2 | DI GATES-PANOCHE #1 14/67 RPR FOND | 44394839 | GATES-PANOCHE #1 | 014/067 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-23 | 2021-06-23 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.258654 | 36.3108 | ETL.4720 | 40818932 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119205128 | Mar | DI FULTON-HOPLAND 9/10 RPR GYWW | 44579280 | FULTON-HOPLAND | 009/010 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.844125 | 38.6132 | ETL.6890 | 40587771 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119205475 | Q2 | DI GATES-PANOCHE #1 9/40 RPR FOND | 44394839 | GATES-PANOCHE #1 | 009/040 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-23 | 2021-06-23 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.203989 | 36.2405 | ETL.4720 | 40604957 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119205584 | Q2 | DI GATES-PANOCHE #1 011/057 RPR STRT | 44394839 | GATES-PANOCHE #1 | 011/057 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-23 | 2021-06-23 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.238632 | 36.2851 | ETL.4720 | 40817992 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119205707 | Feb | T2 DI JOLON TAP 012/168 RPR HRDD | 44578863 | JOLON TAP | 012/168 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 | 2021-02-22 | 2021-02-23 | 2021-02-23 | 2021-02-22 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.174717 | 36.0557 | ETL.7321 | 44212731 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 9 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119205721 | Not Scheduled | T2 WEST POINT-VALLEY SPRINGS 6/76 STUB P |  | WEST POINT-VALLEY SPRINGS | 006/076 | GAR | E | 2020_(4) TD tag on high spread line |  | 2020-03-30 | 2021-03-30 | [7 empty] | TR2 | <60D | Central | WSIP | [6 empty] | '-120.639628 | 38.3753 | ETL.8350 | 40876055 | Structure-Wood | Rotten | Stub |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 586 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  | 2020-09-18 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119205853 | Feb | T2 DI JOLON TAP 012/168 BOND HRDD | 44575318 | JOLON TAP | 012/168 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 | 2021-02-22 | 2021-02-23 | 2021-02-23 | 2021-02-22 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.174717 | 36.0557 | ETL.7321 | 44212731 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 9 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119205991 | Q2 | DI GATES-PANOCHE#1 13/62 RPR STRT | 44394839 | GATES-PANOCHE #1 | 013/062 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-23 | 2021-06-23 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.24886 | 36.2982 | ETL.4720 | 40663938 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119206192 | Q2 | DI GATES-PANOCHE #1 008/039 RPR FOND | 44394839 | GATES-PANOCHE #1 | 008/039 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-06-23 | 2022-06-23 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.201933 | 36.2378 | ETL.4720 | 40863286 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119206361 | Mar | T2 HUMBOLDT-TRINITY 93/7 INST WEIGHTS | 44356920 | HUMBOLDT-TRINITY | 093/007 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-24 | 2021-06-24 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.744908 | 40.7488 | ETL.1820 | 44395220 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119206450 | Q2 | EI T3NT FULTON-IGNACIO #1 016/083 RPR FO | 44310479 | FULTON-IGNACIO #1 | 016/083 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-24 | 2022-06-24 |  |  | 2021-04-23 | 2021-04-19 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592244 | 38.3959 | ETL.4680 | 40651563 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119206491 | Not Scheduled | T3 DI FRH MDW-MDL FRK 10/189 REPL POLE | 31507072 | FRENCH MEADOWS-MIDDLE FORK | 010/189 | 70Y | E | 2020_(1a) PSPS |  | 2020-06-24 | 2020-12-24 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.567083 | 39.0135 | ETL.6870 | 40761240 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119206917 | Not Scheduled | T2 FULTON-HOPLAND 32/006 RPLC STRW | 31478309 | FULTON-HOPLAND | 032/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-24 | 2021-06-24 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.042755 | 38.8749 | ETL.6890 | 40824189 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119207104 | Q2 | T3 CRESTA-RIO OSO 12/100 INST DAMPER |  | CRESTA-RIO OSO | 012/100 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-24 | 2020-12-24 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.451228 | 39.7844 | ETL.4590 | 40910126 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119207350 | Feb | T3 EI KILARC-CEDAR CREEK 6/156 RPR GYWW | 43939119 | KILARC-CEDAR CREEK | 006/156 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-24 | 2020-12-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.994445 | 40.7152 | ETL.7290 | 40877862 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119208013 | Feb | T3 EI KILARC-CEDAR CREEK 012/264 RPR STR | 43939119 | KILARC-CEDAR CREEK | 012/264 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-24 | 2020-12-24 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.950282 | 40.7772 | ETL.7290 | 40693125 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119208043 | Mar | DI FULTON-HOPLAND 9/11 RPL INSS | 31528322 | FULTON-HOPLAND | 009/011 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-24 | 2021-06-24 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.843587 | 38.6133 | ETL.6890 | 40609155 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119208354 | Q2 | DI GATES-PANOCHE #1 14/69 RPR FOND | 44371519 | GATES-PANOCHE #1 | 014/069 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-23 | 2021-06-23 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.263044 | 36.3159 | ETL.4720 | 40863292 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119208358 | Not Scheduled | T3 DI FRNCH MDWS-MDL FRK 9/182 RPR STRW | 44379165 | FRENCH MEADOWS-MIDDLE FORK | 009/182 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-24 | 2020-12-24 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.561664 | 39.0162 | ETL.6870 | 40751850 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119208574 | Q2 | T3 DI KESWICK-CASCADE 6/120 RPR CNDS |  | CRESTA-RIO OSO | 016/133 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-24 | 2020-12-24 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.411538 | 40.6395 | ETL.4590 | 44237870 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119208600 | Not Scheduled | T3NT DI FNCH MDWS-MDL FRK 9/182 RMV BUTT | 44379165 | FRENCH MEADOWS-MIDDLE FORK | 009/182 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-24 | 2022-06-24 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.561664 | 39.0162 | ETL.6870 | 40751850 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119208601 | Not Scheduled | T2 DI COLGATE-CHALLENGE 0/22 RPR GYWW | 44394872 | COLGATE-CHALLENGE | 000/022 | ICW | E | 2020_(1a) PSPS |  | 2020-06-24 | 2021-06-24 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.19013 | 39.3438 | ETL.6480 | 40598490 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119208887 | Mar | BLTA-RVRBNK-MLNES SWSTA :5/0 RPLC POLE | 31507102 | BELLOTA-RIVERBANK-MELONES SW STA | :005/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-03-05 | 2021-03-05 |  |  | 2021-03-05 | 2021-03-04 | [5 empty] | Central | WSIP | [6 empty] | '-120.563946 | 37.8882 | ETL.1070 | 40602879 | Structure-Wood | Rotten | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 15 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-09-23 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119208920 | Feb | DI PHILO JCT-ELK 30/3L RPR ANCW | 44610684 | PHILO JCT-ELK | 030/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-24 | 2021-06-24 |  |  | 2021-02-10 | 2021-02-10 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.600897 | 39.1191 | ETL.7780 | 44744317 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-23 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119209053 | Q4 | T2 EI KESWICK-TRINITY 16/204 RMV DEBRIS |  | KESWICK-TRINITY | 016/204 | ICS | F | 2020_(4) TD tag on high spread line |  | 2020-06-25 | 2022-06-25 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.682609 | 40.719 | ETL.7270 | 44649334 | Anchor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119209109 | Q2 | EI T3NT FULTON-IGNACIO #1 2/13 RPR FOND | 44310479 | FULTON-IGNACIO #1 | 002/013 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-25 | 2022-06-25 |  |  | 2021-04-23 | 2021-04-19 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.723758 | 38.497 | ETL.4680 | 40651555 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119209112 | Q2 | DI GATES-PANOCHE #1 013/064 RPR FOND | 44394839 | GATES-PANOCHE #1 | 013/064 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-06-24 | 2022-06-24 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.252957 | 36.3035 | ETL.4720 | 40753579 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119209223 | Not Scheduled | T3 EI FULTON-LAKEVILLE 028/126 RPR COND |  | FULTON-LAKEVILLE | 028/126 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-25 | 2020-12-25 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.585331 | 38.4514 | ETL.4950 | 40658046 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119209224 | Q2 | T3 EI FULTON-LAKEVILLE 028/126 RPR FOND |  | FULTON-LAKEVILLE | 028/126 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-25 | 2020-12-25 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.585331 | 38.4514 | ETL.4950 | 40658046 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119209249 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 21/591 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 021/591 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.876021 | 39.4713 | ETL.6470 | 40760454 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119209415 | Not Scheduled | EI T3NT ROUND MTN-TABLE MTN #2 0/8 INST | 31507391 | ROUND MTN-TABLE MTN #2 | 000/008 | 93A | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-25 | 2022-06-25 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.929764 | 40.7885 | ETL.6070 | 40871656 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119209622 | Q2 | DI GATES-PANOCHE #1 9/45 RPR STRT | 44394839 | GATES-PANOCHE #1 | 009/045 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-24 | 2021-06-24 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.214345 | 36.2538 | ETL.4720 | 40753529 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119209623 | Q2 | DI GATES-PANOCHE #1 9/45 RPR FOND | 44394839 | GATES-PANOCHE #1 | 009/045 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-24 | 2021-06-24 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.214345 | 36.2538 | ETL.4720 | 40753529 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119209687 | Not Scheduled | T2NT DI CTNWD #1 5/36 RPR FOND | 44406038 | COTTONWOOD #1 | 005/036 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-06-24 | 2022-06-24 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.267779 | 40.3221 | ETL.6620 | 40910979 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119209858 | Not Scheduled | T2 DRUM-SUMMIT #1 26/311 INST DAMPER | 44394772 | DRUM-SUMMIT #1 | 026/311 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2021-06-25 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.334944 | 39.3112 | ETL.1440 | 40756820 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119209870 | Not Scheduled | T3NT DI MR BY-SLR SW ST #1 9/39 INS MRKS |  | MORRO BAY-SOLAR SW STA #1 | 009/039 | ICS | F | 2020_(3) On high spread structure |  | 2020-06-22 | 2022-06-22 | [7 empty] | TR3 |  | South | WSIP | [6 empty] | '-120.68926 | 35.3797 | ETL.5300 | 40870329 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-28 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119210073 | Q2 | EI T3NT FULTON-LAKEVILLE 027/121 RPR FON | 44636937 | FULTON-LAKEVILLE | 027/121 | ICQ | F | 2020_(1a) PSPS |  | 2020-06-25 | 2022-06-25 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592944 | 38.4655 | ETL.4950 | 40864660 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119210253 | Q2 | T3 EI VOLTA-DESCHUTES 4/101 REFRAME CRSW | 31507464 | VOLTA-DESCHUTES | 004/101 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-25 | 2020-12-25 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.95167 | 40.4808 | ETL.8290 | 40667436 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119210255 | Q2 | EI VOLTA-DESCHUTES 17/368 RPR POLE |  | VOLTA-DESCHUTES | 017/368 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-25 | 2021-06-25 |  |  | 2021-04-09 | 2021-04-05 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.172168 | 40.5404 | ETL.8290 | 44949902 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119210289 | Not Scheduled | DI SN LS OBSP-SNT 22/103 RPL INSS | 31510359 | SAN LUIS OBISPO-SANTA MARIA | 022/103 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-06-24 | 2021-06-24 | [9 empty] | South | WSIP | [6 empty] | '-120.44473 | 35.0026 | ETL.3540 | 40677651 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119210452 | Feb | T3 EI MONTA VISTA-JFFRSN #1 18/76 RPR ST | 44614659 | MONTA VISTA-JEFFERSON #1 | 018/076 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-06-25 | 2020-12-25 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.305533 | 37.4384 | ETL.5220 | 40818634 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 11 | Huddart Park | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119210790 | Not Scheduled | T3 EI ROUND MTN-TABLE MTN #2 1/11 RPL HR | 44156941 | ROUND MTN-TABLE MTN #2 | 001/011 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-25 | 2020-12-25 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.931564 | 40.7796 | ETL.6070 | 40595194 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119210911 | Q2 | T2 EI HAT CRK #1-WSTWD 53/1025 RPL POLE | 31508285 | HAT CREEK #1-WESTWOOD | 053/1025 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-25 | 2021-06-25 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.005555 | 40.3306 | ETL.7030 | 40601645 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119210977 | Feb | T3 EI KILARC-CEDAR CREEK 11/246 RPR CON | 43939119 | KILARC-CEDAR CREEK | 011/246 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-25 | 2020-12-25 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.959958 | 40.7656 | ETL.7290 | 40771266 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119210979 | Q2 | EI T3NT FULTON-IGNACIO #1 018/093 INST A | 31529484 | FULTON-IGNACIO #1 | 018/093 | 93A | F | 2020_(3) On high spread structure |  | 2020-06-25 | 2022-06-25 |  |  | 2021-04-23 | 2021-04-19 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592662 | 38.3592 | ETL.4680 | 40651565 | Structure-Steel | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119211146 | Not Scheduled | T2 EI KESWICK-TRINITY 6/214 RMV VEGN |  | KESWICK-TRINITY | 016/214 | HNA | E | 2020_(3) On high spread structure |  | 2020-06-25 | 2021-06-25 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.69117 | 40.7204 | ETL.7270 | 40668383 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119211456 | Q2 | EI T3NT FULTON-IGNACIO #1 018/091 RPR F | 44310479 | FULTON-IGNACIO #1 | 018/091 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-25 | 2022-06-25 |  |  | 2021-04-23 | 2021-04-19 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592571 | 38.3672 | ETL.4680 | 40594162 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119211546 | Q2 | EI T3NT FULTON-LAKEVILLE 033/145 INST AC | 31529485 | FULTON-LAKEVILLE | 033/145 | 93A | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-25 | 2022-06-25 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592176 | 38.3835 | ETL.4950 | 40681705 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119211576 | Feb | T3 EI KILARC-CEDAR CREEK 11/248 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 011/248 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-25 | 2020-12-25 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.958837 | 40.7669 | ETL.7290 | 40822571 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119211577 | Feb | EI T3NT KILARC-CEDAR CRK 11/248 RMV PL B | 43939119 | KILARC-CEDAR CREEK | 011/248 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-25 | 2022-06-25 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.958837 | 40.7669 | ETL.7290 | 40822571 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119211738 | Feb | T3 EI KILARC-CEDAR CREEK 4/104 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 004/104 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-25 | 2020-12-25 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.954213 | 40.7031 | ETL.7290 | 40602035 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119211889 | Q4 | T2 EI KESWICK-TRINITY 16/215 RPL POLE | 31509665 | KESWICK-TRINITY | 016/215 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-25 | 2021-06-25 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.692062 | 40.7206 | ETL.7270 | 40758301 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119212483 | Not Scheduled | SONOMA-PUEBLO 6/010 RPL POLE | 31508659 | SONOMA-PUEBLO | 006/010 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-24 | 2021-06-24 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.355308 | 38.296 | ETL.3810 | 40588275 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119212488 | Mar | EI MENDOCINO-FORT BRAGG 10/07 RPR GYWW | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 010/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-25 | 2021-06-25 |  |  | 2021-03-15 | 2021-03-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.312409 | 39.36 | ETL.7550 | 44211145 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119212585 | Mar | EI MENDOCINO-FORT BRAGG 10/007 RPR GYWW | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 010/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-25 | 2021-06-25 |  |  | 2021-03-15 | 2021-03-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.312409 | 39.36 | ETL.7550 | 44211146 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119212587 | Mar | EI MENDOCINO-FORT BRAGG 10/007 RPR GYWW | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 010/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-25 | 2021-06-25 |  |  | 2021-03-15 | 2021-03-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.312409 | 39.36 | ETL.7550 | 44211147 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119212602 | Feb | T3 EI KILARC-CEDAR CREEK 10/236 RPR GYWW | 43939119 | KILARC-CEDAR CREEK | 010/236 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-25 | 2020-12-25 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.964835 | 40.7598 | ETL.7290 | 44837802 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119212917 | Not Scheduled | T2 EI GARCIA TAP 001/000 RPL ANCW | 31509677 | GARCIA TAP | 001/000A | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-25 | 2021-06-25 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.579512 | 38.8804 | ETL.8411 | 40577441 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119213090 | Feb | LAYTONVILLE-COVELO 10/001 INST DAMPER | 44579513 | LAYTONVILLE-COVELO | 010/001 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-25 | 2021-06-25 |  |  | 2021-02-24 | 2021-02-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.309999 | 39.7323 | ETL.7390 | 44931536 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119213130 | Feb | T3 EI DESABLA-CENTERVILLE 005/067 RPR GY | 44356201 | DESABLA-CENTERVILLE | 005/067 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-25 | 2020-12-25 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.653684 | 39.7951 | ETL.6720 | 44324217 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119213231 | Feb | T3 EAGLE RCK-FULTN-SLVRDO 6/31 INST INSS | 31530073 | EAGLE ROCK-FULTON-SILVERADO | 006/031 | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-25 | 2020-12-25 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7857857 | 38.7536 | ETL.4392 | 40620217 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119213247 | Q2 | DI RIO BRAVO-KERN OIL 17/0 INS NUMBR | 44609890 | RIO BRAVO-KERN OIL (IDLE) | 017/000 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-04 | 2021-05-04 | [5 empty] | South | WSIP | [6 empty] | '-119.17341 | 35.4415 | ETL.1922 | 44182587 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-06-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119213266 | Not Scheduled | T3 EAGLE RCK-FLTON-SLVRDO 4/17 RPR INSS |  | EAGLE ROCK-FULTON-SILVERADO | 004/017 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-25 | 2020-12-25 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7648931 | 38.6743 | ETL.4392 | 40833091 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119213304 | Feb | T3 EAGLE ROCK-FLTN-SLVRDO 3/17 RPL INSS | 31530073 | EAGLE ROCK-FULTON-SILVERADO | 003/017 | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-25 | 2020-12-25 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7993835 | 38.7982 | ETL.4392 | 40839420 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119213630 | Q2 | DI GATES-PANOCHE#1 12/59 RPR FOND | 44371519 | GATES-PANOCHE #1 | 012/059 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.242715 | 36.2903 | ETL.4720 | 40863290 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119213631 | Not Scheduled | DI GATES-PANOCHE#1 12/59 RPR SHLS | 44371620 | GATES-PANOCHE #1 | 012/059 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2021-06-25 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.242715 | 36.2903 | ETL.4720 | 40863290 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119218629 | Q2 | DI RIO BRAVO-KERN OIL 19/0 RPR INSS | 44609891 | RIO BRAVO-KERN OIL (IDLE) | 019/000 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2021-06-25 |  |  | 2021-05-06 | 2021-05-05 | [5 empty] | South | WSIP | [6 empty] | '-119.1408 | 35.4414 | ETL.1922 | 44182785 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119219039 | Q2 | DI GATES-PANOCHE #1 9/48 RPR FOND | 44394839 | GATES-PANOCHE #1 | 009/048 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-06-24 | 2022-06-24 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.220207 | 36.2614 | ETL.4720 | 40863634 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119219201 | Q4 | T2 EI KESWICK-TRINITY 17/222 RPL POLE | 31509665 | KESWICK-TRINITY | 017/222 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2021-06-26 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.696921 | 40.7213 | ETL.7270 | 40771210 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119219277 | Q4 | T2 EI KESWICK-TRINITY 15/186 RMV BUTT | 44406439 | KESWICK-TRINITY | 015/186 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-26 | 2022-06-26 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.670049 | 40.7135 | ETL.7270 | 40876483 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119219295 | Q2 | EI T3NT FULTON-IGNACIO #1 17/089 RPR FON | 44310479 | FULTON-IGNACIO #1 | 017/089 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-06-26 | 2022-12-26 |  |  | 2021-04-23 | 2021-04-19 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592508 | 38.3739 | ETL.4680 | 40872361 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119219525 | Q2 | T2 IGNACIO-BOLINAS #2 18/205 RPL GUY PL | 31507534 | IGNACIO-BOLINAS #2 | 018/205 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-26 | 2021-06-26 |  |  | 2021-04-15 | 2021-04-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.786068 | 38.042 | ETL.7180 | 40585481 | Guy Pole-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119219700 | Q4 | T2 EI KESWICK-TRINITY 17/224 RPR GYWW | 44406439 | KESWICK-TRINITY | 017/224 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2021-06-26 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.698281 | 40.7215 | ETL.7270 | 40827893 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119219813 | Q2 | T3 EI VOLTA-DESCHUTES 6/147 RPL STRW | 31507081 | VOLTA-DESCHUTES | 006/147 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-26 | 2020-12-26 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.991777 | 40.4908 | ETL.8290 | 40867834 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119220467 | Q3 | T2 CARIBOU-PLUMAS JCT 5/0 INST DAMS |  | CARIBOU-PLUMAS JCT | 005/000 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2021-06-26 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.078105 | 40.0408 | ETL.6290 | 44399524 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119220587 | Q4 | T2 EI KESWICK-TRINITY 17/226 RPR GYWW | 44406439 | KESWICK-TRINITY | 017/226 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2021-06-26 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.699964 | 40.7218 | ETL.7270 | 40809923 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119220651 | Q4 | T3 EI MIDDLE FORK-GOLD HILL 9/78C RPR CO | 44371784 | MIDDLE FORK-GOLD HILL | 009/078C | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2020-12-26 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.736619 | 38.9886 | ETL.5140 | 42569836 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119220788 | Q3 | T2 BRIDGEVILLE-COTTONWD 71/513L REFRAME |  | BRIDGEVILLE-COTTONWOOD | 071/513 |  | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2021-06-26 | 2021-06-21 | 2021-07-17 | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.525613 | 40.468 | ETL.1110 | 44424638 | Crossarm-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade |  | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119220904 | Mar | EI MENDOCINO-FORT BRAGG 10/004 RPR PL | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 010/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2021-06-26 |  |  | 2021-03-15 | 2021-03-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.3091851 | 39.353 | ETL.7550 | 44211109 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119220921 | Mar | EI MENDOCINO-FORT BRAGG 10/4 RPR PL | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 010/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2021-06-26 |  |  | 2021-03-15 | 2021-03-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.3091851 | 39.353 | ETL.7550 | 44211110 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119221007 | Q4 | T3 EI MIDDLE FORK-GOLD HILL_013/114 RPL | 31510070 | MIDDLE FORK-GOLD HILL | 013/114 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2020-12-26 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8101286 | 38.9489 | ETL.5140 | 44553583 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119221045 | Q2 | T2 HAT CREEK #1-WESTWD 1/41 RPL POLE | 31527026 | HAT CREEK #1-WESTWOOD | 001/041 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-26 | 2021-06-26 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.507355 | 40.9225 | ETL.7030 | 40671148 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119221091 | Not Scheduled | T2 SAN LUIS OBISPO-OCEANO 18/1 COMPLETED |  | SAN LUIS OBISPO-OCEANO | 018/102 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-26 | 2021-06-26 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.551777 | 35.0979 | ETL.3530 | 40586174 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119221126 | Mar | T2 EI KILARC-DESCHUTES 8/169 REFRAME | 31507189 | KILARC-DESCHUTES | 008/169 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-26 | 2021-06-26 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.978156 | 40.5972 | ETL.7300 | 40771367 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119221233 | Q3 | T2 BRIDGEVILLE-COTTONWD 71/513R REFRAME |  | BRIDGEVILLE-COTTONWOOD | 071/513 |  | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2021-06-26 | 2021-06-21 | 2021-07-17 | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.5256011 | 40.468 | ETL.1110 | 44424640 | Crossarm-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade |  | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119221244 | Not Scheduled | T3 MONTA VISTA-JEFERSON #1 16/67 RMV VEG | 44627168 | MONTA VISTA-JEFFERSON #1 | 016/067 | CHS | E | 2020_(3) On high spread structure |  | 2020-06-26 | 2020-12-26 | [7 empty] | TR3 | LATE | Central | WSIP | [6 empty] | '-122.298797 | 37.4167 | ETL.5220 | 40819489 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119221300 | Q2 | T3 EI VOLTA-DESCHUTES 6/131 RPL CRSW | 31507464 | VOLTA-DESCHUTES | 006/131 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-26 | 2020-12-26 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.978162 | 40.4875 | ETL.8290 | 40656917 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119221347 | Q2 | DI RIO BRAVO-KERN OIL 16/7 RPLC DAMS | 44609892 | RIO BRAVO-KERN OIL (IDLE) | 016/007 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2021-06-25 |  |  | 2021-05-04 | 2021-05-04 | [5 empty] | South | WSIP | [6 empty] | '-119.176163 | 35.4415 | ETL.1922 | 44182586 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119221486 | Mar | T2 CARIBOU-TABLE MTN 33/244 INST INSS |  | CARIBOU-TABLE MTN | 033/244 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2021-06-26 |  |  | 2021-03-11 | 2021-03-11 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.444897 | 39.827 | ETL.4440 | 40758433 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119221531 | Q4 | T2 EI KESWICK-TRINITY 17/231 RPR GYWW | 44406439 | KESWICK-TRINITY | 017/231 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2021-06-26 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.703544 | 40.7223 | ETL.7270 | 40752207 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119221563 | Q2 | T2 EI IGNACIO-BOLINAS #2 0/2 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 000/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-26 | 2021-06-26 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.543051 | 38.075 | ETL.7180 | 40701427 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119221585 | Q2 | T2NT DI IGNACIO-BLINAS #2 7/97 INST MRKW | 44640732 | IGNACIO-BOLINAS #2 | 007/097 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-24 | 2022-06-24 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.651806 | 38.1155 | ETL.7180 | 40658520 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119221621 | Q2 | DI RIO BRAVO-KERN OIL 18/0 INST MRKS | 44609893 | RIO BRAVO-KERN OIL (IDLE) | 018/000 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-04 | 2021-05-04 | [5 empty] | South | WSIP | [6 empty] | '-119.156209 | 35.4415 | ETL.1922 | 44182665 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119221623 | Q2 | DI RIO BRAVO-KERN OIL 19/1 INST MRKS | 44609894 | RIO BRAVO-KERN OIL (IDLE) | 019/001 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-06 | 2021-05-05 | [5 empty] | South | WSIP | [6 empty] | '-119.138397 | 35.4414 | ETL.1922 | 44182673 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119221625 | Q2 | DI RIO BRAVO-KERN OIL 16/6 INST MRKS | 44609895 | RIO BRAVO-KERN OIL (IDLE) | 016/006 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-04 | 2021-05-04 | [5 empty] | South | WSIP | [6 empty] | '-119.178334 | 35.4415 | ETL.1922 | 44182584 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119221627 | Feb | T3 DI MORAGA-OAKLAND #1 2/18 RPR FOND |  | MORAGA-OAKLAND #1 | 002/018 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-25 | 2020-12-25 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.202108 | 37.8297 | ETL.2720 | 40857637 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119221732 | Q2 | T3 FULTON-CALISTOGA - 16/003 RPL INSW | 31507466 | FULTON-CALISTOGA | '-016/003 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2020-12-26 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.488228 | 38.4578 | ETL.6880 | 40677327 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119221873 | Q2 | DI RIO BRAVO-KERN OIL 14/6 INST MRKS | 44609896 | RIO BRAVO-KERN OIL (IDLE) | 014/006 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-04 | 2021-05-04 | [5 empty] | South | WSIP | [6 empty] | '-119.214072 | 35.4416 | ETL.1922 | 44182531 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119221981 | Q4 | T2 EI KESWICK-TRINITY 17/233 RPR GYWW | 44406439 | KESWICK-TRINITY | 017/233 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2021-06-26 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.704582 | 40.7224 | ETL.7270 | 40824079 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119221984 | Q2 | T2 DRUM-SPAULDING 7/182 RPL POLE | 31508495 | DRUM-SPAULDING | 007/182 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-26 | 2021-06-26 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.668049 | 39.3075 | ETL.6770 | 40601226 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119222169 | Feb | T3 EI KILARC-CEDAR CREEK 9/203 RPL POLE | 31507465 | KILARC-CEDAR CREEK | 009/203 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-26 | 2020-12-26 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.981383 | 40.74 | ETL.7290 | 40701755 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-02-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119222382 | Q2 | DI RO BRV-KRN OIL-KRN OL 13/2 INS MRKS | 44609897 | RIO BRAVO-KERN OIL (IDLE) | 013/002 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-03 | 2021-05-03 | [5 empty] | South | WSIP | [6 empty] | '-119.240634 | 35.4416 | ETL.1922 | 44182506 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119222393 | Q4 | T2 EI KESWICK-TRINITY 17/236 RPR GYWW | 44406439 | KESWICK-TRINITY | 017/236 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2021-06-26 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.706245 | 40.7227 | ETL.7270 | 40590478 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119222426 | Q2 | T3 EI UKIAH-HOPLAND-CLVERDALE 17/4 RPL H | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 017/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-26 | 2020-12-26 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.03921 | 38.8875 | ETL.4050 | 40750650 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119222551 | Q2 | DI RIO BVO-KRN OIL-KRN OIL 19/4 INS MRKS |  | RIO BRAVO-KERN OIL (IDLE) | 019/004 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-06 | 2021-05-05 | [5 empty] | South | WSIP | [6 empty] | '-119.131839 | 35.4414 | ETL.1922 | 44183127 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119222686 | Q2 | T2 EI HAT CREEK #1-WESTWOOD 53/1031REFRA | 31508175 | HAT CREEK #1-WESTWOOD | 053/1031 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-26 | 2021-06-26 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.003802 | 40.3262 | ETL.7030 | 40815902 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119222704 | Not Scheduled | DI GATES-PANOCHE #2 3/20 RPLC DAMPER | 44394924 | GATES-PANOCHE #2 | 003/020 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-06-24 | 2021-06-24 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.162908 | 36.188 | ETL.4730 | 44402080 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119222762 | Q2 | T3 EI VOLTA-DESCHUTES 3/073 RPR STRW | 43939089 | VOLTA-DESCHUTES | 003/073 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-26 | 2020-12-26 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.927898 | 40.4749 | ETL.8290 | 40825122 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119222765 | Q2 | T3 EI VOLTA-DESCHUTES 3/68 RPL POLE | 31507081 | VOLTA-DESCHUTES | 003/068 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-26 | 2020-12-26 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.923615 | 40.4739 | ETL.8290 | 40700104 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119222956 | Not Scheduled | T2 DI CRESTA-RIO OSO 29/236 RPR FOND |  | CRESTA-RIO OSO | 029/236 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-24 | 2021-06-24 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.536297 | 39.5541 | ETL.4590 | 41083097 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119222959 | Q2 | DI RIP BRAVO-KERN OIL 13/5 INS MRKS | 44609899 | RIO BRAVO-KERN OIL (IDLE) | 013/005 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-03 | 2021-05-03 | [5 empty] | South | WSIP | [6 empty] | '-119.233907 | 35.4416 | ETL.1922 | 44182516 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119222999 | Q2 | DI LIGHTNER TAP 0/12 RPLC INSW | 31509578 | LIGHTNER TAP (IDLE) | 000/012 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-06-26 | 2021-06-26 |  |  | 2021-05-10 | 2021-05-10 | [5 empty] | South | WSIP | [8 empty] | ETL.8542 | 44169334 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119224709 | Q2 | EI TRINITY-MAPLE CREEK 43/12 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 043/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-27 | 2021-06-27 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6916913 | 40.7409 | ETL.8170 | 44812835 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119224815 | Q2 | EI TRINITY-MAPLE CREEK 43/12 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 043/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-27 | 2021-06-27 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6916913 | 40.7409 | ETL.8170 | 44812833 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119224816 | Q2 | EI TRINITY-MAPLE CREEK 43/12 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 043/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-27 | 2021-06-27 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6916913 | 40.7409 | ETL.8170 | 44812834 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119224924 | Q2 | T2 TRINITY-MAPLE CREEK 48/4C RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 048/004C | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-27 | 2021-06-27 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.769287 | 40.7522 | ETL.8170 | 44948570 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119224961 | Q2 | T2 TRINITY-MAPLE CREEK 48/4B RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 048/004B | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-27 | 2021-06-27 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.769289 | 40.7522 | ETL.8170 | 40751115 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119224962 | Q2 | T2 TRINITY-MAPLE CREEK 48/4A RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 048/004A | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-27 | 2021-06-27 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.769288 | 40.7522 | ETL.8170 | 44948569 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119225109 | Q2 | T2 EI TRINITY-MAPLE CREEK 44/1 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 044/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-27 | 2021-06-27 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.695262 | 40.7435 | ETL.8170 | 40602086 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119225210 | Q2 | T2 EI TRINITY-MAPLE CREEK 40/4 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 040/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-27 | 2021-06-27 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.6342579 | 40.7213 | ETL.8170 | 44769589 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119227760 | Q2 | DI GATES-PANOCHE #1 5/27 RPR FOND | 44394839 | GATES-PANOCHE #1 | 005/027 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.177452 | 36.2063 | ETL.4720 | 40811168 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119227761 | Not Scheduled | DI GATES-PANOCHE #2 5/27 RPL INSLS | 31527040 | GATES-PANOCHE #2 | 005/027 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2021-06-25 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.177268 | 36.2063 | ETL.4730 | 40836447 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119227762 | Q2 | DI GATES-PANOCHE #1 5/27 RPR STRT | 44394839 | GATES-PANOCHE #1 | 005/027 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2021-06-25 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.177452 | 36.2063 | ETL.4720 | 40811168 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119228442 | Not Scheduled | T2 EI KESWICK-TRNTY 18/238 RMV VEG |  | KESWICK-TRINITY | 018/238 | HNA | E | 2020_(3) On high spread structure |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.707625 | 40.7229 | ETL.7270 | 40909472 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119228443 | Not Scheduled | T2 EI KSWCK-TRNTY 18/238 RMV VEG |  | KESWICK-TRINITY | 018/238 | HNA | E | 2020_(3) On high spread structure |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.707625 | 40.7229 | ETL.7270 | 40909472 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119228733 | Q2 | DI RIO BRAVO-KERN OIL 16/2 INST MRKS |  | RIO BRAVO-KERN OIL (IDLE) | 016/002 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-04 | 2021-05-04 | [5 empty] | South | WSIP | [6 empty] | '-119.187228 | 35.4415 | ETL.1922 | 44182565 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119228827 | Q2 | T2 EI IGNAC-BLNS #2 18/210 RMV VEG |  | IGNACIO-BOLINAS #2 | 018/210 | HNA | E | 2020_(4b) On structure in bucket 4 | Budget Owner (Veg/Land/Road) | 2020-06-29 | 2021-06-29 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.786163 | 38.0419 | ETL.7180 | 40588078 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | HNA | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119228882 | Q2 | DI LIGHTNER TAP 000/011 RPL INSW | 31509578 | LIGHTNER TAP (IDLE) | 000/011 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-06-26 | 2021-06-26 |  |  | 2021-05-10 | 2021-05-10 | [5 empty] | South | WSIP | [8 empty] | ETL.8542 | 44169333 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119228912 | Q2 | T2 EI TRINITY-MAPLE CREEK 47/017 RPR ANC | 44273074 | TRINITY-MAPLE CREEK | 047/017 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.764931 | 40.7515 | ETL.8170 | 40826059 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119228914 | Q4 | MIDDLE FORK-GOLD HILL_033/245 RPL INSS | 31510071 | MIDDLE FORK-GOLD HILL | 033/245 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2020-12-29 |  |  | 2021-11-01 | 2021-10-01 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.0018037 | 38.7248 | ETL.5140 | 44377483 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119229011 | Q2 | T3 EI VOLTA-DESCHUTES 003/081 RPR IBWW | 43939089 | VOLTA-DESCHUTES | 003/081 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2020-12-29 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.93473 | 40.4767 | ETL.8290 | 40769424 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119229078 | Q4 | EI MIDDLE FORK-GOLD HILL 008/074 RPL STR | 31510070 | MIDDLE FORK-GOLD HILL | 008/074 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-11-01 | 2021-10-01 |  |  |  |  | SCHD | North Valley | WSIP | [6 empty] | '-120.7322295 | 38.9931 | ETL.5140 | 44553677 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-10-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119229141 | Q2 | T3 EI FULTON-CALISTOGA :011/5 REPLUMB IN | 44597303 | FULTON-CALISTOGA | :001/005 | ICW | E | 2020_(1a) PSPS |  | 2020-06-29 | 2020-12-29 |  |  | 2021-05-31 | 2021-05-31 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.6107492 | 38.747 | ETL.6880 | 44286126 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119229164 | Not Scheduled | T2 DI SPAULDING-SUMMIT 18/563 RMV BUTT | 44378505 | SPAULDING-SUMMIT | 018/563 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.351785 | 39.308 | ETL.8060 | 40603060 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119229165 | Not Scheduled | T2 DI SPAULDING-SUMMIT 18/563 INST HV | 44378505 | SPAULDING-SUMMIT | 018/563 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.351785 | 39.308 | ETL.8060 | 40603060 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119229167 | Not Scheduled | T2 DI SPAULDING-SUMMIT 18/563 RPLC INSW | 31507463 | SPAULDING-SUMMIT | 018/563 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.351768 | 39.308 | ETL.8060 | 40635784 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119229230 | Q2 | T2 EI TRINITY-MAPLE CREEK 47/16 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 047/016 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.763975 | 40.7514 | ETL.8170 | 44812760 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119229814 | Q2 | T3 EI KONOCTI-MIDDLETOWN 27/009 RPL POLE | 31507469 | KONOCTI-MIDDLETOWN | 027/009 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2020-12-29 | 2021-04-19 | 2021-04-23 | 2021-04-21 | 2021-04-21 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.65038 | 38.9078 | ETL.6380 | 40875523 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119229843 | Not Scheduled | T2 DI SPAULDING-SUMMIT 18/597 RMV BUTT | 44378505 | SPAULDING-SUMMIT | 018/597 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.335237 | 39.311 | ETL.8060 | 40771562 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119229845 | Not Scheduled | T2 DI SPAULDING-SUMMIT 18/597 INST HV | 44378505 | SPAULDING-SUMMIT | 018/597 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.335237 | 39.311 | ETL.8060 | 40771562 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119229846 | Q2 | DI RIO BRAVO-KERN OIL 019/002 RPL INSS | 31526366 | RIO BRAVO-KERN OIL (IDLE) | 019/002 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2021-06-25 |  |  | 2021-05-06 | 2021-05-05 | [5 empty] | South | WSIP | [6 empty] | '-119.1363 | 35.4414 | ETL.1922 | 44185163 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119230352 | Q2 | DI RIO BRAVO-KERN OIL 019/002 INS MRKS |  | RIO BRAVO-KERN OIL (IDLE) | 019/002 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-06 | 2021-05-05 | [5 empty] | South | WSIP | [6 empty] | '-119.136268 | 35.4414 | ETL.1922 | 44183125 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119230356 | Q3 | T3 DI DONNELLS-MI-WUK 014/005 RPR INSW | 44623246 | DONNELLS-CURTIS | 014/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2020-12-26 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.161409 | 38.0847 | ETL.1400 | 44810073 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119230359 | Q3 | T3NT DI DONNELLS-MI-WUK 14/5 RMV PL BUTT | 44623247 | DONNELLS-CURTIS | 014/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-26 | 2022-06-26 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.161409 | 38.0847 | ETL.1400 | 44810085 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119230557 | Q2 | T3 EI KONOCTI-EAGLE ROCK 7/8 RPR GRNDW | 44610613 | KONOCTI-EAGLE ROCK | 007/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2020-12-29 |  |  | 2021-05-07 | 2021-05-07 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.763855 | 38.9108 | ETL.6861 | 40876732 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119230569 | Q4 | T2 EI KESWICK-TRINITY 18/244 RPL ANCHOR | 31509681 | KESWICK-TRINITY | 018/244 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.712218 | 40.7223 | ETL.7270 | 44649258 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119230612 | Not Scheduled | T3 EI FULTON-CALISTOGA :011/003 RPR POLE | 44597303 | FULTON-CALISTOGA | :011/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2020-12-29 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.610362 | 38.7447 | ETL.6880 | 40911337 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119230671 | Not Scheduled | DI GATES-PANOCHE #2 7/38 RPR SHLS | 44394924 | GATES-PANOCHE #2 | 007/038 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-06-24 | 2021-06-24 | [8 empty] | WECC | South | WSIP | [8 empty] | ETL.4730 | 44402088 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119230672 | Q4 | T2 EI KESWICK-TRINITY 18/245 RPR GYWW | 44406439 | KESWICK-TRINITY | 018/245 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.713554 | 40.7221 | ETL.7270 | 44649259 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119230751 | Q2 | T3 EI VOLTA-DESCHUTES 3/082 RMV PL BUTT | 43939089 | VOLTA-DESCHUTES | 003/082 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-29 | 2020-12-29 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.935543 | 40.4768 | ETL.8290 | 40827013 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119230774 | Q2 | EI T3NT UKIAH-HPLND-CLVRDLE 16/7 INST GM | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 016/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-29 | 2022-06-29 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.034138 | 38.8801 | ETL.4050 | 40808567 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119230932 | Q2 | EI UKIAH-HOPLAND-CLOVERDALE 16/6 RPL PL | 31515444 | UKIAH-HOPLAND-CLOVERDALE | 016/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-16 | 2021-04-13 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.0337132 | 38.8795 | ETL.4050 | 44329899 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119230944 | Q2 | DI RIO BRAVO-KERN OIL 015/000 INS MRKW | 44610123 | RIO BRAVO-KERN OIL (IDLE) | 015/000 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-04 | 2021-05-04 | [5 empty] | South | WSIP | [6 empty] | '-119.209637 | 35.4416 | ETL.1922 | 44182533 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119230948 | Q2 | DI RIO BRAVO-KERN OIL 016/004 INS MRKS | 44610124 | RIO BRAVO-KERN OIL (IDLE) | 016/004 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-04 | 2021-05-04 | [5 empty] | South | WSIP | [6 empty] | '-119.182824 | 35.4415 | ETL.1922 | 44182567 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119230949 | Q2 | DI RIO BRAVO-KERN OIL 019/003 INS MRKS | 44610125 | RIO BRAVO-KERN OIL (IDLE) | 019/003 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-06 | 2021-05-05 | [5 empty] | South | WSIP | [6 empty] | '-119.134054 | 35.4414 | ETL.1922 | 44183121 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119230951 | Q2 | T3 EI VOLTA-DESCHUTES 3/086 RPL STRW | 31507081 | VOLTA-DESCHUTES | 003/086 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2020-12-29 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.939017 | 40.4777 | ETL.8290 | 40600280 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119230959 | Feb | T2 DI JOLON TAP 12/172 BOND HRDD | 44575318 | JOLON TAP | 012/172 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 | 2021-02-22 | 2021-02-23 | 2021-02-23 | 2021-02-22 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.1743 | 36.0526 | ETL.7321 | 44212734 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 9 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231135 | Q2 | T3 EI UKIAH-HOPLAND-CLOVERDLE 16/5 RPR S | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 016/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2020-12-29 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.032747 | 38.878 | ETL.4050 | 40761341 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231136 | Q2 | EI T3NT UKIAH-HPLND-CLVRDLE 16/5 INST GM |  | UKIAH-HOPLAND-CLOVERDALE | 016/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-29 | 2022-06-29 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.032747 | 38.878 | ETL.4050 | 40761341 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231178 | Q2 | T3 EI VOLTA-DESCHUTES 004/094 REFRAME CR | 31507464 | VOLTA-DESCHUTES | 004/094 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2020-12-29 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.945788 | 40.4794 | ETL.8290 | 40809975 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231179 | Q2 | T3 EI VOLTA-DESCHUTES 4/096 REFRAME CRSW | 31507464 | VOLTA-DESCHUTES | 004/096 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2020-12-29 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.947447 | 40.4799 | ETL.8290 | 40577284 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231180 | Q2 | T3 EI VOLTA-DESCHUTES 4/087 RPL STRW | 31507081 | VOLTA-DESCHUTES | 004/087 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2020-12-29 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.939948 | 40.4779 | ETL.8290 | 40615924 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-10 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231224 | Q2 | DI LIGHTNER TAP 0/13 RPLC PL | 31509579 | LIGHTNER TAP (IDLE) | 000/013 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-06-26 | 2021-06-26 |  |  | 2021-05-11 | 2021-05-11 | [5 empty] | South | WSIP | [6 empty] | '-118.866375 | 35.3109 | ETL.8542 | 41170556 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119231242 | Feb | T3 EI KILARC-CEDAR CREEK 9/221 REPLUMB I | 43939119 | KILARC-CEDAR CREEK | 009/221 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2020-12-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.9727 | 40.7505 | ETL.7290 | 40639133 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231345 | Q4 | T2 EI KESWICK-TRINITY - 60 kV_018/250 | 44406439 | KESWICK-TRINITY | 018/250 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.715791 | 40.7217 | ETL.7270 | 44649357 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231349 | Q4 | T2 EI KESWICK-TRINITY 018/250 RMV DBRIS | 44406439 | KESWICK-TRINITY | 018/250 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-29 | 2021-06-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.715791 | 40.7217 | ETL.7270 | 44649357 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231390 | Q2 | EI T3NT DEER CREEK-DRUM 0/008 RPR ROAD | 44396253 | DEER CREEK-DRUM | 000/008 | CHS | F | 2020_(3) On high spread structure |  | 2020-06-29 | 2022-06-29 |  |  | 2021-06-30 | 2021-06-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.843535 | 39.2943 | ETL.6690 | 40874924 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | CH | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231515 | Q2 | DI RIO BRAVO-KERN OIL 18/6 INS MRKS |  | RIO BRAVO-KERN OIL (IDLE) | 018/006 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-26 | 2022-06-26 |  |  | 2021-05-06 | 2021-05-05 | [5 empty] | South | WSIP | [6 empty] | '-119.142914 | 35.4414 | ETL.1922 | 44182671 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119231670 | Not Scheduled | T3NT DI CLGTE-ALLGHNY 22/609 RMV PL BUTT | 44378466 | COLGATE-ALLEGHANY | 022/609 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.864067 | 39.4738 | ETL.6470 | 40818515 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231671 | Not Scheduled | T3 DI COLGATE-ALLGHNY 22/609 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 022/609 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2020-12-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.864067 | 39.4738 | ETL.6470 | 40818515 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231769 | Q2 | T2 EI TRINITY-MAPLE CREEK 47/007 RPL INS | 31507478 | TRINITY-MAPLE CREEK | 047/007 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.754067 | 40.75 | ETL.8170 | 44928944 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231770 | Q2 | T2 EI TRINITY-MAPLE CREEK 47/007 RPR ANC | 44273074 | TRINITY-MAPLE CREEK | 047/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.754067 | 40.75 | ETL.8170 | 40826094 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231778 | Q2 | T2 EI TRINITY-MAPLE CREEK 44/7 RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 044/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.703384 | 40.7471 | ETL.8170 | 40808963 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231794 | Not Scheduled | T2 DI SPAULDING-SUMMIT 18/569 REPL POLE | 31507462 | SPAULDING-SUMMIT | 018/569 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.349003 | 39.3079 | ETL.8060 | 40818852 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231834 | Q2 | T2 EI FRT RSS-GUALALA 29/5 RPR WP HOLES |  | GUALALA-MONTE RIO | 029/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 | 2021-06-15 | 2021-06-18 | 2021-06-17 | 2021-06-17 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.225632 | 38.5423 | ETL.6980 | 40769859 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231848 | Q2 | T2 EI TRINITY-MAPLE CREEK 42/11 REPL POL | 31507467 | TRINITY-MAPLE CREEK | 042/011 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.677162 | 40.7313 | ETL.8170 | 40602089 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231860 | Q4 | T2 EI KSWCK-TRNTY-WVRVLL_29/492 RPR REGR | 44406439 | KESWICK-TRINITY | 029/492 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.904461 | 40.7108 | ETL.7270 | 44201737 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231880 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 18/594 INST NUM | 44378505 | SPAULDING-SUMMIT | 018/594 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.337069 | 39.3105 | ETL.8060 | 40593597 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231907 | Q2 | DI RIO BRAVO-KERN OIL 13/3 INS MRKS | 44610127 | RIO BRAVO-KERN OIL (IDLE) | 013/003 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-03 | 2021-05-03 | [5 empty] | South | WSIP | [6 empty] | '-119.238388 | 35.4416 | ETL.1922 | 44182509 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119231911 | Q2 | T2 EI TRINITY-MAPLE CREEK 47/10 INST INS | 31507478 | TRINITY-MAPLE CREEK | 047/010 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.756835 | 40.7504 | ETL.8170 | 40588789 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231917 | Q2 | T2 EI TRINITY-MAPLE CREEK 47/9 RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 047/009 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.75576 | 40.7502 | ETL.8170 | 40876572 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231937 | Q2 | T2 EI IGNAC-BLNS #2 18/211 RPR ANCHORS | 44640732 | IGNACIO-BOLINAS #2 | 018/211 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.784347 | 38.0411 | ETL.7180 | 40861081 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119231943 | Feb | T2 DI JOLON TAP 14/197 BOND HRDD | 44575318 | JOLON TAP | 014/197 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-23 | 2021-06-23 | 2021-02-22 | 2021-02-23 | 2021-02-23 | 2021-02-22 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.173572 | 36.0305 | ETL.7321 | 44212736 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 9 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232065 | Q2 | T2 EI LAKEVILLE #2 12/247 RPR GYWW |  | LAKEVILLE #2 | 012/247 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-05-21 | 2021-05-18 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.688997 | 38.2857 | ETL.7340 | 40827743 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232078 | Q3 | EI BRIDGEVILLE-COTTONWOOD 081/574 RPR PL | 44404493 | BRIDGEVILLE-COTTONWOOD | 081/574 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-07-17 | 2021-06-21 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.7038252 | 40.4764 | ETL.1110 | 44424119 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232181 | Not Scheduled | T3 EI FULTON-CALISTOGA :010/002 RPL ANCH | 31507893 | FULTON-CALISTOGA | :010/002 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2020-12-29 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.608146 | 38.731 | ETL.6880 | 40905749 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232182 | Q2 | T2 EI LAKEVILLE #2 12/248 RPR GYWW |  | LAKEVILLE #2 | 012/248 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-05-21 | 2021-05-18 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.689792 | 38.2863 | ETL.7340 | 40818359 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232242 | Not Scheduled | T2 DI SPAULDING-SUMMIT 17/553 RMV PL BUT | 44401161 | SPAULDING-SUMMIT | 017/553 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.356489 | 39.3092 | ETL.8060 | 40817684 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232256 | Q2 | T2 EI FORT ROSS-GLL-58/11 RPR WP HOLES |  | GUALALA-MONTE RIO | 058/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.520825 | 38.7859 | ETL.6980 | 40584673 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232264 | Q2 | DI RIO BRAVO-KERN OIL 12/7 INS MRKS |  | RIO BRAVO-KERN OIL (IDLE) | 012/007 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 |  |  | 2021-05-03 | 2021-05-03 | [5 empty] | South | WSIP | [6 empty] | '-119.249462 | 35.4416 | ETL.1922 | 44182444 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-06 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119232312 | Q2 | T2 EI TRINITY-MAPLE CREEK 47/6 RPL INSW | 31507478 | TRINITY-MAPLE CREEK | 047/006 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.753021 | 40.7498 | ETL.8170 | 40809436 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232314 | Q2 | T2 EI TRINITY-MAPLE CREEK 47/6 RPR WPKR | 44295371 | TRINITY-MAPLE CREEK | 047/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.753021 | 40.7498 | ETL.8170 | 40809436 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232346 | Q2 | T2 EI LAKEVILLE #2 12/249 RPR GYWW |  | LAKEVILLE #2 | 012/249 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-05-25 | 2021-05-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.690589 | 38.2867 | ETL.7340 | 40864179 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232372 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 14/398 RPR SPLW | 44378462 | COLGATE-ALLEGHANY | 014/398 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2020-12-29 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.995581 | 39.4418 | ETL.6470 | 40894345 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232376 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 14/398 RMV BUTT | 44378466 | COLGATE-ALLEGHANY | 014/398 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.995626 | 39.4419 | ETL.6470 | 40869661 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232382 | Q2 | T2 EI TRINITY-MAPLE CREEK 39/010 RPL INS | 31509759 | TRINITY-MAPLE CREEK | 039/010 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.6258384 | 40.7198 | ETL.8170 | 40641476 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232383 | Q2 | TRINITY-MAPLE CREEK 40/6 RPL INSW | 31507478 | TRINITY-MAPLE CREEK | 040/006 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.6391846 | 40.7232 | ETL.8170 | 40855879 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232408 | Q2 | T2 EI TRINITY-MAPLE CREEK 40/002 RPL INS | 31507478 | TRINITY-MAPLE CREEK | 040/002 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.6292093 | 40.7205 | ETL.8170 | 40711439 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232421 | Q2 | T2 EI TRINITY-MAPLE CREEK 39/007 RPL INS | 31509759 | TRINITY-MAPLE CREEK | 039/007 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.6231504 | 40.7191 | ETL.8170 | 40853378 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232423 | Q2 | T2 EI TRINITY-MAPLE CREEK 39/001 RPL INS | 31509759 | TRINITY-MAPLE CREEK | 039/001 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.611108 | 40.7168 | ETL.8170 | 40602113 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232424 | Q2 | T2 EI TRINITY-MAPLE CREEK 38/10 REPL POL | 31507467 | TRINITY-MAPLE CREEK | 038/010 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.604048 | 40.7138 | ETL.8170 | 40617873 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232469 | Q4 | T2 EI KESWICK-TRINITY 28/487 RMV DEBRIS | 44406439 | KESWICK-TRINITY | 028/487 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-29 | 2022-06-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.897661 | 40.7093 | ETL.7270 | 40906118 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232480 | Not Scheduled | T2 DI SPAULDING-SUMMIT 018/571 RPL INSW | 31507463 | SPAULDING-SUMMIT | 018/571 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.347842 | 39.3081 | ETL.8060 | 40902956 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232537 | Q2 | T2 EI MALIN-ROUND MTN #2 91/462 INST GYM | 44408444 | MALIN-ROUND MTN #2 | 091/462 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.915616 | 40.8531 | ETL.6020 | 40647532 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232552 | Not Scheduled | T2 GARCIA TAP 000/004 RPLC ANCW | 31509677 | GARCIA TAP | 000/004 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.587777 | 38.8701 | ETL.8411 | 40770611 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232686 | Q2 | T2 EI TRINITY-MAPLE CREEK 44/2 RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 044/002 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.696549 | 40.7444 | ETL.8170 | 40658329 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232893 | Q2 | T2 EI TRINITY-MAPLE CREEK 39/2 RPL PL | 31509758 | TRINITY-MAPLE CREEK | 039/002 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.613756 | 40.7178 | ETL.8170 | 40701808 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232898 | Feb | T3 EI KILARC-CEDAR CREEK 7/175 RPL POLE | 31507465 | KILARC-CEDAR CREEK | 007/175 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2020-12-29 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.994808 | 40.7239 | ETL.7290 | 40824224 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-02-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119232957 | Mar | T3 EI DEER CREEK-DRUM 02/073 RPL POLE | 31507470 | DEER CREEK-DRUM | 002/073 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2020-12-29 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.818572 | 39.2629 | ETL.6690 | 40818994 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233013 | Q2 | T2 EI TRINITY-MAPLE CREEK_038/011L RPL P | 31509758 | TRINITY-MAPLE CREEK | 038/011 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.606213 | 40.7145 | ETL.8170 | 44771089 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233053 | Q2 | T2 EI TRINITY-MAPLE CREEK_038/011C RPL P | 31509758 | TRINITY-MAPLE CREEK | 038/011 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.606213 | 40.7145 | ETL.8170 | 44771091 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233064 | Q2 | T2 EI TRINITY-MAPLE CREEK_038/011R RPL P | 31509758 | TRINITY-MAPLE CREEK | 038/011 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2021-06-29 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.606213 | 40.7145 | ETL.8170 | 44771090 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233085 | Q2 | DI GATES-PANOCHE 6/34 RPR STRT | 44394839 | GATES-PANOCHE #1 | 006/034 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2021-06-25 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.191787 | 36.2248 | ETL.4720 | 40753575 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-10 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119233150 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 3/123 INS VIS | 44378505 | SPAULDING-SUMMIT | 003/123 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.589626 | 39.3135 | ETL.8060 | 40771495 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233412 | Q2 | T3 IGNACIO-BOLINAS #1 9/104A PRPL ANCW | 31507472 | IGNACIO-BOLINAS #1 | 009/104A | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2020-12-29 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.657499 | 37.9899 | ETL.7140 | 40584912 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-11 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233416 | Q2 | T3 EI IGNACIO-BOLINAS #1 8/100 RPLUMB IN | 44640733 | IGNACIO-BOLINAS #1 | 008/100 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2020-12-29 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.656185 | 37.9976 | ETL.7140 | 40808615 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233419 | Not Scheduled | T3 EI IGNACIO-BOLINAS #1 9/101 RMV VEG |  | IGNACIO-BOLINAS #1 | 009/101 | HNA | E | 2020_(3) On high spread structure | Budget Owner (Veg/Land/Road) | 2020-06-29 | 2020-12-29 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.656368 | 37.9967 | ETL.7140 | 40861143 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233430 | Q2 | T3 EI IGNACIO-BOLINAS #1 009/101 RPR CON | 44640733 | IGNACIO-BOLINAS #1 | 009/101 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2020-12-29 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.656368 | 37.9967 | ETL.7140 | 40861143 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233431 | Q2 | T3 EI IGNACIO-BOLINAS #1 009/101 RPR ANC | 44640733 | IGNACIO-BOLINAS #1 | 009/101 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-29 | 2020-12-29 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.656368 | 37.9967 | ETL.7140 | 40861143 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233475 | Not Scheduled | T2 DI SPAULDING-SUMMIT 3/136 CANCEL | 44396746 | SPAULDING-SUMMIT | 003/136 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.582738 | 39.3092 | ETL.8060 | 40826185 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233552 | Not Scheduled | T2 DI SPAULDING-SUMMIT 19/600 RMV PL BUT | 44401161 | SPAULDING-SUMMIT | 019/600 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.333811 | 39.3113 | ETL.8060 | 40602283 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233591 | Not Scheduled | T2 DI SPAULDING-SUMMIT 4/144 RPLC INSW | 31507463 | SPAULDING-SUMMIT | 004/144 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.579055 | 39.3079 | ETL.8060 | 40855938 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233594 | Q2 | DI RIO BRAVO-KERN OIL 018/003 INS MRKS | 44610130 | RIO BRAVO-KERN OIL (IDLE) | 018/003 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-25 | 2022-06-25 |  |  | 2021-05-06 | 2021-05-05 | [5 empty] | South | WSIP | [6 empty] | '-119.149565 | 35.4415 | ETL.1922 | 44182668 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119233717 | Not Scheduled | T2 DI SPAULDING-SUMMIT 3/125 RPLC INSW | 31507463 | SPAULDING-SUMMIT | 003/125 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.587863 | 39.3139 | ETL.8060 | 40855937 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233810 | Not Scheduled | T2 DI SPAULDING-SUMMIT 003/128 CMPLTD | 44396747 | SPAULDING-SUMMIT | 003/128 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.586159 | 39.3122 | ETL.8060 | 40869721 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233816 | Not Scheduled | T2 DI SPAULDING-SUMMIT 4/145 RPR HRDW | 44401099 | SPAULDING-SUMMIT | 004/145 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.578512 | 39.3078 | ETL.8060 | 40809651 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119233866 | Not Scheduled | T2NT DI SPLDING-SUMMIT 17/560 RMV PL BUT | 44396746 | SPAULDING-SUMMIT | 017/560 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.353061 | 39.3084 | ETL.8060 | 40771538 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119234531 | Not Scheduled | T2NT DI SPLDING-SUMMIT 18/568 RMV PL BUT | 44396746 | SPAULDING-SUMMIT | 018/568 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.34953 | 39.3078 | ETL.8060 | 40770688 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119234535 | Not Scheduled | T2NT DI SPLDING-SUMMIT 17/562 RMV PL BUT | 44396746 | SPAULDING-SUMMIT | 017/562 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.352209 | 39.3081 | ETL.8060 | 40828156 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119234537 | Not Scheduled | T2NT DI SPLDING-SMMT 19/608 INS HI SIGN | 44401161 | SPAULDING-SUMMIT | 019/608 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.330513 | 39.3136 | ETL.8060 | 40861956 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119234557 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 21/578 RPR CNDW | 44378807 | COLGATE-ALLEGHANY | 021/578 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.885107 | 39.4702 | ETL.6470 | 40723270 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119234710 | Not Scheduled | T3 DI COLGATE-ALLEGHANY 21/578 RPR INSW | 44378807 | COLGATE-ALLEGHANY | 021/578 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-23 | 2020-12-23 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.885107 | 39.4702 | ETL.6470 | 40723270 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119234722 | Not Scheduled | T2 DI SPAULDING-SUMMIT 19/606 RMV PL BUT | 44401161 | SPAULDING-SUMMIT | 019/606 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.330831 | 39.313 | ETL.8060 | 40809681 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119234723 | Not Scheduled | T2NT DI SPLDING-SUMMIT 17/557 INST MRKW | 44396746 | SPAULDING-SUMMIT | 017/557 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.354533 | 39.3089 | ETL.8060 | 40593594 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119234724 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 4/157 RMV BUTT | 44401161 | SPAULDING-SUMMIT | 004/157 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.573035 | 39.3066 | ETL.8060 | 40876682 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119235189 | Q2 | T3 EI UKIAH-HOPLAND-CLVERDLE 15/0 RPR GY | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 015/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.011925 | 38.8585 | ETL.4050 | 40603870 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119235282 | Q2 | EI T2NT MALIN-RND MTN #2 91/465 INS GMRK | 44408444 | MALIN-ROUND MTN #2 | 091/465 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-30 | 2022-06-30 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.914241 | 40.8462 | ETL.6020 | 40765412 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119235397 | Mar | DI FULTON-HOPLAND 011/004 RPR GYWW | 44579280 | FULTON-HOPLAND | 011/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.854232 | 38.627 | ETL.6890 | 40750551 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119235416 | Not Scheduled | T2NT DI SPLDNG-SMMT 19/610 INST HI SIGN | 44401161 | SPAULDING-SUMMIT | 019/610 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.329993 | 39.3146 | ETL.8060 | 40586104 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119235417 | Q2 | DI RIO BRAVO-KERN OIL 12/5 INST MRKW | 44610131 | RIO BRAVO-KERN OIL (IDLE) | 012/005 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 |  |  | 2021-05-03 | 2021-05-03 | [5 empty] | South | WSIP | [6 empty] | '-119.253942 | 35.4416 | ETL.1922 | 44182434 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119235419 | Q2 | DI GATES-PANOCHE #1 3/17 RPR FOND | 44402243 | GATES-PANOCHE #1 | 003/017 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.156325 | 36.1802 | ETL.4720 | 40818928 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119235495 | Mar | T2 EI KILARC-DESCHUTES 002/055 RPLC STRW | 31509538 | KILARC-DESCHUTES | 002/055 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.895151 | 40.6447 | ETL.7300 | 40656957 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119235580 | Mar | T3 EI GEYSERS #3-CLVRDLE 10/117L RPR GYW | 44580896 | GEYSERS #3-CLOVERDALE | 010/117 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.9837705 | 38.8008 | ETL.1650 | 44298339 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119235610 | Q2 | DI RIO BRAVO-KERN OIL 12/4 INST MRKS | 44610132 | RIO BRAVO-KERN OIL (IDLE) | 012/004 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 |  |  | 2021-05-03 | 2021-05-03 | [5 empty] | South | WSIP | [6 empty] | '-119.256165 | 35.4416 | ETL.1922 | 44182429 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119235615 | Not Scheduled | T2NT DI SPLDING-SUMMIT 18/585 INST MRKW | 44396746 | SPAULDING-SUMMIT | 018/585 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.340832 | 39.3095 | ETL.8060 | 40771542 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119235628 | Not Scheduled | T2 EI FULTON-CALISTOGA :11/7 RPR STRW | 44597303 | FULTON-CALISTOGA | :011/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.610053 | 38.749 | ETL.6880 | 44247812 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119235764 | Q4 | T2 EI KESWICK-TRINITY 28/484 RMV PL BUTT | 43939188 | KESWICK-TRINITY | 028/484 | ICW | E | 2020_(3) On high spread structure |  | 2020-06-30 | 2021-06-30 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.896223 | 40.709 | ETL.7270 | 40908541 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119235802 | Not Scheduled | T2NT DI SPLDING-SMMIT 18/584 RMV PL BUT | 44396746 | SPAULDING-SUMMIT | 018/584 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.341282 | 39.3094 | ETL.8060 | 40586102 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119235899 | Mar | T3 EI DEER CREEK-DRUM 001/044 RPR STRW | 44379163 | DEER CREEK-DRUM | 001/044 | ICW | E | 2020_(1a) PSPS |  | 2020-06-30 | 2020-12-30 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.833848 | 39.2723 | ETL.6690 | 40671627 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119235901 | Q4 | T2 EI KESWICK-TRINITY 018/251 RPR GYWW | 44406439 | KESWICK-TRINITY | 018/251 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.71718 | 40.7215 | ETL.7270 | 44649276 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119235940 | Not Scheduled | T2NT DI SPLDING-SUMMIT 4/155 RMV BUTT | 44401161 | SPAULDING-SUMMIT | 004/155 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.573803 | 39.3068 | ETL.8060 | 40826188 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119235943 | Mar | DI FULTON-HOPLAND 11/8 RMV PL BUTT | 44579280 | FULTON-HOPLAND | 011/008 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-29 | 2021-06-29 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.85745 | 38.6314 | ETL.6890 | 40874585 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119235944 | Q2 | DI RIO BRAVO-KERN OIL 13/1 INST MRKS | 44610134 | RIO BRAVO-KERN OIL (IDLE) | 013/001 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-26 | 2022-06-26 |  |  | 2021-05-03 | 2021-05-03 | [5 empty] | South | WSIP | [6 empty] | '-119.242849 | 35.4416 | ETL.1922 | 44182477 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119236004 | Q2 | T2 EI TRINITY-MAPLE CREEK 47/3 RPL INSW | 31507478 | TRINITY-MAPLE CREEK | 047/003 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.750779 | 40.7495 | ETL.8170 | 40649282 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236029 | Mar | DI FULTON-HOPLAND 011/004A RPR GYWW | 44579280 | FULTON-HOPLAND | 011/004A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.854288 | 38.6278 | ETL.6890 | 40576013 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236040 | Q2 | T2 IGNACIO-BOLINAS #2 15/175 INST NUMBR | 44640735 | IGNACIO-BOLINAS #2 | 015/175 | ICS | F | 2020_(3) On high spread structure |  | 2020-06-30 | 2022-06-30 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.742111 | 38.0492 | ETL.7180 | 40751201 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236072 | Q4 | T2 EI KESWICK-TRINITY 28/480 RMV PL BUTT | 44406439 | KESWICK-TRINITY | 028/480 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-30 | 2022-06-30 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.892603 | 40.708 | ETL.7270 | 40906117 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236116 | Not Scheduled | T2 DI SPAULDING-SUMMIT 3/129 BOND GUY | 44396747 | SPAULDING-SUMMIT | 003/129 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.585718 | 39.3113 | ETL.8060 | 40618183 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236121 | Q2 | T2 EI TRINITY-MAPLE CREEK 47/2 REFRAME | 31507467 | TRINITY-MAPLE CREEK | 047/002 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.750096 | 40.7494 | ETL.8170 | 40658338 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236163 | Mar | DI FULTON-HOPLAND 011/004A RPL INSW | 31511041 | FULTON-HOPLAND | 011/004A | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.854193 | 38.6277 | ETL.6890 | 40577924 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236260 | Not Scheduled | T2 DI SPAULDING-SUMMIT 3/133 RMV BUTT | 44396746 | SPAULDING-SUMMIT | 003/133 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.584186 | 39.3098 | ETL.8060 | 40771497 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236271 | Not Scheduled | EI ROUND MTN-TABLE MTN #1 - 500 kV_080/3 |  | ROUND MTN-TABLE MTN #1 | 080/327 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.704595 | 39.663 | ETL.6060 | 40808609 | Anchor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236274 | Q2 | T2 EI IGNACIO-BOLINAS #2 15/176 INST GUA | 44640732 | IGNACIO-BOLINAS #2 | 015/176 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-30 | 2022-06-30 |  |  | 2021-04-15 | 2021-04-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.743056 | 38.0483 | ETL.7180 | 40827646 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236276 | Q2 | T2 EI IGNACIO-BOLINAS #2 15/176 RPR ANCW | 44640732 | IGNACIO-BOLINAS #2 | 015/176 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-15 | 2021-04-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.743056 | 38.0483 | ETL.7180 | 40827646 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236361 | Q2 | T2 EI TRINITY-MAPLE CREEK 47/0 RPL INSW | 31507478 | TRINITY-MAPLE CREEK | 047/000 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.74778 | 40.7491 | ETL.8170 | 40617903 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236362 | Q2 | T2 EI TRINITY-MAPLE CREEK 47/0 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 047/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.74778 | 40.7491 | ETL.8170 | 40617903 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236383 | Q4 | T2 EI KESWICK-TRINITY 018/256 RPR GYWW | 44406439 | KESWICK-TRINITY | 018/256 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.722973 | 40.7206 | ETL.7270 | 44649358 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236396 | Mar | T3 EI GEYSERS #3-CLOVRDLE 10/115 RPR STR | 44580896 | GEYSERS #3-CLOVERDALE | 010/115 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.9803157 | 38.8008 | ETL.1650 | 44298334 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236398 | Q3 | T2 EI BRDGVIL-GRBERVILE 21/6 RPR WDPKR | 44299806 | BRIDGEVILLE-GARBERVILLE | 021/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.758843 | 40.2252 | ETL.6220 | 40810939 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236409 | Not Scheduled | T2 DI SPAULDING-SUMMIT 19/599 RMV PL BUT | 44401161 | SPAULDING-SUMMIT | 019/599 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.334275 | 39.3112 | ETL.8060 | 40618247 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236421 | Q4 | EI T2NT KESWICK-TRINITY 018/256 RMV BUTT | 44406439 | KESWICK-TRINITY | 018/256 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-30 | 2022-06-30 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.722973 | 40.7206 | ETL.7270 | 44649358 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236535 | Q2 | T2 EI TRINITY-MAPLE CREEK 46/012 RPL INS | 31507478 | TRINITY-MAPLE CREEK | 046/012 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.7459525 | 40.7488 | ETL.8170 | 40711447 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236577 | Mar | DI FULTON-HOPLAND 11/6 RMV PL BUTT | 44579280 | FULTON-HOPLAND | 011/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-30 | 2022-06-30 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.856163 | 38.6287 | ETL.6890 | 40808865 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236579 | Mar | DI FULTON-HOPLAND 11/6 RPR GYWW | 44579280 | FULTON-HOPLAND | 011/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-28 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.856163 | 38.6287 | ETL.6890 | 40808865 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236596 | Q2 | T2 EI FULTON-CALISTOGA -11/10 REPL POLE | 31507659 | FULTON-CALISTOGA | '-011/010 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.52255 | 38.3985 | ETL.6880 | 40588847 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236690 | Q3 | T2 EI BRIDGEVILLE-GARBERVILLE 21/4 RPR P | 31508614 | BRIDGEVILLE-GARBERVILLE | 021/004 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-08-28 | 2021-08-23 |  |  | Likely MAT error - delink to correct | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.759815 | 40.2279 | ETL.6220 | 40769355 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236722 | Q2 | T3 EI IGNACIO-BOLINAS #2 017/196 RPR GYW | 44640732 | IGNACIO-BOLINAS #2 | 017/196 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-04-15 | 2021-04-15 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.771178 | 38.0383 | ETL.7180 | 44868824 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236725 | Mar | T2 EI EAGLE ROCK-CORTINA 020/001 RPR STR | 44563312 | EAGLE ROCK-CORTINA | :020/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.611978 | 39.0104 | ETL.1470 | 41176412 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236781 | Q2 | T2 EI FORT ROSS-GUALALA 58/005 RMV HRDW |  | GUALALA-MONTE RIO | 058/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.514383 | 38.7801 | ETL.6980 | 40750323 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236899 | Q2 | T3 EI LAKVLE-ST HLNA JCT 07/05C RPR GYWW |  | LAKEVILLE #1 | 007/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 |  |  | 2021-06-01 | 2021-05-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.5701715 | 38.3551 | ETL.7360 | 44562787 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236900 | Not Scheduled | T3 EI LAKVLE-ST HLNA JCT 07/05R RPR GYWW |  | LAKEVILLE #1 | 007/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.5701715 | 38.3551 | ETL.7360 | 44563014 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119236901 | Q2 | T3 EI LAKVLE-ST HLNA JCT 07/05L RPR GYWW |  | LAKEVILLE #1 | 007/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 |  |  | 2021-06-01 | 2021-05-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.5701715 | 38.3551 | ETL.7360 | 44562753 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237030 | Q3 | T2 EI BRIDGEVILE-GARBERVILE 21/0 RPL ANC | 31508615 | BRIDGEVILLE-GARBERVILLE | 021/000 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.760588 | 40.2322 | ETL.6220 | 40591113 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237110 | Q2 | T2 EI LAKEVILLE #2 012/258 RPR GYWW |  | LAKEVILLE #2 | 012/258 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-05-21 | 2021-05-18 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.698516 | 38.2907 | ETL.7340 | 40864181 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-20 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237154 | Mar | T3 MORAGA-OAKLAND #1 0/4 RPR JUMPER | 44621679 | MORAGA-OAKLAND #1 | 000/004 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.1703901 | 37.8467 | ETL.2720 | 40774002 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 15 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237202 | Mar | EI GEYSERS NO. 3-UKIAH_009/114 RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 009/114 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-27 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.9761618 | 38.8007 | ETL.1650 | 44258747 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237264 | Feb | T3 EGL RCK-FULTN-SLVRDO 2/15 RPL INSS |  | EAGLE ROCK-FULTON-SILVERADO | 002/015 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.8007822 | 38.8027 | ETL.4392 | 40785663 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237273 | Q2 | T2 EI TRINITY-MAPLE CREEK 46/6 RPL INSW | 31507478 | TRINITY-MAPLE CREEK | 046/006 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.736973 | 40.7486 | ETL.8170 | 40828017 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237340 | Q3 | T2 EI BRIDGEVILLE-GARBERVILLE 20/11 RPL | 31508614 | BRIDGEVILLE-GARBERVILLE | 020/011 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.761423 | 40.2366 | ETL.6220 | 40600514 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237441 | Not Scheduled | T3 EGLE RCK-FLTN-SILVRDO :3/15 RPL INSS | 31478217 | EAGLE ROCK-FULTON-SILVERADO | :003/015 | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.766466 | 38.6857 | ETL.4392 | 40780773 | Insulator-Steel | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237533 | Q2 | T2 EI FULTON-CALISTOGA -012/002 RPL ANCH | 31509674 | FULTON-CALISTOGA | '-012/002 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.523093 | 38.4026 | ETL.6880 | 40658395 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237647 | Q2 | T2 EI TRINITY-MAPLE CREEK 46/009 RPR GYW | 44273074 | TRINITY-MAPLE CREEK | 046/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.741953 | 40.7484 | ETL.8170 | 40861363 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237649 | Q2 | T2 EI TRINITY-MAPLE CREEK 46/009 RPR ANC | 44364310 | TRINITY-MAPLE CREEK | 046/009 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.741953 | 40.7484 | ETL.8170 | 40861363 | Anchor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237670 | Q2 | T2 EI TRINITY-MAPLE CREEK 46/009 RPR GYW | 44364310 | TRINITY-MAPLE CREEK | 046/009 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.741953 | 40.7484 | ETL.8170 | 40861363 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237677 | Q4 | T2 EI KESWICK-TRINITY 027/470 RPLC STRW | 31509665 | KESWICK-TRINITY | 027/470 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.88406 | 40.7039 | ETL.7270 | 40908530 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237853 | Q4 | T3 MAPLE CREEK-HOOPA 012/006 RPL CONDW | 31508094 | MAPLE CREEK-HOOPA | 012/006 | 93C | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.757625 | 40.9071 | ETL.7490 | 44743797 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237898 | Not Scheduled | EI T2NT MALIN-RND MTN #2 90/457 CANCEL | 44408444 | MALIN-ROUND MTN #2 | 090/457 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-06-30 | 2022-06-30 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.915168 | 40.8631 | ETL.6020 | 40810014 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237961 | Not Scheduled | T3 FULTON-CALISTOGA :009/009 RPL POLE | 31507532 | FULTON-CALISTOGA | :009/009 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.607221 | 38.7255 | ETL.6880 | 40861224 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119237975 | Not Scheduled | T3 EI TMBLR-SN LS OBSP 42/242 REPLUMB IN |  | TEMBLOR-SAN LUIS OBISPO | 042/242 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.4147111 | 35.3694 | ETL.3960 | 40703545 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238057 | Not Scheduled | T3 EI ATASCADERO-CAYUCOS 007/062 RPR CON |  | ATASCADERO-CAYUCOS | 007/062 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.792829 | 35.4567 | ETL.8480 | 40679170 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238163 | Q2 | EI TRINITY-MAPLE CREEK 37/7 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 037/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.5839079 | 40.7147 | ETL.8170 | 44820904 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238170 | Q2 | T2 EI TRINITY-MAPLE CREEK 37/2 RPL INSW | 31509759 | TRINITY-MAPLE CREEK | 037/002 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.5778246 | 40.7168 | ETL.8170 | 40735649 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238172 | Q2 | T2 EI TRINITY-MAPLE CREEK 37/9 RPLC INSW | 31509759 | TRINITY-MAPLE CREEK | 037/009 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.586532 | 40.7129 | ETL.8170 | 40883111 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238173 | Q2 | T2 EI TRNTY-MPL CRK 37/0 RPL INSW | 31509759 | TRINITY-MAPLE CREEK | 037/000 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.5759429 | 40.7173 | ETL.8170 | 40641480 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238174 | Q2 | T2 EI TRINITY-MAPLE CREEK 38/1 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 038/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.592283 | 40.7109 | ETL.8170 | 40602112 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238216 | Q2 | T2 EI TRINITY-MAPLE CREEK 38/8 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 038/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.601175 | 40.7129 | ETL.8170 | 40877943 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238259 | Not Scheduled | T2 DI SPAULDING-SUMMIT 4/141 REMV BUTT | 44396746 | SPAULDING-SUMMIT | 004/141 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.580339 | 39.3084 | ETL.8060 | 40659230 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238262 | Q2 | T2 EI TRINITY-MAPLE CREEK 38/2 RPL POLE | 31509758 | TRINITY-MAPLE CREEK | 038/002 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.594198 | 40.7111 | ETL.8170 | 40701812 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238263 | Q2 | T2 EI TRINITY-MAPLE CREEK 38/6 RPL POLE | 31509758 | TRINITY-MAPLE CREEK | 038/006 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.599019 | 40.7123 | ETL.8170 | 40809432 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238265 | Q2 | T2 EI TRINITY-MAPLE CREEK 37/8 REPL INSU | 31509755 | TRINITY-MAPLE CREEK | 037/008 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.584766 | 40.7142 | ETL.8170 | 44700080 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238266 | Q2 | T2 EI TRINITY-MAPLE CREEK 37/010 RPL INS | 31509759 | TRINITY-MAPLE CREEK | 037/010 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.5883002 | 40.7115 | ETL.8170 | 40641479 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238268 | Q2 | T2 EI TRINITY-MAPLE CREEK 38/8 RPL INSW | 31509759 | TRINITY-MAPLE CREEK | 038/008 | 93I | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.601175 | 40.7129 | ETL.8170 | 40877943 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238313 | Q2 | T2 EI LAKEVILLE #2 13/268 RPR GYWW |  | LAKEVILLE #2 | 013/268 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-05-21 | 2021-05-18 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.705341 | 38.2954 | ETL.7340 | 40876368 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238425 | Q2 | EI UKIAH-HOPLAND-CLOVERDAL 13/4 RPR GYWW | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 013/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-16 | 2021-04-13 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.9979898 | 38.8444 | ETL.4050 | 44838824 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238501 | Q2 | EI UKIAH-HOPLAND-CLOVERDALE 13/004 RPR G | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 013/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-16 | 2021-04-13 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.9979898 | 38.8444 | ETL.4050 | 44838830 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238509 | Q2 | EI UKIAH-HOPLAND-CLOVERDALE 13/4 RPR GYW | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 013/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-16 | 2021-04-13 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.9979898 | 38.8444 | ETL.4050 | 44838827 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238526 | Q3 | T2 BRIDGEVILLE-COTTONWD 71/513C REFRAME |  | BRIDGEVILLE-COTTONWOOD | 071/513 |  | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 | 2021-06-21 | 2021-07-17 | 2021-07-17 | 2021-06-21 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.525613 | 40.468 | ETL.1110 | 44424639 | Crossarm-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade |  | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238543 | Q2 | T2 EI FORT ROSS-GUALALA 57/11 RPR CRSW |  | GUALALA-MONTE RIO | 057/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.515151 | 38.7736 | ETL.6980 | 40584670 | Crossarm-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238556 | Q4 | T2NT EI KESWICK-TRINTY 26/435 RMV DEBRIS | 43939188 | KESWICK-TRINITY | 026/435 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-30 | 2022-06-30 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.860184 | 40.6952 | ETL.7270 | 40906491 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238567 | Q4 | T2 EI KESWICK-TRINITY 26/435 RPR ANCW | 43939188 | KESWICK-TRINITY | 026/435 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.860184 | 40.6952 | ETL.7270 | 40906491 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238570 | Q2 | T3 EI IGNACIO-BOLINAS #1 10/107 RPL STR | 31507533 | IGNACIO-BOLINAS #1 | 010/107 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.658253 | 37.9824 | ETL.7140 | 40750702 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238572 | Q2 | T3 EI IGNACIO-BOLINAS #1 010/108 RPL ANC | 31507567 | IGNACIO-BOLINAS #1 | 010/108 | 93E | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.658882 | 37.9805 | ETL.7140 | 40750567 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-11 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238574 | Q2 | T3 EI IGNACIO-BOLINAS #1 10/110 RPR GYWW | 44640733 | IGNACIO-BOLINAS #1 | 010/110 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.659548 | 37.9782 | ETL.7140 | 40588059 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238737 | Mar | T2 EI KILARC-DESCHUTES 001/031 RPR STRW | 44406470 | KILARC-DESCHUTES | 001/031 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.881354 | 40.6577 | ETL.7300 | 40867878 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238751 | Mar | T2 EI KILARC-DESCHUTES 001/027 RPLC STR | 31509538 | KILARC-DESCHUTES | 001/027 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.878906 | 40.6604 | ETL.7300 | 40770448 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238770 | Q2 | T2 EI LAKEVILLE #2 013/272 RPR GYWW |  | LAKEVILLE #2 | 013/272 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-05-25 | 2021-05-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.708271 | 38.297 | ETL.7340 | 40659324 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238775 | Not Scheduled | T2 VC-VACVILL-JAMESON 8/65 RPL INSS | 31509483 | VACA-VACAVILLE-JAMESON-NTH TWR | 008/065 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.036462 | 38.3331 | ETL.4100 | 40841259 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238796 | Not Scheduled | T2 GARCIA TAP 01/000B RPL ANCHOR | 31509677 | GARCIA TAP | 001/000 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.579544 | 38.8805 | ETL.8411 | 40740720 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238809 | Mar | T2 BELLOTA-RVRBNK-MELNS SS_:0/9 RPR HRDW |  | BELLOTA-RIVERBANK-MELONES SW STA | :000/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-05 | 2021-03-04 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.531594 | 37.9385 | ETL.1070 | 40857249 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 15 | USBR | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-09-23 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238900 | Q2 | T2 EI HAT CRK #1-WSTWD 12/249 REPL POLE | 31508175 | HAT CREEK #1-WESTWOOD | 012/249 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.368238 | 40.8175 | ETL.7030 | 40817101 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-22 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238907 | Mar | T3 MORAGA-OAKLAND #3 1/010 RPL INSS | 31504796 | MORAGA-OAKLAND #3 | 001/010 | 93K | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 | 2021-03-28 | 2021-03-30 | 2021-03-30 | 2021-03-28 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.1823711 | 37.8409 | ETL.2740 | 40621983 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 14 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-25 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119238924 | Not Scheduled | T2 WEST PNT-VLLY SPRINGS 10/121 RPL INSW | 31495257 | WEST POINT-VALLEY SPRINGS | 010/121 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.669403 | 38.3336 | ETL.8350 | 40744886 | Insulator-Wood | No Good/Out of Stdrd | Replace | MAPP srdy | MAPP | Constructed and mapped | Complete | PEND | LC | TLN | Pole Program | Capital | 508 | Victor |  | Y - 36 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-09-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119289776 | Q4 | T3 DI MDL FRK-GLD HL 3/29L REPL POLE | 31510070 | MIDDLE FORK-GOLD HILL | 003/029 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-28 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  | REJECT: Crew was unable to complete work. Woodpecker Holes were repaired under LC# 117359105 and Insulators were changed under LC# 119289773. Crew still needs to replace all three poles LC#'s 119289776, 119304269, 119304312 |  |  | '-120.633678 | 38.9982 | ETL.5140 | 44769627 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  | Reject | 2020-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119289790 | Mar | EI T3NT DEER CREEK-DRUM 3/094 RMV DEBRIS | 44379163 | DEER CREEK-DRUM | 003/094 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-30 | 2022-06-30 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.804343 | 39.2602 | ETL.6690 | 40866094 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119289792 | Mar | T3 EI DEER CREEK-DRUM 04/106 RPR ANCRW | 44379163 | DEER CREEK-DRUM | 004/106 | ICW | E | 2020_(1a) PSPS |  | 2020-06-30 | 2020-12-30 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.797361 | 39.2564 | ETL.6690 | 40822856 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119289794 | Mar | EI T3NT DEER CREEK-DRUM 3/93 RMV PL BUTT | 44379163 | DEER CREEK-DRUM | 003/093 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-30 | 2022-06-30 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.804768 | 39.2608 | ETL.6690 | 40866660 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119289810 | Not Scheduled | T2 DI SPAULDING-SUMMIT 3/135 RPR SPLW | 44379171 | SPAULDING-SUMMIT | 003/135 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.583289 | 39.3094 | ETL.8060 | 40847863 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119289919 | Q2 | T3 DI WEIMAR #1 012/172 RPR STRW | 44379167 | WEIMAR #1 | 012/172 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.7560 | 44414818 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119289939 | Mar | T2 EI KILARC-DESCHUTES 02/57 REFRAME | 31510881 | KILARC-DESCHUTES | 002/057 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.895517 | 40.6444 | ETL.7300 | 40759277 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119289941 | Mar | T2 EI KILARC-DESCHUTES 02/57 RPR POLE | 44406469 | KILARC-DESCHUTES | 002/057 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.895517 | 40.6444 | ETL.7300 | 40759277 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119289946 | Mar | T2 EI KILARC-DESCHUTES 001/041 RPR INSU | 44406470 | KILARC-DESCHUTES | 001/041 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.8866972 | 40.6521 | ETL.7300 | 40890900 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119289947 | Mar | T2NT EI KILARC-DESCHUTES 02/57 INST MRKW | 44406469 | KILARC-DESCHUTES | 002/057 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-30 | 2022-06-30 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.895517 | 40.6444 | ETL.7300 | 40759277 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119289952 | Not Scheduled | EI T2NT KILARC-DESCHUTES 001/041 RMV VE |  | KILARC-DESCHUTES | 001/041 | HNA | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-30 | 2022-06-30 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.886684 | 40.6521 | ETL.7300 | 40867880 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119289956 | Mar | EI T2NT KILARC-DESCHUTES 001/041 RMV BU | 44406470 | KILARC-DESCHUTES | 001/041 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-30 | 2022-06-30 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.886684 | 40.6521 | ETL.7300 | 40867880 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290136 | Q2 | T3 DI WEIMAR #1 012/172 RPR CNDW | 44379167 | WEIMAR #1 | 012/172 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.7560 | 44414817 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290140 | Mar | T2 EI EAGLE ROCK-CORTINA :19/001 RPR POL | 44563312 | EAGLE ROCK-CORTINA | :019/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.610752 | 38.9967 | ETL.1470 | 41176399 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290152 | Q2 | T2NT DI TRNTY-MPLE CRK 35/0 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 035/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-30 | 2022-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.54048 | 40.7176 | ETL.8170 | 44564135 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290260 | Mar | T2 DI FULTON-HOPLAND 12/1 RPLC POLE | 31507646 | FULTON-HOPLAND | 012/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.857787 | 38.6384 | ETL.6890 | 40601384 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290320 | Mar | T2 EI EAGLE ROCK-CORTINA :19/003 RPL HRD | 43730688 | EAGLE ROCK-CORTINA | :019/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.610444 | 38.9988 | ETL.1470 | 41176401 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290353 | Not Scheduled | T3 EI FULTON-CALISTOGA :009/001 RPR GYWW | 44597303 | FULTON-CALISTOGA | :009/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.604302 | 38.7132 | ETL.6880 | 40905738 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290358 | Q2 | T3 EI FULTON-CALISTOGA -012/003 RPL POL | 31507659 | FULTON-CALISTOGA | '-012/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.522566 | 38.4041 | ETL.6880 | 40649308 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290360 | Not Scheduled | T3 EI FULTON-CALISTOGA :009/001 RPL ANCH | 31507893 | FULTON-CALISTOGA | :009/001 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.604302 | 38.7132 | ETL.6880 | 40905738 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290398 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 3/45 RPL HRDW |  | DIVIDE-CABRILLO #2 | 003/045 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.440602 | 34.7805 | ETL.1370 | 40669002 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290417 | Q4 | EI T2NT KESWICK-TRINITY 27/460 RMV PL BU | 43939188 | KESWICK-TRINITY | 027/460 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-01 | 2022-07-01 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.878513 | 40.7032 | ETL.7270 | 40908523 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290418 | Q4 | T2 EI KESWICK-TRINITY 27/460 RPR JUMPER | 43939188 | KESWICK-TRINITY | 027/460 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.878513 | 40.7032 | ETL.7270 | 40908523 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290452 | Mar | T3 EI DRUM-GRASS VALLY-WEIMAR 1/35 RPL S | 31507653 | DRUM-GRASS VALLEY-WEIMAR | 001/035 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.765545 | 39.2452 | ETL.6760 | 40664655 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290466 | Mar | T3 EI MENDOCINO-WILTS-FRT BRG 8/0 RPR PO | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 008/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.29945 | 39.3191 | ETL.7550 | 40614342 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290524 | Q2 | EI BRIDGEVILLE-CTTNWD 1/17 RPR STRW | 44404807 | BRIDGEVILLE-COTTONWOOD | 001/017 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.2987575 | 40.3964 | ETL.1110 | 44424006 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290526 | Q3 | T3 DI DONNELLS-MI-WUK 14/6 RPR INSS | 44623248 | DONNELLS-CURTIS | 014/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.162098 | 38.0842 | ETL.1400 | 44815071 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290538 | Not Scheduled | T3 FULTON-CALISTOGA :008/009 RPR GYWW | 44597303 | FULTON-CALISTOGA | :008/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.604334 | 38.7105 | ETL.6880 | 40905736 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290645 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 3/046 RPL INSW | 31509467 | DIVIDE-CABRILLO #2 | 003/046 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4403698 | 34.779 | ETL.1370 | 40802997 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290646 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 3/046 INST ARMO |  | DIVIDE-CABRILLO #2 | 003/046 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4403698 | 34.779 | ETL.1370 | 40802997 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290661 | Q2 | T3 EI KONOCTI-EAGLE ROCK 5/9 RPR STRW | 44610613 | KONOCTI-EAGLE ROCK | 005/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 |  |  | 2021-05-06 | 2021-05-06 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.78325 | 38.8914 | ETL.6861 | 40861218 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290745 | Not Scheduled | T2 EI DVD-CBRILL #2 3/47 RPL INSUL | 31509467 | DIVIDE-CABRILLO #2 | 003/047 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4401156 | 34.7775 | ETL.1370 | 40786866 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290811 | Not Scheduled | EI T2NT MLN-RND MTN #2 88/449 CANCEL | 44408444 | MALIN-ROUND MTN #2 | 088/449 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.914937 | 40.884 | ETL.6020 | 40868380 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290832 | Mar | T3 EI GEYSERS #3-CLOVERDALE 9/113 RPR ST | 44580896 | GEYSERS #3-CLOVERDALE | 009/113 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.974628 | 38.8007 | ETL.1650 | 44613035 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290874 | Not Scheduled | T2 EI DIVIDE-CBRILL #2 3/48 RPL INSUL | 31509467 | DIVIDE-CABRILLO #2 | 003/048 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4399719 | 34.7767 | ETL.1370 | 40856113 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290875 | Not Scheduled | T2 EI DVD-CABRILLO #2 3/48 INST ARMOR RO | 31509467 | DIVIDE-CABRILLO #2 | 003/048 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 | [6 empty] | Likely MAT error - delink to correct | TR2 |  | South | WSIP | [6 empty] | '-120.439959 | 34.7767 | ETL.1370 | 40828424 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290977 | Q2 | EI T3NT EAGLE EAGOCK-REDBUD :001/011 | 44637023 | EAGLE ROCK-REDBUD | :001/011 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-01 | 2022-07-01 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.783078 | 38.8414 | ETL.1480 | 40585023 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290985 | Not Scheduled | T2 EI DIVIDE-CBRLL #2 3/049 RPL INSUL | 31509467 | DIVIDE-CABRILLO #2 | 003/049 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4397857 | 34.7754 | ETL.1370 | 40840502 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119290986 | Not Scheduled | T2 EI DIVIDE-CBRLL #2 3/49 INST ARMOR RO |  | DIVIDE-CABRILLO #2 | 003/049 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.439773 | 34.7754 | ETL.1370 | 40814797 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291043 | Q2 | T2 EI IGNACIO-BOLINAS #2 14/164 RPL ANCH | 31508167 | IGNACIO-BOLINAS #2 | 014/164 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.727224 | 38.0604 | ETL.7180 | 40577322 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291044 | Q2 | EI T2NT BRDGVLLE-CTTNWD 2/20 RMV PL BUTT | 43939216 | BRIDGEVILLE-COTTONWOOD | 002/020 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-01 | 2022-07-01 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.3047304 | 40.3952 | ETL.1110 | 44423356 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291045 | Q2 | T2 EI BRDGEVLLE-CTTNWD 2/020 RPL HRDWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 002/020 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.3047304 | 40.3952 | ETL.1110 | 44423356 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291061 | Q2 | T2 EI IGNACIO-BOLINAS #2 14/164 REFRAME | 31508167 | IGNACIO-BOLINAS #2 | 014/164 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.727224 | 38.0604 | ETL.7180 | 40577322 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291064 | Q2 | T2 EI BRDGEVLLE-CTTNWD 2/20 RPR STRW | 43939216 | BRIDGEVILLE-COTTONWOOD | 002/020 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.3047304 | 40.3952 | ETL.1110 | 44423356 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291096 | Q2 | T2 EI BRDGEVLLE-CTTNWD 2/20 RPR STRW | 43939216 | BRIDGEVILLE-COTTONWOOD | 002/020 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.3047304 | 40.3952 | ETL.1110 | 44423355 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291137 | Mar | T3 EI DEER CREEK-DRUM 4/113 RPR SRTW | 44379163 | DEER CREEK-DRUM | 004/113 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.792966 | 39.2565 | ETL.6690 | 40767464 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291172 | Q2 | T2 DI HAT CRK #1-WSTWD 4/92 RPR GYWW | 44388736 | HAT CREEK #1-WESTWOOD | 004/092 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.456997 | 40.9146 | ETL.7030 | 40673602 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291261 | Feb | T2NT DI CLGT-GRS VLY 12/304 RMV PL BUTT | 44379160 | COLGATE-GRASS VALLEY | 012/304 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-01 | 2022-07-01 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.068413 | 39.2067 | ETL.6490 | 40823561 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291266 | Feb | T2 DI CLGT-GRS VLY 12/304 RPLC STRW | 31507019 | COLGATE-GRASS VALLEY | 012/304 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-02-27 | 2021-02-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.068413 | 39.2067 | ETL.6490 | 40823561 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291267 | Q2 | EI BRIDGVILLE-COTTONWOOD 2/21 RPRSTR CNC | 44404807 | BRIDGEVILLE-COTTONWOOD | 002/021 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.3067545 | 40.3948 | ETL.1110 | 44423273 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291281 | Q2 | EI BRIDGEVILLE-COTTONWOOD 2/21 RPR CNCL | 31526498 | BRIDGEVILLE-COTTONWOOD | 002/021 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-30 | 2021-03-29 |  |  | CANCEL/CNCL |  |  | North Valley | WSIP | [6 empty] | '-122.3067545 | 40.3948 | ETL.1110 | 44423273 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291282 | Q2 | T2 EI IGNACIO-BOLINAS #2 2/29 RPR CNDW | 44640732 | IGNACIO-BOLINAS #2 | 002/029 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.583532 | 38.0737 | ETL.7180 | 40827656 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291310 | Q2 | EI TRINITY-MAPLE CREEK 45/007 RPL LEFT P | 31509757 | TRINITY-MAPLE CREEK | 045/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.7256181 | 40.7499 | ETL.8170 | 44565531 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291483 | Not Scheduled | T2 EI MALIN-ROUND MTN #2 053/262 CANCEL | 44408444 | MALIN-ROUND MTN #2 | 053/262 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.580964 | 41.2966 | ETL.6020 | 40677654 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291486 | Not Scheduled | EI T2NT MLN-RND MTN #2 088/447 CANCEL | 44408444 | MALIN-ROUND MTN #2 | 088/447 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.916639 | 40.8898 | ETL.6020 | 40821488 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291510 | Not Scheduled | T2 EI DIVIDE-CBRLL #2 4/62 RPL INSUL | 31509468 | DIVIDE-CABRILLO #2 | 004/062 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4377078 | 34.762 | ETL.1370 | 40892024 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291517 | Q4 | EI T2NT KESWICK-TRINITY 27/459 RMV PL BU | 43939188 | KESWICK-TRINITY | 027/459 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-01 | 2022-07-01 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.877108 | 40.7032 | ETL.7270 | 40906111 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291518 | Q4 | T2 EI KESWICK-TRINITY 27/459 RPL CONNW | 44387614 | KESWICK-TRINITY | 027/459 | ICM | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.877108 | 40.7032 | ETL.7270 | 40906111 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119291870 | Not Scheduled | T2NT DI SPAULDING-SMT 4/143 RMV BUTT | 44401161 | SPAULDING-SUMMIT | 004/143 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.579404 | 39.3081 | ETL.8060 | 40751907 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119292226 | Not Scheduled | T2 EI DIVIDE-CBRLL #2 4/63 RPL INSUL | 31509468 | DIVIDE-CABRILLO #2 | 004/063 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4375477 | 34.761 | ETL.1370 | 40889868 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119292237 | Not Scheduled | T2 EI DIVIDE-CBRLL #2 4/63 INST ARMOR RO |  | DIVIDE-CABRILLO #2 | 004/063 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.437535 | 34.761 | ETL.1370 | 40866908 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119292254 | Q2 | EI T3NT UKH-HPLND-CLVRDL 13/1A INST MARK |  | UKIAH-HOPLAND-CLOVERDALE | 013/001A | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-01 | 2022-07-01 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.9953 | 38.8385 | ETL.4050 | 44846556 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119292300 | Not Scheduled | T2 EI DIVIDE-CBRLL #2 4/64 RPL INSUL | 31509468 | DIVIDE-CABRILLO #2 | 004/064 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.43746 | 34.7605 | ETL.1370 | 40618683 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119292301 | Not Scheduled | T2 EI DIVIDE-CBRLL #2 4/64 INST ARMOR RO |  | DIVIDE-CABRILLO #2 | 004/064 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.43746 | 34.7605 | ETL.1370 | 40618683 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119292304 | Q2 | T2 EI BRIDGEVILLE-COTTONWD 2/23R RPL POL | 31526498 | BRIDGEVILLE-COTTONWOOD | 002/023 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.311411 | 40.3938 | ETL.1110 | 44423849 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119292311 | Mar | DI FULTON-HOPLAND 11/0 BOND GUY | 44579280 | FULTON-HOPLAND | 011/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.850505 | 38.6246 | ETL.6890 | 40587777 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119292344 | Q2 | EI TRINITY-MAPLE CREEK_45/7 RPL RIGHT PO | 31509757 | TRINITY-MAPLE CREEK | 045/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.7256181 | 40.7499 | ETL.8170 | 44565546 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119292380 | Q3 | EI MIDWAY-WHIRLWIND 32/130B RMV VEG |  | MIDWAY-WHIRLWIND | 032/130B | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 |  |  | 2021-07-02 | 2021-07-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.020887 | 35.1533 | ETL.6030 | 40740138 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  | 2020-11-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119292465 | Q2 | T2 EI BRIDGEVILLE-COTTONWD 2/23L RPL POL | 31526498 | BRIDGEVILLE-COTTONWOOD | 002/023 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.311411 | 40.3938 | ETL.1110 | 44423848 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119292511 | Q3 | EI MIDWAY-WHIRLWIND 32/130A RMV VEG |  | MIDWAY-WHIRLWIND | 032/130A | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 |  |  | 2021-07-02 | 2021-07-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.020655 | 35.1534 | ETL.6030 | 40575943 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  | 2020-11-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119292594 | Q3 | EI MIDWAY-WHIRLWIND 032/130 RMV VEG |  | MIDWAY-WHIRLWIND | 032/130 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 |  |  | 2021-07-02 | 2021-07-01 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.021312 | 35.1539 | ETL.6030 | 40586513 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  | 2020-11-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119292597 | Q2 | BRIDGEVILLE-COTTONWOOD 0/4 RMV DEBRIS | 44404807 | BRIDGEVILLE-COTTONWOOD | 000/004 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-01 | 2022-07-01 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.272785 | 40.3994 | ETL.1110 | 44424590 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119292599 | Q2 | T2 EI IGNACIO-BOLINAS #2 2/32 RPL INSW | 31510884 | IGNACIO-BOLINAS #2 | 002/032 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.585155 | 38.0762 | ETL.7180 | 40868581 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119292672 | Q2 | T3 EI SAN RAMON-MORAGA 2/12 RPR STRT | 44624389 | SAN RAMON-MORAGA | 002/012 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.966211 | 37.7293 | ETL.5660 | 40805039 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119292677 | Feb | T2 EI PHILO JCT-ELK 36/004 RPL ANCHOR | 31507982 | PHILO JCT-ELK | 036/004 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-02-11 | 2021-02-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.705723 | 39.1382 | ETL.7780 | 40769166 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119292762 | Q2 | T2 EI IGNACIO-BOLINAS #2 14/165 RPL ANCH | 44640732 | IGNACIO-BOLINAS #2 | 014/165 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.728178 | 38.0598 | ETL.7180 | 40649392 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293321 | Not Scheduled | T2NT DI SPLDING-SMMIT 18/578 RMV PL BUT | 44396746 | SPAULDING-SUMMIT | 018/578 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.344207 | 39.3087 | ETL.8060 | 40770690 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293329 | Not Scheduled | T2NT DI SPLDING-SUMMIT 19/611 RMV DEBRIS | 44401161 | SPAULDING-SUMMIT | 019/611 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.329801 | 39.315 | ETL.8060 | 40702036 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293426 | Q2 | T2 EI TRINITY-MAPLE CREEK 46/004 REFRAME | 31507467 | TRINITY-MAPLE CREEK | 046/004 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.733619 | 40.749 | ETL.8170 | 40771328 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293427 | Q2 | T2 EI TRINITY-MAPLE CREEK 46/3 REFRAME | 31507467 | TRINITY-MAPLE CREEK | 046/003 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.732718 | 40.7491 | ETL.8170 | 40649281 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293431 | Q2 | T2 EI TRINITY-MAPLE CREEK 46/2 RPL INSW | 31509755 | TRINITY-MAPLE CREEK | 046/002 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.7314678 | 40.7492 | ETL.8170 | 40735639 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293496 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 7/082 INST ARMO |  | DIVIDE-CABRILLO #2 | 007/082 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436247 | 34.729 | ETL.1370 | 40618689 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293499 | Q2 | EI BRIDGEVILLE-COTTONWOOD 2/25R REPL PL |  | BRIDGEVILLE-COTTONWOOD | 002/025 | 70Y | E | 2020_(1a) PSPS |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.3172912 | 40.3926 | ETL.1110 | 44424010 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119293505 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 7/82 RPL INSW | 31509573 | DIVIDE-CABRILLO #2 | 007/082 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4362592 | 34.729 | ETL.1370 | 40641779 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-02 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293543 | Q4 | T2 EI KESWICK-TRINITY 26/436 REFRAME | 31509681 | KESWICK-TRINITY | 026/436 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.860795 | 40.6953 | ETL.7270 | 40906096 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293545 | Q2 | EI BRIDGEVILLE-COTTONWOOD 2/25L REPL PL |  | BRIDGEVILLE-COTTONWOOD | 002/025 | 70Y | E | 2020_(1a) PSPS |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.3172912 | 40.3926 | ETL.1110 | 44424009 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119293609 | Not Scheduled | T3 EI MRR BY-CALIF FLTS SW STA 8/37 RPR |  | MORRO BAY-GATES #2 | 008/037 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.7496145 | 35.4613 | ETL.5280 | 44358895 | Jumper-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293620 | Not Scheduled | T3 EI MORRO BAY-TEMPLETON 008/037 RPL JM |  | MORRO BAY-TEMPLETON | 008/037 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.7496145 | 35.4613 | ETL.5933 | 44358894 | Jumper-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293623 | Q3 | EI T3NT SN LUIS OBISPO-OCEANO 14/64 RMV |  | SAN LUIS OBISPO-OCEANO | 014/064 | HNA | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-01 | 2022-07-01 |  |  | 2021-08-15 | 2021-08-01 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.502799 | 35.1024 | ETL.3530 | 40751318 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293649 | Not Scheduled | T2 EI DVD-CBRLL #2 6/81 INST ARMOR ROD |  | DIVIDE-CABRILLO #2 | 006/081 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4361968 | 34.7299 | ETL.1370 | 44283613 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293678 | Not Scheduled | T3 EI ATASCADERO-CAYUCOS 1/19 RPR INSW |  | ATASCADERO-CAYUCOS | 001/019 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.700729 | 35.4723 | ETL.8480 | 40868874 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293716 | Not Scheduled | T3 EI FULTON-CALISTOGA :009/007 RPL POLE | 31507659 | FULTON-CALISTOGA | :009/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.606863 | 38.7231 | ETL.6880 | 40905744 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293718 | Mar | T2 EI EAGLE ROCK-CORTINA :20/3 RPR GRNDW | 44563312 | EAGLE ROCK-CORTINA | :020/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.612153 | 39.0118 | ETL.1470 | 41176414 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293755 | Not Scheduled | T2 EI DVD-CBRLL #2 6/81 INST ARMOR ROD |  | DIVIDE-CABRILLO #2 | 006/081 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4361968 | 34.7299 | ETL.1370 | 44283614 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293821 | Q2 | T2 EI IGNACIO-BOLINAS #2 013/159 RPL POL | 31507657 | IGNACIO-BOLINAS #2 | 013/159 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.718793 | 38.0655 | ETL.7180 | 40809520 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293822 | Not Scheduled | T2 EI DVD-CBRLL #2 6/81 INST ARMOR ROD |  | DIVIDE-CABRILLO #2 | 006/081 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.4361968 | 34.7299 | ETL.1370 | 44283615 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293826 | Mar | EI T3NT DEER CREEK-DRUM 3/081 RMV PL BU | 44379163 | DEER CREEK-DRUM | 003/081 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-01 | 2022-07-01 |  |  | 2021-03-16 | 2021-03-08 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.812124 | 39.2623 | ETL.6690 | 40824502 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293908 | Q2 | T3 EI SALT SPRINGS-TIGER CREEK 15/121 | 31502542 | SALT SPRINGS-TIGER CREEK | 015/121 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 |  |  | 2021-04-17 | 2021-04-12 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.483157 | 38.4525 | ETL.3500 | 40604070 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  | Y - 17 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-10-06 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293941 | Q2 | T2 EI PHILO JCT-ELK 3/003 RPL POLE | 31508618 | PHILO JCT-ELK | 003/003 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-06 | 2021-04-06 |  |  | Likely MAT error - delink to correct | TR2 |  | North Coast | WSIP | [6 empty] | '-123.208095 | 39.0902 | ETL.7780 | 40666555 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-16 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293972 | Not Scheduled | T2 DI SPAULDING-SUMMIT 4/146 RPL INSW | 31507463 | SPAULDING-SUMMIT | 004/146 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.57803 | 39.3076 | ETL.8060 | 40902958 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293979 | Not Scheduled | T2NT DI SPLDING-SUMMIT 18/564 RMV PL BUT | 44396746 | SPAULDING-SUMMIT | 018/564 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.351375 | 39.3078 | ETL.8060 | 40602281 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119293985 | Q3 | T2 EI BRIDGEVILLE-GARBERVILLE 20/9 RPL P | 31508614 | BRIDGEVILLE-GARBERVILLE | 020/009 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.761747 | 40.2382 | ETL.6220 | 40875279 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294016 | Mar | T3 EI POTTER VALLEY-WILLITS 9/5 RPL POLE | 31507654 | POTTER VALLEY-WILLITS | 009/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 |  |  | 2021-03-11 | 2021-03-08 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.282175 | 39.3745 | ETL.7820 | 40768613 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-29 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294062 | Q2 | T2 EI FORT ROSS-GUALALA 57/005 RPR GYWW |  | GUALALA-MONTE RIO | 057/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.515879 | 38.7689 | ETL.6980 | 40769855 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294070 | Not Scheduled | EI T3NT CARIBOU-PALERMO 8/063 RMV DEBRIS |  | CARIBOU-PALERMO | :008/063 | ICS | F | 2020_(3) On high spread structure |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.238849 | 40.0064 | ETL.3190 | 40910305 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294085 | Not Scheduled | T3 EI MONTE RIO-FULTON 9/1 RPR POLE |  | MONTE RIO-FULTON | 009/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.923604 | 38.4882 | ETL.7630 | 40584632 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-05 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294133 | Q2 | T3 EI IGNACIO-BOLINAS #2 24/274 REPL INS | 31507790 | IGNACIO-BOLINAS #2 | 024/274 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.716712 | 37.9637 | ETL.7180 | 40668088 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-16 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294146 | Q2 | T2 EI KONOCTI-MIDDLETOWN 23/007 RPL PL | 31509670 | KONOCTI-MIDDLETOWN | 023/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.720101 | 38.9241 | ETL.6380 | 40824735 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294221 | Q3 | T3 BRIDGEVILLE-CTTNWD 85/601 MOVE OPGW | 43939216 | BRIDGEVILLE-COTTONWOOD | 085/601 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 |  |  | 2021-07-17 | 2021-06-21 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.776952 | 40.4819 | ETL.1110 | 44424584 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294411 | Q2 | T2 HAT CREEK #1-WESTWOOD 7/146 REFRAME |  | HAT CREEK #1-WESTWOOD | 007/146 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.420735 | 40.8844 | ETL.7030 | 40876177 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294503 | Q2 | EI HUMBOLDT-TRINITY 103/004 RPR COND | 44299237 | HUMBOLDT-TRINITY | 103/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-06-12 | 2021-05-24 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.9269386 | 40.7657 | ETL.1820 | 44562973 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294505 | Mar | HUMBOLDT-TRINITY 102/003 RPL INSW | 31509856 | HUMBOLDT-TRINITY | 102/003 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-03 | 2021-03-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.915197 | 40.7614 | ETL.1820 | 40699978 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294573 | Not Scheduled | T3 EI SN LS OBISPO-OCEANO 13/62 RPL INSL | 31527004 | SAN LUIS OBISPO-OCEANO | 013/062 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.5010879 | 35.1092 | ETL.3530 | 40711702 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294574 | Not Scheduled | T3 EI SN LS OBSPO-SNTA MRIA 13/62 RPL IN | 31510359 | SAN LUIS OBISPO-SANTA MARIA | 013/062 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.5010879 | 35.1092 | ETL.3540 | 40711700 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 6 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294698 | Not Scheduled | T3 EI ATASCADERO-CAYUCOS 6/52 REFRAME | 31508008 | ATASCADERO-CAYUCOS | 006/052 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.773512 | 35.4619 | ETL.8480 | 40595376 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294699 | Not Scheduled | T3 EI ATASCADERO-CYCS 5/43 INST JUMPR IN |  | ATASCADERO-CAYUCOS | 005/043 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.755688 | 35.4631 | ETL.8480 | 40606006 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294710 | Not Scheduled | T3 EI ATASCADERO-CYCS 4/41 INST JUMPR IN |  | ATASCADERO-CAYUCOS | 004/041 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.748317 | 35.4638 | ETL.8480 | 40764380 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294711 | Not Scheduled | T3 EI ATASCADERO-CAYUCOS 5/47 RPR GYWW |  | ATASCADERO-CAYUCOS | 005/047 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.761226 | 35.4628 | ETL.8480 | 40760577 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294721 | Not Scheduled | T3 EI ATASCADERO-CAYUCOS 4/40 RPR JUMPER |  | ATASCADERO-CAYUCOS | 004/040 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.746562 | 35.464 | ETL.8480 | 40763138 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294738 | Not Scheduled | T3 EI SN LS OBSPO-SNTA MRIA 13/61 RPL IN | 31510359 | SAN LUIS OBISPO-SANTA MARIA | 013/061 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.5012007 | 35.1112 | ETL.3540 | 40610001 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 6 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294990 | Not Scheduled | T2NT DI SPLDING-SUMMIT 15/576 RMV PL BUT | 44396746 | SPAULDING-SUMMIT | 018/576 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.345748 | 39.3084 | ETL.8060 | 40658646 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119294995 | Not Scheduled | T3 EI SN LS OBSPO-SNTA MRIA 13/60 RPL IN | 31510359 | SAN LUIS OBISPO-SANTA MARIA | 013/060 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.5013359 | 35.1135 | ETL.3540 | 40631107 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 6 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-09-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295058 | Mar | T2 EI EAGLE ROCK-CORTINA :18/009 REPLUMB | 44563312 | EAGLE ROCK-CORTINA | :018/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.611914 | 38.9886 | ETL.1470 | 41176392 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295154 | Not Scheduled | EI T3NT SN LS OBSPO-OCEANO 13/58 INS MRK |  | SAN LUIS OBISPO-OCEANO | 013/058 | ICS | F | 2020_(3) On high spread structure |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR3 |  | South | WSIP | [6 empty] | '-120.503912 | 35.1191 | ETL.3530 | 40873231 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295159 | Not Scheduled | EI T2NT MLN-RND MTN #2 077/393 CANCEL | 44408444 | MALIN-ROUND MTN #2 | 077/393 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.886389 | 41.0394 | ETL.6020 | 40657492 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295183 | Q2 | HAT CREEK #1-WESTWOOD 50/966 REFRAME | 31506709 | HAT CREEK #1-WESTWOOD | 050/966 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.014415 | 40.3737 | ETL.7030 | 40667991 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295200 | Not Scheduled | T2 DI SPAULDING-SUMMIT 19/604 RPL INSW | 31507463 | SPAULDING-SUMMIT | 019/604 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.33139 | 39.3122 | ETL.8060 | 40780179 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295303 | Mar | COTTONWOOD-HUMBOLDT 102/000 RPL INSS | 31509856 | HUMBOLDT-TRINITY | 063/004 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-27 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.22427 | 40.7401 | ETL.1820 | 40788606 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295334 | Q2 | T2 EI TRINITY-MAPLE CREEK 45/6R RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 045/006 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2020-08-31 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.7185615 | 40.7501 | ETL.8170 | 44565320 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295337 | Not Scheduled | T2 EI LAKEVILLE #2 13/277 PRP GYWW |  | LAKEVILLE #2 | 013/277 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.712252 | 38.2992 | ETL.7340 | 40864183 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-20 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295340 | Q2 | T2 EI TRINITY-MAPLE CREEK 45/6L RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 045/006 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.7185615 | 40.7501 | ETL.8170 | 44565516 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295341 | Q2 | T2 EI TRINITY-MAPLE CREEK 45/6C RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 045/006 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.7185615 | 40.7501 | ETL.8170 | 44565322 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295345 | Q2 | T2 TRINITY-MAPLE CREEK 17/3 REPLACE POLE | 31507467 | TRINITY-MAPLE CREEK | 017/003 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.210967 | 40.7419 | ETL.8170 | 40662724 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295346 | Q2 | T2 EI TRINITY-MAPLE CREEK 45/4 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 045/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.7164867 | 40.7502 | ETL.8170 | 44565626 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295372 | Mar | T2 EI KILARC-DESCHUTES 7/146 RMV DEBRIS | 44406470 | KILARC-DESCHUTES | 007/146 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-01 | 2022-07-01 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.962545 | 40.608 | ETL.7300 | 40701866 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295402 | Mar | T3 EI DRUM-GRASS VALLEY-WEIMR 2/54 RPL P | 31507653 | DRUM-GRASS VALLEY-WEIMAR | 002/054 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.775766 | 39.2364 | ETL.6760 | 40611206 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295408 | Feb | T3 EGLE RCK-FLTN-SILVERAD 6/23 RPR INSS |  | EAGLE ROCK-FULTON-SILVERADO | 006/023 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.757907 | 38.6543 | ETL.4392 | 41129326 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295471 | Mar | T3 EI DRUM-GRASS VALLEY-WEIMAR 1/33 RPL | 31507653 | DRUM-GRASS VALLEY-WEIMAR | 001/033 | 70Y | E | 2020_(1a) PSPS |  | 2020-07-01 | 2021-01-01 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.764562 | 39.2461 | ETL.6760 | 40598576 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119295483 | Q2 | T2 EI BRIDGEVILLE-CTTNWD 3/30B RMV HRDWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 003/030B | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.326995 | 40.3906 | ETL.1110 | 44894794 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295489 | Not Scheduled | T2NT DI SPLDING-SUMMIT 17/561 RMV PL BUT | 44396746 | SPAULDING-SUMMIT | 017/561 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.352615 | 39.3083 | ETL.8060 | 40770704 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295511 | Q2 | T3 EI UKH-HPLND-CLVRDL 12/6 RPR GYWW | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 012/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.992779 | 38.8329 | ETL.4050 | 40808990 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295550 | Q2 | T2 EI BRIDGEVILLE-CTTNWD 3/30C INST HRDW | 43939216 | BRIDGEVILLE-COTTONWOOD | 003/030C | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.326991 | 40.3906 | ETL.1110 | 44891804 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295611 | Q3 | T2 CARIBOU-PLUMAS 007/010 JCT RMV PL BUT | 44408852 | CARIBOU-PLUMAS JCT | 007/010 | ICW | E | 2020_(3) On high spread structure |  | 2020-07-01 | 2021-07-01 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.061766 | 40.0106 | ETL.6290 | 40589808 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295612 | Q3 | T2 CARIBOU-PLUMAS 007/010 JCT RPR STRW | 44408852 | CARIBOU-PLUMAS JCT | 007/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.061766 | 40.0106 | ETL.6290 | 40589808 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295614 | Not Scheduled | T2NT DI SPLDING-SUMMIT 4/154 RMV DEBRIS | 44401161 | SPAULDING-SUMMIT | 004/154 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.574175 | 39.3068 | ETL.8060 | 40810157 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295615 | Not Scheduled | T2 DI SPAULDING-SUMMIT 004/154 RPL INSW | 31507463 | SPAULDING-SUMMIT | 004/154 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.574203 | 39.3069 | ETL.8060 | 40836948 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295636 | Q2 | T3 EI UKH-HPLND-CLOVERDALE 11/10 RPR GY | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 011/010 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.993299 | 38.8212 | ETL.4050 | 40587979 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295638 | Not Scheduled | T3 EI FULTON-CALISTOGA :008/007 RPL HRDW | 44597303 | FULTON-CALISTOGA | :008/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.604341 | 38.7085 | ETL.6880 | 40905734 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295657 | Q2 | T3 DI DRUM-HIGGINS 1/13 RPL STRW | 31509929 | DRUM-HIGGINS | 001/013 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.770864 | 39.2402 | ETL.4393 | 44172218 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-22 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295662 | Mar | EI HMBLDT-TRINITY 105/1C RPL POLE |  | HUMBOLDT-TRINITY | 105/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-27 | 2021-03-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.9531809 | 40.7657 | ETL.1820 | 44557581 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295712 | Mar | DI FULTON-HOPLAND 010/009 RPL INSW | 31528322 | FULTON-HOPLAND | 010/009 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.848496 | 38.6234 | ETL.6890 | 40882613 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295713 | Mar | DI FULTON-HOPLAND 010/009 RPR GYWW | 44579280 | FULTON-HOPLAND | 010/009 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.848787 | 38.6236 | ETL.6890 | 40860939 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295715 | Mar | DI FULTON-HOPLAND 010/007 RPR GYWW | 44579280 | FULTON-HOPLAND | 010/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.847007 | 38.6211 | ETL.6890 | 40808468 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295718 | Q3 | T2 DI CARIBOU-WESTWOOD 11/216 RPR HRDD |  | CARIBOU-WESTWOOD | 011/216 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.068875 | 40.2169 | ETL.6300 | 40751806 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295719 | Q3 | T2 DI CARIBOU-WESTWOOD 11/216 RPR GYWW |  | CARIBOU-WESTWOOD | 011/216 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.068875 | 40.2169 | ETL.6300 | 40751806 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295733 | Not Scheduled | T3NT DI DRUM-SUMMIT #2 3/44 RMV DEBRIS | 44379081 | DRUM-SUMMIT #2 | 003/044 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.717133 | 39.2839 | ETL.1450 | 44549458 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295734 | Q2 | T2 EI IGNACIO-BOLINAS #2 013/158 RPR ANC | 44640732 | IGNACIO-BOLINAS #2 | 013/158 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.7173767 | 38.0668 | ETL.7180 | 44360898 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295738 | Mar | T2 EI KILARC-DESCHUTES 3/68 RMV DEBRI | 44406470 | KILARC-DESCHUTES | 003/068 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-01 | 2022-07-01 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.903162 | 40.6382 | ETL.7300 | 40770452 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295739 | Mar | T2 EI KILARC-DESCHUTES 3/071 RPL PL | 31509538 | KILARC-DESCHUTES | 003/071 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.905101 | 40.6366 | ETL.7300 | 40868557 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295750 | Mar | T2 EI KILARC-DESCHUTES 4/83 RPL POLE | 31509538 | KILARC-DESCHUTES | 004/083 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.913709 | 40.6307 | ETL.7300 | 40600368 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295751 | Mar | T2 EI KILARC-DESCHUTES 3/68 REFRAME | 31507189 | KILARC-DESCHUTES | 003/068 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.903162 | 40.6382 | ETL.7300 | 40770452 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295755 | Mar | T2 EI KILARC-DESCHUTES 3/072 RPR PL | 44406470 | KILARC-DESCHUTES | 003/072 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.905866 | 40.636 | ETL.7300 | 40862155 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295766 | Feb | T3 DI MORAGA-OAKLAND #1 1/10 RPR STRT |  | MORAGA-OAKLAND #1 | 001/010 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.187276 | 37.8382 | ETL.2720 | 40581554 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 14 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-03 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295775 | Not Scheduled | EI T2NT HAT CREEK #1-WESTWOOD 0/3 RMV VE |  | HAT CREEK #1-WESTWOOD | 000/003 | HNA | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-30 | 2022-06-30 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.543478 | 40.9286 | ETL.7030 | 40701311 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295800 | Feb | T3NT DI MORAGA-OKLND #1 1/10 INST ACG |  | MORAGA-OAKLAND #1 | 001/010 | 93A | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-30 | 2022-06-30 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.187276 | 37.8382 | ETL.2720 | 40581554 | Structure-Tower | Anti-Climbing Guard | Install |  |  |  |  | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - 14 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-02-03 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295806 | Q2 | T3 DI DRUM-HIGGINS 3/36 RPR STRW | 44378765 | DRUM-HIGGINS | 003/036 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.807961 | 39.2199 | ETL.4393 | 44172266 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295834 | Q3 | T2 DI CARIBOU-PLUMAS JCT 7/7 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 007/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.062997 | 40.0123 | ETL.6290 | 40824651 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295839 | Mar | T2 DI DRUM-SUMMIT #1 26/310 BENT STEEL | 44394773 | DRUM-SUMMIT #1 | 026/310 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.337943 | 39.3104 | ETL.1440 | 44768872 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295845 | Q4 | T3 DI MIDDLE FRK-GLD HL 0/3 RPLC STRW | 31510070 | MIDDLE FORK-GOLD HILL | 000/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.597748 | 39.0217 | ETL.5140 | 44552478 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-10-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295852 | Q2 | T2 DI TRINITY-MAPLE CREEK 33/3 RPR INSW | 44273074 | TRINITY-MAPLE CREEK | 033/003 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.514362 | 40.7047 | ETL.8170 | 40700024 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295853 | Q2 | T2NT DI TRINITY-MAPLE CRK 33/3 RMV BUTT | 44299848 | TRINITY-MAPLE CREEK | 033/003 | ICW | F | 2020_(3) On high spread structure |  | 2020-06-30 | 2022-06-30 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420680 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295855 | Not Scheduled | T3 DI DRUM-SUMMIT #2 0/10 RPR STRW | 44378680 | DRUM-SUMMIT #2 | 000/010 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-30 | 2020-12-30 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.752078 | 39.254 | ETL.1450 | 44549887 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295877 | Not Scheduled | T3 DI DRUM-HIGGINS 0/8 CANCEL | 44378765 | DRUM-HIGGINS | 000/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.764879 | 39.2468 | ETL.4393 | 44172276 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295878 | Not Scheduled | T3 DI DRUM-HIGGINS 0/8 CANCEL | 44378765 | DRUM-HIGGINS | 000/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.764879 | 39.2468 | ETL.4393 | 44172277 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295916 | Mar | DI KILARC-DESCHUTES 18/374 RPR INSU | 44406469 | KILARC-DESCHUTES | 018/374 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-26 | 2021-03-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.151742 | 40.5637 | ETL.7300 | 44327689 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295933 | Q2 | T2 DI TRINTY-MAPLE CREEK 35/4 RMV PL BUT | 44299848 | TRINITY-MAPLE CREEK | 035/004 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.549178 | 40.7211 | ETL.8170 | 44565620 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295937 | Q2 | T2 DI TRINTY-MAPLE CREEK 35/4R RPL STRW | 31509757 | TRINITY-MAPLE CREEK | 035/004 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.549178 | 40.7211 | ETL.8170 | 44565473 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295940 | Not Scheduled | T2DI SPLDNG-SUMMIT 18/595 RMV POLE BUTT | 44401161 | SPAULDING-SUMMIT | 018/595 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.336371 | 39.3107 | ETL.8060 | 40702890 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119295991 | Not Scheduled | T3NT DI DRUM-SUMMIT #2 3/41 RMV DEBRIS | 44379081 | DRUM-SUMMIT #2 | 003/041 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.721852 | 39.2822 | ETL.1450 | 44552274 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119296017 | Not Scheduled | T2 DI COTTONWOOD #1 10/67 INST ACG | 44406038 | COTTONWOOD #1 | 010/067 | ICQ | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.267342 | 40.2488 | ETL.6620 | 40906003 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119296065 | Mar | DI FULTON-HOPLAND 10/8 RPR GYWW | 44579280 | FULTON-HOPLAND | 010/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.847908 | 38.6227 | ETL.6890 | 40877294 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119296066 | Mar | DI FULTON-HOPLAND 11/11 RPR GYWW | 44579280 | FULTON-HOPLAND | 011/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.858477 | 38.6356 | ETL.6890 | 40598444 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119296067 | Mar | DI FULTON-HOPLAND 12/6 RPR GYWW | 44579280 | FULTON-HOPLAND | 012/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.85544 | 38.6478 | ETL.6890 | 40808866 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119296081 | Mar | DI KILARC-DESCHUTES 018/376 RPL STRW | 31507070 | KILARC-DESCHUTES | 018/376 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-26 | 2021-03-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.153574 | 40.5637 | ETL.7300 | 40816240 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119296179 | Q2 | T3 DI DRUM-HIGGINS 000/11 RPL STRW | 31509929 | DRUM-HIGGINS | 000/011 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.767471 | 39.2432 | ETL.4393 | 44172234 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-22 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119296280 | Q2 | T2 DI TRNTY-MPLE CRK 37/7 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 037/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.583908 | 40.7147 | ETL.8170 | 44820903 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119296311 | Mar | DI FULTON-HOPLAND 11/1 RPR GYWW | 44579280 | FULTON-HOPLAND | 011/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-29 | 2021-06-29 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.851502 | 38.6252 | ETL.6890 | 40601385 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119296313 | Mar | DI FULTON-HOPLAND 11/1 INST GUY MRKW | 44579280 | FULTON-HOPLAND | 011/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-29 | 2022-06-29 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.851502 | 38.6252 | ETL.6890 | 40601385 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119296370 | Not Scheduled | T2 DI SPAULDING-SUMMIT 18/598 RMV PL BUT | 44401161 | SPAULDING-SUMMIT | 018/598 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.334774 | 39.3111 | ETL.8060 | 40770706 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119299191 | Q2 | T2 EI BRDGVLLE-CTTNWD 8/80 INST SPLIT BO | 44404807 | BRIDGEVILLE-COTTONWOOD | 008/080 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.42868 | 40.3891 | ETL.1110 | 44424454 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119299456 | Not Scheduled | T2 DI DRUM-SUMMIT #2 027/324 RPL INSW | 31508042 | DRUM-SUMMIT #2 | 027/324 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.335204 | 39.3114 | ETL.1450 | 40690175 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119299562 | Not Scheduled | T3 EI SAN LUIS OBISPO-OCEANO 14/64 RPR R | 44378910 | SAN LUIS OBISPO-OCEANO | 014/064 | CHS | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-01 | 2021-01-01 |  |  |  | 2021-01-04 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.502799 | 35.1024 | ETL.3530 | 40751318 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119299567 | Q4 | T2 EI KESWICK-TRINITY 19/284 RPR GYWW | 44406439 | KESWICK-TRINITY | 019/284 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.746688 | 40.7167 | ETL.7270 | 40815299 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119299568 | Q4 | T2 EI KESWICK-TRINITY 19/283 REFRAME | 31509681 | KESWICK-TRINITY | 019/283 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.745358 | 40.7169 | ETL.7270 | 40827895 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119299715 | Q4 | T2 EI KESWICK-TRINITY 20/292 RPR GYWW | 44406439 | KESWICK-TRINITY | 020/292 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.753358 | 40.7162 | ETL.7270 | 44649389 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119299716 | Q4 | T2 EI KESWICK-TRINITY 20/290 RPR GYWW | 44406439 | KESWICK-TRINITY | 020/290 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.752348 | 40.7163 | ETL.7270 | 44649299 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300100 | Q3 | T3NT DI DONNELLS-MI-WUK 0/1 RMV PL BUTT | 44623249 | DONNELLS-CURTIS | 000/001 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-01 | 2022-07-01 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.034255 | 38.2458 | ETL.1400 | 44379627 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-07 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300106 | Not Scheduled | EI SAN LUIS OBISPO-CAYUCOS 6/44 RPL INSW | 31509937 | SAN LUIS OBISPO-CAYUCOS | 006/044 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.670264 | 35.3148 | ETL.9090 | 40784313 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300228 | Mar | T2 EI KILARC-DESCHUTES 3/81 RPL HRDW | 44406470 | KILARC-DESCHUTES | 003/081 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.912104 | 40.6316 | ETL.7300 | 40877962 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300235 | Not Scheduled | T2 DI DRUM-SUMMIT #1 26/311 RPR STRW |  | DRUM-SUMMIT #1 | 026/311 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.334944 | 39.3112 | ETL.1440 | 44768903 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300248 | Mar | T2 EI KILARC-DESCHUTES 3/077 RPL PL | 31509538 | KILARC-DESCHUTES | 003/077 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.90915 | 40.6334 | ETL.7300 | 40771364 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300261 | Mar | T2 EI KILARC-DESCHUTES 3/82 RPL POLE | 31509538 | KILARC-DESCHUTES | 003/082 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.912913 | 40.6311 | ETL.7300 | 40876560 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300301 | Not Scheduled | T2 DI SPAULDING-SUMMIT 17/556 RPL POLE |  | SPAULDING-SUMMIT | 017/556 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.355024 | 39.309 | ETL.8060 | 40618241 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300303 | Not Scheduled | T2 DI SPLDING-SUMMIT 18/570 RMV PL BUTT | 44396747 | SPAULDING-SUMMIT | 018/570 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.348357 | 39.308 | ETL.8060 | 40809679 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300304 | Not Scheduled | T2 DI SPLDING-SUMMIT 18/570 RPR INSW | 44396745 | SPAULDING-SUMMIT | 018/570 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.348357 | 39.308 | ETL.8060 | 40834381 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300305 | Not Scheduled | T2NT DI SPLDING-SUMMIT 18/574 RMV PL BUT | 44396746 | SPAULDING-SUMMIT | 018/574 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.346514 | 39.3083 | ETL.8060 | 40593596 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300307 | Not Scheduled | T2NT DI SPLDING-SMMIT 18/575 RMV PL BUTT | 44396746 | SPAULDING-SUMMIT | 018/575 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.346228 | 39.3083 | ETL.8060 | 40702032 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300334 | Q2 | T2 EI BRIDGEVILLE-COTTONWOOD 5/46 RPR GY | 44404807 | BRIDGEVILLE-COTTONWOOD | 005/046 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.3596654 | 40.3909 | ETL.1110 | 44899402 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300335 | Q2 | T2 EI BRIDGEVILLE-COTTNWD 5/46 FILL HOLE | 44404807 | BRIDGEVILLE-COTTONWOOD | 005/046 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.3596654 | 40.3909 | ETL.1110 | 44899402 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300454 | Mar | DI FULTON-HOPLAND 11/5 RPR GYWW | 44579280 | FULTON-HOPLAND | 011/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 |  |  | 2021-03-12 | 2021-03-08 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.855492 | 38.6279 | ETL.6890 | 40766460 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300606 | Mar | T3 EI DRUM-GRASS VALLEY-WMR 2/58 RPR SPL | 44379639 | DRUM-GRASS VALLEY-WEIMAR | 002/058 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.779099 | 39.2351 | ETL.6760 | 40767233 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300609 | Mar | T2 DI BELDEN TAP 0/1C RPR STRT | 44382654 | BELDEN TAP | 000/001C | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 | 2021-03-24 | 2021-03-25 | 2021-03-25 | 2021-03-24 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.250771 | 40.0077 | ETL.4441 | 43198034 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300648 | Q3 | T2 EI BRIDGEVILLE-GARBERVILLE 19/8 RPL P | 31508615 | BRIDGEVILLE-GARBERVILLE | 019/008 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.765537 | 40.2503 | ETL.6220 | 40876478 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300659 | Q3 | T2 EI BRDGVILLE-GRBRVILLE 19/8 REPL POLE | 31511889 | BRIDGEVILLE-GARBERVILLE | 019/008 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.765537 | 40.2503 | ETL.6220 | 40876478 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300665 | Mar | T2 DI BELDEN TAP 0/1A RPR CONS | 43742043 | BELDEN TAP | 000/001A | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-03-24 | 2021-03-24 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.250817 | 40.0077 | ETL.4441 | 43198032 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300682 | Q2 | T2 EI TRINITY-MAPLE CREEK 40/3 RPL INSW | 31512233 | TRINITY-MAPLE CREEK | 040/003 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.632547 | 40.721 | ETL.8170 | 40649273 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300727 | Q3 | T2 EI BRIDGEVILLE-GARBERVILLE 19/9 REFRA | 31511889 | BRIDGEVILLE-GARBERVILLE | 019/009 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-08-28 | 2021-08-23 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.765252 | 40.2486 | ETL.6220 | 40862532 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300752 | Not Scheduled | EI T2NT MALIN-RND MTN #2 87/440 CANCEL | 44408444 | MALIN-ROUND MTN #2 | 087/440 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.918496 | 40.9088 | ETL.6020 | 40601196 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300824 | Not Scheduled | T2 DI SPLDING-SUMMIT 1/46 RPL STRW |  | SPAULDING-SUMMIT | 001/046 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.625048 | 39.3188 | ETL.8060 | 40861937 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300868 | Not Scheduled | T2 CRESTA-RIO OSO_027/224 RPR STRT |  | CRESTA-RIO OSO | 027/224 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.529846 | 39.5751 | ETL.4590 | 41083086 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300875 | Not Scheduled | T2 DI SPAULDING-SUMMIT 019/601 RPR STRW | 44401099 | SPAULDING-SUMMIT | 019/601 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2021-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.333292 | 39.3115 | ETL.8060 | 40660186 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119300978 | Not Scheduled | T3 DI DRUM-SUMMIT #2 3/42 RPR STRW | 44378680 | DRUM-SUMMIT #2 | 003/042 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.719926 | 39.2829 | ETL.1450 | 44549917 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301261 | Not Scheduled | T2NT DI SPLDNG-SMMIT 18/583 RMV PL BUTT | 44396746 | SPAULDING-SUMMIT | 018/583 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.341826 | 39.3093 | ETL.8060 | 40603063 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301264 | Not Scheduled | T2 DI SPLDING-SUMMIT 18/596 RMV PL BUTT | 44401161 | SPAULDING-SUMMIT | 018/596 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-29 | 2022-06-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.335743 | 39.3109 | ETL.8060 | 40668697 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301305 | Q3 | EI BRDGVILE-CTTNWD 9/085 RPR WDPKR | 44404807 | BRIDGEVILLE-COTTONWOOD | 009/085 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-08-06 | 2021-07-19 |  |  |  |  | SCHD | North Valley | WSIP | [6 empty] | '-122.4397959 | 40.3891 | ETL.1110 | 44423892 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301306 | Q2 | EI BRDGVILE-CTTNWD 9/085 INST ANTI-SPLIT | 44404807 | BRIDGEVILLE-COTTONWOOD | 009/085 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.4397959 | 40.3891 | ETL.1110 | 44423891 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301307 | Q2 | EI BRIDGVILE-CTNWD 9/084 RMV PL BUTT | 44404807 | BRIDGEVILLE-COTTONWOOD | 009/084 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-02 | 2022-07-02 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.437703 | 40.3891 | ETL.1110 | 44423220 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301323 | Mar | T2 EI KILARC-DESCHUTES A025/537 RPR POLE | 43930440 | KILARC-DESCHUTES | A025/537 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.291353 | 40.5711 | ETL.7300 | 41118630 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301642 | Q2 | T3 EI EAGLE ROCK-REDBUD:8/048 RPR FOND | 44637023 | EAGLE ROCK-REDBUD | :008/048 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.685011 | 38.8871 | ETL.1480 | 40861251 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301714 | Not Scheduled | EI T3NT ATASCADERO-CAYUCOS 2/27 RPR JUMP |  | ATASCADERO-CAYUCOS | 002/027 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-01-02 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.717997 | 35.4647 | ETL.8480 | 40870078 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301754 | Mar | T2 EI EAGLE ROCK-CORTINA 17/015 RPR REPL | 44563312 | EAGLE ROCK-CORTINA | :017/015 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.612473 | 38.9783 | ETL.1470 | 41176379 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301787 | Not Scheduled | T2 PHILO JCT-ELK 3/4 RPR ROAD | 44432524 | PHILO JCT-ELK | 003/004 | CHS | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-02 | 2021-07-02 |  |  |  | 2021-06-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.208877 | 39.0881 | ETL.7780 | 40763007 | Road | Grade Change | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301795 | Not Scheduled | T3NT DI DRUM-SUMMIT #2 5/63L INS MRKW | 44379081 | DRUM-SUMMIT #2 | 005/063 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-30 | 2022-06-30 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.69685 | 39.2985 | ETL.1450 | 44549961 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301798 | Not Scheduled | T3NT DI DRUM-SUMMIT #2 5/63R INS MRKW | 44379081 | DRUM-SUMMIT #2 | 005/063 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-06-30 | 2022-06-30 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.69685 | 39.2985 | ETL.1450 | 44550030 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301843 | Q2 | T3 EI FULTON-CALISTOGA -013/004 RPR ANCH |  | FULTON-CALISTOGA | '-013/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-01-02 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.515425 | 38.4197 | ETL.6880 | 40751147 | Anchor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301862 | Q3 | T2 DI CARIBOU-PLUMAS JCT 1/8A RPR STRW | 44408852 | CARIBOU-PLUMAS JCT | 001/008A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.121585 | 40.0765 | ETL.6290 | 40862071 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301916 | Q2 | T3NT DI DRUM-HIGGINS 0/2 RMV PL BUTT | 44378765 | DRUM-HIGGINS | 000/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-30 | 2022-06-30 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 |  | North Valley | WSIP | [8 empty] | ETL.4393 | 44199668 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301955 | Q2 | T3 EI IGNACIO-BOLINAS #1 8/85 RPL STRW | 31508083 | IGNACIO-BOLINAS #1 | 008/085 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.654107 | 38.0121 | ETL.7140 | 40860973 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119301990 | Q2 | T3 EI IGNACIO-BOLINAS #1 008/086 RPR ANC | 44640733 | IGNACIO-BOLINAS #1 | 008/086 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.653864 | 38.0118 | ETL.7140 | 40588050 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302036 | Q2 | T2 EI BRDGEVLLE-CTTNWD 16/147 RMV PL BUT | 43939216 | BRIDGEVILLE-COTTONWOOD | 016/147 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [8 empty] | ETL.1110 | 44423954 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302135 | Q2 | T2 EI BRIDGEVILLE-COTTONWOOD 9/89 RPL HR | 44404807 | BRIDGEVILLE-COTTONWOOD | 009/089 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4484962 | 40.3891 | ETL.1110 | 44424401 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302136 | Q2 | T2 EI BRIDGEVILLE-COTTONWOOD 9/89 RPR WD | 44404807 | BRIDGEVILLE-COTTONWOOD | 009/089 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4484962 | 40.3891 | ETL.1110 | 44424401 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302163 | Q2 | T2 EI IGNACIO-BOLINAS #2 14/166 RPL POLE | 31507657 | IGNACIO-BOLINAS #2 | 014/166 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.729518 | 38.0589 | ETL.7180 | 40770923 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302175 | Not Scheduled | T2 EI IGNACIO-BOLNAS #2 14/166 ANCH CNCL | 31508167 | IGNACIO-BOLINAS #2 | 014/166 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 | [6 empty] | CANCEL/CNCL | TR2 |  | North Coast | WSIP | [6 empty] | '-122.729518 | 38.0589 | ETL.7180 | 40770923 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302178 | Q2 | T2NT TRINITY-MAPLE CREEK 50/8 RMV BUTT | 44401994 | TRINITY-MAPLE CREEK | 050/008 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-02 | 2022-07-02 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.812309 | 40.7617 | ETL.8170 | 40861547 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302215 | Not Scheduled | T2 PHILO JCT-ELK 3/006 RPR ROAD | 44432524 | PHILO JCT-ELK | 003/006 | CHS | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-02 | 2021-07-02 |  |  |  | 2021-06-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.209832 | 39.086 | ETL.7780 | 40820699 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302234 | Q2 | T3 DI SLY CREEK TAP 1/9 RPR STRW | 44391954 | SLY CREEK TAP | 001/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 |  |  | 2021-04-15 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.135825 | 39.5704 | ETL.4221 | 44558988 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302370 | Mar | T3 EI DRUM-GRSS VALLEY-WMAR 3/71 RPL STR | 31507653 | DRUM-GRASS VALLEY-WEIMAR | 003/071 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.788684 | 39.2315 | ETL.6760 | 40756220 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302386 | Q2 | T3 EI FULTON-CALISTOGA -013/005 RPL ANCH | 31507893 | FULTON-CALISTOGA | '-013/005 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-01-02 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.514113 | 38.4215 | ETL.6880 | 40751131 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302423 | Mar | T3 EI DRUM-GRSS VLLY-WMR 3/72 RPL STRW | 31507653 | DRUM-GRASS VALLEY-WEIMAR | 003/072 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.789268 | 39.2312 | ETL.6760 | 40766648 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302429 | Not Scheduled | EI T2NT KILRC-DSCHTS 8/167 RPR REGRADE |  | KILARC-DESCHUTES | 008/167 | ICW | F | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.976999 | 40.5982 | ETL.7300 | 44896011 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302473 | Q2 | T3 DI DRUM-HIGGINS 0/12 RPL STRW | 31509929 | DRUM-HIGGINS | 000/012 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.769053 | 39.2419 | ETL.4393 | 44172202 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-22 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302482 | Not Scheduled | EI DRUM-SUMMIT #1 003/046 RPL PL | 31508705 | DRUM-SUMMIT #1 | 003/046 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.7170282 | 39.2837 | ETL.1440 | 44765656 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119302493 | Q2 | T2NT DI TRINITY-MAPLE CRK 33/4 RMV BUTT | 44401994 | TRINITY-MAPLE CREEK | 033/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-01 | 2022-07-01 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.518887 | 40.7069 | ETL.8170 | 44771073 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302513 | Not Scheduled | T3 EI FULTON-CALISTOGA :8/2 RPL POLE | 31507659 | FULTON-CALISTOGA | :008/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-01-02 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.600416 | 38.7031 | ETL.6880 | 40905729 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302519 | Mar | T3 EI DRUM-GRASS VALLEY-WEIMAR 0/23 RPL | 31507653 | DRUM-GRASS VALLEY-WEIMAR | 000/023 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.757064 | 39.2491 | ETL.6760 | 42549841 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302565 | Not Scheduled | EI DRUM-SUMMIT #1 003/046 RPL POLE | 31508705 | DRUM-SUMMIT #1 | 003/046 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.7170282 | 39.2837 | ETL.1440 | 44765657 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302759 | Q2 | T2 DI TRINITY-MAPLE CRK 33/4 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 033/004 | ICW | E | 2020_(3) On high spread structure |  | 2020-07-01 | 2021-07-01 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.518887 | 40.7069 | ETL.8170 | 44771072 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302801 | Q2 | T2NT DI TRINITY-MAPLE CRK 33/4 INST MRK | 44401954 | TRINITY-MAPLE CREEK | 033/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-01 | 2022-07-01 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.518887 | 40.7069 | ETL.8170 | 44771073 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302913 | Q2 | EI BRIDGVIL-COTNWD-WD 9/091 RPR WDPKR | 44404807 | BRIDGEVILLE-COTTONWOOD | 009/091 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.4526293 | 40.3891 | ETL.1110 | 44424552 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302915 | Q2 | EI BRDGVIL-CTNWD-WD 9/90 RPL PL | 31526498 | BRIDGEVILLE-COTTONWOOD | 009/090 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.4505979 | 40.3891 | ETL.1110 | 44424412 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302923 | Q2 | EI BRIDGVIL-COTNWD-WD 9/091 RPL HRDW | 44404807 | BRIDGEVILLE-COTTONWOOD | 009/091 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.4526293 | 40.3891 | ETL.1110 | 44424551 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302946 | Mar | T3 EI DRM-GRSS VALLEY-WEIMAR 3/73 RPL ST | 31507653 | DRUM-GRASS VALLEY-WEIMAR | 003/073 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.790122 | 39.2309 | ETL.6760 | 40814278 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302995 | Q2 | T2 EI BRIDGVIL-COTNWD-WD 10/93 RPL HRDW | 44404807 | BRIDGEVILLE-COTTONWOOD | 010/093 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4566827 | 40.389 | ETL.1110 | 44423223 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119302998 | Mar | EI T2NT KILARC-DESCHUTES A025/528 RPR RO |  | KILARC-DESCHUTES | A025/528 | CHS | F | 2020_(1b) Lines with special commitments | Budget Owner (Veg/Land/Road) | 2020-07-02 | 2022-07-02 |  |  | 2021-03-15 | 2021-03-15 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.283191 | 40.5711 | ETL.7300 | 40619315 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | CH | Mar |  |  | 2021-02-03 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303033 | Not Scheduled | T2 EI KILARC-DESCHUTES A025/528 RMV VEG |  | KILARC-DESCHUTES | A025/528 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.283191 | 40.5711 | ETL.7300 | 40619315 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303098 | Mar | T3 EI DRUM-GRASS VLLEY-WMR 3/74 RPR INSL | 44382782 | DRUM-GRASS VALLEY-WEIMAR | 003/074 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.7909404 | 39.2306 | ETL.6760 | 40849872 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303128 | Q2 | T2 EI PHILO JCT-ELK 4/000 REPL POLE | 31507793 | PHILO JCT-ELK | 004/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-06 | 2021-04-06 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.211702 | 39.0813 | ETL.7780 | 40614237 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303160 | Not Scheduled | T2 EI KILARC-DESCHUTES A025/527 RMV VEG |  | KILARC-DESCHUTES | A025/527 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.282326 | 40.5712 | ETL.7300 | 40869368 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303166 | Q2 | T2NT EI KONOCTI-MDLETOWN 25/00 RPL MRKW |  | KONOCTI-MIDDLETOWN | 025/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-02 | 2022-07-02 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.69906 | 38.918 | ETL.6380 | 40615187 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303168 | Q2 | T2 EI KONOCTI-MIDDLETOWN 25/00 RPR POLE | 44610651 | KONOCTI-MIDDLETOWN | 025/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.69906 | 38.918 | ETL.6380 | 40615187 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303208 | Mar | T3 EI DRUM-GRASS VALLEY-WMAR 3/75 RPR IN | 44382782 | DRUM-GRASS VALLEY-WEIMAR | 003/075 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.7913651 | 39.2304 | ETL.6760 | 40900625 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303297 | Q2 | T2 EI BRIDGEVILLE-CTTNWD 15/144 RPL X-BR |  | BRIDGEVILLE-COTTONWOOD | 015/144 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.5640532 | 40.3861 | ETL.1110 | 44424548 | Crossarm-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303343 | Not Scheduled | T2 EI KILARC-DESCHUTES A025/525 RMV VEG |  | KILARC-DESCHUTES | A025/525 | HNA | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.280805 | 40.5712 | ETL.7300 | 40826839 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303423 | Not Scheduled | T2 EI FORT ROSS-GUALALA 56/9 RMV VEG |  | GUALALA-MONTE RIO | 056/009 | HNA | E | 2020_(4) TD tag on high spread line | Budget Owner (Veg/Land/Road) | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.512237 | 38.7584 | ETL.6980 | 40860825 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303448 | Not Scheduled | T3 EI FULTON-CALISTOGA :8/1 RPL ANCHOR | 31507893 | FULTON-CALISTOGA | :008/001 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-01-02 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.599351 | 38.7014 | ETL.6880 | 40912491 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303461 | Not Scheduled | EI DRUM-SUMMIT #1 3/47 RPL POLE | 31508705 | DRUM-SUMMIT #1 | 003/047 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.7159835 | 39.2841 | ETL.1440 | 44768900 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303469 | Not Scheduled | EI DRUM-SUMMIT #1 003/047 RPL PL |  | DRUM-SUMMIT #1 | 003/047 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.7159835 | 39.2841 | ETL.1440 | 44768899 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-19 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119303517 | Q2 | EI BRIDGVIL-COTNWD-WD 10/93 RPL HRDW | 44404807 | BRIDGEVILLE-COTTONWOOD | 010/093 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.4566827 | 40.389 | ETL.1110 | 44423224 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303518 | Q2 | T2 EI BRIDGVILE-CTNWD 010/094 RPL HRDW | 44404807 | BRIDGEVILLE-COTTONWOOD | 010/094 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4589287 | 40.389 | ETL.1110 | 44423894 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303519 | Q2 | T2 EI BRIDGVILE-CTNWD 010/094 RPL HRDW | 44404807 | BRIDGEVILLE-COTTONWOOD | 010/094 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4589287 | 40.389 | ETL.1110 | 44423895 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303662 | Mar | T3 EI DRM-GRSS VLY-WMR 0/12 REFRAME CRSW | 31507652 | DRUM-GRASS VALLEY-WEIMAR | 000/012 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.759258 | 39.2543 | ETL.6760 | 40598639 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303752 | Q2 | EI T3NT UKH-HPLND-CLVRDLE 10/7 INST MRKW | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 010/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-02 | 2022-07-02 |  |  | 2021-04-16 | 2021-04-13 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.988195 | 38.802 | ETL.4050 | 40804072 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303783 | Not Scheduled | T2NT DI SPLDING-SUMMIT 2/103 RMV PL BUTT | 44379026 | SPAULDING-SUMMIT | 002/103 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.601104 | 39.3133 | ETL.8060 | 40751901 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-09-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303804 | Q2 | T2 EI KONOCTI-MIDDLETOWN 24/08 RPR POLE | 44610651 | KONOCTI-MIDDLETOWN | 024/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.702709 | 38.919 | ETL.6380 | 40860830 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303805 | Q2 | T2 EI KNCT-MDDLTWN 25/003 RPL POLE | 31509670 | KONOCTI-MIDDLETOWN | 025/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 | 2021-04-19 | 2021-04-23 | 2021-04-23 | 2021-04-23 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.6929 | 38.9161 | ETL.6380 | 40648319 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303817 | Not Scheduled | T3 EI FULTON-CALISTOGA :7/8 RPL ANCHOR | 31507893 | FULTON-CALISTOGA | :007/008 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.597388 | 38.6983 | ETL.6880 | 40906828 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303985 | Mar | T2 EI KILARC-DESCHUTES 4/103 REGRADE | 44406470 | KILARC-DESCHUTES | 004/103 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.925902 | 40.6209 | ETL.7300 | 44837825 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303988 | Q4 | T2 EI KESWICK-TRINITY 24/376 REFRAME | 44406439 | KESWICK-TRINITY | 024/376 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.822266 | 40.7086 | ETL.7270 | 40909425 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119303989 | Q4 | T2 KESWICK-TRINITY 24/380 REFRAME | 44406439 | KESWICK-TRINITY | 024/380 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.824517 | 40.7075 | ETL.7270 | 40909429 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304011 | Mar | T2 EI KILARC-DESCHUTES 4/97 REFRAME | 31510881 | KILARC-DESCHUTES | 004/097 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.92276 | 40.6236 | ETL.7300 | 40759292 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304013 | Mar | T2 EI KILARC-DESCHUTES 4/096 RPL POLE | 31509538 | KILARC-DESCHUTES | 004/096 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.922205 | 40.624 | ETL.7300 | 40656965 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304014 | Mar | EI T2NT KILARC-DESCHUTES 4/102 RMV BUTT | 44406470 | KILARC-DESCHUTES | 004/102 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-02 | 2022-07-02 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.925319 | 40.6214 | ETL.7300 | 40877898 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304022 | Mar | T2 EI EAGLE ROCK-CORTINA 16/015 RPL POLE | 31514526 | EAGLE ROCK-CORTINA | :016/015 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.609462 | 38.9643 | ETL.1470 | 41176361 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304025 | Q2 | EI T2NT MALIN-RND MTN #2 75/380B INST MR | 44408444 | MALIN-ROUND MTN #2 | 075/380B | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.852096 | 41.0619 | ETL.6020 | 41162688 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304026 | Q2 | EI T2NT MLN-RND MTN #2 75/380A INS MRKS | 44408444 | MALIN-ROUND MTN #2 | 075/380A | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.851997 | 41.0618 | ETL.6020 | 41162689 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304075 | Mar | T3 EI DRUM-GRASS VALLEY-WEIMAR 0/9 RPL P | 31507653 | DRUM-GRASS VALLEY-WEIMAR | 000/009 | 70Y | E | 2020_(1a) PSPS |  | 2020-07-02 | 2021-01-02 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.760074 | 39.2552 | ETL.6760 | 40865403 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 119304193 | Not Scheduled | T2 DI SPAULDING-SUMMIT 15/497 RPR SPLW | 44379026 | SPAULDING-SUMMIT | 015/497 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.379673 | 39.3248 | ETL.8060 | 40876711 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304207 | Q3 | T3 DI DONNELLS-MI-WUK 005/002 RPL POLE | 31508011 | DONNELLS-CURTIS | 005/002 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.056954 | 38.1806 | ETL.1400 | 44766897 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  | FERC | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304269 | Q4 | T3 DI MDL FRK-GLD HL 3/29 (C) REPL POLE | 31510070 | MIDDLE FORK-GOLD HILL | 003/029 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-28 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.633678 | 38.9982 | ETL.5140 | 44769628 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304272 | Q2 | T3 EI IGNACIO-BOLINAS #2 25/283 RPR RGRA | 44640732 | IGNACIO-BOLINAS #2 | 025/283 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.708223 | 37.9522 | ETL.7180 | 44837770 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304273 | Q2 | EI IGNACIO-BOLINAS #2 25/284 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 025/284 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-23 | 2021-04-16 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.7079215 | 37.9516 | ETL.7180 | 44360861 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304274 | Q2 | EI IGNACIO-BOLINAS #2 25/284 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 025/284 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-23 | 2021-04-16 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.7079215 | 37.9516 | ETL.7180 | 44360860 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304275 | Q2 | EI IGNACIO-BOLINAS #2 25/284 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 025/284 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-23 | 2021-04-16 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.7079215 | 37.9516 | ETL.7180 | 44360862 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304302 | Q2 | HUMBOLDT-BRIDGEVILLE-WD 105/2 RPR JMPR | 44107184 | HUMBOLDT-BRIDGEVILLE | 105/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.942359 | 40.7161 | ETL.1810 | 44322543 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304312 | Q4 | T3 DI MDL FRK-GLD HL 3/29 (R) REPL POLE | 31510070 | MIDDLE FORK-GOLD HILL | 003/029 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-28 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.633678 | 38.9982 | ETL.5140 | 44769629 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-07-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304337 | Q2 | T2 EI TRINITY-MAPLE CREEK 041/008 RPL PO | 31512223 | TRINITY-MAPLE CREEK | 041/008 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.654869 | 40.7264 | ETL.8170 | 40861533 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304339 | Q2 | T2 EI TRINITY-MAPLE CREEK 041/004 REPL P | 31512224 | TRINITY-MAPLE CREEK | 041/004 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.649192 | 40.7251 | ETL.8170 | 40771335 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304351 | Q2 | T2 EI TRINITY-MAPLE CREEK 41/1 RPR JMPRW | 44401954 | TRINITY-MAPLE CREEK | 041/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.645621 | 40.7248 | ETL.8170 | 40602091 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304355 | Q2 | T2 EI TRINITY-MAPLE CREEK 041/007 RPL PO | 31512223 | TRINITY-MAPLE CREEK | 041/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.653876 | 40.7262 | ETL.8170 | 40826063 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304378 | Not Scheduled | T3 FULTON-CALISTOGA :002/001 REFRAM POLE | 31507893 | FULTON-CALISTOGA | :002/001 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-01-02 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.585685 | 38.6222 | ETL.6880 | 44923819 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304433 | Q4 | T2 EI KESWICK-TRINITY 20/305 INST GYWW | 44406439 | KESWICK-TRINITY | 020/305 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.766251 | 40.7164 | ETL.7270 | 44649373 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304488 | Q3 | T2 DI CARIBOU-WESTWOOD 011/228 RPR GYWW |  | CARIBOU-WESTWOOD | 011/228 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.075105 | 40.2229 | ETL.6300 | 40824687 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304489 | Q2 | T2NT DI HAT CRK #1-WSTWD 1/41 RMV DEBRIS | 44388736 | HAT CREEK #1-WESTWOOD | 001/041 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-01 | 2022-07-01 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.507355 | 40.9225 | ETL.7030 | 40671148 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304744 | Q2 | T2 EI TRINITY-MAPLE CREEK 28/004 INS INS | 31510698 | TRINITY-MAPLE CREEK | 028/004 | 93I | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.4245086 | 40.6989 | ETL.8170 | 40916110 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304749 | Q2 | T2 EI TRINITY-MAPLE CREEK 28/004 ANTI SP | 44401954 | TRINITY-MAPLE CREEK | 028/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.424495 | 40.6989 | ETL.8170 | 40906441 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304757 | Not Scheduled | T2 EI TRINITY-MAPLE CREEK 28/004 RMV VEG |  | TRINITY-MAPLE CREEK | 028/004 | HNA | E | 2020_(3) On high spread structure | Budget Owner (Veg/Land/Road) | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.424495 | 40.6989 | ETL.8170 | 40906441 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304806 | Q2 | EI TRINITY-MAPLE CREEK 35/6 RPL INSW | 31512233 | TRINITY-MAPLE CREEK | 035/006 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.5529089 | 40.7219 | ETL.8170 | 44565604 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304807 | Q2 | EI TRINITY-MAPLE CREEK 35/6 RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 035/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.5529089 | 40.7219 | ETL.8170 | 44565621 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304808 | Q2 | EI TRINITY-MAPLE CREEK 35/6 RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 035/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.5529089 | 40.7219 | ETL.8170 | 44565604 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304809 | Q2 | EI TRINITY-MAPLE CREEK 35/6 RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 035/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.5529089 | 40.7219 | ETL.8170 | 44565595 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304810 | Q2 | EI TRINITY-MAPLE CREEK 35/6 RPL INSW | 31512233 | TRINITY-MAPLE CREEK | 035/006 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.5529089 | 40.7219 | ETL.8170 | 44565595 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304811 | Q2 | EI TRINITY-MAPLE CREEK 35/6 RPL INSW | 31512233 | TRINITY-MAPLE CREEK | 035/006 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.5529089 | 40.7219 | ETL.8170 | 44565621 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304814 | Q2 | EI TRINITY-MAPLE CREEK 35/006 RMV PL BUT | 44401994 | TRINITY-MAPLE CREEK | 035/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-02 | 2022-07-02 |  |  | 2021-04-17 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.5529089 | 40.7219 | ETL.8170 | 44565621 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304965 | Q2 | HAT CREEK #1-WESTWOOD 50/972 RPR GYWW | 44406426 | HAT CREEK #1-WESTWOOD | 050/972 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.013717 | 40.3694 | ETL.7030 | 40861885 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304968 | Q2 | EI HAT CREEK #1-WESTWOOD 50/969 REFRAME |  | HAT CREEK #1-WESTWOOD | 050/969 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.01409 | 40.3718 | ETL.7030 | 40810088 | Crossarm-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304969 | Q2 | EI HAT CREEK #1-WESTWOOD 50/973 RPR GYWW | 44406426 | HAT CREEK #1-WESTWOOD | 050/973 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.013575 | 40.3687 | ETL.7030 | 40589880 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304987 | Not Scheduled | EI T2NT MALIN-RND MTN #2 84/426 CANCEL | 44408444 | MALIN-ROUND MTN #2 | 084/426 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.91541 | 40.9501 | ETL.6020 | 40817713 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119304988 | Not Scheduled | EI T2NT MALIN-RND MTN #2 85/430 CANCEL | 44408444 | MALIN-ROUND MTN #2 | 085/430 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.916315 | 40.938 | ETL.6020 | 40601193 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305000 | Q2 | EI HAT CREEK #1-WESTWOOD 50/977 RPR GYWW | 44406426 | HAT CREEK #1-WESTWOOD | 050/977 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.013052 | 40.3655 | ETL.7030 | 40758936 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305003 | Not Scheduled | EI T2NT MALIN-RD MTN #2 86/435 CANCEL | 44408444 | MALIN-ROUND MTN #2 | 086/435 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.917435 | 40.9229 | ETL.6020 | 40752312 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305004 | Not Scheduled | EI T2NT MALIN-RND MTN #2 85/431 CANCEL | 44408444 | MALIN-ROUND MTN #2 | 085/431 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.916526 | 40.9351 | ETL.6020 | 40592583 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305005 | Q2 | EI T2NT MALIN-RND MTN #2 86/437 INST GMK | 44408444 | MALIN-ROUND MTN #2 | 086/437 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.917928 | 40.9164 | ETL.6020 | 40810012 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305064 | Not Scheduled | T2 DI DRUM-SUMMIT #2 14/168 RPR INSS | 44396379 | DRUM-SUMMIT #2 | 014/168 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.545204 | 39.3152 | ETL.1450 | 40834498 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305069 | Q2 | T2 DI CRESTA-RIO OSO 27/222 RPLC INSS | 31500129 | CRESTA-RIO OSO | 027/222 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.52882 | 39.5786 | ETL.4590 | 41140280 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305110 | Q3 | T3 DI MTCLF-GRN VALLY 16/113B RPL CRSW | 31508012 | METCALF-GREEN VALLEY | 016/113 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-07-09 | 2021-07-08 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.662645 | 37.0344 | ETL.2540 | 43684239 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Moss Landing |  | Y - 11 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-08-06 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305111 | Q3 | T3 DI MTCLF-GRN VALLY 16/113 RPL CRSW | 31508012 | METCALF-GREEN VALLEY | 016/113 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-07-09 | 2021-07-08 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.662645 | 37.0344 | ETL.2540 | 43684237 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Moss Landing |  | Y - 10 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-07-17 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305122 | Q3 | T2 CARIBOU #2 14/025 REPL POLE | 31507891 | CARIBOU #2 | 014/025 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.113667 | 40.0247 | ETL.6280 | 40768817 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305127 | Q4 | T2 KESWICK-TRINITY 24/382 REPLUMB | 44406439 | KESWICK-TRINITY | 024/382 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.82604 | 40.7068 | ETL.7270 | 40909431 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305138 | Not Scheduled | T3 DI DRUM-SUMMIT#2 3/43L RPR STRW | 44378680 | DRUM-SUMMIT #2 | 003/043 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.1450 | 44155576 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305160 | Q4 | T2 KESWICK-TRINITY 24/382 RMV PL BUT | 44406439 | KESWICK-TRINITY | 024/382 | ICW | E | 2020_(3) On high spread structure |  | 2020-07-02 | 2021-07-02 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.82604 | 40.7068 | ETL.7270 | 40909431 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305163 | Q4 | T2 KESWICK-TRINITY 24/380 RMV PL BUTT | 44406439 | KESWICK-TRINITY | 024/380 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-02 | 2022-07-02 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.824517 | 40.7075 | ETL.7270 | 40909429 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305206 | Q2 | T2 DI ELK-GUALALA 40/1 GRD WSH INSU | 44610595 | ELK-GUALALA | 040/001 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2021-06-30 | 2021-05-20 | 2021-05-22 | 2021-05-20 | 2021-05-20 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.69456 | 39.0852 | ETL.8410 | 44645410 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305364 | Not Scheduled | T3NT DI SLO-SANTA MARIA 14/129 INS MRKW |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 014/249 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR3 |  | South | WSIP | [6 empty] | '-120.507827 | 35.1122 | ETL.9100 | 44191390 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305370 | Q3 | T3NT DI DONNELLS-MI-WUK 9/2 RMV BUTT | 44467328 | DONNELLS-CURTIS | 009/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-01 | 2022-07-01 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.111372 | 38.1468 | ETL.1400 | 44770780 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305373 | Q3 | T3 DI DONNELLS-MI-WUK 9/2L RPR GYWW | 44623509 | DONNELLS-CURTIS | 009/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.111372 | 38.1468 | ETL.1400 | 44770780 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305374 | Q3 | T3 DI DONNELLS-MI-WUK 9/2R RPR GYWW | 44623510 | DONNELLS-CURTIS | 009/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.111372 | 38.1468 | ETL.1400 | 44770781 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305385 | Mar | T3 EI KONOCTI-MIDDLETOWN 14/001 RPL HRDW | 44610651 | KONOCTI-MIDDLETOWN | 014/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-01-02 |  |  | 2021-03-02 | 2021-03-02 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.584737 | 38.7744 | ETL.6380 | 44370570 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305386 | Q2 | T2 FORT ROSS-GUALALA 46/0 RPR STRW |  | GUALALA-MONTE RIO | 046/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 | 2021-06-07 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.342741 | 38.7153 | ETL.6980 | 40606918 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305389 | Mar | T3 EI POTTER VALLEY-WILLITS 9/3 REPLUB I | 44610689 | POTTER VALLEY-WILLITS | 009/003A | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-03-09 | 2021-03-09 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.2798165 | 39.3742 | ETL.7820 | 40579265 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119305556 | Q2 | DI GRBRVIL-LYTNVIL 49/6L RPL PL | 31506024 | GARBERVILLE-LAYTONVILLE | 049/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.8365 | 44403656 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119307639 | Q2 | EI TRINITY-MAPLE CREEK 36/1 RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 036/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 | 2021-04-05 | 2021-04-11 | 2021-04-11 | 2021-04-05 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.5576521 | 40.7219 | ETL.8170 | 44271139 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119307692 | Not Scheduled | T2 DI DRUM-SUMMIT #1 026/310 RPL INSS | 31509156 | DRUM-SUMMIT #1 | 026/310 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.337943 | 39.3104 | ETL.1440 | 44768874 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119307693 | Q2 | T2 EI FORT ROSS-GUALALA 038/6 RPR STRW |  | GUALALA-MONTE RIO | 038/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 | 2021-06-15 | 2021-06-18 | 2021-06-15 | 2021-06-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.309053 | 38.6265 | ETL.6980 | 40821470 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119307772 | Q2 | T2 EI TRNTY-MPLE CRK 28/006 RPL PL | 31512223 | TRINITY-MAPLE CREEK | 028/006 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-07-02 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.428153 | 40.6992 | ETL.8170 | 40906443 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308062 | Q2 | T2 DI MI-WUK-CURTIS 026/001 RPR GYWW | 44623511 | ETL.1073.POLE.WDPS | 026/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.308616 | 37.9757 | ETL.1073 | 44771104 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308066 | Q2 | T2 DI MI-WUK-CURTIS 026/001 RPR GYWW | 44623512 | ETL.1073.POLE.WDPS | 026/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.308616 | 37.9757 | ETL.1073 | 44771105 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308082 | Not Scheduled | T3 DI DRUM SUMMIT #1 26/308 RPR ANCW | 44378657 | DRUM-SUMMIT #1 | 026/308 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.1440 | 44149471 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308091 | Q2 | T2 DI MI-WUK-CURTIS 026/001 RPR GYWW | 44623513 | ETL.1073.POLE.WDPS | 026/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.308616 | 37.9757 | ETL.1073 | 44771121 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308110 | Q2 | T2 DI MI-WUK-CURTIS 026/001 RPL ANCW | 31509574 | ETL.1073.POLE.WDPS | 026/001 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.308616 | 37.9757 | ETL.1073 | 44771121 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308118 | Q2 | T2NT DI MI-WUK-CURTIS 026/1 RMV PL BUTT | 44623514 | ETL.1073.POLE.WDPS | 026/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-01 | 2022-07-01 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.308616 | 37.9757 | ETL.1073 | 44771104 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 41 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-09-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308126 | Q3 | T2 DI CARIBOU-WESTWOOD 10/196 RPR STRW |  | CARIBOU-WESTWOOD | 010/196 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.068902 | 40.2032 | ETL.6300 | 40826511 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308158 | Not Scheduled | T2 DI SPAULDING-SUMMIT 2/114 RMV PL BUTT | 44403403 | SPAULDING-SUMMIT | 002/114 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.595975 | 39.3129 | ETL.8060 | 40828163 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308180 | Not Scheduled | T2 DI SPAULDING-SUMMIT 2/114 INST MRKW | 44403402 | SPAULDING-SUMMIT | 002/114 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.595975 | 39.3129 | ETL.8060 | 40828163 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308265 | Q2 | T2NT DI HAT CREK #1-WESTWOD 0/8 RMV BUTT | 44388736 | HAT CREEK #1-WESTWOOD | 000/008 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-01 | 2022-07-01 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.539403 | 40.9274 | ETL.7030 | 40757855 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308316 | Not Scheduled | T2NT DI SPLDING-SUMMIT 16/511 RMV PL BUT | 44402132 | SPAULDING-SUMMIT | 016/511 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.378442 | 39.3169 | ETL.8060 | 40809675 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308326 | Q2 | T3 DI DRUM-HIGGINS 3/40R RPL POLE | 31509929 | DRUM-HIGGINS | 003/040 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.813915 | 39.2192 | ETL.4393 | 44172200 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308332 | Q2 | T2 DI HAT CREK #1-WESTWOD 0/8 RPR GYWW | 44388736 | HAT CREEK #1-WESTWOOD | 000/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.539403 | 40.9274 | ETL.7030 | 40757855 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308374 | Q2 | T3 DI DRUM-HIGGINS 3/40L RPL POLE | 31509929 | DRUM-HIGGINS | 003/040 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-01-01 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.813915 | 39.2192 | ETL.4393 | 44172199 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-22 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308380 | Not Scheduled | T3 EI FULTON-CALISTOGA :007/007 RPR GYWW | 44597303 | FULTON-CALISTOGA | :007/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-03 | 2021-01-03 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.597431 | 38.6959 | ETL.6880 | 40912489 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308411 | Q2 | T2 EI IGNACIO-BOLINAS #2 4/56 RPL POLE | 31507657 | IGNACIO-BOLINAS #2 | 004/056 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-03 | 2021-07-03 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.62022 | 38.0955 | ETL.7180 | 40701434 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308494 | Not Scheduled | T2 DI SPAULDING-SUMMIT 15/499 INST IBW | 44403403 | SPAULDING-SUMMIT | 015/499 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.379476 | 39.324 | ETL.8060 | 40602276 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308504 | Q2 | DI GRBRVLL-LAYTNVLLE 51/10 RMV BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 051/010 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-12 | 2022-06-12 | 2020-08-28 | 2020-09-05 | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.640631 | 40.0452 | ETL.8365 | 40912579 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-09 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308518 | Q2 | T2 EI TRINITY-MAPLE CREEK 51/7 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 051/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.830569 | 40.7658 | ETL.8170 | 40808969 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308521 | Q2 | T3 DI DRUM-HIGGINS 0/10 RPL POLE (L) | 31509929 | DRUM-HIGGINS | 000/010 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.766186 | 39.2444 | ETL.4393 | 44172237 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-22 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308523 | Q2 | T3 DI DRUM-HIGGINS 0/10 RPL POLE (R) | 31509929 | DRUM-HIGGINS | 000/010 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-06-30 | 2020-12-30 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.766186 | 39.2444 | ETL.4393 | 44172238 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-22 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308586 | Q3 | T3 DI DONNELLS-MI-WUK 009/006 RPR GYWW | 44623515 | DONNELLS-CURTIS | 009/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.114562 | 38.1407 | ETL.1400 | 44770782 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308620 | Q3 | T3 DI DONNELLS-MI-WUK 009/006 RPR GYWW | 44623517 | DONNELLS-CURTIS | 009/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.114562 | 38.1407 | ETL.1400 | 44770783 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308947 | Mar | T3 EI SBRNTE-GRZLY-CLRMNT #2 A0/5 RPL IN | 31511124 | SOBRANTE-GRIZLY-CLARMNT #2+ | A000/005 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-03 | 2021-01-03 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.213444 | 37.8979 | ETL.3750 | 40773525 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119308994 | Mar | T3 DI DRUM-HIGGINS 9/88L RPR POLE | 44379027 | DRUM-HIGGINS | 009/088 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-01-02 |  |  | 2021-03-20 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.892148 | 39.1663 | ETL.4393 | 44172182 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309017 | Q2 | T2 EI PHILO JCT-ELK 4/5 RPL POLE | 31507793 | PHILO JCT-ELK | 004/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-04-06 | 2021-04-06 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.216732 | 39.0717 | ETL.7780 | 40762789 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309075 | Not Scheduled | EI SAN LUIS OBISPO-CAYUCOS 012/110 RPR G |  | SAN LUIS OBISPO-CAYUCOS | 012/110 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 | [9 empty] | South | WSIP | [6 empty] | '-120.7615714 | 35.3206 | ETL.9090 | 44565366 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-15 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309122 | Not Scheduled | T2 DI SPLDNG-SMT 2/112 RMV PL BUTT | 44403402 | SPAULDING-SUMMIT | 002/112 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.596911 | 39.3132 | ETL.8060 | 40771550 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309125 | Not Scheduled | T2 DI SPLDNG-SMMT 2/112 RPL HRDD | 44403403 | SPAULDING-SUMMIT | 002/112 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.596911 | 39.3132 | ETL.8060 | 40771550 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309141 | Mar | T3NT DI MDLE FRK-GLD HLL 9/84 RPR FOUND | 44371599 | MIDDLE FORK-GOLD HILL | 009/084 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-07-01 | 2022-07-01 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.746311 | 38.9853 | ETL.5140 | 40764774 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309144 | Mar | T3 DI MDLE FRK-GLD HLL 9/84 RPL HRDT | 44380516 | MIDDLE FORK-GOLD HILL | 009/084 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 |  |  | 2021-03-18 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.746311 | 38.9853 | ETL.5140 | 40764774 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309188 | Q4 | T3 DI MIDDLE FRK-GLD HL 0/3 RPLC STRW | 31510070 | MIDDLE FORK-GOLD HILL | 000/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2020-12-30 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.597748 | 39.0217 | ETL.5140 | 44552523 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  | 2020-10-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309211 | Not Scheduled | T2 DI SPAULDING-SUMMIT 2/81 RMV PL BUTT | 44403403 | SPAULDING-SUMMIT | 002/081 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.612457 | 39.3112 | ETL.8060 | 40681421 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309266 | Q2 | EI HUMBOLDT-BRIDGEV105/006 RPR WP HOLE | 44402106 | HUMBOLDT-BRIDGEVILLE | 105/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.9458477 | 40.7231 | ETL.1810 | 44322560 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309306 | Mar | T3 DI BRUNSWICK #2 TAP 002/019 RPL INSS | 31506897 | BRUNSWICK #2 TAP | 002/019 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-06-04 | 2020-12-04 |  |  | 2021-03-16 | 2021-03-15 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.034517 | 39.1706 | ETL.1431 | 40878325 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309367 | Not Scheduled | T2 DI SPAULDING-SUMMIT 2/98 RMV PL BUTT | 44403402 | SPAULDING-SUMMIT | 002/098 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.603689 | 39.3128 | ETL.8060 | 44349501 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309447 | Mar | EI T2NT EAGLE ROCK-CORTINA 16/006 INST M | 43730688 | EAGLE ROCK-CORTINA | :016/006 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-03 | 2022-07-03 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.608113 | 38.9572 | ETL.1470 | 41176352 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309456 | Q2 | EI T2NT PHILO JCT-ELK 5/4 RMV DEBRIS | 44610684 | PHILO JCT-ELK | 005/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-07-03 | 2022-07-03 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.228235 | 39.0644 | ETL.7780 | 40763009 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309485 | Q2 | EI HUMBOLDT-BRIDGEVILLE 105/006L RPL PL | 31508093 | HUMBOLDT-BRIDGEVILLE | 105/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.9458477 | 40.7231 | ETL.1810 | 44322558 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309536 | Q2 | T2 EI FORT ROSS-GUALALA 56/000 RPL ANCHW | 31507794 | GUALALA-MONTE RIO | 056/000 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 | 2021-06-07 | 2021-06-14 | 2021-06-08 | 2021-06-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.505869 | 38.7483 | ETL.6980 | 40606941 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309641 | Q2 | T3 EI IGNACIO-BOLINAS #2 24/268 RPR STRW | 44640732 | IGNACIO-BOLINAS #2 | 024/268 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-01-03 |  |  | 2021-04-23 | 2021-04-16 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.723059 | 37.9706 | ETL.7180 | 40876295 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309701 | Not Scheduled | T2 DI SPAULDING-SUMMIT 1/49 REMV BUTT | 44402132 | SPAULDING-SUMMIT | 001/049 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624547 | 39.3181 | ETL.8060 | 40660203 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309729 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 26/309 INST MRKS | 44379080 | DRUM-SUMMIT #1 | 026/309 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.338273 | 39.3103 | ETL.1440 | 44768871 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309735 | Not Scheduled | T2 DI DRUM-SUMMIT #2 26/314A RPL POLE | 31510143 | DRUM-SUMMIT #2 | 026/314A | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.350711 | 39.308 | ETL.1450 | 40756993 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309750 | Not Scheduled | T2NT DI DRUM-SUMMIT #1 26/309 RMV DEBRIS | 44379080 | DRUM-SUMMIT #1 | 026/309 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.338273 | 39.3103 | ETL.1440 | 44768871 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309767 | Q4 | T3 DI MDDLE FORK-GOLD HILL 1/13 RPR GYWW | 44379089 | MIDDLE FORK-GOLD HILL | 001/013 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-01-01 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.601335 | 39.0082 | ETL.5140 | 44552440 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309818 | Not Scheduled | T2 DI SPAULDING-SUMMIT 1/77 RMV PL BUTT | 44402132 | SPAULDING-SUMMIT | 001/077 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.614465 | 39.3108 | ETL.8060 | 40810155 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309822 | Q2 | T2 EI IGNACIO-BOLINAS #2 15/174 RPL ANCH | 31508167 | IGNACIO-BOLINAS #2 | 015/174 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.741336 | 38.0499 | ETL.7180 | 44376899 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309834 | Not Scheduled | EI HUMBOLDT-BRIDGVIL 106/0 PAINT STRT | 44585958 | HUMBOLDT-BRIDGEVILLE | 106/000 | ICX | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-03 | 2022-07-03 | [6 empty] | Check FDA |  |  | North Coast | WSIP | [6 empty] | '-123.947839 | 40.7254 | ETL.1810 | 40598279 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Eureka |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309842 | Not Scheduled | T2 DI SPAULDING-SUMMIT 2/85 RMV PL BUTT | 44403402 | SPAULDING-SUMMIT | 002/085 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.610412 | 39.3116 | ETL.8060 | 40819455 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309847 | Mar | DI KILARC-DESCHUTES 18/375 REMV DEBRIS | 44406469 | KILARC-DESCHUTES | 018/375 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-06-30 | 2022-06-30 |  |  | 2021-03-26 | 2021-03-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.152805 | 40.5637 | ETL.7300 | 40827908 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309889 | Not Scheduled | T3 EI DIABLO-MIDWAY #2 1/7 RPL INSS | 31526475 | DIABLO-MIDWAY #2 | 001/007 | 93K | E | 2020_(2) High fire spread TD |  | 2020-07-03 | 2021-01-03 | [7 empty] | TR3 | LATE | South | WSIP | [6 empty] | '-120.8270858 | 35.213 | ETL.5970 | 40843781 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309902 | Not Scheduled | T2 DI SPAULDING-SUMMIT 1/45 REMV BUTT | 44402132 | SPAULDING-SUMMIT | 001/045 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.625174 | 39.3189 | ETL.8060 | 40878046 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309909 | Not Scheduled | T2 DI SPAULDING-SUMMIT 1/62 INST MRKW | 44402132 | SPAULDING-SUMMIT | 001/062 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.620838 | 39.3121 | ETL.8060 | 44349489 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309985 | Not Scheduled | T2NT DI SPAULDING/SUMMIT 1/78 INST HV | 44402132 | SPAULDING-SUMMIT | 001/078 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.613944 | 39.3109 | ETL.8060 | 40826183 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119309986 | Not Scheduled | T2 DI SPAULDING-SUMMIT 1/78 RMV PL BUTT | 44402132 | SPAULDING-SUMMIT | 001/078 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.613944 | 39.3109 | ETL.8060 | 40826183 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310006 | Q2 | T2 EI TRINITY-MAPLE CREEK 52/0 (L) RPL P | 31508602 | TRINITY-MAPLE CREEK | 052/000B | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.838427 | 40.7673 | ETL.8170 | 40588804 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310105 | Not Scheduled | T2 DI SPAULDING-SUMMIT 2/79 RMV PL BUTT | 44403402 | SPAULDING-SUMMIT | 002/079 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.613407 | 39.311 | ETL.8060 | 40603894 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310108 | Not Scheduled | T2 DI SPAULDING-SUMMIT 2/106 RMV PL BUT | 44403403 | SPAULDING-SUMMIT | 002/106 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.599555 | 39.3136 | ETL.8060 | 42571847 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310203 | Not Scheduled | T2 DI SPAULDING-SUMMIT 1/57 REMV DEBRIS | 44402132 | SPAULDING-SUMMIT | 001/057 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.621879 | 39.3139 | ETL.8060 | 44349484 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310209 | Not Scheduled | T2 DI SPAULDING-SUMMIT 1/59 INST HV | 44402132 | SPAULDING-SUMMIT | 001/059 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.621438 | 39.3132 | ETL.8060 | 44349486 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310312 | Not Scheduled | T3NT DI DRUM-HIGGINS 000/006 RMV PL BUTT | 44379085 | DRUM-HIGGINS | 000/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.765411 | 39.2485 | ETL.4393 | 44172133 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310355 | Feb | T3 DI DRUM-HIGGINS 11/110L RPL STRW | 44401855 | DRUM-HIGGINS | 011/110 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-01-02 |  |  | 2021-02-09 | 2021-01-25 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.920806 | 39.1747 | ETL.4393 | 44172315 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-22 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310357 | Not Scheduled | T3 DI DRUM-HIGGINS 12/115R RPLC POLE | 31509929 | DRUM-HIGGINS | 012/115 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-01-02 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.931694 | 39.1704 | ETL.4393 | 44172253 | Structure-Wood | No Good/Out of Stdrd | Replace | erdy DCNL | DCNL |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-22 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310375 | Not Scheduled | T2 DI DRUM-SUMMIT #1 005/070 CANCEL | 44396378 | DRUM-SUMMIT #1 | 005/070 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.689131 | 39.3023 | ETL.1440 | 44767648 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310525 | Not Scheduled | T2NT DI SPLDING-SUMMIT 16/520 INST MRKW | 44402132 | SPAULDING-SUMMIT | 016/520 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.373793 | 39.3125 | ETL.8060 | 40828172 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310545 | Q2 | T3 DI DRUM HIGGINS 4/48 RPR GYWW | 44379027 | DRUM-HIGGINS | 004/048 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-01-02 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.831684 | 39.2144 | ETL.4393 | 44172174 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310549 | Q2 | T3NT DI DRUM HIGGINS 4/48 RMV PL BUTT | 44379027 | DRUM-HIGGINS | 004/048 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-02 | 2022-07-02 |  |  | 2021-04-03 | 2021-03-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.831684 | 39.2144 | ETL.4393 | 44172174 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310705 | Not Scheduled | T2 DI SPAULDING-SUMMIT 16/508 RMV PL BUT | 44403402 | SPAULDING-SUMMIT | 016/508 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.378756 | 39.3187 | ETL.8060 | 40761669 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310784 | Q2 | T2 EI FORT ROSS-GUALALA 35/1 RPR WDPKR |  | GUALALA-MONTE RIO | 035/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-03 | 2021-07-03 | 2021-06-15 | 2021-06-18 | 2021-06-16 | 2021-06-16 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.300814 | 38.5879 | ETL.6980 | 40584647 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310900 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 16/514 INS MRKW | 44402132 | SPAULDING-SUMMIT | 016/514 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.377682 | 39.3151 | ETL.8060 | 40618277 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310908 | Not Scheduled | T2NT DI CARIBOU-PLMS JCT ;9/21 RMV VEG |  | CARIBOU-PLUMAS JCT | ;009/021 | HNA | F | 2020_(3) On high spread structure |  | 2020-07-03 | 2022-07-03 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-120.923886 | 39.9351 | ETL.6290 | 40588932 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119310963 | Not Scheduled | T2 DI SPAULDING-SUMMIT 16/508 INST MRKW | 44403402 | SPAULDING-SUMMIT | 016/508 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.378756 | 39.3187 | ETL.8060 | 40761669 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311015 | Q2 | EI HUMBOLDT-BRIDGEV 104/003 RPL DAMPER | 44107184 | HUMBOLDT-BRIDGEVILLE | 104/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.9383921 | 40.7026 | ETL.1810 | 44322523 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311051 | Q2 | T2 EI PHILO JCT-ELK 5/3 RPR JUMPER | 44610684 | PHILO JCT-ELK | 005/003 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.226165 | 39.0647 | ETL.7780 | 40660548 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311079 | Q2 | T2 EI TRINITY-MAPLE CREEK 52/0(R) RPL PO | 31508602 | TRINITY-MAPLE CREEK | 052/000B | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.838427 | 40.7673 | ETL.8170 | 40588804 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311081 | Q3 | T2 CARIBOU-PLUMAS JCT 9/21 RPR SPLW | 44408852 | CARIBOU-PLUMAS JCT | ;009/021 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-03 | 2021-07-03 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.923886 | 39.9351 | ETL.6290 | 40588932 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311107 | Not Scheduled | T2NT DI SPLDING-SMMIT 17/538 RMV PL BUT | 44402132 | SPAULDING-SUMMIT | 017/538 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.364042 | 39.3098 | ETL.8060 | 40660182 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311173 | Q3 | DI CARIBOU-PLUMAS JCT 10/6 RPL HRDD | 44408852 | CARIBOU-PLUMAS JCT | ;010/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-01 | 2021-07-01 |  |  | 2021-08-20 | 2021-08-02 |  |  |  |  | SCHD | North Valley | WSIP | [6 empty] | '-120.915928 | 39.9348 | ETL.6290 | 40813509 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311177 | Not Scheduled | T2 DI DRUM-SUMMIT #2 2/31L RPL STRW |  | DRUM-SUMMIT #2 | 002/031 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.732862 | 39.2738 | ETL.1450 | 44552263 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311179 | Not Scheduled | T2 DI DRUM-SUMMIT #2 2/31R RPL STRW |  | DRUM-SUMMIT #2 | 002/031 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.732862 | 39.2738 | ETL.1450 | 44552475 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311201 | Not Scheduled | T2NT DI SPLDING-SMMT 17/549 RMV PL BUTT | 44402132 | SPAULDING-SUMMIT | 017/549 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.358361 | 39.3094 | ETL.8060 | 40669472 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311203 | Not Scheduled | T2NT DI SPLDING-SMMIT 17/549 INS MRKW | 44402132 | SPAULDING-SUMMIT | 017/549 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.358361 | 39.3094 | ETL.8060 | 40669472 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311212 | Q2 | T2 TRINITY-MAPLE CREEK 35/001 RPL DAMPER | 44401954 | TRINITY-MAPLE CREEK | 035/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.545724 | 40.7202 | ETL.8170 | 40628822 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311216 | Q2 | T2 EI TRINITY-MAPLE CREEK 35/000 RPR GYW | 44401954 | TRINITY-MAPLE CREEK | 035/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.5404798 | 40.7176 | ETL.8170 | 44564157 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311219 | Q2 | T2 EI TRINITY-MAPLE CREEK 35/000 RPR GYW | 44401954 | TRINITY-MAPLE CREEK | 035/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.5404798 | 40.7176 | ETL.8170 | 44564135 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311220 | Q2 | T2 EI TRINITY-MAPLE CREEK 35/0A RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 035/000A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.5439268 | 40.7193 | ETL.8170 | 44565472 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311223 | Q2 | T2 EI TRINITY-MAPLE CREEK 35/A REPULL GY | 44401954 | TRINITY-MAPLE CREEK | 035/000A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.5439268 | 40.7193 | ETL.8170 | 44565487 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311224 | Q2 | T2 EI TRINITY-MAPLE CREEK 35/0A REPULL G | 44401954 | TRINITY-MAPLE CREEK | 035/000A | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-03 | 2021-07-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.5439268 | 40.7193 | ETL.8170 | 44565471 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311225 | Q2 | T2 EI TRNITY-MAPLE CREEK 35/000 RPR GYWW | 44401954 | TRINITY-MAPLE CREEK | 035/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.5404798 | 40.7176 | ETL.8170 | 44564141 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311245 | Not Scheduled | T2 DI DRUM-SUMMIT #1 021/253 RMV PL BUTT | 44403319 | DRUM-SUMMIT #1 | 021/253 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.425514 | 39.3153 | ETL.1440 | 44338243 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311354 | Not Scheduled | T2NT DI SLDING-SMMIT 19/613 RMV PL BUT | 44402132 | SPAULDING-SUMMIT | 019/613 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.329474 | 39.3156 | ETL.8060 | 40771544 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311355 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 19/613 INS MRKW | 44402132 | SPAULDING-SUMMIT | 019/613 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.329474 | 39.3156 | ETL.8060 | 40771544 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311359 | Not Scheduled | T2 DI SPAULDING-SUMMIT 1/58 RMV BUTT | 44402132 | SPAULDING-SUMMIT | 001/058 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.621658 | 39.3135 | ETL.8060 | 44349485 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311413 | Q3 | T3 DI SPRING GAP TAP 000/010R REPL POLE | 31508013 | SPRING GAP TAP | 000/010 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-09-08 | 2021-08-08 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.109066 | 38.1781 | ETL.1402 | 44550823 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-09-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311414 | Q3 | T3 DI SPRING GAP TAP 000/010L RPL POLE | 31508013 | SPRING GAP TAP | 000/010 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-09-08 | 2021-08-08 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.109066 | 38.1781 | ETL.1402 | 44550765 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-09-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311442 | Not Scheduled | T2 DI SPAULDING-SUMMIT 1/48 RMV BUTT | 44402347 | SPAULDING-SUMMIT | 001/048 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624686 | 39.3183 | ETL.8060 | 40586118 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119311445 | Not Scheduled | T2 DI DRUM-SUMMIT #2 026/319 RPL STRW | 31510068 | DRUM-SUMMIT #2 | 026/319 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.342187 | 39.3095 | ETL.1450 | 44559010 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312481 | Q3 | T2 DI CARIBOU-PLUMAS JCT 12/1 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 012/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-03 | 2021-07-03 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.989939 | 39.9773 | ETL.6290 | 40585989 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312482 | Q3 | T2 DI CARIBOU-PLUMAS JCT 7/12 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 007/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-03 | 2021-07-03 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.058674 | 40.0103 | ETL.6290 | 40659869 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312488 | Not Scheduled | T2 DI SPLDNG-SMMT 1/75 RMV BUTT | 44402132 | SPAULDING-SUMMIT | 001/075 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.615147 | 39.3107 | ETL.8060 | 40751843 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312490 | Not Scheduled | T2 DI SPLDING-SUMMIT 15/496 INST MRKW | 44403402 | SPAULDING-SUMMIT | 015/496 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.379721 | 39.3251 | ETL.8060 | 40862182 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312491 | Q3 | T2 DI CARIBOU-WESTWOOD 6/114A RPR GYWW |  | CARIBOU-WESTWOOD | 006/114A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.105845 | 40.1571 | ETL.6300 | 40698892 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312492 | Q3 | T2NT DI CARIBOU-WSTWD 6/114A RMV BUTT |  | CARIBOU-WESTWOOD | 006/114A | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-02 | 2022-07-02 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.105845 | 40.1571 | ETL.6300 | 40698892 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312496 | Q3 | T2 DI CARIBOU-WESTWOOD 6/114B RPR GYWW |  | CARIBOU-WESTWOOD | 006/114 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.105804 | 40.1571 | ETL.6300 | 42624238 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312516 | Not Scheduled | T2 DI CAYUCOS-CAMBRIA 14/98 RPR GYWW |  | CAYUCOS-CAMBRIA | 014/098 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.056282 | 35.5711 | ETL.8560 | 40763015 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-17 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312529 | Not Scheduled | T2 DI DRUM-SUMMIT #2 22/263L REPL POLE | 44396700 | DRUM-SUMMIT #2 | 022/263 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.411689 | 39.3285 | ETL.1450 | 44557783 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312570 | Not Scheduled | T3 DI DRUM-SUMMIT #2 4/56 RPL INSW | 31508499 | DRUM-SUMMIT #2 | 004/056 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.703817 | 39.2929 | ETL.1450 | 40636105 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312575 | Not Scheduled | T3NT DI DRUM-SUMMIT #2 4/56 RMV PL BUTT | 44378680 | DRUM-SUMMIT #2 | 004/056 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2022-07-01 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.703817 | 39.2929 | ETL.1450 | 44549466 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312577 | Not Scheduled | T2 DI DRUM-SUMMIT #1 4/55 RPL POLE |  | DRUM-SUMMIT #1 | 004/055 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.705508 | 39.2907 | ETL.1440 | 44837693 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-07-16 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312580 | Not Scheduled | T2 DI DRUM-SUMMIT #1 4/55 RPL POLE |  | DRUM-SUMMIT #1 | 004/055 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.705508 | 39.2907 | ETL.1440 | 44837643 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312588 | Q3 | T2 DI CARIBOU-PLUMAS JCT 6/14 RPR GYWW | 44408852 | CARIBOU-PLUMAS JCT | 006/014 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-03 | 2021-07-03 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.062497 | 40.0202 | ETL.6290 | 40769601 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312621 | Q3 | T2 DI CARIBOU-PLUMAS JCT 7/17 RPR WPKRW | 44408852 | CARIBOU-PLUMAS JCT | 007/017 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-03 | 2021-07-03 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.054906 | 40.0091 | ETL.6290 | 40824663 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312665 | Not Scheduled | T3NT DI DRUM-SUMMIT #1 6/74 INST MRKW | 44403319 | DRUM-SUMMIT #1 | 006/074 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.682535 | 39.3059 | ETL.1440 | 44815119 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312743 | Not Scheduled | T2NT DI SPLDNG-SMMIT 17/550 RMV PL BUTT | 44402132 | SPAULDING-SUMMIT | 017/550 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.357854 | 39.3094 | ETL.8060 | 40771560 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312745 | Not Scheduled | T2NT DI SPLDING-SMMIT 17/543 RMV PL BUT | 44402132 | SPAULDING-SUMMIT | 017/543 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.361509 | 39.3096 | ETL.8060 | 40826218 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312747 | Q2 | DI GATES-PANOCHE #1 2/11 RPR BENT STL | 44402243 | GATES-PANOCHE #1 | 002/011 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-06-30 | 2021-06-30 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.143777 | 36.1655 | ETL.4720 | 40594743 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119312760 | Not Scheduled | T2 DI SPAULDING-SUMMIT 2/80 RMV DEBRIS | 44403402 | SPAULDING-SUMMIT | 002/080 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.612956 | 39.3111 | ETL.8060 | 40586078 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119312785 | Q4 | T3 EI MIDDLE FRK-GLD HILL 03/28 RPL POLE | 31509217 | MIDDLE FORK-GOLD HILL | 003/028 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-02 | 2021-01-02 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.6303827 | 38.9995 | ETL.5140 | 44761222 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119313019 | Q2 | T2 EI TRINITY-MAPLE CREEK 29/008 REPL PO | 31512224 | TRINITY-MAPLE CREEK | 029/008 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-03 | 2021-07-03 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.447278 | 40.6967 | ETL.8170 | 40906455 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119313097 | Not Scheduled | T3 EI CARIBOU-PALERMO 16/130 RPR ANCHOR |  | CARIBOU-PALERMO | 016/130 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-01-02 | [7 empty] | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.491961 | 39.6772 | ETL.3190 | 41162784 | Anchor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119313155 | Q3 | T2 EI KILARC-DESCHUTES 5/115 RPL POLE | 31509538 | KILARC-DESCHUTES | 005/115 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-07-18 | 2021-06-28 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.935512 | 40.6167 | ETL.7300 | 40602045 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119313233 | Q2 | T2 EI TRINITY-MAPLE CREEK 29/009 RPL PL | 31512223 | TRINITY-MAPLE CREEK | 029/009 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-03 | 2021-07-03 |  |  | 2021-06-05 | 2021-05-31 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.450354 | 40.6959 | ETL.8170 | 40906456 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119313263 | Not Scheduled | T2 DI SPAUDLING-SUMMIT 2/83 RMV PL BUTT | 44403402 | SPAULDING-SUMMIT | 002/083 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.611403 | 39.3114 | ETL.8060 | 40761660 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119313426 | Not Scheduled | T2 DI SPAUDLING-SUMMIT 17/531 RPR STRW | 44402347 | SPAULDING-SUMMIT | 017/531 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.367724 | 39.31 | ETL.8060 | 40751931 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119313491 | Q2 | T2 EI DI BRDGVLL-CTTNWD 11/106 | 43939216 | BRIDGEVILLE-COTTONWOOD | 011/106 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4828616 | 40.389 | ETL.1110 | 44424030 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119313668 | Q3 | DI DONNELLS-MI-WUK 5/2R RPLC POLE | 31508011 | DONNELLS-CURTIS | 005/002 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-06-30 | 2021-06-30 |  |  | 2021-09-07 | 2021-08-07 |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.056954 | 38.1806 | ETL.1400 | 44766898 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  |  | FERC | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119313689 | Mar | T3 EI DRUM-GRASS VALLEY-WEIMAR 3/80 RPL | 31507653 | DRUM-GRASS VALLEY-WEIMAR | 003/080 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-01-06 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.794652 | 39.229 | ETL.6760 | 40664659 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2020-07-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119313855 | Q2 | EI BRIDGEVILLE-COTTONWD 11/104 RMV PL BU | 44404807 | BRIDGEVILLE-COTTONWOOD | 011/104 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2022-07-06 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.4789338 | 40.389 | ETL.1110 | 44423876 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119313856 | Q2 | T2 EI BRDGVILLE-CTTNWD 011/104R RPL HRDW | 43939216 | BRIDGEVILLE-COTTONWOOD | 011/104 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4789338 | 40.389 | ETL.1110 | 44423877 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119313857 | Q2 | T2 EI BRDGVILLE-CTTNWD 011/104L RPL HRDW | 43939216 | BRIDGEVILLE-COTTONWOOD | 011/104 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4789338 | 40.389 | ETL.1110 | 44423876 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314025 | Mar | T3 EI DRUM-GRASS VLLY-WMAR 3/82 RPR STRW | 44379639 | DRUM-GRASS VALLEY-WEIMAR | 003/082 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-01-06 |  |  | 2021-03-14 | 2021-03-04 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.795411 | 39.2285 | ETL.6760 | 40766650 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314103 | Q2 | T2 EI BRIDGEVILLE-COTNWD 15/141L ANTI-SP | 43939216 | BRIDGEVILLE-COTTONWOOD | 015/141 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.5585249 | 40.3874 | ETL.1110 | 44424112 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314104 | Q2 | EI BRIDGEVILLE-COTTONWD 11/102 RMV PL BU | 44404807 | BRIDGEVILLE-COTTONWOOD | 011/102 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2022-07-06 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.475337 | 40.389 | ETL.1110 | 44423204 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314107 | Mar | T2 EI KILARC-DESCHUTES 011/230 RPR WPKR | 44406470 | KILARC-DESCHUTES | 011/230 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.019579 | 40.5739 | ETL.7300 | 40602021 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314126 | Q2 | EI BRIDGEVILLE-COTTONWOOD 11/102L PRP HR | 44404807 | BRIDGEVILLE-COTTONWOOD | 011/102 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.475337 | 40.389 | ETL.1110 | 44423204 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314173 | Q2 | EI BRIDGEVILLE-COTTONWOOD 11/102R RPR HR | 44404807 | BRIDGEVILLE-COTTONWOOD | 011/102 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.475337 | 40.389 | ETL.1110 | 44423205 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314185 | Q2 | EI T2NT BRIDGEVILLE-COTTNWD 15/141 RMV B | 43939216 | BRIDGEVILLE-COTTONWOOD | 015/141 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2022-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.5585249 | 40.3874 | ETL.1110 | 44424113 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314189 | Not Scheduled | T3 EI DRUM-GRASS VALLY-WMAR 0/15 CANCEL | 44379639 | DRUM-GRASS VALLEY-WEIMAR | 000/015 | ICW | E | 2020_(3) On high spread structure |  | 2020-07-06 | 2021-01-06 | [6 empty] | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.758276 | 39.2525 | ETL.6760 | 40756228 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-07-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314210 | Q2 | T2 EI BRIDGEVILLE-COTNWD 15/141R ANTI-SP | 43939216 | BRIDGEVILLE-COTTONWOOD | 015/141 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.5585249 | 40.3874 | ETL.1110 | 44424113 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314245 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 1/67 INST HV | 44402132 | SPAULDING-SUMMIT | 001/067 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.618909 | 39.3115 | ETL.8060 | 40828161 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314248 | Not Scheduled | T2 DI SPAULDING-SUMMIT 2/84 RMV PL BUTT | 44403402 | SPAULDING-SUMMIT | 002/084 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2022-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.610917 | 39.3115 | ETL.8060 | 40761367 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314316 | Q2 | T2 EI SALINAS-LAURELES 11/255 RPL POLE | 31510180 | SALINAS-LAURELES | 011/255 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 | 2021-05-25 | 2021-05-28 | 2021-05-28 | 2021-05-21 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.754369 | 36.5664 | ETL.7930 | 40809889 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 14 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-08-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314443 | Not Scheduled | T3 EI FULTON-CALISTOGA :6/1 REFRAME CRSW | 31507893 | FULTON-CALISTOGA | :006/001 | 93E | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-01-06 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.58686 | 38.6721 | ETL.6880 | 40912471 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-08-24 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314473 | Q2 | T2 EI BRDGVILE-CTTWD 11/101L RPL HRDW | 43939216 | BRIDGEVILLE-COTTONWOOD | 011/101 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4734515 | 40.389 | ETL.1110 | 44423303 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314484 | Not Scheduled | T2 EI KESWICK-TRINITY 23/359 RMV VEGN |  | KESWICK-TRINITY | 023/359 | HNA | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2022-07-06 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.80784 | 40.7119 | ETL.7270 | 40909538 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314491 | Q4 | T2 EI KESWICK-TRINITY 23/360 RMV BUTT | 43939188 | KESWICK-TRINITY | 023/360 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2021-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.808476 | 40.7117 | ETL.7270 | 40906084 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314528 | Q2 | T2 EI COTTONWOOD-HUMBOLDT 11/103L RPR HR | 44404807 | BRIDGEVILLE-COTTONWOOD | 011/103 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4771359 | 40.389 | ETL.1110 | 44550736 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314540 | Q2 | T2 EI COTTONWOOD-HUMBOLDT 11/103R RPR HR | 44404807 | BRIDGEVILLE-COTTONWOOD | 011/103 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4771359 | 40.389 | ETL.1110 | 44550802 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314550 | Q2 | EI COTTONWOOD-HUMBOLDT 011/103 RMV PL BU | 44404807 | BRIDGEVILLE-COTTONWOOD | 011/103 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2022-07-06 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.477136 | 40.389 | ETL.1110 | 44550736 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314600 | Not Scheduled | T2 DI SPAUDLING-SUMMIT 2/117 RPL INSW | 31507463 | SPAULDING-SUMMIT | 002/117 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.594582 | 39.3124 | ETL.8060 | 40883825 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314602 | Not Scheduled | T3 DI DRUM-SUMMIT#2 3/43R RPR STRW | 44378680 | DRUM-SUMMIT #2 | 003/043 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-01-01 | [7 empty] | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.1450 | 44155577 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314748 | Q2 | T2 EI BRIDGEVLE-CTTNWD 15/140 RMV BUTT | 43939216 | BRIDGEVILLE-COTTONWOOD | 015/140 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.556997 | 40.3878 | ETL.1110 | 44424097 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314834 | Q4 | T2 EI KESWICK-TRINITY 21/312 RMV STEPS |  | KESWICK-TRINITY | 021/312 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.773258 | 40.7174 | ETL.7270 | 44649390 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314870 | Q4 | T2 EI KESWICK-TRINITY 21/312 RPR GYWS | 43939188 | KESWICK-TRINITY | 021/312 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.773258 | 40.7174 | ETL.7270 | 44649390 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314880 | Mar | T2 EI EAGLE ROCK-CORTINA 15/012 RPLC POL | 31509667 | EAGLE ROCK-CORTINA | :015/012 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.608034 | 38.9458 | ETL.1470 | 41176337 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314920 | Q2 | T2 EI TRINITY-MAPLE CREEK 000/011A RPL P | 31512223 | TRINITY-MAPLE CREEK | 000/011A | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.940105 | 40.7224 | ETL.8170 | 40906231 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314923 | Mar | T3 EI DRUM-RIO OSO #2 11/112 RMV NEST | 44380550 | DRUM-RIO OSO #2 | 011/112 | ICS | E | 2020_(3) On high spread structure |  | 2020-07-06 | 2021-01-06 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.945398 | 39.1655 | ETL.1430 | 40647222 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314928 | Mar | T2 EI KILARC-DESCHUTES 11/232 RPL POLE | 31509538 | KILARC-DESCHUTES | 011/232 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.020382 | 40.5726 | ETL.7300 | 40668435 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-02-03 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314929 | Mar | T2 EI KILARC-DESCHUTES 10/220 RPR GYWW | 44406470 | KILARC-DESCHUTES | 010/220 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-03-26 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.015041 | 40.5785 | ETL.7300 | 40656983 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  | In Review | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314931 | Q4 | T2 DI KESWICK-TRINITY 25/412 RPR STRW | 43939188 | KESWICK-TRINITY | 025/412 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-02 | 2021-07-02 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.847458 | 40.7029 | ETL.7270 | 40906092 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314932 | Q4 | T2NT DI KESWICK-TRINITY 25/412 RMV BUTT | 43939188 | KESWICK-TRINITY | 025/412 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-02 | 2022-07-02 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.847458 | 40.7029 | ETL.7270 | 40906092 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314934 | Not Scheduled | T2 DI DRUM-SUMMIT#1 25/296 RPL POLE | 31498145 | DRUM-SUMMIT #1 | 025/296 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-02 | 2021-07-02 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.360197 | 39.3097 | ETL.1440 | 44762505 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314939 | Q2 | T2 DI IGNACIO-BOLINAS#1 5/57 RPR SPLW | 44640733 | IGNACIO-BOLINAS #1 | 005/057 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.617355 | 38.031 | ETL.7140 | 44650694 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314941 | Not Scheduled | T2 EI KILARC-DESCHUTES 10/220 RMV VEG |  | KILARC-DESCHUTES | 010/220 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2021-07-06 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.015041 | 40.5785 | ETL.7300 | 40656983 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119314997 | Q4 | T2 EI KESWICK-TRINITY 21/311 RMV STEP |  | KESWICK-TRINITY | 021/311 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.772299 | 40.7172 | ETL.7270 | 44649280 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315104 | Q2 | T2 DI IGNACIO-BOLINAS#1 5/59 RPLC SPLW | 44640733 | IGNACIO-BOLINAS #1 | 005/059 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.619902 | 38.0299 | ETL.7140 | 40585006 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-07-16 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315109 | Q4 | T2 DI KESWICK-TRINITY 18/247 REPULL GUY | 43939188 | KESWICK-TRINITY | 018/247 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.714589 | 40.7219 | ETL.7270 | 44649355 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315164 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 20/083 RPR GYWT |  | DIABLO-MIDWAY #3 | 020/083 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-06 | 2021-07-06 | [6 empty] | Tower guy | TR2 |  | South | WSIP | [6 empty] | '-120.501133 | 35.1683 | ETL.5980 | 40651888 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-08-05 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315189 | Q2 | EI BRIDGEVIL-CTNWD-WD 11/101 RMV PL BUTT | 44404807 | BRIDGEVILLE-COTTONWOOD | 011/101 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.4734515 | 40.389 | ETL.1110 | 44423304 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315200 | Q2 | EI BRIDGEVILLE-COTTONWOOD 10/100 RPR HDR | 44404807 | BRIDGEVILLE-COTTONWOOD | 010/100 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.4715667 | 40.389 | ETL.1110 | 44424541 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-24 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315201 | Q2 | T2 EI BRDGVILE-CTTWD 010/099R RPL HRDW | 43939216 | BRIDGEVILLE-COTTONWOOD | 010/099 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4696831 | 40.389 | ETL.1110 | 44424497 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315202 | Q2 | T2 EI BRDGVILE-CTTWD 010/099R RPR STRW | 43939216 | BRIDGEVILLE-COTTONWOOD | 010/099 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4696831 | 40.389 | ETL.1110 | 44424497 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315204 | Q2 | EI BRIDGEVILLE-COTTONWOOD 10/100R RPR HD | 31526498 | BRIDGEVILLE-COTTONWOOD | 010/100 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.4715667 | 40.389 | ETL.1110 | 44424542 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315208 | Q2 | T2 EI BRDGVILE-CTTWD 010/099L RPR STRW | 43939216 | BRIDGEVILLE-COTTONWOOD | 010/099 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4696831 | 40.389 | ETL.1110 | 44424496 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315224 | Q2 | T2 EI BRDGVILE-CTTWD 010/098R RPR STRW | 43939216 | BRIDGEVILLE-COTTONWOOD | 010/098 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4677154 | 40.389 | ETL.1110 | 44424486 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315252 | Q2 | T2 EI BRDGVILE-CTTWD 010/098R RPR STRW | 43939216 | BRIDGEVILLE-COTTONWOOD | 010/098 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4677154 | 40.389 | ETL.1110 | 44424487 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-16 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315268 | Q2 | EI T2NT WEIMAR #1 2/40 RMV BUTT | 44409160 | WEIMAR #1 | 002/040 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2022-07-06 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.956686 | 39.0225 | ETL.7560 | 40598724 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315293 | Q2 | T2 EI WEIMAR #1 2/40 RPL POLE | 31517852 | WEIMAR #1 | 002/040 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.956686 | 39.0225 | ETL.7560 | 40598724 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-08-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315342 | Mar | T2NT EI EAGLE ROCK-CRTNA :15/08 RMV DBRS | 43730688 | EAGLE ROCK-CORTINA | :015/008 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2022-07-06 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.608154 | 38.9434 | ETL.1470 | 41176333 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315382 | Q2 | T2 EI BRIDGEVILLE-COTTONWD 10/97 REPL HR | 43939216 | BRIDGEVILLE-COTTONWOOD | 010/097 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2021-07-06 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.4655042 | 40.389 | ETL.1110 | 44424028 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315431 | Q2 | EI T2NT WEIMAR #1 2/031 RMV BUTT | 44409160 | WEIMAR #1 | 002/031 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-07-06 | 2022-07-06 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.965493 | 39.0274 | ETL.7560 | 40611406 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-08-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315439 | Q4 | T2 EI KESWICK-TRINITY 23/366 RPR INSW | 43939188 | KESWICK-TRINITY | 023/366 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.8127706 | 40.7113 | ETL.7270 | 40915754 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119315447 | Q4 | T2 DI KESWICK-TRINITY 27/470 RMV PL BUTT | 43939188 | KESWICK-TRINITY | 027/470 | ICW | E | 2020_(3) On high spread structure |  | 2020-07-06 | 2021-07-06 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.88406 | 40.7039 | ETL.7270 | 40908530 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31