2021 Work Plan | 119924691 | Not Scheduled | T3 WV FULTON-CALISTOGA 3/004 INS DAMS |  | FULTON-CALISTOGA | 003/004 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-19 | 2021-04-19 | [7 empty] | TR3 | <90D | North Coast | WSIP | [6 empty] | '-122.486165 | 38.5359 | ETL.6880 | 40770414 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-02-02 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119924817 | Mar | T3 EI DIABLO-MIDWAY #3 11/043 RPR STRT | 44506755 | DIABLO-MIDWAY #3 | 011/043 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-19 | 2021-04-19 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.65312 | 35.1902 | ETL.5980 | 40662862 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119924955 | Q2 | T2 DI HAT CRK #1-WSTWD 038/747 RPL PL | 31515622 | HAT CREEK #1-WESTWOOD | 038/747 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-19 | 2021-10-19 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.041477 | 40.5339 | ETL.7030 | 40868237 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119925069 | Not Scheduled | T2NT DI SPLDING-SUMMIT 012/411 INST MRKW | 44507816 | SPAULDING-SUMMIT | 012/411 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-19 | 2022-10-19 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.442286 | 39.3192 | ETL.8060 | 44156134 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119925582 | Not Scheduled | T2 MALIN-ROUND MTN #2 66/332 RPR GYWS | 44408444 | MALIN-ROUND MTN #2 | 066/332 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-10-19 | 2021-10-19 | [6 empty] | Tower guy | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.722267 | 41.1373 | ETL.6020 | 40677667 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119926497 | Mar | T2 EI DIABLO-MIDWAY #2 12/046 RPR STRT | 44512895 | DIABLO-MIDWAY #2 | 012/046 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-20 | 2021-10-20 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.643668 | 35.1839 | ETL.5970 | 40818886 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119926524 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 12/46 RPR SHLD WR |  | DIABLO-MIDWAY #3 | 012/046 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-20 | 2021-10-20 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.642702 | 35.184 | ETL.5980 | 40812095 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119926929 | Feb | T3 NN BRIDGVL-GRBRVL 5/19 RPR GYWW | 44476628 | BRIDGEVILLE-GARBERVILLE | 005/019 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-19 | 2021-04-16 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.759937 | 40.4165 | ETL.6220 | 40875287 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119926947 | Q3 | T3NT DI BRIDGVL-GRBRVL 10/4 RMV PL BUTT | 44476761 | BRIDGEVILLE-GARBERVILLE | 010/004 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-19 | 2022-10-19 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.727851 | 40.3645 | ETL.6220 | 40752614 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119927466 | Q2 | WV T2 MS LNDNG-MTCLF 25/109 RPR INSS | 44574297 | MOSS LANDING-METCALF | 025/109 | ICS | E | 2020_(2) High fire spread TD |  | 2020-10-20 | 2021-10-20 | 2021-04-28 | 2021-04-28 | 2021-04-28 | 2021-04-28 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.707724 | 37.1058 | ETL.6050 | 40870822 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119927570 | Not Scheduled | T3 NN FULTON-CALISTOGA 8/0 RPR GYWW |  | FULTON-CALISTOGA | 008/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-19 | 2021-04-19 | [7 empty] | TR3 | <90D | North Coast | WSIP | [6 empty] | '-122.534829 | 38.5808 | ETL.6880 | 40588914 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119927776 | Q3 | T2 CARIBOU-PLUMAS JCT 1/012 REFRAME | 31516678 | CARIBOU-PLUMAS JCT | 001/012 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-10-20 | 2021-10-20 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.119481 | 40.0728 | ETL.6290 | 40698784 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119927963 | Mar | T2 EI DIABLO-MIDWAY #2 14/053 RPR STRT | 44512895 | DIABLO-MIDWAY #2 | 014/053 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-20 | 2021-10-20 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.61919 | 35.1671 | ETL.5970 | 40658675 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119928063 | Mar | T2 EI DIABLO-MIDWAY #2 14/054 RPR FOUND | 44512895 | DIABLO-MIDWAY #2 | 014/054 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-10-20 | 2021-10-20 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.613163 | 35.167 | ETL.5970 | 40753873 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119928105 | Q3 | T2 EI TESLA-METCALF 18/76 BENT STL |  | TESLA-METCALF | 018/076 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-20 | 2021-10-20 |  |  | 2021-07-10 | 2021-07-05 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.641397 | 37.4491 | ETL.6110 | 40811953 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119928294 | Mar | T2 EI DIABLO-MIDWAY #2 14/056 RPR FOUND | 44512895 | DIABLO-MIDWAY #2 | 014/056 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-20 | 2021-10-20 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.602768 | 35.1679 | ETL.5970 | 40812069 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119928358 | Q2 | T2 NN PHILO JCT-ELK 012/007 INS MRKW |  | PHILO JCT-ELK | 012/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-19 | 2022-10-19 |  |  | 2021-04-08 | 2021-04-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.343653 | 39.0234 | ETL.7780 | 40819511 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119928545 | Not Scheduled | T2 EI MALIN-ROUND MTN #2 83/420 RPR STRT |  | MALIN-ROUND MTN #2 | 083/420 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-20 | 2021-10-20 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.914089 | 40.9678 | ETL.6020 | 40590604 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119928572 | Feb | T2 CORTINA-MENDOCNO #1 35/167 INST DMPRS | 44610540 | CORTINA-MENDOCINO #1 | 035/167 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-10-20 | 2021-10-20 |  |  | 2021-02-17 | 2021-02-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.7857897 | 39.0993 | ETL.1330 | 40833009 | Damper-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119928794 | Mar | T2 EI DIABLO-MIDWAY #3 14/054 RPR STRT | 44512896 | DIABLO-MIDWAY #3 | 014/054 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-10-20 | 2021-10-20 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.613366 | 35.1676 | ETL.5980 | 40753907 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-06 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119929017 | Mar | EI DIABLO-MIDWAY #2 46/187 RPL INSS | 31522252 | DIABLO-MIDWAY #2 | 046/187 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-20 | 2021-10-20 |  |  | 2021-03-11 | 2021-03-08 | [5 empty] | South | WSIP | [6 empty] | '-120.066556 | 35.2286 | ETL.5970 | 40832276 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-11-10 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119929449 | Q3 | T3 NN BRDGVLL-GRBRVLL 008/006 RPR STRW | 44299806 | BRIDGEVILLE-GARBERVILLE | 008/006 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-27 | 2021-04-16 |  |  | 2021-08-21 | 2021-08-02 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.74258 | 40.3882 | ETL.6220 | 44836545 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119929495 | Not Scheduled | DI SPAULDING-SUMMIT 008/293 RMV DEBRIS | 44513132 | SPAULDING-SUMMIT | 008/293 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-20 | 2022-10-20 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.501922 | 39.3136 | ETL.8060 | 44349524 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119930539 | Not Scheduled | EI MARTIN-DALY CITY #1 3/019 RPR ROAD | 44627163 | MARTIN-DALY CITY #1 | 003/019 | CHS | B | 2020_(0) A and B Tags |  | 2020-10-21 | 2021-01-21 |  |  |  | 2021-01-28 |  |  |  |  | LATE | Central | WSIP |  |  |  |  | Readiness | Road Tag - waiting on ENV permits from SMCPD; did plant and bird surveys per requirements; waiting for ENV Okay | '-122.446306 | 37.6899 | ETL.2200 | 40866964 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Bay |  |  | SMCPD | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 119930759 | Not Scheduled | T2 DI CAYUCOS-CAMBRIA B14/96 RPLC STRW | 31517522 | CAYUCOS-CAMBRIA | B014/096 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-20 | 2021-10-20 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.055589 | 35.5709 | ETL.8560 | 42573746 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-12-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119930928 | Mar | DI MONTA VISTA-JFFRSN #2 2/12 RPLC INSS | 31528464 | MONTA VISTA-JEFFERSON #2 | 002/012 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-20 | 2021-10-20 |  |  | 2021-03-05 | 2021-02-28 | [5 empty] | Central | WSIP | [6 empty] | '-122.115819 | 37.3305 | ETL.5230 | 40725459 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-11-10 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119930945 | Mar | T2 EI DIABLO-MIDWAY #2 15/061 RPR FOUND | 44512895 | DIABLO-MIDWAY #2 | 015/061 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-21 | 2021-10-21 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.58509 | 35.1698 | ETL.5970 | 40597158 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119931112 | Q2 | T2 BRIDGEVILLE-CTTNWD 58/425A INST DAMS | 44625172 | BRIDGEVILLE-COTTONWOOD | 058/425A | ICS | E | 2020_(3) On high spread structure |  | 2020-10-21 | 2021-10-21 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.337168 | 40.3784 | ETL.1110 | 40676686 | Damper-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119931429 | Not Scheduled | T3NT DI RND MTN-CTNWD#3 30/254 RPLC HRDT | 43932111 | ROUND MTN-COTTONWOOD #3 | 030/254 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-10-20 | 2022-10-20 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.971288 | 40.7526 | ETL.5650 | 40755439 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119931571 | Mar | T2 EI DIABLO-MIDWAY #2 16/062 RPR STRT | 44512895 | DIABLO-MIDWAY #2 | 016/062 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-21 | 2021-10-21 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.57837 | 35.1708 | ETL.5970 | 40664602 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119931656 | Not Scheduled | DI SPAULDING-SUMMIT 8/297 RPR INSW | 44513133 | SPAULDING-SUMMIT | 008/297 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-10-20 | 2021-10-20 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.8060 | 44349618 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119931659 | Not Scheduled | DI SPAULDING-SUMMIT 7/267 RPR GYWW | 44506585 | SPAULDING-SUMMIT | 007/267 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-10-20 | 2021-10-20 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.520138 | 39.3098 | ETL.8060 | 44349518 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119932191 | Mar | T2 EI DIABLO-MIDWAY #2 16/064 RPR FOUND | 44512895 | DIABLO-MIDWAY #2 | 016/064 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-21 | 2021-10-21 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.569491 | 35.172 | ETL.5970 | 40753875 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119932695 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 17/065 RPL INSS | 31527296 | DIABLO-MIDWAY #2 | 017/065 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-21 | 2021-10-21 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.5653763 | 35.1725 | ETL.5970 | 40793027 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119933005 | Not Scheduled | T3NT MONTE RIO-FORT ROSS 15/0 RMV STUB |  | ETL.6979.POLE.WOOD | 015/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-06 | 2022-10-06 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-123.012027 | 38.4718 | ETL.6979 | 40587323 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119933093 | Q2 | T2 NN IGNACIO-BOLINAS #2 0/11 RPR GYWW | 44640732 | IGNACIO-BOLINAS #2 | 000/011 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-20 | 2021-10-20 |  |  | 2021-04-14 | 2021-04-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.558193 | 38.0751 | ETL.7180 | 40592828 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119933339 | Feb | T3 DI ROCK CREEK-POE 14/97 RPLC INSS | 31519504 | ROCK CREEK-POE | 014/097 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-20 | 2021-04-20 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.47645 | 39.7493 | ETL.5630 | 40841156 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-11-10 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119933713 | Not Scheduled | WV T3 FULTON-CALISTOGA :005/010 RPL INSW | 31516660 | FULTON-CALISTOGA | :005/010 | 93I | E | 2020_(2) High fire spread TD |  | 2020-10-21 | 2021-04-21 | [7 empty] | TR3 | <90D | North Coast | WSIP | [6 empty] | '-122.587233 | 38.6692 | ETL.6880 | 40912467 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119934283 | Q2 | LOS BANOS-MIDWAY #2 46/192 BENT STEEL | 44506754 | LOS BANOS-MIDWAY #2 | 046/192 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-09-29 | 2021-09-29 |  |  | 2021-04-15 | 2021-02-16 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.523132 | 36.5308 | ETL.6010 | 40664790 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119934285 | Not Scheduled | T2 COTTONWOOD-HUMBOLDT 59/3 CNCL |  | HUMBOLDT-TRINITY | 059/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-10-22 | 2021-10-22 | [5 empty] | Project work | Email CIRT when complete | TR2 |  | North Coast | WSIP | [5 empty] | NERC - [REDACTED] follow up | '-123.160155 | 40.7536 | ETL.1820 | 44562838 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119934287 | Not Scheduled | T2 COTTONWOOD-HUMBOLDT 61/0 CNCL |  | HUMBOLDT-TRINITY | 061/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-10-22 | 2021-10-22 | [5 empty] | Project work | Email CIRT when complete | TR2 |  | North Coast | WSIP | [5 empty] | NERC - [REDACTED] follow up | '-123.181838 | 40.744 | ETL.1820 | 44560469 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119934288 | Not Scheduled | T2 COTTONWOOD-HUMBOLDT 61/0 CNCL |  | HUMBOLDT-TRINITY | 061/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-10-22 | 2021-10-22 | [5 empty] | Project work | Email CIRT when complete | TR2 |  | North Coast | WSIP | [5 empty] | NERC - [REDACTED] follow up | '-123.181838 | 40.744 | ETL.1820 | 44560504 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119934365 | Q2 | T2 MALIN-ROUND MTN #2 68/346A INST BOLT | 44408444 | MALIN-ROUND MTN #2 | 068/346A | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-10-21 | 2021-10-21 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.755855 | 41.1108 | ETL.6020 | 41111819 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119934410 | Not Scheduled | T2 COTTONWOOD-HUMBOLDT 59/3 CNCL |  | HUMBOLDT-TRINITY | 059/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-10-22 | 2021-10-22 | [5 empty] | Project work | Email CIRT when complete | TR2 |  | North Coast | WSIP | [5 empty] | NERC - [REDACTED] follow up | '-123.160155 | 40.7536 | ETL.1820 | 44562935 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119934411 | Not Scheduled | T2 COTTONWOOD-HUMBOLDT 59/3 CNCL |  | HUMBOLDT-TRINITY | 059/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-10-22 | 2021-10-22 | [5 empty] | Project work | Email CIRT when complete | TR2 |  | North Coast | WSIP | [5 empty] | NERC - [REDACTED] follow up | '-123.160155 | 40.7536 | ETL.1820 | 44562699 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119934463 | Q3 | DI GATES-MSTANG SW STA #1 2/13 RPR FOND | 44506740 | SPARE T-LINE RECORD | 002/013 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-10-21 | 2022-10-21 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.085536 | 36.1565 | ETL.2604 | 40644915 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119935391 | Q2 | T2 NN SALINAS-LAURELES A015/330 RPR INSW | 44391519 | SALINAS-LAURELES | A015/330 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-21 | 2021-10-21 | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-10 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.82242 | 36.5752 | ETL.7930 | 40784361 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 20 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-05 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119935408 | Q2 | T2 NN SALINAS-LAURELES A12/268 RPR GYWW | 44294541 | SALINAS-LAURELES | A012/268 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-20 | 2021-10-20 | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-06-29 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.771939 | 36.5701 | ETL.7930 | 40768981 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119935455 | Mar | T2 NN EAGLE RCK-CORTNA :019/005 RPL INSW | 31516690 | EAGLE ROCK-CORTINA | :019/005 | 93I | E | 2020_(2) High fire spread TD |  | 2020-10-21 | 2021-10-21 |  |  | 2021-03-06 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.610656 | 39.0004 | ETL.1470 | 40802017 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-11-10 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119935860 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 18/073 RPL INSS | 31527296 | DIABLO-MIDWAY #2 | 018/073 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-22 | 2021-10-22 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.5416327 | 35.1744 | ETL.5970 | 40680755 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119936035 | Q2 | T2 TRINITY-MAPLE CRK 015/003 INST DAMP |  | TRINITY-MAPLE CREEK | 015/003 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-22 | 2021-10-22 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.178485 | 40.7459 | ETL.8170 | 40650353 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119936095 | Q3 | T2 DI CARIBOU #2 9/2 RPLC INSW | 31518176 | CARIBOU #2 | 009/002 | 93I | E | 2020_(2) High fire spread TD |  | 2020-10-21 | 2021-10-21 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.205281 | 40.0143 | ETL.6280 | 40733733 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119937206 | Q3 | T2NT DI CARIBOU #2 17/22 RMV BUTT |  | CARIBOU #2 | 017/022 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-21 | 2022-10-21 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.064555 | 40.0226 | ETL.6280 | 43250374 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119937207 | Q3 | T2 DI CARIBOU #2 17/22 RPR GYWW |  | CARIBOU #2 | 017/022 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-21 | 2021-10-21 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.064555 | 40.0226 | ETL.6280 | 43250374 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119937504 | Mar | T3 WV BAHIA-MORAGA 25/138 RPR INSS | 44621943 | BAHIA-MORAGA | 025/138 | ICS | E | 2020_(2) High fire spread TD |  | 2020-10-22 | 2021-04-22 | 2021-03-01 | 2021-03-05 | 2021-03-05 | 2021-03-01 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.1747929 | 37.857 | ETL.4340 | 40844499 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119939813 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/1A RMV DBRS INS | 44506584 | SPAULDING-SUMMIT | 000/001A | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-10-22 | 2021-10-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.8060 | 44326150 | Conductor-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119939814 | Not Scheduled | T2 DI SPAULDING-SUMMIT 0/1A RPR GYWW | 44507819 | SPAULDING-SUMMIT | 000/001A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-10-22 | 2021-10-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.644456 | 39.3245 | ETL.8060 | 44326147 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119940068 | Not Scheduled | DI STANISLAUS-NEWARK #1 95/627 REPL INSS | 31515888 | STANISLAUS-NEWARK #1 (12KV) | 095/627 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-22 | 2021-10-22 | [9 empty] | Central | WSIP | [6 empty] | '-121.908622 | 37.5615 | ETL.3850 | 40854315 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119940095 | Not Scheduled | DI STANISLAUS-NEWARK #2 84/550 RMV NEST | 44598139 | STANISLAUS-NEWARK #2 (12KV) | 084/550 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-10-22 | 2021-10-22 | [9 empty] | Central | WSIP | [6 empty] | '-121.737918 | 37.657 | ETL.3860 | 41196038 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119940169 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 20/082 RPL GYWS |  | DIABLO-MIDWAY #2 | 020/082 | ICS | E | 2020_(2) High fire spread TD |  | 2020-10-22 | 2021-10-22 | [6 empty] | Tower guy | TR2 |  | South | WSIP | [6 empty] | '-120.505606 | 35.1687 | ETL.5970 | 40680291 | Guy Wire-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119941324 | Q2 | T3 NN FULTON-CALISTOGA 15/2 RPR GYWW |  | FULTON-CALISTOGA | '-015/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-21 | 2021-04-21 |  |  | 2021-04-30 | 2021-04-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.495139 | 38.442 | ETL.6880 | 44677455 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119941369 | Mar | T2 CBRL-SNT YNZ SW STA 13/110 INST DMPER |  | CABRILLO-SANTA YNEZ SW STA | 013/110 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-23 | 2021-10-23 | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2021-03-12 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.404947 | 34.6478 | ETL.1200 | 40684376 | Damper-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119941386 | Not Scheduled | T3 CORTINA-MENDOCINO #1 20/095 RPL BRDGE | 31519684 | CORTINA-MENDOCINO #1 | 020/095 | 71Y | F | 2020_(3) On high spread structure |  | 2020-10-23 | 2022-10-23 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.556036 | 39.0036 | ETL.1330 | 40764805 | Road | No Good/Out of Stdrd | Replace | DCNL | DCNL | In Estimating, awaiting settlement to put in ESTS | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119941514 | Not Scheduled | WV T3 MNTE RIO-FRT RSS 22/000 INST DAMPR |  | ETL.6979.POLE.WDPS | 022/000 | ICW | E | 2020_(3) On high spread structure |  | 2020-10-23 | 2021-04-23 | [7 empty] | TR3 | <90D | North Coast | WSIP | [6 empty] | '-123.127845 | 38.4745 | ETL.6979 | 44312246 | Damper-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119942871 | Not Scheduled | DI SPAULDING-SUMMIT 8/271 RMV DEBRIS | 44513131 | SPAULDING-SUMMIT | 008/271 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-10-21 | 2022-10-21 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.518807 | 39.3126 | ETL.8060 | 40650048 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119942872 | Not Scheduled | DI SPAULDING-SUMMIT 8/271 REFRAME | 31514886 | SPAULDING-SUMMIT | 008/271 | 93E | E | 2020_(1b) Lines with special commitments |  | 2020-10-21 | 2021-10-21 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.518807 | 39.3126 | ETL.8060 | 40650048 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119943772 | Not Scheduled | T3 EI DIABLO-MIDWAY #3 23/094 RPR GWRS |  | DIABLO-MIDWAY #3 | 023/094 | ICS | E | 2020_(2) High fire spread TD |  | 2020-10-24 | 2021-04-24 | [7 empty] | TR3 | <90D | South | WSIP | [6 empty] | '-120.454003 | 35.1618 | ETL.5980 | 40761051 | Ground Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119944250 | Not Scheduled | T3 EI DIABLO-MIDWAY #2 24/097 RPR GWRS |  | DIABLO-MIDWAY #2 | 024/097 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-24 | 2021-04-24 | [6 empty] | Tower guy | TR3 | <90D | South | WSIP | [6 empty] | '-120.437814 | 35.1617 | ETL.5970 | 40817655 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119944540 | Not Scheduled | T3 EI DIABLO-MIDWAY #3 24/098 RPR GYWS |  | DIABLO-MIDWAY #3 | 024/098 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-24 | 2021-04-24 | [6 empty] | Tower guy | TR3 | <90D | South | WSIP | [6 empty] | '-120.433195 | 35.1625 | ETL.5980 | 40863927 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119947820 | Q2 | DI STANISLAUS-NEWARK #1 093/618 RPR FOND |  | STANISLAUS-NEWARK #1 (12KV) | 093/618 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-10-22 | 2021-10-22 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | Central | WSIP | [6 empty] | '-121.883363 | 37.5741 | ETL.3850 | 40878651 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119948404 | Not Scheduled | T3 EI DIABLO-MIDWAY #2 24/98 CORNA RING |  | DIABLO-MIDWAY #2 | 024/098 | ICS | E | 2020_(2) High fire spread TD |  | 2020-10-26 | 2021-04-26 | [7 empty] | TR3 | <90D | South | WSIP | [6 empty] | '-120.4318744 | 35.1621 | ETL.5970 | 40890120 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119948626 | Q2 | T2 NN IGNACIO-BOLINAS #1 6/64 RPR GYWW | 44640733 | IGNACIO-BOLINAS #1 | 006/064 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-22 | 2021-10-22 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.632067 | 38.025 | ETL.7140 | 40827642 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119948627 | Q2 | T2NT NN IGNACIO-BLNS #1 6/64 INST MRKW | 44640733 | IGNACIO-BOLINAS #1 | 006/064 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-22 | 2022-10-22 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.632067 | 38.025 | ETL.7140 | 40827642 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119948739 | Not Scheduled | T2 NN DRUM-SUMMIT #2 024/294 RPR STRW | 44507687 | DRUM-SUMMIT #2 | 024/294 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-08-20 | 2021-08-20 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.378 | 39.3173 | ETL.1450 | 44557647 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119948742 | Q2 | DI STNISLS-NEWRK #1 93/619 RPR FOND |  | STANISLAUS-NEWARK #1 (12KV) | 093/619 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-10-21 | 2021-10-21 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | Central | WSIP | [6 empty] | '-121.88565 | 37.5729 | ETL.3850 | 40877299 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119948779 | Q2 | DI STANISLAUS-NWRK #1 084/557 RPR FOUND |  | STANISLAUS-NEWARK #1 (12KV) | 084/557 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-22 | 2021-10-22 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | Central | WSIP | [6 empty] | '-121.748255 | 37.652 | ETL.3850 | 41195976 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119948808 | Mar | DI NEWARK-JARVIS #1 011/068 RPR FOUND |  | NEWARK-JARVIS #1 | 011/068 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-10-22 | 2022-10-22 |  |  | 2021-03-27 | 2021-03-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.973356 | 37.5916 | ETL.3020 | 40857713 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119948854 | Not Scheduled | DI STANISLAUS-NWRK #2 084/552 RMV DEBRIS | 44598139 | STANISLAUS-NEWARK #2 (12KV) | 084/552 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-10-22 | 2021-10-22 | [9 empty] | Central | WSIP | [6 empty] | '-121.741173 | 37.6554 | ETL.3860 | 41196041 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119948858 | Not Scheduled | DI STANISLAUS-NWRK #2 084/552 RPL INSS |  | STANISLAUS-NEWARK #2 (12KV) | 084/552 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-22 | 2021-10-22 | [9 empty] | Central | WSIP | [6 empty] | '-121.741173 | 37.6554 | ETL.3860 | 44190573 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119948861 | Not Scheduled | DI STNISLS-NEWRK #2 94/615 GRD WSH INSS | 44598160 | STANISLAUS-NEWARK #2 (12KV) | 094/615 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-10-22 | 2021-10-22 | [9 empty] | Central | WSIP | [6 empty] | '-121.875208 | 37.58 | ETL.3860 | 40802363 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119948870 | Q2 | T2 MI-WUK-CURTIS 023/006 RPL INSW | 31517524 | ETL.1073.INSL.CERA | 023/006 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-10-22 | 2021-10-22 |  |  | 2021-04-24 | 2021-03-24 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.276577 | 37.9984 | ETL.1073 | 40835069 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119948947 | Q4 | DI MAPLE CREEK-HOOPA 005/000 RPL STRW | 31517694 | MAPLE CREEK-HOOPA | 005/000 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-10-21 | 2021-10-21 |  |  | 2021-10-02 | 2021-07-26 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.828297 | 40.8205 | ETL.7490 | 40591300 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119949210 | Not Scheduled | T3 EI DIABLO-MIDWAY #3 25/102 RPR GYWS |  | DIABLO-MIDWAY #3 | 025/102 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-26 | 2021-04-26 | [6 empty] | Tower guy | TR3 | <90D | South | WSIP | [6 empty] | '-120.412503 | 35.1628 | ETL.5980 | 40664657 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 18 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-06 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119949438 | Feb | T3 NN BRDGVL-GRBRVL 6/11 RPR GYWW | 44476628 | BRIDGEVILLE-GARBERVILLE | 006/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-16 | 2021-04-16 |  |  | 2021-02-18 | 2021-02-16 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.750404 | 40.4087 | ETL.6220 | 40586722 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119949896 | Not Scheduled | DI NEWARK-JARVIS #1 011/066 RPR INSS | 44620199 | NEWARK-JARVIS #1 | 011/066 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-23 | 2021-10-23 | [9 empty] | Central | WSIP | [6 empty] | '-121.967878 | 37.5892 | ETL.3020 | 40830649 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119950691 | Mar | DI NEWARK-JARVIS #1 011/069 RPR STRT |  | NEWARK-JARVIS #1 | 011/069 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-23 | 2021-10-23 |  |  | 2021-03-27 | 2021-03-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.975661 | 37.5924 | ETL.3020 | 40871964 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-21 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119951360 | Q2 | T2 DI MENDOCINO-WILLITS 005/007 RPL STRW | 31516891 | MENDOCINO-WILLITS | 005/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-27 | 2021-10-27 | 2021-04-28 | 2021-04-30 | 2021-04-28 | 2021-04-28 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.275202 | 39.2925 | ETL.7540 | 40824396 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119951394 | Not Scheduled | T3 WV MIDDLE FORK #1 0/2 RPL ANCHOR | 31511848 | MIDDLE FORK #1 | 000/002 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-10-27 | 2021-04-27 | [7 empty] | TR3 | <90D | North Valley | WSIP | [6 empty] | '-120.597131 | 39.0236 | ETL.8405 | 40693676 | Anchor-Wood | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119951435 | Q2 | WV BRIDGVILE-CTNWD 0/07 RPR JUMPER | 44625172 | BRIDGEVILLE-COTTONWOOD | 000/007 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-27 | 2021-10-27 |  |  | 2021-04-30 | 2021-03-29 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.278827 | 40.3997 | ETL.1110 | 40816250 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119951503 | Q2 | WV T2 BRDGVILE-CTWD 19/1 RPR JUMPER | 31512259 | BRIDGEVILLE-COTTONWOOD | 019/178 | 93K | E | 2020_(2) High fire spread TD |  | 2020-10-27 | 2021-10-27 |  |  | 2021-04-30 | 2021-03-29 |  |  | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [6 empty] | '-122.634902 | 40.3783 | ETL.1110 | 40759346 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-10 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119951664 | Q3 | DI TESLA-NEWARK #2 010/069 INS ANTI/STRT |  | TESLA-NEWARK #2 | 010/069 | 93A | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-23 | 2022-10-23 |  |  | 2021-07-30 | 2021-07-26 | [5 empty] | Central | WSIP | [6 empty] | '-121.734695 | 37.6563 | ETL.5354 | 41152614 | Structure-Tower | Anti-Climbing Guard | Install |  |  |  |  | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119951926 | Feb | T2 EI RIO DELL JCT-BRDGVL 26/3 RPLC STRW | 31514233 | RIO DELL JCT-BRIDGEVILLE | 026/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-27 | 2021-10-27 |  |  | 2021-02-27 | 2021-02-15 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.989796 | 40.5056 | ETL.7850 | 40666751 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-11-05 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119953556 | Q2 | T2 NN IGNACIO-BOLINAS #1 0/13 RPR GYWW | 44640733 | IGNACIO-BOLINAS #1 | 000/013 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-22 | 2021-10-22 |  |  | 2021-05-03 | 2021-04-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.557598 | 38.075 | ETL.7140 | 40601730 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119953588 | Q2 | T2 NN LAURELES-OTTER 2/7 RPR POLE | 44587870 | LAURELES-OTTER | 002/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-22 | 2021-10-22 | 2021-05-04 | 2021-05-07 | 2021-05-07 | 2021-05-04 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.714435 | 36.4546 | ETL.7380 | 40809417 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119953873 | Q2 | DI GATES-PANOCHE #1 40/186 RPR FOND | 44512894 | GATES-PANOCHE #1 | 040/186 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-10-27 | 2022-10-27 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.537233 | 36.6016 | ETL.4720 | 40820109 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  | Y - 15 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-10-30 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119954410 | Q2 | T3 DI METCALF-MS LDNG #1 48/207 RPR FOND | 44509296 | METCALF-MOSS LANDING #1 | 048/207 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-10-22 | 2021-04-22 |  |  | 2021-05-21 | 2021-05-03 |  |  |  | TR3 | SCHD | South | WSIP | [6 empty] | '-121.655673 | 36.9434 | ETL.5100 | 40818863 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119954592 | Feb | WV RIO DLL JCT-BRDGVILL 22/11 RPL STRW | 31471951 | RIO DELL JCT-BRIDGEVILLE | 022/011 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-28 | 2021-10-28 |  |  | 2021-02-27 | 2021-02-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-124.032224 | 40.525 | ETL.7850 | 40600600 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-12-10 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119955420 | Not Scheduled | T3 WV FULTON-CALISTOGA 3/3 INST DAMPER | 31514779 | FULTON-CALISTOGA | 003/003 | 92F | E | 2020_(4) TD tag on high spread line |  | 2020-10-28 | 2021-04-28 | [7 empty] | TR3 | <90D | North Coast | WSIP | [6 empty] | '-122.485839 | 38.5347 | ETL.6880 | 40649345 | Damper-Wood | No Good/Out of Stdrd | Replace | DOCC | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119956440 | Q2 | DI STANISLAUS-NEWARK #1 083/553 RPR STRT |  | STANISLAUS-NEWARK #1 (12KV) | 083/553 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-23 | 2021-10-23 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | Central | WSIP | [6 empty] | '-121.739502 | 37.6564 | ETL.3850 | 41196044 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119956494 | Not Scheduled | DI_STAN-NEWARK #1 84/556 RPL INSS | 31530187 | STANISLAUS-NEWARK #1 (12KV) | 084/556 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-23 | 2021-10-23 | [9 empty] | Central | WSIP | [6 empty] | '-121.7463 | 37.653 | ETL.3850 | 44190452 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119957910 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 35/142 RPR GYWS |  | DIABLO-MIDWAY #2 | 035/142 | ICS | E | 2020_(2) High fire spread TD |  | 2020-10-28 | 2021-10-28 | [6 empty] | Tower guy | TR2 |  | South | WSIP | [6 empty] | '-120.243505 | 35.1735 | ETL.5970 | 40664627 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119957914 | Not Scheduled | T2 EI MALIN-ROUND MTN #2 71/360B RPR STR |  | MALIN-ROUND MTN #2 | 071/360B | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-27 | 2021-10-27 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.794525 | 41.0801 | ETL.6020 | 41191655 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119957960 | Feb | T3 NN KILARC-CEDAR CREEK 11/255 RPL INSW | 31519093 | KILARC-CEDAR CREEK | 011/255 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-10-28 | 2021-04-28 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.955209 | 40.7715 | ETL.7290 | 40798661 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-02-12 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119958407 | Feb | T3 NN KILARC-CEDAR CREEK 002/061 RPL INS | 31517461 | KILARC-CEDAR CREEK | 002/061 | 93I | E | 2020_(2) High fire spread TD |  | 2020-10-26 | 2021-04-26 |  |  | 2021-02-26 | 2021-02-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.920303 | 40.6931 | ETL.7290 | 40801254 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-11-10 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119959188 | Mar | WV T2 CARIBOU-TABLE MTN 34/254 RPR INSS |  | CARIBOU-TABLE MTN | 034/254 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-29 | 2021-10-29 |  |  | 2021-03-11 | 2021-03-11 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.45502 | 39.8147 | ETL.4440 | 40761220 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119959279 | Not Scheduled | T2 EI MALIN-ROUND MTN #2 87/443 RPR STRT |  | MALIN-ROUND MTN #2 | 087/443 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-09 | 2021-10-09 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.919127 | 40.8994 | ETL.6020 | 40660400 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119959600 | Q2 | T3 DI MISS FLT-GLD HL #1 15/137 RPL INSS | 31504275 | MISSOURI FLAT-GOLD HILL #1 | 015/137 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-26 | 2021-04-26 |  |  | 2021-04-16 | 2021-04-12 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.846522 | 38.6862 | ETL.2660 | 40845239 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119960123 | Not Scheduled | EI ARCO-CHOLAME 19/183 RPL PL | 31517521 | ARCO-CHOLAME | 019/183 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-10-29 | 2021-10-29 | [9 empty] | South | WSIP | [6 empty] | '-120.216355 | 35.7098 | ETL.8440 | 40667278 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-12-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119960126 | Not Scheduled | EI ARCO-CHOLAME 16/165 RPR GYWW |  | ARCO-CHOLAME | 016/165 | ICW | E | 2020_(2) High fire spread TD |  | 2020-10-29 | 2021-10-29 | [9 empty] | South | WSIP | [6 empty] | '-120.171668 | 35.7085 | ETL.8440 | 44664790 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-01 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119960133 | Not Scheduled | EI ARCO-CHOLAME 18/175 RPL PL | 31517521 | ARCO-CHOLAME | 018/175 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-10-29 | 2021-10-29 | [9 empty] | South | WSIP | [6 empty] | '-120.194075 | 35.7089 | ETL.8440 | 40595352 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-12-01 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119960151 | Not Scheduled | T2 DRUM-SUMMIT #1 24/289L CANCEL | 31497843 | DRUM-SUMMIT #1 | 024/289 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-10-29 | 2021-10-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.370917 | 39.3103 | ETL.1440 | 44744313 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119960194 | Q2 | T2NT EI PT 5-RND MTN #1 12/121A INS MRKS |  | PIT #5-ROUND MTN #1 | 012/121A | ICS | F | 2020_(4) TD tag on high spread line |  | 2020-10-29 | 2022-10-29 |  |  | 2021-06-18 | 2021-06-17 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.933899 | 40.8231 | ETL.5420 | 44150347 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119960245 | Q2 | T2NT EI PT 5-RND MTN #1 12/121B INS MRKS |  | PIT #5-ROUND MTN #1 | 012/121B | ICS | F | 2020_(4) TD tag on high spread line |  | 2020-10-29 | 2022-10-29 |  |  | 2021-06-18 | 2021-06-17 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.933805 | 40.8231 | ETL.5420 | 44150341 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119960248 | Q2 | T2NT EI PT 5-RND MTN #1 12/121C INS MRKS |  | PIT #5-ROUND MTN #1 | 012/121C | ICS | F | 2020_(4) TD tag on high spread line |  | 2020-10-29 | 2022-10-29 |  |  | 2021-06-18 | 2021-06-17 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.933717 | 40.8231 | ETL.5420 | 44150342 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119960562 | Not Scheduled | DI RAVENSWOOD-AMES #1 4/31 RPR OPGW | 44518199 | RAVENSWOOD-AMES #1 | 004/031 | ICS | B | 2020_(0) A and B Tags |  | 2020-10-29 | 2021-01-29 | [8 empty] | LATE | Central | WSIP |  |  |  |  | Readiness | ENV - Agency Denied Access | '-122.077318 | 37.4481 | ETL.3360 | 40812693 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 119960646 | Not Scheduled | T3 EI ROUND MTN-TABLE MTN #1 1/9 RPR GYW | 43622309 | ROUND MTN-TABLE MTN #1 | 001/009 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-29 | 2021-04-29 | [6 empty] | Tower guy | TR3 | <90D | North Valley | WSIP | [6 empty] | '-121.931017 | 40.7851 | ETL.6060 | 40868398 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119960671 | Not Scheduled | T3 EI ROUND MTN-TABLE MTN #1 1/9 RPR STR |  | ROUND MTN-TABLE MTN #1 | 001/009 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-29 | 2021-04-29 | [7 empty] | TR3 | <90D | North Valley | WSIP | [6 empty] | '-121.931017 | 40.7851 | ETL.6060 | 40868398 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119961131 | Mar | T2 EI DIABLO-MIDWAY #3 38/155 RPR STRT | 44512896 | DIABLO-MIDWAY #3 | 038/155 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-29 | 2021-10-29 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.18577 | 35.1847 | ETL.5980 | 40762135 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  | Y - 19 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119961150 | Not Scheduled | T3 EI ROUND MTN-TABLE MTN #1 1/10 RPR ST |  | ROUND MTN-TABLE MTN #1 | 001/010 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-29 | 2021-04-29 | [7 empty] | TR3 | <90D | North Valley | WSIP | [6 empty] | '-121.931547 | 40.7825 | ETL.6060 | 40601310 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119961953 | Q2 | DI STANISLAUS-NEWARK #1 83/554 RPR FOND |  | STANISLAUS-NEWARK #1 (12KV) | 083/554 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-10-22 | 2021-10-22 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | Central | WSIP | [6 empty] | '-121.741256 | 37.6555 | ETL.3850 | 41196046 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119962093 | Q2 | DI STANISLS-NWRK #2 85/555 RPLC HRDT |  | STANISLAUS-NEWARK #2 (12KV) | 085/555 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-22 | 2021-10-22 |  |  | 2021-06-19 | 2021-06-14 | [5 empty] | Central | WSIP | [6 empty] | '-121.748168 | 37.6519 | ETL.3860 | 41195973 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119963094 | Mar | DI COALINGA #1-SAN MIGUEL 4/78 RPR GYWW | 44513741 | COALINGA #1-SAN MIGUEL | 004/078 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-29 | 2021-10-29 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.406761 | 36.1022 | ETL.8580 | 40609725 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119963095 | Mar | DI COALINGA #1-SAN MIGUEL 4/78 RMV BUTT | 44513741 | COALINGA #1-SAN MIGUEL | 004/078 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-29 | 2022-10-29 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.406761 | 36.1022 | ETL.8580 | 40609725 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119964074 | Mar | T2 EI DIABLO-MIDWAY #2 39/158 RPR STRT | 44516079 | DIABLO-MIDWAY #2 | 039/158 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-30 | 2021-10-30 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.175335 | 35.1886 | ETL.5970 | 40871219 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119964345 | Q3 | T2 DI NN BRDGVLLE-CTNWD 61/443 RPL INSS | 31529414 | BRIDGEVILLE-COTTONWOOD | 061/443 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-27 | 2021-08-27 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.384407 | 40.38 | ETL.1110 | 40694255 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119964589 | Not Scheduled | T2 DI SPAULDING-SUMMIT 10/341 RPL PL | 31515501 | SPAULDING-SUMMIT | 010/341 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-10-28 | 2021-10-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.478186 | 39.3174 | ETL.8060 | 40771511 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119964846 | Q2 | T2 DI NN BRDGVLLE-CTNWD 29/248 RPL INSLW | 31515458 | BRIDGEVILLE-COTTONWOOD | 029/248 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.821798 | 40.3651 | ETL.1110 | 40795395 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119965193 | Q2 | T2 DI NN BRDGVLLE-CTNWD 29/247 RPL INSW | 31515458 | BRIDGEVILLE-COTTONWOOD | 029/247 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.819402 | 40.3653 | ETL.1110 | 40781285 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119965222 | Feb | T3 DI DRUM-RIO OSO #1 009/098 RPL INSS | 31505600 | DRUM-RIO OSO #1 | 009/098 | 93K | E | 2020_(2) High fire spread TD |  | 2020-08-25 | 2021-02-25 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 |  | North Valley | WSIP | [8 empty] | ETL.1420 | 44337147 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-28 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119965225 | Q2 | T2 NN PHILO JCT-ELK-ELK 4/2 RPR STRW | 44610684 | PHILO JCT-ELK | 004/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-06 | 2021-04-06 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.213554 | 39.0767 | ETL.7780 | 40698037 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119965434 | Feb | T2 PIT #1-HT CRK #2-BRNY A3/28 RPR SWTCH | 44586071 | PIT #1-HAT CREEK #2-BURNEY | A003/028 | ICE | B | 2020_(0) A and B Tags |  | 2020-10-30 | 2021-01-30 |  |  | 2021-02-23 | 2021-02-23 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Weather | Late due to Storm and material | '-121.550404 | 40.9609 | ETL.7040 | 43242578 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Table Mountain |  |  | YES, FERC appv'd, 1/19 JPO7 | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-25 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 119965587 | Mar | DI COALINGA #1-SAN MIGUEL 3/060 RPR INSW | 44513820 | COALINGA #1-SAN MIGUEL | 003/060 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-29 | 2021-10-29 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.389834 | 36.1084 | ETL.8580 | 40852530 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119967004 | Feb | T3 DI DESABLA-CENTERVILLE 3/35 RPL INSS | 31517691 | DESABLA-CENTERVILLE | 003/035 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-10-30 | 2021-04-30 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.639927 | 39.8261 | ETL.6720 | 42579515 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-11-10 | Released-PERTC | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119967303 | Q2 | DI GATES-PANOCHE #1 017/081 INST HRDT | 44514676 | GATES-PANOCHE #1 | 017/081 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-30 | 2021-10-30 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.29634 | 36.3412 | ETL.4720 | 40587473 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119967304 | Q2 | DI GATES-PANOCHE #1 017/081 RPR FOUND | 44514676 | GATES-PANOCHE #1 | 017/081 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-30 | 2021-10-30 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.29634 | 36.3412 | ETL.4720 | 40587473 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119967325 | Q2 | T2 NN PHILO JCT-ELK-ELK 011/007 RPL STRW | 31515022 | PHILO JCT-ELK | 011/007 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-08-25 |  |  | 2021-04-07 | 2021-04-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.324325 | 39.0241 | ETL.7780 | 40824341 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-21 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119967578 | Mar | T3 NN MORAGA-OAKLAND #1 002/021 RPR INSS | 44621679 | MORAGA-OAKLAND #1 | 002/021 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-02-28 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-122.204056 | 37.8246 | ETL.2720 | 40604473 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 14 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119967633 | Q2 | DI GATES-PANOCHE #1 19/90 RPR FOND | 44513599 | GATES-PANOCHE #1 | 019/090 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-10-30 | 2022-10-30 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.318788 | 36.3625 | ETL.4720 | 40592396 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  | Y - 16 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-03 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119967680 | Q2 | T2 DI NN BRDGVLL-CTTNWD 14/133 RPL INSW | 31515458 | BRIDGEVILLE-COTTONWOOD | 014/133 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.539223 | 40.3923 | ETL.1110 | 40784717 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119967684 | Q2 | T3 NN KONOCTI-EAGLE ROCK 002/11 RPR GYWW | 44565795 | KONOCTI-EAGLE ROCK | 002/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-02-28 |  |  | 2021-05-05 | 2021-05-05 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-122.786245 | 38.8551 | ETL.6861 | 40585194 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119967687 | Q2 | T3NT NN KONOCTI-EAGLE ROCK 2/11 RMV ANCH | 44610613 | KONOCTI-EAGLE ROCK | 002/011 | ICW | F | 2020_(3) On high spread structure |  | 2020-08-29 | 2022-10-28 |  |  | 2021-05-05 | 2021-05-05 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.786245 | 38.8551 | ETL.6861 | 40585194 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119967817 | Q2 | T3NT NN PIT #1-CTTNWD 34/295 INST MRKS |  | PIT #1-COTTONWOOD | 034/295 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-08-28 | 2022-08-28 |  |  | 2021-05-31 | 2021-05-17 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-122.01259 | 40.7028 | ETL.5390 | 40759482 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119967853 | Q2 | T2 DI NN BRDGVLL-CTTNWD 025/216 RPL INSW | 31515458 | BRIDGEVILLE-COTTONWOOD | 025/216 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.73491 | 40.3713 | ETL.1110 | 40634760 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119967857 | Q2 | T2 DI NN BRDGVLLE-CTNWD 25/217 RPL INSW | 31515458 | BRIDGEVILLE-COTTONWOOD | 025/217 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-08-26 | 2021-08-26 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.737385 | 40.3711 | ETL.1110 | 40623872 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119967876 | Q3 | T2 DI BRDGVLL-CTTNWD 064/465 RPR FIBER | 44431445 | BRIDGEVILLE-COTTONWOOD | 064/465 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-31 | 2021-08-31 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.436033 | 40.4025 | ETL.1110 | 40650429 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-16 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119967877 | Q4 | T2 NN KESWICK-TRINITY 018/238 RPR GYWW |  | KESWICK-TRINITY | 018/238 | ICW | E | 2020_(2) High fire spread TD |  | 2020-08-29 | 2021-08-29 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.707625 | 40.7229 | ETL.7270 | 40909472 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119968251 | Feb | T2 NN PHILO JCT-ELK 37/0 RPR GYWW | 44610684 | PHILO JCT-ELK | 037/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-27 | 2021-10-27 |  |  | 2021-02-11 | 2021-02-11 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.710137 | 39.1315 | ETL.7780 | 40614146 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119969859 | Q2 | DI GARBERVILLE-LAYTONVL 49/2 RPLC INSW | 31517448 | GARBERVILLE-LAYTONVILLE | 049/002 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-10-30 | 2021-10-28 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.621905 | 40.0115 | ETL.8365 | 40922355 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119970024 | Mar | T3 NN MORAGA-OAKLAND #1 002/021 RPL INSS | 31530111 | MORAGA-OAKLAND #2 | 002/021 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-02-28 | 2021-03-24 | 2021-03-26 | 2021-03-26 | 2021-03-24 |  |  |  | TR3 | SCHD | Central | WSIP | [6 empty] | '-122.203611 | 37.8253 | ETL.2730 | 40604474 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119970881 | Q2 | T2 DI SALINAS-LAURELES 12/274 RPR GYWW | 44640867 | SALINAS-LAURELES | 012/274 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-28 | 2021-10-28 |  |  | 2021-05-28 | 2021-05-24 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.752988 | 36.5526 | ETL.7930 | 40751582 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119971569 | Mar | T2 EI DIABLO-MIDWAY #2 42/171 RPR FOND | 44516079 | DIABLO-MIDWAY #2 | 042/171 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-02 | 2021-11-02 |  |  | 2021-03-31 | 2021-03-03 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.125932 | 35.2084 | ETL.5970 | 40587692 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119971736 | Q2 | DI GARBERVILLE-LAYTONVILLE 56/3 RMV DBRS | 44484408 | GARBERVILLE-LAYTONVILLE | 056/003 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-02 | 2022-11-02 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.678282 | 40.0933 | ETL.8365 | 40912625 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119971778 | Q2 | DI GARBERVILLE-LAYTONVILLE 56/3 REFRAME | 31516221 | GARBERVILLE-LAYTONVILLE | 056/003 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-11-02 | 2021-11-02 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.678282 | 40.0933 | ETL.8365 | 40912625 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-24 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119972224 | Mar | T3 DRUM-RIO OSO #2 2/25 RPR CRSL | 44523073 | DRUM-RIO OSO #2 | 002/025 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-10-30 | 2021-04-30 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [8 empty] | ETL.1430 | 44304974 | Crossarm-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119973295 | Feb | DI COALINGA #1-SAN MIGUEL 18/0 BRD STUB | 44514678 | COALINGA #1-SAN MIGUEL | 018/000 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-10-29 | 2021-10-29 |  |  | 2021-02-26 | 2021-02-15 | [5 empty] | South | WSIP | [6 empty] | '-120.574338 | 36.001 | ETL.8580 | 40594396 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119973334 | Feb | DI COALINGA #1-SAN MIGUEL 18/2 STEP BOLT | 44514678 | COALINGA #1-SAN MIGUEL | 018/002 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-10-29 | 2022-10-29 |  |  | 2021-02-26 | 2021-02-15 | [5 empty] | South | WSIP | [6 empty] | '-120.580493 | 35.9999 | ETL.8580 | 40690798 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119973678 | Q2 | DI GRBRVL-LYTNVL 55/5 RMV BUTT | 44484408 | GARBERVILLE-LAYTONVILLE | 055/005 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-11-02 | 2021-11-02 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.670963 | 40.0873 | ETL.8365 | 40912619 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119973689 | Mar | DI COALINGA #1-SAN MIGUEL 3/68 REPL HRDD | 44516114 | COALINGA #1-SAN MIGUEL | 003/068 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-29 | 2021-10-29 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.39814 | 36.1057 | ETL.8580 | 40748091 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119973712 | Not Scheduled | T2 NN DRUM SUMMIT #2 006/075 RPL INSW | 31522060 | DRUM-SUMMIT #2 | 006/075 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-10-29 | 2021-10-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.678359 | 39.3068 | ETL.1450 | 40856144 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119973861 | Not Scheduled | DI MUSTANG SW STA-GREGG 16/69 RPR SHWS | 44516144 | GATES-GREGG | 016/069 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-10-29 | 2021-10-29 | [8 empty] | WECC | South | WSIP | [6 empty] | '-119.869744 | 36.2522 | ETL.4700 | 40872013 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119973939 | Mar | DI COALINGA #1-SAN MIGUEL 9/3 RPR FOND | 44514938 | COALINGA #1-SAN MIGUEL | 009/003 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-29 | 2021-10-29 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.482904 | 36.0824 | ETL.8580 | 40663527 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119973950 | Not Scheduled | DI COALINGA #1-SAN MIGUEL 9/3 RMV DEBRIS | 44516142 | COALINGA #1-SAN MIGUEL | 009/003 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-29 | 2022-10-29 | [9 empty] | South | WSIP | [6 empty] | '-120.482904 | 36.0824 | ETL.8580 | 40663527 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119974311 | Not Scheduled | T2 EI DIABLO-MIDWAY #2 43/174 RPR GYWS |  | DIABLO-MIDWAY #2 | 043/174 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-11-02 | 2021-11-02 | [6 empty] | Tower guy | TR2 |  | South | WSIP | [6 empty] | '-120.117426 | 35.2116 | ETL.5970 | 40753891 | Guy Wire-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119974405 | Q3 | DI GATES-MUSTANG SW STA #1 3/15 RPR FOND | 44516077 | SPARE T-LINE RECORD | 003/015 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-02 | 2021-11-02 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.077199 | 36.1595 | ETL.2604 | 40751524 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119974472 | Mar | DI COALINGA #1-SAN MIGUEL 10/3 RPR FOND | 44514938 | COALINGA #1-SAN MIGUEL | 010/003 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-02 | 2021-11-02 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.49121 | 36.0713 | ETL.8580 | 40663533 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119976216 | Feb | T3 CORTINA-MENDOCINO #1 18/89 RPL INSS | 31518808 | CORTINA-MENDOCINO #1 | 018/089 | 93K | E | 2020_(2) High fire spread TD |  | 2020-11-03 | 2021-05-03 |  |  | 2021-02-18 | 2021-02-01 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.5331629 | 39.0039 | ETL.1330 | 40882662 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-02-04 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119976893 | Q2 | DI STANISLAUS-NEWARK #2 084/547 RPR FOND |  | STANISLAUS-NEWARK #2 (12KV) | 084/547 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-30 | 2021-10-30 |  |  | 2021-06-19 | 2021-06-14 | [5 empty] | Central | WSIP | [6 empty] | '-121.731212 | 37.6584 | ETL.3860 | 41196035 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119977035 | Not Scheduled | T2 NN DRUM-SUMMIT #2 18/213 RPLC INSW | 31522060 | DRUM-SUMMIT #2 | 018/213 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-10-29 | 2021-10-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.485723 | 39.3167 | ETL.1450 | 40630550 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119977564 | Not Scheduled | T2 DRUM-SUMMIT #1 24/289R CANCEL | 31497843 | DRUM-SUMMIT #1 | 024/289 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-10-29 | 2021-10-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.370917 | 39.3103 | ETL.1440 | 44744311 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119977566 | Not Scheduled | T2 DRUM-SUMMIT #1 24/289C CANCEL | 31497843 | DRUM-SUMMIT #1 | 024/289 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-10-29 | 2021-10-29 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.370917 | 39.3103 | ETL.1440 | 44744312 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119977911 | Q2 | DI GATES-PANOCHE #1 018/089A RPR FOND | 44516078 | GATES-PANOCHE #1 | 018/089A | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-10-30 | 2022-10-30 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.316523 | 36.3599 | ETL.4720 | 40576243 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119978371 | Feb | DI COALINGA #1-SAN MIGUEL 17/0 RPR STRT | 44514678 | COALINGA #1-SAN MIGUEL | 017/000 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-10-29 | 2021-10-29 |  |  | 2021-02-26 | 2021-02-15 | [5 empty] | South | WSIP | [6 empty] | '-120.557877 | 36.004 | ETL.8580 | 40609736 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119978372 | Not Scheduled | DI COALINGA #1-SAN MIGUEL 17/0 PNT STRS | 44301011 | COALINGA #1-SAN MIGUEL | 017/000 | ICS | F | 2020_(3) On high spread structure |  | 2020-10-29 | 2022-10-29 | [9 empty] | South | WSIP | [6 empty] | '-120.557877 | 36.004 | ETL.8580 | 40609736 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119978453 | Q2 | DI GATES-PANOCHE #1 17/80 RPR FOND | 44516078 | GATES-PANOCHE #1 | 017/080 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-10-30 | 2022-10-30 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.293411 | 36.3392 | ETL.4720 | 40592393 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119978456 | Q2 | DI GATES-PANOCHE #1 17/83 RPR STRT | 44516078 | GATES-PANOCHE #1 | 017/083 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-29 | 2021-10-29 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.301933 | 36.3455 | ETL.4720 | 40651606 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119978473 | Q2 | DI GRBRVLLE-LYTNVLLE 49/10 RPR STRW | 44449697 | GARBERVILLE-LAYTONVILLE | 049/010 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-02 | 2021-11-02 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.62594 | 40.0191 | ETL.8365 | 40912557 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119978474 | Q2 | DI GRBRVLLE-LYTNVLLE 49/10 RMV BUTT | 44484408 | GARBERVILLE-LAYTONVILLE | 049/010 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-11-02 | 2021-11-02 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.62594 | 40.0191 | ETL.8365 | 40912557 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119978475 | Mar | DI COALINGA #1-SAN MGL 12/3 RPR FOND | 44514938 | COALINGA #1-SAN MIGUEL | 012/003 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-03 | 2021-11-03 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.503724 | 36.0489 | ETL.8580 | 40646285 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119978682 | Q2 | DI GATES-PANOCHE #1 20/92 REM STP BLTS | 44516078 | GATES-PANOCHE #1 | 020/092 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-10-30 | 2022-10-30 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.323331 | 36.3675 | ETL.4720 | 40663947 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119978685 | Q2 | DI GATES-PANOCHE #1 20/92 RPR FOND | 44516078 | GATES-PANOCHE #1 | 020/092 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-10-30 | 2022-10-30 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.323331 | 36.3675 | ETL.4720 | 40663947 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119979350 | Not Scheduled | DI NEWARK-JARVIS #1 10/63 RPLC INSS | 31529487 | NEWARK-JARVIS #1 | 010/063 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-10-30 | 2021-10-30 | [9 empty] | Central | WSIP | [6 empty] | '-121.951375 | 37.5844 | ETL.3020 | 40671455 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119979475 | Q2 | DI GATES-PANOCHE #1 15/71 RPR STRT | 44516078 | GATES-PANOCHE #1 | 015/071 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-30 | 2021-10-30 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.267847 | 36.3208 | ETL.4720 | 40587471 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119979547 | Not Scheduled | T2NT EI MALN-RND MTN #2 92/470 INST MRKS |  | MALIN-ROUND MTN #2 | 092/471 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-11-03 | 2022-11-03 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.912107 | 40.8289 | ETL.6020 | 40605581 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119980885 | Feb | DI IGNCIO-ALTO-SAUSLTO #1 9/64 RPR STRT | 44516787 | IGNACIO-ALTO-SAUSALITO #1 | 009/064 | ICQ | B | 2020_(0) A and B Tags |  | 2020-11-03 | 2021-02-01 |  |  | 2021-02-05 | 2021-02-01 |  |  |  |  | LATE | North Coast | WSIP |  |  |  |  | Readiness |  | '-122.504289 | 37.9448 | ETL.7160 | 40877698 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End Before Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 119981888 | Q2 | T3 DI WEIMAR #1 12/174L RPL POLE | 31517853 | WEIMAR #1 | 012/174 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-02-25 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [8 empty] | ETL.7560 | 44414808 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119982090 | Q2 | T3 DI WEIMAR #1 12/174R RPL POLE | 31517853 | WEIMAR #1 | 012/174 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-08-25 | 2021-02-25 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 | SCHD | North Valley | WSIP | [8 empty] | ETL.7560 | 44414810 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119982983 | Mar | DI COALINGA #1-SAN MIGUEL 5/8 BRD STUB | 44516101 | COALINGA #1-SAN MIGUEL | 005/008 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-29 | 2021-10-29 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.4303 | 36.0978 | ETL.8580 | 40873866 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119983305 | Not Scheduled | T2 EI DIABLO-MIDWAY #3 40/161 RPR GYWS |  | DIABLO-MIDWAY #3 | 040/161 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-11-02 | 2021-11-02 | [6 empty] | Tower guy | TR2 |  | South | WSIP | [6 empty] | '-120.165603 | 35.1937 | ETL.5980 | 40593583 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 19 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-12 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119983371 | Not Scheduled | EI DIABLO-MIDWAY #3 45/186 RPR GYWS |  | DIABLO-MIDWAY #3 | 045/186 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-11-03 | 2021-11-03 | [6 empty] | Tower guy |  |  | South | WSIP | [6 empty] | '-120.072437 | 35.2277 | ETL.5980 | 40808234 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - Prog 404 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119983662 | Q2 | DI GARBERVILLE-LAYTONVILLE 55/4 RPR GYWW | 44518352 | GARBERVILLE-LAYTONVILLE | 055/004 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-02 | 2021-11-02 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.669336 | 40.086 | ETL.8365 | 43590411 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119983807 | Not Scheduled | DI SBRNTE-GRZLY-CLRMNT #2 2/23 PNT STRS | 44586183 | SOBRANTE-GRIZLY-CLARMNT #2+ | 002/023 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-30 | 2022-10-30 | [9 empty] | Central | WSIP | [6 empty] | '-122.183663 | 37.8769 | ETL.3750 | 40872284 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119983809 | Q2 | DI SBRNTE-GRZLY-CLRMNT #2 2/23 RPR STRT |  | SOBRANTE-GRIZLY-CLARMNT #2+ | 002/023 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-30 | 2021-10-30 |  |  | 2021-05-08 | 2021-05-03 | [5 empty] | Central | WSIP | [6 empty] | '-122.183663 | 37.8769 | ETL.3750 | 40872284 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 14 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-05 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119983866 | Q3 | DI GATES-MUSTANG SS #1 4/21 RPR STRT | 44518240 | SPARE T-LINE RECORD | 004/021 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-02 | 2021-11-02 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.051672 | 36.1689 | ETL.2604 | 40581381 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119983883 | Q3 | DI BRDGEVL-GARBRVIL 031/002 RPL STRW | 31513483 | BRIDGEVILLE-GARBERVILLE | 031/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-11-02 | 2021-11-02 | 2021-08-30 | 2021-09-01 | 2021-09-01 | 2021-08-30 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.708473 | 40.1126 | ETL.6220 | 40698342 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2020-12-04 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119983888 | Q2 | DI GATES - PANOCHE #1 012/060 RPR STRT | 44565367 | GATES-PANOCHE #1 | 012/060 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-10-30 | 2021-10-30 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.244748 | 36.2929 | ETL.4720 | 40592387 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119983952 | Mar | DI COALINGA #1-SAN MIGUEL 10/2 REP FOND | 44518178 | COALINGA #1-SAN MIGUEL | 010/002 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-02 | 2021-11-02 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.489951 | 36.0736 | ETL.8580 | 40690786 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119984285 | Not Scheduled | T2 MALIN-ROUND MTN #2 76/389 BENT STEEL |  | MALIN-ROUND MTN #2 | 076/389 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-04 | 2021-11-04 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.877702 | 41.0486 | ETL.6020 | 40862229 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119984286 | Not Scheduled | T2 MALIN-ROUND MTN #2 76/388 BENT STEEL |  | MALIN-ROUND MTN #2 | 076/388 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-04 | 2021-11-04 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.875852 | 41.0505 | ETL.6020 | 40862527 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119984316 | Not Scheduled | T2 MALIN-ROUND MTN #2 77/392 BENT STEEL |  | MALIN-ROUND MTN #2 | 077/392 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-04 | 2021-11-04 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.884255 | 41.0417 | ETL.6020 | 40682646 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119985596 | Not Scheduled | T2 EI TRINITY-MAPLE CREEK 016/003A RMV V |  | TRINITY-MAPLE CREEK | 016/003A | HNA | E | 2020_(4b) On structure in bucket 4 | Budget Owner (Veg/Land/Road) | 2020-11-05 | 2021-11-05 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.19517 | 40.7388 | ETL.8170 | 44948567 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119985609 | Not Scheduled | T2 EI TRINITY-MAPLE CREEK 16/003C RMV VE |  | TRINITY-MAPLE CREEK | 016/003C | HNA | E | 2020_(4b) On structure in bucket 4 | Budget Owner (Veg/Land/Road) | 2020-11-05 | 2021-11-05 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-123.195171 | 40.7387 | ETL.8170 | 44948568 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119985610 | Q2 | T2 EI TRINITY-MAPLE CREEK 16/003A RPL PL | 31418582 | TRINITY-MAPLE CREEK | 016/003A | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-11-05 | 2021-11-05 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.19517 | 40.7388 | ETL.8170 | 44948567 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119985645 | Q2 | T2 EI TRINITY-MAPLE CREEK 16/003C RPL PL | 31418582 | TRINITY-MAPLE CREEK | 016/003C | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-11-05 | 2021-11-05 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.195171 | 40.7387 | ETL.8170 | 44948568 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119985818 | Q2 | EI T3NT IGNACIO-BOLINAS_009/104 RPR STRW | 44640733 | IGNACIO-BOLINAS #1 | 009/104 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-05 | 2022-11-05 |  |  | 2021-05-17 | 2021-05-04 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.657464 | 37.9899 | ETL.7140 | 44942596 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119985910 | Mar | WV T2 CLEAR LAKE-HOPLAND 9/004 RPR DMPS | 44611090 | CLEAR LAKE-HOPLAND | 009/004 | ICS | E | 2020_(2) High fire spread TD |  | 2020-11-05 | 2021-11-05 |  |  | 2021-03-30 | 2021-03-30 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.92103 | 38.9944 | ETL.6390 | 45004738 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119986736 | Q2 | DI GATES-PANOCHE #1 43/207 RPR FOND | 44565805 | GATES-PANOCHE #1 | 043/207 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-03 | 2021-11-03 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.582961 | 36.6526 | ETL.4720 | 40805534 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119986782 | Not Scheduled | DI GATES-PANOCHE #1 43/207 RPR GYWS | 44569049 | GATES-PANOCHE #1 | 043/207 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-11-03 | 2021-11-03 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.582961 | 36.6526 | ETL.4720 | 40805534 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119986897 | Not Scheduled | DI GATES-PANOCHE #2 43/207A RPR GYWS | 44569048 | GATES-PANOCHE #2 | 043/207A | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-11-03 | 2021-11-03 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.582789 | 36.6525 | ETL.4730 | 44190882 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119987216 | Q2 | WV T3 IGNACIO-BOLINAS #1 13/142 RPL DMP | 44640733 | IGNACIO-BOLINAS #1 | 013/142A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-05 | 2021-05-05 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.698427 | 37.9419 | ETL.7140 | 40770901 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119987237 | Q2 | WV T3 IGNACIO-BOLINAS #1 13/145 RPL DMP | 44640733 | IGNACIO-BOLINAS #1 | 013/145 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-05 | 2021-05-05 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.7027 | 37.9427 | ETL.7140 | 40576063 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119987323 | Q2 | WV T3 IGNACIO-BOLINAS #1 13/144 RPL DMP | 44640733 | IGNACIO-BOLINAS #1 | 013/144 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-05 | 2021-05-05 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.701127 | 37.9424 | ETL.7140 | 40809056 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119987669 | Q2 | EI T3 IGNCIO-BLNS CENTER 010/111 RPR GWR | 44640733 | IGNACIO-BOLINAS #1 | 010/111 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-05 | 2021-05-05 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.660207 | 37.9765 | ETL.7140 | 44942599 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119987702 | Q2 | EI T3 IGNCIO-BLNS RIGHT 010/111 RPR GWR | 44640733 | IGNACIO-BOLINAS #1 | 010/111 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-05 | 2021-05-05 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.660207 | 37.9765 | ETL.7140 | 44942600 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119987704 | Q2 | EI T3 IGNCIO-BLNS LEFT 010/111 RPR GWR | 44640733 | IGNACIO-BOLINAS #1 | 010/111 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-05 | 2021-05-05 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.660207 | 37.9765 | ETL.7140 | 44942598 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119987849 | Q3 | DI GATES-MUSTANG SW STA #1 4/19 RPR STRT | 44518240 | SPARE T-LINE RECORD | 004/019 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-02 | 2021-11-02 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-120.060368 | 36.1657 | ETL.2604 | 40858218 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119987905 | Q2 | DI GARBERVILLE-LAYTONVILLE 58/2 RPL INSW | 31518255 | GARBERVILLE-LAYTONVILLE | 058/002 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-10-30 | 2021-10-30 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.8365 | 40922464 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119987923 | Not Scheduled | T2 MALIN-ROUND MTN #2 92/471 BENT STEEL |  | MALIN-ROUND MTN #2 | 092/472 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-05 | 2021-11-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.914346 | 40.8272 | ETL.6020 | 40592656 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119988047 | Mar | DI COALING #1 SN MIGUEL 012/004 RPR STRS | 44518178 | COALINGA #1-SAN MIGUEL | 012/004 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-04 | 2021-11-04 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.504159 | 36.0468 | ETL.8580 | 40748097 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119988048 | Mar | DI COALING #1 SN MIGUEL 012/004 RPR FOND | 44518178 | COALINGA #1-SAN MIGUEL | 012/004 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-04 | 2021-11-04 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.504159 | 36.0468 | ETL.8580 | 40748097 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119988375 | Q3 | T2 DI CARIBOU #2 ;001/023 RMV PL BUTT |  | CARIBOU #2 | ;001/023 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-11-04 | 2021-11-04 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.960272 | 40.003 | ETL.6280 | 40666871 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119989337 | Mar | DI COALINGA #1-SAN MIGUEL 13/1 RPR FOND | 44518178 | COALINGA #1-SAN MIGUEL | 013/001 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-03 | 2021-11-03 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.50605 | 36.0369 | ETL.8580 | 40597697 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119989338 | Not Scheduled | DI COALINGA #1-SAN MIGUEL 13/1 RMV BUTT | 44565948 | COALINGA #1-SAN MIGUEL | 013/001 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-04 | 2022-11-04 | [9 empty] | South | WSIP | [6 empty] | '-120.50605 | 36.0369 | ETL.8580 | 40597697 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119989339 | Not Scheduled | DI COALINGA #1-SAN MIGUEL 13/1 PNT STRS | 44565948 | COALINGA #1-SAN MIGUEL | 013/001 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-04 | 2022-11-04 | [9 empty] | South | WSIP | [6 empty] | '-120.50605 | 36.0369 | ETL.8580 | 40597697 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119989418 | Q2 | DI GARBRVLLE-LAYTNVLE 50/6 RPR GYWW | 44542681 | GARBERVILLE-LAYTONVILLE | 050/006 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-02 | 2021-11-02 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.632302 | 40.0275 | ETL.8365 | 40912564 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119989699 | Q3 | DI BRDGVL-GRBRVL 024/008 RPR GYWW | 44542334 | BRIDGEVILLE-GARBERVILLE | 024/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-10-30 | 2021-10-30 |  |  | 2021-08-28 | 2021-08-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.71282 | 40.202 | ETL.6220 | 40876474 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119990113 | Q2 | DI STANISLAUS-NEWARK #1 92/612 RPR STRS |  | STANISLAUS-NEWARK #1 (12KV) | 092/612 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-11-06 | 2021-11-06 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | Central | WSIP | [6 empty] | '-121.873289 | 37.5834 | ETL.3850 | 40702976 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119990428 | Q2 | DI GRBRVILLE-LYTNVILLE 55/3 RMV PL BUTT | 44572981 | GARBERVILLE-LAYTONVILLE | 055/003 | ICW | F | 2020_(3) On high spread structure |  | 2020-11-06 | 2022-11-06 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.667415 | 40.0844 | ETL.8365 | 43590410 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119992061 | Q2 | T2 DI HATCREEK #1-WESTWD 16/311 RPR SHLW |  | HAT CREEK #1-WESTWOOD | 016/311 | ICW | F | 2020_(4) TD tag on high spread line |  | 2020-10-05 | 2022-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.325353 | 40.783 | ETL.7030 | 42625077 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-23 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119992540 | Not Scheduled | T3NT DI MIDDLEFORK #1 009/126 RMV DBRS | 44543336 | MIDDLE FORK #1 | 009/126 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-03 | 2022-11-03 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.737811 | 39.0039 | ETL.8405 | 40619304 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119992691 | Mar | T2 DI DRUM-RIO OSO #2 14/123 RPLC INSS | 31503652 | DRUM-RIO OSO #2 | 014/123 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-11-06 | 2021-11-06 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.979874 | 39.1518 | ETL.1430 | 40680547 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119992772 | Mar | DI COALINGA #1-SAN MIGUEL 12/6 RPR FOND | 44518178 | COALINGA #1-SAN MIGUEL | 012/006 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-04 | 2021-11-04 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.505459 | 36.0402 | ETL.8580 | 40823403 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119992965 | Not Scheduled | DI SPAULDING-SUMMIT 9/309 RPR GYWW | 44543327 | SPAULDING-SUMMIT | 009/309 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-04 | 2021-11-04 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.493589 | 39.3146 | ETL.8060 | 44349532 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119993531 | Mar | DI COALNGA #1-SAN MIGUEL 13/003 RPR FOND | 44518178 | COALINGA #1-SAN MIGUEL | 013/003 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-04 | 2021-11-04 |  |  | 2021-03-19 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.50713 | 36.032 | ETL.8580 | 40663531 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119993532 | Not Scheduled | DI COALNGA #1-SAN MIGUEL 13/003 RMV BUTT | 44565948 | COALINGA #1-SAN MIGUEL | 013/003 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-04 | 2022-11-04 | [9 empty] | South | WSIP | [6 empty] | '-120.50713 | 36.032 | ETL.8580 | 40663531 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119994461 | Not Scheduled | DI GATES-PANOCHE #1 26/125 RPL INSS | 31527142 | GATES-PANOCHE #2 | 026/125 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-11-04 | 2021-11-04 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.398263 | 36.4499 | ETL.4730 | 40782369 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119994462 | Q2 | DI GATES-PANOCHE #1 32/156 RPR STRT | 44565367 | GATES-PANOCHE #1 | 032/156 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-04 | 2021-11-04 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.4718 | 36.525 | ETL.4720 | 40811803 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119994563 | Feb | DI COALINGA #1-SAN MIGUEL 16/2 RPR FOND | 44518178 | COALINGA #1-SAN MIGUEL | 016/002 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-11-03 | 2021-11-03 |  |  | 2021-02-26 | 2021-02-15 | [5 empty] | South | WSIP | [6 empty] | '-120.54436 | 36.0065 | ETL.8580 | 40690794 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119995046 | Q2 | T3NT DI TGER CREEK-ELECTRA 4/35 RPR FOND |  | TIGER CREEK-ELECTRA | 004/035 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-11-05 | 2022-11-05 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.564071 | 38.4289 | ETL.5780 | 40752888 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-23 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119995105 | Not Scheduled | T2NT NN DRUM-SUMMIT #2 18/223 RMV DEBRIS | 44543333 | DRUM-SUMMIT #2 | 018/223 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-05 | 2022-10-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.470923 | 39.3186 | ETL.1450 | 44553897 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119995122 | Q2 | DI GATES-PANOCHE #1 40/193 RPR FOND | 44565367 | GATES-PANOCHE #1 | 040/193 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-11-06 | 2022-11-06 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.552011 | 36.6188 | ETL.4720 | 40651620 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119995179 | Q2 | T3NT DI SBNT-GZLY-CLMNT#2 6/42 RPR FOND | 44326313 | SOBRANTE-GRIZLY-CLARMNT #2+ | 006/042 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-10-02 | 2022-10-02 |  |  | 2021-05-08 | 2021-05-03 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.208075 | 37.852 | ETL.3750 | 40857842 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119995299 | Q2 | T2 DI GATES-PANOCHE #1 037/172 RMV DEBRI |  | HAT CREEK #1-WESTWOOD | 014/276 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-05 | 2022-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.349582 | 40.8025 | ETL.7030 | 40770724 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119995441 | Q2 | T2 DI HAT CRK#1-WESTWD 16/324 RMV PL BUT |  | HAT CREEK #1-WESTWOOD | 016/324 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-05 | 2022-10-05 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.316375 | 40.7757 | ETL.7030 | 40770732 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119995442 | Not Scheduled | T2 DI SPAULDING-SUMMIT 15/485 RMV DEBRIS | 44543419 | SPAULDING-SUMMIT | 015/485 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-01 | 2022-10-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.387676 | 39.3284 | ETL.8060 | 40826237 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119995615 | Q3 | T2NT DI CARIBOU #2 14/18 RMV BUTT |  | CARIBOU #2 | 014/018 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-05 | 2022-10-05 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.117633 | 40.026 | ETL.6280 | 40876625 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119995638 | Not Scheduled | DI GATES-PANOCHE #1 035/167 RMV DEBRIS | 44565940 | GATES-PANOCHE #1 | 035/167 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-10-01 | 2022-10-01 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.497311 | 36.552 | ETL.4720 | 40811182 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119995699 | Not Scheduled | DI GATES-PANOCHE #1 036/170 RMV DEBRIS | 44565940 | GATES-PANOCHE #1 | 036/170 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-10-01 | 2022-10-01 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.503573 | 36.5598 | ETL.4720 | 40592417 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119995795 | Not Scheduled | T2 MALIN-ROUND MTN #2 93/474 RPR STRT |  | MALIN-ROUND MTN #2 | 093/475 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-07 | 2021-11-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.922104 | 40.8203 | ETL.6020 | 40759952 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119995796 | Not Scheduled | T2 MALIN-ROUND MTN #2 72/364 RPR STRT |  | MALIN-ROUND MTN #2 | 072/364 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-06 | 2021-11-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.800247 | 41.076 | ETL.6020 | 40759867 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119995813 | Q2 | DI GATES-PANOCHE #1 43/204 RPR FOND | 44518250 | GATES-PANOCHE #1 | 043/204 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-10-02 | 2022-10-02 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.577349 | 36.6465 | ETL.4720 | 40753596 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 119995946 | Not Scheduled | T3NT DI FLTN-CALISTOGA :9/1 RMV DEBRIS | 44597303 | FULTON-CALISTOGA | :009/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-06 | 2022-10-06 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.604302 | 38.7132 | ETL.6880 | 40905738 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119996778 | Not Scheduled | T2 MALIN-ROUND MTN #2 72/363A RPR GYWS | 44408444 | MALIN-ROUND MTN #2 | 072/363A | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-11-06 | 2021-11-06 | [6 empty] | Tower guy | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.799005 | 41.0768 | ETL.6020 | 40576662 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119999249 | Q2 | T2 EI MLIN-RND MNTAIN #2 80/409 RPL INSS | 31527915 | MALIN-ROUND MTN #2 | 080/409 | 93K | E | 2020_(1b) Lines with special commitments |  | 2019-04-26 | 2020-04-26 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.898443 | 40.9975 | ETL.6020 | 40891288 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119999462 | Q3 | T3 NN DONNELLS-MI-WUK 12/8 RPR GYWW | 44623691 | DONNELLS-CURTIS | 012/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-01-28 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.143302 | 38.1048 | ETL.1400 | 44986666 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119999467 | Q3 | T3 NN DONNELLS-MI-WUK 12/8 RPR GYWW | 44623692 | DONNELLS-CURTIS | 012/008 | ICW | E | 2020_(2) High fire spread TD |  | 2020-07-28 | 2021-01-28 |  |  | 2021-09-07 | 2021-08-07 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.143302 | 38.1048 | ETL.1400 | 44986667 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 119999767 | Not Scheduled | T2 EI MALIN-ROUND MTN #2 72/365A RPR GYW | 44408444 | MALIN-ROUND MTN #2 | 072/365A | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-11-09 | 2021-11-09 | [6 empty] | Tower guy | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.80439 | 41.0737 | ETL.6020 | 40576663 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120000626 | Not Scheduled | EI LAYTONVILLE-COVELO 13/006 RPL PL | 31518250 | LAYTONVILLE-COVELO | 013/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-11-09 | 2021-11-09 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.265621 | 39.7586 | ETL.7390 | 40808783 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2021-01-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120001736 | Not Scheduled | DI VCA-VACVILL-JMSN-NTH 23/162 RPL INSS |  | VACA-VACAVILLE-JAMESON-NTH TWR | 023/162 | 93K | E | 2020_(2) High fire spread TD |  | 2020-11-06 | 2021-11-06 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.170377 | 38.1436 | ETL.4100 | 40622151 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120001737 | Q2 | DI IGNACIO-MRE ISLAND #2 23/162 RPL INSS | 31527362 | IGNACIO-MARE ISLAND #2 | 023/162 | 93K | E | 2020_(2) High fire spread TD |  | 2020-11-06 | 2021-11-06 |  |  | 2021-06-03 | 2021-06-02 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.170377 | 38.1436 | ETL.1840 | 40622154 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120001839 | Not Scheduled | DI CARIBOU-PALERMO 4/40 RPR SHLS |  | CARIBOU-PALERMO | 004/040 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-11-05 | 2021-11-05 | [9 empty] | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539982 | 39.5184 | ETL.3190 | 40599251 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120001872 | Q2 | T2 EI MLN-RND MNT #2-TWR 82/416 RPL INSL | 31527915 | MALIN-ROUND MTN #2 | 082/416 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-11-09 | 2021-11-09 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.909148 | 40.9791 | ETL.6020 | 40845626 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120007297 | Mar | T3 EI GEYSERS #3-CLOVERDAL 5/68 RPL POLE | 31518652 | GEYSERS #3-CLOVERDALE | 005/068 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-11-09 | 2021-05-09 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.91411 | 38.815 | ETL.1650 | 40603859 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-15 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120007300 | Mar | T3 EI GEYSERS #3-CLOVERDAL 6/72 RPR GYWW | 44580898 | GEYSERS #3-CLOVERDALE | 006/072 | ICS | E | 2020_(2) High fire spread TD |  | 2020-11-09 | 2021-05-09 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.919384 | 38.8126 | ETL.1650 | 44398443 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120007386 | Mar | T2 DI SBRNT-GRZLY-CLRMNT#2 7/51 RPR JUMS | 44621450 | SOBRANTE-GRIZLY-CLARMNT #2+ | 007/051 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-11-10 | 2021-11-10 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.2282 | 37.8476 | ETL.3750 | 40804878 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120007483 | Not Scheduled | T2 DI SBRNT-GRZLY-CLRMNT#1 6/54 RPR JUMP |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 006/054 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-11-10 | 2021-11-10 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-122.228018 | 37.8479 | ETL.3740 | 40580980 | Jumper-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-03 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120008394 | Mar | T3 EI GEYSERS #3-CLOVERDALE 4/53 REPLUMB | 44580896 | GEYSERS #3-CLOVERDALE | 004/053 | ICW | E | 2020_(2) High fire spread TD |  | 2020-11-10 | 2021-05-10 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.8863705 | 38.8116 | ETL.1650 | 40792130 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120009179 | Not Scheduled | T2 STAN-MEL SS-MAN #1 11/67 BENT STEEL | 44631702 | STANISLAUS-MELONES SS-MANTECA #1+ | 011/067 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-10 | 2021-11-10 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.541885 | 38.0558 | ETL.3830 | 40803318 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120009336 | Mar | T3 EI GYSRS #3-CLVRDLE-WD 04/55 RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 004/055 | ICW | E | 2020_(2) High fire spread TD |  | 2020-11-10 | 2021-05-10 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.8880772 | 38.8121 | ETL.1650 | 44298327 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120009393 | Mar | T3 EI GYSRS #3-CLVRDLE-WD 04/55 RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 004/055 | ICW | E | 2020_(2) High fire spread TD |  | 2020-11-10 | 2021-05-10 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.8880772 | 38.8121 | ETL.1650 | 44298329 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120009394 | Mar | T3 EI GYSRS #3-CLVRDLE-WD 04/55 RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 004/055 | ICW | E | 2020_(2) High fire spread TD |  | 2020-11-10 | 2021-05-10 |  |  | 2021-03-27 | 2021-03-08 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.8880772 | 38.8121 | ETL.1650 | 44298328 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120009410 | Q2 | WV HUMBOLDT-BRIDGEVILLE 96/1 INST DAMP |  | HUMBOLDT-BRIDGEVILLE | 096/001 | ICS | E | 2020_(2) High fire spread TD |  | 2020-11-10 | 2021-11-10 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.85549 | 40.6101 | ETL.1810 | 44322372 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120009421 | Q2 | WV HUMBOLDT-BRIDGEVILLE 96/1 INST MRKS |  | HUMBOLDT-BRIDGEVILLE | 096/001 | ICS | F | 2020_(3) On high spread structure |  | 2020-11-10 | 2022-11-10 |  |  | 2021-05-22 | 2021-05-03 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.85549 | 40.6101 | ETL.1810 | 44322372 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120010042 | Q2 | T2 EI MLN-RND MTN #2-TWR 74/374 RPL INSS | 31527915 | MALIN-ROUND MTN #2 | 074/374 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-11-10 | 2021-11-10 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.833102 | 41.07 | ETL.6020 | 40790047 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120011402 | Not Scheduled | T2 MALIN-ROUND MTN #2 72/367A RPR FOND |  | MALIN-ROUND MTN #2 | 072/367A | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-05 | 2021-11-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.809236 | 41.0711 | ETL.6020 | 40576756 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120011403 | Not Scheduled | T2 MALIN-ROUND MTN #2 72/367A BENT STEEL |  | MALIN-ROUND MTN #2 | 072/367A | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-05 | 2021-11-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.809236 | 41.0711 | ETL.6020 | 40576756 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120011406 | Not Scheduled | T2 MALIN-ROUND MTN #2 71/361 RPR STRT |  | MALIN-ROUND MTN #2 | 071/361 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-06 | 2021-11-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.794968 | 41.0797 | ETL.6020 | 40595123 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120011407 | Not Scheduled | T2 EI MALIN-ROUND MTN #2 72/367 RPR STRT |  | MALIN-ROUND MTN #2 | 072/367 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-05 | 2021-11-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.808172 | 41.0716 | ETL.6020 | 40819382 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120011408 | Not Scheduled | T2 MALIN-ROUND MTN #2 73/370 RPR STRT |  | MALIN-ROUND MTN #2 | 073/370 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-09 | 2021-11-09 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.814937 | 41.0702 | ETL.6020 | 40601181 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120011410 | Not Scheduled | T2 MALIN-ROUND MTN #2 71/361 RPR GYWS | 44408444 | MALIN-ROUND MTN #2 | 071/361 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-11-06 | 2021-11-06 | [6 empty] | Tower guy | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.794968 | 41.0797 | ETL.6020 | 40595123 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120011411 | Not Scheduled | T2 MALIN-ROUND MTN #2 93/475 RPR STRT |  | MALIN-ROUND MTN #2 | 093/476 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-07 | 2021-11-07 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.924358 | 40.8183 | ETL.6020 | 40759704 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120011412 | Q2 | T2 MALIN-ROUND MTN #2 72/367 RPR ANCHS | 44408444 | MALIN-ROUND MTN #2 | 072/367 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-11-05 | 2021-11-05 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.808172 | 41.0716 | ETL.6020 | 40819382 | Anchor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120011413 | Not Scheduled | T2 EI MALIN-ROUND MTN #2 72/367 RPR STRT |  | MALIN-ROUND MTN #2 | 072/367 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-05 | 2021-11-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.808172 | 41.0716 | ETL.6020 | 40819382 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120011414 | Not Scheduled | T2 MALIN-ROUND MTN #2 71/362B RPR STRT |  | MALIN-ROUND MTN #2 | 071/362B | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-06 | 2021-11-06 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.797676 | 41.0777 | ETL.6020 | 40740258 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120012222 | Feb | GIFFEN TAP 2/008 RPR POLE | 44565489 | GIFFEN TAP | 002/008 | ICW | B | 2020_(0) A and B Tags |  | 2020-11-11 | 2021-02-11 | 2021-02-11 | 2021-02-11 | 2021-02-11 | 2021-02-11 |  |  |  |  | LATE | South | WSIP | [6 empty] | '-120.334323 | 36.5813 | ETL.8985 | 40872650 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | No | Currently Past Due | Scheduled End Before Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-11-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120012431 | Q2 | T3 RND MTN-TABL MTN #2 23/115 RPR STRT |  | ROUND MTN-TABLE MTN #2 | 023/115 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-11-11 | 2021-05-11 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.94745 | 40.4765 | ETL.6070 | 40760720 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120012438 | Q2 | T3 RND MTN-TABL MTN #1 23/115 RPR STRT | 43622309 | ROUND MTN-TABLE MTN #1 | 023/115 | ICS | E | 2020_(2) High fire spread TD |  | 2020-11-11 | 2021-05-11 |  |  | 2021-05-13 | 2021-04-01 |  |  | Likely MAT error - delink to correct | TR3 |  | North Valley | WSIP | [6 empty] | '-121.947992 | 40.4765 | ETL.6060 | 40759734 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120012484 | Not Scheduled | T2 WV SPAULDING-SUMMIT 2/088 RPR STRS | 44543326 | SPAULDING-SUMMIT | 002/088 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-11-11 | 2021-11-11 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.60884 | 39.3119 | ETL.8060 | 40618174 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120013080 | Not Scheduled | DI STANISLAUS-NEWARK #1 92/611 RPLC INSS | 31530187 | STANISLAUS-NEWARK #1 (12KV) | 092/611 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-11-06 | 2021-11-06 | [9 empty] | Central | WSIP | [6 empty] | '-121.869773 | 37.5865 | ETL.3850 | 40629671 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120013257 | Feb | DI COALINGA #1-SAN MIGUEL 18/3 BRD STUB | 44565369 | COALINGA #1-SAN MIGUEL | 018/003 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-11-10 | 2021-11-10 |  |  | 2021-02-26 | 2021-02-15 | [5 empty] | South | WSIP | [6 empty] | '-120.584578 | 35.9991 | ETL.8580 | 40652834 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120013479 | Q2 | DI GATES-PANOCHE #1 026/123 RPR FOND | 44565367 | GATES-PANOCHE #1 | 026/123 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-11-10 | 2022-11-10 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.393684 | 36.4449 | ETL.4720 | 40651610 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120013734 | Not Scheduled | DI GATES-PANOCHE #1 13/61 RPLC INSS | 31527143 | GATES-PANOCHE #1 | 013/061 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-11-09 | 2021-11-09 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.246106 | 36.2947 | ETL.4720 | 40620941 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120013940 | Not Scheduled | T2 MALIN-ROUND MTN #2 90/460 RPR STRT |  | MALIN-ROUND MTN #2 | 090/460 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-12 | 2021-11-12 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.916186 | 40.8563 | ETL.6020 | 40601283 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120014260 | Q3 | T2 EI CARIBOU-WESTWOOD 1/35 RPL HRDW |  | CARIBOU-WESTWOOD | 001/035 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-12 | 2021-11-12 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.127156 | 40.0998 | ETL.6300 | 44942285 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-23 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120014272 | Q3 | EI CARIBOU-WESTWOOD 1/035 RPL HRDW |  | CARIBOU-WESTWOOD | 001/035 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-11-12 | 2021-11-12 |  |  | 2021-08-27 | 2021-08-16 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.127156 | 40.0998 | ETL.6300 | 44942284 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-23 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120014585 | Q3 | DI GATES-MSTANG SW STA #1 12/50 RPR FOND | 44565637 | SPARE T-LINE RECORD | 012/050 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-11-09 | 2022-11-09 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-119.936642 | 36.2231 | ETL.2604 | 40582483 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120014637 | Not Scheduled | DI GATES-MUSTANG #1 12/52 RPR CONS | 44565951 | SPARE T-LINE RECORD | 012/052 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-11-09 | 2021-11-09 | [9 empty] | South | WSIP | [6 empty] | '-119.928625 | 36.227 | ETL.2604 | 40647638 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120014751 | Q3 | DI GATES-MUSTANG #2 12/52 RPR FOND | 44565637 | SPARE T-LINE RECORD | 012/052 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-11-09 | 2022-11-09 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-119.928625 | 36.227 | ETL.2604 | 40647638 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120015079 | Not Scheduled | DI VCA-VCAVLLE-JMSN-NRTH 24/167 RPL INSS |  | VACA-VACAVILLE-JAMESON-NTH TWR | 024/167 | 93K | E | 2020_(2) High fire spread TD |  | 2020-11-06 | 2021-11-06 | [9 empty] | North Coast | WSIP | [6 empty] | '-122.178861 | 38.1309 | ETL.4100 | 40773355 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120015108 | Q2 | DI IGNACIO-MRE ISLAND #2 24/167 RPL INSS | 31527362 | IGNACIO-MARE ISLAND #2 | 024/167 | 93K | E | 2020_(2) High fire spread TD |  | 2020-11-06 | 2021-11-06 |  |  | 2021-06-03 | 2021-06-02 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.178206 | 38.1318 | ETL.1840 | 44985759 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120016301 | Not Scheduled | DI GATES-PANOCHE #1 009/047 INS MRKS |  | GATES-PANOCHE #1 | 009/047 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-11-09 | 2022-11-09 | [8 empty] | WECC | South | WSIP |  |  |  | REJECT: Crew reported work not needed. Please confirm(approve) or reject if disagree. The danger signs are too low per "" SAP before photos"". Need to move/install the danger signs higher. |  |  | '-120.218219 | 36.2588 | ETL.4720 | 40818930 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  | Reject | 2020-11-23 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120016303 | Q2 | DI GATES-PANOCHE #1 009/047 RPR FOND | 44571495 | GATES-PANOCHE #1 | 009/047 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-11-09 | 2022-11-09 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.218219 | 36.2588 | ETL.4720 | 40818930 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120016306 | Q2 | DI GATES-PANOCHE #1 009/047 BENT STEEL | 44571495 | GATES-PANOCHE #1 | 009/047 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-09 | 2021-11-09 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.218219 | 36.2588 | ETL.4720 | 40818930 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120018556 | Mar | T3 DI SBRNT-GRZLY-CLRT #1 4/38C RPL INSS |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 004/038C | 93K | E | 2020_(2) High fire spread TD |  | 2020-11-10 | 2021-05-10 | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-03-18 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.18503 | 37.8528 | ETL.3740 | 42582023 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-13 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120018628 | Q2 | DI GATES-PANOCHE #1 26/124 RPR FOND | 44565367 | GATES-PANOCHE #1 | 026/124 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-11-12 | 2022-11-12 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.395972 | 36.4474 | ETL.4720 | 40753585 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120018681 | Not Scheduled | DI GATES-PANOCHE #2 26/124 RPR INSS | 44571451 | GATES-PANOCHE #2 | 026/124 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-11-12 | 2021-11-12 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.396221 | 36.4473 | ETL.4730 | 40783168 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120018682 | Q2 | T2 DI SNEATH LN-HLF MN BY ;0/2 RPR GYWW | 44621451 | SNEATH LANE-HALF MOON BAY | ;000/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-10 | 2021-11-10 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR2 |  | Central | WSIP | [8 empty] | ETL.7212 | 44384416 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120018683 | Q2 | T2 DI SNEATH LN-HLF MN BY ;0/2 RPR STRW | 44621451 | SNEATH LANE-HALF MOON BAY | ;000/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-10 | 2021-11-10 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR2 |  | Central | WSIP | [8 empty] | ETL.7212 | 44384417 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120019521 | Not Scheduled | DI STANISLAUS-NEWARK #2 89/580 REPL INSS |  | STANISLAUS-NEWARK #2 (12KV) | 089/580 | 93K | E | 2020_(2) High fire spread TD |  | 2020-11-12 | 2021-11-12 | [9 empty] | Central | WSIP | [6 empty] | '-121.806093 | 37.6206 | ETL.3860 | 44190598 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-13 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120019523 | Not Scheduled | DI STANISLAUS-NEWARK #2 89/580 RMV SPLS | 44620193 | STANISLAUS-NEWARK #2 (12KV) | 089/580 | ICS | E | 2020_(2) High fire spread TD |  | 2020-11-12 | 2021-11-10 | [9 empty] | Central | WSIP | [6 empty] | '-121.806093 | 37.6206 | ETL.3860 | 41196249 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120025170 | Not Scheduled | DI OAKLAND """"J""""-GRANT 6/56 RPR OPGW | 44573085 | OAKLAND "J"-GRANT | 006/056 | ICS | B | 2020_(0) A and B Tags |  | 2020-11-12 | 2021-02-12 | [8 empty] | LATE | Central | WSIP |  |  |  |  | Permit/Environmental | ENV Denied Access due to seasonal restrictions | '-122.167761 | 37.6829 | ETL.3140 | 40644256 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-15 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120026353 | Q2 | T2 BRIDGEVILLE-CTTNWD 46/356 RPL INSS | 31512268 | BRIDGEVILLE-COTTONWOOD | 046/356 | 93K | E | 2020_(2) High fire spread TD |  | 2020-11-10 | 2021-11-10 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.124047 | 40.3994 | ETL.1110 | 40621362 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120026559 | Not Scheduled | T2 EI DRUM-SUMMIT #2 27/321 RPLC STRW | 31519087 | DRUM-SUMMIT #2 | 027/321 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-11-12 | 2021-11-12 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.339774 | 39.3104 | ETL.1450 | 44557672 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120042505 | Q2 | DI STANISLAUS-NEWARK #1 088/586 RPR FOND | 43877551 | STANISLAUS-NEWARK #1 (12KV) | 088/586 | ICS | E | 2020_(2) High fire spread TD |  | 2020-11-13 | 2021-11-13 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | Central | WSIP | [6 empty] | '-121.814807 | 37.615 | ETL.3850 | 41196260 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 16 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-27 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120042887 | Not Scheduled | T3 FULTON-CALISTOGA :3/0 RPL POLE | 31518764 | FULTON-CALISTOGA | :003/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-05-13 | 2020-11-13 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.595056 | 38.6326 | ETL.6880 | 40912430 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120043820 | Q3 | DI GREEN VALLEY-LLAGAS :009/064 RMV VEG |  | GREEN VALLEY-LLAGAS | :009/064 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-11-13 | 2021-11-13 |  |  | 2021-08-15 | 2021-08-01 | [5 empty] | South | WSIP | [6 empty] | '-121.656829 | 37.1203 | ETL.1720 | 40761140 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120043822 | Q2 | DI GREEN VALLEY-LLAGAS :009/064 INS ATCG | 31521739 | GREEN VALLEY-LLAGAS | :009/064 | 93A | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-13 | 2022-11-13 |  |  | 2021-05-21 | 2021-05-03 | [5 empty] | South | WSIP | [6 empty] | '-121.656829 | 37.1203 | ETL.1720 | 40761140 | Structure-Steel | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Capital | 988 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120044186 | Not Scheduled | WV T2 COTTONWOOD #1 3/026 INS DMPS |  | COTTONWOOD #1 | 003/026 | ICS | E | 2020_(2) High fire spread TD |  | 2020-11-16 | 2021-11-16 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.26791 | 40.3448 | ETL.6620 | 40910970 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120044327 | Q2 | T3 WV CRESTA-RIO OSO 20/162 INS DAMP |  | CRESTA-RIO OSO | 020/162 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-11-16 | 2021-05-16 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.487239 | 39.6799 | ETL.4590 | 40910174 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-23 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120044771 | Not Scheduled | T3 ROUND MTN-TABLE MTN #2 3/20 RPL ANCS |  | ROUND MTN-TABLE MTN #2 | 003/020 |  | E | 2020_(4) TD tag on high spread line |  | 2020-11-16 | 2021-05-16 | [7 empty] | TR3 | <90D | North Valley | WSIP | [6 empty] | '-121.935347 | 40.7611 | ETL.6070 | 40602990 | Anchor-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLM | Tower | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade |  | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120044888 | Not Scheduled | T2 DI TRINITY-MAPLE CREEK 39/2 CANCEL | 44575117 | TRINITY-MAPLE CREEK | 039/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-07 | 2022-10-07 | [6 empty] | CANCEL/CNCL | TR2 |  | North Coast | WSIP | [6 empty] | '-123.613756 | 40.7178 | ETL.8170 | 40701808 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120044973 | Q3 | T2NT DI CARIBOU #2 ;5/13 RMV BUTT |  | CARIBOU #2 | ;005/013 | ICW | F | 2020_(3) On high spread structure |  | 2020-11-13 | 2022-11-13 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.953162 | 39.9573 | ETL.6280 | 40653383 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120044975 | Q3 | T2NT DI CARIBOU #2 ;5/13 INS MRKW |  | CARIBOU #2 | ;005/013 | ICW | F | 2020_(3) On high spread structure |  | 2020-11-13 | 2022-11-13 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.953162 | 39.9573 | ETL.6280 | 40653383 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-11-23 | Released-PERTC | No Estimate | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120047761 | Q3 | T3 EI MRGN HL JCT-GRN VLY 16/113B RPL PL | 31519130 | METCALF-GREEN VALLEY | 016/113 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-11-17 | 2021-05-17 |  |  | 2021-07-09 | 2021-07-08 |  |  |  | TR3 | SCHD | South | WSIP | [6 empty] | '-121.6626453 | 37.0344 | ETL.2540 | 43684239 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2021-01-07 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120047862 | Q3 | T3 EI MRGN HL JCT-GRN VLY 16/113A RPL PL | 31519130 | METCALF-GREEN VALLEY | 016/113 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-11-17 | 2021-05-17 |  |  | 2021-07-09 | 2021-07-08 |  |  |  | TR3 | SCHD | South | WSIP | [6 empty] | '-121.6626453 | 37.0344 | ETL.2540 | 43684238 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  | 2021-01-07 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120048034 | Not Scheduled | DI DRUM-SUMMIT #1 14/165 INST SPLIT BOLT | 44645317 | DRUM-SUMMIT #1 | 014/165 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-16 | 2021-11-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.545414 | 39.3152 | ETL.1440 | 40814978 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120048201 | Not Scheduled | DI DRUM-SUMMIT #2 14/165B RPR STRW | 44565155 | DRUM-SUMMIT #2 | 014/165B | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-16 | 2021-11-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.549275 | 39.3172 | ETL.1450 | 44155588 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120048909 | Mar | T2 COALINGA #1-SAN MIGUEL 32/2 RPL INSS | 31519494 | COALINGA #1-SAN MIGUEL | 032/002 | 93K | E | 2020_(2) High fire spread TD |  | 2020-11-17 | 2021-11-17 | 2021-03-15 | 2021-03-18 | 2021-03-18 | 2021-03-15 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.635771 | 35.8224 | ETL.8580 | 40729923 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-11-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120050206 | Q2 | DI NEWARK-LIVERMORE 14/87 REPL INSS | 31529488 | NEWARK-LIVERMORE | 014/087 | 93K | E | 2020_(2) High fire spread TD |  | 2020-11-13 | 2021-11-13 |  |  | 2021-05-12 | 2021-05-10 | [5 empty] | Central | WSIP | [6 empty] | '-121.792401 | 37.6251 | ETL.7660 | 40851061 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120050518 | Not Scheduled | T3 EI RND MTN-TBLE MTN #1 4/24 RPR STRT |  | ROUND MTN-TABLE MTN #1 | 004/024 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-17 | 2021-05-17 | [7 empty] | TR3 | <90D | North Valley | WSIP | [6 empty] | '-121.938713 | 40.7495 | ETL.6060 | 40761034 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120055578 | Not Scheduled | T2 VACA-VACAVILLE-JAMESON-NORTH 8/0 | 44565204 | VACA-VACAVILLE-JAMESON-NTH TWR | 008/064 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-17 | 2021-11-17 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.034254 | 38.3367 | ETL.4100 | 40762260 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLM | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120061608 | Feb | DI VACA-SUISUN 17/127 RPR GYWW | 44565080 | VACA-SUISUN | 017/127 | ICS | B | 2020_(0) A and B Tags |  | 2020-11-17 | 2021-02-17 |  |  | 2021-02-15 | 2021-02-15 |  |  | Likely MAT error - delink to correct |  |  | North Valley | WSIP | [6 empty] | '-122.109836 | 38.2162 | ETL.4070 | 40755611 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120061703 | Not Scheduled | DI NEWARK-LAWRENCE LAB 14/86 RPLC INSS | 31507589 | NEWARK-LAWRENCE LAB | 014/086 | 93K | E | 2020_(2) High fire spread TD |  | 2020-11-13 | 2021-11-13 | [9 empty] | Central | WSIP | [6 empty] | '-121.794254 | 37.6241 | ETL.3060 | 40854569 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120064912 | Q2 | EI GARBERVILLE-LAYTONVILLE 47/4C RPL STR | 31506024 | GARBERVILLE-LAYTONVILLE | 047/004C | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-11-18 | 2021-11-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.617968 | 39.9881 | ETL.8365 | 40912532 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120065230 | Not Scheduled | DI STANISLAUS-NEWARK #1 092/610 RPL INSS | 31530187 | STANISLAUS-NEWARK #1 (12KV) | 092/610 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-11-12 | 2021-11-12 | [9 empty] | Central | WSIP | [6 empty] | '-121.866723 | 37.5878 | ETL.3850 | 40642097 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120069582 | Not Scheduled | T3 EI RND MTN-TABLE MTN #2 20/104 RPR GW |  | ROUND MTN-TABLE MTN #2 | 020/104 |  | E | 2020_(4) TD tag on high spread line |  | 2020-11-18 | 2021-05-18 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.945035 | 40.5098 | ETL.6070 | 40765614 | Anchor-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLM | Tower | Expense |  | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade |  | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120069628 | Q2 | DI GARBERVILLE-LAYTONVILLE 56/1 RPR WDPK | 44572648 | GARBERVILLE-LAYTONVILLE | 056/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-18 | 2021-11-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.676688 | 40.092 | ETL.8365 | 40912623 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120069638 | Q2 | T3 RND MTN-TBLE MTN #1 22/114 RPR STRT | 43622309 | ROUND MTN-TABLE MTN #1 | 022/114 | ICS | E | 2020_(2) High fire spread TD |  | 2020-11-18 | 2021-05-18 |  |  | 2021-05-13 | 2021-04-01 |  |  | Likely MAT error - delink to correct | TR3 |  | North Valley | WSIP | [6 empty] | '-121.948173 | 40.4781 | ETL.6060 | 40759985 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120070047 | Q2 | T2 EI TRINITY-MAPLE CREEK 41/5A RPL ANCW | 31519333 | TRINITY-MAPLE CREEK | 041/005A | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-11-18 | 2021-11-18 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.650113 | 40.7252 | ETL.8170 | 44949067 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120070354 | Q2 | EI IGNACIO-BOLINAS #2 18/209 RPR FOND |  | IGNACIO-BOLINAS #2 | 018/209 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-11-18 | 2022-11-18 |  |  | 2021-05-28 | 2021-05-24 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.78639 | 38.042 | ETL.7180 | 43249468 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120070550 | Q2 | T3 RND MTN-TBLE MTN #2 22/112 BENT STEEL |  | ROUND MTN-TABLE MTN #2 | 022/112 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-11-18 | 2021-05-18 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.947057 | 40.4852 | ETL.6070 | 40678023 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120070600 | Mar | WV T2 CLEAR LAKE-HOPLAND 5/000 INS DMPS | 44611090 | CLEAR LAKE-HOPLAND | 005/000 | ICS | E | 2020_(2) High fire spread TD |  | 2020-11-18 | 2021-11-18 |  |  | 2021-03-26 | 2021-03-24 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.999035 | 38.9814 | ETL.6390 | 45005354 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120070645 | Not Scheduled | T2 WV SPAULDING-SUMMIT 2/087 RPR POLE | 44565236 | SPAULDING-SUMMIT | 002/087 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-11-18 | 2021-11-18 | [6 empty] | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.609361 | 39.3118 | ETL.8060 | 40876731 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120071166 | Q2 | T2 DI SALINAS-LAURELES 11/256 RPR GYWW | 44640867 | SALINAS-LAURELES | 011/256 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-13 | 2021-11-13 |  |  | 2021-05-28 | 2021-05-24 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.753759 | 36.5657 | ETL.7930 | 40809404 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 20 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120071168 | Not Scheduled | T2 DI FULTON-CALISTOGA :11/11 RPR INSW | 44597303 | FULTON-CALISTOGA | :011/011 | ICW | E | 2020_(2) High fire spread TD |  | 2020-11-16 | 2021-11-16 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.608428 | 38.7529 | ETL.6880 | 44189694 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120071254 | Not Scheduled | T3 DI COLGATE-CHALLENGE 12/221 RMV DBRS | 44565222 | COLGATE-CHALLENGE | 012/221 | ICW | E | 2020_(3) On high spread structure |  | 2020-11-16 | 2021-05-16 | [7 empty] | TR3 | <90D | North Valley | WSIP | [6 empty] | '-121.220284 | 39.4852 | ETL.6480 | 40672267 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120071255 | Not Scheduled | T3 DI COLGATE-CHALLENGE 12/221 RPR STRW | 44565222 | COLGATE-CHALLENGE | 012/221 | ICW | E | 2020_(2) High fire spread TD |  | 2020-11-16 | 2021-05-16 | [7 empty] | TR3 | <90D | North Valley | WSIP | [6 empty] | '-121.220284 | 39.4852 | ETL.6480 | 40672267 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120071389 | Feb | T2 COALINGA #1-SAN MIGUEL 30/0 RPR STRT | 44565369 | COALINGA #1-SAN MIGUEL | 030/000 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-16 | 2021-11-16 |  |  | 2021-02-26 | 2021-02-15 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.639635 | 35.8584 | ETL.8580 | 40594402 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120071412 | Not Scheduled | T2 COALINGA #1-SAN MIGUEL 30/00 RPR ANCS |  | COALINGA #1-SAN MIGUEL | 030/000 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-11-16 | 2021-11-16 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.639635 | 35.8584 | ETL.8580 | 40594402 | Anchor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-02 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120071413 | Feb | T2 COALINGA #1-SAN MIGUEL 15/1 RPR STRS | 44565369 | COALINGA #1-SAN MIGUEL | 015/001 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-17 | 2021-11-17 |  |  | 2021-02-26 | 2021-02-15 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.53244 | 36.0109 | ETL.8580 | 40588490 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-11-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120071634 | Not Scheduled | DI NEWARK-LIVERMORE 013/078 RPL INSS | 31507589 | NEWARK-LAWRENCE LAB | 013/078 | 93K | E | 2020_(2) High fire spread TD |  | 2020-11-13 | 2021-11-13 | [9 empty] | Central | WSIP | [6 empty] | '-121.813379 | 37.6128 | ETL.3060 | 44779120 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y -12 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-13 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120072138 | Not Scheduled | DI DRUM-SUMMIT #1 014/160 RMV BUTT | 44565296 | DRUM-SUMMIT #1 | 014/160 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-16 | 2022-11-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.552163 | 39.3184 | ETL.1440 | 40579655 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120073515 | Not Scheduled | DI DRUM-SUMMIT #2 14/163 RPR GYWW | 44565153 | DRUM-SUMMIT #2 | 014/163 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-17 | 2021-11-17 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44159101 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120073786 | Q2 | T3 EI RND MTN-TABLE MTN #2 21/1 BENT STE |  | ROUND MTN-TABLE MTN #2 | 021/107 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-11-19 | 2021-05-19 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.945869 | 40.4997 | ETL.6070 | 40816739 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120073817 | Q2 | T2 DI WEIMAR #1 0/1 RPR STRW | 44565224 | WEIMAR #1 | 000/001 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-16 | 2021-11-16 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.987841 | 39.0358 | ETL.7560 | 44263355 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120074720 | Not Scheduled | DI DRUM-SUMMIT #1 17/206 RPR GYWW | 44565152 | DRUM-SUMMIT #1 | 017/206 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-16 | 2021-11-16 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44162409 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120074723 | Not Scheduled | DI DRUM-SUMMIT #1 17/206 RPR GYWW | 44565152 | DRUM-SUMMIT #1 | 017/206 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-16 | 2021-11-16 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44162410 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120074725 | Not Scheduled | DI DRUM-SUMMIT #1 17/206 RPR GYWW | 44565152 | DRUM-SUMMIT #1 | 017/206 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-16 | 2021-11-16 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44162411 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120075293 | Not Scheduled | DI DRUM-SUMMIT #2 14/165A RPR GYWW | 44565155 | DRUM-SUMMIT #2 | 014/165A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-16 | 2021-11-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.549261 | 39.3172 | ETL.1450 | 44155587 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120075296 | Not Scheduled | DI DRUM-SUMMIT #1 17/98 RPR GYWW | 44565152 | DRUM-SUMMIT #1 | 017/198 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-16 | 2021-11-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.501391 | 39.3138 | ETL.1440 | 40671389 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120075297 | Not Scheduled | DI DRUM-SUMMIT #1 17/98 RMV DEBRIS | 44565296 | DRUM-SUMMIT #1 | 017/198 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-16 | 2022-11-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.501391 | 39.3138 | ETL.1440 | 40671389 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120075637 | Not Scheduled | DI DRUM-SUMMIT #1 17/197C RMV BUTT | 44565296 | DRUM-SUMMIT #1 | 017/197C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-16 | 2022-11-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.502744 | 39.3136 | ETL.1440 | 42572701 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120075770 | Q2 | T3 ROUND MTN-TABLE MTN #1 8/45 RPR GYWS | 43622309 | ROUND MTN-TABLE MTN #1 | 008/045 | ICS | E | 2020_(2) High fire spread TD |  | 2020-11-19 | 2021-05-19 |  |  | 2021-05-13 | 2021-04-01 |  |  | Tower guy | TR3 |  | North Valley | WSIP | [6 empty] | '-121.940575 | 40.6894 | ETL.6060 | 40746375 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120075797 | Not Scheduled | DI DRUM-SUMMIT #1 17/200R RPL POLE |  | DRUM-SUMMIT #1 | 017/200 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-16 | 2021-11-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.498477 | 39.3142 | ETL.1440 | 45016520 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120076414 | Q3 | T2 DI CARIBOU #2 ;2/8 RPLC CRSW | 31505337 | CARIBOU #2 | ;002/008 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-11-16 | 2021-11-16 |  |  | 2021-07-30 | 2021-07-12 |  |  | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [6 empty] | '-120.955265 | 39.9992 | ETL.6280 | 40876684 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120076417 | Q3 | T2 DI CARIBOU #2 ;2/8 RMV DEBRIS |  | CARIBOU #2 | ;002/008 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-16 | 2022-11-16 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.955265 | 39.9992 | ETL.6280 | 40876684 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120076419 | Q3 | T2 DI CARIBOU #2 ;2/8 RPR GYWW |  | CARIBOU #2 | ;002/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-16 | 2021-11-16 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.955265 | 39.9992 | ETL.6280 | 40876684 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120076511 | Q3 | T2 DI CARIBOU #2 ;2/8 INS MRKW |  | CARIBOU #2 | ;002/008 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-16 | 2022-11-16 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.955265 | 39.9992 | ETL.6280 | 40876684 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120076616 | Q2 | WV GRBRVLL-LYTNVILLE 60/001 RPL DMPS |  | GARBERVILLE-LAYTONVILLE | 060/001 | ICS | E | 2020_(2) High fire spread TD |  | 2020-11-19 | 2021-11-19 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.746135 | 40.1117 | ETL.8365 | 40912679 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120076685 | Q3 | WV T2 CARIBOU #2 11/019 INS DMPW |  | CARIBOU #2 | 011/019 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-19 | 2021-11-19 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.165363 | 40.0229 | ETL.6280 | 44465287 | Damper-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120076849 | Q2 | T2 VOLTA-DESCHUTES 16/352 RFR STRW | 31519334 | VOLTA-DESCHUTES | 016/352 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-11-19 | 2021-11-19 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.161725 | 40.5381 | ETL.8290 | 40700147 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120078658 | Feb | DI SAN FRANCISCO #2 5/43 REPL HNR PLATES | 44579148 | SAN FRANCISCO #2 (IDLE) | 005/043 | ICQ | B | 2020_(0) A and B Tags |  | 2020-11-18 | 2021-02-18 |  |  | 2021-02-15 | 2021-02-15 | [5 empty] | Central | WSIP | [6 empty] | '-122.237949 | 37.5433 | ETL.3279 | 40688498 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120078746 | Feb | DI SAN MATEO-BAY MEADWS #1 4/26 RPL DAMS | 44574250 | SAN MATEO-BAY MEADOWS #1 (NO FLY) | 004/026 | ICS | B | 2020_(0) A and B Tags |  | 2020-11-18 | 2021-02-16 |  |  | 2021-02-14 | 2021-02-14 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.290348 | 37.5532 | ETL.3550 | 40836236 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120079073 | Q2 | DI TRINITY-MAPLE CREEK 000/000 RPR GYWW | 44565702 | TRINITY-MAPLE CREEK | 000/000 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-11-18 | 2021-11-18 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.934432 | 40.7183 | ETL.8170 | 44191875 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120079133 | Not Scheduled | T2 COLGATE-GRASS VALLEY 2/63 STUB POLE | 44572346 | COLGATE-GRASS VALLEY | 002/063 | GAR | E | 2020_(4) TD tag on high spread line |  | 2020-10-19 | 2021-10-19 | [7 empty] | TR2 |  | North Valley | [7 empty] | '-121.141927 | 39.3219 | ETL.6490 | 40869622 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120079135 | Not Scheduled | T2 COLGATE-GRASS VALLEY 10/244 STUB POLE | 44572346 | COLGATE-GRASS VALLEY | 010/244 | GAR | E | 2020_(4) TD tag on high spread line |  | 2020-10-21 | 2021-10-21 | [7 empty] | TR2 |  | North Valley | [7 empty] | '-121.079248 | 39.2305 | ETL.6490 | 40576820 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120079137 | Not Scheduled | COLGATE-GRASS VALLEY 12/317 STUB POLE | 44572346 | COLGATE-GRASS VALLEY | 012/317 | GAR | E | 2020_(4) TD tag on high spread line |  | 2020-10-20 | 2021-10-20 | [9 empty] | North Valley | [7 empty] | '-121.062793 | 39.2091 | ETL.6490 | 40613027 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120079139 | Not Scheduled | T3 COLGATE-GRASS VALLEY 5/137 STUB POLE | 44572346 | COLGATE-GRASS VALLEY | 005/137 | GAR | E | 2020_(4) TD tag on high spread line |  | 2020-10-23 | 2021-04-23 | [7 empty] | TR3 | <90D | North Valley | [7 empty] | '-121.106155 | 39.2996 | ETL.6490 | 40679384 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120079205 | Not Scheduled | T3 COLGATE-ALLEGHANY 16/456 STUB POLE | 44572345 | COLGATE-ALLEGHANY | 016/456 | GAR | E | 2020_(2) High fire spread TD |  | 2020-09-28 | 2021-03-28 | [7 empty] | TR3 | <60D | North Valley | [7 empty] | '-120.961193 | 39.4492 | ETL.6470 | 40822628 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120079207 | Not Scheduled | T3 COLGATE-ALLEGHANY 15/401 STUB POLE | 44572345 | COLGATE-ALLEGHANY | 015/401 | GAR | E | 2020_(2) High fire spread TD |  | 2020-09-29 | 2021-03-29 | [7 empty] | TR3 | <60D | North Valley | [7 empty] | '-120.99495 | 39.4433 | ETL.6470 | 40693242 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120079315 | Not Scheduled | DI SIERRA #1 18/123 RPLC INSS | 31519234 | SIERRA #2 (IDLE) | 018/123 | 93K | B | 2020_(0) A and B Tags |  | 2020-11-19 | 2021-02-17 | [8 empty] | <15D | Central | WSIP | [8 empty] | ETL.3680 | 41195157 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y-5 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-02-12 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120079431 | Q2 | T3 DRUM-SPAULDING 003/072 RPL POLE | 31529083 | DRUM-SPAULDING | 003/072 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-08-05 | 2021-02-05 |  |  | 2021-04-24 | 2021-04-12 |  |  |  | TR3 | LATE | North Valley | [7 empty] | '-120.728684 | 39.2756 | ETL.6770 | 40751874 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120079434 | Not Scheduled | T2 DRUM-SUMMIT #1 021/254C STUB POLE | 44572351 | DRUM-SUMMIT #1 | 021/254C | GAR | E | 2020_(1b) Lines with special commitments |  | 2020-09-11 | 2021-09-11 | [7 empty] | TR2 | WECC | North Valley | [7 empty] | '-120.424703 | 39.3148 | ETL.1440 | 42572716 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120079436 | Not Scheduled | T2 DRUM-SUMMIT#1 22/270A STUB PL ""LFT"" | 44572351 | DRUM-SUMMIT #1 | 022/270A | GAR | E | 2020_(1b) Lines with special commitments |  | 2020-09-11 | 2021-09-11 | [7 empty] | TR2 | WECC | North Valley | [7 empty] | '-120.40044 | 39.3103 | ETL.1440 | 40597485 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120079439 | Not Scheduled | T3 DRUM-SUMMIT#2 3/045B STUB POLE ""RT"" | 44572354 | DRUM-SUMMIT #2 | 003/045 | GAR | E | 2020_(1b) Lines with special commitments |  | 2020-08-06 | 2021-02-06 | [7 empty] | TR3 | LATE | North Valley | [7 empty] | '-120.716078 | 39.2842 | ETL.1450 | 44549459 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120079557 | Not Scheduled | T2 DRUM-SUMMIT#2 020/248A STUB PL ""LFT"" | 44572354 | DRUM-SUMMIT #2 | 020/248 | GAR | E | 2020_(1b) Lines with special commitments |  | 2020-09-09 | 2021-09-09 | [7 empty] | TR2 | WECC | North Valley | [7 empty] | '-120.435468 | 39.324 | ETL.1450 | 44551525 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120079645 | Not Scheduled | DI DRUM-SUMMIT #1 014/163 RPL STRW | 31521943 | DRUM-SUMMIT #1 | 014/163 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-11-16 | 2021-11-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.547669 | 39.3167 | ETL.1440 | 40756912 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120079893 | Not Scheduled | T3 FRNCH MDWS-MDDLE FRK 12/237 RPL STRW | 31519331 | FRENCH MEADOWS-MIDDLE FORK | 012/237 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-11-20 | 2021-05-20 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.597109 | 39.023 | ETL.6870 | 40826825 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120079900 | Not Scheduled | T3 MIDDLE FORK #1 0/003 RPL STRW | 31519332 | MIDDLE FORK #1 | 000/003 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-11-20 | 2021-05-20 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.597278 | 39.0228 | ETL.8405 | 40664811 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120080540 | Before Feb | DI NEWARK-KIFER 4/27 RPLC DAMS | 44572935 | NEWARK-KIFER | 004/027 | ICS | B | 2020_(0) A and B Tags |  | 2020-11-19 | 2021-02-19 |  |  | 2021-01-15 | 2021-01-15 | [5 empty] | Central | WSIP | [6 empty] | 121.9511 | 37.4516 | ETL.3040 | 40834767 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Before Feb | Found in 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2020-12-07 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120080990 | Not Scheduled | DI SPAULDING-SUMMIT 007/248 RMV BUTT | 44565384 | SPAULDING-SUMMIT | 007/248 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-17 | 2022-11-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.527439 | 39.3067 | ETL.8060 | 44349507 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120080994 | Not Scheduled | DI SPAULDING-SUMMIT 007/248 RPR GYWW | 44565237 | SPAULDING-SUMMIT | 007/248 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-17 | 2021-11-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.527439 | 39.3067 | ETL.8060 | 44349507 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120081116 | Not Scheduled | DI DRUM-SUMMIT #1 17/203 RPR GYWW | 44565152 | DRUM-SUMMIT #1 | 017/203 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-17 | 2021-11-17 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44149457 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120081140 | Not Scheduled | DI DRUM-SUMMIT #1 17/203 RPR GYWW | 44565152 | DRUM-SUMMIT #1 | 017/203 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-17 | 2021-11-17 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44149458 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120081142 | Not Scheduled | DI DRUM-SUMMIT #1 17/203 RPR GYWW | 44565152 | DRUM-SUMMIT #1 | 017/203 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-17 | 2021-11-17 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44149459 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120081148 | Not Scheduled | DI DRUM-SUMMIT #1 17/203 RMV DEBRIS | 44565296 | DRUM-SUMMIT #1 | 017/203 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-17 | 2022-11-17 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44149459 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120081244 | Not Scheduled | DI DRUM-SUMMIT #1 13/154 RMV BUTT | 44565296 | DRUM-SUMMIT #1 | 013/154 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-17 | 2022-11-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.560202 | 39.3225 | ETL.1440 | 40820270 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120081246 | Not Scheduled | DI DRUM-SUMMIT #1 13/154 RPLC STRW | 31521943 | DRUM-SUMMIT #1 | 013/154 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-11-17 | 2021-11-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.560202 | 39.3225 | ETL.1440 | 40820270 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120081403 | Not Scheduled | SPAULDING-SUMMIT 008/275 STUB POLE | 44572586 | SPAULDING-SUMMIT | 008/275 | GAR | E | 2020_(1b) Lines with special commitments |  | 2020-09-22 | 2021-09-22 | [8 empty] | WECC | North Valley | [7 empty] | '-120.516249 | 39.3144 | ETL.8060 | 40826224 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120081510 | Not Scheduled | SPAULDING-SUMMIT 006/237 STUB POLE | 44572586 | SPAULDING-SUMMIT | 006/237 | GAR | E | 2020_(1b) Lines with special commitments |  | 2020-08-26 | 2021-08-26 | [8 empty] | WECC | North Valley | [7 empty] | '-120.533865 | 39.3077 | ETL.8060 | 40650044 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | GAR | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120081739 | Not Scheduled | T3 WV FULTON-CALISTOGA ;10/3 RPR INSS |  | FULTON-CALISTOGA | ;010/003 | ICS | E | 2020_(2) High fire spread TD |  | 2020-11-20 | 2021-05-20 |  |  |  | 2021-04-26 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.560766 | 38.4877 | ETL.6880 | 40658333 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120082632 | Q2 | T3 ROUND MTN-TABLE MTN #2 4/28 RPR STRT |  | ROUND MTN-TABLE MTN #2 | 004/028 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-11-21 | 2021-05-21 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.940712 | 40.7361 | ETL.6070 | 40873564 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120082969 | Q2 | T3 ROUND MTN-TABLE MTN #1 5/30 RPR STRT | 43622309 | ROUND MTN-TABLE MTN #1 | 005/030 | ICS | E | 2020_(2) High fire spread TD |  | 2020-11-21 | 2021-05-21 |  |  | 2021-05-13 | 2021-04-01 |  |  | Likely MAT error - delink to correct | TR3 |  | North Valley | WSIP | [6 empty] | '-121.942084 | 40.7299 | ETL.6060 | 40605584 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120083781 | Q2 | T3 ROUND MTN-TABLE MTN #1 6/36 RPR STRT | 43622309 | ROUND MTN-TABLE MTN #1 | 006/036 | ICS | E | 2020_(2) High fire spread TD |  | 2020-11-21 | 2021-05-21 |  |  | 2021-05-13 | 2021-04-01 |  |  | Likely MAT error - delink to correct | TR3 |  | North Valley | WSIP | [6 empty] | '-121.941509 | 40.7127 | ETL.6060 | 40820543 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120083804 | Q2 | T3 ROUND MTN-TABLE MTN #2 6/38 RPR STRT |  | ROUND MTN-TABLE MTN #2 | 006/038 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-11-21 | 2021-05-21 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.940768 | 40.7077 | ETL.6070 | 40869094 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120084206 | Q2 | T3 ROUND MTN-TABLE MTN #1 7/39 RPR GYWS | 43622309 | ROUND MTN-TABLE MTN #1 | 007/039 | ICS | E | 2020_(2) High fire spread TD |  | 2020-11-22 | 2021-05-22 |  |  | 2021-05-13 | 2021-04-01 |  |  | Tower guy | TR3 |  | North Valley | WSIP | [6 empty] | '-121.941143 | 40.7035 | ETL.6060 | 40868402 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120084234 | Not Scheduled | T2 MALIN-ROUND MTN #2 94/479 RPR FOND |  | MALIN-ROUND MTN #2 | 094/480 | ICQ | E | 2020_(1b) Lines with special commitments |  | 2020-11-22 | 2021-11-22 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.934128 | 40.8104 | ETL.6020 | 40868386 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120084741 | Q2 | DI GARBERVILLE-LAYTONVILLE 51/3 RPL POLE | 31516141 | GARBERVILLE-LAYTONVILLE | 051/003 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-11-20 | 2021-11-20 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.640271 | 40.0368 | ETL.8365 | 40912572 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120084849 | Feb | DI RIO DELL JCT-BRIDGEVL 37/6 RPLC STRW | 31519328 | RIO DELL JCT-BRIDGEVILLE | 037/006 | 70Y | B | 2020_(0) A and B Tags |  | 2020-11-20 | 2021-02-20 | 2021-02-15 | 2021-02-27 | 2021-02-17 | 2021-02-17 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.833152 | 40.4681 | ETL.7850 | 40808726 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-15 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120084873 | Q2 | DI GARBERVILLE-LAYTONVL 57/5 RPR DAMW | 44542681 | GARBERVILLE-LAYTONVILLE | 057/005 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-20 | 2021-11-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.8365 | 40922458 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120084880 | Q3 | T2 DI CARIBOU #2 003/004 RPR GYWW |  | CARIBOU #2 | 003/004 | ICW | E | 2020_(2) High fire spread TD |  | 2020-11-20 | 2021-11-20 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.18961 | 40.0628 | ETL.6280 | 40769523 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120085012 | Q3 | T2 DI CARIBOU #2 016/001 RPR GYWW |  | CARIBOU #2 | 016/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-11-20 | 2021-11-20 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.095375 | 40.0176 | ETL.6280 | 44217548 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120085290 | Q3 | T2 DI CARIBOU #2 002/012 RPR GYWW |  | CARIBOU #2 | 002/012 | ICW | E | 2020_(2) High fire spread TD |  | 2020-11-20 | 2021-11-20 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.179159 | 40.068 | ETL.6280 | 40675373 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120085342 | Q2 | DI GARBERVILLE-LAYTONVILLE 54/2 RPL INSW | 31518255 | GARBERVILLE-LAYTONVILLE | 054/002 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-11-20 | 2021-11-20 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.8365 | 40922413 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120085677 | Q3 | DI CARIBOU #2 ;007/009 RPR GYWW |  | CARIBOU #2 | ;007/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-11-17 | 2021-11-17 |  |  | 2021-07-30 | 2021-07-12 | [5 empty] | North Valley | WSIP | [6 empty] | '-120.963302 | 39.9408 | ETL.6280 | 40864713 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-08 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120085678 | Q3 | DI CARIBOU #2 ;007/009 REFRAME | 31513486 | CARIBOU #2 | ;007/009 | 93E | E | 2020_(2) High fire spread TD |  | 2020-11-17 | 2021-11-17 |  |  | 2021-07-30 | 2021-07-12 | [5 empty] | North Valley | WSIP | [6 empty] | '-120.963302 | 39.9408 | ETL.6280 | 40864713 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-12-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120086247 | Not Scheduled | T2 MALIN-ROUND MTN #2 72/363 RPR GYWW | 44408444 | MALIN-ROUND MTN #2 | 072/363 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-11-22 | 2021-11-22 | [6 empty] | Tower guy | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.798404 | 41.0772 | ETL.6020 | 40663115 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120086315 | Feb | DI BRENTWOOD-KELSO 4/22 RPLC INSS | 31519382 | BRENTWOOD-KELSO | 004/022 | 93K | B | 2020_(0) A and B Tags |  | 2020-11-18 | 2021-02-18 |  |  | 2021-02-12 | 2021-02-12 | [5 empty] | Central | WSIP | [6 empty] | '-121.721574 | 37.9032 | ETL.4410 | 40728987 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-12-07 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120086607 | Feb | DI BRENTWOOD-KELSO 004/023 RPL INSS | 31519382 | BRENTWOOD-KELSO | 004/023 | 93K | B | 2020_(0) A and B Tags |  | 2020-11-19 | 2021-02-19 |  |  | 2021-02-12 | 2021-02-12 | [5 empty] | Central | WSIP | [6 empty] | '-121.720465 | 37.901 | ETL.4410 | 40678878 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-12-07 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120086613 | Feb | DI CARNERAS-TAFT 4/63 RPLC INSW | 31519540 | CARNERAS-TAFT | 004/063 | 93I | B | 2020_(0) A and B Tags |  | 2020-11-20 | 2021-02-18 |  |  | 2021-02-16 | 2021-02-16 | [5 empty] | South | WSIP | [6 empty] | '-119.52796 | 35.1805 | ETL.8540 | 40637733 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Midway |  | Y - 10 | CalTrans | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-14 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120086780 | Not Scheduled | DI STANISLAUS-NEWARK #2 88/578 RPLC INSS |  | STANISLAUS-NEWARK #2 (12KV) | 088/578 | 93K | E | 2020_(2) High fire spread TD |  | 2020-11-13 | 2021-11-13 | [9 empty] | Central | WSIP | [6 empty] | '-121.79316 | 37.6272 | ETL.3860 | 44190596 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120087121 | Mar | T2 EI CORTINA-MENDCIN #1 35/169 RPR FOND |  | CORTINA-MENDOCINO #1 | 035/169 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-23 | 2021-11-23 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.794758 | 39.1041 | ETL.1330 | 40870089 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120087143 | Not Scheduled | DI DRUM-SUMMIT #1 017/201 RMV SWITCH |  | DRUM-SUMMIT #1 | 017/201 | 93S | E | 2020_(1b) Lines with special commitments |  | 2020-11-17 | 2021-11-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.496726 | 39.3144 | ETL.1440 | 40755579 | Switch-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 435 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120088387 | Q2 | T2 TRINITY-MAPLE CREEK 000/000 REPL POLE | 31505649 | TRINITY-MAPLE CREEK | 000/000 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-11-24 | 2021-11-24 |  |  | 2021-06-12 | 2021-06-07 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.530236 | 40.7126 | ETL.8170 | 44966203 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120088937 | Not Scheduled | T2 DI SPAULDING-SUMMIT 12/413 RPR BOND | 44572587 | SPAULDING-SUMMIT | 012/413 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-23 | 2021-11-23 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.441331 | 39.3195 | ETL.8060 | 40770670 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120089213 | Not Scheduled | DI SPAULDING-SUMMIT 5/184 REPL POLE | 31515501 | SPAULDING-SUMMIT | 005/184 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-11-23 | 2021-11-23 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.559508 | 39.3062 | ETL.8060 | 40770651 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120089665 | Not Scheduled | SPAULDING-SUMMIT 005/174 RPL POLE | 31519569 | SPAULDING-SUMMIT | 005/174 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-09-17 | 2021-09-17 | [8 empty] | WECC | North Valley | [7 empty] | '-120.564205 | 39.3059 | ETL.8060 | 40751911 | Structure-Wood | Rotten | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120090719 | Not Scheduled | LOS BANOS-MIDWAY #2 59/249 RPR RPTS | 44571440 | LOS BANOS-MIDWAY #2 | 059/249 | ICB | E | 2020_(1b) Lines with special commitments |  | 2020-11-24 | 2021-11-24 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.374307 | 36.3857 | ETL.6010 | 40863661 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120091277 | Q3 | DI BRIDGEVILLE-GARBERVILLE 24/2 RMV BUTT | 44572647 | BRIDGEVILLE-GARBERVILLE | 024/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-12 | 2022-11-12 |  |  | 2021-08-28 | 2021-08-23 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.721807 | 40.2043 | ETL.6220 | 40698359 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120091372 | Not Scheduled | DI DRUM-SUMMIT #2 014/167C RPR GYWW | 44572356 | DRUM-SUMMIT #2 | 014/167C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-17 | 2021-11-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.545581 | 39.3164 | ETL.1450 | 44155592 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120091491 | Not Scheduled | DRUM-SUMMIT #2 021/255L RPL POLE | 31521951 | DRUM-SUMMIT #2 | 021/255 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-09-10 | 2021-09-10 | [8 empty] | WECC | North Valley | [7 empty] | '-120.42463 | 39.3274 | ETL.1450 | 44553571 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120091494 | Not Scheduled | T2 DRUM-SUMMIT #2 021/254B RPL POLE |  | DRUM-SUMMIT #2 | 021/254 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-09-10 | 2021-09-10 | [7 empty] | TR2 | WECC | North Valley | [7 empty] | '-120.42614 | 39.3272 | ETL.1450 | 44553153 | Structure-Wood | Rotten | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120094811 | Not Scheduled | DI RUM-SUMMIT#2 13/157R REPL POLE |  | DRUM-SUMMIT #2 | 013/157 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-11-19 | 2021-11-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.560067 | 39.3227 | ETL.1450 | 44561223 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120095664 | Mar | T3 DI SBRNT-GRZZLY-CLRMNT #1 4/38E RPL I |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 004/038E | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-11-17 | 2021-05-17 | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-03-18 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.18878 | 37.857 | ETL.3740 | 42582028 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120095687 | Not Scheduled | T2 DI DRUM-SUMMIT #2 023/272 RPL POLE | 31497848 | DRUM-SUMMIT #2 | 023/272 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2019-05-24 | 2021-05-31 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.396444 | 39.329 | ETL.1450 | 44558974 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120095868 | Not Scheduled | CARIBOU-TABLE MTN 56/391 RPR FOND |  | CARIBOU-TABLE MTN | 056/391 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-11-25 | 2022-11-25 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.55911 | 39.5462 | ETL.4440 | 40591417 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120096200 | Not Scheduled | CARIBOU-TABLE MTN 56/389 RPR FOND |  | CARIBOU-TABLE MTN | 056/389 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-11-25 | 2022-11-25 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.551553 | 39.5461 | ETL.4440 | 40867224 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120096482 | Feb | LOS BANOS-GATES #1 1/008 GRND WASH | 44571459 | LOS BANOS-GATES #1 | 001/008 | ICD | E | 2020_(1b) Lines with special commitments |  | 2020-11-25 | 2021-11-25 |  |  | 2021-02-24 | 2021-02-24 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-121.007421 | 37.0288 | ETL.6000 | 40867436 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Fresno |  | Y - 22 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120096891 | Not Scheduled | T2 DI SPAULDING-SUMMIT 12/413 RPR JUMW | 44572587 | SPAULDING-SUMMIT | 012/413 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-23 | 2021-11-23 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.441331 | 39.3195 | ETL.8060 | 40770670 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120096954 | Q3 | T2 DI CARIBOU-PLUMAS JCT 0/1 RMV BUTT |  | CARIBOU-PLUMAS JCT | 000/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-23 | 2022-11-23 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.14748 | 40.0855 | ETL.6290 | 40600690 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-15 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120097021 | Not Scheduled | DI OAKLAND ""J"" GRANT 002/020 RPL SPLS | 44579558 | OAKLAND "J"-GRANT | 002/020 | ICS | B | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) |  | 2020-11-24 | 2021-02-22 | [8 empty] | <15D | Central | WSIP |  |  |  | REJECT: Per [REDACTED], Crew submit to wrong notification. Submission was intended for 119974553. Crew has resubmit to correct notification |  |  | '-122.191661 | 37.7361 | ETL.3140 | 40877411 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  | Reject | 2020-12-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Upgraded_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120097433 | Not Scheduled | LOS BANOS-MIDWAY #2 42/175 INS ZENA GRD | 31527640 | LOS BANOS-MIDWAY #2 | 042/175 | 93R | F | 2020_(1b) Lines with special commitments |  | 2020-11-25 | 2022-11-25 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.579649 | 36.5676 | ETL.6010 | 40764985 | Raptor Guard-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 530 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120097815 | Not Scheduled | T2 FULTON-LAKEVILLE+ 37/160 RPL INSS |  | FULTON-LAKEVILLE | 037/160 | 93K | E | 2020_(2) High fire spread TD |  | 2020-11-25 | 2021-11-25 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.5925256 | 38.3359 | ETL.4950 | 41130021 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120097861 | Not Scheduled | LOS BANOS-GATES #1 1/008 INS ZENA GRD | 31527299 | LOS BANOS-GATES #1 | 001/008 | 93R | F | 2020_(1b) Lines with special commitments |  | 2020-11-25 | 2022-11-25 | [8 empty] | WECC | South | WSIP | [6 empty] | '-121.007421 | 37.0288 | ETL.6000 | 40867436 | Raptor Guard-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 530 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120097971 | Feb | DI PITTSBURG-SAN MATEO 45/184 RPR FOND | 44631223 | PITTSBURG-SAN MATEO | 045/184 | ICQ | B | 2020_(0) A and B Tags |  | 2020-11-24 | 2021-02-22 |  |  | 2021-02-21 | 2021-02-08 | [5 empty] | Central | WSIP | [6 empty] | '-122.295236 | 37.5721 | ETL.5463 | 40911273 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120106996 | Feb | DI JEFFERSON-MARTIN 012/081A COTR KEY | 44579622 | JEFFERSON-MARTIN | 012/081A | ICS | B | 2020_(0) A and B Tags |  | 2020-11-24 | 2021-02-22 |  |  | 2021-02-20 | 2021-02-20 | [5 empty] | Central | WSIP | [6 empty] | '-122.423989 | 37.5991 | ETL.5710 | 44191835 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | SFPUC | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-23 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120107806 | Not Scheduled | DI DRUM-SUMMIT #2 17/2 RPL POLE | 31521945 | DRUM-SUMMIT #2 | 017/202 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-11-19 | 2021-11-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.501207 | 39.314 | ETL.1450 | 44557568 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120107832 | Not Scheduled | DI DRUM-SUMMIT #2 17/2 RPL POLE | 31521945 | DRUM-SUMMIT #2 | 017/202 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-11-19 | 2021-11-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.501207 | 39.314 | ETL.1450 | 44557686 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120108339 | Not Scheduled | T3NT EI SNTH LNE-HLF MN BY ?4/5 RMV BUTT | 44621951 | SNEATH LANE-HALF MOON BAY | ?004/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-11-30 | 2022-11-30 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.467012 | 37.5509 | ETL.7212 | 44846583 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120108373 | Q2 | T3 EI SNTH LNE-HLF MOON BY ?4/5 RPR GYWW | 44621677 | SNEATH LANE-HALF MOON BAY | ?004/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-11-30 | 2021-05-30 |  |  | 2021-05-13 | 2021-04-16 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.467012 | 37.5509 | ETL.7212 | 44846583 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120108399 | Not Scheduled | DI DRUM-SUMMIT #1 13/156 RMV DBRS | 44575084 | DRUM-SUMMIT #1 | 013/156 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-17 | 2022-11-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.556968 | 39.3201 | ETL.1440 | 40866551 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120108418 | Not Scheduled | T3NT EI SNTH LNE-HLF MN BY ?4/5 RMV BUTT | 44621951 | SNEATH LANE-HALF MOON BAY | ?004/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-11-30 | 2022-11-30 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.467012 | 37.5509 | ETL.7212 | 44846581 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120108453 | Not Scheduled | T3NT EI SNTH LNE-HLF MN BY ?4/5 RMV BUTT | 44621951 | SNEATH LANE-HALF MOON BAY | ?004/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-11-30 | 2022-11-30 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.467012 | 37.5509 | ETL.7212 | 44846582 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120108574 | Not Scheduled | T2 WV SPAULDING-SUMMIT 10/358 RPL ANCW | 31519636 | SPAULDING-SUMMIT | 010/358 | 93E | E | 2020_(1b) Lines with special commitments |  | 2020-11-30 | 2021-11-30 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.467695 | 39.3189 | ETL.8060 | 40602288 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120108641 | Not Scheduled | DI DRUM-SUMMIT #1 14/162A RPR WDPKR |  | DRUM-SUMMIT #1 | 014/162A | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-17 | 2021-11-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.549325 | 39.3171 | ETL.1440 | 40663002 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120108716 | Q3 | T2NT DI CARIBOU #2 002/003 INS MRKW |  | CARIBOU #2 | 002/003 | ICW | F | 2020_(3) On high spread structure |  | 2020-11-20 | 2022-11-20 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.175592 | 40.0711 | ETL.6280 | 40649910 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120108821 | Q3 | T2 DI CARIBOU #2 0/32 RPR GYWW |  | CARIBOU #2 | 000/032 | ICW | E | 2020_(2) High fire spread TD |  | 2020-11-20 | 2021-11-20 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.159572 | 40.0791 | ETL.6280 | 40675360 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120109755 | Mar | LOS BANOS-MIDWAY #2 132/543 COND SPACER | 44579971 | LOS BANOS-MIDWAY #2 | 132/543 | ICS | B | 2020_(0) A and B Tags |  | 2020-11-30 | 2021-03-02 |  |  | 2021-03-02 | 2021-03-02 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.577505 | 35.5545 | ETL.6010 | 40651976 | Spacer-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - 37 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120109773 | Q2 | DI GARBRVLLE-LAYTONVLLE 57/2 RPR GYWW | 44542681 | GARBERVILLE-LAYTONVILLE | 057/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-20 | 2021-11-20 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.692292 | 40.103 | ETL.8365 | 40912646 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120109864 | Not Scheduled | DI SPAULDING-SUMMIT 8/291 RPR GYWW | 44579355 | SPAULDING-SUMMIT | 008/291 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-17 | 2021-11-17 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.50276 | 39.3135 | ETL.8060 | 44349522 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120110392 | Q2 | DI GARBERVILLE-LAYTONVILLE 60/2 INS MRKW | 44542681 | GARBERVILLE-LAYTONVILLE | 060/002 | ICW | F | 2020_(3) On high spread structure |  | 2020-11-20 | 2022-11-20 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.749815 | 40.1129 | ETL.8365 | 44913382 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120110413 | Q3 | T2NT DI CARIBOU-WSTWD 000/001 RMV BUTT |  | CARIBOU-WESTWOOD | 000/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-23 | 2022-11-23 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.147269 | 40.0852 | ETL.6300 | 40913188 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120110420 | Q2 | DI GRBRVLLE LYTNVLLE 060/001 RPL STRW | 31516141 | GARBERVILLE-LAYTONVILLE | 060/001 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-11-20 | 2021-11-20 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.746135 | 40.1117 | ETL.8365 | 40912679 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120110463 | Not Scheduled | DI DRUM-SUMMIT #1 17/202L RPR GYWW | 44579270 | DRUM-SUMMIT #1 | 017/202 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-19 | 2021-11-19 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44180211 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120110464 | Not Scheduled | DI DRUM-SUMMIT #1 17/202C RPR GYWW | 44579278 | DRUM-SUMMIT #1 | 017/202 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-19 | 2021-11-19 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44180212 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120110465 | Not Scheduled | DI DRUM-SUMMIT #1 17/202R RPR GYWW | 44579321 | DRUM-SUMMIT #1 | 017/202 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-19 | 2021-11-19 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44180213 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120110466 | Not Scheduled | DI DRUM-SUMMIT #1 17/202R RMV DEBRIS | 44579465 | DRUM-SUMMIT #1 | 017/202 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-19 | 2022-11-19 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44180213 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120110492 | Q2 | DI GARBERVILLE-LAYTONVILLE 60/0 RPL POLE | 31528843 | GARBERVILLE-LAYTONVILLE | 060/000 | 70Y | E | 2020_(1a) PSPS |  | 2020-11-20 | 2021-11-20 |  |  | 2021-04-20 | 2021-04-20 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.743843 | 40.1109 | ETL.8365 | 40912678 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-12-11 | Released-Standard | Complete | Ready for Construction |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 120110504 | Q2 | DI GRBRVLLE-LYTNVLLE 059/010 RPL STRW | 31527338 | GARBERVILLE-LAYTONVILLE | 059/010 | 70Y | E | 2020_(1a) PSPS |  | 2020-11-20 | 2021-11-20 |  |  | 2021-04-19 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.741004 | 40.1106 | ETL.8365 | 40912677 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 120110505 | Q3 | T2 DI CARIBOU #2 001/000 RPR GYWW |  | CARIBOU #2 | 001/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-11-20 | 2021-11-20 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.160663 | 40.0789 | ETL.6280 | 40614758 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120110520 | Q2 | DI GARBERVILLE-LAYTONVILLE 56/7 RPR GYWW | 44542681 | GARBERVILLE-LAYTONVILLE | 056/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-20 | 2021-11-20 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.682087 | 40.0962 | ETL.8365 | 40912629 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120110523 | Q2 | DI GARBERVILLE-LAYTONVILLE 61/8 RMV DBRS | 44572981 | GARBERVILLE-LAYTONVILLE | 061/008 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-11-20 | 2021-11-20 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.769603 | 40.1116 | ETL.8365 | 40912697 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120110526 | Q2 | DI GARBERVILLE-LAYTONVILLE 61/8 RPR GYWW | 44542681 | GARBERVILLE-LAYTONVILLE | 061/008 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-20 | 2021-11-20 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.769603 | 40.1116 | ETL.8365 | 40912697 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120111197 | Not Scheduled | DI DRUM-SUMMIT #1 14/169 INS MRKW | 44575084 | DRUM-SUMMIT #1 | 014/169 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-23 | 2022-11-23 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.540892 | 39.3125 | ETL.1440 | 40597031 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120111985 | Q2 | DI GARBERVILLE-LYTNVL 59/7 RPLC INSW | 31522168 | GARBERVILLE-LAYTONVILLE | 059/007 | 93I | E | 2020_(2) High fire spread TD |  | 2020-11-20 | 2021-11-20 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.8365 | 40922483 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120112546 | Q2 | EI HAT CREEK #1-WESTWOOD 50/972 REFRAME | 31519637 | HAT CREEK #1-WESTWOOD | 050/972 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-12-01 | 2021-12-01 |  |  | 2021-06-25 | 2021-05-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.013717 | 40.3694 | ETL.7030 | 40861885 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-12-11 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120113055 | Not Scheduled | T3 DI CRESTA-RIO OSO 17/142 RMV HRDT |  | CRESTA-RIO OSO | 017/142 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-23 | 2021-05-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.480584 | 39.7208 | ETL.4590 | 40910158 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120113211 | Not Scheduled | DI DRUM-SUMMIT #2 16/197 RPR GYWW | 44575085 | DRUM-SUMMIT #2 | 016/197 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-24 | 2021-11-24 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.508787 | 39.3142 | ETL.1450 | 44557483 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120113213 | Not Scheduled | DI DRUM-SUMMIT #2 16/197 RPR GYWW | 44575085 | DRUM-SUMMIT #2 | 016/197 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-24 | 2021-11-24 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.508787 | 39.3142 | ETL.1450 | 44557785 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120113447 | Not Scheduled | DI DRUM-SUMMIT #1 15/179 RMV PL BUTT | 44575084 | DRUM-SUMMIT #1 | 015/179 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-23 | 2022-11-23 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.528114 | 39.3069 | ETL.1440 | 40870572 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120113638 | Feb | T3 DI DESABLA-CENTERVILE 2/30B REPL ANCW | 31522164 | DESABLA-CENTERVILLE | 002/030 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-11-30 | 2021-05-30 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.635438 | 39.839 | ETL.6720 | 42578821 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-02-12 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120113700 | Feb | T3NT DI DESABLA-CENTERVLE 2/30B RMV BUTT |  | DESABLA-CENTERVILLE | 002/030 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-30 | 2022-11-30 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.635438 | 39.839 | ETL.6720 | 42578821 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-12 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120113834 | Not Scheduled | DI DRUM-SUMMIT #2 014/172 REPL INSW | 31522060 | DRUM-SUMMIT #2 | 014/172 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-11-20 | 2021-11-20 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.540785 | 39.3126 | ETL.1450 | 40614317 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120113914 | Not Scheduled | WV T3 MNTE RIO-FLTN 8/005 RPL POLE | 31516226 | MONTE RIO-FULTON | 008/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-12-01 | 2021-06-01 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.914722 | 38.4883 | ETL.7630 | 40750278 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120114166 | Not Scheduled | T2 COLGATE-GRASS VALLEY 8/200 RPL POLE | 31519799 | COLGATE-GRASS VALLEY | 008/200 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-22 | 2021-10-22 | [7 empty] | TR2 |  | North Valley | [7 empty] | '-121.086663 | 39.2589 | ETL.6490 | 40768242 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120114201 | Not Scheduled | T2 COLGATE-GRASS VALLEY 9/218 RPL POLE | 31519799 | COLGATE-GRASS VALLEY | 009/218 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-10-21 | 2021-10-21 | [7 empty] | TR2 |  | North Valley | [7 empty] | '-121.083132 | 39.2466 | ETL.6490 | 40818423 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120114539 | Not Scheduled | T3 DI BEARDSLEY TAP 1/6C REPL INSS | 31519673 | BEARDSLEY TAP | 001/006C | 93I | E | 2020_(2) High fire spread TD |  | 2020-11-25 | 2021-05-25 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-120.060335 | 38.1922 | ETL.1401 | 42834651 | Insulator-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120114557 | Feb | DI RAVENSWOOD-SAN MATEO 10/75 HANGER PL | 44579151 | RAVENSWOOD-SAN MATEO | 010/075 | ICQ | B | 2020_(0) A and B Tags |  | 2020-11-24 | 2021-02-24 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-16 | [5 empty] | Central | WSIP | [6 empty] | '-122.313247 | 37.5819 | ETL.3430 | 40751218 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120114701 | Not Scheduled | T3NT DI BEARDSLEY TAP 0/8C REMV BUTT |  | BEARDSLEY TAP | 000/008C | ICW | F | 2020_(3) On high spread structure |  | 2020-11-25 | 2022-11-25 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-120.065535 | 38.1993 | ETL.1401 | 42834631 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120114704 | Not Scheduled | T3 DI BEARDSLEY TAP 0/8C REPL INSW | 31519673 | BEARDSLEY TAP | 000/008C | 93I | E | 2020_(2) High fire spread TD |  | 2020-11-25 | 2021-05-25 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-120.065535 | 38.1993 | ETL.1401 | 42834647 | Insulator-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120114709 | Not Scheduled | T3NT DI BEARDSLEY TAP 0/8B REMV BUTT |  | BEARDSLEY TAP | 000/008B | ICW | F | 2020_(3) On high spread structure |  | 2020-11-25 | 2022-11-25 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-120.065596 | 38.1993 | ETL.1401 | 42834630 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120114730 | Not Scheduled | T3 DI BEARDSLEY TAP 0/8B REPL INSW | 31519673 | BEARDSLEY TAP | 000/008B | 93I | E | 2020_(2) High fire spread TD |  | 2020-11-25 | 2021-05-25 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-120.065596 | 38.1993 | ETL.1401 | 42834646 | Insulator-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120114756 | Not Scheduled | T2 DI CRESTA-RIO OSO 027/217 RPR FOND |  | CRESTA-RIO OSO | 027/217 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-11-23 | 2021-11-23 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.526562 | 39.5859 | ETL.4590 | 41083078 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120114758 | Q2 | T2NT DI CRESTA-RIO OSO 027/217 INST MRKS |  | CRESTA-RIO OSO | 027/217 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-23 | 2022-11-23 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.526562 | 39.5859 | ETL.4590 | 41083078 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120114787 | Not Scheduled | DI DRUM-SUMMIT #1 15/178 RMV PL BUTT | 44579465 | DRUM-SUMMIT #1 | 015/178 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-23 | 2022-11-23 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5297 | 39.3072 | ETL.1440 | 44964943 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120114798 | Not Scheduled | DI DRUM-SUMMIT #2 16/190 SPLIT BOLT | 44575085 | DRUM-SUMMIT #2 | 016/190 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-24 | 2021-11-24 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.520386 | 39.3105 | ETL.1450 | 44552480 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120114819 | Not Scheduled | DI DRUM-SUMMIT #1 15/172 RMV DEBRIS | 44575084 | DRUM-SUMMIT #1 | 015/172 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-23 | 2022-11-23 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.537816 | 39.3103 | ETL.1440 | 40702400 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120114889 | Not Scheduled | DI DRUM-SUMMIT #2 15/178B REPL HRDD | 44575085 | DRUM-SUMMIT #2 | 015/178B | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-23 | 2021-11-23 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.5354 | 39.3083 | ETL.1450 | 44270078 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120114946 | Not Scheduled | DI DRUM-SUMMIT #1 15/173 REMV PL BUTT | 44579465 | DRUM-SUMMIT #1 | 015/173 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-23 | 2022-11-23 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.537335 | 39.3097 | ETL.1440 | 40653604 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120115043 | Not Scheduled | DI DRUM-SUMMIT #2 015/180 RPL INSS | 31527914 | DRUM-SUMMIT #2 | 015/180 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-11-24 | 2021-11-24 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.53168 | 39.3076 | ETL.1450 | 40784578 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120117486 | Q2 | WV IGNCIO-MRE ISLND #2 24/165 RPR INSS | 44585045 | IGNACIO-MARE ISLAND #2 | 024/165 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-02 | 2021-12-02 |  |  | 2021-06-03 | 2021-06-02 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.1763941 | 38.1346 | ETL.1840 | 40671464 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120117513 | Not Scheduled | DI DRUM-SUMMIT #1 15/175C RMV PL BUTT | 44579465 | DRUM-SUMMIT #1 | 015/175C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-23 | 2022-11-23 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.535552 | 39.3081 | ETL.1440 | 44338183 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120117518 | Not Scheduled | DI DRUM-SUMMIT #1 15/175C INS GMKW | 44579465 | DRUM-SUMMIT #1 | 015/175C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-23 | 2022-11-23 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.535552 | 39.3081 | ETL.1440 | 44338183 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120117640 | Not Scheduled | DI DRUM-SUMMIT #1 15/175C INS MRKW | 44579465 | DRUM-SUMMIT #1 | 015/175C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-23 | 2022-11-23 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.535552 | 39.3081 | ETL.1440 | 44338183 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120117646 | Mar | T2 DI FULTON-HOPLAND 12/0 RPR WDPKR |  | FULTON-HOPLAND | 012/000 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-23 | 2021-11-23 |  |  | 2021-03-12 | 2021-03-08 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.858097 | 38.6373 | ETL.6890 | 40587783 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120118049 | Q2 | EI SNEATH LANE-HMB ?2/0 RPR GYWS | 44620198 | SNEATH LANE-HALF MOON BAY | ?002/000 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-02 | 2021-12-02 |  |  | 2021-05-13 | 2021-04-16 | [5 empty] | Central | WSIP | [6 empty] | '-122.5006514 | 37.5729 | ETL.7212 | 44810087 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120118240 | Q2 | EI SNEATH LANE-HMB ?2/0 RPR GYWS | 44620198 | SNEATH LANE-HALF MOON BAY | ?002/000 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-02 | 2021-12-02 |  |  | 2021-05-13 | 2021-04-16 | [5 empty] | Central | WSIP | [6 empty] | '-122.5006514 | 37.5729 | ETL.7212 | 44810096 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120118283 | Q2 | EI SNEATH LANE-HMB ?2/0 RPR GYWS | 44620198 | SNEATH LANE-HALF MOON BAY | ?002/000 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-02 | 2021-12-02 |  |  | 2021-05-13 | 2021-04-16 | [5 empty] | Central | WSIP | [6 empty] | '-122.5006514 | 37.5729 | ETL.7212 | 44810095 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120118346 | Not Scheduled | T2 EI DRUM-GRASS VLY-WMR 18/430 RPR STRW | 44579347 | DRUM-GRASS VALLEY-WEIMAR | 018/430 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-12-02 | 2021-12-02 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-120.977281 | 39.0728 | ETL.6760 | 40598603 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120119011 | Not Scheduled | DI SPAULDING-SUMMIT 4/165 RPR GYWW | 44579355 | SPAULDING-SUMMIT | 004/165 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-23 | 2021-11-23 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.568561 | 39.3057 | ETL.8060 | 40809653 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120119098 | Not Scheduled | DI SPAULDING-SUMMIT 4/165 RPR WDPKR | 44579355 | SPAULDING-SUMMIT | 004/165 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-20 | 2021-11-20 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.568561 | 39.3057 | ETL.8060 | 40809653 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120119166 | Not Scheduled | T3 DI BEARDSLEY TAP 001/006B RPR STRW |  | BEARDSLEY TAP | 001/006B | ICW | E | 2020_(2) High fire spread TD |  | 2020-11-25 | 2021-05-25 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-120.060121 | 38.1923 | ETL.1401 | 42834634 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120119202 | Not Scheduled | T3 DI BEARDSLEY TAP 001/006B RPL INSW | 31519673 | BEARDSLEY TAP | 001/006B | 93I | E | 2020_(2) High fire spread TD |  | 2020-11-25 | 2021-05-25 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-120.060262 | 38.192 | ETL.1401 | 42834650 | Insulator-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120119327 | Q3 | T2 DI CARIBOU-WESTWOOD 15/304 RPR CRSW |  | CARIBOU-WESTWOOD | 015/304 | ICW | E | 2020_(2) High fire spread TD |  | 2020-11-23 | 2021-11-23 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.08785 | 40.2687 | ETL.6300 | 40656504 | Crossarm-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120605 | Feb | T3 DI DESABLA-CNTRVILLE 1/22B REPA GYWW |  | DESABLA-CENTERVILLE | 001/022 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-30 | 2021-05-30 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.631202 | 39.8503 | ETL.6720 | 44860100 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120616 | Not Scheduled | T2 EI SPAULDING-SUMMIT 001/042 RPR SPLS | 44579774 | SPAULDING-SUMMIT | 001/042 | ICS | E | 2020_(1b) Lines with special commitments |  | 2020-07-10 | 2021-07-10 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.6257 | 39.3196 | ETL.8060 | 44420793 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120120681 | Feb | T3NT DI DSBLA-CNTRVLLE 1/22C REMV BUTT |  | DESABLA-CENTERVILLE | 001/022 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-30 | 2022-11-30 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.631202 | 39.8503 | ETL.6720 | 44949090 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-31 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120687 | Feb | T3 DI DESABLA-CNTRVILLE 1/22C REPA GYWW |  | DESABLA-CENTERVILLE | 001/022 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-30 | 2021-05-30 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.631202 | 39.8503 | ETL.6720 | 44949090 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120693 | Q2 | T2 EI HAT CRK #1-WSTWD 002/060 RPR SPLS |  | HAT CREEK #1-WESTWOOD | 002/060 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-10 | 2021-07-10 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.488467 | 40.9195 | ETL.7030 | 40866448 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120697 | Q3 | T2 EI CARIBOU-PLUMAS JT 003/013 RPR SPLS |  | CARIBOU-PLUMAS JCT | 003/013 | ICS | E | 2020_(2) High fire spread TD |  | 2020-07-20 | 2021-07-20 |  |  | 2021-08-20 | 2021-08-02 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.095261 | 40.0509 | ETL.6290 | 40666895 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120722 | Mar | T3 EI DRUM-RIO OSO #2 003/035 RPR SPLS | 44579769 | DRUM-RIO OSO #2 | 003/035 | ICS | E | 2020_(1a) PSPS |  | 2020-07-16 | 2021-01-16 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.822226 | 39.2389 | ETL.1430 | 44305006 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1a) PSPS | Pending Repair | 2021 Plan | 2021-05-31
2021 Work Plan | 120120723 | Q2 | T3 EI VOLTA-DESCHUTES 003/066 RPR SPLS |  | VOLTA-DESCHUTES | 003/066 | ICS | E | 2020_(2) High fire spread TD |  | 2020-06-26 | 2020-12-26 |  |  | 2021-04-09 | 2021-04-05 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.92208 | 40.4734 | ETL.8290 | 40634691 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120726 | Q2 | T2 EI WEIMAR #1 004/066 RPR SPLS | 44579775 | WEIMAR #1 | 004/066 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-01 | 2021-07-01 |  |  | 2021-04-08 | 2021-03-22 | [5 empty] | North Valley | WSIP | [8 empty] | ETL.7560 | 44414830 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120727 | Mar | EI COALINGA #1-SAN MGL 005/086 RPR SPLS | 44623665 | COALINGA #1-SAN MIGUEL | 005/086 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-21 | 2021-07-21 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.415576 | 36.0998 | ETL.8580 | 40584310 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120777 | Feb | T3 EI DRUM-RIO OSO #1 007/073 RPR SPLS | 44579268 | DRUM-RIO OSO #1 | 007/073 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-08-28 | 2021-02-28 |  |  | 2021-02-23 | 2021-02-10 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.867843 | 39.2006 | ETL.1420 | 40683423 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120786 | Not Scheduled | T3 DI DRUM-SUMMIT #1 03/41B RPR STRW |  | DRUM-SUMMIT #1 | 003/041B | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-11-30 | 2021-05-30 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.724408 | 39.2811 | ETL.1440 | 42572626 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120787 | Not Scheduled | T3NT DI DRUM-SUMMIT#1 03/41B RMV DBRS | 44575084 | DRUM-SUMMIT #1 | 003/041B | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-30 | 2022-11-30 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.724408 | 39.2811 | ETL.1440 | 42572626 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120870 | Not Scheduled | T3 EI COLGATE-ALLEGHANY 008/231 RPR SPLS | 44579764 | COLGATE-ALLEGHANY | 008/231 | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-24 | 2020-10-24 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.049275 | 39.365 | ETL.6470 | 40635560 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120871 | Not Scheduled | T3 EI COLGATE-ALLEGHANY 009/264 RPR SPLS | 44579764 | COLGATE-ALLEGHANY | 009/264 | ICS | E | 2020_(2) High fire spread TD |  | 2020-04-25 | 2020-10-25 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.036797 | 39.3781 | ETL.6470 | 40846580 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120876 | Mar | T3 EI DRUM-RIO OSO #2 010/109 RPR SPLS | 44579769 | DRUM-RIO OSO #2 | 010/109 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-07-06 | 2021-01-06 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.1430 | 44305019 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120933 | Not Scheduled | DI NEWARK-JARVIS #1 10/64 REPL INSS | 31529487 | NEWARK-JARVIS #1 | 010/064 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-11-25 | 2021-11-25 | [9 empty] | Central | WSIP | [6 empty] | '-121.957116 | 37.5869 | ETL.3020 | 40774137 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120936 | Not Scheduled | DI DRUM-SUMMIT #2 17/208R REPA STRW | 31521949 | DRUM-SUMMIT #2 | 017/208 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-11-30 | 2021-11-30 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.493465 | 39.315 | ETL.1450 | 44549989 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120120937 | Not Scheduled | DI DRUM-SUMMIT #2 17/208L REPA STRW | 31521949 | DRUM-SUMMIT #2 | 017/208 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-11-30 | 2021-11-30 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.493465 | 39.315 | ETL.1450 | 44549862 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120120941 | Q2 | T2 DI TRINITY-MAPLE CRK 53/03B RPL POLE | 31522401 | TRINITY-MAPLE CREEK | 053/003B | 70Y | E | 2020_(2) High fire spread TD |  | 2020-11-30 | 2021-11-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.861912 | 40.7714 | ETL.8170 | 40668488 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120120956 | Feb | T3 DI ROCK CRK-POE 016/113 RPNT / CRSRM |  | ROCK CREEK-POE | 016/113 | ICD | E | 2020_(4) TD tag on high spread line |  | 2020-11-24 | 2021-05-24 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.48287 | 39.7089 | ETL.5630 | 40685743 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120121022 | Q2 | T3 DI WEIMAR #1 014/185C RPR STRW | 44579776 | WEIMAR #1 | 014/185C | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-30 | 2021-05-30 |  |  | 2021-04-08 | 2021-03-22 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.746617 | 39.0116 | ETL.7560 | 44415228 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120121025 | Not Scheduled | DI DRUM-SUMMIT #1 016/185B RPR GYWW | 44579324 | DRUM-SUMMIT #1 | 016/185B | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-12-01 | 2021-12-01 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.520422 | 39.3098 | ETL.1440 | 42572688 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120121061 | Not Scheduled | T2NT DI CLGTE-SMRTVLLE #2 RMV BUTT | 44579681 | COLGATE-SMARTVILLE #2 | 000/007C | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-25 | 2022-11-25 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.193703 | 39.3291 | ETL.6520 | 42562715 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120121583 | Not Scheduled | DI DRUM-SUMMIT #1 16/185C RPR GYWW | 44579324 | DRUM-SUMMIT #1 | 016/185C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-12-01 | 2021-12-01 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.520372 | 39.3098 | ETL.1440 | 42572689 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120122742 | Not Scheduled | DI DRUM-SUMMIT #2 16/191 RPLC STRW | 31521945 | DRUM-SUMMIT #2 | 016/191 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-11-24 | 2021-11-24 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.519883 | 39.3115 | ETL.1450 | 44559186 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120123010 | Not Scheduled | DI DRUM-SUMMIT #2 17/209 RPLC INSW |  | DRUM-SUMMIT #2 | 017/209 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-11-30 | 2021-11-30 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.492487 | 39.3151 | ETL.1450 | 41120245 | Insulator-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120123726 | Feb | DI DIXON-VACA #1 000/004 BENT STL | 44579178 | DIXON-VACA #1 | 000/004 | ICQ | B | 2020_(0) A and B Tags |  | 2020-12-02 | 2021-03-02 |  |  | 2021-02-19 | 2021-02-16 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.913267 | 38.4027 | ETL.6730 | 40576443 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLM | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-14 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120124545 | Not Scheduled | T3NT DI DRUM-SUMMIT #2 0/3C RMV DEBRIS | 44579467 | DRUM-SUMMIT #2 | 000/003C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-12-01 | 2022-06-01 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.763869 | 39.2551 | ETL.1450 | 44868833 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120124547 | Not Scheduled | T3NT DI DRUM-SUMMIT #2 0/3C INS MRKS | 44579467 | DRUM-SUMMIT #2 | 000/003C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-12-01 | 2022-06-01 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.763869 | 39.2551 | ETL.1450 | 44868833 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120124648 | Feb | EI DESABLA-OROVILLE 2/030 RMV DEBRIS |  | DESABLA-CENTERVILLE | 002/030 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-12-03 | 2022-12-03 |  |  | 2021-02-17 | 2021-02-15 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.635438 | 39.839 | ETL.6720 | 44926545 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-12 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120124953 | Q2 | T2 DI TRINITY-MAPLE CRK 53/03C RPL POLE | 31522401 | TRINITY-MAPLE CREEK | 053/003C | 70Y | E | 2020_(2) High fire spread TD |  | 2020-11-30 | 2021-11-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.861922 | 40.7714 | ETL.8170 | 44420778 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120124954 | Q2 | T2 DI TRINITY-MAPLE CRK 53/03A RPL POLE | 31522401 | TRINITY-MAPLE CREEK | 053/003A | 70Y | E | 2020_(2) High fire spread TD |  | 2020-11-30 | 2021-11-30 |  |  | 2021-04-17 | 2021-04-05 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.861905 | 40.7714 | ETL.8170 | 44420777 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120124956 | Feb | SLAC TAP 0/8 RPLC STRW | 31519840 | SLAC TAP (NO FLY) | 000/008 | 70Y | B | 2020_(0) A and B Tags |  | 2020-12-03 | 2021-03-03 |  |  | 2021-02-21 | 2021-02-21 | [5 empty] | Central | WSIP | [6 empty] | '-122.191305 | 37.4194 | ETL.7221 | 40875274 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2020-12-23 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120124959 | Mar | T3 DI MONTA VISTA-BURNS 7/64B RPR GYWW | 44634957 | MONTA VISTA-BURNS | 007/064 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-30 | 2021-05-30 |  |  | 2021-03-18 | 2021-03-17 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-122.139978 | 37.2299 | ETL.7590 | 44950346 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120125151 | Not Scheduled | T3 DI DRUM-SUMMIT #2 4/55C RPL STRW |  | DRUM-SUMMIT #2 | 004/055C | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-01 | 2021-06-01 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.704252 | 39.2923 | ETL.1450 | 42572756 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120125152 | Not Scheduled | T3 DI DRUM-SUMMIT #2 4/55C RPR GYWW | 44579331 | DRUM-SUMMIT #2 | 004/055C | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-12-01 | 2021-06-01 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.704252 | 39.2923 | ETL.1450 | 42572756 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120125154 | Not Scheduled | T3 DI DRUM-SUMMIT #2 4/55C RPLC INSS |  | DRUM-SUMMIT #2 | 004/055C | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-12-01 | 2021-06-01 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.704288 | 39.2923 | ETL.1450 | 42573081 | Insulator-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120125369 | Q2 | DI GARBERVILLE-LAYTONVILLE 37/2 RPR GYWW | 44542681 | GARBERVILLE-LAYTONVILLE | 037/002 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-30 | 2021-11-30 |  |  | 2021-05-17 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.569116 | 39.859 | ETL.8365 | 44403643 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120125426 | Not Scheduled | T3 DI DRUM PH #2 TAP 000/001C DUP CNCL |  | DRUM PH #2 TAP | 000/001C | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-30 | 2021-05-30 | [6 empty] | CANCEL/CNCL | TR3 |  | North Valley | WSIP | [6 empty] | '-120.766333 | 39.2571 | ETL.6375 | 43196977 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120125428 | Feb | T3NT DI DESBLA-CENTERVILLE 1/26 RMV DBRS |  | DESABLA-CENTERVILLE | 001/026 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-30 | 2022-11-30 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.633143 | 39.8452 | ETL.6720 | 42578815 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-31 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120125554 | Not Scheduled | T2 CARIBOU-TABLE MTN 24/173 BENT STL |  | CARIBOU-TABLE MTN | 024/173 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-12-03 | 2021-12-03 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.333232 | 39.928 | ETL.4440 | 40656163 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120125612 | Feb | T3 DI DESABLA-CENTERVILLE 001/026 RPR GY |  | DESABLA-CENTERVILLE | 001/026 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-30 | 2021-05-30 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.633143 | 39.8452 | ETL.6720 | 42578815 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120125727 | Feb | T3 DI DESABLA-CENTERVILLE 2/33 RPR GYWW |  | DESABLA-CENTERVILLE | 002/033 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-12-01 | 2021-06-01 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.637065 | 39.8342 | ETL.6720 | 44922939 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120125728 | Feb | T3 DI DESABLA-CENTERVILLE 2/33 RPL ANCHR | 31522164 | DESABLA-CENTERVILLE | 002/033 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-12-01 | 2021-06-01 |  |  | 2021-02-17 | 2021-02-15 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.637065 | 39.8342 | ETL.6720 | 44922939 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-12-11 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120126165 | Q3 | DI TESLA-NEWARK #2 12/84 REPA FOND |  | TESLA-NEWARK #2 | 012/084 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-10-08 | 2021-10-08 |  |  | 2021-07-30 | 2021-07-26 | [5 empty] | Central | WSIP | [6 empty] | '-121.769002 | 37.6379 | ETL.5354 | 41152629 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120126493 | Q4 | T2 DI KESWICK-TRINITY 18/244 RMV BUTT |  | KESWICK-TRINITY | 018/244 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-07 | 2022-10-07 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.712218 | 40.7223 | ETL.7270 | 44649258 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120126496 | Not Scheduled | DI RAVENSWOOD-AMES #1 002/015 RPR SHLS | 44579636 | RAVENSWOOD-AMES #1 | 002/015 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-01 | 2021-03-01 | [8 empty] | <15D | Central | WSIP |  |  |  |  | Permit/Environmental | AT RISK, (EXEMPTION) work was attempted as scheduled(1/19/2021), could not complete due to weather condition using boat. EVIRO-No work allowed beyond scheduled dates. | '-122.116545 | 37.466 | ETL.3360 | 40644168 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 7 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120126518 | Q3 | T2NT DI CRBOU-WSTWD 001/031A RMV DEBRIS |  | CARIBOU-WESTWOOD | 001/031A | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-07 | 2022-10-07 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.128261 | 40.0979 | ETL.6300 | 40875472 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120126542 | Not Scheduled | DI WEST PNT-VLLY SPRINGS 18/251 RPR POLE |  | WEST POINT-VALLEY SPRINGS | 018/251 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-11-25 | 2021-11-25 | [9 empty] | Central | WSIP | [6 empty] | '-120.75577 | 38.2476 | ETL.8350 | 44885840 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120126593 | Not Scheduled | DI DIVIDE-CABRILLO #1 2/35 RMV BUTT |  | DIVIDE-CABRILLO #1 | 002/035 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-09 | 2022-10-09 | [9 empty] | South | WSIP | [6 empty] | '-120.442411 | 34.7912 | ETL.1380 | 40757625 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120126680 | Q2 | T2 DI SAN LUS OBSP OCNO 4/23 MASTIC | 44584871 | SAN LUIS OBISPO-OCEANO | 004/023 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-10-09 | 2022-10-09 |  |  | 2021-04-15 | 2021-04-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.579139 | 35.2138 | ETL.3530 | 40659675 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120128554 | Mar | T3 DI MONTA VISTA-BURNS 7/65C RPR GYWW | 44634957 | MONTA VISTA-BURNS | 007/065 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-30 | 2021-05-30 |  |  | 2021-03-18 | 2021-03-17 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-122.14192 | 37.2268 | ETL.7590 | 44984471 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120128557 | Mar | T3NT DI MONTA VISTA-BURNS 7/65C RMV DBRS | 44634957 | MONTA VISTA-BURNS | 007/065 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-30 | 2022-11-30 |  |  | 2021-03-18 | 2021-03-17 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-122.14192 | 37.2268 | ETL.7590 | 44984471 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120128573 | Q2 | T2NT DI BRDGVLLE-CTTNWD 051/385 RPR OPGW | 44477511 | BRIDGEVILLE-COTTONWOOD | 051/385 | ICS | F | 2020_(2) High fire spread TD |  | 2020-08-05 | 2022-08-05 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.215351 | 40.415 | ETL.1110 | 40592233 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120129679 | Not Scheduled | DI SPAULDING-SUMMIT 07/250 RMV BUTT | 44579928 | SPAULDING-SUMMIT | 007/250 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-20 | 2022-10-20 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.526327 | 39.3067 | ETL.8060 | 44349509 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120129896 | Q2 | T3NT NN IGNACIO-BOLINAS #1 8/95 RMV BUTT | 44640733 | IGNACIO-BOLINAS #1 | 008/095 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-22 | 2022-10-22 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.6556 | 38.004 | ETL.7140 | 40701396 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120130236 | Feb | T3 WV EGL RCK-FLTN-SLVRD26/116 REPL INSS | 31530073 | EAGLE ROCK-FULTON-SILVERADO | 026/116 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-12-04 | 2021-06-04 |  |  | 2021-02-28 | 2021-02-28 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.598994 | 38.4795 | ETL.4392 | 44942636 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120130239 | Not Scheduled | T3 WV FULTON-PUEBLO 31/152 RPR INSS |  | FULTON-PUEBLO | 031/152 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-04 | 2021-06-04 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.5503 | 38.4856 | ETL.1600 | 40656848 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120130385 | Not Scheduled | COTTONWOOD #1 18/127 RPL HRDS | 44631230 | COTTONWOOD #2 | 018/127 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-04 | 2021-12-04 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.25587 | 40.1231 | ETL.6630 | 45003895 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120130470 | Feb | DI MV-JEFF #1 1/8 MASTIC |  | MONTA VISTA-JEFFERSON #1 | 001/008 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-10-20 | 2022-10-20 |  |  | 2021-02-20 | 2021-02-15 | [5 empty] | Central | WSIP | [6 empty] | '-122.101621 | 37.3283 | ETL.5220 | 40863177 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120130612 | Q3 | T2 DI BRIDGEVILLE-CTTNWD 59/433 RPL INSS | 31529414 | BRIDGEVILLE-COTTONWOOD | 059/433 | 93K | E | 2020_(2) High fire spread TD |  | 2020-12-04 | 2021-12-04 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.35932 | 40.3716 | ETL.1110 | 40799052 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  | 2020-12-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120130653 | Not Scheduled | DI SPAULDING-SUMMIT 008/282 RMV BUTT | 44579928 | SPAULDING-SUMMIT | 008/282 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-20 | 2022-10-20 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.507897 | 39.3138 | ETL.8060 | 44349519 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120130938 | Q3 | T2 DI BRIDGEVILLE-CTTNWD 62/449 RPR INSS |  | BRIDGEVILLE-COTTONWOOD | 062/449 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-04 | 2021-12-04 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.400256 | 40.3833 | ETL.1110 | 43693238 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120131787 | Q2 | T3 GREEN VLLY-PL SWT 11/103 RPR BOND WIR | 44591679 | GREEN VALLEY-PAUL SWEET | 011/103 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-12-04 | 2021-06-04 |  |  | 2021-06-08 | 2021-06-07 |  |  |  | TR3 | SCHD | South | WSIP | [6 empty] | '-121.918551 | 37.0102 | ETL.1730 | 40876809 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120132237 | Not Scheduled | T2 DRUM-SUMMIT #2 021/260 RPL STRW | 31519796 | DRUM-SUMMIT #2 | 021/260 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-04 | 2021-05-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.416796 | 39.3283 | ETL.1450 | 44559031 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120133276 | Q2 | DI PITTSBURG-SAN MATEO 16/63 MASTIC |  | PITTSBURG-SAN MATEO | 016/063 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-10-12 | 2022-10-12 |  |  | 2021-04-24 | 2021-04-19 | [5 empty] | Central | WSIP | [6 empty] | '-121.902647 | 37.8173 | ETL.5463 | 40858018 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120133312 | Not Scheduled | DI SPAULDING-SUMMIT 007/249 RMV BUTT | 44579928 | SPAULDING-SUMMIT | 007/249 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-20 | 2022-10-20 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.526758 | 39.3067 | ETL.8060 | 44349508 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120133345 | Not Scheduled | DI NEWARK-JARVIS #1 010/065 INST MRKS | 44598134 | NEWARK-JARVIS #1 | 010/065 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-22 | 2022-10-22 | [9 empty] | Central | WSIP | [6 empty] | '-121.964475 | 37.5888 | ETL.3020 | 40745980 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120133346 | Mar | DI NEWARK-JARVIS #1 010/065 RPR FOND |  | NEWARK-JARVIS #1 | 010/065 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-10-22 | 2022-10-22 |  |  | 2021-03-27 | 2021-03-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.964475 | 37.5888 | ETL.3020 | 40745980 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120133570 | Not Scheduled | NT DI GTS-MSTNG SS #1 000/006 INST MRKS | 44623661 | SPARE T-LINE RECORD | 000/006 | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-10-21 | 2022-10-21 | [9 empty] | South | WSIP | [6 empty] | '-120.112936 | 36.1464 | ETL.2604 | 40805358 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120133582 | Mar | DI NEWARK-JARVIS #1 011/067 RPR FOND |  | NEWARK-JARVIS #1 | 011/067 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-10-23 | 2022-10-23 |  |  | 2021-03-27 | 2021-03-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.970129 | 37.5904 | ETL.3020 | 40804735 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120133636 | Q2 | NN GATES-PANOCHE #1 10/50 RPR FOND | 44584843 | GATES-PANOCHE #1 | 010/050 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-08-12 | 2022-08-12 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.22429 | 36.2666 | ETL.4720 | 40592384 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120133659 | Not Scheduled | T3NT MISR FLT-GLD HLL #1 19/162 RPR FOND | 44580376 | MISSOURI FLAT-GOLD HILL #1 | 019/162 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-10-23 | 2022-10-23 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.906053 | 38.6618 | ETL.2660 | 40913118 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLM | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120133775 | Not Scheduled | T2 NT DI SPLDNG-SMMT 15/488 INST MRKW | 44579928 | SPAULDING-SUMMIT | 015/488 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-19 | 2022-10-19 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.385753 | 39.3287 | ETL.8060 | 44349563 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120133790 | Not Scheduled | T2NT DI SPALDING-SUMIT 11/382 RMV DEBRIS | 44580885 | SPAULDING-SUMMIT | 011/382 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-19 | 2022-10-19 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.455718 | 39.3182 | ETL.8060 | 44349555 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120133881 | Not Scheduled | T3NT NN MAPLE CREEK-HOOPA 23/11 RMV DBRS | 44593017 | MAPLE CREEK-HOOPA | 023/011 | ICW | F | 2020_(3) On high spread structure |  | 2020-10-16 | 2022-10-16 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-123.645913 | 40.9973 | ETL.7490 | 40602136 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120133882 | Not Scheduled | T2 NT DI SPAULDING-SUMMIT 12/410 INS MRK | 44579928 | SPAULDING-SUMMIT | 012/410 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-19 | 2022-10-19 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.44283 | 39.319 | ETL.8060 | 44156133 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120133889 | Not Scheduled | T2NT DI SPAULDING-SUMMIT 9/331 RMV BUTT | 44580885 | SPAULDING-SUMMIT | 009/331 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-19 | 2022-10-19 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.483039 | 39.3169 | ETL.8060 | 44349540 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120133948 | Mar | T3 DI MNTA VISTA-BURNS 7/65L RPR GYWW | 44634957 | MONTA VISTA-BURNS | 007/065 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-30 | 2021-05-30 |  |  | 2021-03-18 | 2021-03-17 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-122.14192 | 37.2268 | ETL.7590 | 44984470 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120134024 | Feb | NT DI RND MTN CTNWD #3 55/496 RMV DEBRIS | 44624619 | ROUND MTN-COTTONWOOD #3 | 055/496 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-12-05 | 2022-12-05 |  |  | 2021-02-19 | 2021-02-15 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.223248 | 40.4495 | ETL.5650 | 40817529 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120134042 | Mar | T3 DI MONTA VISTA-BURNS 7/65R RPR GYWW | 44634957 | MONTA VISTA-BURNS | 007/065 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-30 | 2021-05-30 |  |  | 2021-03-18 | 2021-03-17 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-122.14192 | 37.2268 | ETL.7590 | 44984469 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120134048 | Not Scheduled | T3NT DI DRUM-SUMMIT#2 0/3A RMV BUTT | 44579833 | DRUM-SUMMIT #2 | 000/003A | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-26 | 2022-10-26 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.763828 | 39.2552 | ETL.1450 | 44868831 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120134078 | Q2 | DI KESWICK-TRINITY 030/526 RPL HRDT |  | KESWICK-TRINITY | 030/526 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-12-05 | 2021-12-05 |  |  | 2021-05-13 | 2021-04-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.928571 | 40.7138 | ETL.7270 | 44422686 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120134237 | Feb | DI MNTA VSTA-JFRSN #1 00/06 MASTIC |  | MONTA VISTA-JEFFERSON #1 | 000/006 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-10-21 | 2022-10-21 |  |  | 2021-02-20 | 2021-02-15 | [5 empty] | Central | WSIP | [6 empty] | '-122.091355 | 37.327 | ETL.5220 | 40811339 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120134242 | Not Scheduled | DI HMBLDT-BRDGVLL 106/001 INST MRKS |  | HUMBOLDT-BRIDGEVILLE | 106/001 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-16 | 2022-10-16 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.951865 | 40.7301 | ETL.1810 | 40590930 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120135331 | Feb | DI STANSLS-MLNS-MNTC 27/167 INST WASHR | 44580178 | STANISLAUS-MELONES SS-MANTECA #1+ | 026/167 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-05 | 2021-03-05 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | Central | WSIP | [6 empty] | '-120.768366 | 37.9236 | ETL.3830 | 40751408 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120135335 | Feb | DI STANISLAUS-MLNS-MNTC 26/168 COTR KEY | 44580240 | STANISLAUS-MELONES SS-MANTECA #1+ | 026/168 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-05 | 2021-03-05 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | Central | WSIP | [6 empty] | '-120.770281 | 37.923 | ETL.3830 | 40829023 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120135336 | Feb | DI STANISLAUS-MLNS-MNTC 26/168 INS HRDS | 44586088 | STANISLAUS-MELONES SS-MANTECA #1+ | 026/168 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-05 | 2021-03-05 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | Central | WSIP | [6 empty] | '-120.770255 | 37.923 | ETL.3830 | 40803337 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120135338 | Feb | DI STANISLAUS-MLNS-MNTC 49/315 INS HRDS | 44580241 | STANISLAUS-MELONES SS-MANTECA #1+ | 049/315 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-05 | 2021-03-05 |  |  | 2021-02-22 | 2021-02-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.153087 | 37.8172 | ETL.3830 | 40750243 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120135341 | Q2 | T3 DI CRESTA-RIO OSO 020/165 RPL DAMS |  | CRESTA-RIO OSO | 020/165 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-12-04 | 2021-06-04 |  |  | 2021-04-02 | 2021-03-29 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.513322 | 39.6324 | ETL.4590 | 44237876 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120135356 | Not Scheduled | T2 DI BLACK TAP 000/003 RMV NEST |  | BLACK TAP | 000/003 | ICS | E | 2020_(4b) On structure in bucket 4 |  | 2020-12-04 | 2021-12-04 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.978299 | 40.9876 | ETL.5431 | 44188817 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120135401 | Mar | DI STANISLAUS-MLNS-MNTC 49/315 RPR STRT | 44580242 | STANISLAUS-MELONES SS-MANTECA #1+ | 049/315 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-05 | 2021-03-05 | 2021-03-03 | 2021-03-03 | 2021-03-03 | 2021-03-03 |  |  | Likely MAT error - delink to correct |  |  | Central | WSIP | [6 empty] | '-121.153087 | 37.8172 | ETL.3830 | 40750243 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120135402 | Feb | DI WEBER-FRENCH CAMP #1 2/43 RPLC POLE | 31418889 | WEBER #1 | 002/043 | 70Y | B | 2020_(0) A and B Tags |  | 2020-12-05 | 2021-03-05 |  |  | 2021-02-16 | 2021-02-16 |  | LC 115464915 exists for same work, DLFL 115464915 | No action |  |  | Central | WSIP | [6 empty] | '-121.273092 | 37.9073 | ETL.8320 | 40825591 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-26 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120135436 | Q2 | DI GARBERVILLE-LYTNVL 56/7 REPULL GUY | 44542681 | GARBERVILLE-LAYTONVILLE | 056/007 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-12-04 | 2021-12-04 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.681971 | 40.0963 | ETL.8365 | 43597914 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120135453 | Feb | DI PTSBRG-KRK-COLUMBIA STL :0/1 RPR SWTS | 44580016 | PITTSBRG-KIRKER-COLUMBIA STEEL | :000/001 | ICE | B | 2020_(0) A and B Tags |  | 2020-12-04 | 2021-03-04 |  |  | 2021-02-18 | 2021-02-18 | [5 empty] | Central | WSIP | [6 empty] | '-121.871401 | 37.9876 | ETL.3310 | 43210302 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120135454 | Feb | DI PTSBRG-COLUMBIA STL :0/1 RPR SWTS | 44580015 | PITTSBURG-COLUMBIA STEEL | 000/001 | ICE | B | 2020_(0) A and B Tags |  | 2020-12-04 | 2021-03-04 |  |  | 2021-02-17 | 2021-02-17 | [5 empty] | Central | WSIP | [6 empty] | '-121.87195 | 37.9874 | ETL.3300 | 40743392 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-18 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120135586 | Not Scheduled | DI KESWICK-TRINITY 030/530 RPR FOND |  | KESWICK-TRINITY | 030/530 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-12-04 | 2022-12-04 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.93172 | 40.7154 | ETL.7270 | 44422690 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120135610 | Feb | DI STNSLS-MLNS SW ST-MTC 27/174 INS WSHR | 44580243 | STANISLAUS-MELONES SS-MANTECA #1+ | 027/174 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-04 | 2021-03-04 |  |  | 2021-02-22 | 2021-02-12 | [5 empty] | Central | WSIP | [6 empty] | '-120.786729 | 37.9181 | ETL.3830 | 40687272 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120135998 | Not Scheduled | T2 DRUM-SUMMIT #2 021/260 RPL STRW |  | DRUM-SUMMIT #2 | 021/260 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-04 | 2021-05-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.416796 | 39.3283 | ETL.1450 | 44558990 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | Yes | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not Scheduled | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120136256 | Not Scheduled | T2 DI DRUM-SUMMIT #2 8/98B CANCEL | 44580361 | DRUM-SUMMIT #2 | 008/098B | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-12-01 | 2021-12-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.642684 | 39.318 | ETL.1450 | 44968859 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120136258 | Not Scheduled | T2 DI DRUM-SUMMIT #2 8/98B CANCEL | 44580361 | DRUM-SUMMIT #2 | 008/098B | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-12-01 | 2021-12-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.642684 | 39.318 | ETL.1450 | 44968859 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120136320 | Not Scheduled | T2 DI DRUM-SUMMIT #2 8/98B CANCEL | 44580370 | DRUM-SUMMIT #2 | 008/098B | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-12-01 | 2022-12-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.642684 | 39.318 | ETL.1450 | 44968859 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120136327 | Mar | T2 DI MONTA VISTA-BURNS 2/22 RPLC INSW | 31520323 | MONTA VISTA-BURNS | 002/022 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-11-30 | 2021-11-30 |  |  | 2021-03-18 | 2021-03-17 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-122.095782 | 37.3034 | ETL.7590 | 42565658 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120136548 | Not Scheduled | WV LAYTONVILLE-WILLITS 4/005 RPL POLE | 35228150 | LAYTONVILLE-WILLITS | 004/005 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-12-07 | 2021-12-07 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.339849 | 39.4595 | ETL.8360 | 40768660 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120136797 | Feb | T2 DI COLGTE-GRASS VALLEY 9/217 RPR WDPK | 44587952 | COLGATE-GRASS VALLEY | 009/217 | ICW | E | 2020_(4b) On structure in bucket 4 |  | 2020-11-25 | 2021-11-25 |  |  | 2021-02-27 | 2021-02-12 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.083287 | 39.2471 | ETL.6490 | 44975419 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120137666 | Not Scheduled | T3NT COLGATE-CHALLENGE 3/079 INS MRKW | 44580718 | COLGATE-CHALLENGE | 003/079 | ICW | F | 2020_(2) High fire spread TD |  | 2020-12-04 | 2022-12-04 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.163176 | 39.3795 | ETL.6480 | 40873617 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120139212 | Q2 | DI GATES-PANOCHE #1 18/86 MASTIC | 44584843 | GATES-PANOCHE #1 | 018/086 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-10-30 | 2022-10-30 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.309537 | 36.3525 | ETL.4720 | 40811792 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120139215 | Not Scheduled | NN SPAULDING-SUMMIT 4/168 INST MRKW | 44580885 | SPAULDING-SUMMIT | 004/168 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-29 | 2022-10-29 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.566941 | 39.3058 | ETL.8060 | 42571849 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120139264 | Not Scheduled | NN SPAULDING-SUMMIT 5/198 RMV BUTT | 44580885 | SPAULDING-SUMMIT | 005/198 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-29 | 2022-10-29 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.553204 | 39.3049 | ETL.8060 | 40876721 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120139266 | Not Scheduled | NN SPAULDING-SUMMIT 5/198 INST MRKW | 44580885 | SPAULDING-SUMMIT | 005/198 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-29 | 2022-10-29 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.553204 | 39.3049 | ETL.8060 | 40876721 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120139270 | Q2 | T2NT DI PTTSBURG-SAN MATEO 7/31 RPR FOND |  | PITTSBURG-SAN MATEO | 007/031 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-10-30 | 2022-10-30 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.893521 | 37.9435 | ETL.5463 | 40822249 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120139282 | Q3 | DI GATES-MUSTANG SW STA#1 12/53 MASTIC | 44584852 | SPARE T-LINE RECORD | 012/053 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-10-29 | 2022-10-29 |  |  | 2021-08-01 | 2021-06-02 | [5 empty] | South | WSIP | [6 empty] | '-119.924542 | 36.2289 | ETL.2604 | 40650475 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120139311 | Not Scheduled | T2NT NN SPALDING-SUMIT 10/356 RMV DEBRIS | 44580885 | SPAULDING-SUMMIT | 010/356 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-10-28 | 2022-10-28 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.469592 | 39.3185 | ETL.8060 | 40861947 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120139367 | Q3 | T2 DI BRIDGEVILLE-CTTNWD 61/466 RPR OPGW |  | BRIDGEVILLE-COTTONWOOD | 061/446 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-05 | 2021-12-05 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.393994 | 40.381 | ETL.1110 | 40817268 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120139386 | Mar | DI NEWARK-JARVIS #1 08/54 RPR FOND | 44631843 | NEWARK-JARVIS #1 | 008/054 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-10-30 | 2022-10-30 |  |  | 2021-03-27 | 2021-03-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.929555 | 37.5694 | ETL.3020 | 40747000 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120139397 | Not Scheduled | DI GATES-MUSTANG SW S #1 13/54A PAINT | 44634134 | SPARE T-LINE RECORD | 013/054A | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-10-29 | 2022-10-29 | [9 empty] | South | WSIP | [6 empty] | '-119.920118 | 36.231 | ETL.2604 | 44212915 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120139430 | Q2 | T2 DI BRIDGEVILLE-CTTNWD 51/386 RPR OPGW | 44477511 | BRIDGEVILLE-COTTONWOOD | 051/386 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-05 | 2021-12-05 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.218267 | 40.4144 | ETL.1110 | 40683980 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120139431 | Mar | DI NEWARK-JARVIS #1 8/53 REPA FOND | 44631843 | NEWARK-JARVIS #1 | 008/053 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-10-30 | 2022-10-30 |  |  | 2021-03-27 | 2021-03-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.927447 | 37.5677 | ETL.3020 | 40644297 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120139479 | Not Scheduled | DI GARBRVLLE-LYTNVLE 51/9 HIGH SIGN | 44542681 | GARBERVILLE-LAYTONVILLE | 051/009 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-30 | 2022-10-30 | [9 empty] | North Coast | WSIP | [6 empty] | '-123.64083 | 40.044 | ETL.8365 | 40912578 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120140205 | Q2 | DI PITTSBURG-SAN MATEO 021/083 RPR FOND |  | PITTSBURG-SAN MATEO | 021/083 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-11-02 | 2022-11-02 |  |  | 2021-04-24 | 2021-04-19 | [5 empty] | Central | WSIP | [6 empty] | '-121.929733 | 37.7458 | ETL.5463 | 40858020 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120140527 | Q2 | DI IGNACIO-SOBRANTE 011/048 RPR FOND |  | IGNACIO-SOBRANTE | 011/048 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-11-02 | 2022-11-02 |  |  | 2021-05-28 | 2021-05-24 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.474842 | 38.1394 | ETL.4920 | 40871764 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-01 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120140704 | Feb | DI STANISLAUS-MLNS-MNTC 27/173 INS WASHR | 44586090 | STANISLAUS-MELONES SS-MANTECA #1+ | 027/173 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-05 | 2021-03-05 |  |  | 2021-02-22 | 2021-02-12 | [5 empty] | Central | WSIP | [6 empty] | '-120.784653 | 37.9187 | ETL.3830 | 40603091 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120140821 | Feb | DI BRIGHTON-GRND ISLND #1 7/65 RPR SPLS | 44580017 | BRIGHTON-GRAND ISLAND #1 | 007/065 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-07 | 2021-03-07 |  |  | 2021-02-23 | 2021-02-22 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.432502 | 38.439 | ETL.1150 | 40785299 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120140828 | Not Scheduled | DI RIO OSO-WOODLAND #2 6/69 RPR SPLS | 44585968 | RIO OSO-WOODLAND #2 | 006/069 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-07 | 2021-12-07 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.989643 | 38.5927 | ETL.3470 | 40848996 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120141043 | Q4 | DI KESWICK-TRINITY 30/529 RPLC INSS | 31520291 | KESWICK-TRINITY | 030/529 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-12-05 | 2021-12-05 |  |  | 2021-10-11 | 2021-10-04 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.930942 | 40.715 | ETL.7270 | 40915798 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120141278 | Q3 | T2 DI BRIDGEVILLE-CTTNWD 58/426 RPLC INS | 31529414 | BRIDGEVILLE-COTTONWOOD | 058/426 | 93K | E | 2020_(2) High fire spread TD |  | 2020-12-07 | 2021-12-07 |  |  | 2021-07-31 | 2021-07-26 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.339005 | 40.3783 | ETL.1110 | 43242896 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 93 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120141315 | Not Scheduled | T3 DIABLO-MIDWAY #3 026/107 RPL INSS |  | DIABLO-MIDWAY #3 | 026/107 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-08 | 2021-06-08 | [7 empty] | TR3 |  | South | WSIP | [6 empty] | '-120.39562 | 35.1639 | ETL.5980 | 40811447 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 19 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-12 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120141351 | Not Scheduled | DI DRUM-SUMMIT #2 15/186 RPR GYWW | 44580361 | DRUM-SUMMIT #2 | 015/186 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-12-07 | 2021-12-07 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44159103 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120141352 | Not Scheduled | DI DRUM-SUMMIT #2 15/186 RPR GYWW | 44580361 | DRUM-SUMMIT #2 | 015/186 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-12-07 | 2021-12-07 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44159104 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120141353 | Not Scheduled | DI DRUM-SUMMIT #2 15/186 RPR GYWW | 44580361 | DRUM-SUMMIT #2 | 015/186 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-12-07 | 2021-12-07 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44159105 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120141354 | Not Scheduled | DI DRUM-SUMMIT #2 15/186 INS GMKW | 44580370 | DRUM-SUMMIT #2 | 015/186 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-12-07 | 2022-12-07 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44159104 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120141414 | Q4 | T2 WV MIDDLE FRK-GLD HILL 37/26 RPR INSS | 44587956 | MIDDLE FORK-GOLD HILL | 037/264 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-12-08 | 2021-12-08 |  |  | 2021-11-01 | 2021-10-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.0508618 | 38.6987 | ETL.5140 | 40775097 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120142748 | Q4 | T3 MAPLE CREEK-HOOPA 13/009L RPL POLE | 31522166 | MAPLE CREEK-HOOPA | 013/009 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-12-08 | 2021-06-08 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.7298938 | 40.9054 | ETL.7490 | 44769632 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120142755 | Q4 | T3 MAPLE CREEK-HOOPA 13/009C RPL POLE | 31522166 | MAPLE CREEK-HOOPA | 013/009 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-12-08 | 2021-06-08 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.7299045 | 40.9054 | ETL.7490 | 44769633 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120142761 | Q4 | T3 MAPLE CREEK-HOOPA 13/009R RPL POLE | 31522166 | MAPLE CREEK-HOOPA | 013/009 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-12-08 | 2021-06-08 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.7299059 | 40.9055 | ETL.7490 | 44769634 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 70 | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120143784 | Mar | T2 DI KONOCTI-MIDDLETOWN 12/1A RPR SPLW | 44585048 | KONOCTI-MIDDLETOWN | 012/001A | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-12-07 | 2021-12-07 | 2021-03-01 | 2021-03-04 | 2021-03-01 | 2021-03-01 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.6380 | 44371582 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120144023 | Not Scheduled | DI ATASCADERO-CAYUCOS 09/78 RPL CRSW | 31520015 | ATASCADERO-CAYUCOS | 009/078 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-12-05 | 2021-12-05 | [9 empty] | South | WSIP | [8 empty] | ETL.8480 | 44319799 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Pismo Beach |  | Y - 13 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-27 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120144086 | Not Scheduled | T3 DI FULTON-PUEBLO- 36/179 RPL INSS |  | FULTON-PUEBLO | 036/179 | 93K | E | 2020_(2) High fire spread TD |  | 2020-12-05 | 2021-06-05 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.633317 | 38.4978 | ETL.1600 | 40879846 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120144200 | Not Scheduled | T3 DI EAGL RCK-FLTN-SLVR 36/179 RPL INSS | 31530073 | EAGLE ROCK-FULTON-SILVERADO | 036/179 | 93K | E | 2020_(2) High fire spread TD |  | 2020-12-05 | 2021-06-05 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.63325 | 38.4981 | ETL.4392 | 40879847 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120144697 | Feb | DI GLD HLL-BLLTA-LCKFRD 39/237 RPL INSS | 31521547 | GOLD HILL-BELLOTA-LOCKEFORD | 039/237 | 93K | B | 2020_(0) A and B Tags |  | 2020-12-08 | 2021-03-08 |  |  | 2021-02-17 | 2021-02-17 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.144098 | 38.5986 | ETL.1690 | 40854010 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-31 | Released-Standard | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120144918 | Not Scheduled | DI DRUM-SUMMIT #1 16/192 RMV PL BUTT | 44587954 | DRUM-SUMMIT #1 | 016/192 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-12-07 | 2022-12-07 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.51116 | 39.3144 | ETL.1440 | 44379172 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120145023 | Not Scheduled | DI DRUM-SUMMIT #1 16/192 RPR GYWW | 44587954 | DRUM-SUMMIT #1 | 016/192 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-12-07 | 2021-12-07 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.51116 | 39.3144 | ETL.1440 | 44379172 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120145024 | Not Scheduled | DI DRUM-SUMMIT #1 16/192R RPR GYWW | 44587954 | DRUM-SUMMIT #1 | 016/192 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-12-07 | 2021-12-07 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.51116 | 39.3144 | ETL.1440 | 44379173 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120145249 | Q4 | T2 DI KESWICK-TRINITY 28/490 RPR GYWW |  | KESWICK-TRINITY | 028/490 | ICW | E | 2020_(2) High fire spread TD |  | 2020-12-08 | 2021-12-08 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.900252 | 40.7099 | ETL.7270 | 44838208 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120147178 | Feb | T3 LONE TREE-CYNO 14/93B RPR SWITCH | 44586081 | LONE TREE-CAYETANO | 014/93B | ICE | B | 2020_(0) A and B Tags |  | 2020-12-09 | 2021-03-09 |  |  | 2021-02-19 | 2021-02-19 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.728702 | 37.7907 | ETL.6160 | 43242955 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Bay |  | Y - 6 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-29 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120148153 | Q2 | DI GARBERVILLE-LAYTONVILLE 56/6 INS MRKW | 44542681 | GARBERVILLE-LAYTONVILLE | 056/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-10-30 | 2022-10-30 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.680921 | 40.0953 | ETL.8365 | 40912628 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120149663 | Not Scheduled | T3 DI ROUND MTN-CTNWD #3 31/261 RMV HRDT | 43932111 | ROUND MTN-COTTONWOOD #3 | 031/261 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-12-09 | 2021-06-09 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.978191 | 40.7444 | ETL.5650 | 40593780 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120149737 | Mar | DI NEWARK-JARVIS #1 006/045 MASTIC | 44631247 | NEWARK-JARVIS #1 | 006/045 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-11-02 | 2022-11-02 |  |  | 2021-03-20 | 2021-03-15 | [5 empty] | Central | WSIP | [6 empty] | '-121.905951 | 37.5516 | ETL.3020 | 40745976 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120149841 | Mar | DI NEWARK-JARVIS #1 006/042 MASTIC |  | NEWARK-JARVIS #1 | 006/042 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-11-02 | 2022-11-02 |  |  | 2021-03-27 | 2021-03-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.901245 | 37.5456 | ETL.3020 | 40646189 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-21 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120150010 | Q3 | T2 DI CARIBOU #2 008/023 RPL STRW | 31522175 | CARIBOU #2 | 008/023 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-12-09 | 2021-12-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.20978 | 40.017 | ETL.6280 | 40656539 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | 70 | Q3 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120150382 | Feb | DI RIO DELL JCT-BRDGVL 40/1 REMV DEBRIS | 44592890 | RIO DELL JCT-BRIDGEVILLE | 040/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-02 | 2022-11-02 |  |  | 2021-02-27 | 2021-02-15 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.791488 | 40.4754 | ETL.7850 | 40584735 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120150523 | Q3 | DI BRIDGEVILLE-COTTONWD 76/548 RPR OPGW |  | BRIDGEVILLE-COTTONWOOD | 076/548 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-09 | 2021-12-09 |  |  | 2021-07-17 | 2021-06-21 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.617699 | 40.4943 | ETL.1110 | 40762813 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120150563 | Not Scheduled | T2NT DI CARIBOU #2 04/001 RMV IDLE ANC | 31527021 | CARIBOU #2 | 004/001 | 93J | F | 2020_(2) High fire spread TD |  | 2020-11-04 | 2022-11-04 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.202353 | 40.0586 | ETL.6280 | 40600563 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120159151 | Feb | DI BRIGHTON-DAVIS :0/116G REPL INSS | 31527641 | BRIGHTON-DAVIS | :000/116G | 93K | B | 2020_(0) A and B Tags |  | 2020-12-09 | 2021-03-09 |  |  | 2021-02-10 | 2021-02-10 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.835619 | 38.2639 | ETL.1140 | 40743097 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-24 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120159223 | Feb | T2 DI FORT ROSS-GUALALA 30/7 RPL POLE | 31516147 | GUALALA-MONTE RIO | 030/007 | 70Y | B | 2020_(0) A and B Tags |  | 2020-12-09 | 2021-03-09 |  |  | 2021-02-25 | 2021-02-25 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.243535 | 38.5484 | ETL.6980 | 40820154 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120160549 | Q2 | T2 EI EXCHQR-INDN FLAT 30/163 RPR STRS | 44588824 | EXCHEQUER-YOSEMITE | 030/163 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-12-09 | 2021-12-09 |  |  | 2021-06-30 | 2021-06-01 |  |  | Likely MAT error - delink to correct | TR2 |  | South | WSIP | [6 empty] | '-119.904347 | 37.6688 | ETL.8650 | 44420190 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 628 | Fresno |  | Y - 48 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120160550 | Mar | DI RAVENSWOOD-BAIR #2 001/011 COTR KEY | 44591715 | RAVENSWOOD-BAIR #2 | 001/011 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-09 | 2021-03-09 |  |  | 2021-03-08 | 2021-02-10 | [5 empty] | Central | WSIP | [8 empty] | ETL.3385 | 41104907 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120160562 | Q2 | T2 EI EXCHQR-INDN FLAT 28/138 RPR ANCS | 44595663 | EXCHEQUER-YOSEMITE | 028/138 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-12-09 | 2021-12-09 |  |  | 2021-06-30 | 2021-06-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.915602 | 37.6495 | ETL.8650 | 44420176 | Anchor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 48 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120160568 | Q2 | T2 EI EXCHQR-INDIAN FLAT 30/157 RPR STRS | 44588824 | EXCHEQUER-YOSEMITE | 030/157 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-12-09 | 2021-12-09 |  |  | 2021-06-30 | 2021-06-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.916409 | 37.6683 | ETL.8650 | 44420188 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 48 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120160582 | Q2 | T2 EI EXCHQR-INDN FLAT 30/163 RPR FOND | 44587947 | EXCHEQUER-YOSEMITE | 030/163 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-12-09 | 2021-12-09 |  |  | 2021-06-30 | 2021-06-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.904347 | 37.6688 | ETL.8650 | 44420190 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120160587 | Q2 | T2 EI EXCHQR-INDN FLAT 28/138 RMV VEG |  | EXCHEQUER-YOSEMITE | 028/138 | HNA | E | 2020_(4b) On structure in bucket 4 |  | 2020-12-09 | 2021-12-09 |  |  | 2021-06-30 | 2021-03-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.915602 | 37.6495 | ETL.8650 | 44420176 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | HNA | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120160592 | Q2 | T2NT EI EXCHQR-INDN FLAT 30/157 RMV DBRS | 44595663 | EXCHEQUER-YOSEMITE | 030/157 | ICS | F | 2020_(4b) On structure in bucket 4 |  | 2020-12-09 | 2022-12-09 |  |  | 2021-06-30 | 2021-06-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.916409 | 37.6683 | ETL.8650 | 44420188 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 48 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120160683 | Q3 | DI BRIDGEVLLE-COTTONWOOD 76/547 RPR OPGW |  | BRIDGEVILLE-COTTONWOOD | 076/547 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-09 | 2021-12-09 |  |  | 2021-07-17 | 2021-06-21 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.613222 | 40.4946 | ETL.1110 | 40657081 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120160831 | Q4 | T3 DI MAPLE CREEK-HOOPA 017/007 RPL INSW | 31521744 | MAPLE CREEK-HOOPA | 017/007 | 93I | E | 2020_(2) High fire spread TD |  | 2020-12-09 | 2021-06-09 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.673802 | 40.9363 | ETL.7490 | 44838061 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 93 | Q4 |  |  | 2021-01-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120160833 | Q2 | T2 DI BRIDGEVLLE-COTTNWD 25/221 RPL INSS | 31515458 | BRIDGEVILLE-COTTONWOOD | 025/221 | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-12-09 | 2021-12-09 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.748315 | 40.3703 | ETL.1110 | 40792817 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-12-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120161564 | Q4 | T2 EI KESWICK-TRINITY 28/490 RPR GYWW |  | KESWICK-TRINITY | 028/490 | ICW | E | 2020_(2) High fire spread TD |  | 2020-12-10 | 2021-12-10 |  |  | 2021-10-11 | 2021-10-04 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.900252 | 40.7099 | ETL.7270 | 44838215 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120161861 | Q3 | T2NT DI CARIBOU #2 16/12 RMV BUTT |  | CARIBOU #2 | 016/012 | ICW | F | 2020_(3) On high spread structure |  | 2020-11-04 | 2022-11-04 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.089025 | 40.0148 | ETL.6280 | 40675435 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120162433 | Q3 | T2NT DI CARIBOU #2 :7/7 RMV DEBRIS |  | CARIBOU #2 | :007/007 | ICW | F | 2020_(3) On high spread structure |  | 2020-12-09 | 2022-12-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.959092 | 39.9591 | ETL.6280 | 40815848 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120162435 | Q3 | T2 DI CARIBOU #2 :7/7 RPR ANCW |  | CARIBOU #2 | :007/007 | ICW | E | 2020_(2) High fire spread TD |  | 2020-12-09 | 2021-12-09 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.959092 | 39.9591 | ETL.6280 | 40815848 | Anchor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120162812 | Not Scheduled | T2 DI ROCK CREEK-POE :006/043B MASTIC |  | ROCK CREEK-POE | :006/043B | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-12-10 | 2021-12-10 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.308009 | 39.9456 | ETL.5630 | 43249823 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120162818 | Not Scheduled | T2 DI ROCK CREEK-POE :006/043C MASTIC |  | ROCK CREEK-POE | :006/043C | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-12-10 | 2021-12-10 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.30792 | 39.9456 | ETL.5630 | 43249825 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120164728 | Not Scheduled | DI DRUM-SUMMIT #2 15/184C INST GMKW |  | DRUM-SUMMIT #2 | 015/184C | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-12-07 | 2022-12-07 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.525615 | 39.307 | ETL.1450 | 44155598 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120164762 | Not Scheduled | DI DRUM-SUMMIT #1 13/151 RPLC INSW | 31521959 | DRUM-SUMMIT #1 | 013/151 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-12-10 | 2021-12-10 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.564561 | 39.3255 | ETL.1440 | 40684225 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120164766 | Not Scheduled | DI SPAULDING-SUMMIT 6/226 CANCEL | 44588323 | SPAULDING-SUMMIT | 006/226 | ICW | B | 2020_(0) A and B Tags |  | 2020-12-10 | 2021-03-10 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.539383 | 39.3086 | ETL.8060 | 40744096 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-31 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120164782 | Q2 | DI GARBERVILLE-LAYTNVLL 057/000 INS MRKW | 44542681 | GARBERVILLE-LAYTONVILLE | 057/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-12-04 | 2022-12-04 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.689894 | 40.1022 | ETL.8365 | 43597919 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120164835 | Not Scheduled | DI DRUM-SUMMIT #1 16/189 CANCEL | 44588583 | DRUM-SUMMIT #1 | 016/189 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-12-07 | 2022-12-07 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.517616 | 39.3137 | ETL.1440 | 40755589 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120164961 | Not Scheduled | T3NT DI DRUM-SUMMIT #2 000/004 INST MRKW | 44588584 | DRUM-SUMMIT #2 | 000/004 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-12-05 | 2022-12-05 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.762586 | 39.255 | ETL.1450 | 44339153 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120165090 | Q2 | NT DI GRBRVLLE-LYTNVLLE 56/6 INST MRKW | 44542681 | GARBERVILLE-LAYTONVILLE | 056/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-12-04 | 2022-12-04 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.680957 | 40.0953 | ETL.8365 | 43597912 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120170328 | Q2 | T2 DI PITTSBURG-SAN MATEO 5/26 MASTIC |  | PITTSBURG-SAN MATEO | 005/026 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-12-09 | 2022-12-09 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.889616 | 37.9619 | ETL.5463 | 40581157 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-21 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120176776 | Not Scheduled | T2NT DI ROCK CREEK-POE :7/051C RPR FOND |  | ROCK CREEK-POE | :007/051C | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-12-10 | 2022-12-10 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.317935 | 39.9384 | ETL.5630 | 43249829 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120176777 | Not Scheduled | DI DRUM-SUMMIT #1 13/148 RPLC INSW | 31521959 | DRUM-SUMMIT #1 | 013/148 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-12-10 | 2021-12-10 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.568277 | 39.3281 | ETL.1440 | 40641829 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120177008 | Not Scheduled | T2 DI ROCK CREEK-POE 6/43A RPR FOND |  | ROCK CREEK-POE | :006/043A | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-12-10 | 2021-12-10 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.308093 | 39.9456 | ETL.5630 | 40656184 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120177035 | Feb | PITTSBURG-COLUMBIA STEEL 4/27 RPR SW | 44589053 | PITTSBURG-COLUMBIA STEEL | 004/027 | ICE | B | 2020_(0) A and B Tags |  | 2020-12-11 | 2021-03-11 |  |  | 2021-02-17 | 2021-02-17 | [5 empty] | Central | WSIP | [6 empty] | '-121.87622 | 37.987 | ETL.3300 | 40821513 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-22 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120177045 | Feb | T2 DI ROCK CREEK-POE 6/43A RPR GYWS |  | ROCK CREEK-POE | :006/043A | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-12-10 | 2021-12-10 |  |  | 2021-02-26 | 2021-02-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.308093 | 39.9456 | ETL.5630 | 40656184 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120177084 | Not Scheduled | T2 DI BEARDSLEY TAP 0/1C RPLC INSW | 31521800 | BEARDSLEY TAP | 000/001C | 93I | E | 2020_(4) TD tag on high spread line |  | 2020-12-10 | 2021-12-10 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.07707 | 38.2027 | ETL.1401 | 42834639 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120177087 | Not Scheduled | T2NT DI ROCK CREEK-POE :7/051A RPR FOND |  | ROCK CREEK-POE | :007/051A | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-12-10 | 2022-12-10 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.317899 | 39.9383 | ETL.5630 | 40597038 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120177321 | Not Scheduled | DI DRUM-SUMMIT #1 13/150 RPLC INSW | 31521959 | DRUM-SUMMIT #1 | 013/150 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-12-10 | 2021-12-10 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.565701 | 39.3261 | ETL.1440 | 40718950 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120177767 | Q2 | T2 DI BRIDGEVILLE-CTNWD 24/212 RMV STUB | 44404807 | BRIDGEVILLE-COTTONWOOD | 024/212 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-12-11 | 2022-12-11 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.724491 | 40.372 | ETL.1110 | 44515793 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120177769 | Q2 | T2 DI BRIDGEVILLE-CTNWD 24/212 RPR ADSS | 44404807 | BRIDGEVILLE-COTTONWOOD | 024/212 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-12-11 | 2021-12-11 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.724491 | 40.372 | ETL.1110 | 44515793 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120178013 | Not Scheduled | T2 DI ROCK CREEK-POE :004/030B RPR FOND |  | ROCK CREEK-POE | :004/030B | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-12-10 | 2021-12-10 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.290811 | 39.9586 | ETL.5630 | 43249821 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120189010 | Not Scheduled | DI DRUM-SUMMIT #1 13/149 RPL INSW | 31521959 | DRUM-SUMMIT #1 | 013/149 | 93I | E | 2020_(1b) Lines with special commitments |  | 2020-12-10 | 2021-12-10 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.566884 | 39.327 | ETL.1440 | 40614316 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120189011 | Not Scheduled | DI DRUM-SUMMIT #1 13/149 SPLIT BOLT | 44645317 | DRUM-SUMMIT #1 | 013/149 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-12-10 | 2021-12-10 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.566891 | 39.327 | ETL.1440 | 40589134 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120189157 | Q2 | T2 EXCHEQUER-INDIAN FLAT 33/181 RPL INSS | 31527643 | EXCHEQUER-YOSEMITE | 033/181 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-12-11 | 2021-12-11 |  |  | 2021-06-30 | 2021-03-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.881768 | 37.6558 | ETL.8650 | 40623312 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 48 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2021-01-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120189161 | Q2 | T2 EXCHEQUER-INDIAN FLAT 33/181 RPR FOND | 44587947 | EXCHEQUER-YOSEMITE | 033/181 | ICQ | E | 2020_(4b) On structure in bucket 4 |  | 2020-12-11 | 2021-12-11 |  |  | 2021-06-30 | 2021-06-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.881768 | 37.6558 | ETL.8650 | 44420198 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120190005 | Feb | EI KRCKHFF-CLVS-SNGR #1 12/7 RPL INSW | 31521779 | KERCKHOFF-CLOVIS-SANGER #1 | 012/007 | 93I | B | 2020_(0) A and B Tags |  | 2020-12-13 | 2021-03-13 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | [5 empty] | South | WSIP | [6 empty] | '-119.6021936 | 36.8977 | ETL.1890 | 40851071 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2020-12-15 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120190806 | Q2 | T2 DI BRDGVLLE-CTTNWD 50/382 RPR FOND | 44634175 | BRIDGEVILLE-COTTONWOOD | 050/382 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-12-11 | 2021-12-11 |  |  | 2021-05-13 | 2021-04-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.205121 | 40.417 | ETL.1110 | 40759374 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLM | Tower | Expense | 543 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120190878 | Q2 | T2 DI BRIDGEVILLE-CTNWD 19/176 RPLC INSW |  | BRIDGEVILLE-COTTONWOOD | 019/176 | 93I | E | 2020_(2) High fire spread TD |  | 2020-12-11 | 2021-12-11 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.631291 | 40.3786 | ETL.1110 | 40721719 | Insulator-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-12-21 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120190879 | Q2 | T2 DI BRIDGEVILLE-CTNWD 19/176 RPR GYWW | 44404807 | BRIDGEVILLE-COTTONWOOD | 019/176 | ICW | E | 2020_(2) High fire spread TD |  | 2020-12-11 | 2021-12-11 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.631291 | 40.3786 | ETL.1110 | 44423921 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120190920 | Q2 | T2 DI BRIDGEVILLE-CTNWD 19/176 RPR GYWW | 44404807 | BRIDGEVILLE-COTTONWOOD | 019/176 | ICW | E | 2020_(2) High fire spread TD |  | 2020-12-11 | 2021-12-11 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.631291 | 40.3786 | ETL.1110 | 44423922 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-21 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120191297 | Feb | WV T2 BKS CRK-RCK CRK-CRST3/30 REPL INSS | 31519646 | BUCKS CREEK-ROCK CREEK-CRESTA | 003/030 | 93K | E | 2020_(2) High fire spread TD |  | 2020-12-14 | 2021-12-14 |  |  | 2021-02-25 | 2021-02-24 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.3790714 | 39.8718 | ETL.4430 | 40634238 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-02-08 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120191441 | Not Scheduled | T3 DI DRUM-SUMMIT #2 0/1 RPR GYWW | 44588330 | DRUM-SUMMIT #2 | 000/001 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-12-11 | 2021-06-11 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.766213 | 39.2562 | ETL.1450 | 44549846 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120191444 | Not Scheduled | T3NT DI DRUM-SUMMIT #2 0/1 RPLC GMKW |  | DRUM-SUMMIT #2 | 000/001 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-12-11 | 2022-12-11 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.766213 | 39.2562 | ETL.1450 | 44550020 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120191746 | Feb | EI CSCDE-BNTN-DSCHTS A5/108 REPL POLE | 31521653 | CASCADE-BENTON-DESCHUTES | A005/108 | 70Y | B | 2020_(0) A and B Tags |  | 2020-12-14 | 2021-03-14 |  |  | 2021-02-28 | 2021-02-28 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.298641 | 40.5886 | ETL.6310 | 40817345 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-02-08 | Released-Standard | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120192025 | Not Scheduled | DI SPAULDING-SUMMIT 005/207 RPL SWIW | 31522176 | SPAULDING-SUMMIT | 005/207 | 93H | E | 2020_(1b) Lines with special commitments |  | 2020-12-10 | 2021-12-10 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.549885 | 39.3055 | ETL.8060 | 40744095 | Switch-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 427 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120192305 | Mar | DIABLO-MIDWAY #2 51/207 RPL INSS | 31522252 | DIABLO-MIDWAY #2 | 051/207 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-12-14 | 2021-12-14 |  |  | 2021-03-10 | 2021-03-08 | [5 empty] | South | WSIP | [6 empty] | '-119.978614 | 35.2505 | ETL.5970 | 40832304 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 8 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-11 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120192556 | Feb | DI LAS GALLINAS-SAN RFL 5/112 RPR GYWW | 44588948 | ETL.1103.POLE.WOOD | 005/112 | ICW | B | 2020_(0) A and B Tags |  | 2020-12-11 | 2021-03-11 |  |  | 2021-02-28 | 2021-02-26 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.539063 | 38.0031 | ETL.1103 | 40826637 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-15 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120192639 | Not Scheduled | T2 DI STNSLS-MLNS-RVRBNK 10/66 RPR SPLS | 44589648 | STAN MEL SW STA-RVERBNK JCT SW STA | 010/066 | ICS | E | 2020_(4) TD tag on high spread line |  | 2020-12-14 | 2021-12-14 | [7 empty] | TR2 |  | Central | WSIP | [6 empty] | '-120.541827 | 38.0557 | ETL.3840 | 41196637 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-12-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120192763 | Feb | T3NT EI MNT VSTA-JFRSN #1 16/67 INS MRKS | 44614659 | MONTA VISTA-JEFFERSON #1 | 016/067 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-12-14 | 2022-12-14 |  |  | 2021-02-20 | 2021-02-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.298797 | 37.4167 | ETL.5220 | 40819489 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-13 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120192764 | Feb | T3NT EI MNT VSTA-JFRSN #1 16/68 INS MRKS |  | MONTA VISTA-JEFFERSON #1 | 016/068 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-12-14 | 2022-12-14 |  |  | 2021-02-20 | 2021-02-15 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.300022 | 37.4198 | ETL.5220 | 40869759 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-08 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120199694 | Q3 | T2NT DI CARIBOU #2 ;001/000 RMV BUTT |  | CARIBOU #2 | ;001/000 | ICW | F | 2020_(3) On high spread structure |  | 2020-12-14 | 2022-12-14 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.966535 | 40.0126 | ETL.6280 | 40614976 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120201054 | Q2 | DI GATES-PANOCHE #1 000/001 MASTIC | 44588823 | GATES-PANOCHE #1 | 000/001 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-12-14 | 2022-12-14 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.125045 | 36.142 | ETL.4720 | 40587467 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120201142 | Not Scheduled | DI GATES-PANOCHE #2 029/135 RPL INSS | 31527142 | GATES-PANOCHE #2 | 029/135 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-12-14 | 2021-12-14 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.42229 | 36.4749 | ETL.4730 | 40782373 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120201319 | Not Scheduled | T3NT DRUM-SUMMIT #1 000/001 RMV DEBRIS | 44593052 | DRUM-SUMMIT #1 | 000/001 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-12-11 | 2022-12-11 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.766429 | 39.2561 | ETL.1440 | 40590089 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120201331 | Not Scheduled | DI DRUM-SUMMIT #2 016/188 RPR STRW | 44592333 | DRUM-SUMMIT #2 | 016/188 | ICW | E | 2020_(1b) Lines with special commitments |  | 2020-12-11 | 2021-12-11 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.521126 | 39.3095 | ETL.1450 | 44550024 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120201333 | Not Scheduled | DI DRUM-SUMMIT #2 016/188 INST HV |  | DRUM-SUMMIT #2 | 016/188 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-12-11 | 2022-12-11 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.521126 | 39.3095 | ETL.1450 | 44550024 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120203823 | Q4 | T3 DI MAPLE CREEK-HOOPA 012/001 RPR WDPK | 44592881 | MAPLE CREEK-HOOPA | 012/001 | ICW | E | 2020_(2) High fire spread TD |  | 2020-12-11 | 2021-06-11 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.762882 | 40.9047 | ETL.7490 | 40586849 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120203994 | Feb | HALSEY-PLACER 4/97 RPR POLE |  | HALSEY-PLACER | 004/097 | ICW | B | 2020_(0) A and B Tags |  | 2020-12-15 | 2021-03-15 |  |  | 2021-02-11 | 2021-02-11 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.082413 | 38.9048 | ETL.6990 | 40815279 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-11 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120204557 | Q2 | T2 HAT CREEK #1-WESTWOOD 1/35 REFRAME | 31521568 | HAT CREEK #1-WESTWOOD | 001/035 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-12-15 | 2021-12-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.513273 | 40.9234 | ETL.7030 | 40757927 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120204558 | Q2 | T2 HAT CREEK #1-WESTWOOD 0/14 REFRAME | 31521568 | HAT CREEK #1-WESTWOOD | 000/014 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-12-15 | 2021-12-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.533692 | 40.9265 | ETL.7030 | 40591006 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120204562 | Q2 | T2 HAT CREEK #1-WESTWOOD 1/40 REFRAME | 31521568 | HAT CREEK #1-WESTWOOD | 001/040 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-12-15 | 2021-12-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.50837 | 40.9226 | ETL.7030 | 40590008 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120204576 | Q2 | T2 BRIDGEVILLE-COTTONWOOD 27/231 REFRAME | 31528321 | BRIDGEVILLE-COTTONWOOD | 027/231 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-12-15 | 2021-12-15 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.778138 | 40.3682 | ETL.1110 | 44565796 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120204595 | Feb | T2 DI ST ML SW S-RK JT SS11/69 INS WASHR | 44589650 | STAN MEL SW STA-RVERBNK JCT SW STA | 011/069 | ICQ | B | 2020_(0) A and B Tags |  | 2020-12-14 | 2021-03-14 |  |  | 2021-02-25 | 2021-02-24 |  | TLN/TLQ error | Recommend delinking prior to edits | TR2 |  | Central | WSIP | [6 empty] | '-120.553225 | 38.0499 | ETL.3840 | 44951567 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-18 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120204600 | Q2 | T2 HAT CREEK #1-WESTWOOD 0/18 REFRAME | 31521568 | HAT CREEK #1-WESTWOOD | 000/018 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-12-15 | 2021-12-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.529792 | 40.9259 | ETL.7030 | 40769933 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120204601 | Q2 | T2 HAT CREEK #1-WESTWOOD 0/16 REFRAME | 31521568 | HAT CREEK #1-WESTWOOD | 000/016 | 93E | E | 2020_(4) TD tag on high spread line |  | 2020-12-15 | 2021-12-15 |  |  | 2021-06-25 | 2021-05-03 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.531657 | 40.9262 | ETL.7030 | 40655749 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120204605 | Q2 | T2 BRIDGEVILLE-COTTONWOOD 39/317 REFRAME | 31528321 | BRIDGEVILLE-COTTONWOOD | 039/317 | 93E | E | 2020_(2) High fire spread TD |  | 2020-12-15 | 2021-12-15 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-123.012212 | 40.3804 | ETL.1110 | 44425577 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120204642 | Q2 | T2 MALIN-ROUND MTN #2 73/372 RPL INSS | 31527915 | MALIN-ROUND MTN #2 | 073/372 | 93K | E | 2020_(1b) Lines with special commitments |  | 2020-12-15 | 2021-12-15 |  |  | 2021-06-15 | 2021-05-01 |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.823127 | 41.07 | ETL.6020 | 40684090 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120204830 | Mar | DIABLO-MIDWAY #2 50/205 RPL INSS | 31522252 | DIABLO-MIDWAY #2 | 050/205 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-12-14 | 2021-12-14 |  |  | 2021-03-10 | 2021-03-08 | [5 empty] | South | WSIP | [6 empty] | '-119.986498 | 35.2482 | ETL.5970 | 40790840 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 8 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-11 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120205116 | Mar | DIABLO-MIDWAY #3 50/202 RPL INSS | 31527297 | DIABLO-MIDWAY #3 | 050/202 | 93K | E | 2020_(4) TD tag on high spread line |  | 2020-12-15 | 2021-12-15 |  |  | 2021-03-10 | 2021-03-08 | [5 empty] | South | WSIP | [6 empty] | '-119.999248 | 35.2456 | ETL.5980 | 40655325 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120205247 | Feb | T2 ATASCADERO-SLO 10/158 BENT STL | 44589015 | ATASCADERO-SAN LUIS OBISPO | 010/158 | ICQ | B | 2020_(0) A and B Tags |  | 2020-12-15 | 2021-03-15 |  |  | 2021-02-25 | 2021-02-22 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.619803 | 35.3275 | ETL.8490 | 40588544 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120205289 | Mar | T3 WV DRUM-RIO OSO #2 5/063 RPR INSS | 44592332 | DRUM-RIO OSO #2 | 005/063 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-15 | 2021-06-15 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.8558754 | 39.213 | ETL.1430 | 40684596 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120205412 | Mar | T3 WV DRUM-RIO OSO #2 1/017 RPR INSS | 44592332 | DRUM-RIO OSO #2 | 001/017 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-15 | 2021-06-15 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.7987685 | 39.256 | ETL.1430 | 40840103 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120205505 | Q2 | T2 DI BRIDGEVL-CTNWD 3/30C RPR OPGW | 44404807 | BRIDGEVILLE-COTTONWOOD | 003/030C | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-12-11 | 2021-12-11 |  |  | 2021-04-30 | 2021-03-29 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.326991 | 40.3906 | ETL.1110 | 44891804 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120205551 | Mar | T3 WV DRUM-RIO OSO #2 6/065 RPR INSS | 44592332 | DRUM-RIO OSO #2 | 006/065 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-15 | 2021-06-15 |  |  | 2021-03-20 | 2021-03-01 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.8585209 | 39.2109 | ETL.1430 | 44319606 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120205680 | Q2 | DI OLEUM-G #1 0/6 RPR STRT |  | OLEUM-G #1 | 000/006 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-12-11 | 2021-12-11 |  |  | 2021-04-02 | 2021-03-29 | [5 empty] | Central | WSIP | [6 empty] | '-122.246756 | 38.0405 | ETL.3150 | 40804781 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-21 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120208128 | Q2 | DI GATES-PANOCHE #1 5/26 RPR FOND | 44589004 | GATES-PANOCHE #1 | 005/026 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-11-09 | 2022-11-09 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.175406 | 36.2037 | ETL.4720 | 40811782 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120208512 | Q2 | T3 MORRO BAY-SOLAR SS #1 14/59 RPR FOND | 44592680 | MORRO BAY-SOLAR SW STA #1 | 014/059 | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-12-15 | 2021-06-15 |  |  | 2021-04-15 | 2021-04-01 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.607225 | 35.3693 | ETL.5300 | 40870323 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2020-12-28 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120209903 | Q2 | DI GATES-PANOCHE #1 11/54 RPR FOND | 44589004 | GATES-PANOCHE #1 | 011/054 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-11-09 | 2022-11-09 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.232512 | 36.2772 | ETL.4720 | 40762371 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120210798 | Q2 | DI STANISLAUS-NEWARK #1 95/626 RMV IDLE |  | STANISLAUS-NEWARK #1 (12KV) | 095/626 | 93J | F | 2020_(4b) On structure in bucket 4 |  | 2020-12-12 | 2022-12-12 |  |  | 2021-06-12 | 2021-06-07 | [5 empty] | Central | WSIP | [6 empty] | '-121.90368 | 37.5623 | ETL.3850 | 40828821 | Structure-Tower | Idle | Remove |  |  |  |  | PEND | LC | TLQ | Tower | Capital | 673 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2021-01-21 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120212428 | Not Scheduled | T2 CABRLO-SNT YNZ SS 10/87 DUP CANCEL | 31521908 | CABRILLO-SANTA YNEZ SW STA | 010/087 | 93I | B | 2020_(0) A and B Tags |  | 2020-12-16 | 2021-03-16 |  | 2021-03-12 |  |  |  |  | CANCEL/CNCL | TR2 | <30D | South | WSIP | [6 empty] | '-120.358494 | 34.6498 | ETL.1200 | 40751493 | Insulator-Wood | No Good/Out of Stdrd | Replace | PROD srdy |  |  |  | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-12-28 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120216419 | Feb | MOSS LANDING-LOS BANOS 4/024 REPL DAMPR | 44597176 | MOSS LANDING-LOS BANOS | 004/024 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-17 | 2021-03-17 |  |  | 2021-02-24 | 2021-02-24 | [5 empty] | South | WSIP | [6 empty] | '-121.714362 | 36.7841 | ETL.6040 | 40753867 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  | Y - 8 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120216430 | Feb | MOSS LANDING-LOS BANOS 1/011 REPL DAMPS | 44597176 | MOSS LANDING-LOS BANOS | 001/011 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-16 | 2021-03-17 |  |  | 2021-02-24 | 2021-02-24 | [5 empty] | South | WSIP | [6 empty] | '-121.764407 | 36.7829 | ETL.6040 | 40589500 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  | Y - 8 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120216442 | Feb | MOSS LANDING-LOS BANOS 11/53 REPL DAMPR | 44597176 | MOSS LANDING-LOS BANOS | 011/053 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-16 | 2021-03-17 |  |  | 2021-02-24 | 2021-02-24 | [5 empty] | South | WSIP | [6 empty] | '-121.600482 | 36.7839 | ETL.6040 | 40651850 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  | Y - 8 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120217742 | Q2 | DI SBRNTE-STNDRD OIL #1 7/46 RPR FOND |  | SOBRANTE-STANDARD OIL SW STA #2 | 007/046 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-11-16 | 2022-11-16 |  |  | 2021-05-22 | 2021-05-17 | [5 empty] | Central | WSIP | [6 empty] | '-122.23903 | 37.9999 | ETL.3800 | 40810740 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120217854 | Not Scheduled | DI DRUM-SUMMIT #1 13/153 RMV DEBRIS | 44592815 | DRUM-SUMMIT #1 | 013/153 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-17 | 2022-11-17 | [8 empty] | WECC | North Valley | WSIP | [8 empty] | ETL.1440 | 44162104 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120217953 | Not Scheduled | DI DRUM-SUMMIT #1 17/196 INS HV | 44592815 | DRUM-SUMMIT #1 | 017/196 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-16 | 2022-11-16 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.504774 | 39.3138 | ETL.1440 | 40603739 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120220801 | Q2 | T3 DI IGNACIO-BOLINAS #1 A8/85 RPR GYWW | 44640733 | IGNACIO-BOLINAS #1 | A008/085 | ICW | E | 2020_(2) High fire spread TD |  | 2020-12-16 | 2021-06-16 |  |  | 2021-05-17 | 2021-05-04 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.65373 | 38.0123 | ETL.7140 | 40577975 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120220901 | Mar | DI TESLA-STCKTN COGN JCT 1/12 COTR KEY | 44592404 | TESLA-STOCKTON COGEN JCT | 001/012 | ICW | B | 2020_(0) A and B Tags |  | 2020-12-16 | 2021-03-16 |  |  | 2021-03-16 | 2021-03-15 | [5 empty] | Central | WSIP | [6 empty] | '-121.550371 | 37.7039 | ETL.4010 | 40716629 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120220907 | Mar | DI NICOLAUS-WLKNS SLGH 12/240 RPL INSS | 31527909 | NICOLAUS-WILKINS SLOUGH | 012/240 | 93K | B | 2020_(0) A and B Tags |  | 2020-12-16 | 2021-03-16 |  |  | 2021-03-11 | 2021-03-11 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.62193 | 38.7781 | ETL.7710 | 40639448 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  | In Review | Complete | Awaiting ERTC |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120220908 | Mar | DI NICOLAUS-PLAINFIELD 12/240 RPL INSS | 31523834 | NICOLAUS-PLAINFIELD | 012/240 | 93K | B | 2020_(0) A and B Tags |  | 2020-12-16 | 2021-03-16 |  |  | 2021-03-11 | 2021-03-11 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.62193 | 38.7781 | ETL.7700 | 40639449 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120221192 | Mar | DI BRDS LDNG-CNTR CST SB 26/167 COTR KEY | 44592246 | BIRDS LNDNG SW STA-CONTRA COSTA PP | 026/167 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-16 | 2021-03-16 |  |  | 2021-03-03 | 2021-03-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.781452 | 38.0332 | ETL.5830 | 40920437 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120221193 | Mar | DI BRDS LDNG-CNTR CST SB 26/167 COTR KEY | 44592247 | BIRDS LANDING SS-CONTRA COSTA SUB | 026/167 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-16 | 2021-03-16 |  |  | 2021-03-03 | 2021-03-03 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.781452 | 38.0332 | ETL.6161 | 40920436 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120222264 | Q3 | DI CARIBOU #2 5/16 RPR GYWW |  | CARIBOU #2 | ;005/016 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-12-18 | 2021-12-18 |  |  | 2021-07-30 | 2021-07-12 | [5 empty] | North Valley | WSIP | [6 empty] | '-120.954754 | 39.9577 | ETL.6280 | 44860476 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120222378 | Mar | EI CLEAR LAKE-HOPLAND 0/13 RPR STRW | 44610498 | CLEAR LAKE-HOPLAND | 000/013 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-19 | 2021-11-19 |  |  | 2021-03-26 | 2021-03-24 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.0691 | 38.9701 | ETL.6390 | 40667038 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120222511 | Not Scheduled | T2 DRUM-SUMMIT #2 10/126B RPL CENTER POL |  | DRUM-SUMMIT #2 | 010/126 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-24 | 2021-08-24 | [7 empty] | TR2 | WECC | North Valley | [7 empty] | '-120.603803 | 39.3267 | ETL.1450 | 44558489 | Structure-Wood | Rotten | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120223960 | Q3 | DI CARIBOU #2 ;5/17 INS MRKW |  | CARIBOU #2 | ;005/017 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-12-18 | 2022-12-18 |  |  | 2021-07-30 | 2021-07-12 | [5 empty] | North Valley | WSIP | [6 empty] | '-120.955159 | 39.9572 | ETL.6280 | 44854690 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2020-12-30 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120224017 | Mar | COLUSA JCT #1 5/114 RPR SPLICE | 44592733 | COLUSA JCT #1 | 005/114 | ICW | B | 2020_(0) A and B Tags |  | 2020-12-17 | 2021-03-17 |  |  | 2021-03-02 | 2021-03-02 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.946789 | 39.127 | ETL.8390 | 40874209 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120224080 | Feb | DI GLD HLL-BLLT-LCKFRD 51/316 INS COT KY | 44592731 | GOLD HILL-BELLOTA-LOCKEFORD | 051/316 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-16 | 2021-03-16 |  |  | 2021-02-17 | 2021-02-17 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.140661 | 38.4272 | ETL.1690 | 40848052 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-31 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120224287 | Q2 | T3 DI TIGER CREEK-ELECTRA 1/11 RPR STRS |  | TIGER CREEK-ELECTRA | 001/011 | ICS | E | 2020_(2) High fire spread TD |  | 2020-12-18 | 2021-06-18 |  |  | 2021-04-01 | 2021-03-18 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.513332 | 38.4447 | ETL.5780 | 40586964 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120224412 | Not Scheduled | T3NT EI IGNCIO-BLINAS #1 7/083 INST ROAD | 31527010 | IGNACIO-BOLINAS #1 | 007/083 | 71Y | F | 2020_(4b) On structure in bucket 4 |  | 2020-12-15 | 2022-12-15 | [7 empty] | TR3 |  | North Coast | WSIP | [6 empty] | '-122.65343 | 38.0137 | ETL.7140 | 40808613 | Road | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120224984 | Not Scheduled | T2 WV VC-VCVL-JMSN-NTH TWR 8/63 RPL INSS | 31528998 | VACA-VACAVILLE-JAMESON-NTH TWR | 008/063 | 93K | E | 2020_(2) High fire spread TD |  | 2020-12-21 | 2021-12-21 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-122.032541 | 38.3394 | ETL.4100 | 44900304 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2021-01-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120226019 | Not Scheduled | T2 MENDOCINO-REDBUD 026/125 RPR SWTCH | 44610678 | MENDOCINO-REDBUD | 026/125 | ICE | E | 2020_(3) On high spread structure |  | 2020-12-21 | 2021-12-21 | [7 empty] | TR2 |  | North Coast | WSIP | [6 empty] | '-122.6614452 | 39.0292 | ETL.2410 | 41119845 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120226237 | Mar | DI COALINGA #1-SAN MIGUEL 2/41 REFRAME | 31522279 | COALINGA #1-SAN MIGUEL | 002/041 | 93E | B | 2020_(0) A and B Tags |  | 2020-12-21 | 2021-03-21 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.369698 | 36.1148 | ETL.8580 | 40606672 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2020-12-29 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120226327 | Mar | DI SAN BENITO-HOLLISTER 002/046 COT KEY | 44597175 | SAN BENITO-HOLLISTER | 002/046 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-21 | 2021-03-21 | 2021-03-15 | 2021-03-15 | 2021-03-15 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-121.52159 | 36.8661 | ETL.2901 | 40631829 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120226750 | Q3 | T2 DI CARIBOU #2 023/620 RPR GYWW |  | CARIBOU #2 | 023/620 | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-12-19 | 2021-12-19 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.970462 | 40.0393 | ETL.6280 | 44259137 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120226752 | Q3 | T2 DI CARIBOU-PLUMAS JCT 14/7B RPR GYWW |  | CARIBOU-PLUMAS JCT | 014/007B | ICW | E | 2020_(2) High fire spread TD |  | 2020-12-19 | 2021-12-19 |  |  | 2021-08-13 | 2021-08-02 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.953239 | 39.9571 | ETL.6290 | 42721921 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120227231 | Feb | DI LAKEVILLE-IGNACIO #1 7/32 COTR KEY | 44594791 | LAKEVILLE-IGNACIO #1 | 007/032 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-21 | 2021-03-21 |  |  | 2021-02-26 | 2021-01-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.501865 | 38.1714 | ETL.4940 | 40723952 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-14 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120227250 | Feb | DI LAKEVILLE-IGNACIO #1 5/24 RPLC INSS | 31518817 | LAKEVILLE-IGNACIO #1 | 005/024 | 93K | B | 2020_(0) A and B Tags |  | 2020-12-21 | 2021-03-21 |  |  | 2021-02-26 | 2021-01-22 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.514651 | 38.1957 | ETL.4940 | 40791594 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  | 2021-01-14 | Released-Standard | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120227392 | Mar | T2NT DI CRTN-MNDCN #1 29/141 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 029/141 | ICQ | F | 2020_(2) High fire spread TD |  | 2020-12-21 | 2022-12-21 |  |  | 2021-03-26 | 2021-03-22 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.725548 | 39.0411 | ETL.1330 | 40584921 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-02-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120228017 | Q4 | T3 DI MAPLE CREEK-HOOPA 012/002 RPR WDPK | 44592881 | MAPLE CREEK-HOOPA | 012/002 | ICW | E | 2020_(2) High fire spread TD |  | 2020-12-22 | 2021-06-22 |  |  | 2021-10-02 | 2021-07-26 |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.762235 | 40.905 | ETL.7490 | 40662163 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q4 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120228086 | Q2 | DI GARBERVILLE-LAYTONVILLE 53/5 RMV DBRS | 44572981 | GARBERVILLE-LAYTONVILLE | 053/005 | ICW | F | 2020_(3) On high spread structure |  | 2020-11-18 | 2022-11-18 |  |  | 2021-05-01 | 2021-04-19 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.647364 | 40.0652 | ETL.8365 | 40912594 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120229559 | Not Scheduled | DI DRM-SMMT #2 013/158 RMV DEBRIS | 44596211 | DRUM-SUMMIT #2 | 013/158 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-19 | 2022-11-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.558434 | 39.3214 | ETL.1450 | 44561375 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120229621 | Not Scheduled | DI DRM-SMMT #2 017/203 INST MRKW | 44596211 | DRUM-SUMMIT #2 | 017/203 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-19 | 2022-11-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.49986 | 39.3141 | ETL.1450 | 44557736 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120229622 | Not Scheduled | DI DRM-SMMT #1 17/204 RMV PL BUTT | 44596212 | DRUM-SUMMIT #1 | 017/204 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-19 | 2022-11-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.492488 | 39.3149 | ETL.1440 | 44777446 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120229629 | Not Scheduled | T2NT DI CARIBOU #2 024/629 RMV IDLE | 31527021 | CARIBOU #2 | 024/629 | 93J | F | 2020_(4) TD tag on high spread line |  | 2020-11-19 | 2022-11-19 | [9 empty] | North Valley | WSIP | [6 empty] | '-120.964437 | 40.0386 | ETL.6280 | 44259151 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120229640 | Q3 | T2NT DI CARIBOU #2 024/629 RMV DEBRIS |  | CARIBOU #2 | 024/629 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-19 | 2022-11-19 |  |  | 2021-07-30 | 2021-07-12 | [5 empty] | North Valley | WSIP | [6 empty] | '-120.964437 | 40.0386 | ETL.6280 | 44259151 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120229956 | Feb | COOLEY LANDING-STANFORD 3/046 RPR SWITCH | 44614178 | COOLEY LANDING-STANFORD | 003/046 | ICE | B | 2020_(0) A and B Tags |  | 2020-12-17 | 2021-03-23 |  |  | 2021-02-19 | 2021-02-19 | [5 empty] | Central | WSIP | [6 empty] | '-122.178895 | 37.456 | ETL.6570 | 44245117 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-30 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120230034 | Before Feb | T2 DI PHILO JCT-ELK 027/000 RPR CNDW | 44610684 | PHILO JCT-ELK | 027/000 | ICW | E | 2020_(2) High fire spread TD |  | 2020-12-22 | 2021-12-22 |  |  | 2021-01-25 | 2021-01-25 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.561013 | 39.0918 | ETL.7780 | 40605869 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Before Feb | Found in 2020 | Not FSR Upgrade | IC | Before Feb |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120232358 | Feb | T3NT DI MRGA-CLRMNT #1 003/025 RPR FOND |  | MORAGA-CLAREMONT #1 | 003/025 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-11-24 | 2022-11-24 |  |  | 2021-02-27 | 2021-02-22 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.21247 | 37.8498 | ETL.2700 | 40745866 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-08 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120232359 | Q3 | T2 DI CARIBOU-WESTWOOD 0/3 RMV DEBRIS |  | CARIBOU-WESTWOOD | 000/003 | ICW | F | 2020_(4b) On structure in bucket 4 |  | 2020-11-23 | 2022-11-23 |  |  | 2021-08-27 | 2021-08-16 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.147266 | 40.0855 | ETL.6300 | 40675245 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4b) On structure in bucket 4 | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120232429 | Mar | NT DI NEWARK-LIVERMORE 006/044 RPR FOND |  | NEWARK-LIVERMORE | 006/044 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-11-24 | 2022-11-24 |  |  | 2021-03-27 | 2021-03-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.887486 | 37.5516 | ETL.7660 | 40768462 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120232544 | Not Scheduled | DI DRUM-SUMMIT #2 016/189B RMV PL BUTT | 44597492 | DRUM-SUMMIT #2 | 016/189B | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-23 | 2022-11-23 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.520693 | 39.3099 | ETL.1450 | 42572817 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120233009 | Feb | DI IGNACIO-MARE ISLAND #1 9/68 RPLC INSS | 31516342 | IGNACIO-MARE ISLAND #1 | 009/068 | 93K | B | 2020_(0) A and B Tags |  | 2020-12-23 | 2021-03-23 |  |  | 2021-02-11 | 2021-02-11 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.403605 | 38.1546 | ETL.1830 | 40891921 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120233471 | Q2 | T2 DI FULTON-PUEBLO 006/034A BENT STL |  | FULTON-PUEBLO | 006/034A | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-12-24 | 2021-12-24 |  |  | 2021-05-14 | 2021-05-10 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.117721 | 38.5183 | ETL.1600 | 44865397 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120233524 | Mar | DI IGNACI-MR ISLND #1 A34/241A RPL SWCH |  | IGNACIO-MARE ISLAND #1 | A034/241A | 93S | B | 2020_(0) A and B Tags |  | 2020-12-24 | 2021-03-24 |  |  | 2021-03-24 | [5 empty] | <60D | North Coast | WSIP | [6 empty] | '-122.197091 | 38.0671 | ETL.1830 | 40743288 | Switch-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 435 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120234837 | Mar | HUMBOLDT-EUREKA 1/005A RPR SWITCH | 44597737 | HUMBOLDT-EUREKA | 001/005A | ICE | B | 2020_(0) A and B Tags |  | 2020-12-27 | 2021-03-27 | 2021-03-01 | 2021-03-01 | 2021-03-01 | 2021-03-01 | [5 empty] | North Coast | WSIP | [6 empty] | '-124.132115 | 40.7808 | ETL.7120 | 44321634 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-20 | Released-Standard | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120235812 | Q3 | T2 DI CARIBOU #2 ;000/009 RPR GYWW |  | CARIBOU #2 | ;000/009 | ICW | E | 2020_(2) High fire spread TD |  | 2020-12-24 | 2021-12-24 |  |  | 2021-07-30 | 2021-07-12 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.962579 | 40.0233 | ETL.6280 | 40863721 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | IC | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120236689 | Mar | DI NEWARK-JARVIS #1 012/071 APPLY MASTIC |  | NEWARK-JARVIS #1 | 012/071 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-11-25 | 2022-11-25 |  |  | 2021-03-27 | 2021-03-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.984116 | 37.5918 | ETL.3020 | 40580877 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-21 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120236778 | Mar | DI NEWARK-JARVIS #1 012/070 APPLY MASTIC |  | NEWARK-JARVIS #1 | 012/070 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-11-25 | 2022-11-25 |  |  | 2021-03-27 | 2021-03-22 | [5 empty] | Central | WSIP | [6 empty] | '-121.978042 | 37.5922 | ETL.3020 | 40581666 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-21 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120237168 | Not Scheduled | DI DRUM-SUMMIT #1 023/277 INS HV | 44598097 | DRUM-SUMMIT #1 | 023/277 | ICW | F | 2020_(1b) Lines with special commitments |  | 2020-11-23 | 2022-11-23 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.39025 | 39.3112 | ETL.1440 | 40814986 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120237827 | Not Scheduled | EI SALINAS-LAURELES A018/383 RPL POLE | 31487465 | SALINAS-LAURELES | A018/383 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-12-29 | 2021-12-29 | [9 empty] | South | WSIP | [6 empty] | '-121.862366 | 36.5857 | ETL.7930 | 40680327 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  |  | Caltrans (DSDD) | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120238333 | Not Scheduled | T3NT DI SNTH LN-HF MN BY ?5/0 RMV PL BUT | 44621950 | SNEATH LANE-HALF MOON BAY | ?005/000 | ICW | F | 2020_(3) On high spread structure |  | 2020-12-02 | 2022-12-02 | [7 empty] | TR3 |  | Central | WSIP | [6 empty] | '-122.463429 | 37.5509 | ETL.7212 | 40601801 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(3) On high spread structure | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120238546 | Feb | T2NT DI MNT VST-JFFRN #1 10/44 APL MASTC |  | MONTA VISTA-JEFFERSON #1 | 010/044 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-12-02 | 2022-12-02 |  |  | 2021-02-20 | 2021-02-15 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.256741 | 37.3437 | ETL.5220 | 40760859 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 11 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-02-08 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120239756 | Feb | EI BELLOTA-WEBER 06/048 INS COTER KEY | 44598059 | BELLOTA-WEBER | 006/048 | ICS | B | 2020_(0) A and B Tags |  | 2020-12-23 | 2021-03-23 |  |  | 2021-02-17 | 2021-02-16 | [5 empty] | Central | WSIP | [6 empty] | '-121.1163236 | 37.9578 | ETL.4390 | 40879128 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 3 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2021-01-04 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120241183 | Q2 | T2NT DI PTTSBRG-SAN MTO 8/34 MASTIC |  | PITTSBURG-SAN MATEO | 008/034 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-12-04 | 2022-12-04 |  |  | 2021-04-24 | 2021-04-19 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.888931 | 37.9278 | ETL.5463 | 40862985 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120241313 | Mar | EI PITTSBURG-MRTINEZ #2 12/067 RPR SWTCH | 44614457 | PITTSBURG-MARTINEZ #2 | 012/067 | ICE | B | 2020_(0) A and B Tags |  | 2020-12-30 | 2021-03-30 |  |  | 2021-03-17 | 2021-03-17 | [5 empty] | Central | WSIP | [6 empty] | '-122.06619 | 38.0178 | ETL.3330 | 40743401 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Bay |  | Y - 4 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-08 | Released-SpecialCond | Complete | Ready for Construction |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120241744 | Q2 | DI SOBRANTE-STNDRD OIL#1 8/48 MASTIC |  | SOBRANTE-STANDARD OIL SW STA #2 | 008/048 | ICQ | F | 2020_(4) TD tag on high spread line |  | 2020-12-10 | 2022-12-10 |  |  | 2021-05-22 | 2021-05-17 | [5 empty] | Central | WSIP | [6 empty] | '-122.243851 | 37.9978 | ETL.3800 | 40857859 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-21 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120242755 | Mar | EI SOLEDAD #1 3/075 RPR SPLW | 44609671 | SOLEDAD #1 | 003/075 | ICW | B | 2020_(0) A and B Tags |  | 2020-12-30 | 2021-03-28 |  |  | 2021-03-26 | 2021-03-26 | [5 empty] | South | WSIP | [6 empty] | '-121.3905037 | 36.4659 | ETL.8010 | 40613192 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120243177 | Not Scheduled | T2 DRUM-SUMMIT #1 6/081 RPL POLE | 31508705 | DRUM-SUMMIT #1 | 006/081 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.6715974 | 39.3073 | ETL.1440 | 44765651 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243178 | Not Scheduled | T2 DRUM-SUMMIT #1 9/105R RPL POLE | 31508705 | DRUM-SUMMIT #1 | 009/105 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.6328541 | 39.3176 | ETL.1440 | 44837642 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243179 | Not Scheduled | T2 DRUM-SUMMIT #1 19/225 RPL POLE | 31453474 | DRUM-SUMMIT #1 | 019/225 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.460476 | 39.3191 | ETL.1440 | 40813766 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243213 | Not Scheduled | T2 DRUM-SUMMIT #1 6/081 RPL POLE | 31508705 | DRUM-SUMMIT #1 | 006/081 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.6715974 | 39.3073 | ETL.1440 | 44765650 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243214 | Not Scheduled | T2 DRUM-SUMMIT #1 9/105L RPL POLE | 31508705 | DRUM-SUMMIT #1 | 009/105 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.6328587 | 39.3176 | ETL.1440 | 44837685 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243216 | Not Scheduled | T2 DRUM-SUMMIT#2 12/139R RPL POLE | 31498154 | DRUM-SUMMIT #2 | 012/139 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.5838238 | 39.333 | ETL.1450 | 44561214 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243217 | Not Scheduled | T2 DRUM-SUMMIT#2 18/219L RPL POLE | 31521949 | DRUM-SUMMIT #2 | 018/219 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4773275 | 39.3178 | ETL.1450 | 44557532 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243219 | Not Scheduled | T2 DRUM-SUMMIT#2 18/219R RPL POLE | 31521949 | DRUM-SUMMIT #2 | 018/219 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4773311 | 39.3178 | ETL.1450 | 44557533 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243220 | Not Scheduled | T2 DRUM-SUMMIT#2 12/139L RPL POLE | 31498154 | DRUM-SUMMIT #2 | 012/139 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.5838163 | 39.333 | ETL.1450 | 44561220 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243221 | Not Scheduled | T2 DRUM-SUMMIT#2 12/139C RPL POLE | 31498154 | DRUM-SUMMIT #2 | 012/139 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.5838002 | 39.333 | ETL.1450 | 44561213 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243225 | Not Scheduled | T2 DRUM-SUMMIT#2 18/222R RPL POLE | 31521949 | DRUM-SUMMIT #2 | 018/222 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4729457 | 39.3182 | ETL.1450 | 44557569 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243227 | Not Scheduled | T2 DRUM-SUMMIT#2 18/223L RPL POLE | 31521949 | DRUM-SUMMIT #2 | 018/223 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4709366 | 39.3186 | ETL.1450 | 44565754 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243228 | Not Scheduled | T2 DRUM-SUMMIT#2 18/223R RPL POLE | 31521949 | DRUM-SUMMIT #2 | 018/223 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4709382 | 39.3186 | ETL.1450 | 44565791 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243229 | Not Scheduled | T2 DRUM-SUMMIT#2 21/258 RPL POLE | 31521951 | DRUM-SUMMIT #2 | 021/258 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4191793 | 39.3281 | ETL.1450 | 44553753 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243270 | Not Scheduled | T2 DRUM-SUMMIT#2 18/222L RPL POLE | 31521949 | DRUM-SUMMIT #2 | 018/222 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4729454 | 39.3182 | ETL.1450 | 44557649 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243271 | Not Scheduled | T2 DRUM-SUMMIT#2 18/222C RPL POLE | 31521949 | DRUM-SUMMIT #2 | 018/222 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4729462 | 39.3182 | ETL.1450 | 44557789 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243274 | Not Scheduled | T2 DRUM-SUMMIT #2 023/282B RPL POLE | 31521951 | DRUM-SUMMIT #2 | 023/282B | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.381056 | 39.3275 | ETL.1450 | 42572841 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243278 | Not Scheduled | T2 DRUM-SUMMIT #2 23/282C RPL POLE | 31521951 | DRUM-SUMMIT #2 | 023/282C | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.381138 | 39.3275 | ETL.1450 | 42572842 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243300 | Not Scheduled | T2 DRUM-SUMMIT#2 21/258 RPL POLE | 31521951 | DRUM-SUMMIT #2 | 021/258 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4191747 | 39.3281 | ETL.1450 | 44553514 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243301 | Not Scheduled | T2 DRUM-SUMMIT #2 23/282A RPL POLE | 31521951 | DRUM-SUMMIT #2 | 023/282A | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.38101 | 39.3275 | ETL.1450 | 40660471 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243305 | Not Scheduled | T2 DRUM-SUMMIT#2 27/329L RPL POLE | 31521951 | DRUM-SUMMIT #2 | 027/329 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.3312367 | 39.3138 | ETL.1450 | 44557779 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243306 | Not Scheduled | T2 DRUM-SUMMIT#2 27/329R RPL POLE | 31521951 | DRUM-SUMMIT #2 | 027/329 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.331232 | 39.3138 | ETL.1450 | 44557643 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243308 | Not Scheduled | T2 DRUM-SUMMIT#2 27/331L RPL POLE | 31521951 | DRUM-SUMMIT #2 | 027/331 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.3298525 | 39.3159 | ETL.1450 | 44553636 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243320 | Not Scheduled | T2 DRUM-SUMMIT#2 27/331R RPL POLE | 31521951 | DRUM-SUMMIT #2 | 027/331 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-31 | 2021-12-31 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.3298531 | 39.3159 | ETL.1450 | 44553708 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243328 | Not Scheduled | T3 DRUM - HIGGINS 0/5 LEFT RPL STRW | 31526384 | DRUM-HIGGINS | 000/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-12-31 | 2021-06-30 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.7660779 | 39.251 | ETL.4393 | 44172123 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243329 | Not Scheduled | T3 DRUM - HIGGINS 0/5 RPL STRW | 31526384 | DRUM-HIGGINS | 000/005 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-12-31 | 2021-06-30 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.76607 | 39.2509 | ETL.4393 | 44172124 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243384 | Not Scheduled | T3 DRUM - HIGGINS 0/6 RIGHT RPL STRW | 31526384 | DRUM-HIGGINS | 000/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-12-31 | 2021-06-30 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.7653622 | 39.2484 | ETL.4393 | 44172134 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243385 | Not Scheduled | T3 DRUM-HIGGINS 0/07 RPL POLE | 31526384 | DRUM-HIGGINS | 000/007 | 70Y | E | 2020_(2) High fire spread TD |  | 2020-12-31 | 2021-06-30 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.765153 | 39.2477 | ETL.4393 | 40862221 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243386 | Not Scheduled | T3 DRUM - HIGGINS 0/5 LEFT RPL STRW | 31526384 | DRUM-HIGGINS | 000/008 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-12-31 | 2021-06-30 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.7649009 | 39.2468 | ETL.4393 | 44172276 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243401 | Not Scheduled | T3 DRUM - HIGGINS 0/6 LEFT RPL STRW | 31526384 | DRUM-HIGGINS | 000/006 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-12-31 | 2021-06-30 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.7653618 | 39.2484 | ETL.4393 | 44172133 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243404 | Not Scheduled | T3 DRUM - HIGGINS 0/8 RIGHT RPL STRW | 31526384 | DRUM-HIGGINS | 000/008 | 70Y | E | 2020_(4) TD tag on high spread line |  | 2020-12-31 | 2021-06-30 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.7648999 | 39.2468 | ETL.4393 | 44172277 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243420 | Not Scheduled | T3 DRUM-HIGGINS 0/009C RPL STR |  | DRUM-HIGGINS | 000/009C | ICQ | E | 2020_(4) TD tag on high spread line |  | 2020-12-31 | 2021-06-30 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.764689 | 39.2458 | ETL.4393 | 44254475 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120243904 | Q2 | DI GATES-PANOCHE #1 0/1B APPLY MASTIC | 44609914 | GATES-PANOCHE #1 | 000/001B | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-12-10 | 2022-12-10 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.123875 | 36.1426 | ETL.4720 | 44192013 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120244781 | Q2 | DI GATES-PANOCHE #1 000/002 APLY MASTIC | 44609915 | GATES-PANOCHE #1 | 000/002 | ICQ | F | 2020_(1b) Lines with special commitments |  | 2020-12-12 | 2022-12-12 |  |  | 2021-06-01 | 2021-04-15 |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.12414 | 36.1425 | ETL.4720 | 40663914 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLO | Tower | Expense | 543 | Fresno |  |  |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120244785 | Not Scheduled | DI GATES-PANOCHE #1 000/001A INS MRKS | 44623663 | GATES-PANOCHE #1 | 000/001A | ICS | F | 2020_(1b) Lines with special commitments |  | 2020-12-12 | 2022-12-12 | [8 empty] | WECC | South | WSIP | [6 empty] | '-120.123999 | 36.1424 | ETL.4720 | 44188770 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120256749 | Not Scheduled | T2 COLGATE-SMARTVILLE #2 000/007C RPR ST | 44611191 | COLGATE-SMARTVILLE #2 | 000/007C | ICW | E | 2020_(4) TD tag on high spread line |  | 2020-11-30 | 2021-11-30 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.193703 | 39.3291 | ETL.6520 | 42562715 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(4) TD tag on high spread line | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120257734 | Not Scheduled | T3 EI BRIDGVL-GRBRVL 11/5 RPR GYWW | 44542334 | BRIDGEVILLE-GARBERVILLE | 011/005 | ICW | E | 2020_(2) High fire spread TD |  | 2020-01-05 | 2020-07-05 | [7 empty] | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.71576 | 40.3508 | ETL.6220 | 40752659 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-01-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120258108 | Mar | T2 EI HMBLDT-TRINTY 90/2R RPL POLE COMP | 31433539 | HUMBOLDT-TRINITY | 090/002 | 70Y | E | 2020_(2) High fire spread TD |  | 2019-01-25 | 2020-01-25 |  |  | 2021-03-27 | 2021-03-01 |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-123.686355 | 40.7374 | ETL.1820 | 45014066 | Structure-Wood | No Good/Out of Stdrd | Replace | MAPP | MAPP | Constructed and mapped | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120259723 | Mar | T2 CAYUCOS-CAMBRIA 17/124 REPL INSW | 31527288 | CAYUCOS-CAMBRIA | 017/124 | 93I | B | 2021_(0) A and B Tags |  | 2021-01-05 | 2021-04-05 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.096078 | 35.5929 | ETL.8560 | 40685070 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Mar | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-11 | Released-SpecialCond | Complete | Ready for Construction |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120278762 | Q2 | T3 DI SOBRANTE-R #2 2/016 HANGER | 44622517 | SOBRANTE-R #2 | 002/016 | ICQ | E | 2020_(2) High fire spread TD |  | 2020-04-20 | 2020-10-20 | 2021-03-22 | 2021-03-22 | 2021-05-15 | 2021-05-10 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.249096 | 37.9103 | ETL.3780 | 40830934 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 1 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-28 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(2) High fire spread TD | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120354820 | Mar | EI COTTONWOOD #2 20/134 RPR SWS | 44623610 | COTTONWOOD #2 | 020/134 | ICE | B | 2021_(0) A and B Tags |  | 2021-01-06 | 2021-04-06 |  |  | 2021-03-25 | 2021-03-25 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.236219 | 40.1281 | ETL.6630 | 41147658 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Mar | Not FSR Upgrade | IC | Mar |  |  | 2021-01-20 | Released-Standard | Complete | Ready for Construction |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120400379 | Mar | EI COTTONWD-GLENN 93/771 REPL INSS | 31527648 | COTTONWOOD-GLENN | 093/771 | 93K | B | 2021_(0) A and B Tags |  | 2021-01-06 | 2021-04-06 |  |  | 2021-03-24 | 2021-03-22 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.2658202 | 39.9122 | ETL.4560 | 40621419 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Mar | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120400580 | Mar | EI COTTONWD-GLENN 93/770 RPL INSS | 31527648 | COTTONWOOD-GLENN | 093/770 | 93K | B | 2021_(0) A and B Tags |  | 2021-01-06 | 2021-04-06 |  |  | 2021-03-24 | 2021-03-22 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.2658043 | 39.9144 | ETL.4560 | 40638357 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Mar | Not FSR Upgrade | 93 | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120400605 | Mar | EI COTTONWD-GLENN 93/769 RPL INSS | 31527648 | COTTONWOOD-GLENN | 093/769 | 93K | B | 2021_(0) A and B Tags |  | 2021-01-06 | 2021-04-06 |  |  | 2021-03-24 | 2021-03-22 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.2658181 | 39.9166 | ETL.4560 | 40891491 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Mar | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120406886 | Mar | BRIONES TAP 0/1 SW65 RPR SWITCH | 44621953 | BRIONES TAP | 000/001 | ICE | B | 2021_(0) A and B Tags |  | 2021-01-08 | 2021-04-08 |  |  | 2021-03-27 | 2021-03-27 | [5 empty] | Central | WSIP | [6 empty] | '-121.72267 | 37.904 | ETL.7055 | 40743794 | Switch | Out of Adjustment | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Bay |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Mar | Not FSR Upgrade | IC | Mar |  |  | 2021-01-21 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120408603 | Q2 | MIDWAY-SHAFTER 5/056 RPL STRT | 31527989 | MIDWAY-SHAFTER | 005/056 | 70S | B | 2021_(0) A and B Tags |  | 2021-01-09 | 2021-04-09 |  |  | 2021-04-05 | 2021-04-05 | [5 empty] | South | WSIP | [6 empty] | '-119.374527 | 35.442 | ETL.2610 | 40749187 | Structure-Tower | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLO | Pole Program | Capital | 426 | Midway |  | Y - 5 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Q2 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-12 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120420719 | Mar | EI JAYNE SW STA-COALINGA 2/17 RPR CRSW | 44624570 | JAYNE SW STA-COALINGA | 002/017 | ICW | B | 2021_(0) A and B Tags |  | 2021-01-08 | 2021-04-07 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-29 | [5 empty] | South | WSIP | [6 empty] | '-120.17796 | 36.1375 | ETL.8670 | 40806385 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 7 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Mar | Not FSR Upgrade | IC | Mar |  |  | 2021-01-15 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120422201 | Mar | EI CORCORAN-GUERNSEY 10/012 RPL POLE | 31528341 | CORCORAN-GUERNSEY | 010/012 | 70Y | B | 2021_(0) A and B Tags |  | 2021-01-12 | 2021-04-12 | 2021-03-02 | 2021-03-02 | 2021-03-02 | 2021-03-02 | [5 empty] | South | WSIP | [6 empty] | '-119.645818 | 36.1948 | ETL.9360 | 40686446 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Mar | Not FSR Upgrade | 70 | Mar |  |  | 2021-01-15 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120425324 | Not Scheduled | SIERRA #1 17/115 RPR SPLS | 44650646 | SIERRA #2 (IDLE) | 017/115 | ICS | B | 2021_(0) A and B Tags |  | 2021-01-13 | 2021-04-13 | [8 empty] | <60D | Central | WSIP | [6 empty] | '-122.2281136 | 37.5376 | ETL.3680 | 41195151 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 5 |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IC | Not Scheduled |  |  | 2021-02-12 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120426298 | Mar | T3 EI BRIDGVL-GRBRVL 3/15 INS COT KEY | 44542334 | BRIDGEVILLE-GARBERVILLE | 003/015 | ICW | B | 2021_(0) A and B Tags |  | 2021-01-12 | 2021-04-12 |  |  | 2021-03-10 | 2021-03-10 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.801002 | 40.4649 | ETL.6220 | 40781059 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Mar | Not FSR Upgrade | IC | Mar |  |  | 2021-01-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120429448 | Feb | WV CORTINA #2 13/226 INS DAMPW | 44630801 | CORTINA #2 | 013/226 | ICW | B | 2021_(0) A and B Tags |  | 2021-01-14 | 2021-04-14 |  |  | 2021-02-18 | 2021-02-18 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.0636404 | 39.0276 | ETL.6590 | 40786629 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Feb | Not FSR Upgrade | IC | Feb |  |  | 2021-02-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120433414 | Mar | EI MERCED #1 11/002 RPL INSW | 31528638 | MERCED #1 | 011/002 | 93I | B | 2021_(0) A and B Tags |  | 2021-01-15 | 2021-04-15 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | [5 empty] | South | WSIP | [6 empty] | '-120.4734298 | 37.1283 | ETL.9000 | 40727584 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Fresno |  | Y - 12 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Mar | Not FSR Upgrade | 93 | Mar |  |  | 2021-01-25 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120460793 | Q2 | TAFT-CUYAMA #1 11/106 REPL INSW | 31528889 | TAFT-CUYAMA #1 | 011/106 | 93I | B | 2021_(0) A and B Tags |  | 2021-01-25 | 2021-04-25 |  |  | 2021-04-01 | 2021-04-01 | [5 empty] | South | WSIP | [6 empty] | '-119.61399 | 35.0167 | ETL.9200 | 40583961 | Insulator-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Midway |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Q2 | Not FSR Upgrade | 93 | Q2 |  |  | 2021-02-01 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120463899 | Q2 | EI BELLOTA-WEBER 13/091 RPL HNGR PLATE | 44639523 | BELLOTA-WEBER | 013/091 | ICQ | B | 2021_(0) A and B Tags |  | 2021-01-26 | 2021-04-26 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | [5 empty] | Central | WSIP | [6 empty] | '-121.225617 | 37.9226 | ETL.4390 | 40603390 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 4 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Q2 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120463919 | Q2 | EI BELLOTA-TESLA#2 13/091 REPL HNRG PL | 44639521 | BELLOTA-TESLA #2 | 013/091 | ICQ | B | 2021_(0) A and B Tags |  | 2021-01-26 | 2021-04-26 | 2021-04-06 | 2021-04-07 | 2021-04-07 | 2021-04-06 | [5 empty] | Central | WSIP | [6 empty] | '-121.225617 | 37.9226 | ETL.4370 | 40603391 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 1 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Q2 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120463965 | Q2 | EI BELLOTA-TESLA #2 13/092 REPL HNGR PL | 44639522 | BELLOTA-TESLA #2 | 013/092 | ICQ | B | 2021_(0) A and B Tags |  | 2021-01-26 | 2021-04-26 | 2021-04-06 | 2021-04-07 | 2021-04-07 | 2021-04-06 | [5 empty] | Central | WSIP | [6 empty] | '-121.2285297 | 37.9219 | ETL.4370 | 40703466 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 1 |  | Yes | No | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Q2 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120464965 | Mar | TAFT-CUYAMA #1 1/20 REPL ANCW | 31528971 | TAFT-CUYAMA #1 | 001/020 | 93E | B | 2021_(0) A and B Tags |  | 2021-01-26 | 2021-04-26 |  |  | 2021-03-15 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-119.504475 | 35.117 | ETL.9200 | 40606525 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Midway |  | Y - 15 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Mar | Not FSR Upgrade | 93 | Mar |  |  | 2021-02-01 | Released-SpecialCond | Complete | Ready for Construction |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120470777 | Not Scheduled | EI WHEELER RIDGE-TEJON 0/012 RPR POLE | 44636848 | WHEELER RIDGE-TEJON | 000/012 | IBE | B | 2021_(0) A and B Tags |  | 2021-01-27 | 2021-04-27 | [8 empty] | <90D | South | WSIP | [6 empty] | '-118.974812 | 35.0806 | ETL.9310 | 40583250 | Emergency | Storm Related | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 591 | Midway |  | Y - 3 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IB | Not Scheduled |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120471016 | Q2 | EI KERN-KERN FRONT 9/144 RPL SPACER BAR | 44636846 | KERN-KERN FRONT | 009/144 | ICW | B | 2021_(0) A and B Tags |  | 2021-01-27 | 2021-04-27 |  |  | 2021-04-07 | 2021-04-06 | [5 empty] | South | WSIP | [6 empty] | '-119.073901 | 35.4959 | ETL.1930 | 40807557 | Spacer-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 4 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Q2 | Not FSR Upgrade | IC | Q2 |  |  | 2021-02-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120471018 | Not Scheduled | EI WHEELER RIDGE-TEJON 0/013 RPR POLE | 44636848 | WHEELER RIDGE-TEJON | 000/013 | IBE | B | 2021_(0) A and B Tags |  | 2021-01-27 | 2021-04-27 | [8 empty] | <90D | South | WSIP | [6 empty] | '-118.974509 | 35.0797 | ETL.9310 | 40652746 | Emergency | Storm Related | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 591 | Midway |  | Y - 3 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IB | Not Scheduled |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120471044 | Not Scheduled | EI WHEELER RIDGE-TEJON 0/014 RPR POLE | 44636848 | WHEELER RIDGE-TEJON | 000/014 | IBE | B | 2021_(0) A and B Tags |  | 2021-01-27 | 2021-04-27 | [8 empty] | <90D | South | WSIP | [6 empty] | '-118.974225 | 35.0787 | ETL.9310 | 40646984 | Emergency | Storm Related | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 591 | Midway |  | Y - 3 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IB | Not Scheduled |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120471152 | Not Scheduled | EI WHEELER RIDGE-TEJON 0/015 RPR POLE | 44636848 | WHEELER RIDGE-TEJON | 000/015 | IBE | B | 2021_(0) A and B Tags |  | 2021-01-27 | 2021-04-27 | [8 empty] | <90D | South | WSIP | [6 empty] | '-118.973923 | 35.0778 | ETL.9310 | 40748774 | Emergency | Storm Related | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 591 | Midway |  | Y - 3 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IB | Not Scheduled |  |  | 2021-02-02 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120475378 | Feb | T3 BURNS-LONE STAR #2 1/029 RPR SPLW | 44638254 | BURNS-LONE STAR #2 | 001/029 | ICW | B | 2021_(0) A and B Tags |  | 2021-01-28 | 2021-04-28 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-122.1400484 | 37.0779 | ETL.6240 | 43601113 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 16 |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Feb | Not FSR Upgrade | IC | Feb |  |  | 2021-02-05 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120475392 | Q2 | WV T2 DEL MONTE-VIEJO 6/147 INST DAMW | 44638255 | DEL MONTE-VIEJO (NO FLY) | 006/147 | ICW | B | 2021_(0) A and B Tags |  | 2021-01-28 | 2021-04-28 | 2021-04-12 | 2021-04-12 | 2021-04-12 | 2021-04-12 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.911722 | 36.5701 | ETL.6710 | 44925284 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Q2 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120485232 | Not Scheduled | HP1, Add N2 | 44640963 | ETU.9954 | H TERMINAL | ICU | B | 2021_(0) A and B Tags |  | 2021-02-01 | 2021-05-01 | [8 empty] | <90D | Central | [7 empty] | '-122.408167 | 37.704 | ETU.9954 | 41113017 | Gas System-Underground | Inadequate Pressure | Adjust | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Expense | 629 | Martin |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120485244 | Q2 | DI IGNACIO-ALTO-SAULITO #1 9/63 RPR OPGW | 44382474 | IGNACIO-ALTO-SAUSALITO #1 | 009/063 | ICS | B | 2021_(0) A and B Tags |  | 2021-01-30 | 2021-04-30 |  |  | 2021-04-30 | [5 empty] | <90D | North Coast | WSIP | [6 empty] | '-122.502587 | 37.9489 | ETL.7160 | 40812265 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Q2 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120486344 | Not Scheduled | AHW2 (Aw2) add N2 | 44640966 | ETU.9955 | A TERMINAL | ICU | B | 2021_(0) A and B Tags |  | 2021-02-01 | 2021-05-01 | [8 empty] | <90D | Central | [7 empty] | '-122.3864993 | 37.7563 | ETU.9955 | 41113090 | Gas System-Underground | Inadequate Pressure | Adjust | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Expense | 629 | Martin |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120486843 | Not Scheduled | PX2 add N2 | 44640967 | ETU.9959 | P TERMINAL | ICU | B | 2021_(0) A and B Tags |  | 2021-02-01 | 2021-05-01 | [8 empty] | <90D | Central | [7 empty] | '-122.3798736 | 37.7376 | ETU.9959 | 41113402 | Gas System-Underground | Inadequate Pressure | Adjust | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Expense | 629 | Martin |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120496126 | Not Scheduled | MM1, add N2 | 44640968 | ETU.9972 | NORTH TERMINAL | ICU | B | 2021_(0) A and B Tags |  | 2021-02-03 | 2021-05-03 | [8 empty] | <90D | Central | [7 empty] | '-122.4054233 | 37.6363 | ETU.9972 | 41113459 | Gas System-Underground | Inadequate Pressure | Adjust | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Expense | 629 | Martin |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120497422 | Q2 | VALLEY SPRINGS #1 16/341 REPL POLE | 31529270 | VALLEY SPRINGS #1 | 016/341 | 92T | B | 2021_(0) A and B Tags |  | 2021-02-03 | 2021-05-01 |  |  | 2021-04-15 | 2021-04-14 | [5 empty] | Central | WSIP | [6 empty] | '-120.991765 | 38.0682 | ETL.8210 | 40904296 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Q2 | Not FSR Upgrade | 92 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120497574 | Q2 | VALLEY SPRINGS #1 16/340 REPL POLE | 31529270 | VALLEY SPRINGS #1 | 016/340 | 92T | B | 2021_(0) A and B Tags |  | 2021-02-01 | 2021-05-03 |  |  | 2021-04-15 | 2021-04-14 | [5 empty] | Central | WSIP | [6 empty] | '-120.990946 | 38.0683 | ETL.8210 | 40904295 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 372 | Victor |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Q2 | Not FSR Upgrade | 92 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120497576 | Not Scheduled | CL-1 add N2 | 44640973 | ETU.9961 | L TERMINAL | ICU | B | 2021_(0) A and B Tags |  | 2021-02-01 | 2021-05-01 | [8 empty] | <90D | Central | [7 empty] | '-122.2713901 | 37.8101 | ETU.9961 | 41113098 | Gas System-Underground | Inadequate Pressure | Adjust | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Expense | 629 | Martin |  |  |  | Yes | No | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120499462 | Q2 | T3 MIDDLE FORK #1 2/038 REPL POLE | 35231517 | MIDDLE FORK #1 | 002/038 | 70Y | B | 2021_(0) A and B Tags |  | 2021-02-04 | 2021-05-04 |  |  | 2021-04-24 | 2021-04-24 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.616504 | 39.0014 | ETL.8405 | 40660036 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Q2 | Not FSR Upgrade | 70 | Q2 |  |  |  |  | Complete | Awaiting ERTC |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120502482 | Mar | EI RIO OSO-BRIGHTON 4/033 RPR OPGW | 44645315 | RIO OSO-BRIGHTON | 004/033 | ICS | B | 2021_(0) A and B Tags |  | 2021-02-05 | 2021-05-05 |  |  | 2021-03-24 | 2021-03-24 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.450048 | 38.8685 | ETL.5600 | 40644519 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Mar | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120502724 | Not Scheduled | EI ARCO-TULARE LAKE 004/075 RPR SW | 44650888 | ARCO-TULARE LAKE | 004/075 | ICW | B | 2021_(0) A and B Tags |  | 2021-02-05 | 2021-05-05 | [8 empty] | <90D | South | WSIP | [6 empty] | '-119.915419 | 35.8436 | ETL.8460 | 40744222 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120504000 | Not Scheduled | T2 EI DRUM-SUMMIT #2 24/289A RPR GYWW | 44644147 | DRUM-SUMMIT #2 | 024/289A | ICW | B | 2021_(0) A and B Tags |  | 2021-02-05 | 2021-05-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.380545 | 39.3221 | ETL.1450 | 44766885 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120506625 | Not Scheduled | PEACHTON-PEASE 23/485 SW59 RPR SWITCH |  | PEACHTON-PEASE | 023/485 | ICE | B | 2021_(0) A and B Tags |  | 2021-02-08 | 2021-05-08 | [8 empty] | <90D | North Valley | WSIP | [6 empty] | '-121.660042 | 39.2763 | ETL.8426 | 40853070 | Switch | Out of Adjustment | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 623 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120507134 | Q2 | EI MOSS LNDING-GRN VALLY #2 1/8 RPR COND | 44649472 | MOSS LANDING-GREEN VALLEY #2 | 001/008 | ICS | B | 2021_(0) A and B Tags |  | 2021-02-08 | 2021-05-08 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2021-04-01 | [5 empty] | South | WSIP | [6 empty] | '-121.7629077 | 36.8037 | ETL.2860 | 40903252 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  |  |  | Yes | No | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Q2 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120526615 | Not Scheduled | T2 DI DRUM-SUMMIT #2 25/305R REPL POLE |  | DRUM-SUMMIT #2 | 025/305 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-24 | 2021-08-24 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.366028 | 39.3102 | ETL.1450 | 44558975 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120526869 | Not Scheduled | HALSEY-PLACER 4/97 REPL POLE | 31521650 | HALSEY-PLACER | 004/097 | 70Y | B | 2021_(0) A and B Tags |  | 2021-02-11 | 2021-05-11 | [8 empty] | <90D | North Valley | [7 empty] | '-121.082413 | 38.9048 | ETL.6990 | 40815279 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120526934 | Not Scheduled | T3 DI DRUM-SUMMIT #2 4/55B RPL STRW |  | DRUM-SUMMIT #2 | 004/055B | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-01 | 2021-06-01 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.704306 | 39.2923 | ETL.1450 | 42572755 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120526936 | Not Scheduled | T3 DI DRUM-SUMMIT #2 4/55A RPL STRW |  | DRUM-SUMMIT #2 | 004/055A | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-12-01 | 2021-06-01 | [7 empty] | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.704355 | 39.2924 | ETL.1450 | 40869617 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120526977 | Not Scheduled | T2 DI DRUM-SUMMIT #2 22/263R REPL POLE |  | DRUM-SUMMIT #2 | 022/263 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-01 | 2021-07-01 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.411689 | 39.3285 | ETL.1450 | 44557730 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120527356 | Not Scheduled | T2 DI DRUM-SUMMIT#2 9/112R RPL POLE |  | DRUM-SUMMIT #2 | 009/112 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-20 | 2021-07-20 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.622018 | 39.321 | ETL.1450 | 44553509 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120527529 | Not Scheduled | T2 DI DRUM-SUMMIT #2 7/81C RPL STRW |  | DRUM-SUMMIT #2 | 007/081C | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.668167 | 39.3078 | ETL.1450 | 44987814 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120527571 | Not Scheduled | T2 DI DRUM-SUMMIT #2 7/81A RPL STRW |  | DRUM-SUMMIT #2 | 007/081A | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-07-14 | 2021-07-14 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.668199 | 39.3078 | ETL.1450 | 44987813 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120528428 | Not Scheduled | T2 DI DRUM-SUMMIT #2 018/216R REPL POLE |  | DRUM-SUMMIT #2 | 018/216 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-05 | 2021-08-05 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.481913 | 39.3173 | ETL.1450 | 44552319 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120528555 | Not Scheduled | T2 DI DRUM-SUMMIT #2 012/145L REPL POLE |  | DRUM-SUMMIT #2 | 012/145 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-08-18 | 2021-08-18 | [7 empty] | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.573569 | 39.3322 | ETL.1450 | 44561286 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-08-31
2021 Work Plan | 120528641 | Not Scheduled | DI RUM-SUMMIT#2 13/157L REPL POLE |  | DRUM-SUMMIT #2 | 013/157 | 70Y | E | 2020_(1b) Lines with special commitments |  | 2020-11-19 | 2021-11-19 | [8 empty] | WECC | North Valley | WSIP | [6 empty] | '-120.560067 | 39.3227 | ETL.1450 | 44561206 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  |  | Yes | No | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(1b) Lines with special commitments | Pending Repair | 2021 Plan | 2021-12-31
2021 Work Plan | 120531117 | Not Scheduled | T3 FULTON-IGNACIO #1 10/54 RPR JUMPR | 44644392 | FULTON-IGNACIO #1 | 010/054 | ICS | B | 2021_(0) A and B Tags |  | 2021-02-12 | 2021-05-12 | [7 empty] | TR3 | <90D | North Coast | [7 empty] | '-122.597244 | 38.4737 | ETL.4680 | 40765346 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
2021 Work Plan | 120533130 | Not Scheduled | DI VACA-VCVL-JMSN-N. TWR A5/44 REPL INSS | 31530203 | VACA-VACAVILLE-JAMESON-NTH TWR | A005/044 | 92S | A | 2021_(0) A and B Tags |  | 2021-02-12 | 2021-03-14 | [8 empty] | <30D | North Coast | WSIP | [6 empty] | '-121.981297 | 38.3591 | ETL.4100 | 40842144 | Emergency-Steel | Other | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 527 | Lakeville |  |  |  | Yes | No | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | 92 | Not Scheduled | Capital A Tag |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(0) A and B Tags | Pending Repair | 2021 Plan
Approved Outside Workplan | 114720736 | Not Scheduled | TAFT-MARICOPA ROAD CONSTRUCTION | 31397747 | TAFT-MARICOPA |  | 71Y | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2018-06-21 | 2020-06-22 |  |  |  | 2021-09-01 |  |  |  |  | LATE | South | Non-WSIP | [8 empty] | ETL.9230 |  | Road | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Midway |  | New |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 115442137 | Q2 | T2 CARIBOU-PALERMO :027/224 RPR RD | 31417592 | CARIBOU-PALERMO | :027/224 | 92F | E | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2018-12-03 | 2019-12-03 |  |  | 2021-05-15 | 2021-05-15 |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP | [6 empty] | '-121.436938 | 39.8102 | ETL.3190 | 40771766 | Road | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Table Mountain |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 92 | Q2 |  |  | 2020-11-23 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 115465340 | Not Scheduled | TEMBLOR-SLO+ 115KV GATES/ROADS/CULVERTS | 31417694 | TEMBLOR-SAN LUIS OBISPO |  | 71Y | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2018-12-06 | 2020-12-06 |  |  |  | 2020-12-06 |  |  |  |  | LATE | South | Non-WSIP | [8 empty] | ETL.3960 |  | Road | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 115660020 | Not Scheduled | T2 EI SAN LUIS OBISPO-OCE 19/117 RMV ENC |  | SAN LUIS OBISPO-OCEANO | 019/117 | CHR | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-01-09 | 2020-01-09 | [7 empty] | TR2 | LATE | South | WSIP | [6 empty] | '-120.577498 | 35.0996 | ETL.3530 | 40809741 | Right of Way | Encroachment | Remove |  |  |  |  | PEND | LC | TLS | Land | Expense | 931 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 115765154 | Not Scheduled | T2 CHC SAN BENITO-115 kV VEG RD CLRING_0 | 44305488 | SAN BENITO TAP | 033/212A | CHS | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-01-29 | 2020-01-29 |  |  |  | 2022-05-01 |  |  | Check FDA | TR2 | LATE | South | Non-WSIP | [5 empty] | Incorrect required end date | '-121.580723 | 36.8304 | ETL.2152 | 44181131 | Vegetation | Overgrown | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 115773393 | Feb | KEARNEY-KERMAN 001/003 RPL POLE | 31425590 | KEARNEY-KERMAN | 001/003 | 70Y | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Clearance restriction (circuit efficiency) | 2019-01-31 | 2021-05-31 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-16 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.882967 | 36.692 | ETL.8840 | 40645719 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  |  |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Feb | 70 | Feb |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 116502844 | Not Scheduled | SALINAS/FIRESTONE #2 3rd party sign_000/ | 43895648 | SALINAS-FIRESTONE #2 (NO FLY) | 000/022 | ICW | E | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-02-20 | 2020-02-20 | [6 empty] | Check FDA |  | LATE | South | Non-WSIP | [6 empty] | '-121.643569 | 36.6772 | ETL.7910 | 40588199 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLS | Land | Expense | 630 | Moss Landing |  | Y - 8 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2019-06-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 116722679 | Q2 | GATES-MIDWAY 027/109 RPL CORONA | 74008740 | GATES-MIDWAY | 027/109 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-03-13 | 2020-03-13 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.819803 | 35.8473 | ETL.5990 | 40817433 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-11 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 116722857 | Q2 | GATES-MIDWAY 019/081 RPL CORONA | 74008740 | GATES-MIDWAY | 019/081 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-03-13 | 2020-03-13 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.900885 | 35.9329 | ETL.5990 | 40872640 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-07-19 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 116879972 | Q4 | T2 SALINAS LAURELES A15/319 RMV VEGN |  | SALINAS-LAURELES | A015/319 | HNA | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-03-21 | 2022-03-21 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | LATE | South | Non-WSIP | [5 empty] | s4r5 - Per Cal Trans District 5, unless the trees are dead, the removal of the trees as a scenic resource will require Coastal Development Permit or some other kind of locally driven approval that complies with CEQA. | '-121.813573 | 36.5725 | ETL.7930 | 40652708 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q4 | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 116884618 | Q2 | T2 CARIBOU-PALERMO :025/210 RPR RD | 31431968 | CARIBOU-PALERMO | :025/210 | 71Y | E | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-03-10 | 2020-03-10 |  |  | 2021-05-15 | 2021-05-15 |  |  | Check FDA | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.42085 | 39.8336 | ETL.3190 | 40599291 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Table Mountain |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 71 | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117060223 | Not Scheduled | MORRO BAY CULVERTS AND BRIDGES | 31436081 | MORRO BAY-DIABLO |  | 71Y | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-04-17 | 2021-04-17 |  |  |  | 2021-07-15 |  |  |  |  | SCHD | South | Non-WSIP | [8 empty] | ETL.5260 |  | Road | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117219056 | Not Scheduled | MONTA VISTA-LOS ALTOS - 60 kV_000/010 | 31471858 | MONTA VISTA-LOS ALTOS | 000/010 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Clearance restriction (circuit efficiency) | 2019-05-12 | 2020-05-12 | [8 empty] | LATE | Central | Non-WSIP |  |  |  | REJECT: Work on this tag was not completed per [REDACTED]. This notification will need to be included in future work plan. |  |  | '-122.071231 | 37.3285 | ETL.7600 | 40616675 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  | Reject | 2019-08-21 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117220394 | Not Scheduled | T2 MOSS LANDING-COBURN 15/073 RMV VEG | 44305489 | MOSS LANDING-COBURN | 015/073 | CHS | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-05-13 | 2021-05-13 |  |  |  | 2022-05-01 |  |  |  | TR2 | SCHD | South | Non-WSIP | [6 empty] | '-121.514124 | 36.7439 | ETL.5330 | 40659872 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117227969 | Mar | LAS PERILLAS TAP 000/001 RPL POLE | 31454078 | LAS PERILLAS TAP | 000/001 | 70Y | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-05-09 | 2021-05-09 |  |  | 2021-03-26 | 2021-03-17 | [5 empty] | South | Non-WSIP | [6 empty] | '-119.913721 | 35.8429 | ETL.8463 | 40642523 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-12-09 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117376251 | Not Scheduled | DIABLO-GATES #1 63/258 ROAD ACCESS RPR | 31509486 | DIABLO-GATES #1 | 063/258 | 71Y | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-05-14 | 2021-05-14 |  |  |  | 2021-12-01 |  |  |  |  | SCHD | South | Non-WSIP | [6 empty] | '-120.242999 | 35.9356 | ETL.5960 | 40858519 | Road | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Fresno |  | New |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117459312 | Not Scheduled | SAN LUIS OBISPO-CAYUCOS 17/159 RMV VEGN |  | SAN LUIS OBISPO-CAYUCOS | 017/159 | CHS | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-06-18 | 2021-06-18 |  |  |  | 2021-06-15 | [5 empty] | South | Non-WSIP | [6 empty] | '-120.822345 | 35.3842 | ETL.9090 | 40809912 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117462042 | Not Scheduled | GOLDTREE TAP 000/015 RMV VEG | 44298386 | GOLDTREE TAP | 000/015 | CHS | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-06-18 | 2021-06-18 |  |  |  | 2021-06-01 | [5 empty] | South | Non-WSIP | [6 empty] | '-120.703055 | 35.3023 | ETL.2821 | 40760117 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117484431 | Q4 | T2 DI SALINAS-LAURELES A12/260 RMV VEGN |  | SALINAS-LAURELES | A012/260 | HNA | E | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-06-18 | 2021-05-31 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.76513 | 36.5705 | ETL.7930 | 40825898 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117485827 | Mar | GUARDIAN #1 TAP 000/003 RPLC POLE | 31486588 | GUARDIAN #1 TAP | 000/003 | 70Y | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-06-24 | 2021-06-24 |  |  | 2021-03-19 | 2021-03-09 | [5 empty] | South | Non-WSIP | [6 empty] | '-119.592869 | 36.5407 | ETL.2301 | 40645024 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117485838 | Mar | GUARDIAN #1 TAP 000/003A RPLC POLE | 31486588 | GUARDIAN #1 TAP | 000/003A | 70Y | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-06-24 | 2021-06-24 |  |  | 2021-03-19 | 2021-03-09 | [5 empty] | South | Non-WSIP | [6 empty] | '-119.592857 | 36.5406 | ETL.2301 | 44191175 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 70 | Mar |  |  | 2019-07-19 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117611224 | Not Scheduled | WATSONVILLE-SALINAS 3/56 CLR ROAD |  | WATSONVILLE-SALINAS | 003/056 | CHS | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-06-26 | 2021-06-26 |  |  |  | 2022-05-01 |  |  |  |  | SCHD | South | Non-WSIP | [8 empty] | ETL.8310 | 44311405 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117612131 | Not Scheduled | WATSONVILLE-SALINAS 04/58A RMV VEG ROAD |  | WATSONVILLE-SALINAS | 004/058A | CHS | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-06-26 | 2024-06-26 |  |  |  | 2022-05-01 |  |  |  |  | SCHD | South | Non-WSIP | [6 empty] | '-121.720911 | 36.8786 | ETL.8310 | 42564362 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Moss Landing |  |  |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117620737 | Q2 | GATES-MIDWAY 042/167 REPL INSS | 31460447 | GATES-MIDWAY | 042/167 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-07-19 | 2021-05-31 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.671022 | 35.6694 | ETL.5990 | 40760545 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-11 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117620753 | Q2 | GATES-MIDWAY 046/182 RPL INSS | 31460447 | GATES-MIDWAY | 046/182 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-07-19 | 2021-05-31 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.6331 | 35.6229 | ETL.5990 | 40637045 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117620754 | Q2 | GATES-MIDWAY 027/110 REPL INSS | 74008740 | GATES-MIDWAY | 027/110 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-07-19 | 2020-07-19 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.816823 | 35.8441 | ETL.5990 | 40894429 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-11 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117620768 | Q2 | GATES-MIDWAY 026/108 RPL INSS | 74008740 | GATES-MIDWAY | 026/108 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-07-19 | 2020-07-19 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.822785 | 35.8504 | ETL.5990 | 40852348 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-11 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117620782 | Q2 | GATES-MIDWAY 036/143 RPL INSS | 31460447 | GATES-MIDWAY | 036/143 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-07-19 | 2021-05-31 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.73092 | 35.74 | ETL.5990 | 40619144 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-08-06 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117620790 | Q2 | GATES-MIDWAY 026/106 REPL INSS | 74008740 | GATES-MIDWAY | 026/106 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-07-19 | 2020-07-19 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.828605 | 35.8566 | ETL.5990 | 40760828 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117744983 | Not Scheduled | LAKEVILLE-IGNACIO #2 033/158 RPL GATE | 31522790 | LAKEVILLE-IGNACIO #2 | 033/158 | 71Y | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-08-08 | 2021-08-08 |  |  |  | 2021-05-01 | [5 empty] | North Coast | Non-WSIP | [6 empty] | '-122.502086 | 38.1787 | ETL.3745 | 40873635 | Fence / Gate | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 374 | Lakeville |  |  |  | No | Yes | M&C Tag | No | North Coast |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117750865 | Not Scheduled | GATES-MIDWAY 43/172 RMV VEG |  | GATES-MIDWAY | 043/172 | HNA | E | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-08-13 | 2020-08-13 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.658361 | 35.6539 | ETL.5990 | 40602681 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  | Streambed | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Already Past Due | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117751125 | Not Scheduled | LOS BANOS-PACHECO 002/001 RPR ROAD | 44400526 | LOS BANOS-PACHECO | 002/001 | CHS | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-08-13 | 2021-08-13 |  |  |  | 2021-12-01 |  |  |  |  | SCHD | South | Non-WSIP | [8 empty] | ETL.8960 | 44236927 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117763290 | Not Scheduled | CYCS-CMBRA (VLA CRK CRSNG) 8/49 RPL ROAD | 31462418 | CAYUCOS-CAMBRIA | 008/049 | 71Y | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-08-14 | 2021-08-14 | 2019-09-09 | 2019-09-12 |  | 2021-07-07 | [5 empty] | South | Non-WSIP | [6 empty] | '-120.967638 | 35.5131 | ETL.8560 | 40594510 | Road | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117781782 | Not Scheduled | MIDWAY-WHEELER RIDGE #1 7/038 RPR ROAD | 44400527 | MIDWAY-WHEELER RIDGE #1 | 007/038 | CHS | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-08-20 | 2021-08-20 |  |  |  | 2022-06-01 |  |  |  |  | SCHD | South | Non-WSIP | [6 empty] | '-119.34074 | 35.3469 | ETL.5190 | 40860243 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117788016 | Q2 | GATES-MIDWAY 4/18 RPL INSS | 74008740 | GATES-MIDWAY | 004/018 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-08-22 | 2020-08-22 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.084583 | 36.0947 | ETL.5990 | 40820605 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-11 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117813938 | Not Scheduled | CARNERAS-TAFT 9/150 RMV VEGN |  | CARNERAS-TAFT | 009/150 | HNA | E | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-08-27 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.590081 | 35.2424 | ETL.8540 | 40860207 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | HNA | Not Scheduled |  |  | 2019-09-24 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117818193 | Q2 | GATES-MIDWAY 046/183 RPL INSS | 31460447 | GATES-MIDWAY | 046/183 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-08-28 | 2021-05-31 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.630496 | 35.6197 | ETL.5990 | 40595177 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117818499 | Q2 | GATES-MIDWAY 046/184 RPL INSS | 31460447 | GATES-MIDWAY | 046/184 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-08-28 | 2021-05-31 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.628078 | 35.6168 | ETL.5990 | 40679709 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2020-08-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117845909 | Feb | SAN MATEO-BAIR 1/12 RPL INSS | 31507435 | SAN MATEO-BAIR | 001/012 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Clearance restriction (circuit efficiency) | 2019-09-05 | 2021-05-31 |  |  | 2021-02-11 | 2021-02-11 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.295067 | 37.5712 | ETL.7940 | 40711560 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 4 |  | No | Yes | M&C Tag | Yes | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Found Before 2020 | Found Before 2020 | Feb | 93 | Feb |  |  | 2020-04-02 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117846600 | Not Scheduled | T2 CBRLL-SNT YNEZ SW STA 12/106 RPR ROAD | 44399719 | CABRILLO-SANTA YNEZ SW STA | 012/106 | CHS | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-09-05 | 2021-09-05 |  |  |  | 2021-01-31 |  |  |  | TR2 |  | South | Non-WSIP | [6 empty] | '-120.39431 | 34.6486 | ETL.1200 | 40809301 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117846767 | Not Scheduled | T2 CBRLL-SNT YNZ SW STA 13/109 RPR GATE | 44399719 | CABRILLO-SANTA YNEZ SW STA | 013/109 | CHS | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-09-05 | 2021-09-05 |  |  |  | 2021-01-31 |  |  |  | TR2 |  | South | Non-WSIP | [6 empty] | '-120.403204 | 34.6479 | ETL.1200 | 40594548 | Fence / Gate | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117869333 | Not Scheduled | GATES-MIDWAY 047/190 RMV VEG |  | GATES-MIDWAY | 047/190 | HNA | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-09-10 | 2022-09-10 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.614345 | 35.5999 | ETL.5990 | 40870028 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | HNA | Not Scheduled |  |  | 2019-10-03 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117869651 | Q2 | GATES-MIDWAY 038/151 RPL INSS | 31472316 | GATES-MIDWAY | 038/151 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-11 | 2021-05-31 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.712638 | 35.7155 | ETL.5990 | 40869029 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117869656 | Q2 | GATES-MIDWAY 037/150 RPL INSS | 31472316 | GATES-MIDWAY | 037/150 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-11 | 2022-09-11 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.714969 | 35.718 | ETL.5990 | 40894433 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-10-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117869713 | Q2 | GATES-MIDWAY 044/178 RPLC INSS | 31472316 | GATES-MIDWAY | 044/178 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-11 | 2021-05-31 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.643123 | 35.6352 | ETL.5990 | 40818612 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-10-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117869750 | Q2 | GATES-MIDWAY 006/026 RPL INSS | 31473303 | GATES-MIDWAY | 006/026 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-11 | 2020-09-11 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.063856 | 36.0704 | ETL.5990 | 40791061 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117869758 | Q2 | GATES-MIDWAY 014/057 RPL INSS | 31473303 | GATES-MIDWAY | 014/057 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-11 | 2020-09-11 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.960749 | 35.9993 | ETL.5990 | 40792992 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2020-08-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117870473 | Q2 | GATES-MIDWAY 013/055 RPL INSS | 31473303 | GATES-MIDWAY | 013/055 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-11 | 2020-09-11 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.96806 | 36.0031 | ETL.5990 | 40679430 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-10-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117872006 | Q2 | GATES-MIDWAY 043/171 RPLC INSS | 31472316 | GATES-MIDWAY | 043/171 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-11 | 2021-05-31 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.660926 | 35.6571 | ETL.5990 | 40892219 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-10-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117873520 | Q2 | GATES-MIDWAY 045/181 RPLC INSS | 31528343 | GATES-MIDWAY | 045/181 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-11 | 2021-05-31 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.636189 | 35.6257 | ETL.5990 | 40892221 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117874931 | Q2 | GATES-MIDWAY 41/164 RPL INSS | 31472316 | GATES-MIDWAY | 041/164 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-11 | 2021-09-11 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.678551 | 35.6787 | ETL.5990 | 40713762 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - Prog Multi |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117874980 | Q2 | GATES-MIDWAY 047/190 RPL INSS | 31472316 | GATES-MIDWAY | 047/190 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-12 | 2021-09-12 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.614345 | 35.5999 | ETL.5990 | 40894799 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - Prog Multi |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117875298 | Q2 | GATES-MIDWAY 041/166 RPL INSS | 31472316 | GATES-MIDWAY | 041/166 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-12 | 2021-09-12 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.673512 | 35.6725 | ETL.5990 | 40791081 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - Prog Multi |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117875413 | Q2 | GATES-MIDWAY 005/023 RPL INSS | 74008740 | GATES-MIDWAY | 005/023 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-12 | 2021-09-12 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-120.071539 | 36.0794 | ETL.5990 | 40597365 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117875414 | Q2 | GATES-MIDWAY 029/119 RPL INSS | 31473303 | GATES-MIDWAY | 029/119 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-12 | 2020-09-12 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.79063 | 35.8153 | ETL.5990 | 40836869 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-10-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117875428 | Q2 | GATES-MIDWAY 5/24 RPL INSS | 31473303 | GATES-MIDWAY | 005/024 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-12 | 2020-09-12 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.068783 | 36.0761 | ETL.5990 | 40723370 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117875557 | Q2 | GATES-MIDWAY 014/058 RPL INSS | 31473303 | GATES-MIDWAY | 014/058 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-12 | 2021-09-12 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.958613 | 35.9974 | ETL.5990 | 40846719 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-05 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117875559 | Q2 | GATES-MIDWAY 043/174 RPL INSS | 31472316 | GATES-MIDWAY | 043/174 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-12 | 2021-09-12 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.6538 | 35.6483 | ETL.5990 | 40726369 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117879142 | Q2 | GATES-MIDWAY 029/118 RPLC INSS | 31473303 | GATES-MIDWAY | 029/118 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-12 | 2020-09-12 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.793444 | 35.8185 | ETL.5990 | 40812217 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-10-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117879206 | Q2 | GATES-MIDWAY 041/165 REPL INSS | 31528343 | GATES-MIDWAY | 041/165 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-12 | 2021-05-31 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.67601 | 35.6756 | ETL.5990 | 40658694 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117879843 | Q2 | GATES-MIDWAY 043/172 REPL INSS | 31528343 | GATES-MIDWAY | 043/172 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-12 | 2020-09-12 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.658361 | 35.6539 | ETL.5990 | 40602681 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-10-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117880112 | Q2 | GATES-MIDWAY 015/064 REPL INSS | 74008740 | GATES-MIDWAY | 015/064 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-13 | 2020-09-13 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.942295 | 35.9793 | ETL.5990 | 40679659 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117880207 | Q2 | GATES-MIDWAY 037/148 REPL INSS | 31528343 | GATES-MIDWAY | 037/148 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-13 | 2021-05-31 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.719762 | 35.7239 | ETL.5990 | 40820609 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-10-03 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117880547 | Q2 | GATES-MIDWAY 17/69 RPL INSS | 31473303 | GATES-MIDWAY | 017/069 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-12 | 2021-09-12 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.929121 | 35.9644 | ETL.5990 | 40843809 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117880613 | Q2 | GATES-MIDWAY 020/083 RPL INSS | 31473303 | GATES-MIDWAY | 020/083 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-13 | 2020-09-13 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.894934 | 35.9266 | ETL.5990 | 40619139 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117880833 | Q2 | GATES-MIDWAY 036/145 REPL INSS | 31528343 | GATES-MIDWAY | 036/145 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-13 | 2021-05-31 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.726201 | 35.7332 | ETL.5990 | 40658417 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117885177 | Q2 | GATES-MIDWAY 021/089 RPL INSS | 74008740 | GATES-MIDWAY | 021/089 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-13 | 2020-09-13 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.87805 | 35.9088 | ETL.5990 | 40843431 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117885440 | Q2 | GATES-MIDWAY 33/134 RPL INSS | 31472316 | GATES-MIDWAY | 033/134 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-16 | 2021-09-16 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.752024 | 35.7684 | ETL.5990 | 40715399 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117885762 | Not Scheduled | GATES-MIDWAY 25/101 TRIM VEGN |  | GATES-MIDWAY | 025/101 | HNA | E | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-09-16 | 2021-05-31 | [8 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.843175 | 35.872 | ETL.5990 | 40870785 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | HNA | Not Scheduled |  |  | 2019-10-03 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117888800 | Q2 | GATES-MIDWAY 27/111 RPL INSS | 31473303 | GATES-MIDWAY | 027/111 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-16 | 2020-09-16 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.813788 | 35.8409 | ETL.5990 | 40894701 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-10-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117890422 | Q2 | GATES-MIDWAY 021/087B RPL INSS | 31473303 | GATES-MIDWAY | 021/087B | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-17 | 2021-09-17 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.882656 | 35.9135 | ETL.5990 | 40741311 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117890493 | Q2 | GATES-MIDWAY 027/109 RPL INSS | 74008740 | GATES-MIDWAY | 027/109 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-17 | 2020-09-17 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.819803 | 35.8473 | ETL.5990 | 40843433 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-10-03 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117892828 | Q2 | GATES-MIDWAY 033/132 REPL INSS | 31472316 | GATES-MIDWAY | 033/132 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-18 | 2021-05-31 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.756996 | 35.7747 | ETL.5990 | 40603170 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-10-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117892990 | Q2 | GATES-MIDWAY 025/104 RPL INSS | 74008740 | GATES-MIDWAY | 025/104 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-18 | 2020-09-18 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.834425 | 35.8627 | ETL.5990 | 40723382 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117893410 | Not Scheduled | LWRNC-MNT VST-SW 0/8 RPL SWIW | 31472801 | LAWRENCE-MONTA VISTA | 000/008 | 93H | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Clearance restriction (circuit efficiency) | 2019-09-12 | 2020-09-12 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-122.013417 | 37.385 | ETL.2090 | 40743303 | Switch-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 427 | Bay |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2019-09-25 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117893527 | Q2 | GATES-MIDWAY 025/103 RPL INSS | 31473303 | GATES-MIDWAY | 025/103 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-18 | 2020-09-18 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.837309 | 35.8658 | ETL.5990 | 40619141 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117893528 | Not Scheduled | GATES-MIDWAY 025/103 REMOVE VEGN |  | GATES-MIDWAY | 025/103 | HNA | E | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-09-18 | 2020-09-18 | [8 empty] | LATE | South | Non-WSIP | [6 empty] | '-119.837309 | 35.8658 | ETL.5990 | 40593368 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2019-10-03 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117894594 | Q2 | GATES-MIDWAY 022/091 RPLC INSS | 74008740 | GATES-MIDWAY | 022/091 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-18 | 2020-09-18 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.87228 | 35.9027 | ETL.5990 | 40892215 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117897086 | Q2 | GATES-MIDWAY 024/100 REPL INSS | 74008740 | GATES-MIDWAY | 024/100 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-18 | 2020-09-18 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.846115 | 35.8751 | ETL.5990 | 40869734 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117897089 | Not Scheduled | GATES-MIDWAY 024/100 RMV VEGN |  | GATES-MIDWAY | 024/100 | HNA | E | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-09-18 | 2020-09-18 | [8 empty] | LATE | South | Non-WSIP | [6 empty] | '-119.846115 | 35.8751 | ETL.5990 | 40869734 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2019-10-03 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117897627 | Q2 | GATES-MIDWAY 022/092 RPL INSS | 31473303 | GATES-MIDWAY | 022/092 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-19 | 2020-09-19 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.869344 | 35.8996 | ETL.5990 | 40637041 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117897941 | Q2 | GATES-MIDWAY 011/045 RPL INSS | 31473303 | GATES-MIDWAY | 011/045 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-19 | 2021-09-19 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-120.000744 | 36.0258 | ETL.5990 | 40688335 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117898885 | Q2 | GATES-MIDWAY 022/090 RPL INSS | 31473303 | GATES-MIDWAY | 022/090 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-19 | 2020-09-19 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.875164 | 35.9058 | ETL.5990 | 40894431 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117899210 | Q2 | GATES-MIDWAY 029/116 RPLC INSS | 31473303 | GATES-MIDWAY | 029/116 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-19 | 2020-09-19 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.799145 | 35.825 | ETL.5990 | 40791407 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-10-03 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117901513 | Q2 | GATES-MIDWAY 023/096 RPL INSS | 31473303 | GATES-MIDWAY | 023/096 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-20 | 2020-09-20 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.857784 | 35.8874 | ETL.5990 | 40791075 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-09-25 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117906589 | Q2 | GATES-MIDWAY 017/073 RPL INSS | 31473303 | GATES-MIDWAY | 017/073 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-12 | 2020-09-12 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.918897 | 35.9542 | ETL.5990 | 40621478 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Already Past Due | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117906660 | Q2 | GATES-MIDWAY 13/56 RPL INSS | 31473123 | GATES-MIDWAY | 013/056 | 93I | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-20 | 2021-09-20 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.963918 | 36.0015 | ETL.5990 | 40791398 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 | DWR | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Complete | Ready for Construction |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117912822 | Q2 | GATES-MIDWAY TOWER 5/21 RPL INSS | 74008740 | GATES-MIDWAY | 005/021 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-24 | 2021-09-24 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-120.076988 | 36.0858 | ETL.5990 | 40892502 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117912825 | Q2 | GATES-MIDWAY TOWER 3/15 RPL INSS | 74008740 | GATES-MIDWAY | 003/015 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-24 | 2021-09-24 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-120.092778 | 36.1043 | ETL.5990 | 40688333 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117913526 | Q2 | GATES-MIDWAY TOWER 5/22 RPL INSS | 74008740 | GATES-MIDWAY | 005/022 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-24 | 2021-09-24 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-120.074227 | 36.0825 | ETL.5990 | 40635621 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117914036 | Q2 | GATES-MIDWAY 7/31 RPL INSS | 74008740 | GATES-MIDWAY | 007/031 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-24 | 2021-09-24 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-120.051383 | 36.0585 | ETL.5990 | 40892211 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117914038 | Q2 | GATES-MIDWAY 7/33 RPL INSS | 74008740 | GATES-MIDWAY | 007/033 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-24 | 2021-09-24 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-120.045879 | 36.0543 | ETL.5990 | 40619136 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117917415 | Q2 | GATES-MIDWAY 007/032 RPL INSS | 31526375 | GATES-MIDWAY | 007/032 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-24 | 2021-09-24 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-120.048683 | 36.0564 | ETL.5990 | 40635823 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117917418 | Q2 | GATES-MIDWAY 009/040 RPL INSS | 31526375 | GATES-MIDWAY | 009/040 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-24 | 2021-09-24 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-120.019651 | 36.0376 | ETL.5990 | 40894423 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117917530 | Q2 | GATES-MIDWAY 010/042 RPL INSS | 31526375 | GATES-MIDWAY | 010/042 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-24 | 2021-09-24 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-120.011971 | 36.0328 | ETL.5990 | 40637040 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117917531 | Q2 | GATES-MIDWAY 011/046 RPL INSS | 31526375 | GATES-MIDWAY | 011/046 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-24 | 2021-09-24 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.997029 | 36.0235 | ETL.5990 | 40791071 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117917945 | Q4 | T2 DI SALINAS-LAURELES A014/302 CANCEL |  | SALINAS-LAURELES | A014/302 | HNA | E | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-09-25 | 2020-09-25 |  |  | 2021-12-31 | 2021-12-01 |  |  | CANCEL/CNCL | TR2 | LATE | South | WSIP | [6 empty] | '-121.799503 | 36.5697 | ETL.7930 | 40876195 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117918630 | Q2 | GATES-MIDWAY 4/19 RPL INSS | 31526375 | GATES-MIDWAY | 004/019 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-24 | 2021-09-24 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-120.081843 | 36.0915 | ETL.5990 | 40817425 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117918876 | Q2 | GATES-MIDWAY 014/059 RPL INSS | 31526375 | GATES-MIDWAY | 014/059 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.956173 | 35.995 | ETL.5990 | 40843429 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117918878 | Q2 | GATES-MIDWAY 015/062 RPL INSS | 31526377 | GATES-MIDWAY | 015/062 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.94784 | 35.9857 | ETL.5990 | 40635622 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117918963 | Q2 | GATES MIDWAY 12/52 RPL INSS | 31526375 | GATES-MIDWAY | 012/052 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.977255 | 36.01 | ETL.5990 | 40635626 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117918966 | Q2 | GATES MIDWAY 12/51 RPL INSS | 31526375 | GATES-MIDWAY | 012/051 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.980431 | 36.0124 | ETL.5990 | 40894694 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117919095 | Q2 | GATES-MIDWAY 016/066 RPL INSS | 31526377 | GATES-MIDWAY | 016/066 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.936881 | 35.9731 | ETL.5990 | 40791065 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117919122 | Q2 | GATES-MIDWAY 013/054 RPL INSS | 31526375 | GATES-MIDWAY | 013/054 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.971424 | 36.0057 | ETL.5990 | 40723374 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117922663 | Q2 | GATES-MIDWAY 021/087A RPL INSS | 31526377 | GATES-MIDWAY | 021/087A | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.882407 | 35.9136 | ETL.5990 | 40578714 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117927027 | Q2 | GATES-MIDWAY TOWER 19/80 RPL INSS | 31526377 | GATES-MIDWAY | 019/080 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.903305 | 35.9355 | ETL.5990 | 40897198 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117927222 | Q2 | GATES-MIDWAY 013/053 RPL INSS | 31526375 | GATES-MIDWAY | 013/053 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.973967 | 36.0076 | ETL.5990 | 40619138 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117927264 | Q2 | GATES-MIDWAY 16/67 RPL INSS | 31526377 | GATES-MIDWAY | 016/067 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.934209 | 35.97 | ETL.5990 | 40790060 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117927353 | Q2 | GATES-MIDWAY 16/65 RPL INSS | 31526377 | GATES-MIDWAY | 016/065 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.939655 | 35.9763 | ETL.5990 | 40688337 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117928357 | Q2 | GATES-MIDWAY 038/152 RPL INSS | 31528346 | GATES-MIDWAY | 038/152 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.71032 | 35.713 | ETL.5990 | 40638375 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117928386 | Q2 | GATES-MIDWAY 036/146 RPLC INSS | 31528346 | GATES-MIDWAY | 036/146 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.724271 | 35.7304 | ETL.5990 | 40791079 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117928401 | Q2 | GATES-MIDWAY 038/154 RPL INSS | 31528346 | GATES-MIDWAY | 038/154 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.705411 | 35.7079 | ETL.5990 | 40723763 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117928483 | Q2 | GATES-MIDWAY 033/131 RPL INSS | 31528342 | GATES-MIDWAY | 033/131 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.759789 | 35.7782 | ETL.5990 | 40894145 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117928484 | Q2 | GATES-MIDWAY 033/133 RPL INSS | 31528342 | GATES-MIDWAY | 033/133 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.754651 | 35.7718 | ETL.5990 | 40619153 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117928485 | Q2 | GATES-MIDWAY 034/135 RPL INSS | 31528342 | GATES-MIDWAY | 034/135 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.748938 | 35.7649 | ETL.5990 | 40680901 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117928486 | Q2 | GATES-MIDWAY 037/147 RPL INSS | 31528346 | GATES-MIDWAY | 037/147 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.721977 | 35.7271 | ETL.5990 | 40793035 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117928487 | Q2 | GATES-MIDWAY 038/153 RPL INSS | 31528346 | GATES-MIDWAY | 038/153 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.708015 | 35.7105 | ETL.5990 | 40619154 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117928488 | Q2 | GATES-MIDWAY 042/170 RPL INSS | 31528347 | GATES-MIDWAY | 042/170 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.663388 | 35.6601 | ETL.5990 | 40894437 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117928489 | Q2 | GATES-MIDWAY 039/156 RPL INSS | 31528346 | GATES-MIDWAY | 039/156 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.699663 | 35.7016 | ETL.5990 | 40793939 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117928605 | Q2 | GATES-MIDWAY 043/173 RPL INSS | 31528347 | GATES-MIDWAY | 043/173 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.655913 | 35.6509 | ETL.5990 | 40621509 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117928607 | Q2 | GATES-MIDWAY 048/192 RPL INSS | 31528348 | GATES-MIDWAY | 048/192 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.609166 | 35.5935 | ETL.5990 | 40635631 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117928609 | Q2 | GATES-MIDWAY 048/191 RPL INSS | 31528348 | GATES-MIDWAY | 048/191 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.611781 | 35.5967 | ETL.5990 | 40892231 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117928751 | Q2 | GATES-MIDWAY 026/107 RPL INSS |  | GATES-MIDWAY | 026/107 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2020-09-27 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-119.825703 | 35.8535 | ETL.5990 | 40790064 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117931253 | Q2 | GATES-MIDWAY 042/167 RPL INSS | 31528347 | GATES-MIDWAY | 042/167 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-25 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.671322 | 35.669 | ETL.5990 | 40790081 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117931256 | Q2 | GATES-MIDWAY 046/185 RPL INSS | 31528347 | GATES-MIDWAY | 046/185 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.625991 | 35.6134 | ETL.5990 | 40694342 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117931258 | Q2 | GATES-MIDWAY 042/169A RPL INSS | 31528347 | GATES-MIDWAY | 042/169A | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.664017 | 35.6611 | ETL.5990 | 40578715 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117931271 | Q2 | GATES MIDWAY 34/136 RPL INSS | 31528342 | GATES-MIDWAY | 034/136 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.746241 | 35.7616 | ETL.5990 | 40783659 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117931274 | Q2 | GATES MIDWAY 18/74 RPL INSS | 31526377 | GATES-MIDWAY | 018/074 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.917234 | 35.952 | ETL.5990 | 40723378 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117931275 | Q2 | GATES MIDWAY 41/163 RPL INSS | 31528346 | GATES-MIDWAY | 041/163 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.681266 | 35.6812 | ETL.5990 | 40619145 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117931276 | Q2 | GATES MIDWAY 17/72 RPL INSS | 31526377 | GATES-MIDWAY | 017/072 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  |  | South | Non-WSIP | [6 empty] | '-119.920979 | 35.9566 | ETL.5990 | 40635623 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117931306 | Q2 | GATES-MIDWAY 039/158 RPL INSS | 31528346 | GATES-MIDWAY | 039/158 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.693911 | 35.6958 | ETL.5990 | 40846725 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117931406 | Q2 | GATES-MIDWAY 040/160 RPL INSS | 31528346 | GATES-MIDWAY | 040/160 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.688536 | 35.6902 | ETL.5990 | 40894435 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117931408 | Q2 | GATES-MIDWAY 040/159 RPL INSS | 31528346 | GATES-MIDWAY | 040/159 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.691021 | 35.6928 | ETL.5990 | 40843451 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117931512 | Q2 | GATES-MIDWAY 023/095 RPL INSS |  | GATES-MIDWAY | 023/095 | 93K | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2020-09-27 | 2021-04-19 | 2021-05-28 | 2021-05-28 | 2021-04-19 |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-119.860526 | 35.8903 | ETL.5990 | 40688343 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117935143 | Q2 | DI GATES-MIDWAY 044/178 RPL INSS | 31528347 | GATES-MIDWAY | 044/178 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-30 | 2021-09-30 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.643502 | 35.6348 | ETL.5990 | 40846727 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117935149 | Q2 | GATES-MIDWAY 045/179 RPL INSS | 31528347 | GATES-MIDWAY | 045/179 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-30 | 2021-09-30 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.640879 | 35.6316 | ETL.5990 | 40843823 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117935211 | Q2 | GATES-MIDWAY 047/188 RPL INSS | 31528348 | GATES-MIDWAY | 047/188 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-30 | 2021-09-30 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.618868 | 35.6046 | ETL.5990 | 40846735 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117935212 | Q2 | GATES-MIDWAY 045/180 RPL INSS | 31528344 | GATES-MIDWAY | 045/180 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-30 | 2022-09-30 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.638759 | 35.6289 | ETL.5990 | 40894439 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117935215 | Q2 | GATES-MIDWAY 047/189 RPL INSS | 31528348 | GATES-MIDWAY | 047/189 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-30 | 2021-09-30 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.616949 | 35.6022 | ETL.5990 | 40843445 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117935357 | Q2 | GATES-MIDWAY 47/186 RPL INSS | 31528347 | GATES-MIDWAY | 047/186 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.623536 | 35.6104 | ETL.5990 | 40797050 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117935528 | Q2 | GATES-MIDWAY 034/138 RPL INSS | 31528342 | GATES-MIDWAY | 034/138 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-25 | 2021-09-25 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.741845 | 35.7558 | ETL.5990 | 40839637 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117935559 | Q2 | GATES-MIDWAY 036/144 RPL INSS | 31528342 | GATES-MIDWAY | 036/144 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.728559 | 35.7366 | ETL.5990 | 40723388 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117935567 | Q2 | GATES-MIDWAY 035/139 RPL INSS | 31528342 | GATES-MIDWAY | 035/139 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.739836 | 35.7529 | ETL.5990 | 40845627 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117935614 | Q2 | GATES-MIDWAY 035/141 RPLC INSS | 31528342 | GATES-MIDWAY | 035/141 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.735387 | 35.7465 | ETL.5990 | 40896953 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117935627 | Q2 | GATES-MIDWAY 035/142 RPL INSS | 31528342 | GATES-MIDWAY | 035/142 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.733071 | 35.7431 | ETL.5990 | 40635628 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117935735 | Q2 | GATES-MIDWAY 035/140 RPL INSS | 31528342 | GATES-MIDWAY | 035/140 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.737621 | 35.7497 | ETL.5990 | 40894797 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117935738 | Q2 | GATES-MIDWAY 044/175 RPL INSS | 31528347 | GATES-MIDWAY | 044/175 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.651319 | 35.6453 | ETL.5990 | 40688348 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117936070 | Q2 | GATES-MIDWAY 47/187 RPL INSS | 31528347 | GATES-MIDWAY | 047/187 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-09-27 | 2021-09-27 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.62095 | 35.608 | ETL.5990 | 40790068 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117942165 | Q2 | GATES-MIDWAY 55/221 RPL INSS | 31528349 | GATES-MIDWAY | 055/221 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-10-02 | 2021-10-02 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.538632 | 35.5065 | ETL.5990 | 40894731 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117942724 | Q2 | GATES-MIDWAY 056/226 RPL INSS | 74008740 | GATES-MIDWAY | 056/226 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-10-02 | 2021-10-02 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.527793 | 35.4933 | ETL.5990 | 40578716 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  |  | CalTrans | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-08-24 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117942726 | Q2 | GATES-MIDWAY 056/225 RPL INSS | 31528349 | GATES-MIDWAY | 056/225 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-10-02 | 2021-10-02 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.529886 | 35.4962 | ETL.5990 | 40688351 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117943122 | Q2 | GATES-MIDWAY 56/224 RPL INSS | 31528349 | GATES-MIDWAY | 056/224 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-10-02 | 2021-10-02 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.531916 | 35.499 | ETL.5990 | 40723392 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117946504 | Q2 | GATES-MIDWAY 056/227 RPL INSS | 31528349 | GATES-MIDWAY | 056/227 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-10-02 | 2021-10-02 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.526216 | 35.4911 | ETL.5990 | 40791088 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117955808 | Q2 | GATES-MIDWAY 062/250 RPL INSS | 31528349 | GATES-MIDWAY | 062/250 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-10-02 | 2021-10-02 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.469695 | 35.4214 | ETL.5990 | 40843449 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117955981 | Q2 | GATES-MIDWAY 55/222 RPL INSS | 31528349 | GATES-MIDWAY | 055/222 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-10-02 | 2021-10-02 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.536297 | 35.5041 | ETL.5990 | 40637042 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117956122 | Q2 | GATES-MIDWAY 063/253 RPL INSS | 31528349 | GATES-MIDWAY | 063/253 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-10-02 | 2021-10-02 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.463809 | 35.4143 | ETL.5990 | 40637044 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117956126 | Q2 | GATES-MIDWAY 063/255 RPL INSS | 31528349 | GATES-MIDWAY | 063/255 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-10-02 | 2021-10-02 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.459607 | 35.4092 | ETL.5990 | 40723396 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117956200 | Q2 | GATES-MIDWAY 063/254 RPL INSS | 31528349 | GATES-MIDWAY | 063/254 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-10-02 | 2021-10-02 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.461603 | 35.4116 | ETL.5990 | 40619151 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117956423 | Q2 | GATES-MIDWAY 064/257 RPL INSS | 31528350 | GATES-MIDWAY | 064/257 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-10-02 | 2021-10-02 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.456678 | 35.4057 | ETL.5990 | 40791091 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117956426 | Q2 | GATES-MIDWAY 063/256 RPL INSS | 31528350 | GATES-MIDWAY | 063/256 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-10-02 | 2021-10-02 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.457851 | 35.4071 | ETL.5990 | 40688354 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117956427 | Q2 | GATES-MIDWAY 051/205 RPL INSS | 31528345 | GATES-MIDWAY | 051/205 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-10-02 | 2022-10-02 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.577929 | 35.5544 | ETL.5990 | 40688356 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Q2 | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117956774 | Q2 | GATES-MIDWAY 063/252 RPL INSS | 31528349 | GATES-MIDWAY | 063/252 | 93K | F | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-10-02 | 2021-10-02 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | Non-WSIP | [6 empty] | '-119.465753 | 35.4166 | ETL.5990 | 40892227 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 10 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2019-10-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 117966294 | Not Scheduled | ARCO-CARNERAS 13/210 INST GATE | 31510049 | ARCO-CARNERAS | 013/210 | 71Y | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-10-07 | 2021-10-07 |  |  |  | 2021-06-01 | [5 empty] | South | Non-WSIP | [6 empty] | '-119.840939 | 35.5958 | ETL.8430 | 40823894 | Fence / Gate | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  | 2019-12-02 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117985731 | Not Scheduled | NEWARK-LOS ESTEROS - 230 KV_6 |  | ETU.9936 | 6 | 72Z | E | 2020_(9d) All other tags | Underground Transmission | 2019-10-10 | 2020-10-10 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.942525 | 37.4787 | ETU.9936 | 41168516 | Hardware-Underground | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TUG | Maintenance | Capital | 377 | Martin |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 72Z | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 117985736 | Not Scheduled | LOS ESTEROS-METCALF - 230 KV_6 |  | ETU.9937 | 6 | 72Z | E | 2020_(9d) All other tags | Underground Transmission | 2019-10-10 | 2020-10-10 | [8 empty] | LATE | Central | Non-WSIP | [6 empty] | '-121.942412 | 37.4786 | ETU.9937 | 41168528 | Hardware-Underground | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TUG | Maintenance | Capital | 377 | Martin |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 72Z | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118167702 | Q3 | HENRIETTA-LEMOORE 008/020 RPL POLE | 31489246 | HENRIETTA-LEMOORE | 008/020 | 70Y | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-11-13 | 2021-05-31 |  |  | 2021-09-24 | 2021-09-21 |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.801156 | 36.3055 | ETL.8770 | 40584593 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 2 |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Scheduled Past Due | 70 | Q3 |  |  | 2020-03-10 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 118178173 | Not Scheduled | BIOLA-GLASS-MDRA-SW ?006/004 RPL SWITCH | 31490618 | GLASS-BIOLA-MADERA | ?006/004 | 93H | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-11-15 | 2021-05-31 | 2021-03-09 | 2021-03-09 | [6 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.110308 | 36.8785 | ETL.9350 | 43242637 | Switch-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 427 | Fresno |  | Released |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 118196054 | Not Scheduled | BIOLA-GLASS-MADERA-SWITCH ?6/4 RPL POLE | 31490618 | GLASS-BIOLA-MADERA | ?006/004 | 93H | E | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2019-11-15 | 2021-05-31 | 2021-03-09 | 2021-03-09 | [6 empty] | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.110308 | 36.8785 | ETL.9350 | 43242637 | Switch-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 427 | Fresno |  | Released |  | No | Yes | M&C Tag | Yes | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not Scheduled | 93 | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 118201654 | Not Scheduled | T3NT DIABLO-GATES #1 21/088 RPR ROAD | 44298383 | DIABLO-GATES #1 | 021/088 | CHS | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-11-25 | 2021-11-25 |  |  |  | 2021-04-15 |  |  |  | TR3 |  | South | Non-WSIP | [6 empty] | '-120.736174 | 35.4914 | ETL.5960 | 40873355 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118201939 | Not Scheduled | DIABLO-MIDWAY #2 52/212 INST GATE | 31510049 | DIABLO-MIDWAY #2 | 052/212 | 71Y | F | Pre-2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-11-25 | 2021-11-25 |  |  |  | 2021-09-01 | [5 empty] | South | Non-WSIP | [6 empty] | '-119.957893 | 35.2563 | ETL.5970 | 40655342 | Fence / Gate | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | Pre-2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118269265 | Q4 | EI DEL MONTE-VIEJO A001/033 RMV VEGN |  | DEL MONTE-VIEJO (NO FLY) | A001/033 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-12-13 | 2020-12-13 |  |  | 2021-12-31 | 2021-12-01 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-121.86527 | 36.5871 | ETL.6710 | 41082485 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118358015 | Q4 | DEL MONTE-VIEJO A001/032 RMV VEGN |  | DEL MONTE-VIEJO (NO FLY) | A001/032 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2019-12-20 | 2020-12-20 |  |  | 2021-12-31 | 2021-12-01 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-121.866062 | 36.5877 | ETL.6710 | 41082483 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Found Before 2020 | Found Before 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118474681 | Q2 | KING CITY-COBURN #2 A011/170 REFRAME | 31462266 | KING CITY-COBURN #2 | A011/170 | 92T | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2020-01-28 | 2021-01-28 | 2021-04-13 | 2021-04-13 | 2021-04-13 | 2021-04-13 |  |  | 92T/IBT |  | LATE | South | WSIP | [6 empty] | '-121.222521 | 36.328 | ETL.7330 | 40812038 | Crossarm-Wood | No Good/Out of Stdrd | Replace | hold srdy dcpr POST |  |  |  | PEND | LC | TLN | Maintenance | Capital | 637 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Yes | Currently Past Due | Scheduled End On/After Today | Already Past Due | Found in 2020 | Not FSR Upgrade | 92 | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 118528418 | Not Scheduled | T2 DEL MONTE-VIEJO 4/109 RPL ROAD |  | DEL MONTE-VIEJO (NO FLY) | 004/109 | 71Y | F | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-02-12 | 2022-02-12 |  |  |  | 2021-04-10 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.894067 | 36.5583 | ETL.6710 | 40600105 | Road | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLR | Roads | Capital | 374 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 118537964 | Not Scheduled | T2 COLGATE-PALERMO 4/71 RPL SPLW | 44197729 | COLGATE-PALERMO | 004/071 | ICW | E | 2020_(5) TD tag on other lines | Customer clearance | 2020-02-14 | 2021-02-14 | [7 empty] | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.260678 | 39.3304 | ETL.6500 | 42564736 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-05-07 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(5) TD tag on other lines | Pending Repair
Approved Outside Workplan | 118552792 | Not Scheduled | T2 OAKHURST TAP 14/7 RMV VEG | 44298388 | OAKHURST TAP | 014/007 | CHS | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-02-20 | 2021-02-20 |  |  |  | 2021-02-08 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.652347 | 37.2864 | ETL.1252 | 40806854 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118654287 | Feb | PEASE-RIO OSO SW 159 27/201 RPR SWIS | 44242658 | PEASE-RIO OSO | 027/197 | ICE | E | 2020_(9d) All other tags | Clearance restriction (circuit efficiency) | 2020-03-09 | 2021-03-09 |  |  | 2021-02-24 | 2021-02-24 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.542199 | 39.0955 | ETL.3270 | 40594989 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118681491 | Not Scheduled | T3 CENTERVILLE-TABLE MTN 0/8 RPL POLE | 31498696 | CENTERVILLE-TABLE MTN | 000/008 | 70Y | E | 2020_(5) TD tag on other lines | Clearance restriction (circuit efficiency) | 2020-03-11 | 2020-09-11 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.661898 | 39.7828 | ETL.6320 | 44820183 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-06-19 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(5) TD tag on other lines | Pending Repair
Approved Outside Workplan | 118715197 | Not Scheduled | EI HERNDON-BARTON 10/87 RMV ROW |  | HERNDON-BARTON (NO FLY) | 010/087 | CHR | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-03-17 | 2021-03-17 | [8 empty] | <30D | South | WSIP | [6 empty] | '-119.772758 | 36.7828 | ETL.1750 | 44261435 | Right of Way | Encroachment | Remove |  |  |  |  | PEND | LC | TLS | Land | Expense | 931 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118715347 | Not Scheduled | EI HERNDON-BARTON 10/084 RMV ROW |  | HERNDON-BARTON (NO FLY) | 010/084 | CHR | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-03-17 | 2021-03-17 | [8 empty] | <30D | South | WSIP | [6 empty] | '-119.777778 | 36.7846 | ETL.1750 | 44261432 | Right of Way | Encroachment | Remove |  |  |  |  | PEND | LC | TLS | Land | Expense | 931 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118734245 | Not Scheduled | P-X #2 potholing for CCSF | 44270974 | ETU.9959 |  | ICU | E | 2020_(9d) All other tags | Underground Transmission | 2020-03-23 | 2021-03-23 | [8 empty] | <60D | Central | [7 empty] | '-122.3942205 | 37.7462 | ETU.9959 |  | Cable-Underground | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Expense | 629 | Martin |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118755689 | Not Scheduled | EI HERNDON-BARTON 10/80 RMV ROW |  | HERNDON-BARTON (NO FLY) | 010/080 | CHR | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-03-17 | 2021-03-17 | [8 empty] | <30D | South | WSIP | [6 empty] | '-119.783631 | 36.7867 | ETL.1750 | 44261428 | Right of Way | Encroachment | Remove |  |  |  |  | PEND | LC | TLS | Land | Expense | 931 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118757683 | Not Scheduled | CARNERAS-TAFT 23/362 INST GATE | 31510049 | CARNERAS-TAFT | 023/362 | 71Y | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-03-31 | 2022-03-31 |  |  |  | 2021-04-01 | [5 empty] | South | WSIP | [6 empty] | '-119.706913 | 35.3975 | ETL.8540 | 40749943 | Fence / Gate | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118771438 | Not Scheduled | T2 EXCHEQUER-MARIPOSA 16/0 RPR ROAD | 44399865 | EXCHEQUER-MARIPOSA | 016/000 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-04-02 | 2022-04-02 |  |  |  | 2021-06-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.060222 | 37.4914 | ETL.8640 | 44435832 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118771465 | Not Scheduled | T2NT EXCHEQUER-MARIPOSA 17/0 RMV VEGN RD | 44399865 | EXCHEQUER-MARIPOSA | 017/000 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-04-02 | 2022-04-02 |  |  |  | 2021-06-01 |  |  | Check FDA | TR2 |  | South | WSIP | [6 empty] | '-120.042876 | 37.4902 | ETL.8640 | 40584786 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118796601 | Not Scheduled | T3 EI CENTERVILLE-TABLE MTN 2/34 RPL PL | 31499717 | CENTERVILLE-TABLE MTN | 002/034 | 70Y | E | 2020_(5) TD tag on other lines | Clearance restriction (circuit efficiency) | 2020-04-08 | 2020-10-08 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.677132 | 39.7641 | ETL.6320 | 40599605 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-06-19 | Released-Standard | Complete | Ready for Construction |  | 2020_(5) TD tag on other lines | Pending Repair
Approved Outside Workplan | 118922288 | Not Scheduled | T3 EI CENTERVILLE-TABLE MTN 3/58 RPL STR | 31500437 | CENTERVILLE-TABLE MTN | 003/058 | 70Y | E | 2020_(5) TD tag on other lines | Clearance restriction (circuit efficiency) | 2020-04-15 | 2020-10-15 | [7 empty] | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.692422 | 39.7467 | ETL.6320 | 40874520 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | 70 | Not Scheduled |  |  | 2020-06-19 | Released-Standard | Complete | Ready for Construction |  | 2020_(5) TD tag on other lines | Pending Repair
Approved Outside Workplan | 118932910 | Q2 | T2 VOLTA-DESCHUTES 19/441 INST GATE |  | VOLTA-DESCHUTES | 019/441 | 71Y | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-04-20 | 2021-04-20 |  |  | 2021-04-15 | 2021-04-15 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.22489 | 40.5514 | ETL.8290 | 40770183 | Fence / Gate | Missing | Install |  |  |  |  | PEND | LC | TLR | Roads | Capital | 374 | Table Mountain |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 71 | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118964620 | Not Scheduled | TEMPLETON-GATES 0/5 BOLLARDS | 31521952 | TEMPLETON-GATES | 000/005 | 71Y | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-04-30 | 2021-04-30 | [8 empty] | <90D | South | WSIP | [6 empty] | '-120.674253 | 35.5626 | ETL.5934 | 40608580 | Road | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118981749 | Not Scheduled | EI DIABLO-GATES #1 026/108 RPR ROAD | 44298383 | DIABLO-GATES #1 | 026/108 | CHS | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-05-04 | 2021-05-04 |  |  |  | 2021-05-04 | [5 empty] | South | WSIP | [6 empty] | '-120.684314 | 35.5522 | ETL.5960 | 40871229 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 118995070 | Not Scheduled | DI KRCKHFF-CLVS-SNGR#2 24/157 RMV VEG |  | KERCKHOFF-CLOVIS-SANGER #2 | 024/157 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-05-01 | 2021-05-01 | [8 empty] | <90D | South | WSIP | [6 empty] | '-119.591914 | 36.7373 | ETL.1900 | 40806909 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119013807 | Not Scheduled | MESA-SISQUOC 6/108 REPL POLE | 31502628 | MESA-SISQUOC | 006/108 | 92T | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2020-05-11 | 2021-05-11 | [6 empty] | 92T/IBT |  | <90D | South | WSIP | [6 empty] | '-120.453599 | 34.9526 | ETL.2460 | 44157073 | Structure-Wood | No Good/Out of Stdrd | Replace | hold erdy dcpr ADER |  |  |  | PEND | LC | TLX | Contract | Capital | 372 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 119015940 | Not Scheduled | T2NT DI SAN LUS OBSP-CYCS 14/135 RMV VEG |  | SAN LUIS OBISPO-CAYUCOS | 014/135 | HNA | F | 2020_(9a) Other ignition related | Budget Owner (Veg/Land/Road) | 2020-05-05 | 2022-05-05 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.801839 | 35.3503 | ETL.9090 | 40869569 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9a) Other ignition related | Pending Repair
Approved Outside Workplan | 119018265 | Not Scheduled | T2NT DI EXCHQUR-INDN FLT 3/17 PNT CNCL |  | EXCHEQUER-YOSEMITE | 003/017 | ICS | F | 2020_(9a) Other ignition related | Project efficiency (capital work) | 2020-05-05 | 2022-05-05 | [5 empty] | DLFL; Completed on project 74001200 |  | TR2 |  | South | WSIP | [6 empty] | '-120.229149 | 37.588 | ETL.8650 | 40806454 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 42 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  | 2020-06-09 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(9a) Other ignition related | Pending Repair
Approved Outside Workplan | 119020267 | Not Scheduled | LONE TREE-CAYETANO Replace SW#295 | 31502982 | ETU.9935 |  | 93S | E | 2020_(9d) All other tags | Underground Transmission | 2020-05-12 | 2021-05-12 | [8 empty] | <90D | Central | [7 empty] | '-121.7333444 | 37.7426 | ETU.9935 |  | Cable Termination-Underground | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Capital | 377 | Martin |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119023209 | Not Scheduled | T2NT TEJON-LEBEC 7/136 RPR ROAD | 44400528 | TEJON-LEBEC | 007/136 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-05-12 | 2022-05-12 |  |  |  | 2022-05-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-118.925837 | 34.9158 | ETL.9250 | 44766410 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119029677 | Not Scheduled | Oakmont North. Install Temp Generator | 44323609 | ETU.9984 |  | ICU | E | 2020_(9d) All other tags | Underground Transmission | 2020-05-14 | 2021-05-14 | [8 empty] | <90D | Central | [7 empty] | '-122.5837236 | 38.4428 | ETU.9984 |  | Cable-Underground | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Expense | 629 | Martin |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119039205 | Not Scheduled | CARNERAS-TAFT 023/363 RPR ROAD | 44644935 | CARNERAS-TAFT | 023/363 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-05-12 | 2022-05-12 |  |  |  | 2021-08-01 | [5 empty] | South | WSIP | [6 empty] | '-119.707549 | 35.3983 | ETL.8540 | 40763644 | Road | Grade Change | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119046634 | Not Scheduled | T2 DI CORTINA-MENDOCINO#1 13/62 RMV VEG |  | CORTINA-MENDOCINO #1 | 013/062 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-05-13 | 2021-05-13 | [7 empty] | TR2 | <90D | North Valley | WSIP | [6 empty] | '-122.437368 | 39.0383 | ETL.1330 | 40672386 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119068537 | Not Scheduled | DIABLO-GATES #1 041/167 RMV VEG |  | DIABLO-GATES #1 | 041/167 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-05-27 | 2021-05-27 | [9 empty] | South | WSIP | [6 empty] | '-120.512668 | 35.7103 | ETL.5960 | 40811465 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119104614 | Not Scheduled | T2 TEJON-LEBEC 009/152 RPR RD | 44400528 | TEJON-LEBEC | 009/152 | CHS | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-04 | 2021-06-04 |  |  |  | 2020-12-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-118.922603 | 34.8976 | ETL.9250 | 40586063 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119112364 | Not Scheduled | DI CALLENDER SW STA-MESA 3/52 RMV VEG |  | CALLENDAR SW STA-MESA | 003/052 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-05-21 | 2021-05-21 | [9 empty] | South | WSIP | [6 empty] | '-120.536052 | 35.0518 | ETL.1210 | 40590125 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119116280 | Q2 | T2 DI EXCH-YSMT-IND FLT 30/165 RMV VEG | 44623675 | EXCHEQUER-YOSEMITE | 031/165 | ICS | E | 2020_(9a) Other ignition related | Budget Owner (Veg/Land/Road) | 2020-06-02 | 2021-06-02 |  |  | 2021-06-30 | 2021-03-01 |  |  | Likely veg | TR2 |  | South | WSIP | [6 empty] | '-119.902006 | 37.6688 | ETL.8650 | 40764105 | Vegetation | Overgrown | Trim | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  | AA | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9a) Other ignition related | Pending Repair
Approved Outside Workplan | 119117817 | Not Scheduled | T3NT DI COLGATE-ALLEGHANY 5/140 RMV VEGN |  | COLGATE-ALLEGHANY | 005/140 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-01 | 2022-06-01 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.097724 | 39.3342 | ETL.6470 | 40598542 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2020-06-12 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119119000 | Q4 | T2 SLNS LRLS LRLS 17/159 RMV VEG |  | SALINAS-LAURELES | 007/159 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-03 | 2021-06-03 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | SCHD | South | WSIP | [6 empty] | '-121.6931 | 36.6059 | ETL.7930 | 40768300 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119119074 | Q2 | T2 DI EXCHEQUER-YOSEMITE 28/140 RMV VEG | 44623675 | EXCHEQUER-YOSEMITE | 028/140 | ICS | E | 2020_(9a) Other ignition related | Budget Owner (Veg/Land/Road) | 2020-06-03 | 2021-06-03 |  |  | 2021-06-30 | 2021-03-01 |  |  | Likely veg | TR2 |  | South | WSIP | [6 empty] | '-119.914381 | 37.6536 | ETL.8650 | 40584424 | Vegetation | Overgrown | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9a) Other ignition related | Pending Repair
Approved Outside Workplan | 119119859 | Not Scheduled | T2 DI CAPE HORN TAP 0/1 RMV VEG |  | CAPE HORN TAP | 000/001 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-04 | 2021-06-04 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-120.948581 | 39.1198 | ETL.6761 | 44355526 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119119923 | Q2 | GATES-MIDWAY 62/247 RPL INSS | 31528352 | GATES-MIDWAY | 062/247 | 93K | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2020-06-08 | 2021-06-08 | 2021-04-01 | 2021-05-31 | 2021-05-31 | 2021-04-01 |  | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | WSIP | [6 empty] | '-119.4760687 | 35.4292 | ETL.5990 | 40797052 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 11 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 93 | Q2 |  |  | 2020-07-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 119124139 | Not Scheduled | DI DEL MONTE-FORT ORD #1 4/64 RMV VEG |  | DEL MONTE-FORT ORD #1 (NO FLY) | 004/064 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-08 | 2021-06-08 | [9 empty] | South | WSIP | [6 empty] | '-121.807525 | 36.6382 | ETL.8400 | 40600249 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119125768 | Not Scheduled | T2 DI INDN FLT-YSMITE 39/232 RMV VEG | 44623678 | ETL.1112.POLE.NWOD | 039/232 | ICS | E | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-06-04 | 2021-06-04 | [6 empty] | Likely veg | TR2 |  | South | WSIP | [6 empty] | '-119.779176 | 37.6776 | ETL.1112 | 44420226 | Vegetation | Overgrown | Trim | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  | AA | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119142132 | Not Scheduled | T2 EI DIVIDE-CABRILLO #2 10/126 RMV VEG |  | DIVIDE-CABRILLO #2 | 010/126 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-10 | 2021-06-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.436635 | 34.6832 | ETL.1370 | 40771820 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119144214 | Not Scheduled | DI CRZY HRS CYN-SLNS-SLD 37/235 RMV VEG |  | CRZY HORSE CYN-SALNS-SOLDAD#1 | 037/235 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-05 | 2021-06-05 | [9 empty] | South | WSIP | [6 empty] | '-121.603256 | 36.7737 | ETL.2900 | 40760908 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119144723 | Q2 | DI WTSNVLLE-SLNS 6/81 RMV VEG |  | WATSONVILLE-SALINAS | 006/081 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-08 | 2021-06-08 |  |  | 2021-06-08 | 2021-06-01 | [5 empty] | South | WSIP | [6 empty] | '-121.683408 | 36.8767 | ETL.8310 | 40649069 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | HNA | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119145855 | Not Scheduled | DI SAN LUIS OBISP-CAY 18/169 REMV VEG |  | SAN LUIS OBISPO-CAYUCOS | 018/169 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-05 | 2021-06-05 | [9 empty] | South | WSIP | [6 empty] | '-120.828364 | 35.3968 | ETL.9090 | 40809421 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119155647 | Not Scheduled | DI DEL MONTE-FORT ORD #1 5/70 RMV VEG |  | DEL MONTE-FORT ORD #1 (NO FLY) | 005/070 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-09 | 2021-06-09 | [9 empty] | South | WSIP | [6 empty] | '-121.802039 | 36.6441 | ETL.8400 | 40768343 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119158495 | Not Scheduled | DI RIO OSO-WOODLND #1 ;00/004 RMV VEG |  | RIO OSO-WOODLAND #1 | ;000/004 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-09 | 2021-06-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.748287 | 38.8 | ETL.3460 | 40762541 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119159087 | Not Scheduled | DI WATSONVILLE-SALINAS 6/82 RMV VEG |  | WATSONVILLE-SALINAS | 006/082 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-08 | 2021-06-08 | [9 empty] | South | WSIP | [6 empty] | '-121.68216 | 36.8764 | ETL.8310 | 40668632 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119159611 | Not Scheduled | SIERRA #1 17/116 RPR BAY WATER TOWER | 44394558 | SIERRA #1 (IDLE) | 017/116 | ICJ | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Access | 2020-06-12 | 2021-06-12 | [9 empty] | Central | WSIP | [6 empty] | '-122.230784 | 37.5391 | ETL.3670 | 40818421 | Bay Water-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 510 | Bay |  |  |  | No | Yes | M&C Tag | No | Tower |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 119162144 | Not Scheduled | DI GOLD HILL-BLT-LCKFRD 44/267 RMV VEG |  | GOLD HILL-BELLOTA-LOCKEFORD | 044/267 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-08 | 2021-06-08 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.142714 | 38.533 | ETL.1690 | 40826605 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119163261 | Not Scheduled | DI CRZY HRS CNYN-SLNS-SLD :4/25 RMV VEG |  | CRZY HORSE CYN-SALNS-SOLDAD#1 | :004/025 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-08 | 2021-06-08 | [9 empty] | South | WSIP | [6 empty] | '-121.546769 | 36.6726 | ETL.2900 | 40752798 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119163407 | Not Scheduled | DI WILSON-ORO LOMA 030/000 RMV VEG |  | WILSON-ORO LOMA | 030/000 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-11 | 2021-06-11 | [9 empty] | South | WSIP | [6 empty] | '-120.583662 | 36.9817 | ETL.4200 | 40905365 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119166668 | Not Scheduled | T2 EI BALCH-SANGER 17/093 INST GATE | 44644078 | BALCH-SANGER | 017/093 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-15 | 2022-06-15 |  |  |  | 2021-03-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.347928 | 36.8166 | ETL.1050 | 40663232 | Fence / Gate | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119166669 | Not Scheduled | EI T2NT BALCH-SANGER 018/096 RPR ROAD | 44399717 | BALCH-SANGER | 018/096 | CHS | F | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-06-15 | 2022-06-15 |  |  |  | 2021-03-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.357749 | 36.8158 | ETL.1050 | 40807137 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119183447 | Not Scheduled | T2 BALCH-SANGER 1/10 INS ROAD |  | BALCH-SANGER | 001/010 | 71Y | F | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-06-18 | 2022-06-18 |  |  |  | 2021-06-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.112541 | 36.904 | ETL.1050 | 40608217 | Road | Missing | Install |  |  |  |  | PEND | LC | TLR | Roads | Capital | 374 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119183448 | Not Scheduled | T2 EI BALCH-SANGER 01/011 RPR ROAD | 44399717 | BALCH-SANGER | 001/011 | CHS | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-18 | 2021-06-18 |  |  |  | 2020-12-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.116429 | 36.903 | ETL.1050 | 40583098 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119186879 | Not Scheduled | DI SALINAS-LAGUNITAS 4/91 RMV DEBRIS |  | SALINAS-LAGUNITAS | 004/091 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-18 | 2021-06-18 | [9 empty] | South | WSIP | [6 empty] | '-121.613503 | 36.7339 | ETL.7920 | 40701930 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119189106 | Not Scheduled | DI BELL-PLACER 003/024 RMV VEG |  | BELL-PLACER | 003/024 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-18 | 2021-06-18 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.071213 | 38.9239 | ETL.4395 | 40817273 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119211534 | Feb | DI WINTU TAP 001/027 RPL STRW | 31509663 | WINTU TAP | 001/027 | 70Y | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Customer clearance | 2020-06-25 | 2021-06-25 |  |  | 2021-02-18 | 2021-02-16 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.358593 | 40.5931 | ETL.6311 | 40759191 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 119230728 | Not Scheduled | T3 EI MTCLF-MSS LANDING #1 42/185 RMV VE |  | METCALF-MOSS LANDING #1 | 042/185 | CHS | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-29 | 2020-12-29 |  |  |  | 2021-03-05 |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.664317 | 37.025 | ETL.5100 | 40764508 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | Yes |  | Not Scheduled | Not Scheduled, Past Due | No Scheduled End | Already Past Due | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119235599 | Feb | EI WINTU TAP 0/10 RPL STRW | 31509664 | WINTU TAP | 000/010 | 70Y | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Customer clearance | 2020-06-30 | 2021-06-30 |  |  | 2021-02-18 | 2021-02-16 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.353231 | 40.5839 | ETL.6311 | 40600485 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-01-18 | Released-Standard | Complete | Ready for Construction |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 119237641 | Not Scheduled | EI T3NT MORRO BAY-TEMPLETON 6/31 RMV VEG | 44638217 | MORRO BAY-TEMPLETON | 006/031 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-06-30 | 2022-06-30 |  |  |  | 2022-05-01 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.763972 | 35.4379 | ETL.5933 | 40587200 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119290804 | Q2 | DI CNTRVL-TBL MTN-ORVL 21/423A REPL POLE | 31507569 | CENTERVILLE-TABLE MTN-OROVILLE | 021/423A | 70Y | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2020-06-30 | 2021-06-30 |  |  | 2021-05-24 | 2021-05-24 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.578557 | 39.5089 | ETL.6330 | 40598408 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-27 | Released-Standard | Complete | Ready for Construction |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 119291065 | Q2 | DI CNTRVL-TBL MTN-ORVL 21/423C REPL POLE | 31507569 | CENTERVILLE-TABLE MTN-OROVILLE | 021/423C | 70Y | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2020-06-30 | 2021-06-30 |  |  | 2021-05-24 | 2021-05-24 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.578578 | 39.5089 | ETL.6330 | 42560771 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2020-07-17 | Released-Standard | Complete | Ready for Construction |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 119291081 | Q2 | DI CNTRVL-TBL MTN-ORVL 21/423B REPL POLE | 31507569 | CENTERVILLE-TABLE MTN-OROVILLE | 021/423 | 70Y | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2020-06-30 | 2021-06-30 |  |  | 2021-05-24 | 2021-05-24 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.578568 | 39.5089 | ETL.6330 | 42560770 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 70 | Q2 |  |  | 2021-01-27 | Released-Standard | Complete | Ready for Construction |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 119294731 | Not Scheduled | EI T3NT DEER CREEK-DRUM 5/132 RMV VEG |  | DEER CREEK-DRUM | 005/132 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-01 | 2022-07-01 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.779995 | 39.2593 | ETL.6690 | 40664845 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119302211 | Not Scheduled | T3 EI TEMBLOR-SAN LUIS OBISO 46/261 RMV |  | TEMBLOR-SAN LUIS OBISPO | 046/261 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-02 | 2022-07-02 | [7 empty] | TR3 |  | South | WSIP | [6 empty] | '-120.475924 | 35.3603 | ETL.3960 | 40585713 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119302636 | Not Scheduled | EI DRUM-RIO OSO #1 40/289 RMV VEG |  | DRUM-RIO OSO #1 | 040/289 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-02 | 2021-07-02 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.419221 | 38.9691 | ETL.1420 | 40868098 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119308553 | Not Scheduled | EI ARCO-TULARE LAKE 014/221 TRIM VEGN |  | ARCO-TULARE LAKE | 014/221 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-03 | 2022-07-03 | [9 empty] | South | WSIP | [6 empty] | '-119.934615 | 35.977 | ETL.8460 | 40748407 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119308554 | Not Scheduled | EI ARCO-TULARE LAKE 014/217 TRIM VEGN |  | ARCO-TULARE LAKE | 014/217 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-03 | 2022-07-03 | [9 empty] | South | WSIP | [6 empty] | '-119.932685 | 35.9735 | ETL.8460 | 40595371 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119308555 | Not Scheduled | EI ARCO-TULARE LAKE 014/218 TRIM VEGN |  | ARCO-TULARE LAKE | 014/218 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-03 | 2022-07-03 | [9 empty] | South | WSIP | [6 empty] | '-119.933158 | 35.9744 | ETL.8460 | 40687733 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119310137 | Not Scheduled | T3NT DIABLO-MIDWAY #2 7/029 RMV VEG |  | DIABLO-MIDWAY #2 | 007/029 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-03 | 2022-07-03 | [7 empty] | TR3 |  | South | WSIP | [6 empty] | '-120.711642 | 35.2018 | ETL.5970 | 40863575 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119313774 | Not Scheduled | EI GREEN VLY-CAMP EVRS 00/04 RMV VEGN |  | GREEN VALLEY-CAMP EVERS | 000/004 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-06 | 2022-07-06 | [9 empty] | South | WSIP | [6 empty] | '-121.759403 | 36.9541 | ETL.1710 | 41088855 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119314282 | Not Scheduled | EI T3NT ATSCDR-SN LUIS OBISPO 8/142 RMV |  | ATASCADERO-SAN LUIS OBISPO | 008/142 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-06 | 2022-07-06 | [7 empty] | TR3 |  | South | WSIP | [6 empty] | '-120.630694 | 35.3592 | ETL.8490 | 40606014 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119314405 | Not Scheduled | MORGAN HILL JCT-GRN VLLY 23/178 RMV VEG |  | METCALF-GREEN VALLEY | 023/178 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-06 | 2022-07-06 | [9 empty] | South | WSIP | [6 empty] | '-121.747649 | 36.9539 | ETL.2540 | 43684236 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119314457 | Not Scheduled | EI GRN VALLEY-CAMP EVERS 02/40 RMV VEGN |  | GREEN VALLEY-CAMP EVERS | 002/040 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-06 | 2022-07-06 | [9 empty] | South | WSIP | [6 empty] | '-121.791477 | 36.9757 | ETL.1710 | 41139760 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119315831 | Not Scheduled | EI SAN LUIS OBISPO-CAYUCOS 9/81 RMV VEG |  | SAN LUIS OBISPO-CAYUCOS | 009/081 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-06 | 2021-07-06 | [9 empty] | South | WSIP | [6 empty] | '-120.70504 | 35.3044 | ETL.9090 | 40766120 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119316352 | Not Scheduled | EI GREEN VALLEY-CAMP EVERS 3/045L RMV VE |  | GREEN VALLEY-CAMP EVERS | 003/045 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-06 | 2022-07-06 | [9 empty] | South | WSIP | [6 empty] | '-121.797641 | 36.9781 | ETL.1710 | 44510517 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119324354 | Not Scheduled | EI PEASE-HARTER A14/306 RMV VEG |  | PEASE-HARTER | A014/306 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-07 | 2021-07-07 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.906356 | 39.1455 | ETL.7760 | 40815458 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119325994 | Q4 | EI METCALF-GREEN VALLEY 5/037 RMV VEG |  | METCALF-GREEN VALLEY | 005/037 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-07 | 2022-07-07 |  |  | 2021-12-31 | 2021-12-01 | [5 empty] | South | WSIP | [6 empty] | '-121.698051 | 37.1733 | ETL.2540 | 40817769 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119326110 | Not Scheduled | EI VACA-SUISUN 21/195 RMV VEGN |  | VACA-SUISUN | 021/195 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-07 | 2021-07-07 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.045119 | 38.2436 | ETL.4070 | 40653645 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119326906 | Not Scheduled | EI T3NT FRENCH MDWS-MDDLE FRK 1/25 RMV V |  | FRENCH MEADOWS-MIDDLE FORK | 001/025 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-07 | 2022-07-07 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.421382 | 39.0678 | ETL.6870 | 40751808 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119327558 | Not Scheduled | EI GOLD HILL-EIGHT MLE RD 49/208 RMV VEG |  | GOLD HILL-EIGHT MILE ROAD | 049/208 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-07 | 2022-07-07 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.351216 | 38.4593 | ETL.4800 | 40865560 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119327881 | Not Scheduled | TEJON-LEBEC 02/041 RPL FENCE | 31510049 | TEJON-LEBEC | 002/041 | 71Y | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-07 | 2021-07-07 |  |  |  | 2021-09-01 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-118.947364 | 34.9918 | ETL.9250 | 40647163 | Fence / Gate | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119331425 | Not Scheduled | EI DELEVAN-VACA #2 192/1433 RMV VEG |  | DELEVAN-VACA #2 | 192/1433 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-08 | 2021-07-08 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.926241 | 38.5266 | ETL.4231 | 40656851 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119331515 | Q4 | EI DEL MONTE-VIEJO A001/029 RMV VEG |  | DEL MONTE-VIEJO (NO FLY) | A001/029 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-08 | 2022-07-08 |  |  | 2021-12-31 | 2021-12-01 | [5 empty] | South | WSIP | [6 empty] | '-121.867101 | 36.589 | ETL.6710 | 40583755 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119331646 | Q4 | EI DEL MONTE-VIEJO A001/028 RMV VEG |  | DEL MONTE-VIEJO (NO FLY) | A001/028 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-08 | 2022-07-08 |  |  | 2021-12-31 | 2021-12-01 | [5 empty] | South | WSIP | [6 empty] | '-121.867306 | 36.5895 | ETL.6710 | 40588370 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119331965 | Q4 | EI DEL MONTE-VIEJO A001/026 RMV VEG |  | DEL MONTE-VIEJO (NO FLY) | A001/026 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-08 | 2022-07-08 |  |  | 2021-12-31 | 2021-12-01 | [5 empty] | South | WSIP | [6 empty] | '-121.867564 | 36.5909 | ETL.6710 | 40652678 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119331996 | Not Scheduled | EI DELEVAN-VACA #2 192/1431 RMV VEG |  | DELEVAN-VACA #2 | 192/1431 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-08 | 2021-07-08 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.925608 | 38.5307 | ETL.4231 | 40592047 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119332072 | Q4 | EI DEL MONTE-VIEJO A001/025 RMV VEG |  | DEL MONTE-VIEJO (NO FLY) | A001/025 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-08 | 2022-07-08 |  |  | 2021-12-31 | 2021-12-01 | [5 empty] | South | WSIP | [6 empty] | '-121.867506 | 36.5915 | ETL.6710 | 40754709 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119332890 | Not Scheduled | EI PALERMO-PEASE :4/019 RMV VEG |  | PALERMO-PEASE | :004/019 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-08 | 2021-07-08 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.641556 | 39.1747 | ETL.3220 | 40909242 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119332950 | Not Scheduled | EI GREEN VALLEY-CAMP EVERS 5/63C RMV VEG |  | GREEN VALLEY-CAMP EVERS | 005/063C | HNA | E | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-07-08 | 2021-07-08 | [9 empty] | South | WSIP | [6 empty] | '-121.834875 | 36.9922 | ETL.1710 | 44509623 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119333204 | Not Scheduled | EI VACA-SUISUN 16/110 RMV VEG |  | VACA-SUISUN | 016/110 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-08 | 2021-07-08 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.095926 | 38.2368 | ETL.4070 | 40869887 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119333498 | Not Scheduled | EI VACA-SUISUN 16/109 RMV VEG |  | VACA-SUISUN | 016/109 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-08 | 2021-07-08 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.095013 | 38.2382 | ETL.4070 | 40607880 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119333938 | Not Scheduled | EI VACA-SUISUN 15/108 RMV VEG |  | VACA-SUISUN | 015/108 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-08 | 2021-07-08 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.093588 | 38.2405 | ETL.4070 | 40865463 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119334284 | Not Scheduled | EI VACA-SUISUN 15/108 CANCEL |  | VACA-SUISUN | 015/108 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-08 | 2021-07-08 | [6 empty] | CANCEL/CNCL |  |  | North Valley | WSIP | [6 empty] | '-122.093588 | 38.2405 | ETL.4070 | 40865463 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119334331 | Not Scheduled | EI DELEVAN-VACA #2 180/1347 RMV VEG |  | DELEVAN-VACA #2 | 180/1347 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-08 | 2021-07-08 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.956994 | 38.7067 | ETL.4231 | 40816021 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119336112 | Not Scheduled | EI PEASE-HARTER A010/235 RMV VEG |  | PEASE-HARTER | A010/235 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2022-07-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.841168 | 39.1456 | ETL.7760 | 40598124 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119337312 | Not Scheduled | EI T3NT BRUNSWICK #1 TAP 1/13 RMV VEG |  | BRUNSWICK #1 TAP | 001/013 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2022-07-09 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-121.024316 | 39.162 | ETL.1422 | 40650073 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119337326 | Not Scheduled | EI WEST SACRAMENTO-DAVIS 10/171 RMV VEG |  | WEST SACRAMENTO-DAVIS | 010/171 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2021-07-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.731229 | 38.5605 | ETL.4120 | 40813132 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119338472 | Before Feb | T2 EI DEL MNTE-VIJ 2/52 RMV VEG |  | DEL MONTE-VIEJO (NO FLY) | 002/052 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2021-07-09 |  |  | 2021-01-22 | 2021-01-22 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.874137 | 36.582 | ETL.6710 | 44291076 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Before Feb | Found in 2020 | Not FSR Upgrade | HNA | Before Feb |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119338557 | Q3 | T2 EI DEL MONTE-VIEJO 04/112 RMV VEG |  | DEL MONTE-VIEJO (NO FLY) | 004/112 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2021-07-09 |  |  | 2021-07-09 | 2021-07-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.896891 | 36.5579 | ETL.6710 | 40769005 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | HNA | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119338743 | Not Scheduled | EI WEST SACRAMENTO-DAVIS 11/178 RMV VEG |  | WEST SACRAMENTO-DAVIS | 011/178 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2021-07-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.735667 | 38.5595 | ETL.4120 | 40752028 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119338809 | Not Scheduled | EI VACA-SUISUN-JAMESON A17/115 RMV VEG |  | VACA-SUISUN-JAMESON | A017/115 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2021-07-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.094401 | 38.2309 | ETL.4080 | 40590892 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119338861 | Not Scheduled | EI VACA-SUISUN-JAMESON B18/125 RMV VEG |  | VACA-SUISUN-JAMESON | B018/125 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2021-07-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.128598 | 38.2211 | ETL.4080 | 44266983 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119338972 | Not Scheduled | EI PALERMO-NICOLAUS 40/289C RMV VEG |  | PALERMO-NICOLAUS | 040/289C | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2021-07-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.531019 | 38.9144 | ETL.3210 | 40912971 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119338981 | Not Scheduled | EI WEST SACRAMENTO-DAVIS 11/180 RMV VEG |  | WEST SACRAMENTO-DAVIS | 011/180 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2021-07-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.735683 | 38.558 | ETL.4120 | 40812250 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119339043 | Not Scheduled | EI GOLD HILL-EIGHT MILE RD 55/233 RMV VE |  | GOLD HILL-EIGHT MILE ROAD | 055/233 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2021-07-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.351377 | 38.3747 | ETL.4800 | 40660090 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119339175 | Not Scheduled | EI VACA-SUISUN-JAMESON B18/129 RMV VEG |  | VACA-SUISUN-JAMESON | B018/129 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2021-07-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.135727 | 38.2159 | ETL.4080 | 40576452 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119339773 | Not Scheduled | EI GREEN VALLEY-CAMP EVERS 6/78 RMV VEG |  | GREEN VALLEY-CAMP EVERS | 006/078 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2021-07-09 | [9 empty] | South | WSIP | [6 empty] | '-121.874149 | 37.0022 | ETL.1710 | 44696026 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119340075 | Not Scheduled | EI PALERMO-PEASE 1/10 RMV VEG |  | PALERMO-PEASE | :001/010 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2021-07-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.606165 | 39.1766 | ETL.3220 | 40905537 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119340808 | Not Scheduled | EI TEMPLETON-GATES 49/212 RMV VEG |  | TEMPLETON-GATES | 049/212 | HNA | E | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2021-07-09 | [9 empty] | South | WSIP | [6 empty] | '-120.279678 | 35.9119 | ETL.5934 | 40647367 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119341158 | Not Scheduled | EI T3NT FRNCH MDWS-MDDLE FRK 2/41 RMV VE |  | FRENCH MEADOWS-MIDDLE FORK | 002/041 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2022-07-09 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.431785 | 39.0585 | ETL.6870 | 40611465 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119341159 | Not Scheduled | EI T3NT FRENCH MDWS-MDDLE FRK 2/42 RMV V |  | FRENCH MEADOWS-MIDDLE FORK | 002/042 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2022-07-09 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.432588 | 39.0579 | ETL.6870 | 40593746 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119341212 | Not Scheduled | EI T3NT FRNCH MDWS-MDDLE FORK 2/43 RMV V |  | FRENCH MEADOWS-MIDDLE FORK | 002/043 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2022-07-09 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.433368 | 39.0573 | ETL.6870 | 44340600 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119341367 | Not Scheduled | EI T3NT DRUM-RIO OSO #2 - 8/088 RMV VEG |  | DRUM-RIO OSO #2 | 008/088 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2022-07-09 | [7 empty] | TR3 |  | North Valley | WSIP | [6 empty] | '-120.888981 | 39.1875 | ETL.1430 | 40866979 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119341368 | Q4 | EI T3NT DRUM-RIO OSO #2 8/88 RPR ROAD | 43663366 | DRUM-RIO OSO #2 | 008/088 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-09 | 2022-07-09 |  |  | 2021-12-31 | 2021-12-31 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.888981 | 39.1875 | ETL.1430 | 40866979 | Road | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLR | Roads | Expense | 932 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | CH | Q4 |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119351092 | Not Scheduled | T2 EI DEL MONTE-VIEJO 4/108 RMV VEG |  | DEL MONTE-VIEJO (NO FLY) | 004/108 | HNA | E | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.893136 | 36.5578 | ETL.6710 | 40589422 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119353414 | Not Scheduled | EI VACA-SUISUN 1/013 RMV VEG |  | VACA-SUISUN | 001/013 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-10 | 2021-07-10 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.949741 | 38.4026 | ETL.4070 | 40653647 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119354497 | Not Scheduled | T2 EI DEL MONTE-VIEJO 3/075 RMV VEG |  | DEL MONTE-VIEJO (NO FLY) | 003/075 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.879907 | 36.5732 | ETL.6710 | 40613858 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119354499 | Not Scheduled | T2 EI DEL MONTE-VIEJO 4/080 RMV VEG |  | DEL MONTE-VIEJO (NO FLY) | 004/080 | HNA | E | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-07-10 | 2021-07-10 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-121.883211 | 36.5725 | ETL.6710 | 40768279 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119354522 | Q4 | T2 EI DEL MONTE-VIEJO 3/71 RMV VEG |  | DEL MONTE-VIEJO (NO FLY) | 003/071 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-10 | 2022-07-10 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.877425 | 36.5731 | ETL.6710 | 44379220 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119354766 | Q4 | T2 EI SALINAS-LAURELES A14/299 RMV VEG |  | SALINAS-LAURELES | A014/299 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-10 | 2021-07-10 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | SCHD | South | WSIP | [6 empty] | '-121.797478 | 36.5693 | ETL.7930 | 40768296 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119358195 | Not Scheduled | JEFFERSON-MARTIN - 230 kV_66 | 44387836 | ETU.9931 | 66 | ICU | E | 2020_(9d) All other tags | Underground Transmission | 2020-07-11 | 2021-07-11 | [9 empty] | Central | [7 empty] | '-122.452249 | 37.6958 | ETU.9931 | 41353802 | Cover / Manhole-Underground | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Expense | 629 | Martin |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119360773 | Not Scheduled | EI MESA-SISQUOC 003/052 TRIM VEGN |  | MESA-SISQUOC | 003/052 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-13 | 2022-07-13 | [9 empty] | South | WSIP | [6 empty] | '-120.437393 | 34.9806 | ETL.2460 | 40753243 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119361172 | Not Scheduled | DI BRIGHTON-DAVIS 12/90 RMV VEG |  | BRIGHTON-DAVIS | 012/090 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-13 | 2021-07-13 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.543036 | 38.4666 | ETL.1140 | 43249418 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119361384 | Not Scheduled | DI BRIGHTON-DAVIS 10/80 RMV VEG |  | BRIGHTON-DAVIS | 010/080 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-13 | 2022-07-13 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.519633 | 38.4648 | ETL.1140 | 44163639 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119362459 | Not Scheduled | DI BRIGHTON-DAVIS 13/97 RMV VEG |  | BRIGHTON-DAVIS | 013/097 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-13 | 2021-07-13 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.559196 | 38.4722 | ETL.1140 | 40809785 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119364718 | Not Scheduled | DI BRIGHTON-DAVIS 013/099 RMV VEG |  | BRIGHTON-DAVIS | 013/099 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-13 | 2021-07-13 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.563788 | 38.4738 | ETL.1140 | 40872734 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119366393 | Not Scheduled | MESA-SISQUOC 14/246 ROW DEBRIS |  | MESA-SISQUOC | 014/246 | CHR | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-14 | 2021-07-14 | [9 empty] | South | WSIP | [6 empty] | '-120.354241 | 34.9073 | ETL.2460 | 40815333 | Right of Way | Encroachment | Remove |  |  |  |  | PEND | LC | TLS | Land | Expense | 931 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119366394 | Not Scheduled | MESA-SISQUOC 15/247 ROW DEBRIS |  | MESA-SISQUOC | 015/247 | CHR | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-14 | 2021-07-14 | [9 empty] | South | WSIP | [6 empty] | '-120.35352 | 34.9066 | ETL.2460 | 40590850 | Right of Way | Encroachment | Remove |  |  |  |  | PEND | LC | TLS | Land | Expense | 931 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119366838 | Not Scheduled | DI BRIGHTON-DAVIS 12/92 RMV VEG |  | BRIGHTON-DAVIS | 012/092 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-13 | 2021-07-13 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.547654 | 38.4682 | ETL.1140 | 40689238 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119367041 | Not Scheduled | EI PEASE-MARYSVILLE-HARTER A0/8 RMV VEG |  | PEASE-MARYSVILLE-HARTER | A000/008 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-14 | 2021-07-14 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.66221 | 39.1617 | ETL.7770 | 40875835 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119367294 | Not Scheduled | EI SALINAS-FIRESTONE #1 05/136 RMV VEG |  | SALINAS-FIRESTONE #1 (NO FLY) | 005/136 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-14 | 2022-07-14 | [9 empty] | South | WSIP | [6 empty] | '-121.591807 | 36.6302 | ETL.7900 | 40666501 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119368307 | Not Scheduled | EI PEASE-MARYSVILLE-HARTER 1/25 RMV VEG |  | PEASE-MARYSVILLE-HARTER | 001/025 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-14 | 2021-07-14 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.63564 | 39.1707 | ETL.7770 | 40822178 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119368796 | Not Scheduled | EI GOLD HILL-EIGHT MILE ROAD 57/242 RMV |  | GOLD HILL-EIGHT MILE ROAD | 057/242 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-14 | 2021-07-14 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.353053 | 38.3419 | ETL.4800 | 40694803 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119369002 | Not Scheduled | EI GOLD HILL-EIGHT MILE ROAD 57/243 RMV |  | GOLD HILL-EIGHT MILE ROAD | 057/243 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-14 | 2021-07-14 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.353247 | 38.3381 | ETL.4800 | 40662952 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119369870 | Not Scheduled | EI GOLD HILL-EIGHT MILE RD 57/243A RMV V |  | GOLD HILL-EIGHT MILE ROAD | 057/243A | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-14 | 2021-07-14 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.353338 | 38.3363 | ETL.4800 | 41162712 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119371809 | Not Scheduled | DI RIO OSO-WOODLAND #1 27/169 TRIM VEGN |  | RIO OSO-WOODLAND #1 | 027/169 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-13 | 2022-07-13 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.886929 | 38.7189 | ETL.3460 | 40866700 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119372519 | Not Scheduled | EI SALINAS-LAGUNITAS 0/9 RMV VEG |  | SALINAS-LAGUNITAS | 000/009 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-15 | 2021-07-15 | [9 empty] | South | WSIP | [6 empty] | '-121.647805 | 36.6854 | ETL.7920 | 40826129 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119372641 | Q4 | T2 EI SALINAS-LAURELES A15/333 RMV VEG |  | SALINAS-LAURELES | A015/333 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-15 | 2021-07-15 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | SCHD | South | WSIP | [6 empty] | '-121.824379 | 36.5768 | ETL.7930 | 40824196 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119373732 | Not Scheduled | EI RIO OSO-WOODLAND #2 - 115 kV_033/207 |  | RIO OSO-WOODLAND #2 | 033/207 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-15 | 2022-07-15 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.948372 | 38.6437 | ETL.3470 | 40813056 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119373983 | Not Scheduled | EI RIO OSO-WOODLAND #2 35/216 RMV VEG |  | RIO OSO-WOODLAND #2 | 035/216 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-15 | 2022-07-15 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.96186 | 38.6271 | ETL.3470 | 40813875 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119374017 | Not Scheduled | EI ARCO-TULARE LAKE 12/199 RMV VEG |  | ARCO-TULARE LAKE | 012/199 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-15 | 2021-07-15 | [9 empty] | South | WSIP | [6 empty] | '-119.926773 | 35.9581 | ETL.8460 | 41196720 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119374159 | Not Scheduled | EI SALINAS-FIRESTONE #1 4/104 RMV VEG |  | SALINAS-FIRESTONE #1 (NO FLY) | 004/104 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-15 | 2021-07-15 | [9 empty] | South | WSIP | [6 empty] | '-121.611921 | 36.6449 | ETL.7900 | 40652406 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119375191 | Q4 | EI SALINAS-LAURELES A17/362 RMV VEG |  | SALINAS-LAURELES | A017/362 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-15 | 2021-07-15 |  |  | 2021-12-31 | 2021-12-01 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-121.845293 | 36.5828 | ETL.7930 | 40754707 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119376526 | Not Scheduled | EI SOLEDAD #1 14/274 RMV VEG |  | SOLEDAD #1 | 014/274 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-15 | 2021-07-15 | [9 empty] | South | WSIP | [6 empty] | '-121.519791 | 36.5718 | ETL.8010 | 40864394 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119377544 | Not Scheduled | EI VACA-PLAINFIELD 09/137 RMV VEG |  | VACA-PLAINFIELD | 009/137 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-15 | 2021-07-15 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.95996 | 38.5295 | ETL.8200 | 40824827 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119379440 | Not Scheduled | T2 EI SMARTVILLE-MARYSVILLE 0/3 RMV VEG |  | SMARTVILLE-MARYSVILLE | 000/003 | HNA | E | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-07-15 | 2021-07-15 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.304246 | 39.2098 | ETL.7980 | 40657995 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119379627 | Not Scheduled | T2NT DI CLLNDR SW ST-MSA 21/100 RMV VEG |  | CALLENDAR SW STA-MESA | 021/100 | HNA | F | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-07-15 | 2022-07-15 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.446403 | 35.0114 | ETL.1210 | 40604611 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119380535 | Not Scheduled | EI POE-RIO OSO 054/352 RMV VEG |  | POE-RIO OSO | 054/352 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-16 | 2021-07-16 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.477736 | 39.2167 | ETL.5540 | 40673128 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119380551 | Not Scheduled | EI PEASE-MARYSVILLE-HARTER 7/138 RMV VEG |  | PEASE-MARYSVILLE-HARTER | 007/138 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-16 | 2021-07-16 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.576801 | 39.1499 | ETL.7770 | 40692031 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119380688 | Not Scheduled | EI WATSONVILLE-SALINAS 020/250 RMV VEGN |  | WATSONVILLE-SALINAS | 020/250 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-16 | 2021-07-16 | [9 empty] | South | WSIP | [6 empty] | '-121.61048 | 36.7583 | ETL.8310 | 40754187 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119380804 | Not Scheduled | Replace N2 valves at K and D | 31509731 | ETU.9967 | D TERMINAL | 72Z | E | 2020_(9d) All other tags | Underground Transmission | 2020-07-16 | 2021-07-16 | [9 empty] | Central | [7 empty] | '-122.2634778 | 37.8374 | ETU.9967 | 41113533 | Riser-Underground | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Capital | 377 | Martin |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 72Z | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119381302 | Not Scheduled | EI COLGATE-RIO OSO 030/142 RMV VEG |  | COLGATE-RIO OSO | 030/142 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-16 | 2021-07-16 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.477999 | 39.2194 | ETL.5900 | 40672142 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119381913 | Not Scheduled | EI NICOLAUS-MARYSVILLE 4/88 RMV VEG |  | NICOLAUS-MARYSVILLE | 004/088 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-16 | 2021-07-16 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.557105 | 39.0981 | ETL.7690 | 40598919 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119382024 | Not Scheduled | EI SALINAS-FIRESTONE #1 00/029 RMV VEGN |  | SALINAS-FIRESTONE #1 (NO FLY) | 000/029 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-16 | 2021-07-16 | [9 empty] | South | WSIP | [6 empty] | '-121.6412 | 36.6741 | ETL.7900 | 40593702 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119382443 | Not Scheduled | EI DEL MONTE-FORT ORD #2 00/011 TRIM VEG |  | DEL MONTE-FORT ORD #2 (NF) | 000/011 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-16 | 2021-07-16 | [9 empty] | South | WSIP | [6 empty] | '-121.847445 | 36.5996 | ETL.8422 | 40812104 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119382888 | Not Scheduled | EI POE-RIO OSO 054/356 RMV VEG |  | POE-RIO OSO | 054/356 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-16 | 2021-07-16 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.476097 | 39.2086 | ETL.5540 | 40822820 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119453301 | Not Scheduled | EI COLGATE-RIO OSO 31/146 RMV VEGN |  | COLGATE-RIO OSO | 031/146 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-16 | 2021-07-16 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.47561 | 39.2075 | ETL.5900 | 40815294 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119464442 | Not Scheduled | EI DELEVAN-VACA #3 201/1491B REV VEG |  | DELEVAN-VACA #3 | 201/1491B | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2022-07-17 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.91928 | 38.4031 | ETL.4790 | 40910444 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119464630 | Not Scheduled | EI POE-RIO OSO 70/454 RMV VEG |  | POE-RIO OSO | 070/454 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2022-07-17 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.467805 | 38.9844 | ETL.5540 | 40757694 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119464890 | Not Scheduled | EI DELEVAN-VACA #3 196/1460 RMV VEG |  | DELEVAN-VACA #3 | 196/1460 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2022-07-17 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.931941 | 38.4693 | ETL.4790 | 43203090 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119466187 | Not Scheduled | EI DIXON-VACA #1 8/180 RMV VEG |  | DIXON-VACA #1 | 008/180 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2021-07-17 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.825829 | 38.4452 | ETL.6730 | 41195902 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119466437 | Not Scheduled | EI POE-RIO OSO 069/452 RMV VEG |  | POE-RIO OSO | 069/452 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2022-07-17 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.468383 | 38.9895 | ETL.5540 | 40680767 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119467240 | Not Scheduled | EI MSS LNDNG-GRN VLLY #1 6/34 RMV VEG |  | MOSS LANDING-GREEN VALLEY #1 | 006/034 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2021-07-17 | [9 empty] | South | WSIP | [6 empty] | '-121.72318 | 36.8543 | ETL.2850 | 40755345 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119467338 | Not Scheduled | EI NICOLAUS-MARYSVILLE 001/022 RMV VEG |  | NICOLAUS-MARYSVILLE | 001/022 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2022-07-17 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.569821 | 39.1256 | ETL.7690 | 40694249 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119467648 | Not Scheduled | EI MOSS LANDING-SALINAS #1 3/19 RMV VEG |  | MOSS LANDING-SALINAS #1 | 003/019 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2021-07-17 | [9 empty] | South | WSIP | [6 empty] | '-121.741971 | 36.7785 | ETL.2880 | 40872437 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119467670 | Not Scheduled | EI DIXON-VACA #1 6/146 RMV VEG |  | DIXON-VACA #1 | 006/146 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2021-07-17 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.842387 | 38.4265 | ETL.6730 | 40817728 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119467673 | Not Scheduled | EI MOSS LANDING-GRN VLLY #1 5/32 RMV VEG |  | MOSS LANDING-GREEN VALLEY #1 | 005/032 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2021-07-17 | [9 empty] | South | WSIP | [6 empty] | '-121.723863 | 36.85 | ETL.2850 | 40702765 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119467801 | Not Scheduled | EI DIXON-VACA #2 06/147 RMV VEG |  | DIXON-VACA #2 | 006/147 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2021-07-17 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.842682 | 38.4258 | ETL.6740 | 40823482 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119467832 | Not Scheduled | EI MOSS LANDING-SALINAS #1 3/18 RMV VEG |  | MOSS LANDING-SALINAS #1 | 003/018 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2021-07-17 | [9 empty] | South | WSIP | [6 empty] | '-121.743051 | 36.7805 | ETL.2880 | 40861802 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119467922 | Not Scheduled | EI SALINAS-FORT ORD #2 9/009 RMV VEG |  | SALINAS-FORT ORD #2+ (NO FLY) | 009/009 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2021-07-17 | [9 empty] | South | WSIP | [6 empty] | '-121.791116 | 36.644 | ETL.8423 | 42566611 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119468137 | Not Scheduled | EI DIXON-VACA #2 6/146 RMV VEG |  | DIXON-VACA #2 | 006/146 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2021-07-17 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.84265 | 38.4253 | ETL.6740 | 40869021 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119468324 | Not Scheduled | EI DIXON-VACA #2 6/145 RMV VEG |  | DIXON-VACA #2 | 006/145 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2021-07-17 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.843013 | 38.4248 | ETL.6740 | 40874395 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119468843 | Not Scheduled | EI COLGATE-RIO OSO 47/214 RMV VEG |  | COLGATE-RIO OSO | 047/214 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2022-07-17 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.468644 | 38.9895 | ETL.5900 | 40757234 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119468978 | Not Scheduled | EI WATSONVILLE-SALINAS 18/227B RMV VEGN |  | WATSONVILLE-SALINAS | 018/227B | CHS | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2021-07-17 | [9 empty] | South | WSIP | [6 empty] | '-121.59992 | 36.7849 | ETL.8310 | 42564297 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119469036 | Not Scheduled | EI WATSONVILLE-SALINAS 18/227A RMV VEGN |  | WATSONVILLE-SALINAS | 018/227A | CHS | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2021-07-17 | [9 empty] | South | WSIP | [6 empty] | '-121.599892 | 36.7849 | ETL.8310 | 42564296 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119469479 | Not Scheduled | EI DIXON-VACA #2 14/310 RMV VEG |  | DIXON-VACA #2 | 014/310 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2021-07-17 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.761078 | 38.5168 | ETL.6740 | 40875534 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119469540 | Not Scheduled | EI DIXON-VACA #2 16/344 RMV VEG |  | DIXON-VACA #2 | 016/344 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-17 | 2021-07-17 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.761208 | 38.5168 | ETL.6740 | 40868980 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119473700 | Not Scheduled | EI DIXON-VACA #1 0/4 RMV VEG |  | DIXON-VACA #1 | 000/004 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2021-07-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.913267 | 38.4027 | ETL.6730 | 40576443 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119474323 | Not Scheduled | EI SALINAS-FIRESTONE #1 002/056 RMV VEG |  | SALINAS-FIRESTONE #1 (NO FLY) | 002/056 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2022-07-20 | [9 empty] | South | WSIP | [6 empty] | '-121.639963 | 36.6605 | ETL.7900 | 40754432 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119474670 | Not Scheduled | EI NICOLAUS-MARYSVILLE 13/287 RMV VEGN |  | NICOLAUS-MARYSVILLE | 013/287 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2021-07-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.542604 | 38.9714 | ETL.7690 | 44191008 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119474762 | Not Scheduled | EI DIXON-VACA #2 04/116 RMV VEG |  | DIXON-VACA #2 | 004/116 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2021-07-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.858175 | 38.4072 | ETL.6740 | 44837804 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119475263 | Not Scheduled | EI WATSONVILLE-SALINAS 6/086B RMV VEG |  | WATSONVILLE-SALINAS | 006/086B | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2021-07-20 | [9 empty] | South | WSIP | [6 empty] | '-121.675155 | 36.8749 | ETL.8310 | 42564365 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119476377 | Not Scheduled | EI WOODLAND-DAVIS 11/220 RMV VEG |  | WOODLAND-DAVIS | 011/220 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2021-07-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.735057 | 38.5469 | ETL.4210 | 40589307 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119476637 | Not Scheduled | EI RIO OSO-WOODLAND #1 24/150 RMV VEG |  | RIO OSO-WOODLAND #1 | 024/150 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2022-07-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.851746 | 38.7536 | ETL.3460 | 40595425 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119476906 | Not Scheduled | EI WOODLAND-DAVIS 11/217 RMV VEG |  | WOODLAND-DAVIS | 011/217 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2021-07-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.735551 | 38.5487 | ETL.4210 | 40877284 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119477189 | Not Scheduled | EI WOODLAND-DAVIS 11/216 RMV VEG |  | WOODLAND-DAVIS | 011/216 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2021-07-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.735783 | 38.5495 | ETL.4210 | 40813165 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119477265 | Not Scheduled | T2 MORRO BAY-MESA 3/14 ROAD | 44440710 | MORRO BAY-MESA | 003/014 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2022-07-20 |  |  |  | 2021-06-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.810175 | 35.356 | ETL.5290 | 40762302 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119477329 | Not Scheduled | EI WOODLAND-DAVIS 10/207 RMV VEG |  | WOODLAND-DAVIS | 010/207 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2021-07-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.735808 | 38.5553 | ETL.4210 | 40595623 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119477352 | Not Scheduled | EI WATSONVILLE-SALINAS 17/223A RMV VEG |  | WATSONVILLE-SALINAS | 017/223A | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2021-07-20 | [9 empty] | South | WSIP | [6 empty] | '-121.597192 | 36.793 | ETL.8310 | 42564282 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119477454 | Not Scheduled | EI DIXON-VACA #2 A7/164 RMV VEG |  | DIXON-VACA #2 | A007/164 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2021-07-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.915703 | 38.3429 | ETL.6740 | 40823442 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119477549 | Q3 | EI DEL MAR-ATLANTIC #1 2/12 RPR FENCE |  | DEL MAR-ATLANTIC #1 | 002/012 | CHS | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2021-07-20 |  |  | 2021-07-01 | 2021-07-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.247862 | 38.7774 | ETL.1410 | 44191948 | Fence / Gate | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | CH | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119477550 | Not Scheduled | EI RIO OSO-WOODLAND #1 24/151 RMV VEG |  | RIO OSO-WOODLAND #1 | 024/151 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2021-07-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.854044 | 38.7523 | ETL.3460 | 40589179 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119477717 | Not Scheduled | EI DIXON-VACA #1 A6/161 RMV VEG |  | DIXON-VACA #1 | A006/161 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2021-07-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.915556 | 38.3433 | ETL.6730 | 40816621 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119477745 | Not Scheduled | EI DEL MAR-ATLANTIC #1 2/13 RMV VEG |  | DEL MAR-ATLANTIC #1 | 002/013 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2021-07-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.249194 | 38.7758 | ETL.1410 | 44191956 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119477899 | Not Scheduled | EI DEL MAR-ATLANTIC #1 2/14 RMV VEG |  | DEL MAR-ATLANTIC #1 | 002/014 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-20 | 2021-07-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.250862 | 38.7739 | ETL.1410 | 44191961 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119479195 | Q3 | EI WOODLAND-DAVIS 11/214 FENCE |  | WOODLAND-DAVIS | 011/214 | CHR | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 |  |  | 2021-07-01 | 2021-07-01 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.735857 | 38.5506 | ETL.4210 | 40769653 | Road | Encroachment | Remove |  |  |  |  | PEND | LC | TLS | Land | Expense | 931 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | CH | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119479532 | Not Scheduled | EI SALINAS-FIRESTONE #1 A002/081 RMV VEG |  | SALINAS-FIRESTONE #1 (NO FLY) | A002/081 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [9 empty] | South | WSIP | [6 empty] | '-121.629796 | 36.6537 | ETL.7900 | 42561900 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119479630 | Not Scheduled | EI DIXON-VACA #2 2/077 RMV VEGN |  | DIXON-VACA #2 | 002/077 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.877706 | 38.3867 | ETL.6740 | 40599352 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119479671 | Not Scheduled | EI LINCOLN-PLEASANT GROVE 1/41 RMV VEG |  | LINCOLN-PLEASANT GROVE | 001/041 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.303017 | 38.8845 | ETL.7400 | 44262674 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119481152 | Not Scheduled | EI NICOLAUS-WILKINS SLOUGH 1/32 RMV VEG |  | NICOLAUS-WILKINS SLOUGH | 001/032 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.554533 | 38.8956 | ETL.7710 | 44145638 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119481254 | Not Scheduled | EI WOODLAND-DAVIS 9/177 RMV VEG |  | WOODLAND-DAVIS | 009/177 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.730765 | 38.5722 | ETL.4210 | 40669352 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119481723 | Not Scheduled | EI TABLE MTN-VACA -55/220 RMV VEG |  | TABLE MTN-VACA | 055/220 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.875776 | 38.7945 | ETL.6090 | 40596961 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119481853 | Not Scheduled | EI WOODLAND-DAVIS 8/164 RMV VEG |  | WOODLAND-DAVIS | 008/164 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.730614 | 38.5801 | ETL.4210 | 40813159 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119481922 | Not Scheduled | EI TABLE MTN-VACA -54/219 RMV VEG |  | TABLE MTN-VACA | 054/219 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.873264 | 38.7978 | ETL.6090 | 40869187 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119482460 | Not Scheduled | EI WATSONVILLE-SALINAS 6/90 RMV VEG |  | WATSONVILLE-SALINAS | 006/090 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [9 empty] | South | WSIP | [6 empty] | '-121.668593 | 36.8736 | ETL.8310 | 40583296 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119482461 | Not Scheduled | EI MADISON-VACA 48/303 RMV VEGN |  | MADISON-VACA | 048/303 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.98922 | 38.4371 | ETL.2170 | 40653679 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119483722 | Not Scheduled | EI RIO OSO-WOODLAND #1 7/044 RMV VEGN |  | RIO OSO-WOODLAND #1 | 007/044 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.585648 | 38.8875 | ETL.3460 | 40757385 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119483842 | Not Scheduled | EI NICOLAUS-WILKINS SLOUGH 13/243 RMV VE |  | NICOLAUS-WILKINS SLOUGH | 013/243 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.624653 | 38.7723 | ETL.7710 | 40665138 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119483843 | Not Scheduled | EI NICOLAUS-WILKINS SLOUGH 12/239 RMV VE |  | NICOLAUS-WILKINS SLOUGH | 012/239 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.619331 | 38.7814 | ETL.7710 | 40670726 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119484270 | Not Scheduled | T2 EI GOLD HILL #1 6/69 RMV VEG |  | GOLD HILL #1 | 006/069 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.037737 | 38.6574 | ETL.6950 | 44194014 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119484844 | Not Scheduled | DI RIO OSO-WOODLAND #1 17/102 RMV VEG |  | RIO OSO-WOODLAND #1 | 017/102 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2022-07-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.738632 | 38.8122 | ETL.3460 | 40673200 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119485055 | Not Scheduled | EI COALINGA #1-SAN MIGUEL 4/075 RMV VEG |  | COALINGA #1-SAN MIGUEL | 004/075 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | South | WSIP | [6 empty] | '-120.404123 | 36.103 | ETL.8580 | 40806614 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119485068 | Not Scheduled | BORDEN-COPPERMINE :08/03 LC STRW | 31509258 | BORDEN-COPPERMINE | :018/013 | 92T | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2020-07-22 | 2021-07-22 | [6 empty] | 92T/IBT |  |  | South | WSIP | [6 empty] | '-119.970065 | 36.9231 | ETL.8500 | 44843329 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND hold dcpr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 372 | Fresno |  | Y - 8 |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 92 | Not Scheduled |  |  | 2020-08-06 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 119485161 | Not Scheduled | EI RIO OSO-WOODLAND #1 4/28 RMV VEG |  | RIO OSO-WOODLAND #1 | 004/028 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.547713 | 38.9062 | ETL.3460 | 40867010 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119485320 | Not Scheduled | EI WOODLAND-DAVIS 11/213 RMV VEG |  | WOODLAND-DAVIS | 011/213 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.735853 | 38.5513 | ETL.4210 | 40755905 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119485336 | Not Scheduled | EI BRIGHTON-DAVIS 00/008 RMV VEGN |  | BRIGHTON-DAVIS | 000/008 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.408775 | 38.5354 | ETL.1140 | 40862294 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119485404 | Q4 | T3 EI DRUM-HIGGINS 10/099 RMV DEBRIS |  | DRUM-HIGGINS | 010/099 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2022-07-22 |  |  | 2021-12-31 | 2021-12-31 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.903104 | 39.1797 | ETL.4393 | 44172246 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | CH | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119485417 | Not Scheduled | EI RIO OSO-WOODLAND #1 5/29 RMV VEG |  | RIO OSO-WOODLAND #1 | 005/029 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.550093 | 38.905 | ETL.3460 | 40866412 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119485614 | Not Scheduled | EI NICOLAUS-WILKINS SLOUGH 1/35 RMV VEG |  | NICOLAUS-WILKINS SLOUGH | 001/035 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.557325 | 38.8955 | ETL.7710 | 44145641 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119485811 | Not Scheduled | EI RIO OSO-WOODLAND #1 5/32 RMV VEG |  | RIO OSO-WOODLAND #1 | 005/032 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.557236 | 38.9015 | ETL.3460 | 40683656 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119486217 | Not Scheduled | EI RIO OSO-WOODLAND #1 2/14 RMV VEG |  | RIO OSO-WOODLAND #1 | 002/014 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.514256 | 38.9183 | ETL.3460 | 40757379 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119486464 | Not Scheduled | EI ALMENDRA JCT-NICOLAUS 9/194 RMV VEG |  | ALMENDRA JCT-NICOLAUS | 009/194 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.68976 | 39.0134 | ETL.6150 | 40817683 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119486493 | Not Scheduled | EI RIO OSO-WOODLAND #1 2/13 RMV VEG |  | RIO OSO-WOODLAND #1 | 002/013 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.510143 | 38.9198 | ETL.3460 | 40655235 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119486512 | Not Scheduled | EI WOODLAND-DAVIS 11/209 RMV VEG |  | WOODLAND-DAVIS | 011/209 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.735829 | 38.554 | ETL.4210 | 40595641 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119487205 | Not Scheduled | EI WOODLAND-DAVIS 1/31 RMV VEG |  | WOODLAND-DAVIS | 001/031 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.737566 | 38.6808 | ETL.4210 | 40616512 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119487412 | Not Scheduled | EI DRUM-GRASS VALLEY-WEIMAR B18/413 RMV |  | DRUM-GRASS VALLEY-WEIMAR | B018/413 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-120.973891 | 39.149 | ETL.6760 | 40766688 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119487911 | Not Scheduled | EI TABLE MTN-VACA 51/206 RMV VEG |  | TABLE MTN-VACA | 051/206 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.853129 | 38.8395 | ETL.6090 | 40818838 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119488051 | Not Scheduled | EI GREEN VALLEY-WATSONVILLE 2/057 RMV VE |  | GREEN VALLEY-WATSONVILLE | 002/057 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | South | WSIP | [6 empty] | '-121.777018 | 36.9177 | ETL.6970 | 40593995 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119488491 | Not Scheduled | EI T3NT MORRO BY-SLR SS #1 24/105 RPR RO | 44598153 | MORRO BAY-SOLAR SW STA #1 | 024/105 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2022-07-22 |  |  |  | 2022-03-01 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.427746 | 35.3668 | ETL.5300 | 40753269 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119488824 | Not Scheduled | EI TABLE MTN-VACA 51/205 RMV VEG |  | TABLE MTN-VACA | 051/205 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.853194 | 38.8425 | ETL.6090 | 40762360 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119488891 | Not Scheduled | EI MADISON-VACA 05/061 RMV VEG |  | MADISON-VACA | 005/061 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.977636 | 38.6078 | ETL.2170 | 40871339 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119488895 | Not Scheduled | EI MADISON-VACA 06/068 RMV VEG |  | MADISON-VACA | 006/068 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.988199 | 38.5948 | ETL.2170 | 40762429 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119488898 | Not Scheduled | EI MADISON-VACA - 115 kV_005/062 RMV VEG |  | MADISON-VACA | 005/062 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2022-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.979146 | 38.6059 | ETL.2170 | 40866706 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119488899 | Not Scheduled | EI MADISON-VACA 4/060 RMV VEG |  | MADISON-VACA | 004/060 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.976109 | 38.6097 | ETL.2170 | 40814904 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119488902 | Not Scheduled | EI MADISON-VACA 05/066 RMV VEG |  | MADISON-VACA | 005/066 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.985183 | 38.5985 | ETL.2170 | 40653672 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119488975 | Not Scheduled | EI TABLE MTN-VACA 51/204 RMV VEG |  | TABLE MTN-VACA | 051/204 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.853138 | 38.8464 | ETL.6090 | 40746610 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119489485 | Not Scheduled | EI NICOLAUS-WILKINS SLOUGH 14/252 RMV VE |  | NICOLAUS-WILKINS SLOUGH | 014/252 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.644512 | 38.7561 | ETL.7710 | 40589702 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119489486 | Not Scheduled | EI NICOLAUS-WILKINS SLOUGH 13/244 RMV VE |  | NICOLAUS-WILKINS SLOUGH | 013/244 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.625816 | 38.7703 | ETL.7710 | 40767758 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119489487 | Not Scheduled | EI NICOLAUS-WILKINS SLOUGH 13/245 RMV VE |  | NICOLAUS-WILKINS SLOUGH | 013/245 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.626906 | 38.7684 | ETL.7710 | 40756339 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119489488 | Not Scheduled | EI NICOLAUS-WILKINS SLOUGH 14/253 RMV VE |  | NICOLAUS-WILKINS SLOUGH | 014/253 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.647156 | 38.7546 | ETL.7710 | 40694490 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119489491 | Not Scheduled | EI NICOLAUS-WILKINS SLOUGH 15/256 RMV VE |  | NICOLAUS-WILKINS SLOUGH | 015/256 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.656308 | 38.7494 | ETL.7710 | 40596304 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119489492 | Not Scheduled | EI NICOLAUS-WILKINS SLOUGH 14/250 RMV VE |  | NICOLAUS-WILKINS SLOUGH | 014/250 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.638381 | 38.7595 | ETL.7710 | 40767760 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119489493 | Not Scheduled | EI NICOLAUS-WILKINS SLOUGH 14/251 RMV VE |  | NICOLAUS-WILKINS SLOUGH | 014/251 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.64206 | 38.7575 | ETL.7710 | 40611960 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119489621 | Not Scheduled | DI NICOLAUS-CTLT JCT 63/469 RMV VEG |  | NICOLAUS-CATLETT JCT | 063/469 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2022-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.515021 | 38.8681 | ETL.7680 | 40908467 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119489714 | Not Scheduled | T2 EI GOLD HILL #1 7/092 RMV VEG |  | GOLD HILL #1 | 007/092 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-121.013819 | 38.6556 | ETL.6950 | 40908761 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119491616 | Not Scheduled | EI TABLE MTN-VACA 50/200 RMV VEG |  | TABLE MTN-VACA | 050/200 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.852926 | 38.8614 | ETL.6090 | 40596958 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119491674 | Not Scheduled | EI TABLE MTN-TESLA 65/261 RMV VEG |  | TABLE MTN-TESLA | 065/261 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-22 | 2021-07-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.667248 | 38.6383 | ETL.6080 | 40597210 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119491762 | Not Scheduled | EI CRAZY HORSE CNYN-SN BNT 30/195 RMV VE |  | SAN BENITO TAP | 030/195 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | South | WSIP | [6 empty] | '-121.562707 | 36.8706 | ETL.2152 | 40760898 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119491819 | Not Scheduled | EI TABLE MTN-VACA 49/199 RMV VEG |  | TABLE MTN-VACA | 049/199 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.852883 | 38.8652 | ETL.6090 | 40870556 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119491906 | Not Scheduled | EI TABLE MTN-VACA 49/198 RMV VEG |  | TABLE MTN-VACA | 049/198 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.852873 | 38.869 | ETL.6090 | 40866484 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119492264 | Not Scheduled | EI RIO OSO-WOODLAND #1 09/057 RMV VEG |  | RIO OSO-WOODLAND #1 | 009/057 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.619082 | 38.8711 | ETL.3460 | 40819074 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119492318 | Not Scheduled | EI TABLE MTN-VACA 48/194 RMV VEG |  | TABLE MTN-VACA | 048/194 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.852871 | 38.8834 | ETL.6090 | 40756830 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119492384 | Not Scheduled | EI MADISON-VACA 06/070 RMV VEG |  | MADISON-VACA | 006/070 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.991209 | 38.5911 | ETL.2170 | 40820696 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119492391 | Not Scheduled | EI MADISON-VACA 38/237 RMV VEG |  | MADISON-VACA | 038/237 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.992637 | 38.5894 | ETL.2170 | 41162711 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119492635 | Not Scheduled | EI BRIGHTON-DAVIS-6/051 RMV VEG |  | BRIGHTON-DAVIS | 006/051 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.442843 | 38.4747 | ETL.1140 | 40586229 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2020-11-06 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119492712 | Not Scheduled | EI TABLE MTN-VACA 43/171 RMV VEG |  | TABLE MTN-VACA | 043/171 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.847977 | 38.963 | ETL.6090 | 40593569 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119492994 | Not Scheduled | EI WOODLAND-DAVIS 10/202 RMV VEG |  | WOODLAND-DAVIS | 010/202 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.735762 | 38.5587 | ETL.4210 | 40755812 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119493260 | Not Scheduled | EI WOODLAND-DAVIS 10/206 RMV VEG |  | WOODLAND-DAVIS | 010/206 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.735801 | 38.556 | ETL.4210 | 40865105 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119493414 | Not Scheduled | EI SAN LUIS OBISPO-SNT MRI 25/131 RMV VE |  | SAN LUIS OBISPO-SANTA MARIA | 025/131 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | South | WSIP | [6 empty] | '-120.444485 | 34.9509 | ETL.3540 | 42573681 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119493466 | Not Scheduled | EI WOODLAND-DAVIS 10/208 RMV VEG |  | WOODLAND-DAVIS | 010/208 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.735822 | 38.5546 | ETL.4210 | 40601368 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119493594 | Not Scheduled | EI MADISON-VACA 38/239 RMV VEG |  | MADISON-VACA | 038/239 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.992737 | 38.5851 | ETL.2170 | 40864995 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119493616 | Not Scheduled | EI MADISON-VACA 8/240 RMV VEG |  | MADISON-VACA | 038/240 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.992788 | 38.5829 | ETL.2170 | 40595436 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119493915 | Not Scheduled | EI ALMENDRA JCT-NICOLAUS 15/325 RMV VEG |  | ALMENDRA JCT-NICOLAUS | 015/325 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.63496 | 38.9695 | ETL.6150 | 40760482 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119494094 | Not Scheduled | EI RIO OSO-WOODLAND #1 10/059 RMV VEG |  | RIO OSO-WOODLAND #1 | 010/059 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.62681 | 38.8673 | ETL.3460 | 40864982 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119494114 | Not Scheduled | EI WOODLAND-DAVIS 10/203 RMV VEG |  | WOODLAND-DAVIS | 010/203 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.735771 | 38.558 | ETL.4210 | 40827205 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119494325 | Not Scheduled | EI TABLE MTN-VACA 40/160 RMV VEG |  | TABLE MTN-VACA | 040/160 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.847293 | 39.0044 | ETL.6090 | 40596952 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119494622 | Not Scheduled | EI RIO OSO-WOODLAND #1 10/061 RMV VEG |  | RIO OSO-WOODLAND #1 | 010/061 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.63335 | 38.8641 | ETL.3460 | 40589171 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119494799 | Not Scheduled | EI TABLE MTN-VACA 40/162 RMV VEG |  | TABLE MTN-VACA | 040/162 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.847351 | 38.9979 | ETL.6090 | 40683559 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119494825 | Not Scheduled | EI RIO OSO-WOODLAND #1 10/062 RMV VEG |  | RIO OSO-WOODLAND #1 | 010/062 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.636619 | 38.8625 | ETL.3460 | 40669013 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119495035 | Not Scheduled | EI TABLE MTN-VACA 41/164 RMV VEG |  | TABLE MTN-VACA | 041/164 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.847458 | 38.9902 | ETL.6090 | 40756826 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119495101 | Not Scheduled | EI TABLE MTN-VACA 41/165 RMV VEG |  | TABLE MTN-VACA | 041/165 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.847532 | 38.9863 | ETL.6090 | 40756755 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119495174 | Not Scheduled | EI RIO OSO-WOODLAND #1 11/63 RMV VEG |  | RIO OSO-WOODLAND #1 | 011/063 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.639444 | 38.8611 | ETL.3460 | 40653660 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119495176 | Not Scheduled | EI RIO OSO-WOODLAND #1 11/063 RMV VEG |  | RIO OSO-WOODLAND #1 | 011/063 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.639444 | 38.8611 | ETL.3460 | 40653660 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119495430 | Not Scheduled | EI RIO OSO-WOODLAND #1 11/064 RMV VEG |  | RIO OSO-WOODLAND #1 | 011/064 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.642711 | 38.8595 | ETL.3460 | 40762531 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119495542 | Not Scheduled | EI WOODLAND-DAVIS 11/211 RMV VEG |  | WOODLAND-DAVIS | 011/211 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.73584 | 38.5527 | ETL.4210 | 40700626 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119495580 | Not Scheduled | EI NICOLAUS-WILKINS SLOUGH 15/259 RMV VE |  | NICOLAUS-WILKINS SLOUGH | 015/259 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.664386 | 38.7448 | ETL.7710 | 40654305 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119495583 | Not Scheduled | EI NICOLAUS-WILKINS SLOUGH 15/258 RMV VE |  | NICOLAUS-WILKINS SLOUGH | 015/258 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.661988 | 38.7462 | ETL.7710 | 40694519 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119495691 | Not Scheduled | EI TEMBLOR-SAN LUIS OBISPO 10/63 RMV VEG |  | TEMBLOR-SAN LUIS OBISPO | 010/063 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | South | WSIP | [6 empty] | '-119.867571 | 35.3683 | ETL.3960 | 40906933 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119495893 | Not Scheduled | EI DRUM-RIO OSO #1 39/281 RMV VEG |  | DRUM-RIO OSO #1 | 039/281 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.400045 | 38.9784 | ETL.1420 | 40596791 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119495902 | Not Scheduled | EI DRUM-RIO OSO #1 39/280 RMV VEG |  | DRUM-RIO OSO #1 | 039/280 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.397659 | 38.9796 | ETL.1420 | 40600928 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119495911 | Not Scheduled | EI DRUM-RIO OSO #1 39/278 RMV VEG |  | DRUM-RIO OSO #1 | 039/278 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.392885 | 38.9819 | ETL.1420 | 40858249 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119497784 | Not Scheduled | EI BRIGHTON-DAVIS-07/057 RMV VEG |  | BRIGHTON-DAVIS | 007/057 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.458529 | 38.4747 | ETL.1140 | 40809781 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2020-11-06 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119498051 | Not Scheduled | EI ALMENDRA JCT-NICOLAUS 14/291 RMV VEG |  | ALMENDRA JCT-NICOLAUS | 014/291 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.650594 | 38.9814 | ETL.6150 | 44185123 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119498072 | Not Scheduled | EI MADISON-VACA 49/305 RMV VEGN |  | MADISON-VACA | 049/305 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.988589 | 38.4329 | ETL.2170 | 40762276 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119498214 | Not Scheduled | EI NICOLAUS-WILKINS SLOUGH 4/78 RMV VEG |  | NICOLAUS-WILKINS SLOUGH | 004/078 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.589818 | 38.8792 | ETL.7710 | 44145657 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119498484 | Not Scheduled | EI RIO OSO-WOODLAND #1 11/66 RMV VEG |  | RIO OSO-WOODLAND #1 | 011/066 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.649871 | 38.856 | ETL.3460 | 40813807 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119498497 | Not Scheduled | EI BRIGHTON-GRAND ISLAND #1 8/73 RMV VEG |  | BRIGHTON-GRAND ISLAND #1 | 008/073 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.444714 | 38.4251 | ETL.1150 | 40654213 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119498829 | Not Scheduled | EI BRIGHTON-GRAND ISLAND #1 4/36 RMV VEG |  | BRIGHTON-GRAND ISLAND #1 | 004/036 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.408568 | 38.4835 | ETL.1150 | 40811687 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119498908 | Not Scheduled | EI ALMENDRA JCT-NICOLAUS 16/344 RMV VEG |  | ALMENDRA JCT-NICOLAUS | 016/344 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.634888 | 38.9541 | ETL.6150 | 40760486 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119498997 | Not Scheduled | EI CORTINA #4 00/015 RMV VEG |  | CORTINA #4 | 000/015 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.221735 | 39.1336 | ETL.6610 | 40758224 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119498999 | Not Scheduled | EI CORTINA #4 0/14 RMV VEG |  | CORTINA #4 | 000/014 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.221901 | 39.1325 | ETL.6610 | 40758373 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119499088 | Not Scheduled | EI BRIGHTON-GRAND ISLAND #1 24/183 RMV V |  | BRIGHTON-GRAND ISLAND #1 | 024/183 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.58696 | 38.2402 | ETL.1150 | 40654228 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119499089 | Not Scheduled | EI BRIGHTON-GRAND ISLAND #1 24/185 RMV V |  | BRIGHTON-GRAND ISLAND #1 | 024/185 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.58839 | 38.2364 | ETL.1150 | 40756245 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119499144 | Not Scheduled | EI BRIGHTON-GRAND ISLAND #1 5/47 RMV VEG |  | BRIGHTON-GRAND ISLAND #1 | 005/047 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.408943 | 38.4656 | ETL.1150 | 40819134 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119499170 | Not Scheduled | EI RIO OSO-WOODLAND #1 12/068 RMV VEG |  | RIO OSO-WOODLAND #1 | 012/068 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.655691 | 38.8531 | ETL.3460 | 40865477 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119500209 | Not Scheduled | EI RIO OSO-WOODLAND #1 12/069 RMV VEG |  | RIO OSO-WOODLAND #1 | 012/069 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.658066 | 38.8519 | ETL.3460 | 40870483 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119500506 | Not Scheduled | EI BRIGHTON-GRAND ISLAND #1 9/76 RMV VEG |  | BRIGHTON-GRAND ISLAND #1 | 009/076 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.448923 | 38.4204 | ETL.1150 | 40811691 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119503694 | Not Scheduled | EI TABLE MTN-TESLA 94/369 RMV VEG |  | TABLE MTN-TESLA | 094/369 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.730164 | 38.2451 | ETL.6080 | 40870469 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119504619 | Not Scheduled | EI RIO OSO-WOODLAND #1 12/72 RMV VEG |  | RIO OSO-WOODLAND #1 | 012/072 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.665197 | 38.8484 | ETL.3460 | 40669018 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119504856 | Not Scheduled | EI RIO OSO-WOODLAND #1 13/75 RMV VEG |  | RIO OSO-WOODLAND #1 | 013/075 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.672326 | 38.8449 | ETL.3460 | 40755641 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119505017 | Q4 | T3 DRUM-HIGGINS 005/060 REPLACE CULVERT | 31510498 | DRUM-HIGGINS | 005/060 | 71Y | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2022-07-23 |  |  | 2021-12-31 | 2021-12-31 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.842668 | 39.2033 | ETL.4393 | 40595827 | Road | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | 71 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119505611 | Not Scheduled | EI RIO OSO-WOODLAND #1 12/73 RMV VEG |  | RIO OSO-WOODLAND #1 | 012/073 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.667573 | 38.8473 | ETL.3460 | 40660072 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119508875 | Not Scheduled | DI RIO OSO-WOODLAND #1 3/20 RMV VEG |  | RIO OSO-WOODLAND #1 | 003/020 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2022-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.530936 | 38.9142 | ETL.3460 | 40608846 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119509394 | Not Scheduled | DI RIO OSO-WOODLAND #1 10/58 RMV VEG |  | RIO OSO-WOODLAND #1 | 010/058 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.623538 | 38.8689 | ETL.3460 | 40865475 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119509544 | Not Scheduled | T2 DI EXQR-INN FLT-YMT 28/139 RMV VEG |  | EXCHEQUER-YOSEMITE | 028/139 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-119.914439 | 37.6514 | ETL.8650 | 44420177 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2020-08-14 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119510526 | Not Scheduled | DI RIO OSO-WOODLAND #1 17/100 RMV VEG |  | RIO OSO-WOODLAND #1 | 017/100 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-24 | 2021-07-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.73389 | 38.8146 | ETL.3460 | 40608764 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119510721 | Not Scheduled | EI RIO OSO-WOODLAND #1 14/082 RMV VEG |  | RIO OSO-WOODLAND #1 | 014/082 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.688747 | 38.8368 | ETL.3460 | 40673212 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119511035 | Not Scheduled | EI RIO OSO-WOODLAND #1 14/083 RMV VEGN |  | RIO OSO-WOODLAND #1 | 014/083 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.691591 | 38.8354 | ETL.3460 | 40653662 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119511248 | Not Scheduled | EI MIDWAY-TUPMAN-RIO BRAVO- A13/91 RMV V |  | MIDWAY-TUPMAN-RIO BRAVO-RENFRO | A013/091 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | South | WSIP | [6 empty] | '-119.25628 | 35.4227 | ETL.2600 | 40808044 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119511397 | Not Scheduled | EI BRIGHTON-GRAND ISLAND #1 21/167 RMV V |  | BRIGHTON-GRAND ISLAND #1 | 021/167 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.574929 | 38.2723 | ETL.1150 | 40811052 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119511413 | Not Scheduled | EI BRIGHTON-GRAND ISLAND #1 21/163 RMV V |  | BRIGHTON-GRAND ISLAND #1 | 021/163 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.572697 | 38.2783 | ETL.1150 | 40654224 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119511415 | Not Scheduled | EI BRIGHTON-GRAND ISLAND #1 21/164 RMV V |  | BRIGHTON-GRAND ISLAND #1 | 021/164 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.572844 | 38.2779 | ETL.1150 | 40753461 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119511416 | Not Scheduled | EI BRIGHTON-GRAND ISLAND #1 21/166 RMV V |  | BRIGHTON-GRAND ISLAND #1 | 021/166 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.574184 | 38.2743 | ETL.1150 | 40820326 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119511460 | Not Scheduled | EI CORTINA #4 A7/116 RMV VEG |  | CORTINA #4 | A007/116 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.156036 | 39.1681 | ETL.6610 | 40742678 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119511536 | Not Scheduled | EI RIO OSO-WOODLAND #1 14/084 RMV VEG |  | RIO OSO-WOODLAND #1 | 014/084 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2022-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.693966 | 38.8343 | ETL.3460 | 40755743 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119511641 | Not Scheduled | EI TABLE MTN-TESLA 55/220 RMV VEG |  | TABLE MTN-TESLA | 055/220 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.682891 | 38.7878 | ETL.6080 | 40605079 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119511827 | Not Scheduled | EI MIDWAY-TUPMAN-R BRV-RNFR A13/94 RMV V |  | MIDWAY-TUPMAN-RIO BRAVO-RENFRO | A013/094 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | South | WSIP | [6 empty] | '-119.256392 | 35.4268 | ETL.2600 | 40860322 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119511872 | Not Scheduled | DI RIO OSO-WOODLAND #1 10/60 RMV VEG |  | RIO OSO-WOODLAND #1 | 010/060 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.63008 | 38.8657 | ETL.3460 | 40595410 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119512066 | Not Scheduled | EI RIO OSO-WOODLAND #1 14/085 RMV VEG |  | RIO OSO-WOODLAND #1 | 014/085 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2022-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.696342 | 38.8331 | ETL.3460 | 40757726 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119512282 | Not Scheduled | EI ALMENDRA JCT-NICOLAUS 22/449 RMV VEG |  | ALMENDRA JCT-NICOLAUS | 022/449 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.584614 | 38.9104 | ETL.6150 | 40664000 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119512495 | Not Scheduled | DI RIO OSO-BRIGHTON 21/147 RMV VEG |  | RIO OSO-BRIGHTON | 021/147 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.420799 | 38.6267 | ETL.5600 | 40818725 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119512535 | Not Scheduled | EI RIO OSO-WOODLAND #1 14/086 RMV VEGN |  | RIO OSO-WOODLAND #1 | 014/086 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.698717 | 38.8319 | ETL.3460 | 40813809 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119513010 | Not Scheduled | EI BRIGHTON-DAVIS 14/104 RMV VEG |  | BRIGHTON-DAVIS | 014/104 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.576882 | 38.4743 | ETL.1140 | 40746923 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119514574 | Not Scheduled | EI BRIGHTON-DAVIS 13/101 RMV DEBRIS |  | BRIGHTON-DAVIS | 013/101 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2022-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.569038 | 38.4741 | ETL.1140 | 40586235 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119514671 | Not Scheduled | EI DAIRYLAND-MENDOTA 19/003 RMV VEGN |  | DAIRYLAND-MENDOTA | 019/003 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | South | WSIP | [6 empty] | '-120.424477 | 36.8377 | ETL.1360 | 40645110 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119514878 | Not Scheduled | EI NICOLAUS-CATLETT JCT 60/446 RMV VEG |  | NICOLAUS-CATLETT JCT | 060/446 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.523521 | 38.9128 | ETL.7680 | 40908444 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119514880 | Not Scheduled | EI NICOLAUS-CATLETT JCT 61/447 RMV VEG |  | NICOLAUS-CATLETT JCT | 061/447 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.523177 | 38.9109 | ETL.7680 | 40908445 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119514890 | Not Scheduled | EI NICOLAUS-CATLETT JCT 61/451 RMV VEG |  | NICOLAUS-CATLETT JCT | 061/451 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.521672 | 38.9027 | ETL.7680 | 40908449 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119514891 | Not Scheduled | EI NICOLAUS-CATLETT JCT 61/449 RMV VEG |  | NICOLAUS-CATLETT JCT | 061/449 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-27 | 2021-07-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.522333 | 38.9068 | ETL.7680 | 40908447 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119514998 | Not Scheduled | EI BRIGHTON-DAVIS 13/098 RMV VEG |  | BRIGHTON-DAVIS | 013/098 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.561291 | 38.4729 | ETL.1140 | 44163642 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119515130 | Not Scheduled | EI BRIGHTON-DAVIS 28/325 RMV VEGN |  | BRIGHTON-DAVIS | 028/325 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.732233 | 38.5452 | ETL.1140 | 40608048 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119515606 | Not Scheduled | EI RIO OSO-WOODLAND #1 9/059 RMV VEG |  | RIO OSO-WOODLAND #1 | ;009/059 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.746878 | 38.6904 | ETL.3460 | 40876522 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119515609 | Not Scheduled | EI DEL MONTE-FORT ORD #1 1/39 RMV VEG |  | DEL MONTE-FORT ORD #1 (NO FLY) | 001/039 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | South | WSIP | [6 empty] | '-121.827303 | 36.6019 | ETL.8400 | 44274402 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119516017 | Not Scheduled | EI KERN-MAGUNDEN-WITCO 11/64 RMV VEG |  | KERN-MAGUNDEN-WITCO | 011/064 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | South | WSIP | [6 empty] | '-118.924418 | 35.4017 | ETL.1970 | 40575360 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119516329 | Not Scheduled | EI ALMENDRA JCT-NICLS 20/423 RMV VEGN |  | ALMENDRA JCT-NICOLAUS | 020/423 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.606889 | 38.9178 | ETL.6150 | 40812883 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119516498 | Not Scheduled | EI KERN-MAGUNDEN-WITCO 10/062 RMV VEG |  | KERN-MAGUNDEN-WITCO | 010/062 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | South | WSIP | [6 empty] | '-118.929729 | 35.4067 | ETL.1970 | 40575361 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119516535 | Not Scheduled | EI ALMENDRA JCT-NICOLAUS 20/420 RMV VEGN |  | ALMENDRA JCT-NICOLAUS | 020/420 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.60647 | 38.9201 | ETL.6150 | 40658355 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119516542 | Not Scheduled | DI RIO OSO-WOODLAND #1 18/111 RMV VEG |  | RIO OSO-WOODLAND #1 | 018/111 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-23 | 2021-07-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.761293 | 38.801 | ETL.3460 | 40589176 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119516587 | Not Scheduled | EI RIO OSO-BRIGHTON 26/179 RMV VEG |  | RIO OSO-BRIGHTON | 026/179 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.408084 | 38.5584 | ETL.5600 | 40864814 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119516593 | Not Scheduled | EI DEL MONTE-FORT ORD #1 5/69 RMV VEG |  | DEL MONTE-FORT ORD #1 (NO FLY) | 005/069 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-21 | 2021-07-21 | [9 empty] | South | WSIP | [6 empty] | '-121.80365 | 36.6441 | ETL.8400 | 40812825 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119516909 | Not Scheduled | EI RIO OSO-BRIGHTON 26/178 RMV VEGN |  | RIO OSO-BRIGHTON | 026/178 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.408026 | 38.5614 | ETL.5600 | 40865304 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119517235 | Not Scheduled | EI RIO OSO-BRIGHTON 25/176 RMV VEG |  | RIO OSO-BRIGHTON | 025/176 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.407946 | 38.5656 | ETL.5600 | 40813644 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119517504 | Not Scheduled | EI RIO OSO-WOODLAND #1 16/098 RMV VEG |  | RIO OSO-WOODLAND #1 | 016/098 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.72914 | 38.8169 | ETL.3460 | 40865481 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119517648 | Not Scheduled | EI RIO OSO-WOODLAND #1 5/037 RMV VEG |  | RIO OSO-WOODLAND #1 | 005/037 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.754719 | 38.7261 | ETL.3460 | 40813036 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119517899 | Not Scheduled | EI KERN-MAGUNDEN-WITCO 9/055 RMV VEG |  | KERN-MAGUNDEN-WITCO | 009/055 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | South | WSIP | [6 empty] | '-118.953538 | 35.4166 | ETL.1970 | 40575367 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119518582 | Not Scheduled | EI RIO OSO-WOODLAND #1 16/099 RMV VEG |  | RIO OSO-WOODLAND #1 | 016/099 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.731515 | 38.8157 | ETL.3460 | 40866715 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119518708 | Not Scheduled | EI NICOLAUS-WILKINS SLGH 27/485 RMV VEGN |  | NICOLAUS-WILKINS SLOUGH | 027/485 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.778267 | 38.8289 | ETL.7710 | 40694343 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119518988 | Not Scheduled | EI TABLE MTN-TESLA 40/159 RMV VEGN |  | TABLE MTN-TESLA | 040/159 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.715885 | 38.9979 | ETL.6080 | 40869294 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119519118 | Not Scheduled | EI BRIGHTON-DAVIS 27/316 RMV VEG |  | BRIGHTON-DAVIS | 027/316 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.725024 | 38.5469 | ETL.1140 | 40608740 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2020-11-06 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119519136 | Not Scheduled | EI BRIGHTON-DAVIS 28/321 RMV VEG |  | BRIGHTON-DAVIS | 028/321 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.729406 | 38.5459 | ETL.1140 | 40813638 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119519141 | Not Scheduled | EI BRIGHTON-DAVIS 28/324 RMV VEGN |  | BRIGHTON-DAVIS | 028/324 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-28 | 2021-07-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.731303 | 38.5454 | ETL.1140 | 40870451 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119520753 | Not Scheduled | EI SMARTVILLE-NICOLAUS #2 15/322 RMV VEG |  | SMARTVILLE-NICOLAUS #2 | 015/322 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.42239 | 39.0083 | ETL.8000 | 40911475 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119520768 | Not Scheduled | EI ATLANTIC-GOLD HILL 028/121 RMV VEG |  | ATLANTIC-GOLD HILL | 028/121 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2022-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.133928 | 38.6627 | ETL.4330 | 40585247 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119520780 | Not Scheduled | EI ATLANTIC-GOLD HILL 028/122 RMV VEG |  | ATLANTIC-GOLD HILL | 028/122 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2022-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.134724 | 38.659 | ETL.4330 | 40657980 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119520863 | Not Scheduled | EI RIO OSO-WOODLAND #1 17/103 RMV VEG |  | RIO OSO-WOODLAND #1 | 017/103 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.741007 | 38.811 | ETL.3460 | 40653664 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119520880 | Not Scheduled | EI BRIGHTN-GRND ISLAND #1 9/78 RMV VEG |  | BRIGHTON-GRAND ISLAND #1 | 009/078 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.451915 | 38.417 | ETL.1150 | 40866038 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119520915 | Not Scheduled | EI ATLANTIC-GOLD HILL 028/120 RMV VEG |  | ATLANTIC-GOLD HILL | 028/120 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2022-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.134933 | 38.666 | ETL.4330 | 40588520 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119521035 | Not Scheduled | EI BRIGHTON-GRND ISLND #1 19/148 RMV VEG |  | BRIGHTON-GRAND ISLAND #1 | 019/148 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.551382 | 38.3053 | ETL.1150 | 40863527 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119521286 | Not Scheduled | EI RIO OSO-WOODLAND #1 17/105 RMV VEG |  | RIO OSO-WOODLAND #1 | 017/105 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.745089 | 38.809 | ETL.3460 | 40755643 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119521599 | Not Scheduled | EI RIO OSO-WOODLAND #1 17/106 RMV VEG |  | RIO OSO-WOODLAND #1 | 017/106 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.747846 | 38.8077 | ETL.3460 | 40813814 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119521870 | Not Scheduled | EI RIO OSO-WOODLAND #1 18/107 RMV VEG |  | RIO OSO-WOODLAND #1 | 018/107 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.75022 | 38.8065 | ETL.3460 | 40813010 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119521993 | Not Scheduled | EI ATLANTIC-GOLD HILL 17/074 RMV VEG |  | ATLANTIC-GOLD HILL | 017/074 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.262027 | 38.7646 | ETL.4330 | 40753657 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119522275 | Not Scheduled | EI COLUSA JCT #1 1/28 RMV VEG |  | COLUSA JCT #1 | 001/028 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.977478 | 39.1764 | ETL.8390 | 40766028 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119522307 | Not Scheduled | EI SMART-NICOLAUS #2 14/294 RMV VEG |  | SMARTVILLE-NICOLAUS #2 | 014/294 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.408498 | 39.02 | ETL.8000 | 40912215 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119522396 | Not Scheduled | EI BRIGHTON-DAVIS 11/85 RMV VEG |  | BRIGHTON-DAVIS | 011/085 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.53148 | 38.4651 | ETL.1140 | 40746912 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119522397 | Not Scheduled | EI BRIGHTON-DAVIS 11/82 RMV VEG |  | BRIGHTON-DAVIS | 011/082 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.524461 | 38.4652 | ETL.1140 | 40682070 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119522398 | Not Scheduled | EI BRIGHTON-DAVIS 10/75 RMV VEG |  | BRIGHTON-DAVIS | 010/075 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.505837 | 38.4668 | ETL.1140 | 40764540 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119522481 | Not Scheduled | EI BRIGHTON-DAVIS 10/79 RMV VEG |  | BRIGHTON-DAVIS | 010/079 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.516981 | 38.4644 | ETL.1140 | 40862046 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119522483 | Not Scheduled | EI BRIGHTON-DAVIS 11/83 RMV VEG |  | BRIGHTON-DAVIS | 011/083 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.526829 | 38.4652 | ETL.1140 | 40650181 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119522805 | Not Scheduled | EI GOLD HILL-BLLTA-LCKFRD 35/213 RMV VEG |  | GOLD HILL-BELLOTA-LOCKEFORD | 035/213 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.135185 | 38.652 | ETL.1690 | 40659244 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119523358 | Not Scheduled | EI RIO OSO-BRIGHTON 23/162 RMV VEG |  | RIO OSO-BRIGHTON | 023/162 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.412943 | 38.5954 | ETL.5600 | 40668596 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119523712 | Not Scheduled | EI RIO BRAVO-KERN OIL 15/005A RMV VEG |  | RIO BRAVO-KERN OIL (IDLE) | 015/005A | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | South | WSIP | [6 empty] | '-119.198678 | 35.442 | ETL.1922 | 43207477 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119524215 | Not Scheduled | EI LAURELES-OTTER 11/0 RMV VEG |  | LAURELES-OTTER | 011/000 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | South | WSIP | [6 empty] | '-121.83038 | 36.4035 | ETL.7380 | 44562749 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119524367 | Not Scheduled | EI NICOLAUS-WILKIS SLOUGH 28/500 RMV VEG |  | NICOLAUS-WILKINS SLOUGH | 028/500 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.77795 | 38.8397 | ETL.7710 | 40866191 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119524368 | Not Scheduled | NICOLAUS-WILKINS SLOUGH 28/499 RMV VEG |  | NICOLAUS-WILKINS SLOUGH | 028/499 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.777957 | 38.8391 | ETL.7710 | 40874040 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119524411 | Not Scheduled | WV EXCHEQUER-MARIPOSA 1/11 RPR FENCE |  | EXCHEQUER-MARIPOSA | 001/011 | CHS | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 |  |  |  | 2021-06-01 | [5 empty] | South | WSIP | [6 empty] | '-120.266642 | 37.5598 | ETL.8640 | 40582832 | Fence / Gate | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119524448 | Not Scheduled | EI RIO OSO-BRIGHTON 22/153 RMV VEG |  | RIO OSO-BRIGHTON | 022/153 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.417788 | 38.6143 | ETL.5600 | 40653503 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119524785 | Not Scheduled | EI DRUM-RIO OSO #1 42/299 RMV VEG |  | DRUM-RIO OSO #1 | 042/299 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.443088 | 38.9574 | ETL.1420 | 40876955 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119525228 | Not Scheduled | EI CORTINA #4 3/064 RMV VEG |  | CORTINA #4 | 003/064 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.206428 | 39.1637 | ETL.6610 | 40646797 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119525235 | Not Scheduled | EI CORTINA #4 C29/547 RMV VEG |  | CORTINA #4 | C029/547 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.011295 | 39.3991 | ETL.6610 | 40597824 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119526539 | Not Scheduled | EI RIO OSO-BRIGHTON 022/156 RMV VEG |  | RIO OSO-BRIGHTON | 022/156 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-30 | 2021-07-30 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.416375 | 38.6088 | ETL.5600 | 40813640 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119526936 | Not Scheduled | EI CORDELIA #1 TAP 1/33 RMV VEG |  | CORDELIA #1 TAP | 001/033 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-30 | 2021-07-30 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.136153 | 38.2192 | ETL.8182 | 40874319 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119526990 | Not Scheduled | EI BRIGHTON-BELLOTA 46/311 RMV VEGN |  | BRIGHTON-BELLOTA | 046/311 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-30 | 2021-07-30 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.228034 | 38.3091 | ETL.4420 | 40589049 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119528092 | Not Scheduled | EI KERN-MAGUNDEN-WITCO 8/53 RMV VEG |  | KERN-MAGUNDEN-WITCO | 008/053 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-30 | 2021-07-30 | [9 empty] | South | WSIP | [6 empty] | '-118.962135 | 35.4159 | ETL.1970 | 40575383 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119533903 | Not Scheduled | EI RIO OSO-BRIGHTON 21/148 RMV VEG |  | RIO OSO-BRIGHTON | 021/148 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-31 | 2021-07-31 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.420475 | 38.6252 | ETL.5600 | 40875114 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119534123 | Not Scheduled | EI CORDELIA #1 TAP 1/035 RMV VEG |  | CORDELIA #1 TAP | 001/035 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-31 | 2021-07-31 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.13832 | 38.2184 | ETL.8182 | 40823394 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119534157 | Q4 | EI BRIGHTON-DAVIS 16/117 RPR ROAD |  | BRIGHTON-DAVIS | 016/117 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-31 | 2022-07-31 |  |  | 2021-12-31 | 2021-12-31 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.61523 | 38.4713 | ETL.1140 | 40805621 | Road | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | CH | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119534479 | Not Scheduled | EI RIO OSO-BRIGHTON 021/145 RMV VEG |  | RIO OSO-BRIGHTON | 021/145 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-31 | 2022-07-31 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.421603 | 38.6304 | ETL.5600 | 40751695 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119535105 | Not Scheduled | EI MRCY SPRNGS SS-CNL-ORO 12/8 RMV VEG |  | LOS BANOS-CANAL-ORO LOMA | 012/008 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-31 | 2021-07-31 | [9 empty] | South | WSIP | [6 empty] | '-120.819798 | 36.9367 | ETL.8930 | 40859159 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119535304 | Not Scheduled | EI BRIGHTON-DAVIS 15/111 RMV VEG |  | BRIGHTON-DAVIS | 015/111 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-31 | 2021-07-31 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.599381 | 38.4725 | ETL.1140 | 40581644 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119535706 | Not Scheduled | EI COLUSA JCT #1 A005/111 RMV VEG |  | COLUSA JCT #1 | A005/111 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-31 | 2021-07-31 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.919373 | 39.1465 | ETL.8390 | 40912122 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119535752 | Not Scheduled | EI MIDWAY-KERN #3 11/52 RMV SHED |  | MIDWAY-KERN #3 | 011/052 | CHR | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-31 | 2021-07-31 | [9 empty] | South | WSIP | [6 empty] | '-119.255702 | 35.387 | ETL.5160 | 40654705 | Right of Way | Encroachment | Remove |  |  |  |  | PEND | LC | TLS | Land | Expense | 931 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119536607 | Not Scheduled | EI RIO OSO-BRIGHTON 020/139 RMV VEGN |  | RIO OSO-BRIGHTON | 020/139 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-31 | 2021-07-31 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.423033 | 38.6421 | ETL.5600 | 40864810 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119547300 | Not Scheduled | EI NICOLAUS-CATLETT JCT 65/479 RMV VEG |  | NICOLAUS-CATLETT JCT | 065/479 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.511104 | 38.8477 | ETL.7680 | 40911029 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119547320 | Not Scheduled | EI NICLUS-CATLETT JCT 66/492 RMV VEG |  | NICOLAUS-CATLETT JCT | 066/492 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-31 | 2021-07-31 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.506456 | 38.8232 | ETL.7680 | 40911042 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119547321 | Not Scheduled | EI NICOLAUS-CATLETT JCT 63/470 RMV VEG |  | NICOLAUS-CATLETT JCT | 063/470 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.514605 | 38.8661 | ETL.7680 | 40908468 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119547326 | Not Scheduled | EI NICOLAUS-CATLETT JCT 64/475 RMV VEG |  | NICOLAUS-CATLETT JCT | 064/475 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.512647 | 38.8558 | ETL.7680 | 40908473 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119547327 | Not Scheduled | EI NICOLAUS-CATLETT JCT 65/477 RMV VEG |  | NICOLAUS-CATLETT JCT | 065/477 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.511868 | 38.8517 | ETL.7680 | 40908475 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119547328 | Not Scheduled | EI NICOLAUS-CATLETT JCT 64/476 RMV VEG |  | NICOLAUS-CATLETT JCT | 064/476 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.512259 | 38.8538 | ETL.7680 | 40908474 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119547457 | Not Scheduled | EI VACA-TESLA 02/012 RMV VEG |  | VACA-TESLA | 002/012 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-03 | 2021-08-03 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.919401 | 38.3691 | ETL.6140 | 40671298 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119547528 | Not Scheduled | EI RIO OSO-BRIGHTON 22/152 RMV VEGN |  | RIO OSO-BRIGHTON | 022/152 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-31 | 2021-07-31 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.418237 | 38.616 | ETL.5600 | 40668592 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119547579 | Not Scheduled | EI VACA-TESLA 02/011 RMV VEG |  | VACA-TESLA | 002/011 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-03 | 2021-08-03 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.919401 | 38.3724 | ETL.6140 | 40590063 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119548655 | Not Scheduled | EI VACA-TESLA 02/013 RMV VEG |  | VACA-TESLA | 002/013 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-03 | 2021-08-03 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.919401 | 38.3661 | ETL.6140 | 40654731 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119549503 | Not Scheduled | EI VACA-TESLA 03/014 RMV VEG |  | VACA-TESLA | 003/014 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-03 | 2021-08-03 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.919401 | 38.3625 | ETL.6140 | 40762641 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119550009 | Not Scheduled | EI RIO OSO-BRIGHTON 20/134 RMV VEG |  | RIO OSO-BRIGHTON | 020/134 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-03 | 2021-08-03 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.423822 | 38.6506 | ETL.5600 | 40765427 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119551906 | Not Scheduled | EI VACA-LAMBIE SW STA 04/032 RMV VEG |  | VACA-LAMBIE SW STA | 004/032 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-03 | 2021-08-03 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.919813 | 38.3308 | ETL.5845 | 40683775 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119552043 | Not Scheduled | EI VACA-LAMBIE SW STA 04/031 RMV VEG |  | VACA-LAMBIE SW STA | 004/031 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-03 | 2021-08-03 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.919797 | 38.333 | ETL.5845 | 41162710 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119552249 | Not Scheduled | EI VACA-LAMBIE SW STA 04/033 RMV VEG |  | VACA-LAMBIE SW STA | 004/033 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-03 | 2021-08-03 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.919858 | 38.3286 | ETL.5845 | 40650214 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119552540 | Not Scheduled | EI RIO OSO-WEST SCRMENTO 26/189 RMV VEG |  | RIO OSO-WEST SACRAMENTO | 026/189 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-03 | 2021-08-03 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.408535 | 38.5514 | ETL.3450 | 40865236 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119552571 | Not Scheduled | EI RIO OSO-WST SCRMENTO 25/182 RMV VEG |  | RIO OSO-WEST SACRAMENTO | 025/182 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-03 | 2021-08-03 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.408188 | 38.5656 | ETL.3450 | 44869319 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119552918 | Not Scheduled | EI VACA-TESLA 28/119 RMV VEG |  | VACA-TESLA | 028/119 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-03 | 2021-08-03 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.741997 | 38.0746 | ETL.6140 | 40872649 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119558403 | Not Scheduled | EI RIO OSO-WEST SACRAMNTO 24/177 RMV VEG |  | RIO OSO-WEST SACRAMENTO | 024/177 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-04 | 2021-08-04 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.409092 | 38.5752 | ETL.3450 | 40813289 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119561124 | Not Scheduled | EI RIO OSO-BRIGHTON 0/1 RMV VEG |  | RIO OSO-BRIGHTON | 000/001 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-05 | 2021-08-05 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.464405 | 38.9346 | ETL.5600 | 40585909 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119561628 | Not Scheduled | EI RIO OSO-BRIGHTON 0/2 RMV VEG |  | RIO OSO-BRIGHTON | 000/002 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-05 | 2021-08-05 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.460506 | 38.9347 | ETL.5600 | 40659678 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119562521 | Not Scheduled | EI BRIGHTON DAVIS 24/260 RMV VEGN |  | BRIGHTON-DAVIS | 024/260 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-05 | 2021-08-05 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.704319 | 38.5241 | ETL.1140 | 40586245 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2020-11-06 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119562554 | Not Scheduled | EI RIO OSO-BRIGHTON 0/3 RMV VEG |  | RIO OSO-BRIGHTON | 000/003 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-05 | 2021-08-05 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.460282 | 38.9333 | ETL.5600 | 40644616 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119562712 | Not Scheduled | EI RIO OSO-BRIGHTON 0/4 RMV VEG |  | RIO OSO-BRIGHTON | 000/004 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-05 | 2021-08-05 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.459937 | 38.9311 | ETL.5600 | 40746323 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119563144 | Not Scheduled | EI RIO OSO-BRIGHTON 0/5 RMV VEG |  | RIO OSO-BRIGHTON | 000/005 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-05 | 2021-08-05 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.459586 | 38.9289 | ETL.5600 | 40746291 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119564044 | Not Scheduled | EI RIO OSO-BRIGHTON 1/7 RMV VEG |  | RIO OSO-BRIGHTON | 001/007 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-05 | 2021-08-05 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.458834 | 38.9241 | ETL.5600 | 40809499 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119564217 | Not Scheduled | DISTRICT 1500 TAP 0/014 RMV VEGN |  | DISTRICT 1500 TAP | 000/014 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-05 | 2021-08-05 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.692211 | 38.7594 | ETL.7711 | 40654310 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119564767 | Not Scheduled | EI RIO OSO-BRIGHTON 1/10 RMV VEG |  | RIO OSO-BRIGHTON | 001/010 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-05 | 2021-08-05 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.457819 | 38.9177 | ETL.5600 | 40591814 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119564793 | Not Scheduled | EI MOSS LANDING-COBURN 12/59 RMV VEG |  | MOSS LANDING-COBURN | 012/059 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-05 | 2021-08-05 | [9 empty] | South | WSIP | [6 empty] | '-121.570676 | 36.7632 | ETL.5330 | 40862757 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119564954 | Not Scheduled | EI BRIGHTON DAVIS 0/128A RMV VEGN |  | BRIGHTON-DAVIS | :000/128A | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-05 | 2021-08-05 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.029342 | 38.233 | ETL.1140 | 40576456 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119564958 | Not Scheduled | EI BRIGHTON DAVIS 0/128C RMV VEGN |  | BRIGHTON-DAVIS | :000/128C | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-05 | 2021-08-05 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.035201 | 38.2321 | ETL.1140 | 40741806 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119565076 | Not Scheduled | EI RIO OSO-BRIGHTON 1/11 RMV VEG |  | RIO OSO-BRIGHTON | 001/011 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-05 | 2021-08-05 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.457457 | 38.9154 | ETL.5600 | 40594314 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119565257 | Not Scheduled | EI RIO OSO-WEST SACRAMENTO 23/171 RMV VE |  | RIO OSO-WEST SACRAMENTO | 023/171 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-05 | 2021-08-05 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.415153 | 38.5862 | ETL.3450 | 40597228 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119567081 | Q4 | T3NT MIDDLE FORK-GOLD HILL 15/12 RMV VEG | 44591222 | MIDDLE FORK-GOLD HILL | 015/125 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-06 | 2022-08-06 |  |  | 2021-12-31 | 2021-12-31 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.831264 | 38.9302 | ETL.5140 | 40761210 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | CH | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119567469 | Not Scheduled | EI NICOLAUS-CATLETT JCT 70/520 RMV VEG |  | NICOLAUS-CATLETT JCT | 070/520 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-06 | 2021-08-06 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.496367 | 38.7702 | ETL.7680 | 40911070 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119567644 | Not Scheduled | EI CISCO GROVE TAP 00/008 RMV VEG |  | CISCO GROVE TAP | 000/008 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-06 | 2021-08-06 | [9 empty] | North Valley | WSIP | [6 empty] | '-120.5485 | 39.3097 | ETL.8061 | 40878102 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119567752 | Not Scheduled | EI NICOLAUS-CATLETT JCT 70/521 RMV VEG |  | NICOLAUS-CATLETT JCT | 070/521 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-06 | 2021-08-06 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.495996 | 38.7681 | ETL.7680 | 40911071 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119568613 | Not Scheduled | EI NICOLAUS-CATLETT JCT 70/521 RMV VEG |  | NICOLAUS-CATLETT JCT | 071/524 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-06 | 2021-08-06 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.494824 | 38.762 | ETL.7680 | 40911074 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119571127 | Not Scheduled | EI PLACER-GOLD HILL #1 016/110 RMV VEG |  | PLACER-GOLD HILL #1 | 016/110 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-06 | 2021-08-06 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.152579 | 38.683 | ETL.3340 | 40913124 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119571128 | Not Scheduled | EI PLACER-GOLD HILL #1 016/109 RMV VEG |  | PLACER-GOLD HILL #1 | 016/109 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-06 | 2021-08-06 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.155201 | 38.683 | ETL.3340 | 40913123 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119573963 | Not Scheduled | EI PLACER-GOLD HILL #1 010/078 RMV VEG |  | PLACER-GOLD HILL #1 | 010/078 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-07 | 2021-08-07 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.16045 | 38.7457 | ETL.3340 | 44418708 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119575025 | Not Scheduled | EI NICOLAUS-CATLETT JCT 73/542 RMV VEG |  | NICOLAUS-CATLETT JCT | 073/542 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-07 | 2021-08-07 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.488248 | 38.7275 | ETL.7680 | 40910560 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119575452 | Not Scheduled | EI NICOLAUS-CATLETT JCT 74/546 RMV VEG |  | NICOLAUS-CATLETT JCT | 074/546 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-07 | 2021-08-07 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.486874 | 38.7202 | ETL.7680 | 40643300 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119576319 | Not Scheduled | EI TABLE MTN-VACA 037/151 RMV VEG |  | TABLE MTN-VACA | 037/151 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-07 | 2021-08-07 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.83553 | 39.036 | ETL.6090 | 40590045 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119576849 | Not Scheduled | EI LAS PALMAS TAP 0/006 RMV VEG |  | LAS PALMAS TAP (NO FLY) | 000/006 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-07 | 2021-08-07 | [9 empty] | South | WSIP | [6 empty] | '-119.700818 | 36.7519 | ETL.2181 | 40819735 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119577493 | Not Scheduled | EI TABLE MTN-VACA 037/147 RMV VEG |  | TABLE MTN-VACA | 037/147 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-07 | 2021-08-07 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.830767 | 39.0484 | ETL.6090 | 40814967 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119577682 | Not Scheduled | EI DEL MONTE-FORT ORD #1 0/011 RMV VEG |  | DEL MONTE-FORT ORD #1 (NO FLY) | 000/011 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-06 | 2021-08-06 | [9 empty] | South | WSIP | [6 empty] | '-121.844869 | 36.5957 | ETL.8400 | 40588360 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119577776 | Not Scheduled | EI RIO OSO-BRIGHTON 5/035 RMV VEG |  | RIO OSO-BRIGHTON | 005/035 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-07 | 2021-08-07 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.449327 | 38.8639 | ETL.5600 | 40746200 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119579246 | Not Scheduled | EI BUENA VISTA PP #1 1/7 RMV VEG |  | BUENA VISTA PP #1 TAP | 001/007 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-08 | 2021-08-08 | [9 empty] | South | WSIP | [6 empty] | '-119.34953 | 35.157 | ETL.5191 | 40811073 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119579261 | Not Scheduled | EI WILSON-BORDEN #1 91/601 RMV VEG |  | WILSON-GREGG | 091/601 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-08 | 2021-08-08 | [9 empty] | South | WSIP | [6 empty] | '-120.026643 | 36.9755 | ETL.5890 | 40588958 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119580610 | Not Scheduled | EI KERN-KERN OIL-FAMOSO 27/0 RMV VEG |  | KERN-KERN OIL-FAMOSO | 027/000 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-08 | 2021-08-08 | [9 empty] | South | WSIP | [6 empty] | '-119.022883 | 35.4414 | ETL.8870 | 41168956 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119591263 | Not Scheduled | EI HIGGINS-BELL 037/277 RMV VEG |  | HIGGINS-BELL | 037/277 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-10 | 2022-08-10 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.090722 | 38.9448 | ETL.1412 | 40679252 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119595156 | Not Scheduled | EI RIO OSO-BRIGHTON 05/037 RMV VEG |  | RIO OSO-BRIGHTON | 005/037 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-10 | 2021-08-10 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.448845 | 38.8595 | ETL.5600 | 40811199 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119595707 | Not Scheduled | EI TEMPLETON-ATASCADERO 2/39 RMV VEG |  | TEMPLETON-ATASCADERO | 002/039 | CHS | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-10 | 2021-08-10 |  |  |  | 2021-03-01 | [5 empty] | South | WSIP | [6 empty] | '-120.70718 | 35.5447 | ETL.9410 | 40765632 | Road | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119595900 | Not Scheduled | EI RIO OSO-BRIGHTON 06/043 RMV VEG |  | RIO OSO-BRIGHTON | 006/043 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-10 | 2021-08-10 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.447442 | 38.8469 | ETL.5600 | 40659924 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119596167 | Not Scheduled | EI T2NT BALCH-SANGER 02/020 RMV VEGN RD | 44644078 | BALCH-SANGER | 002/020 | CHS | F | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-08-10 | 2022-08-10 |  |  |  | 2020-12-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.120016 | 36.8791 | ETL.1050 | 40585027 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119596338 | Not Scheduled | NT HAAS-MCCALL 3/27 RPL ACCSS RD | 31512000 | HAAS-MCCALL | 003/027 | 71Y | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-02 | 2022-08-02 |  |  |  | 2021-10-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.073495 | 36.9081 | ETL.4850 | 40805255 | Road | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119596421 | Not Scheduled | NT DIVCAB 8/106 ACCSS RD HRD SURFACING | 31512265 | DIVIDE-CABRILLO #1 | 008/106 | 71Y | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-02 | 2022-08-02 |  |  |  | 2021-10-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.436448 | 34.7052 | ETL.1380 | 40826472 | Road | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119598184 | Feb | EI T2NT LAURELES-OTTER 3/003 RPR ROAD |  | LAURELES-OTTER | 003/003 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-11 | 2022-08-11 |  |  | 2021-02-19 | 2021-02-11 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.71857 | 36.4425 | ETL.7380 | 40666353 | Road | Grade Change | Repair |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | CH | Feb |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119598306 | Feb | EI T2NT LAURELES-OTTER 3/002 RPR ROAD |  | LAURELES-OTTER | 003/002 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-11 | 2022-08-11 |  |  | 2021-02-19 | 2021-02-11 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.718171 | 36.444 | ETL.7380 | 40697477 | Road | Grade Change | Repair |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | CH | Feb |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119598393 | Not Scheduled | T2 EI LAURELES-OTTER 3/000 RPR ROAD |  | LAURELES-OTTER | 003/000 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-11 | 2022-08-11 |  |  |  | 2021-08-11 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.717337 | 36.4468 | ETL.7380 | 40589530 | Road | Grade Change | Repair |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119599071 | Not Scheduled | EI POST OFFICE TAP 000/010 RMV VEG |  | POST OFFICE TAP | 000/010 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-11 | 2021-08-11 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.566135 | 38.5666 | ETL.4122 | 40583616 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119600617 | Q4 | T2 DI SALNAS-LAURELES A14/303 RMV VEG |  | SALINAS-LAURELES | A014/303 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-11 | 2021-08-11 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | SCHD | South | WSIP | [6 empty] | '-121.800441 | 36.5699 | ETL.7930 | 40875006 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119600952 | Not Scheduled | EI ZAMORA TAP 1/23 RMV VEG |  | ZAMORA TAP | 001/023 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-11 | 2021-05-11 | [8 empty] | <90D | North Valley | WSIP | [6 empty] | '-121.858757 | 38.7738 | ETL.3471 | 40865007 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119604971 | Not Scheduled | EI MIDWY-WHELER RIDGE #1 11/054 RMV VEG |  | MIDWAY-WHEELER RIDGE #1 | 011/054 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-12 | 2021-08-12 | [9 empty] | South | WSIP | [6 empty] | '-119.335553 | 35.2904 | ETL.5190 | 40764572 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  | DWR | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119604991 | Not Scheduled | EI TEMPLETON-ATASCADERO 2/51 RMV VEG |  | TEMPLETON-ATASCADERO | 002/051 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-12 | 2021-08-12 | [9 empty] | South | WSIP | [6 empty] | '-120.712037 | 35.5387 | ETL.9410 | 40609698 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119605223 | Not Scheduled | EI TEMPLETON-ATASCADERO 2/50 RMV VEG |  | TEMPLETON-ATASCADERO | 002/050 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-12 | 2021-08-12 | [9 empty] | South | WSIP | [6 empty] | '-120.71101 | 35.5387 | ETL.9410 | 40872996 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119605386 | Not Scheduled | EI TEMPLETON-ATASCADERO 2/38 RMV VEG |  | TEMPLETON-ATASCADERO | 002/038 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-12 | 2021-08-12 | [9 empty] | South | WSIP | [6 empty] | '-120.705806 | 35.5435 | ETL.9410 | 40754904 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119605771 | Not Scheduled | EI ARCO-TULARE LAKE 12/191 RMV VEG |  | ARCO-TULARE LAKE | 012/191 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-12 | 2021-08-12 | [9 empty] | South | WSIP | [6 empty] | '-119.925292 | 35.9505 | ETL.8460 | 40819606 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119605774 | Not Scheduled | EI ARCO-TULARE LAKE 12/189 RMV VEG |  | ARCO-TULARE LAKE | 012/189 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-12 | 2021-08-12 | [9 empty] | South | WSIP | [6 empty] | '-119.925104 | 35.9497 | ETL.8460 | 40806931 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119605775 | Not Scheduled | EI ARCO-TULARE LAKE 12/187 RMV VEG |  | ARCO-TULARE LAKE | 012/187 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-12 | 2021-08-12 | [9 empty] | South | WSIP | [6 empty] | '-119.924775 | 35.948 | ETL.8460 | 40763123 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119606378 | Not Scheduled | DI RIO OSO-WOODLAND #1 16/97 RMV VEG |  | RIO OSO-WOODLAND #1 | 016/097 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-12 | 2021-08-12 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.725588 | 38.8187 | ETL.3460 | 40814915 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119607161 | Not Scheduled | EI ARCO-TULARE LAKE 12/193 RMV VEG |  | ARCO-TULARE LAKE | 012/193 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-12 | 2021-08-12 | [9 empty] | South | WSIP | [6 empty] | '-119.92557 | 35.9524 | ETL.8460 | 40871713 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119609190 | Not Scheduled | EI MIDWAY-KERN #1 2/016 RMV VEG |  | MIDWAY-KERN #1 | 002/016 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-13 | 2021-08-13 | [9 empty] | South | WSIP | [6 empty] | '-119.423293 | 35.3932 | ETL.5150 | 40585229 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119609614 | Not Scheduled | EI RIO OSO-BRIGHTON 3/021 RMV VEG |  | RIO OSO-BRIGHTON | 003/021 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-13 | 2021-08-13 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.453973 | 38.8933 | ETL.5600 | 40581041 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119609745 | Not Scheduled | EI CORTINA #3 18/297 RMV VEG |  | CORTINA #3 | 018/297 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-13 | 2021-08-13 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.998772 | 39.1883 | ETL.6600 | 44161233 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119610810 | Not Scheduled | T2 EI INDIAN FLAT-YOSEMITE 39/228 INS RD |  | ETL.1112.POLE.NWOD | 039/228 | 71Y | F | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-08-13 | 2022-08-13 |  |  |  | 2022-12-01 |  |  |  | TR2 | SCHD | South | WSIP | [6 empty] | '-119.784503 | 37.6774 | ETL.1112 | 44420223 | Road | Missing | Install |  |  |  |  | PEND | LC | TLR | Roads | Capital | 374 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119610842 | Not Scheduled | T2 EI INDIAN FLAT-YSEMITE 39/227 INST RD |  | ETL.1112.TOWR | 039/227 | 71Y | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-13 | 2022-08-13 |  |  |  | 2022-12-01 |  |  |  | TR2 | SCHD | South | WSIP | [6 empty] | '-119.786655 | 37.6772 | ETL.1112 | 40806472 | Road | Missing | Install |  |  |  |  | PEND | LC | TLR | Roads | Capital | 374 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119611007 | Not Scheduled | EI DELEVAN-VACA #1 48/320B RMV VEG |  | DELEVAN-VACA #1 | 048/320B | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-13 | 2021-08-13 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.932254 | 38.4693 | ETL.5010 | 43203080 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119611081 | Not Scheduled | T2 EI INDIAN FLT-YOSEMITE 38/226 INST RD |  | ETL.1112.TOWR | 038/226 | 71Y | F | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-08-13 | 2022-08-13 |  |  |  | 2022-12-01 |  |  |  | TR2 | SCHD | South | WSIP | [6 empty] | '-119.790723 | 37.6771 | ETL.1112 | 40820895 | Road | Missing | Install |  |  |  |  | PEND | LC | TLR | Roads | Capital | 374 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119616443 | Not Scheduled | T2 EI EXCHEQUER-INDIAN FLAT 35/198 INS R |  | EXCHEQUER-YOSEMITE | 035/198 | 71Y | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-14 | 2022-08-14 |  |  |  | 2021-07-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.848178 | 37.6602 | ETL.8650 | 44420209 | Road | Missing | Install |  |  |  |  | PEND | LC | TLR | Roads | Capital | 374 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119617677 | Not Scheduled | EI WADHAM TAP 1/27 RMV VEG |  | WADHAM TAP | 001/027 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-14 | 2021-08-14 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.11313 | 39.1052 | ETL.6601 | 40873676 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119617779 | Not Scheduled | EI MIDWAY-KERN #1 16/97 RMV VEG |  | MIDWAY-KERN #1 | 016/097 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-14 | 2021-08-14 | [9 empty] | South | WSIP | [6 empty] | '-119.167204 | 35.3871 | ETL.5150 | 40584101 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119617782 | Not Scheduled | EI SMARTVILLE-NICOLAUS #1 16/321 RMV VEG |  | SMARTVILLE-NICOLAUS #1 | 016/321 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-14 | 2021-08-14 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.422572 | 39.0083 | ETL.7990 | 40909161 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119630446 | Not Scheduled | EI SALINAS-FIRESTONE #2 7/181 RMV VEG |  | SALINAS-FIRESTONE #2 (NO FLY) | 007/181 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-15 | 2021-07-15 | [9 empty] | South | WSIP | [6 empty] | '-121.54125 | 36.6292 | ETL.7910 | 40659368 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119630898 | Not Scheduled | EI KERN-OLD RIVER #2 8/092 RMV VEG |  | KERN-OLD RIVER #2 | 008/092 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-18 | 2021-08-18 | [9 empty] | South | WSIP | [6 empty] | '-119.046388 | 35.2961 | ETL.8900 | 40807513 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119632606 | Not Scheduled | EI BRIGHTON DAVIS 4/039 RMV VEGN |  | BRIGHTON-DAVIS | 004/039 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-18 | 2021-08-18 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.412633 | 38.4772 | ETL.1140 | 40862044 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2020-11-06 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119632931 | Q4 | T2 DI DEL MONTE-VIEJO 4/82 RMV VEG |  | DEL MONTE-VIEJO (NO FLY) | 004/082 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-18 | 2021-08-18 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | SCHD | South | WSIP | [6 empty] | '-121.884491 | 36.5719 | ETL.6710 | 40809358 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119638174 | Not Scheduled | EI CORTINA #4 023/432 RMV VEG |  | CORTINA #4 | 023/432 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-19 | 2021-08-19 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.022606 | 39.2497 | ETL.6610 | 40867098 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119640146 | Not Scheduled | EI TAFT-CUYAMA #1 11/109B RMV VEG |  | TAFT-CUYAMA #1 | 011/109 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-19 | 2021-08-19 | [9 empty] | South | WSIP | [6 empty] | '-119.619281 | 35.0104 | ETL.9200 | 42696685 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119640151 | Not Scheduled | EI TAFT-CUYAMA #1 11/108A RMV VEGN |  | TAFT-CUYAMA #1 | 011/108A | HNA | E | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-08-19 | 2021-08-19 | [9 empty] | South | WSIP | [6 empty] | '-119.616898 | 35.0133 | ETL.9200 | 40647777 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119641551 | Not Scheduled | EI KERN OIL-WITCO 001/018 RMV VEG |  | KERN OIL-WITCO | 001/018 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-20 | 2021-08-20 | [9 empty] | South | WSIP | [6 empty] | '-119.013039 | 35.4173 | ETL.1920 | 40859980 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119642293 | Not Scheduled | EI RIO OSO-WST SCRMNTO 1/11 RMV VEG |  | RIO OSO-WEST SACRAMENTO | 001/011 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-20 | 2021-08-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.519914 | 38.8925 | ETL.3450 | 40589390 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119644243 | Not Scheduled | EI MANVILLE TAP 01/17 RMV VEG |  | MANVILLE TAP | 001/017 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-20 | 2021-08-20 | [9 empty] | South | WSIP | [6 empty] | '-120.431982 | 34.6574 | ETL.1372 | 40618701 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119644387 | Not Scheduled | EI RIO OSO-WEST SCRMNT 22/161 TRIM VEGN |  | RIO OSO-WEST SACRAMENTO | 022/161 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-20 | 2021-08-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.425633 | 38.6052 | ETL.3450 | 40594921 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119647911 | Not Scheduled | VACA-VCVILLE-JMON-NRTH 15/106 RMV VEG |  | VACA-VACAVILLE-JAMESON-NTH TWR | 015/106 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-21 | 2021-08-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.091293 | 38.2446 | ETL.4100 | 40810471 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119648495 | Feb | T3 EI MSSR FLT-GLD HLL #1 15/1 RMV VEG |  | MISSOURI FLAT-GOLD HILL #1 | 015/136 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-21 | 2021-02-21 |  |  | 2021-02-15 | 2021-01-18 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.844313 | 38.686 | ETL.2660 | 40822542 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | HNA | Feb |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119649054 | Not Scheduled | EI VACA-VACVIL-JMESN-NRTH 16/113 RMV VEG |  | VACA-VACAVILLE-JAMESON-NTH TWR | 016/113 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-21 | 2021-08-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.09982 | 38.2308 | ETL.4100 | 40752799 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119649799 | Q3 | T2 WV SMARTVILLE-MARYSVILLE 2/40 FENCE |  | SMARTVILLE-MARYSVILLE | 002/040 | CHR | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-21 | 2021-08-21 |  |  | 2021-08-01 | 2021-08-01 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.334176 | 39.2008 | ETL.7980 | 44191998 | Right of Way | Encroachment | Remove |  |  |  |  | PEND | LC | TLS | Land | Expense | 931 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q3 | Found in 2020 | Not FSR Upgrade | CH | Q3 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119649987 | Not Scheduled | VACA-VACVLLE-JMSN-NRTH 016/112 RMV VEG |  | VACA-VACAVILLE-JAMESON-NTH TWR | 016/112 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-21 | 2021-08-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.098547 | 38.2329 | ETL.4100 | 40653593 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119652149 | Q4 | DI SALINAS-LAURELES A017/366 RMV VEG |  | SALINAS-LAURELES | A017/366 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-20 | 2021-08-20 |  |  | 2021-12-31 | 2021-12-01 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-121.848588 | 36.5838 | ETL.7930 | 40870014 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119652846 | Not Scheduled | EI VACA-VACVL-JMSN-N TWR 16/115 RMV VEGN |  | VACA-VACAVILLE-JAMESON-NTH TWR | 016/115 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-21 | 2021-08-21 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.102917 | 38.2271 | ETL.4100 | 40811086 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119661263 | Not Scheduled | DI WATSONVILLE-SALINAS 24/296 RMV DEBRIS |  | WATSONVILLE-SALINAS | 024/296 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-22 | 2021-08-22 | [9 empty] | South | WSIP | [6 empty] | '-121.638316 | 36.7119 | ETL.8310 | 40652228 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119661608 | Not Scheduled | DI SALINAS-LAGUNITAS 000/006 RMV VEG |  | SALINAS-LAGUNITAS | 000/006 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-22 | 2021-08-22 | [9 empty] | South | WSIP | [6 empty] | '-121.649458 | 36.683 | ETL.7920 | 40771473 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119664211 | Not Scheduled | EI WOODLAND-DAVIS 11/210 RMV VEGN |  | WOODLAND-DAVIS | 011/210 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-24 | 2021-08-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.735841 | 38.5534 | ETL.4210 | 40601471 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119668149 | Q4 | DI DEL MONTE-VIEJO 1/28 RMV VEG |  | DEL MONTE-VIEJO (NO FLY) | 001/028 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-21 | 2021-08-21 |  |  | 2021-12-31 | 2021-12-01 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-121.874085 | 36.5935 | ETL.6710 | 40809352 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119668161 | Not Scheduled | DI WEST SACRAMENTO-DV 11/175 RMV VEGN |  | WEST SACRAMENTO-DAVIS | 011/175 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-22 | 2021-08-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.734655 | 38.5605 | ETL.4120 | 40586257 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119669556 | Not Scheduled | EI MORRO BAY-MESA 2/011 RMV VEG |  | MORRO BAY-MESA | 002/011 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-25 | 2021-08-25 | [9 empty] | South | WSIP | [6 empty] | '-120.819311 | 35.3628 | ETL.5290 | 40587103 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119670753 | Not Scheduled | EI BRIGHTON DAVIS 12/094 RMV VEG |  | BRIGHTON-DAVIS | 012/094 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-25 | 2021-08-25 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.552186 | 38.4698 | ETL.1140 | 40764782 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119674473 | Not Scheduled | EI CITY #2 TAP 00/2A RMV VEG |  | CITY #2 TAP | 000/002A | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-26 | 2021-08-26 | [9 empty] | South | WSIP | [6 empty] | '-120.444886 | 34.6658 | ETL.1371 | 40678762 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119674537 | Not Scheduled | EI RIO OSO-WEST SCRMNT 20/150 RMV VEGN |  | RIO OSO-WEST SACRAMENTO | 020/150 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-26 | 2021-08-26 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.436078 | 38.6241 | ETL.3450 | 40605123 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119674793 | Not Scheduled | DI FLINT TAP 001/015 RMV VEG |  | FLINT TAP | 001/015 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-24 | 2021-08-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.07735 | 38.8863 | ETL.3341 | 40862272 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119674966 | Not Scheduled | DI WATSONVILLE-SALINAS 5/72 RMV VEG |  | WATSONVILLE-SALINAS | 005/072 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-22 | 2021-08-22 | [9 empty] | South | WSIP | [6 empty] | '-121.693968 | 36.8788 | ETL.8310 | 40876647 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119675193 | Not Scheduled | DI SALINAS-LAGUNITAS 003/071 RMV VEG |  | SALINAS-LAGUNITAS | 003/071 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-22 | 2021-08-22 | [9 empty] | South | WSIP | [6 empty] | '-121.621475 | 36.722 | ETL.7920 | 40668614 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119679058 | Not Scheduled | DI GOLD HILL-BELLOT-LOCK 48/293 RMV VEG |  | GOLD HILL-BELLOTA-LOCKEFORD | 048/293 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-26 | 2021-08-26 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.141602 | 38.4779 | ETL.1690 | 40659254 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119679449 | Not Scheduled | DI GOLD HILL-BELLO-LOCK 44/271 RMV VEG |  | GOLD HILL-BELLOTA-LOCKEFORD | 044/271 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-26 | 2021-08-26 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.142544 | 38.5246 | ETL.1690 | 40594114 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119679859 | Not Scheduled | EI BUELLTON TAP 01/31 RMV VEG |  | BUELLTON TAP | 001/031 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-27 | 2021-08-27 | [9 empty] | South | WSIP | [6 empty] | '-120.186392 | 34.6255 | ETL.1201 | 40689779 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119684809 | Not Scheduled | DI NICOLAUS-WILKINS SLGH 4/80 RMV VEG |  | NICOLAUS-WILKINS SLOUGH | 004/080 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-24 | 2021-08-24 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.591328 | 38.879 | ETL.7710 | 44145658 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119688305 | Not Scheduled | T2 EI MORRO BAY-MESA 16/73 RMV VEG |  | MORRO BAY-MESA | 016/073 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-28 | 2021-08-28 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-120.648684 | 35.2111 | ETL.5290 | 40659091 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119696151 | Mar | EI TESLA-STCKTN COGEN JCT 1/012 RPR GYWW | 44598407 | TESLA-STOCKTON COGEN JCT | 001/012 | ICW | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Clearance restriction (circuit efficiency) | 2020-08-31 | 2021-08-31 |  |  | 2021-03-16 | 2021-03-15 | [5 empty] | Central | WSIP | [6 empty] | '-121.551232 | 37.7041 | ETL.4010 | 40667469 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-10-22 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 119696584 | Not Scheduled | WATSONVILLE-SALINAS 2/40 INS ROAD |  | WATSONVILLE-SALINAS | 002/040 | 71Y | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-31 | 2022-08-31 |  |  |  | 2021-08-21 | [5 empty] | South | WSIP | [6 empty] | '-121.748965 | 36.8788 | ETL.8310 | 40770606 | Road | Missing | Install |  |  |  |  | PEND | LC | TLR | Roads | Capital | 374 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119700772 | Not Scheduled | DI ARCO-CARNERAS 002/039 RMV VEG |  | ARCO-CARNERAS | 002/039 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-28 | 2021-08-28 | [9 empty] | South | WSIP | [6 empty] | '-119.915278 | 35.7397 | ETL.8430 | 44183256 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119711878 | Not Scheduled | EI SANTA MARIA-SISQUOC 6/090 RMV VEG |  | SANTA MARIA-SISQUOC | 006/090 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-03 | 2021-09-03 | [9 empty] | South | WSIP | [6 empty] | '-120.355512 | 34.9308 | ETL.3610 | 40772308 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119716599 | Not Scheduled | DI SALINAS-FIRESTONE #2 7/189 RMV VEG |  | SALINAS-FIRESTONE #2 (NO FLY) | 007/189 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-03 | 2021-09-03 | [9 empty] | South | WSIP | [6 empty] | '-121.54922 | 36.6242 | ETL.7910 | 40589428 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119720868 | Not Scheduled | DI KING CITY-COBURN #1 0/13 RMV VEGN |  | KING CITY-COBURN #1 | 000/013 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-04 | 2021-09-04 | [9 empty] | South | WSIP | [6 empty] | '-121.132692 | 36.2137 | ETL.7320 | 40585785 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119726538 | Not Scheduled | DI DEL MONTE-FORT ORD #1 5/66 RMV VEG |  | DEL MONTE-FORT ORD #1 (NO FLY) | 005/066 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-08-12 | 2021-08-12 | [9 empty] | South | WSIP | [6 empty] | '-121.805837 | 36.6416 | ETL.8400 | 40864176 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119729798 | Not Scheduled | EI CALLENDER SW STA-MESA 1/33 RMV VEG |  | CALLENDAR SW STA-MESA | 001/033 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-09 | 2021-09-09 | [9 empty] | South | WSIP | [6 empty] | '-120.557772 | 35.0514 | ETL.1210 | 40660340 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119730169 | Not Scheduled | EI OCEANO-CLENDR SW STA 22/165 RMV VEG |  | OCEANO-CALLENDAR SW STA | 022/165 | HNA | E | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-09-09 | 2021-09-09 | [9 empty] | South | WSIP | [6 empty] | '-120.583991 | 35.0649 | ETL.2394 | 40809739 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119730551 | Not Scheduled | PANOCHE-EXCELSIOR SW S#1 20/095 RMV VEGN |  | PANOCHE-SCHINDLER #1 | 020/095 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-09 | 2021-09-09 | [9 empty] | South | WSIP | [6 empty] | '-120.370906 | 36.4203 | ETL.3250 | 40746887 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119740858 | Not Scheduled | Fulton-Lakeville replace HMI | 31513273 | ETU.9984 | 1A NORTH TERMINAL | 72Z | E | 2020_(9d) All other tags | Underground Transmission | 2020-09-10 | 2021-09-10 | [9 empty] | Central | [7 empty] | '-122.5838804 | 38.4429 | ETU.9984 | 41113551 | Pump-Underground | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Capital | 377 | Martin |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 72Z | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119741712 | Not Scheduled | EI CITY TAP #2 0/1 RMV VEG |  | CITY #2 TAP | 000/001 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-10 | 2021-09-10 | [9 empty] | South | WSIP | [6 empty] | '-120.4412894 | 34.6677 | ETL.1371 | 44404967 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119742423 | Not Scheduled | EI DIVIDE-CABRILLO #1 10/133 RMV VEG |  | DIVIDE-CABRILLO #1 | 010/133 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-10 | 2021-09-10 | [9 empty] | South | WSIP | [6 empty] | '-120.451369 | 34.675 | ETL.1380 | 44887067 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119761727 | Not Scheduled | DI COBURN-OIL FIELDS #1 8/147 RMV VEGN |  | COBURN-OIL FIELDS #1 | 008/147 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-03 | 2021-09-03 | [9 empty] | South | WSIP | [6 empty] | '-121.069678 | 36.1859 | ETL.6410 | 40666477 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119764977 | Not Scheduled | EI DEEPWATER #1 TAP 000/001 RMV VEG |  | DEEPWATER #1 TAP | 000/001 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-11 | 2021-09-11 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.564409 | 38.5832 | ETL.4121 | 40589280 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119764995 | Not Scheduled | EI WEST SACRAMENTO-BRGHTN 0/8 RMV VEG |  | WEST SACRAMENTO-BRIGHTON | 000/008 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-12 | 2021-09-12 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.558008 | 38.5846 | ETL.4110 | 40908409 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119768723 | Q4 | DI DEL MONTE-VIEJO 001/032 RMV VEG |  | DEL MONTE-VIEJO (NO FLY) | 001/032 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-03 | 2021-09-03 |  |  | 2021-12-31 | 2021-12-01 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-121.8779 | 36.5921 | ETL.6710 | 40585764 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119777355 | Q4 | T2 ROUND MTN-TABLE MTN #1 50/2 ROAD | 31514755 | ROUND MTN-TABLE MTN #1 | 050/218 | 71Y | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-17 | 2021-09-17 |  |  | 2021-11-10 | 2020-11-10 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.894389 | 40.0824 | ETL.6060 | 40869085 | Road | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Table Mountain |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | 71 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119777691 | Not Scheduled | VACA-VCVL-JMN-N TWR B019/133 RMV VEGN |  | VACA-VACAVILLE-JAMESON-NTH TWR | B019/133 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-17 | 2021-09-17 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.137313 | 38.205 | ETL.4100 | 40755563 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119779757 | Not Scheduled | NN SN LS OBSPO-CYUCS 020/177 RMV VEG |  | SAN LUIS OBISPO-CAYUCOS | 020/177 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-10 | 2021-09-10 | [9 empty] | South | WSIP | [6 empty] | '-120.833522 | 35.4075 | ETL.9090 | 40602137 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119786025 | Not Scheduled | EI WEST SACRAMENTO-BRIGHTN 9/059 RMV VEG |  | WEST SACRAMENTO-BRIGHTON | 009/059 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-18 | 2021-09-18 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.473366 | 38.5989 | ETL.4110 | 40912125 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119786155 | Not Scheduled | EI WEST SACRAMENTO-BRIGHTN 9/057 RMV VEG |  | WEST SACRAMENTO-BRIGHTON | 009/057 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-18 | 2021-09-18 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.477789 | 38.6025 | ETL.4110 | 40908361 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119786212 | Not Scheduled | EI WEST SACRAMENTO-BRTN 08/55 RMV VEGN |  | WEST SACRAMENTO-BRIGHTON | 008/055 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-18 | 2021-09-18 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.483178 | 38.6069 | ETL.4110 | 40908363 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119786242 | Not Scheduled | EI WEST SACRAMENTO-BRIGHTON 8/53 RMV VEG |  | WEST SACRAMENTO-BRIGHTON | 008/053 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-18 | 2021-09-18 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.490677 | 38.6077 | ETL.4110 | 40908365 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119786652 | Not Scheduled | DI WOODLAND-DAVIS 011/214 RMV VEG |  | WOODLAND-DAVIS | 011/214 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-15 | 2021-09-15 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.735857 | 38.5506 | ETL.4210 | 40769653 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119787862 | Not Scheduled | DI COTINA #4 D026/491 RMV VEG |  | CORTINA #4 | D026/491 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-17 | 2021-09-17 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.030523 | 39.2158 | ETL.6610 | 40757473 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119788738 | Not Scheduled | DI GLENN #2 034/656 RMV VEG |  | GLENN #2 | 034/656 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-18 | 2021-09-18 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.011615 | 39.408 | ETL.6930 | 40757501 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119789603 | Not Scheduled | DI BRIGHTON DAVIS 26/289 RMV VEG |  | BRIGHTON-DAVIS | 026/289 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-18 | 2021-09-18 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.713404 | 38.5375 | ETL.1140 | 40608444 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119789674 | Not Scheduled | GATES-MIDWAY 59/237 RPL INSS | 31528351 | GATES-MIDWAY | 059/237 | 93K | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2020-09-20 | 2021-09-20 | [5 empty] | DLFL once tag is confirmed complete PM 74008740 |  |  |  | South | WSIP | [6 empty] | '-119.501783 | 35.4609 | ETL.5990 | 44677479 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  | 2020-11-10 | Released-PERTC | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 119796812 | Not Scheduled | EI DIABLO-GATES #1 77/318 RMV VEG |  | DIABLO-GATES #1 | 077/318 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-22 | 2021-09-22 | [9 empty] | South | WSIP | [6 empty] | '-120.132342 | 36.1171 | ETL.5960 | 40858527 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119798108 | Not Scheduled | EI WEST SACRAMENTO-BRIGHTON 8/52 RMV VEG |  | WEST SACRAMENTO-BRIGHTON | 008/052 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-22 | 2021-09-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.494504 | 38.6075 | ETL.4110 | 40908366 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119798154 | Not Scheduled | EI WEST SACRAMENTO-BRIGHTON 8/51 RMV VEG |  | WEST SACRAMENTO-BRIGHTON | 008/051 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-22 | 2021-09-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.49768 | 38.6073 | ETL.4110 | 40908367 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119798197 | Not Scheduled | EI WEST SACRAMENTO-BRIGHTON 8/50 RMV VEG |  | WEST SACRAMENTO-BRIGHTON | 008/050 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-22 | 2021-09-22 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.500951 | 38.6069 | ETL.4110 | 40908368 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119800619 | Not Scheduled | DI CORTINA #2 A005/086 RMV VEG |  | CORTINA #2 | A005/086 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-18 | 2021-09-18 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.132905 | 39.1143 | ETL.6590 | 41121498 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119802573 | Not Scheduled | EI VIEJO-MONTEREY 1/034 RMV VEGN |  | VIEJO-MONTEREY (NO FLY) | 001/034 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-23 | 2021-09-23 | [9 empty] | South | WSIP | [6 empty] | '-121.893623 | 36.5925 | ETL.8270 | 40697372 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119802644 | Not Scheduled | EI VIEJO-MONTEREY 01/033 RMV VEG |  | VIEJO-MONTEREY (NO FLY) | 001/033 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-23 | 2021-09-23 | [9 empty] | South | WSIP | [6 empty] | '-121.893964 | 36.5922 | ETL.8270 | 40600148 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119803546 | Not Scheduled | EI PASO ROBLES-TEMPLETON 4/71 RMV VEG |  | PASO ROBLES-TEMPLETON | 004/071 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-23 | 2021-09-23 | [9 empty] | South | WSIP | [6 empty] | '-120.68727 | 35.5575 | ETL.9400 | 40669092 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119804975 | Not Scheduled | EI VIEJO-MONTEREY 01/031 RMV VEG |  | VIEJO-MONTEREY (NO FLY) | 001/031 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-23 | 2021-09-23 | [9 empty] | South | WSIP | [6 empty] | '-121.895083 | 36.5912 | ETL.8270 | 40875001 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119816970 | Not Scheduled | DI KING CITY-COBURN #1 0/12 RMV VEGN |  | KING CITY-COBURN #1 | 000/012 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-04 | 2021-09-04 | [9 empty] | South | WSIP | [6 empty] | '-121.132122 | 36.214 | ETL.7320 | 40699521 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119819430 | Not Scheduled | NN METCALF-GRN VLLY 22/158L RMV VEGN |  | METCALF-GREEN VALLEY | 022/158 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-14 | 2021-09-14 | [9 empty] | South | WSIP | [8 empty] | ETL.2540 | 44401583 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119820999 | Not Scheduled | T3 EI TMBLOR-SN LS OBISPO 43/249 RPR RD | 44571817 | TEMBLOR-SAN LUIS OBISPO | 043/249 | CHS | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-16 | 2021-03-16 |  |  |  | 2020-12-01 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.440636 | 35.3692 | ETL.3960 | 40870130 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119824049 | Not Scheduled | DI GUARDIAN #1 TAP 000/006 RMV VEG |  | GUARDIAN #1 TAP | 000/006 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-03 | 2021-09-03 | [9 empty] | South | WSIP | [6 empty] | '-119.589337 | 36.5407 | ETL.2301 | 40819731 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119825409 | Not Scheduled | EI DIABLO-MIDWAY #2 83/337 RMV VEG |  | DIABLO-MIDWAY #2 | 083/337 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-29 | 2021-09-29 | [9 empty] | South | WSIP | [6 empty] | '-119.466956 | 35.3917 | ETL.5970 | 40807959 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119825926 | Not Scheduled | DI HELM-KERMAN 13/4 RMV VEGN |  | HELM-KERMAN | 013/004 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-28 | 2021-09-28 | [9 empty] | South | WSIP | [6 empty] | '-120.060427 | 36.691 | ETL.8740 | 44298679 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  | 2020-10-02 | Released-SpecialCond | No Estimate | Awaiting Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119826329 | Not Scheduled | EI SURF TAP 9/158 RMV VEG |  | SURF TAP | 009/158 | HNA | E | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-09-29 | 2021-09-29 | [9 empty] | South | WSIP | [6 empty] | '-120.571258 | 34.6757 | ETL.1381 | 44844656 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119827614 | Not Scheduled | EI SURF TAP 000/007 RMV VEG |  | SURF TAP | 000/007 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-29 | 2021-09-29 | [9 empty] | South | WSIP | [6 empty] | '-120.457055 | 34.67 | ETL.1381 | 44315951 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119827901 | Not Scheduled | EI ATWATER-EL CAPITAN 14/097 RMV VEG |  | ATWATER-EL CAPITAN | 014/097 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-29 | 2021-09-29 | [9 empty] | South | WSIP | [6 empty] | '-120.5955 | 37.3676 | ETL.1020 | 40805688 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119829388 | Not Scheduled | DI RIO OSO-WEST SAC 19/143 RMV VEGN |  | RIO OSO-WEST SACRAMENTO | 019/143 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-28 | 2021-09-28 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.443401 | 38.6373 | ETL.3450 | 40662956 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119829669 | Q4 | T2 NN SALINAS-LAURELES 9/203 RMV VEG |  | SALINAS-LAURELES | 009/203 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-28 | 2021-09-28 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | SCHD | South | WSIP | [6 empty] | '-121.717284 | 36.5816 | ETL.7930 | 40864636 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119829763 | Not Scheduled | DI TEMPLETON-GATES 66/279 RMV VEGN |  | TEMPLETON-GATES | 066/279 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-28 | 2021-09-28 | [9 empty] | South | WSIP | [6 empty] | '-120.13489 | 36.1109 | ETL.5934 | 40858106 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119832337 | Not Scheduled | EI SAN LUIS OBISPO-OCEANO 16/076 CANCEL |  | SAN LUIS OBISPO-OCEANO | 016/076 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-30 | 2021-09-30 | [6 empty] | CANCEL/CNCL |  |  | South | WSIP | [6 empty] | '-120.517915 | 35.0973 | ETL.3530 | 40650136 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119835165 | Not Scheduled | DI RIO OSO-WST SACRMENTO 20/146 RMV VEG |  | RIO OSO-WEST SACRAMENTO | 020/146 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-30 | 2021-09-30 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.440317 | 38.6317 | ETL.3450 | 40814097 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119838105 | Not Scheduled | DI RIO OSO-WST SACRMENTO 19/144 RMV DBRS |  | RIO OSO-WEST SACRAMENTO | 019/144 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-29 | 2021-09-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.44235 | 38.6354 | ETL.3450 | 40756057 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119847220 | Not Scheduled | DI CORTINA #4 D26/490 RMV VEGN |  | CORTINA #4 | D026/490 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-29 | 2021-09-29 | [9 empty] | North Valley | WSIP | [6 empty] | '-122.030524 | 39.2165 | ETL.6610 | 40757484 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119850038 | Not Scheduled | San Mateo-Martin, 2021 Encroachment perm | 44486467 | ETU.9980 | SM TERMINAL | ICU | E | 2020_(9d) All other tags | Underground Transmission | 2020-10-03 | 2021-10-03 | [9 empty] | Central | [7 empty] | '-122.3188314 | 37.5827 | ETU.9980 | 41113607 | Other-Underground | Other | Other | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TUG | Maintenance | Expense | 629 | Martin |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119852617 | Not Scheduled | EI CALLENDER SW STA-MESA 2/44 RMV VEG |  | CALLENDAR SW STA-MESA | 002/044 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-01 | 2021-10-01 | [9 empty] | South | WSIP | [6 empty] | '-120.544137 | 35.0514 | ETL.1210 | 40576131 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119860113 | Not Scheduled | EI DIABLO-MIDWAY #2 81/329 RMV VEG |  | DIABLO-MIDWAY #2 | 081/329 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-06 | 2021-10-06 | [9 empty] | South | WSIP | [6 empty] | '-119.496685 | 35.383 | ETL.5970 | 40860569 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119872417 | Not Scheduled | EI MORRO BY-SN LS OBP #1 13/75 RMV VEGN |  | MORRO BAY-SAN LUIS OBISPO #1 | 015/087 | HNA | E | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-10-08 | 2021-10-08 | [9 empty] | South | WSIP | [6 empty] | '-120.641034 | 35.2575 | ETL.2810 | 40818660 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 119887429 | Not Scheduled | DI SALINAS-LAGUNITAS 004/089 TRIM VEGT |  | SALINAS-LAGUNITAS | 004/089 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-09 | 2021-10-09 | [9 empty] | South | WSIP | [6 empty] | '-121.613097 | 36.7326 | ETL.7920 | 40593393 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119906283 | Not Scheduled | EI METCALF-MOSS LANDING #1 54/235 RMV VE |  | METCALF-MOSS LANDING #1 | 054/235 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-14 | 2021-10-14 | [9 empty] | South | WSIP | [6 empty] | '-121.684383 | 36.8572 | ETL.5100 | 40761097 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119907884 | Not Scheduled | DI SALINAS-LAGNITAS 003/088 RMV VEG |  | SALINAS-LAGUNITAS | 003/088 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-08 | 2021-10-08 | [9 empty] | South | WSIP | [6 empty] | '-121.612851 | 36.732 | ETL.7920 | 40618142 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119910789 | Not Scheduled | EI MRRO BAY-TEMPLETON 2/014 REM VEG |  | MORRO BAY-TEMPLETON | 002/014 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-15 | 2021-10-15 | [9 empty] | South | WSIP | [6 empty] | '-120.815854 | 35.396 | ETL.5933 | 40761447 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119910985 | Not Scheduled | T2 DRUM-RIO OSO #1 12/113A RMV VEG |  | DRUM-RIO OSO #1 | 012/113A | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-15 | 2021-10-15 | [7 empty] | TR2 |  | North Valley | WSIP | [6 empty] | '-120.955019 | 39.1617 | ETL.1420 | 41162717 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119911910 | Not Scheduled | DI BRIGHTON-DAVIS 024/243 RMV VEG |  | BRIGHTON-DAVIS | 024/243 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-08 | 2021-10-08 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.695297 | 38.5193 | ETL.1140 | 40650193 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119921140 | Not Scheduled | CRZY HRS CNYN-SLNS-SOL 40/253 INST ROAD |  | CRZY HORSE CYN-SALNS-SOLDAD#1 | 040/253 | 71Y | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-19 | 2022-10-19 |  |  |  | 2021-10-12 | [5 empty] | South | WSIP | [6 empty] | '-121.602824 | 36.7362 | ETL.2900 | 40658808 | Road | Missing | Install |  |  |  |  | PEND | LC | TLR | Roads | Capital | 374 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119925526 | Not Scheduled | EI MORRO BAY-TEMPLETON 3/018 RPR GATE | 44638217 | MORRO BAY-TEMPLETON | 003/018 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-19 | 2022-10-19 |  |  |  | 2022-06-01 | [5 empty] | South | WSIP | [6 empty] | '-120.803314 | 35.4051 | ETL.5933 | 40863310 | Fence / Gate | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119925528 | Not Scheduled | EI MRRO BY-SN LS BISP #1 2/014 REM VEG |  | MORRO BAY-SAN LUIS OBISPO #1 | 002/014 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-19 | 2021-10-19 | [9 empty] | South | WSIP | [6 empty] | '-120.818928 | 35.3628 | ETL.2810 | 40762244 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119925546 | Not Scheduled | EI MORRO BAY-TEMPLETON 3/019 REM VEG |  | MORRO BAY-TEMPLETON | 003/019 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-19 | 2021-10-19 | [9 empty] | South | WSIP | [6 empty] | '-120.801017 | 35.4068 | ETL.5933 | 40869522 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119927608 | Not Scheduled | EI MESA-SANTA MARIA 22/106 RMV VEG |  | MESA-SANTA MARIA | 022/106 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-20 | 2021-10-20 | [9 empty] | South | WSIP | [6 empty] | '-120.444225 | 34.9919 | ETL.2450 | 40809703 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119929379 | Not Scheduled | EI MRRO BAY-TEMPLETON 16/066 RPR ROAD | 44638217 | MORRO BAY-TEMPLETON | 016/066 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-20 | 2022-10-20 |  |  |  | 2021-05-04 | [5 empty] | South | WSIP | [6 empty] | '-120.683482 | 35.5525 | ETL.5933 | 40818864 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119929413 | Not Scheduled | EI MRO BAY-TEMPLETON 16/067A RPR ROAD | 44638217 | MORRO BAY-TEMPLETON | 016/067A | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-20 | 2022-10-20 |  |  |  | 2021-05-04 | [5 empty] | South | WSIP | [6 empty] | '-120.680471 | 35.5545 | ETL.5933 | 40576221 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119930349 | Not Scheduled | DI WOODLAND-DAVIS 0/1 RMV VEGN |  | WOODLAND-DAVIS | 000/001 | HNA | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-20 | 2022-10-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.759856 | 38.6775 | ETL.4210 | 40589286 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119930653 | Q4 | T2 NN SALINAS-LAURELES A014/296 RMV VEGN |  | SALINAS-LAURELES | A014/296 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-20 | 2021-10-20 |  |  | 2021-12-31 | 2021-12-01 |  |  |  | TR2 | SCHD | South | WSIP | [6 empty] | '-121.795349 | 36.569 | ETL.7930 | 40666671 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119932510 | Not Scheduled | T2 GRN VALY-PL SWT 6/78 RMV VEG | 44503032 | GREEN VALLEY-PAUL SWEET | 006/078 | CHS | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-21 | 2021-10-21 |  |  |  | 2021-08-05 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.863373 | 36.975 | ETL.1730 | 44413314 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119932663 | Not Scheduled | DI COLUSA JCT #1 A005/111 RMV VEG |  | COLUSA JCT #1 | A005/111 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-20 | 2021-10-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.919373 | 39.1465 | ETL.8390 | 40912122 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119932887 | Not Scheduled | DI MADISON-VACA 045/280 RMV VEG |  | MADISON-VACA | 045/280 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-20 | 2021-10-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.996611 | 38.491 | ETL.2170 | 40598140 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119934451 | Not Scheduled | TAFT-CUYAMA #1 2/032 RPR RD | 44644938 | TAFT-CUYAMA #1 | 002/032 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-22 | 2022-10-22 |  |  |  | 2022-12-01 |  |  |  |  | SCHD | South | WSIP | [6 empty] | '-119.51378 | 35.1082 | ETL.9200 | 40819919 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Midway |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119936500 | Not Scheduled | EI CALLENDER SW STA-MESA 1/34 RMV VEG |  | CALLENDAR SW STA-MESA | 001/034 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-22 | 2021-10-22 | [9 empty] | South | WSIP | [6 empty] | '-120.556587 | 35.0514 | ETL.1210 | 40650121 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119936590 | Not Scheduled | EI CALLENDER SW STA-MESA 1/035 RMV VEG |  | CALLENDAR SW STA-MESA | 001/035 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-22 | 2021-10-22 | [9 empty] | South | WSIP | [6 empty] | '-120.555282 | 35.0514 | ETL.1210 | 40761142 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119945705 | Not Scheduled | DI CHENEY #1 TAP 4/1 RMV VEGN |  | CHENEY #1 TAP | 004/001 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-23 | 2021-10-23 | [9 empty] | South | WSIP | [6 empty] | '-120.531361 | 36.6327 | ETL.3231 | 42633348 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119950742 | Not Scheduled | EI MESA-DIVIDE #1 005/035 RMV VEG |  | MESA-DIVIDE #1 | 005/035 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-27 | 2021-10-27 | [9 empty] | South | WSIP | [6 empty] | '-120.49816 | 34.9356 | ETL.2430 | 40764827 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119950796 | Not Scheduled | EI MESA-DIVIDE #1 5/034 RMV VEG |  | MESA-DIVIDE #1 | 005/034 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-27 | 2021-10-27 | [9 empty] | South | WSIP | [6 empty] | '-120.497595 | 34.9377 | ETL.2430 | 40762111 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119951049 | Not Scheduled | EI MESA-DIVIDE #1 004/028 RMV VEG |  | MESA-DIVIDE #1 | 004/028 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-27 | 2021-10-27 | [9 empty] | South | WSIP | [6 empty] | '-120.496831 | 34.9521 | ETL.2430 | 40861709 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119951821 | Not Scheduled | RIO OSO-BRIGHTON 9/66 TRIM VEGN |  | RIO OSO-BRIGHTON | 009/066 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-27 | 2021-10-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.441835 | 38.7964 | ETL.5600 | 40804981 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119961730 | Not Scheduled | DI VACA-PLAINFIELD-PLFD 9/136 RMV VEG |  | VACA-PLAINFIELD | 009/136 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-27 | 2021-10-27 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.959444 | 38.5285 | ETL.8200 | 40756570 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119964904 | Not Scheduled | GOLDTREE TAP 115KV 000/003 HARD SURFACIN | 31517465 | GOLDTREE TAP |  | 71Y | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-10-29 | 2022-10-29 |  |  |  | 2021-07-01 | [5 empty] | South | WSIP | [8 empty] | ETL.2821 |  | Road | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119972029 | Q2 | T3 EI MOSS LANDING-METCALF 14/65 RMV VEG |  | MOSS LANDING-METCALF | 014/065 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-11-02 | 2021-05-02 |  |  | 2021-05-02 | 2021-05-01 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.660236 | 36.9511 | ETL.6050 | 40753739 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | HNA | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119972691 | Q2 | T3 EI MOSS LANDING-METCALF 14/68 RMV VEG |  | MOSS LANDING-METCALF | 014/068 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-11-02 | 2021-05-02 |  |  | 2021-05-02 | 2021-05-01 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.664557 | 36.9604 | ETL.6050 | 40865899 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | HNA | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119975310 | Not Scheduled | DI NICOLAUS-PLAINFIELD 002/056 RMV VEG |  | NICOLAUS-PLAINFIELD | 002/056 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-09-30 | 2021-09-30 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.573816 | 38.8893 | ETL.7700 | 40912871 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119977687 | Not Scheduled | EI FAIRWAY #1 TAP 1/025 REM VEG |  | FAIRWAY #1 TAP | 001/025 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-11-03 | 2021-11-03 | [9 empty] | South | WSIP | [6 empty] | '-120.444903 | 34.9289 | ETL.2451 | 44191797 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119981128 | Not Scheduled | JEFFERSON-MARTIN - 230 kV_32 | 31517723 | ETU.9931 | 32 | 72Z | E | 2020_(9d) All other tags | Underground Transmission | 2020-11-04 | 2021-11-04 | [9 empty] | Central | [7 empty] | '-122.386077 | 37.5637 | ETU.9931 | 41353730 | Cable-Underground | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Capital | 377 | Martin |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 72Z | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119985985 | Not Scheduled | EI DIVIDE-VANDENBERG #1 0/003 RMV VEG |  | DIVIDE-VANDENBERG #1 | 000/003 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-11-05 | 2021-11-05 | [9 empty] | South | WSIP | [6 empty] | '-120.452482 | 34.8256 | ETL.8620 | 44564963 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119985989 | Q4 | T3NT MIDDLE FORK-GLD HILL 20/16 INS GATE | 31521953 | MIDDLE FORK-GOLD HILL | 020/160A | 71Y | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-11-05 | 2022-11-05 |  |  | 2021-12-31 | 2021-12-31 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.877059 | 38.8846 | ETL.5140 | 40608897 | Fence / Gate | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q4 | Found in 2020 | Not FSR Upgrade | 71 | Q4 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 119999959 | Not Scheduled | EI CRAZ HOR CAN-SAL-SOL 38/241 RMV VEG |  | CRZY HORSE CYN-SALNS-SOLDAD#1 | 038/241 | CHS | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-11-09 | 2021-11-09 |  |  |  | 2021-07-09 | [5 empty] | South | WSIP | [6 empty] | '-121.60369 | 36.7608 | ETL.2900 | 40595214 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120013332 | Not Scheduled | EI HERNDON-BULLARD #1 8/047 RMV VEG |  | HERNDON-BULLARD #1 | 008/047 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-11-12 | 2021-11-12 | [9 empty] | South | WSIP | [6 empty] | '-119.781476 | 36.8502 | ETL.1760 | 40816897 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120013472 | Not Scheduled | DI CRCRN-OLIVE SW ST 55/422 RMV VEG |  | CORCORAN-OLIVE SW STA | 055/422 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-11-10 | 2021-11-10 | [9 empty] | South | WSIP | [6 empty] | '-119.455956 | 35.8841 | ETL.1310 | 41127863 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120017996 | Feb | DI KEARNEY-KERMAN 10/10 RPR SPLW | 44543954 | KEARNEY-KERMAN | 010/010 | ICW | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Downgraded Splice Project | 2020-11-10 | 2021-11-10 | 2021-02-03 | 2021-02-03 | 2021-02-03 | 2021-02-03 | [5 empty] | South | WSIP | [6 empty] | '-120.053999 | 36.6914 | ETL.8840 | 43686201 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-11-17 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 120047863 | Feb | DI GLENN #5 3/64 RPLC STRW | 31519091 | GLENN #5 | 003/064 | 70Y | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Clearance restriction (circuit efficiency) | 2020-11-16 | 2021-11-16 |  |  | 2021-02-19 | 2021-02-18 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.197002 | 39.768 | ETL.8427 | 40809232 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 70 | Feb |  |  | 2021-02-08 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 120048035 | Not Scheduled | EI GREGG-ASHLAN A002/015 RMV VEG |  | GREGG-ASHLAN (NO FLY) | A002/015 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-11-16 | 2021-11-16 | [9 empty] | South | WSIP | [6 empty] | '-119.88981 | 36.8289 | ETL.4820 | 40761644 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120079903 | Not Scheduled | EI RIO OSO-LOCKEFORD :1/006 REM VEG |  | RIO OSO-LOCKEFORD | :001/006 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-11-20 | 2021-11-20 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.106346 | 38.1213 | ETL.5620 | 40803585 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120090694 | Not Scheduled | Jefferson - Martin | 31519252 | ETU.9931 | MARTIN SUB TERM | 72Z | E | 2020_(9d) All other tags | Underground Transmission | 2020-11-24 | 2021-11-24 | [9 empty] | Central | [7 empty] | '-122.410334 | 37.7026 | ETU.9931 | 41353899 | Distrib Temp Sensor-Underground | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Capital | 377 | Martin |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 72Z | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120106995 | Feb | DI VACA-SUISUN 15/108 RPR SPLS | 44574891 | VACA-SUISUN | 015/108 | ICS | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Downgraded Splice Project | 2020-11-25 | 2021-11-25 |  |  | 2021-02-15 | 2021-02-15 | [5 empty] | North Valley | WSIP | [6 empty] | 122.0936 | 38.2406 | ETL.4070 | 40889585 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End Before Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-11 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 120110473 | Not Scheduled | T2NT DVDE-VANDENBERG #1 002/014 RPR ROAD | 44579804 | DIVIDE-VANDENBERG #1 | 002/014 | CHS | F | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-11-30 | 2022-11-30 |  |  |  | 2021-01-04 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.472805 | 34.8062 | ETL.8620 | 44564341 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120111108 | Not Scheduled | ZA-1-230 kV MH#1 repair ladder-up | 44572549 | ETU.9921.MANH | 1 | ICU | E | 2020_(9d) All other tags | Underground Transmission | 2020-11-25 | 2021-11-24 | [9 empty] | Central | [7 empty] | '-122.389623 | 37.7891 | ETU.9921 | 44249025 | Enclosure / Vault-Underground | No Good/Out of Stdrd | Repair | UNSE htnl | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Expense | 629 | Martin |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120112589 | Q2 | T2NT KESWICK-CASCADE 1/036 RPR ROAD | 44575105 | KESWICK-CASCADE | 001/036 | CHS | F | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-12-01 | 2022-12-01 |  |  | 2021-06-15 | 2021-06-15 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.347552 | 40.6714 | ETL.7260 | 40601951 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Table Mountain |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | CH | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 120114555 | Feb | DI RAVENSWOOD-SAN MATEO 010/075 RPL INSS | 31528731 | RAVENSWOOD-SAN MATEO | 010/075 | 93K | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Clearance restriction (circuit efficiency) | 2020-11-24 | 2021-11-24 |  |  | 2021-02-16 | 2021-02-16 | [5 empty] | Central | WSIP | [6 empty] | '-122.313794 | 37.5817 | ETL.3430 | 40779335 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | 93 | Feb |  |  |  |  | Complete | Awaiting ERTC |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 120119152 | Not Scheduled | DI BELL-PLACER 2/18 RMV VEGN |  | BELL-PLACER | 002/018 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-11-23 | 2021-11-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.062242 | 38.9335 | ETL.4395 | 40592840 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120120419 | Not Scheduled | WV MESA-SISQUOC 3/54 RPR FENCE |  | MESA-SISQUOC | 003/054 | CHS | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-12-02 | 2021-12-02 | [9 empty] | South | WSIP | [6 empty] | '-120.439635 | 34.9822 | ETL.2460 | 40811492 | Fence / Gate | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120128453 | Q2 | DI CENTRVLLE-TBL MTN-ORO 21/423 INS MRKW |  | CENTERVILLE-TABLE MTN-OROVILLE | 021/423 | ICW | F | 2020_(9d) All other tags | Planner approved CCSC Check Off List | 2020-11-25 | 2022-11-25 |  |  | 2021-05-24 | 2021-05-24 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.578568 | 39.5089 | ETL.6330 | 44975434 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | IC | Q2 |  |  | 2021-01-27 | Released-Standard | No Estimate | Awaiting Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120131607 | Not Scheduled | T2 DI EXCHEQUER-INDN FLT 23/89 RMV VEG |  | EXCHEQUER-YOSEMITE | 023/089 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-12-04 | 2021-12-04 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-119.975205 | 37.5991 | ETL.8650 | 40871008 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120133682 | Q2 | DAIRYLAND-MENDOTA 3/047 REPL STRW | 31519850 | DAIRYLAND-MENDOTA | 003/047 | 92T | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Project efficiency (capital work) | 2020-12-05 | 2021-12-05 | 2021-04-05 | 2021-04-05 | 2021-04-05 | 2021-04-05 |  |  | 92T/IBT |  |  | South | WSIP | [6 empty] | '-120.328371 | 37.0023 | ETL.1360 | 44191620 | Structure-Wood | No Good/Out of Stdrd | Replace | DOCC | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Contract | Capital | 372 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | 92 | Q2 |  |  | 2021-02-09 | Released-Standard | Complete | Ready for Construction |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 120140748 | Not Scheduled | T2 EXCHEQUER-INDIAN FLAT 23/90 RMV DBRS | 44623675 | EXCHEQUER-YOSEMITE | 023/090 | ICS | F | 2020_(9a) Other ignition related | Project efficiency (capital work) | 2020-12-08 | 2022-12-08 | [7 empty] | TR2 |  | South | WSIP | [6 empty] | '-119.972681 | 37.6005 | ETL.8650 | 40584411 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9a) Other ignition related | Pending Repair
Approved Outside Workplan | 120146549 | Not Scheduled | VACA-VACAVILLE-JMSN-NRTH A2/20 RMV VEG |  | VACA-VACAVILLE-JAMESON-NTH TWR | A002/020 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-12-09 | 2021-12-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.962428 | 38.3987 | ETL.4100 | 40668815 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120147112 | Feb | T2 DI OLEUM-MARTINEZ 2/20 RPR SPLS | 44589050 | OLEUM-MARTINEZ | 002/020 | ICS | E | 2020_(5) TD tag on other lines | Clearance restriction (circuit efficiency) | 2020-12-07 | 2021-12-07 |  |  | 2021-02-23 | 2021-02-23 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.209075 | 38.0306 | ETL.3170 | 40632254 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Feb | Found in 2020 | Not FSR Upgrade | IC | Feb |  |  | 2020-12-22 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(5) TD tag on other lines | Pending Repair
Approved Outside Workplan | 120149572 | Not Scheduled | DI RIO OSO-BRIGHTON 8/54 RMV VEG |  | RIO OSO-BRIGHTON | 008/054 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-12-09 | 2021-12-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.44477 | 38.8228 | ETL.5600 | 40746227 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120158987 | Not Scheduled | EI PEASE-RIO OSO 36/266 RMV VEG |  | PEASE-RIO OSO | 036/263 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-12-09 | 2021-12-09 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.534811 | 38.9697 | ETL.3270 | 40820389 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120160589 | Q2 | T2 EI EXCHQR-INDIAN FLAT 29/149 RMV VEG |  | EXCHEQUER-YOSEMITE | 029/149 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-12-09 | 2021-12-09 |  |  | 2021-06-30 | 2021-03-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.922468 | 37.6643 | ETL.8650 | 40871014 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Q2 | Found in 2020 | Not FSR Upgrade | HNA | Q2 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120161425 | Not Scheduled | T2 BALCH-SANGER 0/5 RPR ROAD | 44644078 | BALCH-SANGER | 000/005 | CHS | F | 2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2020-12-08 | 2022-12-08 |  |  |  | 2021-08-01 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.095437 | 36.9078 | ETL.1050 | 40748612 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 120161595 | Not Scheduled | DI ATWATER-EL CAPITAN 14/98 RMV VEG |  | ATWATER-EL CAPITAN | 014/098 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-12-10 | 2021-12-10 | [9 empty] | South | WSIP | [6 empty] | '-120.59862 | 37.3676 | ETL.1020 | 40873040 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120163131 | Not Scheduled | EI PALERMO-PEASE 0/3 RMV VEG |  | PALERMO-PEASE | :000/003 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-12-10 | 2021-12-10 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.578353 | 39.179 | ETL.3220 | 40911540 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120163438 | Q4 | SALINAS-LAURELES A17/373 RMV VEG |  | SALINAS-LAURELES | A017/373 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-12-10 | 2021-12-10 |  |  | 2021-12-31 | 2021-12-01 | [5 empty] | South | WSIP | [6 empty] | '-121.853954 | 36.5833 | ETL.7930 | 40754642 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Yes | Scheduled Past Due | Scheduled End On/After Today | Scheduled Past Due | Found in 2020 | Not FSR Upgrade | HNA | Q4 |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120210727 | Not Scheduled | TABLE MTN-TESLA 72/286 RMV VEG |  | TABLE MTN-TESLA | 072/286 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-12-11 | 2021-12-11 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.649173 | 38.5431 | ETL.6080 | 40813715 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120221590 | Not Scheduled | DI ATLANTIC-GOLD HILL 18/76 RPLC INSS | 31529042 | ATLANTIC-GOLD HILL | 018/076 | 93K | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Clearance restriction (circuit efficiency) | 2020-12-16 | 2021-12-16 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.255578 | 38.7587 | ETL.4330 | 42567804 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | 93 | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 120224014 | Mar | COLUSA JCT #1 3/074 RPR SPLICE | 44592733 | COLUSA JCT #1 | 003/074 | ICW | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Downgraded Splice Project | 2020-12-17 | 2021-12-17 |  |  | 2021-03-02 | 2021-03-02 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.956277 | 39.1496 | ETL.8390 | 40598098 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 120224024 | Mar | COLUSA JCT #1 13/272 REPAIR SPLICE | 44592733 | COLUSA JCT #1 | 013/272 | ICW | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Downgraded Splice Project | 2020-12-17 | 2021-12-17 |  |  | 2021-03-02 | 2021-03-02 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.885463 | 39.031 | ETL.8390 | 40692117 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2021-01-20 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 120224057 | Mar | COLUSA JCT #1 0/021 RPR SPLICE | 44592733 | COLUSA JCT #1 | 000/021 | ICW | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Downgraded Splice Project | 2020-12-17 | 2021-12-17 |  |  | 2021-03-02 | 2021-03-02 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.980925 | 39.1803 | ETL.8390 | 40592825 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 120227212 | Mar | DI COALINGA #1-SAN MIGUEL 1/37 RPR SPLW | 44598104 | COALINGA #1-SAN MIGUEL | 001/037 | ICW | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Downgraded Splice Project | 2020-12-21 | 2021-12-21 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.365964 | 36.1177 | ETL.8580 | 40766230 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-29 | Released-SpecialCond | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 120227215 | Mar | DI COALINGA #1-SAN MIGUEL 1/30 RPR SPLW | 44598105 | COALINGA #1-SAN MIGUEL | 001/030 | ICW | E | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Downgraded Splice Project | 2020-12-21 | 2021-12-21 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-15 | [5 empty] | South | WSIP | [6 empty] | '-120.360907 | 36.1216 | ETL.8580 | 40806414 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Mar | Found in 2020 | Not FSR Upgrade | IC | Mar |  |  | 2020-12-29 | Released-Standard | Incomplete, In Estimating | Awaiting Job Package |  | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 120227258 | Not Scheduled | DI COALINGA #1-SAN MIGUEL 0/7 RMV VEG |  | COALINGA #1-SAN MIGUEL | 000/007 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-12-21 | 2021-12-21 | [9 empty] | South | WSIP | [6 empty] | '-120.343821 | 36.131 | ETL.8580 | 40806412 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120227593 | Not Scheduled | SAN LUIS OBISPO-CAYUCOS 21/193 RMV VEG |  | SAN LUIS OBISPO-CAYUCOS | 021/193 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-12-21 | 2021-12-21 | [9 empty] | South | WSIP | [6 empty] | '-120.850095 | 35.4296 | ETL.9090 | 40869444 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120231175 | Not Scheduled | EI TABLE MTN-TESLA 95/373 RMV VEGN |  | TABLE MTN-TESLA | 095/373 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-12-23 | 2021-12-23 | [9 empty] | North Valley | WSIP | [6 empty] | '-121.735492 | 38.2306 | ETL.6080 | 40653572 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  |  | No | Yes | M&C Tag | No | North Valley |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120256600 | Not Scheduled | DEL MONTE-FORT ORD #1 003/057 RMV VEG |  | DEL MONTE-FORT ORD #1 (NO FLY) | 003/057 | HNA | E | 2020_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2020-07-29 | 2021-07-29 | [9 empty] | South | WSIP | [6 empty] | '-121.813222 | 36.6265 | ETL.8400 | 40614050 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Not Scheduled | Found in 2020 | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2020_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120402394 | Not Scheduled | LLAGAS-HOLLISTER_000/000A RMV VEGN |  | LLAGAS-HOLLISTER | 000/000A | HNA | E | 2021_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2021-01-07 | 2022-01-07 | [9 empty] | South | WSIP | [6 empty] | '-121.555257 | 36.8869 | ETL.2911 | 43242763 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2021_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120422013 | Not Scheduled | MONTA VISTA-WOLFE_10321 | 44622974 | ETU.9991 |  | ICU | E | 2021_(9d) All other tags | Underground Transmission | 2021-01-12 | 2022-01-12 | [9 empty] | Central | [7 empty] | '-122.0650471 | 37.3348 | ETU.9991 |  | Cable-Underground | No Good/Out of Stdrd | Repair | UNSE htnl | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Expense | 629 | Martin |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120428225 | Not Scheduled | A-H-W #1 MH#4 pipe-to-soil | 44624069 | ETU.9950 | 217-4 | ICU | E | 2021_(9d) All other tags | Underground Transmission | 2021-01-14 | 2022-01-14 | [9 empty] | Central | [7 empty] | '-122.401064 | 37.7177 | ETU.9950 | 41113047 | Pipe / Duct-Underground | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Expense | 629 | Martin |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120428228 | Not Scheduled | A-H-W #1 MH#5 pipe-to-soil | 44624070 | ETU.9950 | 217-5 | ICU | E | 2021_(9d) All other tags | Underground Transmission | 2021-01-14 | 2022-01-14 | [9 empty] | Central | [7 empty] | '-122.402324 | 37.7244 | ETU.9950 | 41113048 | Pipe / Duct-Underground | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TUG | Maintenance | Expense | 629 | Martin |  |  |  | No | Yes | M&C Tag | No | Central |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | IC | Not Scheduled |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120463072 | Not Scheduled | EI DINUBA ENERGY TAP 0/017 RMV PALMS |  | DINUBA ENERGY TAP | 000/017 | HNA | E | 2021_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2021-01-25 | 2022-01-25 | [9 empty] | South | WSIP | [6 empty] | '-119.384715 | 36.5748 | ETL.9051 | 40821745 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2021_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120470992 | Q2 | EI NAVY LAB TAP 000/003 RPR SPLW | 44638257 | NAVY LAB TAP (NO FLY) | 000/003 | ICW | E | 2021_(9c) Time-dependent non-HFTD tags, (last year and later) | Downgraded Splice Project | 2021-01-27 | 2022-01-27 | 2021-04-13 | 2021-04-13 | 2021-04-13 | 2021-04-13 | [5 empty] | South | WSIP | [6 empty] | '-121.864319 | 36.5894 | ETL.6711 | 40668641 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | No | Scheduled | Scheduled End On/After Today | Found in 2021 | Q2 | Not FSR Upgrade | IC | Q2 |  |  |  |  | Incomplete, In Estimating | Need ERTC & Job Package |  | 2021_(9c) Time-dependent non-HFTD tags, (last year and later) | Pending Repair
Approved Outside Workplan | 120470996 | Not Scheduled | EI PASO ROBLES-TEMPLETN 2/043 RMV VEG |  | PASO ROBLES-TEMPLETON | 002/043 | HNA | E | 2021_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2021-01-27 | 2022-01-27 | [9 empty] | South | WSIP | [6 empty] | '-120.681198 | 35.5803 | ETL.9400 | 40823296 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | HNA | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2021_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120490962 | Not Scheduled | ARCO-CHOLAME 70 KV CROSSING REPAIRS AND |  | ARCO-CHOLAME |  | 71Y | F | 2021_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2021-01-15 | 2023-01-15 | [9 empty] | South | WSIP | [8 empty] | ETL.8440 |  | Road | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLR | Roads | Capital | 374 | Pismo Beach |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2021_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120505650 | Not Scheduled | DUNLAP TAP 15/14 ACCESS ROAD OBSTRUCTION |  | DUNLAP TAP | 015/014 | CHS | F | 2021_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) | 2021-02-04 | 2023-02-04 |  |  |  | 2021-02-15 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.031207 | 36.7075 | ETL.9061 | 40747119 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2021_(5b) On structure in bucket 5 | Pending Repair
Approved Outside Workplan | 120505655 | Not Scheduled | GATES-TULARE LAKE ACCESS ROADS CONSTRUCT |  | GATES-TULARE LAKE | 007/011 | 71Y | F | 2021_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2021-02-04 | 2023-02-04 |  |  |  | 2021-07-01 | [5 empty] | South | WSIP | [6 empty] | '-120.092671 | 36.0387 | ETL.8700 | 40581823 | Road | Missing | Install |  |  |  |  | PEND | LC | TLR | Roads | Capital | 374 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | 71 | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2021_(9d) All other tags | Pending Repair
Approved Outside Workplan | 120505657 | Not Scheduled | HELMS-GREGG ACCESS ROADS 2/21A VGETATION |  | HELMS-GREGG #1 | 002/021A | CHS | F | 2021_(9d) All other tags | Budget Owner (Veg/Land/Road) | 2021-02-04 | 2023-02-04 |  |  |  | 2021-12-01 | [5 empty] | South | WSIP | [6 empty] | '-119.001397 | 37.023 | ETL.4870 | 40576280 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Fresno |  |  |  | No | Yes | M&C Tag | No | South |  |  | Pending Repair | Pending Repair | No |  | Not Scheduled | Not Scheduled | No Scheduled End | Found in 2021 | Not Scheduled | Not FSR Upgrade | CH | Not Scheduled |  |  |  |  | No Estimate | Need ERTC & Job Package |  | 2021_(9d) All other tags | Pending Repair