## Definitions - EDIT HERE
Column | Source | Point of Contact | Date Added | Definition / Purpose | Current Order | updated Order | [REDACTED] Notes
Region | Reference File |  |  | Based on Division / Location | 1 | 1
Div | SAP Notification / Order |  |  |  | 2 | 2
City | From SAP Notification |  |  |  | 16 | 3
Main Work Center | SAP Order |  |  |  | 3 | 4
Resource | MPP Import File |  |  | Resources are coming from the MPP import file. For switches between MPP and DO resources, once RCRs are approved, the WPML is updated within a couple of business days to reflect changes. For changes made between DO resources, see "Exception file" link in "Useful Links" table for details. | 4 | 5
Civil Support | MPP Import File |  |  |  | 5 | 6
Notif Status | Calculation |  |  | Based on the "Notif Ref Date" in WWE file. | 6 | 7
Notification | SAP Notification |  |  | From SAP | 7 | 8
Notification Desc | SAP Notification |  |  | From SAP | 8 | 9
Order | SAP Order |  |  | Order associated to the notification. Note: some orders will have multiple Notifications. If blank, the order has not yet been created in SAP. | 9 | 10
Job Owner | SAP Order |  | 2020-10-07 | Job Owner LanID, who has been assigned to the Order in SAP. | 10 | 11
Job Owner Name | SAP Order |  | 2020-10-07 | Job Owner Name who has been assigned to the Order in SAP. | 11 | 12
Order Desc | SAP Order |  |  |  | 54 | 13
Primary Status | Calculation |  |  | Based on the SAP User Status | 55 | 14
Order User Status | SAP Order |  |  |  | 56 | 15
Program | Calculation / MPP Import File |  |  |  | 27 | 16
Category | Calculation |  |  |  | 28 | 17
Sub-Category | Calculation |  |  |  | 29 | 18
MAT | Calculation |  |  | Maps the Notification Work Type Code to MAT code. If no Notification then Order MAT code is used. | 30 | 19
Work Plan Date | Calculation / DO/MPP Import files |  |  | If source file for the job is DO (see "Unique List of MATs..." table for details), then see "Logic File" in "Useful Links" table for information on how the WPD is determined. MPP projects; P6 BL Construction start date if there is one, | 12 | 20
Work Plan Year | MPP: MPP Import File |  |  |  | 13 | 21 | to be renamed (Initial Funding Year)
Planned Construction Complete Year | Calculation |  |  | Year of the P6 FISD baseline date, if not available it defaults to Initial funding year |  | 22
Work Plan Deferral Year | MPP Import File |  |  | Year the project has been deferred to | 72 | 23 | to be renamed (New Construction Complete Year)
2020 funded | Calculation |  |  | Represents if the project is funded for the year (it allows to manage funding status on multi year projects, deferred projects and program managed work) |  | 24
2021 funded | Calculation |  |  | Represents if the project is funded for the year (it allows to manage funding status on multi year projects, deferred projects and program managed work) |  | 25
2022 funded | Calculation |  |  | Represents if the project is funded for the year (it allows to manage funding status on multi year projects, deferred projects and program managed work) |  | 26
2023 funded | Calculation |  |  | Represents if the project is funded for the year (it allows to manage funding status on multi year projects, deferred projects and program managed work) |  | 27
Project Reporting Year | Calculation |  |  | Can be used to sort for work plan by year |  | 28
Order Readiness | Calculation |  |  | Closed - If notification is closed and no order assigned. Pending Verification - Order user status is UNSC and Order exists in the pending verification reference file Needs Order, Estimated - No order assigned and is estimate required Estimating - Order user status is either UNSE, ESTS, ADER, APPR or POST Pending - Order user status is PEND Ready - Order user status is UNSC or CONS Closed - Order user status is CLSD or CNCL Beyond CONS - if it doesn't fall within above statements then it is assigned beyond CONS | 14 | 29
Open Dependencies | Calculation |  |  | Logic based on open dependencies (task data) | 15 | 30
Permit Exp Date | ZPERMIT |  |  |  | 17 | 31
Permit Action | Calculation |  |  | No Action - if Readiness is Beyond CONS or Closed Renew Permit - if Permit Exp Date is earlier than today's date No Action - if click end date is earlier than 3 weeks prior to the permit exp date Change Schedule/Request Extension - if click end date is later than 4 weeks prior to the permit exp date Permit Expiring Schedule Job/Request Extenseion - if click end date is blank and 4 weeks prior the permit exp date has passed | 18 | 32
Latitude | SAP Notification |  |  |  | 19 | 33
Longitude | SAP Notification |  |  |  | 20 | 34
Loading Order | Reference File |  |  | Helps determine the risk of the job | 21 | 35
HFTD | SAP Notification |  |  | High Fire Threat District | 22 | 36
Circuit Rank | Reference File |  |  | Circuits are ranked based on risk | 23 | 37
Circuit | From SAP Notification |  |  |  | 24 | 38
Plat Map | SAP Notification |  |  |  | 25 | 39
Source Side Device | SAP Notification |  |  |  | 26 | 40
Est Req | Calculation |  |  | Flag if an order/notification needs an estimate | 31 | 41
Work Type Code | SAP Notification |  |  | From SAP Notification. WTC=564 is part of the HNA Mat that is part of the Veg Management organization and excluded from the WPML. | 32 | 42
CLICK Resource | Click / Order Operation |  |  | Historicals are pulled from the order operation | 33 | 43
CLICK Crew Class | Click / Order Operation |  |  | Historicals are pulled from the order operation | 34 | 44
CLICK Start Date | Click / Order Operation |  |  | Historicals are pulled from the order operation | 35 | 45
CLICK End Date | Click / Order Operation |  |  | Historicals are pulled from the order operation | 36 | 46
CLICK Source | Calculation |  |  | Flag to signify if click schedule was pulled from Click or Order Operation. Historicals are pulled from the Order Operation | 37 | 47
Unit Measure | DOT - SAP UC50 |  | 2020-11-03 | This reflects the Primary Unit Measure entered into SAP for each Order | 38 | 48
Unit Measure Desc | DOT - SAP UC50 |  | 2020-11-03 | This reflects the Primary Unit Measure Desc entered into SAP for each Order | 39 | 49
Plan | DOT - SAP UC50 |  | 2020-11-03 | This reflects the Primary Planned Units entered into SAP for each Order | 40 | 50
Actual | DOT - SAP UC50 |  | 2020-11-03 | This reflects the Primary Actual Units that have been entered into SAP once the project has been completed. | 41 | 51
Est Const Hours | SAP Order Operation |  |  | Planned Construction Hours | 42 | 52
Act Const Hours | SAP Order Operation |  |  |  | 43 | 53
Rem Const Hours | SAP Operation |  |  |  | 44 | 54
Notification Type | SAP Notification |  |  |  | 45 | 55
Priority | SAP Notification |  |  |  | 46 | 56
Object Code Text | SAP Notification |  |  |  | 47 | 57
Damage Code Text | SAP Notification |  |  | FDA - Damage details of the notification. | 48 | 58
Activity Code Text | SAP Notification |  |  |  | 49 | 59
M&C Notif Tracking | SAP Notification |  |  |  | 50 | 60
Equipment | SAP Notification |  |  |  | 51 | 61
Notif User Status | SAP Notification |  |  |  | 52 | 62
Pole/Cap/Exp | Reference File |  |  | Reference file based on Work Type Code | 53 | 63
CN24 Out Date | SAP Task |  |  | Field Construction Complete Out Date | 57 | 64
SP56 Out | SAP Task |  |  | Encroachment permits sent to city/county | 58 | 65
RP56 Out | SAP Task |  |  | Received documents for city/county encroachment permit(s) | 59 | 66
CSTRT BL Date (P6) | P6 |  | 2020-10-07 | Construction Start Baseline Date. This is the date when construction (civil, electrical, tower, line, grading etc.) starts on a project. Including crew mobilization | 60 | 67
CSTRT Finish Date (P6) | P6 |  | 2020-10-07 | Construction Start Date. This is the date when construction (civil, electrical, tower, line, grading etc.) starts on a project. Including crew mobilization | 61 | 68
CENDD BL Date (P6) | P6 |  | 2020-10-07 | Construction Finish Baseline Date. This is the date when construction (civil, electrical, tower, line, grading etc.) starts on a project. Including crew mobilization | 62 | 69
CENDD Finish Date (P6) | P6 |  | 2020-10-07 | Construction Finish Date. This is the date when construction (civil, electrical, tower, line, grading etc.) starts on a project. Including crew mobilization | 63 | 70
FISD BL Date (P6) | P6 |  | 2020-10-07 | Forecast in Service Baseline Date. This date is defined as the forecast date the project will be energized and placed in service, based on the project’s current CPM schedule plan performance. This date must be before or at the baseline date to be on schedule. | 64 | 71
FISD Finish Date (P6) | P6 |  | 2020-10-07 | Forecast in Service date. This date is defined as the forecast date the project will be energized and placed in service, based on the project’s current CPM schedule plan performance. This date must be before or at the baseline date to be on schedule. | 65 | 72
FISD Actualized | P6 |  | 2020-10-07 | FISD Actualized will show Actualized if the milestone has been completed, or Forecasted if the milestone has not been completed yet. | 66 | 73
Completion Date | SAP Notification |  |  | Date that construction was done and the notification was marked COMP, either in the Notif task screen or PM Order task DC33. | 67 | 74
Reference Date | SAP Notification |  |  | Not a static field, this date can indicate when the staging notification (S6, S9, etc) was completed, and will overwrite with the date the Notification (EC, CE, etc) was completed in SAP. | 68 | 75
Req End Date | SAP Notification |  |  | Automated date from SAP for required Order completion and closure, based on date issue was found and tag Priority level (A-H). | 69 | 76
Funded Repair Date | SAP Notification |  |  | Date entered by the Compliance team that overrides the original Req End Date, either bringing date forward or moved out as determined by extenuating circumstances. | 70 | 77
Authorized End Date | Calculation |  |  | Based on the Funded Repair Date of the Notification if avaialble, if not use Required End Date | 71 | 78
Origin | MPP Import File |  |  |  | 73 | 79
Est Out Date | SAP Order |  |  | Estimating's goal for B tags is to have them out of Estimating within 30 days of receiving the tag. | 74 | 80
Est Assignment | SAP Order |  |  |  | 75 | 81
Est Resource | SAP Order |  |  |  | 76 | 82
Circuit ID | From SAP Notification |  |  |  | 77 | 83
Plan Hours | Reference File |  |  | Hours per Unit file | 78 | 84
Authorized Amt | DOT - SAP BW (ORD999) |  | 2020-10-16 | The Total Authorized Amount includes all capital and expense for the entire project, including Risk Allowance. This is also known as the High Case of the project. This can be found SAP in the ZORDER screen. | 79 | 85
ITD Actual Amt | DOT - SAP BW (ORD999) |  | 2020-10-16 | Inception to Date Actual Amt includes prior year spend plus current year spend. | 80 | 86
YTD Actual Amt | DOT - SAP BW (ORD999) |  | 2020-10-16 | Year to Date Actual Amt includes spend that occurred in the current year. | 81 | 87
CY EAC (PRJ) | DOT - SAP BW (ORD999) |  | 2020-10-16 | Estimate at Completion - The total forecasted cost of the project is measured by the actual costs from the beginning of the fiscal year to the last closted month + the PRJ forecast to the end of the year. | 82 | 88
CY EAC (PRB) | DOT - SAP BW (ORD999) |  | 2020-10-16 | Estimate at Completion - The total forecasted cost of the project is measured by the actual costs from the beginning of the fiscal year to the last closted month + the PRB (Project Baseline Budget) to the end of the year. PRB: Reflects the approved annual budget within the Actual Orders for Project Management. Once a year, after the annual DET is taken, targets are copied from PRJ into PRB to set the annual Budget/Baseline for Project Management Work. | 83 | 89
MPP Approved Budget (2020) | DOT - SAP BW (ORD999) |  | 2020-10-16 | April PRM (Monthly Project Forecast Snapshot) plus any approved budget changes that occurred through the legacy change control process (weekly calls) or through the new DOT change process. | 84 | 90
Source Data | Calculation |  |  |  | 85 | 91
Project Managed Flag | Reference File | Erica Sinkey | 2020-10-16 | Flag is set to Y if the Job Owner is found in the Job Owner reference table for Project Management. | 86 | 92
MPP Flag | Calculation |  |  | Flag is set to Y if the Order/Notification is in the import file | 87 | 93
LoadDate | MPP Import File |  |  | When Order/Notification was added to the MPP import file | 88 | 94
MPP Approved Budget (2021) | DOT - SAP BW (ORD999) | Erica Sinkey | 2020-10-16 | Approved Budget Changes that occurred through the new DOT change process; if not, defaults to 2021 PRB Budget for Project Managed Work.
Current Year Organization | DOT - SAP BW (ORD999) | Erica Sinkey | 2020-10-16 | Current Year Organization is used to flag the Budget Owner assigned to an order. This includes Electric Transmission, Distribution, FRMMA/WMPMA, and others.
New Construction Complete Year | MPP Import File |  | 2020-10-19 | Year the project has been deferred to
Initial Funding Year | MPP Import File |  | 2020-10-19
CSTRT Actualized | Calculation / P6 | Erica Sinkey | 2020-10-19 | CSTRT Actualized will flag the order as "Actualized" if the CSTRT Metric Milestone has been completed. It will flag the order as "Forecasted" if the Metric Milestone has not been completed.
CENDD Actualized | Calculation / P6 | Erica Sinkey | 2020-10-19 | CENDD Actualized will flag the order as "Actualized" if the CENDD Metric Milestone has been completed. It will flag the order as "Forecasted" if the Metric Milestone has not been completed.
Total MPP Approved Budget | Calculation | Erica Sinkey | 2020-10-19 | The Total MPP Approved Budget is the sum of MPP Approved Budget (2020) and MPP Approved Budget (2021)
OH Elec Est Cons Hours | SAP Order Operation | Erica Sinkey | 2020-11-10 | Total estimate hours for OH construction ; Crew Class's included: GC_ECNT4, GC_ECNT5, NEW_E.
UG Elec Est Cons Hours | SAP Order Operation | Erica Sinkey | 2020-11-10 | Total estimate hours for UG construction ; Crew Class's included: UG.
Civil Est Cons Hours | SAP Order Operation | Erica Sinkey | 2020-11-10 | Total estimate hours for Civil construction ; Crew Class's included: GC_CNT, GC_Gas, GD_C.
OH Elec Rem Cons Hours | SAP Order Operation | Erica Sinkey | 2020-11-10 | Total remaining hours for OH construction ; Crew Class's included: GC_ECNT4, GC_ECNT5, NEW_E ; Excludes completed operations.
UG Elec Rem Cons Hours | SAP Order Operation | Erica Sinkey | 2020-11-10 | Total remaining hours for UG construction ; Crew Class's included: UG. Excludes completed operations.
Civil Rem Cons Hours | SAP Order Operation | Erica Sinkey | 2020-11-10 | Total remaining hours for Civil construction ; Crew Class's included: GC_CNT, GC_Gas, GD_C. Excludes completed operations.
CBP 2020 Flag |  | Erica Sinkey
EENDT BL Date (P6) | P6 | Erica Sinkey | 2020-01-29 | Engineering End Baseline Date. This is the date when all main engineering tasks are completed, including, but not limited to, EMM's, F1004 (Caiso Form), Outdoor, Indoor, T-Line, Civil Design, and Job Estimates are completed. This date is an indication when the PE has switched from a lead role to a support role in construction.
EENDT Finish Date (P6) | P6 | Erica Sinkey | 2020-01-29 | Engineering End Date. This is the date when all main engineering tasks are completed, including, but not limited to, EMM's, F1004 (Caiso Form), Outdoor, Indoor, T-Line, Civil Design, and Job Estimates are completed. This date is an indication when the PE has switched from a lead role to a support role in construction.
EENDT Actualized | Calculation / P6 | Erica Sinkey | 2020-01-29 | EENDT Actualized will flag the order as "Actualized" if the EENDT Metric Milestone has been completed. It will flag the order as "Forecasted" if the Metric Milestone has not been completed.
2020 Planned Units | DOT - SAP UC50 | Erica Sinkey | 2020-01-29 | This reflects the 2020 Primary Planned Units entered into SAP for each Order.
2020 Actual Units | DOT - SAP UC50 | Erica Sinkey | 2020-01-29 | This reflects the 2020 Primary Actual Units that have been entered into SAP once the project has been completed.
2021 Planned Units | DOT - SAP UC50 | Erica Sinkey | 2020-01-29 | This reflects the 2021 Primary Planned Units entered into SAP for each Order.
2021 Actual Units | DOT - SAP UC50 | Erica Sinkey | 2020-01-29 | This reflects the 2021 Primary Actual Units that have been entered into SAP once the project has been completed.

## MPP Data
Region | Div | City | Main Work Center | Resource | Civil Support | Notif Status | Notification | Notification Desc | Order | Job Owner | Job Owner Name | Order Desc | Primary Status | Order User Status | Program | Category | Sub-Category | MAT | Population | Sub-Population | Strike Force Loading Order | Exclusion Notes | Business Justification | 2021 Loading Order | Work Plan Date | Initial Funding Year | Planned Construction Complete Year | New Construction Complete Year | 2020 Funded | 2021 Funded | 2022 Funded | 2023 Funded | Project Reporting Year | Order Readiness | Open Dependencies | Permit Exp Date | Permit Action | Latitude | Longitude | 1 thru N Rank | HFTD | Circuit Rank | Circuit | Plat Map | Source Side Device | Est Req | Work Type Code | CLICK Resource | CLICK Crew Class | CLICK Start Date | CLICK End Date | CLICK Oper User Status | CLICK Source | Unit Measure | Unit Measure Desc | 2020 Planned Units | 2020 Actual Units | 2021 Planned Units | 2021 Actual Units | Est Const Hours | OH Elec Est Cons Hours | UG Elec Est Cons Hours | Civil Est Cons Hours | Act Const Hours | Rem Const Hours | OH Elec Rem Cons Hours | UG Elec Rem Cons Hours | Civil Rem Cons Hours | Notification Type | Priority | Object Code Text | Damage Code Text | Activity Code Text | M&C Notif Tracking | Equipment | Notif User Status | Pole/Cap/Exp | PEND In Date | UNSC In Date | DS18 | DS18 Out Date | CN24 | CN24 Out Date | SP56 Out | RP56 Out | DS83 | DS83 Out | CSTRT BL Date (P6) | CSTRT Finish Date (P6) | CSTRT Actualized | CENDD BL Date (P6) | CENDD Finish Date (P6) | CENDD Actualized | EENDT BL Date (P6) | EENDT Finish Date (P6) | EENDT Actualized | Completion Date | Reference Date | Req End Date | Funded Repair Date | Authorized End Date | Origin | Est Out Date | Est Assignment | Est Resource | Circuit ID | Authorized Amt | ITD Actual Amt | YTD Actual Amt | CY EAC (PRJ) | CY EAC (PRB) | MPP Approved Budget (2020) | MPP Approved Budget (2021) | Total MPP Approved Budget | Current Year Organization | CBP 2020 Flag | Source Data | Project Managed Flag | Past Due Reason | MPP Flag | LoadDate
Bay/Central | DI | ANTIOCH | Antioch |  |  | OPEN | 117072623 | POLE_BROK_REPL - #1 E/O 5655 CHADBOURNE | 35215506 |  |  | STS-POLE_BROK_REPL - #1 E/O 5655 CHADBOU | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.9255 | -121.803 |  | TIER 2 | 1111 | 01323-2105, LONE TREE | D16 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 17.5 | 17.5 |  |  | 0 | 17.5 | 17.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100483929 | OH PRI CLR JPOL GO RELW REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-17 |  | COMP | 2021-02-17 | [16 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013232105 | 9840.28 | 66.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | BRENTWOOD | Antioch |  |  | OPEN | 117072624 | POLE_BROK_REPL - #1 S/O ENTRANCE 7247 CH | 35215511 |  |  | STS-POLE_BROK_REPL - #1 S/O ENTRANCE 724 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.9245 | -121.8058 |  | TIER 2 | 1111 | 01323-2105, LONE TREE | D16 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100483916 | RELW OH PRI CLR JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013232105 | 1 | 86.8 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | BRENTWOOD | Antioch |  |  | OPEN | 117143314 | POLE_BROK_REPL - #3S MARSH CREEK RD ON L | 35202442 |  |  | STS-POLE_BROK_REPL - #3S MARSH CREEK RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.8692 | -121.7421 |  | TIER 2 | 224 | 01202-2212, CLAYTON | E18 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 13.8 | 13.8 |  |  | 0 | 13.8 | 13.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100496392 | OH RELW PRI CLR JPOL RESD REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-08 |  | COMP | 2021-01-08 | [16 empty] | 2019-05-02 | 2020-05-02 | 2020-10-17 | 2020-10-17 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 012022212 | 6398.94 | 713.4 | -90.5 | 199.3 | 199.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | BRENTWOOD | Antioch |  |  | OPEN | 117147353 | POLE_DECA_REPL - #2W 18700 MARSH CREEK R | 35215114 |  |  | STS-POLE_DECA_REPL - #2W 18700 MARSH CRE | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.8781 | -121.7677 |  | TIER 2 | 224 | 01202-2212, CLAYTON | E17 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 14.8 | 14.8 |  |  | 0 | 14.8 | 14.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100496252 | RELW OH PRI CLR JPOL RESD FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-27 |  | COMP | 2021-01-27 | [16 empty] | 2019-05-02 | 2020-05-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012022212 | 12135.1 | 164.3 | 110.9 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | BRENTWOOD | Antioch |  |  | OPEN | 117160074 | POLE_DECA_REPL - 17301 MARSH CREEK RD W/ | 35215238 |  |  | STS-POLE_DECA_REPL - 17301 MARSH CREEK R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.8914 | -121.7886 |  | TIER 2 | 224 | 01202-2212, CLAYTON | E17 | 2944 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100496187 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012022212 | 1 | 100.2 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | BRENTWOOD | Antioch |  |  | OPEN | 117160219 | POLE_DECA_REPL - #2W ON LINE @ 17301 MAR | 35202479 |  |  | STS-POLE_DECA_REPL - #2W ON LINE @ 17301 | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 37.8923 | -121.7904 |  | TIER 2 | 224 | 01202-2212, CLAYTON | E17 | 2944 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 34.7 | 34.7 |  |  | 0 | 34.7 | 34.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100496184 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-18 |  | COMP | 2020-12-18 | [16 empty] | 2019-05-04 | 2020-05-04 | 2020-10-17 | 2020-10-17 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 012022212 | 17330.52 | 226.6 | 0 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | CLAYTON | Concord |  |  | OPEN | 117156480 | POLE_DECA_REPL - #3E 18900 MARSH CREEK R | 35202473 |  |  | STS-POLE_DECA_REPL - #3E 18900 MARSH CRE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.8749 | -121.763 |  | TIER 2 | 224 | 01202-2212, CLAYTON | E17 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100496288 | RELW OH PRI PGEA CLR RESD REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2020-10-17 | 2020-10-17 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 012022212 | 1 | 131.2 | 104.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | CLAYTON | Concord |  |  | OPEN | 117156841 | POLE_DECA_REPL - #4E 18900 MARSH CREEK R | 35215184 |  |  | STS-POLE_DECA_REPL - #4E 18900 MARSH CRE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.8742 | -121.7618 |  | TIER 2 | 224 | 01202-2212, CLAYTON | E17 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 18 | 18 |  |  | 0 | 18 | 18 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100496290 | RELW OH PRI PGEA CLR REMT FMOB ESTR REAR USA TER2 PRTO FSRP | Pole | 2021-02-04 |  | COMP | 2021-02-04 | [16 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012022212 | 8191.94 | 368.8 | 315.3 | 280.5 | 280.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | CLAYTON | Concord |  |  | OPEN | 117163287 | POLE_DECA_REPL - #2NE 16300 MARSH CREEK | 35215282 |  |  | STS-POLE_DECA_REPL - #2NE 16300 MARSH CR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.8939 | -121.7964 |  | TIER 2 | 224 | 01202-2212, CLAYTON | E17 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100496160 | RELW OH PRI PGEA CLR RESD REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012022212 | 1 | 121.6 | 81.5 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | CONCORD | Antioch |  |  | OPEN | 117191946 | POLE_LEAN_REPL - 9W/O 104 AVILA RD CONCO | 35202561 |  |  | STS-POLE_LEAN_REPL - 9W/O 104 AVILA RD C | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.0143 | -121.9926 |  | TIER 2 | 403 | 01391-1101, WILLOW PASS | B1207 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Leaning | Replace |  | 100449680 | RELW OH PRI JPOL REMT FLAG GO BTKA USA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-09 | 2020-05-09 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013911101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | DANVILLE | Concord |  |  | COMP | 117076838 | POLE_DECA_REPL - 3 W/O 1965 DIABLO RDDAN | 35174593 |  |  | B PF STS-POLE_DECA_REPL - 3 W/O 1965 DIA | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-06-21 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-03-08 | No Action | 37.8327 | -121.9582 |  | TIER 2 | 431 | 01466-2112, TASSAJARA | F1311 | 38868 | Y | 311 |  |  | 2021-02-18 07:00 | 2021-02-19 16:00 | Completed | CLICK | [6 empty] | 81.6 | 81.6 |  |  | 246.5 | 0.1 | 0.1 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100502057 | RELW OH PRI INSP COMP CLR JPOL RESD FLAG ESTR BTKA USA CPGG FMOB TER2 FSRP | Pole | 2020-05-26 | 2020-12-09 | COMP | 2020-05-26 |  |  | 2020-12-01 | 2020-12-08 | [11 empty] | 2021-02-22 | 2021-02-19 | 2020-04-22 | 2020-07-19 | 2020-07-19 | B-Tag Clean Up 5/14/20 |  | UNASSIGNED |  | 014662112 | 39137.73 | 29306.6 | 23558.5 | 1819.2 | 1819.2 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-05-25
Bay/Central | DI | DIABLO | Concord |  |  | OPEN | 117051286 | POLE_DECA_REPL - 1984 LA CADENA DIABLO A | 35202341 |  |  | STS-POLE_DECA_REPL - 1984 LA CADENADIABL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 37.8335 | -121.9559 |  | TIER 2 | 431 | 01466-2112, TASSAJARA | F1311 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 10.8 | 10.8 |  |  | 0 | 10.8 | 10.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100502068 | RELW OH PRI INSP ESTR FMOB TER2 FSRP | Pole | 2020-12-22 |  | COMP | 2020-12-22 | [16 empty] | 2019-04-17 | 2020-04-17 | 2020-10-19 | 2020-10-19 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 014662112 | 15399.69 | 1288.8 | 78.7 | -108.6 | -108.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | DIABLO | Concord |  |  | OPEN | 117052009 | POLE_DECA_REPL - 1973 LA CADENADIABLO945 | 35215255 |  |  | STS-POLE_DECA_REPL - 1973 LA CADENADIABL | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.8336 | -121.9563 |  | TIER 2 | 431 | 01466-2112, TASSAJARA | F1311 | 7959 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100502065 | RELW OH PRI INSP CLR JPOL RESD FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014662112 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | LAFAYETTE | Concord |  |  | OPEN | 116760405 | POLE_DECA_REPL - AT 3969 HAPPY VALLEY RD | 35202164 |  |  | STS-POLE_DECA_REPL - AT 3969 HAPPY VALLE | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land JointPole |  |  | 37.9053 | -122.15 |  | TIER 2 | 402 | 01467-1102, SOBRANTE | D0817 | 7725 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100474837 | RELW OH PRI JPOL RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-22 |  | COMP | 2021-01-22 | [16 empty] | 2019-03-18 | 2020-03-18 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 014671102 | 20315.63 | 75.9 | -1013.6 | 172.4 | 172.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | LAFAYETTE | Concord |  |  | OPEN | 116764530 | POLE_DECA_REPL - A/F 3954 LOS ARABIS DR | 35202182 |  |  | STS-POLE_DECA_REPL - A/F 3954 LOS ARABIS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.8957 | -122.1475 |  | TIER 2 | 402 | 01467-1102, SOBRANTE | D0822 | 20234 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.7 | 37.7 |  |  | 0 | 37.7 | 37.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100475132 | RELW OH PRI CLR JPOL RESD FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-16 |  | COMP | 2020-12-16 | [16 empty] | 2019-03-19 | 2020-03-19 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 014671102 | 21368.85 | 1176.3 | 633.3 | -135.8 | -135.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | LAFAYETTE | Concord |  |  | OPEN | 116766892 | POLE_BROK_REPL - A/F 1227 UPPER HAPPY VA | 35215130 |  |  | STS-POLE_BROK_REPL - A/F 1227 UPPER HAPP | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9042 | -122.153 |  | TIER 2 | 402 | 01467-1102, SOBRANTE | D0816 | L510R | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100474812 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-04-14 | 2021-04-14 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014671102 | 1 | 40.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | LAFAYETTE | Concord |  |  | OPEN | 116803914 | POLE_DECA_REPL - 1S/O 4055 HAPPY VALLEY | 35202235 |  |  | STS-POLE_DECA_REPL - 1S/O 4055 HAPPY VAL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9072 | -122.156 |  | TIER 2 | 402 | 01467-1102, SOBRANTE | D0816 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.1 | 21.1 |  |  | 0 | 21.1 | 21.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100474789 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-05 |  | COMP | 2021-02-05 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 014671102 | 12786.71 | 404.4 | -497.8 | -497.8 | -497.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | LAFAYETTE | Concord |  |  | OPEN | 116811651 | POLE_DECA_REPL - 4175 CANYON DR LAFAYETT | 35215445 |  |  | STS-POLE_DECA_REPL - 4175 CANYON DR LAFA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9027 | -122.1587 |  | TIER 2 | 402 | 01467-1102, SOBRANTE | D0821 | 2182 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100474956 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-04-15 | 2021-04-15 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014671102 | 1 | 26.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | LAFAYETTE | Concord |  |  | OPEN | 116818097 | POLE_DECA_REPL - G/P 1148 HAPPY VALLEY R | 35214577 |  |  | STS-POLE_DECA_REPL - G/P 1148 HAPPY VALL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 37.9007 | -122.1495 |  | TIER 2 | 402 | 01467-1102, SOBRANTE | D0822 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100475100 | RELW OH SEC JPOL RESD ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 | 2021-04-14 | 2021-04-14 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014671102 | 1 | 57.5 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | LAFAYETTE | Concord |  |  | OPEN | 116820404 | POLE_DECA_REPL - G/P R/O 46 CHARLES HILL | 35214640 |  |  | STS-POLE_DECA_REPL - G/P R/O 46 CHARLES | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9005 | -122.1661 |  | TIER 2 | 470 | 01467-1101, SOBRANTE | D0725 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100474675 | RELW OH SEC JPOL RESD ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-07-09 | 2021-07-09 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014671101 | 1 | 26.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | LAFAYETTE | Concord |  |  | OPEN | 116846988 | POLE_BROK_REPL - AF 1020 DOLORES DR LAFA | 35214909 |  |  | STS-POLE_BROK_REPL - AF 1020 DOLORES DR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.8932 | -122.1296 |  | TIER 2 | 402 | 01467-1102, SOBRANTE | E0804 | 8080 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100489311 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014671102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | LAFAYETTE | Concord |  |  | OPEN | 116862131 | POLE_BROK_REPL - 3286 VALS LN LAFAYETTE | 35215190 |  |  | STS-POLE_BROK_REPL - 3286 VALS LN LAFAYE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9096 | -122.1013 |  | TIER 2 | 36 | 01416-1101, ROSSMOOR | D0918 | 81770 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100476840 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014161101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | LAFAYETTE | Concord |  |  | OPEN | 116862621 | POLE_BROK_REPL - R/O 3294 PLEASANT HILL | 35215210 |  |  | STS-POLE_BROK_REPL - R/O 3294 PLEASANT H | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land JointPole |  |  | 37.909 | -122.1009 |  | TIER 2 | 36 | 01416-1101, ROSSMOOR | D0918 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100476847 | RELW OH SEC JPOL RESD ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014161101 | 1 | 32.4 | 32.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | LAFAYETTE | Concord |  |  | OPEN | 116865558 | POLE_DECA_REPL - SPRINGHILL ELEMENTARY L | 35215409 |  |  | STS-POLE_DECA_REPL - SPRINGHILL ELEMENTA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9069 | -122.1029 |  | TIER 2 | 85 | 01353-2107, LAKEWOOD | D0918 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103616474 | RELW OH SEC PUBL ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013532107 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | LAFAYETTE | Concord |  |  | OPEN | 116949871 | POLE_DECA_REPL - R/O 8 SESSIONS DR LAFAY | 35214625 |  |  | STS-POLE_DECA_REPL - R/O 8 SESSIONS DR L | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9002 | -122.1146 |  | TIER 2 | 36 | 01416-1101, ROSSMOOR | D0921 | L503R | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103772198 | RELW OH PRI CLR JPOL REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-03 | 2020-04-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014161101 | 1 | 26.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | LAFAYETTE | Concord |  |  | OPEN | 116950023 | POLE_DECA_REPL - 9/W/O/3461 SKYLINE DR L | 35214629 |  |  | STS-POLE_DECA_REPL - 9/W/O/3461 SKYLINE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.8997 | -122.1159 |  | TIER 2 | 36 | 01416-1101, ROSSMOOR | D0921 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100477055 | RELW OH PRI CLR JPOL REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-03 | 2020-04-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014161101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | LAFAYETTE | Concord |  |  | OPEN | 116951587 | POLE_DECA_REPL - 8/W/O/2/N/0/3461 SKYLIN | 35202616 |  |  | STS-POLE_DECA_REPL - 8/W/O/2/N/0/3461 SK | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.9012 | -122.1142 |  | TIER 2 | 36 | 01416-1101, ROSSMOOR | D0921 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 27.9 | 27.9 |  |  | 0 | 27.9 | 27.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100477071 | OH RELW PRI CLR JPOL REAR REMT ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-09 |  | COMP | 2020-12-09 | [16 empty] | 2019-04-03 | 2020-04-03 | 2020-08-11 | 2020-08-11 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 014161101 | 13099.95 | 999 | 972.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | LAFAYETTE | Concord |  |  | OPEN | 116486531 | POLE_BROK_REPL - 779 MORAGA RD LAFAYETTE | 35076744 |  |  | STS-POLE_BROK_REPL - 779 MORAGA RD LAFAY | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-02 | Renew Permit | 37.8808 | -122.1256 |  | TIER 2 | 71 | 01416-1108, ROSSMOOR | E0810 | 8221 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Dispatched | CLICK | [6 empty] | 56.8 | 55.8 | 1 |  | 9 | 56.7 | 55.7 | 1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 103768050 | REGW OH PRI TRAF FLAG ESTR BTKA USA TER2 | Pole | 2019-06-10 | 2019-10-03 | COMP | 2019-06-10 |  |  | 2019-10-01 | 2019-10-03 | [12 empty] | 2019-02-13 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-06-30 | QUES |  | 014161108 | 21840.12 | 6825.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | DI | MARTINEZ | Concord |  |  | OPEN | 117175190 | POLE_DECA_REPL - 1N/O C/O GREEN ST/HILLS | 35202513 |  |  | STS-POLE_DECA_REPL - 1N/O C/O GREEN ST/H | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.0111 | -122.141 |  | TIER 2 | 652 | 01343-2207, FAIRVIEW | B0808 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 15.8 | 15.8 |  |  | 0 | 15.8 | 15.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103885686 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-17 |  | COMP | 2020-12-17 | [16 empty] | 2019-05-07 | 2020-05-07 | 2020-10-18 | 2020-10-18 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013432207 | 9441.83 | 1745.6 | 1141.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | MARTINEZ | Concord |  |  | OPEN | 117176111 | POLE_DECA_REPL - 930 W. ARLINGTON WY MAR | 35215391 |  |  | STS-POLE_DECA_REPL - 930 W. ARLINGTON WY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land JointPole |  |  | 38.0127 | -122.1405 |  | TIER 2 | 652 | 01343-2207, FAIRVIEW | B0808 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100443950 | RELW OH SEC JPOL RESD ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013432207 | 1 | 59.1 | 32.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | MARTINEZ | Concord |  |  | OPEN | 117176352 | POLE_DECA_REPL - 1000 W. ARLINGTON WY MA | 35100973 |  |  | STS-POLE_DECA_REPL - 1000 W. ARLINGTON W | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole | 2021-07-23 |  | 38.0125 | -122.1398 |  | TIER 2 | 652 | 01343-2207, FAIRVIEW | B0808 | 15396 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 121.1 | 118.7 | 2.4 |  | 0 | 121.1 | 118.7 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100443979 | RELW OH PRI CLR JPOL RESD ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2021-02-22 |  | COMP | 2021-02-22 |  |  | 2020-07-14 | 2020-08-14 | [12 empty] | 2019-05-07 | 2019-10-07 | 2020-10-18 | 2020-10-18 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 013432207 | 33300.73 | 3669 | 55.7 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | MARTINEZ | Concord |  |  | OPEN | 117186669 | POLE_DECA_REPL - #1E SHERIDAN LN ON ALHA | 35215475 |  |  | STS-POLE_DECA_REPL - #1E SHERIDAN LN ON | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.9796 | -122.1248 |  | TIER 2 | 131 | 01410-1105, ALHAMBRA | C0805 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100459017 | RELW OH PRI INSP TRAF FLAG ESTR GO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014101105 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | MARTINEZ | Concord |  |  | OPEN | 117205627 | POLE_DECA_REPL - #3N DEODARA WY ON PEGGY | 35202567 |  |  | STS-POLE_DECA_REPL - #3N DEODARA WY ON P | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9766 | -122.1256 |  | TIER 2 | 131 | 01410-1105, ALHAMBRA | C0805 | 1655 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 53.5 | 53.5 |  |  | 0 | 53.5 | 53.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100459000 | RELW OH PRI INSP JPOL RESD ESTR GO BTKA REAR FMOB TER2 FSRP | Pole | 2021-01-27 |  | COMP | 2021-01-27 | [16 empty] | 2019-05-09 | 2020-05-09 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 014101105 | 25885.47 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | MARTINEZ | Concord |  |  | OPEN | 117176941 | POLE_DECA_REPL - 5069 ALHAMBRA VALLEY RD | 35202519 |  |  | STS-POLE_DECA_REPL - 5069 ALHAMBRA VALLE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9743 | -122.1265 |  | TIER 2 | 131 | 01410-1105, ALHAMBRA | C0810 | 933567 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 61.7 | 61.7 |  |  | 0 | 61.7 | 61.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100459112 | PRI RELW OH CLR JPOL RESD TRAF ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-17 | 2021-02-08 | COMP | 2020-12-17 |  |  | 2020-12-17 | 2020-12-17 | [12 empty] | 2019-05-07 | 2020-05-07 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 014101105 | 27815.42 | 1562.9 | 1549.5 | 633.5 | 633.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | MORAGA | Concord |  |  | OPEN | 117104312 | POLE_DECA_REPL - #6 ON LINE N/O CO#12595 | 35173551 |  |  | B-STS-POLE_DECA_REPL - #6 ON LINE N/O C | PEND | PEND | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.8532 | -122.1296 |  | TIER 2 | 132 | 01380-1103, MORAGA | E0824 |  | Y | 311 |  |  | 2021-03-19 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | [6 empty] | 32.9 | 32.9 |  |  | 0 | 32.9 | 32.9 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100490354 | RELW OH PRI PGEA CLR REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-02-18 | 2021-02-16 | COMP | 2020-05-14 |  |  | 2021-02-16 | 2021-02-16 | [12 empty] | 2019-04-26 | 2020-04-26 | 2020-06-11 | 2020-06-11 | B-Tag Clean Up 5/14/20 |  | Concord |  | 013801103 | 31125.61 | 2965.1 | 1032.4 | 877.1 | 877.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-05-25
Bay/Central | DI | ORINDA | Concord |  |  | OPEN | 116819017 | POLE_BROK_REPL - 5 HARTFORD RDORINDA9456 | 35214593 |  |  | STS-POLE_BROK_REPL - 5 HARTFORD RDORINDA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.8966 | -122.1668 |  | TIER 2 | 470 | 01467-1101, SOBRANTE | D0725 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100474664 | RELW SEC OH JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 | 2021-04-09 | 2021-04-09 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014671101 | 1 | 13.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | ORINDA | Concord |  |  | OPEN | 116821297 | POLE_BROK_REPL - G/P 1WO 1 STAWBERRY HOL | 35214650 |  |  | STS-POLE_BROK_REPL - G/P 1WO 1 STAWBERRY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9027 | -122.1664 |  | TIER 2 | 470 | 01467-1101, SOBRANTE | D0725 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100474668 | RELW OH SEC JPOL RESD ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-04-09 | 2021-04-09 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014671101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | ORINDA | Concord |  |  | OPEN | 116864353 | POLE_BROK_REPL - A/F 66 EL GAVILAN RDORI | 35215311 |  |  | STS-POLE_BROK_REPL - A/F 66 EL GAVILAN R | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9011 | -122.1753 |  | TIER 2 | 1397 | 01360-0401, LAS AROMAS | D0723 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100474504 | RELW RESD OH SEC JPOL FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-04-06 | 2021-04-06 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013600401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | ORINDA | Concord |  |  | OPEN | 116867434 | POLE_DECA_REPL - 1 S/O R/O 15 VALLEY VIE | 35215423 |  |  | STS-POLE_DECA_REPL - 1 S/O R/O 15 VALLEY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 37.9008 | -122.1819 |  | TIER 2 | 1397 | 01360-0401, LAS AROMAS | D0723 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100474390 | RELW OH SERV JPOL RESD ESTR REAR PRTO USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-04-07 | 2021-04-07 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013600401 | 1 | 26.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | ORINDA | Concord |  |  | OPEN | 116883233 | POLE_DECA_REPL - 1 E/O A/F 39 VIA HERMOS | 35202594 |  |  | STS-POLE_DECA_REPL - 1 E/O A/F 39 VIA HE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8944 | -122.1862 |  | TIER 2 | 1397 | 01360-0401, LAS AROMAS | D0722 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 40 | 40 |  |  | 0 | 40 | 40 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100474288 | OH RELW SERV JPOL RESD ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-14 | 2021-02-17 | COMP | 2020-12-14 |  |  | 2021-02-17 | 2021-02-17 | [12 empty] | 2019-04-01 | 2020-04-01 |  | 2020-04-01 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 013600401 | 21862.81 | 1906 | -125.4 | -669.7 | -669.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | ORINDA | Concord |  |  | OPEN | 116952326 | POLE_DECA_REPL - 7 DIOS DORRADOSORINDA94 | 35202624 |  |  | STS 7 DIOS DORRADOSORIN | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.9004 | -122.1891 |  | TIER 2 | 465 | 01235-0401, ORINDA | D0722 | 5648 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 58.7 | 58.7 |  |  | 0 | 58.7 | 58.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100474218 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-04 |  | COMP | 2020-12-04 | [16 empty] | 2019-04-03 | 2020-04-03 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 012350401 | 29355.12 | 3150.9 | 2179.7 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | ORINDA | Concord |  |  | OPEN | 116955539 | POLE_DECA_REPL - 420 MINER RDORINDA94563 | 35202634 |  |  | STS-POLE_DECA_REPL - 420 MINER RDORINDA9 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land Enviro |  |  | 37.9016 | -122.1906 |  | TIER 2 | 470 | 01467-1101, SOBRANTE | D0722 | N517S | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 62.8 | 62.8 |  |  | 0 | 62.8 | 62.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102347304 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-14 |  | COMP | 2020-12-14 | [16 empty] | 2019-04-04 | 2020-04-04 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 014671101 | 34704.54 | 1548.3 | 527.4 | -316.7 | -316.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | ORINDA | Concord |  |  | OPEN | 116955777 | POLE_DECA_REPL - #1S 420 MINER RDORINDA9 | 35214673 |  |  | STS-POLE_DECA_REPL - #1S 420 MINER RDORI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9013 | -122.1908 |  | TIER 2 | 470 | 01467-1101, SOBRANTE | D0722 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102347305 | RELW OH SEC JPOL ESTR RESD TRAF FLAG BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-04 | 2020-04-04 | 2021-07-08 | 2021-07-08 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014671101 | 1 | 86.8 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | ORINDA | Concord |  |  | OPEN | 116978402 | POLE_DECA_REPL - 1 S/O 140 CAMINO DON MI | 35202149 |  |  | STS-POLE_DECA_REPL - 1 S/O 140 CAMINO DO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.8947 | -122.1956 |  | TIER 2 | 465 | 01235-0401, ORINDA | D0721 | 5699 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 26.7 | 26.7 |  |  | 0 | 26.7 | 26.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100474105 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-08 |  | COMP | 2020-12-08 | [16 empty] | 2019-04-08 | 2020-04-08 | 2020-10-07 | 2020-10-07 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 012350401 | 14403.77 | 580.4 | -507.5 | -162.9 | -162.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | ORINDA | Concord |  |  | OPEN | 117034815 | POLE_WOOD_ASES - 1 SUNNYSIDE LN ORINDA | 35215068 |  |  | STS-POLE_WOOD_ASES - 1 SUNNYSIDE LN ORIN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9177 | -122.1868 |  | TIER 2 | 402 | 01467-1102, SOBRANTE | D0712 | 2955 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Woodpecker Damage | Assessment |  | 100473606 | RELW OH PRI ESTR JPOL RESD BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014671102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | ORINDA | Concord |  |  | OPEN | 117183976 | POLE_DECA_REPL - 1 S/O 29 OAK RDORINDA94 | 35202535 |  |  | STS-POLE_DECA_REPL - 1 S/O 29 OAK RDORIN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.871 | -122.1796 |  | TIER 2 | 61 | 01380-1101, MORAGA | E0713 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 46 | 46 |  |  | 0 | 46 | 46 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100488163 | RELW ESTR OH PRI CLR JPOL RESD REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-14 |  | COMP | 2021-01-14 | [16 empty] | 2019-05-08 | 2020-05-08 | 2020-06-15 | 2020-06-15 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013801101 | 25940.38 | 67.1 | 0 | 489 | 489 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | ORINDA | Concord |  |  | OPEN | 117926484 | STS - 45 VISTA DEL MAR ORINDA | 35202618 |  |  | STS-STS - 45 VISTA DEL MAR ORINDA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land |  |  | 37.8949 | -122.201 |  | TIER 2 |  | 01235-0402, ORINDA | D0625 | 5686 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 34.8 | 34.8 |  |  | 0 | 34.8 | 34.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102347238 | RELW OH JPOL ESTR TER2 FSRP | Pole | 2020-12-30 |  | COMP | 2020-12-30 | [16 empty] | 2019-09-26 | 2020-03-26 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  |  | 25159.29 | 53.7 | 0 | 362 | 362 |  |  |  | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | DI | PITTSBURG | Antioch |  |  | OPEN | 117159485 | POLE_BROK_REPL - R/O 5799 NORTINVILLE RD | 35222963 |  |  | STS-POLE_BROK_REPL - R/O 5799 NORTINVILL | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 37.9764 | -121.8966 |  | TIER 2 | 236 | 01445-2104, KIRKER | C1409 | 156719 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100469600 | RELW OH PRI INSP CLR JPOL RESD REMT CGI ESTR GO BTKA PROG FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan |  | UNASSIGNED |  | 014452104 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Oakport |  |  | OPEN | 116810908 | POLE_BROK_REPL - 18 COWPER AVBERKELEY947 | 35154361 |  |  | STS-POLE_BROK_REPL - 18 COWPER AVBERKELE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9155 | -122.2818 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0415 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101439188 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 |  | 2020-03-22 | 2021 CBP Plan | 2020-10-31 | QUES |  | 012501105 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 110837699 | POLE_DECA_REPL - A/F 452 COVENTRY RD BER | 35214478 |  |  |  | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land JointPole |  |  | 37.901 | -122.283 |  | TIER 2 | 1187 | 01260-0401, OAK | D0425 | SWR4255 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | F | Pole | Decayed/Rotten | Replace |  | 101436472 | RELW OH PRI INSP JPOL RESD TRAF SPCR GO BTKA TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2015-10-01 | 2020-02-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012600401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116688009 | STS - 990 REGAL RD BERKELEY | 35202095 |  |  | STS-STS - 990 REGAL RD BERKELEY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land JointPole |  |  | 37.892 | -122.2621 |  | TIER 2 | 1283 | 01370-0401, ARLINGTON | E0503 | R3679 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101449297 | OH PRI INSP JPOL RESD TRAF BTKA FMOB FSRP RELW SCOP SCPA TER2 | Pole |  |  | REQD | [17 empty] | 2019-03-08 | 2020-03-08 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013700401 | 1 | 8640.4 | 32.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116733429 | POLE_DECA_REPL - 272 AMHERST AVBERKELEY9 | 35214747 |  |  | STS-POLE_DECA_REPL - 272 AMHERST AVBERKE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.9041 | -122.2776 |  | TIER 2 | 922 | 01334-0401, SPRUCE | D0516 | R3461 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439607 | RELW OH PRI CLR JPOL PUBL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-14 | 2020-03-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013340401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116734773 | POLE_DECA_REPL - 206 AMHERST AVBERKELEY9 | 35214752 |  |  | STS-POLE_DECA_REPL - 206 AMHERST AVBERKE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.9071 | -122.2786 |  | TIER 2 | 922 | 01334-0401, SPRUCE | D0516 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439546 | RELW JPOL OH PRI CLR RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2021-02-05 | 2021-02-05 | [12 empty] | 2019-03-14 | 2020-03-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013340401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116734940 | POLE_DECA_REPL - 198 AMHERST AVBERKELEY9 | 35214758 |  |  | STS-POLE_DECA_REPL - 198 AMHERST AVBERKE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9074 | -122.2787 |  | TIER 2 | 922 | 01334-0401, SPRUCE | D0516 | R3461 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439601 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-14 | 2020-03-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013340401 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116735275 | POLE_DECA_REPL - NW CRNR OBERLIN AV/AMHE | 35214763 |  |  | STS-POLE_DECA_REPL - NW CRNR OBERLIN AV/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.9076 | -122.2789 |  | TIER 2 | 922 | 01334-0401, SPRUCE | D0516 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439545 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-14 | 2020-03-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013340401 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116736451 | POLE_DECA_REPL - NE CRNR YALE AV/YALE CI | 35214803 |  |  | STS-POLE_DECA_REPL - NE CRNR YALE AV/YAL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.905 | -122.2765 |  | TIER 2 | 922 | 01334-0401, SPRUCE | D0516 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439591 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-14 | 2020-03-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013340401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116736846 | POLE_DECA_REPL - 18 YALE CIR.BERKELEY947 | 35214807 |  |  | STS-POLE_DECA_REPL - 18 YALE CIR.BERKELE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9042 | -122.2761 |  | TIER 2 | 922 | 01334-0401, SPRUCE | D0516 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439595 | RELW OH SEC CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-14 | 2020-03-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013340401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116736889 | STS - 705 HILLDALE AVE BERKELEY | 35202133 |  |  | STS-STS - 705 HILLDALE AVE BERKELEY | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.8985 | -122.2659 |  | TIER 2 | 1224 | 01334-0402, SPRUCE | D0522 | R3327 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101452628 | RELW PRI OH CLR JPOL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-14 | 2020-03-14 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013340402 | 1 | 1009.6 | 16.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116741079 | POLE_DECA_REPL - NE CRNR YALE AV/YALE CI | 35214823 |  |  | STS-POLE_DECA_REPL - NE CRNR YALE AV/YAL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.905 | -122.2763 |  | TIER 2 | 922 | 01334-0401, SPRUCE | D0516 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439590 | RELW OH PRI CLR JPOL COMM FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-15 | 2020-03-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013340401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116741900 | POLE_DECA_REPL - 232 STANFORD AVBERKELEY | 35214832 |  |  | STS-POLE_DECA_REPL - 232 STANFORD AVBERK | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9068 | -122.2765 |  | TIER 2 | 922 | 01334-0401, SPRUCE | D0516 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439532 | RELW OH PRI CLR JPOL RESD TRAF FMOB FLAG ESTR BTKA TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-15 | 2020-03-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013340401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116748114 | POLE_DECA_REPL - 229 CAMBRIDGE AVBERKELE | 35214868 |  |  | STS-POLE_DECA_REPL - 229 CAMBRIDGE AVBER | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9076 | -122.276 |  | TIER 2 | 922 | 01334-0401, SPRUCE | D0516 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439510 | RELW PRI OH CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-16 | 2020-03-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013340401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116751674 | STS - 840 GRIZZLY PEAK BERKELEY | 35214921 |  |  | STS-STS - 840 GRIZZLY PEAK BERKELEY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.8977 | -122.262 |  | TIER 2 | 922 | 01334-0401, SPRUCE | D0523 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101452591 | OH SEC CLR JPOL RESD FIRE FLAG BTKA USA FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013340401 | 1 | 1115.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116751695 | POLE_DECA_REPL - 204 COLUMBIA AVBERKELEY | 35214926 |  |  | STS-POLE_DECA_REPL - 204 COLUMBIA AVBERK | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9089 | -122.2747 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0516 | R7864 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439318 | RELW OH PRI TRAF CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012501105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116756423 | STS - 1126 KEITH AVE BERKELEY | 35202147 |  |  | STS-STS - 1126 KEITH AVE BERKELEY | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.8889 | -122.2604 |  | TIER 2 | 1286 | 01284-0401, RIDGE | E0503 | R3729 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 33.6 | 33.6 |  |  | 0 | 33.6 | 33.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101449253 | RELW OH PRI INSP CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-12-17 |  | COMP | 2020-12-17 | [16 empty] | 2019-03-18 | 2020-03-18 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 012840401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116756593 | STS - 1126 KEITH AVE/1PE BERKELEY | 35202150 |  |  | STS-STS - 1126 KEITH AVE/1PE BERKELEY | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land |  |  | 37.8889 | -122.2604 |  | TIER 2 | 1286 | 01284-0401, RIDGE | E0503 | R3729 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.1 | 15.1 |  |  | 0 | 15.1 | 15.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101449254 | RELW OH PRI INSP JPOL RESD TRAF FLAG ESTR TER2 BTKA USA FMOB FSRP | Pole | 2020-12-22 |  | COMP | 2020-12-22 | [16 empty] | 2019-03-18 | 2020-03-18 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 012840401 | 10154.37 | 1199.2 | -4.3 | -651.6 | -651.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116806191 | POLE_DECA_REPL - 627 COVENTRY RDBERKELEY | 35215345 |  |  | STS-POLE_DECA_REPL - 627 COVENTRY RDBERK | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9015 | -122.281 |  | TIER 2 | 1187 | 01260-0401, OAK | D0425 | R4313 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439243 | RELW OH PRI INSP RESD TRAF FLAG ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012600401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116811977 | POLE_DECA_REPL - 49 LENOX RD BERKELEY | 35215464 |  |  | STS-POLE_DECA_REPL - 49 LENOX RD BERKELE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9042 | -122.2817 |  | TIER 2 | 1187 | 01260-0401, OAK | D0420 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439154 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012600401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116820358 | POLE_DECA_REPL - 1196 EUCLID AVEBERKELEY | 35202436 |  |  | STS-POLE_DECA_REPL - 1196 EUCLID AVEBERK | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 37.8868 | -122.2624 |  | TIER 2 | 736 | 01206-1105, BERKELEY F | E0503 | R9005 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.5 | 44.5 |  |  | 0 | 44.5 | 44.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101449102 | OH RELW PRI INSP CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-12-17 |  | COMP | 2020-12-17 |  |  | 2020-11-18 | 2020-11-18 | [12 empty] | 2019-03-24 | 2020-03-24 | 2020-10-07 | 2020-10-07 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 012061105 | 19996.69 | 1839.3 | 1176.3 | 271.5 | 271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116824609 | POLE_DECA_REPL - 178 ARDMORE DRBERKELEY9 | 35202463 |  |  | STS-POLE_DECA_REPL - 178 ARDMORE DRBERKE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.9028 | -122.2799 |  | TIER 2 | 1187 | 01260-0401, OAK | D0420 | R4029 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.6 | 40.6 |  |  | 0 | 40.6 | 40.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439214 | RELW PRI OH JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-07 |  | COMP | 2020-12-07 | [16 empty] | 2019-03-25 | 2020-03-25 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 012600401 | 26231.2 | 1241 | 580.9 | -162.9 | -162.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116825777 | STS - 756 COVENTRY RD BERKELEY | 35214766 |  |  | STS-STS - 756 COVENTRY RD BERKELEY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land Enviro JointPole |  |  | 37.9024 | -122.2803 |  | TIER 2 | 1187 | 01260-0401, OAK | D0420 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439216 | RELW OH PRI RESD JAR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-25 | 2020-03-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012600401 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116825863 | POLE_DECA_REPL - 801 COVENTRY RD BERKELE | 35214771 |  |  | STS-POLE_DECA_REPL - 801 COVENTRY RD BER | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9025 | -122.28 |  | TIER 2 | 1187 | 01260-0401, OAK | D0420 | R7252 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439215 | RELW OH SEC JPOL RESD ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-25 | 2020-03-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012600401 | 1 | 114.8 | 114.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116828031 | POLE_DECA_REPL - AF 87 EDGECROFT RD BERK | 35214811 |  |  | STS-POLE_DECA_REPL - AF 87 EDGECROFT RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9018 | -122.2798 |  | TIER 2 | 1187 | 01260-0401, OAK | D0420 | R7252 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439227 | RELW OH PRI RESD TRAF FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-25 | 2020-03-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012600401 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116828623 | STS - AF 155 ARDMORE DR/1PE BERKELEY | 35214816 |  |  | STS-STS - AF 155 ARDMORE DR/1PE BERKELEY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.904 | -122.2791 |  | TIER 2 | 1187 | 01260-0401, OAK | D0420 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439210 | OH SEC CUST RESD NOAC GO REAR FSRP RELW PROG FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-25 | 2020-03-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012600401 | 1 | 1747 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116848956 | POLE_BROK_REPL - 216 LAKE DR BERKELEY | 35214924 |  |  | STS-POLE_BROK_REPL - 216 LAKE DR BERKELE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9106 | -122.2729 |  | TIER 2 | 922 | 01334-0401, SPRUCE | D0516 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101439301 | RELW OH PRI JPOL RESD REMT TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013340401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116849243 | POLE_BROK_REPL - 131 PURDUE AVBERKELEY94 | 35214938 |  |  | STS-POLE_BROK_REPL - 131 PURDUE AVBERKEL | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land JointPole |  |  | 37.9117 | -122.2755 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0511 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101455211 | RELW OH PRI JPOL TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012501105 | 1 | 32.4 | 32.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116849336 | POLE_BROK_REPL - 123 PURDUE AVBERKELEY94 | 35214943 |  |  | STS-POLE_BROK_REPL - 123 PURDUE AVBERKEL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9125 | -122.276 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0511 | R8686 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101445363 | JPOL RELW OH PRI RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012501105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116849570 | POLE_BROK_REPL - 113 PURDUE AV BERKELEY | 35214948 |  |  | STS-POLE_BROK_REPL - 113 PURDUE AV BERKE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land Enviro JointPole |  |  | 37.913 | -122.2766 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0511 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101455342 | RELW OH SEC JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012501105 | 1 | 32.4 | 32.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116849648 | POLE_BROK_REPL - AF 96 PURDUE AVBERKELEY | 35214955 |  |  | STS-POLE_BROK_REPL - AF 96 PURDUE AVBERK | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9132 | -122.2771 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0511 | R8448 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101445369 | RELW OH PRI JPOL RESD REMT FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012501105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116850857 | POLE_DECA_REPL - 92 PURDUE AVBERKELEY947 | 35214960 |  |  | STS-POLE_DECA_REPL - 92 PURDUE AVBERKELE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.913 | -122.2775 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0511 | R8448 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103772784 | RELW OH PRI JPOL RESD FLAG ESTR BTKA FMOB FSRP TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012501105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116851912 | POLE_BROK_REPL - AF 164 HIGHLAND BVDBERK | 35214964 |  |  | STS-POLE_BROK_REPL - AF 164 HIGHLAND BVD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9107 | -122.2767 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0511 | R8794 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101445358 | RELW OH PRI JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012501105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116852378 | STS - 96 WINDSOR AVE BERKELEY | 35202524 |  |  | STS-STS - 96 WINDSOR AVE BERKELEY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro JointPole |  |  | 37.9127 | -122.2784 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0511 | R8448 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101445351 | RELW OH PRI JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 012501105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116852432 | POLE_BROK_REPL - NW CRNR HIGHLAND BVD/WI | 35214979 |  |  | STS-POLE_BROK_REPL - NW CRNR HIGHLAND BV | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9124 | -122.2783 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0511 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101445350 | RELW OH PRI JPOL PUBL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012501105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116852569 | POLE_BROK_REPL - 39 KENYON AVBERKELEY947 | 35214993 |  |  | STS-POLE_BROK_REPL - 39 KENYON AVBERKELE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.9112 | -122.2779 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0511 | R7864 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101445345 | RELW OH PRI TRAF FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012501105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116852604 | POLE_BROK_REPL - AF 36 KENYON AVBERKELEY | 35214998 |  |  | STS-POLE_BROK_REPL - AF 36 KENYON AVBERK | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9115 | -122.278 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0511 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101445346 | RELW OH PRI JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-12-31 | 2021-12-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012501105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116852627 | POLE_BROK_REPL - 51 KENYON AVBERKELEY947 | 35215004 |  |  | STS-POLE_BROK_REPL - 51 KENYON AVBERKELE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9109 | -122.2777 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0511 | R7864 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101445344 | RELW OH PRI JPOL TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012501105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116852743 | POLE_BROK_REPL - 25 WINDSOR AVBERKELEY94 | 35215014 |  |  | STS-POLE_BROK_REPL - 25 WINDSOR AVBERKEL | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.9115 | -122.2791 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0511 | R9075 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101445343 | RELW OH PRI JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012501105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116960961 | POLE_DECA_REPL - AF 1415 SUMMIT RDBERKEL | 35154094 |  |  | STS-POLE_DECA_REPL - AF 1415 SUMMIT RDBE | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.8838 | -122.2471 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | E0509 | R9871 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101442317 | PRI RELW OH INSP ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-05 | 2020-04-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 012501105 | 1 | 565.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 117268569 | POLE_DECA_REPL - 22 FRANCISCAN WAY BERKE | 35215252 |  |  | STS-POLE_DECA_REPL - 22 FRANCISCAN WAY B | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.913 | -122.2871 |  | TIER 2 | 1125 | 01335-0402, WALDO | D0415 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101438765 | RELW OH PRI JPOL FLAG RESD ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013350402 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 117268996 | POLE_BROK_REPL - 55 FRANCISCAN WAYBERKEL | 35215275 |  |  | STS-POLE_BROK_REPL - 55 FRANCISCAN WAYBE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9117 | -122.286 |  | TIER 2 | 1125 | 01335-0402, WALDO | D0415 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101439728 | RELW OH SEC CLR JPOL RESD FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013350402 | 1 | 87.1 | 87.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | Berkeley | Richmond |  |  | OPEN | 117686599 | POLE_DECA_REPL - A/F 570 COVENTRY RD BER | 35216234 |  |  | STS-POLE_DECA_REPL - A/F 570 COVENTRY RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9014 | -122.281 |  | TIER 2 |  |  | D0425 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439245 | RELW OH PRI TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG | [11 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 119497853 | STS - NE CRNR SUMMIT RD/GRIZZLY BLVD | 35207103 |  |  | B-STS-STS - NE CRNR SUMMIT RD/GRIZZLY BL | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8824 | -122.2483 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | E0509 | R9871 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-08 16:00 | Scheduled | CLICK | [6 empty] | 41 | 40.2 | 0.8 |  | 0 | 41 | 40.2 | 0.8 |  | EC | B | Pole | Broken/Damaged | Replace |  | 101454578 | RELW OH PRI INSP GO PROG FMOB TER2 SCPA JPOL SCOP | Pole | 2020-12-12 | 2020-12-15 | COMP | 2020-11-30 |  |  | 2020-12-07 | 2020-12-08 | [12 empty] | 2020-07-24 | 2020-10-24 |  | 2020-10-24 | B tag clean up 10/18/2020 |  | Concord |  | 012501105 | 26254.88 | 1308 | 394.5 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Estimating Delays | Y | 2020-10-18
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116686551 | POLE_DECA_REPL - 974 REGAL RDBERKELEY947 | 35089962 |  |  | STS-POLE_DECA_REPL - 974 REGAL RDBERKELE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8928 | -122.2624 |  | TIER 2 | 1283 | 01370-0401, ARLINGTON | E0503 | R3679 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 104.4 | 104.4 |  |  | 0 | 104.4 | 104.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101449219 | RELW OH PRI INSP CLR JPOL RESD TRAF ESTR BTKA USA FMOB TER2 FSRP | Pole | 2019-11-06 | 2021-01-26 | COMP | 2019-11-06 |  |  | 2021-01-25 | 2021-01-25 | [12 empty] | 2019-03-08 | 2020-03-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-09 | CALENG |  | 013700401 | 38934.55 | 69.6 | 69.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116686692 | POLE_DECA_REPL - 971 REGAL RDBERKELEY947 | 35089964 |  |  | STS-POLE_DECA_REPL - 971 REGAL RDBERKELE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8928 | -122.2623 |  | TIER 2 | 1283 | 01370-0401, ARLINGTON | E0503 | R3679 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 15.1 | 15.1 |  |  | 0 | 15.1 | 15.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101449299 | RELW OH PRI INSP JPOL RESD TRAF ESTR BTKA USA FMOB TER2 FSRP | Pole | 2019-11-15 | 2021-01-26 | COMP | 2019-11-15 |  |  | 2021-01-22 | 2021-01-22 | [12 empty] | 2019-03-08 | 2020-03-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-09 | CALENG |  | 013700401 | 8327.11 | 153.9 | 153.9 | 112.1 | 112.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | BERKELEY | Richmond |  |  | OPEN | 116828793 | POLE_DECA_REPL - 74 NORWOOD CT BERKELEY | 35154563 |  |  | STS-POLE_DECA_REPL - 74 NORWOOD CT BERKE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9107 | -122.2821 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0415 | R8278 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 67.5 | 67.5 |  |  | 0 | 67.5 | 67.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439734 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-12-29 | 2020-12-29 | COMP | 2020-05-04 |  |  | 2020-12-11 | 2020-12-28 | [12 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | 2021 CBP Plan | 2020-05-01 | QUES |  | 012501105 | 29006.22 | 3436.3 | 74.8 | 74.8 | 74.8 | 1503.2 |  | 1503.2 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL CERRITO | Richmond |  |  | OPEN | 115596945 | STS - 8506 TERRACE DR EL CERRITO | 35069215 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9196 | -122.2892 |  | TIER 2 |  |  | D0409 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 96.8 | 96.6 | 0.2 |  | 0 | 96.8 | 96.6 | 0.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101441289 | REGW TER2 OH | Pole | 2020-07-08 | 2021-02-16 | COMP | 2020-07-08 |  |  | 2021-01-20 | 2021-02-12 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | 2021 CBP Plan | 2020-12-31 | ENENG |  |  | 36872 | 55.7 | 55.7 | [5 empty] | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL CERRITO | Richmond |  |  | OPEN | 116747647 | STS - 1335 CONTRA COSTA DR EL CERRITO | 35214863 |  |  | STS-STS - 1335 CONTRA COSTA DR EL CERRIT | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land JointPole |  |  | 37.925 | -122.2985 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0408 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101444520 | RELW OH SEC CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-16 | 2020-03-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012501105 | 1 | 32.4 | 32.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL CERRITO | Richmond |  |  | OPEN | 116748172 | STS - 8413 BUCKINGHAM DR EL CERRITO | 35202120 |  |  | STS-STS - 8413 BUCKINGHAM DR EL CERRITO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.9234 | -122.2968 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0408 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.8 | 36.8 |  |  | 0 | 36.8 | 36.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101440437 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-11 |  | COMP | 2021-01-11 | [16 empty] | 2019-03-16 | 2020-03-16 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 012501105 | 21696.41 | 981 | -1104.1 | -207.9 | -207.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL CERRITO | Richmond |  |  | OPEN | 116748203 | STS - A/F 1261 CONTRA COSTA DR EL CERRIT | 35202122 |  |  | STS-STS - A/F 1261 CONTRA COSTA DR EL CE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.9232 | -122.2966 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0408 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 28.6 | 28.6 |  |  | 0 | 28.6 | 28.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101444527 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-06 |  | COMP | 2021-01-06 | [16 empty] | 2019-03-16 | 2020-03-16 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 012501105 | 17877.48 | 1711.2 | -1319.3 | 547 | 547 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL CERRITO | Richmond |  |  | OPEN | 116748319 | STS - 8324 BUCKINGHAM DR/1PS EL CERRITO | 35154145 |  |  | STS - 8324 BUCKINGHAM DR/1PS EL CERRRITO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.9231 | -122.2971 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0408 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50.1 | 50.1 |  |  | 0 | 50.1 | 50.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101440439 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-09-17 |  | COMP | 2020-09-17 |  |  | 2021-02-02 | [13 empty] | 2019-03-16 | 2020-03-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 012501105 | 22727.04 | 1571.7 | 1457.7 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL CERRITO | Richmond |  |  | OPEN | 116748490 | POLE_DECA_REPL - 8320 BUCKINGHAM DREL CE | 35214873 |  |  | STS-POLE_DECA_REPL - 8320 BUCKINGHAM DRE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9227 | -122.2972 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0408 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101440440 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-16 | 2020-03-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012501105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL CERRITO | Richmond |  |  | OPEN | 116748613 | STS - 1245 CONTRA COSTA DR EL CERRITO | 35202124 |  |  | STS-STS - 1245 CONTRA COSTA DR EL CERRIT | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.9226 | -122.296 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0408 | R8823 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 26.8 | 26.8 |  |  | 0 | 26.8 | 26.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101444529 | RELW OH RESD PRI CLR JPOL TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-04 |  | COMP | 2020-12-04 | [16 empty] | 2019-03-16 | 2020-03-16 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 012501105 | 18466.17 | 1217 | 1176.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL CERRITO | Richmond |  |  | OPEN | 116748915 | POLE_DECA_REPL - 1226 KING DREL CERRITO9 | 35214881 |  |  | STS-POLE_DECA_REPL - 1226 KING DREL CERR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9215 | -122.2959 |  | TIER 2 | 400 | 01250-1105, EL CERRITO G | D0408 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101440457 | RELW PRI OH CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-16 | 2020-03-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012501105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL CERRITO | Richmond |  |  | OPEN | 116762107 | STS - 613 BALRA DR EL CERRITO | 35202170 |  |  | STS-STS - 613 BALRA DR EL CERRITO | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.9096 | -122.2919 |  | TIER 2 | 1246 | 01265-0401, FAIRMOUNT | D0419 | R4345 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 69.8 | 68.6 | 1.2 |  | 0 | 69.8 | 68.6 | 1.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101436501 | RELW OH PRI JPOL RESD SPCR ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-09 |  | COMP | 2021-02-09 | [16 empty] | 2019-03-19 | 2020-03-19 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 012650401 | 29721.93 | 691.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL CERRITO | Richmond |  |  | OPEN | 116762280 | POLE_DECA_REPL - 605 BALRA DREL CERRITO9 | 35215039 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9092 | -122.2916 |  | TIER 2 | 1246 | 01265-0401, FAIRMOUNT | D0419 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101436500 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012650401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL CERRITO | Richmond |  |  | OPEN | 116763220 | POLE_DECA_REPL - 528 BALRA DREL CERRITO9 | 35215054 |  |  | STS-POLE_DECA_REPL - 528 BALRA DREL CERR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9081 | -122.2912 |  | TIER 2 | 1246 | 01265-0401, FAIRMOUNT | D0419 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101436527 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012650401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL CERRITO | Richmond |  |  | OPEN | 116764457 | STS - A/F 410 VILLAGE DR EL CERRITO | 35202179 |  |  | STS-STS - A/F 410 VILLAGE DR EL CERRITO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.9064 | -122.2899 |  | TIER 2 | 1246 | 01265-0401, FAIRMOUNT | D0419 | R3739 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 55 | 55 |  |  | 0 | 55 | 55 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101439968 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 |  | COMP | 2021-01-19 | [16 empty] | 2019-03-19 | 2020-03-19 | 2020-12-30 | 2020-12-30 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 012650401 | 27435.55 |  | -597.3 | -72.3 | -72.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL CERRITO | Richmond |  |  | OPEN | 115597144 | STS - 852 GALVIN DR EL CERRITO | 35070095 |  |  | STS - 852 GALVIN DR EL CERRITO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-08-05 | Renew Permit | 37.914 | -122.2955 |  | TIER 2 |  |  | D0413 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 79.5 | 79.5 |  |  | 0.5 | 79 | 79 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101441100 | REGW OH TER2 | Pole | 2019-05-07 | 2020-02-19 | COMP | 2019-05-07 |  |  | 2019-10-30 | 2020-02-19 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-06-30 | ENENG |  |  | 28515.65 | 2375.6 |  |  |  | 1630.2 |  | 1630.2 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | EB | EL CERRITO | Richmond |  |  | OPEN | 115597350 | STS - 901 STOCKTON AVE EL CERRITO | 35069397 |  |  | STS POD - 901 STOCKTON AVE EL CERRITO | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-07-29 | Renew Permit | 37.914 | -122.2975 |  | TIER 2 | 1156 | 01335-0401, WALDO | D0413 |  | Y | 311 |  |  | 2021-04-22 07:00 | 2021-04-22 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 176.1 | 176 | 0.1 |  | 9 | 175.1 | 175 | 0.1 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101441069 | REGW OH TER2 | Pole | 2019-06-04 | 2020-02-07 | COMP | 2019-06-04 |  |  | 2019-10-30 | 2020-02-07 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-06-30 | ENENG |  | 013350401 | 30618.04 | 17538.6 |  |  |  | 1522.3 |  | 1522.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | EB | EL SOBRANTE | Richmond |  |  | OPEN | 116751532 | POLE_DECA_REPL - 5550 CIRCLE DREL SOBRAN | 35214911 |  |  | STS-POLE_DECA_REPL - 5550 CIRCLE DREL SO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9807 | -122.2876 |  | TIER 2 | 162 | 01434-1105, VALLEY VIEW | C0405 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101429112 | RELW OH PRI JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014341105 | 1 | 26.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL SOBRANTE | Richmond |  |  | OPEN | 116752783 | STS - MAIL BOX 5699 CIRCLE DR EL SOBRANT | 35202134 |  |  | STS-STS - MAIL BOX 5699 CIRCLE DR EL SOB | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Enviro JointPole |  |  | 37.9807 | -122.2835 |  | TIER 2 | 162 | 01434-1105, VALLEY VIEW | C0405 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.1 | 17.1 |  |  | 0 | 17.1 | 17.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101429099 | RELW OH PRI JPOL RESD FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-20 |  | COMP | 2021-01-20 | [16 empty] | 2019-03-17 | 2020-03-17 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 014341105 | 10941.45 | 26.7 | -850.6 | -44.9 | -44.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL SOBRANTE | Richmond |  |  | OPEN | 116752898 | STS - 5705 CIRCLE DR EL SOBRANTE | 35214959 |  |  | STS-STS - 5705 CIRCLE DR EL SOBRANTE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9808 | -122.283 |  | TIER 2 | 162 | 01434-1105, VALLEY VIEW | C0405 | 866524 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101429098 | RELW OH PRI JPOL RESD FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014341105 | 1 | 26.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL SOBRANTE | Richmond |  |  | OPEN | 116752960 | POLE_DECA_REPL - 5709 CIRCLE DREL SOBRAN | 35214965 |  |  | STS-POLE_DECA_REPL - 5709 CIRCLE DREL SO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9807 | -122.2826 |  | TIER 2 | 162 | 01434-1105, VALLEY VIEW | C0405 | R9493 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101429097 | OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014341105 | 1 | 26.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL SOBRANTE | Richmond |  |  | OPEN | 116756270 | POLE_DECA_REPL - MAIL BOX 5557 SABRONTE | 35214994 |  |  | STS-POLE_DECA_REPL - MAIL BOX 5557 SABRO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9813 | -122.2871 |  | TIER 2 | 162 | 01434-1105, VALLEY VIEW | C0405 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101429074 | RELW OH PRI JPOL RESD FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014341105 | 1 | 26.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | EL SOBRANTE | Richmond |  |  | OPEN | 116826878 | POLE_BROK_REPL - R/O 33 RANCHO VISTA RD | 35214801 |  |  | STS-POLE_BROK_REPL - R/O 33 RANCHO VISTA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.9862 | -122.2895 |  | TIER 2 | 162 | 01434-1105, VALLEY VIEW | B0424 | R5395 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101443542 | RELW OH PRI JPOL RESD TRAF FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-25 | 2020-03-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014341105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116691260 | STS - 4742 BELFAST AVE OAKLAND | 35089976 |  |  | STS - 4742 BELFAST AVE OAKLAND | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-04-03 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7904 | -122.1779 |  | TIER 2 | 530 | 01209-1102, OAKLAND J | G0708 | 9994 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | [6 empty] | 69.2 | 69.2 |  |  | 0 | 69.2 | 69.2 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101349636 | RELW OH PRI CLR JPOL PUBL TRAF FLAG ESTR BTKA RTRN USA FMOB TER2 FSRP PRTO | Pole | 2019-11-18 | 2021-02-01 | COMP | 2019-11-18 |  |  | 2021-02-01 | 2021-02-01 | [12 empty] | 2019-03-09 | 2020-03-09 | 2021-05-01 | 2021-05-01 | B tag clean up 2/19/2021 | 2019-11-10 | CALENG |  | 012091102 | 30380.84 | 27.8 | 27.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-02-19
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116705485 | STS - 7530 CIRCLE HILL DR OAKLAND | 35202097 |  |  | STS-STS - 7530 CIRCLE HILL DR OAKLAND | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.774 | -122.1624 |  | TIER 2 | 368 | 01368-1112, EDES | G0720 | 1540 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.5 | 57.5 |  |  | 0 | 57.5 | 57.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101354088 | RELW OH PRI JPOL RESD ESTR BTKA RTRN FMOB TER2 PRTO FSRP | Pole | 2020-11-30 |  | COMP | 2020-11-30 | [16 empty] | 2019-03-10 | 2020-03-10 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013681112 | 30117.4 | 1364.3 | 1002.3 | -362 | -362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116705940 | POLE_DECA_REPL - 7550 ALTURA PLOAKLAND94 | 35214651 |  |  | STS-POLE_DECA_REPL - 7550 ALTURA PLOAKLA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.7757 | -122.1586 |  | TIER 2 | 368 | 01368-1112, EDES | G0720 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101353865 | RELW OH SERV CLR JPOL RESD REMT FIRE ESTR BTKA RTRN FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-10 | 2020-03-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013681112 | 1 | 26.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116707659 | POLE_DECA_REPL - 8022 CREST AVOAKLAND946 | 35214656 |  |  | STS-POLE_DECA_REPL - 8022 CREST AVOAKLAN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.7669 | -122.1581 |  | TIER 2 | 516 | 01209-1106, OAKLAND J | G0725 | CR330 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101353679 | OH PRI CLR JPOL RESD TRAF FLAG ESTR GO BTKA USA FMOB TER2 FSRP PRTO RELW | Pole |  |  | REQD | [17 empty] | 2019-03-11 | 2020-03-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012091106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116708882 | POLE_LEAN_REPL - 7977 STERLING DROAKLAND | 35214667 |  |  | STS-POLE_LEAN_REPL - 7977 STERLING DROAK | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.7678 | -122.1581 |  | TIER 2 | 516 | 01209-1106, OAKLAND J | G0725 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Leaning | Replace |  | 101353657 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-11 | 2020-03-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012091106 | 1 | 32.4 | 32.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116709808 | POLE_DECA_REPL - 3427 82ND AVOAKLAND9460 | 35214675 |  |  | STS-POLE_DECA_REPL - 3427 82ND AVOAKLAND | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.7659 | -122.1587 |  | TIER 2 | 516 | 01209-1106, OAKLAND J | G0725 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101353427 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR GO BTKA USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-11 | 2020-03-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012091106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116710661 | POLE_DECA_REPL - 3056 EL MONTEOAKLAND946 | 35214680 |  |  | STS-POLE_DECA_REPL - 3056 EL MONTEOAKLAN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.7648 | -122.1591 |  | TIER 2 | 516 | 01209-1106, OAKLAND J | G0725 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101353531 | RELW OH SEC CLR JPOL RESD TRAF FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-11 | 2020-03-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012091106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116711512 | POLE_BURN_REPL - 8459 ASTER AVOAKLAND946 | 35214685 |  |  | STS-POLE_BURN_REPL - 8459 ASTER AVOAKLAN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.7631 | -122.1584 |  | TIER 2 | 516 | 01209-1106, OAKLAND J | G0725 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 101353537 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-11 | 2020-03-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012091106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116721533 | POLE_BROK_REPL - 12770 SKYLINE BLVD. ON | 35214734 |  |  | STS-POLE_BROK_REPL - 12770 SKYLINE BLVD. | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.7929 | -122.1562 |  | TIER 2 | 330 | 01254-1106, OAKLAND X | G0806 | 6643 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101359098 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-13 | 2020-03-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 012541106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116792024 | POLE_BROK_REPL - 11144[HSE]SUN VALLEY DR | 35215201 |  |  | STS-POLE_BROK_REPL - 11144[HSE]SUN VALLE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.7523 | -122.1176 |  | TIER 2 | 906 | 01311-1109, SAN LEANDRO U | H0805 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101346531 | RELW OH SEC INSP CLR JPOL RESD REMT ESTR GO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013111109 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 117135464 | STS POD - 3400 CRANE OAKLAND | 35098180 |  |  | STS-STS POD - 3400 CRANE OAKLAND | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro JointPole |  |  | 37.8089 | -122.1858 |  | TIER 2 | 330 | 01254-1106, OAKLAND X | F0722 | 6765 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101370181 | RELW OH SEC INSP RESD ESTR PROG FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-01 | 2019-11-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | Concord |  | 012541106 | 1 | 696.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 117147756 | POLE_DECA_REPL - A/F 2038 MELVIN RDOAKLA | 35215119 |  |  | STS-POLE_DECA_REPL - A/F 2038 MELVIN RDO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.8134 | -122.2052 |  | TIER 2 | 1220 | 01318-0401, PALO SECO | F0625 | 5500 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101365798 | RELW OH PRI INSP JPOL RESD TRAF FLAG ESTR BTKA USA PROG FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-02 | 2020-05-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013180401 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 117208872 | STS - 2830 BUTTERS OAKLAND | 35154663 |  |  | STS - 2830 BUTTERS OAKLAND | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.8093 | -122.1902 |  | TIER 2 | 330 | 01254-1106, OAKLAND X | F0721 | CR008 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.8 | 57.8 | 0 |  | 0 | 57.8 | 57.8 | 0 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101360011 | RELW OH PRI INSP JPOL RESD FIRE TRAF ESTR GO FMOB TER2 | Pole | 2021-01-26 |  | COMP | 2021-01-26 | [16 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | QUES |  | 012541106 | 29611.41 | 1000.1 | -173.5 | 78.5 | 78.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116691418 | POLE_DECA_REPL - 4678 BELFAST AVEOAKLAND | 35089982 |  |  | STS-POLE_DECA_REPL - 4678 BELFAST AVEOAK | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | DMD |  |  | 37.7904 | -122.1785 |  | TIER 2 | 530 | 01209-1102, OAKLAND J | G0708 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 189.8 | 189.8 |  |  | 0 | 189.8 | 189.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101349635 | RELW OH PRI CLR JPOL PUBL TRAF FLAG ESTR BTKA RTRN USA FMOB TER2 PRTO | Pole | 2019-11-12 |  | COMP | 2019-11-12 |  |  | 2020-02-24 | 2020-02-24 | [12 empty] | 2019-03-09 | 2020-03-09 |  | 2020-03-09 | Program Manager | 2019-11-12 | CALENG |  | 012091102 | 36724.87 | 349.7 |  |  |  | 71.9 |  | 71.9 |  | Y | MPP File Only | N |  | Y | 2020-02-20
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116749152 | STS - A/F 4727 DUNKIRK AVE OAKLAND | 35206087 |  |  | STS-STS - A/F 4727 DUNKIRK AVE OAKLAND | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7531 | -122.1251 |  | TIER 2 | 906 | 01311-1109, SAN LEANDRO U | H0804 | 9531 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 59.2 | 59.2 |  |  | 0 | 59.2 | 59.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101373310 | RELW OH PRI CLR JPOL RESD SPCR FLAG BTKA SCPA FMOB TER2 PRTO SCOP | Pole | 2020-11-09 | 2021-01-05 | COMP | 2020-11-09 |  |  | 2020-11-16 | 2020-11-16 | [12 empty] | 2019-03-16 | 2020-03-16 |  | 2020-03-16 | Q1 Work Plan File |  | Concord |  | 013111109 | 36133.65 | 1281 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-07
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 119645282 | POLE_DECA_REPL - WARREN FREEWAY/BROADWAY | 35194457 |  |  | STS-POLE_DECA_REPL - WARREN FREEWAY/BROA | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8452 | -122.2279 |  | TIER 2 | 938 | 01210-1103, OAKLAND K | F0602 | 1103/2 | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-04 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101360556 | RELW OH ESTR TER2 | Pole | 2020-09-30 | 2020-10-23 | COMP | 2020-09-30 | [16 empty] | 2020-08-20 | 2020-11-20 |  | 2020-11-20 | B-Tag Clean Up 8/25/20 | 2020-12-31 | QUES |  | 012101103 | 11538.09 | 3607.9 | 816.8 | 443.2 | 443.2 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-08-27
Bay/Central | EB | OAKLAND | Oakport |  |  | COMP | 116705874 | POLE_DECA_REPL - 7548 ALTURA PLOAKLAND94 | 35090008 |  |  | STS-POLE_DECA_REPL - 7548 ALTURA PLOAKLA | MAPP | MAPP SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.7754 | -122.1588 |  | TIER 2 | 368 | 01368-1112, EDES | G0720 |  | Y | 311 |  |  | 2021-02-13 07:00 | 2021-02-13 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 14.5 | 14.5 |  |  | 54.5 | 2.5 | 2.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101353864 | RELW OH SERV COMP CLR ESTR CPGG FMOB TER2 PRTO FSRP | Pole | 2019-10-18 | 2021-01-21 | COMP | 2019-10-18 | COMP | 2021-02-13 | 2021-01-21 | 2021-01-21 | [11 empty] | 2021-02-16 | 2021-02-13 | 2020-03-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-11 | CALENG |  | 013681112 | 8013.45 | 5604.7 | 5604.7 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 115597280 | STS - 4985 SCOTIA AVE | 35069185 |  |  | STS - 4985 SCOTIA AVE OAKLAND | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.754 | -122.1199 |  | TIER 2 | 906 | 01311-1109, SAN LEANDRO U | H0805 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 88.1 | 88.1 |  |  | 0 | 88.1 | 88.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101346537 | REGW OH TER2 | Pole | 2019-06-05 |  | COMP | 2019-06-05 |  |  | 2019-10-29 | 2019-10-29 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | 2021 CBP Plan | 2019-06-30 | ENENG |  | 013111109 | 33069.47 | 5244.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116691002 | POLE_DECA_REPL - 4776 BELFAST AVEOAKLAND | 35089972 |  |  | STS-POLE_DECA_REPL - 4776 BELFAST AVEOAK | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7903 | -122.1774 |  | TIER 2 | 530 | 01209-1102, OAKLAND J | G0708 |  | Y | 311 |  |  | 2021-02-12 07:00 | 2021-02-12 16:00 | Completed | CLICK | [6 empty] | 63.5 | 63.5 |  |  | 63 | 3.5 | 3.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101349637 | RELW OH SEC CLR JPOL PUBL TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2019-11-05 | 2021-01-21 | COMP | 2019-11-05 |  |  | 2021-01-21 | 2021-01-21 | [12 empty] | 2019-03-09 | 2020-03-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-10 | CALENG |  | 012091102 | 24435.57 | 10504.6 | 10504.6 | 144.1 | 144.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116705589 | POLE_BROK_REPL - 7506 CIRCLE HILL DR OAK | 35090003 |  |  | STS-POLE_BROK_REPL - 7506 CIRCLE HILL DR | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7742 | -122.1628 |  | TIER 2 | 368 | 01368-1112, EDES | G0720 | 1540 | Y | 311 |  |  | 2021-02-27 07:00 | 2021-02-27 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 55 | 55 |  |  | 0.5 | 54.5 | 54.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101354089 | RELW OH PRI JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2019-11-18 | 2021-01-21 | COMP | 2019-11-18 |  |  | 2021-01-21 | 2021-01-21 | [12 empty] | 2019-03-10 | 2020-03-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-11 | CALENG |  | 013681112 | 19820.31 | 1741.2 | 1741.2 | 74.8 | 74.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116707344 | STS - 8105 STERLING ST OAKLAND | 35090014 |  |  | STS- 8105 STERLING ST OAKLAND | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7666 | -122.1581 |  | TIER 2 | 516 | 01209-1106, OAKLAND J | G0725 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 40.4 | 40.4 |  |  | 0 | 40.4 | 40.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101353677 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2019-10-28 | 2021-01-21 | COMP | 2019-10-28 |  |  | 2021-01-21 | 2021-01-21 | [12 empty] | 2019-03-11 | 2020-03-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-12 | CALENG |  | 012091106 | 14922.55 | 760.2 | 760.2 | 106.7 | 106.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | OAKLAND | Oakport |  |  | OPEN | 116712918 | POLE_BROK_REPL - 4212 ST ANDREWS RDOAKLA | 35154039 |  |  | STS-POLE_BROK_REPL - 4112 ST ANDREWS RDO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7636 | -122.145 |  | TIER 2 | 368 | 01368-1112, EDES | G0822 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 48.9 | 48.7 | 0.2 |  | 0 | 48.9 | 48.7 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101359244 | RELW OH PRI INSP CLR JPOL RESD REMT FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-07-10 | 2021-01-20 | COMP | 2020-07-10 |  |  | 2021-01-20 | 2021-01-20 | [12 empty] | 2019-03-12 | 2020-03-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | QUES |  | 013681112 | 22728.49 | 1008 | 1008 | 106.7 | 106.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | EB | PORT COSTA | Richmond |  |  | OPEN | 116816946 | ST - 95 CANYON LAKE DR PORT COSTA | 35202365 |  |  | STS-ST - 95 CANYON LAKE DR PORT COSTA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.0451 | -122.1878 |  | TIER 2 | 652 | 01343-2207, FAIRVIEW | A0717 | P150 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 89.9 | 89.9 |  |  | 0 | 89.9 | 89.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101423672 | RELW OH PRI JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-17 |  | COMP | 2020-12-17 | [16 empty] | 2019-03-23 | 2020-03-23 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013432207 | 25903.36 | 1050.3 | 36.7 | -561.1 | -561.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | CASTRO VALLEY | Hayward |  |  | OPEN | 116816948 | POLE_DECA_REPL - STANTON AV/SHEFFIELD RD | 35202370 |  |  | STS-POLE_DECA_REPL - STANTON AV/SHEFFIEL | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.7098 | -122.104 |  | TIER 2 | 482 | 01311-1114, SAN LEANDRO U | I0902 | 7120 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100953648 | RELW OH PRI INSP JPOL RESD ESTR BTKA OTRG FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013111114 | 1 | 238.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | CASTRO VALLEY | Hayward |  |  | OPEN | 117129271 | POLE_DECA_REPL - 19100[ENTR]CREST AVE.1P | 35215045 |  |  | STS-POLE_DECA_REPL - 19100[ENTR]CREST AV | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.7059 | -122.1032 |  | TIER 2 | 482 | 01311-1114, SAN LEANDRO U | I0907 | 886265 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100918099 | RELW OH PRI INSP JPOL RESD ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013111114 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | CASTRO VALLEY | Hayward |  |  | OPEN | 117147127 | POLE_DECA_REPL - 18597 CARLTON AV CASTRO | 35202452 |  |  | STS-POLE_DECA_REPL - 18597 CARLTON AV CA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.709 | -122.0974 |  | TIER 2 | 11 | 01409-1104, CASTRO VALLEY | I0903 | 9454 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 56.9 | 56.9 |  |  | 0 | 56.9 | 56.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100916846 | RELW OH PRI INSP CLR JPOL RESD FIRE ESTR GO BTKA OTRG RTRN USA FMOB TER2 FSRP | Pole | 2021-01-05 |  | COMP | 2021-01-05 | [16 empty] | 2019-05-02 | 2020-05-02 | 2020-10-07 | 2020-10-07 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 014091104 | 23666.6 | 265.4 | -917.1 | 1090.6 | 1090.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | CASTRO VALLEY | Hayward |  |  | OPEN | 115597231 | 5979 GREENRIDGE RD. | 35069310 |  |  | 5979 GREENRIDGE RD. | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7163 | -122.0456 |  | TIER 2 |  |  | I1004 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 54.5 | 54.5 |  |  | 3.5 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100912510 | REGW OH TER2 | Pole | 2020-08-04 | 2021-02-03 | COMP | 2020-08-04 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | 2021 CBP Plan | 2020-10-31 | QUES |  |  | 23944.48 | 1825.1 | 1048.6 | [5 empty] | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | DANVILLE | Livermore |  |  | OPEN | 116958251 | POLE_DECA_REPL - 5990 CAMINO TASSAJARA/1 | 35214686 |  |  | STS-POLE_DECA_REPL - 5990 CAMINO TASSAJA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.7825 | -121.8632 |  | TIER 2 | 245 | 01405-2103, NORTH DUBLIN | G1512 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100898797 | RELW OH PRI CLR JPOL RESD REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-04 | 2020-04-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014052103 | 1 | 106.9 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | HAYWARD | Hayward |  |  | OPEN | 117112482 | POLE_BROK_REPL - 26841 PARKSIDE DR HAYWA | 35214870 |  |  | STS-POLE_BROK_REPL - 26841 PARKSIDE DR H | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.6586 | -122.0435 |  | TIER 2 | 356 | 01409-1101, CASTRO VALLEY | J1009 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100928015 | RELW OH SERV ESTR GO FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-27 | 2020-04-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014091101 | 1 | 13.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | HAYWARD | Hayward |  |  | OPEN | 117112582 | POLE_DECA_REPL - OPP. 26935 PARKSIDE DR | 35202254 |  |  | STS-POLE_DECA_REPL - OPP. 26935 PARKSIDE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.6584 | -122.043 |  | TIER 2 | 356 | 01409-1101, CASTRO VALLEY | J1009 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48.1 | 47.5 | 0.6 |  | 0 | 48.1 | 47.5 | 0.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100928018 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-21 |  | COMP | 2020-12-21 | [16 empty] | 2019-04-27 | 2020-04-27 | 2020-09-23 | 2020-09-23 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 014091101 | 23280.81 | 1156.7 | 1143.4 | 588.3 | 588.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | HAYWARD | Hayward |  |  | OPEN | 117128426 | POLE_DECA_REPL - 26164 CLOVER RD 2P S/0 | 35215041 |  |  | STS-POLE_DECA_REPL - 26164 CLOVER RD 2P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.6668 | -122.0372 |  | TIER 2 |  | 01409-1109, CASTRO VALLEY | J1005 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100950847 | RELW OH PRI INSP CLR JPOL REMT NOAC SPCR ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 1 | 40.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | HAYWARD | Livermore |  |  | COMP | 117100872 | POLE_DECA_REPL - 1475 CALHOUN ST HOUSE 2 | 35154110 |  |  | STS-POLE_DECA_REPL - 1475 CALHOUN ST HOU | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.6437 | -122.0499 |  | TIER 2 | 398 | 01350-1101, JARVIS | J1019 |  | Y | 311 |  |  | 2021-01-21 | 2021-01-21 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 51.7 | 51.7 |  |  | 40 | 1.7 | 1.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100953133 | RELW OH PRI COMP JPOL ESTR CPGG FMOB TER2 PRTO FSRP | Pole | 2020-10-08 | 2020-11-29 | COMP | 2020-10-08 | COMP | 2021-01-21 | [13 empty] | 2021-01-27 | 2021-01-21 | 2020-04-25 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 013501101 | 6956.48 | 13075.2 | 11547.4 | 12746.8 | 12746.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | LIVERMORE | Livermore |  |  | OPEN | 116881330 | POLE_DECA_REPL - 9055 HIGHLAND RDLIVERMO | 35215607 |  |  | STS-POLE_DECA_REPL - 9055 HIGHLAND RDLIV | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.765 | -121.7949 |  | TIER 2 | 279 | 01442-2109, CAYETANO | G17 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100953339 | RELW OH PRI CLR JPOL REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-01 | 2020-04-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014422109 | 1 | 120.2 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | LIVERMORE | Livermore |  |  | OPEN | 116937587 | POLE_BROK_REPL - A/F 2002 VICTORINE RD/1 | 35214580 |  |  | STS-POLE_BROK_REPL - A/F 2002 VICTORINE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.7818 | -121.7991 |  | TIER 2 | 279 | 01442-2109, CAYETANO | G16 | 11775 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100899313 | RELW OH PRI CLR JPOL REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-02 | 2020-04-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014422109 | 1 | 40.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | LIVERMORE | Livermore |  |  | OPEN | 116957033 | POLE_DECA_REPL - 12112 MINES RD./2PE DRW | 35149786 |  |  | STS-POLE_DECA_REPL - 12112 MINES RD./2PE | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.5963 | -121.6365 |  | TIER 2 | 54 | 01375-1102, VASCO | K21 | 6772 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 45.6 | 45 | 0.6 |  | 0 | 45.6 | 45 | 0.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100953971 | RELW OH PRI CLR JPOL RESD REMT TRAF FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-05-26 |  | COMP | 2020-05-26 | [16 empty] | 2019-04-04 | 2020-04-04 |  | 2020-04-04 | 2021 CBP Plan | 2020-07-31 | ENENG |  | 013751102 | 25826.11 | 105.4 |  |  |  | 105.4 |  | 105.4 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | LIVERMORE | Livermore |  |  | OPEN | 116970133 | POLE_BROK_REPL - MAIL BOX 8000 COLLIER C | 35214727 |  |  | STS-POLE_BROK_REPL - MAIL BOX 8000 COLLI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.7662 | -121.8252 |  | TIER 2 | 245 | 01405-2103, NORTH DUBLIN | G16 | 9143 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100899039 | RELW OH PRI CLR REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-06 | 2020-04-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014052103 | 1 | 26.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | LIVERMORE | Livermore |  |  | OPEN | 116979206 | POLE_BURN_REPL - 4533 ARROYO RD./2PSE/4P | 35214769 |  |  | STS-POLE_BURN_REPL - 4533 ARROYO RD./2PS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.6295 | -121.7595 |  | TIER 2 | 296 | 01440-2108, LAS POSITAS | K1705 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 100933407 | RELW OH PRI JPOL ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-08 | 2020-04-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014402108 | 1 | 120.2 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | LIVERMORE | Livermore |  |  | OPEN | 116979860 | POLE_BROK_REPL - AF 5555 CALAVERAS RD.10 | 35214778 |  |  | STS-POLE_BROK_REPL - AF 5555 CALAVERAS R | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro JointPole |  |  | 37.5499 | -121.8575 |  | TIER 2 | 363 | 01424-1101, SUNOL | L15 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100937708 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-08 | 2020-04-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 014241101 | 1 | 40.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | Oakland | Hayward |  |  | OPEN | 118474023 | REPL POLE:CHABOT PUMPSTATION/1S,Oakland | 35203382 |  |  | STS-REPL POLE:CHABOT PUMPSTATION/1S,OAKL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.7319 | -122.1294 |  | TIER 2 |  |  | H0819 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 54.9 | 43.4 | 11.5 |  | 0 | 54.9 | 43.4 | 11.5 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101342113 | RELW OH TNT JPOL TER2 FSRP | Pole | 2020-12-29 |  | COMP | 2020-12-29 | [16 empty] | 2019-11-26 | 2020-11-26 | 2020-11-26 | 2020-11-26 | 2021 CBP Plan | 2021-01-31 | ENENG |  |  | 31597.68 | 3653.9 | 1623.5 | [5 empty] | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | PLEASANTON | Livermore |  |  | OPEN | 116866050 | POLE_BROK_REPL - 7303 CAMINO TASSAJARA P | 35202556 |  |  | STS-POLE_BROK_REPL - 7303 CAMINO TASSAJA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land |  |  | 37.7587 | -121.8677 |  | TIER 2 | 446 | 01405-2101, NORTH DUBLIN | H15 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.1 | 16.1 |  |  | 0 | 16.1 | 16.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103513522 | RELW OH PRI TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-27 |  | COMP | 2021-01-27 | [16 empty] | 2019-03-29 | 2020-03-29 | 2020-07-26 | 2020-07-26 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 014052101 | 9128.24 | 152.6 | -90.5 | 158.5 | 158.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | PLEASANTON | Livermore |  |  | OPEN | 116952037 | POLE_BROK_REPL - OPP. CASTLEWOOD CO. CLU | 35202619 |  |  | STS-POLE_BROK_REPL - OPP. CASTLEWOOD CO. | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land Enviro JointPole |  |  | 37.6376 | -121.8912 |  | TIER 2 | 373 | 01315-1105, RADUM | J1424 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.1 | 29.1 |  |  | 0 | 29.1 | 29.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103046034 | RELW OH PRI FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-09 |  | COMP | 2021-02-09 | [16 empty] | 2019-04-03 | 2020-04-03 | 2020-09-28 | 2020-09-28 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013151105 | 15738.79 | 710.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | PLEASANTON | Livermore |  |  | OPEN | 116962904 | POLE_BROK_REPL - 5/P W/O 302 HAPPY VALLE | 35202338 |  |  | STS-POLE_BROK_REPL - 5/P W/O 302 HAPPY V | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.6371 | -121.8868 |  | TIER 2 | 373 | 01315-1105, RADUM | J1424 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36 | 36 |  |  | 0 | 36 | 36 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100960904 | RELW OH PRI FMOB TER2 PRTO FSRP | Pole | 2020-12-31 |  | COMP | 2020-12-31 | [16 empty] | 2019-04-05 | 2020-04-05 | 2020-08-31 | 2020-08-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013151105 | 26274.53 | 187.3 | 0 | 362 | 362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SAN LEANDRO | Hayward |  |  | OPEN | 116982467 | POLE_DECA_REPL - 2406 EASY ST.SAN LEANDR | 35084884 |  |  | STS-POLE_DECA_REPL - 2406 EASY ST.SAN LE | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.7069 | -122.1077 |  | TIER 2 | 482 | 01311-1114, SAN LEANDRO U | I0906 | 8061 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100918103 | RELW OH PRI CLR RESD TRAF FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-08 | 2019-10-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | Concord |  | 013111114 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SAN LEANDRO | Hayward |  |  | OPEN | 116990605 | POLE_DECA_REPL - AF 15977 GRAMERCY DR.SA | 35202172 |  |  | STS-POLE_DECA_REPL - AF 15977 GRAMERCY D | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.7074 | -122.1097 |  | TIER 2 | 482 | 01311-1114, SAN LEANDRO U | I0906 | 11371 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 35.1 | 35.1 |  |  | 0 | 35.1 | 35.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100912987 | RELW OH PRI JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 |  | COMP | 2021-01-19 | [16 empty] | 2019-04-09 | 2020-04-09 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013111114 | 16896.51 | 44.5 | 0 | 855.8 | 855.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SAN LEANDRO | Hayward |  |  | OPEN | 117009720 | POLE_BROK_REPL - 16098 SELBORNE DR. SAN | 35202183 |  |  | STS-POLE_BROK_REPL - 16098 SELBORNE DR. | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.7053 | -122.1083 |  | TIER 2 | 482 | 01311-1114, SAN LEANDRO U | I0906 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 49.3 | 48.8 | 0.5 |  | 0 | 49.3 | 48.8 | 0.5 |  | EC | E | Pole | Broken/Damaged | Replace |  | 103521666 | RELW OH SEC ESTR JPOL RESD FLAG BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 |  | COMP | 2021-01-19 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013111114 | 22502.45 | 44.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SAN LEANDRO | Hayward |  |  | OPEN | 117013058 | POLE_DECA_REPL - 16050 SELBORNE DRSAN LE | 35202192 |  |  | STS-POLE_DECA_REPL - 16050 SELBORNE DRSA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land |  |  | 37.7067 | -122.1096 |  | TIER 2 | 482 | 01311-1114, SAN LEANDRO U | I0906 | 11371 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43.3 | 43.3 |  |  | 0 | 43.3 | 43.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103526289 | RELW OH PRI JPOL RESD ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2020-12-15 |  | COMP | 2020-12-15 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013111114 | 25428.88 | 1329.3 | 475 | -235.3 | -235.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SAN LEANDRO | Hayward |  |  | OPEN | 117013173 | POLE_DECA_REPL - 16042 SELBORNE DR. SAN | 35202198 |  |  | STS-POLE_DECA_REPL - 16042 SELBORNE DR. | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.7069 | -122.11 |  | TIER 2 | 482 | 01311-1114, SAN LEANDRO U | I0906 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 37.3 | 37.3 |  |  | 0 | 37.3 | 37.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100912346 | RELW OH PRI JPOL RESD ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2020-12-01 |  | COMP | 2020-12-01 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013111114 | 18551.72 | 4965.3 | 1226.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SAN LEANDRO | Hayward |  |  | OPEN | 117047663 | POLE_DECA_REPL - 16011 GRAMERCY DR. SAN | 35202302 |  |  | STS-POLE_DECA_REPL - 16011 GRAMERCY DR. | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.707 | -122.1108 |  | TIER 2 | 482 | 01311-1114, SAN LEANDRO U | I0906 | 11371 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48.2 | 48.2 |  |  | 0 | 48.2 | 48.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100912989 | RELW OH PRI JPOL RESD TRAF ESTR GO BTKA USA PROG FMOB TER2 PRTO FSRP | Pole | 2020-12-17 |  | COMP | 2020-12-17 | [16 empty] | 2019-04-12 | 2020-04-12 | 2020-08-31 | 2020-08-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013111114 | 27861.36 | 594.5 | -997.4 | -470.6 | -470.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SAN LEANDRO | Hayward |  |  | OPEN | 117099944 | POLE_DECA_REPL - 2122 MANCHESTER RD.SAN | 35214757 |  |  | STS-POLE_DECA_REPL - 2122 MANCHESTER RD. | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land Enviro JointPole |  |  | 37.7075 | -122.1123 |  | TIER 2 | 482 | 01311-1114, SAN LEANDRO U | I0906 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100915948 | RELW OH PRI JPOL RESD TRAF ESTR GO BTKA USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013111114 | 1 | 67.2 | 67.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SAN LEANDRO | Hayward |  |  | OPEN | 117104273 | POLE_DECA_REPL - A/F 1377 SANDERLIN CTSA | 35214810 |  |  | STS-POLE_DECA_REPL - A/F 1377 SANDERLIN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro JointPole |  |  | 37.7311 | -122.1349 |  | TIER 2 | 482 | 01311-1114, SAN LEANDRO U | H0818 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100903681 | RELW OH SEC CLR JPOL RESD FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-26 | 2020-04-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013111114 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SAN LEANDRO | Hayward |  |  | OPEN | 117104432 | POLE_DECA_REPL - 1351 GRAFF AVESAN LEAND | 35214815 |  |  | STS-POLE_DECA_REPL - 1351 GRAFF AVESAN L | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.731 | -122.1354 |  | TIER 2 | 482 | 01311-1114, SAN LEANDRO U | H0818 | 9621 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100903684 | RELW OH PRI CLR JPOL RESD FIRE TRAF FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-26 | 2020-04-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013111114 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SAN LEANDRO | Hayward |  |  | OPEN | 117105772 | POLE_DECA_REPL - 1301 GRAFF AVE 1PNW/1PN | 35202219 |  |  | STS-POLE_DECA_REPL - 1301 GRAFF AVE 1PNW | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land |  |  | 37.7314 | -122.1354 |  | TIER 2 | 1213 | 01348-0401, ESTUDILLO | H0818 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 35.9 | 35.9 |  |  | 0 | 35.9 | 35.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100903711 | RELW OH PRI CLR TRAF JPOL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 |  | COMP | 2020-12-11 | [16 empty] | 2019-04-26 | 2020-04-26 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013480401 | 22364.1 | 1455.3 | 990.2 | -162.9 | -162.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SAN LEANDRO | Hayward |  |  | OPEN | 117106354 | POLE_DECA_REPL - A/F 1200 BROOKVALE DR S | 35202225 |  |  | STS-POLE_DECA_REPL - A/F 1200 BROOKVALE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.7324 | -122.1347 |  | TIER 2 | 1213 | 01348-0401, ESTUDILLO | H0818 | 11962 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100903466 | RELW OH PRI FIRE CLR JPOL RESD TRAF FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-26 | 2020-04-26 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013480401 | 1 | 1177.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SAN LEANDRO | Hayward |  |  | OPEN | 117107106 | POLE_DECA_REPL - 1111 BROOKVALE DRSAN LE | 35202228 |  |  | STS-POLE_DECA_REPL - 1111 BROOKVALE DRSA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.7338 | -122.1344 |  | TIER 2 | 1213 | 01348-0401, ESTUDILLO | H0818 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 35.9 | 35.5 | 0.4 |  | 0 | 35.9 | 35.5 | 0.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100903688 | RELW OH SEC CLR JPOL RESD FIRE TRAF FLAG ESTR BTKA USA FMOB FSRP PRTO TER2 | Pole | 2020-11-16 |  | COMP | 2020-11-16 | [16 empty] | 2019-04-26 | 2020-04-26 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013480401 | 21949.87 | 221.2 | -121.5 | -271.5 | -271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SAN LEANDRO | Hayward |  |  | OPEN | 117107178 | POLE_DECA_REPL - 1615 DANIELS DRSAN LEAN | 35214839 |  |  | STS-POLE_DECA_REPL - 1615 DANIELS DRSAN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.7328 | -122.1343 |  | TIER 2 | 1213 | 01348-0401, ESTUDILLO | H0818 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100903694 | RELW OH PRI CLR JPOL RESD FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-26 | 2020-04-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013480401 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SAN LEANDRO | Hayward |  |  | OPEN | 117110284 | POLE_DECA_REPL - 1805 SYLVAN CIRSAN LEAN | 35214851 |  |  | STS-POLE_DECA_REPL - 1805 SYLVAN CIRSAN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 37.7325 | -122.1319 |  | TIER 2 | 1213 | 01348-0401, ESTUDILLO | H0818 | 4600 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100903697 | RELW OH PRI CLR JPOL RESD FIRE TRAF FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2021-02-05 | 2021-02-05 | [12 empty] | 2019-04-27 | 2020-04-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 013480401 | 1 | 26.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SAN LEANDRO | Hayward |  |  | OPEN | 117111984 | POLE_DECA_REPL - NW C/O LAKE CHABOT RD/ | 35202243 |  |  | STS-POLE_DECA_REPL - NW C/O LAKE CHABOT | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.7299 | -122.1318 |  | TIER 2 | 482 | 01311-1114, SAN LEANDRO U | H0818 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26 | 26 |  |  | 0 | 26 | 26 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100903468 | RELW OH PRI CLR JPOL RESD FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-04 |  | COMP | 2021-01-04 | [16 empty] | 2019-04-27 | 2020-04-27 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 013111114 | 17501.02 | 89.3 | 0 | 407.3 | 407.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | MI | SUNOL | Livermore |  |  | OPEN | 117037098 | POLE_BROK_REPL-R/O/7484 SHERIDAN RD SUNO | 35215122 |  |  | STS-POLE_BROK_REPL-R/O/7484 SHERIDAN RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.5499 | -121.8822 |  | TIER 2 | 363 | 01424-1101, SUNOL | L14 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100937838 | RELW CLR OH PRI JPOL REMT TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-16 | 2020-04-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 014241101 | 1 | 106.9 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | BURLINGAME | San Carlos |  |  | OPEN | 117033615 | POLE_DECA_REPL - 1201 MARLBOROUGH RD BUR | 35202249 |  |  | STS-POLE_DECA_REPL - 1201 MARLBOROUGH RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.5521 | -122.3545 |  | TIER 2 | 505 | 02406-0404, CAROLANDS | B0520 | 13459 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100264288 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR GO BTKA PROG FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 024060404 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | BURLINGAME | San Carlos |  |  | COMP | 117056163 | POLE_DECA_REPL - 165 RIDGEWAY RD/1PNBURL | 35172374 |  |  | BC8 POLE_DECA_REPL - 165 RIDGEWAY RD/1PN | UNSC | UNSC ERDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-05-26 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Out of PEND | 2021-06-28 | No Action | 37.5522 | -122.3432 |  | TIER 2 | 384 | 02404-0403, BERESFORD | B0616 |  | Y | 311 |  |  | 2020-12-30 | 2020-12-30 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 1 | 0 | 0 | 1.7 | 1.7 |  |  | 0 | 1.7 | 1.7 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100261183 | RELW OH SEC CLR JPOL RESD ESTR GO REAR FMOB TER2 PRTO FSRP CREW COMP CCNT | Pole | 2020-04-29 | 2020-12-29 | COMP | 2020-04-29 |  |  | 2020-06-08 | 2020-12-29 | [11 empty] | 2021-01-04 | 2020-05-26 | 2020-04-18 | 2020-07-08 | 2020-07-08 | B-Tag Clean Up 5/14/20 |  | San Francisco |  | 024040403 | 29060.1 | 10390.5 | -12062.1 | -1679.3 | -1679.3 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N |  | Y | 2020-05-25
Bay/Central | PN | BURLINGAME | San Carlos |  |  | OPEN | 115597171 | CONN_INCR_REPL - SW C/O CRYSTAL SPRINGS | 35069164 |  |  | STS-POLE_DECA_REPL-CRYSTAL SPRINGS/RIDGE | PEND | PEND CONT | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.5511 | -122.3411 |  | TIER 2 | 384 | 02404-0403, BERESFORD | B0617 | 13611 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 89.5 | 89.5 |  |  | 0 | 89.5 | 89.5 |  |  | EC | E | Connector | Incorrectly Installed | Replace |  | 100263412 | REGW OH TER2 | Pole | 2019-04-25 |  | COMP | 2019-04-25 |  |  | 2019-10-29 | [13 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | 2021 CBP Plan | 2019-09-02 | San Francisco |  | 024040403 | 37126.16 | 3418.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | BURLINGAME | San Carlos |  |  | OPEN | 115597240 | POLE_DECA_REPL - A/F 100 RIDGEWAY RD | 35069296 |  |  | STS-POLE_DECA_REPL - A/F 100 RIDGEWAY RD | PEND | PEND CONT | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.553 | -122.3408 |  | TIER 2 | 384 | 02404-0403, BERESFORD | B0612 | 9154 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 60.9 | 60.9 |  |  | 0 | 60.9 | 60.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100305422 | REGW OH TER2 | Pole | 2019-06-20 |  | COMP | 2019-06-20 |  |  | 2019-03-12 | [13 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | 2021 CBP Plan | 2019-09-02 | San Francisco |  | 024040403 | 24488.66 | 1095.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | BURLINGAME | San Carlos |  |  | OPEN | 116734304 | POLE_BROK_REPL - MB 1210 KENILWORTH RD B | 35090897 |  |  | STS-POLE_BROK_REPL - MB 1210 KENILWORTH | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.5532 | -122.3547 |  | TIER 2 | 505 | 02406-0404, CAROLANDS | B0515 | 13459 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 69.8 | 69.8 |  |  | 0 | 69.8 | 69.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100264220 | RELW OH PRI INSP JPOL RESD FIRE FLAG ESTR GO BTKA FMOB TER2 | Pole | 2019-08-20 |  | COMP | 2019-08-20 |  |  | 2020-02-13 | [13 empty] | 2019-03-14 | 2020-03-14 |  | 2020-03-14 | 2021 CBP Plan | 2020-01-31 | QUES |  | 024060404 | 23681.8 | 836.1 |  |  |  | 553.6 |  | 553.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | BURLINGAME | San Carlos |  |  | OPEN | 117066262 | POLE_DECA_REPL - 1060 PARROT DR BURLINGA | 35093567 |  |  | STS-POLE_DECA_REPL - 1060 PARROT DR BURL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5418 | -122.3447 |  | TIER 2 | 921 | 02401-2102, BAY MEADOWS | B0621 | 13659 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 101.9 | 99.5 | 2.4 |  | 0 | 101.9 | 99.5 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100317533 | RELW OH PRI CLR JPOL RESD ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-03 | 2021-01-21 | COMP | 2020-12-03 | [16 empty] | 2019-04-19 | 2019-10-19 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 024012102 | 23121.25 |  | -1648.9 | -90.5 | -90.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | HILLSBOROUGH | San Carlos |  |  | COMP | 118946316 | POLE_BROK_REPL - 900 VISTA RD HILLSBOROU | 35174428 |  |  | BC8 ANCH_BROK_REPL-900 VISTA RD HILLSBO | MAPP | MAPP SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-06-26 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2021-07-21 | No Action | 37.5523 | -122.3461 |  | TIER 2 | 384 | 02404-0403, BERESFORD | B0616 | 2881 | Y | 311 |  |  | 2021-02-01 | 2021-02-01 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 0 |  |  |  | 0 | 0 |  |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100304560 | OH RELW PRI TMAN CREW COMP RESD ESTR BTKA CCNT TER2 | Pole | 2020-05-11 | 2021-01-21 | COMP | 2020-05-11 | COMP | 2021-02-01 | 2020-05-15 | 2021-01-19 | [11 empty] | 2021-02-04 | 2021-02-01 | 2020-07-24 |  | 2020-07-24 | B-Tag Clean Up 5/14/20 |  | San Francisco |  | 024040403 | 12016.02 | 8819.2 | 5776.1 | 11505 | 11505 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-05-25
Bay/Central | PN | LA HONDA | San Carlos |  |  | OPEN | 116818338 | POLE_DECA_REPL - 1185 SKYLINE BLVD/2PSE | 35214581 |  |  | STS-POLE_DECA_REPL - 1185 SKYLINE BLVD/2 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro |  |  | 37.3114 | -122.1726 |  | TIER 2 | 228 | 02413-1103, MENLO | H1002 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100265479 | RELW OH PRI TRAF PGEA CLR FIRE FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 024131103 | 1 | 13.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | LA HONDA | San Carlos |  |  | COMP | 116752731 | POLE_BROK_REPL - 61 LAGUNA DR.LA HONDA94 | 35182521 |  |  | STS-POLE_BROK_REPL - 61 LAGUNA DR.LA HON | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-08-18 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.3141 | -122.2718 |  | TIER 2 | 77 | 02410-1103, HALF MOON BAY | G0725 |  | Y | 311 |  |  | 2021-01-05 | 2021-01-05 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 34.9 | 34.9 |  |  | 7 | 1.8 | 1.8 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 103810915 | RELW PRI OH CREW COMP CLR JPOL RESD FIRE ESTR BTKA USA CCNT FMOB PRTO TER2 | Pole | 2020-07-02 | 2020-07-16 | COMP | 2020-07-02 | COMP | 2021-01-05 | 2020-07-08 | 2020-07-10 | [11 empty] | 2021-01-09 | 2021-01-05 | 2020-03-17 | 2020-09-15 | 2020-09-15 | B-Tag Addition 06.24.20 |  | San Francisco |  | 024101103 | 16197.18 | 13320.2 | -6435.8 | 13726.8 | 13726.8 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permit Delay - Did not receive permit in time | Y | 2020-06-29
Bay/Central | PN | LA HONDA | San Carlos |  |  | COMP | 116764112 | POLE_DECA_REPL - 2/P/N 11860 LA HONDA RD | 35189586 |  |  | STS-POLE_DECA_REPL - 2/P/N 11860 LA HOND | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-09-19 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.3544 | -122.2646 |  | TIER 2 | 107 | 02413-1102, MENLO | G0801 |  | Y | 311 |  |  | 2021-01-25 | 2021-01-25 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 27.2 | 27.2 |  |  | 2.5 | 27.1 | 27.1 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100312987 | OH PRI CREW COMP CLR JPOL PUBL TRAF FLAG ESTR BTKA CCNT FMOB TER2 PRTO RELW | Pole | 2020-09-02 | 2020-11-17 | COMP | 2020-09-02 | COMP | 2021-01-25 | 2020-11-10 | 2020-11-10 | [11 empty] | 2021-02-01 | 2021-01-25 | 2020-03-19 | 2020-10-17 | 2020-10-17 | B-tag addition 8/4/2020 |  | San Francisco |  | 024131102 | 16149.43 | 11652.5 | 8325.4 | 20305.8 | 20305.8 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-08-04
Bay/Central | PN | LA HONDA | San Carlos |  |  | OPEN | 115098059 | REPL POLE:A/F PESCADERO CR RD ON LA HOND | 35064190 |  |  |  | UNSC | UNSC CONT SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-08-31 | Renew Permit | 37.3121 | -122.2763 |  | TIER 2 |  |  | H0704 |  | Y | 311 |  |  | 2021-03-19 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 75 | 75 |  |  | 6.5 | 68.5 | 68.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100316361 | POHW OH TNT JPOL TER2 | Pole | 2020-05-19 | 2020-07-14 | COMP | 2019-06-12 |  |  | 2019-10-25 | 2020-05-18 | [12 empty] | 2018-10-29 | 2019-10-29 |  | 2019-10-29 | Q1 Work Plan | 2019-07-01 | San Francisco |  |  | 28103.87 | 9215.9 | 905.1 | 581.5 | 581.5 | 492 |  | 492 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | PN | LA HONDA | San Carlos |  |  | OPEN | 115597215 | TREE_OVRG_TRIM - CUESTA REAL AT BEVERLY | 35070256 |  |  | STS-POLE_DECA_REPL-CUESTA REAL AT BEVERL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3207 | -122.2661 |  | TIER 2 | 77 | 02410-1103, HALF MOON BAY | G0725 | 13831 | Y | 311 |  |  |  |  | Scheduled | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 61.1 | 61.1 |  |  | 0 | 61.1 | 61.1 |  |  | EC | E | Tree/Vine | Overgrown | Trim |  | 100271743 | REGW OH TER2 | Pole | 2019-09-24 | 2021-02-11 | COMP | 2019-04-11 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | 2021 CBP Plan | 2019-09-02 | San Francisco |  | 024101103 | 26708.84 | 253 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | LA HONDA | San Carlos |  |  | OPEN | 117209464 | POLE_DECA_REPL - NE CUESTA REAL AT ENTRA | 35136314 |  |  | STS-POLE_DECA_REPL - NE CUESTA REAL AT E | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-16 | Renew Permit | 37.3188 | -122.2713 |  | TIER 2 | 77 | 02410-1103, HALF MOON BAY | G0725 | 695411 | Y | 311 |  |  | 2021-03-17 07:00 | 2021-03-17 16:00 | Scheduled | CLICK | [6 empty] | 57.3 | 57.3 |  |  | 2 | 55.3 | 55.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100271721 | RELW OH PRI JPOL RESD ESTR BTKA OTHR TER2 | Pole | 2020-02-20 | 2020-07-11 | COMP | 2020-02-20 |  |  | 2020-06-24 | 2020-07-10 | [12 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | circuit based plan 2.14 | 2020-01-24 | TRC |  | 024101103 | 25672.04 | 4628.6 | 503.8 | 503.8 | 503.8 | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | PN | LOMA MAR | San Carlos |  |  | OPEN | 117043402 | POLE_LEAN_REPL - SW C/O PESCADERO CR. RD | 35089883 |  |  | STS-POLE_LEAN_REPL - SW C/O PESCADERO CR | PEND | PEND SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD | 2019-08-30 | Renew Permit | 37.2765 | -122.2879 |  | TIER 2 | 77 | 02410-1103, HALF MOON BAY | H0723 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 33.8 | 33.8 |  |  | 0 | 33.8 | 33.8 |  |  | EC | E | Pole | Leaning | Replace |  | 100267239 | RELW OH PRI CLR GO SCOP SCPA FMOB TER2 PRTO | Pole | 2019-09-08 | 2019-06-07 | COMP | 2019-05-02 |  |  | 2019-06-05 | 2019-06-07 | [12 empty] | 2019-04-16 | 2019-10-25 |  | 2019-10-25 | 2021 CBP Plan |  | UNASSIGNED |  | 024101103 | 11103.73 | 1367.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | LOMA MAR | San Carlos |  |  | OPEN | 117113538 | TREE_DECA_INPL - REDWOOD AV AND CANYON R | 35118418 |  |  | STS-TREE_DECA_INPL - REDWOOD AV AND CANY | PEND | PEND | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Land |  |  | 37.2298 | -122.3272 |  | TIER 2 | 77 | 02410-1103, HALF MOON BAY | I0622 | 10497 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-22 16:00 | Scheduled | CLICK | [6 empty] | 506.3 | 470.2 | 16.8 | 19.3 | 0 | 506.3 | 470.2 | 16.8 | 19.3 | EC | B | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100267168 | RELW OH PRI REMT CLR JPOL RESD FIRE ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-12-15 |  | COMP | 2020-12-15 |  |  | 2020-12-30 | 2020-12-30 | [12 empty] | 2019-04-27 | 2019-10-27 | 2020-10-27 | 2020-10-27 | B-tag addition 8/12/2020 |  | San Francisco |  | 024101103 | 102814.46 | 8368.9 | 2002.4 | 1516.4 | 1516.4 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-08-18
Bay/Central | PN | LOS GATOS | San Carlos |  |  | OPEN | 116829601 | POLE_BROK_REPL - #2 S/O 11825 SKYLINE BL | 35202490 |  |  | STS-POLE_BROK_REPL - #2 S/O 11825 SKYLIN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.2771 | -122.1502 |  | TIER 2 | 228 | 02413-1103, MENLO | H10 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13 | 13 |  |  | 0 | 13 | 13 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100265530 | RELW OH PRI CLR JPOL PUBL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-22 |  | COMP | 2020-12-22 | [16 empty] | 2019-03-25 | 2020-03-25 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-01-31 | EEI |  | 024131103 | 14255.18 | 357.4 | 0 | 1543 | 1543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | PACIFICA | Colma |  |  | OPEN | 117163095 | POLE_DECA_REPL - 2POLE E/O.801 SAN DIEGO | 35215269 |  |  | STS-POLE_DECA_REPL - 2POLE E/O.801 SAN D | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.6422 | -122.4899 |  | TIER 2 | 87 | 02281-1102, PACIFICA | E0213 | 2277 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100283655 | RELW OH PRI CLR JPOL RESD FLAG USA ESTR GO BTKA FMOB PRTO FSRP TER2 | Pole |  |  | REQD | [17 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 022811102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | PESCADERO | San Carlos |  |  | OPEN | 117042289 | POLE_DECA_REPL - 423 DEARBORN PARK RDPES | 35136282 |  |  | STS-POLE_DECA_REPL - 423 DEARBORN PARK R | ESTS | ESTS ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2601 | -122.322 |  | TIER 2 |  |  | I0603 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50.1 | 50.1 |  |  | 0 | 50.1 | 50.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100322387 | RELW OH SERV CLR JPOL REMT ESTR GO BTKA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | Per DOT Approved Request 45774 | 2020-12-31 | TRC |  |  | 1 | 107.1 | -1385 |  |  | 107.1 |  | 107.1 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2021-02-06
Bay/Central | PN | PESCADERO | San Carlos |  |  | OPEN | 115694244 | POLE_DECA_REPL - 6375 PESCADERO ROAD PES | 35090305 |  |  | STS-POLE_DECA_REPL - 6375 PESCADERO ROAD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2655 | -122.3221 |  | TIER 2 | 77 | 02410-1103, HALF MOON BAY | I0603 | 8894 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.6 | 39.6 |  |  | 0 | 39.6 | 39.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100322139 | RELW OH PRI JPOL REMT ESTR BTKA OTHR TER2 | Pole | 2020-01-15 |  | COMP | 2020-01-15 |  |  | 2021-02-02 | [13 empty] | 2019-01-16 | 2020-01-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-30 | QUES |  | 024101103 | 14846.83 | 47.7 | 47.7 | [5 empty] | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | PESCADERO | San Carlos |  |  | OPEN | 117032465 | POLE_DECA_REPL - 5401 PESCADERO RD 1SPES | 35136280 |  |  | STS-POLE_DECA_REPL - 5401 PESCADERO RD 1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2651 | -122.3369 |  | TIER 2 | 77 | 02410-1103, HALF MOON BAY | I0601 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.8 | 32.8 |  |  | 0 | 32.8 | 32.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100268153 | RELW OH PRI CLR JPOL REMT FIRE ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-07-27 | 2020-08-29 | COMP | 2020-05-28 | [16 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2020-05-31 | TRC |  | 024101103 | 17540.27 | 1523.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | PESCADERO | San Carlos |  |  | OPEN | 117302145 | POLE_DECA_REPL - 5675 CLOVERDALE RD 1S/1 | 35136322 |  |  | STS-POLE_DECA_REPL - 5675 CLOVERDALE RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-02-26 | Permit Expiring Schedule Job/Request Extension | 37.2514 | -122.371 |  | TIER 2 | 77 | 02410-1103, HALF MOON BAY | I0507 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.3 | 16.3 |  |  | 0 | 16.3 | 16.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100268068 | RELW OH PRI CLR JPOL REMT FIRE NOAC ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-02-20 | 2020-11-18 | COMP | 2020-02-18 |  |  | 2020-06-19 | 2020-11-18 | [12 empty] | 2019-05-22 | 2020-05-22 |  | 2020-05-22 | 2021 CBP Plan | 2020-01-24 | TRC |  | 024101103 | 25671.64 | 853.4 | 0 | 167.5 | 167.5 | 391.5 |  | 391.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | PORTOLA VALLEY | San Carlos |  |  | OPEN | 116755323 | POLE_BROK_REPL - #7 E/O #1 S/O SKYLINE B | 35113258 |  |  | STS-POLE_BROK_REPL - #7 E/O #1 S/O SKYLI | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.359 | -122.2418 |  | TIER 2 | 107 | 02413-1102, MENLO | F0824 |  | Y | 311 |  |  | 2021-02-18 07:00 | 2021-02-18 16:00 | Completed | CLICK | [6 empty] | 30.9 | 30.9 |  |  | 8 | 25.4 | 25.4 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100295706 | RELW OH PRI CLR ESTR COMM REMT NOAC GO PROG FMOB TER2 PRTO | Pole | 2020-11-03 | 2020-11-07 | COMP | 2020-11-03 |  |  | 2020-11-07 | 2020-11-07 | [12 empty] | 2019-03-18 | 2019-11-01 | 2020-11-05 | 2020-11-05 | B tag clean up 8/29/2020 |  | San Francisco |  | 024131102 | 25524.29 | 12055.6 | -32549.5 | -17879.6 | -17879.6 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Access/Customer Issue | Y | 2020-08-29
Bay/Central | PN | PORTOLA VALLEY | San Carlos |  |  | OPEN | 117025652 | POLE_DECA_REPL - R/O 2 VISTA VERDE RD/4P | 35136278 |  |  | STS-POLE_DECA_REPL - R/O 2 VISTA VERDE R | PEND | PEND ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.3342 | -122.1904 |  | TIER 2 | 107 | 02413-1102, MENLO | G0915 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.1 | 17.1 |  |  | 0 | 17.1 | 17.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100312883 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-26 | 2020-10-23 | COMP | 2020-10-23 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | TRC |  | 024131102 | 7378.18 | 376.7 | -1385 |  |  | 195.8 |  | 195.8 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 116762368 | POLE_DECA_REPL - 250 [ENT] FERNDALE WYRE | 35202173 |  |  | STS-POLE_DECA_REPL - 250 [ENT] FERNDALE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.4712 | -122.276 |  | TIER 2 | 334 | 02408-0402, EMERALD LAKE | D0715 | 3487 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100318728 | RELW OH PRI CLR JPOL RESD FIRE FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-01-31 | EEI |  | 024080402 | 1 |  | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 116819091 | POLE_DECA_REPL - 334 [ENT] LAKEVIEW WYRE | 35214598 |  |  | STS-POLE_DECA_REPL - 334 [ENT] LAKEVIEW | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.4712 | -122.2709 |  | TIER 2 | 334 | 02408-0402, EMERALD LAKE | D0715 | 3491 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100278669 | RELW OH RESD PRI CLR JPOL FIRE FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-03-23 | 2020-03-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 024080402 | 1 | 97.2 | 97.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 116863909 | POLE_DECA_REPL - 167 MONTALVO RD REDWOOD | 35215263 |  |  | STS-POLE_DECA_REPL - 167 MONTALVO RD RED | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro JointPole |  |  | 37.4778 | -122.2734 |  | TIER 2 | 695 | 02418-1104, SAN CARLOS | D0710 | 1089 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100317719 | RELW OH PRI CLR JPOL RESD REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 024181104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 117308540 | POLE_DECA_REPL - R/O 3300 BEAR GULCH RD | 35136324 |  |  | STS-POLE_DECA_REPL - R/O 3300 BEAR GULCH | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.362 | -122.3261 |  | TIER 2 | 77 | 02410-1103, HALF MOON BAY | F0623 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100272022 | RELW OH PRI CLR JPOL FIRE NOAC ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-23 | 2020-05-23 |  | 2020-05-23 | 2021 CBP Plan | 2020-10-31 | TRC |  | 024101103 | 1 | 32.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 116805302 | POLE_BROK_REPL - 619 GLENLOCK WAY REDWOO | 35220339 |  |  |  | PEND | PEND | Poles | MPP | Not Funded as 2020 Wildfire OII | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.4647 | -122.2731 |  | TIER 2 | 334 | 02408-0402, EMERALD LAKE | D0715 | 14243 | Y | 311 |  |  | 2021-04-14 07:00 | 2021-04-14 15:00 | Reserved | CLICK | [6 empty] | 7.3 | 2.5 | 4.8 |  | 0 | 7.3 | 2.5 | 4.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100269512 | OH PRI CLR JPOL RESD FIRE FLAG BTKA FMOB TER2 PRTO FSRP RELW SCOP SCPA | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2019-03-21 | 2021-06-17 | 2024-03-19 | 2024-03-19 | work plan year cleanup 01/21/2021 |  | San Francisco |  | 024080402 | 47099.3 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-21
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | COMP | 116751615 | POLE_BROK_REPL - 12700 0LD LA HONDA RD.2 | 35203685 |  |  | STS-POLE_BROK_REPL - 12700 0LD LA HONDA | DOCC | DOCC SRDY CRDY REDL IDOC | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-10-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.3599 | -122.2526 |  | TIER 2 | 107 | 02413-1102, MENLO | F0822 |  | Y | 311 |  |  | 2021-01-11 | 2021-01-11 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 21.8 | 21.8 |  |  | 38.5 | 0.8 | 0.8 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100295617 | OH PRI CREW COMP CLR REMT FIRE NOAC CCNT PROG FMOB TER2 PRTO SCPA RELW SCOP | Pole | 2020-11-30 | 2021-01-05 | COMP | 2020-10-30 | COMP | 2021-01-11 | 2020-12-04 | 2020-12-23 | [11 empty] | 2021-01-14 | 2021-01-11 | 2020-03-17 | 2020-11-27 | 2020-11-27 | B tag clean up 9/26/2020 |  | San Francisco |  | 024131102 | 11614.13 | 26910.7 | 11315 | 22983.6 | 22983.6 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permit Delay - Was scheduled for 12/10 and required road closure that wasn’t included in the permit. Permit was requested but won't be ready by our scheduled date and advised to push this job out 1-2wks | Y | 2020-09-26
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | COMP | 116862892 | POLE_BROK_REPL - 653 EASTVIEW REDWOOD CI | 35189587 |  |  | STS-POLE_BROK_REPL - 653 EASTVIEW REDWOO | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-09-20 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.4592 | -122.2749 |  | TIER 2 | 198 | 02408-0401, EMERALD LAKE | D0720 |  | Y | 311 |  |  | 2021-02-16 07:00 | 2021-02-16 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 23 | 23 |  |  | 9.5 | 14.5 | 14.5 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100278803 | RELW OH PRI CREW COMP CLR JPOL RESD FIRE ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-08-11 | 2020-12-02 | COMP | 2020-08-11 | COMP | 2021-02-16 | 2020-10-26 | 2020-12-02 | [11 empty] | 2021-02-19 | 2021-02-16 | 2020-03-29 | 2020-10-18 | 2020-10-18 | B-tag addition 8/4/2020 |  | San Francisco |  | 024080401 | 9713.02 | 6134.2 | 5872.9 | 19110.6 | 19110.6 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-08-04
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 115597162 | POLE_DECA_REPL - 421 HILLCREST WY | 35070333 |  |  | STS-POLE_DECA_REPL - 421 HILLCREST WY | PEND | PEND SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD | 2019-12-31 | Renew Permit | 37.4601 | -122.2743 |  | TIER 2 | 198 | 02408-0401, EMERALD LAKE | D0720 | 2495 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 78.3 | 77.2 | 1.1 |  | 0 | 78.3 | 77.2 | 1.1 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100278796 | REGW OH TER2 | Pole | 2020-02-07 | 2019-10-18 | COMP | 2019-04-23 |  |  | 2019-10-15 | 2019-10-18 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | 2021 CBP Plan | 2019-09-02 | San Francisco |  | 024080401 | 29740.35 | 212 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 116751094 | POLE_DECA_REPL - 12700 OLD LA HONDA RD. | 35136171 |  |  | STS-POLE_DECA_REPL - 12700 OLD LA HONDA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.36 | -122.2499 |  | TIER 2 | 107 | 02413-1102, MENLO | F0823 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.9 | 31.9 |  |  | 0 | 31.9 | 31.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100277286 | RELW OH PRI CLR REMT FIRE NOAC ESTR FMOB TER2 PRTO | Pole | 2020-07-06 | 2020-07-06 | COMP | 2020-07-06 | [16 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | TRC |  | 024131102 | 28115.71 | 1957.9 |  |  |  | 657.4 |  | 657.4 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 116821333 | POLE_DECA_REPL - 561 LAKEVIEW WYREDWOOD | 35184046 |  |  | STS-POLE_DECA_REPL - 561 LAKEVIEW WYREDW | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4686 | -122.27 |  | TIER 2 | 20 | 02425-1104, WOODSIDE | D0715 | 14791 | Y | 311 |  |  | 2021-02-18 07:00 | 2021-02-18 16:00 | Completed | CLICK | [6 empty] | 69 | 69 |  |  | 10.5 | 58.5 | 58.5 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100278733 | RELW OH PRI CLR JPOL RESD FIRE FLAG ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-07-24 | 2020-08-21 | COMP | 2020-07-24 |  |  | 2020-07-31 | 2020-08-20 | [12 empty] | 2019-03-24 | 2020-03-24 | 2020-09-22 | 2020-09-22 | Work Plan Reconcilation (B-Tags) |  | San Francisco |  | 024251104 | 22254.51 | 7863.3 | 4897.8 | 19789 | 19789 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-07-21
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 116870685 | POLE_DECA_REPL - 507 EASTVIEW WYREDWOOD | 35189588 |  |  | STS-POLE_DECA_REPL - 507 EASTVIEW WYREDW | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4574 | -122.2762 |  | TIER 2 | 198 | 02408-0401, EMERALD LAKE | D0720 |  | Y | 311 |  |  | 2021-03-18 07:00 | 2021-03-18 16:00 | Dispatched | CLICK | [6 empty] | 40.5 | 40.5 |  |  | 6.25 | 34.25 | 34.25 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100278821 | RELW OH PRI CLR JPOL RESD FIRE FLAG ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-08-24 | 2020-12-03 | COMP | 2020-08-24 |  |  | 2020-09-14 | 2020-12-03 | [12 empty] | 2019-03-30 | 2020-03-30 | 2020-10-18 | 2020-10-18 | B-tag addition 8/4/2020 |  | San Francisco |  | 024080401 | 15522.39 | 8138.5 | 6989 | 20003.2 | 20003.2 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-08-04
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 116873634 | POLE_DECA_REPL - R/O 715 W. CALIFORNIA W | 35136262 |  |  | STS-POLE_DECA_REPL - R/O 715 W. CALIFORN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4572 | -122.2742 |  | TIER 2 | 198 | 02408-0401, EMERALD LAKE | D0720 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 74 | 74 |  |  | 0 | 74 | 74 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100317758 | RELW OH SEC CLR JPOL RESD FIRE ESTR REAR SMTR FMOB TER2 PRTO | Pole | 2020-04-27 | 2021-02-10 | COMP | 2020-03-29 | [16 empty] | 2019-03-30 | 2020-03-30 |  | 2020-03-30 | 2021 CBP Plan | 2020-01-24 | TRC |  | 024080401 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 116876668 | POLE_DECA_REPL - 3624 HIGHLAND AV 1PWRED | 35136264 |  |  | STS-POLE_DECA_REPL - 3624 HIGHLAND AV 1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-06-30 |  | 37.4676 | -122.2553 |  | TIER 2 | 334 | 02408-0402, EMERALD LAKE | D0812 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25 | 25 |  |  | 0 | 25 | 25 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100296143 | RELW OH SEC CLR JPOL RESD FIRE FLAG ESTR BTKA USA FMOB PRTO TER2 | Pole | 2020-03-04 | 2020-09-23 | COMP | 2020-03-04 |  |  | 2020-06-17 | 2020-09-23 | [12 empty] | 2019-03-31 | 2020-03-31 |  | 2020-03-31 | 2021 CBP Plan | 2020-01-24 | TRC |  | 024080402 | 14911.35 | 268.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 116957299 | POLE_DECA_REPL - 3349 OAK KNOLL DRREDWOO | 35184049 |  |  | STS-POLE_DECA_REPL - 3349 OAK KNOLL DRRE | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4683 | -122.2605 |  | TIER 2 | 20 | 02425-1104, WOODSIDE | D0812 | 801301 | Y | 311 |  |  | 2021-03-26 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 48.2 | 48.2 |  |  | 1.5 | 46.7 | 46.7 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100296209 | RELW OH PRI CLR JPOL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-07-13 | 2020-09-03 | COMP | 2020-07-13 |  |  | 2020-07-31 | 2020-09-03 | [12 empty] | 2019-04-04 | 2020-04-04 | 2020-09-22 | 2020-09-22 | Work Plan Reconcilation (B-Tags) |  | San Francisco |  | 024251104 | 30872.28 | 13394.4 | 12454 | 8810.9 | 8810.9 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-07-21
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 117088739 | POLE_DECA_REPL - 12670 SKYLINE BLREDWOOD | 35136286 |  |  | STS-POLE_DECA_REPL - 12670 SKYLINE BLRED | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.459 | -122.3416 |  | TIER 2 | 53 | 02410-1101, HALF MOON BAY | D0616 | 13181 | Y | 311 |  |  | 2021-03-06 07:00 | 2021-03-06 16:00 | Scheduled | CLICK | [6 empty] | 54.1 | 54.1 |  |  | 10.5 | 54 | 54 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100265874 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-02-18 | 2020-04-15 | COMP | 2020-02-18 | [16 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | circuit based plan 2.14 | 2020-01-24 | TRC |  | 024101101 | 17444.12 | 15675.9 | -15251.2 | -3290.4 | -3290.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 115597272 | POLE_DECA_REPL - 1935 EDGEWOOD RD REDWOO | 35069462 |  |  | STS-POLE_DECA_REPL - 1935 EDGEWOOD RD. 1 | PEND | PEND CONT | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.4748 | -122.2686 |  | TIER 2 | 695 | 02418-1104, SAN CARLOS | D0806 | 14685 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 23.8 | 23.8 |  |  | 0 | 23.8 | 23.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100299560 | RELW OH TER2 | Pole | 2019-06-17 |  | COMP | 2019-06-17 |  |  | 2019-10-14 | [13 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | 2021 CBP Plan | 2019-09-02 | San Francisco |  | 024181104 | 11876.36 | 922.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 116790868 | POLE_BROK_REPL - A/F 239 HILLSDALE WAY 1 | 35202199 |  |  | STS-POLE_BROK_REPL - A/F 239 HILLSDALE W | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4694 | -122.273 |  | TIER 2 | 334 | 02408-0402, EMERALD LAKE | D0715 | 3493 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100318714 | RELW OH PRI CLR JPOL RESD FIRE FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-01 | 2021-01-21 | COMP | 2020-12-01 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-03-20 | 2020-03-20 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | EEI |  | 024080402 | 22348.32 | 639.3 | -1362.8 | -865 | -865 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 116805507 | POLE_DECA_REPL - 550 HILLCREST WY 2PNRED | 35202251 |  |  | STS-POLE_DECA_REPL - 550 HILLCREST WY 2P | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.4646 | -122.2741 |  | TIER 2 | 334 | 02408-0402, EMERALD LAKE | D0715 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.6 | 57.6 |  |  | 0 | 57.6 | 57.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100269509 | OH PRI CLR JPOL RESD FIRE FMOB RELW FLAG ESTR GO BTKA TER2 PRTO FSRP | Pole | 2020-12-04 | 2021-02-08 | COMP | 2020-12-04 |  |  | 2021-01-08 | 2021-02-08 | [12 empty] | 2019-03-21 | 2020-03-21 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | EEI |  | 024080402 | 30334.05 | 575.3 | -1311.3 | 413.6 | 413.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 116808028 | POLE_DECA_REPL - 545 MOUNTAIN VIEW WYRED | 35136221 |  |  | STS-POLE_DECA_REPL - 545 MOUNTAIN VIEW W | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.4675 | -122.273 |  | TIER 2 | 334 | 02408-0402, EMERALD LAKE | D0715 | 10393 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 45.9 | 45.9 |  |  | 0 | 45.9 | 45.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100278718 | OH RELW PRI CLR JPOL RESD FIRE FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-03-23 |  | COMP | 2020-03-23 |  |  | 2020-06-25 | [13 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-24 | TRC |  | 024080402 | 27719.88 | 95.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | REDWOOD CITY | San Carlos |  |  | OPEN | 116881697 | POLE_DECA_REPL - 56 LOMA RDREDWOOD CITY9 | 35202592 |  |  | STS-POLE_DECA_REPL - 56 LOMA RDREDWOOD C | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4813 | -122.2734 |  | TIER 2 | 695 | 02418-1104, SAN CARLOS | D0710 | 1089 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 58.3 | 58.3 |  |  | 0 | 58.3 | 58.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100278535 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-14 | 2021-02-04 | COMP | 2020-12-14 |  |  | 2021-01-04 | 2021-01-04 | [12 empty] | 2019-04-01 | 2020-04-01 | 2020-07-22 | 2020-07-22 | 2021 CBP Plan | 2021-01-31 | EEI |  | 024181104 | 25166.4 | 65.5 | -2048.1 | -134.1 | -134.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | SAN BRUNO | Colma |  |  | OPEN | 116826112 | POLE_DECA_REPL - R/O 425 MADISON AVE SAN | 35214776 |  |  | STS-POLE_DECA_REPL - R/O 425 MADISON AVE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.6162 | -122.4317 |  | TIER 2 | 1184 | 02272-1101, SNEATH LANE | F0305 | 10041 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100292835 | RELW OH PRI CLR JPOL RESD FIRE ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-25 | 2020-03-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 022721101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | SAN BRUNO | Colma |  |  | OPEN | 116861053 | POLE_LEAN_REPL - R/O 2190 CRESTMOOR DR S | 35215149 |  |  | STS-POLE_LEAN_REPL - R/O 2190 CRESTMOOR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.6254 | -122.432 |  | TIER 2 | 1184 | 02272-1101, SNEATH LANE | E0325 | 3071 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Leaning | Replace |  | 100283400 | RELW OH PRI CLR JPOL RESD FIRE GO REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 022721101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | SAN BRUNO | Colma |  |  | OPEN | 116863859 | POLE_DECA_REPL - R/O 1340 CLAREMONT DR S | 35202548 |  |  | STS-POLE_DECA_REPL - R/O 1340 CLAREMONT | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 37.6244 | -122.4393 |  | TIER 2 | 333 | 02272-1106, SNEATH LANE | E0324 | 3185 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 59.4 | 59.4 |  |  | 0 | 59.4 | 59.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100315281 | RELW OH PRI CLR JPOL RESD FIRE ESTR GO REAR FSRP FMOB TER2 PRTO | Pole | 2020-12-31 | 2020-12-29 | COMP | 2020-12-04 | [16 empty] | 2019-03-28 | 2020-03-28 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | EEI |  | 022721106 | 33903.49 | 37.4 | -1675.9 | 37.4 | 37.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | SAN CARLOS | San Carlos |  |  | OPEN | 116913637 | POLE_BROK_REPL - 10[ENT] ESTRADA PL. SAN | 35215844 |  |  | STS-POLE_BROK_REPL - 10[ENT] ESTRADA PL. | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.4821 | -122.2683 |  | TIER 2 | 695 | 02418-1104, SAN CARLOS | D0806 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100299580 | RELW OH PRI CLR JPOL RESD FIRE JAR TRAF FLAG BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-02 | 2020-04-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 024181104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | SAN GREGORIO | San Carlos |  |  | OPEN | 116821762 | POLE_BROK_REPL - 1501 STAGE RD 19/P/E SA | 35136247 |  |  | STS-POLE_BROK_REPL - 1501 STAGE RD 19/P/ | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.3048 | -122.3679 |  | TIER 2 | 77 | 02410-1103, HALF MOON BAY | H0502 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.2 | 17.2 |  |  | 0 | 17.2 | 17.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100267777 | RELW OH PRI FIRE CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-02-14 |  | COMP | 2020-02-14 |  |  | 2020-06-19 | [13 empty] | 2019-03-24 | 2020-03-24 |  | 2020-03-24 | 2021 CBP Plan | 2020-01-24 | TRC |  | 024101103 | 11299.78 | 612.4 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | SAN MATEO | San Carlos |  |  | OPEN | 117303301 | POLE_DECA_REPL - IRO 771 CRYSTAL SPRINGS | 35215617 |  |  | STS-POLE_DECA_REPL - IRO 771 CRYSTAL SPR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land Enviro JointPole |  |  | 37.5527 | -122.3386 |  | TIER 2 | 384 | 02404-0403, BERESFORD | B0612 | 3319 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100259748 | RELW OH PRI SEC TMAN CLR ESTR TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-22 | 2020-01-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 024040403 | 1 | 145.7 | 145.7 | 93.5 | 93.5 |  |  |  | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | PN | WOODSIDE | San Carlos |  |  | OPEN | 115076078 | POLE_BROK_REPL - 515-599 Maple WayWoodsi | 35063146 |  |  | STS-POLE_BROK_REPL - 515-599 MAPLE WAYWO | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.4546 | -122.2772 |  | TIER 2 | 198 | 02408-0401, EMERALD LAKE | D0724 | 3513 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.9 | 33.9 |  |  | 0 | 33.9 | 33.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100317486 | REGW OH PRI PATR REMT ESTR BTKA FMOB TER2 | Pole | 2020-10-25 | 2020-10-25 | COMP | 2019-01-23 |  |  | 2020-10-30 | [13 empty] | 2018-10-20 | 2019-10-20 |  | 2019-10-20 | 2021 CBP Plan | 2019-02-28 | San Francisco |  | 024080401 | 13761.23 | 559.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST |  | Angels Camp |  |  | OPEN | 117771677 | REPL POLE:1N/O 2E/O 2567 STALLION WAY PV | 35202444 |  |  | STS-REPL POLE:1N/O 2E/O 2567 STALLION WA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.0269 | -120.5958 |  | TIER 2 |  |  | T2807 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.8 | 15.8 |  |  | 0 | 15.8 | 15.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101272685 | OH RELW TNT JPOL TER2 FSRP | Pole | 2021-01-27 | 2021-01-25 | COMP | 2021-01-25 | [16 empty] | 2019-05-01 | 2020-05-01 | 2020-11-19 | 2020-11-19 | 2021 CBP Plan | 2021-01-31 | TRC |  |  | 5942.79 |  | -210 | 882 | 882 |  |  |  | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST |  | Jackson |  |  | OPEN | 117605401 | POLE_DECA_REPL - #2S ON LINE @ SW#1723 S | 35182564 |  |  | STS-POLE_DECA_REPL - #2S ON LINE @ SW#17 | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2712 | -120.7131 |  | TIER 2 | 864 | 16216-1102, ELECTRA | NN25 | 1723 | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Dispatched | CLICK | [6 empty] | 23 | 23 |  |  | 16.5 | 22 | 22 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101243036 | OH ESTR GO TER2 RELW | Pole | 2020-06-24 | 2020-06-24 | COMP | 2020-06-24 | [16 empty] | 2019-07-13 | 2020-03-13 | 2020-08-08 | 2020-08-08 | B-Tag Addition 06.24.20 |  | Stockton |  | 162161102 | 9875 | 7091 | 50.2 | 12.1 | 12.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-06-29
Bay/Central | ST | AMADOR CITY | Jackson |  |  | OPEN | 116804688 | POLE_BROK_REPL - 1SW\O 10951 AMADOR CK R | 35082811 |  |  | STS-POLE_BROK_REPL - 1SW\O 10951 AMADOR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.4209 | -120.8219 |  | TIER 2 | 483 | 16354-1101, OLETA | K2223 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.7 | 33.7 |  |  | 0 | 33.7 | 33.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101239288 | RELW TRAF OH PRI REMT FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-08-31 |  | COMP | 2020-08-31 | [16 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 163541101 | 25229.66 | 44.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | AMADOR CITY | Jackson |  |  | OPEN | 116816702 | POLE_DECA_REPL - HOUSE 14631 BURKER HILL | 35202360 |  |  | STS-POLE_DECA_REPL - HOUSE 14631 BURKER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4221 | -120.8271 |  | TIER 2 | 483 | 16354-1101, OLETA | K2222 | L3481 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.7 | 36.7 |  |  | 0 | 36.7 | 36.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239105 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-15 | 2021-02-11 | COMP | 2020-12-15 | [16 empty] | 2019-03-23 | 2020-03-23 | 2020-11-05 | 2020-11-05 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163541101 | 17047.02 | 8.8 | -1865.3 | -1412.8 | -1412.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | ANGELS CAMP | Angels Camp |  |  | OPEN | 116828364 | POLE_DECA_REPL - 4314 RED HILL RDANGELS | 35202484 |  |  | STS-POLE_DECA_REPL - 4314 RED HILL RDANG | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.0766 | -120.4894 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | S30 | 2227 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14 | 14 |  |  | 0 | 14 | 14 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101278174 | RELW OH PRI INSP ESTR FMOB TER2 FSRP | Pole | 2020-11-06 |  | COMP | 2020-11-06 | [16 empty] | 2019-03-25 | 2020-03-25 | 2020-11-30 | 2020-11-30 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451702 | 10363.2 | 362 | -1141.3 | -411.3 | -411.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | ANGELS CAMP | Angels Camp |  |  | OPEN | 116877472 | POLE_BROK_REPL - #1S/O #3E/O HOUSE 601 S | 35202581 |  |  | STS-POLE_BROK_REPL - #1S/O #3E/O HOUSE 6 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.1056 | -120.5466 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | R29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101269392 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2020-11-29 | 2020-11-29 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | ANGELS CAMP | Angels Camp |  |  | OPEN | 116936628 | POLE_BROK_REPL - #1N/O #1E/O HOUSE 1523 | 35202601 |  |  | STS-POLE_BROK_REPL - #1N/O #1E/O HOUSE 1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.0949 | -120.5854 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | R28 | 6851 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101270366 | RELW OH PRI CLR RESD REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-02 | 2020-04-02 | 2020-10-18 | 2020-10-18 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451702 | 1 |  | -945 | 115 | 115 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | ANGELS CAMP | Angels Camp |  |  | OPEN | 116941451 | POLE_BROK_REPL - #1W/O #7N/O ENTRANCE 33 | 35202604 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1027 | -120.6017 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | R28 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.2 | 21.2 |  |  | 0 | 21.2 | 21.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101269590 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-29 | 2021-02-17 | COMP | 2020-12-29 | [16 empty] | 2019-04-03 | 2020-04-03 | 2020-10-18 | 2020-10-18 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451702 | 14556.21 | 89.6 | -1141.3 | 605.7 | 605.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | ANGELS CAMP | Angels Camp |  |  | OPEN | 116954484 | POLE_BROK_REPL - #10N/O ENTRANCE 1111 MU | 35202629 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.0924 | -120.5377 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | R2924 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.4 | 29.4 |  |  | 0 | 29.4 | 29.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101268964 | RELW OH PRI NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2019-04-04 | 2020-04-04 | 2020-11-29 | 2020-11-29 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451702 | 11402.84 |  | 0 | 1092 | 1092 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | ANGELS CAMP | Angels Camp |  |  | OPEN | 117133454 | POLE_DECA_REPL - 4 S/O 2 N/O R/O 7570 AI | 35202421 |  |  | STS-POLE_DECA_REPL - 4 S/O 2 N/O R/O 757 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.0373 | -120.4721 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | T31 | 767179 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101279115 | RELW OH PRI INSP FSRP ESTR FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-05-01 | 2020-05-01 | 2020-11-28 | 2020-11-28 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | ANGELS CAMP | Angels Camp |  |  | OPEN | 117170566 | POLE_DECA_REPL - #2N/O ENTRANCE 109 GELD | 35202504 |  |  | STS-POLE_DECA_REPL - #2N/O ENTRANCE 109 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.0572 | -120.6165 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | S2719 | L3091 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101272439 | RELW OH PRI INSP REMT ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-06 | 2020-05-06 | 2020-11-16 | 2020-11-16 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163451702 | 1 |  | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | ANGELS CAMP | Angels Camp |  |  | OPEN | 117183108 | POLE_DECA_REPL - 20E/O 2567 STALLION WAY | 35202533 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0208 | -120.5853 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | T28 | L3773 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.8 | 32.8 |  |  | 0 | 32.8 | 32.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101272663 | RELW OH PRI INSP ESTR FMOB TER2 FSRP | Pole | 2020-12-22 | 2021-02-17 | COMP | 2020-12-22 | [16 empty] | 2019-05-08 | 2020-05-08 | 2020-11-18 | 2020-11-18 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451702 | 16798.41 |  | -1322.3 | 108 | 108 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | ANGELS CAMP | Angels Camp |  |  | COMP | 117159444 | POLE_DECA_REPL - C/O RIATA ST AND CHARAP | 35192761 |  |  | STS-POLE_DECA_REPL - C/O RIATA ST AND CH | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-10-02 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.1188 | -120.6919 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | R2510 |  | Y | 311 |  |  | 2021-01-05 | 2021-01-05 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 35 | 35 |  |  | 0 | 35 | 35 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101277090 | RELW OH PRI COMP REMT FLAG ESTR BTKA USA CCNT FMOB TER2 PRTO | Pole | 2020-10-08 | 2020-11-16 | COMP | 2020-10-08 | COMP | 2021-01-05 | 2020-11-14 | 2020-11-14 | [11 empty] | 2021-01-15 | 2021-01-05 | 2020-05-04 | 2020-10-30 | 2020-10-30 | B-tag addition 8/12/2020 |  | Stockton |  | 162211101 | 15460.34 | 9777.7 | 7228.9 | 11337.9 | 11337.9 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-08-18
Bay/Central | ST | ANGELS CAMP | Angels Camp |  |  | COMP | 119577005 | POLE_DECA_REPL - 3N/O 6340 CHARAPAJOS ST | 35192764 |  |  | STS-POLE_DECA_REPL - 3N/O 6340 CHARAPAJO | DOCC | DOCC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-10-02 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.1174 | -120.692 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | R2510 | L835 | Y | 311 |  |  | 2021-01-07 | 2021-01-07 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 61 | 61 |  |  | 0.5 | 60.5 | 60.5 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101277091 | RELW OH COMP ESTR OTRG CCNT TER2 | Pole | 2020-10-08 | 2020-10-08 | COMP | 2020-10-08 | COMP | 2021-01-07 | [13 empty] | 2021-01-15 | 2021-01-07 | 2020-10-30 |  | 2020-10-30 | B-tag addition 8/12/2020 |  | Stockton |  | 162211101 | 12214.74 | 7252.3 | 4572.5 | 13208.3 | 13208.3 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-08-18
Bay/Central | ST | ANGELS CAMP | Angels Camp |  |  | OPEN | 116978657 | POLE_DECA_REPL - 691 purdy rd.Angels Cam | 35160440 |  |  | STS-POLE_DECA_REPL - 691 PURDY RD.ANGELS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0815 | -120.5413 |  | TIER 2 |  |  | S2903 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.1 | 20.1 |  |  | 0 | 20.1 | 20.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101268007 | RELW OH PRI INSP URBW ESTR USA FMOB TER2 FSRP | Pole | 2020-10-29 | 2020-10-30 | COMP | 2020-09-01 | [16 empty] | 2019-04-08 | 2020-04-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  |  | 8046.49 | 362 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | ANGELS CAMP | Angels Camp |  |  | OPEN | 117191848 | POLE_DECA_REPL - #16W/O #1S/O HOUSE 2119 | 35181307 |  |  | STS-POLE_DECA_REPL - #16W/O #1S/O HOUSE | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0619 | -120.6091 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | S27 |  | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Dispatched | CLICK | [6 empty] | 21.9 | 21.9 |  |  | 14 | 20.9 | 20.9 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101272873 | RELW OH PRI INSP CLR REMT FSRP TER2 ESTR BTKA FMOB | Pole | 2020-07-20 | 2020-07-24 | COMP | 2020-07-20 | [16 empty] | 2019-05-09 | 2020-05-09 | 2020-08-30 | 2020-08-30 | B-Tag Addition 06.24.20 |  | Stockton |  | 163451702 | 5440.52 | 7492.1 | -6718.4 | 231.9 | 231.9 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | ST | ANGELS CAMP | Angels Camp |  |  | OPEN | 117194687 | POLE_BROK_REPL - CO L835 ROMEL STANGELS | 35152577 |  |  | STS-POLE_BROK_REPL - CO L835 ROMEL STANG | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1193 | -120.6907 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | R2510 | 585 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 45.5 | 45.5 |  |  | 0 | 45.5 | 45.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101277086 | RELW OH PRI INSP NOAC ESTR TER2 GO BTKA FMOB | Pole | 2020-06-05 | 2020-06-05 | COMP | 2020-06-05 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | circuit based plan 2.14 | 2020-06-30 | Stockton |  | 162211101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | ANGELS CAMP | Angels Camp |  |  | OPEN | 117371853 | POLE_BROK_REPL - 3E/O 3S/O 2W/O 5430 HOU | 35182563 |  |  | STS-POLE_BROK_REPL - 3E/O 3S/O 2W/O 5430 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1209 | -120.6745 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | R26 |  | Y | 311 |  |  | 2021-02-12 07:00 | 2021-02-12 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 21.9 | 21.9 |  |  | 0 | 21.9 | 21.9 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101277767 | RELW OH PRI NOAC ESTR GO FMOB TER2 PRTO | Pole | 2020-07-20 | 2020-07-20 | COMP | 2020-07-20 | [16 empty] | 2019-06-01 | 2019-09-08 | 2020-09-12 | 2020-09-12 | B-Tag Addition 06.24.20 |  | Stockton |  | 162211101 | 23770.61 | 10353.8 | -7069.6 | 342.3 | 342.3 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | ST | ANGELS CAMP | Stockton |  |  | OPEN | 117299904 | POLE_DECA_REPL - 4N/O 2E/O A/F 4363 HWY | 35180713 |  |  | STS-POLE_DECA_REPL - 4N/O 2E/O A/F 4363 | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0357 | -120.5053 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | T30 |  | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 40.9 | 40.9 |  |  | 4.5 | 40.3 | 40.3 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101277239 | RELW OH PRI JPOL REMT NOAC ESTR PROG FMOB TER2 PRTO FSRP | Pole | 2020-07-15 | 2020-07-23 | COMP | 2020-07-14 | [16 empty] | 2019-05-22 | 2020-05-22 | 2020-08-22 | 2020-08-22 | B-Tag Addition 06.24.20 | 2020-07-31 | CALENG |  | 163451702 | 30572.67 | 3978 | 273.2 | 235.1 | 235.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-06-29
Bay/Central | ST | ANGLSCMP | Angels Camp |  |  | OPEN | 117689644 | POLE _DECA _REPL_6056 MICHEL RD ROAD | 35196067 |  |  | STS-POLE _DECA _REPL_6056 MICHEL RD ROAD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.1976 | -120.5667 |  | TIER 2 |  |  | P28 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24 | 24 |  |  | 0 | 24 | 24 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101280544 | RELW OH PRI TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | Per DOT Approved Request 45810 | 2020-12-31 | CALENG |  |  | 1 | 96.6 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP Owned but exists in DO Pull | N |  | Y | 2021-02-06
Bay/Central | ST | ANGLSCMP | Angels Camp |  |  | COMP | 117689561 | POLE _BROK _REPL_#1N ON LINE @ R/O 5720 | 35149894 |  |  | STS-POLE _BROK _REPL_#1N ON LINE @ R/O 5 | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.1732 | -120.3701 |  | TIER 2 |  |  | Q33 |  | Y | 311 |  |  | 2021-01-15 | 2021-01-15 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 31.1 | 31.1 |  |  | 0 | 31.1 | 31.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101275764 | RELW OH PRI COMP ESTR CCNT TER2 PRTO | Pole | 2020-04-21 | 2020-06-12 | COMP | 2020-04-21 | COMP | 2021-01-15 | [13 empty] | 2021-02-01 | 2021-01-15 | 2020-07-31 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-04-10 | TRC |  |  | 18817.97 | 20727.4 | 20638.8 | 30368.1 | 30368.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | ANGLSCMP | Angels Camp |  |  | OPEN | 117685409 | POLE _BROK _REPL_SUB STATION 282C/O POLE | 35149860 |  |  | STS-POLE _BROK _REPL_SUB STATION 282C/O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1424 | -120.3623 |  | TIER 2 |  |  | Q34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27 | 27 |  |  | 0 | 27 | 27 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029053 | RELW OH PRI ESTR TER2 PRTO | Pole | 2020-08-28 | 2020-10-27 | COMP | 2020-08-28 | [16 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | 2021 CBP Plan | 2020-10-31 | TRC |  |  | 24645.24 | 2329 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | ANGLSCMP | Angels Camp |  |  | OPEN | 117689587 | POLE_DECA_REPL - R/O 7685 RED HILL RD PV | 35180437 |  |  | STS-POLE_DECA_REPL - R/O 7685 RED HILL R | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0384 | -120.5046 |  | TIER 2 |  |  | T30 |  | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 42.7 | 42.7 |  |  | 0.5 | 42.2 | 42.2 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101277179 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2020-07-09 | 2020-07-19 | COMP | 2020-07-09 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-08-25 | 2020-08-25 | B-Tag Addition 06.24.20 |  | Stockton |  |  | 22846.61 | 4138.5 | [7 empty] | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | ST | ARNOLD | Angels Camp |  |  | OPEN | 117175193 | POLE_DECA_REPL - 202 munari ln.Arnold | 35149835 |  |  | STS-POLE_DECA_REPL - 202 MUNARI LN.ARNOL | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3521 | -120.2119 |  | TIER 2 |  |  | MM3705 |  | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 32.7 | 32.7 |  |  | 0 | 32.7 | 32.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101275048 | RELW OH PRI INSP URBW ESTR USA FMOB TER2 | Pole | 2020-05-11 | 2020-05-11 | COMP | 2020-05-11 | [16 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | circuit based plan 2.14 | 2020-04-10 | TRC |  |  | 13707.09 | 3078.2 |  |  |  | 391.6 |  | 391.6 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | ARNOLD | Angels Camp |  |  | OPEN | 117175257 | POLE_DECA_REPL - 192 MUNARI LN. ARNOLD | 35149838 |  |  | STS-POLE_DECA_REPL - 192 MUNARI LN.ARNOL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3523 | -120.2117 |  | TIER 2 |  |  | LL3725 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 19 | 19 |  |  | 0 | 19 | 19 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101275049 | RELW OH ESTR PRI INSP URBW BTKA USA FMOB TER2 | Pole | 2020-06-03 | 2020-06-03 | COMP | 2020-06-03 | [16 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-07-31 | TRC |  |  | 11264.46 | 3046.1 |  |  |  | 517.1 |  | 517.1 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | ARNOLD | Angels Camp |  |  | OPEN | 117361920 | POLE_BROK_REPL - POLE 216 - 4N/O C/O#994 | 35125860 |  |  | STS-POLE_BROK_REPL - POLE 216 - 4N/O C/O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3878 | -120.1861 |  | TIER 2 | 63 | 16369-2102, SALT SPRINGS | LL38 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101274968 | RELW OH PRI INSP CLR ESTR FMOB TER2 | Pole | 2019-11-15 | 2019-12-17 | COMP | 2019-11-15 | [16 empty] | 2019-05-30 | 2020-05-30 |  | 2020-05-30 | circuit based plan 2.14 |  | UNASSIGNED |  | 163692102 | 61607.68 | 10940.2 |  |  |  | 5861 |  | 5861 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | ARNOLD | Angels Camp |  |  | OPEN | 117367715 | POLE_BROK_REPL - 47N/O C/O#9945 N/O HWY | 35125861 |  |  | STS-POLE_BROK_REPL - 47N/O C/O#9945 N/O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3958 | -120.1733 |  | TIER 2 | 63 | 16369-2102, SALT SPRINGS | LL38 |  | Y | 311 |  |  | 2021-04-07 07:00 | 2021-04-07 15:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 18.9 | 18.9 |  |  | 0 | 18.9 | 18.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101274944 | RELW OH PRI INSP CLR JPOL REMT NOAC ESTR FMOB TER2 | Pole | 2019-11-15 | 2020-01-23 | COMP | 2019-11-15 | [16 empty] | 2019-05-31 | 2020-05-31 |  | 2020-05-31 | circuit based plan 2.14 |  | UNASSIGNED |  | 163692102 | 12778.86 | 2003.3 |  |  |  | 531.9 |  | 531.9 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | BEAR VALLEY | Angels Camp |  |  | OPEN | 117383301 | POLE_BROK_REPL - 27WO POLE 482 KITCH TR | 35203107 |  |  | STS-POLE_BROK_REPL - 27WO POLE 482 KITCH | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.4266 | -120.0828 |  | TIER 2 | 211 | 16369-2101, SALT SPRINGS | KK41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101275122 | RELW OH PRI REMT ESTR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-04 | 2020-06-04 | 2020-06-04 | 2020-06-04 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163692101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | CAMPO SECO | Angels Camp |  |  | OPEN | 117232657 | POLE_BROK_REPL - #3W 5686 CAMPO SECO RD | 35206580 |  |  | STS-POLE_BROK_REPL - #3W 5686 CAMPO SECO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.2212 | -120.8834 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 16.5 | 16.5 |  |  | 0 | 16.5 | 16.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101234206 | RELW OH PRI PGEA REMT FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2020-11-10 |  | COMP | 2020-11-10 | [16 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 163231101 | 10391.17 | 44.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | CAMPO SECO | Angels Camp |  |  | OPEN | 117163740 | POLE_BROK_REPL - #1W ON LINE @ #2NW 4442 | 35206556 |  |  | STS-POLE_BROK_REPL - #1W ON LINE @ #2NW | UNSC | UNSC ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 38.2301 | -120.8641 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101233801 | RELW OH PRI JPOL REMT ESTR REAR PRTO USA FMOB TER2 FSRP | Pole |  | 2020-12-08 | INPR | [17 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 163231101 | 1 | 40.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | CAMPO SECO | Angels Camp |  |  | OPEN | 117163968 | POLE_BROK_REPL - #1NW 4442 PENN MINE RDC | 35206557 |  |  | STS-POLE_BROK_REPL - #1NW 4442 PENN MINE | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2303 | -120.8625 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 13 | 13 |  |  | 0 | 13 | 13 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101233789 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 | 2021-01-13 | COMP | 2020-12-11 | [16 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 163231101 | 6581.14 | 44.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | COPPEROPOLIS | Angels Camp |  |  | OPEN | 117049978 | POLE_BROK_REPL - A/F 2247 STAGECOACH RD | 35202320 |  |  | STS-POLE_BROK_REPL - A/F 2247 STAGECOACH | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.9584 | -120.6961 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | U2524 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 15.4 | 15.4 |  |  | 0 | 15.4 | 15.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101284366 | RELW OH PRI CLR TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-10 |  | COMP | 2021-02-10 | [16 empty] | 2019-04-17 | 2020-04-17 | 2020-10-18 | 2020-10-18 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451702 | 8897.01 | 8.8 | -1060 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | COPPEROPOLIS | Angels Camp |  |  | OPEN | 117039511 | POLE_BROK_REPL - 3678 CHUCKWAGON DR COPP | 35202270 |  |  | STS-POLE_BROK_REPL - 3678 CHUCKWAGON DR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9673 | -120.6926 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | U2519 | 264157 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101284421 | RELW OH PRI CLR ESTR PROG FMOB TER2 PRTO FSRP | Pole | 2021-01-12 | 2021-01-12 | COMP | 2021-01-12 | [16 empty] | 2019-04-16 | 2020-04-16 | 2020-10-21 | 2020-10-21 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163451702 | 21896.2 | 8.8 | -1738.6 | 239.4 | 239.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | COPPEROPOLIS | Angels Camp |  |  | OPEN | 117065541 | POLE_WOOD_REPL - R/O 2314 STAGECOACH RDC | 35215944 |  |  | STS-POLE_WOOD_REPL - R/O 2314 STAGECOACH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9567 | -120.694 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | U2524 | L2767 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.9 | 32.9 |  |  | 0 | 32.9 | 32.9 |  |  | EC | E | Pole | Woodpecker Damage | Replace |  | 101284362 | OH PRI PGEA CLR FMOB TER2 PRTO FSRP RELW | Pole | 2021-01-29 | 2021-01-29 | COMP | 2021-01-29 | [16 empty] | 2019-04-19 | 2020-04-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163451702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | COPPEROPOLIS | Angels Camp |  |  | OPEN | 117092932 | POLE_BROK_REPL - #5SW ON LINE @ #1N 75 R | 35180428 |  |  | STS-POLE_BROK_REPL - #5SW ON LINE @ #1N | PEND | PEND SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | DMD |  |  | 37.9811 | -120.6497 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | U2610 |  | Y | 311 |  |  | 2021-02-12 07:00 | 2021-02-12 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.9 | 41.9 |  |  | 0.5 | 41.4 | 41.4 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101284815 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-12 | 2020-07-24 | COMP | 2020-07-09 | [16 empty] | 2019-04-24 | 2020-04-24 | 2020-08-23 | 2020-08-23 | B-Tag Addition 06.24.20 |  | Stockton |  | 163451702 | 25239.24 | 3759.5 | [7 empty] | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | ST | COPPEROPOLIS | Angels Camp |  |  | OPEN | 117209626 | POLE_DECA_REPL - S/O 3932 TETON CTCOPPER | 35149918 |  |  | STS-POLE_DECA_REPL - S/O 3932 TETON CTCO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9097 | -120.6127 |  | TIER 2 | 93 | 16378-1704, PEORIA | V2725 | L2277 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 40.9 | 40.9 |  |  | 0 | 40.9 | 40.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101283767 | RELW OH PRI PGEA INSP CUST CLR RESD ESTR GO BTKA USA FMOB TER2 FSRP | Pole | 2020-04-20 | 2020-11-16 | COMP | 2020-04-20 |  |  | 2020-11-16 | 2020-11-16 | [12 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-04-10 | TRC |  | 163781704 | 21265.33 | 200.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | COPPEROPOLIS | Angels Camp |  |  | OPEN | 117219627 | POLE_DECA_REPL - A/F 4346 COUNCIL TRL CO | 35218019 |  |  | STS-POLE_DECA_REPL - A/F 4346 COUNCIL TR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9145 | -120.6039 |  | TIER 2 | 93 | 16378-1704, PEORIA | V2821 | L3753 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 47.1 | 47.1 |  |  | 0 | 47.1 | 47.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101283738 | PRI OH RELW INSP CLR RESD TRAF FLAG BTKA FMOB TER2 | Pole | 2020-12-23 | 2021-01-05 | COMP | 2020-12-23 |  |  | 2021-01-05 | 2021-01-05 | [12 empty] | 2019-05-12 | 2020-05-12 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 35657 |  | UNASSIGNED |  | 163781704 | 25469.06 | 412.5 | 213.5 | 213.5 | 213.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-02-02
Bay/Central | ST | COTTAGE SPRINGS | Angels Camp |  |  | OPEN | 117347713 | POLE_BROK_REPL - POLE 213 - 1N/O C/O#994 | 35125860 |  |  | STS-POLE_BROK_REPL - POLE 216 - 4N/O C/O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3863 | -120.1862 |  | TIER 2 | 63 | 16369-2102, SALT SPRINGS | LL38 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51.8 | 51.8 |  |  | 5.5 | 46.3 | 46.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101274970 | REGW OH PRI REMT NOAC ESTR GO PROG FMOB TER2 PRTO | Pole | 2019-11-15 | 2019-12-17 | COMP | 2019-11-15 | [16 empty] | 2019-05-30 | 2020-05-30 |  | 2020-05-30 | circuit based plan 2.14 |  | UNASSIGNED |  | 163692102 | 61607.68 | 10940.2 |  |  |  | 5861 |  | 5861 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | COTTAGE SPRINGS | Angels Camp |  |  | OPEN | 117347714 | POLE_DECA_REPL - POLE 214 - 2N/O C/O#994 | 35125860 |  |  | STS-POLE_BROK_REPL - POLE 216 - 4N/O C/O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3868 | -120.1861 |  | TIER 2 | 63 | 16369-2102, SALT SPRINGS | LL38 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101274969 | REGW OH PRI REMT NOAC ESTR PROG FMOB TER2 PRTO | Pole | 2019-11-15 | 2019-12-17 | COMP | 2019-11-15 | [16 empty] | 2019-05-30 | 2020-05-30 |  | 2020-05-30 | circuit based plan 2.14 |  | UNASSIGNED |  | 163692102 | 61607.68 | 10940.2 |  |  |  | 5861 |  | 5861 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | FARMINGTON | Angels Camp |  |  | OPEN | 117214658 | POLE_DECA_REPL - 1 W/O R/O 2604 SULKEY C | 35202593 |  |  | STS-POLE_DECA_REPL - 1 W/O R/O 2604 SULK | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9519 | -120.7019 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | U2523 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.2 | 23.2 |  |  | 0 | 23.2 | 23.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101284387 | RELW OH PRI PGEA RESD REMT NOAC CGI ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-01 | 2020-12-01 | COMP | 2020-12-01 | [16 empty] | 2019-05-11 | 2020-05-11 | 2020-11-29 | 2020-11-29 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451702 | 9205.63 | 8.8 | -1928 | -1656.5 | -1656.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FARMINGTON | Angels Camp |  |  | OPEN | 117216028 | POLE_DECA_REPL - R/O 4883 ROCK CREEK RD | 35206583 |  |  | STS-POLE_DECA_REPL - R/O 4883 ROCK CREEK | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0219 | -120.7171 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | T25 | L2831 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 39.4 | 39.4 |  |  | 0 | 39.4 | 39.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101279698 | RELW OH PRI INSP CLR JPOL REMT NOAC ESTR GO FMOB TER2 FSRP | Pole | 2020-12-11 | 2021-01-19 | COMP | 2020-12-11 | [16 empty] | 2019-05-11 | 2020-05-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 163451702 | 21991.27 | 1763.2 | 1476.5 | 1476.5 | 1476.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLE TOWN | Jackson |  |  | OPEN | 117028338 | TREE_DECA_INPL - 2 S/O A/F 19270 FIDDLET | 35115835 |  |  | STS-TREE_DECA_INPL - 2 S/O A/F 19270 FID | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 38.5013 | -120.6682 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J26 | L1253 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 8.9 | 8.9 |  |  | 0 | 8.9 | 8.9 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 101261624 | RELW OH SEC ESTR BTKA FMOB TER2 PRTO | Pole | 2020-07-13 |  | COMP | 2020-07-13 | [16 empty] | 2019-04-14 | 2020-04-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-31 | Bakersfield |  | 163751102 | 7118.23 | 279.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLE TOWN | Jackson |  |  | OPEN | 117028342 | POLE_BROK_REPL - 4 N/O A/F 19331 FIDDLET | 35115836 |  |  | STS-POLE_BROK_REPL - 4 N/O A/F 19331 FID | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5067 | -120.6646 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.5 | 23.5 |  |  | 0 | 23.5 | 23.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101261660 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-06-29 | 2020-06-29 | COMP | 2020-06-29 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-05-31 | Bakersfield |  | 163751102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117055053 | POLE_DECA_REPL - #3 E/O ENTRANCE 15360 T | 35093373 |  |  | STS-POLE_DECA_REPL - #3 E/O ENTRANCE 153 | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.519 | -120.7366 |  | TIER 2 | 528 | 16354-1102, OLETA | I24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.3 | 29.3 |  |  | 0 | 29.3 | 29.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101241456 | RELW OH PRI JPOL REMT TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-21 |  | COMP | 2020-12-21 | [16 empty] | 2019-04-18 | 2019-09-27 | 2020-12-23 | 2020-12-23 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163541102 | 16018.42 |  | -1141.3 | 1058.2 | 1058.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117070072 | POLE_BROK_REPL - #1E/O HOUSE 16602 TYLER | 35202410 |  |  | STS-POLE_BROK_REPL - #1E/O HOUSE 16602 T | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5224 | -120.7169 |  | TIER 2 | 528 | 16354-1102, OLETA | I25 | L2325 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 46.4 | 45.3 | 1.1 |  | 0 | 46.4 | 45.3 | 1.1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101260609 | RELW OH PRI JPOL REMT ESTR REAR FMOB FSRP TER2 PRTO | Pole | 2020-12-30 | 2021-02-11 | COMP | 2020-12-30 | [16 empty] | 2019-04-20 | 2019-10-20 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163541102 | 23251.4 | 89.3 | -2109 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117072358 | POLE_DECA_REPL - ENTRANCE 16960 MARY LNF | 35115871 |  |  | STS-POLE_DECA_REPL - ENTRANCE 16960 MARY | ADER | ADER ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.4967 | -120.71 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 | L3635 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101260676 | RELW OH PRI JPOL REMT TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2020-02-04 | 2020-02-04 | [12 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 163751102 | 1 | 292.3 |  |  |  | 88.7 |  | 88.7 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117072430 | POLE_DECA_REPL - #1 S/O ENTRANCE 20200 S | 35115872 |  |  | STS-POLE_DECA_REPL - #1 S/O ENTRANCE 202 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.4994 | -120.7122 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 | L3635 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101260656 | RELW OH PRI JPOL REMT TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2020-02-14 | 2020-02-14 | [12 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 163751102 | 1 | 62.8 |  |  |  | 62.8 |  | 62.8 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117072598 | POLE_DECA_REPL - #1 S/O ENTRANCE 20331 B | 35115873 |  |  | STS-POLE_DECA_REPL - #1 S/O ENTRANCE 203 | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.4999 | -120.7053 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 19.8 | 19.8 |  |  | 0 | 19.8 | 19.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101260695 | RELW OH PRI REMT TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-12-26 |  | COMP | 2020-12-26 | [16 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 163751102 | 15443.09 | 395.4 |  |  |  | 284.4 |  | 284.4 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117072609 | POLE_DECA_REPL - ENTRANCE 20260 BERTONE | 35115874 |  |  | STS-POLE_DECA_REPL - ENTRANCE 20260 BERT | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.4995 | -120.7051 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 |  | Y | 311 |  |  |  |  | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 78.6 | 78.6 |  |  | 0 | 78.6 | 78.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101260693 | RELW OH PRI REMT TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2021-01-07 |  | COMP | 2021-01-07 | [16 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 163751102 | 18091.27 | 347.7 |  |  |  | 125.6 |  | 125.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117087997 | POLE_BROK_REPL - #2S/O HOUSE 17860 TYLER | 35202165 |  |  | STS-POLE_BROK_REPL - #2S/O HOUSE 17860 T | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.5253 | -120.6922 |  | TIER 2 | 528 | 16354-1102, OLETA | I25 | L2325 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101260569 | RELW OH PRI REMT ESTR GO BTKA REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-23 | 2020-04-23 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163541102 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117317091 | POLE_BROK_REPL - 17501 OLD RIVER RD FIDD | 35116270 |  |  | STS-POLE_BROK_REPL - 17501 OLD RIVER RD | ADER | ADER ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.4909 | -120.6997 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 | L1117 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103105884 | RELW OH PRI CLR REMT NOAC ESTR OTHR REAR USA TER2 | Pole |  |  | REQD | [17 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2021-01-31 | Stockton |  | 163751102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117148411 | POLE_DECA_REPL - #1S/O #2W/O HOUSE 17050 | 35116252 |  |  | XSTS-POLE_DECA_REPL -#1S/O #2W/O HOUSE 1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4797 | -120.7056 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 35.2 | 35.2 |  |  | 0 | 35.2 | 35.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261189 | PRI RELW OH REMT NOAC ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | [16 empty] | 2019-05-02 | 2020-04-02 |  | 2020-04-02 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 163751102 | 24423.2 | 246.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | COMP | 116754960 | POLE_LEAN_REPL - #4E 18294 FIDDLETOWN RD | 35117136 |  |  | STS-POLE_LEAN_REPL - #4E 18294 FIDDLETOW | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.5002 | -120.6825 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J2505 | L1253 | Y | 311 |  |  | 2021-01-15 | 2021-01-15 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 27 | 27 |  |  | 2 | 26 | 26 |  |  | EC | E | Pole | Leaning | Replace |  | 101260733 | RELW OH PRI COMP TRAF INSP CLR REMT ESTR BTKA RTRN USA CCNT FMOB TER2 | Pole | 2020-03-09 | 2020-04-17 | COMP | 2020-03-09 | COMP | 2021-01-15 | 2020-03-09 | 2020-03-09 | [11 empty] | 2021-01-28 | 2021-01-15 | 2020-03-18 |  | 2020-03-18 | Per DOT Approved Request |  | W. Sac |  | 163751102 | 15949.31 | 9786.7 | 2238.3 | 9981.9 | 9981.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-07-12
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | COMP | 116802467 | POLE_DECA_REPL - 2 S/O 19520 CEDAR PINES | 35115829 |  |  | STS-POLE_DECA_REPL - 2 S/O 19520 CEDAR P | FICL | FICL SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.4897 | -120.6749 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J2611 | L1339 | Y | 311 |  |  | 2021-01-14 | 2021-01-14 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 15.8 | 15.8 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261427 | RELW OH PRI INSP COMP CLR REMT FLAG ESTR BTKA CCNT FMOB TER2 | Pole | 2020-06-29 | 2020-06-29 | COMP | 2020-06-29 | COMP | 2021-01-14 | 2019-07-31 | 2019-07-31 | [11 empty] | 2021-01-25 | 2021-01-14 | 2020-03-21 |  | 2020-03-21 | circuit based plan 2.14 | 2020-05-31 | Bakersfield |  | 163751102 | 9653.27 | 5018.7 | 5018.7 | 11125.4 | 11125.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | COMP | 117072232 | POLE_DECA_REPL - #1 S/O C/O FIDDLETOWN R | 35115868 |  |  | STS-POLE_DECA_REPL - #1 S/O C/O FIDDLETO | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.4978 | -120.7121 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 |  | Y | 311 |  |  | 2021-01-14 | 2021-01-14 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 58.8 | 58.8 |  |  | 0 | 58.8 | 58.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101260607 | RELW OH PRI COMP JPOL REMT TRAF USA FLAG ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-02-28 | 2020-05-31 | COMP | 2020-02-28 | COMP | 2021-01-14 | 2020-05-31 | 2020-05-31 | [11 empty] | 2021-01-25 | 2021-01-14 | 2020-04-21 |  | 2020-04-21 | circuit based plan 2.14 |  | UNASSIGNED |  | 163751102 | 17741.1 | 7471.6 | 2262 | 9981.9 | 9981.9 | 487.5 |  | 487.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 116723918 | POLE_BROK_REPL - 18801 VIEW CIRCLE - FID | 35115827 |  |  | STS-POLE_BROK_REPL - 18801 VIEW CIRCLE - | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4915 | -120.676 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J2606 | L1339 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50.3 | 50.3 |  |  | 0 | 50.3 | 50.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101261442 | RELW OH PRI INSP CLR REMT ESTR BTKA FMOB TER2 | Pole | 2020-06-29 | 2020-06-29 | COMP | 2020-06-29 | [16 empty] | 2019-03-13 | 2020-03-13 |  | 2020-03-13 | 2021 CBP Plan | 2020-05-31 | Bakersfield |  | 163751102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117016090 | POLE_BROK_REPL - 19860 CAMINO DEL APARIC | 35115832 |  |  | STS-POLE_BROK_REPL - 19860 CAMINO DEL AP | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.499 | -120.6548 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J26 | L1253 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.5 | 32.5 |  |  | 0 | 32.5 | 32.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103188357 | RELW OH PRI REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-06-26 | 2020-10-15 | COMP | 2020-06-26 |  |  | 2020-10-15 | 2020-10-15 | [12 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-05-31 | Bakersfield |  | 163751102 | 14412.49 | 544.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117082277 | POLE_BROK_REPL - #2E/O 17800 RED MULE RD | 35149976 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4933 | -120.692 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 | L1117 | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 36.7 | 36.7 |  |  | 0 | 36.7 | 36.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101260789 | RELW OH PRI ESTR RTRN FMOB TER2 PRTO | Pole | 2020-06-01 | 2020-06-01 | COMP | 2020-06-01 |  |  | 2020-03-16 | 2020-03-16 | [12 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | circuit based plan 2.14 | 2020-06-30 | TRC |  | 163751102 | 18566.67 | 1915.5 | 1915.5 | 1336.4 | 1336.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117083063 | POLE_DECA_REPL - #1 S/O ENTRANCE 19777 H | 35115900 |  |  | STS-POLE_DECA_REPL - #1 S/O ENTRANCE 197 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4946 | -120.6947 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 19.9 | 19.9 |  |  | 0 | 19.9 | 19.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101260769 | RELW OH PRI REMT TRAF FLAG ESTR TER2 BTKA USA FMOB PRTO | Pole | 2019-10-25 | 2020-09-02 | COMP | 2019-10-24 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan |  | UNASSIGNED |  | 163751102 | 13096.11 | 81.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117109807 | POLE_BROK_REPL - 18000 COSOL DR FIDDLETO | 35115947 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4874 | -120.6971 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 | L9723 | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | [6 empty] | 36.8 | 36.8 |  |  | 0 | 36.8 | 36.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103118274 | REMT RELW OH PRI ESTR BTKA FMOB TER2 PRTO | Pole | 2020-01-08 | 2020-07-27 | COMP | 2020-01-08 | [16 empty] | 2019-04-27 | 2020-04-27 |  | 2020-04-27 | circuit based plan 2.14 |  | W. Sac |  | 163751102 | 16282.68 | 875.8 | 793.5 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117110436 | POLE_DECA_REPL - #1 ON LINE E/O CO#9723 | 35116025 |  |  | STS-POLE_DECA_REPL - #1 ON LINE E/O CO#9 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4873 | -120.7063 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.1 | 18.1 |  |  | 0 | 18.1 | 18.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261065 | RELW OH PRI REMT ESTR BTKA USA FMOB PRTO TER2 | Pole | 2020-03-09 | 2021-02-11 | COMP | 2020-03-06 |  |  | 2019-11-05 | 2019-11-05 | [12 empty] | 2019-04-27 | 2020-04-27 |  | 2020-04-27 | 2021 CBP Plan |  | UNASSIGNED |  | 163751102 | 8391.96 | 55.7 | 55.7 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117113459 | POLE REPL - 1S/O 1E/O ENTRANCE 1640 | 35152569 |  |  | STS-POLE REPL - 1S/O 1E/O ENTRANCE 1640 | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4961 | -120.7199 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J24 | L3635 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 42.2 | 42.2 |  |  | 0 | 42.2 | 42.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101263880 | RELW OH TRAF PRI JPOL RESD FLAG BTKA PROG FMOB TER2 PRTO SCPA SCOP | Pole | 2020-08-03 | 2020-08-10 | COMP | 2020-06-05 |  |  | 2020-04-29 | 2020-04-29 | [12 empty] | 2019-04-27 | 2020-04-27 |  | 2020-04-27 | 2021 CBP Plan |  | UNASSIGNED |  | 163751102 | 24615.81 | 236 |  |  |  | 88.7 |  | 88.7 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117113472 | POLE_BROK_REPL - #1W/O 16380 ROLLING OAK | 35116051 |  |  | STS-POLE_BROK_REPL - #1W/O 16380 ROLLING | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4941 | -120.722 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J24 | 1439 | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 62.1 | 62.1 |  |  | 2.5 | 59.6 | 59.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101263823 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-06-25 | 2020-08-22 | COMP | 2020-06-25 | [16 empty] | 2019-04-27 | 2020-04-27 |  | 2020-04-27 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 163751102 | 27620.92 | 7548 | 7548 | 7548 | 7548 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117115533 | POLE_DECA_REPL - #2E/O 16800 NINA LNFIDD | 35116100 |  |  | STS-POLE_DECA_REPL - #2E/O 16800 NINA LN | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4798 | -120.7141 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 |  | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | [6 empty] | 62 | 62 |  |  | 1.75 | 61 | 61 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261157 | RELW OH PRI REMT TRAF FLAG ESTR BTKA USA PRTO FMOB TER2 | Pole | 2020-06-25 | 2020-06-25 | COMP | 2020-06-25 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-04-28 | 2020-04-28 |  | 2020-04-28 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 163751102 | 14215.08 | 3966.2 | 451.6 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117117897 | POLE_DECA_REPL - R/O 17121 FIDDLETOWN RD | 35116113 |  |  | STS-POLE_DECA_REPL - R/O 17121 FIDDLETOW | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.502 | -120.7084 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 | L3635 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 43.8 | 43.8 |  |  | 0 | 43.8 | 43.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101260670 | RELW OH PRI JPOL REMT ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-04-01 | 2020-05-26 | COMP | 2020-04-01 | [16 empty] | 2019-04-29 | 2019-10-29 |  | 2019-10-29 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 163751102 | 18969.12 | 3791.4 | 3605.7 | 3604.9 | 3604.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117117976 | POLE_DECA_REPL - #1 N/O R/O 17121 FIDDLE | 35116116 |  |  | STS-POLE_DECA_REPL - #1 N/O R/O 17121 FI | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5026 | -120.7087 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 |  | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 2 | 30 | 30 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101260669 | RELW OH PRI JPOL REMT ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-06-22 | 2020-08-24 | COMP | 2020-06-22 | [16 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 163751102 | 12658.33 | 3109.8 | 2656.1 | 1810.7 | 1810.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117118120 | POLE_DECA_REPL - #1 E/O #1 N/O 17005 FID | 35116119 |  |  | STS-POLE_DECA_REPL - #1 E/O #1 N/O 17005 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5027 | -120.7093 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 |  | Y | 311 |  |  | 2021-02-18 07:00 | 2021-02-18 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 33.7 | 33.7 |  |  | 0 | 33.7 | 33.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101260668 | RELW OH PRI JPOL REMT ESTR REAR USA FMOB PRTO TER2 | Pole | 2020-05-18 | 2020-07-28 | COMP | 2020-05-18 | [16 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 163751102 | 15006.09 | 3310.8 | 3176 | 3176 | 3176 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117128315 | POLE_DECA_REPL - #1S/O #4E/O ENTRANCE 17 | 35116172 |  |  | STS-POLE_DECA_REPL - #1S/O #4E/O ENTRANC | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4784 | -120.702 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 | 43975 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43 | 43 |  |  | 0 | 43 | 43 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261188 | RELW OH PRI REMT ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-12-18 | 2020-12-18 | COMP | 2020-12-18 | [16 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 163751102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117078278 | POLE_DECA_REPL - #1S/O RED MULE RD ON OL | 35115893 |  |  | STS-POLE_DECA_REPL - #1S/O RED MULE RD O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4926 | -120.7011 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101260862 | OH RELW PRI TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2021-01-10 | 2021-01-10 | COMP | 2021-01-10 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-04-22 | 2020-04-22 |  | 2020-04-22 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 163751102 | 14134.23 | 72.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117078539 | POLE_DECA_REPL - #2N/O HOUSE 17501 OLD R | 35115894 |  |  | STS-POLE_DECA_REPL - #2N/O HOUSE 17501 O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4914 | -120.7007 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 | L1117 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101260856 | RELW OH BTKA PRI FLAG ESTR FMOB TER2 PRTO | Pole | 2021-01-10 | 2021-01-10 | COMP | 2021-01-10 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-04-22 | 2020-04-22 | 2020-12-23 | 2020-12-23 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 163751102 | 20006.14 | 85.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117088014 | POLE_BROK_REPL - #1W/O HOUSE 17250 TYLER | 35214595 |  |  | STS-POLE_BROK_REPL - #1W/O HOUSE 17250 T | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5252 | -120.704 |  | TIER 2 | 528 | 16354-1102, OLETA | I25 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103388420 | RELW OH PRI REMT ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-15 | 2021-01-15 | COMP | 2021-01-15 | [16 empty] | 2019-04-23 | 2020-04-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163541102 | 5631.77 |  | 0 | 851 | 851 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117114638 | POLE_DECA_REPL - #1 W/O HOUSE @ 17050 HA | 35116090 |  |  | STS-POLE_DECA_REPL - #1 W/O HOUSE @ 1705 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.48 | -120.7046 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 | 43975 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50.9 | 50.9 |  |  | 0 | 50.9 | 50.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261129 | RELW OH PRI REMT FLAG ESTR BTKA USA PROG FMOB TER2 PRTO | Pole | 2021-01-10 | 2021-01-10 | COMP | 2021-01-10 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-04-28 | 2020-04-28 |  | 2020-04-28 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 163751102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Jackson |  |  | OPEN | 117120890 | POLE_BROK_REPL - R/O 17005 FIDDLETOWN RD | 35116143 |  |  | STS-POLE_BROK_REPL - R/O 17005 FIDDLETOW | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5021 | -120.7103 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 | L3635 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101260664 | RELW OH PRI JPOL REMT ESTR GO REAR FMOB TER2 PRTO | Pole | 2019-09-12 | 2021-01-14 | COMP | 2019-09-12 | [16 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan |  | Fresno |  | 163751102 | 27925.17 | 39.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FIDDLETOWN | Stockton |  |  | OPEN | 117325714 | POLE_DECA_REPL - #2S/O #1W/O HOUSE 16915 | 35116275 |  |  | STS-POLE_DECA_REPL - #2S/O #1W/O HOUSE 1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4928 | -120.7096 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50.9 | 50.9 |  |  | 0 | 50.9 | 50.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101260894 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-12-31 | 2020-12-31 | COMP | 2020-12-31 | [16 empty] | 2019-05-27 | 2020-05-27 |  | 2020-05-27 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 163751102 | 6773.17 | 75.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FOREST MEADOWS | Angels Camp |  |  | OPEN | 116973027 | POLE_DECA_REPL - A/F 3401 BRICE STATION | 35086353 |  |  | STS-POLE_DECA_REPL - A/F 3401 BRICE STAT | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1687 | -120.411 |  | TIER 2 | 230 | 16282-1701, STANISLAUS | Q3205 | 43569 | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | [6 empty] | 32.5 | 32.5 |  |  | 0 | 32.5 | 32.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101275809 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-09-03 | 2020-11-05 | COMP | 2020-09-02 | [16 empty] | 2019-04-07 | 2020-04-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 162821701 | 11197.57 | 10700.7 | 10112.3 | 21112.3 | 21112.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FOREST MEADOWS | Angels Camp |  |  | OPEN | 117126254 | POLE_BROK_REPL - R/O 5696 DARBY RUSELL R | 35122914 |  |  | STS-POLE_DECA_REPL - 5696 DARBY RUSSELL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1697 | -120.3831 |  | TIER 2 | 230 | 16282-1701, STANISLAUS | Q3303 | L1861 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 478.9 | 478.9 |  |  | 0 | 478.9 | 478.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101275702 | REGW OH PRI CLR REMT NOAC ESTR GO REAR FMOB TER2 PRTO FSRP | Pole | 2020-06-05 | 2020-11-29 | COMP | 2020-06-05 | [16 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-07-31 | Stockton |  | 162821701 | 248281.49 | 409.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FOREST MEADOWS | Angels Camp |  |  | OPEN | 117126424 | POLE_BROK_REPL - R/O 5613 DARBY RUSSELL | 35122914 |  |  | STS-POLE_DECA_REPL - 5696 DARBY RUSSELL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1705 | -120.3834 |  | TIER 2 | 230 | 16282-1701, STANISLAUS | Q3303 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101275704 | REGW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-06-05 | 2020-11-29 | COMP | 2020-06-05 | [16 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-07-31 | Stockton |  | 162821701 | 248281.49 | 409.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FOREST MEADOWS | Angels Camp |  |  | OPEN | 117126580 | POLE_BROK_REPL - R/O 5597 DARBY RUSSELL | 35122914 |  |  | STS-POLE_DECA_REPL - 5696 DARBY RUSSELL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1712 | -120.3836 |  | TIER 2 | 230 | 16282-1701, STANISLAUS | Q3303 | L1861 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101275706 | REGW OH PRI REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-06-05 | 2020-11-29 | COMP | 2020-06-05 | [16 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-07-31 | Stockton |  | 162821701 | 248281.49 | 409.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | FOREST MEADOWS | Angels Camp |  |  | OPEN | 117137709 | POLE_BROK_REPL - #1E @ R/O 395 SNOWBERRY | 35123123 |  |  | STS-POLE_BROK_REPL - #1E @ R/O 395 SNOWB | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1718 | -120.3981 |  | TIER 2 | 230 | 16282-1701, STANISLAUS | Q3302 | L593 | Y | 311 |  |  |  |  | Dispatched | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 33.8 | 32.8 | 1 |  | 0 | 33.8 | 32.8 | 1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101276013 | RELW ESTR OH PRI REMT BTKA USA FMOB TER2 PRTO | Pole | 2019-10-29 | 2019-10-29 | COMP | 2019-10-29 | [16 empty] | 2019-05-01 | 2020-05-01 |  | 2020-05-01 | circuit based plan 2.14 |  | UNASSIGNED |  | 162821701 | 41712.51 | 14822.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | IONE | Angels Camp |  |  | OPEN | 117171804 | POLE_BROK_REPL - #7S/O ENTRANCE 4900 STO | 35202508 |  |  | STS-POLE_BROK_REPL - #7S/O ENTRANCE 4900 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2747 | -120.8715 |  | TIER 2 | 254 | 16334-1103, CLAY | O21A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101238578 | RELW OH PRI REMT FIRE NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-06 | 2020-05-06 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163341103 | 1 | 8.8 | -1141.3 | -49.3 | -49.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Angels Camp |  |  | OPEN | 117271578 | POLE_DECA_REPL - #1NE/O ENTRANCE 1923 BU | 35206542 |  |  | STS-POLE_DECA_REPL - #1NE/O ENTRANCE 192 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2406 | -120.8849 |  | TIER 2 | 254 | 16334-1103, CLAY | P20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 15.6 | 15.6 |  |  | 0 | 15.6 | 15.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239224 | RELW OH PRI PGEA CLR REMT FIRE NOAC ESTR GO USA FMOB TER2 PRTO FSRP | Pole | 2020-12-22 | 2020-12-22 | COMP | 2020-12-22 | [16 empty] | 2019-05-19 | 2019-08-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 163341103 | 6455.08 | 376.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Angels Camp |  |  | OPEN | 117271811 | POLE_DECA_REPL - #1N/W/O ENTRANCE 1923 B | 35206479 |  |  | STS-POLE_DECA_REPL - #1N/W/O ENTRANCE 19 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2404 | -120.8862 |  | TIER 2 | 254 | 16334-1103, CLAY | P20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 16.9 | 16.9 |  |  | 0 | 16.9 | 16.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239239 | RELW OH SEC PGEA REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 | 2020-12-11 | COMP | 2020-12-11 | [16 empty] | 2019-05-19 | 2020-05-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 163341103 | 7244.29 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 116791558 | POLE_DECA_REPL - C/O HWY 49/SPANISH ST O | 35202202 |  |  | STS-POLE_DECA_REPL - C/O HWY 49/SPANISH | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.4407 | -120.8545 |  | TIER 2 | 483 | 16354-1101, OLETA | K2114 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101236278 | RELW OH PRI CLR JPOL RESD REMT FIRE ESTR PRTO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2020-11-04 | 2020-11-04 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163541101 | 1 |  | -945 | 147 | 147 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 116812330 | POLE_DECA_REPL - #2S ON LINE @ R/O 15050 | 35215469 |  |  | STS-POLE_DECA_REPL - #2S ON LINE @ R/O 1 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.4245 | -120.8599 |  | TIER 2 | 483 | 16354-1101, OLETA | K21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31 | 31 |  |  | 0 | 31 | 31 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101236543 | RELW OH PRI CLR REMT FIRE NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-16 | 2020-12-15 | COMP | 2020-12-15 | [16 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163541101 | 14537.2 | 17.7 | -506.9 | -280.6 | -280.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 116815517 | POLE_DECA_REPL - 1 N/O 16500 IRISH HILL | 35202345 |  |  | STS-POLE_DECA_REPL - 1 N/O 16500 IRISH H | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.4241 | -120.9555 |  | TIER 2 | 1293 | 16388-1101, IONE | K19 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239361 | RELW OH PRI JPOL REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163881101 | 1 | 8.8 | -1141.3 | -49.3 | -49.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117120593 | POLE_DECA_REPL - CO-L471 HWY 88IONE95640 | 35202304 |  |  | STS-POLE_DECA_REPL - CO-L471 HWY 88IONE9 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 38.3393 | -120.8933 |  | TIER 2 | 715 | 16301-1103, MARTELL | M20 | 1819 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.7 | 57.7 |  |  | 0 | 57.7 | 57.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101240186 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-28 | 2021-01-27 | COMP | 2021-01-27 | [16 empty] | 2019-04-29 | 2020-04-29 | 2020-11-27 | 2020-11-27 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011103 | 25707.95 | 730.4 | -1041.1 | 50.9 | 50.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117126726 | POLE_DECA_REPL - 1E/O C/O BLUE SKY DR/BU | 35202368 |  |  | STS-POLE_DECA_REPL - 1E/O C/O BLUE SKY D | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.3526 | -120.88 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 19.2 | 19.2 |  |  | 0 | 19.2 | 19.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239439 | RELW OH PRI REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-14 |  | COMP | 2020-12-14 | [16 empty] | 2019-04-30 | 2020-04-30 | 2020-11-20 | 2020-11-20 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011103 | 10542.32 | 8.8 | -1141.3 | -1141.3 | -1141.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117179993 | POLE_BROK_REPL - #2N/O ENTRANCE 3501 BUE | 35166907 |  |  | STS-POLE_BROK_REPL - #2N/O ENTRANCE 3501 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.2627 | -120.8785 |  | TIER 2 | 254 | 16334-1103, CLAY | O21A | L1963 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 32.5 | 32.5 |  |  | 0 | 32.5 | 32.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101238943 | RELW OH PRI JPOL REMT TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-04 |  | COMP | 2021-02-04 | [16 empty] | 2019-05-07 | 2020-05-07 | 2024-05-05 | 2024-05-05 | 2021 CBP Plan | 2020-10-31 | TRC |  | 163341103 | 15546.63 | 44.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117182140 | POLE_BROK_REPL - #1E/O HOUSE 3725 BUENA | 35166908 |  |  | STS-POLE_BROK_REPL - #1E/O HOUSE 3725 BU | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2641 | -120.8794 |  | TIER 2 | 254 | 16334-1103, CLAY | O21A | L1963 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101238942 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 163341103 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117215018 | POLE_DECA_REPL - 1S/O 10202 BLUE SKY DRI | 35202603 |  |  | STS-POLE_DECA_REPL - 1S/O 10202 BLUE SKY | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.3574 | -120.8791 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 | L917 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 55.9 | 55.9 |  |  | 0 | 55.9 | 55.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239486 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-11-10 |  | COMP | 2020-11-10 | [16 empty] | 2019-05-11 | 2020-05-11 | 2020-11-13 | 2020-11-13 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011103 | 24372.16 | 1154.3 | -1520.8 | -1520.8 | -1520.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117218249 | POLE_DECA_REPL - 2S/O 9300 BROOK RANCH R | 35202630 |  |  | STS-POLE_DECA_REPL - 2S/O 9300 BROOK RAN | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 38.3451 | -120.8764 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 29.7 | 29.7 |  |  | 0 | 29.7 | 29.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239389 | OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP RELW | Pole | 2020-12-01 |  | COMP | 2020-12-01 | [16 empty] | 2019-05-12 | 2020-05-12 | 2020-11-18 | 2020-11-18 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163011103 | 11664.54 | 92.5 | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117218365 | POLE_BROK_REPL - #2 S/O C/O COMANCHE PKW | 35166909 |  |  | STS-POLE_BROK_REPL - #2 S/O C/O COMANCHE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.2489 | -120.9441 |  | TIER 2 | 254 | 16334-1103, CLAY | O1923 | L1687 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 49.3 | 49.3 |  |  | 0 | 49.3 | 49.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101245068 | RELW OH PRI FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-09-03 |  | COMP | 2020-09-03 | [16 empty] | 2019-05-12 | 2020-05-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 163341103 | 24487.34 | 44.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117227598 | POLE_BROK_REPL - 11051 RANCHO RDIONE9564 | 35202680 |  |  | STS-POLE_BROK_REPL - 11051 RANCHO RDIONE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.37 | -120.8696 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 | L3863 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 30.2 | 30.2 | 0 |  | 0 | 30.2 | 30.2 | 0 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101238769 | RELW FLAG OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-11-10 |  | COMP | 2020-11-10 | [16 empty] | 2019-05-13 | 2020-05-13 | 2020-11-26 | 2020-11-26 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011103 | 15655.23 | 1246.5 | -1656.5 | -1656.5 | -1656.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117322511 | POLE_DECA_REPL - 5E/O 8100 HWY 88 IONE | 35215707 |  |  | STS-POLE_DECA_REPL - 5E/O 8100 HWY 88 IO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.3431 | -120.8733 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239315 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-26 | 2020-05-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163011103 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117322693 | POLE_BROK_REPL - 2E/O R/O 9561 SUTTER CR | 35203020 |  |  | STS-POLE_BROK_REPL - 2E/O R/O 9561 SUTTE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3483 | -120.8676 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101239174 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-26 | 2020-05-26 | 2020-11-26 | 2020-11-26 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011103 | 1 | 1483 | -1040.3 | 887.7 | 887.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117325389 | POLE_BROK_REPL - 1E/O R/O 8251 BUFFALO R | 35203030 |  |  | STS-POLE_BROK_REPL - 1E/O R/O 8251 BUFFA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3576 | -120.8723 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101238911 | RELW OH PRI NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-27 | 2020-05-27 | 2020-11-22 | 2020-11-22 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011103 | 1 | 1626.1 | 8.7 | 1345.2 | 1345.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117325430 | POLE_BROK_REPL - AT 8050 BUFFALO RIDGE R | 35203032 |  |  | STS-POLE_BROK_REPL - AT 8050 BUFFALO RID | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3557 | -120.8729 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 | L1247 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101238905 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-27 | 2020-05-27 | 2020-11-20 | 2020-11-20 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011103 | 1 | 44.5 | -1060 | 32 | 32 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117327885 | POLE_BROK_REPL - 1N/O 9901 BLUE SKY DR I | 35203041 |  |  | STS-POLE_BROK_REPL - 1N/O 9901 BLUE SKY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3566 | -120.879 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101239480 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-28 | 2020-05-28 | 2020-11-13 | 2020-11-13 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011103 | 1 |  | -945 | 115 | 115 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117327955 | POLE_BROK_REPL - AT 10601 BLUE SKY DRION | 35203045 |  |  | STS-POLE_BROK_REPL - AT 10601 BLUE SKY D | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3655 | -120.876 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 | L3863 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101239514 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-28 | 2020-05-28 | 2020-11-24 | 2020-11-24 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163011103 | 1 | 89.3 | -945 | 115 | 115 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117120646 | POLE_BROK_REPL - 3E/O REG-R210 HWY 88(WE | 35202310 |  |  | STS-POLE_BROK_REPL - 3E/O REG-R210 HWY 8 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3364 | -120.8994 |  | TIER 2 | 254 | 16334-1103, CLAY | M20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 16.9 | 16.9 |  |  | 0 | 16.9 | 16.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101240196 | RELW OH PRI CLR REMT FMOB ESTR BTKA USA TER2 PRTO FSRP | Pole | 2020-11-12 | 2020-11-12 | COMP | 2020-11-12 | [16 empty] | 2019-04-29 | 2020-04-29 | 2020-11-28 | 2020-11-28 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163341103 | 6503.69 | 1030.6 | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117178075 | POLE_BROK_REPL - 1W/O 5S/O C/O#1619 S/O | 35180703 |  |  | STS-POLE_BROK_REPL - 1W/O 5S/O C/O#1619 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3567 | -120.9253 |  | TIER 2 | 254 | 16334-1103, CLAY | M1915 | 717 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | [6 empty] | 31.8 | 31.8 |  |  | 1 | 30.8 | 30.8 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101243054 | RELW OH PRI CLR FLAG ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-11 | 2020-12-11 | COMP | 2020-12-11 |  |  | 2020-12-11 | 2020-12-11 | [12 empty] | 2019-05-07 | 2020-05-07 | 2020-08-27 | 2020-08-27 | B-Tag Addition 06.24.20 | 2020-12-31 | Stockton |  | 163341103 | 16115.35 | 2882 | 2882 | 2881.2 | 2881.2 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-06-29
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117277842 | POLE_BROK_REPL - 1S/O R/O 9300 BROOK RAN | 35202932 |  |  | STS-POLE_BROK_REPL - 1S/O R/O 9300 BROOK | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3448 | -120.8742 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.8 | 16.8 |  |  | 0 | 16.8 | 16.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101239384 | RELW OH PRI CLR NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2021-02-05 | 2021-02-05 | COMP | 2021-02-05 | [16 empty] | 2019-05-20 | 2020-05-20 | 2020-11-26 | 2020-11-26 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163011103 | 9215.37 | 8.8 | -1412.8 | -320.8 | -320.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117071668 | POLE_DECA_REPL - 1/O 13241 MT ECHO RD IO | 35166905 |  |  | STS-POLE_DECA_REPL - 1/O 13241 MT ECHO R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4035 | -120.9122 |  | TIER 2 | 243 | 16334-1101, CLAY | L2006 | L3787 | Y | 311 |  |  | 2021-07-29 07:00 | 2021-07-29 16:00 | Reserved | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101286072 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-08-22 | 2021-02-02 | COMP | 2020-08-18 |  |  | 2021-02-02 | 2021-02-02 | [12 empty] | 2019-04-20 | 2020-04-20 | 2024-04-18 | 2024-04-18 | 2021 CBP Plan | 2020-10-31 | TRC |  | 163341101 | 15138.91 | 482.5 | 120.5 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117094201 | POLE_BROK_REPL - N/0 A/F 11640 PANE RDIO | 35166906 |  |  | STS-POLE_BROK_REPL - N/0 A/F 11640 PANE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3786 | -120.8771 |  | TIER 2 | 243 | 16334-1101, CLAY | L21 | 1781 | Y | 311 |  |  | 2021-07-29 07:00 | 2021-07-29 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 28.3 | 28.3 |  |  | 0.5 | 27.8 | 27.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101238612 | RELW OH PRI CLR USA FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-10-14 | 2021-02-03 | COMP | 2020-10-14 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-24 | 2020-04-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-09-30 | Stockton |  | 163341101 | 15715.91 | 286.6 | 120.5 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117105333 | POLE_BROK_REPL - 4E/O OF 6636 0F TONZI R | 35202216 |  |  | STS-POLE_BROK_REPL - 4E/O OF 6636 0F TON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4007 | -120.9 |  | TIER 2 | 243 | 16334-1101, CLAY | L20 | L1267 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 52.7 | 52.7 |  |  | 0 | 52.7 | 52.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101237541 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-01-20 | COMP | 2021-01-20 | [16 empty] | 2019-04-26 | 2020-04-26 | 2020-11-30 | 2020-11-30 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163341101 | 13966.88 | 8.8 | -945 | 147 | 147 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117120164 | POLE_DECA_REPL - R/O 6451 HWY 104 IONE | 35202294 |  |  | STS-POLE_DECA_REPL - R/O 6451 HWY 104 IO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3329 | -120.9074 |  | TIER 2 | 254 | 16334-1103, CLAY | M20 | 1819 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101240206 | RELW OH PRI JPOL ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-26 | 2021-01-26 | COMP | 2021-01-26 | [16 empty] | 2019-04-29 | 2020-04-29 | 2020-11-28 | 2020-11-28 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163341103 | 16636.19 | 8.8 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117120735 | POLE_DECA_REPL - 8E/O 3N/O 1E/O R/O 6451 | 35214958 |  |  | STS-POLE_DECA_REPL - 8E/O 3N/O 1E/O R/O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.336 | -120.9014 |  | TIER 2 | 254 | 16334-1103, CLAY | M20 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101240198 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-07 | 2021-01-08 | COMP | 2021-01-06 | [16 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163341103 | 12757.55 | 8.8 | 0 | 688 | 688 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117121211 | POLE_BROK_REPL - 9E/O 3N/O 1E/O R/O 6451 | 35202319 |  |  | STS-POLE_BROK_REPL - 9E/O 3N/O 1E/O R/O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3361 | -120.901 |  | TIER 2 | 254 | 16334-1103, CLAY | M20 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101240197 | RELW OH PRI CLR REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-25 | 2021-01-25 | COMP | 2021-01-25 | [16 empty] | 2019-04-29 | 2020-04-29 | 2020-11-28 | 2020-11-28 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163341103 | 6066.21 | 8.8 | -945 | 147 | 147 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117127480 | POLE_DECA_REPL - 9900 SUTTER CR RANCHOS | 35202385 |  |  | STS-POLE_DECA_REPL - 9900 SUTTER CR RANC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3539 | -120.8676 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 |  | Y | 311 |  |  | 2021-07-29 07:00 | 2021-07-29 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 14.1 | 14.1 |  |  | 0 | 14.1 | 14.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101238868 | RELW OH PRI JPOL REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-10 | 2021-01-29 | COMP | 2020-12-09 | [16 empty] | 2019-04-30 | 2020-04-30 | 2020-11-19 | 2020-11-19 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163011103 | 7525.99 | 53.4 | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117132149 | POLE_DECA_REPL - 1S/O 1E/O 1N/O 9900 SUT | 35202411 |  |  | STS-POLE_DECA_REPL - 1S/O 1E/O 1N/O 9900 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3543 | -120.8668 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101238882 | RELW OH SERV REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-01 | 2021-01-20 | COMP | 2020-12-01 | [16 empty] | 2019-04-30 | 2020-04-30 | 2020-11-21 | 2020-11-21 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163011103 | 7690.72 | 44.5 | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117163099 | POLE_BROK_REPL - #1N/O #1E/O HOUSE 2500 | 35215274 |  |  | STS-POLE_BROK_REPL - #1N/O #1E/O HOUSE 2 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2459 | -120.8799 |  | TIER 2 | 254 | 16334-1103, CLAY | O21A | L1963 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101239191 | RELW OH PRI JPOL REMT ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-27 | 2021-01-27 | COMP | 2021-01-27 | [16 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163341103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117215111 | POLE_DECA_REPL - 10916–11516 BLUE SKY DR | 35202606 |  |  | STS-POLE_DECA_REPL - 10916–11516 BLUE SK | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3579 | -120.8777 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 | L917 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103182656 | RELW OH PRI CLR ESTR BTKA USA FSRP PRTO FMOB TER2 | Pole | 2020-11-16 | 2021-01-04 | COMP | 2020-11-16 | [16 empty] | 2019-05-11 | 2020-05-11 | 2020-11-13 | 2020-11-13 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163011103 | 20353.2 | 8.8 | -1520.8 | -1520.8 | -1520.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117216332 | POLE_DECA_REPL - ENT TO 10501 BLUE SKY D | 35202608 |  |  | STS-POLE_DECA_REPL - ENT TO 10501 BLUE S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3623 | -120.8786 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103375011 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-04 | 2021-01-05 | COMP | 2020-11-10 | [16 empty] | 2019-05-11 | 2020-05-11 | 2020-11-24 | 2020-11-24 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011103 | 9133.78 | 1122.8 | -2109 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117218285 | POLE_DECA_REPL - 1S/O 9300 BROOK RANCH R | 35202633 |  |  | STS-POLE_DECA_REPL - 1S/O 9300 BROOK RAN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3457 | -120.8765 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239390 | RELW OH PRI CLR ESTR TER2 BTKA USA FMOB PRTO FSRP | Pole | 2020-11-23 | 2021-01-15 | COMP | 2020-11-23 | [16 empty] | 2019-05-12 | 2020-05-12 | 2020-11-18 | 2020-11-18 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011103 | 7346.52 | 92.2 | -1701.7 | -1656.5 | -1656.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117218680 | POLE_BROK_REPL - 1E\O 9500 BROOK RANCH R | 35202641 |  |  | STS-POLE_BROK_REPL - 1E\O 9500 BROOK RAN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3477 | -120.8754 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101239394 | RELW OH PRI RESD USA REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-11-23 | 2021-01-15 | COMP | 2020-11-23 | [16 empty] | 2019-05-12 | 2020-05-12 | 2020-11-18 | 2020-11-18 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011103 | 15818.9 | 8.8 | -1747 | -1656.5 | -1656.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Jackson |  |  | OPEN | 117322434 | POLE_DECA_REPL - 5W/O 8100 HWY 88 IONE | 35203016 |  |  | STS-POLE_DECA_REPL - 5W/O 8100 HWY 88 IO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3427 | -120.8802 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239377 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-07 | 2021-01-07 | COMP | 2021-01-07 | [16 empty] | 2019-05-26 | 2020-05-26 | 2020-11-19 | 2020-11-19 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011103 | 5157.85 | 8.8 | -945.1 | 833.7 | 833.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Stockton |  |  | OPEN | 117126060 | POLE_DECA_REPL - CO-L1247 SUTTER CR RANC | 35215017 |  |  | STS-POLE_DECA_REPL - CO-L1247 SUTTER CR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.3454 | -120.8667 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 | L1247 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 55.3 | 53.6 | 1.7 |  | 0 | 55.3 | 53.6 | 1.7 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101238808 | RELW OH PRI RESD REMT ESTR BTKA USA FMOB FSRP PRTO TER2 | Pole | 2020-12-15 |  | COMP | 2020-12-15 | [16 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163011103 | 28193.33 | 17.7 | -506.8 | -235.3 | -235.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | IONE | Stockton |  |  | OPEN | 117312106 | POLE_DECA_REPL - R/O 220 HWY 16IONE95640 | 35202976 |  |  | STS-POLE_DECA_REPL - R/O 220 HWY 16IONE9 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.477 | -121.0214 |  | TIER 2 | 483 | 16354-1101, OLETA | J17 | 1179 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101233450 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-23 | 2020-05-23 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163541101 | 1 | 17.4 | -1042.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 116813500 | POLE_BROK_REPL - N C/O TABEAU RD ON E CL | 35202321 |  |  | STS-POLE_BROK_REPL - N C/O TABEAU RD ON | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.3629 | -120.6486 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M26A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101269420 | RELW OH FLAG PRI CLR REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2020-11-17 | 2020-11-17 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 1 | 3790 | 3580.1 | 2700.7 | 2700.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 116817634 | POLE_DECA_REPL - 2 S/O 5530 OVERLOOK CT | 35202380 |  |  | STS-POLE_DECA_REPL - 2 S/O 5530 OVERLOOK | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.4271 | -120.9217 |  | TIER 2 | 483 | 16354-1101, OLETA | K1925 | L3785 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.3 | 36.3 |  |  | 0 | 36.3 | 36.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239178 | RELW OH PRI JPOL RESD ESTR FMOB REAR RTRN TER2 PRTO FSRP | Pole | 2021-02-22 |  | COMP | 2021-02-22 | [16 empty] | 2019-03-23 | 2020-03-23 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163541101 | 15478.97 |  | -1060 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 116875206 | POLE_BROK_REPL - C/O BAKER LN AND MANZAN | 35082855 |  |  | STS-POLE_BROK_REPL - C/O BAKER LN AND MA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.4343 | -120.7466 |  | TIER 2 | 498 | 16301-1101, MARTELL | K24 |  | Y | 311 | [5 empty] | Order Operation | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101262637 | RELW OH PRI CLR JPOL REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2019-09-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Stockton |  | 163011101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 116876046 | POLE_DECA_REPL - 8927 LAUREN LNJACKSON95 | 35202575 |  |  | STS-POLE_DECA_REPL - 8927 LAUREN LNJACKS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.33 | -120.7135 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2521 | 9775 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103378114 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2020-11-20 | 2020-11-20 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 1 |  | -1060 | 32 | 32 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117128478 | POLE_DECA_REPL - 4N/O 9411 GOMEZ LNJACKS | 35202390 |  |  | STS-POLE_DECA_REPL - 4N/O 9411 GOMEZ LNJ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.353 | -120.8503 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239910 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-30 | 2020-11-19 | 2020-11-19 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011103 | 1 | 8.8 | -1060 | 32 | 32 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117229205 | POLE_DECA_REPL - #4SW 10827 PREVITALI RD | 35202686 |  |  | STS-POLE_DECA_REPL - #4SW 10827 PREVITAL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.3632 | -120.7091 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M25A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.8 | 25.8 |  |  | 0 | 25.8 | 25.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101263004 | RELW OH PRI REMT FIRE FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-09 |  | COMP | 2021-02-09 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-11-17 | 2020-11-17 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 20808.89 | 44.5 | -1060 | 32 | 32 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117234430 | POLE_DECA_REPL - #2S ON LINE R/O HOUSE @ | 35202821 |  |  | STS-POLE_DECA_REPL - #2S ON LINE R/O HOU | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3619 | -120.6924 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2509 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101263381 | RELW OH PRI REMT FIRE ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2020-11-18 | 2020-11-18 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 1 |  | -2290 | -452.5 | -452.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117242226 | POLE_DECA_REPL - #4 ON LINE N/O HOUSE @ | 35202850 |  |  | STS-POLE_DECA_REPL - #4 ON LINE N/O HOUS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.3376 | -120.7014 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M25A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.1 | 21.1 |  |  | 0 | 21.1 | 21.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101263372 | RELW FIRE OH PRI REMT ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-07 |  | COMP | 2020-12-07 | [16 empty] | 2019-05-15 | 2020-05-15 | 2020-11-20 | 2020-11-20 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 15735.44 |  | -2109 | -1747 | -1747 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117260305 | POLE_BROK_REPL - #3 ON LINE E/O HOUSE @ | 35202905 |  |  | STS-POLE_BROK_REPL - #3 ON LINE E/O HOUS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 38.3627 | -120.6977 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2508 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101263316 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-17 | 2020-05-17 | 2020-11-19 | 2020-11-19 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 1 | 77.5 | -1060 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117324387 | POLE_DECA_REPL - 1W/O 5S/O 1W/O 19121 W | 35203022 |  |  | STS-POLE_DECA_REPL - 1W/O 5S/O 1W/O 1912 | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3617 | -120.6752 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2606 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101270444 | RELW OH PRI CLR REMT NOAC SWRK ESTR BTKA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-27 | 2020-05-27 | 2020-11-18 | 2020-11-18 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 1 |  | -1060 | 32 | 32 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117325058 | POLE_DECA_REPL - 1S/O 1W/O 19121 W CLINT | 35215735 |  |  | STS-POLE_DECA_REPL - 1S/O 1W/O 19121 W C | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3642 | -120.6729 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2606 | L2549 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101270471 | RELW OH PRI CLR REMT NOAC SWRK ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-27 | 2020-05-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162161101 | 1 | 67.6 | 67.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117325061 | POLE_DECA_REPL - @18662 W CLINTON RDJACK | 35203024 |  |  | STS-POLE_DECA_REPL - @18662 W CLINTON RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3609 | -120.6751 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2606 | 494583 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.5 | 34.5 |  |  | 0 | 34.5 | 34.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101270462 | RELW OH PRI CLR RESD REMT NOAC SWRK ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-02-08 | 2021-02-16 | COMP | 2021-02-04 | [16 empty] | 2019-05-27 | 2020-05-27 | 2020-11-18 | 2020-11-18 | 2021 CBP Plan | 2021-02-28 | TRC |  | 162161101 | 14532.1 | 1265.1 | 187.4 | 1249.8 | 1249.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117339902 | POLE_BROK_REPL - 4SE/O 2E/O 10551 HWY 88 | 35203079 |  |  | STS-POLE_BROK_REPL - 4SE/O 2E/O 10551 HW | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.35 | -120.8264 |  | TIER 2 | 715 | 16301-1103, MARTELL | M22 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.7 | 16.7 |  |  | 0 | 16.7 | 16.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101239830 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-05 | 2021-02-04 | COMP | 2021-02-04 | [16 empty] | 2019-05-29 | 2020-05-29 | 2020-11-21 | 2020-11-21 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011103 | 7509.27 | 46.7 | -163.3 | 928.7 | 928.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117408153 | POLE_DECA_REPL - #2 ON LINE NW/O HOUSE @ | 35203119 |  |  | STS-POLE_DECA_REPL - #2 ON LINE NW/O HOU | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3503 | -120.7024 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M25A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101263596 | RELW OH PRI PGEA REMT NOAC CGI ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-07 | 2020-06-07 | 2020-11-20 | 2020-11-20 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 1 | 233.7 | 23.7 | 1115.7 | 1115.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117689201 | POLE _BROK _REPL_#1NE #1W ON LINE @ CO#1 | 35149869 |  |  | STS-POLE _BROK _REPL_#1NE #1W ON LINE @ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4181 | -120.6461 |  | TIER 2 |  |  | L2605 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.6 | 19.6 |  |  | 0 | 19.6 | 19.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101256263 | RELW OH PRI ESTR TER2 PRTO | Pole | 2020-09-11 | 2021-02-12 | COMP | 2020-09-11 | [16 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | 2021 CBP Plan | 2020-10-31 | TRC |  |  | 9570.15 | 495.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 116846964 | POLE_BROK_REPL - 4W/O 10299 TABEAUD RDJA | 35083610 |  |  | STS-POLE_BROK_REPL - 4W/O 10299 TABEAUD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.359 | -120.6628 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M26A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.3 | 14.3 |  |  | 0 | 14.3 | 14.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101269208 | RELW OH PRI CLR REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-11-30 | 2020-11-30 | COMP | 2020-11-30 | [16 empty] | 2019-03-26 | 2020-03-26 | 2020-11-17 | 2020-11-17 | 2021 CBP Plan | 2021-02-28 | TRC |  | 162161101 | 7831.57 |  | -1837.5 | -1747 | -1747 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 116876304 | POLE_DECA_REPL - #2E CO#9975 W/O SHIRLEY | 35202577 |  |  | STS-POLE_DECA_REPL - #2E CO#9975 W/O SHI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3436 | -120.7178 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2516 | L5691 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.1 | 41.6 | 2.5 |  | 0 | 44.1 | 41.6 | 2.5 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101263222 | RELW OH PRI CLR ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-15 | 2020-12-15 | COMP | 2020-12-15 | [16 empty] | 2019-03-31 | 2020-03-31 | 2020-11-20 | 2020-11-20 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 20757.33 |  | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117325112 | POLE_DECA_REPL - 2S/O 1W/O 19121 W CLINT | 35203026 |  |  | STS-POLE_DECA_REPL - 2S/O 1W/O 19121 W C | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3631 | -120.6733 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2606 | 494583 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.9 | 37.9 |  |  | 0 | 37.9 | 37.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101270467 | RELW OH PRI CLR REMT NOAC SWRK ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-07 | 2020-12-07 | COMP | 2020-12-07 | [16 empty] | 2019-05-27 | 2020-05-27 | 2020-11-18 | 2020-11-18 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 17267.09 |  | -2181.4 | 857.6 | 857.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 116816587 | POLE_DECA_REPL - R/O 14977 PATTON RD JAC | 35202355 |  |  | STS-POLE_DECA_REPL - R/O 14977 PATTON RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4279 | -120.9239 |  | TIER 2 | 483 | 16354-1101, OLETA | K1925 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239167 | RELW OH SERV JPOL ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-01 | 2021-01-20 | COMP | 2020-12-01 | [16 empty] | 2019-03-23 | 2020-03-23 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163541101 | 3495.66 |  | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117126999 | POLE_BROK_REPL - 1E/O R/O 9411 EGGIMANN | 35202377 |  |  | STS-POLE_BROK_REPL - 1E/O R/O 9411 EGGIM | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.351 | -120.8508 |  | TIER 2 | 715 | 16301-1103, MARTELL | M21 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101239905 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-11-30 | 2021-01-22 | COMP | 2020-11-30 | [16 empty] | 2019-04-30 | 2020-04-30 | 2020-11-19 | 2020-11-19 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163011103 | 9286.21 | 8.8 | -2018.5 | -1837.5 | -1837.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117228847 | POLE_BROK_REPL - 11190 RANCHETTE RD @ HO | 35202683 |  |  | STS-POLE_BROK_REPL - 11190 RANCHETTE RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3698 | -120.6913 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2504 | 494583 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101263445 | RELW OH PRI JPOL REMT TER2 ESTR BTKA USA FMOB PRTO FSRP | Pole | 2020-12-02 | 2021-01-19 | COMP | 2020-12-02 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-11-19 | 2020-11-19 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 24223.47 |  | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117242143 | POLE_BROK_REPL - #4 ON LINE N/O HOUSE @ | 35202848 |  |  | STS-POLE_BROK_REPL - #4 ON LINE N/O HOUS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3361 | -120.703 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M25A |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101263370 | RELW OH PRI REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-08 | 2021-01-25 | COMP | 2020-12-07 | [16 empty] | 2019-05-15 | 2020-05-15 | 2020-11-20 | 2020-11-20 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 17504.45 |  | -2109 | -1747 | -1747 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | JACKSON | Jackson |  |  | OPEN | 117691543 | POLE_BROK_REPL - #4W ON LINE @ REG#R210 | 35202364 |  |  | STS-POLE_BROK_REPL - #4W ON LINE @ REG#R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3362 | -120.9003 |  | TIER 2 |  |  | M20 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102315969 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-01-20 | COMP | 2021-01-20 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-11-28 | 2020-11-28 | 2021 CBP Plan | 2021-01-31 | TRC |  |  | 5986.89 | 8.8 | -945 | 147 | 147 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | Jackson | Jackson |  |  | OPEN | 120217211 | POLE_BROK_REPL - 16046 BUTTE MOUNTAIN RD | 35220989 |  |  | STS-POLE_BROK_REPL - 16046 BUTTE MOUNTAI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-09 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3457 | -120.7287 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2419 | L2231 | Y | 311 |  |  | 2021-07-29 07:00 | 2021-07-29 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101263773 | OH ESTR TER2 RELW | Pole | 2021-01-20 | 2021-02-01 | COMP | 2021-01-11 |  |  | 2021-01-20 | 2021-02-01 | [12 empty] | 2020-12-06 | 2021-02-06 |  | 2021-02-06 | B tag clean up 12/21/2020 |  | Stockton |  | 162161101 | 17260.85 | 299.1 | 299.1 | 299.1 | 299.1 |  |  |  | Electric Distribution | N | Pulled from MPP Import File | N |  | Y | 2020-12-21
Bay/Central | ST | K26 | Jackson |  |  | OPEN | 116864797 | POLE_DECA_REPL - 2SW\O 19650 BUCKEYE DRK | 35215342 |  |  | STS-POLE_DECA_REPL - 2SW\O 19650 BUCKEYE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.4544 | -120.6601 |  | TIER 2 | 498 | 16301-1101, MARTELL | K26 | L3947 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261550 | RELW OH PRI CLR ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163011101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | K26 | Jackson |  |  | OPEN | 116864806 | POLE_BROK_REPL - 1SW\O 19650 BUCKEYE DR | 35215352 |  |  | STS-POLE_BROK_REPL - 1SW\O 19650 BUCKEYE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 38.4544 | -120.6601 |  | TIER 2 | 498 | 16301-1101, MARTELL | K26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.2 | 20.2 |  |  | 0 | 20.2 | 20.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101261548 | RELW RESD OH PRI CLR ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-17 |  | COMP | 2020-12-17 | [16 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163011101 | 9435.93 |  | 0 | 226.3 | 226.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MH | Angels Camp |  |  | OPEN | 116865424 | POLE_BROK_REPL - #1E 4670 LOMBARDI DRMH | 35152567 |  |  | STS-POLE_BROK_REPL - #1E 4670 LOMBARDI D | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2512 | -120.7033 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | O25 | L2147 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101249885 | RELW OH PRI INSP ESTR FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 |  | 2020-03-29 | 2021 CBP Plan | 2021-01-31 | Stockton |  | 162211101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MOKELUMNE HILL | Angels Camp |  |  | OPEN | 117450489 | POLE_BROK_REPL - #1SE S MAIN ST ON HWY 4 | 35152621 |  |  | STS-POLE_BROK_REPL - #1SE S MAIN ST ON H | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2982 | -120.7051 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | NN2503 | 1577 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 58.9 | 58.9 |  |  | 0 | 58.9 | 58.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101240967 | RELW OH PRI ESTR GO FMOB TER2 PRTO | Pole | 2020-07-13 | 2020-09-28 | COMP | 2020-07-13 | [16 empty] | 2019-06-16 | 2020-06-16 |  | 2020-06-16 | 2021 CBP Plan | 2020-08-31 | Stockton |  | 162211101 | 40064.73 | 156.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MOUNTAIN RANCH | Angels Camp |  |  | COMP | 117191603 | POLE_BROK_REPL - CO#5247 S/O 7495 DOSTER | 35180066 |  |  | STS-POLE_BROK_REPL - CO#5247 S/O 7495 DO | DOCC | DOCC ERDY SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-03 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.2444 | -120.615 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | O27 | 2143 | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 47.1 | 47.1 |  |  | 0 | 47.1 | 47.1 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101250692 | RELW OH PRI INSP COMP REMT ESTR BTKA CCNT FMOB TER2 | Pole | 2020-07-03 | 2020-07-07 | COMP | 2020-06-26 | COMP | 2021-01-06 | [13 empty] | 2021-01-07 | 2021-01-06 | 2020-05-09 | 2020-07-31 | 2020-07-31 | B-Tag Addition 06.24.20 |  | Stockton |  | 162211101 | 12972.57 | 10247.3 | 6275.6 | 15848.5 | 15848.5 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | ST | MOUNTAIN RANCH | Angels Camp |  |  | OPEN | 117107467 | POLE_BROK_REPL - #2N ON LINE @ 8260 GARA | 35152568 |  |  | STS-POLE_BROK_REPL - #2N ON LINE @ 8260 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2267 | -120.5409 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | O29 | L5225 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 52.7 | 52.7 |  |  | 0 | 52.7 | 52.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101268206 | RELW OH PRI INSP ESTR TER2 FMOB | Pole | 2020-07-20 | 2021-01-19 | COMP | 2020-07-20 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-04-26 | 2020-04-26 |  | 2020-04-26 | 2021 CBP Plan | 2020-08-31 | Stockton |  | 162211101 | 27154.65 | 292.9 | 293 | 213.5 | 213.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MOUNTAIN RANCH | Angels Camp |  |  | OPEN | 117132708 | POLE_BROK_REPL - 9395 ELDORADO TR W/TRAN | 35152572 |  |  | STS-POLE_BROK_REPL - 9395 ELDORADO TR W/ | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2381 | -120.5381 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | O29 | 1167 | Y | 311 |  |  | 2021-02-16 07:00 | 2021-02-16 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 56.1 | 56.1 |  |  | 0 | 56.1 | 56.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101268174 | RELW OH PRI INSP ESTR FMOB TER2 | Pole | 2020-04-23 | 2020-06-11 | COMP | 2020-04-23 | [16 empty] | 2019-05-01 | 2020-05-01 |  | 2020-05-01 | circuit based plan 2.14 | 2020-06-30 | Stockton |  | 162211101 | 27831.68 | 2927.2 | 2882.9 | 1011.7 | 1011.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | MOUNTAIN RANCH | Angels Camp |  |  | OPEN | 117167818 | POLE_DECA_REPL - 6693 SIERRA VISTA LOOKO | 35180702 |  |  | STS-POLE_DECA_REPL - 6693 SIERRA VISTA L | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2341 | -120.6148 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | O27 | L3211 | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 128.8 | 128.8 |  |  | 2 | 126.8 | 126.8 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101250880 | RELW INSP OH PRI REMT ESTR GO FMOB TER2 | Pole | 2020-07-17 | 2020-07-20 | COMP | 2020-07-16 | [16 empty] | 2019-05-06 | 2020-05-06 | 2020-08-28 | 2020-08-28 | B-Tag Addition 06.24.20 | 2020-08-31 | TRC |  | 162211101 | 34826.83 | 7995.8 | 825.2 | 624.4 | 624.4 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | ST | MOUNTAIN RANCH | Angels Camp |  |  | OPEN | 117209185 | POLE_BURN_REPL - 1N/O/R/O 8027 PONDEROSA | 35218160 |  |  | STS-POLE_BURN_REPL - 1N/O/R/O 8027 PONDE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2033 | -120.5353 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | P29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 26.5 | 26.5 |  |  | 0 | 26.5 | 26.5 |  |  | EC | E | Pole | Burnt | Replace |  | 101279994 | RELW OH PRI INSP CLR RESD ESTR GO BTKA REAR PROG SCOP SCPA FMOB TER2 | Pole | 2020-12-23 | 2020-12-23 | COMP | 2020-12-23 | [16 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 35658 |  | UNASSIGNED |  | 162211101 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-02
Bay/Central | ST | MOUNTAIN RANCH | Angels Camp |  |  | OPEN | 117267654 | POLE_DECA_REPL - 7578 SHEEP RANCH RD W/T | 35152578 |  |  | STS-POLE_DECA_REPL - 7578 SHEEP RANCH RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2433 | -120.5141 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | O3012 | L4045 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 53.2 | 53.2 |  |  | 0 | 53.2 | 53.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101273671 | RELW OH PRI CLR ESTR FMOB TER2 PRTO | Pole | 2020-08-07 | 2020-10-19 | COMP | 2020-08-07 | [16 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-07-31 | Stockton |  | 162211101 | 24180.25 | 375.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MOUNTAIN RANCH | Jackson |  |  | COMP | 117232104 | POLE_BROK_REPL - #6S ON LINE @ 18502 RAI | 35124063 |  |  | STS-POLE_BROK_REPL - #6S ON LINE @ 18502 | FICL | FICL SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-06-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.2701 | -120.5446 |  | TIER 2 | 23 | 16320-1102, WEST POINT | N29 |  | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 8 | 8 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101249545 | COMP REMT RELW OH SERV ESTR BTKA USA CCNT FMOB TER2 PRTO | Pole | 2019-11-04 | 2019-11-04 | COMP | 2019-11-04 | COMP | 2021-01-13 | [13 empty] | 2021-01-25 | 2021-01-13 | 2020-05-14 |  | 2020-05-14 | circuit based plan 2.14 | 2019-12-04 | QUES |  | 163201102 | 2333.95 | 9740.5 | 9328 | 8798.7 | 8798.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | MOUNTAIN RANCH | Jackson |  |  | OPEN | 117250063 | POLE_DECA_REPL - A/F 17424 BAKER RILEY R | 35124195 |  |  | STS-POLE_DECA_REPL - A/F 17424 BAKER RIL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2732 | -120.5615 |  | TIER 2 | 23 | 16320-1102, WEST POINT | N29 | 1289 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 47.8 | 47.8 |  |  | 1 | 46.8 | 46.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101249930 | RELW OH PRI REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-04-23 | 2020-11-02 | COMP | 2020-04-23 | [16 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-04-23 | EEI |  | 163201102 | 19270.56 | 388.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MOUNTAIN RANCH | Jackson |  |  | OPEN | 117259895 | POLE_OVRL_REPL - #1S 4316 RAILROAD FLAT | 35140292 |  |  | STS-POLE_OVRL_REPL - #1S 4316 RAILROAD F | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.282 | -120.5053 |  | TIER 2 | 23 | 16320-1102, WEST POINT | N30 |  | Y | 311 |  |  | 2020-10-15 | 2020-10-15 | Completed | Order Operation | [6 empty] | 17 | 17 |  |  | 0 | 17 | 17 |  |  | EC | E | Pole | Overloaded | Replace |  | 101273770 | RELW OH PRI CLR REMT FLAG ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-04-14 | 2020-07-28 | COMP | 2019-12-19 |  |  | 2019-12-07 | 2019-12-07 | [12 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | circuit based plan 2.14 | 2019-12-19 | CALENG |  | 163201102 | 10364.76 | 5401.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | MOUNTAIN RANCH | Jackson |  |  | OPEN | 117336622 | POLE_DECA_REPL - #8S ON LINE @ 14300 PON | 35152620 |  |  | STS-POLE_DECA_REPL - #8S ON LINE @ 14300 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2978 | -120.6022 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | N28 |  | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 15.9 | 15.9 |  |  | 0 | 15.9 | 15.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101247123 | RELW OH PRI PGEA CLR REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-06-26 | 2020-06-26 | COMP | 2020-06-26 | [16 empty] | 2019-05-29 | 2020-05-29 |  | 2020-05-29 | circuit based plan 2.14 | 2020-04-30 | Stockton |  | 162211101 | 6840.21 | 1216.9 | 1172.6 | 1178.9 | 1178.9 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | MOUNTAIN RANCH | Stockton |  |  | OPEN | 117274513 | POLE_BROK_REPL - #1S ON LINE @ 17255 JES | 35124461 |  |  | STS-POLE_BROK_REPL - #1S ON LINE @ 17255 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2819 | -120.5696 |  | TIER 2 | 23 | 16320-1102, WEST POINT | N28 |  | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | [6 empty] | 51 | 51 |  | 0 | 0 | 51 | 51 |  | 0 | EC | E | Pole | Broken/Damaged | Replace |  | 101248243 | RELW OH PRI CLR ESTR GO FMOB TER2 PRTO | Pole | 2020-01-29 | 2020-02-18 | COMP | 2020-01-24 | [16 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | circuit based plan 2.14 | 2020-01-24 | EEI |  | 163201102 | 12615.56 | 19953.3 | 16959.7 | 26006.9 | 26006.9 | 1529.5 |  | 1529.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 116848188 | POLE_BROK_REPL - @1N\O 396 CHURCH STMURP | 35202520 |  |  | STS-POLE_BROK_REPL - @1N\O 396 CHURCH ST | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.1389 | -120.4633 |  | TIER 2 | 452 | 16345-1701, FROGTOWN | Q3118 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103103874 | RELW ESTR OH SERV CLR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2020-11-23 | 2020-11-23 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451701 | 1 |  | -945 | 147 | 147 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 116854190 | POLE_DECA_REPL - 4S\O R/O HOUSE 1465 FRE | 35202528 |  |  | STS-POLE_DECA_REPL - 4S\O R/O HOUSE 1465 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.1373 | -120.4824 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | Q31 | L6029 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101276332 | OH RELW PRI JPOL REMT NOAC ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2020-11-23 | 2020-11-23 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451702 | 1 |  | -1060 | 32 | 32 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 116877728 | POLE_BROK_REPL - 5W\O AF 2690 SAN DOMING | 35202583 |  |  | STS-POLE_BROK_REPL - 5W\O AF 2690 SAN DO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.154 | -120.4855 |  | TIER 2 | 452 | 16345-1701, FROGTOWN | Q31 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103367962 | RELW OH PRI CLR RESD REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2020-11-23 | 2020-11-23 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163451701 | 1 | 2985.9 | 2041 | 3101 | 3101 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 117073460 | POLE_DECA_REPL - 3027 MURPHYS GRADE RD M | 35215856 |  |  | STS-POLE_DECA_REPL - 3027 MURPHYS GRADE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Enviro |  |  | 38.1147 | -120.5022 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | R30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.4 | 19.4 |  |  | 0 | 19.4 | 19.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101282410 | RELW OH SERV MINR REMT JAR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-13 |  | COMP | 2021-01-13 | [16 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163451702 | 10284.52 | 98.4 | 0 | 724 | 724 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 117115095 | POLE_BROK_REPL - #1W ON LINE @ R/O 3626 | 35214891 |  |  | STS-POLE_BROK_REPL - #1W ON LINE @ R/O 3 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.1542 | -120.3999 |  | TIER 2 | 230 | 16282-1701, STANISLAUS | Q33 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101275614 | RELW OH PRI REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-28 | 2020-04-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162821701 | 1 | 75.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 117123275 | POLE_BROK_REPL - R/O 3338 SKUNK RANCH RD | 35214973 |  |  | STS-POLE_BROK_REPL - R/O 3338 SKUNK RANC | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.1322 | -120.4021 |  | TIER 2 | 452 | 16345-1701, FROGTOWN | Q33 | L563 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101275581 | RELW PRI OH JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163451701 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 117129180 | POLE_BROK_REPL - #3N ON LINE @ R/O 3500 | 35202395 |  |  | STS-POLE_BROK_REPL - #3N ON LINE @ R/O 3 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.1374 | -120.3928 |  | TIER 2 | 452 | 16345-1701, FROGTOWN | Q33 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.1 | 38.1 |  |  | 0 | 38.1 | 38.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101275597 | RELW OH PRI JPOL REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-02-17 | 2021-02-16 | COMP | 2021-02-16 | [16 empty] | 2019-04-30 | 2020-04-30 | 2020-09-28 | 2020-09-28 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163451701 | 26199.73 | 34.8 | -1025.2 | 32 | 32 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 117130589 | POLE_BROK_REPL - 3400 SKUNK RANCH RD W/T | 35206586 |  |  | STS-POLE_BROK_REPL - 3400 SKUNK RANCH RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.135 | -120.3975 |  | TIER 2 | 452 | 16345-1701, FROGTOWN | Q33 | L563 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 38.9 | 38.9 |  |  | 0 | 38.9 | 38.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101275588 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 |  | COMP | 2020-12-11 | [16 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 163451701 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 117131083 | POLE_BROK_REPL - 647 FAIR OAKS LN MURPHY | 35202400 |  |  | STS-POLE_BROK_REPL - 647 FAIR OAKS LN MU | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.1289 | -120.4604 |  | TIER 2 | 452 | 16345-1701, FROGTOWN | R31 | 2563 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.6 | 32 | 0.6 |  | 0 | 32.6 | 32 | 0.6 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101285620 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-01-19 | COMP | 2021-01-19 | [16 empty] | 2019-04-30 | 2020-04-30 | 2020-11-26 | 2020-11-26 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451701 | 14153.16 |  | -1060 | 814 | 814 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 117132187 | POLE_BROK_REPL - S/O 647 FAIR OAKS LN MU | 35202416 |  |  | STS-POLE_BROK_REPL - S/O 647 FAIR OAKS L | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.1283 | -120.4599 |  | TIER 2 | 452 | 16345-1701, FROGTOWN | R31 | 2563 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.2 | 43.8 | 0.4 |  | 0 | 44.2 | 43.8 | 0.4 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101285622 | RELW PRI OH JPOL REMT ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2021-02-22 |  | COMP | 2021-02-22 | [16 empty] | 2019-04-30 | 2020-04-30 | 2020-11-26 | 2020-11-26 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451701 | 18331.89 |  | -1060 | 32 | 32 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 117301719 | POLE_DECA_REPL - 39 N/O 3675 SIX MILE RD | 35202956 |  |  | STS-POLE_DECA_REPL - 39 N/O 3675 SIX MIL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1238 | -120.4709 |  | TIER 2 | 452 | 16345-1701, FROGTOWN | R31 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.9 | 31.9 |  |  | 0 | 31.9 | 31.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101285599 | RELW OH PRI CLR JPOL REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-02-16 | 2021-02-16 | COMP | 2021-02-16 | [16 empty] | 2019-05-22 | 2020-05-22 | 2020-11-27 | 2020-11-27 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451701 | 13548.64 |  | -1060 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 116859084 | POLE_BROK_REPL - 3W\O 1N\O C\O ALLEN LN | 35212192 |  |  | STS-POLE_BROK_REPL - 3W\O 1N\O C\O ALLEN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-05-03 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1333 | -120.4568 |  | TIER 2 | 452 | 16345-1701, FROGTOWN | Q3124 | L6055 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 24 | 24 |  |  | 0 | 24 | 24 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101278320 | RELW OH PRI JPOL REMT ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 | 2021-01-28 | COMP | 2020-12-09 | [16 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | B tag clean up 11/8/2020 |  | Stockton |  | 163451701 | [9 empty] | N | MPP File Only | N |  | Y | 2020-11-08
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 116873184 | POLE_BROK_REPL - @HOUSE #99 BIG TREE RD8 | 35192894 |  |  | STS-POLE_BROK_REPL - @HOUSE #99 BIG TREE | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1377 | -120.4591 |  | TIER 2 | 452 | 16345-1701, FROGTOWN | Q3124 | 13412 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 80.2 | 80.2 |  |  | 0 | 80.2 | 80.2 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101277636 | RELW OH PRI JPOL REMT FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-09 | 2020-12-17 | COMP | 2020-12-09 |  |  | 2020-11-20 | 2020-11-20 | [12 empty] | 2019-03-30 | 2020-03-30 | 2020-11-02 | 2020-11-02 | B-Tag Clean Up 8/25/20 |  | Stockton |  | 163451701 | 39743.85 | 596 | 188.6 | 188.6 | 188.6 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-08-27
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 116876274 | POLE_BROK_REPL - 8S\O 6W\O 1071 POWER HO | 35083085 |  |  | STS-POLE_BROK_REPL - 7S\O 6W\O 1071 POWE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1452 | -120.4474 |  | TIER 2 | 230 | 16282-1701, STANISLAUS | Q3120 | L6887 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 52.1 | 52.1 |  |  | 0 | 52.1 | 52.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101277062 | REGW OH PRI CLR TRAF ESTR BTKA PRTO USA FMOB TER2 FSRP | Pole | 2020-07-27 | 2020-10-11 | COMP | 2020-07-27 | [16 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-09-30 | Stockton |  | 162821701 | 33941.06 | 123.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 116876533 | POLE_BROK_REPL - 7S\O 6W\O 1071 POWER HO | 35083085 |  |  | STS-POLE_BROK_REPL - 7S\O 6W\O 1071 POWE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1456 | -120.4473 |  | TIER 2 | 230 | 16282-1701, STANISLAUS | Q3120 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101277061 | RELW OH PRI CLR NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-07-27 | 2020-10-11 | COMP | 2020-07-27 | [16 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-09-30 | Stockton |  | 162821701 | 33941.06 | 123.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 116970240 | POLE_BROK_REPL - R/O 1253 PENNSYLVANIA G | 35202138 |  |  | STS-POLE_BROK_REPL - R/O 1253 PENNSYLVAN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1314 | -120.4358 |  | TIER 2 | 452 | 16345-1701, FROGTOWN | Q3222 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.8 | 20.8 |  |  | 0 | 20.8 | 20.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101275420 | RELW OH PRI JPOL REMT ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-15 | 2021-01-15 | COMP | 2021-01-15 | [16 empty] | 2019-04-06 | 2019-10-06 | 2020-10-21 | 2020-10-21 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451701 | 7533.3 |  | -1092.6 | 808.4 | 808.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 117130930 | POLE_BROK_REPL - 2 R/O 735 SIX MILE RDMU | 35180430 |  |  | STS-POLE_BROK_REPL - 2 R/O 735 SIX MILE | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1268 | -120.4606 |  | TIER 2 | 452 | 16345-1701, FROGTOWN | R31 |  | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 30 | 30 |  |  | 0.25 | 29.75 | 29.75 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101285616 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-07-27 | 2020-08-05 | COMP | 2020-06-27 | [16 empty] | 2019-04-30 | 2019-09-30 | 2020-08-26 | 2020-08-26 | B-Tag Addition 06.24.20 |  | Stockton |  | 163451701 | 13365.41 | 4678.7 | 191.5 | -9.3 | -9.3 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 119844946 | POLE_DECA_REPL - C/O HWY 4/BRICE STATION | 35205319 |  |  | STS-POLE_DECA_REPL - C/O HWY 4/BRICE STA | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1696 | -120.412 |  | TIER 2 | 230 | 16282-1701, STANISLAUS | Q3205 | 43569 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 23 | 23 |  |  | 0 | 23 | 23 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101275808 | RELW OH ESTR GO PROG TER2 | Pole | 2021-02-11 | 2021-02-12 | COMP | 2020-11-09 |  |  | 2020-11-14 | 2020-11-14 | [12 empty] | 2020-09-22 | 2020-12-22 |  | 2020-12-22 | B tag clean up 10/11/2020 |  | UNASSIGNED |  | 162821701 | 15918.79 | 1121 | 297.6 | 113.1 | 113.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-10-11
Bay/Central | ST | MURPHYS | Angels Camp |  |  | OPEN | 117129039 | POLE_DECA_REPL - #1N ON LINE @ R/O 3500 | 35206587 |  |  | STS-POLE_DECA_REPL - #1N ON LINE @ R/O 3 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1362 | -120.3941 |  | TIER 2 | 452 | 16345-1701, FROGTOWN | Q33 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.9 | 50.9 |  |  | 0 | 50.9 | 50.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101275595 | RELW OH PRI JPOL REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-11-18 | 2021-01-02 | COMP | 2020-11-18 | [16 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 163451701 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | NEW CHICAGO | Jackson |  |  | OPEN | 116789558 | POLE_DECA_REPL - 9472 SPANISH STNEW CHIC | 35082792 |  |  | STS-POLE_DECA_REPL - 9472 SPANISH STNEW | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.4421 | -120.849 |  | TIER 2 | 483 | 16354-1101, OLETA | K2114 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101236274 | RELW OH PRI CLR RESD REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163541101 | 1 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PG | Jackson |  |  | OPEN | 116842323 | POLE_BROK_REPL - #2S ON LINE @ 13201 SPA | 35115515 |  |  | STS-POLE_BROK_REPL - #2S ON LINE @ 13201 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4 | -120.6595 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | L2613 | L357 | Y | 311 |  |  | 2021-03-03 07:00 | 2021-03-03 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 35.5 | 35.5 |  |  | 9 | 35.3 | 35.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101257083 | RELW OH PRI INSP ESTR REAR FMOB TER2 | Pole | 2020-09-03 | 2021-02-13 | COMP | 2020-09-03 |  |  | 2019-11-24 | 2019-11-24 | [12 empty] | 2019-03-26 | 2020-03-26 |  | 2020-03-26 | Q1 Work Plan |  | Bakersfield |  | 163751102 | 19474.99 | 17408.5 | -2677.7 | 235.1 | 235.1 | 2912.7 |  | 2912.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | PG | Jackson |  |  | OPEN | 116842386 | POLE_BROK_REPL - #1E #2S ON LINE @ 13201 | 35115516 |  |  | STS-POLE_BROK_REPL - #1E #2S ON LINE @ 1 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4 | -120.6579 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | L2613 | L357 | Y | 311 |  |  | 2021-03-03 07:00 | 2021-03-03 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101257076 | RELW ESTR OH PRI INSP REAR FMOB TER2 | Pole | 2019-10-29 | 2019-11-24 | COMP | 2019-10-22 |  |  | 2019-11-24 | 2019-11-24 | [12 empty] | 2019-03-26 | 2020-03-26 |  | 2020-03-26 | circuit based plan 2.14 |  | UNASSIGNED |  | 163751102 | 16092.63 | 3808.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | PG | Jackson |  |  | OPEN | 116842387 | POLE_BROK_REPL - #1W 13280 SPAGNOLI MINE | 35115517 |  |  | STS-POLE_BROK_REPL - #1W 13280 SPAGNOLI | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3996 | -120.6594 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | L2613 | L357 | Y | 311 |  |  | 2021-03-03 07:00 | 2021-03-03 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 24.9 | 24.9 |  |  | 0 | 24.9 | 24.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101257086 | RELW OH PRI INSP ESTR FMOB TER2 | Pole | 2019-12-08 | 2020-05-14 | COMP | 2019-12-08 |  |  | 2020-05-14 | 2020-05-14 | [12 empty] | 2019-03-26 | 2020-03-26 |  | 2020-03-26 | circuit based plan 2.14 | 2020-03-26 | W. Sac |  | 163751102 | 13330.49 | 1880.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 116756610 | POLE_BROK_REPL - 3W/O 11141 TABEAUD RDPI | 35082761 |  |  | STS-POLE_BROK_REPL - 3W/O 11141 TABEAUD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.37 | -120.6441 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2605 | L3993 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101269715 | RELW OH PRI CLR JPOL REMT ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2020-11-17 | 2020-11-17 | 2021 CBP Plan | 2021-02-28 | TRC |  | 162161101 | 1 |  | -1060 | 1092 | 1092 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 116757130 | POLE_DECA_REPL - 1N/O 11141 PINE GROVE T | 35082763 |  |  | STS-POLE_DECA_REPL - 1N/O 11141 PINE GRO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.3697 | -120.6414 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2605 | L1581 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101269801 | RELW OH PRI CLR REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2020-11-17 | 2020-11-17 | 2021 CBP Plan | 2021-02-28 | TRC |  | 162161101 | 1 |  | -1060 | 1092 | 1092 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 116757323 | POLE_DECA_REPL - 11141 TABEAU RDPINE GRO | 35082990 |  |  | STS-POLE_DECA_REPL - 11141 TABEAU RDPINE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.3706 | -120.6412 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2605 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 24.8 | 24.8 |  |  | 0.5 | 24.3 | 24.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101269802 | RELW OH PRI CLR REMT TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-23 | 2020-12-22 | COMP | 2020-12-22 | [16 empty] | 2019-03-18 | 2020-03-18 | 2020-11-16 | 2020-11-16 | 2021 CBP Plan | 2021-02-28 | TRC |  | 162161101 | 15243.94 | 215.5 | -1503.3 | 453.7 | 453.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 116757719 | POLE_DECA_REPL - @21441 DOVE CT PINE GRO | 35202153 |  |  | STS-POLE_DECA_REPL - @21441 DOVE CT PINE | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3669 | -120.6308 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2702 | L1697 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101270033 | RELW OH PRI CLR JPOL REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2020-11-18 | 2020-11-18 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 1 |  | -1060 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 116760096 | POLE_DECA_REPL - 11411 PINE GROVE TABEAU | 35082995 |  |  | STS-POLE_DECA_REPL - 11411 PINE GROVE TA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.3734 | -120.6405 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2605 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101269807 | RELW OH PRI CLR FMOB REMT NOAC ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2020-11-16 | 2020-11-16 | 2021 CBP Plan | 2021-02-28 | TRC |  | 162161101 | 1 |  | -210 | 1092 | 1092 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 116803010 | POLE_BROK_REPL - 115' S/W CRISTINA PINE | 35202220 |  |  | STS-POLE_BROK_REPL - 115' S/W CRISTINA P | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.3721 | -120.6697 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M26A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.6 | 15.6 |  |  | 0 | 15.6 | 15.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103129187 | RELW OH PRI CLR JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-25 |  | COMP | 2021-01-25 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-11-17 | 2020-11-17 | 2021 CBP Plan | 2021-02-28 | TRC |  | 162161101 | 7115.15 |  | -1060 | 32 | 32 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 116803166 | POLE_BROK_REPL - 1S/O 5W/O C/O CHRISTINA | 35215256 |  |  | STS-POLE_BROK_REPL - 1S/O 5W/O C/O CHRIS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.3723 | -120.6702 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M26A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101270572 | RELW OH PRI CLR JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162161101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 116846797 | POLE_BROK_REPL - 1E/O R/O 10380 TABEAU R | 35084389 |  |  | STS-POLE_BROK_REPL - 1E/O R/O 10380 TABE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 38.3568 | -120.6541 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M26A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101269007 | RELW OH PRI CLR REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162161101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 116975417 | POLE_BROK_REPL - 1S\O 1W\O 1N\O 20340 WI | 35116059 |  |  | STS-POLE_BROK_REPL - 1S\O 1W\O 1N\O 2034 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.4233 | -120.649 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K26 | 1051 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101261159 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-07 | 2020-04-07 |  | 2020-04-07 | 2021 CBP Plan | 2021-01-31 | Bakersfield |  | 163751102 | 1 | 78.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 117153981 | POLE_DECA_REPL - AT 17105 RIDGE RDPINE G | 35152573 |  |  | STS-POLE_DECA_REPL - AT 17105 RIDGE RDPI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4107 | -120.7097 |  | TIER 2 | 140 | 16375-1101, PINE GROVE | L2502 | 99963 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.2 | 38.2 |  |  | 0 | 38.2 | 38.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101271607 | OH PRI INSP CLR FIRE ESTR USA FMOB TER2 RELW | Pole | 2021-02-18 | 2021-02-18 | COMP | 2021-02-18 | [16 empty] | 2019-05-03 | 2020-05-03 |  | 2020-05-03 | 2021 CBP Plan | 2020-06-30 | Stockton |  | 163751101 | 17291.86 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 117181990 | POLE_DECA_REPL - #1N 12544 ELDEL RD/ROAD | 35215435 |  |  | STS-POLE_DECA_REPL - #1N 12544 ELDEL RD/ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.3893 | -120.6413 |  | TIER 2 | 540 | 16216-1101, ELECTRA | L2620 | L3917 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101255247 | RELW OH PRI RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162161101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 117181995 | POLE_DECA_REPL - 12606 ELDEL RD/ROADSIDE | 35202529 |  |  | STS-POLE_DECA_REPL - 12606 ELDEL RD/ROAD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.3901 | -120.6413 |  | TIER 2 | 540 | 16216-1101, ELECTRA | L2620 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.8 | 21.8 |  |  | 0 | 21.8 | 21.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101255250 | RELW OH PRI BTKA RESD FLAG ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-07 |  | COMP | 2020-12-07 | [16 empty] | 2019-05-07 | 2020-05-07 | 2020-11-16 | 2020-11-16 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 8374.65 |  | -2109 | -1928 | -1928 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 117212498 | POLE_DECA_REPL - #1S ON LINE @ 12120 MAR | 35202587 |  |  | STS-POLE_DECA_REPL - #1S ON LINE @ 12120 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3916 | -120.6461 |  | TIER 2 | 540 | 16216-1101, ELECTRA | L2615 | L3873 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101255446 | RELW OH PRI RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-10 | 2020-05-10 | 2020-11-16 | 2020-11-16 | 2021 CBP Plan | 2021-02-28 | TRC |  | 162161101 | 1 |  | -1092.6 | -0.6 | -0.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 117217026 | POLE_DECA_REPL - 20501 DUNSHEE RD/ROADSI | 35202617 |  |  | STS-POLE_DECA_REPL - 20501 DUNSHEE RD/RO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.3757 | -120.6462 |  | TIER 2 | 540 | 16216-1101, ELECTRA | L2625 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.3 | 16.3 |  |  | 0 | 16.3 | 16.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101254770 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-03 |  | COMP | 2021-02-03 | [16 empty] | 2019-05-11 | 2020-05-11 | 2020-11-14 | 2020-11-14 | 2021 CBP Plan | 2021-02-28 | TRC |  | 162161101 | 6068.98 |  | -1060 | 32 | 32 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 117217037 | POLE_DECA_REPL - 20500 DUTSHEE RDPINE GR | 35202620 |  |  | STS-POLE_DECA_REPL - 20500 DUTSHEE RDPIN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.3756 | -120.6468 |  | TIER 2 | 540 | 16216-1101, ELECTRA | L2625 | L1279 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.5 | 37.5 |  |  | 0 | 37.5 | 37.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101254772 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-05 |  | COMP | 2021-02-05 | [16 empty] | 2019-05-11 | 2020-05-11 | 2020-11-14 | 2020-11-14 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 16017.65 |  | -1060 | 32 | 32 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 117271843 | POLE_DECA_REPL - 198 CHURCH STPINE GROVE | 35115809 |  |  | STS-POLE_DECA_REPL - 198 CHURCH STPINE G | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.4128 | -120.6585 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | L2603 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101256649 | RELW OH SERV COMM FLAG ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2021-01-31 | Stockton |  | 163751102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 116842063 | POLE_BROK_REPL - 6W/O 10299 TAABEAUD RDP | 35202505 |  |  | STS-POLE_BROK_REPL - 6W/O 10299 TAABEAUD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3589 | -120.6648 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M26A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.7 | 14.7 |  |  | 0 | 14.7 | 14.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101269215 | RELW PRI OH CLR REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-07 | 2020-12-07 | COMP | 2020-12-07 | [16 empty] | 2019-03-26 | 2020-03-26 | 2020-11-17 | 2020-11-17 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 5906.32 |  | -1928 | -1656.5 | -1656.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 116975055 | POLE_DECA_REPL - 1S\O 1W\O 1S\O 20340 WI | 35116056 |  |  | STS-POLE_DECA_REPL - 1S\O 1W\O 1S\O 2034 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4219 | -120.6484 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K26 | 1051 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.2 | 29.2 |  |  | 0 | 29.2 | 29.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261148 | RELW OH PRI CLR REMT ESTR REAR FMOB TER2 PRTO | Pole | 2020-06-29 | 2020-06-29 | COMP | 2020-06-29 | [16 empty] | 2019-04-07 | 2020-04-07 |  | 2020-04-07 | 2021 CBP Plan | 2020-05-31 | Bakersfield |  | 163751102 | 18887.54 | 2227.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 117220053 | POLE_BROK_REPL - NORTH C/O PINE VIEW DR/ | 35115784 |  |  | STS-POLE_BROK_REPL - NORTH C/O PINE VIEW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4065 | -120.6634 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | L2607 | L2333 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51 | 49.7 | 1.3 |  | 0 | 51 | 49.7 | 1.3 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101257020 | RELW OH PRI JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-08 | 2020-09-24 | COMP | 2019-11-18 |  |  | 2019-12-04 | 2019-12-04 | [12 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan |  | UNASSIGNED |  | 163751102 | 18880.84 | 1370.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 117254003 | POLE_BROK_REPL - 14371 TOBACCO RD PINE G | 35116204 |  |  | STS-POLE_BROK_REPL - 14371 TOBACCO RD PI | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4158 | -120.6427 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | L2605 | 1037 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 2 | 0 | 0 | 0 | 65.5 | 64.1 | 1.4 |  | 0 | 65.5 | 64.1 | 1.4 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101256159 | RELW OH PRI RESD FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-05-31 | Stockton |  | 163751102 | 31111.27 | 44.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 117271830 | POLE_BROK_REPL - #1W IRISH TOWN RD ON HO | 35115801 |  |  | STS-POLE_BROK_REPL - #1W IRISH TOWN RD O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4104 | -120.6609 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | L2603 | L2333 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101256769 | OH RELW PRI RESD FLAG ESTR BTKA PROG FMOB TER2 PRTO | Pole | 2020-05-12 | 2020-10-30 | COMP | 2020-05-12 |  |  | 2020-07-05 | 2020-07-05 | [12 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 163751102 | 22959.06 | 563.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 117271833 | POLE_DECA_REPL - A/F 19724 HWY 88 W/TRAN | 35179339 |  |  | STS-POLE_DECA_REPL - A/F 19724 HWY 88 W/ | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4138 | -120.6613 |  | TIER 2 | 140 | 16375-1101, PINE GROVE | L2603 | L5823 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 61 | 61 |  |  | 0 | 61 | 61 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101256717 | RELW OH PRI FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2021-02-12 | 2021-02-18 | COMP | 2020-06-27 |  |  | 2020-07-28 | 2020-07-28 | [12 empty] | 2019-05-19 | 2020-05-19 | 2020-08-19 | 2020-08-19 | B-Tag Addition 06.24.20 |  | Stockton |  | 163751101 | 33588.73 | 11793.2 | 452.5 | 452.5 | 452.5 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permit Delay - Need caltrans permit | Y | 2020-06-29
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 117327897 | POLE_DECA_REPL - #3NW ON LINE @ 11601 PI | 35203043 |  |  | STS-POLE_DECA_REPL - #3NW ON LINE @ 1160 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3777 | -120.6425 |  | TIER 2 | 540 | 16216-1101, ELECTRA | L2625 | L1581 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 39 | 39 |  |  | 0 | 39 | 39 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101254744 | RELW OH PRI CLR RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-08 | 2020-12-08 | COMP | 2020-12-08 | [16 empty] | 2019-05-28 | 2020-05-28 | 2020-11-14 | 2020-11-14 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 17929.18 |  | -1385 | 1292 | 1292 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 117809240 | POLE_DECA_REPL - AT 17295 RIDGE RDPINE G | 35152622 |  |  | STS-POLE_DECA_REPL - AT 17295 RIDGE RDPI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4109 | -120.7068 |  | TIER 2 | 140 | 16375-1101, PINE GROVE | L2502 | L5879 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.7 | 31.7 |  |  | 0 | 31.7 | 31.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101271601 | OH RELW PRI INSP ESTR BTKA USA FMOB TER2 | Pole | 2020-06-26 | 2020-06-26 | COMP | 2020-06-26 |  |  | 2020-02-21 | 2020-02-21 | [12 empty] | 2019-08-26 | 2020-08-26 |  | 2020-08-26 | 2021 CBP Plan | 2020-06-30 | Stockton |  | 163751101 | 17578.51 | 155.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 116842278 | POLE_BROK_REPL - 15344 MITCHELL MINE RDP | 35115984 |  |  | STS-POLE_BROK_REPL - 15344 MITCHELL MINE | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4301 | -120.6496 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K26 | 1051 | Y | 311 |  |  | 2021-03-11 07:00 | 2021-03-11 15:00 | Dispatched | CLICK | [6 empty] | 32 | 32 |  |  | 1.75 | 30.25 | 30.25 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101261097 | CLR RELW OH PRI REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-06-29 | 2020-06-29 | COMP | 2020-06-29 | [16 empty] | 2019-03-26 | 2020-03-26 |  | 2020-03-26 | 2021 CBP Plan | 2020-05-31 | Bakersfield |  | 163751102 | 19683.26 | 2503.5 | 2503.5 | 2377.2 | 2377.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 116762435 | POLE_BROK_REPL - 2E/O C/O TIMBER RIDGE R | 35082776 |  |  | STS-POLE_BROK_REPL - 2E/O C/O TIMBER RID | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3727 | -120.645 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M2605 | L1279 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101269770 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-07 | 2021-01-22 | COMP | 2020-12-07 | [16 empty] | 2019-03-19 | 2020-03-19 | 2020-11-17 | 2020-11-17 | 2021 CBP Plan | 2021-02-28 | TRC |  | 162161101 | 19375.49 |  | -2290 | -1747 | -1747 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Jackson |  |  | OPEN | 116818759 | POLE_BROK_REPL - 7S/O 10812 TABEAU RDPIN | 35202412 |  |  | STS-POLE_BROK_REPL - 7S/O 10812 TABEAU R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3606 | -120.643 |  | TIER 2 | 540 | 16216-1101, ELECTRA | M26A | L3991 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101269618 | RELW OH PRI CLR REMT ESTR BTKA PRTO USA FMOB TER2 FSRP | Pole | 2021-01-25 | 2021-01-25 | COMP | 2021-01-25 | [16 empty] | 2019-03-23 | 2020-03-23 | 2020-11-23 | 2020-11-23 | 2021 CBP Plan | 2021-02-28 | TRC |  | 162161101 | 19454.61 | 44.6 | -1060 | 32 | 32 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Stockton |  |  | OPEN | 117208002 | POLE_DECA_REPL - 1ST GP@11917 BIG OAK CT | 35202580 |  |  | STS-POLE_DECA_REPL - 1ST GP@11917 BIG OA | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.3805 | -120.6361 |  | TIER 2 | 540 | 16216-1101, ELECTRA | L2721 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 10.8 | 10.8 |  |  | 0 | 10.8 | 10.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101257347 | RELW OH SERV INSP JPOL RESD ESTR BTKA FMOB TER2 FSRP | Pole | 2021-01-26 |  | COMP | 2021-01-26 | [16 empty] | 2019-05-10 | 2020-05-10 | 2020-11-16 | 2020-11-16 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162161101 | 3790.85 |  | -945 | 147 | 147 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PINE GROVE | Stockton |  |  | OPEN | 117180963 | POLE_BROK_REPL - GP@11860 GOLD STRIKE RD | 35225216 |  |  | STS-POLE_BROK_REPL - GP@11860 GOLD STRIK | APPR | APPR | Poles | MPP | Not Funded as 2020 Wildfire OII | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.3805 | -120.6343 |  | TIER 2 | 540 | 16216-1101, ELECTRA | L2721 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101286082 | RELW OH SERV INSP JPOL RESD FLAG BTKA FMOB TER2 FSRP | Pole |  |  | INPR | [17 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | work plan year cleanup 01/21/2021 |  | Stockton |  | 162161101 | [9 empty] | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-21
Bay/Central | ST | PIONEER | Jackson |  |  | COMP | 116716243 | POLE_BROK_REPL - 1 W/O 4 N/O C/O 19901 C | 35149640 |  |  | STS-POLE_BROK_REPL - 1 W/O 4 N/O C/O 199 | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.4971 | -120.6769 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J2606 | L1339 | Y | 311 |  |  | 2021-01-16 | 2021-01-16 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 49.2 | 49.2 |  |  | 0.25 | 48.95 | 48.95 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101261465 | RELW OH PRI INSP COMP CLR REMT FLAG ESTR BTKA RTRN CCNT FMOB TER2 | Pole | 2020-07-28 | 2020-07-28 | COMP | 2020-07-28 | COMP | 2021-01-16 | 2020-02-21 | 2020-02-21 | [11 empty] | 2021-01-25 | 2021-01-16 | 2020-03-12 |  | 2020-03-12 | circuit based plan 2.14 | 2020-09-30 | TRC |  | 163751102 | 19604.26 | 11842.3 | 10709.5 | 22580.3 | 22580.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | PIONEER | Jackson |  |  | OPEN | 119871154 | POLE_BROK_REPL - 23791 HWY 88 PIONEER | 35206398 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-12-11 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4318 | -120.5721 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K2817 | L4021 | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 40.1 | 40.1 |  |  | 0 | 40.1 | 40.1 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101267906 | RELW OH PRI TMAN CLR RESD ESTR GO BTKA USA PROG TER2 | Pole | 2020-11-18 | 2021-01-04 | COMP | 2020-11-18 | [16 empty] | 2020-10-08 | 2021-01-08 |  | 2021-01-08 | B tag clean up 10/18/2020 |  | UNASSIGNED |  | 163751102 | 23724.16 | 1380.8 | 789.8 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N |  | Y | 2020-10-18
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116791587 | POLE_DECA_REPL - 5 E/O 2001 CARBONDALE R | 35202205 |  |  | STS-POLE_DECA_REPL - 5 E/O 2001 CARBONDA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.4485 | -120.9732 |  | TIER 2 | 483 | 16354-1101, OLETA | K18 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.1 | 15.1 |  |  | 0 | 15.1 | 15.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101234371 | RELW OH PRI CLR REMT FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-20 |  | COMP | 2021-01-20 | [16 empty] | 2019-03-20 | 2020-03-20 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163541101 | 9832.94 | 8.8 | -1141.3 | 605.7 | 605.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116794138 | POLE_DECA_REPL - 5 S/O 14880 BARNEY RDPL | 35084361 |  |  | STS-POLE_DECA_REPL - 5 S/O 14880 BARNEY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.4225 | -120.928 |  | TIER 2 | 483 | 16354-1101, OLETA | K19 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239295 | RELW OH PRI REMT ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2019-09-20 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163541101 | 1 |  | -1060 | 394 | 394 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116805670 | POLE_DECA_REPL - 1 S/O 15643 MULLER RDPL | 35082816 |  |  | STS-POLE_DECA_REPL - 1 S/O 15643 MULLER | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.437 | -120.9199 |  | TIER 2 | 483 | 16354-1101, OLETA | K1920 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 24.8 | 24.8 |  |  | 0 | 24.8 | 24.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103380193 | OH RELW PRI JPOL RESD ESTR BTKA RTRN FMOB TER2 PRTO FSRP | Pole | 2021-01-07 | 2021-01-06 | COMP | 2021-01-06 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163541101 | 12726.65 | 73.2 | -210 | 2560 | 2560 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116807910 | POLE_DECA_REPL - 5785 VOORHIES CT/ROADSI | 35084252 |  |  | STS-POLE_DECA_REPL - 5785 VOORHIES CT/RO | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 38.4335 | -120.9155 |  | TIER 2 | 483 | 16354-1101, OLETA | K2016 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.9 | 20.9 |  |  | 0 | 20.9 | 20.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101234593 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-22 | 2021-02-22 | COMP | 2021-02-22 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-12-30 | 2020-12-30 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163541101 | 7633.81 |  | -1060 | 1060 | 1060 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116810795 | POLE_BROK_REPL - 1NW\O 1W\O 11161 AMADOR | 35202285 |  |  | STS-POLE_BROK_REPL - 1NW\O 1W\O 11161 AM | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 38.4215 | -120.8175 |  | TIER 2 | 483 | 16354-1101, OLETA | K2223 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 32.9 | 32.9 |  |  | 0 | 32.9 | 32.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101239198 | RELW OH PRI CLR JPOL REMT ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-22 | 2021-02-03 | COMP | 2020-12-22 | [16 empty] | 2019-03-22 | 2020-03-22 | 2020-11-05 | 2020-11-05 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163541101 | 15316.46 | 17.7 | -1747 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116813227 | POLE_BROK_REPL - HOUSE 14350 HWY 49PLYMO | 35215479 |  |  | STS-POLE_BROK_REPL - HOUSE 14350 HWY 49P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.4207 | -120.8343 |  | TIER 2 | 483 | 16354-1101, OLETA | K22 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101238936 | RELW OH PRI CLR JPOL ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163541101 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116813287 | POLE_DECA_REPL - R/O 15217 PATTON RDPLYM | 35083590 |  |  | STS-POLE_DECA_REPL - R/O 15217 PATTON RD | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.4309 | -120.9233 |  | TIER 2 | 483 | 16354-1101, OLETA | K1920 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239036 | RELW OH SERV JPOL RESD ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2019-09-22 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163541101 | 1 |  | -1060 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116814709 | POLE_BROK_REPL - 1W\O 8615 OLD AMADOR RD | 35202334 |  |  | STS-POLE_BROK_REPL - 1W\O 8615 OLD AMADO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.4236 | -120.8352 |  | TIER 2 | 483 | 16354-1101, OLETA | K22 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.2 | 22.2 |  |  | 0 | 22.2 | 22.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101238869 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-01-19 | COMP | 2021-01-19 | [16 empty] | 2019-03-22 | 2020-03-22 | 2020-11-05 | 2020-11-05 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163541101 | 9531.94 | 62.3 | -945 | 880.5 | 880.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116817558 | POLE_DECA_REPL - 1 S/O 5530 OVERLOOK CTP | 35082829 |  |  | STS-POLE_DECA_REPL - 1 S/O 5530 OVERLOOK | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.4279 | -120.9217 |  | TIER 2 | 483 | 16354-1101, OLETA | K1925 |  | Y | 311 |  |  |  |  | Completed | Order Operation | [6 empty] | 69.4 | 69.4 |  |  | 0 | 19.4 | 19.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239176 | RELW OH ESTR PRI JPOL RESD REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-21 |  | COMP | 2021-01-21 | COMP | 2019-08-15 | [14 empty] | 2019-03-23 | 2020-03-23 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2020-10-31 | TRC |  | 163541101 | 8533.58 | 90.8 | 0 | 2184 | 2184 | 90.8 |  | 90.8 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116823014 | POLE_DECA_REPL - 6N/O AT 6200 HOUT RDPLY | 35082840 |  |  | STS-POLE_DECA_REPL - 6N/O AT 6200 HOUT R | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.4434 | -120.9081 |  | TIER 2 | 483 | 16354-1101, OLETA | K20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.2 | 16.2 |  |  | 0 | 16.2 | 16.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103380228 | RELW OH PRI CLR NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2021-02-03 |  | COMP | 2021-02-03 | [16 empty] | 2019-03-24 | 2020-03-24 | 2020-11-07 | 2020-11-07 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163541101 | 7083.77 | 204.9 | -1060 | 1417 | 1417 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116825959 | POLE_DECA_REPL - #4N 15900 WILLOW CREEK | 35202476 |  |  | STS-POLE_DECA_REPL - #4N 15900 WILLOW CR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.4459 | -120.8996 |  | TIER 2 | 483 | 16354-1101, OLETA | K20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25 | 25 |  |  | 0 | 25 | 25 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101234805 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-02 |  | COMP | 2020-12-02 | [16 empty] | 2019-03-25 | 2020-03-25 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163541101 | 14193.1 | 62.2 | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116834199 | POLE_BROK_REPL - #1W #2N 15900 WILLOW CR | 35202494 |  |  | STS-POLE_BROK_REPL - #1W #2N 15900 WILLO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.4441 | -120.8997 |  | TIER 2 | 483 | 16354-1101, OLETA | K20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101234796 | RELW OH PRI CLR NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163541101 | 1 | 53.4 | -1060 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116847083 | POLE_DECA_REPL - 14931 WILLOW CREEK RD/R | 35202518 |  |  | STS-POLE_DECA_REPL - 14931 WILLOW CREEK | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.426 | -120.9016 |  | TIER 2 | 243 | 16334-1101, CLAY | K20 | L3799 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.8 | 37.8 |  |  | 0 | 37.8 | 37.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101234758 | RELW OH PRI CLR REMT FLAG ESTR BTKA USA FMOB TER2 FSRP PRTO | Pole | 2020-12-02 |  | COMP | 2020-12-02 | [16 empty] | 2019-03-27 | 2020-03-27 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163341101 | 19439.84 | 8.8 | -1928 | -1656.5 | -1656.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116951590 | POLE_DECA_REPL - 4 E/O R/O 1350 HWY 16PL | 35214643 |  |  | STS-POLE_DECA_REPL - 4 E/O R/O 1350 HWY | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 38.4761 | -120.9894 |  | TIER 2 | 483 | 16354-1101, OLETA | J18 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.8 | 22.8 |  |  | 0 | 22.8 | 22.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101233650 | RELW OH PRI REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-23 | 2020-12-21 | COMP | 2020-12-21 | [16 empty] | 2019-04-03 | 2020-04-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163541101 | 8674.27 | 939.5 | 297.2 | -316.7 | -316.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 117319293 | POLE_DECA_REPL - 1E/O/5S/O 240 HWY 16[R/ | 35203008 |  |  | STS-POLE_DECA_REPL - 1E/O/5S/O 240 HWY 1 | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.4794 | -121.0124 |  | TIER 2 | 483 | 16354-1101, OLETA | J17 | 1179 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 60.4 | 60.4 |  |  | 0 | 60.4 | 60.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101233268 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-03 |  | COMP | 2020-12-03 | [16 empty] | 2019-05-24 | 2020-05-24 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163541101 | 35785.74 |  | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116794315 | POLE_DECA_REPL - 3 S/O 14880 BARNEY RDPL | 35084248 |  |  | STS-POLE_DECA_REPL - 3 S/O 14880 BARNEY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4234 | -120.9279 |  | TIER 2 | 483 | 16354-1101, OLETA | K19 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.3 | 13.3 |  |  | 0 | 13.3 | 13.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239290 | RELW OH PRI REMT ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-11-09 | 2020-11-09 | COMP | 2020-11-09 | [16 empty] | 2019-03-20 | 2019-09-16 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163541101 | 5066.99 | 1148.7 | -1475.5 | -1611.3 | -1611.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116805463 | POLE_DECA_REPL - #1S VOORHIES CT ON MULL | 35082815 |  |  | STS-POLE_DECA_REPL - #1S VOORHIES CT ON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4329 | -120.9195 |  | TIER 2 | 483 | 16354-1101, OLETA | K1920 |  | Y | 311 | [5 empty] | Order Operation | [6 empty] | 65 | 65 |  |  | 0 | 65 | 65 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101234579 | RELW OH PRI CLR ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-06-06 | 2020-12-02 | COMP | 2020-06-06 |  |  | 2020-12-02 | 2020-12-02 | [12 empty] | 2019-03-21 | 2019-09-21 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2020-08-31 | Stockton |  | 163541101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116813774 | POLE_DECA_REPL - AT 15874 DEEP CUT CT W/ | 35082824 |  |  | STS-POLE_DECA_REPL - AT 15874 DEEP CUT C | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.44 | -120.9142 |  | TIER 2 | 483 | 16354-1101, OLETA | K2011 | L2275 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 115.1 | 115.1 |  |  | 0 | 115.1 | 115.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103380126 | RELW OH PRI CLR NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-07-09 | 2020-08-14 | COMP | 2020-07-09 | [16 empty] | 2019-03-22 | 2019-09-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-07-31 | Stockton |  | 163541101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116821586 | POLE_BROK_REPL - #2E ON LINE @ R/O 5910 | 35082836 |  |  | STS-POLE_BROK_REPL - #2E ON LINE @ R/O 5 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.447 | -120.9105 |  | TIER 2 | 483 | 16354-1101, OLETA | K20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.7 | 15.7 |  |  | 0 | 15.7 | 15.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101234637 | RELW OH PRI CLR NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2021-02-08 | 2021-02-08 | COMP | 2021-02-08 | [16 empty] | 2019-03-24 | 2020-03-24 | 2020-11-05 | 2020-11-05 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163541101 | 7125.3 | 204.9 | -1060 | 1124 | 1124 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 117008877 | POLE_BROK_REPL - 9448 BUSH ST W/TRANS PL | 35202181 |  |  | STS-POLE_BROK_REPL - 9448 BUSH ST W/TRAN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.468 | -120.8478 |  | TIER 2 | 483 | 16354-1101, OLETA | J2124 | 163225 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.5 | 37.5 |  |  | 0 | 37.5 | 37.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101233419 | RELW PRI OH REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-16 | 2020-12-16 | COMP | 2020-12-16 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-10-07 | 2020-10-07 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163541101 | 20657.97 | 136.9 | -1738.6 | -1105.1 | -1105.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 117306702 | POLE_BROK_REPL - 1 E/O R/O 5015 CARBONDA | 35228752 |  |  | STS-POLE_BROK_REPL - 1 E/O R/O 5015 CARB | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-04-04 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 38.4463 | -120.9315 |  | TIER 2 | 483 | 16354-1101, OLETA | K1914 | L4003 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101238261 | RELW OH PRI JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-23 | 2020-05-23 | 2021-05-02 | 2021-05-02 | B tag clean up 2/19/2021 |  | UNASSIGNED |  | 163541101 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116814958 | POLE_DECA_REPL - 15145 PATTON RDPLYMOUTH | 35202340 |  |  | STS-POLE_DECA_REPL - 15145 PATTON RDPLYM | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4297 | -120.9236 |  | TIER 2 | 483 | 16354-1101, OLETA | K1925 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101239141 | RELW OH SERV JPOL RESD ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-02 | 2021-01-25 | COMP | 2020-12-01 | [16 empty] | 2019-03-22 | 2020-03-22 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163541101 | 6071.12 |  | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | PLYMOUTH | Jackson |  |  | OPEN | 116819264 | POLE_DECA_REPL - 3 S/O 1W/O 3900 HWY 16P | 35214603 |  |  | STS-POLE_DECA_REPL - 3 S/O 1W/O 3900 HWY | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4603 | -120.9515 |  | TIER 2 | 483 | 16354-1101, OLETA | K19 | 1255 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101237901 | RELW OH PRI REMT ESTR GO BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-22 | 2021-01-22 | COMP | 2021-01-22 | [16 empty] | 2019-03-23 | 2020-03-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163541101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | RAIL ROAD FLAT | Jackson |  |  | OPEN | 117269322 | POLE_BROK_REPL - #1SW #1 ON LINE W/O CO# | 35124255 |  |  | STS-POLE_BROK_REPL - #1SW #1 ON LINE W/O | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.337 | -120.5062 |  | TIER 2 | 23 | 16320-1102, WEST POINT | M30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101282652 | RELW OH PRI REMT ESTR BTKA REAR USA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-09-30 | EEI |  | 163201102 | 1 | 396.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | RAIL ROAD FLAT | Jackson |  |  | OPEN | 117231422 | POLE_BROK_REPL - #2SE ON LINE @ R/O 1310 | 35124056 |  |  | STS-POLE_BROK_REPL - #2SE ON LINE @ R/O | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3507 | -120.5097 |  | TIER 2 | 23 | 16320-1102, WEST POINT | M3002 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 16 | 16 |  |  | 0 | 16 | 16 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101282446 | RELW OH SERV REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-01-08 | 2020-01-08 | COMP | 2020-01-08 | [16 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | circuit based plan 2.14 | 2020-01-08 | QUES |  | 163201102 | 5367.03 | 1154.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | RAIL ROAD FLAT | Jackson |  |  | OPEN | 117239913 | POLE_BROK_REPL - 1441 SUMMIT LEVEL RD W/ | 35124146 |  |  | STS-POLE_BROK_REPL - 1441 SUMMIT LEVEL R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3379 | -120.498 |  | TIER 2 | 23 | 16320-1102, WEST POINT | M30 | 1387 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 46.5 | 45.3 | 1.2 |  | 0 | 46.5 | 45.3 | 1.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101282664 | RELW OH PRI JPOL REMT ESTR BTKA TER2 REAR USA FMOB PRTO | Pole | 2020-10-22 | 2020-11-17 | COMP | 2020-10-22 | [16 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-10-31 | QUES |  | 163201102 | 19439.95 | 553.8 | -90.5 | -90.5 | -90.5 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | RAIL ROAD FLAT | Jackson |  |  | OPEN | 117269130 | POLE_BROK_REPL - 1190 SUMMIT LEVEL RD A/ | 35124246 |  |  | STS-POLE_BROK_REPL - 1190 SUMMIT LEVEL R | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3375 | -120.5044 |  | TIER 2 | 23 | 16320-1102, WEST POINT | M30 |  | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | [6 empty] | 22.1 | 22.1 |  |  | 1 | 22 | 22 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101282655 | RELW OH PRI JPOL BTKA REMT ESTR GO REAR FMOB TER2 PRTO | Pole | 2020-03-05 | 2020-08-01 | COMP | 2020-03-05 | [16 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | circuit based plan 2.14 | 2020-03-05 | EEI |  | 163201102 | 8146.39 | 2333.4 | 1013.2 | 1013.2 | 1013.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | RAIL ROAD FLAT | Jackson |  |  | OPEN | 117271953 | POLE_BROK_REPL - #3S ON LINE @ 505 RAILR | 35124428 |  |  | STS-POLE_BROK_REPL - #3S ON LINE @ 505 R | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3229 | -120.52 |  | TIER 2 | 23 | 16320-1102, WEST POINT | M30 |  | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 25.8 | 25.8 |  |  | 19.25 | 24.8 | 24.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101284209 | RELW OH PRI REMT TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-04-03 | 2020-05-14 | COMP | 2020-04-03 |  |  | 2020-05-14 | 2020-05-14 | [12 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | circuit based plan 2.14 | 2020-04-03 | EEI |  | 163201102 | 12552.76 | 19411.7 | 8333.6 | 6462.4 | 6462.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | RAIL ROAD FLAT | Jackson |  |  | OPEN | 117272067 | POLE_BROK_REPL - #1W #1S ON LINE @ 304 B | 35124430 |  |  | STS-POLE_BROK_REPL - #1W #1S ON LINE @ 3 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3307 | -120.5171 |  | TIER 2 | 23 | 16320-1102, WEST POINT | M30 |  | Y | 311 |  |  | 2021-02-12 07:00 | 2021-02-12 16:00 | Completed | CLICK | [6 empty] | 13.8 | 13.8 |  |  | 0 | 13.8 | 13.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101284230 | RELW OH PRI REMT ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-04-07 | 2020-08-03 | COMP | 2020-04-06 |  |  | 2020-08-03 | 2020-08-03 | [12 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | circuit based plan 2.14 | 2020-04-06 | EEI |  | 163201102 | 5750.8 | 762.5 | 694 | 694 | 694 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | RAIL ROAD FLAT | Jackson |  |  | OPEN | 117292562 | POLE_BROK_REPL - #2E ON LINE @ CO#3838 E | 35124558 |  |  | STS-POLE_BROK_REPL - #2E ON LINE @ CO#38 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3275 | -120.5147 |  | TIER 2 | 23 | 16320-1102, WEST POINT | M30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 34.7 | 34.7 |  |  | 0 | 34.7 | 34.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101284296 | RELW OH PRI JPOL REMT ESTR GO REAR FMOB TER2 PRTO | Pole | 2020-09-21 | 2020-10-08 | COMP | 2020-09-21 | [16 empty] | 2019-05-21 | 2020-05-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | EEI |  | 163201102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | RAIL ROAD FLAT | Jackson |  |  | OPEN | 117418710 | POLE_BROK_REPL - #1NE ON LINE @ R/O 888 | 35125302 |  |  | STS-POLE_BROK_REPL - #1NE ON LINE @ R/O | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3588 | -120.4979 |  | TIER 2 | 23 | 16320-1102, WEST POINT | L30 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 15 | 15 |  |  | 0 | 15 | 15 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101251069 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-01-02 | 2020-01-02 | COMP | 2020-01-02 | [16 empty] | 2019-06-08 | 2020-06-08 |  | 2020-06-08 | circuit based plan 2.14 | 2020-01-02 | CALENG |  | 163201102 | 5767.2 | 1571.9 |  |  |  | 403.2 |  | 403.2 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | RAIL ROAD FLAT | Jackson |  |  | OPEN | 117298373 | POLE_BROK_REPL - #1E ON LINE @ CO#3838 E | 35124591 |  |  | STS-POLE_BROK_REPL - #1E ON LINE @ CO#38 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3278 | -120.5157 |  | TIER 2 | 23 | 16320-1102, WEST POINT | M30 |  | Y | 311 |  |  | 2021-05-31 08:20 | 2021-05-31 13:50 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101284295 | RELW OH PRI JPOL REMT ESTR REAR USA FMOB TER2 PRTO | Pole | 2021-01-22 | 2021-01-22 | COMP | 2021-01-22 | [16 empty] | 2019-05-21 | 2020-05-21 |  | 2020-05-21 | 2021 CBP Plan | 2020-10-31 | EEI |  | 163201102 | 14349.91 | 903 | 903 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | RAIL ROAD FLAT | Stockton |  |  | OPEN | 117227491 | POLE_DECA_REPL - 2195 SUMMIT LEVEL RD W/ | 35124028 |  |  | STS-POLE_DECA_REPL - 2195 SUMMIT LEVEL R | CONS | CONS ERDY SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3386 | -120.4842 |  | TIER 2 | 23 | 16320-1102, WEST POINT | M31 | 1387 | Y | 311 |  |  | 2021-02-27 07:00 | 2021-02-27 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 50.1 | 50.1 |  |  | 1 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101282593 | RELW OH PRI CLR TRAF FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2019-10-28 | 2019-10-28 | COMP | 2019-10-28 |  |  | 2019-10-24 | 2019-10-24 | [12 empty] | 2019-05-13 | 2020-05-13 |  | 2020-05-13 | circuit based plan 2.14 | 2019-12-04 | QUES |  | 163201102 | 18483.56 | 5860.7 | 2670.5 | 2598.3 | 2598.3 | 891.9 |  | 891.9 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | RANCHO CALAVERAS | Angels Camp |  |  | OPEN | 116805785 | POLE_BROK_REPL - 1S/O C/O PALONI/HANLEY | 35215339 |  |  | STS-POLE_BROK_REPL - 1S/O C/O PALONI/HAN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.1469 | -120.8544 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2114 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101246870 | RELW OH PRI JPOL FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | RANCHO CALAVERAS | Angels Camp |  |  | OPEN | 116808483 | POLE_DECA_REPL - 1N/O C/O DUNN/BOTFUHER | 35215385 |  |  | STS-POLE_DECA_REPL - 1N/O C/O DUNN/BOTFU | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.1496 | -120.8521 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2115 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101247167 | RELW OH PRI ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | RANCHO CALAVERAS | Angels Camp |  |  | OPEN | 116811709 | POLE_DECA_REPL - 3287 BOTFUHER RD RANCHO | 35215449 |  |  | STS-POLE_DECA_REPL - 3287 BOTFUHER RD RA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.152 | -120.851 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2115 | L9733 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101247177 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | RANCHO CALAVERAS | Angels Camp |  |  | OPEN | 116819543 | POLE_DECA_REPL - 1W/O C/O BALDWIN/TREOST | 35202427 |  |  | STS-POLE_DECA_REPL - 1W/O C/O BALDWIN/TR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.1401 | -120.8614 |  | TIER 2 | 325 | 16299-1103, CORRAL | Q2118 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101248076 | RELW OH PRI JPOL REMT FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 | 2020-09-28 | 2020-09-28 | 2021 CBP Plan | 2021-02-28 | TRC |  | 162991103 | 1 | 89.6 | -1060 | 32 | 32 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | RANCHO CALAVERAS | Angels Camp |  |  | OPEN | 116948032 | POLE_BROK_REPL - 6310 FRIEDMAN WAYRANCHO | 35214596 |  |  | STS-POLE_BROK_REPL - 6310 FRIEDMAN WAYRA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.1235 | -120.8731 |  | TIER 2 | 325 | 16299-1103, CORRAL | R2102 | 59770 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101237175 | RELW REMT OH PRI JPOL ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-03 | 2020-04-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991103 | 1 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | RANCHO CALAVERAS | Angels Camp |  |  | OPEN | 116948278 | POLE_BROK_REPL - 1S/O 6310 FREEMAN WAY R | 35214610 |  |  | STS-POLE_BROK_REPL - 1S/O 6310 FREEMAN W | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.1239 | -120.8728 |  | TIER 2 | 325 | 16299-1103, CORRAL | R2102 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.9 | 25.9 |  |  | 0 | 25.9 | 25.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101237173 | OH RELW PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-30 |  | COMP | 2020-12-30 | [16 empty] | 2019-04-03 | 2020-04-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991103 | 12460.06 | 80.7 | 0 | 497.8 | 497.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | RANCHO CALAVERAS | Angels Camp |  |  | OPEN | 116817387 | POLE_BROK_REPL - D/P AT 5855 CLEMENTS PL | 35202375 |  |  | STS-POLE_BROK_REPL - D/P AT 5855 CLEMENT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1327 | -120.8447 |  | TIER 2 | 325 | 16299-1103, CORRAL | Q2221 | 98399 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.9 | 16.9 |  |  | 0 | 16.9 | 16.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101241849 | RELW OH SEC JPOL FIRE ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-08 | 2021-02-04 | COMP | 2020-12-07 | [16 empty] | 2019-03-23 | 2020-03-23 | 2020-11-30 | 2020-11-30 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162991103 | 11003.38 | 8.8 | -2199.5 | -1566 | -1566 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | RANCHO CALAVERAS | Angels Camp |  |  | OPEN | 116956193 | POLE_DECA_REPL - F/O 6332 MC CAULEY RD R | 35212193 |  |  | STS-POLE_DECA_REPL - F/O 6332 MC CAULEY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-06 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1266 | -120.8561 |  | TIER 2 | 325 | 16299-1103, CORRAL | R2104 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13 | 13 |  |  | 0 | 13 | 13 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101236637 | RELW OH PRI JPOL REMT FLAG TER2 ESTR BTKA FMOB PRTO FSRP | Pole | 2020-12-09 | 2020-12-17 | COMP | 2020-12-09 |  |  | 2020-12-14 | 2020-12-14 | [12 empty] | 2019-04-04 | 2020-04-04 | 2021-02-03 | 2021-02-03 | B tag clean up 11/8/2020 |  | Stockton |  | 162991103 | 8779.05 | 761.1 | 448.7 | 448.7 | 448.7 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-11-08
Bay/Central | ST | SA | Angels Camp |  |  | OPEN | 116977316 | POLE_BROK_REPL - #1E 3579 GLODEN GATE DR | 35152549 |  |  | STS-POLE_BROK_REPL - #1E 3579 GLODEN GAT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2415 | -120.7137 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | O25 | 6305 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.5 | 38.5 |  |  | 0 | 38.5 | 38.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101250066 | RELW OH PRI INSP ESTR FMOB TER2 | Pole | 2020-05-15 | 2020-06-20 | COMP | 2020-02-14 |  |  | 2020-05-14 | 2020-05-14 | [12 empty] | 2019-04-08 | 2020-04-08 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 |  | Stockton |  | 162211101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | SAN ANDREAS | Angels Camp |  |  | OPEN | 117148485 | POLE_BROK_REPL - 1661 CALAVERITAS RD R/O | 35202460 |  |  | STS-POLE_BROK_REPL - 1661 CALAVERITAS RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | FAA |  |  | 38.1842 | -120.6562 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | P2619 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.4 | 16.4 |  |  | 0 | 16.4 | 16.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101251848 | RELW OH SERV JPOL REMT ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 |  | COMP | 2021-01-19 | [16 empty] | 2019-05-02 | 2020-05-02 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2021-02-28 | TRC |  | 162211101 | 5227.45 |  | -210 | 1371 | 1371 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | SAN ANDREAS | Angels Camp |  |  | COMP | 117003664 | POLE_BROK_REPL - 2S/O 2800 WILLOW CRK RD | 35178266 |  |  | STS-POLE_BROK_REPL - 2S/O 2800 WILLOW CR | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.1832 | -120.6419 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | P27 | L811 | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 38.1 | 38.1 |  |  | 2.5 | 38 | 38 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101251326 | RELW OH PRI COMP REMT ESTR GO BTKA CCNT FMOB TER2 PRTO | Pole | 2020-06-10 | 2020-06-13 | COMP | 2020-06-03 | COMP | 2021-01-08 | 2020-06-13 | 2020-06-13 | [11 empty] | 2021-01-15 | 2021-01-08 | 2020-04-10 | 2020-08-12 | 2020-08-12 | B-Tag Clean Up 6/8/2020 |  | Stockton |  | 162211101 | 21224.62 | 10372.2 | 6478.3 | 12003.3 | 12003.3 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-08
Bay/Central | ST | SAN ANDREAS | Angels Camp |  |  | OPEN | 117022134 | POLE_DECA_REPL - 1N/E/O 2S/O R/O 4621 FO | 35180423 |  |  | STS-POLE_DECA_REPL - 1N/E/O 2S/O R/O 462 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1352 | -120.6315 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | Q27 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 25 | 25 |  |  | 0 | 25 | 25 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101280758 | RELW OH PRI NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-06-30 | 2020-06-30 | COMP | 2020-06-30 | [16 empty] | 2019-04-13 | 2020-04-13 | 2020-08-21 | 2020-08-21 | B-Tag Addition 06.24.20 |  | Stockton |  | 163451702 | 20573.48 | 1472.8 | [7 empty] | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | ST | SAN ANDREAS | Angels Camp |  |  | OPEN | 117160345 | POLE_BROK_REPL - R/O 891 MTN RANCH RD 2E | 35212194 |  |  | STS-POLE_BROK_REPL - R/O 891 MTN RANCH R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-07 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1919 | -120.6649 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | P2618 | L6327 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101251633 | RELW OH PRI ESTR PROG FMOB TER2 PRTO | Pole | 2020-12-09 | 2020-12-11 | COMP | 2020-12-09 | [16 empty] | 2019-05-04 | 2020-05-04 | 2021-02-04 | 2021-02-04 | B tag clean up 11/8/2020 |  | Stockton |  | 162211101 | 23437.13 | 2532.6 | 2321.9 | 2321.9 | 2321.9 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-11-08
Bay/Central | ST | SAN ANDREAS | Angels Camp |  |  | OPEN | 117215583 | POLE_BROK_REPL - #7N ON LINE @ R/O 4225 | 35180433 |  |  | STS-POLE_BROK_REPL - #7N ON LINE @ R/O 4 | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1329 | -120.6456 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | Q26 |  | Y | 311 |  |  | 2021-02-12 07:00 | 2021-02-12 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 21.8 | 21.8 |  |  | 9 | 20.8 | 20.8 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101276782 | RELW OH PRI INSP CLR JPOL REMT FIRE NOAC SPCR ESTR FMOB TER2 FSRP | Pole | 2020-07-07 | 2020-07-07 | COMP | 2020-07-07 | [16 empty] | 2019-05-11 | 2020-05-11 | 2020-08-23 | 2020-08-23 | B-Tag Addition 06.24.20 |  | Stockton |  | 163451702 | 20642.06 | 8119.1 | -4348.9 | 173.8 | 173.8 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | ST | SAN ANDREAS | Angels Camp |  |  | OPEN | 117459439 | POLE_BURN_REPL - #2SE ON LINE @ R/O 5320 | 35152556 |  |  | STS-POLE_BURN_REPL - #2SE ON LINE @ R/O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2523 | -120.6506 |  | TIER 2 | 141 | 16221-1101, CALAVERAS CEMENT | O26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.1 | 13.1 |  |  | 0 | 13.1 | 13.1 |  |  | EC | E | Pole | Burnt | Replace |  | 101249782 | RELW OH PRI CLR JPOL REMT NOAC PRTO ESTR FMOB TER2 | Pole | 2020-04-23 | 2020-05-13 | COMP | 2020-04-23 | [16 empty] | 2019-06-18 | 2020-06-18 |  | 2020-06-18 | circuit based plan 2.14 | 2020-05-31 | Stockton |  | 162211101 | 8650.82 | 2579.5 | 983.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | SONORA | Angels Camp |  |  | OPEN | 117241035 | POLE_BROK_REPL - R/O 20497 TUTTLE TOWN R | 35202840 |  |  | STS-POLE_BROK_REPL - R/O 20497 TUTTLE TO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land JointPole |  |  | 37.9968 | -120.4636 |  | TIER 2 | 485 | 16376-1704, RACETRACK | T31 | L443 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.8 | 32.8 |  |  | 0 | 32.8 | 32.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101285045 | RELW CLR OH PRI INSP RESD REMT ESTR BTKA FMOB TER2 FSRP | Pole | 2021-02-10 |  | COMP | 2021-02-10 | [16 empty] | 2019-05-15 | 2020-05-15 | 2020-11-26 | 2020-11-26 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163761704 | 14373.72 |  | 0 | 2070 | 2070 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | SONORA | Angels Camp |  |  | COMP | 117240832 | POLE_DECA_REPL - R/O 20765 JACKASS HILL | 35180435 |  |  | STS-POLE_DECA_REPL - R/O 20765 JACKASS H | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-28 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.9973 | -120.4756 |  | TIER 2 | 485 | 16376-1704, RACETRACK | T31 |  | Y | 311 |  |  | 2021-01-10 | 2021-01-10 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 33.1 | 33.1 |  |  | 1.5 | 33 | 33 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101285069 | RELW OH PRI INSP COMP CLR REMT ESTR BTKA CCNT FMOB TER2 FSRP | Pole | 2020-07-08 | 2020-07-23 | COMP | 2020-07-08 | COMP | 2021-01-10 | [13 empty] | 2021-01-21 | 2021-01-10 | 2020-05-15 | 2020-08-25 | 2020-08-25 | B-Tag Addition 06.24.20 |  | Stockton |  | 163761704 | 14151.48 | 16174.2 | 13825.7 | 17650 | 17650 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | ST | SONORA | Stockton |  |  | OPEN | 117292792 | TREE_DECA_INPL - 1 NE/O 4 W/O R/O 20765 | 35180712 |  |  | STS-TREE_DECA_INPL - 1 NE/O 4 W/O R/O 20 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0033 | -120.4778 |  | TIER 2 | 485 | 16376-1704, RACETRACK | T31 |  | Y | 311 |  |  | 2021-02-13 07:00 | 2021-02-13 16:00 | Dispatched | CLICK | [6 empty] | 27 | 27 |  |  | 0 | 27 | 27 |  |  | EC | B | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 101285102 | RELW OH SERV REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-08-06 | 2020-08-07 | COMP | 2020-08-05 | [16 empty] | 2019-05-21 | 2020-05-21 | 2020-08-28 | 2020-08-28 | B-Tag Addition 06.24.20 | 2020-08-31 | CALENG |  | 163761704 | 18335.51 | 2889.7 | [7 empty] | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | ST | SUTTER CREEK | Jackson |  |  | OPEN | 116822490 | POLE_DECA_REPL - 1S/O 16931 LAKE MARIE R | 35202451 |  |  | STS-POLE_DECA_REPL - 1S/O 16931 LAKE MAR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.4463 | -120.7106 |  | TIER 2 | 498 | 16301-1101, MARTELL | K2507 | 1525 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.3 | 37.3 |  |  | 0 | 37.3 | 37.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101265463 | RELW OH PRI JPOL REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-13 |  | COMP | 2021-01-13 | [16 empty] | 2019-03-24 | 2020-03-24 | 2020-11-12 | 2020-11-12 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011101 | 18000.83 |  | -1231.8 | 769 | 769 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | SUTTER CREEK | Jackson |  |  | OPEN | 116848353 | POLE_DECA_REPL - 15900 LUNAL TRAIL SUTTE | 35202522 |  |  | STS-POLE_DECA_REPL - 15900 LUNAL TRAIL S | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.4389 | -120.7087 |  | TIER 2 | 498 | 16301-1101, MARTELL | K2512 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101265381 | RELW OH PRI JPOL REMT ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2020-11-12 | 2020-11-12 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | SUTTER CREEK | Jackson |  |  | OPEN | 116862176 | POLE_DECA_REPL - 18023 SHAKE RIDGE RD SU | 35202538 |  |  | STS-POLE_DECA_REPL - 18023 SHAKE RIDGE R | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.4451 | -120.6891 |  | TIER 2 | 498 | 16301-1101, MARTELL | K25 | L581 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48 | 48 |  |  | 0 | 48 | 48 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101265106 | RELW OH PRI REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-14 |  | COMP | 2021-01-14 | [16 empty] | 2019-03-29 | 2020-03-29 | 2020-11-19 | 2020-11-19 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011101 | 25664.61 | 89.6 | -1231.8 | 1095 | 1095 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | SUTTER CREEK | Jackson |  |  | OPEN | 117226467 | POLE_DECA_REPL - AT 8490 SUTTER CR IONE | 35202671 |  |  | STS-POLE_DECA_REPL - AT 8490 SUTTER CR I | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.3754 | -120.8684 |  | TIER 2 | 243 | 16334-1101, CLAY | M21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15 | 15 |  |  | 0 | 15 | 15 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101238713 | RELW OH SERV CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-03 | 2021-02-01 | COMP | 2021-02-01 | [16 empty] | 2019-05-13 | 2020-05-13 | 2020-11-19 | 2020-11-19 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163341101 | 6461.96 | 8.8 | -1060 | 32 | 32 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | SUTTER CREEK | Jackson |  |  | OPEN | 116864292 | POLE_BROK_REPL - 15W\O CO#1541 PONDEROSA | 35116027 |  |  | X STS-POLE_BROK_REPL-15W\O CO#1541 PONDE | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4469 | -120.6608 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K26 |  | Y | 311 |  |  | 2020-12-10 | 2020-12-10 | Completed | Order Operation | [6 empty] | 17.9 | 17.9 |  |  | 0 | 17.9 | 17.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101261248 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2019-11-24 | 2019-11-24 | COMP | 2019-11-24 | [16 empty] | 2019-03-28 | 2020-03-28 |  | 2020-03-28 | circuit based plan 2.14 |  | UNASSIGNED |  | 163751102 | 10234.28 | 7114.5 | 299.2 | 299.2 | 299.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | SUTTER CREEK | Jackson |  |  | OPEN | 116811538 | POLE_BROK_REPL - 2S\O C\O TURNER RD ON A | 35202300 |  |  | STS-POLE_BROK_REPL - 2S\O C\O TURNER RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4204 | -120.8133 |  | TIER 2 | 483 | 16354-1101, OLETA | K22 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.5 | 23.5 |  |  | 0 | 23.5 | 23.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101239317 | RELW OH PRI CLR REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-04 | 2020-12-11 | COMP | 2020-12-03 |  |  | 2020-12-03 | 2020-12-03 | [12 empty] | 2019-03-22 | 2020-03-22 | 2020-11-05 | 2020-11-05 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163541101 | 10943.59 | 93.8 | -1928 | -1656.5 | -1656.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | SUTTER CREEK | Jackson |  |  | OPEN | 116876276 | POLE_DECA_REPL - AT 16625 SONSHINE LNSUT | 35084420 |  |  | STS-POLE_DECA_REPL - AT 16625 SONSHINE L | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4498 | -120.7049 |  | TIER 2 | 498 | 16301-1101, MARTELL | K2507 | L1113 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.2 | 39.2 |  |  | 0 | 39.2 | 39.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101265216 | RELW OH PRI REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-10 | 2020-12-10 | COMP | 2020-12-10 | [16 empty] | 2019-03-31 | 2019-09-30 | 2020-11-09 | 2020-11-09 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163011101 | 18065.73 |  | -2398.6 | -2036.6 | -2036.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | SUTTER CREEK | Jackson |  |  | OPEN | 116952211 | POLE_BROK_REPL - 1E\O 18878 PONDEROSA AN | 35202622 |  |  | STS-POLE_BROK_REPL - 1E\O 18878 PONDEROS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4447 | -120.6749 |  | TIER 2 | 498 | 16301-1101, MARTELL | K26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.3 | 15.3 |  |  | 0 | 15.3 | 15.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101261298 | RELW OH PRI REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-22 | 2020-12-22 | COMP | 2020-12-22 | [16 empty] | 2019-04-03 | 2020-04-03 | 2020-11-09 | 2020-11-09 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163011101 | 6047.68 |  | -1648.1 | -36.8 | -36.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | SUTTER CREEK | Jackson |  |  | OPEN | 117163780 | POLE_BROK_REPL - 1SO 13468 PINE GULCH CT | 35225869 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  |  | 1 | 2021-03-16 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4042 | -120.7637 |  | TIER 2 | 498 | 16301-1101, MARTELL | L23 | L6021 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 29.4 | 29.4 |  |  | 0 | 29.4 | 29.4 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101254686 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-01 | 2021-02-17 | COMP | 2021-02-01 |  |  | 2021-02-17 | 2021-02-17 | [12 empty] | 2019-05-05 | 2020-05-05 | 2021-04-13 | 2021-04-13 | B tag clean up 1/19/2021 |  | UNASSIGNED |  | 163011101 | 18180.2 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-19
Bay/Central | ST | SUTTER CREEK | Jackson |  |  | OPEN | 116868127 | POLE_BROK_REPL - 3SE/O 1S/O 4W/O 17111 R | 35082851 |  |  | STS-POLE_BROK_REPL - 3SE/O 1S/O 4W/O 171 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4333 | -120.7125 |  | TIER 2 | 498 | 16301-1101, MARTELL | K25 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101264891 | REMT RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-06 | 2021-01-07 | COMP | 2020-06-13 |  |  | 2020-12-02 | 2020-12-02 | [12 empty] | 2019-03-29 | 2019-09-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-07-31 | Stockton |  | 163011101 | 10939.49 | 649.2 |  |  |  | 603.7 |  | 603.7 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | SUTTER CREEK | Jackson |  |  | OPEN | 116876003 | POLE_BROK_REPL - 6N/E/O 17250 SUTTER CRE | 35082859 |  |  | STS-POLE_BROK_REPL - 6N/E/O 17250 SUTTER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4361 | -120.7043 |  | TIER 2 | 498 | 16301-1101, MARTELL | K25 |  | Y | 311 |  |  | 2021-07-29 07:00 | 2021-07-29 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 71.2 | 71.2 |  |  | 0 | 71.2 | 71.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101264917 | RELW OH PRI JPOL REMT ESTR GO REAR USA PROG FMOB TER2 PRTO FSRP | Pole | 2020-08-26 | 2021-02-02 | COMP | 2020-08-26 |  |  | 2021-02-02 | 2021-02-02 | [12 empty] | 2019-03-31 | 2019-09-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 163011101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | SUTTER CREEK | Jackson |  |  | OPEN | 117227462 | POLE_DECA_REPL - 7SE/O 1E/O SUTTER CR IO | 35202677 |  |  | STS-POLE_DECA_REPL - 7SE/O 1E/O SUTTER C | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3758 | -120.8621 |  | TIER 2 | 243 | 16334-1101, CLAY | M21 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101238737 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-01 | 2021-01-19 | COMP | 2020-12-01 | [16 empty] | 2019-05-13 | 2020-05-13 | 2020-11-24 | 2020-11-24 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163341101 | 6704.88 | 8.8 | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALCANO | Jackson |  |  | OPEN | 116853504 | POLE_DECA_REPL - 2S\O 2E\O 16752 RAMS HO | 35152566 |  |  | STS-POLE_DECA_REPL - 2S\O 2E\O 16752 RAM | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.452 | -120.6166 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K27 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 17.9 | 17.9 |  |  | 0 | 17.9 | 17.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261931 | OH PRI REMT REAR SCOP SCPA FMOB TER2 PRTO RELW | Pole | 2020-04-27 | 2020-04-27 | COMP | 2020-04-27 | [16 empty] | 2019-03-27 | 2020-03-27 |  | 2020-03-27 | 2021 CBP Plan |  | UNASSIGNED |  | 163751102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLECITO | Angels Camp |  |  | OPEN | 117030817 | POLE_DECA_REPL - R/O 3425 MAIN STVALLECI | 35202233 |  |  | STS-POLE_DECA_REPL - R/O 3425 MAIN STVAL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.0886 | -120.472 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | R3122 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101285325 | RELW OH PRI CLR RESD REMT ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2019-11-15 | 2020-11-27 | 2020-11-27 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451702 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLECITO | Angels Camp |  |  | OPEN | 117033616 | POLE_DECA_REPL - 3670 CHURCH STVALLECITO | 35107090 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.088 | -120.4739 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | R3122 | 1639 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48.3 | 48.3 |  |  | 0 | 48.3 | 48.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101285370 | RELW OH PRI CLR JPOL RESD REMT FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-22 |  | COMP | 2021-01-22 | [16 empty] | 2019-04-15 | 2019-09-15 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163451702 | 29061.83 | 269.7 | -945 | 1125 | 1125 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLECITO | Angels Camp |  |  | OPEN | 117033748 | POLE_DECA_REPL - A/F 3737 CHURCH STVALLE | 35202253 |  |  | STS-POLE_DECA_REPL - A/F 3737 CHURCH STV | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.0868 | -120.474 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | R3122 | 1639 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 40.8 | 40.8 |  |  | 0 | 40.8 | 40.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101285375 | RELW OH PRI CLR JPOL RESD REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-02 |  | COMP | 2020-12-02 | [16 empty] | 2019-04-15 | 2020-04-15 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451702 | 23710.49 | 465.6 | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLECITO | Angels Camp |  |  | OPEN | 117040901 | POLE_DECA_REPL - 4 N/O 3168 HWY 4VALLECI | 35202273 |  |  | STS-POLE_DECA_REPL - 4 N/O 3168 HWY 4VAL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.0926 | -120.4743 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | R3122 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.9 | 19.9 |  |  | 0 | 19.9 | 19.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101285350 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 |  | COMP | 2021-01-19 | [16 empty] | 2019-04-16 | 2020-04-16 | 2020-11-21 | 2020-11-21 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451702 | 7041.55 |  | -1092.6 | 592.4 | 592.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLECITO | Angels Camp |  |  | OPEN | 117068100 | POLE_BROK_REPL - 1 S/O 3663 POAG RD VALL | 35202381 |  |  | STS-POLE_BROK_REPL - 1 S/O 3663 POAG RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land Enviro |  |  | 38.0897 | -120.4783 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | R3121 | 1639 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.7 | 57.7 |  |  | 0 | 57.7 | 57.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101285249 | RELW OH PRI REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-27 |  | COMP | 2021-01-27 | [16 empty] | 2019-04-20 | 2020-04-20 | 2020-10-27 | 2020-10-27 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451702 | 27263.38 | 125.9 | -1092.6 | 600.1 | 600.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLECITO | Angels Camp |  |  | OPEN | 117122630 | POLE_DECA_REPL - 1 W/O 2388 HWY 4VALLECI | 35202337 |  |  | STS-POLE_DECA_REPL - 1 W/O 2388 HWY 4VAL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.1015 | -120.4714 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | R31 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101285535 | RELW OH PRI CLR JPOL RESD REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2020-11-27 | 2020-11-27 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163451702 | 1 | 40.4 | -945 | 115 | 115 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLECITO | Angels Camp |  |  | OPEN | 117006669 | POLE_BROK_REPL - 2388 HWY 4 VALLECITO | 35180658 |  |  | STS-POLE_BROK_REPL - 2388 HWY 4 VALLECIT | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1021 | -120.4728 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | R31 | L2657 | Y | 311 |  |  | 2021-02-13 07:00 | 2021-02-13 16:00 | Dispatched | CLICK | [6 empty] | 31.1 | 31.1 |  |  | 0.5 | 31 | 31 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101285537 | RELW OH PRI CLR JPOL REMT FIRE NOAC ESTR BTKA OTHR USA TER2 FSRP | Pole | 2020-07-02 | 2020-07-24 | COMP | 2020-07-02 | [16 empty] | 2019-02-07 | 2020-02-07 | 2020-08-27 | 2020-08-27 | B-Tag Addition 06.24.20 | 2020-07-31 | W. Sac |  | 163451702 | 11799.73 | 2616.7 | [7 empty] | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | ST | VALLECITO | Angels Camp |  |  | OPEN | 117131093 | POLE_BROK_REPL - 3NW/O 3528 HWY 4VALLECI | 35206584 |  |  | STS-POLE_BROK_REPL - 3NW/O 3528 HWY 4VAL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0953 | -120.4807 |  | TIER 2 | 332 | 16345-1702, FROGTOWN | R31 | L5343 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 44.1 | 44.1 |  |  | 0 | 44.1 | 44.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101285490 | RELW OH PRI JPOL FIRE NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-11-12 | 2021-01-26 | COMP | 2020-11-10 | [16 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 163451702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 115612417 | POLE_DECA_REPL - 2175 EVANS RD VALLEY SP | 35069425 |  |  | STS-POLE_DECA_REPL - 2244 EVANS RD VALLE | PEND | PEND ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.1852 | -120.8704 |  | TIER 2 | 46 | 16299-1101, CORRAL | PP2117 | 11811 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 78.5 | 78.5 |  |  | 0 | 78.5 | 78.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102045749 | POHW OH PRI CREW REMT ESTR REAR USA TER2 | Pole | 2020-12-17 |  | COMP | 2020-12-17 | [16 empty] | 2018-12-20 | 2019-12-20 |  | 2019-12-20 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 162991101 | 14297.58 | 221.6 |  |  |  | 221.6 |  | 221.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116752689 | POLE_BURN_REPL - C/O BROOKS LN & ROSS DR | 35214954 |  |  | STS-POLE_BURN_REPL - C/O BROOKS LN & ROS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.1651 | -120.8639 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2103 | L2171 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28 | 28 |  |  | 0 | 28 | 28 |  |  | EC | E | Pole | Burnt | Replace |  | 103375938 | RELW OH PRI JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-13 |  | COMP | 2021-01-13 | [16 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 15996.99 | 127.5 | 46.7 | 897.7 | 897.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116756884 | POLE_DECA_REPL - 1W/O C/O EMERIFF/LEARY | 35215003 |  |  | STS-POLE_DECA_REPL - 1W/O C/O EMERIFF/LE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.1624 | -120.8584 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2109 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.9 | 16.9 |  |  | 0 | 16.9 | 16.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101246434 | RELW OH PRI JPOL REMT FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-06 |  | COMP | 2021-01-06 | [16 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 9864.46 |  | 0 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116757235 | POLE_DECA_REPL - 2N/O 3444 LEARY CT VALL | 35215013 |  |  | STS-POLE_DECA_REPL - 2N/O 3444 LEARY CT | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.1628 | -120.8576 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2109 | L2171 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.5 | 31.5 |  |  | 0 | 31.5 | 31.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101246417 | OH PRI JPOL REMT FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP RELW | Pole | 2021-01-06 |  | COMP | 2021-01-06 | [16 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 16792.87 | 8.8 | 0 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116759893 | POLE_BROK_REPL - 9485 LECKIE RDVALLEY SP | 35202161 |  |  | STS-POLE_BROK_REPL - 9485 LECKIE RDVALLE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land JointPole |  |  | 38.1022 | -120.5201 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2103 | L2251 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.1 | 36.1 |  |  | 0 | 36.1 | 36.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101246033 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-20 |  | COMP | 2021-01-20 | [16 empty] | 2019-03-18 | 2020-03-18 | 2020-11-18 | 2020-11-18 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162991102 | 16557.49 | 49.2 | -944.9 | 1141.8 | 1141.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116762740 | POLE_BROK_REPL - 3W/O CLAIR/BERKESEY DRV | 35215049 |  |  | STS-POLE_BROK_REPL - 3W/O CLAIR/BERKESEY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.1658 | -120.8469 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2105 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101246254 | RELW OH SEC REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116763594 | POLE_BROK_REPL - 2135 LEWIS WYVALLEY SPR | 35215066 |  |  | STS-POLE_BROK_REPL - 2135 LEWIS WYVALLEY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land JointPole |  |  | 38.1672 | -120.8476 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2105 | L2249 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101246246 | OH RELW PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 1 | 326 | 326 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116764130 | POLE_DECA_REPL - A/F C/O LEWIS WY ON BLA | 35215075 |  |  | STS-POLE_DECA_REPL - A/F C/O LEWIS WY ON | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.1672 | -120.8487 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2105 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101246227 | RELW OH SERV JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116765427 | POLE_BROK_REPL - 1N/O 2023 BERKESEY DRVA | 35215098 |  |  | STS-POLE_BROK_REPL - 1N/O 2023 BERKESEY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.168 | -120.8456 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2105 | L2249 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101246243 | RELW OH PRI JPOL REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2021-01-22 | 2021-01-22 | [12 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116766153 | POLE_BROK_REPL - C/O BERKESEY/BLAKE LNVA | 35215110 |  |  | STS-POLE_BROK_REPL - C/O BERKESEY/BLAKE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.1693 | -120.8456 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2105 | L2249 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.7 | 39.7 |  |  | 0 | 39.7 | 39.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101246238 | RELW OH PRI JPOL REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 |  | COMP | 2021-01-19 | [16 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 20409.8 |  | 0 | 1467 | 1467 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116808136 | POLE_BROK_REPL - 2321 SILVER RAPIDS RD V | 35215380 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.1614 | -120.8519 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2110 | 36666 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101246293 | RELW OH PRI JPOL FIRE ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116810294 | POLE_BROK_REPL - MB 2284 GALLIUS LN 1P/N | 35215390 |  |  | STS-POLE_BROK_REPL - MB 2284 GALLIUS LN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.1638 | -120.8521 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2110 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103375973 | RELW OH PRI FIRE SWRK ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116810335 | POLE_DECA_REPL - MB 2284 GALLIUS LN 1P/N | 35215395 |  |  | STS-POLE_DECA_REPL - MB 2284 GALLIUS LN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.1638 | -120.8518 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2110 | 46677 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103375970 | RELW OH PRI FIRE SWRK ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116811580 | POLE_BROK_REPL - 1W/O 2385 BLAKE LNVALLE | 35215439 |  |  | STS-POLE_BROK_REPL - 1W/O 2385 BLAKE LNV | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.1637 | -120.8496 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2110 | L2249 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101246282 | RELW OH PRI JPOL FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 1 | 87 | 87 | 87 | 87 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116817825 | POLE_BROK_REPL - 2NW/O C/O #L3859 HOGAN | 35202393 |  |  | STS-POLE_BROK_REPL - 2NW/O C/O #L3859 HO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 38.1431 | -120.8119 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | Q22 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32 | 32 |  |  | 0 | 32 | 32 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101242355 | RELW OH PRI REMT SWRK ESTR GO USA FMOB TER2 PRTO FSRP | Pole | 2020-12-17 |  | COMP | 2020-12-17 | [16 empty] | 2019-03-23 | 2020-03-23 | 2020-11-29 | 2020-11-29 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163231101 | 18735.93 | 1942.4 | -6.9 | -337.6 | -337.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116818340 | POLE_BROK_REPL - 3NW/O OF C/O#3859 HOGAN | 35202403 |  |  | STS-POLE_BROK_REPL - 3NW/O OF C/O#3859 H | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro JointPole |  |  | 38.1437 | -120.8128 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | Q22 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.9 | 16.9 |  |  | 0 | 16.9 | 16.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101242354 | RELW OH PRI REMT SWRK ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-03 |  | COMP | 2021-02-03 | [16 empty] | 2019-03-23 | 2020-03-23 | 2020-11-29 | 2020-11-29 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163231101 | 12512.56 | 1992.4 | 721.7 | 713.7 | 713.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116818556 | POLE_BROK_REPL - 5NW/O C/O #3859 HOGAN D | 35202408 |  |  | STS-POLE_BROK_REPL - 5NW/O C/O #3859 HOG | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro JointPole |  |  | 38.145 | -120.8153 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | Q22 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.8 | 27.8 |  |  | 0 | 27.8 | 27.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101242352 | RELW OH PRI REMT SWRK ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-09 |  | COMP | 2020-12-09 | [16 empty] | 2019-03-23 | 2020-03-23 | 2020-11-29 | 2020-11-29 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163231101 | 13908.08 | 1972.1 | -456.9 | -1285.4 | -1285.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116822554 | POLE_BROK_REPL - #10S CO#9753 @ C/O VIST | 35202455 |  |  | STS-POLE_BROK_REPL - #10S CO#9753 @ C/O | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro JointPole |  |  | 38.1553 | -120.8152 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | Q22 | L3681 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 60.5 | 59.5 | 1 |  | 0 | 60.5 | 59.5 | 1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101242341 | RELW OH PRI REMT ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-16 |  | COMP | 2021-02-16 | [16 empty] | 2019-03-24 | 2020-03-24 | 2020-11-29 | 2020-11-29 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163231101 | 25461.94 | 513.3 | 513.3 | 1466 | 1466 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117021327 | POLE_BROK_REPL - A/F 13432 FRAUSTO LN VA | 35149891 |  |  | STS-POLE_BROK_REPL - A/F 13432 FRAUSTO L | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.1973 | -120.8764 |  | TIER 2 | 46 | 16299-1101, CORRAL | PP21 | 11807 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 35.3 | 35.3 |  |  | 0 | 35.3 | 35.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101248765 | RELW OH PRI JPOL REMT ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-04-21 | 2020-04-20 | COMP | 2020-04-20 |  |  | 2020-04-10 | 2020-04-10 | [12 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-04-10 | TRC |  | 162991101 | 19464.05 | 287.8 |  |  |  | 88.6 |  | 88.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117038706 | POLE_BROK_REPL - 1PS/O CRNR/O WILKINSON | 35202265 |  |  | STS-POLE_BROK_REPL - 1PS/O CRNR/O WILKIN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.2146 | -120.8787 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | PP21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.6 | 21.6 |  |  | 0 | 21.6 | 21.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101248712 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-22 | 2021-01-19 | COMP | 2021-01-19 | [16 empty] | 2019-04-16 | 2020-04-16 | 2020-09-20 | 2020-09-20 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163231101 | 9222.23 | 49.2 | -1092.6 | 977.4 | 977.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117117204 | POLE_BROK_REPL - 2434 HENEY LN VALLEY SP | 35214913 |  |  | STS-POLE_BROK_REPL - 2434 HENEY LN VALLE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.1643 | -120.8562 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2109 | 36666 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101246394 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 1 | 43.7 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117118146 | POLE_DECA_REPL - 1W/O C/O GALLIUS/HENEY | 35214929 |  |  | STS-POLE_DECA_REPL - 1W/O C/O GALLIUS/HE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.163 | -120.8541 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2109 | 36666 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101246385 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 1 | 108.6 | 108.6 | 108.6 | 108.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117120440 | POLE_DECA_REPL - 1N/O EMERIFF/DANAHRR LN | 35214949 |  |  | STS-POLE_DECA_REPL - 1N/O EMERIFF/DANAHR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.1598 | -120.8539 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2109 | 93139 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 49.3 | 49.3 |  |  | 0 | 49.3 | 49.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101246397 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-10 |  | COMP | 2021-02-10 | [16 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117120610 | POLE_BROK_REPL - 2306 DANAHER LN VALLEY | 35214953 |  |  | STS-POLE_BROK_REPL - 2306 DANAHER LN VAL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.1604 | -120.8539 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2109 | 36666 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101246396 | RELW OH PRI CLR JPOL RESD FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 1 | 73.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117120923 | POLE_DECA_REPL - 2266 DANAHER LN VALLEY | 35214963 |  |  | STS-POLE_DECA_REPL - 2266 DANAHER LN VAL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.1609 | -120.854 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2109 | 36666 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 62.6 | 61.8 | 0.8 |  | 0 | 62.6 | 61.8 | 0.8 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101246395 | RELW OH RESD PRI CLR JPOL FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-08 |  | COMP | 2021-02-08 | [16 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117164189 | POLE_DECA_REPL - #2SE 5638 CAMPO SECO RD | 35206551 |  |  | STS-POLE_DECA_REPL - #2SE 5638 CAMPO SEC | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.2186 | -120.8766 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 17.4 | 17.4 |  |  | 0 | 17.4 | 17.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101234099 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-11-12 | 2020-11-10 | COMP | 2020-11-10 | [16 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 163231101 | 10159.79 | 44.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117164408 | POLE_BROK_REPL - #2NE ON LINE @ 5638 CAM | 35206553 |  |  | STS-POLE_BROK_REPL - #2NE ON LINE @ 5638 | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 38.221 | -120.8787 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 14.4 | 14.4 |  |  | 0 | 14.4 | 14.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101234114 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 |  | COMP | 2020-12-11 | [16 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 163231101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117164461 | POLE_DECA_REPL - 5686 CAMPO SECO RD W/TR | 35206547 |  |  | STS-POLE_DECA_REPL - 5686 CAMPO SECO RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.2211 | -120.8808 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 | 1115 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 36.7 | 36.7 |  |  | 0 | 36.7 | 36.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101234187 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 |  | COMP | 2020-12-11 | [16 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 163231101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117164535 | POLE_BROK_REPL - #1W 5686 CAMPO SECO RDV | 35206554 |  |  | STS-POLE_BROK_REPL - #1W 5686 CAMPO SECO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.2208 | -120.8821 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 19.4 | 19.4 |  |  | 0 | 19.4 | 19.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101234194 | RELW OH PRI REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 |  | COMP | 2020-12-11 | [16 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 163231101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117178085 | POLE_BROK_REPL - #1E 3949 CAMPO SECO RDV | 35206543 |  |  | STS-POLE_BROK_REPL - #1E 3949 CAMPO SECO | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.2279 | -120.8529 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 13.1 | 13.1 |  |  | 0 | 13.1 | 13.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101233767 | RELW OH PRI JPOL REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-11-10 |  | COMP | 2020-11-10 | [16 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 163231101 | 10019.44 | 538.8 | 109.7 | 109.7 | 109.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117178532 | POLE_BROK_REPL - #2E 3949 CAMPO SECO RD | 35206544 |  |  | STS-POLE_BROK_REPL - #2E 3949 CAMPO SECO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.228 | -120.8527 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 38 | 38 |  |  | 0 | 38 | 38 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101233769 | RELW OH PRI JPOL REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-11-10 |  | COMP | 2020-11-10 | [16 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 163231101 | 17971.2 | 353.1 | 85.4 | 85.4 | 85.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117188568 | POLE_BROK_REPL - AF ENT OF 5821 BALDWIN | 35215485 |  |  | STS-POLE_BROK_REPL - AF ENT OF 5821 BALD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.1728 | -120.8721 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2102 | L2251 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103375940 | OH PRI JPOL FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117188894 | POLE_BROK_REPL - AF ENT OF 5821 BALDWIN | 35215490 |  |  | STS-POLE_BROK_REPL - AF ENT OF 5821 BALD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.1727 | -120.8706 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2102 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.8 | 21.8 |  |  | 0 | 21.8 | 21.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103375971 | RELW OH PRI JPOL FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-04 |  | COMP | 2021-01-04 | [16 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991102 | 9621.23 | 89.6 | 0 | 407.5 | 407.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117232614 | POLE_BROK_REPL - #2W 5686 CAMPO SECO RD | 35206581 |  |  | STS-POLE_BROK_REPL - #2W 5686 CAMPO SECO | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.2213 | -120.8829 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 18.3 | 18.3 |  |  | 0 | 18.3 | 18.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101234199 | RELW OH PRI PGEA REMT FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 |  | COMP | 2020-12-11 | [16 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 163231101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117233268 | POLE_BROK_REPL - #1N ON LINE @ 5883 CAMA | 35206559 |  |  | STS-POLE_BROK_REPL - #1N ON LINE @ 5883 | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.2188 | -120.8844 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 18.2 | 18.2 |  |  | 0 | 18.2 | 18.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101234286 | RELW OH PRI PGEA CLR REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-11-10 |  | COMP | 2020-11-10 | [16 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 163231101 | 12460.31 | 275.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | COMP | 117022057 | POLE_BROK_REPL - 13391 STONE LN VALLEY S | 35149896 |  |  | STS-POLE_BROK_REPL - 13391 STONE LN VALL | DOCC | DOCC ERDY SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-11-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.1965 | -120.8799 |  | TIER 2 | 46 | 16299-1101, CORRAL | PP21 | 11807 | Y | 311 |  |  | 2021-01-16 | 2021-01-16 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 43.7 | 43.7 |  |  | 0 | 43.7 | 43.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101248759 | RELW OH PRI COMP JPOL REMT ESTR BTKA CCNT PROG FMOB TER2 PRTO | Pole | 2020-04-21 | 2020-06-23 | COMP | 2020-04-20 | COMP | 2021-01-16 | [13 empty] | 2021-01-25 | 2021-01-16 | 2020-04-13 |  | 2020-04-13 | circuit based plan 2.14 | 2020-04-10 | TRC |  | 162991101 | 21971.11 | 12583 | 12494.3 | 24129 | 24129 | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 108533128 | POLE REPL - 6020 CENTRAL HILL RD VA | 35071119 |  |  | STS-POLE REPL - 6020 CENTRAL HILL RD VA | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.252 | -120.752 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | O24 | 1587 | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Dispatched | CLICK | [6 empty] | 49.9 | 46 | 3.9 |  | 0 | 49.9 | 46 | 3.9 |  | EC | F | Pole | Broken/Damaged | Replace |  | 101246988 | RELW OH PRI INSP MINR REMT JARC GO SCOP SCPA TER2 | Pole | 2020-07-30 | 2020-07-30 | COMP | 2020-07-30 | [16 empty] | 2014-06-05 | 2019-06-30 | 2019-12-31 | 2019-12-31 | Q1 Work Plan | 2020-09-30 | W. Sac |  | 163231101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116821227 | POLE_BROK_REPL - #9S ON LINE @ CO#3681 S | 35202441 |  |  | STS-POLE_BROK_REPL - #9S ON LINE @ CO#36 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1663 | -120.8161 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | Q22 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.6 | 17.6 |  |  | 0 | 17.6 | 17.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101242339 | RELW OH PRI REMT SWRK ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-17 | 2021-02-01 | COMP | 2020-12-17 | [16 empty] | 2019-03-24 | 2020-03-24 | 2020-11-29 | 2020-11-29 | 2021 CBP Plan | 2021-02-28 | TRC |  | 163231101 | 9634.32 | 203.4 | -1141.3 | -1141.3 | -1141.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 116821520 | POLE_BROK_REPL - #3S ON LINE @ CO#3681 S | 35202446 |  |  | STS-POLE_BROK_REPL - #3S ON LINE @ CO#36 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1714 | -120.816 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | Q22 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.6 | 17.6 |  |  | 0 | 17.6 | 17.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101242333 | RELW OH PRI REMT ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-01 | 2021-02-01 | COMP | 2020-12-09 | [16 empty] | 2019-03-24 | 2020-03-24 | 2020-11-29 | 2020-11-29 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163231101 | 9057.97 | 89.6 | -2434.8 | -1982.3 | -1982.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117121633 | POLE_DECA_REPL - 1S/O 3058 BLAIR RDVALLE | 35202331 |  |  | STS-POLE_DECA_REPL - 1S/O 3058 BLAIR RDV | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1644 | -120.8588 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2109 | L2251 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43.1 | 43.1 |  |  | 0 | 43.1 | 43.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101246450 | OH RELW PRI CLR JPOL RESD NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-09 | 2021-02-01 | COMP | 2020-12-08 | [16 empty] | 2019-04-29 | 2020-04-29 | 2020-11-29 | 2020-11-29 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162991102 | 22546.17 | 98.1 | -2615.9 | -2027.6 | -2027.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117162978 | POLE_BROK_REPL - #8S #3W ON LINE @ #2NW | 35206558 |  |  | STS-POLE_BROK_REPL - #8S #3W ON LINE @ # | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2247 | -120.8653 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 14.4 | 14.4 |  |  | 0 | 14.4 | 14.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101233851 | RELW OH SERV JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 | 2021-01-13 | COMP | 2020-12-11 | [16 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 163231101 | 6631.51 | 44.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117164371 | POLE_BROK_REPL - 5635 CAMPO SECO RD/ROAD | 35206550 |  |  | STS-POLE_BROK_REPL - 5635 CAMPO SECO RD/ | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2201 | -120.8793 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 24.1 | 24.1 |  |  | 0 | 24.1 | 24.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101234125 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 | 2021-01-13 | COMP | 2020-12-11 | [16 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 163231101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117164540 | POLE_BROK_REPL - R/O 5686 CAMPO SECO RDV | 35206555 |  |  | STS-POLE_BROK_REPL - R/O 5686 CAMPO SECO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2213 | -120.8806 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 14.7 | 14.7 |  |  | 0 | 14.7 | 14.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101234190 | RELW OH SERV REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 | 2020-12-11 | COMP | 2020-12-11 | [16 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 163231101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117165409 | POLE_BROK_REPL - 5535 CAMPO SECO RD W/TR | 35206546 |  |  | STS-POLE_BROK_REPL - 5535 CAMPO SECO RD | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2184 | -120.8791 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 | 1115 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.7 | 41.7 |  |  | 0 | 41.7 | 41.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101234129 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 | 2021-01-14 | COMP | 2020-12-11 | [16 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 163231101 | 19244.37 | 587.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117256024 | POLE_BROK_REPL - #9 ON LINE N/O CAMPO SE | 35202887 |  |  | STS-POLE_BROK_REPL - #9 ON LINE N/O CAMP | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2367 | -120.8409 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO22 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.4 | 20.4 |  |  | 0 | 20.4 | 20.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101274651 | RELW OH PRI PGEA REMT NOAC ESTR FSRP FMOB TER2 PRTO | Pole | 2021-01-25 | 2021-01-25 | COMP | 2021-01-25 | [16 empty] | 2019-05-17 | 2020-05-17 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-01-31 | TRC |  | 163231101 | 8443.48 | 49.2 | -1092.6 | -0.6 | -0.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117280658 | POLE_BROK_REPL - #1S 5919 PALOMA RD VALL | 31496107 |  |  | STS-POLE_BROK_REPL - #1S 5919 PALOMA RD | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2571 | -120.7681 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | O23 |  | Y | 311 |  |  |  |  | Returned | Order Operation | [6 empty] | 15 | 15 |  |  | 0 | 15 | 15 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101246647 | REGW OH PRI JPOL RESD TRAF FLAG GO BTKA FMOB TER2 PRTO | Pole |  | 2020-03-13 | [18 empty] | 2019-05-20 | 2020-05-20 |  | 2020-05-20 | Per DOT Approved Request 45787 |  | UNASSIGNED |  | 163231101 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-06
Bay/Central | ST | Valley Springs | Angels Camp |  |  | OPEN | 120031357 | POLE_BROK_REPL - 7828 ADAMS AV, VALLEY S | 35214129 |  |  | STS-POLE_BROK_REPL - 7828 ADAMS AV, VALL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-12 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.134 | -120.9266 |  | TIER 2 | 46 | 16299-1101, CORRAL | Q1925 | 965803 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.7 | 38.7 |  |  | 0 | 38.7 | 38.7 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 102040215 | PRI OH RELW CREW REMT FLAG ESTR BTKA USA FMOB TER2 | Pole | 2021-01-07 | 2021-01-08 | COMP | 2021-01-07 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2020-11-09 | 2021-02-09 |  | 2021-02-09 | B tag clean up 11/19/2020 |  | Stockton |  | 162991101 | 17411.49 | 217 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-11-19
Bay/Central | ST | VALLEY SPRINGS | Angels Camp |  |  | OPEN | 117178530 | POLE_BROK_REPL - 3949 CAMPO SECO RD @ HO | 35206545 |  |  | STS-POLE_BROK_REPL - 3949 CAMPO SECO RD | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2277 | -120.8523 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | OO21 | 1115 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101233771 | RELW OH PRI JPOL REMT ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-11-10 | 2021-01-02 | COMP | 2020-11-10 | [16 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 163231101 | 21868.94 | 100.2 | 55.5 | 55.5 | 55.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Stockton |  |  | OPEN | 116729846 | POLE_BROK_REPL - 4526 BURSON RDVALLEY SP | 35149644 |  |  | STS-POLE_BROK_REPL - 4526 BURSON RDVALLE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1655 | -120.893 |  | TIER 2 | 46 | 16299-1101, CORRAL | Q2004 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21 | 20.6 |  | 0.4 | 0 | 21 | 20.6 |  | 0.4 | EC | E | Pole | Broken/Damaged | Replace |  | 102040855 | RELW REMT OH SEC ESTR BTKA USA FMOB TER2 PRTO | Pole | 2021-01-11 | 2021-02-12 | COMP | 2021-01-11 | [16 empty] | 2019-03-13 | 2020-03-13 |  | 2020-03-13 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 162991101 | 8291.9 | 406.7 | 0 | 701.7 | 701.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Stockton |  |  | OPEN | 116756199 | POLE_DECA_REPL - 2997 DENNIS COURTVALLEY | 35202143 |  |  | STS-POLE_DECA_REPL - 2997 DENNIS COURTVA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.1712 | -120.8589 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2104 | L7389 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.9 | 31.9 |  |  | 0 | 31.9 | 31.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103183748 | RELW OH PRI CLR JPOL ESTR BTKA FSRP FMOB TER2 PRTO | Pole | 2020-12-08 |  | COMP | 2020-12-08 | [16 empty] | 2019-03-18 | 2020-03-18 | 2020-11-29 | 2020-11-29 | 2021 CBP Plan | 2021-01-31 | TRC |  | 162991102 | 19138.05 | 40.4 | -2615.8 | -2072.8 | -2072.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Stockton |  |  | OPEN | 120464623 | TREE_DECA_INPL - 10060 WHALEN RD VALLEY | 35229145 |  |  | STS-TREE_DECA_INPL - 10060 WHALEN RD VAL | ESTS | ESTS | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  |  | 1 | 2021-03-26 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.1756 | -120.9547 |  | TIER 2 | 46 | 16299-1101, CORRAL | PP18 | 8699 | Y | 311 |  |  | 2021-04-19 07:15 | 2021-04-19 15:15 | Reserved | CLICK | [6 empty] | 24 | 24 |  |  | 0 | 24 | 24 |  |  | EC | B | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 102046766 | RELW OH ESTR GO PROG TER2 | Pole |  |  | REQD | [17 empty] | 2021-01-23 | 2021-04-23 |  | 2021-04-23 | B tag clean up 2/22/2021 |  | UNASSIGNED |  | 162991101 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-22
Bay/Central | ST | VALLEY SPRINGS | Stockton |  |  | OPEN | 117174264 | POLE_DECA_REPL - #1E 7233 WARREN RD CO#1 | 35149828 |  |  | STS-POLE_DECA_REPL - #1E 7233 WARREN RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.134 | -120.9118 |  | TIER 2 | 46 | 16299-1101, CORRAL | Q2022 | 12608 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23 | 23 |  |  | 0 | 23 | 23 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102040360 | RELW OH PRI CLR JPOL RESD REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-04 | 2020-09-08 | COMP | 2020-04-14 |  |  | 2020-05-14 | 2020-05-14 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-04-10 | ENENG |  | 162991101 | 14431.38 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VALLEY SPRINGS | Stockton |  |  | OPEN | 117214970 | POLE_BROK_REPL - R/O 60 LONG HORN CT/OFF | 35149943 |  |  | STS-POLE_BROK_REPL - R/O 60 LONG HORN CT | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1047 | -120.9265 |  | TIER 2 | 46 | 16299-1101, CORRAL | R1915 | 19621 | Y | 311 |  |  | 2021-02-13 07:00 | 2021-02-13 16:00 | Dispatched | CLICK | [6 empty] | 42.1 | 42.1 |  |  | 2 | 42 | 42 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102043428 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-04-13 | 2020-06-11 | COMP | 2020-04-13 | [16 empty] | 2019-05-11 | 2019-11-11 |  | 2019-11-11 | circuit based plan 2.14 | 2020-04-10 | ENENG |  | 162991101 | 19240.29 | 5236.7 | 4933.8 | 4875 | 4875 | 302.9 |  | 302.9 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VALLEY SPRINGS | Stockton |  |  | OPEN | 117219710 | POLE_DECA_REPL - #6 N/O R/O 8106 OLIVE B | 35107127 |  |  | STS-POLE_DECA_REPL - #6 N/O R/O 8106 OLI | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1286 | -120.8911 |  | TIER 2 | 319 | 16299-1102, CORRAL | Q2025 |  | Y | 311 | [5 empty] | Order Operation | [6 empty] | 28.9 | 28.9 |  |  | 0 | 28.9 | 28.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102049221 | RELW OH PRI CLR NOAC ESTR FMOB TER2 PRTO | Pole | 2019-07-09 | 2019-07-10 | COMP | 2019-07-09 | [16 empty] | 2019-05-12 | 2019-08-12 |  | 2019-08-12 | Q1 Work Plan |  | W. Sac |  | 162991102 | 28908.14 | 349.9 | -3738.7 |  |  | 5702.4 |  | 5702.4 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VALLEY SPRINGS | Stockton |  |  | OPEN | 117242453 | POLE_BROK_REPL - 7655–8199 GOODELL RDVAL | 35181314 |  |  | STS-POLE_BROK_REPL - 7655–8199 GOODELL R | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2729 | -120.7843 |  | TIER 2 | 399 | 16323-1101, NORTH BRANCH | NN23 |  | Y | 311 |  |  | 2021-02-13 07:00 | 2021-02-13 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 29 | 29 |  |  | 1 | 28 | 28 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 103181593 | RELW OH PRI INSP CLR JPOL REMT TRAF FLAG ESTR BTKA FMOB TER2 FSRP | Pole | 2020-11-18 | 2020-12-03 | COMP | 2020-11-18 |  |  | 2020-11-20 | 2020-11-20 | [12 empty] | 2019-05-15 | 2020-05-15 | 2020-08-30 | 2020-08-30 | B-Tag Addition 06.24.20 |  | Stockton |  | 163231101 | 14944.63 | 2532.9 | 2388.1 | 2345.2 | 2345.2 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-06-29
Bay/Central | ST | VALLEY SPRINGS | Stockton |  |  | OPEN | 119068993 | POLE_DECA_REPL - 7159 ELIZABETH CT VALLE | 35179451 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.161 | -120.9396 |  | TIER 2 | 46 | 16299-1101, CORRAL | Q1909 | 11653 | Y | 311 |  |  | 2021-02-20 07:00 | 2021-02-20 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 103796971 | OH RELW ESTR TER2 | Pole | 2020-06-29 | 2020-07-28 | COMP | 2020-06-27 |  |  | 2020-07-28 | 2020-07-28 | [12 empty] | 2020-05-20 | 2020-08-20 |  | 2020-08-20 | B-Tag Addition 06.24.20 |  | Stockton |  | 162991101 | 5601.37 | 45.4 | [7 empty] | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-06-29
Bay/Central | ST | VALLEY SPRINGS | Stockton |  |  | CNCL | 116752434 | POLE_BROK_REPL - A/F 5478 MESSING RD VAL | 35159257 |  |  | BC10 POLE_BROK_REPL -A/F 5478 MESSING RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Excluded A&B Tags |  |  |  |  | 1 | 2020-06-05 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1632 | -120.9132 |  | TIER 2 | 46 | 16299-1101, CORRAL | Q2007 | 4587 | Y | 311 |  |  |  |  | Cancelled | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 67 | 67 |  |  | 1 | 66 | 66 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 102040692 | RELW OH PRI CNCL JPOL REMT FLAG PROG ESTR GO BTKA CPGD FMOB TER2 PRTO | Pole | 2020-03-23 | 2020-05-01 | COMP | 2020-03-23 |  |  | 2020-03-20 | 2020-03-20 | [11 empty] | 2020-06-10 | 2020-06-05 | 2020-03-17 |  | 2020-03-17 | Per DOT Approved Request 19754 | 2020-05-31 | Stockton |  | 162991101 | 31542.61 | 188.2 |  |  |  | 188.2 |  | 188.2 |  | N | MPP File Only | N |  | Y | 2020-12-15
Bay/Central | ST | VOLCANO | Angels Camp |  |  | COMP | 117320406 | POLE_DECA_REPL - A\F 19411 MELLA DRVOLCA | 35116223 |  |  | STS-POLE_DECA_REPL - A\F 19411 MELLA DRV | FICL | FICL SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-05-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.4632 | -120.6647 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K26 | L2927 | Y | 311 |  |  | 2021-01-09 | 2021-01-09 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0.5 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261829 | RELW OH PRI COMP REMT ESTR CCNT PRTO BTKA FMOB TER2 | Pole | 2019-11-15 | 2019-12-04 | COMP | 2019-11-15 | COMP | 2021-01-09 | 2019-12-04 | 2019-12-04 | [11 empty] | 2021-01-20 | 2021-01-09 | 2020-05-25 |  | 2020-05-25 | circuit based plan 2.14 |  | Fresno |  | 163751102 | 16759.42 | 27741.8 | 24407.3 | 20674.6 | 20674.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 116878620 | POLE_BROK_REPL - 19640 SHAKE RIDGE RDVOL | 35083092 |  |  | STS-POLE_BROK_REPL - 19640 SHAKE RIDGE R | ESTS | ESTS ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.4591 | -120.66 |  | TIER 2 | 498 | 16301-1101, MARTELL | K26 | 96293 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101261529 | RELW OH PRI ESTR CLR REMT FLAG BTKA USA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 |  | 2020-03-31 | 2021 CBP Plan | 2021-01-31 | Bakersfield |  | 163011101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117012752 | POLE_BROK_REPL - 3 W/O 3 S/O R/O 19001 H | 35115831 |  |  | STS-POLE_BROK_REPL - 3 W/O 3 S/O R/O 190 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4643 | -120.677 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.2 | 15.2 |  |  | 0 | 15.2 | 15.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101261345 | RELW OH PRI REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-06-29 | 2021-02-16 | COMP | 2020-06-29 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-04-11 | 2020-04-11 |  | 2020-04-11 | 2021 CBP Plan | 2020-05-31 | Bakersfield |  | 163751102 | 11403.84 | 57.5 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117323249 | POLE_DECA_REPL - 6W\O SW#1595 HALE RDVOL | 35116273 |  |  | STS-POLE_DECA_REPL - 6W\O SW#1595 HALE R | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.461 | -120.6652 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K26 | L1595 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 42.4 | 42.1 | 0.3 |  | 0 | 42.4 | 42.1 | 0.3 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261362 | RELW FMOB OH PRI ESTR TER2 PRTO | Pole | 2020-12-26 |  | COMP | 2020-12-26 | [16 empty] | 2019-05-26 | 2020-05-26 |  | 2020-05-26 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 163751102 | 19336.78 | 165.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VOLCANO | Jackson |  |  | COMP | 116875846 | POLE_BROK_REPL - 19805 SHAKE RIDGE RDVOL | 35116041 |  |  | OCLH-POLE_BROK_REPL -19805 SHAKE RIDGE R | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.4616 | -120.6577 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K26 | L2469 | Y | 311 |  |  | 2021-01-09 | 2021-01-09 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 30.7 | 30.7 |  |  | 0 | 2.7 | 2.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101261370 | RELW OH PRI COMP REMT FLAG ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-03-19 | 2020-03-19 | COMP | 2020-03-19 | COMP | 2021-01-09 | 2019-07-31 | 2019-07-31 | [11 empty] | 2021-01-25 | 2021-01-09 | 2020-03-31 |  | 2020-03-31 | circuit based plan 2.14 | 2020-05-31 | Stockton |  | 163751102 | 24950.71 | 10010.9 | 8150.2 | 26263.6 | 26263.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 116848735 | POLE_BROK_REPL - 2S\O 20219 PONDEROSA TR | 35116001 |  |  | XSTS-POLE_BROK_REPL -2S\O 20219 PONDEROS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4533 | -120.6514 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 18.9 | 2.9 | 16 |  | 0 | 18.9 | 2.9 | 16 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101261512 | RELW OH PRI REMT SWRK ESTR BTKA PRTO FMOB TER2 | Pole | 2019-12-04 | 2019-12-04 | COMP | 2019-12-04 | [16 empty] | 2019-03-27 | 2020-03-27 |  | 2020-03-27 | circuit based plan 2.14 |  | UNASSIGNED |  | 163751102 | 16969.86 | 8551.2 | 978.2 | 248.4 | 248.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 116866535 | POLE_DECA_REPL - 3N\O 1W\O 15825 PINE GR | 35116029 |  |  | XSTS-POLE_DECA_REPL -3N\O 1W\O 15825 PIN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4395 | -120.6327 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K2711 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21 | 21 |  |  | 0 | 21 | 21 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101262028 | RELW OH PRI JPOL REMT ESTR REAR FMOB TER2 PRTO | Pole | 2020-03-25 | 2020-03-25 | COMP | 2020-03-25 | [16 empty] | 2019-03-29 | 2020-03-29 |  | 2020-03-29 | circuit based plan 2.14 |  | UNASSIGNED |  | 163751102 | 25607.67 | 68.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | COMP | 116863482 | POLE_DECA_REPL - R\O 19835 BUCKEYE DRVOL | 35116016 |  |  | STS-POLE_DECA_REPL - R\O 19835 BUCKEYE D | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-05-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.4563 | -120.6564 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K26 |  | Y | 311 |  |  | 2021-01-11 | 2021-01-11 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 20.1 | 20.1 |  |  | 7.5 | 20 | 20 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261580 | RELW OH SEC COMP CLR RESD ESTR GO USA CCNT FMOB TER2 PRTO | Pole | 2019-12-20 | 2019-12-20 | COMP | 2019-12-13 | COMP | 2021-01-11 | [13 empty] | 2021-01-20 | 2021-01-11 | 2020-03-28 |  | 2020-03-28 | circuit based plan 2.14 |  | UNASSIGNED |  | 163751102 | 5673.36 | 8254.6 | 5830.3 | 11038.8 | 11038.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | COMP | 116863586 | POLE_DECA_REPL - 1W\O R\O 20005 BUCKEYE | 35116018 |  |  | STS-POLE_DECA_REPL - 1W\O R\O 20005 BUCK | FICL | FICL SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-05-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.4564 | -120.6554 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K26 |  | Y | 311 |  |  | 2021-01-11 | 2021-01-11 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 23.2 | 21.9 | 1.3 |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261576 | RELW OH PRI COMP CLR ESTR USA CCNT FMOB TER2 PRTO | Pole | 2019-11-01 | 2019-11-01 | COMP | 2019-11-01 | COMP | 2021-01-11 | [13 empty] | 2021-01-20 | 2021-01-11 | 2020-03-28 |  | 2020-03-28 | circuit based plan 2.14 |  | UNASSIGNED |  | 163751102 | 7209.55 | 7353.7 | 5596.5 | 13001.1 | 13001.1 | 1571.3 |  | 1571.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | COMP | 116863656 | POLE_DECA_REPL - R\O 20005 BUCKEYE DRVOL | 35116020 |  |  | STS-POLE_DECA_REPL - R\O 20005 BUCKEYE D | FICL | FICL SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-05-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.4565 | -120.6549 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K26 |  | Y | 311 |  |  | 2021-01-11 | 2021-01-11 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 23.2 | 21.9 | 1.3 |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261568 | RELW OH PRI COMP CLR RESD ESTR GO USA CCNT FMOB TER2 PRTO | Pole | 2019-10-21 | 2019-10-21 | COMP | 2019-10-21 | COMP | 2021-01-11 | [13 empty] | 2021-01-20 | 2021-01-11 | 2020-03-28 |  | 2020-03-28 | circuit based plan 2.14 |  | UNASSIGNED |  | 163751102 | 11628.36 | 12789.5 | 10619.6 | 12877.3 | 12877.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | COMP | 116871466 | POLE_BROK_REPL - #1S 16755 CHARLESTON RD | 35116035 |  |  | STS-POLE_BROK_REPL - #1S 16755 CHARLESTO | FICL | FICL SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-05-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.4484 | -120.6402 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K26 |  | Y | 311 |  |  | 2021-01-05 | 2021-01-05 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 21 | 21 |  |  | 0.75 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102315977 | RELW OH PRI COMP CLR REMT ESTR CCNT FMOB TER2 PRTO | Pole | 2020-02-19 | 2020-02-19 | COMP | 2020-02-19 | COMP | 2021-01-05 | [13 empty] | 2021-01-12 | 2021-01-05 | 2020-03-30 |  | 2020-03-30 | circuit based plan 2.14 |  | UNASSIGNED |  | 163751102 | 13592.9 | 26513.4 | 23500.1 | 20753.3 | 20753.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 116850965 | POLE_DECA_REPL - 1S\O 19491 CHARLESTON R | 35116006 |  |  | STS-POLE_DECA_REPL - 1S\O 19491 CHARLEST | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4617 | -120.6505 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | K26 | 1837 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.8 | 33.8 |  |  | 0 | 33.8 | 33.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261379 | RELW OH PRI CLR RESD FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2019-10-16 | 2021-02-11 | COMP | 2019-10-08 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-03-27 | 2020-03-27 |  | 2020-03-27 | 2021 CBP Plan |  | UNASSIGNED |  | 163751102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117002013 | POLE_BROK_REPL - 3 E/O 20601 SHAKE RIDGE | 35116065 |  |  | STS-POLE_BROK_REPL - 3 E/O 20601 SHAKE R | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.466 | -120.6392 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J26 |  | Y | 311 |  |  | 2021-02-19 07:00 | 2021-02-19 16:00 | Completed | CLICK | [6 empty] | 22.1 | 22.1 |  |  | 2 | 22 | 22 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101261802 | RELW OH PRI BTKA REMT FLAG ESTR FMOB TER2 PRTO | Pole | 2020-08-07 | 2020-08-07 | COMP | 2020-08-07 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-04-10 | 2020-04-10 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-08-31 | W. Sac |  | 163751102 | 8419.91 | 2127 | 2126.9 | 2075.5 | 2075.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117071556 | POLE_DECA_REPL - 7 S/O C/O SHAKE RIDGE R | 35116101 |  |  | STS-POLE_DECA_REPL - 7 S/O C/O SHAKE RID | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4687 | -120.6261 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J27 |  | Y | 311 |  |  | 2021-03-05 07:00 | 2021-03-05 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 30.9 | 30.9 |  |  | 0 | 30.9 | 30.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101258354 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2019-10-24 | 2019-10-24 | COMP | 2019-10-24 | [16 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | circuit based plan 2.14 |  | UNASSIGNED |  | 163751102 | 17157.5 | 2017.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117071557 | POLE_DECA_REPL - 9 S/O C/O SHAKE RIDGE R | 35116103 |  |  |  | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4671 | -120.6263 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J27 |  | Y | 311 |  |  | 2021-03-06 07:00 | 2021-03-06 16:00 | Scheduled | CLICK | [6 empty] | 22.8 | 22.8 |  |  | 0 | 22.8 | 22.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101258351 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-06-22 | 2020-06-22 | COMP | 2020-06-22 | [16 empty] | 2019-04-20 | 2019-10-20 |  | 2019-10-20 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 163751102 | 12389.08 | 1030.2 | 793.5 |  |  | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117071558 | POLE_DECA_REPL - 6 S/O C/O SHAKE RIDGE R | 35116105 |  |  | STS-POLE_DECA_REPL - 6 S/O C/O SHAKE RID | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4692 | -120.6261 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J27 |  | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | [6 empty] | 30.9 | 30.9 |  |  | 0 | 30.9 | 30.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101258356 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2019-11-07 | 2019-11-07 | COMP | 2019-11-07 | [16 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | circuit based plan 2.14 |  | UNASSIGNED |  | 163751102 | 16796.67 | 1856.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117071559 | POLE_DECA_REPL - 4 S/O C/O SHAKE RIDGE R | 35116108 |  |  | STS-POLE_DECA_REPL - 4 S/O C/O SHAKE RID | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4709 | -120.6259 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J27 |  | Y | 311 |  |  | 2021-03-01 07:00 | 2021-03-01 16:00 | Dispatched | CLICK | [6 empty] | 30.9 | 30.9 |  |  | 0 | 30.9 | 30.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101258358 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2019-11-07 | 2019-11-07 | COMP | 2019-11-07 | [16 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | circuit based plan 2.14 |  | UNASSIGNED |  | 163751102 | 16868.02 | 1580.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117071620 | POLE_DECA_REPL - 10 S/O C/O SHAKE RIDGE | 35116111 |  |  | STS-POLE_DECA_REPL - 10 S/O C/O SHAKE RI | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4666 | -120.6263 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J27 |  | Y | 311 |  |  | 2021-03-06 07:00 | 2021-03-06 16:00 | Scheduled | CLICK | [6 empty] | 19.8 | 19.8 |  |  | 0 | 19.8 | 19.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101258349 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-02-19 | 2020-02-19 | COMP | 2020-02-19 | [16 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | circuit based plan 2.14 | 2020-04-20 | W. Sac |  | 163751102 | 9607.39 | 3194.5 |  |  |  | 953.6 |  | 953.6 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117071622 | POLE_DECA_REPL - 5 S/O C/O SHAKE RIDGE R | 35116114 |  |  | STS-POLE_DECA_REPL - 5 S/O C/O SHAKE RID | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4702 | -120.626 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J27 |  | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | [6 empty] | 34.8 | 34.8 |  |  | 0 | 34.8 | 34.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101258357 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-02-27 | 2020-02-27 | COMP | 2020-02-27 | [16 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | circuit based plan 2.14 | 2020-04-20 | W. Sac |  | 163751102 | 18326.66 | 1859.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117071624 | POLE_DECA_REPL - 1 S/O 22463 BERONE RD V | 35116117 |  |  | STS-POLE_DECA_REPL - 1 S/O 22463 BERONE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4633 | -120.6114 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J27 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.3 | 18.3 |  |  | 0 | 18.3 | 18.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101258481 | RELW OH PRI REMT ESTR FMOB TER2 PRTO | Pole | 2020-10-11 | 2020-10-11 | INPR | 2020-10-11 | [16 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 163751102 | 9393.58 | 92.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117071625 | POLE_DECA_REPL - 8 S/O C/O SHAKE RIDGE R | 35116120 |  |  | STS-POLE_DECA_REPL - 8 S/O C/O SHAKE RID | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4681 | -120.6262 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J27 |  | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | [6 empty] | 21.9 | 21.9 |  |  | 0 | 21.9 | 21.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101258352 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-03-31 | 2020-03-31 | COMP | 2020-03-31 | [16 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 163751102 | 16507.85 | 1710.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117087398 | POLE_DECA_REPL - 1 W/O R/O 17575 RAMS HO | 35116123 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4639 | -120.626 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J27 |  | Y | 311 |  |  | 2021-02-27 07:00 | 2021-02-27 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 17 | 17 |  |  | 0 | 17 | 17 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101258200 | RELW OH PRI REMT ESTR REAR FMOB TER2 PRTO | Pole | 2019-10-30 | 2019-10-30 | COMP | 2019-10-30 | [16 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | circuit based plan 2.14 |  | Fresno |  | 163751102 | 14956.96 | 2234.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117136253 | POLE_DECA_REPL - #2S/O HOUSE 17206 HALE | 35103005 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4669 | -120.7107 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 | L6621 | Y | 311 |  |  | 2021-02-27 07:00 | 2021-02-27 16:00 | Dispatched | CLICK | [6 empty] | 39.8 | 39.8 |  |  | 0 | 39.8 | 39.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261279 | RELW OH PRI REMT ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2019-12-30 | 2020-07-27 | COMP | 2019-12-30 | [16 empty] | 2019-05-01 | 2019-11-01 |  | 2019-11-01 | circuit based plan 2.14 |  | W. Sac |  | 163751102 | 18461.28 | 920 | 793.5 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117148762 | POLE_DECA_REPL - #1E 18000 HALE RD VOLCA | 35116254 |  |  | STS-POLE_DECA_REPL - #1E 18000 HALE RDVO | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4666 | -120.6914 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 33.9 | 33.9 |  |  | 0 | 33.9 | 33.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261324 | RELW OH PRI REMT TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-01-31 | 2020-01-31 | COMP | 2020-01-31 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-05-02 | 2020-05-02 |  | 2020-05-02 | circuit based plan 2.14 |  | UNASSIGNED |  | 163751102 | 22447.66 | 3657 |  |  |  | 1488.1 |  | 1488.1 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117154880 | POLE_DECA_REPL - #1E/O 18500 HALE RDVOLC | 35116262 |  |  | STS-POLE_DECA_REPL - #1E/O 18500 HALE RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4651 | -120.6819 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J25 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.6 | 22.6 |  |  | 0 | 22.6 | 22.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101261340 | RELW OH PRI REMT TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2019-12-07 | 2020-10-08 | COMP | 2019-11-07 |  |  | 2019-11-04 | 2019-11-04 | [12 empty] | 2019-05-03 | 2020-05-03 |  | 2020-05-03 | 2021 CBP Plan |  | UNASSIGNED |  | 163751102 | 13463.78 | 37.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | VOLCANO | Jackson |  |  | OPEN | 117011636 | POLE_BROK_REPL - 2 W/O 19570 CHARLESTON | 35116097 |  |  | STS-POLE_BROK_REPL - 2 W/O 19570 CHARLES | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4643 | -120.6533 |  | TIER 2 | 4 | 16375-1102, PINE GROVE | J26 | L2469 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101261756 | RELW OH PRI REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2021-01-10 | 2021-01-10 | COMP | 2021-01-10 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-04-11 | 2020-04-11 |  | 2020-04-11 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 163751102 | 24507.14 | 75 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | WALLACE | Stockton |  |  | OPEN | 116706074 | POLE_DECA_REPL - 3S/O8090 SAWMIL ST WALL | 35082649 |  |  | STS-POLE_DECA_REPL - 3S/O8090 SAWMIL STW | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Enviro JointPole |  |  | 38.1946 | -120.9773 |  | TIER 2 | 46 | 16299-1101, CORRAL | PP1814 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 36.7 | 36.7 |  |  | 0 | 36.7 | 36.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102048152 | RELW OH PRI CLR ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-03 |  | COMP | 2021-02-03 | [16 empty] | 2019-03-10 | 2020-03-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 162991101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | WEST POINT | Jackson |  |  | OPEN | 116979904 | POLE_BROK_REPL - #1W HWY 26 ON NIDEROST | 35123473 |  |  | STS-POLE_BROK_REPL - #1W HWY 26 ON NIDER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.413 | -120.5419 |  | TIER 2 | 23 | 16320-1102, WEST POINT | KK2918 | L6413 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.5 | 30.9 | 0.6 |  | 0 | 31.5 | 30.9 | 0.6 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101244535 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-05-23 | 2020-05-26 | COMP | 2020-01-30 |  |  | 2020-05-14 | 2020-05-14 | [12 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | circuit based plan 2.14 | 2020-01-30 | ENENG |  | 163201102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | WEST POINT | Jackson |  |  | OPEN | 117093074 | POLE_BROK_REPL - 3 N/O 4457 SUMMER RD WE | 35123577 |  |  | STS-POLE_BROK_REPL - 3 N/O 4457 SUMMER R | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3875 | -120.5906 |  | TIER 2 | 23 | 16320-1102, WEST POINT | LL28 | 1839 | Y | 311 |  |  | 2021-03-06 07:00 | 2021-03-06 16:00 | Scheduled | CLICK | [6 empty] | 34 | 34 |  |  | 1 | 33 | 33 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101250526 | RELW OH PRI CREW CLR REMT FIRE NOAC SPCR SWRK ESTR TER2 | Pole | 2020-02-25 | 2020-05-12 | COMP | 2020-02-25 | [16 empty] | 2019-04-18 | 2020-04-18 |  | 2020-04-18 | circuit based plan 2.14 | 2020-02-25 | ENENG |  | 163201102 | 15836.41 | 3656.2 | 51.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | WEST POINT | Jackson |  |  | OPEN | 117147444 | POLE_DECA_REPL - #1E ON LINE @ 1734 SPIN | 35123596 |  |  | STS-POLE_DECA_REPL - #1E ON LINE @ 1734 | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4002 | -120.548 |  | TIER 2 | 23 | 16320-1102, WEST POINT | KK29 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 14 | 14 |  |  | 0 | 14 | 14 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101245142 | RELW OH PRI REMT FIRE ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-01-09 | 2020-05-14 | COMP | 2020-01-09 |  |  | 2020-05-14 | 2020-05-14 | [12 empty] | 2019-05-02 | 2020-05-02 |  | 2020-05-02 | circuit based plan 2.14 | 2020-01-09 | ENENG |  | 163201102 | 8154.45 | 1154.8 |  |  |  | 940.7 |  | 940.7 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | WEST POINT | Jackson |  |  | OPEN | 117148755 | POLE_DECA_REPL - R/O 1734 SPINK RD W/TRA | 35123598 |  |  | STS-POLE_DECA_REPL - R/O 1734 SPINK RD W | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4011 | -120.5495 |  | TIER 2 | 23 | 16320-1102, WEST POINT | KK29 | L1259 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 53.9 | 53.3 | 0.6 |  | 2.5 | 51.4 | 50.8 | 0.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101245140 | RELW OH PRI REMT FIRE FMOB ESTR BTKA USA TER2 PRTO | Pole | 2020-01-14 | 2020-01-31 | COMP | 2020-01-14 | [16 empty] | 2019-05-02 | 2020-05-02 |  | 2020-05-02 | circuit based plan 2.14 | 2020-01-14 | ENENG |  | 163201102 | 21561.93 | 5182 |  |  |  | 940.7 |  | 940.7 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | WEST POINT | Jackson |  |  | OPEN | 117301326 | POLE_DECA_REPL - 505 STANLEY RD @ ENTRAN | 35124675 |  |  | STS-POLE_DECA_REPL - 505 STANLEY RD @ EN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3833 | -120.5587 |  | TIER 2 | 23 | 16320-1102, WEST POINT | LL29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.3 | 33.3 |  |  | 0 | 33.3 | 33.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101248574 | RELW OH PRI CLR RESD REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-09 | 2020-10-13 | COMP | 2020-07-20 |  |  | 2020-10-08 | 2020-10-08 | [12 empty] | 2019-05-22 | 2020-05-22 |  | 2020-05-22 | 2021 CBP Plan | 2020-07-31 | EEI |  | 163201102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | ST | WEST POINT | Jackson |  |  | OPEN | 117337259 | POLE_DECA_REPL - #1 N/O #1 W/O R/O 2352 | 35125191 |  |  | STS-POLE_DECA_REPL - #1 N/O #1 W/O R/O 2 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4002 | -120.5639 |  | TIER 2 | 23 | 16320-1102, WEST POINT | KK29 |  | Y | 311 |  |  | 2021-02-16 07:00 | 2021-02-16 16:00 | Dispatched | CLICK | [6 empty] | 19.1 | 19.1 |  |  | 1 | 19 | 19 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101245095 | RELW OH PRI CLR ESTR BTKA FMOB TER2 PRTO | Pole | 2020-02-03 | 2020-02-03 | COMP | 2020-02-03 | [16 empty] | 2019-05-29 | 2020-05-29 |  | 2020-05-29 | circuit based plan 2.14 | 2020-02-03 | QUES |  | 163201102 | 8656.23 | 1805.4 | 51.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | WEST POINT | Jackson |  |  | OPEN | 117344650 | POLE_DECA_REPL - #1S #1E ON LINE @ R/O 1 | 35125189 |  |  | STS-POLE_DECA_REPL - #1S #1E ON LINE @ R | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3924 | -120.5754 |  | TIER 2 | 23 | 16320-1102, WEST POINT | LL28 |  | Y | 311 |  |  | 2021-02-13 07:00 | 2021-02-13 16:00 | Completed | CLICK | [6 empty] | 19.8 | 19.8 |  |  | 1.5 | 18.8 | 18.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101250486 | RELW OH PRI CLR RESD REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-04-03 | 2020-04-03 | COMP | 2020-04-03 | [16 empty] | 2019-05-30 | 2020-05-30 |  | 2020-05-30 | circuit based plan 2.14 | 2020-04-03 | QUES |  | 163201102 | 5366 | 648.6 | 108.3 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | WEST POINT | Jackson |  |  | OPEN | 117371283 | POLE_DECA_REPL - #2N #2W ON LINE @ R/O 2 | 35125250 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3946 | -120.5727 |  | TIER 2 | 23 | 16320-1102, WEST POINT | LL28 | 1839 | Y | 311 |  |  | 2021-02-27 07:00 | 2021-02-27 16:00 | Dispatched | CLICK | [6 empty] | 37.8 | 37.8 |  |  | 0 | 37.8 | 37.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101250471 | RELW OH PRI CLR REMT NOAC SWRK ESTR GO FMOB TER2 PRTO | Pole | 2020-02-27 | 2020-02-28 | COMP | 2020-01-15 |  |  | 2020-01-23 | 2020-01-23 | [12 empty] | 2019-06-01 | 2020-06-01 |  | 2020-06-01 | circuit based plan 2.14 | 2020-01-15 | CALENG |  | 163201102 | 22022.32 | 2224.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | WEST POINT | Jackson |  |  | OPEN | 117371284 | POLE_DECA_REPL - #3N #2W ON LINE @ R/O 2 | 35125253 |  |  | STS-POLE_DECA_REPL - #3N #2W ON LINE @ R | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3951 | -120.5727 |  | TIER 2 | 23 | 16320-1102, WEST POINT | LL28 |  | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 26.1 | 26.1 |  |  | 0 | 26.1 | 26.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101250475 | RELW OH PRI CLR REMT NOAC SWRK ESTR FMOB TER2 PRTO | Pole | 2019-12-04 | 2019-12-04 | COMP | 2019-12-04 | [16 empty] | 2019-06-01 | 2020-06-01 |  | 2020-06-01 | circuit based plan 2.14 | 2019-12-25 | CALENG |  | 163201102 | 21809.57 | 1097.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | WEST POINT | Jackson |  |  | OPEN | 117371294 | POLE_DECA_REPL - #1N #2W ON LINE @ R/O 2 | 35125256 |  |  | STS-POLE_DECA_REPL - #1N #2W ON LINE @ R | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3941 | -120.5727 |  | TIER 2 | 23 | 16320-1102, WEST POINT | LL28 |  | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 14.1 | 14.1 |  |  | 1.25 | 14 | 14 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101250468 | RELW OH PRI CLR REMT NOAC SWRK ESTR FMOB TER2 PRTO | Pole | 2019-12-20 | 2019-12-20 | COMP | 2019-12-20 | [16 empty] | 2019-06-01 | 2020-06-01 |  | 2020-06-01 | circuit based plan 2.14 | 2019-12-25 | CALENG |  | 163201102 | 18267.33 | 1076.4 | 90.2 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | ST | WEST POINT | Jackson |  |  | OPEN | 119029002 | POLE_BROK_REPL - 22180 HWY 26 W/TRANS WE | 35185251 |  |  | STS-POLE_BROK_REPL - 22180 HWY 26 W/TRAN | CONS | CONS | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3969 | -120.5274 |  | TIER 2 | 23 | 16320-1102, WEST POINT | KK2925 | L1503 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.7 | 39.7 |  |  | 85.5 | 39.6 | 39.6 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101244761 | RELW PRI OH INSP REMT GO BTKA SCOP SCPA FMOB TER2 | Pole | 2020-08-15 |  | COMP | 2020-08-15 | COMP | 2020-07-14 | 2020-10-15 | 2020-10-15 | [12 empty] | 2020-05-14 | 2020-08-14 |  | 2020-08-14 | Work Plan Reconcilation (B-Tags) |  | Stockton |  | 163201102 | 28663.1 | 42609.3 | 635 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Tag in Closure Status | Y | 2020-07-21
Bay/Central | ST | WEST POINT | Jackson |  |  | OPEN | 117056817 | POLE_DECA_REPL - #3S ON LINE @ 22803 HWY | 35123548 |  |  | STS-POLE_DECA_REPL - #3S ON LINE @ 22803 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4037 | -120.5305 |  | TIER 2 | 23 | 16320-1102, WEST POINT | KK2925 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Reserved | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101244621 | RELW OH BTKA PRI REMT ESTR USA PRTO FMOB TER2 | Pole | 2020-07-02 | 2021-01-14 | COMP | 2020-07-01 |  |  | 2021-01-14 | 2021-01-14 | [12 empty] | 2019-04-18 | 2020-04-18 |  | 2020-04-18 | 2021 CBP Plan | 2020-07-31 | ENENG |  | 163201102 | 20688.4 | 113.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO |  | Mariposa |  |  | OPEN | 115597253 | SE C/O HWY 49/UTAH ST ROAD | 35069325 |  |  | SE C/O HWY 49/UTAH ST ROAD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.5687 | -120.1189 |  | TIER 2 |  |  | 0000417216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 134.6 | 134.6 |  |  | 2 | 132.6 | 132.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101019303 | REGW OH TER2 FSRP | Pole | 2020-10-26 |  | COMP | 2020-10-26 | [16 empty] | 2018-12-26 | 2019-12-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | EEI |  |  | 34260.02 | 2995.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO |  | Mariposa |  |  | OPEN | 117771564 | REPL POLE:R/O 5916 WHITLOCK RD\2PE\5PS P | 35154894 |  |  | STS-REPL POLE:R/O 5916 WHITLOCK RD\2PE\5 | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.5516 | -120.0158 |  | TIER 2 |  |  | 0000004186 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.2 | 18.2 |  |  | 0 | 18.2 | 18.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077470 | RELW OH TNT TER2 FSRP | Pole | 2020-09-03 | 2020-09-02 | COMP | 2020-08-31 | [16 empty] | 2019-04-16 | 2020-04-16 | 2024-04-14 | 2024-04-14 | 2021 CBP Plan | 2020-10-31 | TRC |  |  | 20939.96 | 181 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO |  | Mariposa |  |  | OPEN | 115597295 | POLE_DECA_REPL - | 35069993 |  |  | 1PS HWY49 SO/3RD ST ROAD | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4829 | -119.9635 |  | TIER 2 |  |  | 0000518234 |  | Y | 311 |  |  | 2020-07-02 | 2020-07-03 | Completed | Order Operation | [6 empty] | 227.3 | 227.3 |  |  | 410.5 | 58.8 | 58.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087084 | REGW OH TER2 | Pole | 2019-04-11 | 2019-04-25 | COMP | 2019-04-11 |  |  | 2019-03-20 | 2019-03-20 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-02 | EEI |  |  | 24475.36 | 166405.7 | 33 | 33 | 33 | 763.1 |  | 763.1 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO |  | Mariposa |  |  | OPEN | 117771385 | REPL POLE:5781 HWY 49 PVTP, | 35154887 |  |  | STS-REPL POLE:5781 HWY 49 PVTP, | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5055 | -120.0205 |  | TIER 2 |  |  | 0000005182 |  | Y | 311 |  |  | 2021-06-29 07:00 | 2021-06-29 16:00 | Reserved | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101086789 | RELW TNT OH TER2 FSRP | Pole | 2020-05-27 | 2020-05-27 | COMP | 2020-05-27 | [16 empty] | 2019-05-20 | 2020-05-20 | 2024-05-18 | 2024-05-18 | 2021 CBP Plan | 2020-12-31 | TRC |  |  | 10324.24 | 1345 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO |  | Oakhurst |  |  | OPEN | 115597133 | 7947 SPELT RD. ROAD | 35069275 |  |  | 7947 SPELT RD. ROAD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | DMD |  |  | 37.5468 | -119.6474 |  | TIER 2 |  |  | 0000421353 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016674 | REGW OH TER2 | Pole | 2019-11-26 | 2019-11-25 | COMP | 2019-05-14 |  |  | 2019-09-09 | 2019-09-09 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-02 | EEI |  |  | 23264.39 | 4184.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | ARIPOSA | Mariposa |  |  | OPEN | 116861496 | POLE_BROK_REPL - 4061 OLD HIGHWAY 140 AR | 35215159 |  |  | STS-POLE_BROK_REPL - 4061 OLD HIGHWAY 14 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4298 | -120.0055 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182D | 22467 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101067111 | RELW OH PRI REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | N/A | Oakhurst |  |  | OPEN | 117186758 | POLE_DECA_REPL - 44100 CROOKS MTN. RD. | 35134235 |  |  | BUNDLE - 4 POLES - AHWAHNEE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.3949 | -119.7425 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000006204 | 298585 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016534 | REGW OH PRI REMT FIRE TRAF ESTR BTKA USA FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254421101 | 1 |  | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OARSEGOLD | Oakhurst |  |  | OPEN | 117367649 | POLE_BROK_REPL - 46014 JORDON LN/1PS OA | 35208959 |  |  | STS-POLE_BROK_REPL - 46014 JORDON LN/1PS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2705 | -119.708 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101061687 | RELW OH PRI CLR REMT FIRE SWRK ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-31 | 2020-05-31 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | 101053823 | Madera |  |  | OPEN | 117324075 | POLE_BROK_REPL - 44756 RD 415 101053823 | 35215726 |  |  | STS-POLE_BROK_REPL - 44756 RD 415 101053 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2451 | -119.7308 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820125 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101053823 | RELW OH PRI PGEA RESD FIRE FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-26 | 2020-05-26 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116977326 | POLE_DECA_REPL - 45748 RD 621/ 2S 1W 1NA | 35188671 |  |  | STS-POLE_DECA_REPL - 45748 RD 621/ 2S 1W | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 37.3638 | -119.7133 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 49.2 | 49.2 |  |  | 0 | 49.2 | 49.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101023877 | RELW OH SERV JPOL USA RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-16 | 2020-10-15 | COMP | 2020-10-15 | [16 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 24646.51 | 550.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116981622 | POLE_DECA_REPL - AF/45282 RD.621AHWAHNEE | 35187656 |  |  | STS-POLE_DECA_REPL - AF/45282 RD.621AHWA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3625 | -119.7209 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C | 10225 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 53.7 | 53.7 |  |  | 0 | 53.7 | 53.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024012 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-11 | 2021-02-16 | COMP | 2020-09-11 |  |  | 2021-02-11 | 2021-02-12 | [12 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 26614.42 | 1268.3 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116981692 | POLE_DECA_REPL - 42068 LONE TREE LN.2N 3 | 35187663 |  |  | STS-POLE_DECA_REPL - 42068 LONE TREE LN. | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.3623 | -119.7216 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C | 10225 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 32.3 | 32.3 |  |  | 0 | 32.3 | 32.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024006 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-15 |  | COMP | 2020-09-15 | [16 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 19176.67 | 1330.3 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116985573 | POLE_BROK_REPL - 1/2 M/E/O HARONY ON OPA | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 37.3642 | -119.6927 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216D |  | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101023695 | REGW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan |  | UNASSIGNED |  | 254421103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 117186220 | POLE_DECA_REPL - 44261 CROOKS MTN. RD. 3 | 35134235 |  |  | BUNDLE - 4 POLES - AHWAHNEE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.3948 | -119.741 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000006204 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 120 | 120 |  |  | 0 | 120 | 120 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016528 | REGW OH SEC REMT FIRE USA TRAF ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28466 | 2021-03-31 | TRC |  | 254421101 | 1 |  | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 117186907 | POLE_DECA_REPL - 44261 CROOKS MTN. RD.AH | 35134232 |  |  | BUNDLE - 8 POLES - AHWAHNEE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.3948 | -119.7382 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000006204 | 298585 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0.2 | 0.2 |  |  | 0 | 0.2 | 0.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016483 | PRI REGW OH PGEA CLR RESD REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-31 |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28469 | 2021-02-28 | CALENG |  | 254421101 | 20720.02 | 2785.8 | 1474.6 | 1656.6 | 1656.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 117187102 | POLE_DECA_REPL - 44440 HWY 49AHWAHNEE936 | 35134232 |  |  | BUNDLE - 8 POLES - AHWAHNEE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.3943 | -119.7377 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000006204 | 5546 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016467 | RELW OH PRI PGEA CLR RESD REMT FIRE TRAF FLAG ESTR BTKA USA FSRP PRTO FMOB TER2 | Pole | 2020-12-31 |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28470 | 2021-02-28 | CALENG |  | 254421101 | 20720.02 | 2785.8 | 1474.6 | 1656.6 | 1656.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 117187108 | POLE_DECA_REPL - ACF 44555 HWY 49 1WAHWA | 35134232 |  |  | BUNDLE - 8 POLES - AHWAHNEE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.3965 | -119.7379 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000006204 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016480 | REGW OH PRI REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-31 |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28471 | 2021-02-28 | CALENG |  | 254421101 | 20720.02 | 2785.8 | 1474.6 | 1656.6 | 1656.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 117187192 | POLE_DECA_REPL - ACF 44555 HWY 49 1SAHWA | 35134232 |  |  | BUNDLE - 8 POLES - AHWAHNEE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.396 | -119.7378 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000006204 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016475 | REGW FIRE OH PRI REMT TRAF ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-31 |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28472 | 2021-02-28 | CALENG |  | 254421101 | 20720.02 | 2785.8 | 1474.6 | 1656.6 | 1656.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 117187299 | POLE_DECA_REPL - 44440 HWY 49 1WAHWAHNEE | 35134232 |  |  | BUNDLE - 8 POLES - AHWAHNEE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.3942 | -119.738 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000006204 | 5546 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016468 | REGW OH PRI PGEA CLR RESD REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-31 |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28473 | 2021-02-28 | CALENG |  | 254421101 | 20720.02 | 2785.8 | 1474.6 | 1656.6 | 1656.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 117187338 | POLE_DECA_REPL - 44512 HWY 49AHWAHNEE936 | 35134232 |  |  | BUNDLE - 8 POLES - AHWAHNEE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.3953 | -119.7379 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000006204 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016471 | REGW OH PRI REMT FIRE TRAF FMOB ESTR BTKA USA TER2 PRTO FSRP | Pole | 2020-12-31 |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28474 | 2021-02-28 | CALENG |  | 254421101 | 20720.02 | 2785.8 | 1474.6 | 1656.6 | 1656.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 117187480 | POLE_DECA_REPL - 44512 HWY 49 1WAHWAHNEE | 35134232 |  |  | BUNDLE - 8 POLES - AHWAHNEE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.3953 | -119.7383 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000006204 | 298585 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016478 | REGW OH PRI REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-31 |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28475 | 2021-02-28 | CALENG |  | 254421101 | 20720.02 | 2785.8 | 1474.6 | 1656.6 | 1656.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 117187533 | POLE_DECA_REPL - 44512 HWY 49 2W AHWAHNE | 35134232 |  |  | BUNDLE - 8 POLES - AHWAHNEE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.3953 | -119.7387 |  | TIER 2 |  |  | 0000006204 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016484 | REGW OH SEC REMT FIRE ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-31 |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2020-09-13 | 2020-09-13 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 20720.02 | 2785.8 | 1474.6 | 1656.6 | 1656.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Ahwahnee | Oakhurst |  |  | OPEN | 117693166 | POLE _ BROK _ REPL_41225 RD.600 4N PVTP | 35209526 |  |  | STS-POLE _ BROK _ REPL_41225 RD.600 4N P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.35 | -119.7513 |  | TIER 2 |  |  | 07201A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103797171 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116970508 | POLE_DECA_REPL - 46946 RD.620 5NAHWAHNEE | 35188392 |  |  | STS-POLE_DECA_REPL - 46946 RD.620 5NAHWA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3876 | -119.6906 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000006216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.5 | 18.5 |  |  | 0 | 18.5 | 18.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024543 | RELW OH PRI CLR JPOL REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-13 | 2021-01-26 | COMP | 2020-10-13 |  |  | 2021-01-23 | 2021-01-25 | [12 empty] | 2019-04-06 | 2020-04-06 |  | 2020-04-06 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 9297.35 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116985768 | POLE_DECA_REPL - 47380 MIAMI HIGHLANDS 3 | 35187846 |  |  | STS-POLE_DECA_REPL - 47380 MIAMI HIGHLAN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3597 | -119.6859 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.2 | 16.2 |  |  | 0 | 16.2 | 16.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101023749 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-16 | 2021-01-26 | COMP | 2020-10-16 |  |  | 2021-01-23 | 2021-01-25 | [12 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 11424.37 | 531.9 | 55.7 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 114841379 | POLE_DECA_REPL - 45230 ROAD 621 AHWAHNEE | 35099885 |  |  |  | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3613 | -119.7216 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C | 10657 | Y | 311 |  |  | 2021-10-29 07:00 | 2021-10-29 16:00 | Reserved | CLICK | [6 empty] | 53.4 | 53.4 |  |  | 0 | 53.4 | 53.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024079 | RELW OH PRI INSP JPOL MINR RESD FIRE NOAC BTKA REAR PROG SCOP SCPA FMOB TER2 | Pole | 2020-06-16 | 2020-06-16 | COMP | 2020-06-16 | [16 empty] | 2018-08-01 | 2019-10-03 |  | 2019-10-03 | 2021 CBP Plan | 2020-12-31 | QUES |  | 254421103 | 14014.97 | 58.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116766591 | POLE_DECA_REPL - RD.600 APACHE RANCH RD. | 35154223 |  |  | STS-POLE_DECA_REPL - RD.600 APACHE RANCH | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.331 | -119.7719 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000007201 | 10357 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 1.5 | 49.3 | 49.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101022514 | RELW OH PRI CLR ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-05-11 | 2020-05-11 | COMP | 2020-05-11 | [16 empty] | 2019-03-19 | 2020-03-19 | 2024-03-17 | 2024-03-17 | circuit based plan 2.14 | 2020-05-01 | PIKEENG |  | 254421101 | 18838.4 | 8100.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116956409 | POLE_DECA_REPL - 44189 LITTLE RIVER RD. | 35187929 |  |  | STS-POLE_DECA_REPL - 44189 LITTLE RIVER | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.386 | -119.7146 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216B | 5559 | Y | 311 |  |  | 2021-07-02 06:58 | 2021-07-02 16:58 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103330652 | RELW OH PRI CLR JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-10-12 | COMP | 2020-10-12 | [16 empty] | 2019-04-04 | 2020-04-04 |  | 2020-04-04 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 20321.14 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116961964 | POLE_DECA_REPL - 44189 LITTLE RIVER RD. | 35188051 |  |  | STS-POLE_DECA_REPL - 44189 LITTLE RIVER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3799 | -119.7073 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216B |  | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024431 | RELW OH PRI CLR JPOL REMT ESTR USA FMOB TER2 PRTO | Pole | 2020-10-16 | 2020-10-16 | COMP | 2020-10-16 | [16 empty] | 2019-04-05 | 2020-04-05 |  | 2020-04-05 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 24968.52 | 246.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116962837 | POLE_DECA_REPL - 44189 LITTLE RIVER RD. | 35188136 |  |  | STS-POLE_DECA_REPL - 44189 LITTLE RIVER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3857 | -119.7107 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216B |  | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024334 | RELW OH PRI CLR USA JPOL REMT ESTR FMOB TER2 PRTO | Pole | 2020-09-25 | 2020-10-29 | COMP | 2020-09-24 | [16 empty] | 2019-04-05 | 2020-04-05 |  | 2020-04-05 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 25751.98 | 1640.8 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116963333 | POLE_DECA_REPL - 42930 TROJAN LN.AHWAHNE | 35188149 |  |  | STS-POLE_DECA_REPL - 42930 TROJAN LN.AHW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3726 | -119.7036 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C |  | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103330632 | RELW JPOL OH SERV RESD ESTR USA FMOB TER2 PRTO | Pole | 2020-09-10 | 2020-09-10 | COMP | 2020-09-10 | [16 empty] | 2019-04-05 | 2020-04-05 |  | 2020-04-05 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 3310.16 | 2005 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116963892 | POLE_DECA_REPL - 45748 RD 621/1PN/8PE 5N | 35188180 |  |  | STS-POLE_DECA_REPL - 45748 RD 621/1PN/8P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3699 | -119.7049 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C | 1564 | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | [6 empty] | 51.8 | 51.8 |  |  | 0 | 51.8 | 51.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101023769 | RELW OH PRI CLR JPOL REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-21 | 2020-09-21 | COMP | 2020-09-21 |  |  | 2020-08-14 | 2020-08-14 | [12 empty] | 2019-04-05 | 2020-04-05 |  | 2020-04-05 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 28863.83 | 1592.2 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116967674 | POLE_DECA_REPL - 45748 RD 621/1N/8E/8N 1 | 35188275 |  |  | STS-POLE_DECA_REPL - 45748 RD 621/1N/8E/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.372 | -119.7044 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C |  | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101023827 | RELW OH PRI CLR JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-28 | 2020-09-28 | COMP | 2020-09-28 | [16 empty] | 2019-04-05 | 2020-04-05 |  | 2020-04-05 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 12368.91 | 94.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116967725 | POLE_DECA_REPL - 45748 RD 621/1PN/8PE 7N | 35188281 |  |  | STS-POLE_DECA_REPL - 45748 RD 621/1PN/8P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3711 | -119.7055 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C | 10225 | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101023812 | RELW OH PRI CLR JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-13 | 2020-11-04 | COMP | 2020-10-12 | [16 empty] | 2019-04-05 | 2020-04-05 | 2021-01-30 | 2021-01-30 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 23531.13 | 217.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116969415 | POLE_DECA_REPL - 44189 LITTLE RIVER RD. | 35188357 |  |  | STS-POLE_DECA_REPL - 44189 LITTLE RIVER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3761 | -119.7069 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216B |  | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024436 | RELW OH PRI CLR JPOL REMT ESTR USA FMOB TER2 PRTO | Pole | 2020-11-23 | 2020-12-04 | COMP | 2020-09-25 | [16 empty] | 2019-04-06 | 2020-04-06 |  | 2020-04-06 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 21524.56 | 1698.2 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116971438 | POLE_DECA_REPL - 46946 RD.620 2NAHWAHNEE | 35188443 |  |  | STS-POLE_DECA_REPL - 46946 RD.620 2NAHWA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3868 | -119.6912 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000006216 |  | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024546 | PRI RELW OH CLR JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-10 | 2020-09-10 | COMP | 2020-09-10 | [16 empty] | 2019-04-06 | 2020-04-06 |  | 2020-04-06 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 6288 | 1216.8 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116975342 | POLE_DECA_REPL - 45748 RD 621/ 3SAHWAHNE | 35188639 |  |  | STS-POLE_DECA_REPL - 45748 RD 621/ 3SAHW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3626 | -119.7122 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C |  | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101013167 | RELW OH PRI CLR JPOL REMT ESTR TER2 BTKA USA FMOB PRTO | Pole | 2020-09-28 | 2020-09-28 | COMP | 2020-09-28 | [16 empty] | 2019-04-07 | 2020-04-07 |  | 2020-04-07 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 7199.98 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116975843 | POLE_DECA_REPL - HIGH POINT CIRAHWAHNEE9 | 35188653 |  |  | STS-POLE_DECA_REPL - HIGH POINT CIRAHWAH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3615 | -119.7146 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C | 10658 | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024136 | RELW OH PRI CLR NOAC ESTR USA FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-10-12 | COMP | 2020-10-12 | [16 empty] | 2019-04-07 | 2020-04-07 |  | 2020-04-07 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 14546.23 | 174.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116977216 | POLE_DECA_REPL - 45748 RD 621/ 2S 1WAHWA | 35188668 |  |  | STS-POLE_DECA_REPL - 45748 RD 621/ 2S 1W | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3636 | -119.7131 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C | 10662 | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101023876 | RELW OH PRI CLR JPOL REMT ESTR USA FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-10-15 | COMP | 2020-10-15 | [16 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 23964.52 | 401.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116978571 | POLE_DECA_REPL - 45387 RD.621 1NAHWAHNEE | 35188675 |  |  | STS-POLE_DECA_REPL - 45387 RD.621 1NAHWA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3633 | -119.719 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C | 10225 | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024104 | RELW OH PRI CLR FMOB ESTR BTKA USA TER2 PRTO | Pole | 2020-10-13 | 2020-10-13 | COMP | 2020-10-13 | [16 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 17675.13 | 51.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116981775 | POLE_DECA_REPL - 42068 LONE TREE LN.2N 3 | 35187669 |  |  | STS-POLE_DECA_REPL - 42068 LONE TREE LN. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3639 | -119.7216 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C | 10657 | Y | 311 |  |  | 2021-07-01 05:47 | 2021-07-01 15:47 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024009 | RELW OH PRI NOAC ESTR USA FMOB TER2 PRTO | Pole | 2020-09-16 | 2020-09-16 | COMP | 2020-09-16 | [16 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 21348.79 | 1268.3 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116981846 | POLE_DECA_REPL - 42068 LONE TREE LN.2N 3 | 35187675 |  |  | STS-POLE_DECA_REPL - 42068 LONE TREE LN. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.364 | -119.7212 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C |  | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024010 | RELW OH SEC ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-08 | 2020-09-08 | COMP | 2020-09-08 | [16 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 7066.9 | 1249.3 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116982164 | POLE_DECA_REPL - 42068 LONE TREE LN.AHWA | 35187694 |  |  | STS-POLE_DECA_REPL - 42068 LONE TREE LN. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3603 | -119.7203 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C | 10657 | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024098 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-10-15 | COMP | 2020-10-15 | [16 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 24077.13 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116984633 | POLE_DECA_REPL - 45748 RD 621/ 4SAHWAHNE | 35187761 |  |  | STS-POLE_DECA_REPL - 45748 RD 621/ 4SAHW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3618 | -119.7122 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216C | 10662 | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 51.8 | 51.8 |  |  | 0 | 51.8 | 51.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024160 | RELW ESTR OH PRI USA FMOB TER2 PRTO | Pole | 2020-10-08 | 2020-10-08 | COMP | 2020-10-08 |  |  | 2020-09-28 | 2020-09-28 | [12 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 17766.44 | 251.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116985460 | POLE_BROK_REPL - 1/2 M/E/O HARONY ON OPA | 35187796 |  |  | STS-POLE_BROK_REPL - 1/2 M/E/O HARONY ON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3636 | -119.6935 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216D | 49309 | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101023691 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-10-15 | COMP | 2020-10-15 | [16 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 23665.05 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116986218 | POLE_DECA_REPL - 47380 MIAMI HIGHLANDS 3 | 35187876 |  |  | STS-POLE_DECA_REPL - 47380 MIAMI HIGHLAN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3615 | -119.6919 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216D | 97427 | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101023723 | RELW OH PRI ESTR USA FMOB TER2 PRTO | Pole | 2020-09-09 | 2020-09-09 | COMP | 2020-09-09 | [16 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 37296.05 | 1273.3 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 116986269 | POLE_DECA_REPL - 1/2 M/E/O HARONY ON OPA | 35187888 |  |  | STS-POLE_DECA_REPL - 1/2 M/E/O HARONY ON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3622 | -119.6923 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216D |  | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101023717 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-21 | 2020-09-21 | COMP | 2020-09-21 | [16 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 7148.64 | 1273.3 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AHWAHNEE | Oakhurst |  |  | OPEN | 117194851 | POLE_DECA_REPL - 44745 HWY 49AHWAHNEE936 | 35154628 |  |  | STS-POLE_DECA_REPL - 44745 HWY 49AHWAHNE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3986 | -119.7359 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000006204 | 5546 | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016776 | RELW OH PRI PGEA CLR RESD REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-06-24 | 2020-06-25 | COMP | 2020-06-24 |  |  | 2020-04-02 | 2020-04-02 | [12 empty] | 2019-05-09 | 2020-05-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | PIKEENG |  | 254421101 | 23710.63 | 2180.7 |  |  |  | 1520.2 |  | 1520.2 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | AUBERRY | Oakhurst |  |  | OPEN | 117031403 | POLE_DECA_REPL - 50998 RD210/12PE/7PNAUB | 35177962 |  |  | STS-POLE_DECA_REPL - 50998 RD210/12PE/7P | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0967 | -119.5909 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000010222 |  | Y | 311 |  |  | 2021-03-16 07:00 | 2021-03-16 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 46 | 46 |  |  | 0.5 | 45.5 | 45.5 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101064505 | RELW OH PRI REMT SPCR ESTR FMOB TER2 PRTO FSRP | Pole | 2020-06-05 | 2020-06-16 | COMP | 2020-06-05 | [16 empty] | 2019-04-15 | 2020-04-15 | 2020-08-07 | 2020-08-07 | B-Tag Clean Up 6/8/2020 |  | Bakersfield |  | 252561101 | 16066.04 | 1975.3 | 172.9 | 118.8 | 118.8 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Access/Customer Issue - Unable to gain access | Y | 2020-06-08
Bay/Central | YO | AWAHNEE | Oakhurst |  |  | OPEN | 117186366 | POLE_DECA_REPL - 44261 CROOKS MTN. RD. 2 | 35134235 |  |  | BUNDLE - 4 POLES - AHWAHNEE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.3946 | -119.74 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000006204 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016523 | RELW OH PRI PGEA CLR RESD REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28467 | 2021-03-31 | TRC |  | 254421101 | 1 |  | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
Bay/Central | YO | BEAR VALLEY | Mariposa |  |  | OPEN | 117077781 | POLE_DECA_REPL - 8022 HUNTERS VALLEY RD | 35209657 |  |  | STS-POLE_DECA_REPL - 8022 HUNTERS VALLEY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.6078 | -120.2 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004161 | 4594 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101078230 | RELW OH PRI CLR RESD REMT NOAC ESTR PROG FSRP FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-22 | 2020-04-22 | 2020-12-03 | 2020-12-03 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BEAR VALLEY | Mariposa |  |  | OPEN | 117077815 | POLE_DECA_REPL - 8015 HUNTERS VALLEY RD | 35215577 |  |  | STS-POLE_DECA_REPL - 8015 HUNTERS VALLEY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.6012 | -120.1971 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004161 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101078118 | RELW OH SERV REMT NOAC CGI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-22 | 2020-04-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BEAR VALLEY | Mariposa |  |  | OPEN | 117077816 | POLE_DECA_REPL - 7999 HUNTERS VALLEYBEAR | 35215600 |  |  | STS-POLE_DECA_REPL - 7999 HUNTERS VALLEY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.6011 | -120.1964 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004161 | 4594 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101078107 | RELW OH PRI RESD REMT NOAC ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-22 | 2020-04-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BEAR VALLEY | Mariposa |  |  | OPEN | 117077821 | POLE_DECA_REPL - 7972 HUNTERS VALLEY RD | 35215603 |  |  | STS-POLE_DECA_REPL - 7972 HUNTERS VALLEY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.603 | -120.1959 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004161 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101078128 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-22 | 2020-04-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BEAR VALLEY | Mariposa |  |  | OPEN | 117084501 | POLE_DECA_REPL - 7915 HUNTERS VALLEY RD | 35214571 |  |  | STS-POLE_DECA_REPL - 7915 HUNTERS VALLEY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5968 | -120.1966 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004161 | 4594 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101078152 | RELW OH PRI REMT NOAC ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-23 | 2020-04-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BEAR VALLEY | Mariposa |  |  | OPEN | 117343050 | POLE_DECA_REPL - 8103 HUNTERS VALLEY 4PS | 35215795 |  |  | STS-POLE_DECA_REPL - 8103 HUNTERS VALLEY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.6044 | -120.2058 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004162 | 4594 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101078261 | RELW OH PRI CLR REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-30 | 2020-05-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BEAR VALLEY | Mariposa |  |  | OPEN | 117077813 | POLE_DECA_REPL - 8015 HUNTERS VALLEY RD | 35105875 |  |  | STS-POLE_DECA_REPL - 8015 HUNTERS VALLEY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.6014 | -120.1983 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004161 | 4594 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101078115 | RELW OH PRI REMT NOAC ESTR GO REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-11 | 2020-12-11 | COMP | 2020-12-11 | [16 empty] | 2019-04-22 | 2019-10-22 | 2020-09-04 | 2020-09-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | 25763.23 |  | -506.8 | -325.8 | -325.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BEAR VALLEY | Mariposa |  |  | OPEN | 117084526 | POLE_DECA_REPL - 7887 HUNTERS VALLEY RDB | 35209665 |  |  | STS-POLE_DECA_REPL - 7887 HUNTERS VALLEY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5983 | -120.1885 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004161 |  | Y | 311 |  |  | 2021-06-29 07:00 | 2021-06-29 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101078058 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-10 | 2020-12-10 | COMP | 2020-12-10 | [16 empty] | 2019-04-23 | 2020-04-23 | 2020-09-28 | 2020-09-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | 11610.67 | 127.5 | -724 | -362 | -362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116755082 | POLE_DECA_REPL - 5049 COLE RD 3PN/2PWBOO | 35214990 |  |  | STS-POLE_DECA_REPL - 5049 COLE RD 3PN/2P | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4679 | -119.8885 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A | 10505 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101088260 | RELW OH PRI RESD COMM REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116756748 | POLE_DECA_REPL - AMELIA/SPRING 1PE/6PNBO | 35214999 |  |  | STS-POLE_DECA_REPL - AMELIA/SPRING 1PE/6 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4707 | -119.8948 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A | 23686 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101088280 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116759519 | POLE_DECA_REPL - AMELIA/SPRING 3PEBOOTJA | 35082345 |  |  | STS-POLE_DECA_REPL - AMELIA/SPRING 3PEBO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.4662 | -119.8929 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087089 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2019-09-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | Fresno |  | 254452102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116761170 | POLE_DECA_REPL - 4040 AMELIA 2PE/1PSEBOO | 35082351 |  |  | STS-POLE_DECA_REPL - 4040 AMELIA 2PE/1PS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.4658 | -119.895 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51 | 51 |  |  | 1 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087080 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2019-09-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | Fresno |  | 254452102 | 1 | 187.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116761917 | POLE_DECA_REPL - 4045 SEBASTOPOL RD 2PNE | 35215024 |  |  | STS-POLE_DECA_REPL - 4045 SEBASTOPOL RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4614 | -119.8961 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A | 9590 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087336 | OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116761953 | POLE_DECA_REPL - 4039 SEBASTOPOL 1PSE/1P | 35215029 |  |  | STS-POLE_DECA_REPL - 4039 SEBASTOPOL 1PS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.461 | -119.8954 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A | 11947 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087342 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116762753 | POLE_DECA_REPL - STREETER MTN RD W/O HWY | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 37.4537 | -119.8675 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005195 | 4562 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085395 | REGW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-03-19 | 2020-03-19 |  | 2020-03-19 | 2021 CBP Plan |  | UNASSIGNED |  | 254452102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116764483 | POLE_DECA_REPL - 4047 SEBASTOPOLBOOTJACK | 35215084 |  |  | STS-POLE_DECA_REPL - 4047 SEBASTOPOLBOOT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4607 | -119.897 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A | 9590 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087339 | RELW OH PRI RESD REMT ESTR PRTO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116764552 | POLE_DECA_REPL - 4046 SEBASTOPOL RDBOOTJ | 35215090 |  |  | STS-POLE_DECA_REPL - 4046 SEBASTOPOL RDB | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4612 | -119.8975 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087340 | RELW OH PRI RESD REMT ESTR GO BTKA FMOB FSRP TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116764734 | POLE_DECA_REPL - 4060 SEBASTOPOL/2PN BOO | 35215095 |  |  | STS-POLE_DECA_REPL - 4060 SEBASTOPOL/2PN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4616 | -119.898 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A | 23685 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087366 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116765773 | POLE_BROK_REPL - 4045 SEBASTOPOL RD 1PNE | 35215105 |  |  | STS-POLE_BROK_REPL - 4045 SEBASTOPOL RD | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.461 | -119.8967 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101087337 | RELW OH PRI RESD REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116767411 | POLE_DECA_REPL - C/O MOONSHADOW/STREETER | 35208848 |  |  | STS-POLE_DECA_REPL - C/O MOONSHADOW/STRE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4494 | -119.8751 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005195 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085451 | RELW OH PRI PGEA CLR REMT FIRE ESTR GO BTKA OTHR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2020-08-31 | 2020-08-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116767490 | POLE_DECA_REPL - 4840 MOONSHADOW/1NBOOTJ | 35215135 |  |  | STS-POLE_DECA_REPL - 4840 MOONSHADOW/1NB | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4489 | -119.8752 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005195 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085452 | RELW OH PRI PGEA REMT FIRE ESTR BTKA OTHR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116788087 | POLE_DECA_REPL - MOONSHADOW AT 4840BOOTJ | 35215146 |  |  | STS-POLE_DECA_REPL - MOONSHADOW AT 4840B | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.448 | -119.8749 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005195 | 4562 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085453 | RELW OH PRI PGEA CLR REMT FIRE ESTR BTKA OTHR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116790934 | POLE_DECA_REPL - 4899 HIDDEN SPRINGS RD/ | 35215186 |  |  | STS-POLE_DECA_REPL - 4899 HIDDEN SPRINGS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4549 | -119.8744 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005195 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085768 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116791247 | POLE_DECA_REPL - E/O 5005 BOYER RDBOOTJA | 35208868 |  |  | STS-POLE_DECA_REPL - E/O 5005 BOYER RDBO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.4589 | -119.8685 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005195 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.1 | 34.7 | 2.4 |  | 0 | 37.1 | 34.7 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085785 | RELW OH PRI REMT TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-04 |  | COMP | 2021-01-04 | [16 empty] | 2019-03-20 | 2020-03-20 | 2020-10-10 | 2020-10-10 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 15230.59 | 249.8 | 236.4 | 1761 | 1761 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116792259 | POLE_DECA_REPL - 3935A BOOTJACK LN.2PE/1 | 35215206 |  |  | STS-POLE_DECA_REPL - 3935A BOOTJACK LN.2 | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.464 | -119.887 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101088247 | RELW SERV OH PGEA REMT FIRE ESTR BTKA OTHR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116794029 | POLE_DECA_REPL - 5049 COLE RD 1PNBOOTJAC | 35215233 |  |  | STS-POLE_DECA_REPL - 5049 COLE RD 1PNBOO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.4672 | -119.8872 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101088255 | RELW OH PRI PGEA CLR RESD FIRE TRAF FLAG ESTR BTKA OTHR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116794214 | POLE_DECA_REPL - 5049 COLE RD 3PNBOOTJAC | 35215239 |  |  | STS-POLE_DECA_REPL - 5049 COLE RD 3PNBOO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.468 | -119.8876 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101088258 | RELW OH PRI PGEA CLR COMM FIRE ESTR BTKA OTHR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116796765 | POLE_DECA_REPL - 3815A HWY49BOOTJACK | 35208887 |  |  | STS-POLE_DECA_REPL - 3815A HWY49BOOTJACK | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4601 | -119.8791 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005195 | 4565 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101086373 | RELW OH PRI REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2020-10-18 | 2020-10-18 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116802854 | POLE_DECA_REPL - SW/O 5104 DARRAH RDBOOT | 35215253 |  |  | STS-POLE_DECA_REPL - SW/O 5104 DARRAH RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4679 | -119.8815 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B | 4567 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084441 | RELW OH PRI PGEA CLR REMT FIRE ESTR BTKA OTHR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116804907 | POLE_DECA_REPL - HWY49 2NE/O 3836BOOTJAC | 35215310 |  |  | STS-POLE_DECA_REPL - HWY49 2NE/O 3836BOO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.461 | -119.8782 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B | 4565 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084646 | RELW OH PRI REMT ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116804935 | POLE_DECA_REPL - R/O 5127 COLE RDBOOTJAC | 35215315 |  |  | STS-POLE_DECA_REPL - R/O 5127 COLE RDBOO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4717 | -119.8862 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084394 | RELW OH SERV PGEA REMT FIRE ESTR OTHR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116805608 | POLE_DECA_REPL - COLE RD A/F MB5142BOOTJ | 35215325 |  |  | STS-POLE_DECA_REPL - COLE RD A/F MB5142B | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.4731 | -119.8871 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084284 | RELW OH PRI PGEA REMT FIRE TRAF ESTR BTKA OTHR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116805676 | POLE_BROK_REPL - W/O 3840 HWY49 BOOTJACK | 35215330 |  |  | STS-POLE_BROK_REPL - W/O 3840 HWY49 BOOT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4643 | -119.8783 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101084629 | RELW OH SEC REMT ESTR GO FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116807416 | POLE_DECA_REPL - #1 SW/O 3896 BOOTJACK L | 35208907 |  |  | STS-POLE_DECA_REPL - #1 SW/O 3896 BOOTJA | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.4624 | -119.8803 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084622 | RELW OH PRI REMT NOAC FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 1 | 13.5 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116810603 | POLE_DECA_REPL - A/F 5128 DARRAH RD/1SWB | 35215400 |  |  | STS-POLE_DECA_REPL - A/F 5128 DARRAH RD/ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4697 | -119.881 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B | 4567 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084437 | RELW OH PRI PGEA REMT FIRE NOAC ESTR OTHR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116810651 | POLE_DECA_REPL - 3861 HWY49BOOTJACK | 35208927 |  |  | STS-POLE_DECA_REPL - 3871 HWY49BOOTJACK | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 37.4625 | -119.882 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B | 4565 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084615 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2020-10-02 | 2020-10-02 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 1 | 787.3 | 773.8 | 1873.8 | 1873.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116813728 | POLE_DECA_REPL - 5150 BOYER RDBOOTJACK | 35215494 |  |  | STS-POLE_DECA_REPL - 5150 BOYER RDBOOTJA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4701 | -119.8783 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084455 | RELW OH SERV PGEA REMT FIRE NOAC ESTR OTHR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116822135 | POLE_DECA_REPL - ENTRANCE TO 4929 MEADOW | 35214681 |  |  | STS-POLE_DECA_REPL - ENTRANCE TO 4929 ME | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4732 | -119.8659 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084551 | RELW OH PRI PGEA REMT FIRE ESTR BTKA OTHR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116860399 | POLE_DECA_REPL - 3386 WODLAND DR/2WBOOTJ | 35209313 |  |  | STS-POLE_DECA_REPL - 3386 WODLAND DR/2WB | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4526 | -119.8493 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085012 | RELW OH PRI CLR REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2020-09-25 | 2020-09-25 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 1 | 13.5 | 0 | 1426 | 1426 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116860400 | POLE_DECA_REPL - A/F 3834 BROOKS RD/1NE/ | 35215088 |  |  | STS-POLE_DECA_REPL - A/F 3834 BROOKS RD/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4507 | -119.8531 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195D | 4562 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084916 | OH PRI CLR REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116860401 | POLE_DECA_REPL - 3386 WOODLAND DR/2W/3NB | 35215094 |  |  | STS-POLE_DECA_REPL - 3386 WOODLAND DR/2W | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4555 | -119.8493 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085023 | RELW OH PRI CLR REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116860402 | POLE_DECA_REPL - A/F 3834 BROOKS RD/1NE/ | 35215100 |  |  | STS-POLE_DECA_REPL - A/F 3834 BROOKS RD/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4515 | -119.8536 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084906 | RELW OH PRI CLR REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 53.8 | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116860403 | POLE_DECA_REPL - 3386 WOODLAND DR/2W/4NB | 35215104 |  |  | STS-POLE_DECA_REPL - 3386 WOODLAND DR/2W | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4566 | -119.8493 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085024 | RELW OH PRI CLR REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116860410 | POLE_DECA_REPL - WOODLAND DR E/O BROOKS | 35209318 |  |  | STS-POLE_DECA_REPL - WOODLAND DR E/O BRO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.4504 | -119.8506 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.3 | 21.3 |  |  | 0 | 21.3 | 21.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084932 | RELW OH PRI PUBL TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-29 |  | COMP | 2020-12-29 | [16 empty] | 2019-03-28 | 2020-03-28 | 2020-09-25 | 2020-09-25 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 11904.27 |  | 0 | 1371.3 | 1371.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116860411 | POLE_DECA_REPL - 3386 WOODLAND DR/1SBOOT | 35215112 |  |  | STS-POLE_DECA_REPL - 3386 WOODLAND DR/1S | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4522 | -119.8479 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195D | 4681 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085006 | RELW OH PRI CLR REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 735 | 735 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116860412 | POLE_DECA_REPL - 3386 WOODLAND DR/1WBOOT | 35215118 |  |  | STS-POLE_DECA_REPL - 3386 WOODLAND DR/1W | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4528 | -119.8489 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085010 | RELW OH PRI REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116860414 | POLE_DECA_REPL - WOODLAND SCHOOL/2NBOOTJ | 35084398 |  |  | STS-POLE_DECA_REPL - WOODLAND SCHOOL/2NB | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4521 | -119.8498 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103093853 | RELW OH PRI CLR REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 |  | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 117323670 | POLE_DECA_REPL - 5649 COLE RDBOOTJACK | 35108874 |  |  | STS-POLE_DECA_REPL - 5649 COLE RDBOOTJAC | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.494 | -119.8702 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 0000005194 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101078979 | RELW OH NOAC PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-30 |  | COMP | 2020-12-30 | [16 empty] | 2019-05-26 | 2019-11-26 | 2020-12-04 | 2020-12-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452101 | 18112.19 | 83.9 | -380.1 | -153.8 | -153.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116753273 | POLE_DECA_REPL - 5154 ALLRED 2PE/4PNEBOO | 35082986 |  |  | STS-POLE_DECA_REPL - 5154 ALLRED 2PE/4PN | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4707 | -119.9109 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05196A |  | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | [6 empty] | 17.8 | 17.8 |  |  | 0 | 17.8 | 17.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087891 | RELW OH PRI REMT NOAC ESTR TER2 BTKA RTRN FMOB PRTO FSRP | Pole | 2020-05-28 | 2020-05-28 | COMP | 2020-05-28 | [16 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | Program Manager | 2020-05-20 | TRC |  | 254452101 | 6568.25 | 11193.4 | 1250.6 | 1250.6 | 1250.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116757402 | POLE_DECA_REPL - AMELIA/SPRING 1PE/3PNBO | 35082991 |  |  | STS-POLE_DECA_REPL - AMELIA/SPRING 1PE/3 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.468 | -119.8947 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.5 | 26.5 |  |  | 0 | 26.5 | 26.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101088275 | RELW OH PRI RESD REMT ESTR BTKA RTRN FMOB TER2 PRTO FSRP | Pole | 2021-01-29 | 2021-01-29 | COMP | 2021-01-29 | [16 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 9547.77 | 118.2 | 118.2 | 1420.2 | 1420.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116757564 | POLE_DECA_REPL - 5111 SILVA 3PW BOOTJACK | 35208812 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4672 | -119.9027 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A |  | Y | 311 |  |  | 2021-03-03 05:35 | 2021-03-03 13:06 | Scheduled | CLICK | [6 empty] | 2.4 |  | 2.4 |  | 0 | 2.4 |  | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087224 | RELW OH PRI CLR RESD REMT NOAC TER2 CGI ESTR FMOB PRTO FSRP | Pole | 2021-01-20 | 2021-01-20 | COMP | 2021-01-20 | [16 empty] | 2019-03-18 | 2020-03-18 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 11403.56 | 1014.4 | 925 | 1426 | 1426 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116764600 | POLE_DECA_REPL - WILDWOOD DR A/F 4895BOO | 35083002 |  |  | STS-POLE_DECA_REPL - WILDWOOD DR A/F 489 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4521 | -119.8745 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005195 | 4562 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 46.9 | 46.9 |  |  | 0 | 46.9 | 46.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085467 | RELW OH PRI PGEA REMT FIRE ESTR GO BTKA OTHR FMOB TER2 PRTO FSRP | Pole | 2021-01-25 | 2021-01-25 | COMP | 2021-01-25 | [16 empty] | 2019-03-19 | 2020-03-19 | 2020-08-31 | 2020-08-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 20705.69 | 348 | 348 | 348 | 348 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116793375 | POLE_DECA_REPL - R/O 5060 COLE RDBOOTJAC | 35084359 |  |  | STS-POLE_DECA_REPL - R/O 5060 COLE RDBOO | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4673 | -119.8862 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 51.6 | 51.6 |  |  | 0 | 51.6 | 51.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084268 | RELW OH PRI PGEA CLR COMM FIRE ESTR BTKA OTHR FMOB TER2 PRTO FSRP | Pole | 2021-02-04 | 2021-02-04 | COMP | 2021-02-03 | [16 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 19889.8 |  | 0 | 1092 | 1092 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116808518 | POLE_DECA_REPL - 5103 DARRAH RD BOOTJACK | 35208922 |  |  | STS-POLE_DECA_REPL - 5103 DARRAH RD BOOT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4689 | -119.8819 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B | 4567 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.8 | 33.8 |  |  | 0 | 33.8 | 33.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084434 | RELW OH PRI PGEA REMT FIRE ESTR BTKA OTHR FMOB TER2 PRTO FSRP | Pole | 2021-01-26 | 2021-01-26 | COMP | 2021-01-26 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-10-02 | 2020-10-02 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 13458.67 | 1260.5 | 1247 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116822360 | POLE_DECA_REPL - 4945 MEADOW VIEW DR/1WB | 35209010 |  |  | STS-POLE_DECA_REPL - 4945 MEADOW VIEW DR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4753 | -119.8658 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05194C | 10582 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 58.6 | 56 | 2.6 |  | 0 | 58.6 | 56 | 2.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084556 | RELW PRI OH PGEA CLR REMT FIRE ESTR OTHR REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-01-20 | COMP | 2021-01-20 | [16 empty] | 2019-03-24 | 2020-03-24 | 2020-10-10 | 2020-10-10 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 21590.72 | 13.5 | 0 | 1589 | 1589 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116860407 | POLE_DECA_REPL - WOODLAND SCHOOL/1NBOOTJ | 35215109 |  |  | STS-POLE_DECA_REPL - WOODLAND SCHOOL/1NB | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4514 | -119.85 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195D | 4681 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.6 | 39.6 |  |  | 0 | 39.6 | 39.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103093852 | RELW OH PRI REMT FIRE ESTR BTKA FMOB FSRP PRTO TER2 | Pole | 2021-02-02 | 2021-02-02 | COMP | 2021-02-02 | [16 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 17702.21 | 242.2 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116860415 | POLE_DECA_REPL - R/O 5286 ITALIAN CR.RD/ | 35215123 |  |  | STS-POLE_DECA_REPL - R/O 5286 ITALIAN CR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4592 | -119.8481 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.3 | 14.3 |  |  | 0 | 14.3 | 14.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085089 | RELW OH PRI CLR REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-02 | 2021-02-02 | COMP | 2021-02-02 | [16 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 6761.86 | 53.8 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 117319579 | POLE_DECA_REPL - NW C/O DEER SPRING RD/D | 35209690 |  |  | STS-POLE_DECA_REPL - NW C/O DEER SPRING | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.493 | -119.8559 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005194 | 88295 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.7 | 32.7 |  |  | 0 | 32.7 | 32.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101078760 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 | 2021-01-28 | COMP | 2021-01-28 | [16 empty] | 2019-05-25 | 2020-05-25 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 13502.74 | 89.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116762326 | POLE_DECA_REPL - TAVIS RD/1ST POLE INSID | 35208821 |  |  | STS-POLE_DECA_REPL - TAVIS RD/1ST POLE I | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4553 | -119.8656 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005195 | 4562 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.6 | 42.6 |  |  | 0 | 42.6 | 42.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085361 | RELW OH PRI COMM REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-31 | 2020-12-31 | COMP | 2020-12-31 | [16 empty] | 2019-03-19 | 2020-03-19 | 2020-08-31 | 2020-08-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 18299.92 | 13.5 | 0 | 1224 | 1224 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 116860388 | POLE_DECA_REPL - 3386 WOODLAND DR/2W/1NB | 35083625 |  |  | STS-POLE_DECA_REPL - 3386 WOODLAND DR/2W | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4538 | -119.8494 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195D |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085021 | RELW OH PRI CLR REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-02 | 2020-12-02 | COMP | 2020-12-02 | [16 empty] | 2019-03-28 | 2020-03-28 | 2020-09-25 | 2020-09-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 9708.86 | 40.4 | -181 | -90.5 | -90.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BOOTJACK | Mariposa |  |  | OPEN | 117323668 | POLE_DECA_REPL - 5639 DARRAH RD/1PWBOOTJ | 35154363 |  |  | STS-POLE_DECA_REPL - 5639 DARRAH RD/1PWB | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4967 | -119.86 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 0000005194 |  | Y | 311 |  |  | 2021-06-29 07:00 | 2021-06-29 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101078956 | RELW OH PRI CLR RESD REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-08-19 | 2020-08-19 | COMP | 2020-08-19 | [16 empty] | 2019-05-26 | 2020-05-26 | 2020-08-18 | 2020-08-18 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254452101 | 16664.17 | 670.6 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BUCK MEADOWS | Sonora |  |  | OPEN | 116867612 | POLE_DECA_REPL - NE\OF\ENT\TO\2755 HWY 1 | 35188563 |  |  | STS-POLE_DECA_REPL - NE\OF\ENT\TO\2755 H | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.8202 | -120.0245 |  | TIER 2 | 72 | 16335-1703, CURTIS | X42 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.4 | 23.4 |  |  | 0 | 23.4 | 23.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101038393 | OH RELW PRI REMT ESTR REAR FMOB TER2 PRTO | Pole | 2020-09-09 |  | COMP | 2020-09-09 | [16 empty] | 2019-03-29 | 2020-03-29 |  | 2020-03-29 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 12580.89 | 495.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BUCK MEADOWS | Sonora |  |  | OPEN | 116873917 | POLE_BROK_REPL - W\OF\HS\11488 CHERRY LA | 35188598 |  |  | STS-POLE_BROK_REPL - SE OF HE 11401 CHER | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.8263 | -120.0072 |  | TIER 2 | 72 | 16335-1703, CURTIS | X42 | 2579 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 68.4 | 67.3 | 1.1 |  | 0 | 68.4 | 67.3 | 1.1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 103109936 | RELW OH PRI BTKA CLR FLAG ESTR USA FMOB TER2 PRTO | Pole | 2020-10-12 |  | COMP | 2020-10-12 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-03-30 | 2020-03-30 |  | 2020-03-30 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 38727.88 | 320.2 | 320.2 | 320.2 | 320.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BUCK MEADOWS | Sonora |  |  | OPEN | 116870253 | POLE_BURN_REPL - 7647 HWY 120 1PS\20PEBU | 35188579 |  |  | STS-POLE_BURN_REPL - 7647 HWY 120 1PS\20 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8196 | -120.0281 |  | TIER 2 | 72 | 16335-1703, CURTIS | X42 | 2579 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 75.5 | 74.7 | 0.8 |  | 0 | 75.5 | 74.7 | 0.8 |  | EC | E | Pole | Burnt | Replace |  | 101038379 | OH PRI CLR REMT NOAC ESTR USA FMOB TER2 PRTO RELW | Pole | 2020-09-14 | 2020-11-13 | COMP | 2020-09-14 | [16 empty] | 2019-03-29 | 2020-03-29 |  | 2020-03-29 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 31732.62 | 715 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BUCK MEADOWS | Sonora |  |  | OPEN | 116873919 | POLE_BURN_REPL - S\OF\ENT\TO\27997\HWY 1 | 35188602 |  |  | STS-POLE_BURN_REPL - S\OF\ENT\TO\27997\H | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8238 | -120.0186 |  | TIER 2 | 72 | 16335-1703, CURTIS | X42 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 30.7 | 30.7 |  |  | 0 | 30.7 | 30.7 |  |  | EC | E | Pole | Burnt | Replace |  | 101038426 | RELW OH PRI CLR REMT NOAC ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-09-11 | 2020-11-05 | COMP | 2020-09-11 | [16 empty] | 2019-03-30 | 2020-03-30 |  | 2020-03-30 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 15384.71 | 2854.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | BUCK MEADOWS | Sonora |  |  | OPEN | 116873923 | POLE_BROK_REPL - W\OF\HS\11488 CHERRY LA | 35083081 |  |  | STS-POLE_BROK_REPL - W\OF\HS\11488 CHERR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.829 | -120.003 |  | TIER 2 | 72 | 16335-1703, CURTIS | X43 | 2579 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 89 | 89 |  |  | 0 | 89 | 89 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101038445 | RELW OH PRI GO CLR REMT ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-05-20 | 2020-07-30 | COMP | 2020-05-20 | [16 empty] | 2019-03-30 | 2019-09-30 |  | 2019-09-30 | circuit based plan 2.14 | 2020-05-31 | TRC |  | 163351703 | 17105.32 | 5048.2 |  |  |  | 88.7 |  | 88.7 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | BUCK MEDDOWS | Sonora |  |  | OPEN | 116872354 | POLE_BURN_REPL - W\OF\ENT\30840\HARDEN F | 35188583 |  |  | STS-POLE_BURN_REPL - W\OF\ENT\30840\HARD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8241 | -119.963 |  | TIER 2 | 72 | 16335-1703, CURTIS | X44 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.2 | 28.2 |  |  | 0 | 28.2 | 28.2 |  |  | EC | E | Pole | Burnt | Replace |  | 101038565 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-09-14 | 2020-09-24 | COMP | 2020-09-11 | [16 empty] | 2019-03-30 | 2020-03-30 |  | 2020-03-30 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 22766.86 | 890.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 116811371 | POLE_DECA_REPL - 2821 HWY 140 12PNE/1PSE | 35208932 |  |  | STS-POLE_DECA_REPL - 2821 HWY 140 12PNE/ | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land Enviro |  |  | 37.4442 | -120.0758 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000006171 | 10349 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101069549 | RELW OH PRI PGEA REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-19 |  | COMP | 2021-02-19 | [16 empty] | 2019-03-22 | 2020-03-22 | 2020-10-07 | 2020-10-07 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192101 | 25908.96 | 742.2 | 728.7 | 391.5 | 391.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 116813125 | POLE_BROK_REPL - 1PS/E 2866 OLD HWY/NIFC | 35208938 |  |  | STS-POLE_BROK_REPL - 1PS/E 2866 OLD HWY/ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4035 | -120.0605 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000006174 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103090976 | RELW OH PRI REMT ESTR BTKA FSRP FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2020-09-13 | 2020-09-13 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 116815296 | POLE_DECA_REPL - 2718 HWY 140 2PNE/1PSEC | 35215572 |  |  | STS-POLE_DECA_REPL - 2718 HWY 140 2PNE/1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 37.4353 | -120.0923 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000006171 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101069654 | OH PRI PGEA RESD REMT FIRE ESTR BTKA TER2 RELW USA FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 522.5 | -119.6 | 957.4 | 957.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 116822656 | POLE_DECA_REPL - HORNITOS RD/HWY 140 3PN | 35209041 |  |  | STS-POLE_DECA_REPL - HORNITOS RD/HWY 140 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4326 | -120.0965 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000006171 | 10349 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101069675 | RELW OH PRI PGEA REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 |  | 2020-03-24 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 116822937 | POLE_BROK_REPL - 1PN OLD HWY/SCHOOL HOUS | 35214719 |  |  | STS-POLE_BROK_REPL - 1PN OLD HWY/SCHOOL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.4084 | -120.0853 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 06174B | 4548 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101068943 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2019-08-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 116822991 | POLE_BROK_REPL - 2PN OLD HWY/SCHOOL HOUS | 35214723 |  |  | STS-POLE_BROK_REPL - 2PN OLD HWY/SCHOOL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.4093 | -120.0853 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 06174B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101068945 | RELW OH PRI REMT ESTR BTKA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 53.8 | -1092.6 | -32.6 | -32.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 116824289 | POLE_BROK_REPL - AT 2392 OLD HWY RD 2PNC | 35214738 |  |  | STS-POLE_BROK_REPL - AT 2392 OLD HWY RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4074 | -120.0985 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 06174B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103341206 | RELW OH PRI REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-25 | 2020-03-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 116824396 | POLE_BROK_REPL - 1PN 2392 OLD HWYCATHEYS | 35214743 |  |  | STS-POLE_BROK_REPL - 1PN 2392 OLD HWYCAT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4072 | -120.0986 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 06174B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101069238 | RELW OH PRI REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-25 | 2020-03-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 116825757 | POLE_DECA_REPL - 3217 HWY 140 1PW/5PN/1P | 35209087 |  |  | STS-POLE_DECA_REPL - 3217 HWY 140 1PW/5P | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.4623 | -120.0735 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000005175 | 670373 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.7 | 41.4 | 1.3 |  | 0 | 42.7 | 41.4 | 1.3 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101019509 | RELW OH PRI JPOL FIRE NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2021-02-16 |  | COMP | 2021-02-16 | [16 empty] | 2019-03-25 | 2020-03-25 | 2020-08-08 | 2020-08-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192101 | 20720.31 | 364.1 | 350.7 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 116846888 | POLE_DECA_REPL - 2PN/E 1PS 3946 HWY140CA | 35214904 |  |  | STS-POLE_DECA_REPL - 2PN/E 1PS 3946 HWY1 | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4763 | -120.0323 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000005183 | 4618 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087756 | RELW OH PRI PGEA CLR RESD REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 116847320 | POLE_DECA_REPL - 4983 YAQUI GULCHCATHEYS | 35209222 |  |  | STS-POLE_DECA_REPL - 4983 YAQUI GULCHCAT | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.4791 | -120.0104 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000005183 | 427365 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087613 | OH PRI PGEA CLR RESD REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2020-09-27 | 2020-09-27 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 116860623 | POLE_DECA_REPL - N/O M/B 4034 OLD HIGHWA | 35215128 |  |  | STS-POLE_DECA_REPL - N/O M/B 4034 OLD HI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4283 | -120.0043 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103341186 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -945 | 115 | 115 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 116878050 | POLE_BROK_REPL - 4132 WILBURS WAYCATHEYS | 35215566 |  |  | STS-POLE_BROK_REPL - 4132 WILBURS WAYCAT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4335 | -120.011 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A | 10388 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103837931 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -945 | 115 | 115 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 116878092 | POLE_BROK_REPL - AT 4136 WILBERS WAYCATH | 35215576 |  |  | STS-POLE_BROK_REPL - AT 4136 WILBERS WAY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.4342 | -120.0103 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103341192 | RELW OH PRI REMT ESTR BTKA FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 53.8 | -945 | 115 | 115 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 116822700 | POLE_BROK_REPL - 2PW 2589 OLD HWYCATHEYS | 35214703 |  |  | STS-POLE_BROK_REPL - 2PW 2589 OLD HWYCAT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.41 | -120.0845 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 06174B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 20.6 | 20.6 |  |  | 0 | 20.6 | 20.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101068960 | RELW OH PRI REMT SWRK ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-28 | 2021-02-01 | COMP | 2021-01-28 | [16 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 8533.68 | 100.5 | -123 | 969 | 969 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CATHEYS VALLEY | Mariposa |  |  | OPEN | 117160829 | POLE_DECA_REPL - 95306CATHEYS VALLEY9530 | 35209171 |  |  | STS-POLE_DECA_REPL - 95306CATHEYS VALLEY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4245 | -120.1019 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000006171 |  | Y | 311 |  |  | 2021-06-29 07:00 | 2021-06-29 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103370917 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-22 | 2020-12-22 | COMP | 2020-12-22 | [16 empty] | 2019-05-04 | 2020-05-04 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | 6835.1 | 943.5 | 930.1 | 271.5 | 271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSE GOLD. | Oakhurst |  |  | OPEN | 117270417 | POLE_BROK_REPL - 32044 DELAWARE RD 1PW 1 | 35209263 |  |  | STS-POLE_BROK_REPL - 32044 DELAWARE RD 1 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2151 | -119.682 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821216 | 10536 | Y | 311 |  |  |  |  | Scheduled | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 61.2 | 61.2 | 0 |  | 0 | 61.2 | 61.2 | 0 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101060870 | RELW OH PRI RESD REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-12 | 2021-01-12 | COMP | 2021-01-12 | [16 empty] | 2019-05-18 | 2019-11-18 | 2020-09-05 | 2020-09-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 29536.29 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Madera |  |  | OPEN | 117324073 | POLE_DECA_REPL - 44794 RD 415 COARSEGOLD | 35215723 |  |  | STS-POLE_DECA_REPL - 44794 RD 415 COARSE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2457 | -119.7304 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820125 | 5677 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101053815 | RELW OH PRI PGEA RESD FIRE FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-26 | 2020-05-26 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116810639 | POLE_DECA_REPL - 42775 ELLERBROCK STATIO | 35215405 |  |  | STS-POLE_DECA_REPL - 42775 ELLERBROCK ST | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2701 | -119.7687 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101054149 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 503.5 | 490 | 490 | 490 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116810961 | POLE_DECA_REPL - 42775 ELLERBROCK STATIO | 35215424 |  |  | STS-POLE_DECA_REPL - 42775 ELLERBROCK ST | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2658 | -119.7662 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 | 10607 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101054140 | RELW OH PRI REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116815107 | POLE_DECA_REPL - 42636 BEAN GULCH RD/1PN | 35215562 |  |  | STS-POLE_DECA_REPL - 42636 BEAN GULCH RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2444 | -119.7707 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101054710 | RELW OH SERV NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116820281 | POLE_DECA_REPL - 43611 FRANKLIN RD/1PSWC | 35214631 |  |  | STS-POLE_DECA_REPL - 43611 FRANKLIN RD/1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2668 | -119.7523 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101053097 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116821603 | POLE_DECA_REPL - A/F 35725 FRANKLIN RD/1 | 35214659 |  |  | STS-POLE_DECA_REPL - A/F 35725 FRANKLIN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2701 | -119.7502 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101053129 | RELW OH PRI ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116821735 | POLE_DECA_REPL - A/F 35725 FRANKLIN RD/2 | 35214664 |  |  | STS-POLE_DECA_REPL - A/F 35725 FRANKLIN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2698 | -119.751 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 | 735111 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101053133 | RELW OH PRI REMT ESTR REAR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116821898 | POLE_BROK_REPL - 35877 WELLS RD COARSEGO | 35214668 |  |  | STS-POLE_BROK_REPL - 35877 WELLS RD COAR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2701 | -119.7371 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 | 6288 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101053047 | RELW OH PRI CLR NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116822456 | POLE_DECA_REPL - 35863 CHART WELL RDCOAR | 35209015 |  |  | STS-POLE_DECA_REPL - 35863 CHART WELL RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2699 | -119.747 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101053142 | RELW OH PRI CLR NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116822878 | POLE_DECA_REPL - 35879 FRANKLIN RDCOARSE | 35209046 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2705 | -119.7487 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 | 735111 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101053157 | RELW OH PRI CLR FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116828184 | POLE_DECA_REPL - 43941 TRABUCO RDCOARSEG | 35209126 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2576 | 119.7458 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 | 10609 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101053277 | RELW OH PRI CLR FLAG ESTR BTKA USA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-25 | 2020-03-25 | 2020-09-24 | 2020-09-24 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116835383 | POLE_DECA_REPL - 30568 SENTINEL DRCOARSE | 35214828 |  |  | STS-POLE_DECA_REPL - 30568 SENTINEL DRCO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1936 | -119.7521 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205D | 6165 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103233856 | RELW OH PRI CLR RESD FLAG ESTR BTKA FMOB FSRP TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116842081 | POLE_BROK_REPL - 33893 SKYLINE 1PW 1PS/O | 35214857 |  |  | STS-POLE_BROK_REPL - 33893 SKYLINE 1PW 1 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2412 | -119.7021 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B | 10335 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101061071 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116842154 | POLE_DECA_REPL - 46225 SKYLINE RDG RD 1P | 35209168 |  |  | STS-POLE_DECA_REPL - 46225 SKYLINE RDG R | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2374 | -119.7051 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B | 10335 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061085 | RELW OH PRI CLR RESD ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2020-10-30 | 2020-10-30 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116842193 | POLE_BROK_REPL - 46321 SKYLINE RDG CIR 1 | 35214867 |  |  | STS-POLE_BROK_REPL - 46321 SKYLINE RDG C | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.241 | -119.703 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B | 10335 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101061076 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116842694 | POLE_DECA_REPL - 46315 COMSTOCK DR 1PW 1 | 35214876 |  |  | STS-POLE_DECA_REPL - 46315 COMSTOCK DR 1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2336 | -119.7052 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061026 | RELW OH SERV RESD ESTR BTKA USA FSRP FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116844195 | POLE_BROK_REPL - 43763 TRABUCO RD/1PN/1P | 35209182 |  |  | STS-POLE_BROK_REPL - 43763 TRABUCO RD/1P | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2583 | -119.7498 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 | 10609 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101053296 | RELW OH SERV JPOL REMT NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2020-11-14 | 2020-11-14 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116846842 | POLE_BROK_REPL - 33590 COMSTOCK DR 1PW/O | 35214899 |  |  | STS-POLE_BROK_REPL - 46382 COMSTOCK DR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2359 | -119.7016 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B | 10335 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101061054 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116846918 | POLE_BROK_REPL - 33893 SKYLINE 1PW 2PS/O | 35209207 |  |  | STS-POLE_BROK_REPL - 33893 SKYLINE 1PW 2 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2402 | -119.7022 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B | 10335 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101061072 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 146.5 | 146.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116848508 | POLE_DECA_REPL - 46376 PALOMA RDCOARSEGO | 35209226 |  |  | STS-POLE_DECA_REPL - 46376 PALOMA RDCOAR | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 37.2312 | -119.7031 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 29.6 | 29.6 |  |  | 0 | 29.6 | 29.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061017 | RELW OH PRI CLR RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-22 |  | COMP | 2021-02-22 | [16 empty] | 2019-03-27 | 2020-03-27 | 2020-09-01 | 2020-09-01 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116848943 | POLE_DECA_REPL - 46443 PALOMA RD COARSEG | 35209236 |  |  | STS-POLE_DECA_REPL - 46443 PALOMA RD COA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2314 | -119.7014 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B | 10335 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 45 | 45 |  |  | 0 | 45 | 45 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061022 | RELW OH PRI CLR RESD ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-16 | 2021-02-16 | COMP | 2021-02-16 | [16 empty] | 2019-03-27 | 2020-03-27 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 17862.1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116852075 | POLE_BROK_REPL - 45878 OLD CORRAL TR 4PS | 35209251 |  |  | STS-POLE_BROK_REPL - 45878 OLD CORRAL TR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 37.2356 | -119.7085 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101061092 | RELW OH PRI CLR ESTR BTKA USA FMOB FSRP TER2 PRTO | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2019-03-27 | 2020-03-27 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 15933.99 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116852401 | POLE_DECA_REPL - A/F 35946 WELLS RD/2PNW | 35209256 |  |  | STS-POLE_DECA_REPL - A/F 35946 WELLS RD/ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2721 | -119.7401 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101053082 | RELW OH PRI TRAF FLAG ESTR BTKA USA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 63.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116852469 | POLE_DECA_REPL - 46264 PALOMA RD 1PN/OCO | 35209261 |  |  | STS-POLE_DECA_REPL - 46264 PALOMA RD 1PN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.231 | -119.7052 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061014 | RELW OH PRI CLR REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116852545 | POLE_DECA_REPL - 45991 BLACK OAK RD 1PE | 35209266 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2287 | -119.7094 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 30.8 | 30 | 0.8 |  | 0 | 30.8 | 30 | 0.8 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060999 | RELW OH SERV CLR RESD ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-02-17 | 2021-02-17 | COMP | 2021-02-17 | [16 empty] | 2019-03-27 | 2020-03-27 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 12080.09 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116854716 | POLE_DECA_REPL - 33900 HWY 41 #2 SCOARSE | 35209283 |  |  | STS-POLE_DECA_REPL - 33900 HWY 41 #2 SCO | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2409 | -119.709 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061150 | RELW OH PRI CLR REMT ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 45.9 | 32.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116861105 | POLE_DECA_REPL - 33402 MAID MARION 2PS 1 | 35209337 |  |  | STS-POLE_DECA_REPL - 33402 MAID MARION 2 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2297 | -119.7245 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061289 | RELW OH SERV CLR NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2020-10-07 | 2020-10-07 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 48.3 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116861342 | POLE_DECA_REPL - 33402 MAID MARION 2PS 1 | 35209362 |  |  | STS-POLE_DECA_REPL - 33402 MAID MARION 2 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.232 | -119.7247 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061293 | RELW OH PRI CLR REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2020-10-07 | 2020-10-07 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 78.3 | 64.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116863891 | POLE_DECA_REPL - 46376 PALOMA RD 1PW 1PS | 35215257 |  |  | STS-POLE_DECA_REPL - 46376 PALOMA RD 1PW | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2304 | -119.7024 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B | 10335 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061020 | RELW OH ESTR PRI CLR REMT BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116863925 | POLE_DECA_REPL - 46376 PALOMA RD 1PW 2PS | 35209437 |  |  | STS-POLE_DECA_REPL - 46376 PALOMA RD 1PW | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2296 | -119.7039 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B | 10335 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061021 | RELW OH PRI CLR RESD ESTR BTKA REAR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116865048 | POLE_DECA_REPL - 33402 MAID MARION 2PS 1 | 35209458 |  |  | STS-POLE_DECA_REPL - 33402 MAID MARION 2 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.231 | -119.7235 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213B | 5677 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061291 | RELW OH PRI CLR REMT NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2020-10-07 | 2020-10-07 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116865659 | POLE_DECA_REPL - SHAH CT SUNSET RDG E/NW | 35209503 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2194 | -119.7165 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213C | 10623 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060390 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA USA FMOB FSRP TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116877911 | POLE_BROK_REPL - 47143 RD.200 COARSEGOLD | 35209666 |  |  | STS-POLE_BROK_REPL - 47143 RD.200 COARSE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1306 | -119.6927 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000009213 | 5369 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101062654 | RELW OH PRI CLR JPOL BTKA RESD ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432103 | 1 | 46.3 | 32.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116877954 | POLE_DECA_REPL - 42816 BADGER CIR 1PN/1P | 35215563 |  |  | STS-POLE_DECA_REPL - 42816 BADGER CIR 1P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1963 | -119.7682 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205C | 5509 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059069 | RELW OH SEC CLR JPOL RESD FIRE NOAC ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116951525 | POLE_BROK_REPL - R/O END OF EDEN LN COAR | 35214639 |  |  | STS-POLE_BROK_REPL - R/O END OF EDEN LN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2628 | -119.7386 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 | 5523 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052815 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-03 | 2020-04-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117015523 | POLE_DECA_REPL - 43169 RUNNING DEER DRCO | 35209274 |  |  | STS-POLE_DECA_REPL - 43169 RUNNING DEER | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.1847 | -119.7621 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B | 10217 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103229908 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-12 | 2020-04-12 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117018965 | POLE_BROK_REPL - A/F 29040 REVIS RD.COAR | 35209327 |  |  | STS-POLE_BROK_REPL - A/F 29040 REVIS RD. | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1703 | -119.7554 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201A | 10574 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101107128 | RELW OH PRI RESD FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-12 | 2020-04-12 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117023928 | POLE_BROK_REPL - 93614COARSEGOLD93614 | 35209406 |  |  | STS-POLE_BROK_REPL - 93614COARSEGOLD9361 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1846 | -119.7533 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201A | 10217 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103201892 | RELW OH PRI CLR REMT ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 78.3 | 64.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117219240 | POLE_DECA_REPL - HWY 41 C/O POLE 603\1PN | 35209714 |  |  | STS-POLE_DECA_REPL - HWY 41 C/O POLE 603 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2949 | -119.648 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 07215B | 10324 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101026529 | RELW OH PRI CLR REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-12 | 2020-05-12 | 2020-10-23 | 2020-10-23 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 324.1 | 310.7 | 310.7 | 310.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117223537 | POLE_DECA_REPL - R/O 36660 SERPA CANYON | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 37.2869 | -119.6716 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 07215B |  | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101026468 | REGW OH SERV REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-05-13 | 2020-05-13 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan |  | UNASSIGNED |  | 254432104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117223958 | POLE_DECA_REPL - R/O 36662 SERPA CANYON | 35209754 |  |  | STS-POLE_DECA_REPL - R/O 36662 SERPA CAN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2874 | -119.6716 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 07215B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101026414 | RELW OH PRI REMT FIRE NOAC ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-13 | 2020-05-13 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117224119 | POLE_BROK_REPL - 44410 RD 415 CO#5676COA | 35214850 |  |  | STS-POLE_BROK_REPL - 44410 RD 415 CO#567 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2411 | -119.7369 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204A | 369777 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101050145 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-13 | 2020-05-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117226943 | POLE_BROK_REPL - 33211 VETOLL RDCOARSEGO | 35214874 |  |  | STS-POLE_BROK_REPL - 33211 VETOLL RDCOAR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2305 | -119.7608 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101050803 | OH RELW PRI JPOL REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-13 | 2020-05-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117227110 | POLE_BROK_REPL - 33273 VETOLL RD 3PW/OCO | 35214879 |  |  | STS-POLE_BROK_REPL - 33273 VETOLL RD 3PW | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2314 | -119.7625 |  | TIER 2 |  |  | 08204B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101050818 | RELW SERV OH JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-13 | 2020-05-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  |  | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117228744 | POLE_DECA_REPL - A\F 37348 RD 425-CCOARS | 35209769 |  |  | STS-POLE_DECA_REPL - A\F 37348 RD 425-CC | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2909 | -119.6531 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 07215B | 5673 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 75.7 | 75.7 |  |  | 0 | 75.7 | 75.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101026347 | RELW OH PRI FIRE NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-01-19 | COMP | 2021-01-19 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-10-30 | 2020-10-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 32002.97 | 194 | 180.5 | 180.5 | 180.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117229280 | POLE_BROK_REPL - 44684 RD415 2PS/OCOARSE | 35214897 |  |  | STS-POLE_BROK_REPL - 44684 RD415 2PS/OCO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2408 | -119.7322 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204A | 5677 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101050119 | RELW OH PRI TER2 CLR ESTR FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117229805 | POLE_DECA_REPL - 43667 RANCHO DE FRUTALN | 35209774 |  |  | STS-POLE_DECA_REPL - 43667 RANCHO DE FRU | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.2321 | -119.7499 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.2 | 13.2 |  |  | 0 | 13.2 | 13.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101050716 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-19 | 2021-02-19 | COMP | 2021-02-19 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 4485.45 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117229893 | POLE_BROK_REPL - 44684 RD415 1PS 3PW/OCO | 35209779 |  |  | STS-POLE_BROK_REPL - 44684 RD415 1PS 3PW | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2397 | -119.7351 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204A | 5677 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101050158 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117230219 | POLE_DECA_REPL - 36741 MATTIE FHY CT\1PS | 35209785 |  |  | STS-POLE_DECA_REPL - 36741 MATTIE FHY CT | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.2823 | -119.6547 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 07215C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101026680 | RELW OH PRI RESD FIRE TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 53.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117230468 | POLE_DECA_REPL - 43667 RANCHO DE FRUTALN | 35214912 |  |  | STS-POLE_DECA_REPL - 43667 RANCHO DE FRU | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2342 | -119.751 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204A | 5675 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101050710 | RELW OH PRI ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117230633 | POLE_DECA_REPL - R/O 37084 RD 425-C\1PSW | 35209788 |  |  | STS-POLE_DECA_REPL - R/O 37084 RD 425-C\ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2858 | -119.6551 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 07215C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101026653 | RELW OH PRI REMT SWRK ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 53.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117230762 | POLE_DECA_REPL - A\F 36927 HWY 41\1PSCOA | 35208788 |  |  | STS-POLE_DECA_REPL - A\F 36927 HWY 41\1P | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2855 | -119.6551 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 07215C | 10788 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 46 | 46 |  |  | 0 | 46 | 46 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101026658 | RELW OH PRI REMT FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-25 |  | COMP | 2021-01-25 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 25268.92 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117231292 | POLE_DECA_REPL - 93614 COARSEGOLD HIGHWA | 35208811 |  |  | STS-POLE_DECA_REPL - 93614 COARSEGOLD HI | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2646 | -119.6981 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000821054 | 21702 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 54.6 | 54.6 |  |  | 0 | 54.6 | 54.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103235631 | RELW OH PRI REMT TER2 SPCR ESTR FMOB PRTO FSRP | Pole | 2021-01-13 | 2021-01-11 | COMP | 2021-01-11 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 24594.36 | 53.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117231335 | POLE_DECA_REPL - SW C/O ONEIDA AV/CHICKA | 35214922 |  |  | STS-POLE_DECA_REPL - SW C/O ONEIDA AV/CH | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2202 | -119.6848 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821213 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060951 | RELW OH SERV NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-04-25 | 2021-04-25 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117231695 | POLE_BROK_REPL - 33615 JOHN/ROBIN HOOD D | 35214932 |  |  | STS-POLE_BROK_REPL - 33615 JOHN/ROBIN HO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2366 | -119.7306 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204A | 5677 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101050624 | RELW PRI OH CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117233909 | POLE_DECA_REPL - 47672 CHEYENNE RDCOARSE | 35208857 |  |  | STS-POLE_DECA_REPL - 47672 CHEYENNE RDCO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2211 | -119.6782 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821214 | 10783 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39 | 39 |  |  | 0 | 39 | 39 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060918 | RELW OH PRI CLR RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-04 |  | COMP | 2021-01-04 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-09-06 | 2020-09-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 21574.49 | 13.5 | 0 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117233951 | POLE_BROK_REPL - 33211 VETOLL RD 2PE 1PS | 35214977 |  |  | STS-POLE_BROK_REPL - 33211 VETOLL RD 2PE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2302 | -119.7598 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101050808 | RELW OH SERV JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117238409 | POLE_DECA_REPL - DELAWARE RD OTTAWA AVE | 35208882 |  |  | STS-POLE_DECA_REPL - DELAWARE RD OTTAWA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.219 | -119.6836 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821213 | 10783 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.2 | 31.2 |  |  | 0 | 31.2 | 31.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060943 | RELW OH PRI FLAG ESTR GO TER2 BTKA USA FMOB PRTO FSRP | Pole | 2020-12-29 |  | COMP | 2020-12-29 | [16 empty] | 2019-05-15 | 2020-05-15 | 2020-07-25 | 2020-07-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 21885.01 | 1291.4 | 1277.9 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117239232 | POLE_BROK_REPL - 43359 SESAME ST 1PW/O C | 35215005 |  |  | STS-POLE_BROK_REPL - 43359 SESAME ST 1PW | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2305 | -119.7579 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204B | 5514 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101050836 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP CNCL | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117239345 | POLE_BROK_REPL - 33055 ROBINHOOD DR 2PE/ | 35208898 |  |  | STS-POLE_BROK_REPL - 33055 ROBINHOOD DR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2284 | -119.7334 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.7 | 18.7 |  |  | 0 | 18.7 | 18.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101050562 | RELW OH PRI TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-27 |  | COMP | 2021-01-27 | [16 empty] | 2019-05-15 | 2020-05-15 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 11281.86 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117239624 | POLE_BROK_REPL - 33449 ROBIN HOOD DR 1PS | 35215015 |  |  | STS-POLE_BROK_REPL - 33449 ROBIN HOOD DR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2318 | -119.7303 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204A | 5677 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103330934 | RELW OH PRI TER2 CLR ESTR FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117239952 | POLE_DECA_REPL - 46982 PONY EXPRESS RD/1 | 35208917 |  |  | STS-POLE_DECA_REPL - 46982 PONY EXPRESS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2655 | -119.691 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000821054 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101063300 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 60.2 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117242273 | POLE_BURN_REPL - 47954 KLAMATH AVE 1PE/O | 35208933 |  |  | STS-POLE_BURN_REPL - 47954 KLAMATH AVE 1 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2172 | -119.6742 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821215 | 5506 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 101060609 | RELW OH PRI RESD ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 |  | COMP | 2021-01-19 | [16 empty] | 2019-05-15 | 2020-05-15 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 25634.69 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117242487 | POLE_DECA_REPL - 31864 CHEROKEE RDCOARSE | 35208942 |  |  | STS-POLE_DECA_REPL - 31864 CHEROKEE RDCO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2122 | -119.6815 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821281 | 58171 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.2 | 41.2 |  |  | 0 | 41.2 | 41.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056634 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-04 |  | COMP | 2021-01-04 | [16 empty] | 2019-05-15 | 2020-05-15 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 29174.87 | 13.5 | 0 | 353 | 353 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117242835 | POLE_DECA_REPL - 31767 CHEROKEE RD 1PWCO | 35208952 |  |  | STS-POLE_DECA_REPL - 31767 CHEROKEE RD 1 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2108 | -119.6807 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821281 | 58171 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.3 | 41.3 |  |  | 0 | 41.3 | 41.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056637 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-13 |  | COMP | 2021-01-13 | [16 empty] | 2019-05-15 | 2020-05-15 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 24157.21 | 40.4 | 0 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117242951 | POLE_DECA_REPL - 31767 CHEROKEE RDCOARSE | 35208956 |  |  | STS-POLE_DECA_REPL - 31767 CHEROKEE RDCO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2108 | -119.6804 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821281 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056638 | RELW OH SEC ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 53.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117254730 | POLE_DECA_REPL - 33325 SESAME ST 2PW/OCO | 35215182 |  |  | STS-POLE_DECA_REPL - 33325 SESAME ST 2PW | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2318 | -119.7564 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101050839 | RELW OH PRI JPOL REMT ESTR BTKA PRTO USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-17 | 2020-05-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117254855 | POLE_DECA_REPL - 47745 KLAMATH AVE 1PN/O | 35209070 |  |  | STS-POLE_DECA_REPL - 47745 KLAMATH AVE 1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2153 | -119.6777 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821215 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060620 | RELW OH SEC RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-17 | 2020-05-17 | 2020-09-04 | 2020-09-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117255267 | POLE_DECA_REPL - DELAWARE/DELAWARE CT 3P | 35209079 |  |  | STS-POLE_DECA_REPL - DELAWARE/DELAWARE C | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2129 | -119.6784 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821281 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.5 | 17.5 |  |  | 0 | 17.5 | 17.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056653 | OH SEC ESTR PRTO RELW BTKA USA FMOB TER2 FSRP | Pole | 2020-12-29 | 2020-12-28 | COMP | 2020-12-28 | [16 empty] | 2019-05-17 | 2020-05-17 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 10220.06 | 1033.5 | 1020.1 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117256669 | POLE_DECA_REPL - 47600 KLAMATH AVE 1PW/O | 35209099 |  |  | STS-POLE_DECA_REPL - 47600 KLAMATH AVE 1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2143 | -119.6801 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821215 | 81295 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060627 | RELW OH PRI PROG RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-17 | 2020-05-17 | 2020-08-04 | 2020-08-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117261113 | POLE_DECA_REPL - 32044 DELAWARE RD 2PW/O | 35209129 |  |  | STS-POLE_DECA_REPL - 32044 DELAWARE RD 2 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2146 | -119.6818 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821215 | 10536 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060632 | RELW OH PRI RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-17 | 2020-05-17 | 2020-10-05 | 2020-10-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | -1230.8 | -687.8 | -687.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117265218 | CRSS_BROK_REPL - 47883 HURON CT 2PE 1PN/ | 35209141 |  |  | STS-CRSS_BROK_REPL - 47883 HURON CT 2PE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2161 | -119.6744 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821215 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Crossarm | Broken/Damaged | Replace |  | 101060605 | RELW OH PRI NOAC ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-17 | 2020-05-17 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117268009 | POLE_BROK_REPL - 31058 WILLOW POND LN CO | 35209146 |  |  | STS-POLE_BROK_REPL - 31058 WILLOW POND L | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2011 | -119.6732 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821285 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 19.6 | 19.6 |  |  | 0 | 19.6 | 19.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103225001 | RELW OH PRI FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-14 |  | COMP | 2020-12-14 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-11-05 | 2020-11-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 11302.11 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117268062 | POLE_DECA_REPL - RD 417/QUARTZ MTN RD 1P | 35209150 |  |  | STS-POLE_DECA_REPL - RD 417/QUARTZ MTN R | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2106 | -119.6897 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 | 23266 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 46.5 | 46.5 |  |  | 0 | 46.5 | 46.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056274 | RELW OH PRI CLR JPOL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-01 |  | COMP | 2021-02-01 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 23055.56 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117268172 | POLE_BROK_REPL - 47663 WILLOW POND RD 1P | 35209156 |  |  | STS-POLE_BROK_REPL - 47663 WILLOW POND R | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2014 | -119.6795 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821285 | 10776 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 59.8 | 58.8 | 1 |  | 0 | 59.8 | 58.8 | 1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101056623 | RELW OH PRI RESD ESTR BTKA FMOB TER2 FSRP PRTO | Pole | 2021-01-27 |  | COMP | 2021-01-27 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 29497.2 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117268201 | POLE_DECA_REPL - 31730 ERIE 1PN/1PE COAR | 35215230 |  |  | STS-POLE_DECA_REPL - 31730 ERIE 1PN/1PE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2101 | -119.6751 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821281 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056662 | RELW OH SEC ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117268331 | POLE_DECA_REPL - 46968 RD 417 2PSECOARSE | 35215241 |  |  | STS-POLE_DECA_REPL - 46968 RD 417 2PSECO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2094 | -119.6909 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821291 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056410 | RELW OH REMT PRI CLR JPOL FIRE NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117268475 | POLE_DECA_REPL - 47832 SEMINOLE AV (4183 | 35215247 |  |  | STS-POLE_DECA_REPL - 47832 SEMINOLE AV ( | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 37.212 | -119.6752 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821281 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102316200 | RELW OH SEC ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 48.3 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117268579 | POLE_DECA_REPL - MIWOC/COMANCHE 1PSCOARS | 35209170 |  |  | STS-POLE_DECA_REPL - MIWOC/COMANCHE 1PSC | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.212 | -119.6834 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 | 10536 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056252 | RELW OH PRI CLR REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117268597 | POLE_DECA_REPL - 47179 MODOC RD 1PS/OCOA | 35209174 |  |  | STS-POLE_DECA_REPL - 47179 MODOC RD 1PS/ | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.214 | -119.6897 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821216 | 10783 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 41.4 | 41.4 |  |  | 0 | 41.4 | 41.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060843 | RELW PRI OH CLR JPOL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-25 |  | COMP | 2021-01-25 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-10-30 | 2020-10-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 20939.95 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117268680 | POLE_DECA_REPL - #1 W/O SIOUX RD/SEMINOL | 35215262 |  |  | STS-POLE_DECA_REPL - #1 W/O SIOUX RD/SEM | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2121 | -119.6741 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821281 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056480 | RELW BTKA OH SEC ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 48.3 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117268682 | POLE_DECA_REPL - MODOCO/RD 417 1PNCOARSE | 35215267 |  |  | STS-POLE_DECA_REPL - MODOCO/RD 417 1PNCO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2132 | -119.6899 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 | 10783 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056196 | RELW OH PRI CLR JPOL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117268707 | POLE_DECA_REPL - #1 W/O SIOUX RD/SEMINOL | 35209180 |  |  | STS-POLE_DECA_REPL - #1 W/O SIOUX RD/SEM | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro |  |  | 37.2119 | -119.6741 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821281 | 5506 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056479 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2020-12-29 | 2020-12-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117269201 | POLE_DECA_REPL - MIWOC/COMANCHE 1PSWCOAR | 35209206 |  |  | STS-POLE_DECA_REPL - MIWOC/COMANCHE 1PSW | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2123 | -119.6845 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 | 63475 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 62.5 | 61.2 | 1.3 |  | 0 | 62.5 | 61.2 | 1.3 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056255 | OH RELW PRI CLR REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-01 |  | COMP | 2021-02-01 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117269419 | POLE_DECA_REPL - MIWOC/BLACKFOOTCOARSEGO | 35209211 |  |  |  | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.212 | -119.6854 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 | 63475 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 41.7 | 41.7 |  |  | 0 | 41.7 | 41.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056227 | RELW OH PRI CLR REMT FIRE TRAF FLAG ESTR BTKA USA FSRP PRTO FMOB TER2 | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-12-29 | 2020-12-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 20944.42 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117269708 | zxiE_DECA_REPL - APACHE/RD 417COARSEGOLD | 35209224 |  |  | STS-POLE_DECA_REPL - APACHE/RD 417COARSE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2127 | -119.6889 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 | 10536 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056200 | RELW OH PRI CLR JPOL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2020-12-29 | 2020-12-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117269748 | POLE_DECA_REPL - 31666 BLACKFOOT 2PNW/1P | 35215285 |  |  | STS-POLE_DECA_REPL - 31666 BLACKFOOT 2PN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2114 | -119.6851 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056230 | RELW OH SEC CLR REMT FIRE ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117269777 | POLE_BROK_REPL - 31200 WILLOW POND LN CO | 35215290 |  |  | STS-POLE_BROK_REPL - 31200 WILLOW POND L | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2018 | -119.6762 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821285 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101056618 | RELW OH PRI RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117269860 | POLE_DECA_REPL - APACHE/RD 417 1PNE/1PSE | 35215296 |  |  | STS-POLE_DECA_REPL - APACHE/RD 417 1PNE/ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2129 | -119.6876 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056207 | RELW OH SERV CLR JPOL RESD FIRE ESTR GO BTKA USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117270032 | POLE_DECA_REPL - 31666 BLACKFOOT 1PNW/1P | 35209233 |  |  | STS-POLE_DECA_REPL - 31666 BLACKFOOT 1PN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2104 | -119.6842 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 11.4 | 10.3 | 1.1 |  | 0 | 11.4 | 10.3 | 1.1 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056245 | RELW OH SEC REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-22 |  | COMP | 2021-01-22 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-12-29 | 2020-12-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 7825.78 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117270401 | POLE_DECA_REPL - APACHE/RD 417 3PNE/1PS/ | 35215301 |  |  | STS-POLE_DECA_REPL - APACHE/RD 417 3PNE/ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2137 | -119.6857 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056217 | RELW OH SERV CLR JPOL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117270508 | POLE_BROK_REPL - MIWOC/BLACKFOOT 2PSW CO | 35215304 |  |  | STS-POLE_BROK_REPL - MIWOC/BLACKFOOT 2PS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2116 | -119.6863 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 | 63475 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101056222 | RELW OH SEC CLR REMT FIRE ESTR BTKA REAR USA FMOB FSRP TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117270517 | POLE_BROK_REPL - 31484 SIOUX 1PECOARSEGO | 35209273 |  |  | STS-POLE_BROK_REPL - 31484 SIOUX 1PECOAR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.206 | -119.6732 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821284 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057063 | RELW OH SEC CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117270588 | POLE_BROK_REPL - #1 W/O 47335 RD 417 #2 | 35215309 |  |  | STS-POLE_BROK_REPL - #1 W/O 47335 RD 417 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2139 | -119.6847 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102339461 | RELW OH SERV CLR JPOL RESD FIRE ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117270603 | POLE_BROK_REPL - 47463 RD417COARSEGOLD93 | 35209284 |  |  | STS-POLE_BROK_REPL - 47463 RD417COARSEGO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2155 | -119.6822 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821216 | 10536 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101060868 | RELW OH PRI RESD FIRE FLAG ESTR BTKA USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2020-10-05 | 2020-10-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117271299 | POLE_BROK_REPL - COMANCHE/CHEROKEE COARS | 35209314 |  |  | STS-POLE_BROK_REPL - COMANCHE/CHEROKEE C | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2069 | -119.6802 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821284 | 10536 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.9 | 40.9 |  |  | 0 | 40.9 | 40.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057021 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-03 |  | COMP | 2021-02-03 | [16 empty] | 2019-05-19 | 2020-05-19 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 21312.22 | 361.2 | 347.7 | 347.7 | 347.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117271611 | POLE_BROK_REPL - 31416 ERIE RD IN YARDCO | 35215319 |  |  | STS-POLE_BROK_REPL - 31416 ERIE RD IN YA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2054 | -119.6752 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821284 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103904509 | RELW OH SEC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-19 | 2020-05-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117271612 | POLE_BROK_REPL - CROW/CHEROKEE 1PSE/1PNE | 35209319 |  |  | STS-POLE_BROK_REPL - CROW/CHEROKEE 1PSE/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2077 | -119.6793 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821284 | 2305 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057030 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-19 | 2020-05-19 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117271624 | POLE_BROK_REPL - ERIE/HOPI 1PNW/1PSWCOAR | 35209324 |  |  | STS-POLE_BROK_REPL - ERIE/HOPI 1PNW/1PSW | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2045 | -119.675 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821284 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057058 | RELW OH SEC CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-19 | 2020-05-19 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117272478 | POLE_BROK_REPL - R/O 31649 SIOUX RDCOARS | 35209358 |  |  | STS-POLE_BROK_REPL - R/O 31649 SIOUX RDC | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2079 | -119.6727 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821284 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103904551 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-19 | 2020-05-19 | 2020-11-04 | 2020-11-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117275740 | POLE_DECA_REPL - 30233 HOGANS MTN RD 3PN | 35209369 |  |  | STS-POLE_DECA_REPL - 30233 HOGANS MTN RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1893 | -119.7117 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000008216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.2 | 14.2 |  |  | 0 | 14.2 | 14.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103089949 | RELW OH PRI NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-18 | 2020-12-17 | COMP | 2020-12-17 | [16 empty] | 2019-05-20 | 2020-05-20 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 9257.74 | 13.5 | -1013.6 | -561.1 | -561.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117275872 | CUTO_BROK_REPL - 31761 APACHECOARSEGOLD9 | 35209374 |  |  | STS-CUTO_BROK_REPL - 31761 APACHECOARSEG | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.2103 | -119.6861 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 | 21546 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Cutout | Broken/Damaged | Replace |  | 101056266 | RELW OH PRI CLR REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-20 | 2020-05-20 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117276297 | POLE_DECA_REPL - 47362 RD417COARSEGOLD93 | 35209379 |  |  | STS-POLE_DECA_REPL - 47362 RD417COARSEGO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2145 | -119.6839 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43 | 43 |  |  | 0 | 43 | 43 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060859 | RELW OH FIRE PRI RESD REMT FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-20 |  | COMP | 2021-01-20 | [16 empty] | 2019-05-20 | 2020-05-20 | 2020-10-05 | 2020-10-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 20442.79 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117277210 | POLE_DECA_REPL - APACHE/MIWOC 2PNW/1PSWC | 35215399 |  |  | STS-POLE_DECA_REPL - APACHE/MIWOC 2PNW/1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2116 | -119.688 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056204 | RELW OH SEC CLR JPOL RESD FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-20 | 2020-05-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117277374 | POLE_DECA_REPL - APACHE/MIWOC 1PNWCOARSE | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 37.2115 | -119.6875 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 |  | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056218 | REGW OH PRI CLR JPOL RESD FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-05-20 | 2020-05-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 254432103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117277775 | POLE_DECA_REPL - 93614COARSEGOLD93614 | 35215408 |  |  | STS-POLE_DECA_REPL - 93614COARSEGOLD9361 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2077 | -119.6979 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821294 | 23266 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103200585 | RELW OH PRI CLR JPOL RESD REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-20 | 2020-05-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117280878 | POLE_DECA_REPL - #6 W/O QUARTZ MTN RD/RD | 35215438 |  |  | STS-POLE_DECA_REPL - #6 W/O QUARTZ MTN R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2086 | -119.6928 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821291 | 23266 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103089565 | RELW OH PRI CLR JPOL RESD REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-20 | 2020-05-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117281160 | POLE_DECA_REPL - HOPI/BLACKFOOT 2PWCOARS | 35209396 |  |  | STS-POLE_DECA_REPL - HOPI/BLACKFOOT 2PWC | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2036 | -119.6844 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821286 | 10772 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 31.8 | 31.8 |  |  | 0 | 31.8 | 31.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056290 | RELW OH PRI CLR REMT FIRE TRAF FLAG ESTR BTKA USA FMOB FSRP TER2 PRTO | Pole | 2020-12-17 |  | COMP | 2020-12-17 | [16 empty] | 2019-05-20 | 2020-05-20 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 20481.45 | 403.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117281572 | POLE_DECA_REPL - 46968 RD 417 2PSE/4PS/5 | 35215452 |  |  | STS-POLE_DECA_REPL - 46968 RD 417 2PSE/4 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2039 | -119.6942 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821294 | 23266 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056424 | RELW OH PRI CLR JPOL RESD REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-20 | 2020-05-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117281833 | POLE_DECA_REPL - 31405 APACHE 1PNWCOARSE | 35215458 |  |  | STS-POLE_DECA_REPL - 31405 APACHE 1PNWCO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2055 | -119.6849 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821283 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056159 | RELW OH SERV RESD ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-20 | 2020-05-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117281837 | POLE_DECA_REPL - 31405 APACHECOARSEGOLD9 | 35209405 |  |  | STS-POLE_DECA_REPL - 31405 APACHECOARSEG | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2054 | -119.6845 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821283 | 21546 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056160 | OH PRI CLR RESD ESTR BTKA USA FMOB TER2 PRTO FSRP RELW | Pole | 2021-02-11 |  | COMP | 2021-02-11 | [16 empty] | 2019-05-20 | 2020-05-20 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 26940.59 | 217.2 | 217.2 | 217.2 | 217.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117282006 | POLE_DECA_REPL - HOPI/APACHE CT 1PW/1PSW | 35209410 |  |  | STS-POLE_DECA_REPL - HOPI/APACHE CT 1PW/ | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2038 | -119.6859 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821286 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 18.1 | 18.1 |  |  | 0 | 18.1 | 18.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056275 | RELW OH PRI CLR REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-17 |  | COMP | 2020-12-17 | [16 empty] | 2019-05-20 | 2020-05-20 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 8534.25 | 89.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117282164 | POLE_BROK_REPL - 46968 RD 417 2PSE/4PS/4 | 35215463 |  |  | STS-POLE_BROK_REPL - 46968 RD 417 2PSE/4 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2039 | -119.6931 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821294 | 23266 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101056423 | RELW OH PRI CLR JPOL RESD REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-20 | 2020-05-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 52.2 | 52.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117291678 | POLE_DECA_REPL - RD 417/QUARTZ MTN RD 4P | 35215483 |  |  | STS-POLE_DECA_REPL - RD 417/QUARTZ MTN R | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.208 | -119.6876 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821283 | 23266 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056145 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-21 | 2020-05-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117291715 | POLE_DECA_REPL - 31573 QUARTZ MOUNTAIN R | 35215488 |  |  | STS-POLE_DECA_REPL - 31573 QUARTZ MOUNTA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2081 | -119.6872 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821283 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103199891 | RELW OH SEC ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-21 | 2020-05-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117293408 | POLE_DECA_REPL - CHEROKEE/BLACKFOOT 2PNW | 35209479 |  |  | STS-POLE_DECA_REPL - CHEROKEE/BLACKFOOT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2072 | -119.6825 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821283 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056177 | RELW OH SEC ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-21 | 2020-05-21 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117293705 | POLE_BROK_REPL - 47947 RD417 12N 10PE 14 | 35215504 |  |  | STS-POLE_BROK_REPL - 47947 RD417 12N 10P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2402 | -119.6705 |  | TIER 2 | 385 | 25443-2102, COARSEGOLD | 0000008214 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101055541 | RELW OH PRI ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-21 | 2020-05-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432102 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117295425 | POLE_DECA_REPL - EAST DE ERIECOARSEGOLD9 | 35215555 |  |  | STS-POLE_DECA_REPL - EAST DE ERIECOARSEG | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2002 | -119.6699 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000008215 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103921033 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-21 | 2020-05-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117297004 | POLE_DECA_REPL - 47947 RD417 8PN CO#1033 | 35215560 |  |  | STS-POLE_DECA_REPL - 47947 RD417 8PN CO# | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2265 | -119.6677 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000008214 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101055666 | OH PRI REMT RELW CLR JPOL FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-21 | 2020-05-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117298567 | POLE_BROK_REPL - 31362 APACHE COARSEGOLD | 35209538 |  |  | STS-POLE_BROK_REPL - 31362 APACHE COARSE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2045 | -119.6855 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821283 | 87159 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 39.6 | 39.6 |  |  | 0 | 39.6 | 39.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101056162 | RELW OH PRI CLR RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-17 |  | COMP | 2020-12-17 | [16 empty] | 2019-05-20 | 2020-05-20 | 2020-09-01 | 2020-09-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 22904.89 | 75.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117303485 | POLE_BROK_REPL - LONG VIEW LN/LONG VIEW | 35215618 |  |  | STS-POLE_BROK_REPL - LONG VIEW LN/LONG V | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1965 | -119.6833 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216D | 10776 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101056355 | RELW OH PRI CLR RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-22 | 2020-05-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117305004 | POLE_DECA_REPL - 47752 WILLOW POND RDCOA | 35215642 |  |  | STS-POLE_DECA_REPL - 47752 WILLOW POND R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1991 | -119.6768 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103206971 | RELW OH PRI CLR RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-23 | 2020-05-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117307334 | POLE_DECA_REPL - 47947 RD417 12N 28PE/OC | 35209624 |  |  | STS-POLE_DECA_REPL - 47947 RD417 12N 28P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2308 | -119.644 |  | TIER 2 | 385 | 25443-2102, COARSEGOLD | 0000008214 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101055625 | RELW OH PRI CLR JPOL REMT FIRE NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-23 | 2020-05-23 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432102 | 1 | 60.2 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117318064 | POLE_DECA_REPL - #4 W/O QUARTZ MTN RD/RD | 35215662 |  |  | STS-POLE_DECA_REPL - #4 W/O QUARTZ MTN R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 37.2122 | -119.6944 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821291 | 23268 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101057015 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-24 | 2020-05-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117319943 | POLE_DECA_REPL - 46417 RD417 4PE/OCOARSE | 35215675 |  |  | STS-POLE_DECA_REPL - 46417 RD417 4PE/OCO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 37.2139 | -119.6981 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08213D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060491 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-25 | 2020-05-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 48.3 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117321528 | POLE_DECA_REPL - 31551 RD 416 2PN COARSE | 35209706 |  |  | STS-POLE_DECA_REPL - 31551 RD 416 2PN CO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land Enviro |  |  | 37.2086 | -119.7268 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B | 5508 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101055746 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-25 | 2020-05-25 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 45.9 | 32.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117323551 | POLE_BROK_REPL - 31398 KENEDY LN 2PNE/2P | 35215711 |  |  | STS-POLE_BROK_REPL - 31398 KENEDY LN 2PN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2062 | -119.7112 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101056931 | RELW OH SERV CLR REMT ESTR GO PRTO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-26 | 2020-05-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 48.3 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117323558 | POLE_DECA_REPL - KENNEDY LN/BUCK RUN LN | 35215713 |  |  | STS-POLE_DECA_REPL - KENNEDY LN/BUCK RUN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2079 | -119.7097 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B | 10765 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056950 | RELW PRI OH CLR RESD REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-26 | 2020-05-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117323610 | POLE_DECA_REPL - 31671 BUCK RUN LN 1PNWC | 35209730 |  |  | STS-POLE_DECA_REPL - 31671 BUCK RUN LN 1 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2086 | -119.7105 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B | 10765 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 54.8 | 54.1 | 0.7 |  | 0 | 54.8 | 54.1 | 0.7 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056947 | RELW OH PRI CLR REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-28 |  | COMP | 2020-12-28 | [16 empty] | 2019-05-26 | 2020-05-26 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 26872.99 | 13.5 | 0 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117324244 | POLE_DECA_REPL - HWY 41/KENNEDY 3PNE/1PE | 35209735 |  |  | STS-POLE_DECA_REPL - HWY 41/KENNEDY 3PNE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2122 | -119.7088 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.7 | 12.7 |  |  | 0 | 12.7 | 12.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056969 | RELW OH SEC CLR FLAG JPOL RESD TRAF ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-15 |  | COMP | 2020-12-15 | [16 empty] | 2019-05-27 | 2020-05-27 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 9221.37 | 365.3 | 109.6 | 335.9 | 335.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117324280 | POLE_DECA_REPL - HWY 41/KENNEDY 2PNE/1PN | 35209740 |  |  | STS-POLE_DECA_REPL - HWY 41/KENNEDY 2PNE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2113 | -119.7103 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B | 21592 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 39.8 | 39.8 |  |  | 0 | 39.8 | 39.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056967 | RELW OH PRI CLR JPOL RESD TRAF TER2 FLAG ESTR FMOB PRTO FSRP | Pole | 2020-12-17 |  | COMP | 2020-12-17 | [16 empty] | 2019-05-27 | 2020-05-27 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 18190.17 | 13.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117324286 | POLE_DECA_REPL - HWY 41/KENNEDY 2PNE/1PN | 35215729 |  |  | STS-POLE_DECA_REPL - HWY 41/KENNEDY 2PNE | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2106 | -119.7106 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B | 21592 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056963 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-27 | 2020-05-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117325360 | POLE_DECA_REPL - HOGANS MTN RD/HWY 41 2P | 35209757 |  |  | STS-POLE_DECA_REPL - HOGANS MTN RD/HWY 4 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2076 | -119.7169 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.9 | 21.9 |  |  | 0 | 21.9 | 21.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056907 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 |  | COMP | 2020-12-11 | [16 empty] | 2019-05-27 | 2020-05-27 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 8659.69 | 13.5 | -1267 | -814.5 | -814.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117325561 | POLE_DECA_REPL - HOGANS MTN RD/HWY 41 4P | 35215747 |  |  | STS-POLE_DECA_REPL - HOGANS MTN RD/HWY 4 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2033 | -119.7201 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101055941 | RELW OH SEC CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-27 | 2020-05-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117325573 | POLE_DECA_REPL - HOGANS MTN RD/HWY 41 3P | 35209761 |  |  | STS-POLE_DECA_REPL - HOGANS MTN RD/HWY 4 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2038 | -119.7193 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 29.4 | 29.4 |  |  | 0 | 29.4 | 29.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101055938 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-15 |  | COMP | 2020-12-15 | [16 empty] | 2019-05-27 | 2020-05-27 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 15972.3 | 13.5 | -1230.8 | -687.8 | -687.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117326566 | POLE_DECA_REPL - NW C/O EDEN/WELLS RD/2P | 35215751 |  |  | STS-POLE_DECA_REPL - NW C/O EDEN/WELLS R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2641 | -119.7351 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820014 | 10628 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052800 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-28 | 2020-05-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117327412 | POLE_DECA_REPL - 35649 WELLS RD/1PNWCOAR | 35209778 |  |  | STS-POLE_DECA_REPL - 35649 WELLS RD/1PNW | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2666 | -119.7359 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820014 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.1 | 34.1 |  |  | 0 | 34.1 | 34.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052910 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-05 |  | COMP | 2021-01-05 | [16 empty] | 2019-05-28 | 2020-05-28 | 2020-10-26 | 2020-10-26 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 16320.38 | 13.5 | 0 | 525 | 525 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117327641 | POLE_DECA_REPL - A/F 35472 WELLS RD COAR | 35209780 |  |  | STS-POLE_DECA_REPL - A/F 35472 WELLS RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2631 | -119.7342 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820014 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 22.8 | 22.8 |  |  | 0 | 22.8 | 22.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052784 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-17 |  | COMP | 2020-12-17 | [16 empty] | 2019-05-28 | 2020-05-28 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 13623.93 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117328779 | POLE_DECA_REPL - 44979 DOUGLAS RD/1PSW C | 35209792 |  |  | STS-POLE_DECA_REPL - 44979 DOUGLAS RD/1P | APPR | APPR ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2647 | -119.7292 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820014 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052870 | RELW OH PRI REMT ESTR GO BTKA FSRP PRTO FMOB TER2 | Pole |  |  | INPR | [17 empty] | 2019-05-28 | 2020-05-28 | 2020-10-26 | 2020-10-26 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117328791 | POLE_DECA_REPL - R/O 44810 DOUGLAS RD/1P | 35215755 |  |  | STS-POLE_DECA_REPL - R/O 44810 DOUGLAS R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2642 | -119.7312 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820014 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052860 | RELW OH PRI NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-28 | 2020-05-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117330005 | POLE_DECA_REPL - 31367 KENNEDY RD.COARSE | 35215758 |  |  | STS-POLE_DECA_REPL - 31367 KENNEDY RD.CO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2047 | -119.7093 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B | 10765 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056942 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-28 | 2020-05-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117335218 | POLE_BROK_REPL - 44648 TRABUCO RDCOARSEG | 35208803 |  |  | STS-POLE_BROK_REPL - 44648 TRABUCO RDCOA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2532 | -119.7348 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820121 | 10575 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052651 | RELW OH PRI CLR REMT ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-28 | 2020-05-28 | 2020-12-26 | 2020-12-26 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117336155 | POLE_DECA_REPL - 46525 OONAY NATION RD # | 35208808 |  |  | STS-POLE_DECA_REPL - 46525 OONAY NATION | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.2307 | -119.6985 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08213A | 10335 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060504 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-29 | 2020-05-29 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117336577 | POLE_DECA_REPL - 44617 FOXTAIL RDCOARSEG | 35208817 |  |  | STS-POLE_DECA_REPL - 44617 FOXTAIL RDCOA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2588 | -119.7337 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820015 | 10575 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103233191 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR PRTO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-29 | 2020-05-29 | 2020-10-26 | 2020-10-26 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117336722 | POLE_DECA_REPL - 44630 FOXTAIL RDCOARSEG | 35208823 |  |  | STS-POLE_DECA_REPL - 44630 FOXTAIL RDCOA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2583 | -119.7334 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820015 | 10575 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052692 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-29 | 2020-05-29 | 2020-12-26 | 2020-12-26 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117337011 | POLE_DECA_REPL - 44644 FOXTAIL RDCOARSEG | 35215778 |  |  | STS-POLE_DECA_REPL - 44644 FOXTAIL RDCOA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2576 | -119.7329 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820015 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052695 | RELW OH PRI CLR JPOL ESTR RESD TRAF FLAG BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-29 | 2020-05-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117338189 | POLE_DECA_REPL - 44705 TRABUCO RD COARSE | 35208833 |  |  | STS-POLE_DECA_REPL - 44705 TRABUCO RD CO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2512 | -119.7321 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820124 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.4 | 16.4 |  |  | 0 | 16.4 | 16.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052630 | RELW OH PRI CLR JPOL RESD ESTR BTKA FSRP PRTO FMOB TER2 | Pole | 2021-01-07 |  | COMP | 2021-01-07 | [16 empty] | 2019-05-29 | 2020-05-29 | 2020-09-24 | 2020-09-24 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 10061.58 | 13.5 | 0 | 448.2 | 448.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117338403 | POLE_DECA_REPL - TRANS STRCTR. 12/8 OAKH | 35208844 |  |  | STS-POLE_DECA_REPL - TRANS STRCTR. 12/8 | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2699 | -119.6736 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212A | 10160 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101063233 | RELW OH PRI CLR REMT FIRE NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-29 | 2020-05-29 | 2020-10-26 | 2020-10-26 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 348.8 | 335.3 | 335.3 | 335.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117338923 | POLE_DECA_REPL - 44817 FOXTAIL RD/1PSE/2 | 35208849 |  |  | STS-POLE_DECA_REPL - 44817 FOXTAIL RD/1P | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2567 | -119.7289 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820121 | 5523 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052727 | OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-05-29 | 2020-05-29 | 2020-09-26 | 2020-09-26 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117338970 | POLE_DECA_REPL - 35729 HWY 41/1PWCOARSEG | 35208854 |  |  | STS-POLE_DECA_REPL - 35729 HWY 41/1PWCOA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 37.2641 | -119.6793 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212A | 6299 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101063194 | PRI RELW OH CLR RESD FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-29 | 2020-05-29 | 2020-07-26 | 2020-07-26 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 151 | 137.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117342069 | POLE_DECA_REPL - 44669 TRABUCO RD/1PNWCO | 35208874 |  |  | STS-POLE_DECA_REPL - 44669 TRABUCO RD/1P | UNSC | UNSC ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.253 | -119.733 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820121 | 10575 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.8 | 19.8 |  |  | 0 | 19.8 | 19.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052643 | RELW OH PRI CLR REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-19 | 2021-02-19 | COMP | 2021-02-19 | [16 empty] | 2019-05-30 | 2020-05-30 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 6586.38 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117343045 | POLE_DECA_REPL - 45225 DOUGLAS RD COARSE | 35215791 |  |  | STS-POLE_DECA_REPL - 45225 DOUGLAS RD CO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2632 | -119.7237 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B | 10628 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103911225 | RELW OH PRI CLR JPOL REMT ESTR PRTO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-30 | 2020-05-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117343342 | POLE_DECA_REPL - 2 POLES EAST OF 35729 H | 35208884 |  |  | STS-POLE_DECA_REPL - 2 POLES EAST OF 357 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2647 | -119.6767 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101063211 | RELW OH PRI CLR REMT FIRE NOAC ESTR PRTO USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-30 | 2020-05-30 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 782 | 414.9 | 414.9 | 414.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117343746 | POLE_BROK_REPL - A/F 34943 HWY 41/1PW CO | 35208899 |  |  | STS-POLE_BROK_REPL - A/F 34943 HWY 41/1P | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.2551 | -119.7041 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 21.8 | 21.8 |  |  | 0 | 21.8 | 21.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101062011 | RELW OH PRI CLR RESD REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-25 |  | COMP | 2021-01-25 | [16 empty] | 2019-05-30 | 2020-05-30 | 2020-09-01 | 2020-09-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 9662.3 | 392.2 | 392.2 | 392.2 | 392.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117344746 | CRSS_DECA_REPL - 46920 FORREST GLENN RD/ | 35215806 |  |  | STS-CRSS_DECA_REPL - 46920 FORREST GLENN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2682 | -119.694 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Crossarm | Decayed/Rotten | Replace |  | 101063398 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-30 | 2020-05-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 48.3 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117346572 | TREE_DECA_INPL - 35838 HILL DR COARSEGOL | 35208929 |  |  | STS-TREE_DECA_INPL - 35838 HILL DR COARS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2695 | -119.6928 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212A | 19625 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 101063422 | RELW OH SEC CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-30 | 2020-05-30 | 2020-09-27 | 2020-09-27 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 63.3 | 49.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117364082 | POLE_DECA_REPL - SE C/O PENNY LN/RD 415C | 35208955 |  |  | STS-POLE_DECA_REPL - SE C/O PENNY LN/RD | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2629 | -119.7139 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.2 | 19.2 |  |  | 0 | 19.2 | 19.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061373 | RELW OH PRI CLR JPOL FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-13 |  | COMP | 2021-01-13 | [16 empty] | 2019-05-31 | 2020-05-31 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 10729.81 | 13.5 | 0 | 937.3 | 937.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117366917 | POLE_DECA_REPL - 46580 KONKLIN RDCOARSEG | 35140884 |  |  |  | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2581 | -119.6976 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212A | 10336 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103236722 | RELW OH PRI CLR ESTR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-31 | 2020-05-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254432104 | 1 | 548.1 | 282 | 217.2 | 217.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117370431 | POLE_DECA_REPL - 35589 TEXAS FLAT MINE R | 35208964 |  |  | STS-POLE_DECA_REPL - 35589 TEXAS FLAT MI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2658 | -119.7107 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B | 10110 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061422 | RELW PRI OH CLR JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-01 | 2020-06-01 | 2020-09-27 | 2020-09-27 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117377352 | POLE_DECA_REPL - 45577 RD 415/1PSCOARSEG | 35208985 |  |  | STS-POLE_DECA_REPL - 45577 RD 415/1PSCOA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2591 | -119.7166 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B | 5523 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.5 | 25.5 |  |  | 0 | 25.5 | 25.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061328 | RELW OH PRI CLR JPOL FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 |  | COMP | 2021-01-28 | [16 empty] | 2019-06-03 | 2020-06-03 | 2020-09-28 | 2020-09-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 21244.91 | 170.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117377891 | POLE_DECA_REPL - R/O 45806 STRAWBERRY RD | 35215882 |  |  | STS-POLE_DECA_REPL - R/O 45806 STRAWBERR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 37.2591 | -119.7075 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B | 10769 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061555 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-06-03 | 2020-06-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117378481 | POLE_DECA_REPL - 35708 TEXAS FLAT MINE R | 35208989 |  |  | STS-POLE_DECA_REPL - 35708 TEXAS FLAT MI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2689 | -119.7109 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B | 10779 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061479 | RELW OH PRI CLR JPOL REMT SPCR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-03 | 2020-06-03 | 2020-10-27 | 2020-10-27 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117379161 | POLE_DECA_REPL - 35708 TEXAS FLAT MINE R | 35154615 |  |  | STS-POLE_DECA_REPL - 35708 TEXAS FLAT MI | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 37.2695 | -119.7132 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B | 10779 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 30.6 | 30.6 |  |  | 0 | 30.6 | 30.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061463 | RELW OH PRI CLR JPOL REMT ESTR BTKA USA PROG FMOB TER2 PRTO FSRP | Pole | 2020-05-28 | 2020-05-27 | COMP | 2020-05-27 | [16 empty] | 2019-06-03 | 2020-06-03 | 2020-09-27 | 2020-09-27 | 2021 CBP Plan | 2020-12-31 | PIKEENG |  | 254432104 | 12738.49 | 212.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117383564 | POLE_DECA_REPL - #4 N/O 35708 TEXAS FLAT | 35208994 |  |  | STS-POLE_DECA_REPL - #4 N/O 35708 TEXAS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2713 | -119.7141 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B | 6210 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061483 | RELW OH REMT PRI CLR JPOL ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-04 | 2020-06-04 | 2020-08-27 | 2020-08-27 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117387342 | POLE_DECA_REPL - 45543 RD 415/1PW/1PNCOA | 35208999 |  |  | STS-POLE_DECA_REPL - 45543 RD 415/1PW/1P | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2594 | -119.7179 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061331 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-04 | 2020-06-04 | 2020-09-28 | 2020-09-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | 0 | 851 | 851 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117401614 | POLE_DECA_REPL - 31166 ROLLING MEADOW CT | 35215892 |  |  | STS-POLE_DECA_REPL - 31166 ROLLING MEADO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2006 | -119.7003 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103219131 | RELW PRI OH RESD REMT FIRE TRAF ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-06 | 2020-06-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117401915 | POLE_DECA_REPL - 31166 ROLLING MEADOW CT | 35215901 |  |  | STS-POLE_DECA_REPL - 31166 ROLLING MEADO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2013 | -119.7013 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103199692 | RELW OH PRI RESD FIRE TRAF ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-06 | 2020-06-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117408392 | POLE_DECA_REPL - 44699 TRABUCO RDCOARSEG | 35209019 |  |  | STS-POLE_DECA_REPL - 44699 TRABUCO RDCOA | APPR | APPR | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2502 | -119.7319 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820124 | 10575 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052586 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | INPR | [17 empty] | 2019-06-07 | 2020-06-07 | 2020-08-27 | 2020-08-27 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117409712 | POLE_BROK_REPL - 30101 HWY 41 2PSECOARSE | 35209054 |  |  | STS-POLE_BROK_REPL - 30101 HWY 41 2PSECO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 37.1878 | -119.7249 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000008216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15 | 15 |  |  | 0 | 15 | 15 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101055808 | RELW OH PRI RESD REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-10 |  | COMP | 2021-02-10 | [16 empty] | 2019-06-07 | 2020-06-07 | 2020-11-07 | 2020-11-07 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 5883.31 | 187.5 | 174 | 174 | 174 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117409797 | POLE_BROK_REPL - 30309 CA-41COARSEGOLD93 | 35215913 |  |  | STS-POLE_BROK_REPL - 30309 CA-41COARSEGO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1881 | -119.726 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000008216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103224703 | RELW OH PRI JPOL REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-07 | 2020-06-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Coarsegold | Oakhurst |  |  | OPEN | 117478223 | POLE_DECA_REPL - 31809 Blackfoot RdCoars | 35209086 |  |  | STS-POLE_DECA_REPL - 31809 BLACKFOOT RDC | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2114 | -119.6847 |  | TIER 2 |  |  | 0000821282 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.9 | 17.9 |  |  | 0 | 17.9 | 17.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056231 | RELW OH SERV CLR ESTR URBW RESD FIRE BTKA OTHR USA FMOB TER2 FSRP | Pole | 2021-02-03 |  | COMP | 2021-02-03 | [16 empty] | 2019-06-21 | 2020-06-21 | 2020-10-30 | 2020-10-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 10998.25 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Coarsegold | Oakhurst |  |  | OPEN | 117687626 | POLE _BROK _REPL_49330 RANCH HOUSE RD PV | 35216254 |  |  | STS-POLE _BROK _REPL_49330 RANCH HOUSE R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1685 | -119.656 |  | TIER 2 |  |  | 0000009211 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101062462 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  |  | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117956322 | POLE_DECA_REPL - 44934 RD 415Coarsegold | 35215676 |  |  | STS-POLE_DECA_REPL - 44934 RD 415COARSEG | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2487 | -119.728 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820124 | 2428 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101053764 | PRI RELW OH INSP CLR REMT FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-10-03 | 2020-10-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | COMP | 116814209 | POLE_DECA_REPL - 34651[HSE] SPANGLE GOLD | 35154380 |  |  | STS-POLE_DECA_REPL - 34651[HSE] SPANGLE | FICL | FICL SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-06-04 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.2464 | -119.7856 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008202 |  | Y | 311 |  |  | 2021-01-10 | 2021-01-10 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 11.8 | 11.8 |  |  | 0 | 0 |  |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101052320 | OH RELW PRI COMP CLR REMT ESTR BTKA USA CCNT FMOB TER2 FSRP PRTO | Pole | 2020-05-05 | 2020-05-05 | COMP | 2020-05-05 | COMP | 2021-01-10 | [13 empty] | 2021-01-13 | 2021-01-10 | 2020-03-22 | 2020-07-02 | 2020-07-02 | B-Tag Clean Up 6/8/2020 | 2020-05-01 | PIKEENG |  | 254432104 | 10850.86 | 5884.8 | 4474.4 | 14759 | 14759 |  |  |  | FRMMA/WMPMA - Electric | Y | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-06-08
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | COMP | 116880129 | POLE_BROK_REPL - 1PE 1PS 47697 RD.200COA | 35178956 |  |  | STS-POLE_BROK_REPL - 1PE 1PS 47697 RD.20 | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-16 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.1391 | -119.6818 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000009213 | 5369 | Y | 311 |  |  | 2021-02-16 07:00 | 2021-02-16 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101062706 | RELW OH PRI COMP CLR ESTR USA CCNT FMOB TER2 PRTO FSRP | Pole | 2020-06-25 | 2020-06-25 | COMP | 2020-06-25 | COMP | 2021-02-16 | [13 empty] | 2021-02-18 | 2021-02-16 | 2020-04-01 | 2020-08-13 | 2020-08-13 | B-Tag Addition 06.24.20 |  | Bakersfield |  | 254432103 | 32622.65 | 5286.4 | [7 empty] | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116790344 | POLE_BROK_REPL - 36017 FRANKLIN RDCOARSE | 35208863 |  |  | STS-POLE_BROK_REPL - 36017 FRANKLIN RDCO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2731 | -119.7464 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000007205 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 34.3 | 33.7 | 0.6 |  | 0 | 34.3 | 33.7 | 0.6 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101022930 | RELW OH SEC CLR RESD FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-27 | 2021-02-03 | COMP | 2021-01-27 |  |  | 2021-01-29 | 2021-02-03 | [12 empty] | 2019-03-20 | 2020-03-20 | 2020-10-05 | 2020-10-05 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 14389.15 | 913.6 | 900.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116807460 | POLE_DECA_REPL - 36772 BATTI RD/1PNWCOAR | 35208912 |  |  | STS-POLE_DECA_REPL - 36772 BATTI RD/1PNW | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2854 | -119.7469 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000007205 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 23.3 | 23.3 |  |  | 0 | 23.3 | 23.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101022695 | OH PRI CLR RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP RELW | Pole | 2021-01-15 | 2021-02-03 | COMP | 2021-01-15 |  |  | 2021-01-29 | 2021-02-03 | [12 empty] | 2019-03-21 | 2020-03-21 | 2020-09-02 | 2020-09-02 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 12799.56 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116815463 | POLE_DECA_REPL - 42827 BEAN GULCH RD/1PE | 35208953 |  |  | STS-POLE_DECA_REPL - 42827 BEAN GULCH RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2497 | -119.7686 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 15 | 15 |  |  | 0 | 15 | 15 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101054725 | PRI OH RELW ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-26 | 2021-01-26 | COMP | 2021-01-26 | [16 empty] | 2019-03-22 | 2020-03-22 | 2020-09-23 | 2020-09-23 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 6378.31 | 1036.6 | 1023.1 | 1274 | 1274 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116815565 | POLE_DECA_REPL - 42827 BEAN GULCH RD/2PE | 35154392 |  |  | STS-POLE_DECA_REPL - 42827 BEAN GULCH RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2496 | -119.7676 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.8 | 23.8 |  |  | 0 | 23.8 | 23.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101054726 | RELW OH PRI NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-05-14 | 2020-05-14 | COMP | 2020-05-14 | [16 empty] | 2019-03-22 | 2020-03-22 | 2020-09-23 | 2020-09-23 | 2021 CBP Plan | 2020-05-01 | PIKEENG |  | 254432104 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116820433 | POLE_BROK_REPL - 35600 WELLS RDCOARSEGOL | 35178794 |  |  | STS-POLE_BROK_REPL - 35600 WELLS RDCOARS | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2662 | -119.7384 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 | 6288 | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 44.3 | 43 | 1.3 |  | 0 | 44.3 | 43 | 1.3 |  | EC | B | Pole | Broken/Damaged | Replace |  | 101052918 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-07-08 | 2020-10-29 | COMP | 2020-07-08 |  |  | 2020-12-23 | 2020-12-23 | [12 empty] | 2019-03-24 | 2020-03-24 | 2020-08-14 | 2020-08-14 | B-Tag Addition 06.24.20 |  | Fresno |  | 254432104 | 21619.2 | -1345.4 | -1579.4 | 2633.5 | 2633.5 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-06-29
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116821390 | POLE_DECA_REPL - 35839 WELLS RD/IN YARD/ | 35178798 |  |  | STS-POLE_DECA_REPL - 35839 WELLS RD/IN Y | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2697 | -119.7364 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 | 6288 | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 38.1 | 38.1 |  |  | 0 | 38.1 | 38.1 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101053049 | RELW OH PRI CLR NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-04 | 2020-12-07 | COMP | 2020-12-03 | [16 empty] | 2019-03-24 | 2020-03-24 | 2020-08-14 | 2020-08-14 | B-Tag Addition 06.24.20 |  | Fresno |  | 254432104 | 18043.62 | 2130.9 | 2130.9 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-06-29
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116821798 | POLE_BROK_REPL - 35910 WELLS RD/2PW COAR | 35178940 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.27 | -119.7404 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 |  | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 2.25 | 39.55 | 39.55 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101053061 | RELW OH PRI CLR NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-08-04 | 2020-08-04 | COMP | 2020-08-04 | [16 empty] | 2019-03-24 | 2020-03-24 | 2020-08-20 | 2020-08-20 | B-Tag Addition 06.24.20 |  | Fresno |  | 254432104 | 23415.1 | 7226 | 38.6 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-06-29
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116821988 | POLE_BROK_REPL - A/F 35946 WELLS RD COAR | 35209005 |  |  | STS-POLE_BROK_REPL - A/F 35946 WELLS RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2711 | -119.7388 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 22.6 | 22.6 |  |  | 0 | 22.6 | 22.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101053068 | RELW OH PRI FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 | 2021-02-03 | COMP | 2021-01-19 |  |  | 2021-01-29 | 2021-02-03 | [12 empty] | 2019-03-24 | 2020-03-24 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 11941.64 | 361.5 | 348 | 1448 | 1448 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116823296 | POLE_DECA_REPL - R/O 35941 FRANKLIN RDCO | 35178944 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2709 | -119.7459 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 | 735111 | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 1.75 | 39.25 | 39.25 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101053187 | RELW OH PRI REMT ESTR BTKA REAR PROG FMOB TER2 PRTO FSRP | Pole | 2020-06-11 | 2020-06-11 | COMP | 2020-06-11 | [16 empty] | 2019-03-24 | 2020-03-24 | 2020-08-20 | 2020-08-20 | B-Tag Addition 07.06.2020 |  | Fresno |  | 254432104 | 17799.8 | 4020.2 | 41.5 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-07-06
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116824902 | POLE_DECA_REPL - R/O 35465 FRANKLIN RDCO | 35178945 |  |  | STS-POLE_DECA_REPL - R/O 35465 FRANKLIN | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2714 | -119.7462 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 | 735111 | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101053181 | RELW OH PRI ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2020-06-11 | 2020-06-11 | COMP | 2020-06-11 | [16 empty] | 2019-03-25 | 2020-03-25 | 2020-08-20 | 2020-08-20 | B-Tag Addition 07.06.2020 |  | Bakersfield |  | 254432104 | 16803.28 | 3423.7 | 156.3 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-07-06
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116878867 | POLE_DECA_REPL - 1P/E 47023 RD.COARSEGOL | 35177570 |  |  | B STS-POLE_DECA_REPL - 1P/E 47023 RD.COA | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1314 | -119.6909 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000009213 |  | Y | 311 |  |  | 2021-02-16 07:00 | 2021-02-16 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 11.5 | 39 | 39 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101062668 | RELW OH PRI CLR JPOL RESD ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-06-02 | 2020-06-04 | COMP | 2020-06-02 | [16 empty] | 2019-03-31 | 2020-03-31 |  | 2020-03-31 | B-Tag Clean Up 6/8/2020 |  | Concord |  | 254432103 | 17229.53 | 6296.2 | -360.8 | -954.8 | -954.8 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-06-08
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116951662 | POLE_DECA_REPL - END OF EDEN LNCOARSEGOL | 35178959 |  |  | STS-POLE_DECA_REPL - END OF EDEN LNCOAR | CONS | CONS ERDY SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2617 | -119.7372 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 |  | Y | 311 |  |  | 2021-02-19 07:00 | 2021-02-19 16:00 | Completed | CLICK | [6 empty] | 41.9 | 41.9 |  |  | 0.5 | 41.4 | 41.4 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101052814 | RELW BTKA OH PRI ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-06-26 | 2020-07-24 | COMP | 2020-06-26 |  |  | 2020-07-24 | 2020-07-24 | [12 empty] | 2019-04-03 | 2020-04-03 | 2020-08-18 | 2020-08-18 | B-Tag Addition 06.24.20 |  | Fresno |  | 254432104 | 11842.97 | 3353.1 | 38.1 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117230852 | POLE_DECA_REPL - 36927 HWY 41[IN YARD]CO | 35208792 |  |  | STS-POLE_DECA_REPL - 36927 HWY 41[IN YAR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2854 | -119.6553 |  | TIER 2 |  |  | 07215C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.2 | 16.2 |  |  | 0 | 16.2 | 16.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101026660 | OH SEC REMT NOAC ESTR GO USA FMOB TER2 PRTO FSRP RELW | Pole | 2021-02-05 | 2021-02-05 | COMP | 2021-02-05 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-12-24 | 2020-12-24 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 10900.56 | 745.8 | 732.4 | 465.9 | 465.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117232782 | POLE_DECA_REPL - R/O 42786 SERPA CANYON | 35208831 |  |  | STS-POLE_DECA_REPL - R/O 42786 SERPA CAN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2856 | -119.6698 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 07215C | 10338 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 39.8 | 39.8 |  |  | 0 | 39.8 | 39.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101026605 | RELW OH PRI RESD REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-14 | 2020-12-14 | COMP | 2020-12-14 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 17987.49 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117234918 | POLE_DECA_REPL - 32370 CHICKASAW RDCOARS | 35208867 |  |  | STS-POLE_DECA_REPL - 32370 CHICKASAW RDC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2192 | -119.6851 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821213 | 10783 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.7 | 33.7 |  |  | 0 | 33.7 | 33.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060947 | RELW OH PRI FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-15 | 2020-12-15 | COMP | 2020-12-15 |  |  | 2020-12-04 | 2020-12-04 | [12 empty] | 2019-05-14 | 2020-05-14 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 15737.13 | 13.5 | 0 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117238830 | POLE_DECA_REPL - 33060 ROBINHOOD DR 1PSC | 35178528 |  |  | STS-POLE_DECA_REPL - 33060 ROBINHOOD DR | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2285 | -119.7352 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204A | 369777 | Y | 311 |  |  | 2021-03-10 07:00 | 2021-03-10 16:00 | Dispatched | CLICK | [6 empty] | 51.4 | 51.4 |  |  | 5 | 50.4 | 50.4 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 103330932 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-06-29 | 2020-11-07 | COMP | 2020-06-28 |  |  | 2020-07-08 | 2020-07-08 | [12 empty] | 2019-05-15 | 2020-05-15 | 2020-08-16 | 2020-08-16 | B-Tag Addition 06.24.20 |  | Fresno |  | 254432104 | 26659.26 | 8076.6 | 5446.6 | 5453.9 | 5453.9 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-06-29
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117239714 | POLE_DECA_REPL - 47226 OTTOWA AVE 1PW 1P | 35208913 |  |  | STS-POLE_DECA_REPL - 47226 OTTOWA AVE 1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2191 | -119.6875 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821213 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.8 | 15.8 |  |  | 0 | 15.8 | 15.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060991 | RELW OH SERV NOAC ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-15 | 2020-12-15 | COMP | 2020-12-15 | [16 empty] | 2019-05-15 | 2020-05-15 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 8936.21 | 13.5 | -1013.6 | -470.6 | -470.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117255026 | POLE_DECA_REPL - DELAWARE/DELAWARE CT 2P | 35209074 |  |  | STS-POLE_DECA_REPL - DELAWARE/DELAWARE C | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2126 | -119.6785 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821281 | 2304 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 29.9 | 29.9 |  |  | 0 | 29.9 | 29.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056652 | RELW ESTR OH PRI CLR FMOB TER2 PRTO FSRP | Pole | 2020-12-17 | 2020-12-17 | COMP | 2020-12-17 | [16 empty] | 2019-05-17 | 2020-05-17 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 21593.67 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117268546 | POLE_DECA_REPL - 47663 WILLOW POND RD.CO | 35209165 |  |  | STS-POLE_DECA_REPL - 47663 WILLOW POND R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2011 | -119.6777 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821285 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 11.4 | 11.4 |  |  | 0 | 11.4 | 11.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103224710 | RELW OH SEC RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-17 | 2020-12-17 | COMP | 2020-12-17 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 5022.4 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117269124 | POLE_DECA_REPL - 47459 MODOC RD 1PE 1PN/ | 35209196 |  |  | STS-POLE_DECA_REPL - 47459 MODOC RD 1PE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2176 | -119.6834 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821216 | 10783 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 46.7 | 46.7 |  |  | 0 | 46.7 | 46.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060671 | RELW OH PRI RESD REMT FIRE ESTR GO BTKA USA PROG FMOB TER2 PRTO FSRP | Pole | 2021-02-09 | 2021-02-09 | COMP | 2021-02-09 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-09-05 | 2020-09-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 19201.25 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117269626 | POLE_BROK_REPL - 31200 WILLOW POND LN 1P | 35209220 |  |  | STS-POLE_BROK_REPL - 31200 WILLOW POND L | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2013 | -119.676 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821285 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 12.3 | 12.3 |  |  | 0 | 12.3 | 12.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103329483 | RELW OH SEC RESD REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-17 | 2020-12-17 | COMP | 2020-12-17 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 5454.98 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117270069 | POLE_DECA_REPL - DELAWARE RD OTTAWA AVE | 35209238 |  |  | STS-POLE_DECA_REPL - DELAWARE RD OTTAWA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2187 | -119.6836 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 10 | 10 |  |  | 0 | 10 | 10 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060642 | RELW OH FIRE SEC RESD REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-01 | 2021-02-01 | COMP | 2021-02-01 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-10-05 | 2020-10-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 6312.12 | 13.5 | 0 | 1159 | 1159 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117277222 | POLE_DECA_REPL - ERIE/HOPI 1PSW/1PWCOARS | 35209384 |  |  | STS-POLE_DECA_REPL - ERIE/HOPI 1PSW/1PWC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2035 | -119.6755 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821285 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.8 | 12.2 | 0.6 |  | 0 | 12.8 | 12.2 | 0.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056610 | RELW OH SEC RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-10 | 2021-02-10 | COMP | 2021-02-10 | [16 empty] | 2019-05-20 | 2020-05-20 | 2020-05-31 | 2020-05-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 5421.34 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117277519 | POLE_BROK_REPL - ERIE/HOPI 1PSW COARSEGO | 35209389 |  |  | STS-POLE_BROK_REPL - ERIE/HOPI 1PSW COAR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2036 | -119.6751 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821285 | 5506 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.5 | 44.5 |  |  | 0 | 44.5 | 44.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101056611 | RELW OH SEC RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-10 | 2021-02-10 | COMP | 2021-02-10 | [16 empty] | 2019-05-20 | 2020-05-20 | 2020-10-05 | 2020-10-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 20063.4 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117291332 | POLE_DECA_REPL - HWY 41/MECCA LNCOARSEGO | 35177982 |  |  | STS-POLE_DECA_REPL - HWY 41/MECCA LNCOAR | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.19 | -119.7248 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000008216 |  | Y | 311 |  |  | 2021-02-19 07:00 | 2021-02-19 16:00 | Completed | CLICK | [6 empty] | 41 | 41 |  |  | 2.75 | 38.25 | 38.25 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101055797 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-06-26 | 2020-09-28 | COMP | 2020-06-25 |  |  | 2020-09-28 | 2020-09-28 | [12 empty] | 2019-05-21 | 2020-05-21 | 2020-08-08 | 2020-08-08 | B-Tag Addition 06.24.20 |  | Fresno |  | 254432103 | 11280.25 | 6649.7 | -15404.6 | 8.1 | 8.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-06-29
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117307335 | POLE_DECA_REPL - 47947 RD417 12N 22PE/OC | 35154259 |  |  | STS-POLE_DECA_REPL - 47947 RD417 12N 22P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2305 | -119.6504 |  | TIER 2 | 385 | 25443-2102, COARSEGOLD | 0000008214 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.7 | 33.7 |  |  | 0 | 33.7 | 33.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101055616 | RELW OH PRI CLR JPOL REMT FIRE NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-06-25 | 2020-07-02 | COMP | 2020-06-25 | [16 empty] | 2019-05-23 | 2020-05-23 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2020-12-31 | PIKEENG |  | 254432102 | 26547.87 | 2066.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117317886 | POLE_DECA_REPL - LUCKY LN/RD 417 4PWCOAR | 35209679 |  |  | STS-POLE_DECA_REPL - LUCKY LN/RD 417 4PW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2139 | -119.703 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.5 | 16.5 |  |  | 0 | 16.5 | 16.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056979 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-14 | 2020-12-17 | COMP | 2020-12-14 | [16 empty] | 2019-05-24 | 2020-05-24 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 7942.01 | 219.9 | -801.5 | -484.8 | -484.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117325615 | POLE_DECA_REPL - HOGANS MTN RD/HWY 41 1P | 35177423 |  |  | STS-POLE_DECA_REPL - HOGANS MTN RD/HWY 4 | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2051 | -119.7165 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B |  | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 26.9 | 26.9 |  |  | 1 | 25.9 | 25.9 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101055928 | RELW OH PRI CLR JPOL FMOB RESD NOAC ESTR TER2 PRTO FSRP | Pole | 2020-06-19 | 2020-11-18 | COMP | 2020-06-02 |  |  | 2020-07-21 | 2020-07-21 | [12 empty] | 2019-05-27 | 2020-05-27 | 2020-08-11 | 2020-08-11 | B-Tag Clean Up 6/8/2020 |  | San Francisco |  | 254432103 | 16970.69 | 3796.5 | 3658.9 | 3599.6 | 3599.6 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-06-08
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117326763 | POLE_DECA_REPL - A/F 44700 DOUGLAS RDCOA | 35154429 |  |  | STS-POLE_DECA_REPL - A/F 44700 DOUGLAS R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-06-05 |  | 37.2677 | -119.7324 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820011 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.3 | 18.3 |  |  | 0 | 18.3 | 18.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052939 | RELW OH PRI FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-05-12 | 2020-06-05 | COMP | 2020-05-12 |  |  | 2020-06-03 | 2020-06-05 | [12 empty] | 2019-05-28 | 2020-05-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | PIKEENG |  | 254432104 | 10304.7 | 672.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117328218 | POLE_DECA_REPL - A/F 44700 DOUGLAS RD/2P | 35209784 |  |  | STS-POLE_DECA_REPL - A/F 44700 DOUGLAS R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2675 | -119.7286 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820011 | 10628 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.5 | 44.5 |  |  | 0 | 44.5 | 44.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103088295 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-08 | 2021-02-08 | COMP | 2021-02-08 | [16 empty] | 2019-05-28 | 2020-05-28 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 18141.82 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117337482 | POLE_DECA_REPL - TRANS STRCTR. 12/6 OAKH | 35154449 |  |  | STS-POLE_DECA_REPL - TRANS STRCTR. 12/6 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2683 | -119.6756 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43.2 | 43.2 |  |  | 0 | 43.2 | 43.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101063225 | RELW OH PRI CLR REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-05-18 | 2020-06-24 | COMP | 2020-05-18 | [16 empty] | 2019-05-29 | 2020-05-29 | 2020-10-26 | 2020-10-26 | 2021 CBP Plan | 2020-12-31 | PIKEENG |  | 254432104 | 20205.39 | 401.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117338337 | POLE_DECA_REPL - 44699 TRABUCO RD/1PS CO | 35154453 |  |  | STS-POLE_DECA_REPL - 44699 TRABUCO RD/1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-02-24 | Permit Expiring Schedule Job/Request Extension | 37.2497 | -119.7318 |  | TIER 2 |  |  | 0000820124 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 10.4 | 10.4 |  |  | 0 | 10.4 | 10.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052584 | RELW OH RESD PRI CLR JPOL ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-05-14 | 2020-05-14 | COMP | 2020-05-14 |  |  | 2020-02-20 | 2020-02-26 | [12 empty] | 2019-05-29 | 2020-05-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | PIKEENG |  |  | 7308.35 | 806.4 |  |  |  | 575.4 |  | 575.4 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117344137 | POLE_DECA_REPL - 35580-A SPANISH OAKCOAR | 35208909 |  |  | STS-POLE_DECA_REPL - 35580-A SPANISH OAK | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2678 | -119.7013 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B | 10337 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48.1 | 48.1 |  |  | 0 | 48.1 | 48.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061639 | RELW OH PRI CLR TRAF RESD REMT FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-27 | 2021-01-27 | COMP | 2021-01-27 |  |  | 2020-12-23 | 2020-12-23 | [12 empty] | 2019-05-30 | 2020-05-30 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 20700.91 | 53.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117345899 | POLE_DECA_REPL - 46567 MC CALISTER RDCOA | 35154542 |  |  | STS-POLE_DECA_REPL - 46567 MC CALISTER R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2694 | -119.6962 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16 | 16 |  |  | 0 | 16 | 16 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101063363 | RELW PRI OH CLR RESD REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-05-22 | 2020-06-05 | COMP | 2020-05-21 | [16 empty] | 2019-05-30 | 2020-05-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | PIKEENG |  | 254432104 | 6046.04 | 83 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117370632 | POLE_DECA_REPL - R/O OAK CREEK PARK/4604 | 35154589 |  |  | STS-POLE_DECA_REPL - R/O OAK CREEK PARK/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2676 | -119.7087 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44 | 44 |  |  | 0 | 44 | 44 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061699 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-05-27 | 2020-05-27 | COMP | 2020-05-27 | [16 empty] | 2019-06-01 | 2020-06-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | PIKEENG |  | 254432104 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117383976 | POLE_DECA_REPL - 34419 RD 415/1PNCOARSEG | 35154620 |  |  | STS-POLE_DECA_REPL - 34419 RD 415/1PNCOA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2485 | -119.7042 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212C | 10336 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 46.5 | 46.5 |  |  | 0 | 46.5 | 46.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101062045 | RELW OH PRI REMT FIRE CGI ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-06-25 | 2020-06-25 | COMP | 2020-06-25 | [16 empty] | 2019-06-04 | 2020-06-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | PIKEENG |  | 254432104 | 24330.88 | 458 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117387460 | POLE_DECA_REPL - #4 N/O 35708 TEXAS FLAT | 35209004 |  |  | STS-POLE_DECA_REPL - #4 N/O 35708 TEXAS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2719 | -119.7185 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 22.1 | 22.1 |  |  | 0 | 22.1 | 22.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061701 | RELW OH PRI NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-21 | 2020-12-21 | COMP | 2020-12-21 | [16 empty] | 2019-06-04 | 2020-06-04 | 2020-09-27 | 2020-09-27 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 8503.62 | 943.5 | 930.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117404742 | POLE_DECA_REPL - 30564 HOGANS MTN RD 1PE | 35209009 |  |  | STS-POLE_DECA_REPL - 30564 HOGANS MTN RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1982 | -119.7154 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000008216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.1 | 17.1 |  |  | 0 | 17.1 | 17.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101055886 | RELW OH PRI REMT FIRE CGI SPCR ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-10 | 2020-12-10 | COMP | 2020-12-10 | [16 empty] | 2019-06-06 | 2020-06-06 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 6697.3 | 13.5 | -724 | -362 | -362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117409635 | POLE_BROK_REPL - 30101 HWY 41 3PSECOARSE | 35209049 |  |  | STS-POLE_BROK_REPL - 30101 HWY 41 3PSECO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1876 | -119.7238 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000008216 | 10037 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.7 | 39.7 |  |  | 0 | 39.7 | 39.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101055809 | RELW OH PRI JPOL RESD USA FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 | 2021-01-28 | COMP | 2021-01-28 | [16 empty] | 2019-06-07 | 2020-06-07 | 2020-11-07 | 2020-11-07 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 16703.72 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 116815280 | POLE_DECA_REPL - 42636 BEAN GULCH RD/2PN | 35208948 |  |  | STS-POLE_DECA_REPL - 42636 BEAN GULCH RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2458 | -119.7699 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 | 5678 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 31.9 | 31.3 | 0.6 |  | 0 | 31.9 | 31.3 | 0.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101054678 | RELW OH PRI CLR NOAC ESTR USA FSRP FMOB TER2 PRTO | Pole | 2021-01-25 | 2021-01-25 | COMP | 2021-01-25 | [16 empty] | 2019-03-22 | 2020-03-22 | 2020-09-23 | 2020-09-23 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 13689.98 | 13.5 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117239574 | POLE_BROK_REPL - 33055 ROBINHOOD DR 4PE/ | 35208903 |  |  | STS-POLE_BROK_REPL - 33055 ROBINHOOD DR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2285 | -119.732 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204A | 259803 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.2 | 39.2 |  |  | 0 | 39.2 | 39.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101050565 | RELW OH PRI FLAG ESTR BTKA REAR USA FSRP PRTO FMOB TER2 | Pole | 2021-01-25 | 2021-01-25 | COMP | 2021-01-25 |  |  | 2020-12-23 | 2020-12-23 | [12 empty] | 2019-05-15 | 2020-05-15 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 17195.04 | 118.2 | 118.2 | 118.2 | 118.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117240133 | POLE_DECA_REPL - 33050 RD 416 3PN/NIFCOA | 35208923 |  |  | STS-POLE_DECA_REPL - 33050 RD 416 3PN/NI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.232 | -119.7376 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204A | 369777 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.2 | 41.2 |  |  | 0 | 41.2 | 41.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103088544 | RELW OH PRI NOAC ESTR REAR FMOB FSRP PRTO TER2 | Pole | 2021-01-21 | 2021-01-21 | COMP | 2021-01-21 | [16 empty] | 2019-05-15 | 2020-05-15 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 25660.05 | 13.5 | 0 | 489 | 489 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117257544 | POLE_BROK_REPL - 32044 DELAWARE RD COARS | 35209109 |  |  | STS-POLE_BROK_REPL - 32044 DELAWARE RD C | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2149 | -119.6807 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821215 | 10536 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48.5 | 48.5 |  |  | 0 | 48.5 | 48.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101060629 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-01-20 | COMP | 2021-01-20 | [16 empty] | 2019-05-17 | 2020-05-17 | 2020-11-05 | 2020-11-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 20507.57 | 13.5 | 0 | 1222.5 | 1222.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117269091 | POLE_DECA_REPL - RD 417/QUARTZ MTN RD 2P | 35209191 |  |  | STS-POLE_DECA_REPL - RD 417/QUARTZ MTN R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.21 | -119.6891 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 | 23266 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 42.2 | 42.2 |  |  | 0 | 42.2 | 42.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056270 | RELW OH PRI CLR JPOL RESD FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-25 | 2021-01-25 | COMP | 2021-01-25 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 17193.88 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117270361 | POLE_BROK_REPL - 31484 SIOUX 1PSWCOARSEG | 35209253 |  |  | STS-POLE_BROK_REPL - 31484 SIOUX 1PSWCOA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2043 | -119.6737 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821284 | 5506 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 36.9 | 36.9 |  |  | 0 | 36.9 | 36.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057060 | RELW OH PRI CLR ESTR GO FMOB TER2 PRTO FSRP | Pole | 2021-01-25 | 2021-01-25 | COMP | 2021-01-25 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-11-05 | 2020-11-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 16418.87 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117270633 | POLE_DECA_REPL - PP 1/S OF CORNER HOPI A | 35209289 |  |  | STS-POLE_DECA_REPL - PP 1/S OF CORNER HO | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2033 | -119.6785 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821285 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.3 | 12.3 |  |  | 0 | 12.3 | 12.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056606 | RELW OH SEC RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-13 | 2021-01-13 | COMP | 2021-01-13 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-09-05 | 2020-09-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 10853.21 |  | 0 | 1711.5 | 1711.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117293116 | POLE_DECA_REPL - 31541 APACHE 1PS/1PE CO | 35209469 |  |  | STS-POLE_DECA_REPL - 31541 APACHE 1PS/1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2062 | -119.6835 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821283 | 21546 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.1 | 37.1 |  |  | 0 | 37.1 | 37.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056158 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-21 | 2021-01-21 | COMP | 2021-01-21 | [16 empty] | 2019-05-21 | 2020-05-21 | 2020-07-30 | 2020-07-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 14881.58 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117319714 | POLE_DECA_REPL - 30936 HOGANS MTN RD 2PN | 35209695 |  |  | STS-POLE_DECA_REPL - 30936 HOGANS MTN RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1996 | -119.7159 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08216B | 5868 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 43.7 | 43.7 |  |  | 0 | 43.7 | 43.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101055897 | RELW OH PRI CLR JPOL REMT ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-25 | 2021-01-25 | COMP | 2021-01-25 | [16 empty] | 2019-05-25 | 2020-05-25 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 20850.95 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117343525 | POLE_DECA_REPL - 35215 CUTTER RDCOARSEGO | 35208889 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2605 | -119.7066 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B | 10769 | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-04 15:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061536 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA PROG FSRP PRTO FMOB TER2 | Pole | 2021-01-21 | 2021-01-21 | COMP | 2021-01-21 | [16 empty] | 2019-05-30 | 2020-05-30 | 2020-07-27 | 2020-07-27 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 18884.8 | 800.3 | 706.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117363327 | POLE_BROK_REPL - 45911 PENNY LN COARSEGO | 35208934 |  |  | STS-POLE_BROK_REPL - 45911 PENNY LN COAR | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2621 | -119.7108 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B | 53825 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 56.8 | 56 | 0.8 |  | 0.75 | 56.05 | 55.25 | 0.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101061355 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB FSRP PRTO TER2 | Pole | 2021-01-19 | 2021-01-19 | COMP | 2021-01-19 | [16 empty] | 2019-05-31 | 2020-05-31 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 23018.85 | 145.5 | 132 | 704.7 | 704.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117363984 | POLE_BROK_REPL - 45364 DOUGLAS FIG RD CO | 35208949 |  |  | STS-POLE_BROK_REPL - 45364 DOUGLAS FIG R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2644 | -119.7214 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B | 10628 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.4 | 38.4 |  |  | 0 | 38.4 | 38.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101061303 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 | 2021-01-19 | COMP | 2021-01-19 | [16 empty] | 2019-05-31 | 2020-05-31 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 16712.87 | 131.6 | 118.2 | 892.4 | 892.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117370479 | POLE_DECA_REPL - R/O OAK CREEK PARK/4604 | 35208969 |  |  | STS-POLE_DECA_REPL - R/O OAK CREEK PARK/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2667 | -119.7108 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.1 | 19.1 |  |  | 0 | 19.1 | 19.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061421 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-22 | 2021-01-22 | COMP | 2021-01-22 | [16 empty] | 2019-06-01 | 2020-06-01 | 2020-09-27 | 2020-09-27 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 8367.15 | 53.8 | 0 | 366.8 | 366.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117230663 | POLE_BROK_REPL - 43667 RANCHO DE FRUTALN | 35209794 |  |  | STS-POLE_BROK_REPL - 43667 RANCHO DE FRU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2333 | -119.751 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.1 | 14.1 |  |  | 0 | 14.1 | 14.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101050712 | RELW OH PRI NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-07 | 2021-01-07 | COMP | 2021-01-07 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 4661.56 | 13.5 | 0 | 489 | 489 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117231284 | 3OLE_DECA_REPL - 49150 CAVIN LN\1PNWCOAR | 35208805 |  |  | STS-POLE_DECA_REPL - 49150 CAVIN LN\1PNW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2832 | -119.6527 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 07215C | 10788 | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101026690 | RELW OH PRI RESD REMT NOAC ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-28 | 2020-12-28 | COMP | 2020-12-28 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 23751.87 | 94.2 | 0 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117242343 | POLE_DECA_REPL - 31933 CHEROKEE RDCOARSE | 35208937 |  |  | STS-POLE_DECA_REPL - 31933 CHEROKEE RDCO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2132 | -119.6817 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821281 |  | Y | 311 |  |  | 2021-06-25 07:00 | 2021-06-25 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056632 | RELW OH SEC ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-30 | 2020-12-30 | COMP | 2020-12-30 | [16 empty] | 2019-05-15 | 2020-05-15 | 2020-12-28 | 2020-12-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 3888.85 | 983.5 | 970.1 | 271.5 | 271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117262250 | POLE_DECA_REPL - 47315 NAVAJO AVE 1PE/OC | 35105462 |  |  | STS-POLE_DECA_REPL - 47315 NAVAJO AVE 1P | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 37.2167 | -119.685 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821216 | 10783 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 41.2 | 41.2 |  |  | 0 | 41.2 | 41.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060665 | OH RELW PRI RESD REMT FIRE FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-01 |  | COMP | 2020-12-01 |  |  | 2021-02-08 | 2021-02-12 | [12 empty] | 2019-05-17 | 2019-10-17 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2020-09-30 | QUES |  | 254432103 | 26437.17 | 1685 | 936 | -181 | -181 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117268516 | POLE_BROK_REPL - 47663 WILLOW POND RD 1P | 35209161 |  |  | STS-POLE_BROK_REPL - 47663 WILLOW POND R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2011 | -119.6779 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821285 |  | Y | 311 |  |  | 2021-06-25 07:00 | 2021-06-25 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101056622 | RELW OH SEC RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-06 | 2021-01-06 | COMP | 2021-01-06 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 14401.13 | 13.5 | 0 | 353 | 353 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117269060 | POLE_DECA_REPL - 31308 ERIE RD 13PNCOARS | 35209186 |  |  | STS-POLE_DECA_REPL - 31308 ERIE RD 13PNC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2112 | -119.6729 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821281 | 5506 | Y | 311 |  |  | 2021-06-25 07:00 | 2021-06-25 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103089427 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-07 | 2021-01-07 | COMP | 2021-01-07 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 14438.76 | 94.2 | 0 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117270153 | POLE_DECA_REPL - APACHE/RD 417 2PNE/1PSE | 35209243 |  |  | STS-POLE_DECA_REPL - APACHE/RD 417 2PNE/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2133 | -119.6867 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821282 |  | Y | 311 |  |  | 2021-06-25 07:00 | 2021-06-25 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056210 | RELW OH SEC CLR JPOL RESD FIRE FLAG ESTR GO BTKA USA PROG FMOB TER2 PRTO FSRP | Pole | 2021-01-06 | 2021-01-06 | COMP | 2021-01-06 |  |  | 2020-12-30 | 2020-12-30 | [12 empty] | 2019-05-18 | 2020-05-18 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 10864.98 | 13.5 | 0 | 353 | 353 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117270649 | POLE_BROK_REPL - 31680 SIOUXCOARSEGOLD93 | 35209298 |  |  | STS-POLE_BROK_REPL - 31680 SIOUXCOARSEGO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2088 | -119.6738 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821284 | 5506 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057067 | RELW OH PRI CLR ESTR GO FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2020-11-04 | 2020-11-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117272323 | POLE_BROK_REPL - DELAWARE/DELAWARE CT 1P | 35209349 |  |  | STS-POLE_BROK_REPL - DELAWARE/DELAWARE C | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2084 | -119.6777 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821284 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.2 | 13.2 |  |  | 0 | 13.2 | 13.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057032 | RELW OH SEC ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-30 | 2020-12-30 | COMP | 2020-12-30 | [16 empty] | 2019-05-19 | 2020-05-19 | 2020-11-04 | 2020-11-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 11590.91 | 983.5 | 970.1 | 271.5 | 271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117295327 | POLE_DECA_REPL - 31308 ERIE RD 1PSECOARS | 35209519 |  |  | STS-POLE_DECA_REPL - 31308 ERIE RD 1PSEC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2014 | -119.6713 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000008215 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 19.9 | 19.9 |  |  | 0 | 19.9 | 19.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101055481 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-06 | 2021-01-06 | COMP | 2021-01-06 | [16 empty] | 2019-05-21 | 2020-05-21 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 7061.44 | 53.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117328888 | POLE_DECA_REPL - R/O 44810 DOUGLAS RD/1P | 35209795 |  |  | STS-POLE_DECA_REPL - R/O 44810 DOUGLAS R | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2653 | -119.7311 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820014 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.8 | 14.8 |  |  | 0 | 14.8 | 14.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052894 | RELW OH SERV NOAC ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-05 | 2021-01-05 | COMP | 2021-01-04 | [16 empty] | 2019-05-28 | 2020-05-28 | 2020-10-26 | 2020-10-26 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 5210.86 | 13.5 | 0 | 688 | 688 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COARSEGOLD | Oakhurst |  |  | OPEN | 117339996 | POLE_DECA_REPL - 28700 HWY41 COARSEGOLD | 35208864 |  |  | STS-POLE_DECA_REPL - 28700 HWY41 COARSEG | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1697 | -119.7267 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000009212 | 10037 | Y | 311 |  |  | 2021-06-25 07:00 | 2021-06-25 16:00 | Reserved | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101062276 | RELW OH PRI JPOL REMT ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2021-01-11 | 2021-01-11 | COMP | 2021-01-11 | [16 empty] | 2019-05-29 | 2020-05-29 | 2020-11-10 | 2020-11-10 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 18000.61 | 13.5 | 0 | 692.7 | 692.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COLTURVILLE | Mariposa |  |  | OPEN | 117338401 | TREE_DECA_INPL - 9799 HOTZLE ROADCOLTURV | 35208837 |  |  | STS-TREE_DECA_INPL - 9799 HOTZLE ROADCOL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.7227 | -120.0982 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002176 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103228103 | RELW OH SERV FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-29 | 2020-05-29 | 2020-09-06 | 2020-09-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192105 | 1 | 53.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COLUMBIA | Sonora |  |  | COMP | 117110008 | POLE_BROK_REPL - 23339 ITALIAN BAR RDCOL | 35154134 |  |  | STS-POLE_BROK_REPL - 23339 ITALIAN BAR R | DOCC | DOCC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.0451 | -120.396 |  | TIER 2 | 157 | 16335-1704, CURTIS | S3322 | 98909 | Y | 311 |  |  | 2021-01-07 | 2021-01-07 | Completed | Order Operation | POLRPL | # of Poles Replaced | 2 | 0 | 0 | 1 | 51.1 | 49.8 | 1.3 |  | 0 | 51.1 | 49.8 | 1.3 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041085 | RELW OH PRI COMP CLR JPOL RESD ESTR BTKA USA CCNT FMOB TER2 PRTO | Pole | 2020-04-20 | 2020-07-28 | COMP | 2020-04-20 | COMP | 2021-01-07 | 2020-03-24 | 2020-03-24 | [11 empty] | 2021-01-15 | 2021-01-07 | 2020-04-27 |  | 2020-04-27 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351704 | 21749.95 | 9813.7 | 9238.5 | 18368.1 | 18368.1 | 127.7 |  | 127.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COLUMBIA | Sonora |  |  | OPEN | 117072500 | POLE_BROK_REPL - SW POLE L-749 BREWSTER | 35197611 |  |  | STS-POLE_BROK_REPL - SW POLE L-749 BREWS | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0532 | -120.4032 |  | TIER 2 | 157 | 16335-1704, CURTIS | S33 |  | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Dispatched | CLICK | [6 empty] | 47 | 47 |  |  | 34.5 | 20 | 20 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101042519 | RELW OH PRI REMT NOAC ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-10-07 | 2020-10-07 | COMP | 2020-10-07 | [16 empty] | 2019-04-21 | 2020-04-21 | 2020-10-29 | 2020-10-29 | B tag clean up 8/29/2020 |  | UNASSIGNED |  | 163351704 | 14178.35 | 22230.9 | -32638.8 | -17875.1 | -17875.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-08-29
Bay/Central | YO | COLUMBIA | Sonora |  |  | OPEN | 117100505 | POLE_BROK_REPL - A/F 23876 ITALIAN BAR R | 35154106 |  |  | STS-POLE_BROK_REPL - A/F 23876 ITALIAN B | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0552 | -120.3826 |  | TIER 2 | 157 | 16335-1704, CURTIS | S3318 |  | Y | 311 |  |  | 2021-03-13 07:00 | 2021-03-13 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 29.8 | 29.8 |  |  | 0 | 29.8 | 29.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041352 | RELW OH PRI JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-06-16 | 2020-06-22 | COMP | 2020-04-23 | [16 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351704 | 12632.33 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COLUMBIA | Sonora |  |  | OPEN | 117104015 | POLE_BROK_REPL - A/F 12753 YANKEE HILL R | 35154117 |  |  | STS-POLE_BROK_REPL - A/F 12753 YANKEE HI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-01-09 | Renew Permit | 38.0514 | -120.367 |  | TIER 2 | 157 | 16335-1704, CURTIS | S3320 | 20771 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 32 | 32 |  |  | 0 | 32 | 32 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101042081 | RELW OH PRI RESD FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-06-02 | 2020-06-02 | COMP | 2020-06-02 |  |  | 2021-02-21 | 2021-02-21 | [12 empty] | 2019-04-26 | 2020-04-26 |  | 2020-04-26 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351704 | 19201.65 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COLUMBIA | Sonora |  |  | OPEN | 117183330 | POLE_DECA_REPL - UNION HILL RD/BRIAN LN/ | 35100816 |  |  | STS-POLE_DECA_REPL - UNION HILL RD/BRIAN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0157 | -120.3973 |  | TIER 2 | 165 | 16376-1703, RACETRACK | T3312 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.5 | 20.5 |  |  | 0 | 20.5 | 20.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101053086 | RELW OH PRI FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-06-02 | 2020-08-01 | COMP | 2020-06-02 |  |  | 2020-08-01 | 2020-08-01 | [12 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | circuit based plan 2.14 | 2020-05-20 | TRC |  | 163761703 | 12499.09 | 1237.5 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COLUMBIA | Sonora |  |  | OPEN | 117206468 | POLE_BROK_REPL - 11655 RAMBLER RD/2PECOL | 35154648 |  |  | STS-POLE_BROK_REPL - 11655 RAMBLER RD/2P | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0219 | -120.3895 |  | TIER 2 | 165 | 16376-1703, RACETRACK | T3313 | L2073 | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.5 | 50.5 |  |  | 0 | 50.5 | 50.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052806 | PRI OH RELW CLR REMT NOAC ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-05-19 | 2020-07-24 | COMP | 2020-05-19 | [16 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | circuit based plan 2.14 | 2020-05-31 | CALENG |  | 163761703 | 21603.66 | 3238.2 | 3193.9 | 1016.4 | 1016.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COLUMBIA | Sonora |  |  | OPEN | 117210654 | POLE_BROK_REPL - CRNR PACIFIC/COLUMBIA S | 35154674 |  |  | STS-POLE_BROK_REPL - CRNR PACIFIC/COLUMB | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0367 | -120.3996 |  | TIER 2 | 157 | 16335-1704, CURTIS | T3301 |  | Y | 311 |  |  | 2021-03-17 07:00 | 2021-03-17 16:00 | Scheduled | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101049733 | RELW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-06-03 | 2020-07-28 | COMP | 2020-06-03 |  |  | 2020-07-28 | 2020-07-28 | [12 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351704 | 23907.41 | 374.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COLUMBIA | Sonora |  |  | OPEN | 117220602 | POLE_DECA_REPL - 11282 COLUMBIA ST/1PNEC | 35154745 |  |  | STS-POLE_DECA_REPL - 11282 COLUMBIA ST/1 | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0382 | -120.3997 |  | TIER 2 | 157 | 16335-1704, CURTIS | T3301 |  | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | [6 empty] | 43.3 | 43.3 |  |  | 0.5 | 42.8 | 42.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101049739 | RELW OH PRI RESD ESTR GO REAR USA FMOB TER2 PRTO | Pole | 2020-07-03 | 2020-07-03 | COMP | 2020-05-04 | [16 empty] | 2019-05-13 | 2020-05-13 |  | 2020-05-13 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351704 | 21567.51 | 6976.3 | 3202 | 3202 | 3202 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COLUMBIA | Sonora |  |  | OPEN | 119493835 | POLE_BROK_REPL - R/O 12330 CATTLE TRAIL | 35199301 |  |  | STS-POLE_BROK_REPL - R/O 12330 CATTLE TR | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0575 | -120.3761 |  | TIER 2 | 157 | 16335-1704, CURTIS | S33 | 20769 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Dispatched | CLICK | [6 empty] | 22.2 | 21 | 1.2 |  | 0 | 22.2 | 21 | 1.2 |  | EC | B | Pole | Broken/Damaged | Replace |  | 101042342 | RELW INSP OH PRI RESD ESTR GO REAR FMOB TER2 | Pole | 2020-11-09 | 2020-11-09 | COMP | 2020-11-06 | [16 empty] | 2020-07-23 | 2020-10-23 |  | 2020-10-23 | B tag clean up 9/13/2020 |  | Fresno |  | 163351704 | 19174.85 | 7211.7 | -12527.2 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-09-13
Bay/Central | YO | CORSEGOLD | Oakhurst |  |  | OPEN | 117956658 | POLE_DECA_REPL - 44699 TRABUCO RD/2PWCor | 35215678 |  |  | STS-POLE_DECA_REPL - 44699 TRABUCO RD/2P | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2498 | -119.7345 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820124 | 10575 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052591 | RELW OH PRI INSP CLR REMT NOAC ESTR USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-10-03 | 2020-06-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CORUSEGOLD | Oakhurst |  |  | OPEN | 117270369 | POLE_BROK_REPL - 31484 SIOUX 1PSW/1PE CO | 35209259 |  |  | STS-POLE_BROK_REPL - 31484 SIOUX 1PSW/1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2044 | -119.6732 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821284 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 12.3 | 12.3 |  |  | 0 | 12.3 | 12.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101014407 | RELW OH SEC CLR PRTO ESTR FMOB TER2 FSRP | Pole | 2021-01-05 | 2021-01-05 | COMP | 2021-01-05 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-05-31 | 2020-05-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 12178.39 | 94.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COSARSEGOLD | Oakhurst |  |  | OPEN | 117301143 | POLE_DECA_REPL - 47947 RD417 11PN 13PE 3 | 35215609 |  |  | STS-POLE_DECA_REPL - 47947 RD417 11PN 13 | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2271 | -119.6593 |  | TIER 2 | 385 | 25443-2102, COARSEGOLD | 0000008214 | 53499 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101055708 | RELW OH PRI REMT FIRE SWRK ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-22 | 2020-05-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432102 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTER ILL | Merced |  |  | OPEN | 117345078 | POLE_BROK_REPL - WSIPCOULTER ILL | 35154514 |  |  | STS-POLE_BROK_REPL - WSIPCOULTER ILL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7167 | -120.1959 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000216346 | 10434 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43.9 | 43.9 |  |  | 0 | 43.9 | 43.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103227619 | RELW OH PRI RESD ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-08-27 | 2020-10-04 | COMP | 2020-08-17 | [16 empty] | 2019-05-30 | 2020-05-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 252192105 | 24627.68 | 541.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116873505 | POLE_DECA_REPL - R/O 9688 ERNST 1/P/W/O | 35209615 |  |  | STS-POLE_DECA_REPL - R/O 9688 ERNST 1/P/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.7161 | -120.1084 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002176 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101076277 | RELW OH SERV REMT FIRE SWRK ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116873508 | POLE_DECA_REPL - R/O 9688 ERNST 1E/3NCOU | 35209621 |  |  | STS-POLE_DECA_REPL - R/O 9688 ERNST 1E/3 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.7161 | -120.1081 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002176 | 23939 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101076274 | RELW OH PRI CLR REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116875729 | POLE_DECA_REPL - 6594[MB]DOGTOWN 2/P/W/O | 35209630 |  |  | STS-POLE_DECA_REPL - 6594[MB]DOGTOWN 2/P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.7161 | -120.0984 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002176 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101015494 | RELW SERV OH REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192105 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116877536 | POLE_DECA_REPL - 9805[ENTR]HOLTZEL 3SCOU | 35209651 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 37.7197 | -120.0994 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002176 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101076710 | RELW OH PRI CLR REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2020-09-06 | 2020-09-06 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116882651 | POLE_DECA_REPL - 9997 ERNST 2E/1N COULTE | 35209671 |  |  | STS-POLE_DECA_REPL - 9997 ERNST 2E/1N CO | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.7265 | -120.1282 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002176 | 10712 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 61 | 59.8 | 1.2 |  | 0 | 61 | 59.8 | 1.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101075273 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-05 |  | COMP | 2021-02-05 | [16 empty] | 2019-04-01 | 2020-04-01 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192105 | 38830.81 | 211.7 | 211.7 | 211.7 | 211.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116936646 | POLE_DECA_REPL - 6427[ENTR]MILBROW 1NCOU | 35209709 |  |  | STS-POLE_DECA_REPL - 6427[ENTR]MILBROW 1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.7396 | -120.123 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002176 | 10708 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101073158 | RELW OH PRI REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-02 | 2020-04-02 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116940269 | POLE_DECA_REPL - 10134 HOLTZELCOULTERVIL | 35209722 |  |  | STS-POLE_DECA_REPL - 10134 HOLTZELCOULTE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.734 | -120.1228 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002176 | 4632 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101073029 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-02 | 2020-04-02 | 2020-09-06 | 2020-09-06 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116940339 | POLE_DECA_REPL - A/F 10217 SHETLAND 3SCO | 35209727 |  |  | STS-POLE_DECA_REPL - A/F 10217 SHETLAND | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.7345 | -120.1283 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002176 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101072614 | RELW OH PRI JPOL REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-02 | 2020-04-02 | 2020-09-14 | 2020-09-14 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116951622 | POLE_DECA_REPL - A/F 10217 SHETLANDCOULT | 35208789 |  |  | STS-POLE_DECA_REPL - A/F 10217 SHETLANDC | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.7361 | -120.1275 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002176 | 10709 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 66.4 | 65 | 1.4 |  | 0 | 66.4 | 65 | 1.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101072608 | RELW OH PRI CLR JPOL REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2019-04-03 | 2020-04-03 | 2020-11-14 | 2020-11-14 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116952245 | POLE_DECA_REPL - ERNST/WAGNER RD 3PSCOUL | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 37.7086 | -120.1134 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 03172A | 9560 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077404 | REGW OH PRI RESD REMT FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-04-03 | 2020-04-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 252192105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116956099 | POLE_DECA_REPL - 9688 ERNST RD 2PNECOULT | 35208845 |  |  | STS-POLE_DECA_REPL - 9688 ERNST RD 2PNEC | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.711 | -120.1094 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 03172A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077496 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-04 | 2020-04-04 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192105 | 1 | 2288.9 | 1912.9 | 1753.9 | 1753.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116958252 | POLE_DECA_REPL - 6509 DOGTOWN RD 2PNE/4P | 35214691 |  |  | STS-POLE_DECA_REPL - 6509 DOGTOWN RD 2PN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 37.7107 | -120.0986 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002176 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077509 | RELW OH FIRE PRI JPOL REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-04 | 2020-04-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192105 | 1 | 34.8 | 34.8 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116964044 | POLE_DECA_REPL - TEXAS HILL RD/QUAIL MIN | 35208865 |  |  | STS-POLE_DECA_REPL - TEXAS HILL RD/QUAIL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.7016 | -120.0939 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 03172A | 4609 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077565 | RELW OH PRI JPOL REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-05 | 2020-04-05 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192105 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116987399 | POLE_DECA_REPL - 5587 GREELY HILLCOULTER | 35209042 |  |  | STS-POLE_DECA_REPL - 5587 GREELY HILLCOU | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.7346 | -120.1763 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002165 | 23175 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.2 | 41.2 |  |  | 0 | 41.2 | 41.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101073782 | RELW OH PRI JPOL REMT FIRE ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2019-04-09 | 2020-04-09 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192105 | 19292.15 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 117011698 | POLE_DECA_REPL - 4286 PENON BLANCO 5PECO | 35086606 |  |  | STS-POLE_DECA_REPL - 4286 PENON BLANCO 5 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 37.7221 | -120.2781 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002155 | 11210 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101193857 | RELW OH PRI JPOL REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-11 | 2020-04-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 252192105 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 117300825 | POLE_DECA_REPL - 10265 PINEY CREEK RD 1P | 35209552 |  |  | STS-POLE_DECA_REPL - 10265 PINEY CREEK R | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.6977 | -120.3007 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000003151 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.9 | 23.9 |  |  | 0 | 23.9 | 23.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101079395 | RELW OH PRI RESD REMT TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-07 |  | COMP | 2020-12-07 | [16 empty] | 2019-05-22 | 2020-05-22 | 2020-10-18 | 2020-10-18 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192105 | 15873.7 | 58.1 | -1086 | -543 | -543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 117343819 | POLE_BURN_REPL - 95311COULTERVILLE95311 | 35208904 |  |  | STS-POLE_BURN_REPL - 95311COULTERVILLE95 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.7956 | -120.298 |  | TIER 2 | 523 | 16378-1701, PEORIA | Y35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 103202417 | RELW OH PRI JPOL REMT ESTR FIRE NOAC SPCR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-30 | 2020-05-30 |  | 2020-05-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163781701 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116873502 | POLE_DECA_REPL - R/O 9688 ERNST 1E/2NCOU | 35209609 |  |  | STS-POLE_DECA_REPL - R/O 9688 ERNST 1E/2 | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7153 | -120.1086 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002176 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 15.8 | 15.8 |  |  | 0 | 15.8 | 15.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101076278 | RELW OH PRI REMT FIRE SWRK ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 | 2021-01-28 | COMP | 2021-01-28 | [16 empty] | 2019-03-30 | 2020-03-30 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192105 | 7996.11 | 280.5 | 280.5 | 280.5 | 280.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116875748 | POLE_DECA_REPL - 6594[MB]DOGTOWN 1/P/W/O | 35154796 |  |  | STS-POLE_DECA_REPL - 6594[MB]DOGTOWN 1/P | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7158 | -120.0979 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002176 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 11.4 | 11.4 |  |  | 0 | 11.4 | 11.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101076325 | RELW OH SERV REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-05-04 | 2020-05-04 | COMP | 2020-05-01 | [16 empty] | 2019-03-31 | 2020-03-31 | 2020-11-04 | 2020-11-04 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252192105 | 5160.67 | 1013 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116882324 | POLE_DECA_REPL - 9997 ERNST 1ECOULTERVIL | 35178957 |  |  | STS-POLE_DECA_REPL - 9997 ERNST 1ECOULTE | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.726 | -120.1288 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002176 | 10712 | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Dispatched | CLICK | [6 empty] | 40.1 | 40.1 |  |  | 0 | 40.1 | 40.1 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101075274 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-07-03 | 2020-07-11 | COMP | 2020-07-03 | [16 empty] | 2019-04-01 | 2020-04-01 | 2020-08-08 | 2020-08-08 | B-Tag Addition 06.24.20 |  | Bakersfield |  | 252192105 | 14903.75 | 2864.3 | 9.3 | 9.3 | 9.3 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-06-29
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116961611 | POLE_DECA_REPL - 10436 PRIEST COULTERVIL | 35154101 |  |  | STS-POLE_DECA_REPL - 10436 PRIEST COULTE | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-12 | Renew Permit | 37.7541 | -120.2038 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002163 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 1.8 | 1.8 |  |  | 0 | 1.8 | 1.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102338970 | RELW OH PRI PGEA CLR REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-04-28 | 2020-04-28 | COMP | 2020-04-28 |  |  | 2020-04-06 | 2020-04-07 | [12 empty] | 2019-04-05 | 2020-04-05 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252192105 | 10205.26 | 1783.7 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116976255 | POLE_DECA_REPL - 4882 HWY 49 3PSWCOULTER | 35154196 |  |  | STS-POLE_DECA_REPL - 4882 HWY 49 3PSWCOU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.6874 | -120.1824 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000003161 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.5 | 22.5 |  |  | 0 | 22.5 | 22.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077110 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-05-04 | 2020-08-04 | COMP | 2020-05-04 | [16 empty] | 2019-04-07 | 2020-04-07 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252192105 | 8353.83 | 1840.2 |  |  |  | 88.7 |  | 88.7 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116981845 | POLE_DECA_REPL - 9688 ERNST RD 4PS/2PNWC | 35154248 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7083 | -120.1143 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 03172A |  | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 23.8 | 23.8 |  |  | 0 | 23.8 | 23.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077357 | RELW OH PRI REMT FMOB ESTR GO BTKA TER2 PRTO FSRP | Pole | 2020-08-08 | 2020-08-10 | COMP | 2020-04-24 | [16 empty] | 2019-04-08 | 2020-04-08 | 2024-04-06 | 2024-04-06 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252192105 | 8478.71 | 2244.5 | 2200.1 | 1300.3 | 1300.3 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 116989559 | POLE_DECA_REPL - 3219 CHICHARRA 1PW 3PS | 35198142 |  |  | STS-POLE_DECA_REPL - 3219 CHICHARRA 1PW | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7235 | -120.3228 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 02156D | 22393 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 43.1 | 43.1 |  |  | 0 | 43.1 | 43.1 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101190894 | RELW OH PRI REMT FIRE ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-24 | 2020-10-07 | COMP | 2020-09-24 | [16 empty] | 2019-04-09 | 2020-04-09 | 2020-11-07 | 2020-11-07 | B tag clean up 9/5/2020 |  | Fresno |  | 252811102 | 16554.59 | 18647.4 | -19591.3 | 10.7 | 10.7 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-09-05
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 117004399 | POLE_DECA_REPL - A/F 5248[MB]GREELY HILL | 35154331 |  |  | STS-POLE_DECA_REPL - A/F 5248[MB]GREELY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7235 | -120.1863 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002165 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.9 | 15.9 |  |  | 0.5 | 15.4 | 15.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101073913 | RELW OH PRI JPOL REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-04-23 | 2020-07-17 | COMP | 2020-04-23 |  |  | 2020-03-03 | 2020-03-03 | [12 empty] | 2019-04-10 | 2020-04-10 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252192105 | 9092.88 | 155.6 | 111.2 | 111.2 | 111.2 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 117004474 | POLE_DECA_REPL - 5121 DOGTOWNCOULTERVILL | 35154339 |  |  | STS-POLE_DECA_REPL - 5121 DOGTOWNCOULTER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-12 | Renew Permit | 37.7173 | -120.1906 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000216344 | 21160 | Y | 311 |  |  |  |  | Completed | Order Operation | [6 empty] | 50.8 | 50.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101076004 | RELW OH PRI JPOL REMT FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-04-29 | 2020-11-16 | COMP | 2020-04-28 |  |  | 2020-03-13 | 2020-03-13 | [12 empty] | 2019-04-10 | 2020-04-10 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252192105 | 17569.7 | 2572.7 |  |  |  | 398.4 |  | 398.4 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 117028329 | POLE_DECA_REPL - RANCHITO/MERCED FALLS 2 | 35154602 |  |  | STS-POLE_DECA_REPL - RANCHITO/MERCED FAL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.6421 | -120.2895 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03155B | 22769 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 55.6 | 55.6 |  |  | 0 | 55.6 | 55.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101189341 | RELW OH PRI RESD REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2020-05-14 | 2020-05-14 | COMP | 2020-05-14 | [16 empty] | 2019-04-14 | 2020-04-14 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252811102 | 26545.77 | 5115.7 | 1443.7 | 1443.7 | 1443.7 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 117293953 | POLE_DECA_REPL - 3710 GRANITE SPGS RD 3P | 35154228 |  |  | STS-POLE_DECA_REPL - 3710 GRANITE SPGS R | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7055 | -120.2975 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000003151 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 1.8 | 1.8 |  |  | 0 | 1.8 | 1.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101079002 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-05-05 | 2020-05-05 | COMP | 2020-05-05 | [16 empty] | 2019-05-21 | 2020-05-21 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252192105 | 6186.6 | 1602.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 119170795 | POLE_BROK_REPL - 8920 HIGHWAY 132 COULTE | 35182818 |  |  | STS-POLE_BROK_REPL - 8920 HIGHWAY 132 CO | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7086 | -120.2038 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000003161 | 4546 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Dispatched | CLICK | [6 empty] | 40.1 | 40.1 |  |  | 0 | 40.1 | 40.1 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101076798 | RELW OH ESTR TER2 | Pole | 2020-07-19 | 2020-07-19 | COMP | 2020-07-19 | [16 empty] | 2020-03-26 | 2020-06-26 |  | 2020-06-26 | B-Tag Addition 06.24.20 | 2021-03-26 | W. Sac |  | 252192105 | 16771.51 | 1834.3 | 9.3 | 9.3 | 9.3 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | COMP | 116961343 | POLE_DECA_REPL - 6509 DOGTOWN RDCOULTERV | 35154097 |  |  | STS-POLE_DECA_REPL - 6509 DOGTOWN RDCOUL | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.7078 | -120.099 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 03172A |  | Y | 311 |  |  | 2021-01-16 | 2021-01-16 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 50.8 | 50.8 |  |  | 18 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077518 | RELW OH SEC COMP JPOL REMT FIRE ESTR BTKA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-05-11 | 2020-06-30 | COMP | 2020-05-11 | COMP | 2021-01-17 | [13 empty] | 2021-01-29 | 2021-01-17 | 2020-04-05 | 2024-04-03 | 2024-04-03 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252192105 | 7626.85 | 12824.1 | 12296.6 | 12382.8 | 12382.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | COMP | 117002467 | POLE_DECA_REPL - 10776 DEXTER RD.1PWGREE | 35094279 |  |  | STS-POLE_DECA_REPL - 10776 DEXTER RD.1PW | FICL | FICL SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-10-09 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.7726 | -120.1597 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | Y39 |  | Y | 311 |  |  | 2021-01-09 | 2021-01-09 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 51.9 | 51.9 |  |  | 28 | 0.9 | 0.9 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 42537624 | RELW OH PRI COMP REMT NOAC ESTR CPGG TER2 PRTO FMOB | Pole | 2020-12-02 | 2020-12-08 | COMP | 2020-12-02 | COMP | 2021-01-09 | [13 empty] | 2021-01-21 | 2021-01-09 | 2019-10-07 | 2020-11-06 | 2020-11-06 | B tag clean up 9/5/2020 |  | Fresno |  | 252192105 | 12997.98 | 10744.2 | 10654.9 | 10654.9 | 10654.9 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Estimating Delays | Y | 2020-09-05
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 117026619 | POLE_DECA_REPL - 14410 POTRERO WAYCOULTE | 35154569 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-01-09 | Renew Permit | 37.6786 | -120.3291 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03153A | 4453 | Y | 311 |  |  | 2021-10-29 07:00 | 2021-10-29 16:00 | Scheduled | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101190013 | RELW OH PRI JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-05-22 | 2020-07-11 | COMP | 2020-05-21 |  |  | 2020-03-26 | 2020-03-26 | [12 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252811102 | 18076.02 | 4454.8 | 1296.1 | 1296.1 | 1296.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | COULTERVILLE | Mariposa |  |  | OPEN | 117296351 | POLE_DECA_REPL - #2 N/O 3778 HWY 132 #13 | 35154236 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7005 | -120.2702 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000003151 |  | Y | 311 |  |  | 2021-10-29 07:00 | 2021-10-29 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101078907 | RELW OH SERV REMT FIRE NOAC WATR ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-05-19 | 2020-06-26 | COMP | 2020-05-19 | [16 empty] | 2019-05-21 | 2020-05-21 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-31 | TRC |  | 252192105 | 6800.93 | 3140 | 51.4 |  |  | 177.3 |  | 177.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | Coulterville | Mariposa |  |  | OPEN | 119569583 | TREE_DECA_INPL - 5875 COULTERVILLE | 35192350 |  |  | STS-TREE_DECA_INPL - 5875 COULTERVILLE | CONS | CONS SRDY CDOC | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7784 | -120.1852 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002161 | 25883 | Y | 311 |  |  | 2021-01-17 | 2021-01-17 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | B | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103231136 | RELW OH SERV INSP ESTR FMOB TER2 PRTO | Pole | 2020-10-28 | 2020-10-28 | COMP | 2020-10-28 | [16 empty] | 2020-08-06 | 2020-11-06 |  | 2020-11-06 | B-tag addition 8/12/2020 |  | Bakersfield |  | 252192105 | 2661.2 | 845.1 | 312.2 | 312.2 | 312.2 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-08-18
Bay/Central | YO | COULTERVILLE | Oakhurst |  |  | OPEN | 117002385 | POLE_DECA_REPL - 5222[ENTR]DOGTOWN 1NCOU | 35209127 |  |  | STS-POLE_DECA_REPL - 5222[ENTR]DOGTOWN 1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.7171 | -120.1841 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002165 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101075942 | RELW OH PRI PGEA CLR ESTR REMT FIRE NOAC FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-10 | 2020-04-10 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192105 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COULTERVILLE | Oakhurst |  |  | OPEN | 117019577 | POLE_DECA_REPL - 10678[ENTR]HWY49 5ECOUL | 35209346 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7301 | -120.21 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002166 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.7 | 31.7 |  |  | 0 | 31.7 | 31.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101076266 | RELW PRI OH PGEA CLR REMT FIRE NOAC ESTR GO FMOB TER2 PRTO FSRP | Pole | 2020-12-17 | 2021-02-17 | COMP | 2020-12-17 | [16 empty] | 2019-04-12 | 2020-04-12 | 2020-09-06 | 2020-09-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192105 | 16423.77 | 53.8 | 0 | 497.8 | 497.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COURSEGOLD | Oakhurst |  |  | OPEN | 116811266 | POLE_DECA_REPL - 42775 ELLERBROCK STATIO | 35215434 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2649 | -119.7655 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008201 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101054138 | RELW OH PRI NOAC ESTR USA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COURSEGOLD | Oakhurst |  |  | OPEN | 117231598 | POLE_BROK_REPL - 33615 JOHN/ROBIN HOOD D | 35208822 |  |  | STS-POLE_BROK_REPL - 33615 JOHN/ROBIN HO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2349 | -119.7318 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.9 | 18.9 |  |  | 0 | 18.9 | 18.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101050620 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-21 | 2021-01-13 | COMP | 2021-01-13 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 9376.49 | 13.5 | 0 | 1467 | 1467 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COURSEGOLD | Oakhurst |  |  | OPEN | 117270579 | POLE_BROK_REPL - 31680 SIOUX 2PSCOURSEGO | 35209278 |  |  | STS-POLE_BROK_REPL - 31680 SIOUX 2PSCOUR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.2066 | -119.6735 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821284 | 5506 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057065 | OH RELW PRI CLR ESTR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2020-09-04 | 2020-09-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COURSEGOLD | Oakhurst |  |  | OPEN | 117270639 | POLE_BROK_REPL - 31680 SIOUX 1PSCOURSEGO | 35209294 |  |  | STS-POLE_BROK_REPL - 31680 SIOUX 1PSCOUR | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2078 | -119.6737 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821284 | 5506 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33 | 33 |  |  | 0 | 33 | 33 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057066 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-06 |  | COMP | 2021-01-06 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-09-04 | 2020-09-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 17400.85 | 13.5 | 0 | 407.5 | 407.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COURSEGOLD | Oakhurst |  |  | OPEN | 117270813 | POLE_BURN_REPL - ERIE/HOPI 1PNW/3PN COUR | 35209304 |  |  | STS-POLE_BURN_REPL - ERIE/HOPI 1PNW/3PN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2076 | -119.6753 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821284 | 5506 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 101057070 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COURSEGOLD | Oakhurst |  |  | OPEN | 117272898 | POLE_DECA_REPL - 31549 DELAWARE 2PS/1PW | 35209363 |  |  | STS-POLE_DECA_REPL - 31549 DELAWARE 2PS/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2059 | -119.677 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000821284 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101057053 | RELW OH SEC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2020-12-10 | 2020-12-10 | [12 empty] | 2019-05-19 | 2020-05-19 | 2020-11-04 | 2020-11-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | COURSEGOLD | Oakhurst |  |  | OPEN | 116890166 | POLE_BROK_REPL - ELLEN MINE RD/3NECOURSE | 35179989 |  |  | STS-POLE_BROK_REPL - ELLEN MINE RD/3NECO | CONS | CONS ERDY SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3053 | -119.7595 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000007204 |  | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 42.3 | 41 | 1.3 |  | 1.5 | 41.3 | 40 | 1.3 |  | EC | B | Pole | Broken/Damaged | Replace |  | 101024932 | OH PRI CLR REMT NOAC ESTR FMOB TER2 PRTO FSRP RELW | Pole | 2020-07-06 | 2020-07-06 | COMP | 2020-07-06 | [16 empty] | 2019-03-22 | 2020-03-22 | 2020-08-21 | 2020-08-21 | B-Tag Addition 06.24.20 |  | Fresno |  | 254432104 | 23001.33 | 1628 | 298.7 | 222.6 | 222.6 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | YO | COURSEGOLD | Oakhurst |  |  | OPEN | 117270464 | POLE_BROK_REPL - 31308 ERIE RD 3PNCOURSE | 35209268 |  |  | STS-POLE_BROK_REPL - 31308 ERIE RD 3PNCO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.205 | -119.6725 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000008215 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.7 | 17.7 |  |  | 0 | 17.7 | 17.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101056471 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-13 | 2021-01-13 | COMP | 2021-01-13 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 7281.79 | 53.8 | 0 | 1711.5 | 1711.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CROSSGOLD | Oakhurst |  |  | OPEN | 117341589 | POLE_DECA_REPL - #1 E/O 35507 HWY 41 #1 | 35208869 |  |  | STS-POLE_DECA_REPL - #1 E/O 35507 HWY 41 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.2646 | -119.6889 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.4 | 19.4 |  |  | 0 | 19.4 | 19.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101063280 | RELW OH SEC ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-03 |  | COMP | 2021-02-03 |  |  | 2020-12-18 | 2020-12-18 | [12 empty] | 2019-05-29 | 2020-05-29 | 2020-09-27 | 2020-09-27 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 8182.69 | 440.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | CULTREVILLE | Mariposa |  |  | OPEN | 117347091 | POLE_BROK_REPL - 10361 HWY49 1SCULTREVIL | 35215818 |  |  | STS-POLE_BROK_REPL - 10361 HWY49 1SCULTR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.7133 | -120.2006 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000216346 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101076217 | RELW OH PRI CLR RESD ESTR GO BTKA REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-30 | 2020-05-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192105 | 1 | 30.9 | 17.4 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | EAST SONORA | Sonora |  |  | OPEN | 117086751 | POLE_BROK_REPL - 14405 EDGEMONT ACRES RD | 35209670 |  |  | STS-POLE_BROK_REPL - 14405 EDGEMONT ACRE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9793 | -120.3291 |  | TIER 2 | 157 | 16335-1704, CURTIS | U3410 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24 | 24 |  |  | 0 | 24 | 24 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047854 | RELW OH PRI RESD USA ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-23 | 2021-02-12 | COMP | 2020-12-23 | [16 empty] | 2019-04-23 | 2020-04-23 | 2020-10-23 | 2020-10-23 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163351704 | 11494.52 | 1207.9 | 1207.9 | 362 | 362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | EAST SONORA | Sonora |  |  | OPEN | 117119294 | POLE_BROK_REPL - 19478 HESS AVEEAST SONO | 35188125 |  |  | STS-POLE_BROK_REPL - 19478 HESS AVEEAST | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9767 | -120.3332 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3415 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 47.2 | 47.2 |  |  | 0 | 47.2 | 47.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101019727 | RELW OH PRI INSP TRAF JPOL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-09-21 |  | COMP | 2020-09-21 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 21670.45 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | EAST SONORA | Sonora |  |  | OPEN | 117031681 | POLE_BROK_REPL - 19531 CORDEILA 3PNE OF | 35141603 |  |  | STS-POLE_BROK_REPL - 19531 CORDEILA 3PNE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9776 | -120.3369 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3414 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16 | 15.8 | 0.2 |  | 0 | 16 | 15.8 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101045337 | RELW OH SEC RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2019-11-22 | 2019-12-11 | COMP | 2019-11-22 | [16 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | Fresno |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | EAST SONORA | Sonora |  |  | OPEN | 117070867 | POLE_BROK_REPL - 14557 PEACEFUL VALLEY R | 35188141 |  |  | STS-POLE_BROK_REPL - 14557 PEACEFUL VALL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9796 | -120.3248 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3506 | S1299 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48.4 | 48.4 |  |  | 0 | 48.4 | 48.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032194 | PRI RELW OH PGEA JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-09-27 | 2021-01-15 | COMP | 2020-09-27 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 24809.22 | 511.5 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | EAST SONORA | Sonora |  |  | OPEN | 117121674 | POLE_BROK_REPL - 19245 HESS AVEEAST SONO | 35154226 |  |  | STS-POLE_BROK_REPL - 19245 HESS AVEEAST | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-12-31 | No Action | 37.9728 | -120.3315 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3415 | 90035 | Y | 311 |  |  | 2021-02-18 07:00 | 2021-02-18 16:00 | Completed | CLICK | [6 empty] | 53.8 | 53.8 |  |  | 0.5 | 53.3 | 53.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103152402 | PRI RELW OH INSP JPOL RESD FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-04-20 | 2020-08-06 | COMP | 2020-04-20 |  |  | 2021-02-21 | 2021-02-21 | [12 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351703 | 25298.33 | 4292.9 | 4149 | 4149 | 4149 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | EAST SONORA | Sonora |  |  | OPEN | 117122646 | POLE_BROK_REPL - 19879 PHOENIX LAKE RD E | 35188259 |  |  | STS-POLE_BROK_REPL - 19879 PHOENIX LAKE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9736 | -120.3287 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3415 | 19559 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.4 | 36.4 |  |  | 0 | 36.4 | 36.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048198 | RELW OH PRI INSP JPOL RESD FIRE NOAC ESTR REAR USA FMOB TER2 FSRP | Pole | 2020-09-21 | 2020-11-16 | COMP | 2020-09-21 | [16 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 15639.15 | 477.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | EAST SONORA | Sonora |  |  | COMP | 117086499 | POLE_DECA_REPL - 13030 FIR DR 2PN/1PW EA | 35218864 |  |  | STS-POLE_DECA_REPL - 13030 FIR DR 2PN/1P | FICL | FICL SRDY CRDY | Poles | MPP | Veg+CONST - OH | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-11-28 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.9789 | -120.3599 |  | TIER 2 | 492 | 16335-1701, CURTIS | U3406 | 180505 | Y | 311 |  |  | 2021-01-15 | 2021-01-15 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 28.6 | 28.6 |  |  | 65.75 | 4.6 | 4.6 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101046834 | MINR COMP OH PRI PGEA JPOL RELW RESD JAR BTKA CPGE CPGD FMOB TER2 PRTO FSRP | Pole | 2020-12-15 | 2020-12-17 | COMP | 2020-12-15 | COMP | 2021-01-14 | 2020-12-16 | 2020-12-16 | [11 empty] | 2021-01-18 | 2021-01-14 | 2020-04-23 | 2020-12-26 | 2020-12-26 | B tag clean up 12/8/2020 |  | Fresno |  | 163351701 | 27433.29 | 22570.5 | 22489.7 | 22489.7 | 22489.7 |  |  |  | FRMMA/WMPMA - Electric | Y | Not Assigned 11/2 in MPP Import File | N | Readiness -- became UNSC on 12/18 | Y | 2020-12-08
Bay/Central | YO | Fish Camp | Oakhurst |  |  | OPEN | 119762041 | TREE_DECA_INPL - YOSEMITE NATIONAL PARK | 35200170 |  |  | STS-TREE_DECA_INPL - YOSEMITE NATIONAL P | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5466 | -119.6473 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000421353 | 5555 | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Dispatched | CLICK | [6 empty] | 22.5 | 22.5 |  |  | 0 | 22.5 | 22.5 |  |  | EC | B | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103202058 | RELW OH SEC INSP JPOL RESD REMT ESTR BTKA TER2 USA FMOB | Pole | 2020-10-15 | 2020-12-14 | COMP | 2020-10-15 | [16 empty] | 2020-09-14 | 2020-12-14 |  | 2020-12-14 | B tag clean up 9/20/2020 |  | Fresno |  | 254421103 | 11949.98 | 2928.4 | 750.7 | 749.2 | 749.2 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-09-20
Bay/Central | YO | FISH CAMP | Oakhurst |  |  | OPEN | 119770535 | TREE_DECA_INPL - Yosemite National ParkF | 35201614 |  |  | STS-TREE_DECA_INPL - YOSEMITE NATIONAL P | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5482 | -119.6404 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000421352 | 5727 | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | [6 empty] | 7.1 | 7.1 |  |  | 0 | 7.1 | 7.1 |  |  | EC | B | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103217443 | RELW OH SEC INSP RESD ESTR USA FMOB TER2 | Pole | 2020-10-12 | 2020-12-11 | COMP | 2020-10-12 | [16 empty] | 2020-09-16 | 2020-12-16 |  | 2020-12-16 | B tag clean up 9/20/2020 |  | Fresno |  | 254421103 | 2624.39 | 2526.2 | 1935.7 | 1939.5 | 1939.5 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-09-20
Bay/Central | YO | Fish Camp | Oakhurst |  |  | OPEN | 119772303 | TREE_DECA_INPL - Yosemite National ParkF | 35201619 |  |  | STS-TREE_DECA_INPL - YOSEMITE NATIONAL P | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5471 | -119.6442 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000421352 | 5728 | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 11.1 | 11.1 |  |  | 0 | 11.1 | 11.1 |  |  | EC | B | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103217592 | RELW OH SEC INSP RESD REMT ESTR BTKA USA FMOB TER2 | Pole | 2020-11-13 | 2020-12-11 | COMP | 2020-11-13 |  |  | 2020-11-16 | 2020-11-16 | [12 empty] | 2020-09-16 | 2020-12-16 |  | 2020-12-16 | B tag clean up 9/26/2020 |  | Fresno |  | 254421103 | 14601.44 | 2527.2 | 1383 | 1383 | 1383 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-09-26
Bay/Central | YO | FRAINT | Oakhurst |  |  | OPEN | 117011667 | POLE_BROK_REPL - 20455 GALILEO DR/1PN FR | 35209234 |  |  | STS-POLE_BROK_REPL - 20455 GALILEO DR/1P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.0457 | -119.6525 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0001021233 | 2958 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101064635 | RELW PRI OH RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-11 | 2020-04-11 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 116937827 | POLE_DECA_REPL - 45180 RD 211 #3 E #1 N | 35209715 |  |  | STS-POLE_DECA_REPL - 45180 RD 211 #3 E # | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.0994 | -119.6886 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000009216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101062923 | RELW OH PRI CLR JPOL REMT ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-02 | 2020-04-02 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432103 | 1 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117008223 | POLE_BROK_REPL - RALSTON WAY/HIDDEN LAKE | 35209147 |  |  | STS-POLE_BROK_REPL - RALSTON WAY/HIDDEN | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.0541 | -119.6497 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0000010214 | 13044 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 38.7 | 38.7 |  |  | 0 | 38.7 | 38.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101060762 | RELW OH PRI CLR RESD FLAG ESTR BTKA USA PROG FMOB TER2 PRTO FSRP | Pole | 2021-02-22 | 2021-02-22 | COMP | 2021-02-22 |  |  | 2021-01-07 | 2021-01-07 | [12 empty] | 2019-04-11 | 2020-04-11 | 2020-09-05 | 2020-09-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 16583.17 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117008350 | POLE_DECA_REPL - 20941 HIDDEN LAKE BLVDF | 35209157 |  |  | STS-POLE_DECA_REPL - 20941 HIDDEN LAKE B | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.053 | -119.6466 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0001021231 | 13044 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 64.9 | 61.3 | 3.6 |  | 0 | 64.9 | 61.3 | 3.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101064602 | RELW OH PRI CLR ESTR JPOL RESD FLAG BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 25299.01 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117009240 | POLE_DECA_REPL - RALSTON RIDGE/FINE GOLD | 35209184 |  |  | STS-POLE_DECA_REPL - RALSTON RIDGE/FINE | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.0518 | -119.6467 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0001021231 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101064592 | OH RELW PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-11 | 2020-04-11 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 1 | 60.2 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117009396 | POLE_DECA_REPL - 21052 ANZA DR/1PE/1PN/4 | 35209189 |  |  | STS-POLE_DECA_REPL - 21052 ANZA DR/1PE/1 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 37.0569 | -119.6619 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0000010214 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 45.6 | 45.6 |  |  | 0 | 45.6 | 45.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101064255 | OH RELW PRI CLR JPOL REMT FIRE NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-17 | 2020-12-16 | COMP | 2020-12-16 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 30835.74 | 53.8 | -724 | -362 | -362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117009594 | POLE_DECA_REPL - SW5008-RD211 14PE/6PNE/ | 35209194 |  |  | STS-POLE_DECA_REPL - SW5008-RD211 14PE/6 | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.037 | -119.6941 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0000010216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101064366 | RELW OH PRI REMT SPCR ESTR GO FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-11 | 2020-04-11 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 1 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117010353 | POLE_DECA_REPL - HIDDEN LAKE BLVD/RALSTO | 35209204 |  |  | STS-POLE_DECA_REPL - HIDDEN LAKE BLVD/RA | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0515 | -119.6488 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0001021231 | 13044 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 33.7 | 33.7 |  |  | 0 | 33.7 | 33.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101064610 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-12 | 2021-02-12 | COMP | 2021-02-12 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-09-06 | 2020-09-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 15129.81 | 60.2 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117010364 | POLE_DECA_REPL - 20746 GALILEO DR/1PEFRI | 35209209 |  |  | STS-POLE_DECA_REPL - 20746 GALILEO DR/1P | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.0505 | -119.6493 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0001021232 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.3 | 34.3 |  |  | 0 | 34.3 | 34.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060812 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-29 |  | COMP | 2020-12-29 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 18787.87 | 1318.7 | 1237.9 | 534 | 534 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117011779 | POLE_DECA_REPL - LOT L HIDDEN LAKE BLVD. | 35209240 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.0465 | -119.6494 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0001021233 | 13044 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 55.2 | 55.2 |  |  | 0 | 55.2 | 55.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101064622 | RELW OH PRI REMT FIRE ESTR BTKA USA PROG FMOB TER2 PRTO FSRP | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 33190.41 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117015814 | POLE_DECA_REPL - 48022–48198 ROAD 210FRI | 35209279 |  |  | STS-POLE_DECA_REPL - 48022–48198 ROAD 21 | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.0646 | -119.6754 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0000010214 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.9 | 25.9 |  |  | 0 | 25.9 | 25.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103205455 | RELW OH PRI CLR JPOL REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-12 |  | COMP | 2021-02-12 | [16 empty] | 2019-04-12 | 2020-04-12 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 14213.17 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117015874 | POLE_BROK_REPL - 20665 GALILEO DR/7PNFRI | 35209287 |  |  | STS-POLE_BROK_REPL - 20665 GALILEO DR/7P | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.0512 | -119.6498 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0001021232 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 25.9 | 25.9 |  |  | 0 | 25.9 | 25.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101060810 | RELW OH PRI CLR RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-29 |  | COMP | 2020-12-29 | [16 empty] | 2019-04-12 | 2020-04-12 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 15781.77 | 1291.7 | 1237.9 | 603.3 | 603.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117015979 | POLE_DECA_REPL - 48094 ROAD 210FRIANT936 | 35209291 |  |  | STS-POLE_DECA_REPL - 48094 ROAD 210FRIAN | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.0653 | -119.6747 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0000010214 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.8 | 24.4 | 2.4 |  | 0 | 26.8 | 24.4 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103205676 | RELW OH PRI CLR JPOL REMT FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-04 |  | COMP | 2021-01-04 | [16 empty] | 2019-04-12 | 2020-04-12 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 11147.3 | 53.8 | 0 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117032402 | POLE_BROK_REPL - 93626FRIANT93626 | 35209470 |  |  | STS-POLE_BROK_REPL - 93626FRIANT93626 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1093 | -119.6378 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009215 | 19022 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103225473 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2020-09-06 | 2020-09-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252561101 | 1 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117032467 | POLE_DECA_REPL - 50998 RD210FRIANT93626 | 35209478 |  |  | STS-POLE_DECA_REPL - 50998 RD210FRIANT93 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.0912 | -119.6133 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000010222 | 10234 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101064540 | RELW OH PRI NOAC ESTR USA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2020-09-07 | 2020-09-07 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252561101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117033444 | POLE_DECA_REPL - WILLOW CREEK RANCH/RD21 | 35209506 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0976 | -119.6713 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000009215 | 10819 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.9 | 29.9 |  |  | 0 | 29.9 | 29.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101062909 | RELW OH USA PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-17 | 2021-02-17 | COMP | 2021-02-17 | [16 empty] | 2019-04-15 | 2020-04-15 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 12027.01 | 48.3 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117034789 | POLE_DECA_REPL - 51232 RD210/1PSE/5PSFRI | 35209518 |  |  | STS-POLE_DECA_REPL - 51232 RD210/1PSE/5P | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.099 | -119.6262 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009215 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.6 | 27.6 |  |  | 0 | 27.6 | 27.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101062863 | RELW OH PRI JPOL REMT ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-23 | 2020-12-22 | COMP | 2020-12-22 | [16 empty] | 2019-04-15 | 2020-04-15 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252561101 | 15045.26 | 13.5 | 0 | 362 | 362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117047078 | POLE_DECA_REPL - 50990 RD210/6PNFRIANT93 | 35209554 |  |  | STS-POLE_DECA_REPL - 50990 RD210/6PNFRIA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1017 | -119.6189 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009226 | 19022 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101063714 | RELW OH PRI ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2020-11-07 | 2020-11-07 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252561101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117003523 | POLE_DECA_REPL - #1 E/O 22268 RD 211 #5 | 35086594 |  |  | B3 -POLE_DECA_REPL - #1 E/O 22268 RD 211 | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0717 | -119.6941 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0000010212 |  | Y | 311 |  |  | 2021-03-09 07:00 | 2021-03-09 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101064008 | RELW OH PRI CLR REMT FIRE ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-09-16 | 2020-11-08 | COMP | 2020-09-14 |  |  | 2020-09-24 | 2020-09-24 | [12 empty] | 2019-04-10 | 2020-04-10 | 2020-08-08 | 2020-08-08 | B-Tag Addition 06.24.20 | 2020-04-10 | W. Sac |  | 255292108 | 16033.34 | 2986 | 2986 | 2993.3 | 2993.3 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-06-29
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117008995 | POLE_DECA_REPL - FINE GOLD DR/RALSTON RI | 35209175 |  |  | STS-POLE_DECA_REPL - FINE GOLD DR/RALSTO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0516 | -119.6461 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0001021231 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.6 | 22.6 |  |  | 0 | 22.6 | 22.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101064588 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-15 | 2020-12-15 | COMP | 2020-12-15 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-09-06 | 2020-09-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 11483.56 | 251.8 | -1013.6 | -651.6 | -651.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117009604 | POLE_DECA_REPL - 21052 ANZA DR/1PE/1PN/3 | 35209199 |  |  | STS-POLE_DECA_REPL - 21052 ANZA DR/1PE/1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0561 | -119.6596 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0000010214 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.9 | 26.9 |  |  | 0 | 26.9 | 26.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101064254 | OH RELW PRI CLR JPOL REMT FIRE NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-29 | 2021-01-29 | COMP | 2021-01-29 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 23568.15 | 219.9 | 85.4 | 85.4 | 85.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117012057 | POLE_DECA_REPL - SW5008-RD211 14PE/15PNE | 35209245 |  |  | STS-POLE_DECA_REPL - SW5008-RD211 14PE/1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0489 | -119.6768 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0000010213 | 5591 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.7 | 41.7 |  |  | 0 | 41.7 | 41.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101064103 | RELW OH PRI CLR JPOL REMT FIRE ESTR GO BTKA REAR FMOB TER2 PRTO FSRP | Pole | 2021-02-01 | 2021-02-01 | COMP | 2021-02-01 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 18290.36 | 60.2 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117031837 | POLE_DECA_REPL - KIRCKHOFF PWR.HOUSE/8PN | 35177963 |  |  | STS-POLE_DECA_REPL - KIRCKHOFF PWR.HOUSE | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1016 | -119.5683 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009225 |  | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 39 | 39 |  |  | 0.5 | 38.5 | 38.5 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101063629 | OH PRI CLR JPOL REMT FIRE NOAC ESTR USA FMOB TER2 PRTO FSRP RELW | Pole | 2020-06-05 | 2020-07-02 | COMP | 2020-06-05 | [16 empty] | 2019-04-15 | 2020-04-15 | 2020-08-07 | 2020-08-07 | B-Tag Clean Up 6/8/2020 |  | Bakersfield |  | 252561101 | 29440.73 | 3628 | 72.1 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Access/Customer Issue - Unable to gain access | Y | 2020-06-08
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117032194 | POLE_DECA_REPL - 53903 RD210FRIANT93626 | 35209465 |  |  | STS-POLE_DECA_REPL - 53903 RD210FRIANT93 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1094 | -119.6726 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000009215 | 10819 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 62.1 | 60.4 | 1.7 |  | 0 | 62.1 | 60.4 | 1.7 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101062916 | PRI RELW OH CLR ESTR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 | 2021-01-28 | COMP | 2021-01-28 | [16 empty] | 2019-04-15 | 2020-04-15 | 2020-08-08 | 2020-08-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 24704.26 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117032316 | POLE_DECA_REPL - 53903 RD210/1PSFRIANT93 | 35177964 |  |  | STS-POLE_DECA_REPL - 53903 RD210/1PSFRIA | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1077 | -119.6724 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000009215 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101062915 | RELW OH PRI NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-06-24 | 2020-06-24 | COMP | 2020-06-24 | [16 empty] | 2019-04-15 | 2020-04-15 | 2020-08-08 | 2020-08-08 | B-Tag Addition 06.24.20 |  | Fresno |  | 254432103 | 8945.65 | 4133.4 | 1553 | 9.4 | 9.4 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Tag in Closure Status | Y | 2020-06-29
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117032629 | POLE_DECA_REPL - 50998 RD210/12PEFRIANT9 | 35177398 |  |  | STS-POLE_DECA_REPL - 50998 RD210/12PEFRI | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0904 | -119.5956 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000010222 |  | Y | 311 |  |  | 2021-03-16 07:00 | 2021-03-16 16:00 | Scheduled | CLICK | [6 empty] | 31.5 | 31.5 |  |  | 0 | 31.5 | 31.5 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101064515 | RELW OH PRI REMT SPCR ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-05-30 | 2020-05-30 | COMP | 2020-05-30 | [16 empty] | 2019-04-15 | 2020-04-15 | 2020-08-08 | 2020-08-08 | B-Tag Clean Up 6/8/2020 |  | San Francisco |  | 252561101 | 10697.69 | 2354.4 | [7 empty] | N | 11/2 in MPP Import File | N | Access/Customer Issue - Unable to gain access | Y | 2020-06-08
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117033157 | POLE_DECA_REPL - 45180 RD 211 #11 E #1 N | 35177965 |  |  | STS-POLE_DECA_REPL - 45180 RD 211 #11 E | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.098 | -119.6768 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000009216 |  | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | [6 empty] | 41.9 | 41.9 |  |  | 2 | 39.9 | 39.9 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101062920 | RELW OH PRI NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-07-19 | 2020-07-19 | COMP | 2020-07-19 | [16 empty] | 2019-04-15 | 2020-04-15 | 2020-08-08 | 2020-08-08 | B-Tag Addition 06.24.20 |  | Fresno |  | 254432103 | 8168.46 | 2257.6 | [7 empty] | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-06-29
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117046847 | POLE_DECA_REPL - 50990 RD210/4PNFRIANT93 | 35209544 |  |  | STS-POLE_DECA_REPL - 50990 RD210/4PNFRIA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0983 | -119.6184 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009226 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 17.2 | 17.2 |  |  | 0 | 17.2 | 17.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101063711 | RELW OH PRI NOAC ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-15 | 2020-12-15 | COMP | 2020-12-15 | [16 empty] | 2019-04-17 | 2020-04-17 | 2020-10-07 | 2020-10-07 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252561101 | 6711.4 | 13.5 | -1230.8 | -687.8 | -687.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Friant | Oakhurst |  |  | OPEN | 117687761 | POLE_BROK_REPL - 50990 RD210/7PN PVTP Fr | 35209373 |  |  | STS-POLE_BROK_REPL - 50990 RD210/7PN PVT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1018 | -119.6193 |  | TIER 2 |  |  | 0000009226 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16 | 16 |  |  | 0 | 16 | 16 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101063716 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2020-12-14 | 2020-12-14 | COMP | 2020-12-14 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 6224.88 | 13.5 | -633.6 | -407.3 | -407.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117008082 | POLE_DECA_REPL - 49752 RALSTON RIDGE/2PN | 35209143 |  |  | STS-POLE_DECA_REPL - 49752 RALSTON RIDGE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0508 | -119.6443 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0001021231 |  | Y | 311 |  |  | 2021-06-25 07:00 | 2021-06-25 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101064574 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-29 | 2020-12-29 | COMP | 2020-12-29 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-09-05 | 2020-09-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 7374.39 | 1064.2 | 970.1 | 407.3 | 407.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117008264 | POLE_DECA_REPL - 49966 RALSTON RIDGE/1PS | 35209152 |  |  | STS-POLE_DECA_REPL - 49966 RALSTON RIDGE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0512 | -119.6452 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0001021231 |  | Y | 311 |  |  | 2021-06-25 07:00 | 2021-06-25 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101064579 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-04 | 2021-01-04 | COMP | 2021-01-04 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-10-05 | 2020-10-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 8619.91 | 53.8 | 0 | 489 | 489 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117008978 | POLE_DECA_REPL - HIDDEN LAKE BLVD/BALBOA | 35209163 |  |  | STS-POLE_DECA_REPL - HIDDEN LAKE BLVD/BA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0544 | -119.6521 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0000010214 |  | Y | 311 |  |  | 2021-06-25 07:00 | 2021-06-25 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060767 | RELW OH PRI CLR RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-04 | 2021-01-04 | COMP | 2021-01-04 |  |  | 2020-12-09 | 2020-12-09 | [12 empty] | 2019-04-11 | 2020-04-11 | 2020-09-06 | 2020-09-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 15569.22 | 53.8 | 0 | 715 | 715 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117008991 | POLE_DECA_REPL - 21244 HIDDEN LAKE BL./1 | 35209169 |  |  | STS-POLE_DECA_REPL - 21244 HIDDEN LAKE B | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0546 | -119.6532 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0000010214 | 13044 | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060770 | RELW OH PRI CLR RESD ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-23 | 2020-12-23 | COMP | 2020-12-23 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-09-06 | 2020-09-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 17302.33 | 1201.8 | 1147.9 | 362 | 362 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117008998 | POLE_DECA_REPL - SW5008-RD211 11PE/1PNFR | 35209179 |  |  | STS-POLE_DECA_REPL - SW5008-RD211 11PE/1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0315 | -119.7079 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0000010216 |  | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101064386 | RELW OH PRI NOAC ESTR GO USA FMOB TER2 PRTO FSRP | Pole | 2020-12-28 | 2020-12-28 | COMP | 2020-12-28 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 7377.86 | 53.8 | 0 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117011302 | POLE_BROK_REPL - CAPITAN AVEFRIANT93626 | 35209221 |  |  | STS-POLE_BROK_REPL - CAPITAN AVEFRIANT93 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0494 | -119.6485 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0001021231 | 13044 | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101064619 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-23 | 2020-12-23 | COMP | 2020-12-23 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 18642.29 | 1242.1 | 1147.9 | 362 | 362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117012626 | POLE_DECA_REPL - 47744–47996 ROAD 210FRI | 35209260 |  |  | STS-POLE_DECA_REPL - 47744–47996 ROAD 21 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0639 | -119.6763 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0000010214 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.8 | 18.8 |  |  | 0 | 18.8 | 18.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103232099 | RELW OH PRI CLR JPOL REMT FIRE ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-04 | 2021-01-04 | COMP | 2021-01-04 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 9037.68 | 247.5 | 0 | 525 | 525 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | FRIANT | Oakhurst |  |  | OPEN | 117015835 | POLE_BROK_REPL - 21815–21899 ROAD 216 FR | 35209282 |  |  | STS-POLE_BROK_REPL - 21815–21899 ROAD 21 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.066 | -119.6722 |  | TIER 2 | 598 | 25529-2108, WOODWARD | 0000010214 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.1 | 17.1 |  |  | 0 | 17.1 | 17.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103227338 | RELW OH PRI CLR REMT FIRE TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-11 | 2021-01-11 | COMP | 2021-01-11 |  |  | 2020-12-16 | 2020-12-16 | [12 empty] | 2019-04-12 | 2020-04-12 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 255292108 | 7289.95 | 205.7 | 0 | 244.5 | 244.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Friant | Oakhurst |  |  | OPEN | 117687762 | POLE _BROK _REPL_50990 RD210/8PN PVTP | 35209378 |  |  | STS-POLE _BROK _REPL_50990 RD210/8PN PVT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.102 | -119.6201 |  | TIER 2 |  |  | 0000009226 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 37.3 | 37.3 |  |  | 0 | 37.3 | 37.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101063718 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-01-05 | 2021-01-05 | COMP | 2021-01-05 |  |  | 2020-11-27 | 2020-11-27 | [12 empty] | 2019-07-31 | 2020-07-31 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 15190.85 | 13.5 | -1013.6 | -651.6 | -651.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GREELEY HILL | Mariposa |  |  | OPEN | 117307660 | POLE_DECA_REPL - 10488 CONVERSE RD.15PW\ | 35154262 |  |  | STS-POLE_DECA_REPL - 10488 CONVERSE RD.1 | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.7743 | -120.147 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002172 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101074443 | RELW OH SERV RESD REMT NOAC ESTR USA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-23 | 2020-05-23 |  | 2020-05-23 | 2021 CBP Plan | 2020-10-31 | TRC |  | 252192105 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GREELEY HILL | Mariposa |  |  | OPEN | 117002466 | POLE_DECA_REPL - 6381K RD.3PN GREELEY HI | 35198143 |  |  | STS-POLE_DECA_REPL - 6381K RD.3PN GREELE | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7699 | -120.1633 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002161 |  | Y | 311 |  |  | 2021-02-12 07:00 | 2021-02-12 16:00 | Dispatched | CLICK | [6 empty] | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101074166 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-06 | 2020-10-06 | COMP | 2020-10-06 | [16 empty] | 2019-04-10 | 2020-04-10 | 2020-09-30 | 2020-09-30 | B tag clean up 9/5/2020 |  | Fresno |  | 252192105 | 7185.98 | 44.5 | [7 empty] | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-09-05
Bay/Central | YO | GREELEY HILL | Mariposa |  |  | COMP | 116966223 | POLE_DECA_REPL - 10347 FISKE RD #2 S GRE | 35086554 |  |  | STS-POLE_DECA_REPL - 10347 FISKE RD #2 S | FICL | FICL SRDY CDOC CDPR | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-09-09 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.7469 | -120.1345 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 02173C |  | Y | 311 |  |  | 2021-01-09 | 2021-01-09 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 73.6 | 73.6 |  |  | 34 | 0.8 | 0.8 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101075866 | RELW OH SERV COMP RESD REMT NOAC ESTR CPGG FMOB TER2 PRTO | Pole | 2020-11-24 | 2020-12-04 | COMP | 2020-11-24 | COMP | 2021-01-16 | [13 empty] | 2021-01-21 | 2021-01-16 | 2019-10-05 | 2020-10-07 | 2020-10-07 | B-tag addition 8/12/2020 | 2020-04-05 | Santa Rosa |  | 252192105 | 18304.64 | 18026.5 | 16734.4 | 16820.9 | 16820.9 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-08-18
Bay/Central | YO | GREELEY HILL | Mariposa |  |  | OPEN | 117311183 | POLE_DECA_REPL - 10488 CONVERSE RD.15PWG | 35154297 |  |  | STS-POLE_DECA_REPL - 10488 CONVERSE RD.1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7747 | -120.1466 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000002172 | 22379 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.7 | 21.7 |  |  | 0 | 21.7 | 21.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101074440 | RELW OH PRI RESD REMT NOAC ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-28 | 2020-11-12 | COMP | 2020-08-28 | [16 empty] | 2019-05-23 | 2020-05-23 |  | 2020-05-23 | 2021 CBP Plan | 2020-10-31 | TRC |  | 252192105 | 9966.85 | 426.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GREENLY | Mariposa |  |  | OPEN | 116962460 | POLE_BROK_REPL - DEXTER RD.\PINE LAKE DR | 35094209 |  |  | STS-POLE_BROK_REPL - DEXTER RD.\PINE LAK | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.7676 | -120.1545 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 02164A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.1 | 27.1 |  |  | 0 | 27.1 | 27.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101075841 | RELW OH PRI REMT FIRE NOAC ESTR GO USA PROG FMOB PRTO TER2 | Pole | 2021-01-20 |  | COMP | 2021-01-20 | [16 empty] | 2019-04-05 | 2019-10-05 |  | 2019-10-05 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 252192105 | 13280.26 | 80.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND | Sonora |  |  | OPEN | 116872955 | POLE_OVRL_TEST - R\OF\HS\11255 SAWMILL M | 35084818 |  |  | STS-POLE_OVRL_TEST - R\OF\HS\11255 SAWMI | UNSC | UNSC ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.8313 | -119.9781 |  | TIER 2 | 72 | 16335-1703, CURTIS | X43 |  | Y | 311 | [5 empty] | Order Operation | [6 empty] | 12.6 | 12.6 |  |  | 0 | 12.6 | 12.6 |  |  | EC | E | Pole | Overloaded | Test |  | 103350139 | RELW OH PRI CLR JPOL REMT ESTR GO USA FMOB TER2 PRTO | Pole | 2020-12-01 | 2021-02-17 | COMP | 2020-12-01 |  |  | 2021-02-17 | 2021-02-17 | [12 empty] | 2019-03-30 | 2019-11-20 |  | 2019-11-20 | 2021 CBP Plan | 2020-10-31 | EEI |  | 163351703 | 8074.42 | 1752.3 | -814.1 | -728.2 | -728.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Groveland | Sonora |  |  | COMP | 119379333 | POLE_BROK_REPL - 20011 OLD HWY 120 8SGro | 35187219 |  |  | STS-POLE_BROK_REPL - 20011 OLD HWY 120 8 | DOCC | DOCC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-09-18 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.8257 | -120.198 |  | TIER 2 | 72 | 16335-1703, CURTIS | X38 | 9330 | Y | 311 |  |  | 2021-02-12 07:00 | 2021-02-12 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 13.1 | 13.1 |  |  | 0.5 | 13 | 13 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101049380 | RELW OH PRI INSP JPOL REMT FIRE ESTR BTKA USA TER2 COMP CCNT FMOB | Pole | 2020-09-22 | 2020-12-14 | COMP | 2020-09-22 | COMP | 2021-02-12 | [13 empty] | 2021-02-18 | 2021-02-12 | 2020-10-16 |  | 2020-10-16 | B-tag addition 8/4/2020 |  | Fresno |  | 163351703 | 5674.5 | 3000.1 | 936.2 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-08-04
Bay/Central | YO | Groveland | Sonora |  |  | COMP | 119380728 | POLE_BROK_REPL - 20011 OLD HWY 120 5S 4W | 35187460 |  |  | STS-POLE_BROK_REPL - 20011 OLD HWY 120 5 | DOCC | DOCC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-09-18 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.8226 | -120.2002 |  | TIER 2 | 72 | 16335-1703, CURTIS | X38 | 21013 | Y | 311 |  |  | 2021-02-12 07:00 | 2021-02-12 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 33.1 | 33.1 |  |  | 0 | 33.1 | 33.1 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101049362 | RELW OH PRI INSP CLR REMT FIRE ESTR BTKA REAR USA FMOB TER2 CCNT COMP | Pole | 2020-09-22 | 2020-12-21 | COMP | 2020-09-22 | COMP | 2021-02-12 | [13 empty] | 2021-02-18 | 2021-02-12 | 2020-10-16 |  | 2020-10-16 | B-tag addition 8/4/2020 |  | Fresno |  | 163351703 | 14041.64 | 5844.4 | 2333.1 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-08-04
Bay/Central | YO | Groveland | Sonora |  |  | COMP | 119473488 | POLE_BROK_REPL - 19922 PINE MNT.DR GROVE | 35187468 |  |  | STS-POLE_BROK_REPL - 19922 PINE MNT.DR G | DOCC | DOCC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-09-22 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.8451 | -120.1972 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3807 | 90320 | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 54.1 | 54.1 |  |  | 0.5 | 54 | 54 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101040307 | RELW OH PRI INSP CUST COMP CLR RESD FLAG ESTR CCNT FMOB TER2 | Pole | 2020-12-09 | 2020-12-09 | COMP | 2020-12-02 | COMP | 2021-02-09 | 2020-12-03 | 2020-12-03 | [11 empty] | 2021-02-11 | 2021-02-09 | 2020-10-20 |  | 2020-10-20 | B-tag addition 8/4/2020 |  | Fresno |  | 163351703 | 33880.03 | 4739 | 4433.9 | [5 empty] | Electric Distribution | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-08-04
Bay/Central | YO | GROVELAND | Sonora |  |  | OPEN | 116851289 | POLE_BROK_REPL - BK\OF\TOLE BOOTH TO YOS | 35084810 |  |  | STS-POLE_BROK_REPL - BK\OF\TOLE BOOTH TO | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7993 | -119.8717 |  | TIER 2 | 72 | 16335-1703, CURTIS | Y46 |  | Y | 311 |  |  | 2021-03-01 07:00 | 2021-03-01 16:00 | Dispatched | CLICK | [6 empty] | 44 | 44 |  |  | 0 | 44 | 44 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 103350151 | RELW OH PRI PGEA CLR REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2021-01-14 | 2021-01-19 | COMP | 2020-08-22 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-03-27 | 2020-03-27 | 2020-09-23 | 2020-09-23 | B-tag addition 8/12/2020 |  | Fresno |  | 163351703 | 20749.79 | 4470.3 | 1476.5 | 1476.5 | 1476.5 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-08-18
Bay/Central | YO | GROVELAND | Sonora |  |  | OPEN | 116871057 | POLE_BROK_REPL - AF\ENT\TO\11450 MOORE C | 35084814 |  |  | STS-POLE_BROK_REPL - AF\ENT\TO\11450 MOO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-10-12 |  | 37.8106 | -120.0644 |  | TIER 2 | 72 | 16335-1703, CURTIS | Y41 |  | Y | 311 | [5 empty] | Order Operation | [6 empty] | 18.7 | 18.7 |  |  | 0 | 18.7 | 18.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101012913 | RELW OH PRI PGEA RESD ESTR TER2 BTKA USA FMOB PRTO | Pole | 2020-05-28 | 2020-07-29 | COMP | 2020-05-28 |  |  | 2020-04-15 | 2020-04-15 | [12 empty] | 2019-03-30 | 2019-11-11 |  | 2019-11-11 | circuit based plan 2.14 | 2020-05-31 | TRC |  | 163351703 | 8528.6 | 1697.6 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | GROVELAND | Sonora |  |  | OPEN | 116881220 | POLE_DECA_REPL - 16890 PRIEST GRADE 5PW/ | 35084433 |  |  | STS-POLE_DECA_REPL - 16890 PRIEST GRADE | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8179 | -120.3001 |  | TIER 2 | 523 | 16378-1701, PEORIA | X35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.9 | 38.9 |  |  | 0 | 38.9 | 38.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101030290 | RELW OH PRI REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-02-11 | COMP | 2021-01-20 | [16 empty] | 2019-04-01 | 2020-04-01 | 2020-11-07 | 2020-11-07 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163781701 | 27274.02 | 698.2 | 698.1 | 327.2 | 327.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND | Sonora |  |  | OPEN | 116882267 | POLE_BROK_REPL - SW555-HWY120 1PS/2PNW G | 35084852 |  |  | STS-POLE_BROK_REPL - SW555-HWY120 1PS/2P | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8181 | -120.304 |  | TIER 2 | 523 | 16378-1701, PEORIA | X35 |  | Y | 311 |  |  | 2021-05-12 07:00 | 2021-05-12 16:00 | Reserved | CLICK | [6 empty] | 16 | 16 |  |  | 1 | 15 | 15 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101030296 | RELW OH PRI JPOL REMT ESTR FMOB TER2 PRTO FSRP | Pole | 2020-05-06 | 2020-06-05 | COMP | 2020-05-06 | [16 empty] | 2019-04-01 | 2020-04-01 | 2020-08-07 | 2020-08-07 | Program Manager | 2020-05-20 | TRC |  | 163781701 | 20484.27 | 6006.2 |  |  |  | 250.2 |  | 250.2 |  | Y | 11/2 in MPP Import File | N | Tag in Closure Status | Y | 2020-02-20
Bay/Central | YO | GROVELAND | Sonora |  |  | OPEN | 116882736 | POLE_BROK_REPL - 11195 BIG CREEK SHAFT R | 35187632 |  |  | STS-POLE_BROK_REPL - 11195 BIG CREEK SHA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8255 | -120.1433 |  | TIER 2 | 72 | 16335-1703, CURTIS | X39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.3 | 12.3 |  |  | 0 | 12.3 | 12.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101036554 | RELW OH PRI JPOL REMT ESTR BTKA PROG FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-11-29 | COMP | 2020-10-12 | [16 empty] | 2019-04-01 | 2020-04-01 |  | 2020-04-01 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 6077.44 | 85.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND | Sonora |  |  | OPEN | 116937009 | POLE_BROK_REPL - 11340 WARDS FERRY RD 10 | 35084446 |  |  | STS-POLE_BROK_REPL - 11340 WARDS FERRY R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8249 | -120.2659 |  | TIER 2 | 523 | 16378-1701, PEORIA | X36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.4 | 28.4 |  |  | 0 | 28.4 | 28.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030187 | RELW OH PRI NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-10-19 | 2020-12-07 | COMP | 2020-10-19 | [16 empty] | 2019-04-02 | 2019-10-01 | 2024-03-31 | 2024-03-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 163781701 | 29910.34 | 11538.5 | 3094.9 | 1722.9 | 1722.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND | Sonora |  |  | OPEN | 116951567 | POLE_BROK_REPL - 10966 YOSEMITE SPRINGS | 35191325 |  |  |  | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8155 | -120.1946 |  | TIER 2 | 72 | 16335-1703, CURTIS | Y38 | 1993 | Y | 311 |  |  | 2021-02-27 07:00 | 2021-02-27 16:00 | Dispatched | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101043184 | REMT RELW OH PRI NOAC ESTR GO PROG FMOB TER2 PRTO | Pole | 2020-12-05 | 2020-12-05 | COMP | 2020-12-05 | [16 empty] | 2019-04-03 | 2019-09-30 | 2020-10-30 | 2020-10-30 | B-tag addition 8/12/2020 |  | Fresno |  | 163351703 | 16993.42 | 44.6 | [7 empty] | Y | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-08-18
Bay/Central | YO | GROVELAND | Sonora |  |  | OPEN | 117322743 | POLE_DECA_REPL - E\OF\ENT\TO\24545 HWY 1 | 35189375 |  |  | STS-POLE_DECA_REPL - E\OF\ENT\TO\24545 H | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8225 | -120.0984 |  | TIER 2 | 72 | 16335-1703, CURTIS | X40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 10.6 | 10.6 |  |  | 0 | 10.6 | 10.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101037640 | RELW OH SERV RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-24 | 2020-10-29 | COMP | 2020-09-24 | [16 empty] | 2019-05-26 | 2020-05-26 |  | 2020-05-26 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 4771.24 | 2212.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND | Sonora |  |  | OPEN | 117323229 | POLE_BROK_REPL - 18480 DEER FLAT RD/1PNW | 35189381 |  |  | STS-POLE_BROK_REPL - 18480 DEER FLAT RD/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8375 | -120.2361 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3712 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.6 | 14.6 |  |  | 0 | 14.6 | 14.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101035208 | RELW OH SERV RESD REMT ESTR FMOB TER2 PRTO | Pole | 2020-10-02 | 2020-10-02 | COMP | 2020-10-02 | [16 empty] | 2019-05-26 | 2020-05-26 |  | 2020-05-26 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 5144.45 | 114.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Groveland | Sonora |  |  | OPEN | 119489295 | POLE_BROK_REPL - R\OF\RIVER STORE\COSA L | 35198567 |  |  | STS-POLE_BROK_REPL - R\OF\RIVER STORE\CO | PEND | PEND | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Land |  |  | 37.8176 | -120.1085 |  | TIER 2 | 72 | 16335-1703, CURTIS | X40 | 27336 | Y | 311 |  |  | 2021-04-26 07:00 | 2021-04-26 16:00 | Scheduled | CLICK | [6 empty] | 41.2 | 41.2 |  |  | 0 | 41.2 | 41.2 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101037610 | RELW PRI OH INSP CLR RESD FIRE TRAF FLAG SWRK ESTR GO BTKA USA PROG FMOB TER2 | Pole | 2020-10-14 |  | COMP | 2020-10-14 |  |  | 2020-10-15 | 2020-10-15 | [12 empty] | 2020-07-22 | 2020-10-22 |  | 2020-10-22 | B tag clean up 9/5/2020 |  | Fresno |  | 163351703 | 24357.48 | 2730.9 | 679.3 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-09-05
Bay/Central | YO | GROVELAND | Sonora |  |  | COMP | 116827620 | POLE_BROK_REPL - 20011 OLD HWY 120 7SGRO | 35084382 |  |  | STS-POLE_BROK_REPL - 20011 OLD HWY 120 7 | FICL | FICL SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-09-16 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.8257 | -120.1981 |  | TIER 2 | 72 | 16335-1703, CURTIS | X38 |  | Y | 311 |  |  | 2021-01-16 | 2021-01-16 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 50.8 | 50.8 |  |  | 13.5 | 0.8 | 0.8 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101049377 | RELW COMP RESD OH PRI JPOL ESTR BTKA USA CPGG FMOB TER2 PRTO | Pole | 2020-08-07 | 2020-12-14 | COMP | 2020-08-07 | COMP | 2021-01-17 | [13 empty] | 2021-01-29 | 2021-01-17 | 2020-03-25 | 2020-10-14 | 2020-10-14 | B-tag addition 8/4/2020 |  | Bakersfield |  | 163351703 | 9349.83 | 7939.4 | 5534.6 | 5534.6 | 5534.6 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-08-04
Bay/Central | YO | GROVELAND AREA | Sonora |  |  | OPEN | 116876767 | POLE_BROK_REPL - FT\YD\OF 23057 HELLS HO | 35188631 |  |  | STS-POLE_BROK_REPL - FT\YD\OF 23057 HELL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.81 | -120.1325 |  | TIER 2 | 72 | 16335-1703, CURTIS | Y39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.7 | 28.7 |  |  | 0 | 28.7 | 28.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101038031 | OH PRI REMT NOAC ESTR USA FMOB TER2 PRTO RELW | Pole | 2020-09-08 | 2020-10-19 | COMP | 2020-09-08 | [16 empty] | 2019-03-31 | 2020-03-31 |  | 2020-03-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 20560.59 | 4240.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116751187 | POLE_BROK_REPL - 21096 HILLCROFTGROVELAN | 35208767 |  |  | STS-POLE_BROK_REPL - 21096 HILLCROFTGROV | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.8655 | -120.1797 |  | TIER 2 | 523 | 16378-1701, PEORIA | W3824 | S1465 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 43.1 | 43.1 |  |  | 0 | 43.1 | 43.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041771 | RELW OH PRI CLR JPOL RESD ESTR GO PRTO BTKA FMOB TER2 FSRP | Pole | 2021-02-22 |  | COMP | 2021-02-22 | [16 empty] | 2019-03-17 | 2020-03-17 | 2020-10-23 | 2020-10-23 | 2021 CBP Plan | 2021-02-28 | EEI |  | 163781701 | 21379.02 |  | -1100 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116751535 | POLE_BROK_REPL - 20830 ELDERBERRYGROVELA | 35214916 |  |  | STS-POLE_BROK_REPL - 20830 ELDERBERRYGRO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.8612 | -120.1824 |  | TIER 2 | 523 | 16378-1701, PEORIA | W3824 | 20283 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 45.8 | 45.8 |  |  | 0 | 45.8 | 45.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041740 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-07 | 2021-01-06 | COMP | 2021-01-06 | [16 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 163781701 | 21963.78 |  | -945 | 1132.7 | 1132.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116755609 | POLE_DECA_REPL - 13130 BOITANOGROVELAND- | 35208797 |  |  | STS-POLE_DECA_REPL - 13130 BOITANOGROVEL | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.8614 | -120.194 |  | TIER 2 | 523 | 16378-1701, PEORIA | W3822 | 20082 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101041979 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2020-10-23 | 2020-10-23 | 2021 CBP Plan | 2021-02-28 | EEI |  | 163781701 | 1 |  | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116755758 | POLE_DECA_REPL - 19775 FERRETTIGROVELAND | 35208802 |  |  |  | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.8612 | -120.2027 |  | TIER 2 | 523 | 16378-1701, PEORIA | X3801 | 20299 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101042007 | RELW OH TER2 PRI ESTR FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-02-28 | EEI |  | 163781701 | 1 |  | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116765240 | POLE_DECA_REPL - 12901 GREENVALLEY GROVE | 35208832 |  |  | STS-POLE_DECA_REPL - 12901 GREENVALLEY G | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.8575 | -120.1792 |  | TIER 2 | 523 | 16378-1701, PEORIA | X3804 | 20281 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101040802 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2020-12-04 | 2020-12-04 | 2021 CBP Plan | 2021-02-28 | EEI |  | 163781701 | 1 |  | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116792559 | POLE_DECA_REPL - 13035 GAMBLE STGROVELAN | 35083021 |  |  | STS-POLE_DECA_REPL - 13035 GAMBLE STGROV | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.8597 | -120.2208 |  | TIER 2 | 523 | 16378-1701, PEORIA | X3704 | L2099 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101035964 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2020-09-05 | 2020-09-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163781701 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116792591 | POLE_BROK_REPL - 19155 FERRETTI RDGROVEL | 35208873 |  |  | STS-POLE_BROK_REPL - 19155 FERRETTI RDGR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.8506 | -120.2235 |  | TIER 2 | 523 | 16378-1701, PEORIA | X3708 | 69124 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 69 | 69 |  |  | 0 | 69 | 69 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101035494 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-01 |  | COMP | 2021-02-01 | [16 empty] | 2019-03-20 | 2020-03-20 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-02-28 | EEI |  | 163781701 | 31656.05 | 116.3 | 0 | 1833.5 | 1833.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116792998 | POLE_BROK_REPL - 19674 COTTONWOOD ST GRO | 35208878 |  |  | STS-POLE_BROK_REPL - 19674 COTTONWOOD ST | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.8603 | -120.2073 |  | TIER 2 | 523 | 16378-1701, PEORIA | X3705 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 28.9 | 28.9 |  |  | 0 | 28.9 | 28.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101036277 | RELW OH PRI JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 |  | COMP | 2021-01-19 | [16 empty] | 2019-03-20 | 2020-03-20 | 2020-10-15 | 2020-10-15 | 2021 CBP Plan | 2021-02-28 | EEI |  | 163781701 | 21425.63 |  | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116793039 | POLE_BROK_REPL - 19762 COTTONWOOD STGROV | 35208883 |  |  | STS-POLE_BROK_REPL - 19762 COTTONWOOD ST | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.8595 | -120.2066 |  | TIER 2 | 523 | 16378-1701, PEORIA | X3705 | 20299 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 44 | 44 |  |  | 0 | 44 | 44 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101036232 | RELW OH SEC CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 |  | COMP | 2021-01-19 | [16 empty] | 2019-03-20 | 2020-03-20 | 2020-08-28 | 2020-08-28 | 2021 CBP Plan | 2021-02-28 | EEI |  | 163781701 | 24641.39 |  | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116803681 | POLE_DECA_REPL - SE C/O MUELLER DR/TANNA | 35208897 |  |  | STS-POLE_DECA_REPL - SE C/O MUELLER DR/T | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.8543 | -120.221 |  | TIER 2 | 523 | 16378-1701, PEORIA | X3704 | L2109 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 74.7 | 71 | 3.7 |  | 0 | 74.7 | 71 | 3.7 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101036049 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 |  | COMP | 2021-01-28 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-11-05 | 2020-11-05 | 2021 CBP Plan | 2021-02-28 | EEI |  | 163781701 | 31901.35 |  | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116813422 | POLE_BROK_REPL - 19481 CHAFFE CIRGROVELA | 35154372 |  |  | STS-POLE_BROK_REPL - 19481 CHAFFE CIRGRO | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.8513 | -120.2135 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3710 | L2103 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 63.3 | 63.3 |  |  | 0 | 63.3 | 63.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101036477 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2021-02-10 |  | COMP | 2021-02-10 |  |  | 2021-02-17 | 2021-02-17 | [12 empty] | 2019-03-22 | 2020-03-22 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 29745.68 | 87 | 87 | 87 | 87 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116814983 | POLE_DECA_REPL - 12749 MT.JEFFERSON GROV | 35215557 |  |  | STS-POLE_DECA_REPL - 12749 MT.JEFFERSON | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.8537 | -120.2044 |  | TIER 2 | 523 | 16378-1701, PEORIA | X3801 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101042077 | RELW OH PRI JPOL RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 163781701 | 1 |  | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116818289 | POLE_BROK_REPL - 19779 COTTONWOOD GROVEL | 35208973 |  |  | STS-POLE_BROK_REPL - 19779 COTTONWOOD GR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.8597 | -120.2058 |  | TIER 2 | 523 | 16378-1701, PEORIA | X3801 | 20299 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101042029 | RELW PRI OH JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-02-28 | EEI |  | 163781701 | 1 |  | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116818881 | TREE_DECA_INPL - 20100 FERRETTI GROVELAN | 35208978 |  |  | STS-TREE_DECA_INPL - 20100 FERRETTI GROV | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.86 | -120.1945 |  | TIER 2 | 523 | 16378-1701, PEORIA | X3802 | 20082 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 101049129 | RELW OH PRI CLR RESD ESTR GO BTKA USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 |  | 2020-03-23 | 2021 CBP Plan | 2021-02-28 | EEI |  | 163781701 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116824825 | POLE_BROK_REPL - 20854 BIGFOOT CIR.GROVE | 35154503 |  |  | STS-POLE_BROK_REPL - 20854 BIGFOOT CIR.G | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.8484 | -120.1846 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3808 | 54505 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040701 | RELW PRI OH JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116828108 | POLE_BROK_REPL - MYER CT. LOT 81GROVELAN | 35154559 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.841 | -120.1983 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3812 | L2293 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 54.1 | 54.1 |  |  | 0 | 54.1 | 54.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040338 | RELW OH PRI CLR JPOL RESD REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-17 | 2021-02-17 | COMP | 2020-09-17 |  |  | 2021-02-17 | 2021-02-17 | [12 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 31882.04 | 422.9 |  |  |  | 83.4 |  | 83.4 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116828693 | POLE_BROK_REPL - 20011 OLD HWY 120 5S 1W | 35188403 |  |  | STS-POLE_BROK_REPL - 20011 OLD HWY 120 5 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 37.8258 | -120.1995 |  | TIER 2 | 72 | 16335-1703, CURTIS | X38 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.4 | 25.4 |  |  | 0 | 25.4 | 25.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101049350 | RELW OH PRI CLR JPOL REMT ESTR PRTO USA FMOB TER2 | Pole | 2020-09-02 |  | COMP | 2020-09-02 | [16 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 12604.33 | 3241.2 | 187 | 187 | 187 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116877299 | POLE_BROK_REPL - 19400 ROLFE RD. GROVELA | 35209641 |  |  | STS-POLE_BROK_REPL - 19400 ROLFE RD. GRO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.8606 | -120.2387 |  | TIER 2 | 523 | 16378-1701, PEORIA | X37 | 26957 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101035682 | PRI RELW OH CLR REMT ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 163781701 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116877517 | POLE_BROK_REPL - 19400 ROLFE RD./2PSE/6P | 35209647 |  |  | STS-POLE_BROK_REPL - 19400 ROLFE RD./2PS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.856 | -120.2452 |  | TIER 2 | 523 | 16378-1701, PEORIA | X37 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101035710 | RELW OH PRI REMT ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2020-11-12 | 2020-11-12 | 2021 CBP Plan | 2021-02-28 | EEI |  | 163781701 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116877683 | POLE_BROK_REPL - 19400 ROLFE RD./2PSE/6P | 35209656 |  |  | STS-POLE_BROK_REPL - 19400 ROLFE RD./2PS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.8547 | -120.2433 |  | TIER 2 | 523 | 16378-1701, PEORIA | X37 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101035714 | RELW OH PRI REMT ESTR REAR USA WATR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2020-11-12 | 2020-11-12 | 2021 CBP Plan | 2021-02-28 | EEI |  | 163781701 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | COMP | 116815214 | POLE_DECA_REPL - 12736 MT.JEFFERSON GROV | 35180524 |  |  | STS-CUTO_BROK_REPL - 12736 MT.JEFFERSON | DOCC | DOCC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-03 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.8533 | -120.2048 |  | TIER 2 | 523 | 16378-1701, PEORIA | X3801 | 26966 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 43.1 | 43.1 |  |  | 0 | 43.1 | 43.1 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101042080 | RELW OH PRI JPOL RESD ESTR GO BTKA FMOB TER2 PRTO FSRP CCNT COMP | Pole | 2020-12-03 | 2020-12-08 | COMP | 2020-12-03 | COMP | 2021-02-10 | 2020-12-04 | 2020-12-04 | [11 empty] | 2021-02-18 | 2021-02-10 | 2020-03-22 | 2020-07-31 | 2020-07-31 | B-Tag Addition 06.24.20 |  | UNASSIGNED |  | 163781701 | 26332.61 | 3558.4 | 2957.4 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-06-29
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | COMP | 116828185 | POLE_BROK_REPL - 20011 OLD HWY 120 5S 3W | 35188394 |  |  | STS-POLE_BROK_REPL - 20011 OLD HWY 120 5 | FICL | FICL ERDY SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.8253 | -120.2015 |  | TIER 2 | 72 | 16335-1703, CURTIS | X38 |  | Y | 311 |  |  | 2021-01-09 | 2021-01-09 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 0.8 | 0.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101049352 | OH RELW PRI COMP CLR JPOL REMT ESTR BTKA USA CCNT FMOB TER2 PRTO | Pole | 2020-08-25 | 2021-01-08 | COMP | 2020-08-25 | COMP | 2021-01-09 | [13 empty] | 2021-01-18 | 2021-01-09 | 2020-03-25 |  | 2020-03-25 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 9810.9 | 12237.6 | 9271.9 | 21547.9 | 21547.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116752164 | POLE_BROK_REPL - 13521 CLEMENTS/8PNGROVE | 35187811 |  |  | STS-POLE_BROK_REPL - 13521 CLEMENTS/8PNG | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8732 | -120.1688 |  | TIER 2 | 72 | 16335-1703, CURTIS | W3820 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 25 | 25 |  |  | 0 | 25 | 25 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041306 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-25 | 2020-10-16 | COMP | 2020-08-25 | [16 empty] | 2019-03-17 | 2020-03-17 |  | 2020-03-17 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 11055.62 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116752261 | POLE_DECA_REPL - 13521 CLEMENTS/10PN/1PE | 35187817 |  |  | STS-POLE_DECA_REPL - 13521 CLEMENTS/10PN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8744 | -120.1675 |  | TIER 2 | 72 | 16335-1703, CURTIS | W3820 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 19.9 | 19.9 |  |  | 0 | 19.9 | 19.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101041315 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-25 | 2020-10-11 | COMP | 2020-08-25 | [16 empty] | 2019-03-17 | 2020-03-17 | 2021-07-14 | 2021-07-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 9415.98 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116752334 | POLE_BROK_REPL - 13521 CLEMENTS/10PN/1PS | 35187849 |  |  | STS-POLE_BROK_REPL - 13521 CLEMENTS/10PN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8744 | -120.1686 |  | TIER 2 | 72 | 16335-1703, CURTIS | W3820 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 9.4 | 9.4 |  |  | 0 | 9.4 | 9.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041312 | RELW OH PRI PGEA REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-08-28 | 2021-01-14 | COMP | 2020-08-28 |  |  | 2021-01-14 | 2021-01-14 | [12 empty] | 2019-03-17 | 2020-03-17 |  | 2020-03-17 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 5412.1 | 192.6 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116752649 | POLE_BROK_REPL - 13980 CLEMENTS/2PSGROVE | 35187861 |  |  | STS-POLE_BROK_REPL - 13980 CLEMENTS/2PSG | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8777 | -120.1719 |  | TIER 2 | 72 | 16335-1703, CURTIS | W3820 | S1281 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 54 | 53.2 | 0.8 |  | 0 | 54 | 53.2 | 0.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041330 | RELW OH PRI CLR JPOL REMT ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-08-28 | 2021-01-14 | COMP | 2020-08-28 |  |  | 2021-01-14 | 2021-01-14 | [12 empty] | 2019-03-17 | 2020-03-17 |  | 2020-03-17 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 27534.17 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116755615 | POLE_BROK_REPL - 14025 CLEMENTS/1PSGROVE | 35187895 |  |  | STS-POLE_BROK_REPL - 14025 CLEMENTS/1PSG | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8802 | -120.1734 |  | TIER 2 | 72 | 16335-1703, CURTIS | W3815 | S1281 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 59.7 | 58.9 | 0.8 |  | 0 | 59.7 | 58.9 | 0.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041337 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-08-28 | 2021-01-14 | COMP | 2020-08-28 |  |  | 2021-01-14 | 2021-01-14 | [12 empty] | 2019-03-18 | 2019-11-01 |  | 2019-11-01 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 32152.34 | 276.3 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116755970 | POLE_BROK_REPL - 13955 BOITANOGROVELAND- | 35187900 |  |  | STS-POLE_BROK_REPL - 13955 BOITANOGROVEL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8775 | -120.2014 |  | TIER 2 | 72 | 16335-1703, CURTIS | W38 | L1493 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 39 | 39 |  |  | 0 | 39 | 39 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101042353 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-25 | 2020-10-27 | COMP | 2020-08-25 | [16 empty] | 2019-03-18 | 2020-03-18 |  | 2020-03-18 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 18049.16 | 121.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116759576 | CRSS_BROK_REPL - 13700 CLEMENTSGROVELAND | 35187930 |  |  | STS-CRSS_BROK_REPL - 13700 CLEMENTSGROVE | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8744 | -120.166 |  | TIER 2 | 72 | 16335-1703, CURTIS | W39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 25.3 | 25.3 |  |  | 0 | 25.3 | 25.3 |  |  | EC | E | Crossarm | Broken/Damaged | Replace |  | 101041928 | RELW OH PRI JPOL REMT ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-10-20 | 2020-10-20 | COMP | 2020-08-25 | [16 empty] | 2019-03-18 | 2020-03-18 |  | 2020-03-18 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 12723.15 | 87.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116764699 | POLE_BROK_REPL - 19264 FERRETTI RD/2PNWG | 35083003 |  |  | STS-POLE_BROK_REPL - 19264 FERRETTI RD/2 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8603 | -120.2299 |  | TIER 2 | 523 | 16378-1701, PEORIA | X3703 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.5 | 25.5 |  |  | 0 | 25.5 | 25.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103108954 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-11 | 2020-12-11 | COMP | 2020-12-11 | [16 empty] | 2019-03-19 | 2020-03-19 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163781701 | 12587.44 |  | -253.4 | -162.9 | -162.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116803408 | POLE_BROK_REPL - 19273 SALVADOR CT. GROV | 35188060 |  |  | STS-POLE_BROK_REPL - 19273 SALVADOR CT. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8495 | -120.2218 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3709 | L2105 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 66 | 65.8 | 0.2 |  | 0 | 66 | 65.8 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101034428 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-28 | 2021-01-19 | COMP | 2020-08-28 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-03-21 | 2020-03-21 |  | 2020-03-21 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 32120.52 | 342.2 | 299.1 | 299.1 | 299.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116810499 | POLE_BROK_REPL - 19289 BECK RDGROVELAND- | 35188111 |  |  | STS-POLE_BROK_REPL - 19289 BECK RDGROVEL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8418 | -120.2187 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3714 | 20305 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 51.4 | 51.4 |  |  | 0 | 51.4 | 51.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101034456 | RELW OH PRI CLR REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-19 | 2020-11-05 | COMP | 2020-08-25 |  |  | 2020-07-28 | 2020-07-28 | [12 empty] | 2019-03-22 | 2020-03-22 |  | 2020-03-22 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 22163.82 | 101.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116811600 | POLE_BROK_REPL - 12639 MT. JEFFERSON STG | 35188129 |  |  | STS-POLE_BROK_REPL - 12639 MT. JEFFERSON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8522 | -120.2075 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3710 | 20267 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 55.4 | 55.4 |  |  | 0 | 55.4 | 55.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101036539 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA PRTO FMOB TER2 | Pole | 2020-10-14 | 2021-01-19 | COMP | 2020-10-14 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 27216.98 | 375.2 | 299.1 | 299.1 | 299.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116814628 | POLE_BROK_REPL - SW C/O BULTER WAY/CHAMB | 35188183 |  |  | STS-POLE_BROK_REPL - SW C/O BULTER WAY/C | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8461 | -120.2122 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3710 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 15.7 | 15.7 |  |  | 0 | 15.7 | 15.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101036709 | RELW OH SEC JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-15 | 2021-02-01 | COMP | 2020-09-15 |  |  | 2021-02-01 | 2021-02-01 | [12 empty] | 2019-03-22 | 2020-03-22 |  | 2020-03-22 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 6699.44 | 404.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116818399 | POLE_BROK_REPL - 19494 PINE MOUNTAIN DRG | 35154443 |  |  | STS-POLE_BROK_REPL - 19494 PINE MOUNTAIN | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-01-09 | Renew Permit | 37.8484 | -120.2115 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3710 |  | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | [6 empty] | 33.5 | 33.5 |  |  | 0 | 33.5 | 33.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101036648 | RELW OH PRI JPOL RESD FLAG ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-04-29 | 2020-07-10 | COMP | 2020-04-29 |  |  | 2021-02-19 | 2021-02-19 | [12 empty] | 2019-03-23 | 2020-03-23 |  | 2020-03-23 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351703 | 17217.82 | 1678.1 | 1332.9 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116818997 | POLE_BROK_REPL - 18548 EL CAPITIAN WY/1P | 35188236 |  |  | STS-POLE_BROK_REPL - 18548 EL CAPITIAN W | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.827 | -120.2352 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3717 | 1891 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 52.5 | 52.5 |  |  | 0 | 52.5 | 52.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101034822 | RELW OH PRI CLR JPOL RESD REMT NOAC ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-26 | 2020-11-04 | COMP | 2020-08-25 |  |  | 2020-11-04 | 2020-11-04 | [12 empty] | 2019-03-23 | 2020-03-23 |  | 2020-03-23 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116821438 | POLE_BROK_REPL - 12600 CRESTHAVEN GROVEL | 35188266 |  |  | STS-POLE_BROK_REPL - 12600 CRESTHAVEN GR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8523 | -120.1895 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3808 | 26964 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 43 | 43 |  |  | 0 | 43 | 43 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040740 | RELW OH PRI CLR JPOL BTKA RESD ESTR FMOB TER2 PRTO | Pole | 2021-01-15 | 2021-02-01 | COMP | 2020-08-28 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-03-24 | 2020-03-24 |  | 2020-03-24 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 23773.84 | 117.9 | 74.8 | 74.8 | 74.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116821560 | POLE_BROK_REPL - 12612 CRESTHAVEN/1PSGRO | 35188271 |  |  | STS-POLE_BROK_REPL - 12612 CRESTHAVEN/1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8527 | -120.1896 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3803 | L2285 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 55.9 | 55.9 |  |  | 0 | 55.9 | 55.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101042287 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-27 | 2020-10-27 | COMP | 2020-08-27 | [16 empty] | 2019-03-24 | 2020-03-24 |  | 2020-03-24 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 26100.79 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116822248 | POLE_BROK_REPL - 12314 TOWER PEAK CT. GR | 35188286 |  |  | STS-POLE_BROK_REPL - 12314 TOWER PEAK CT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8464 | -120.1995 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3806 | 64269 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 59.8 | 59.8 |  |  | 0 | 59.8 | 59.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040301 | OH PRI RESD ESTR BTKA FMOB TER2 PRTO RELW | Pole | 2020-09-09 | 2020-11-16 | COMP | 2020-09-09 | [16 empty] | 2019-03-24 | 2020-03-24 |  | 2020-03-24 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 22236.37 | 1404 | 1041.9 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116822860 | POLE_BROK_REPL - 20157 UPPER SKYRIDGE/1P | 35188300 |  |  | STS-POLE_BROK_REPL - 20157 UPPER SKYRIDG | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.846 | -120.1937 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3807 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.8 | 23.6 | 0.2 |  | 0 | 23.8 | 23.6 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040250 | RELW OH SEC CLR FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-11 | 2021-02-01 | COMP | 2020-09-11 |  |  | 2021-02-01 | 2021-02-01 | [12 empty] | 2019-03-24 | 2020-03-24 |  | 2020-03-24 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 11355.08 | 543 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116825184 | POLE_BROK_REPL - 12300 SHOOTING STAR CTG | 35154508 |  |  |  | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8463 | -120.1967 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3807 | 20271 | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | [6 empty] | 53.8 | 53.8 |  |  | 0.5 | 53.3 | 53.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040320 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-05-05 | 2020-07-24 | COMP | 2020-05-05 |  |  | 2020-07-24 | 2020-07-24 | [12 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351703 | 28994.26 | 3014.7 | 2970.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116825633 | POLE_BROK_REPL - 10966 YOSEMITE SPRINGS | 35188315 |  |  | STS-POLE_BROK_REPL - 10966 YOSEMITE SPRI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8221 | -120.1951 |  | TIER 2 | 72 | 16335-1703, CURTIS | X38 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 32.4 | 32.2 | 0.2 |  | 0 | 32.4 | 32.2 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101049409 | RELW OH SEC RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-08-25 | 2020-08-25 | COMP | 2020-08-25 | [16 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116828089 | POLE_DECA_REPL - HETCH HETCHY CT. CRESTH | 35188379 |  |  | STS-POLE_DECA_REPL - HETCH HETCHY CT. CR | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8511 | -120.1788 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3809 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 60.2 | 58.2 | 2 |  | 0 | 60.2 | 58.2 | 2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101040778 | RELW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-08-28 | 2021-01-14 | COMP | 2020-08-28 |  |  | 2021-01-14 | 2021-01-14 | [12 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 34205.91 | 76.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116828090 | POLE_BROK_REPL - 20011 OLD HWY 120 5S 4W | 35188383 |  |  | STS-POLE_BROK_REPL - 20011 OLD HWY 120 5 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.825 | -120.2025 |  | TIER 2 | 72 | 16335-1703, CURTIS | X38 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 32 | 32 |  |  | 0 | 32 | 32 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101049353 | RELW OH PRI CLR JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-08-26 | 2020-12-29 | COMP | 2020-08-26 | [16 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 14792.19 | 2796.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116836472 | POLE_BROK_REPL - 19920 OLD HWY 120 1N 1W | 35188422 |  |  | STS-POLE_BROK_REPL - 19920 OLD HWY 120 1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8308 | -120.2028 |  | TIER 2 | 72 | 16335-1703, CURTIS | X38 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.2 | 40.2 |  |  | 0 | 40.2 | 40.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101049313 | RELW OH SEC CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-12-03 | COMP | 2020-10-12 | [16 empty] | 2019-03-26 | 2020-03-26 |  | 2020-03-26 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 13061.15 | 42.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116841827 | POLE_BROK_REPL - WHITE GULCH HWY 120 1NG | 35188442 |  |  | STS-POLE_BROK_REPL - WHITE GULCH HWY 120 | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.8326 | -120.1992 |  | TIER 2 | 72 | 16335-1703, CURTIS | X38 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.8 | 33.8 |  |  | 0 | 33.8 | 33.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101049300 | RELW OH PRI CLR JPOL REMT ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-09-10 | 2021-01-21 | COMP | 2020-09-10 | [16 empty] | 2019-03-26 | 2020-03-26 |  | 2020-03-26 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 25911.74 | 631.3 | -253.4 | -162.9 | -162.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116841986 | TREE_DECA_INPL - #1 W/O MB 11828 GREG CT | 35188447 |  |  | STS-TREE_DECA_INPL - #1 W/O MB 11828 GRE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8388 | -120.1956 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3812 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 9.8 | 9.8 |  |  | 0 | 9.8 | 9.8 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 102339769 | RELW OH SERV REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-14 | 2020-11-05 | COMP | 2020-09-11 | [16 empty] | 2019-03-26 | 2019-10-02 |  | 2019-10-02 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 3172.45 | 588.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116842622 | POLE_BROK_REPL - 20401 WHITE GULCH RD.GR | 35154612 |  |  | STS-POLE_BROK_REPL - 20401 WHITE GULCH R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8357 | -120.1945 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3812 | 2071 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 62.3 | 62.3 |  |  | 0 | 62.3 | 62.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101042620 | RELW OH PRI CLR JPOL RESD REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-05 | 2020-11-03 | COMP | 2020-08-05 |  |  | 2020-10-24 | 2020-10-24 | [12 empty] | 2019-03-26 | 2020-03-26 |  | 2020-03-26 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 29139.42 | 400.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116846382 | POLE_BROK_REPL - 21050 WHITE GULCH RD.GR | 35188467 |  |  | STS-POLE_BROK_REPL - 21050 WHITE GULCH R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8359 | -120.1962 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3812 | 2071 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.1 | 33.1 |  |  | 0 | 33.1 | 33.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101042616 | RELW OH PRI CLR JPOL RESD REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-10 | 2021-02-01 | COMP | 2020-09-10 |  |  | 2021-02-01 | 2021-02-01 | [12 empty] | 2019-03-27 | 2020-03-27 |  | 2020-03-27 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 19508.37 | 920.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116848069 | POLE_DECA_REPL - 20887 MCKINLEY GROVELAN | 35188483 |  |  | STS-POLE_DECA_REPL - 20887 MCKINLEY GROV | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8418 | -120.1692 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3815 | L2301 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.1 | 42.1 |  |  | 0 | 42.1 | 42.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101040577 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-21 | 2020-11-23 | COMP | 2020-09-21 | [16 empty] | 2019-03-27 | 2020-03-27 |  | 2020-03-27 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 23201.83 | 562.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116879735 | POLE_BROK_REPL - 21925 BIG CREEK SHAFT R | 35187568 |  |  | STS-POLE_BROK_REPL - 21925 BIG CREEK SHA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8346 | -120.1569 |  | TIER 2 | 72 | 16335-1703, CURTIS | X39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.4 | 15.4 |  |  | 0 | 15.4 | 15.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101036602 | RELW OH ESTR PRI RESD BTKA RTRN USA FMOB TER2 PRTO | Pole | 2020-09-10 | 2020-09-10 | COMP | 2020-09-10 | [16 empty] | 2019-04-01 | 2020-04-01 |  | 2020-04-01 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 6888 | 495.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116880217 | POLE_BROK_REPL - 21925 BIG CREEK SHAFT R | 35154025 |  |  | STS-POLE_BROK_REPL - 21925 BIG CREEK SHA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-01-09 | Renew Permit | 37.8334 | -120.155 |  | TIER 2 | 72 | 16335-1703, CURTIS | X39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17 | 17 |  |  | 0 | 17 | 17 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101036600 | RELW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-04-30 | 2020-07-01 | COMP | 2020-04-30 |  |  | 2021-02-19 | 2021-02-19 | [12 empty] | 2019-04-01 | 2020-04-01 |  | 2020-04-01 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351703 | 10391.49 | 233.2 |  |  |  | 143.8 |  | 143.8 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116882737 | POLE_BROK_REPL - 11350 BIG CREEK SHAFT R | 35187639 |  |  | STS-POLE_BROK_REPL - 11350 BIG CREEK SHA | UNSC | UNSC srdy | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8274 | -120.1485 |  | TIER 2 | 72 | 16335-1703, CURTIS | X39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.5 | 14.5 |  |  | 0 | 14.5 | 14.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101036575 | RELW OH SERV REMT TRAF ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-14 | 2020-10-14 | COMP | 2020-10-14 |  |  | 2020-09-08 | 2020-09-08 | [12 empty] | 2019-04-01 | 2020-04-01 |  | 2020-04-01 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116883238 | POLE_BROK_REPL - 18511 BAIRDS/6PS/2PNWGR | 35187644 |  |  | STS-POLE_BROK_REPL - 18511 BAIRDS/6PS/2P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.832 | -120.2395 |  | TIER 2 | 72 | 16335-1703, CURTIS | X37 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.6 | 38.6 |  |  | 0 | 38.6 | 38.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101035032 | RELW OH PRI REMT NOAC ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-11-25 | 2020-12-11 | COMP | 2020-09-04 | [16 empty] | 2019-04-01 | 2020-04-01 |  | 2020-04-01 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 27569.02 | 808.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116884625 | POLE_BROK_REPL - 11722 BIG CREEK SHAFT R | 35187668 |  |  | STS-POLE_BROK_REPL - 11722 BIG CREEK SHA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8303 | -120.1511 |  | TIER 2 | 72 | 16335-1703, CURTIS | X39 | 2015 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.7 | 36.7 |  |  | 0 | 36.7 | 36.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101036587 | RELW OH PRI PGEA CLR RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-21 | 2020-09-21 | COMP | 2020-09-21 | [16 empty] | 2019-04-01 | 2020-04-01 |  | 2020-04-01 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 15468.27 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116884626 | POLE_BROK_REPL - 11485 BIG CREEK SHAFT R | 35187674 |  |  | STS-POLE_BROK_REPL - 11485 BIG CREEK SHA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8301 | -120.1494 |  | TIER 2 | 72 | 16335-1703, CURTIS | X39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 30 | 28.2 | 1.8 |  | 0 | 30 | 28.2 | 1.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101036576 | RELW OH SEC PGEA CLR RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-08 | 2021-02-01 | COMP | 2020-09-08 |  |  | 2021-02-01 | 2021-02-01 | [12 empty] | 2019-04-01 | 2020-04-01 |  | 2020-04-01 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 14399.01 | 576.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116899409 | POLE_BROK_REPL - 11722 BIG CREEK SHAFT R | 35187679 |  |  | STS-POLE_BROK_REPL - 11722 BIG CREEK SHA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8287 | -120.1521 |  | TIER 2 | 72 | 16335-1703, CURTIS | X39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.3 | 44.3 |  |  | 0 | 44.3 | 44.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103109809 | RELW OH PRI REMT NOAC ESTR USA FMOB TER2 PRTO | Pole | 2020-10-07 | 2020-10-24 | COMP | 2020-09-09 | [16 empty] | 2019-04-01 | 2020-04-01 |  | 2020-04-01 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 30317.07 | 1120.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116941544 | POLE_BROK_REPL - 22550 FERRETTI RD.5W 1S | 35187741 |  |  | STS-POLE_BROK_REPL - 22550 FERRETTI RD.5 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8497 | -120.1486 |  | TIER 2 | 72 | 16335-1703, CURTIS | X39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.3 | 15.3 |  |  | 0 | 15.3 | 15.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101036777 | RELW PRI OH JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-08 | 2020-11-09 | COMP | 2020-09-08 | [16 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 5940.53 | 703 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116950147 | POLE_BROK_REPL - R/O 19732 OLD HWY 120GR | 35187792 |  |  | STS-POLE_BROK_REPL - R/O 19732 OLD HWY 1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8334 | -120.2091 |  | TIER 2 | 72 | 16335-1703, CURTIS | X37 | 27332 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 58 | 57 | 1 |  | 0 | 58 | 57 | 1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101034611 | RELW OH PRI CLR REMT TER2 NOAC ESTR REAR USA FMOB PRTO | Pole | 2020-09-09 | 2020-11-17 | COMP | 2020-09-09 | [16 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 25974.54 | 540.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116950373 | POLE_BROK_REPL - 19728 OLD HWY 120GROVEL | 35154081 |  |  | STS-POLE_BROK_REPL - 19728 OLD HWY 120GR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8342 | -120.2091 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3715 | 27332 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.8 | 37.8 |  |  | 0 | 37.8 | 37.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101034609 | RELW OH PRI CLR REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-22 | 2020-12-03 | COMP | 2020-09-21 | [16 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 16051.88 | 295.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116954708 | POLE_BROK_REPL - 19639 OLD HWY 120/2PW/2 | 35187842 |  |  | STS-POLE_BROK_REPL - 19639 OLD HWY 120/2 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.834 | -120.2135 |  | TIER 2 | 72 | 16335-1703, CURTIS | X37 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.3 | 18.3 |  |  | 0 | 18.3 | 18.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101034625 | RELW OH PRI REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-10 | 2020-11-18 | COMP | 2020-09-10 | [16 empty] | 2019-04-04 | 2020-04-04 |  | 2020-04-04 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 7913.57 | 628.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 117322619 | POLE_DECA_REPL - 19440 BECK RD GROVELAND | 35189372 |  |  | STS-POLE_DECA_REPL - 19440 BECK RD GROVE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8436 | -120.2133 |  | TIER 2 | 72 | 16335-1703, CURTIS | X3710 | 56715 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 46.3 | 46.3 |  |  | 0 | 46.3 | 46.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101034494 | RELW OH PRI CLR JPOL RESD REMT ESTR GO FMOB TER2 PRTO | Pole | 2020-09-14 | 2020-11-05 | COMP | 2020-09-14 | [16 empty] | 2019-05-26 | 2020-05-26 |  | 2020-05-26 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 22882.72 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Groveland-Big Oak Flat | Sonora |  |  | OPEN | 118168241 | POLE_BROK_REPL - 22177 FERRETTI RD.4W 2S | 35189090 |  |  | STS-POLE_BROK_REPL - 22177 FERRETTI RD.4 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8487 | -120.1563 |  | TIER 2 | 72 | 16335-1703, CURTIS | X39 | 1945 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 44.2 | 44 | 0.2 |  | 0 | 44.2 | 44 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101036733 | OH RELW PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-16 | 2020-11-20 | COMP | 2020-09-16 | [16 empty] | 2019-11-13 | 2020-05-13 |  | 2020-05-13 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 19910.29 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116751236 | POLE_DECA_REPL - 21066 HEMLOCK GROVELAND | 35225844 |  |  | STS-POLE_DECA_REPL - 21066 HEMLOCK GROVE | APPR | APPR | Poles | MPP | Not Funded as 2020 Wildfire OII | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | Permit FAA JointPole |  |  | 37.8659 | -120.181 |  | TIER 2 | 523 | 16378-1701, PEORIA | W3824 | S1465 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101041762 | RELW OH PRI BTKA JPOL RESD JAR PROG FMOB TER2 PRTO FSRP | Pole |  |  | NOTN | 2021-01-15 | [16 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | work plan year cleanup 01/21/2021 |  | Fresno |  | 163781701 | [9 empty] | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-21
Bay/Central | YO | GROVELAND-BIG OAK FLAT | Sonora |  |  | OPEN | 116877110 | POLE_BROK_REPL - 19400 ROLFE RD./2PSEGRO | 35084315 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8591 | -120.238 |  | TIER 2 | 523 | 16378-1701, PEORIA | X37 | 9250 | Y | 311 |  |  | 2021-11-02 07:00 | 2021-11-02 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101035674 | RELW OH PRI CLR REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-12 | 2021-01-12 | COMP | 2021-01-12 | [16 empty] | 2019-03-31 | 2020-03-31 | 2020-09-08 | 2020-09-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163781701 | 13442.87 |  | 0 | 570.5 | 570.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116921907 | POLE_BROK_REPL - 1N 14801 JACKSONVILLE R | 35209694 |  |  | STS-POLE_BROK_REPL - 1N 14801 JACKSONVIL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.897 | -120.4012 |  | TIER 2 | 434 | 16378-1705, PEORIA | W33 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.2 | 17.2 |  |  | 0 | 17.2 | 17.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029071 | RELW OH PRI REMT ESTR GO USA FMOB TER2 PRTO FSRP | Pole | 2021-02-18 | 2021-02-18 | COMP | 2021-02-18 | [16 empty] | 2019-04-02 | 2020-04-02 | 2020-10-09 | 2020-10-09 | 2021 CBP Plan | 2021-02-28 | EEI |  | 163781705 | 8455.93 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116961653 | POLE_BROK_REPL - PEORIA FLAT RD/OBYRNS F | 35154105 |  |  | STS-POLE_BROK_REPL - PEORIA FLAT RD/OBYR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.9016 | -120.5049 |  | TIER 2 | 93 | 16378-1704, PEORIA | W30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 46.4 | 46.4 |  |  | 0 | 46.4 | 46.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040469 | RELW OH PRI REMT ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-04-24 |  | COMP | 2020-04-24 |  |  | 2020-07-27 | 2020-07-27 | [12 empty] | 2019-04-05 | 2020-04-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 163781704 | 22722.3 | 282.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116962315 | POLE_BROK_REPL - 2W 14301 SIMS RDJAMESTO | 35208860 |  |  | STS-POLE_BROK_REPL - 2W 14301 SIMS RDJAM | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.8866 | -120.4481 |  | TIER 2 | 523 | 16378-1701, PEORIA | W31 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101028590 | RELW OH PRI REMT NOAC ESTR GO USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-05 | 2020-04-05 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163781701 | 1 | 44.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116969865 | POLE_BROK_REPL - 15400 OBYRNS FERRY RD 3 | 35214721 |  |  | STS-POLE_BROK_REPL - 15400 OBYRNS FERRY | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9022 | -120.5525 |  | TIER 2 | 93 | 16378-1704, PEORIA | W29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041495 | RELW OH PRI GO REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-06 | 2020-04-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 163781704 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116970092 | POLE_DECA_REPL - 15400 OBYRNS FERRY RD 3 | 35208900 |  |  | STS-POLE_DECA_REPL - 15400 OBYRNS FERRY | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.9025 | -120.5566 |  | TIER 2 | 93 | 16378-1704, PEORIA | W29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27 | 27 |  |  | 0 | 27 | 27 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101041489 | RELW OH PRI REMT NOAC ESTR GO FMOB TER2 PRTO FSRP | Pole | 2020-12-14 | 2020-12-14 | COMP | 2020-12-11 | [16 empty] | 2019-04-06 | 2020-04-06 |  | 2020-04-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163781704 | 22954.46 | 8.8 | -1267 | -814.5 | -814.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116976637 | POLE_BROK_REPL - 13400 HWY 108 1PS/0JAME | 35086579 |  |  | STS-POLE_BROK_REPL - 13400 HWY 108 1PS/0 | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.8623 | -120.5152 |  | TIER 2 | 93 | 16378-1704, PEORIA | W30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041794 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-08 | 2019-10-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | Fresno |  | 163781704 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116978896 | POLE_DECA_REPL - 16700 CHICKEN RANCHJAME | 35154222 |  |  | STS-POLE_DECA_REPL - 16700 CHICKEN RANCH | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 37.9264 | -120.4536 |  | TIER 2 | 434 | 16378-1705, PEORIA | V31 | L473 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.2 | 29.2 |  |  | 0 | 29.2 | 29.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101042278 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-01 | 2020-11-29 | COMP | 2020-08-13 |  |  | 2020-03-13 | 2020-03-13 | [12 empty] | 2019-04-08 | 2020-04-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781705 | 15957.44 | 586.4 |  |  |  | 88.7 |  | 88.7 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116990463 | POLE_BROK_REPL - HARVEY MINE RD W/HWY 49 | 35154307 |  |  | STS-POLE_BROK_REPL - HARVEY MINE RD W/HW | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9394 | -120.436 |  | TIER 2 | 434 | 16378-1705, PEORIA | V3207 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.2 | 22.2 |  |  | 0 | 22.2 | 22.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101034852 | RELW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-08 |  | COMP | 2021-01-08 | [16 empty] | 2019-04-09 | 2020-04-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781705 | 8620.74 | 172.4 | 132 | 458 | 458 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117137637 | POLE_DECA_REPL - 18860 RAWHIDE RDJAMESTO | 35154275 |  |  | STS-POLE_DECA_REPL - 18860 RAWHIDE RDJAM | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9654 | -120.4317 |  | TIER 2 | 434 | 16378-1705, PEORIA | U3217 | 6697 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 49.3 | 49.3 |  |  | 0 | 49.3 | 49.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101050367 | RELW OH PRI ESTR CLR JPOL RESD BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-20 |  | COMP | 2021-01-20 | [16 empty] | 2019-05-01 | 2020-05-01 | 2024-04-29 | 2024-04-29 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781705 | 20863.36 |  | 0 | 978 | 978 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117138259 | POLE_BROK_REPL - RO 18321 SHELL 2/NJAMES | 35097558 |  |  | STS-POLE_BROK_REPL - RO 18321 SHELL 2/NJ | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.9538 | -120.4525 |  | TIER 2 | 434 | 16378-1705, PEORIA | U3125 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.1 | 40.1 |  |  | 0 | 40.1 | 40.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101012459 | RELW OH PRI REMT NOAC FLAG ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-17 | 2020-12-16 | COMP | 2020-12-16 | [16 empty] | 2019-05-01 | 2020-05-01 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163781705 | 20902.18 | 217.2 | -760.2 | -398.2 | -398.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117142898 | POLE_BROK_REPL - 18790 RAILBED RDJAMESTO | 35215103 |  |  | STS-POLE_BROK_REPL - 18790 RAILBED RDJAM | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.9636 | -120.435 |  | TIER 2 | 434 | 16378-1705, PEORIA | U3217 | 4893 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 38.5 | 38.5 |  |  | 0 | 38.5 | 38.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101050222 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-25 | 2021-01-22 | COMP | 2021-01-22 | [16 empty] | 2019-05-02 | 2019-11-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 163781705 | 25538.14 | 40.4 | -210 | 1175 | 1175 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117145888 | POLE_DECA_REPL - MB 10510 WIGWAM RDJAMES | 35208972 |  |  | STS-POLE_DECA_REPL - MB 10510 WIGWAM RDJ | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.962 | -120.417 |  | TIER 2 | 434 | 16378-1705, PEORIA | U3219 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17 | 17 |  |  | 0 | 17 | 17 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101051862 | RELW OH PRI JPOL ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-15 |  | COMP | 2020-12-15 | [16 empty] | 2019-05-02 | 2020-05-02 | 2020-10-23 | 2020-10-23 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163781705 | 9003.86 | 62.3 | -724 | -362 | -362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117155775 | POLE_DECA_REPL - ENT 9192 HWY 49 1/WJAME | 35215181 |  |  | STS-POLE_DECA_REPL - ENT 9192 HWY 49 1/W | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land JointPole |  |  | 37.9897 | -120.4479 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U3105 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.5 | 13.5 |  |  | 0 | 13.5 | 13.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101012659 | RELW OH PRI JPOL FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-10 |  | COMP | 2021-02-10 | [16 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 163761704 | 10088.77 | 19.4 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117156326 | POLE_DECA_REPL - 8111 WILLIAMSON 1/W JAM | 35209103 |  |  | STS-POLE_DECA_REPL - 8111 WILLIAMSON 1/W | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.9684 | -120.4734 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U31 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101012570 | OH RELW PRI CLR JPOL RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2020-09-16 | 2020-09-16 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163761704 | 1 | 40.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117159187 | POLE_BROK_REPL - 7755 FRENCH FLAT 1/E 3/ | 35215219 |  |  | STS-POLE_BROK_REPL - 7755 FRENCH FLAT 1/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9747 | -120.4843 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U31 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101012586 | RELW OH PRI CLR RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 163761704 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117159432 | POLE_BROK_REPL - 7755 1/E 2N JAMESTOWN | 35215224 |  |  | STS-POLE_BROK_REPL - 7755 1/E 2N JAMESTO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9743 | -120.4831 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U31 | 1695 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101012587 | RELW OH PRI CLR RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 163761704 | 1 |  | -210 | 735 | 735 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117168418 | POLE_BROK_REPL - 1PN 17977 CALLE OESTEJA | 35154426 |  |  | STS-POLE_BROK_REPL - 1PN 17977 CALLE OES | UNSC | UNSC | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND | 2021-01-09 | Renew Permit | 37.9494 | -120.3845 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3303 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.8 | 13.8 |  |  | 0 | 13.8 | 13.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030997 | RELW PRI OH INSP JPOL RESD FIRE ESTR BTKA USA PROG FMOB TER2 | Pole | 2020-06-22 | 2021-02-19 | COMP | 2020-05-07 |  |  | 2021-02-19 | 2021-02-19 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 163351703 | 11268.6 | 188.2 |  |  |  | 188.2 |  | 188.2 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117169701 | POLE_BROK_REPL - 17975 VIA SERENAJAMESTO | 35188308 |  |  | STS-POLE_BROK_REPL - 17975 VIA SERENAJAM | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 37.9492 | -120.3829 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3303 | 19687 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.8 | 56.8 | 1 |  | 0 | 57.8 | 56.8 | 1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031006 | RELW OH PRI INSP JPOL RESD FIRE ESTR BTKA USA PROG FMOB TER2 | Pole | 2020-09-15 |  | COMP | 2020-09-15 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 28298.33 | 493.9 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117190149 | POLE_BROK_REPL - 1PS 2PE 13030 ALGERINE | 35188677 |  |  | STS-POLE_BROK_REPL - 1PS 2PE 13030 ALGER | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.9021 | -120.359 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.8 | 20.8 |  |  | 0 | 20.8 | 20.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029414 | RELW OH PRI INSP RESD FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-09-16 | 2021-02-03 | COMP | 2020-09-16 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 12155.88 | 756.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117240193 | POLE_DECA_REPL - 14777 TWIST RD JAMESTOW | 35189241 |  |  | STS-POLE_DECA_REPL - 14777 TWIST RD JAME | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.8813 | -120.3579 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 | 557573 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.1 | 35.5 | 0.6 |  | 0 | 36.1 | 35.5 | 0.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101029375 | RELW OH PRI PGEA INSP JPOL RESD ESTR BTKA FMOB TER2 | Pole | 2020-10-05 | 2021-02-19 | COMP | 2020-10-05 | [16 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 16129.3 | 60.5 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117295317 | POLE_BROK_REPL - MAP V29 N512/E160 1PW 2 | 35215550 |  |  | STS-POLE_BROK_REPL - MAP V29 N512/E160 1 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9144 | -120.4854 |  | TIER 2 | 434 | 16378-1705, PEORIA | V30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101042917 | RELW OH PRI CLR REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-21 | 2020-05-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 163781705 | 1 | 93.5 | -116.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | COMP | 117168647 | POLE_BROK_REPL - 18051 CALLE OESTEJAMEST | 35154435 |  |  | STS-POLE_BROK_REPL - 18051 CALLE OESTEJA | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-11-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2021-01-09 | No Action | 37.95 | -120.3846 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3303 | 19686 | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 91.9 | 90.7 | 1.2 |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030998 | RELW OH PRI INSP JPOL RESD FIRE ESTR BTKA USA PROG FMOB TER2 CCNT COMP | Pole | 2020-05-18 | 2020-07-24 | COMP | 2020-05-18 | COMP | 2021-01-06 | 2020-03-11 | 2020-03-11 | [11 empty] | 2021-01-19 | 2021-01-06 | 2020-05-06 |  | 2020-05-06 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351703 | 25105.34 | 21615.8 | 21427.7 | 18471.5 | 18471.5 | 188.2 |  | 188.2 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116905998 | POLE_BROK_REPL - SW555-HWY120 1PS/5PNW/1 | 35176856 |  |  | BC3 STS-POLE_BROK_REPL - SW555-HWY120 1P | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8251 | -120.3326 |  | TIER 2 | 523 | 16378-1701, PEORIA | X34 | 94653 | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Dispatched | CLICK | [6 empty] | 41.9 | 41.9 |  |  | 0.5 | 41.4 | 41.4 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101030353 | RELW OH PRI CLR REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-06-09 | 2020-06-09 | COMP | 2020-06-09 | [16 empty] | 2019-04-02 | 2020-04-02 | 2020-08-08 | 2020-08-08 | B-Tag Clean Up 5/14/20 |  | Fresno |  | 163781701 | 44109.76 | 18158.2 | -21215.4 | -17545.7 | -17545.7 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-05-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116937308 | POLE_BROK_REPL - 1N 13383 LONE BEND RDJA | 35154068 |  |  | STS-POLE_BROK_REPL - 1N 13383 LONE BEND | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8676 | -120.376 |  | TIER 2 | 434 | 16378-1705, PEORIA | W33 | L843 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 63.1 | 61.1 | 2 |  | 0 | 63.1 | 61.1 | 2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029273 | RELW OH PRI CLR REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-09-08 | 2020-09-08 | COMP | 2020-09-08 |  |  | 2020-07-31 | 2020-07-31 | [12 empty] | 2019-04-02 | 2020-04-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781705 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116940838 | POLE_BROK_REPL - 6PW2PS 12882 ALGERINE R | 35154073 |  |  | STS-POLE_BROK_REPL - 6PW2PS 12882 ALGERI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.905 | -120.3756 |  | TIER 2 | 72 | 16335-1703, CURTIS | W33 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 29.4 | 29.4 |  |  | 0 | 29.4 | 29.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029120 | RELW OH SEC CLR REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-04-09 | 2020-06-05 | COMP | 2020-04-09 | [16 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351703 | 19665.94 | 495.1 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116959043 | POLE_BROK_REPL - R/O 13944 HALL DRJAMEST | 35154089 |  |  | STS-POLE_BROK_REPL - R/O 13944 HALL DRJA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8764 | -120.4016 |  | TIER 2 | 434 | 16378-1705, PEORIA | W3316 | 21455 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 42.5 | 42.5 |  |  | 0 | 42.5 | 42.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029130 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-09-08 | 2020-10-28 | COMP | 2020-09-08 | [16 empty] | 2019-04-04 | 2020-04-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781705 | 22051.34 | 45.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116961773 | POLE_DECA_REPL - PEORIA FLAT RD/OBYRNS F | 35188034 |  |  | STS-POLE_DECA_REPL - PEORIA FLAT RD/OBYR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9016 | -120.5057 |  | TIER 2 | 93 | 16378-1704, PEORIA | W30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.4 | 16.4 |  |  | 0 | 16.4 | 16.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101040473 | RELW OH PRI REMT ESTR GO BTKA REAR FMOB TER2 PRTO FSRP | Pole | 2020-09-15 | 2020-09-15 | COMP | 2020-09-15 | [16 empty] | 2019-04-05 | 2020-04-05 | 2024-04-03 | 2024-04-03 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 7310.2 | 461.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116961965 | POLE_BROK_REPL - PEORIA FLAT RD/OBYRNS F | 35188059 |  |  | STS-POLE_BROK_REPL - PEORIA FLAT RD/OBYR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9016 | -120.5071 |  | TIER 2 | 93 | 16378-1704, PEORIA | W30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.1 | 41.1 |  |  | 0 | 41.1 | 41.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040476 | RELW OH PRI CLR REMT SPCR ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-09-22 | 2020-09-22 | COMP | 2020-09-22 | [16 empty] | 2019-04-05 | 2020-04-05 | 2024-04-03 | 2024-04-03 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 16556.39 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116962280 | POLE_BROK_REPL - 15400 OBYRNS FERRY RD 3 | 35188095 |  |  | STS-POLE_BROK_REPL - 15400 OBYRNS FERRY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9017 | -120.5076 |  | TIER 2 | 93 | 16378-1704, PEORIA | W30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.3 | 15.3 |  |  | 0 | 15.3 | 15.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040477 | RELW OH PRI REMT SPCR ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-09-16 | 2020-09-16 | COMP | 2020-09-16 | [16 empty] | 2019-04-05 | 2020-04-05 | 2024-04-03 | 2024-04-03 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 7096.06 | 51.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116966639 | POLE_DECA_REPL - 6060 OBYRNS FERRY RD 2P | 35188216 |  |  | STS-POLE_DECA_REPL - 6060 OBYRNS FERRY R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8883 | -120.5243 |  | TIER 2 | 93 | 16378-1704, PEORIA | W30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.2 | 18.2 |  |  | 0 | 18.2 | 18.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101041398 | RELW OH PRI REMT FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2020-09-22 | 2021-02-03 | COMP | 2020-09-22 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-05 | 2020-04-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 11635.82 | 55.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116966992 | POLE_BROK_REPL - 2S 14555 TWIST RDJAMEST | 35188234 |  |  | STS-POLE_BROK_REPL - 2S 14555 TWIST RDJA | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8808 | -120.3658 |  | TIER 2 | 72 | 16335-1703, CURTIS | W33 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.8 | 31.8 |  |  | 0 | 31.8 | 31.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029326 | RELW OH PRI JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-22 | 2020-11-17 | COMP | 2020-09-22 | [16 empty] | 2019-04-05 | 2020-04-05 |  | 2020-04-05 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 11594.88 | 81.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116967270 | POLE_BROK_REPL - 14733 TWIST RD 1P S JAM | 35188252 |  |  | STS-POLE_BROK_REPL - 14733 TWIST RD 1P S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8864 | -120.3684 |  | TIER 2 | 72 | 16335-1703, CURTIS | W33 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.8 | 21.8 |  |  | 0 | 21.8 | 21.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103354673 | RELW OH PRI CLR JPOL USA REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-28 | 2020-11-24 | COMP | 2020-09-28 | [16 empty] | 2019-04-05 | 2020-04-05 |  | 2020-04-05 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 8828.3 | 346.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116967483 | POLE_BROK_REPL - 14741 TWIST RDJAMESTOWN | 35188269 |  |  | STS-POLE_BROK_REPL - 14741 TWIST RDJAMES | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8894 | -120.3657 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 | 1721 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40 | 40 |  |  | 0 | 40 | 40 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029332 | RELW OH PRI CLR RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-04-05 | 2020-04-05 |  | 2020-04-05 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116968883 | POLE_BROK_REPL - PEORIA FLAT RD/OBYRNS F | 35188291 |  |  | STS-POLE_BROK_REPL - PEORIA FLAT RD/OBYR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8945 | -120.5066 |  | TIER 2 | 93 | 16378-1704, PEORIA | W30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.2 | 26.2 |  |  | 0 | 26.2 | 26.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040458 | RELW OH SERV CUST CLR REMT SPCR ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-09-30 | 2020-09-30 | COMP | 2020-09-30 | [16 empty] | 2019-04-06 | 2020-04-06 | 2024-04-04 | 2024-04-04 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 8945.27 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116968928 | POLE_BROK_REPL - 15400 OBYRNS FERRY RD 3 | 35154140 |  |  | STS-POLE_BROK_REPL - 15400 OBYRNS FERRY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9021 | -120.5433 |  | TIER 2 | 93 | 16378-1704, PEORIA | W29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.4 | 32.4 |  |  | 0 | 32.4 | 32.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040672 | RELW OH PRI REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-05-13 | 2020-05-13 | COMP | 2020-05-13 | [16 empty] | 2019-04-06 | 2020-04-06 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163781704 | 27164.26 | 4472.5 |  |  |  | 88.7 |  | 88.7 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116968981 | POLE_BROK_REPL - 15400 OBYRNS FERRY RD 3 | 35188302 |  |  | STS-POLE_BROK_REPL - 15400 OBYRNS FERRY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9022 | -120.5437 |  | TIER 2 | 93 | 16378-1704, PEORIA | W29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.9 | 24.9 |  |  | 0 | 24.9 | 24.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040673 | RELW OH PRI REMT NOAC ESTR GO REAR USA WATR PROG FMOB TER2 PRTO FSRP | Pole | 2020-10-16 | 2020-10-19 | COMP | 2020-10-15 | [16 empty] | 2019-04-06 | 2020-04-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 14831.23 | 134.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116969035 | POLE_BROK_REPL - 15400 OBYRNS FERRY RD 3 | 35188312 |  |  | STS-POLE_BROK_REPL - 15400 OBYRNS FERRY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9022 | -120.5449 |  | TIER 2 | 93 | 16378-1704, PEORIA | W29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.3 | 18.3 |  |  | 0 | 18.3 | 18.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040683 | RELW OH PRI REMT NOAC ESTR GO USA FMOB TER2 PRTO FSRP | Pole | 2020-09-18 | 2020-09-24 | COMP | 2020-09-17 | [16 empty] | 2019-04-06 | 2020-04-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 13246.01 | 213.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116969130 | POLE_BROK_REPL - 15400 OBYRNS FERRY RD 3 | 35188317 |  |  | STS-POLE_BROK_REPL - 15400 OBYRNS FERRY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9022 | -120.5451 |  | TIER 2 | 93 | 16378-1704, PEORIA | W29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.3 | 18.3 |  |  | 0 | 18.3 | 18.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040685 | OH PRI REMT NOAC SPCR ESTR BTKA REAR USA WATR FMOB TER2 PRTO FSRP RELW | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-04-06 | 2020-04-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 13246.01 | 133 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116969161 | POLE_BROK_REPL - 15400 OBYRNS FERRY RD 3 | 35188322 |  |  | STS-POLE_BROK_REPL - 15400 OBYRNS FERRY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9018 | -120.5476 |  | TIER 2 | 93 | 16378-1704, PEORIA | W29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.3 | 28.3 |  |  | 0 | 28.3 | 28.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041504 | RELW OH PRI REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-04-06 | 2020-04-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 14360.8 | 134.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116969185 | POLE_BROK_REPL - 14560 TWIST RDJAMESTOWN | 35188326 |  |  | STS-POLE_BROK_REPL - 14560 TWIST RDJAMES | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8893 | -120.3762 |  | TIER 2 | 72 | 16335-1703, CURTIS | W33 | 1721 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 64.3 | 56.4 | 7.9 |  | 0 | 64.3 | 56.4 | 7.9 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029315 | RELW OH PRI CLR JPOL REMT ESTR USA FMOB TER2 PRTO | Pole | 2020-10-16 | 2020-11-24 | COMP | 2020-10-15 | [16 empty] | 2019-04-06 | 2020-04-06 |  | 2020-04-06 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 24540.02 | 62.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116969231 | POLE_BROK_REPL - 15400 OBYRNS FERRY RD 3 | 35188332 |  |  | STS-POLE_BROK_REPL - 15400 OBYRNS FERRY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9022 | -120.5481 |  | TIER 2 | 93 | 16378-1704, PEORIA | W29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.3 | 18.3 |  |  | 0 | 18.3 | 18.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041502 | RELW OH PRI REMT SPCR ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-10-05 | 2020-10-05 | COMP | 2020-10-05 | [16 empty] | 2019-04-06 | 2020-04-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 11234.79 | 134.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116969244 | POLE_BROK_REPL - 15400 OBYRNS FERRY RD 3 | 35188337 |  |  | STS-POLE_BROK_REPL - 15400 OBYRNS FERRY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9022 | -120.5489 |  | TIER 2 | 93 | 16378-1704, PEORIA | W29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.3 | 18.3 |  |  | 0 | 18.3 | 18.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041501 | RELW OH PRI REMT NOAC ESTR GO USA FMOB TER2 PRTO FSRP | Pole | 2020-10-05 | 2020-10-05 | COMP | 2020-10-05 | [16 empty] | 2019-04-06 | 2020-04-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 11746.01 | 134.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116969284 | POLE_BROK_REPL - 15400 OBYRNS FERRY RD 3 | 35188342 |  |  | STS-POLE_BROK_REPL - 15400 OBYRNS FERRY | UNSC | UNSC srdy | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9023 | -120.5493 |  | TIER 2 | 93 | 16378-1704, PEORIA | W29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.2 | 18.2 |  |  | 0 | 18.2 | 18.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041499 | RELW OH PRI REMT SPCR ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-10-14 | 2020-10-14 | COMP | 2020-10-14 | [16 empty] | 2019-04-06 | 2020-04-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 6211.34 | 134.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116969308 | POLE_BROK_REPL - 15400 OBYRNS FERRY RD 3 | 35188347 |  |  | STS-POLE_BROK_REPL - 15400 OBYRNS FERRY | UNSC | UNSC srdy | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9021 | -120.5503 |  | TIER 2 | 93 | 16378-1704, PEORIA | W29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.6 | 14.6 |  |  | 0 | 14.6 | 14.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041498 | RELW PRI OH REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-10-14 | 2020-10-14 | COMP | 2020-10-14 | [16 empty] | 2019-04-06 | 2020-04-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 5302.39 | 134.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116969935 | POLE_BROK_REPL - 15400 OBYRNS FERRY RD 3 | 35188367 |  |  | STS-POLE_BROK_REPL - 15400 OBYRNS FERRY | UNSC | UNSC srdy | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9023 | -120.5533 |  | TIER 2 | 93 | 16378-1704, PEORIA | W29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.6 | 14.6 |  |  | 0 | 14.6 | 14.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041494 | RELW OH PRI REMT NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-10-14 | 2020-10-14 | COMP | 2020-10-14 | [16 empty] | 2019-04-06 | 2020-04-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 6398.15 | 51.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116973587 | POLE_BROK_REPL - 14670 HWY108 3PS/OJAMES | 35154180 |  |  | STS-POLE_BROK_REPL - 14670 HWY108 3PS/OJ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.892 | -120.4957 |  | TIER 2 | 93 | 16378-1704, PEORIA | W30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.6 | 17.6 |  |  | 0 | 17.6 | 17.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040411 | RELW OH PRI JPOL REMT ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-04-20 | 2020-06-08 | COMP | 2020-04-20 | [16 empty] | 2019-04-07 | 2020-04-07 | 2024-04-05 | 2024-04-05 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163781704 | 6127.99 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116973881 | POLE_BROK_REPL - 15400 OBYRNS FERRY RD 4 | 35086576 |  |  |  | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9374 | -120.5318 |  | TIER 2 | 93 | 16378-1704, PEORIA | V29 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101041083 | RELW OH PRI REMT ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-05-14 | 2020-06-22 | COMP | 2020-05-14 | [16 empty] | 2019-04-07 | 2019-10-07 | 2020-06-17 | 2020-06-17 | B-Tag Clean Up 6/8/2020 |  | Fresno |  | 163781704 | 6787.71 | 5015.8 | 819.5 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-06-08
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116974539 | POLE_BROK_REPL - 17984 HARVEY MINE RD 3P | 35154184 |  |  | STS-POLE_BROK_REPL - 17984 HARVEY MINE R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9483 | -120.4278 |  | TIER 2 | 434 | 16378-1705, PEORIA | V3203 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.1 | 27.1 |  |  | 0 | 27.1 | 27.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101034507 | RELW OH SEC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-04-29 | 2020-06-16 | COMP | 2020-04-28 | [16 empty] | 2019-04-07 | 2020-04-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 163781705 | 14042.25 | 495.1 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116974887 | POLE_BROK_REPL - 6060 OBYRNS FERRY RD 9P | 35188618 |  |  | STS-POLE_BROK_REPL - 6060 OBYRNS FERRY R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8795 | -120.5119 |  | TIER 2 | 93 | 16378-1704, PEORIA | W30 | 987307 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.8 | 37.8 |  |  | 0 | 37.8 | 37.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041640 | OH PRI REMT SPCR ESTR BTKA TER2 RELW REAR USA FMOB PRTO FSRP | Pole | 2020-09-30 | 2020-09-30 | COMP | 2020-09-30 | [16 empty] | 2019-04-07 | 2020-04-07 | 2024-04-05 | 2024-04-05 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 20494.07 | 133 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116976289 | POLE_BROK_REPL - 1445 HWY 108 #1 SWJAMES | 35188656 |  |  | STS-POLE_BROK_REPL - 1445 HWY 108 #1 SWJ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8822 | -120.505 |  | TIER 2 | 93 | 16378-1704, PEORIA | W30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.5 | 44.5 |  |  | 0 | 44.5 | 44.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101015488 | RELW OH PRI REMT ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-10-05 | 2020-10-05 | COMP | 2020-10-05 | [16 empty] | 2019-04-07 | 2020-04-07 | 2024-04-05 | 2024-04-05 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 18628 | 392.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116977387 | POLE_BROK_REPL - 1445 HWY 108 2PSW/O JAM | 35154200 |  |  | STS-POLE_BROK_REPL - 1445 HWY 108 2PSW/O | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8809 | -120.5075 |  | TIER 2 | 93 | 16378-1704, PEORIA | W30 |  | Y | 311 |  |  | 2021-02-13 07:00 | 2021-02-13 16:00 | Dispatched | CLICK | [6 empty] | 49.8 | 49.8 |  |  | 3.75 | 48.8 | 48.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101015487 | RELW OH PRI REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-04-22 | 2020-04-22 | COMP | 2020-04-22 | [16 empty] | 2019-04-08 | 2020-04-08 | 2024-04-06 | 2024-04-06 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163781704 | 34339.19 | 13665.6 | 412.2 |  |  | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117021440 | POLE_BROK_REPL - 5015 O'BYRNES FERRY RD | 35188344 |  |  | STS-POLE_BROK_REPL - 5015 O'BYRNES FERRY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8953 | -120.5428 |  | TIER 2 | 93 | 16378-1704, PEORIA | W29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.4 | 16.4 |  |  | 0 | 16.4 | 16.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040691 | RELW PRI OH REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-10-06 | 2020-10-06 | COMP | 2020-10-06 | [16 empty] | 2019-04-13 | 2020-04-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 5359.48 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117138603 | POLE_BROK_REPL - 18727 JAMESTOWN RDJAMES | 35154287 |  |  | STS-POLE_BROK_REPL - 18727 JAMESTOWN RDJ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9627 | -120.4173 |  | TIER 2 | 434 | 16378-1705, PEORIA | U3219 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 11.4 | 11.4 |  |  | 0 | 11.4 | 11.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101051805 | OH SERV ESTR BTKA USA FMOB TER2 PRTO FSRP RELW | Pole | 2020-04-03 | 2020-05-27 | COMP | 2020-04-03 | [16 empty] | 2019-05-01 | 2020-05-01 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 163781705 | 5753.79 | 344.8 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117160234 | POLE_BROK_REPL - 11718 CAMPBELLS FLATS R | 35187982 |  |  | STS-POLE_BROK_REPL - 11718 CAMPBELLS FLA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9494 | -120.3899 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3302 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.8 | 15.8 |  |  | 0 | 15.8 | 15.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030907 | RELW OH SEC INSP JPOL REMT FIRE ESTR REAR USA FMOB TER2 | Pole | 2020-09-21 | 2020-09-21 | COMP | 2020-09-21 | [16 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 8427.79 | 524.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117160316 | POLE_BROK_REPL - 3PS 15PE 3PN 11030 CAMP | 35187988 |  |  | STS-POLE_BROK_REPL - 3PS 15PE 3PN 11030 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9497 | -120.3902 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3302 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25 | 25 |  |  | 0 | 25 | 25 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030905 | RELW OH PRI INSP CLR ESTR FMOB TER2 | Pole | 2020-09-23 | 2020-09-23 | COMP | 2020-09-23 | [16 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 10681.31 | 335.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117166979 | POLE_BROK_REPL - 17991 AVENIDA BONITAJAM | 35188196 |  |  | STS-POLE_BROK_REPL - 17991 AVENIDA BONIT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9481 | -120.3873 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3303 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.1 | 18.1 |  |  | 0 | 18.1 | 18.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030932 | RELW OH PRI INSP JPOL REMT FIRE ESTR REAR USA PROG FMOB TER2 | Pole | 2020-09-18 | 2020-09-18 | COMP | 2020-09-18 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 7677.63 | 224.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117169789 | POLE_BROK_REPL - 1PN 2PE 12000 ALGERINE | 35188313 |  |  | STS-POLE_BROK_REPL - 1PN 2PE 12000 ALGER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9113 | -120.3819 |  | TIER 2 | 72 | 16335-1703, CURTIS | V33 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030866 | RELW OH PRI INSP RESD FIRE ESTR BTKA FMOB TER2 | Pole | 2020-08-24 | 2020-08-24 | COMP | 2020-08-24 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117170243 | POLE_BROK_REPL - 17895 VIAV SERENAJAMEST | 35188358 |  |  | STS-POLE_BROK_REPL - 17895 VIAV SERENAJA | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9475 | -120.3838 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3303 | 19687 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 63.2 | 63 | 0.2 |  | 0 | 63.2 | 63 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031001 | RELW OH PRI INSP PUBL FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-09-17 | 2021-02-03 | COMP | 2020-09-17 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 28516.2 | 164.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117175996 | POLE_DECA_REPL - 1PW 15270 TWIST RDJAMES | 35188479 |  |  | STS-POLE_DECA_REPL - 1PW 15270 TWIST RDJ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9019 | -120.3623 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 21.1 | 21.1 |  |  | 0 | 21.1 | 21.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101029407 | RELW OH PRI PGEA INSP CLR REMT NOAC ESTR USA FMOB TER2 | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 11929.21 | 353.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117180679 | POLE_DECA_REPL - 8PN 13100 HOG MOUTAIN R | 35188530 |  |  | STS-POLE_DECA_REPL - 8PN 13100 HOG MOUTA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8953 | -120.3586 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 21.7 | 21.7 |  |  | 0 | 21.7 | 21.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101029395 | RELW OH PRI PGEA INSP CLR REMT ESTR BTKA USA FMOB TER2 | Pole | 2020-09-17 | 2020-11-09 | COMP | 2020-09-17 | [16 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 11629.47 | 114.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117183675 | POLE_BROK_REPL - 73901 ALGERINE RD JAMES | 35188581 |  |  | STS-POLE_BROK_REPL - 73901 ALGERINE RD J | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9027 | -120.3392 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 | 1715 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 54.8 | 54.1 | 0.7 |  | 0 | 54.8 | 54.1 | 0.7 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029451 | RELW OH PRI INSP CLR JPOL RESD REMT ESTR BTKA REAR USA FMOB TER2 | Pole | 2020-09-15 | 2020-09-15 | COMP | 2020-09-15 | [16 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117183860 | POLE_BROK_REPL - 1PW 73901 ALGERINE RD J | 35188586 |  |  | STS-POLE_BROK_REPL - 1PW 73901 ALGERINE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9033 | -120.3396 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.5 | 16.5 |  |  | 0 | 16.5 | 16.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029450 | RELW PRI OH INSP JPOL RESD REMT FIRE ESTR GO BTKA REAR USA FMOB TER2 | Pole | 2020-10-07 | 2020-10-07 | COMP | 2020-10-07 | [16 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117186802 | POLE_DECA_REPL - 15995 WARDS FERRY RDJAM | 35188651 |  |  | STS-POLE_DECA_REPL - 15995 WARDS FERRY R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8942 | -120.3548 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 | 22203 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.1 | 36.1 |  |  | 0 | 36.1 | 36.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101029384 | RELW OH PRI INSP CLR JPOL RESD REMT FIRE ESTR BTKA REAR USA FMOB TER2 | Pole | 2020-10-01 | 2020-11-24 | COMP | 2020-09-30 | [16 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117187723 | POLE_DECA_REPL - 1PS 2PW 14775 TWIST RDJ | 35188663 |  |  | STS-POLE_DECA_REPL - 1PS 2PW 14775 TWIST | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8829 | -120.3613 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.8 | 19.8 |  |  | 0 | 19.8 | 19.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101029371 | RELW OH PRI PGEA INSP CLR REMT ESTR FMOB TER2 | Pole | 2020-09-23 | 2020-11-23 | COMP | 2020-09-23 | [16 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 6334.83 | 443.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117188166 | POLE_DECA_REPL - 1S 3PW 1PS 14775 TWIST | 35188670 |  |  | STS-POLE_DECA_REPL - 1S 3PW 1PS 14775 TW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8818 | -120.3628 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 | 557573 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 35.1 | 35.1 |  |  | 0 | 35.1 | 35.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101029370 | CLR OH PRI INSP RELW ESTR FMOB TER2 | Pole | 2020-09-23 | 2020-11-19 | COMP | 2020-09-23 | [16 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 16613.59 | 309.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117188997 | POLE_DECA_REPL - 1PS 4PW 1PS 14775 TWIST | 35188672 |  |  | STS-POLE_DECA_REPL - 1PS 4PW 1PS 14775 T | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8822 | -120.3639 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21 | 21 |  |  | 0 | 21 | 21 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101029366 | RELW OH PRI PGEA INSP CLR REMT ESTR BTKA USA FMOB TER2 | Pole | 2020-09-23 | 2020-11-23 | COMP | 2020-09-23 | [16 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 7868.49 | 81.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117189075 | POLE_DECA_REPL - 1S 14555 TWIST RDJAMEST | 35188674 |  |  | STS-POLE_DECA_REPL - 1S 14555 TWIST RDJA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8809 | -120.3655 |  | TIER 2 | 72 | 16335-1703, CURTIS | W33 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.8 | 21.8 |  |  | 0 | 21.8 | 21.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101029325 | RELW OH PRI PGEA INSP RESD ESTR BTKA USA FMOB TER2 | Pole | 2020-09-23 | 2020-11-17 | COMP | 2020-09-23 | [16 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 7639.47 | 443.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117189406 | POLE_DECA_REPL - 8PW 73901 WARDS FERRY R | 35188676 |  |  | STS-POLE_DECA_REPL - 8PW 73901 WARDS FER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9062 | -120.3481 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.2 | 20.2 |  |  | 0 | 20.2 | 20.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101029432 | RELW OH ESTR PRI INSP REMT BTKA USA FMOB TER2 | Pole | 2020-09-16 | 2021-02-03 | COMP | 2020-09-16 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 10349.74 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117191550 | POLE_OVRL_TEST - 1PS 4PE 13030 ALGERINE | 35188689 |  |  | STS-POLE_OVRL_TEST - 1PS 4PE 13030 ALGER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9027 | -120.3573 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.5 | 13.5 |  |  | 0 | 13.5 | 13.5 |  |  | EC | E | Pole | Overloaded | Test |  | 101029417 | RELW OH PRI INSP JPOL RESD FIRE TRAF FLAG ESTR GO BTKA USA FMOB TER2 | Pole | 2020-09-24 | 2021-02-03 | COMP | 2020-09-24 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 10004.46 | 90.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117240327 | POLE_DECA_REPL - 14775 TWIST RDJAMESTOWN | 35189248 |  |  | STS-POLE_DECA_REPL - 14775 TWIST RDJAMES | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8844 | -120.3588 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 | 557573 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.4 | 44.4 |  |  | 0 | 44.4 | 44.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101029376 | RELW OH PRI PGEA INSP CLR JPOL RESD ESTR BTKA FMOB TER2 | Pole | 2020-09-14 | 2020-11-10 | COMP | 2020-09-14 | [16 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 19418.52 | 443.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117240563 | POLE_DECA_REPL - 14771 TWIST RDJAMESTOWN | 35189273 |  |  | STS-POLE_DECA_REPL - 14771 TWIST RDJAMES | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8844 | -120.3599 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 | 557573 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.5 | 33.5 |  |  | 0 | 33.5 | 33.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101029377 | RELW OH PRI PGEA INSP CLR JPOL RESD ESTR BTKA USA FMOB TER2 | Pole | 2020-10-05 | 2020-11-22 | COMP | 2020-10-05 | [16 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 15008 | 162.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117326885 | POLE_DECA_REPL - 1PS 13030 ALGERINE RDJA | 35189433 |  |  | STS-POLE_DECA_REPL - 1PS 13030 ALGERINE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9015 | -120.3611 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 22.5 | 22.5 |  |  | 0 | 22.5 | 22.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101029411 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-10-05 | 2020-10-07 | COMP | 2020-10-05 |  |  | 2020-09-29 | 2020-09-29 | [12 empty] | 2019-05-28 | 2020-05-28 |  | 2020-05-28 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 9352.78 | 51.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 118008995 | POLE_DECA_REPL - 17447 CAMBELLS FLAT RD | 35189002 |  |  | STS-POLE_DECA_REPL - 17447 CAMBELLS FLAT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9395 | -120.386 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3308 | 4909 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 27 | 27 |  |  | 0 | 27 | 27 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101033286 | RELW OH ESTR GO TER2 | Pole | 2020-09-08 | 2020-10-27 | COMP | 2020-09-08 | [16 empty] | 2019-08-16 | 2019-12-16 |  | 2019-12-16 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 10654.05 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116968652 | POLE_DECA_REPL - 5E 14570 TWIST RD JAMES | 35188285 |  |  | STS-POLE_DECA_REPL - 5E 14570 TWIST RD J | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8869 | -120.3686 |  | TIER 2 | 72 | 16335-1703, CURTIS | W33 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40 | 40 |  |  | 0 | 40 | 40 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101029319 | OH PRI JPOL RESD FLAG ESTR GO BTKA FMOB TER2 PRTO RELW | Pole | 2021-01-15 | 2021-01-15 | COMP | 2020-08-31 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-04-06 | 2020-04-06 |  | 2020-04-06 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 16537.62 | 283 | 74.8 | 74.8 | 74.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 116970471 | POLE_BROK_REPL - OBYRNS FERRY RD/HWY108 | 35188387 |  |  | STS-POLE_BROK_REPL - OBYRNS FERRY RD/HWY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8866 | -120.4998 |  | TIER 2 | 93 | 16378-1704, PEORIA | W30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.2 | 18.2 |  |  | 0 | 18.2 | 18.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101040441 | RELW OH PRI SPCR USA FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-08-24 | 2021-01-19 | COMP | 2020-08-24 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-04-06 | 2020-04-06 | 2024-04-04 | 2024-04-04 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163781704 | 12172.74 | 351 | 299.1 | 299.1 | 299.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117132259 | POLE_DECA_REPL - 1PS MB10135 PEPPERMINT | 35154250 |  |  | STS-POLE_DECA_REPL - 1PS MB10135 PEPPERM | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9686 | -120.4271 |  | TIER 2 | 434 | 16378-1705, PEORIA | U3213 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.8 | 18.8 |  |  | 0 | 18.8 | 18.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101050563 | RELW RESD OH PRI JPOL ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-04-22 | 2021-01-19 | COMP | 2020-04-22 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-05-01 | 2020-05-01 | 2024-04-29 | 2024-04-29 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 163781705 | 14294.69 | 314 |  |  |  | 88.7 |  | 88.7 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117191413 | POLE_DECA_REPL - ALGERINE RDJAMESTOWN953 | 35188684 |  |  | STS-POLE_DECA_REPL - ALGERINE RDJAMESTOW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9035 | -120.3552 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.9 | 19.9 |  |  | 0 | 19.9 | 19.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101029418 | RELW OH PRI PGEA INSP RESD FLAG ESTR BTKA USA TER2 FMOB | Pole | 2020-09-17 | 2021-01-15 | COMP | 2020-09-17 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 11638.47 | 709.1 | 213.5 | 213.5 | 213.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | JAMESTOWN | Sonora |  |  | OPEN | 117239973 | POLE_BROK_REPL - 1PS 1PW 14775 TWIST RDJ | 35189228 |  |  | STS-POLE_BROK_REPL - 1PS 1PW 14775 TWIST | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8829 | -120.3601 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 | 557573 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43.9 | 43.9 |  |  | 0 | 43.9 | 43.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029372 | PRI RELW OH INSP CLR JPOL RESD ESTR USA FMOB TER2 | Pole | 2020-09-23 | 2021-01-17 | COMP | 2020-09-22 |  |  | 2021-01-17 | 2021-01-17 | [12 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 20575.15 | 496.4 | 53.4 | 53.4 | 53.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | LA GRANDE | Mariposa |  |  | COMP | 117015825 | POLE_DECA_REPL - 13747 CADENA WY #1 ELA | 35154427 |  |  | STS-POLE_DECA_REPL - 13747 CADENA WY #1 | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2021-01-09 | No Action | 37.7273 | -120.3433 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 02156B |  | Y | 311 |  |  | 2021-02-16 07:00 | 2021-02-16 16:00 | Completed | CLICK | [6 empty] | 17.7 | 17.7 |  |  | 0 | 17.7 | 17.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101191925 | PRI RELW OH COMP CLR JPOL RESD REMT FIRE TRAF FLAG ESTR GO BTKA USA CCNT FMOB TER2 PRTO | Pole | 2020-04-30 | 2020-06-19 | COMP | 2020-04-29 | COMP | 2021-02-13 | 2020-02-25 | 2020-02-25 | [11 empty] | 2021-02-22 | 2021-02-13 | 2020-04-12 |  | 2020-04-12 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252811102 | 9010.07 | 4016 | 3601.1 | 869.6 | 869.6 | 414.9 |  | 414.9 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | LA GRANGE | Mariposa |  |  | OPEN | 117027996 | POLE_DECA_REPL - 2663 ALAMEDA DRLA GRANG | 35154594 |  |  | STS-POLE_DECA_REPL - 2663 ALAMEDA DRLA G | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole | 2021-01-09 | Renew Permit | 37.6732 | -120.3241 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03153A | 25113 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.3 | 34.3 |  |  | 0 | 34.3 | 34.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101189949 | RELW PRI OH JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-05-18 | 2020-05-14 | COMP | 2020-05-14 |  |  | 2020-03-10 | 2020-03-10 | [12 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-05-01 | TRC |  | 252811102 | 18120.27 | 1535.8 | 1392 | 1392 | 1392 | 143.8 |  | 143.8 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | LA GRANGE | Mariposa |  |  | COMP | 117027608 | POLE_BROK_REPL - RANCHITO/PICADERO WAY 3 | 35154586 |  |  | STS-POLE_BROK_REPL - RANCHITO/PICADERO W | FICL | FICL ERDY SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2020-10-12 | No Action | 37.6422 | -120.3314 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03156A |  | Y | 311 |  |  | 2021-01-05 | 2021-01-05 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 16.8 | 16.8 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101188671 | PRI OH RELW COMP REMT FIRE CCNT TER2 ESTR BTKA FMOB PRTO | Pole | 2020-07-29 | 2020-08-03 | COMP | 2020-05-11 | COMP | 2021-01-05 | 2020-03-13 | 2020-03-13 | [11 empty] | 2021-01-15 | 2021-01-05 | 2020-04-14 |  | 2020-04-14 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252811102 | 10897.32 | 14770.8 | 13375.5 | 9974.5 | 9974.5 | 531.2 |  | 531.2 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | LA GRANGE | Mariposa |  |  | OPEN | 117034183 | POLE_DECA_REPL - ZELMA/BANDERILLA 3PN/1P | 35154646 |  |  | STS-POLE_DECA_REPL - ZELMA/BANDERILLA 3P | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-12 | Renew Permit | 37.6406 | -120.324 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03156A | 11934 | Y | 311 |  |  | 2021-02-18 07:00 | 2021-02-18 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 31.7 | 31.7 |  |  | 0 | 31.7 | 31.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101188577 | PRI OH RELW JPOL REMT FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-04-24 | 2020-07-20 | COMP | 2020-04-24 |  |  | 2020-04-06 | 2020-07-20 | [12 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252811102 | 16410.45 | 2969.3 | 2689.3 | 2637.9 | 2637.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | LA GRANGE | Mariposa |  |  | OPEN | 117039040 | POLE_DECA_REPL - MERCED FALLS/MERCADO 1P | 35154654 |  |  | STS-POLE_DECA_REPL - MERCED FALLS/MERCAD | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-12 | Renew Permit | 37.6358 | -120.3065 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03155C | 25554 | Y | 311 |  |  | 2021-03-09 07:00 | 2021-03-09 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 56.2 | 41.8 | 14.4 |  | 0 | 56.2 | 41.8 | 14.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101189226 | RELW OH PRI JPOL REMT TRAF FLAG TER2 ESTR BTKA FMOB PRTO | Pole | 2020-04-24 | 2020-06-19 | COMP | 2020-04-24 |  |  | 2020-03-02 | 2020-03-06 | [12 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252811102 | 24705.14 | 427.7 |  |  |  | 287.7 |  | 287.7 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | LA GRANGE | Mariposa |  |  | OPEN | 117048885 | POLE_DECA_REPL - MERCED FALLS/CORONADO 1 | 35154675 |  |  | STS-POLE_DECA_REPL - MERCED FALLS/CORONA | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-12 | Renew Permit | 37.628 | -120.308 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03155C |  | Y | 311 |  |  | 2021-02-16 07:00 | 2021-02-16 16:00 | Completed | CLICK | [6 empty] | 18.7 | 18.7 |  |  | 0 | 18.7 | 18.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101189165 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-05-11 | 2020-07-20 | COMP | 2020-05-11 |  |  | 2020-03-13 | 2020-03-13 | [12 empty] | 2019-04-17 | 2020-04-17 |  | 2020-04-17 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252811102 | 15395.12 | 2374.4 | 1350.7 | 1299.3 | 1299.3 | 398.4 |  | 398.4 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | LA GRANGE | Mariposa |  |  | OPEN | 117064495 | POLE_DECA_REPL - 9744 LAREDO DR.LA GRANG | 35154725 |  |  | STS-POLE_DECA_REPL - 9744 LAREDO DR.LA G | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-12 | Renew Permit | 37.6541 | -120.334 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03153D | 22767 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 35.8 | 35.8 |  |  | 0 | 35.8 | 35.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101189705 | RELW OH PRI JPOL RESD FIRE TRAF FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-05-29 | 2020-07-28 | COMP | 2020-05-29 |  |  | 2020-03-16 | 2020-03-16 | [12 empty] | 2019-04-19 | 2020-04-19 |  | 2020-04-19 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252811102 | 21346.19 | 1943.2 | 1492.9 | 1492.9 | 1492.9 | 310.3 |  | 310.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | LA GRANGE | Mariposa |  |  | OPEN | 117064506 | POLE_DECA_REPL - 1PS OF 9744 LAREDO DRLA | 35154730 |  |  | STS-POLE_DECA_REPL - 1PS OF 9744 LAREDO | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-12 | Renew Permit | 37.6531 | -120.3338 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03153D |  | Y | 311 |  |  | 2021-02-18 07:00 | 2021-02-18 16:00 | Completed | CLICK | [6 empty] | 17 | 17 |  |  | 11.25 | 16 | 16 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101189708 | RELW OH PRI JPOL RESD FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-05-07 | 2020-07-20 | COMP | 2020-05-07 |  |  | 2020-03-17 | 2020-03-17 | [12 empty] | 2019-04-19 | 2020-04-19 |  | 2020-04-19 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252811102 | 10424.41 | 3239.4 | 2995.9 | 2564.3 | 2564.3 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | LA GRANGE | Mariposa |  |  | OPEN | 117065164 | POLE_DECA_REPL - 9662 VILLARREALLA GRANG | 35154734 |  |  | STS-POLE_DECA_REPL - 9662 VILLARREALLA G | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-12 | Renew Permit | 37.6408 | -120.3473 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03156B |  | Y | 311 |  |  | 2021-02-16 07:00 | 2021-02-16 16:00 | Completed | CLICK | [6 empty] | 16.2 | 16.2 |  |  | 0 | 16.2 | 16.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101189039 | RELW OH FIRE PRI JPOL REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-05-07 | 2020-07-20 | COMP | 2020-05-07 |  |  | 2020-03-18 | 2020-03-18 | [12 empty] | 2019-04-19 | 2020-04-19 |  | 2020-04-19 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252811102 | 10061.43 | 1770.6 | 1387.1 | 1284.2 | 1284.2 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | LA GRANGE | Mariposa |  |  | OPEN | 117077301 | POLE_DECA_REPL - RANCHITO/GAZA 6PN/2PWLA | 35154813 |  |  | STS-POLE_DECA_REPL - RANCHITO/GAZA 6PN/2 | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.6336 | -120.358 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03156C |  | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | [6 empty] | 17.9 | 17.9 |  |  | 0 | 17.9 | 17.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101188863 | OH PRI CLR FMOB RELW REMT ESTR BTKA TER2 PRTO | Pole | 2020-05-08 | 2020-07-17 | COMP | 2020-05-07 | [16 empty] | 2019-04-22 | 2020-04-22 |  | 2020-04-22 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252811102 | 6151.94 | 1101.6 | 1101.6 | 1101.6 | 1101.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | LA GRANGE | Mariposa |  |  | OPEN | 117027435 | POLE_DECA_REPL - PEPITO CT./PEPITO DR.LA | 35154581 |  |  | STS-POLE_DECA_REPL - PEPITO CT./PEPITO D | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.6755 | -120.326 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03153A |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101190031 | RELW OH PRI JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-05-12 | 2020-10-16 | COMP | 2020-05-12 |  |  | 2020-10-16 | 2020-10-16 | [12 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-05-01 | TRC |  | 252811102 | 15453.14 | 1392 | 1392 | 1392 | 1392 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | LA GRANGE | Mariposa |  |  | OPEN | 117027610 | POLE_BROK_REPL - RANCHITO/ZELMA LA GRANG | 35154590 |  |  | STS-POLE_BROK_REPL - RANCHITO/ZELMA LA G | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-12 | Renew Permit | 37.6404 | -120.3332 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03156A |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | F | Pole | Broken/Damaged | Replace |  | 101188625 | RELW OH PRI REMT FIRE FLAG ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-05-19 | 2020-10-17 | COMP | 2020-05-19 |  |  | 2020-03-13 | 2020-03-13 | [12 empty] | 2019-04-14 | 2020-04-14 | 2021-12-31 | 2021-12-31 | 2021 CBP Plan | 2020-05-31 | TRC |  | 252811102 | 8519.47 | 1537.7 |  |  |  | 298.8 |  | 298.8 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | LA GRANGE | Mariposa |  |  | OPEN | 117030464 | POLE_DECA_REPL - RANCHITO/PICADERO WAY 1 | 35154606 |  |  | STS-POLE_DECA_REPL - RANCHITO/PICADERO W | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-12 | Renew Permit | 37.6431 | -120.3327 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03156A |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101188683 | RELW OH PRI JPOL REMT FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-06-02 | 2020-08-13 | COMP | 2020-06-02 |  |  | 2020-03-17 | 2020-03-17 | [12 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2020-05-01 | TRC |  | 252811102 | 10384.17 | 1655.6 | 1299.8 | 1299.8 | 1299.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | LA GRANGE | Mariposa |  |  | OPEN | 117048251 | POLE_DECA_REPL - MERCED FALLS/CORONADO 4 | 35093537 |  |  |  | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.6315 | -120.3092 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03155C | 22772 | Y | 311 |  |  | 2021-10-29 07:00 | 2021-10-29 16:00 | Dispatched | CLICK | [6 empty] | 100 | 100 |  |  | 42 | 58 | 58 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101189171 | RELW OH PRI JPOL RESD REMT TRAF FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-28 | 2020-11-16 | COMP | 2020-10-28 |  |  | 2020-11-02 | 2020-11-16 | [12 empty] | 2019-04-17 | 2019-10-17 | 2020-11-03 | 2020-11-03 | B tag clean up 9/5/2020 |  | Fresno |  | 252811102 | 16136.93 | 15810.8 | 59.4 | -28.1 | -28.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-09-05
Bay/Central | YO | LA GRANGE | Mariposa |  |  | OPEN | 117048888 | POLE_BROK_REPL - MERCED FALLS/CORONADO 7 | 35154679 |  |  | STS-POLE_BROK_REPL - MERCED FALLS/CORONA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-12 | Renew Permit | 37.6231 | -120.3085 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03155C | 25554 | Y | 311 |  |  | 2021-06-29 07:00 | 2021-06-29 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101189156 | RELW OH PRI REMT TRAF FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-05-11 | 2020-09-01 | COMP | 2020-05-11 |  |  | 2020-08-27 | 2020-09-01 | [12 empty] | 2019-04-17 | 2020-04-17 |  | 2020-04-17 | 2021 CBP Plan | 2020-05-01 | TRC |  | 252811102 | 21977.04 | 276 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | LA GRANGE | Mariposa |  |  | OPEN | 117072373 | POLE_DECA_REPL - 1PS OF BANDERILLA DR/HI | 35191756 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.6714 | -120.3573 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03153B |  | Y | 311 |  |  | 2021-10-29 07:00 | 2021-10-29 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.9 | 50.9 |  |  | 40 | 50.8 | 50.8 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101189658 | RELW OH PRI JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-11-16 | 2020-12-02 | COMP | 2020-11-16 |  |  | 2020-11-18 | 2020-11-20 | [12 empty] | 2019-04-21 | 2019-10-08 | 2020-09-11 | 2020-09-11 | B-tag addition 8/12/2020 |  | Santa Rosa |  | 252811102 | 13832.08 | 4113.3 | 3765.6 | 1011 | 1011 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-08-18
Bay/Central | YO | LA GRANGE | Merced |  |  | OPEN | 117055715 | POLE_DECA_REPL - 8422 MERCED FALLS RD 1P | 35215273 |  |  | STS-POLE_DECA_REPL - 8422 MERCED FALLS R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.6125 | -120.3082 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 0000004151 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103226202 | RELW TRAF OH PRI REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-18 | 2020-04-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252811102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | LA GRANGE | Merced |  |  | OPEN | 120177592 | POLE_BROK_REPL - 14635 AVENIDA CENTRAL L | 35220829 |  |  | STS-POLE_BROK_REPL - 14635 AVENIDA CENTR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-14 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.6512 | -120.324 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 03156A | 22768 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17 | 17 |  |  | 0 | 17 | 17 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101188764 | RELW OH PRI CUST REMT FIRE BTKA RTRN USA TER2 PROG ESTR GO | Pole | 2020-12-30 | 2021-01-12 | COMP | 2020-12-30 |  |  | 2021-01-12 | 2021-01-12 | [12 empty] | 2020-12-11 | 2021-02-11 | 2021-02-11 | 2021-02-11 | B tag clean up 12/21/2020 |  | UNASSIGNED |  | 252811102 | 10675.63 | 149.5 | 149.5 | 149.5 | 149.5 |  |  |  | Electric Distribution | N | Pulled from MPP Import File | N |  | Y | 2020-12-21
Bay/Central | YO | LA GRANGE | Oakhurst |  |  | OPEN | 117072625 | POLE_DECA_REPL - #22 S/O 9558 MCCLURE PT | 35209635 |  |  | STS-POLE_DECA_REPL - #22 S/O 9558 MCCLUR | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5806 | -120.3028 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 0000004154 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101195810 | RELW OH PRI CLR REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-21 | 2020-04-21 | 2020-10-07 | 2020-10-07 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252811102 | 1 | 13.5 | 0 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | LA GRANGE | Oakhurst |  |  | OPEN | 117072595 | POLE_DECA_REPL - #22 S/O 9558 MCCLURE PT | 35209629 |  |  | STS-POLE_DECA_REPL - #22 S/O 9558 MCCLUR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5809 | -120.3036 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 0000004154 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.7 | 17.7 |  |  | 0 | 17.7 | 17.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101195824 | RELW OH PRI CLR REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-05 | 2021-01-05 | COMP | 2021-01-05 | [16 empty] | 2019-04-21 | 2019-10-08 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252811102 | 6256.2 | 13.5 | 0 | 489 | 489 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | LAKE MCCLURE | Mariposa |  |  | OPEN | 117072763 | POLE_DECA_REPL - #22 S/O 9558 MCCLURE PT | 35154793 |  |  | STS-POLE_DECA_REPL - #22 S/O 9558 MCCLUR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5734 | -120.2873 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 0000004154 |  | Y | 311 |  |  | 2021-06-29 07:00 | 2021-06-29 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101196317 | RELW OH PRI CLR REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-09-03 | 2020-09-22 | COMP | 2020-09-02 | [16 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 252811102 | 25819.28 | 569.3 | -2526.3 | -1141.3 | -1141.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MADERA | Madera |  |  | OPEN | 117687801 | POLE _BROK _REPL_SW5008-RD211 14PE/6PNE/ | 35178326 |  |  | STS-POLE _BROK _REPL_SW5008-RD211 14PE/6 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0279 | -119.6941 |  | TIER 2 |  |  | 0000010216 |  | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Dispatched | CLICK | [6 empty] | 34.9 | 34.9 |  |  | 0 | 34.9 | 34.9 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101064362 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2020-06-30 | 2020-08-03 | COMP | 2020-06-30 |  |  | 2020-08-03 | 2020-08-03 | [12 empty] | 2019-07-31 | 2020-07-31 | 2020-10-12 | 2020-10-12 | B-Tag Addition 06.24.20 |  | Fresno |  |  | 17210.49 | 1334.4 | 1334.5 | 1340.8 | 1340.8 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-06-29
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116754451 | POLE_DECA_REPL - 4954 FALCON 1PSEMARIPOS | 35208776 |  |  | STS-POLE_DECA_REPL - 4954 FALCON 1PSEMAR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4717 | -119.8881 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101088272 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 |  | 2020-03-18 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116763764 | POLE_DECA_REPL - 4960 PEGLEG RDMARIPOSA9 | 35215071 |  |  | STS-POLE_DECA_REPL - 4960 PEGLEG RDMARIP | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4613 | -119.8905 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05196A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103218436 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116767077 | POLE_DECA_REPL - CYA RD/MT BULLION RDG 1 | 35083004 |  |  | STS-POLE_DECA_REPL - CYA RD/MT BULLION R | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5365 | -120.0473 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004175 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101080021 | RELW OH SERV COMM REMT ESTR BTKA RTRN FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2020-09-26 | 2020-09-26 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116789124 | CRSS_DECA_REPL - CYA RD/MT BULLION RDG 1 | 35208858 |  |  | STS-CRSS_DECA_REPL - CYA RD/MT BULLION R | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5438 | -120.0504 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004175 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Crossarm | Decayed/Rotten | Replace |  | 101080049 | RELW OH PRI REMT TER2 ESTR BTKA FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2020-08-26 | 2020-08-26 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116796766 | POLE_DECA_REPL - 3756 MC NALLEY RDMARIPO | 35208892 |  |  | STS-POLE_DECA_REPL - 3756 MC NALLEY RDMA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4625 | -119.8696 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B | 4565 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084650 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116805310 | POLE_DECA_REPL - 4954 FALCON 2PSEMARIPOS | 35215320 |  |  | STS-POLE_DECA_REPL - 4954 FALCON 2PSEMAR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4715 | -119.8876 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101088271 | RELW OH PRI PGEA BTKA REMT FIRE ESTR OTHR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116821901 | POLE_DECA_REPL - 5101 BOYER RDMARIPOSA95 | 35214672 |  |  | STS-POLE_DECA_REPL - 5101 BOYER RDMARIPO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4616 | -119.8621 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195B | 4681 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084710 | RELW OH PRI USA REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116843194 | POLE_DECA_REPL - 1PN 5PW 4120 HWY140MARI | 35209172 |  |  | STS-POLE_DECA_REPL - 1PN 5PW 4120 HWY140 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4835 | -120.0214 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000005183 | 427365 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087538 | RELW OH PRI REMT PGEA CLR RESD FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2020-09-28 | 2020-09-28 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116847499 | POLE_DECA_REPL - 1/S OF 4417 YAQUI GULCH | 35214914 |  |  | STS-POLE_DECA_REPL - 1/S OF 4417 YAQUI G | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.4396 | -119.9974 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.5 | 23.5 |  |  | 0 | 23.5 | 23.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067643 | RELW PRI OH REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-11 |  | COMP | 2021-02-11 | [16 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 10714.17 | 13.5 | -945 | 147 | 147 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116849242 | POLE_DECA_REPL - MB 4489 LAKE VIEW 3/SMA | 35214933 |  |  | STS-POLE_DECA_REPL - MB 4489 LAKE VIEW 3 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4436 | -120.0034 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.2 | 20.2 |  |  | 0 | 20.2 | 20.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067665 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-17 | 2021-02-17 | COMP | 2021-02-16 | [16 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 7129.88 | 13.5 | -945 | 147 | 147 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116852149 | POLE_DECA_REPL - LAKEVIEW DRMARIPOSA9533 | 35214970 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4442 | -120.0087 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A | 11898 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 52.2 | 50.8 | 1.4 |  | 0 | 52.2 | 50.8 | 1.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103205124 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-16 | 2021-02-16 | COMP | 2021-02-16 | [16 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 19117.6 | 13.5 | -945 | 147 | 147 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116852412 | POLE_DECA_REPL - 1/E OF OLD HIGHWAY 140 | 35214975 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4204 | -120.0065 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.2 | 26.2 |  |  | 0 | 26.2 | 26.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067039 | RELW OH PRI REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-16 | 2021-02-16 | COMP | 2021-02-16 | [16 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 9206.59 | 13.5 | -945 | 147 | 147 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116852560 | POLE_DECA_REPL - #1 E/O 3455 MULLEN RDMA | 35214988 |  |  | STS-POLE_DECA_REPL - #1 E/O 3455 MULLEN | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4472 | -119.8519 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195D | 64813 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102322987 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116854138 | POLE_DECA_REPL - 3704 HWY 140 1SW 11SMAR | 35209271 |  |  | STS-POLE_DECA_REPL - 3704 HWY 140 1SW 11 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4665 | -120.0525 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000005175 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101019653 | RELW OH PRI PGEA CLR REMT FIRE CUSI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2020-08-31 | 2020-08-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 252192101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116854340 | POLE_DECA_REPL - AF 4108 LAKE VIEWMARIPO | 35215018 |  |  | STS-POLE_DECA_REPL - AF 4108 LAKE VIEWMA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4434 | -120.0095 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A | 11898 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067681 | RELW OH PRI REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116858080 | POLE_BROK_REPL - 4040 OLD HIGHWAY 140MAR | 35215038 |  |  | STS-POLE_BROK_REPL - 4040 OLD HIGHWAY 14 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4278 | -120.0008 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182D | 22467 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101067097 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116858197 | CONN_INCR_REPL - R/O 3341 WOODLAND DR MA | 35215043 |  |  | STS-CONN_INCR_REPL - R/O 3341 WOODLAND D | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.4485 | -119.8451 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05195D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.1 | 28.1 |  |  | 0 | 28.1 | 28.1 |  |  | EC | E | Connector | Incorrectly Installed | Replace |  | 101085104 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-22 | 2021-02-22 | COMP | 2021-02-22 | [16 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452101 | 10126.27 | 100.5 | -123 | 969 | 969 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116858202 | POLE_DECA_REPL - WOODLAND DR N/O ENTRANC | 35215053 |  |  | STS-POLE_DECA_REPL - WOODLAND DR N/O ENT | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 37.4473 | -119.8427 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05195D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16 | 16 |  |  | 0 | 16 | 16 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085123 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-22 |  | COMP | 2021-02-22 | [16 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452101 | 6158.81 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116858209 | POLE_DECA_REPL - WOODLAND DR E/O ENTRANC | 35209299 |  |  | STS-POLE_DECA_REPL - WOODLAND DR E/O ENT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.45 | -119.8463 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05195D | 4067 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084999 | RELW OH PRI PUBL ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2020-09-25 | 2020-09-25 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116858212 | POLE_DECA_REPL - R/O 3341 WOODLAND DR/1S | 35215058 |  |  | STS-POLE_DECA_REPL - R/O 3341 WOODLAND D | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4482 | -119.8456 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05195D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085105 | RELW OH PRI REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-04-14 | 2021-04-14 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452101 | 1 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116858214 | POLE_DECA_REPL - WOODLAND DR AT 3386AMAR | 35209303 |  |  | STS-POLE_DECA_REPL - WOODLAND DR AT 3386 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4502 | -119.8468 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05195D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085003 | RELW OH SEC REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116858220 | POLE_DECA_REPL - N/O WOODLAND DR AT 3386 | 35209308 |  |  | STS-POLE_DECA_REPL - N/O WOODLAND DR AT | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.4502 | -119.8464 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05195D | 4067 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085002 | RELW OH PRI RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452101 | 1 | 1056 | 1042.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116858222 | POLE_DECA_REPL - WOODLAND DR AT WOODLAND | 35215067 |  |  | STS-POLE_DECA_REPL - WOODLAND DR AT WOOD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.4499 | -119.8502 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05195D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.9 | 38.9 |  |  | 0 | 38.9 | 38.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103093847 | RELW OH PRI COMM FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-26 |  | COMP | 2021-01-26 | [16 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 18313.8 |  | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116858514 | POLE_BROK_REPL - RO 4036 OLD HIGHWAY 140 | 35215078 |  |  | STS-POLE_BROK_REPL - RO 4036 OLD HIGHWAY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.427 | -120.0034 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101067091 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116860777 | POLE_DECA_REPL - 4166 HERITAGE MARIPOSA | 35215133 |  |  | STS-POLE_DECA_REPL - 4166 HERITAGE MARIP | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4473 | -120.0051 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005186 | 11898 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084585 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116861020 | POLE_DECA_REPL - RO 4156 HERITAGEMARIPOS | 35215143 |  |  | STS-POLE_DECA_REPL - RO 4156 HERITAGEMAR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.4466 | -120.0051 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A | 11898 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 52.5 | 48.1 | 4.4 |  | 0 | 52.5 | 48.1 | 4.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067669 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-05 | 2021-02-04 | COMP | 2021-02-04 | [16 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 18290.99 | 13.5 | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116861559 | POLE_DECA_REPL - 4199 HERITAGE RD MARIPO | 35215169 |  |  | STS-POLE_DECA_REPL - 4199 HERITAGE RD MA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4495 | -120.0049 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005186 | 11898 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084582 | RELW OH PRI RESD REMT ESTR BTKA FSRP FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116861580 | POLE_BROK_REPL - ENT 4061 OLD HIGHWAY 14 | 35215174 |  |  | STS-POLE_BROK_REPL - ENT 4061 OLD HIGHWA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4299 | -120.0047 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182D | 22467 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101067110 | RELW OH PRI REMT ESTR BTKA FSRP PRTO FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 |  | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116862167 | POLE_DECA_REPL - 1PS 2PW 5086 MARTIN RDM | 35215195 |  |  | STS-POLE_DECA_REPL - 1PS 2PW 5086 MARTIN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4812 | -119.975 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000518236 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087717 | RELW OH PRI PGEA CLR RESD REMT FIRE NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-21 | 2021-05-21 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 30.9 | 17.4 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116862817 | POLE_BROK_REPL - 4097 OLD HIGHWAY 140MAR | 35215217 |  |  | STS-POLE_BROK_REPL - 4097 OLD HIGHWAY 14 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.432 | -120.0046 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A | 22467 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101067115 | RELW PRI OH RESD ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 |  | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116863490 | POLE_DECA_REPL - 2PS 4343 HWY140MARIPOSA | 35215237 |  |  | STS-POLE_DECA_REPL - 2PS 4343 HWY140MARI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4917 | -119.9993 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005183 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087642 | RELW OH PRI PGEA REMT FIRE SWRK ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 48.3 | -175.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116863702 | POLE_DECA_REPL - RO 3988 OLD HIGHWAY 140 | 35215246 |  |  | STS-POLE_DECA_REPL - RO 3988 OLD HIGHWAY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4241 | -120.0059 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067081 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116863942 | POLE_DECA_REPL - 3PN/W 4375 HWY140MARIPO | 35215268 |  |  | STS-POLE_DECA_REPL - 3PN/W 4375 HWY140MA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4896 | -119.9979 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005183 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087669 | RELW OH PRI PGEA REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116863953 | POLE_DECA_REPL - 4PN/W 4375 HWY140MARIPO | 35215272 |  |  | STS-POLE_DECA_REPL - 4PN/W 4375 HWY140MA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4894 | -119.9985 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005183 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087635 | RELW OH PRI PGEA REMT FIRE NOAC ESTR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116864032 | POLE_DECA_REPL - ENT 4475 KIMBERLYMARIPO | 35215277 |  |  | STS-POLE_DECA_REPL - ENT 4475 KIMBERLYMA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4413 | -120.0087 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A | 11898 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067701 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116864044 | POLE_DECA_REPL - ENT 4475 KIMBERLYMARIPO | 35215281 |  |  | STS-POLE_DECA_REPL - ENT 4475 KIMBERLYMA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4416 | -120.0071 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067702 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116864192 | POLE_DECA_REPL - ENT 4475 KIMBERLYMARIPO | 35215286 |  |  | STS-POLE_DECA_REPL - ENT 4475 KIMBERLYMA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4412 | -120.009 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A | 11898 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067700 | RELW PRI OH REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116864201 | POLE_DECA_REPL - 4036 OLD HIGHWAY 140 2/ | 35215291 |  |  | STS-POLE_DECA_REPL - 4036 OLD HIGHWAY 14 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4261 | -120.005 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182D | 22467 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067060 | RELW OH PRI REMT SWRK ESTR REAR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116864521 | POLE_DECA_REPL - RO 4156 HERITAGE 1/SMAR | 35215316 |  |  | STS-POLE_DECA_REPL - RO 4156 HERITAGE 1/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4453 | -120.0052 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A | 11898 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067668 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116864522 | POLE_DECA_REPL - ENT 4036 OLD HIGHWAY 14 | 35215321 |  |  | STS-POLE_DECA_REPL - ENT 4036 OLD HIGHWA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4276 | -120.005 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182D | 22467 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067057 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116864529 | POLE_BROK_REPL - MB 4041 OLD HIGHWAY 140 | 35215327 |  |  | STS-POLE_BROK_REPL - MB 4041 OLD HIGHWAY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4285 | -120.0048 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101067086 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116864533 | POLE_BROK_REPL - MB 4038 OLD HIGHWAY 140 | 35215332 |  |  | STS-POLE_BROK_REPL - MB 4038 OLD HIGHWAY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.4289 | -120.0047 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101067087 | RELW ESTR OH PRI REMT BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -945 | 147 | 147 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116864990 | POLE_BROK_REPL - 4040 OLD HIGHWAY 140 1/ | 35215358 |  |  | STS-POLE_BROK_REPL - 4040 OLD HIGHWAY 14 | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4278 | -120.0002 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101067101 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116865001 | POLE_DECA_REPL - 4027 WILBURS WAYMARIPOS | 35215383 |  |  | STS-POLE_DECA_REPL - 4027 WILBURS WAYMAR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 37.4415 | -120.012 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067515 | OH FMOB RELW PRI REMT ESTR BTKA TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116865045 | POLE_DECA_REPL - ENT 4587 JEANNIEMARIPOS | 35215387 |  |  | STS-POLE_DECA_REPL - ENT 4587 JEANNIEMAR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4493 | -120.0091 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005186 | 11898 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084603 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116865171 | POLE_BROK_REPL - MB 4529 BRIDGEPORT 1/EM | 35215398 |  |  | STS-POLE_BROK_REPL - MB 4529 BRIDGEPORT | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4276 | -119.998 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101067843 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116868581 | POLE_BROK_REPL - 4026 GUADALUPE CREEKMAR | 35209535 |  |  | STS-POLE_BROK_REPL - 4026 GUADALUPE CREE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.453 | -120.0182 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005186 | 11898 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101084436 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2019-09-29 | 2020-08-13 | 2020-08-13 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 1 | 484.1 | 470.6 | 438.2 | 438.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116872298 | POLE_DECA_REPL - 4640 BURNEY IN YARDMARI | 35215457 |  |  | STS-POLE_DECA_REPL - 4640 BURNEY IN YARD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4548 | -120.0015 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005186 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084242 | RELW OH SERV RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116872311 | POLE_DECA_REPL - ENT 4576 BURNEYMARIPOSA | 35209596 |  |  | STS-POLE_DECA_REPL - ENT 4576 BURNEYMARI | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4529 | -120.0022 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005186 | 11898 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084230 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2020-09-11 | 2020-09-11 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116872312 | POLE_DECA_REPL - 4576 BURNEYMARIPOSA9533 | 35215462 |  |  | STS-POLE_DECA_REPL - 4576 BURNEYMARIPOSA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4527 | -120.002 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005186 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084231 | RELW OH SERV RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116873085 | POLE_DECA_REPL - 4607 YAQUI GULCH RD MAR | 35215482 |  |  | STS-POLE_DECA_REPL - 4607 YAQUI GULCH RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4545 | -120.0029 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005186 | 11898 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084256 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116877180 | POLE_BROK_REPL - 3978 WILBURS WAY 1/N MA | 35215519 |  |  |  | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4405 | -120.0168 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A | 10388 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101067498 | OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116877628 | POLE_DECA_REPL - ENT 4117 WILBURS WAY MA | 35215553 |  |  | STS-POLE_DECA_REPL - ENT 4117 WILBURS WA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4373 | -120.0106 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A | 10388 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067476 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116877670 | POLE_DECA_REPL - 4117 WILBURS WAY IN VIN | 35215558 |  |  | STS-POLE_DECA_REPL - 4117 WILBURS WAY IN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4367 | -120.0098 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067473 | RELW PRI OH REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116879861 | POLE_BROK_REPL - RO 4455A SCUBBY OAK MAR | 35215840 |  |  | STS-POLE_BROK_REPL - RO 4455A SCUBBY OAK | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4363 | -120.0056 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A | 10388 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101067630 | OH PRI CLR MINR RESD REMT NOAC GO FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-04-01 | 2020-04-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116880658 | POLE_DECA_REPL - 4093A OLD HIGHWAY 140MA | 35215604 |  |  | STS-POLE_DECA_REPL - 4093A OLD HIGHWAY 1 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.4324 | -120.0049 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A | 10388 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.9 | 31.9 |  |  | 0 | 31.9 | 31.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067523 | RELW OH PRI REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-31 |  | COMP | 2020-12-31 | [16 empty] | 2019-04-01 | 2020-04-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 24169.09 | 13.5 | -210 | 1627.5 | 1627.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117010428 | POLE_DECA_REPL - BEAR VALLEY SUB STATION | 35086252 |  |  | STS-POLE_DECA_REPL - BEAR VALLEY SUB STA | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.6139 | -120.1318 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000004172 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101018843 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-11 | 2020-04-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117090862 | POLE_DECA_REPL - 7255 CA-49MARIPOSA95338 | 35214654 |  |  | STS-POLE_DECA_REPL - 7255 CA-49MARIPOSA9 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.565 | -120.1167 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004176 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103211110 | RELW OH SERV JPOL REMT FIRE ESTR BTKA FSRP FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117093471 | POLE_BROK_REPL - 6737 HWY 49 2PNMARIPOSA | 35209676 |  |  | STS-POLE_BROK_REPL - 6737 HWY 49 2PNMARI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5347 | -120.0903 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000005171 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101068505 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117093615 | POLE_DECA_REPL - 7291 HWY 49 1PSWMARIPOS | 35214670 |  |  | STS-POLE_DECA_REPL - 7291 HWY 49 1PSWMAR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 37.5672 | -120.1181 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000417216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101028430 | RELW OH SEC REMT TER2 ESTR BTKA FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 464.1 | 464.1 | 1178.2 | 1178.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117093652 | POLE_BROK_REPL - 6737 HWY 49 1PN 1PWMARI | 35214674 |  |  | STS-POLE_BROK_REPL - 6737 HWY 49 1PN 1PW | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5344 | -120.0913 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000005171 | 10019 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101068507 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117094061 | POLE_DECA_REPL - 7293 HWY 49MARIPOSA9533 | 35214679 |  |  | STS-POLE_DECA_REPL - 7293 HWY 49MARIPOSA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.5676 | -120.1188 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000417216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101028432 | OH SEC JPOL REMT ESTR FSRP PRTO RELW BTKA FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117095465 | POLE_DECA_REPL - 95338MARIPOSA95338 | 35209681 |  |  | STS-POLE_DECA_REPL - 95338MARIPOSA95338 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5357 | -120.105 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000005171 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103234604 | RELW OH PRI JPOL REMT FIRE NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2020-09-26 | 2020-09-26 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117096136 | POLE_DECA_REPL - 7333 HWY 49 1PNEMARIPOS | 35105514 |  |  | STS-POLE_DECA_REPL - 7333 HWY 49 1PNEMAR | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.5698 | -120.1197 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004173 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103090751 | RELW OH SEC RESD FIRE TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2019-10-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | Fresno |  | 252192101 | 1 | 527.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117096676 | POLE_DECA_REPL - SW C/O HWY 49/UTAH ST # | 35214698 |  |  | STS-POLE_DECA_REPL - SW C/O HWY 49/UTAH | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5681 | -120.1205 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000417216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101019304 | RELW OH SEC REMT ESTR BTKA FMOB FSRP TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117096988 | POLE_DECA_REPL - SW C/O HWY 49/UTAH ST # | 35214712 |  |  | STS-POLE_DECA_REPL - SW C/O HWY 49/UTAH | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 37.5683 | -120.1215 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000417216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101019328 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 34.8 | 34.8 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117098004 | POLE_DECA_REPL - 4919 BEAR VALLEY RD 1PS | 35214716 |  |  | STS-POLE_DECA_REPL - 4919 BEAR VALLEY RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.5679 | -120.1246 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004173 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101019045 | RELW OH SEC REMT FLAG ESTR BTKA FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117099054 | POLE_DECA_REPL - 4170 BEAR VALLEY RD 2PS | 35214737 |  |  | STS-POLE_DECA_REPL - 4170 BEAR VALLEY RD | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5542 | -120.1733 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004165 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103372816 | RELW OH PRI REMT FIRE NOAC CGI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117099060 | POLE_DECA_REPL - 4170 BEAR VALLEY RD, MA | 35214742 |  |  | STS-POLE_DECA_REPL - 4170 BEAR VALLEY RD | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5549 | -120.1731 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004165 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103928773 | RELW OH PRI PGEA CLR RESD REMT FIRE ESTR BTKA REAR PRTO USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117099156 | POLE_DECA_REPL - 4170 BEAR VALLEY RD 1PS | 35214746 |  |  | STS-POLE_DECA_REPL - 4170 BEAR VALLEY RD | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5556 | -120.1729 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004165 | 23028 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103372815 | RELW OH PRI REMT FIRE CGI ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117099270 | POLE_DECA_REPL - 4170 BEAR VALLEY RD 2PN | 35214748 |  |  | STS-POLE_DECA_REPL - 4170 BEAR VALLEY RD | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.556 | -120.1728 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004165 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101079707 | RELW JPOL OH PRI CLR RESD REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117099620 | POLE_DECA_REPL - 4977 MT.BULLION CUTOFF | 35214753 |  |  | STS-POLE_DECA_REPL - 4977 MT.BULLION CUT | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5054 | -120.0431 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000518182 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084001 | RELW OH SERV RESD REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117099845 | POLE_BURN_REPL - 4919 BEAR VALLEY RD 2PW | 35209723 |  |  | STS-POLE_BURN_REPL - 4919 BEAR VALLEY RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5673 | -120.1291 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004173 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 103838072 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2020-09-24 | 2020-09-24 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117099988 | POLE_DECA_REPL - 1PS/E 4975 MT.BULLION C | 35214762 |  |  | STS-POLE_DECA_REPL - 1PS/E 4975 MT.BULLI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5049 | -120.0428 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000518182 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084004 | RELW OH SERV RESD REMT ESTR BTKA FSRP PRTO FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117100674 | POLE_DECA_REPL - 7411 HWY 49MARIPOSA9533 | 35209733 |  |  | STS-POLE_DECA_REPL - 7411 HWY 49MARIPOSA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5725 | -120.1244 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004173 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101019062 | RELW OH PRI REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2020-09-25 | 2020-09-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117101328 | POLE_DECA_REPL - 4852 BEAR VALLEY RD 1PW | 35209737 |  |  | STS-POLE_DECA_REPL - 4852 BEAR VALLEY RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5662 | -120.133 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004173 | 24487 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101018967 | OH RELW PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2020-09-25 | 2020-09-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117103429 | POLE_DECA_REPL - 6894 HWY 49 3PSWMARIPOS | 35209742 |  |  | STS-POLE_DECA_REPL - 6894 HWY 49 3PSWMAR | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5431 | -120.0982 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004176 | 24032 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101018960 | RELW OH PRI CLR REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-26 | 2020-04-26 | 2020-09-25 | 2020-09-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117104782 | POLE_DECA_REPL - 4771 BEAR VALLEY RD @ H | 35209753 |  |  | STS-POLE_DECA_REPL - 4771 BEAR VALLEY RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5689 | -120.1371 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004173 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.6 | 18.6 |  |  | 0 | 18.6 | 18.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101018986 | RELW OH PRI REMT SWRK ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-01 | 2021-02-01 | COMP | 2021-02-01 | [16 empty] | 2019-04-26 | 2020-04-26 | 2020-09-25 | 2020-09-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117105159 | POLE_BROK_REPL - #2 W/O 4771 BEAR VALLEY | 35215872 |  |  | STS-POLE_BROK_REPL - #2 W/O 4771 BEAR VA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5692 | -120.1389 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004173 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102320177 | MINR OH PRI RELW REMT JAR NOAC FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-26 | 2020-04-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117105876 | POLE_DECA_REPL - 4771 BEAR VALLEY RD 4PW | 35209758 |  |  | STS-POLE_DECA_REPL - 4771 BEAR VALLEY RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.5694 | -120.1397 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004173 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.4 | 27.4 |  |  | 0 | 27.4 | 27.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101018987 | RELW OH PRI REMT NOAC ESTR GO FMOB TER2 PRTO FSRP | Pole | 2020-12-22 | 2020-12-18 | COMP | 2020-12-18 | [16 empty] | 2019-04-26 | 2020-04-26 | 2020-09-25 | 2020-09-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | 15584.04 | 13.5 | 0 | 452.5 | 452.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117106785 | POLE_DECA_REPL - 4608 BEAR VALLEY RD MAR | 35214834 |  |  | STS-POLE_DECA_REPL - 4608 BEAR VALLEY RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.5695 | -120.151 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004164 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103234154 | RELW OH PRI REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-26 | 2020-04-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117110005 | POLE_DECA_REPL - 2794[HSE]OAK GROVE RD/1 | 35209776 |  |  | STS-POLE_DECA_REPL - 2794[HSE]OAK GROVE | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.3492 | -119.8611 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000007191 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067941 | RELW OH PRI CLR REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-27 | 2020-04-27 | 2020-09-24 | 2020-09-24 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117111022 | POLE_DECA_REPL - 2794[HSE]OAK GROVE RD/1 | 35209781 |  |  | STS-POLE_DECA_REPL - 2794[HSE]OAK GROVE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.3399 | -119.863 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000007191 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067968 | RELW OH PRI CLR REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-27 | 2020-04-27 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117111023 | POLE_DECA_REPL - 2794[HSE]OAK GROVE RDMA | 35208769 |  |  | STS-POLE_DECA_REPL - 2794[HSE]OAK GROVE | UNSC | UNSC ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.3412 | -119.8614 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000007191 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 10.9 | 10.9 |  |  | 0 | 10.9 | 10.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067966 | RELW OH SERV REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-22 | 2021-02-22 | COMP | 2021-02-22 | [16 empty] | 2019-04-27 | 2020-04-27 | 2020-10-21 | 2020-10-21 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 3728.96 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117112041 | POLE_DECA_REPL - 3197[HSE]OAK GROVE RD2P | 35214865 |  |  | STS-POLE_DECA_REPL - 3197[HSE]OAK GROVE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.3552 | -119.8745 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000007191 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067915 | RELW OH PRI REMT FIRE NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-27 | 2020-04-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 | 13.5 | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117113962 | POLE_DECA_REPL - S/W C/O HWY 49 AND MOUN | 35214886 |  |  | STS-POLE_DECA_REPL - S/W C/O HWY 49 AND | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.5062 | -120.0417 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000518076 | 24003 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103844720 | RELW OH SEC PGEA RESD REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-28 | 2020-04-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 32.4 | 32.4 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117147742 | POLE_DECA_REPL - 4881 LEONARDMARIPOSA953 | 35208998 |  |  | STS-POLE_DECA_REPL - 4881 LEONARDMARIPOS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4511 | -119.8085 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05206C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101072949 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-02 | 2020-05-02 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117148258 | POLE_DECA_REPL - 4894 LEONARDMARIPOSA953 | 35209013 |  |  | STS-POLE_DECA_REPL - 4894 LEONARDMARIPOS | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4506 | -119.8052 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05206C | 4585 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101072917 | OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-05-02 | 2020-05-02 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452101 | 1 | 13.5 | -1230.8 | -687.8 | -687.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117155309 | POLE_DECA_REPL - 4946 LEONARDMARIPOSA953 | 35215170 |  |  | STS-POLE_DECA_REPL - 4946 LEONARDMARIPOS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4538 | -119.8064 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05206C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101072886 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452101 | 1 | 13.5 | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117166264 | POLE_DECA_REPL - 4960 USONA/3PEMARIPOSA9 | 35209285 |  |  | STS-POLE_DECA_REPL - 4960 USONA/3PEMARIP | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.4515 | -119.8227 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05206C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 13.4 | 13.4 |  |  | 0 | 13.4 | 13.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101073723 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-15 |  | COMP | 2020-12-15 | [16 empty] | 2019-05-05 | 2020-05-05 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452101 | 9311.23 | 240.3 | -1079.9 | -536.9 | -536.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117166272 | POLE_DECA_REPL - 4994 USONAMARIPOSA95338 | 35209290 |  |  | STS-POLE_DECA_REPL - 4994 USONAMARIPOSA9 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 37.4517 | -119.8218 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05206C | 4585 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 2 | 0 | 0 | 0 | 37.4 | 37.4 |  |  | 0 | 37.4 | 37.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101073715 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-27 |  | COMP | 2021-01-27 | [16 empty] | 2019-05-05 | 2020-05-05 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452101 | 16771.12 | 13.5 | 0 | 558.1 | 558.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117308496 | POLE_DECA_REPL - 5450 CLOUDS REST RDMARI | 35209639 |  |  | STS-POLE_DECA_REPL - 5450 CLOUDS REST RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4901 | -119.8297 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 0000520186 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103811384 | RELW OH SERV RESD ESTR BTKA USA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-23 | 2020-05-23 |  | 2020-05-23 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117316012 | POLE_DECA_REPL - N/AMARIPOSA95338 | 35209669 |  |  | STS-POLE_DECA_REPL - N/AMARIPOSA95338 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro |  |  | 37.4998 | -119.8494 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005194 | 22286 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103347808 | RELW OH PRI PGEA CLR RESD REMT FIRE TRAF FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-24 | 2020-05-24 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117330376 | POLE_DECA_REPL - DRIVEWAY 4091 OLD HIGHW | 35215767 |  |  | STS-POLE_DECA_REPL - DRIVEWAY 4091 OLD H | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4327 | -120.0054 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A | 10388 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067524 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-28 | 2020-05-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 1 |  | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117337322 | POLE_BROK_REPL - 8107 CEDAR LN 12PWMARIP | 35215782 |  |  | STS-POLE_BROK_REPL - 8107 CEDAR LN 12PWM | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.6086 | -120.2124 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004162 | 4594 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101078390 | RELW OH PRI CLR REMT FMOB ESTR BTKA USA TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-29 | 2020-05-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117337834 | POLE_DECA_REPL - 8107 CEDAR LN 5PW/3PS M | 35208828 |  |  | STS-POLE_DECA_REPL - 8107 CEDAR LN 5PW/3 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.6059 | -120.2074 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004162 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103090593 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-29 | 2020-05-29 |  | 2020-05-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117339596 | POLE_DECA_REPL - HUNTER VALLEY RD AT 753 | 35208859 |  |  | STS-POLE_DECA_REPL - HUNTER VALLEY RD AT | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5821 | -120.1766 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004164 | 4594 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.1 | 39.1 |  |  | 0 | 39.1 | 39.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077344 | RELW PRI OH CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-18 | 2021-02-18 | COMP | 2021-02-18 | [16 empty] | 2019-05-29 | 2020-05-29 | 2020-09-28 | 2020-09-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | 16012.24 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117687907 | POLE _BROK _REPL_2881 TROWER 1PNW/3PSW/2 | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 37.4452 | -120.1 |  | TIER 2 |  |  | 0000006171 |  | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101069758 | REGW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-07-31 | 2020-07-31 | 2020-11-09 | 2020-11-09 | 2021 CBP Plan |  | UNASSIGNED | [11 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117687930 | POLE _BROK _REPL_4878 LEONARD PVTP | 35209393 |  |  | STS-POLE _BROK _REPL_4878 LEONARD PVTP | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4501 | -119.8056 |  | TIER 2 |  |  | 05206C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101072922 | RELW OH PRI ESTR TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117692129 | POLE _ BROK _ REPL_4485 Kimberly Ln, Mar | 35216335 |  |  | STS-POLE _ BROK _ REPL_4485 KIMBERLY LN, | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4408 | -120.0087 |  | TIER 2 |  |  | 06182A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103205615 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  |  | 1 | 13.5 | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Mariposa | Mariposa |  |  | OPEN | 118166312 | POLE_BROK_REPL - 5693 OLD ORCHARD LN/1PS | 35215721 |  |  | STS-POLE_BROK_REPL - 5693 OLD ORCHARD LN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.4916 | -119.8265 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 0000520186 | 22024 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101065599 | RELW OH PRI JPOL ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-11-12 | 2020-11-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452101 | 1 |  | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | COMP | 116985910 | POLE_DECA_REPL - 5617 DOGTWOWN RD 2PWMAR | 35154290 |  |  | STS-POLE_DECA_REPL - 5617 DOGTWOWN RD 2P | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.7057 | -120.1549 |  | TIER 2 | 291 | 25219-2105, BEAR VALLEY | 0000003161 |  | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077268 | OH RELW PRI COMP REMT NOAC ESTR CCNT FMOB TER2 PRTO FSRP | Pole | 2020-04-23 | 2020-06-09 | COMP | 2020-04-23 | COMP | 2021-01-13 | [13 empty] | 2021-02-04 | 2021-01-13 | 2020-04-09 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252192105 | 25903.66 | 50948.4 | 30140.2 | 31023.5 | 31023.5 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116753189 | POLE_DECA_REPL - ENT/O 5284 ALLRED RDMAR | 35084224 |  |  | STS-POLE_DECA_REPL - ENT/O 5284 ALLRED R | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4748 | -119.9236 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 0000005193 |  | Y | 311 |  |  | 2021-03-01 07:52 | 2021-03-01 15:19 | Dispatched | CLICK | [6 empty] | 0.8 | 0.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103331524 | RELW OH PRI REMT ESTR BTKA FMOB PRTO TER2 | Pole | 2021-01-11 | 2021-01-14 | COMP | 2021-01-11 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-03-17 | 2019-09-13 |  | 2019-09-13 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254452101 | 5512.89 | 904.4 | 904.4 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116759156 | POLE_DECA_REPL - 5236 ALLRED RD.4PSMARIP | 35084780 |  |  | STS-POLE_DECA_REPL - 5236 ALLRED RD.4PSM | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4704 | -119.9217 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 0000005196 | 21175 | Y | 311 |  |  | 2021-03-01 06:52 | 2021-03-01 11:24 | Dispatched | CLICK | [6 empty] | 0.8 | 0.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087843 | OH RELW PRI REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-15 | 2021-01-15 | COMP | 2021-01-15 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-03-18 | 2019-09-14 |  | 2019-09-14 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254452101 | 8539.38 | 1170.9 | 1170.9 | 1316 | 1316 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116841969 | POLE_DECA_REPL - 2PN/W 4006 HWY140MARIPO | 35214852 |  |  | STS-POLE_DECA_REPL - 2PN/W 4006 HWY140MA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4807 | -120.0277 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000005183 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.8 | 15.8 |  |  | 0 | 15.8 | 15.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087736 | RELW OH PRI PGEA REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 | 2021-01-28 | COMP | 2021-01-28 | [16 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 5649.29 | 13.5 | -210 | 1126.5 | 1126.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116854774 | POLE_DECA_REPL - 4343 HWY140MARIPOSA9533 | 35215028 |  |  | STS-POLE_DECA_REPL - 4343 HWY140MARIPOSA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4928 | -119.9998 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005183 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 32.4 | 32.4 |  |  | 0 | 32.4 | 32.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087646 | RELW PGEA OH PRI REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-28 | 2021-01-28 | COMP | 2021-01-28 | [16 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 15679.01 | 100.6 | -163.3 | 928.7 | 928.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116858198 | POLE_DECA_REPL - W/O WOODLAND DR S/O E.W | 35215048 |  |  | STS-POLE_DECA_REPL - W/O WOODLAND DR S/O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4486 | -119.8442 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05195D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 31.3 | 31.3 |  |  | 0 | 31.3 | 31.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085113 | PRI RELW OH REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-04 | 2021-02-04 | COMP | 2021-02-04 | [16 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452101 | 10799.06 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116858215 | POLE_DECA_REPL - R/O 3341 WOODLAND DR/2S | 35215062 |  |  | STS-POLE_DECA_REPL - R/O 3341 WOODLAND D | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.448 | -119.8461 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05195D | 90351 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.8 | 39.8 |  |  | 0 | 39.8 | 39.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085144 | RELW OH PRI REMT ESTR REAR FMOB FSRP TER2 PRTO | Pole | 2021-01-21 | 2021-01-21 | COMP | 2021-01-21 | [16 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452101 | 18190.4 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116858224 | POLE_DECA_REPL - R/O 3290 WOODLAND DRMAR | 35215072 |  |  | STS-POLE_DECA_REPL - R/O 3290 WOODLAND D | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4462 | -119.8442 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05195D |  | Y | 311 |  |  | 2021-03-10 09:07 | 2021-03-10 13:01 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101085127 | RELW OH SEC REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-22 | 2021-01-22 | COMP | 2021-01-22 | [16 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452101 | 6046.51 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116860375 | POLE_DECA_REPL - DRIVEWAY 4576 JEANNINE | 35215083 |  |  | STS-POLE_DECA_REPL - DRIVEWAY 4576 JEANN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4486 | -120.0083 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005186 |  | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-08 15:00 | Scheduled | CLICK | [6 empty] | 0.8 | 0.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084601 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-22 | 2021-01-22 | COMP | 2021-01-22 | [16 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 5539.28 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116863704 | POLE_BROK_REPL - RO 3988 OLD HIGHWAY 140 | 35215251 |  |  | STS-POLE_BROK_REPL - RO 3988 OLD HIGHWAY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4255 | -120.0058 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182D | 22467 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.4 | 32.4 |  |  | 0 | 32.4 | 32.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101067084 | OH PRI REMT ESTR REAR FMOB TER2 PRTO FSRP RELW | Pole | 2021-02-10 | 2021-02-10 | COMP | 2021-02-10 | [16 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 13340.71 |  | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116865381 | POLE_DECA_REPL - 4581 QUAIL CTMARIPOSA95 | 35209472 |  |  | STS-POLE_DECA_REPL - 4581 QUAIL CTMARIPO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4543 | -120.0119 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005186 | 11898 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 58.2 | 57 | 1.2 |  | 0 | 58.2 | 57 | 1.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084213 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-27 | 2021-02-01 | COMP | 2021-01-27 |  |  | 2021-01-29 | 2021-02-01 | [12 empty] | 2019-03-29 | 2020-03-29 | 2020-09-13 | 2020-09-13 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 27569.88 | 392.6 | 379.2 | 1479.2 | 1479.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116865531 | POLE_DECA_REPL - ENT 4529 BRIDGEPORTMARI | 35209476 |  |  | STS-POLE_DECA_REPL - ENT 4529 BRIDGEPORT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4276 | -119.9988 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182D | 10377 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 54 | 52.8 | 1.2 |  | 0 | 54 | 52.8 | 1.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067840 | RELW OH PRI REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-27 | 2021-02-01 | COMP | 2021-01-27 |  |  | 2021-01-29 | 2021-02-01 | [12 empty] | 2019-03-29 | 2020-03-29 | 2020-09-09 | 2020-09-09 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 28158.59 | 542 | 528.5 | 1628.5 | 1628.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116866752 | POLE_DECA_REPL - 4632 HWY49MARIPOSA95338 | 35191626 |  |  | STS-POLE_DECA_REPL - 4632 HWY49MARIPOSA9 | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4625 | -119.9458 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000518255 | 58531 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101084739 | OH PRI PGEA REMT FIRE ESTR BTKA PRTO RELW FMOB TER2 | Pole | 2020-10-21 | 2020-10-21 | COMP | 2020-10-21 | [16 empty] | 2019-03-29 | 2020-03-29 | 2020-10-21 | 2020-10-21 | B-tag addition 8/12/2020 |  | Bakersfield |  | 254452102 | 23273.94 | 3595.6 | [7 empty] | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-08-18
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116871761 | POLE_DECA_REPL - 4607 YAQUI GULCHMARIPOS | 35209589 |  |  | STS-POLE_DECA_REPL - 4607 YAQUI GULCHMAR | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4548 | -120.0052 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005186 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 13.3 | 13.3 |  |  | 0 | 13.3 | 13.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084261 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-04 | 2021-02-04 | COMP | 2021-02-04 | [16 empty] | 2019-03-30 | 2020-03-30 | 2020-09-13 | 2020-09-13 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 7447.75 | 13.5 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116872606 | POLE_DECA_REPL - 4649 BURNEY 1/SMARIPOSA | 35209601 |  |  | STS-POLE_DECA_REPL - 4649 BURNEY 1/SMARI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4565 | -120.0032 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005186 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.2 | 28.2 |  |  | 0 | 28.2 | 28.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101084250 | RELW OH PRI RESD REMT ESTR BTKA FSRP FMOB TER2 PRTO | Pole | 2021-02-11 | 2021-02-11 | COMP | 2021-02-11 | [16 empty] | 2019-03-30 | 2020-03-30 | 2020-09-11 | 2020-09-11 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 9897.33 | 13.5 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117095841 | POLE_DECA_REPL - MB 6969 HWY 49 8PNWMARI | 35209692 |  |  | STS-POLE_DECA_REPL - MB 6969 HWY 49 8PNW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.557 | -120.1055 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004176 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22 | 22 |  |  | 0 | 22 | 22 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101028394 | RELW OH PRI CLR REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-19 | 2021-01-19 | COMP | 2021-01-19 | [16 empty] | 2019-04-25 | 2020-04-25 | 2020-09-25 | 2020-09-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | 9436.05 | 53.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117097538 | POLE_DECA_REPL - 6973 HWY 49 3PSWMARIPOS | 35209703 |  |  | STS-POLE_DECA_REPL - 6973 HWY 49 3PSWMAR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5472 | -120.1017 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004176 | 24034 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.1 | 26.1 |  |  | 0 | 26.1 | 26.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101018944 | RELW OH PRI REMT FIRE ESTR BTKA USA FMOB TER2 FSRP PRTO | Pole | 2021-01-29 | 2021-01-29 | COMP | 2021-01-29 | [16 empty] | 2019-04-25 | 2020-04-25 | 2020-09-25 | 2020-09-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117100649 | OLE_DECA_REPL - 6657 A HWY 49MARIPOSA95 | 35209728 |  |  | STS- OLE_DECA_REPL - 6657 A HWY 49MARIPO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5293 | -120.0858 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000005171 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 16.1 | 16.1 |  |  | 0 | 16.1 | 16.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101068449 | RELW OH SEC REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-25 | 2021-01-25 | COMP | 2021-01-25 | [16 empty] | 2019-04-25 | 2020-04-25 | 2020-10-09 | 2020-10-09 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | 6264.97 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117111133 | POLE_DECA_REPL - 2794[HSE]OAK GROVE RD/1 | 35208772 |  |  | STS-POLE_DECA_REPL - 2794[HSE]OAK GROVE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3424 | -119.8611 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000007191 |  | Y | 311 |  |  | 2021-03-12 07:04 | 2021-03-12 10:13 | Scheduled | CLICK | [6 empty] | 0.8 | 0.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067958 | RELW OH PRI CLR REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 | 2021-01-19 | COMP | 2021-01-19 | [16 empty] | 2019-04-27 | 2020-04-27 | 2020-10-21 | 2020-10-21 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 4851.42 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117318401 | POLE_DECA_REPL - 5633 DARRAH RD/3PSMARIP | 35209684 |  |  | STS-POLE_DECA_REPL - 5633 DARRAH RD/3PSM | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4966 | -119.8537 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005194 | 22286 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101078751 | RELW OH PRI REMT FIRE NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-21 | 2021-01-21 | COMP | 2021-01-21 | [16 empty] | 2019-05-24 | 2020-05-24 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 18922.24 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117330375 | POLE_DECA_REPL - 4093A OLD HIGHWAYMARIPO | 35215762 |  |  | STS-POLE_DECA_REPL - 4093A OLD HIGHWAYMA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4334 | -120.0056 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 06182A | 10388 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.9 | 40.9 | 0 |  | 0 | 40.9 | 40.9 | 0 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101067528 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-10 | 2021-02-10 | COMP | 2021-02-10 | [16 empty] | 2019-05-28 | 2020-05-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 254452102 | 14956.57 | 13.5 | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 119495154 | POLE_DECA_REPL - 5990 EVERGREEN LN/3PE M | 35199302 |  |  | STS-POLE_DECA_REPL - 5990 EVERGREEN LN/3 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5062 | -119.8234 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 0000520075 | 10303 | Y | 311 |  |  | 2021-03-09 07:00 | 2021-03-09 16:00 | Scheduled | CLICK | [6 empty] | 40.9 | 40.9 |  |  | 0 | 40.9 | 40.9 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101064692 | RELW OH PRI INSP ESTR BTKA USA FMOB TER2 PRTO PROG GO | Pole | 2020-09-24 | 2020-09-24 | COMP | 2020-09-24 | [16 empty] | 2020-07-23 | 2020-10-23 |  | 2020-10-23 | B tag clean up 9/13/2020 |  | Fresno |  | 254452101 | 15188.79 | 4737.5 | 430.6 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-09-13
Bay/Central | YO | Mariposa | Mariposa |  |  | OPEN | 119522222 | POLE_DECA_REPL - R/O 5102 OAK RD MARIPOS | 35190703 |  |  | STS-POLE_DECA_REPL - R/O 5102 OAK RD MAR | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5499 | -119.9327 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 04185A | 4579 | Y | 311 |  |  | 2021-02-16 07:00 | 2021-02-16 16:00 | Completed | CLICK | [6 empty] | 42.8 | 42.8 |  |  | 0 | 42.8 | 42.8 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101073602 | RELW OH PRI INSP CUST RESD FIRE ESTR BTKA FMOB TER2 | Pole | 2020-08-15 | 2020-08-15 | COMP | 2020-08-15 | [16 empty] | 2020-07-29 | 2020-10-29 |  | 2020-10-29 | B-tag addition 8/4/2020 |  | Fresno |  | 254452101 | 17534.33 | 5213.4 | 2046.1 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-08-04
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 120509530 | TREE_DECA_INPL - 3028 TRIANGLE PARK RD M | 35232360 |  |  | STS-TREE_DECA_INPL - 3028 TRIANGLE PARK | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-04-11 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4827 | -119.7919 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 0000005203 | 56325 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.9 | 17.9 |  |  | 0 | 17.9 | 17.9 |  |  | EC | B | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 101075162 | RELW OH SEC TMAN BTKA TER2 ESTR | Pole | 2021-02-16 | 2021-02-16 | COMP | 2021-02-16 | [16 empty] | 2021-02-09 | 2021-05-09 |  | 2021-05-09 | B tag clean up 2/19/2021 |  | Fresno |  | 254452101 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 116754904 | POLE_DECA_REPL - 5236 ALLRED RD. 2PEMARI | 35084316 |  |  | STS-POLE_DECA_REPL - 5236 ALLRED RD. 2PE | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.4718 | -119.9215 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 0000005196 | 21158 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.8 | 40.6 | 0.2 |  | 0 | 40.8 | 40.6 | 0.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101087823 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-25 | 2020-12-29 | COMP | 2020-12-23 | [16 empty] | 2019-03-18 | 2019-09-14 |  | 2019-09-14 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254452101 | 18356.58 | 1207.9 | 1207.9 | 181 | 181 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117098306 | POLE_DECA_REPL - 4941 BEAR VALLEY RDMARI | 35105519 |  |  | STS-POLE_DECA_REPL - 4941 BEAR VALLEY RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5695 | -120.1238 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004173 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.5 | 19.5 |  |  | 0 | 19.5 | 19.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103225370 | RELW OH PRI REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-07 | 2021-01-07 | COMP | 2021-01-07 | [16 empty] | 2019-04-25 | 2019-10-25 | 2020-09-24 | 2020-09-24 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117108194 | POLE_DECA_REPL - R/O 5802 DARRAH RDMARIP | 35209773 |  |  | STS-POLE_DECA_REPL - R/O 5802 DARRAH RDM | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5064 | -119.8448 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05191D |  | Y | 311 |  |  | 2021-06-29 07:00 | 2021-06-29 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077989 | RELW OH SERV RESD BTKA REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-10 | 2020-12-10 | COMP | 2020-12-10 | [16 empty] | 2019-04-26 | 2020-04-26 | 2020-10-14 | 2020-10-14 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 5542.13 | 40.4 | -1267 | -814.5 | -814.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117111906 | POLE_BROK_REPL - 6595 HWY 49 1PN MARIPOS | 35208775 |  |  | STS-POLE_BROK_REPL - 6595 HWY 49 1PN MAR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.527 | -120.0828 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000005171 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.6 | 12.6 |  |  | 0 | 12.6 | 12.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101068418 | RELW OH SEC REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-30 | 2020-12-30 | COMP | 2020-12-30 | [16 empty] | 2019-04-27 | 2020-04-27 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | 7377.22 | 60.2 | 46.8 | 612.5 | 612.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117112310 | POLE_DECA_REPL - 5802 DARRAH RD/1PWMARIP | 35208778 |  |  | STS-POLE_DECA_REPL - 5802 DARRAH RD/1PWM | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5067 | -119.8453 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 05191D | 46623 | Y | 311 |  |  | 2021-06-29 07:00 | 2021-06-29 16:00 | Reserved | CLICK | [6 empty] | 51.8 | 51.8 |  |  | 0 | 51.8 | 51.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077980 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-15 | 2020-12-15 | COMP | 2020-12-10 | [16 empty] | 2019-04-27 | 2020-04-27 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 21554.07 |  | -1267 | -814.5 | -814.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA | Mariposa |  |  | OPEN | 117155320 | POLE_DECA_REPL - 4982 LEONARD/2PSWMARIPO | 35209088 |  |  | STS-POLE_DECA_REPL - 4982 LEONARD/2PSWMA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4557 | -119.806 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 05206C |  | Y | 311 |  |  | 2021-06-29 07:00 | 2021-06-29 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101072897 | RELW OH SEC REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-15 | 2020-12-15 | COMP | 2020-12-15 | [16 empty] | 2019-05-03 | 2020-05-03 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452101 | 4435.57 | 943.5 | -83.5 | -561.1 | -561.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MARIPOSA, BEAR VALLEY | Oakhurst |  |  | OPEN | 117506538 | POLE_DECA_REPL - 4715 BEAR VALLEY RD 1PS | 35209115 |  |  | STS-POLE_DECA_REPL - 4715 BEAR VALLEY RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5693 | -120.1432 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004173 | 4191 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101028361 | RELW PRI OH CLR REMT FIRE ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-29 | 2020-06-29 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MCCLURE LAKE | Merced |  |  | OPEN | 117072762 | POLE_BURN_REPL - LAKE MCCLURE DR. AND VI | 35215516 |  |  | STS-POLE_BURN_REPL - LAKE MCCLURE DR. AN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5763 | -120.286 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 0000004154 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 103236035 | RELW OH PRI CLR RESD REMT NOAC TER2 ESTR USA FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252811102 | 1 | 48.3 | 34.8 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MIDPINES | Mariposa |  |  | OPEN | 117115993 | POLE_BROK_REPL - 5PW 7PS 5354 RUMLEY MIN | 35208795 |  |  | STS-POLE_BROK_REPL - 5PW 7PS 5354 RUMLEY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5691 | -119.9863 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 0000004183 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101077654 | RELW OH PRI FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-28 | 2020-04-28 |  | 2020-04-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MIDPINES | Mariposa |  |  | OPEN | 117118295 | POLE_DECA_REPL - 5PW 5354 RUMBLEY MINEMI | 35154201 |  |  | STS-POLE_DECA_REPL - 5PW 5354 RUMBLEY MI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5732 | -119.9867 |  | TIER 2 | 450 | 25445-2101, MARIPOSA | 0000004183 | 10238 | Y | 311 |  |  | 2021-06-29 07:00 | 2021-06-29 16:00 | Reserved | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077602 | RELW OH PRI REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-10-14 | 2020-10-15 | COMP | 2020-09-02 |  |  | 2020-08-19 | 2020-08-19 | [12 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254452101 | 20284.07 | 771.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MOCCASIN CA | Mariposa |  |  | OPEN | 116973683 | POLE_DECA_REPL - 7785 MARSH FLATS RD MOC | 35208925 |  |  | STS-POLE_DECA_REPL - 7785 MARSH FLATS RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.7647 | -120.3275 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 0000002153 | 8525 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101191218 | RELW OH PRI REMT FIRE ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-07 | 2020-04-07 | 2020-10-18 | 2020-10-18 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252811102 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117047898 | POLE_BROK_REPL - 20550 N.SUNSHINE DR.MON | 35187771 |  |  | STS-POLE_BROK_REPL - 20550 N.SUNSHINE DR | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.9948 | -120.2732 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3602 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.5 | 26.5 |  |  | 0 | 26.5 | 26.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101039629 | RELW OH PRI PGEA COMM ESTR BTKA USA FMOB FSRP TER2 PRTO | Pole | 2020-09-16 | 2021-02-01 | COMP | 2020-09-16 |  |  | 2021-02-01 | 2021-02-01 | [12 empty] | 2019-04-17 | 2020-04-17 | 2024-04-15 | 2024-04-15 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 15264.86 | 476.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117048695 | POLE_BROK_REPL - A/F AIM TERMITE CONTROL | 35154671 |  |  | STS-POLE_BROK_REPL - A/F AIM TERMITE CON | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD | 2021-01-09 | Renew Permit | 37.9927 | -120.2755 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3602 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101039613 | OH PRI ESTR RELW JPOL RESD BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2021-02-19 | 2021-02-19 | [12 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 1 | 308.7 |  |  |  | 83.4 |  | 83.4 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117082353 | POLE_BROK_REPL - 20709 GREEN ACRES RDMON | 35188223 |  |  | STS-POLE_BROK_REPL - 20709 GREEN ACRES R | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 37.9974 | -120.2782 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3621 | L1363 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.1 | 56.5 | 0.6 |  | 0 | 57.1 | 56.5 | 0.6 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101055102 | RELW OH PRI CLR RESD ESTR TER2 BTKA USA FMOB PRTO | Pole | 2020-10-06 | 2020-10-05 | COMP | 2020-10-05 | [16 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117097590 | POLE_BROK_REPL - 16607 CREEKSIDEMONO VIS | 35187757 |  |  | STS-POLE_BROK_REPL - 16607 CREEKSIDEMONO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.0179 | -120.2746 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3612 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.1 | 36.1 |  |  | 0 | 36.1 | 36.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057444 | RELW OH PRI RESD FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-22 |  | COMP | 2020-09-22 | [16 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 15829.87 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117099055 | POLE_BROK_REPL - 21834 JOYCE CTMONO VIST | 35187769 |  |  | STS-POLE_BROK_REPL - 21834 JOYCE CTMONO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.0186 | -120.2773 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3612 | 2505 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 46.9 | 46.9 |  |  | 0 | 46.9 | 46.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057494 | RELW OH PRI CLR RESD FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-02 |  | COMP | 2020-10-02 |  |  | 2021-01-17 | 2021-01-17 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 19610.25 | 137.1 | -127.7 | -127.7 | -127.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117050029 | POLE_BROK_REPL - 20424 N.SUNSHINE DR. 2N | 35187819 |  |  | STS-POLE_BROK_REPL - 20424 N.SUNSHINE DR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9937 | -120.2749 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3602 | 64399 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 56.5 | 56.3 | 0.2 |  | 0 | 56.5 | 56.3 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101039619 | RELW OH PRI CLR RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-09-21 | 2020-11-24 | COMP | 2020-09-21 |  |  | 2020-08-18 | 2020-08-18 | [12 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 21315.39 | 443.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117064817 | POLE_BROK_REPL - 20311 SUNSHINE DR. 1SW | 35188033 |  |  | STS-POLE_BROK_REPL - 20311 SUNSHINE DR. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9907 | -120.2804 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3601 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.7 | 21.7 |  |  | 0 | 21.7 | 21.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101039267 | RELW OH SERV JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-11-09 | 2020-11-24 | COMP | 2020-09-27 | [16 empty] | 2019-04-19 | 2020-04-19 |  | 2020-04-19 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 11294.41 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117064941 | POLE_DECA_REPL - 20670 N. SUNSHINE RD/2P | 35188038 |  |  | STS-POLE_DECA_REPL - 20670 N. SUNSHINE R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9962 | -120.2726 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3622 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.8 | 13.8 |  |  | 0 | 13.8 | 13.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101014397 | RELW OH SEC JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-09-22 | 2020-11-20 | COMP | 2020-09-22 | [16 empty] | 2019-04-19 | 2020-04-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 4310.1 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117068239 | POLE_DECA_REPL - 3PN/ 20280 CRIPPLE HILL | 35188093 |  |  | STS-POLE_DECA_REPL - 3PN/ 20280 CRIPPLE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9933 | -120.2886 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3505 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.6 | 15.6 |  |  | 0 | 15.6 | 15.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101032910 | RELW OH PRI RESD REMT SPCR ESTR BTKA REAR FMOB TER2 PRTO | Pole | 2020-09-22 | 2020-09-22 | COMP | 2020-09-22 | [16 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 5863.61 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117068646 | POLE_BROK_REPL - 16071 AVENIDA DEL SOL 4 | 35188104 |  |  | STS-POLE_BROK_REPL - 16071 AVENIDA DEL S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.995 | -120.2907 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3505 | 8365 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.8 | 22.8 |  |  | 0 | 22.8 | 22.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033549 | RELW OH PRI CLR RESD REMT ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-09-22 | 2020-11-22 | COMP | 2020-09-22 | [16 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 10652.54 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117084609 | POLE_BROK_REPL - 21211 RIDGEVIEW DR MONO | 35187598 |  |  | STS-POLE_BROK_REPL - 21211 RIDGEVIEW DR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0074 | -120.2742 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3617 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.4 | 24.4 |  |  | 21.25 | 3.15 | 3.15 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101039759 | RELW OH PRI JPOL RESD REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-21 | 2021-02-01 | COMP | 2020-09-21 |  |  | 2021-02-01 | 2021-02-01 | [12 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 12934.79 | 8376.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117088363 | POLE_BROK_REPL - 21436 GREEN OAKS CTMONO | 35126412 |  |  | BUNDLE 4 POLES - MONO VISTA / SONORA | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-12-31 | No Action | 38.0113 | -120.2745 |  | TIER 2 | 58 | 16366-1702, MIWUK | T3617 | L2019 | Y | 311 |  |  | 2021-03-06 07:00 | 2021-03-06 16:00 | Scheduled | CLICK | [6 empty] | 181.5 | 181.5 |  |  | 0 | 181.5 | 181.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101039718 | RESD RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-01-22 | 2020-06-11 | COMP | 2020-01-22 |  |  | 2021-02-19 | 2021-02-19 | [12 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | circuit based plan 2.14 |  | UNASSIGNED |  | 163661702 | 84545.68 | 27826.6 | -19341.3 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117089285 | POLE_BROK_REPL - 21413 GREEN OAKS CTMONO | 35126412 |  |  | BUNDLE 4 POLES - MONO VISTA / SONORA | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-12-31 | No Action | 38.0106 | -120.2739 |  | TIER 2 | 58 | 16366-1702, MIWUK | T3617 |  | Y | 311 |  |  | 2021-03-06 07:00 | 2021-03-06 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101039710 | JPOL RELW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-01-22 | 2020-06-11 | COMP | 2020-01-22 |  |  | 2021-02-19 | 2021-02-19 | [12 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | circuit based plan 2.14 |  | UNASSIGNED |  | 163661702 | 84545.68 | 27826.6 | -19341.3 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117090162 | POLE_DECA_REPL - 21348 CRESTVIEW DR MONO | 35126412 |  |  | BUNDLE 4 POLES - MONO VISTA / SONORA | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-12-31 | No Action | 38.0097 | -120.2729 |  | TIER 2 | 58 | 16366-1702, MIWUK | T3617 | L2019 | Y | 311 |  |  | 2021-03-06 07:00 | 2021-03-06 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101039696 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-01-22 | 2020-06-11 | COMP | 2020-01-22 |  |  | 2021-02-19 | 2021-02-19 | [12 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | circuit based plan 2.14 |  | UNASSIGNED |  | 163661702 | 84545.68 | 27826.6 | -19341.3 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117096474 | POLE_BROK_REPL - S/E CORNER SALLANDER AN | 35187739 |  |  | STS-POLE_BROK_REPL - S/E CORNER SALLANDE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0152 | -120.276 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3612 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.5 | 16.5 |  |  | 0 | 16.5 | 16.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103111774 | RELW OH SERV RESD NOAC ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-10-05 | 2020-11-25 | COMP | 2020-10-05 | [16 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117082356 | POLE_BROK_REPL - 21301 RIDGEVIEW DR/1PSE | 35188229 |  |  | STS-POLE_BROK_REPL - 21301 RIDGEVIEW DR/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0086 | -120.2751 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3617 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 34.1 | 34.1 |  |  | 0 | 34.1 | 34.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101039792 | RELW OH PRI RESD TRAF FLAG ESTR BTKA USA FMOB PRTO TER2 | Pole | 2020-10-05 | 2021-01-16 | COMP | 2020-10-05 |  |  | 2021-01-16 | 2021-01-16 | [12 empty] | 2019-04-23 | 2020-04-23 | 2020-10-10 | 2020-10-10 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 16069.68 | 129.5 | 53.4 | 53.4 | 53.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117085123 | POLE_BROK_REPL - 21120 RIDGEVIEW DR/1PNE | 35187635 |  |  | STS-POLE_BROK_REPL - 21120 RIDGEVIEW DR/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0062 | -120.2756 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3617 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.3 | 26.3 |  |  | 0 | 26.3 | 26.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101039768 | RELW OH PRI JPOL REMT TRAF ESTR BTKA USA FMOB PRTO TER2 | Pole | 2020-10-02 | 2021-01-17 | COMP | 2020-10-02 |  |  | 2021-01-17 | 2021-01-17 | [12 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 14657.12 | 178.9 | 53.4 | 53.4 | 53.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117089922 | POLE_DECA_REPL - 16542 CREEKSIDE MONO VI | 35187687 |  |  | STS-POLE_DECA_REPL - 16542 CREEKSIDE MON | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0142 | -120.2756 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3612 | 19283 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.8 | 40.8 |  |  | 0 | 40.8 | 40.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101057455 | RELW OH PRI FLAG ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-10-12 | 2021-01-19 | COMP | 2020-10-12 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 19461.8 | 373.9 | 373.9 | 373.9 | 373.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117095462 | POLE_BROK_REPL - 16760 WOODSIDEMONO VIST | 35187710 |  |  | STS-POLE_BROK_REPL - 16760 WOODSIDEMONO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0166 | -120.2741 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3612 | 2507 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 46.2 | 46.2 |  |  | 0 | 46.2 | 46.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057426 | RELW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-02 | 2021-01-17 | COMP | 2020-10-02 |  |  | 2021-01-17 | 2021-01-17 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 18206.5 | 53.4 | 53.4 | 53.4 | 53.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MONO VISTA | Sonora |  |  | OPEN | 117097483 | POLE_BROK_REPL - 16607 CREEKSIDE 1P/WMON | 35187751 |  |  | STS-POLE_BROK_REPL - 16607 CREEKSIDE 1P/ | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0178 | -120.2746 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3612 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14 | 14 |  |  | 0 | 14 | 14 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057445 | RELW OH PRI RESD FLAG TER2 ESTR BTKA USA FMOB PRTO | Pole | 2020-10-16 | 2021-01-19 | COMP | 2020-10-16 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 7544.31 | 213.5 | 213.5 | 213.5 | 213.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | MORIPOSA | Mariposa |  |  | OPEN | 116868559 | POLE_BROK_REPL - ENT 4026 GUADALUPE CREE | 35209530 |  |  | STS-POLE_BROK_REPL - ENT 4026 GUADALUPE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4544 | -120.0184 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000005186 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17 | 17 |  |  | 0 | 17 | 17 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101084439 | RELW OH PRI RESD REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-03 | 2021-02-03 | COMP | 2021-02-03 | [16 empty] | 2019-03-29 | 2020-03-29 | 2020-09-13 | 2020-09-13 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254452102 | 5907.49 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | N/A | Mariposa |  |  | OPEN | 117084028 | POLE_DECA_REPL - #23 N/O 4170 BEAR VALLE | 35215613 |  |  | STS-POLE_DECA_REPL - #23 N/O 4170 BEAR V | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5672 | -120.1642 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004164 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077701 | RELW OH PRI REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-23 | 2020-04-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | N/A | Mariposa |  |  | OPEN | 117085329 | POLE_DECA_REPL - #2 NE/O 4561 BEAR VALLE | 35214578 |  |  | STS-POLE_DECA_REPL - #2 NE/O 4561 BEAR V | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5702 | -120.1526 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004164 | 23029 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077708 | RELW OH PRI REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-23 | 2020-04-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | N/A | Mariposa |  |  | OPEN | 117098594 | POLE_DECA_REPL - 3969 BEAR VALLEY RD 2PE | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 37.5523 | -120.1762 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004165 |  | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101078934 | REGW OH PRI PGEA CLR REMT FIRE NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-04-25 | 2020-04-25 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan |  | UNASSIGNED |  | 252192101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | N/A | Mariposa |  |  | OPEN | 117104130 | POLE_DECA_REPL - 3860 BEAR VALLEY RD 2PN | 35214805 |  |  | STS-POLE_DECA_REPL - 3860 BEAR VALLEY RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro |  |  | 37.5451 | -120.1942 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004165 | 10427 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101078987 | RELW OH PRI REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-26 | 2020-04-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252192101 | 1 | 48.3 | 34.8 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | N/A | Mariposa |  |  | OPEN | 117122080 | OLE_DECA_REPL - 42652 RD812 1PN 9PE 4PS | 35208820 |  |  |  | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3599 | -119.7982 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000006206 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.2 | 14.2 |  |  | 0 | 14.2 | 14.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101069078 | PRI RELW OH PGEA CLR REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-16 | 2021-02-16 | COMP | 2021-02-16 | [16 empty] | 2019-04-29 | 2020-04-29 | 2020-08-31 | 2020-08-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 6536.77 | 60.2 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | N/A | Mariposa |  |  | OPEN | 117149320 | POLE_DECA_REPL - 42652 RD812 6PW 3PS/ON/ | 35209053 |  |  | STS-POLE_DECA_REPL - 42652 RD812 6PW 3PS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.3672 | -119.8213 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000006206 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.2 | 20.2 |  |  | 0 | 20.2 | 20.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101068728 | RELW OH PRI PGEA CLR REMT FIRE NOAC FMOB ESTR REAR USA TER2 PRTO FSRP | Pole | 2021-02-03 | 2021-02-02 | COMP | 2021-02-02 | [16 empty] | 2019-05-02 | 2020-05-02 | 2020-12-23 | 2020-12-23 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 6949.86 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | N/A | Mariposa |  |  | OPEN | 117162926 | POLE_DECA_REPL - 33804 RD 613/15N/1EN/A | 35209235 |  |  | STS-POLE_DECA_REPL - 33804 RD 613/15N/1E | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.2548 | -119.9236 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008192 | 5521 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 39.6 | 39.6 |  |  | 0 | 39.6 | 39.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059737 | RELW OH PRI REMT FIRE ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-22 |  | COMP | 2021-01-22 | [16 empty] | 2019-05-04 | 2020-05-04 | 2020-10-16 | 2020-10-16 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 18767.42 | 60.2 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | N/A | Mariposa |  |  | OPEN | 117008826 | POLE_DECA_REPL - 2986 CADENAN/A | 35154373 |  |  | STS-POLE_DECA_REPL - 2986 CADENAN/A | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-12 | Renew Permit | 37.7264 | -120.3368 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 02156A |  | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 16.8 | 16.8 |  |  | 0 | 16.8 | 16.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101191365 | RELW OH PRI REMT FIRE ESTR BTKA FMOB TER2 PRTO | Pole | 2020-05-06 | 2020-07-20 | COMP | 2020-05-06 |  |  | 2020-02-26 | 2020-02-26 | [12 empty] | 2019-04-11 | 2020-04-11 |  | 2020-04-11 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252811102 | 9668.83 | 1265.8 | 1121.9 | 869.6 | 869.6 | 143.8 |  | 143.8 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | N/A | Mariposa |  |  | OPEN | 117024825 | POLE_DECA_REPL - 5077 POZUELON/A | 35154552 |  |  | STS-POLE_DECA_REPL - 5077 POZUELON/A | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7164 | -120.3502 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 02156C |  | Y | 311 |  |  | 2021-02-19 07:00 | 2021-02-19 16:00 | Completed | CLICK | [6 empty] | 18.3 | 18.3 |  |  | 0 | 18.3 | 18.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101192011 | RELW OH PRI REMT FIRE ESTR FMOB PRTO TER2 | Pole | 2020-05-19 | 2020-05-19 | COMP | 2020-05-19 | [16 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252811102 | 6071.75 | 3777.7 | 1203.9 | 1203.9 | 1203.9 | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | N/A | Mariposa |  |  | OPEN | 117077859 | POLE_DECA_REPL - HUNTER VALLEY RD AT 753 | 35209660 |  |  | STS-POLE_DECA_REPL - HUNTER VALLEY RD AT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5795 | -120.1781 |  | TIER 2 | 608 | 25219-2101, BEAR VALLEY | 0000004164 | 23028 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.3 | 44.3 |  |  | 0 | 44.3 | 44.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101077543 | RELW OH PRI PGEA CLR RESD REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-03 | 2021-02-03 | COMP | 2021-02-03 | [16 empty] | 2019-04-22 | 2020-04-22 | 2020-09-29 | 2020-09-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252192101 | 18273 | 100.5 | 87 | 87 | 87 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | N/A | Mariposa |  |  | COMP | 117070260 | POLE_DECA_REPL - 3166 GRANITE SPR. 3PE 3 | 35198151 |  |  | STS-POLE_DECA_REPL - 3166 GRANITE SPR. 3 | FICL | FICL SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-10-10 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.7135 | -120.3187 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 02156D |  | Y | 311 |  |  | 2021-01-16 | 2021-01-16 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 1 | 50.1 | 50.1 |  |  | 30 | 0 |  |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101190568 | RELW OH PRI COMP REMT FIRE NOAC TRAF ESTR CPGG FMOB TER2 PRTO | Pole | 2020-11-04 | 2020-12-28 | COMP | 2020-11-04 | COMP | 2021-01-16 | 2020-11-09 | 2020-11-09 | [11 empty] | 2021-01-21 | 2021-01-16 | 2019-09-19 | 2020-11-07 | 2020-11-07 | B tag clean up 9/5/2020 |  | Fresno |  | 252811102 | 6474.05 | 11263.6 | 10336.4 | 10336.4 | 10336.4 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Estimating Delays | Y | 2020-09-05
Bay/Central | YO | N/A | Mariposa |  |  | OPEN | 116981138 | POLE_DECA_REPL - 14570 BLANCHARD RD 11PN | 35198140 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7393 | -120.3231 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 02156A |  | Y | 311 |  |  | 2021-10-29 07:00 | 2021-10-29 16:00 | Scheduled | CLICK | [6 empty] | 50.1 | 50.1 |  |  | 0 | 50.1 | 50.1 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101191018 | RELW OH PRI REMT FIRE NOAC ESTR BTKA FMOB PRTO TER2 | Pole | 2020-10-06 | 2020-10-23 | COMP | 2020-10-06 | [16 empty] | 2019-04-08 | 2020-04-08 | 2020-11-04 | 2020-11-04 | B tag clean up 9/5/2020 |  | Fresno |  | 252811102 | 16262.36 | 1361.9 | [7 empty] | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-09-05
Bay/Central | YO | N/A | Mariposa |  |  | OPEN | 116984802 | POLE_DECA_REPL - 10533 BLANCHARD RDN/A | 35154277 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-12 | Renew Permit | 37.7271 | -120.3271 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 02156A |  | Y | 311 |  |  | 2021-10-29 07:00 | 2021-10-29 16:00 | Scheduled | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101190980 | RELW OH PRI CLR JPOL RESD REMT ESTR FIRE TRAF FLAG BTKA USA FMOB TER2 PRTO | Pole | 2020-07-01 | 2020-07-01 | COMP | 2020-05-11 |  |  | 2020-02-25 | 2020-02-26 | [12 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252811102 | 11649.25 | 2426.4 | 866.8 | 866.8 | 866.8 | 442.6 |  | 442.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | N/A | Mariposa |  |  | OPEN | 117039256 | POLE_DECA_REPL - 10470 LOZANON/A | 35198565 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7252 | -120.3399 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 02156A | 25874 | Y | 311 |  |  | 2021-10-29 07:00 | 2021-10-29 16:00 | Scheduled | CLICK | [6 empty] | 50.1 | 50.1 |  |  | 0 | 50.1 | 50.1 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101191543 | RELW OH PRI REMT FIRE ESTR BTKA FMOB TER2 PRTO | Pole | 2020-11-25 | 2020-12-23 | COMP | 2020-11-19 |  |  | 2020-12-18 | 2020-12-23 | [12 empty] | 2019-04-16 | 2020-04-16 | 2020-11-03 | 2020-11-03 | B tag clean up 9/5/2020 |  | Fresno |  | 252811102 | 14406.52 | 1351.9 | 1011 | 1011 | 1011 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-09-05
Bay/Central | YO | N/A | Merced |  |  | OPEN | 116976260 | POLE_DECA_REPL - 6560 MARSHS FLAT RD/7NN | 35174947 |  |  |  | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.7574 | -120.3293 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 0000002153 |  | Y | 311 |  |  | 2021-10-29 07:00 | 2021-10-29 16:00 | Dispatched | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101191190 | RELW OH PRI PGEA CLR REMT FIRE ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-05-13 | 2020-06-15 | COMP | 2020-05-13 | [16 empty] | 2019-04-07 | 2020-04-07 | 2020-07-22 | 2020-07-22 | B-Tag Clean Up 5/14/20 |  | Fresno |  | 252811102 | 27503.33 | 1571.8 | [7 empty] | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-05-25
Bay/Central | YO | N/A | Oakhurst |  |  | OPEN | 117186700 | POLE_DECA_REPL - 44052 CROOKS MTN. RD.N/ | 35134235 |  |  | BUNDLE - 4 POLES - AHWAHNEE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.395 | -119.7415 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000006204 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016533 | REGW OH PRI REMT FIRE TRAF ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28468 | 2021-03-31 | TRC |  | 254421101 | 1 |  | -210 | 882 | 882 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
Bay/Central | YO | N/A | Oakhurst |  |  | OPEN | 117241361 | POLE_DECA_REPL - R/O 37267 THUNDER RIDGE | 35208928 |  |  | STS-POLE_DECA_REPL - R/O 37267 THUNDER R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2932 | -119.674 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000007216 | 10338 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101026574 | RELW OH PRI PGEA CLR RESD REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | N/A | Oakhurst |  |  | OPEN | 117214275 | POLE_DECA_REPL - 58634 RD. 601N/A | 35154685 |  |  | STS-POLE_DECA_REPL - 58634 RD. 601N/A | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.4068 | -119.7282 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000006204 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.4 | 26.4 |  |  | 0 | 26.4 | 26.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101017189 | RELW OH PRI PGEA CLR RESD REMT FIRE NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-06-11 | 2020-06-11 | COMP | 2020-06-11 | [16 empty] | 2019-05-11 | 2020-05-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | PIKEENG |  | 254421101 | 20516.98 | 622.8 |  |  |  | 172.1 |  | 172.1 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | N/A | Oakhurst |  |  | OPEN | 117260495 | POLE_DECA_REPL - 1ST P N OF MB 43721 SKY | 35189501 |  |  | STS-POLE_DECA_REPL - 1ST P N OF MB 43721 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3773 | -119.6246 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000006215 | 5480 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 25.4 | 25.4 |  |  | 0 | 25.4 | 25.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101021946 | RELW OH PRI PGEA CLR RESD REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-13 | 2020-10-26 | COMP | 2020-10-12 |  |  | 2020-10-24 | 2020-10-24 | [12 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-11-15 | QUES |  | 254421103 | 12878.13 | 1099.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | N/A | Oakhurst |  |  | OPEN | 117267658 | TREE_DECA_INPL - N/AN/A | 35188697 |  |  | STS-TREE_DECA_INPL - N/AN/A | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.3763 | -119.6242 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000621255 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 28.2 | 28.2 |  |  | 0 | 28.2 | 28.2 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103200105 | RELW OH SERV PGEA CLR COMM REMT FIRE ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-25 | 2020-10-21 | COMP | 2020-09-25 | [16 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-11-15 | QUES |  | 254421103 | 11958.54 | 1539.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NA | Sonora |  |  | OPEN | 116873866 | POLE_BROK_REPL - AF\ENT\TO\23066 HELLS H | 35188593 |  |  | STS-POLE_BROK_REPL - AF\ENT\TO\23066 HEL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8134 | -120.1318 |  | TIER 2 | 72 | 16335-1703, CURTIS | Y39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24 | 24 |  |  | 0 | 24 | 24 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101038010 | RELW OH PRI JPOL REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-13 | 2021-01-15 | COMP | 2020-10-13 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-03-30 | 2020-03-30 |  | 2020-03-30 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 12553.77 | 149.5 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117137937 | POLE_DECA_REPL - 54481 PINCHOT DR.2PENOR | 35208926 |  |  | STS-POLE_DECA_REPL - 54481 PINCHOT DR.2P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2471 | -119.5538 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08221C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101117805 | RELW OH PRI CLR REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-01 | 2020-05-01 | 2020-09-04 | 2020-09-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117138291 | POLE_DECA_REPL - 54481 PINCHOT DR.2PE\1P | 35208931 |  |  | STS-POLE_DECA_REPL - 54481 PINCHOT DR.2P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2473 | -119.5538 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08221C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101117806 | RELW OH PRI CLR RESD REMT FIRE ESTR GO REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-01 | 2020-05-01 | 2020-09-04 | 2020-09-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117155628 | POLE_DECA_REPL - 56144 WILD PLUM LN 1PEN | 35215176 |  |  | STS-POLE_DECA_REPL - 56144 WILD PLUM LN | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2211 | -119.5238 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08224D | 10242 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101117872 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252521103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117156372 | POLE_DECA_REPL - 56144 WILD PLUM LN 2PE/ | 35209108 |  |  | STS-POLE_DECA_REPL - 56144 WILD PLUM LN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2217 | -119.5213 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08224D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 14.9 | 14.9 |  |  | 0 | 14.9 | 14.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101117878 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-14 | 2021-01-13 | COMP | 2021-01-13 | [16 empty] | 2019-05-03 | 2020-05-03 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 10042.98 | 87 | 87 | 87 | 87 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117156681 | POLE_DECA_REPL - CR200/MARANTHA 5PNNORTH | 35209118 |  |  | STS-POLE_DECA_REPL - CR200/MARANTHA 5PNN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2149 | -119.5212 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08224D | 55121 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101118161 | RELW OH PRI CLR RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117159557 | POLE_DECA_REPL - 56144 WILD PLUM LN 2PE/ | 35215234 |  |  | STS-POLE_DECA_REPL - 56144 WILD PLUM LN | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2215 | -119.5191 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08224D | 10242 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101117883 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252521103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117159568 | POLE_DECA_REPL - CR200/MARANTHA 1PE/2PN/ | 35209142 |  |  | STS-POLE_DECA_REPL - CR200/MARANTHA 1PE/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.213 | -119.5208 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08224D | 55121 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101118148 | RELW OH PRI CLR REMT ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2020-08-17 | 2020-08-17 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 1 | 205.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117160191 | POLE_BROK_REPL - CR200/CR221 1PNE NORTH | 35215243 |  |  | STS-POLE_BROK_REPL - CR200/CR221 1PNE NO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 37.2131 | -119.5527 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008224 | 10235 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101117714 | RELW OH PRI REMT FIRE ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252521103 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117160598 | POLE_DECA_REPL - 54792 KOWANA 2PE/6PN/ 1 | 35209155 |  |  | STS-POLE_DECA_REPL - 54792 KOWANA 2PE/6P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2258 | -119.544 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008224 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101117261 | RELW OH SERV CLR JPOL REMT FIRE ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2020-10-05 | 2020-10-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117160758 | POLE_DECA_REPL - 56432 PRIEST RD 2PE/2PN | 35215254 |  |  | STS-POLE_DECA_REPL - 56432 PRIEST RD 2PE | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2258 | -119.5185 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08224D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101118226 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252521103 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117160819 | POLE_DECA_REPL - 32040 RD221 3PW/1PNNORT | 35209166 |  |  | STS-POLE_DECA_REPL - 32040 RD221 3PW/1PN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 37.2138 | -119.556 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008224 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101117318 | RELW OH PRI REMT FIRE ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 1 | 94.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117161201 | POLE_DECA_REPL - 56432 PRIEST RD 2PE/1PN | 35215259 |  |  | STS-POLE_DECA_REPL - 56432 PRIEST RD 2PE | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2251 | -119.5186 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08224D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101118225 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252521103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117161254 | POLE_DECA_REPL - 54792 KOWANA 2PE/13PN O | 35209190 |  |  | STS-POLE_DECA_REPL - 54792 KOWANA 2PE/13 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 37.226 | -119.5417 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008224 | 19102 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.8 | 37.8 |  |  | 0 | 37.8 | 37.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103086583 | RELW OH PRI CLR JPOL REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-12 | 2021-02-11 | COMP | 2021-02-11 | [16 empty] | 2019-05-04 | 2020-05-04 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 16750.1 | 304.9 | 291.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117162997 | POLE_DECA_REPL - 32221 CR221 2PS NORTH F | 35209239 |  |  | STS-POLE_DECA_REPL - 32221 CR221 2PS NOR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2148 | -119.5523 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008224 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.6 | 23.6 |  |  | 0 | 23.6 | 23.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101117711 | PRI RELW OH CLR REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-04 |  | COMP | 2021-02-04 | [16 empty] | 2019-05-05 | 2020-01-27 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 14007.16 | 13.5 | 0 | 851 | 851 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117163165 | POLE_DECA_REPL - 32221 CR221 1PSNORTH FO | 35209248 |  |  | STS-POLE_DECA_REPL - 32221 CR221 1PSNORT | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2159 | -119.552 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008224 | 10320 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101117704 | RELW OH PRI CLR REMT FIRE ESTR REAR USA FMOB FSRP TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-05 | 2020-05-05 | 2020-12-06 | 2020-12-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 1 | 217.2 | 217.2 | 217.2 | 217.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117163273 | POLE_DECA_REPL - 33360 RD2217 1PS/2PW/11 | 35215279 |  |  | STS-POLE_DECA_REPL - 33360 RD2217 1PS/2P | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2224 | -119.551 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008224 | 5731 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101117288 | OH RELW PRI CLR JPOL REMT FIRE ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252521103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117163445 | POLE_DECA_REPL - 33360 RD2217 1PS/2PW/17 | 35215288 |  |  | STS-POLE_DECA_REPL - 33360 RD2217 1PS/2P | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2169 | -119.5516 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008224 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101117310 | RELW OH SEC CLR RESD REMT FIRE ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252521103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117163467 | POLE_DECA_REPL - CR200/WILD PLUM 3PNNORT | 35209265 |  |  | STS-POLE_DECA_REPL - CR200/WILD PLUM 3PN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2198 | -119.5101 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08224D | 19817 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101118194 | RELW OH PRI CLR REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-05 | 2020-05-05 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117164196 | POLE_DECA_REPL - CR200/WILD PLUM 6PN/1PW | 35215298 |  |  | STS-POLE_DECA_REPL - CR200/WILD PLUM 6PN | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2208 | -119.5126 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08224D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101118205 | RELW OH PRI CLR RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252521103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117164443 | POLE_DECA_REPL - 53647 RD 200\1PWNORTH F | 35215313 |  |  | STS-POLE_DECA_REPL - 53647 RD 200\1PWNOR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2084 | -119.5702 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008226 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101054337 | OH PRI JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252521103 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117164448 | POLE_DECA_REPL - C\O RD 200\QUAIL CREEK | 35215318 |  |  | STS-POLE_DECA_REPL - C\O RD 200\QUAIL CR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2064 | -119.5714 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008226 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101054384 | RELW OH PRI JPOL RESD REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 252521103 | 1 | 13.5 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117164667 | POLE_DECA_REPL - C\O RD 200\QUAIL CREEK | 35215328 |  |  | STS-POLE_DECA_REPL - C\O RD 200\QUAIL CR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2059 | -119.5729 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008226 | 5596 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101054398 | RELW OH PRI CLR ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252521103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117170389 | POLE_DECA_REPL - 31982 HADLEY RDNORTH FO | 35215347 |  |  | STS-POLE_DECA_REPL - 31982 HADLEY RDNORT | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2124 | -119.5659 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008223 | 5596 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101054056 | RELW OH PRI CLR RESD ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-06 | 2020-05-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252521103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117171745 | POLE_BROK_REPL - CR200/MOUNTAIN LN 1PN N | 35215351 |  |  | STS-POLE_BROK_REPL - CR200/MOUNTAIN LN 1 | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2112 | -119.5601 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B | 5596 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052406 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-06 | 2020-05-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252521103 | 1 | 87 | 87 | 87 | 87 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117177701 | POLE_DECA_REPL - 54565 RIDGEWAY NORTH FO | 35209425 |  |  | STS-POLE_DECA_REPL - 54565 RIDGEWAY NORT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2032 | -119.5527 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B | 5596 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102317454 | RELW OH SERV NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2020-05-07 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117179102 | COND_BROK_REPL - 54280 PINE TREE 3PE/2PN | 35100810 |  |  | STS-COND_BROK_REPL - 54280 PINE TREE 3PE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2057 | -119.5548 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.2 | 15.2 |  |  | 0 | 15.2 | 15.2 |  |  | EC | E | Conductor | Broken/Damaged | Replace |  | 101052388 | RELW OH SERV FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-11-23 |  | COMP | 2020-11-23 | [16 empty] | 2019-05-07 | 2020-05-07 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 9881.93 |  | -362 | -271.5 | -271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117185912 | POLE_DECA_REPL - CR200/CR221 3PSW/1PW NO | 35100819 |  |  | STS-POLE_DECA_REPL - CR200/CR221 3PSW/1P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2108 | -119.5567 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B | 5596 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052145 | RELW OH PRI NOAC ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117210582 | POLE_DECA_REPL - CR200/ROCKY RD 8PN/2PWN | 35209667 |  |  | STS-POLE_DECA_REPL - CR200/ROCKY RD 8PN/ | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2124 | -119.54 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 14 | 14 |  |  | 0 | 14 | 14 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052891 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2019-05-10 | 2020-05-10 | 2020-09-12 | 2020-09-12 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 9423.04 | 131.6 | 118.2 | 798.6 | 798.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117210871 | POLE_BROK_REPL - 32040 RD221 4PW/2PS NOR | 35214652 |  |  | STS-POLE_BROK_REPL - 32040 RD221 4PW/2PS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2128 | -119.5571 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B | 81519 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052449 | RELW OH PRI NOAC ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252521103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117211130 | POLE_DECA_REPL - CR200/ROCKY RD 8PN/3PW | 35209672 |  |  | STS-POLE_DECA_REPL - CR200/ROCKY RD 8PN/ | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2124 | -119.5409 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B | 10619 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 47.6 | 47.6 |  |  | 0 | 47.6 | 47.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052893 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-22 |  | COMP | 2021-01-22 | [16 empty] | 2019-05-10 | 2020-05-10 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 25140.78 | 165.3 | 0 | 479.7 | 479.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117366727 | HARD_BROK_REPL - 34204 RD 223NORTH FORK9 | 35215847 |  |  | STS-HARD_BROK_REPL - 34204 RD 223NORTH F | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.245 | -119.5614 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08221C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Hardware/Framing | Broken/Damaged | Replace |  | 103225743 | RELW OH SEC REMT ESTR BTKA USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-31 | 2020-05-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252521103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | North Fork | Oakhurst |  |  | OPEN | 117692354 | OLE _ BROK _ REPL_RD 224/MOUNTAIN SPRIN | 35209516 |  |  | STS- OLE _ BROK _ REPL_RD 224/MOUNTAIN S | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2272 | -119.5237 |  | TIER 2 |  |  | 08224A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.3 | 17.3 |  |  | 0 | 17.3 | 17.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103340289 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-01-25 |  | COMP | 2021-01-25 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-10-27 | 2020-10-27 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 10039.31 |  | 0 | 244.5 | 244.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | COMP | 117208493 | POLE_DECA_REPL - R\O 54016 RD 200NORTH F | 35178989 |  |  |  | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-16 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.2091 | -119.5633 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B |  | Y | 311 |  |  | 2021-02-16 07:00 | 2021-02-16 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 42.7 | 42.7 |  |  | 1 | 41.7 | 41.7 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101054295 | RELW OH PRI COMP REMT ESTR BTKA CCNT FMOB TER2 PRTO FSRP | Pole | 2020-08-04 | 2020-08-04 | COMP | 2020-08-04 | COMP | 2021-02-16 | [13 empty] | 2021-02-18 | 2021-02-16 | 2020-05-10 | 2020-08-13 | 2020-08-13 | B-Tag Addition 06.24.20 |  | Bakersfield |  | 252521103 | 14136.27 | 6901.7 | -7051.6 | 8.1 | 8.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-06-29
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117137203 | POLE_DECA_REPL - FRONT OF 54912 PINCHOT | 35097514 |  |  | STS-POLE_DECA_REPL - FRONT OF 54912 PINC | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2516 | -119.5517 |  | TIER 2 | 388 | 25253-1102, SAN JOAQUIN #3 | 08221C | 5403 | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-04 16:00 | Dispatched | CLICK | [6 empty] | 27.9 | 27.9 |  |  | 2 | 26.9 | 26.9 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101117632 | RELW OH PRI CLR JPOL RESD FIRE ESTR BTKA FMOB PRTO TER2 | Pole | 2020-11-12 | 2020-11-12 | COMP | 2020-11-12 | [16 empty] | 2019-05-01 | 2019-11-01 | 2020-11-04 | 2020-11-04 | B tag clean up 9/5/2020 |  | Fresno |  | 252531102 | 12799.85 | 3144.5 | 3144.5 | 3151.9 | 3151.9 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-09-05
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117159714 | POLE_DECA_REPL - 54792 KOWANA 2PE/3PN ON | 35099900 |  |  | STS-POLE_DECA_REPL - 54792 KOWANA 2PE/3P | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2255 | -119.5469 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008224 | 19102 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50.9 | 50.3 | 0.6 |  | 0 | 50.9 | 50.3 | 0.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101117265 | RELW OH PRI CLR JPOL REMT FIRE ESTR BTKA USA PROG FMOB TER2 PRTO FSRP | Pole | 2020-12-08 | 2020-12-08 | COMP | 2020-12-08 | [16 empty] | 2019-05-04 | 2019-10-15 | 2020-09-05 | 2020-09-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 20803.13 |  | -271.5 | -271.5 | -271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117163243 | POLE_BROK_REPL - 32221 CR221 1PS/1PW NOR | 35209258 |  |  | STS-POLE_BROK_REPL - 32221 CR221 1PS/1PW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2161 | -119.5531 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008224 | 10320 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.2 | 38.2 |  |  | 0 | 38.2 | 38.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101117708 | RELW OH PRI CLR REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-18 | 2020-12-18 | COMP | 2020-12-18 | [16 empty] | 2019-05-05 | 2020-05-05 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 17656.16 | 1121.4 | 383.9 | -362 | -362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117163674 | POLE_DECA_REPL - 33360 RD2217 1PS/2PW/14 | 35181074 |  |  | STS-POLE_DECA_REPL - 33360 RD2217 1PS/2P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2193 | -119.5511 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008224 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.4 | 19.4 |  |  | 0 | 19.4 | 19.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101117302 | RELW OH PRI CLR JPOL REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-10-16 | 2020-10-16 | COMP | 2020-10-16 | [16 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | Fresno |  | 252521103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117178217 | POLE_DECA_REPL - 54366 RD 200 NORTH FORK | 35100809 |  |  | STS-POLE_DECA_REPL - 54366 RD 200 NORTH | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2087 | -119.5559 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.2 | 15.2 |  |  | 0 | 15.2 | 15.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103150204 | RELW OH SEC RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-11-23 | 2020-11-23 | COMP | 2020-11-23 | [16 empty] | 2019-05-07 | 2020-05-07 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 6858.35 |  | -362 | -271.5 | -271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117180373 | POLE_DECA_REPL - DUKE/HAZELWOOD 1PSWNORT | 35209455 |  |  | STS-POLE_DECA_REPL - DUKE/HAZELWOOD 1PSW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2088 | -119.561 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B | 5596 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 47 | 47 |  |  | 0 | 47 | 47 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052191 | RELW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 | 2021-01-28 | COMP | 2021-01-28 | [16 empty] | 2019-05-07 | 2020-05-07 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 18983.89 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117180701 | POLE_DECA_REPL - 33874 CR221 3PN/2PWNORT | 35209463 |  |  | STS-POLE_DECA_REPL - 33874 CR221 3PN/2PW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.24 | -119.5484 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08224B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 14 | 14 |  |  | 0 | 14 | 14 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101118332 | RELW OH PRI CLR JPOL REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-15 | 2020-12-15 | COMP | 2020-12-15 | [16 empty] | 2019-05-07 | 2020-05-07 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 13149.75 | 97.4 | -1230.8 | -687.8 | -687.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117185651 | POLE_DECA_REPL - CR200/CR221 3PSWNORTH F | 35209543 |  |  | STS-POLE_DECA_REPL - CR200/CR221 3PSWNOR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2101 | -119.5552 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.8 | 33.8 |  |  | 0 | 33.8 | 33.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052144 | RELW OH PRI NOAC ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 | 2020-12-11 | COMP | 2020-12-11 | [16 empty] | 2019-05-08 | 2020-05-08 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 12976.92 | 13.5 | -1267 | -814.5 | -814.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117188990 | POLE_DECA_REPL - CR200/CR221 4PSW/1PE/1P | 35099937 |  |  | STS-POLE_DECA_REPL - CR200/CR221 4PSW/1P | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2082 | -119.5553 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B | 5596 | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 34.3 | 34.3 |  |  | 0.5 | 33.8 | 33.8 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101052156 | RELW OH PRI NOAC ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-10-29 | 2020-11-08 | COMP | 2020-10-28 | [16 empty] | 2019-05-08 | 2019-11-08 | 2020-08-13 | 2020-08-13 | B-Tag Addition 06.24.20 |  | Concord |  | 252521103 | 12814.9 | 4662.8 | 4662.8 | 2764.3 | 2764.3 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-06-29
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117193374 | POLE_BROK_REPL - CR200/ROCKY RD 3PN/1PW | 35209617 |  |  | STS-POLE_BROK_REPL - CR200/ROCKY RD 3PN/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2092 | -119.5388 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B | 10235 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 60.1 | 60.1 |  |  | 0 | 60.1 | 60.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052855 | OH RELW PRI RESD ESTR BTKA USA PROG FMOB TER2 PRTO FSRP | Pole | 2021-01-29 | 2021-01-29 | COMP | 2021-01-29 | [16 empty] | 2019-05-09 | 2019-11-15 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 21833.7 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117210091 | POLE_DECA_REPL - R/O 58190 RD 225 #1 ENO | 35191634 |  |  | STS-POLE_DECA_REPL - R/O 58190 RD 225 #1 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2243 | -119.4898 |  | TIER 2 | 298 | 25253-1103, SAN JOAQUIN #3 | 08233C | 10458 | Y | 311 |  |  | 2021-02-20 07:00 | 2021-02-20 16:00 | Dispatched | CLICK | [6 empty] | 45.1 | 45.1 |  |  | 0 | 45.1 | 45.1 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101057821 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-12-10 | 2020-12-10 | COMP | 2020-12-10 | [16 empty] | 2019-05-10 | 2020-05-10 | 2020-10-31 | 2020-10-31 | B-tag addition 8/12/2020 |  | Fresno |  | 252531103 | 20869.01 | 137.6 | [7 empty] | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-08-18
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117213797 | POLE_DECA_REPL - R/O 58190 RD 225 #3 N O | 35154681 |  |  | STS-POLE_DECA_REPL - R/O 58190 RD 225 #3 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2247 | -119.4924 |  | TIER 2 | 298 | 25253-1103, SAN JOAQUIN #3 | 08233C | 10458 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.6 | 34.6 | 0 |  | 0 | 34.6 | 34.6 | 0 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101057825 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-05-18 | 2020-05-18 | COMP | 2020-05-18 | [16 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-12-31 | PIKEENG |  | 252531103 | 18177.83 | 294.5 |  |  |  | 294.5 |  | 294.5 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117214358 | POLE_BROK_REPL - 58258 RD 225/1PE NORTH | 35154689 |  |  | STS-POLE_BROK_REPL - 58258 RD 225/1PE NO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-05-11 |  | 37.2222 | -119.4883 |  | TIER 2 | 298 | 25253-1103, SAN JOAQUIN #3 | 08233C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 25 | 25 |  |  | 0 | 25 | 25 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057827 | RELW OH SEC FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-27 | 2020-10-27 | COMP | 2020-10-27 |  |  | 2020-04-22 | 2020-05-14 | [12 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | PIKEENG |  | 252531103 | 15529.01 | 1385.8 | -1400 | -1400 | -1400 | 310.3 |  | 310.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117217384 | POLE_DECA_REPL - A\F 34599 RD 236NORTH F | 35105906 |  |  | STS-POLE_DECA_REPL - A\F 34599 RD 236NOR | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2502 | -119.5661 |  | TIER 2 | 385 | 25443-2102, COARSEGOLD | 0000008222 |  | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 26.8 | 24.4 | 2.4 |  | 1 | 25.8 | 23.4 | 2.4 |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101051756 | RELW OH PRI REMT FIRE TRAF FLAG ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-11-20 | 2020-11-30 | COMP | 2020-11-20 |  |  | 2020-12-23 | 2020-12-23 | [12 empty] | 2019-05-12 | 2019-11-12 | 2020-09-30 | 2020-09-30 | B-tag addition 8/12/2020 | 2020-05-12 | Santa Rosa |  | 254432102 | 12882.31 | 2477.6 | 2070.9 | 1977.1 | 1977.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-08-18
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117217810 | POLE_BROK_REPL - 58288 RD 225/5PW NORTH | 35198153 |  |  | STS-POLE_BROK_REPL - 58288 RD 225/5PW NO | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2219 | -119.4931 |  | TIER 2 | 298 | 25253-1103, SAN JOAQUIN #3 | 08233C |  | Y | 311 |  |  | 2021-03-01 07:00 | 2021-03-01 16:00 | Dispatched | CLICK | [6 empty] | 19 | 19 |  |  | 2 | 18 | 18 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101057855 | RELW OH PRI NOAC ESTR USA FMOB TER2 PRTO | Pole | 2020-11-02 | 2020-11-07 | COMP | 2020-11-02 | [16 empty] | 2019-05-12 | 2020-05-12 | 2020-11-03 | 2020-11-03 | B tag clean up 9/5/2020 |  | Fresno |  | 252531103 | 16582.55 | 1884 | 1756.4 | 1762.7 | 1762.7 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-09-05
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117222974 | POLE_DECA_REPL - 58296 RD 225 #2 N #2 WN | 35198764 |  |  | STS-POLE_DECA_REPL - 58296 RD 225 #2 N # | CONS | CONS ERDY SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2176 | -119.4885 |  | TIER 2 | 298 | 25253-1103, SAN JOAQUIN #3 | 08233C | 10458 | Y | 311 |  |  |  |  | Returned | Order Operation | [6 empty] | 46.9 | 46.9 |  |  | 4 | 45.9 | 45.9 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101057868 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-13 | 2020-10-13 | COMP | 2020-10-13 | [16 empty] | 2019-05-13 | 2020-05-13 | 2020-11-03 | 2020-11-03 | B tag clean up 9/5/2020 |  | Fresno |  | 252531103 | 16906.96 | 6166.1 | 6108.1 | 4431.3 | 4431.3 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-09-05
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117277052 | POLE_DECA_REPL - MILLVIEW MT. CT.\RD222\ | 35191637 |  |  | STS-POLE_DECA_REPL - MILLVIEW MT. CT.\RD | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2194 | -119.5071 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08233C |  | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 28.9 | 28.9 |  |  | 0 | 28.9 | 28.9 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101059749 | RELW OH SEC ESTR USA FMOB TER2 PRTO | Pole | 2020-12-01 | 2020-12-04 | COMP | 2020-12-01 | [16 empty] | 2019-05-20 | 2020-05-20 | 2020-11-01 | 2020-11-01 | B-tag addition 8/12/2020 | 2020-05-20 | Santa Rosa |  | 252521103 | 21232.41 | 3855.9 | [7 empty] | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-08-18
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117320264 | TREE_DECA_INPL - HARD TIMES RANCHNORTH F | 35209700 |  |  | STS-TREE_DECA_INPL - HARD TIMES RANCHNOR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2376 | -119.5344 |  | TIER 2 | 298 | 25253-1103, SAN JOAQUIN #3 | 08224A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.5 | 12.5 |  |  | 0 | 12.5 | 12.5 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103214071 | RELW OH SERV ESTR GO BTKA USA TER2 FSRP FMOB PRTO | Pole | 2021-01-29 | 2021-01-29 | COMP | 2021-01-29 | [16 empty] | 2019-05-25 | 2020-05-25 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252531103 | 6726.89 | 53.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | North Fork | Oakhurst |  |  | OPEN | 117692356 | POLE _ BROK _ REPL_33939 RD 224 @ HSE RO | 35209521 |  |  | STS-POLE _ BROK _ REPL_33939 RD 224 @ HS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2413 | -119.5262 |  | TIER 2 |  |  | 08224A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.3 | 12.3 |  |  | 0 | 12.3 | 12.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103340294 | RELW TER2 OH PRI ESTR PRTO FSRP | Pole | 2020-12-14 | 2020-12-14 | COMP | 2020-12-14 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 5954.98 | 40.4 | -1013.6 | -470.6 | -470.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | North Fork | Oakhurst |  |  | OPEN | 119858679 | POLE_BROK_REPL - REAR OF 34426RD.222Nort | 35205414 |  |  | STS-POLE_BROK_REPL - REAR OF 34426RD.222 | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-12-09 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2474 | -119.5213 |  | TIER 2 | 298 | 25253-1103, SAN JOAQUIN #3 | 0000008221 | 6094 | Y | 311 |  |  | 2021-02-19 07:00 | 2021-02-19 16:00 | Dispatched | CLICK | [6 empty] | 40.2 | 40.2 |  |  | 0 | 40.2 | 40.2 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101118377 | RELW CLR OH SEC CREW FIRE NOAC ESTR USA FMOB TER2 | Pole | 2020-10-17 | 2020-10-17 | COMP | 2020-10-17 | [16 empty] | 2020-10-06 | 2021-01-06 |  | 2021-01-06 | B tag clean up 10/11/2020 |  | Fresno |  | 252531103 | 12123.76 | 13.5 | [7 empty] | N | 11/2 in MPP Import File | N |  | Y | 2020-10-11
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117161266 | POLE_DECA_REPL - 56654 ROAD 200, NORTH F | 35209195 |  |  | STS-POLE_DECA_REPL - 56654 ROAD 200, NOR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2145 | -119.5144 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08224D |  | Y | 311 |  |  | 2021-03-09 07:00 | 2021-03-09 15:00 | Scheduled | CLICK | [6 empty] | 0.8 | 0.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103208542 | RELW OH SERV NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-14 | 2021-01-14 | COMP | 2021-01-14 | [16 empty] | 2019-05-04 | 2020-05-04 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 3109.34 | 13.5 | 0 | 448.2 | 448.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117170471 | POLE_DECA_REPL - CR200/MOUNTAIN LN 2PN N | 35100805 |  |  | STS-POLE_DECA_REPL - CR200/MOUNTAIN LN 2 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2124 | -119.5595 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B | 5596 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43.9 | 43.9 | 0 |  | 0 | 43.9 | 43.9 | 0 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052407 | RELW OH PRI RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-01-20 | COMP | 2021-01-20 | [16 empty] | 2019-05-06 | 2020-05-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252521103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117177823 | POLE_BROK_REPL - 33874 CR221 3PN/6PW NOR | 35209430 |  |  | STS-POLE_BROK_REPL - 33874 CR221 3PN/6PW | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.24 | -119.5518 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08224B | 10236 | Y | 311 |  |  |  |  | Scheduled | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 41.1 | 41.1 |  |  | 0 | 41.1 | 41.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101117697 | RELW OH PRI REMT FIRE ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-22 | 2021-01-22 | COMP | 2021-01-22 | [16 empty] | 2019-05-07 | 2020-05-07 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 16832.41 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117194702 | POLE_BROK_REPL - CR200/ROCKY RD 4PN/1PW | 35209622 |  |  | STS-POLE_BROK_REPL - CR200/ROCKY RD 4PN/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2099 | -119.5385 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 9.7 | 9.7 |  |  | 0 | 9.7 | 9.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052866 | RELW OH SEC REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-15 | 2021-01-15 | COMP | 2021-01-15 | [16 empty] | 2019-05-09 | 2020-05-09 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 6124.17 | 53.8 | 0 | 851 | 851 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117299258 | POLE_LEAN_REPL - R\O 34528 RD 236\8PSWNO | 35154244 |  |  | STS-POLE_LEAN_REPL - R\O 34528 RD 236\8P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2465 | -119.5719 |  | TIER 2 | 385 | 25443-2102, COARSEGOLD | 0000008222 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 11.2 | 11.2 |  |  | 0 | 11.2 | 11.2 |  |  | EC | E | Pole | Leaning | Replace |  | 101053679 | RELW OH PRI CLR JPOL REMT FIRE ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-05-23 | 2021-01-23 | COMP | 2020-05-12 |  |  | 2021-01-23 | 2021-01-23 | [12 empty] | 2019-05-22 | 2020-05-22 |  | 2020-05-22 | 2021 CBP Plan | 2020-05-01 | PIKEENG |  | 254432102 | 6695.68 | 344.8 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | COMP | 117218023 | POLE_DECA_REPL - 58288 RD 225 #4 W #3 WN | 35198679 |  |  | STS-POLE_DECA_REPL - 58288 RD 225 #4 W # | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-10-06 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.2213 | -119.4956 |  | TIER 2 | 298 | 25253-1103, SAN JOAQUIN #3 | 08233C | 10367 | Y | 311 |  |  | 2021-01-12 | 2021-01-12 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 50 | 50 |  |  | 63 | 0 |  |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101057854 | RELW OH PRI COMP CLR ESTR BTKA USA CPGG FMOB TER2 PRTO | Pole | 2020-11-06 | 2020-11-12 | COMP | 2020-11-05 | COMP | 2020-12-12 | [13 empty] | 2021-01-13 | 2021-01-12 | 2020-05-12 | 2020-11-03 | 2020-11-03 | B tag clean up 9/5/2020 |  | Fresno |  | 252531103 | 17249.47 | 21543.4 | 17965.6 | 17965.6 | 17965.6 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-09-05
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117156035 | POLE_DECA_REPL - 31040 WYLE RANCH WY 3PW | 35209098 |  |  | STS-POLE_DECA_REPL - 31040 WYLE RANCH WY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1985 | -119.545 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B | 5503 | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052758 | RELW OH SEC REMT NOAC ESTR GO FMOB TER2 PRTO FSRP | Pole | 2020-12-02 | 2020-12-02 | COMP | 2020-12-02 | [16 empty] | 2019-05-03 | 2020-05-03 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 32954.79 | 53.8 | -859.8 | -226.3 | -226.3 |  |  |  | FRMMA/WMPMA - Electric | Y | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117160732 | POLE_BROK_REPL - 32040 RD221 3PW NORTH F | 35209160 |  |  | STS-POLE_BROK_REPL - 32040 RD221 3PW NOR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2133 | -119.5562 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008224 |  | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101117315 | RELW OH PRI REMT FIRE ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-28 | 2020-12-28 | COMP | 2020-12-28 | [16 empty] | 2019-05-04 | 2020-05-04 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 8997.37 | 1121.4 | 1107.9 | 362 | 362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117162078 | POLE_DECA_REPL - 33360 RD2217 1PS/2PW/9P | 35209225 |  |  | STS-POLE_DECA_REPL - 33360 RD2217 1PS/2P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2246 | -119.5518 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008224 |  | Y | 311 |  |  | 2021-06-25 07:00 | 2021-06-25 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101117284 | RELW OH PRI CLR JPOL REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-30 | 2021-01-05 | COMP | 2020-12-29 | [16 empty] | 2019-05-04 | 2020-05-04 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 7259.41 | 930.1 | 930.1 | 271.5 | 271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117178461 | POLE_DECA_REPL - 53732 RD 200\2PWNORTH F | 35209442 |  |  | STS-POLE_DECA_REPL - 53732 RD 200\2PWNOR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2074 | -119.5682 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008226 | 5596 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 35 | 35 |  |  | 0 | 35 | 35 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101054326 | RELW CLR OH PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-07 | 2021-01-07 | COMP | 2021-01-06 | [16 empty] | 2019-05-07 | 2020-05-07 | 2020-11-21 | 2020-11-21 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 15679.18 | 13.5 | 0 | 489 | 489 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117189002 | POLE_DECA_REPL - 31105 WYLE RANCH WY 2PN | 35215496 |  |  | STS-POLE_DECA_REPL - 31105 WYLE RANCH WY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2001 | -119.542 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B |  | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Reserved | CLICK | [6 empty] | 12.2 | 12.2 |  |  | 0 | 12.2 | 12.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103086967 | OH REMT RELW SEC RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-16 | 2021-02-16 | COMP | 2021-02-16 | [16 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252521103 | 3888.26 | 13.5 | 0 | 978 | 978 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117191861 | POLE_BROK_REPL - 31419 WYLE RANCH RDNORT | 35209602 |  |  | STS-POLE_BROK_REPL - 31419 WYLE RANCH RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2039 | -119.5428 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B | 5503 | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052581 | RELW OH PRI REMT SWRK ESTR GO BTKA USA PROG FMOB TER2 PRTO FSRP | Pole | 2021-01-06 | 2021-01-06 | COMP | 2021-01-06 | [16 empty] | 2019-05-09 | 2020-05-09 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 15913.52 | 13.5 | 0 | 489 | 489 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117192727 | POLE_DECA_REPL - CR200/OAK JUNCTION 12PE | 35209612 |  |  | STS-POLE_DECA_REPL - CR200/OAK JUNCTION | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2083 | -119.541 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B |  | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052573 | RELW OH PRI RESD REMT TER2 ESTR BTKA FMOB PRTO FSRP | Pole | 2020-12-29 | 2020-12-29 | COMP | 2020-12-29 | [16 empty] | 2019-05-09 | 2020-05-09 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 15222.99 | 1107.9 | 1107.9 | 362 | 362 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117196374 | POLE_BROK_REPL - CR200/ROCKY RD 5PN/1PNE | 35209640 |  |  | STS-POLE_BROK_REPL - CR200/ROCKY RD 5PN/ | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.211 | -119.5376 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B | 59879 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.6 | 40.6 |  |  | 0 | 40.6 | 40.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052876 | RELW OH PRI REMT ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-29 | 2021-01-08 | COMP | 2020-12-28 | [16 empty] | 2019-05-09 | 2020-05-09 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 18293.57 | 13.5 | 0 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117196460 | POLE_DECA_REPL - 31867 ROCKY RD. NORTH F | 35209650 |  |  | STS-POLE_DECA_REPL - 31867 ROCKY RD. NOR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2104 | -119.5381 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 08225B |  | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052872 | RELW OH PRI CLR REMT NOAC SWRK ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-28 | 2020-12-28 | COMP | 2020-12-28 | [16 empty] | 2019-05-09 | 2020-05-09 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 13609.37 | 151.9 | 0 | 633.5 | 633.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | NORTH FORK | Oakhurst |  |  | OPEN | 117325137 | POLE_DECA_REPL - 33249 CR224 4PN/12PNE/4 | 35209751 |  |  | STS-POLE_DECA_REPL - 33249 CR224 4PN/12P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2411 | -119.5201 |  | TIER 2 | 298 | 25253-1103, SAN JOAQUIN #3 | 08224A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.8 | 17.8 |  |  | 0 | 17.8 | 17.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101118254 | RELW OH PRI NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-04 | 2021-01-04 | COMP | 2021-01-04 | [16 empty] | 2019-05-27 | 2020-05-27 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252531103 | 7636.23 | 13.5 | 0 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 116883666 | POLE_DECA_REPL - 47186 RD.200O NEALS9364 | 35209675 |  |  | STS-POLE_DECA_REPL - 47186 RD.200O NEALS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1293 | -119.6906 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000009213 | 5369 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101062651 | RELW OH PRI CLR JPOL REMT ESTR BTKA USA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-01 | 2020-04-01 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432103 | 1 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 116954886 | POLE_BROK_REPL - 49896 RD200 O NEALS | 35208824 |  |  | STS-POLE_BROK_REPL - 49896 RD200 O NEALS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1592 | -119.6448 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000009211 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.7 | 24.7 |  |  | 0 | 24.7 | 24.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101062389 | RELW OH PRI FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-06 |  | COMP | 2021-01-06 | [16 empty] | 2019-04-04 | 2020-04-04 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 10119.59 | 53.8 | 0 | 606.5 | 606.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 116954947 | POLE_BROK_REPL - 48092 LILLY MINE WAY/3P | 35107152 |  |  | STS-POLE_BROK_REPL - 48092 LILLY MINE WA | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1384 | -119.6749 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 0000009214 | 5369 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101062772 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-04 | 2019-10-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | Fresno |  | 254432103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 116964124 | POLE_DECA_REPL - 49201 RD200 O NEALS | 35085461 |  |  | STS-POLE_DECA_REPL - 49201 RD200 O NEALS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 37.1538 | -119.6537 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000009214 | 5324 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101062852 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-05 | 2020-04-05 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 1 | 41.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 116967068 | POLE_DECA_REPL - 49376 HOUSE RANCH RD/1P | 35214711 |  |  | STS-POLE_DECA_REPL - 49376 HOUSE RANCH R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1668 | -119.6528 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000009211 | 10599 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101062452 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-05 | 2020-04-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252521103 | 1 | 225.2 | 211.7 | 211.7 | 211.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 117031512 | POLE_BROK_REPL - 50998 RD210/12PE/14PN/6 | 35209461 |  |  | STS-POLE_BROK_REPL - 50998 RD210/12PE/14 | APPR | APPR | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1106 | -119.5775 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009226 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101063672 | OH PRI REMT FIRE ESTR BTKA FMOB RELW USA PROG TER2 PRTO FSRP | Pole |  |  | INPR | [17 empty] | 2019-04-15 | 2020-04-15 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252561101 | 1 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 117032987 | POLE_BROK_REPL - 50998 RD210/12PE/14PN/9 | 35209501 |  |  | STS-POLE_BROK_REPL - 50998 RD210/12PE/14 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1026 | -119.5722 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009226 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101063639 | RELW OH PRI REMT FIRE ESTR USA FMOB FSRP TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2020-11-07 | 2020-11-07 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252561101 | 1 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 117035628 | POLE_BROK_REPL - 50998 RD210/12PE/14PN/6 | 35209534 |  |  | STS-POLE_BROK_REPL - 50998 RD210/12PE/14 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1134 | -119.5815 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009226 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.2 | 19.2 |  |  | 0 | 19.2 | 19.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101063680 | RELW OH PRI REMT FIRE ESTR USA FMOB TER2 FSRP PRTO | Pole | 2021-02-11 | 2021-02-11 | COMP | 2021-02-11 | [16 empty] | 2019-04-15 | 2020-04-15 | 2020-11-07 | 2020-11-07 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252561101 | 8550.84 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 117047004 | POLE_BROK_REPL - 51525 LONG GOLD RD/7PW | 35209549 |  |  | STS-POLE_BROK_REPL - 51525 LONG GOLD RD/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1135 | -119.6189 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009226 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103088199 | OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2020-09-06 | 2020-09-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252561101 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 117171604 | POLE_BROK_REPL - R\O 34528 RD 236\43PSW | 35209347 |  |  | STS-POLE_BROK_REPL - R\O 34528 RD 236\43 | APPR | APPR | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2348 | -119.6073 |  | TIER 2 | 385 | 25443-2102, COARSEGOLD | 0000008223 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101053722 | RELW OH ESTR PRI REMT BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | INPR | [17 empty] | 2019-05-06 | 2020-05-06 | 2020-09-04 | 2020-09-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432102 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | COMP | 117047764 | POLE_BROK_REPL - 50998 RD210/12PE/14PN/6 | 35177968 |  |  |  | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-10 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.1287 | -119.6006 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009223 | 10233 | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101063603 | RELW OH COMP ESTR PRI REMT NOAC REAR CCNT FMOB TER2 PRTO FSRP | Pole | 2020-08-24 | 2020-08-24 | COMP | 2020-08-24 | COMP | 2021-02-17 | [13 empty] | 2021-02-19 | 2021-02-17 | 2020-04-17 | 2020-08-07 | 2020-08-07 | B-Tag Addition 06.24.20 |  | Concord |  | 252561101 | 35064.55 | 4020.2 | [7 empty] | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-06-29
Bay/Central | YO | O NEALS | Oakhurst |  |  | COMP | 117048479 | POLE_BROK_REPL - 50998 RD210 12PE 14PN 6 | 35177970 |  |  |  | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-10 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.128 | -119.5976 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009223 |  | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101063599 | RELW OH PRI COMP REMT SPCR ESTR BTKA REAR USA CCNT FMOB TER2 PRTO FSRP | Pole | 2020-06-10 | 2020-06-29 | COMP | 2020-06-10 | COMP | 2021-02-17 | [13 empty] | 2021-02-19 | 2021-02-17 | 2020-04-17 | 2020-08-07 | 2020-08-07 | Work Plan Reconcilation (B-Tags) |  | Concord |  | 252561101 | 10096.78 | 1306 | 8.1 | 8.1 | 8.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-07-21
Bay/Central | YO | O NEALS | Oakhurst |  |  | COMP | 117048693 | POLE_BROK_REPL - 50998 RD210/12PE/14PN/6 | 35177971 |  |  |  | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-10 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.1265 | -119.5958 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009223 |  | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101063598 | RELW OH PRI COMP REMT SPCR ESTR BTKA REAR CCNT FMOB TER2 PRTO FSRP | Pole | 2020-06-04 | 2020-06-04 | COMP | 2020-06-04 | COMP | 2021-02-17 | [13 empty] | 2021-02-19 | 2021-02-17 | 2020-04-17 | 2020-08-07 | 2020-08-07 | B-Tag Clean Up 6/8/2020 |  | Concord |  | 252561101 | 10096.78 | 1250.1 | [7 empty] | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-06-08
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 116961327 | POLE_DECA_REPL - 50640 RD200/4PS O NEALS | 35214702 |  |  | STS-POLE_DECA_REPL - 50640 RD200/4PS O N | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1758 | -119.6301 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000009211 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.3 | 21.3 |  |  | 0 | 21.3 | 21.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101062534 | RELW OH PRI ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2021-01-29 | 2021-01-29 | COMP | 2021-01-29 | [16 empty] | 2019-04-05 | 2020-04-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252521103 | 15637.17 | 94.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 116964049 | POLE_DECA_REPL - 48957 RANCH HOUSE RDO N | 35214706 |  |  | STS-POLE_DECA_REPL - 48957 RANCH HOUSE R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1717 | -119.6511 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000009211 | 10599 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29 | 29 |  |  | 0 | 29 | 29 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101062447 | RELW BTKA OH PRI ESTR USA PROG FMOB TER2 PRTO FSRP | Pole | 2021-01-26 | 2021-01-26 | COMP | 2021-01-26 | [16 empty] | 2019-04-05 | 2020-04-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252521103 | 14741.71 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 117034981 | POLE_BROK_REPL - 50998 RD210/12PE/14PN/6 | 35209523 |  |  | STS-POLE_BROK_REPL - 50998 RD210/12PE/14 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1111 | -119.5782 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009226 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.1 | 21.1 |  |  | 0 | 21.1 | 21.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101063674 | RELW OH PRI REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-11 | 2021-02-11 | COMP | 2021-02-11 | [16 empty] | 2019-04-15 | 2020-04-15 | 2020-10-07 | 2020-10-07 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252561101 | 9161.76 | 60.2 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 117035461 | POLE_BROK_REPL - 50998 RD210/12PE/14PN/6 | 35209529 |  |  | STS-POLE_BROK_REPL - 50998 RD210/12PE/14 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1173 | -119.5872 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009226 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.4 | 16.4 |  |  | 0 | 16.4 | 16.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101063690 | RELW OH PRI REMT NOAC CUSI SPCR ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-11 | 2021-02-11 | COMP | 2021-02-11 | [16 empty] | 2019-04-15 | 2020-04-15 | 2020-11-07 | 2020-11-07 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252561101 | 7287.2 | 211.4 | 198 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 117035504 | POLE_BROK_REPL - 50998 RD210/12PE/14PN/6 | 35177966 |  |  | STS-POLE_BROK_REPL - 50998 RD210/12PE/14 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1121 | -119.5797 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009226 |  | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101063678 | RELW OH PRI REMT FIRE ESTR FMOB TER2 PRTO FSRP | Pole | 2020-06-11 | 2020-06-13 | COMP | 2020-06-11 | [16 empty] | 2019-04-15 | 2020-04-15 | 2020-08-07 | 2020-08-07 | B-Tag Addition 07.06.2020 |  | Bakersfield |  | 252561101 | 13614.9 | 2117.2 | [7 empty] | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-07-06
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 117047086 | POLE_DECA_REPL - 50998 RD210/12PE/14PN/6 | 35177967 |  |  | B STS-POLE_DECA_REPL - 50998 RD210/12PE/ | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1193 | -119.591 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009226 |  | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 18 | 18 |  |  | 0 | 18 | 18 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101063698 | RELW OH REMT SERV CLR JPOL FIRE ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-06-18 | 2020-06-18 | COMP | 2020-06-18 | [16 empty] | 2019-04-17 | 2020-04-17 | 2020-08-07 | 2020-08-07 | B-Tag Addition 06.24.20 |  | Bakersfield |  | 252561101 | 5304.02 | 637 | [7 empty] | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-06-29
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 117048223 | POLE_DECA_REPL - 50998 RD210/12PE/14PN/6 | 35177969 |  |  | STS-POLE_DECA_REPL - 50998 RD210/12PE/14 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.12 | -119.5918 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009226 |  | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Dispatched | CLICK | [6 empty] | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101063699 | RELW OH PRI CLR JPOL REMT FIRE NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-06-11 | 2020-06-14 | COMP | 2020-06-11 | [16 empty] | 2019-04-17 | 2020-04-17 | 2020-08-07 | 2020-08-07 | Per DOT Approved Request |  | Bakersfield |  | 252561101 | 17964.02 | 2203.5 | 8.1 | 8.1 | 8.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-07-12
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 117170865 | POLE_BROK_REPL - R\O 34528 RD 236\31PSW | 35209335 |  |  | STS-POLE_BROK_REPL - R\O 34528 RD 236\31 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2376 | -119.5959 |  | TIER 2 | 385 | 25443-2102, COARSEGOLD | 0000008223 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.2 | 15.2 |  |  | 0 | 15.2 | 15.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101053739 | OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP RELW | Pole | 2021-02-09 | 2021-02-09 | COMP | 2021-02-09 | [16 empty] | 2019-05-06 | 2020-05-06 | 2020-09-04 | 2020-09-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432102 | 7016.11 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 117171613 | POLE_DECA_REPL - R\O 34528 RD 236\42PSWO | 35209351 |  |  | STS-POLE_DECA_REPL - R\O 34528 RD 236\42 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2349 | -119.6066 |  | TIER 2 | 385 | 25443-2102, COARSEGOLD | 0000008223 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14 | 14 |  |  | 0 | 14 | 14 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101053724 | RELW OH PRI REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-09 | 2021-02-09 | COMP | 2021-02-09 | [16 empty] | 2019-05-06 | 2020-05-06 | 2020-09-04 | 2020-09-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432102 | 5073.43 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 117177050 | POLE_BROK_REPL - 32161 HADLEY RD 3PN/1PE | 35215406 |  |  | STS-POLE_BROK_REPL - 32161 HADLEY RD 3PN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2157 | -119.5693 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008223 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.6 | 17.6 |  |  | 0 | 17.6 | 17.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101054085 | RELW OH PRI REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-29 | 2021-01-29 | COMP | 2021-01-29 | [16 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252521103 | 16399.96 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 117293263 | POLE_DECA_REPL - CHURCH RANCH RD/RD 2OO | 35209474 |  |  | STS-POLE_DECA_REPL - CHURCH RANCH RD/RD | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1902 | -119.6201 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008215 | 5324 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 43.5 | 43.5 |  |  | 0 | 43.5 | 43.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101055506 | RELW OH PRI CLR JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-27 | 2021-01-28 | COMP | 2021-01-27 | [16 empty] | 2019-05-21 | 2020-05-21 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 16483.25 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 116957148 | POLE_BROK_REPL - 50640 RD200 2.5 MILES S | 35208850 |  |  | STS-POLE_BROK_REPL - 50640 RD200 2.5 MIL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1651 | -119.6383 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000009211 |  | Y | 311 |  |  | 2021-06-25 07:00 | 2021-06-25 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101062503 | RELW OH PRI NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-31 | 2020-12-31 | COMP | 2020-12-31 | [16 empty] | 2019-04-04 | 2020-04-04 | 2020-11-20 | 2020-11-20 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 9407.35 | 53.8 | 0 | 606.5 | 606.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 116964628 | POLE_DECA_REPL - 49151 RANCH HOUSE RD/2P | 35208870 |  |  | STS-POLE_DECA_REPL - 49151 RANCH HOUSE R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1691 | -119.6514 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000009211 |  | Y | 311 |  |  | 2021-06-25 07:00 | 2021-06-25 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101062443 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-06 | 2021-01-06 | COMP | 2021-01-06 | [16 empty] | 2019-04-05 | 2020-04-05 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 8642.71 | 53.8 | 0 | 570.5 | 570.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | O NEALS | Oakhurst |  |  | OPEN | 117293061 | POLE_BROK_REPL - CHURCH RANCH RD/RD 2OO | 35209460 |  |  | STS-POLE_BROK_REPL - CHURCH RANCH RD/RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1916 | -119.6189 |  | TIER 2 | 764 | 25252-1103, SAN JOAQUIN #2 | 0000008215 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.9 | 14.9 |  |  | 0 | 14.9 | 14.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101055514 | RELW OH PRI REMT SWRK ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-04 | 2021-01-04 | COMP | 2021-01-04 | [16 empty] | 2019-05-21 | 2020-05-21 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252521103 | 4965.04 | 13.5 | 0 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 116813694 | POLE_BROK_REPL - R/O 37999 RD 600/2PNE/2 | 35215489 |  |  | STS-POLE_BROK_REPL - R/O 37999 RD 600/2P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.3003 | -119.7644 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000007205 | 5674 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101025159 | RELW OH PRI JPOL REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 116954179 | POLE_DECA_REPL - 40814 HWY 49OAKHURST936 | 35208814 |  |  | STS-POLE_DECA_REPL - 40814 HWY 49OAKHURS | APPR | APPR ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.3416 | -119.7021 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000721082 | 5490 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101025736 | RELW OH SEC INSP RESD FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | INPR | [17 empty] | 2019-04-04 | 2020-04-04 | 2020-07-30 | 2020-07-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254421101 | 1 | 89.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 116990973 | POLE_DECA_REPL - SW C/O BOLLINGER PLACE/ | 35086229 |  |  | STS-POLE_DECA_REPL - SW C/O BOLLINGER PL | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land Enviro |  |  | 37.338 | -119.6703 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000721103 | 19083 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101025549 | RELW OH PRI INSP CLR JPOL COMM FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-09 | 2020-04-09 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254421101 | 1 | 304.2 | 304.2 | 304.2 | 304.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117171597 | POLE_BROK_REPL - R\O 34528 RD 236\24PSWO | 35209340 |  |  | STS-POLE_BROK_REPL - R\O 34528 RD 236\24 | APPR | APPR | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.239 | -119.5904 |  | TIER 2 | 385 | 25443-2102, COARSEGOLD | 0000008223 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101053750 | RELW OH PRI REMT FIRE ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | INPR | [17 empty] | 2019-05-06 | 2020-05-06 | 2020-09-04 | 2020-09-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432102 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117177249 | POLE_DECA_REPL - 41048 HARMONY LN. 1S OA | 35209415 |  |  | STS-POLE_DECA_REPL - 41048 HARMONY LN. 1 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.3438 | -119.6951 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000007212 | 10389 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 59.9 | 58.3 | 1.6 |  | 0 | 59.9 | 58.3 | 1.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101025708 | RELW OH PRI CLR FLAG RESD NOAC TRAF ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-11 |  | COMP | 2021-02-11 | [16 empty] | 2019-05-07 | 2020-05-07 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254421101 | 25941.39 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117177325 | POLE_DECA_REPL - RD425B NE/O STILLMEADOW | 35209420 |  |  | STS-POLE_DECA_REPL - RD425B NE/O STILLME | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.3099 | -119.6499 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 07214C | 949915 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 60.7 | 60.7 | 0 |  | 0 | 60.7 | 60.7 | 0 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101020224 | RELW OH PRI JPOL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-14 |  | COMP | 2020-12-14 | [16 empty] | 2019-05-07 | 2020-05-07 | 2020-08-28 | 2020-08-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 28587.09 | 13.5 | -352.9 | -36.2 | -36.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117178216 | POLE_DECA_REPL - 40697 HWY 49 4E 6S 2E 2 | 35209436 |  |  | STS-POLE_DECA_REPL - 40697 HWY 49 4E 6S | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.3395 | -119.6984 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000007212 | 5490 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 69.8 | 69.8 | 0 |  | 0 | 69.8 | 69.8 | 0 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101025715 | RELW OH PRI CLR RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-10 |  | COMP | 2021-02-10 | [16 empty] | 2019-05-07 | 2020-05-07 | 2020-10-26 | 2020-10-26 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254421101 | 28999.75 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117186183 | TREE_DECA_INPL - 38568 ROAD 425BOAKHURST | 35215470 |  |  | STS-TREE_DECA_INPL - 38568 ROAD 425BOAKH | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 37.3068 | -119.6512 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 07214C | 5438 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103813069 | RELW OH SERV FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 1 | 78.3 | 64.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117249017 | POLE_DECA_REPL - 46208 EASTWOOD DROAKHUR | 35209006 |  |  | STS-POLE_DECA_REPL - 46208 EASTWOOD DROA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.352 | -119.7037 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000721053 | 10676 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 60.9 | 59.3 | 1.6 |  | 0 | 60.9 | 59.3 | 1.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103923394 | RELW FIRE OH PRI RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 |  | COMP | 2021-01-19 | [16 empty] | 2019-05-16 | 2020-05-16 | 2020-07-21 | 2020-07-21 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254421101 | 26495.17 | 187.5 | 174.1 | 785.3 | 785.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117303152 | POLE_DECA_REPL - 49357 SKUNK LN.OAKHURST | 35189083 |  |  | STS-POLE_DECA_REPL - 49357 SKUNK LN.OAKH | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.3397 | -119.6476 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721112 | 10562 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.7 | 49.9 | 0.8 |  | 0 | 50.7 | 49.9 | 0.8 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101025241 | RELW OH PRI INSP CLR JPOL RESD FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-09-08 | 2021-02-03 | COMP | 2020-09-08 |  |  | 2021-02-02 | 2021-02-03 | [12 empty] | 2019-05-22 | 2020-05-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254421103 | 22817.75 | 79.5 | 79.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117308178 | POLE_DECA_REPL - R/O 49273 HODGES HILL R | 35189197 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3413 | -119.6494 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721112 | 996291 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37 | 37 |  |  | 0 | 37 | 37 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101025244 | RELW OH PRI INSP CLR JPOL RESD FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-10-01 | 2021-02-18 | COMP | 2020-09-30 | [16 empty] | 2019-05-23 | 2020-05-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254421103 | 15220.56 | 1201.9 | -45.2 | -45.2 | -45.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117376465 | POLE_DECA_REPL - 49969 WHOYATEH RDOAKHUR | 35188767 |  |  | STS-POLE_DECA_REPL - 49969 WHOYATEH RDOA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.363 | -119.6344 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000621355 | 23725 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32 | 32 |  |  | 0 | 32 | 32 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101022618 | RELW OH PRI CLR REMT FIRE ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-08-27 |  | COMP | 2020-08-27 | [16 empty] | 2019-06-03 | 2020-06-03 |  | 2020-06-03 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254421103 | 16546.45 | 51.5 | -1385 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117409253 | POLE_DECA_REPL - R/O 44700 DOUGLAS RDOAK | 35209044 |  |  | STS-POLE_DECA_REPL - R/O 44700 DOUGLAS R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2656 | -119.7326 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000820014 | 10628 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052853 | RELW OH PRI RESD ESTR REMT NOAC SWRK FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-07 | 2020-06-07 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117686659 | POLE_DECA_REPL - DOGWOOD/HAZELWOOD 1PW R | 35209252 |  |  | STS-POLE_DECA_REPL - DOGWOOD/HAZELWOOD 1 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2051 | -119.5593 |  | TIER 2 |  |  | 08225B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.7 | 21.7 |  |  | 0 | 21.7 | 21.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052273 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2020-12-14 |  | COMP | 2020-12-14 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 11892.2 | 13.5 | -506.8 | -325.8 | -325.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117686703 | POLE _BROK _REPL_54280 PINE TREE 3PE/1PS | 35209257 |  |  | STS-POLE _BROK _REPL_54280 PINE TREE 3PE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2034 | -119.5542 |  | TIER 2 |  |  | 08225B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052361 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117686725 | POLE _BROK _REPL_CR200/OAK JUNCTION 2PE/ | 35209262 |  |  | STS-POLE _BROK _REPL_CR200/OAK JUNCTION | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2111 | -119.5475 |  | TIER 2 |  |  | 08225B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052524 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2020-11-12 | 2020-11-12 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 1 | 60.2 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117686729 | POLE_DECA_REPL - CR200/OAK JUNCTION 7PE | 35216238 |  |  | STS-POLE_DECA_REPL - CR200/OAK JUNCTION | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 37.2116 | -119.5447 |  | TIER 2 |  |  | 08225B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101052534 | RELW OH PRI GO TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 1 | 100.5 | 87 | 87 | 87 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117686826 | POLE _BROK _REPL_A/F 35946 WELLS RD/1PNW | 35209281 |  |  | STS-POLE _BROK _REPL_A/F 35946 WELLS RD/ | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2714 | -119.7397 |  | TIER 2 |  |  | 0000008201 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101053078 | OH RELW PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687064 | POLE _BROK _REPL_#4 W/O QUARTZ MTN RD/RD | 35209301 |  |  | STS-POLE _BROK _REPL_#4 W/O QUARTZ MTN R | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.2123 | -119.6922 |  | TIER 2 |  |  | 0000821291 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.9 | 34.9 |  |  | 0 | 34.9 | 34.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057011 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-01-04 |  | COMP | 2021-01-04 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 17288.39 | 94.2 | 0 | 525 | 525 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687066 | POLE_DECA_REPL - 31680 SIOUX 2PS/1PE ROA | 35209307 |  |  | STS-POLE_DECA_REPL - 31680 SIOUX 2PS/1PE | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2066 | -119.6733 |  | TIER 2 |  |  | 0000821284 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 9.5 | 9.5 |  |  | 0 | 9.5 | 9.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101057064 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-01-25 |  | COMP | 2021-01-25 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 7117.5 | 831.6 | 818.2 | 818.2 | 818.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687424 | POLE _BROK _REPL_4753O MODOC RD 2PE/O RO | 35209343 |  |  | STS-POLE _BROK _REPL_4753O MODOC RD 2PE/ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.218 | -119.6799 |  | TIER 2 |  |  | 0000821215 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101060569 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2020-11-05 | 2020-11-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687426 | POLE _BROK _REPL_32264 DELAWARE RD 1PN/O | 35209348 |  |  | STS-POLE _BROK _REPL_32264 DELAWARE RD 1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2176 | -119.6819 |  | TIER 2 |  |  | 0000821215 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101060575 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2020-10-05 | 2020-10-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687503 | POLE_DECA_REPL - 47330 MODOC RD 1PS/O RO | 35209353 |  |  | STS-POLE_DECA_REPL - 47330 MODOC RD 1PS/ | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2154 | -119.6865 |  | TIER 2 |  |  | 0000821216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 48 | 48 |  |  | 0 | 48 | 48 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060826 | RELW OH PRI ESTR GO TER2 PRTO FSRP | Pole | 2021-01-26 |  | COMP | 2021-01-26 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-11-05 | 2020-11-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 22900.55 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687540 | POLE _BROK _REPL_46315 COMSTOCK DR 1PW/O | 35209364 |  |  | STS-POLE _BROK _REPL_46315 COMSTOCK DR 1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2345 | -119.7044 |  | TIER 2 |  |  | 08213B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101061027 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687661 | POLE _BROK _REPL_50640 RD200 2.5 MILES S | 35216258 |  |  | STS-POLE _BROK _REPL_50640 RD200 2.5 MIL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1573 | -119.6308 |  | TIER 2 |  |  | 0000009211 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101062498 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 1 | 147.2 | 133.7 | 133.7 | 133.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687687 | POLE _BROK _REPL_50760 RD200 PVTP | 35216262 |  |  | STS-POLE _BROK _REPL_50760 RD200 PVTP | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.181 | -119.626 |  | TIER 2 |  |  | 0000009211 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.4 | 23.4 |  |  | 0 | 23.4 | 23.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101062550 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-02-10 | 2021-02-10 | COMP | 2021-02-10 | [16 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 7516.71 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687689 | POLE _BROK _REPL_1691 CIRCLE J RANCH RD/ | 35216266 |  |  | STS-POLE _BROK _REPL_1691 CIRCLE J RANCH | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1605 | -119.6636 |  | TIER 2 |  |  | 0000009211 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101062572 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 1 | 436.1 | 422.7 | 422.7 | 422.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687702 | POLE _BROK _REPL_28263 CIRCLE J RANCH RD | 35216271 |  |  | STS-POLE _BROK _REPL_28263 CIRCLE J RANC | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1603 | -119.6677 |  | TIER 2 |  |  | 0000009211 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101062583 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687768 | POLE _BROK _REPL_51525 LONG GOLD RD/3PW | 35209388 |  |  | STS-POLE _BROK _REPL_51525 LONG GOLD RD/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1137 | -119.6151 |  | TIER 2 |  |  | 0000009226 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101063730 | RELW OH PRI ESTR TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117688664 | POLE _BROK _REPL_33249 CR224 1PN/2PE/2PN | 35216280 |  |  | STS-POLE _BROK _REPL_33249 CR224 1PN/2PE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2339 | -119.5255 |  | TIER 2 |  |  | 08224A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101117944 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG | [11 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117688686 | POLE _BROK _REPL_56184 CR226 1PE PVTP | 35216283 |  |  | STS-POLE _BROK _REPL_56184 CR226 1PE PVT | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 37.2414 | -119.5232 |  | TIER 2 |  |  | 0000008221 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101118256 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG | [11 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117688703 | POLE _BROK _REPL_33478 RD222 1PS/2PW PVT | 35216286 |  |  | STS-POLE _BROK _REPL_33478 RD222 1PS/2PW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2324 | -119.5169 |  | TIER 2 |  |  | 08224A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.8 | 18.8 |  |  | 0 | 18.8 | 18.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101118283 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-02-12 | 2021-02-12 | COMP | 2021-02-12 | [16 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 7275.96 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117691976 | POLE _ BROK _ REPL_51662 RD 200 1PE/1PN | 35216331 |  |  | STS-POLE _ BROK _ REPL_51662 RD 200 1PE/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1949 | -119.6044 |  | TIER 2 |  |  | 0000008226 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103150208 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117692188 | POLE _ BROK _ REPL_47801 Willow Pond Rd, | 35216339 |  |  | STS-POLE _ BROK _ REPL_47801 WILLOW POND | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1997 | -119.6761 |  | TIER 2 |  |  | 0000821285 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103224709 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117692190 | POLE _ BROK _ REPL_31174 Willow Pond Ln, | 35209507 |  |  | STS-POLE _ BROK _ REPL_31174 WILLOW POND | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2019 | -119.6745 |  | TIER 2 |  |  | 0000821285 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.7 | 18.7 |  |  | 0 | 18.7 | 18.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103224988 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-01-04 |  | COMP | 2021-01-04 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-11-05 | 2020-11-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 11118.45 | 13.5 | 0 | 525 | 525 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117692231 | POLE _ BROK _ REPL_R/O 42971 RANGER CIRC | 35209512 |  |  | STS-POLE _ BROK _ REPL_R/O 42971 RANGER | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.1997 | -119.7631 |  | TIER 2 |  |  | 08205B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.2 | 42.2 |  |  | 0 | 42.2 | 42.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103233837 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-02-04 |  | COMP | 2021-02-04 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 17844.02 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 116963411 | POLE_BROK_REPL - 47402 RD.620 2EOAKHURST | 35188162 |  |  | STS-POLE_BROK_REPL - 47402 RD.620 2EOAKH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3833 | -119.6806 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000006216 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 29.5 | 29.5 |  |  | 0 | 29.5 | 29.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101024589 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-07 | 2020-10-07 | COMP | 2020-10-07 | [16 empty] | 2019-04-05 | 2020-04-05 |  | 2020-04-05 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 12976.88 | 2270.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 116963670 | POLE_BROK_REPL - 47402 RD.620OAKHURST936 | 35188173 |  |  | STS-POLE_BROK_REPL - 47402 RD.620OAKHURS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3835 | -119.6822 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000006216 | 5561 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 29 | 29 |  |  | 0 | 29 | 29 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101024586 | RELW OH PRI CLR ESTR USA FMOB TER2 PRTO | Pole | 2020-10-13 | 2020-10-13 | COMP | 2020-10-13 | [16 empty] | 2019-04-05 | 2020-04-05 |  | 2020-04-05 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 14469.72 | 240.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 116971521 | POLE_BROK_REPL - 47556 RD.620 2SOAKHURST | 35188455 |  |  | STS-POLE_BROK_REPL - 47556 RD.620 2SOAKH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3837 | -119.6785 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000006216 | 49309 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 26.9 | 26.9 |  |  | 0 | 26.9 | 26.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101024730 | RELW OH PRI CLR NOAC ESTR USA FMOB TER2 PRTO | Pole | 2020-10-16 | 2021-01-27 | COMP | 2020-10-15 |  |  | 2021-01-27 | 2021-01-27 | [12 empty] | 2019-04-06 | 2020-04-06 |  | 2020-04-06 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 12902.74 | 349.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 116971534 | POLE_BROK_REPL - 47556 RD.620 1S 1WOAKHU | 35188460 |  |  | STS-POLE_BROK_REPL - 47556 RD.620 1S 1WO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3834 | -119.6794 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000006216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 19.8 | 19.8 |  |  | 0 | 19.8 | 19.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101024597 | RELW OH PRI CLR ESTR USA FMOB TER2 PRTO | Pole | 2020-10-08 | 2020-10-08 | COMP | 2020-10-08 | [16 empty] | 2019-04-06 | 2020-04-06 |  | 2020-04-06 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 7257.07 | 57.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 116972070 | POLE_DECA_REPL - 47112 RD.620 1NOAKHURST | 35188475 |  |  | STS-POLE_DECA_REPL - 47112 RD.620 1NOAKH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3848 | -119.6855 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000006216 | 5561 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 27.9 | 27.9 |  |  | 0 | 27.9 | 27.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024570 | RELW OH PRI CLR JPOL REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-12 | 2021-01-26 | COMP | 2020-10-12 |  |  | 2021-01-23 | 2021-01-25 | [12 empty] | 2019-04-06 | 2020-04-06 |  | 2020-04-06 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 17392.53 | 191.4 | 111.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 116973268 | POLE_BROK_REPL - 1/2 M/E/O HARONY ON OPA | 35188535 |  |  | STS-POLE_BROK_REPL - 1/2 M/E/O HARONY ON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3807 | -119.6792 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000006216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 17 | 17 |  |  | 0 | 17 | 17 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101024646 | RELW OH PRI CLR ESTR USA FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-10-12 | COMP | 2020-10-12 | [16 empty] | 2019-04-07 | 2020-04-07 |  | 2020-04-07 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 8500.14 | 101.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 116986332 | POLE_DECA_REPL - 1/2 M/E/O HARONY ON OPA | 35187894 |  |  | STS-POLE_DECA_REPL - 1/2 M/E/O HARONY ON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3681 | -119.6878 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.7 | 14.7 |  |  | 0 | 14.7 | 14.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101023713 | RELW OH PRI JPOL REMT ESTR FMOB TER2 PRTO | Pole | 2020-09-28 | 2020-09-28 | COMP | 2020-09-28 | [16 empty] | 2019-04-09 | 2020-04-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 5569.87 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 116986381 | POLE_BROK_REPL - 1/2 M/E/O HARONY ON OPA | 35187901 |  |  | STS-POLE_BROK_REPL - 1/2 M/E/O HARONY ON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3686 | -119.6872 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 06216D |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.7 | 14.7 |  |  | 0 | 14.7 | 14.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101023711 | RELW OH PRI JPOL REMT ESTR USA FMOB TER2 PRTO | Pole | 2020-09-24 | 2020-09-24 | COMP | 2020-09-24 | [16 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 5287.13 | 1230.2 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117010522 | POLE_DECA_REPL - BRANDYWINE LN 2S/O 3936 | 35086254 |  |  | STS-POLE_DECA_REPL - BRANDYWINE LN 2S/O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3193 | -119.6447 |  | TIER 2 | 728 | 25442-1102, OAKHURST | 0000721145 | 10682 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.6 | 14.6 |  |  | 0 | 14.6 | 14.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101020269 | RELW OH PRI INSP JPOL RESD FLAG ESTR GO BTKA USA FMOB TER2 FSRP | Pole | 2020-07-28 | 2020-07-28 | COMP | 2020-07-28 | [16 empty] | 2019-04-11 | 2020-04-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117014764 | POLE_DECA_REPL - W/O 39089 WASHBURN LNOA | 35188135 |  |  | STS-POLE_DECA_REPL - W/O 39089 WASHBURN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3162 | -119.6397 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721145 | 10407 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 59.7 | 59.5 | 0.2 |  | 0 | 59.7 | 59.5 | 0.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101020281 | RELW OH PRI INSP CLR RESD ESTR BTKA USA FMOB TER2 | Pole | 2020-10-08 | 2020-10-08 | COMP | 2020-10-08 | [16 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 20946 | 94.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117015213 | POLE_DECA_REPL - W/O 39163 WASHBURN LN O | 35188147 |  |  | STS-POLE_DECA_REPL - W/O 39163 WASHBURN | UNSC | UNSC srdy | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.318 | -119.6404 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721145 | 10407 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.4 | 22.4 |  |  | 0 | 22.4 | 22.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101015823 | RELW OH PRI INSP CLR RESD ESTR BTKA USA FMOB TER2 | Pole | 2020-10-14 | 2020-10-14 | COMP | 2020-10-14 | [16 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 7520.52 | 93.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117040699 | POLE_DECA_REPL - 39642 HIGHVIEW DROAKHUR | 35190155 |  |  | B3 -POLE_DECA_REPL - 39642 HIGHVIEW DROA | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3241 | -119.6406 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000721144 | 10669 | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-04 16:00 | Dispatched | CLICK | [6 empty] | 22.1 | 22.1 |  |  | 0 | 22.1 | 22.1 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101019078 | RELW OH SERV INSP RESD FLAG ESTR BTKA USA TER2 FMOB | Pole | 2020-09-22 | 2020-12-28 | COMP | 2020-08-21 |  |  | 2020-09-08 | [13 empty] | 2019-04-16 | 2020-04-16 | 2020-10-11 | 2020-10-11 | B-tag addition 8/4/2020 | 2020-04-16 | W. Sac |  | 254421101 | 17513.29 | 1031.7 | 663.7 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-08-04
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117171747 | POLE_DECA_REPL - R\O 34528 RD 236\41PSWO | 35209355 |  |  | STS-POLE_DECA_REPL - R\O 34528 RD 236\41 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2352 | -119.6057 |  | TIER 2 | 385 | 25443-2102, COARSEGOLD | 0000008223 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14 | 14 |  |  | 0 | 14 | 14 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101053726 | RELW OH PRI REMT FIRE ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-09 | 2021-02-09 | COMP | 2021-02-09 | [16 empty] | 2019-05-06 | 2020-05-06 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432102 | 5073.43 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117230661 | POLE_DECA_REPL - A\F 36927 HWY 41OAKHURS | 35209791 |  |  | STS-POLE_DECA_REPL - A\F 36927 HWY 41OAK | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2856 | -119.6549 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 07215C | 10788 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.8 | 26.8 |  |  | 0 | 26.8 | 26.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101026655 | RELW OH PRI REMT FMOB SWRK ESTR BTKA TER2 PRTO FSRP | Pole | 2020-12-18 | 2020-12-18 | COMP | 2020-12-18 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 12874 | 208.2 | -724 | -362 | -362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117238517 | POLE_DECA_REPL - 39064 TOM TILLERY DR/1S | 35208888 |  |  | STS-POLE_DECA_REPL - 39064 TOM TILLERY D | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3162 | -119.6629 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 07214B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.5 | 27.5 |  |  | 0 | 27.5 | 27.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101020988 | RELW OH PRI RESD REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-16 | 2020-12-16 | COMP | 2020-12-16 | [16 empty] | 2019-05-15 | 2020-05-15 | 2020-10-26 | 2020-10-26 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 13986.01 | 53.8 | 0 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117270073 | POLE_DECA_REPL - 48261 RD 620 @ HSE #1 N | 35188849 |  |  | STS-POLE_DECA_REPL - 48261 RD 620 @ HSE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3626 | -119.6437 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000621355 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 28.1 | 28.1 |  |  | 0 | 28.1 | 28.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103089303 | RELW OH PRI CLR REMT ESTR BTKA REAR FMOB TER2 PRTO | Pole | 2020-10-16 | 2020-10-16 | COMP | 2020-10-16 | [16 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-11-15 | QUES |  | 254421103 | 10433 | 56 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117281897 | POLE_DECA_REPL - 50044 RD 620 3P SOAKHUR | 35188944 |  |  | STS-POLE_DECA_REPL - 50044 RD 620 3P SOA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3685 | -119.634 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000621363 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.3 | 27.3 |  |  | 0 | 27.3 | 27.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101022350 | OH PRI CLR FMOB RELW REMT NOAC ESTR USA TER2 PRTO | Pole | 2020-10-05 | 2020-10-05 | COMP | 2020-10-05 | [16 empty] | 2019-05-20 | 2020-05-20 |  | 2020-05-20 | 2021 CBP Plan | 2020-11-15 | QUES |  | 254421103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117299493 | POLE_BROK_REPL - 41903 RIVER FALLS RD./1 | 35188948 |  |  | STS-POLE_BROK_REPL - 41903 RIVER FALLS R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3572 | -119.6391 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721021 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 10.4 | 10.4 |  |  | 0 | 10.4 | 10.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101024708 | RELW OH SERV JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-25 | 2020-09-25 | COMP | 2020-09-25 | [16 empty] | 2019-05-22 | 2020-05-22 |  | 2020-05-22 | 2021 CBP Plan | 2020-11-15 | QUES |  | 254421103 | 8710.16 | 1311.4 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117299839 | POLE_BROK_REPL - 41468 OLD BARN WAY/3PNE | 35188969 |  |  | STS-POLE_BROK_REPL - 41468 OLD BARN WAY/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3511 | -119.64 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721024 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 13 | 13 |  |  | 0 | 13 | 13 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101024835 | RELW OH SERV ESTR BTKA REAR FMOB TER2 PRTO | Pole | 2020-09-25 | 2020-09-25 | COMP | 2020-09-25 | [16 empty] | 2019-05-22 | 2020-05-22 |  | 2020-05-22 | 2021 CBP Plan | 2020-11-15 | QUES |  | 254421103 | 6003.18 | 1372.4 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117300247 | POLE_DECA_REPL - 49988 GAMEGAN CT/1PSWOA | 35188990 |  |  | STS-POLE_DECA_REPL - 49988 GAMEGAN CT/1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3589 | -119.6364 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721021 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 13 | 13 |  |  | 0 | 13 | 13 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024678 | RELW OH SERV JPOL RESD ESTR USA FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-10-12 | COMP | 2020-10-12 | [16 empty] | 2019-05-22 | 2020-05-22 |  | 2020-05-22 | 2021 CBP Plan | 2020-11-15 | QUES |  | 254421103 | 7056.85 | 51.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117300481 | POLE_BROK_REPL - 40719 STAGECOACH RD/1PE | 35189001 |  |  | STS-POLE_BROK_REPL - 40719 STAGECOACH RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3412 | -119.6513 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721112 | 996291 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 13.2 | 13.2 |  |  | 0 | 13.2 | 13.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101025248 | RELW OH PRI INSP RESD FIRE NOAC ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-10-05 | 2020-10-05 | COMP | 2020-10-05 | [16 empty] | 2019-05-22 | 2020-05-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | QUES |  | 254421103 | 4372.31 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117301365 | POLE_DECA_REPL - 40811 STAGECOACH RDOAKH | 35189036 |  |  | STS-POLE_DECA_REPL - 40811 STAGECOACH RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3421 | -119.6536 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721112 | 996291 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 52.2 | 52.2 |  |  | 0 | 52.2 | 52.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101025261 | RELW OH PRI INSP CLR RESD FIRE ESTR GO BTKA USA PROG FMOB TER2 FSRP | Pole | 2020-10-15 | 2020-10-15 | COMP | 2020-10-15 | [16 empty] | 2019-05-22 | 2020-05-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | QUES |  | 254421103 | 22535.89 | 51.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117302565 | POLE_BROK_REPL - 41634 OLD BARN WAY OAKH | 35189063 |  |  | STS-POLE_BROK_REPL - 41634 OLD BARN WAY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.353 | -119.6418 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721024 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 10.4 | 10.4 |  |  | 0 | 10.4 | 10.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101024830 | RELW OH SERV ESTR BTKA PRTO USA FMOB TER2 | Pole | 2020-10-19 | 2020-10-19 | COMP | 2020-10-16 | [16 empty] | 2019-05-22 | 2020-05-22 |  | 2020-05-22 | 2021 CBP Plan | 2020-11-15 | QUES |  | 254421103 | 4406.42 | 51.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117302599 | POLE_DECA_REPL - 41468 OLD BARN WAY/1PNE | 35189068 |  |  | STS-POLE_DECA_REPL - 41468 OLD BARN WAY/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3526 | -119.6411 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721024 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 13.2 | 13.2 |  |  | 0 | 13.2 | 13.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024827 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-16 | 2020-10-16 | COMP | 2020-10-16 | [16 empty] | 2019-05-22 | 2020-05-22 |  | 2020-05-22 | 2021 CBP Plan | 2020-11-15 | QUES |  | 254421103 | 5676.34 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117302763 | POLE_DECA_REPL - 40907 STAGECOACH RD/1PS | 35189073 |  |  | STS-POLE_DECA_REPL - 40907 STAGECOACH RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3425 | -119.6518 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721112 | 996291 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.1 | 34.1 |  |  | 0 | 34.1 | 34.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101025259 | RELW OH PRI INSP RESD FIRE ESTR BTKA FMOB TER2 FSRP | Pole | 2020-10-05 | 2020-11-05 | COMP | 2020-10-02 | [16 empty] | 2019-05-22 | 2020-05-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254421103 | 13677.11 | 1100.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117309717 | POLE_DECA_REPL - 40888 HODGES HILL RD/1P | 35189215 |  |  | STS-POLE_DECA_REPL - 40888 HODGES HILL R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.343 | -119.6474 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721112 | 19574 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 10.4 | 10.4 |  |  | 0 | 10.4 | 10.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101025214 | RELW OH PRI INSP JPOL RESD FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-08-27 | 2020-08-27 | COMP | 2020-08-27 | [16 empty] | 2019-05-23 | 2020-05-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254421103 | 4018.72 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117309825 | POLE_BROK_REPL - 40888 HODGES HILL RD/1P | 35189223 |  |  | STS-POLE_BROK_REPL - 40888 HODGES HILL R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3431 | -119.6473 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721112 | 19574 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 15.7 | 15.7 |  |  | 0 | 15.7 | 15.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101025213 | RELW OH PRI INSP JPOL RESD FIRE ESTR BTKA FMOB FSRP TER2 | Pole | 2020-08-28 | 2021-01-26 | COMP | 2020-08-28 |  |  | 2021-01-23 | 2021-01-25 | [12 empty] | 2019-05-23 | 2020-05-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254421103 | 10318.55 | 126.2 | 55.7 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117310637 | POLE_DECA_REPL - SW C/O HODGES HILL DR/H | 35189235 |  |  | STS-POLE_DECA_REPL - SW C/O HODGES HILL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3443 | -119.6435 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721025 | 2038 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 49.5 | 49.5 |  |  | 0 | 49.5 | 49.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024952 | RELW ESTR OH PRI CLR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-15 | 2021-02-03 | COMP | 2020-09-15 |  |  | 2021-02-02 | 2021-02-03 | [12 empty] | 2019-05-23 | 2020-05-23 |  | 2020-05-23 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254421103 | 19960.68 | 3257.2 | 79.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117314996 | POLE_DECA_REPL - 40888 HODGES HILL RD/1P | 35189280 |  |  | STS-POLE_DECA_REPL - 40888 HODGES HILL R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3441 | -119.6486 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721112 | 19574 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.8 | 39.8 |  |  | 0 | 39.8 | 39.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101025216 | RELW OH PRI INSP CLR JPOL RESD FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-10-02 | 2020-10-02 | COMP | 2020-10-02 | [16 empty] | 2019-05-24 | 2020-05-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254421103 | 15289.9 | 1100.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117315094 | POLE_DECA_REPL - 40888 HODGES HILL RD/1P | 35189286 |  |  | STS-POLE_DECA_REPL - 40888 HODGES HILL R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3431 | -119.6466 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721112 | 19574 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.4 | 42.4 |  |  | 0 | 42.4 | 42.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101025212 | RELW OH PRI INSP JPOL RESD FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-10-05 | 2020-10-05 | COMP | 2020-10-05 | [16 empty] | 2019-05-24 | 2020-05-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254421103 | 17345.04 | 1570.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117376599 | POLE_DECA_REPL - 50021 LILAC LN 2PSOAKHU | 35188770 |  |  | STS-POLE_DECA_REPL - 50021 LILAC LN 2PSO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3631 | -119.6345 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000621366 | 23725 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.2 | 14.2 |  |  | 0 | 14.2 | 14.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101023765 | RELW OH SEC CLR RESD REMT FIRE ESTR GO BTKA PRTO USA FMOB TER2 | Pole | 2020-10-07 | 2020-10-07 | COMP | 2020-10-07 | [16 empty] | 2019-06-03 | 2020-06-03 |  | 2020-06-03 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254421103 | 4480.32 | 1026.4 | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117403693 | POLE_BROK_REPL - 41969 HWY 41 OAKHURST | 35188966 |  |  | STS-POLE_BROK_REPL - 41969 HWY 41 OAKHUR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3594 | -119.6437 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000006215 | 2035 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.7 | 36.7 |  |  | 0 | 36.7 | 36.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103212778 | RELW OH PRI CLR JPOL RESD NOAC ESTR USA FMOB TER2 PRTO | Pole | 2020-09-28 | 2021-01-27 | COMP | 2020-09-28 | [16 empty] | 2019-06-06 | 2020-06-06 |  | 2020-06-06 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254421103 | 20807.23 | 1881.3 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117685270 | POLE _BROK _REPL_44574 WISE RD/@ HOUSE/3 | 35216230 |  |  | STS-POLE _BROK _REPL_44574 WISE RD/@ HOU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2923 | -119.7336 |  | TIER 2 |  |  | 0000007205 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.8 | 32.8 |  |  | 0 | 32.8 | 32.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101025125 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-02-03 | 2021-02-04 | COMP | 2021-02-01 | [16 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 24204.54 | 48.3 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117686777 | POLE _BROK _REPL_CR200/ROCKY RD 1PN ROAD | 35216246 |  |  | STS-POLE _BROK _REPL_CR200/ROCKY RD 1PN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.208 | -119.5391 |  | TIER 2 |  |  | 08225B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15 | 15 |  |  | 0 | 15 | 15 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052843 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-02-09 | 2021-02-09 | COMP | 2021-02-09 | [16 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 7293.49 | 13.5 | 0 | 978 | 978 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687041 | POLE _BROK _REPL_31308 ERIE RD 2PN PVTP | 35209292 |  |  | STS-POLE _BROK _REPL_31308 ERIE RD 2PN P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2042 | -119.6725 |  | TIER 2 |  |  | 0000008215 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.4 | 16.4 |  |  | 0 | 16.4 | 16.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101056474 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-02-04 | 2021-02-04 | COMP | 2021-02-04 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-10-05 | 2020-10-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 7287.2 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687328 | POLE _BROK _REPL_MILLVIEW MT. CT.RD2222P | 35198767 |  |  | STS-POLE _BROK _REPL_MILLVIEW MT. CT.RD2 | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2181 | -119.5077 |  | TIER 2 |  |  | 08233C |  | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 29.5 | 29.5 |  |  | 0 | 29.5 | 29.5 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101059738 | RELW OH PRI ESTR TER2 PRTO | Pole | 2020-10-26 | 2020-11-07 | COMP | 2020-10-26 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-11-03 | 2020-11-03 | B tag clean up 9/5/2020 |  | Fresno |  |  | 9477.23 | 2066.9 | 1901.2 | 1901.2 | 1901.2 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-09-05
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687527 | POLE _BROK _REPL_47226 OTTOWA AVE 1PW 2P | 35209359 |  |  | STS-POLE _BROK _REPL_47226 OTTOWA AVE 1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2194 | -119.6875 |  | TIER 2 |  |  | 0000821213 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.7 | 15.7 |  |  | 0 | 15.7 | 15.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101060992 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2020-12-15 | 2020-12-15 | COMP | 2020-12-15 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 8783.45 | 13.5 | 0 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687725 | POLE _BROK _REPL_BUTTERFIELD STAGE RD/BU | 35216274 |  |  | STS-POLE _BROK _REPL_BUTTERFIELD STAGE R | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1404 | -119.6696 |  | TIER 2 |  |  | 0000009214 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18 | 18 |  |  | 0 | 18 | 18 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101062794 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-02-11 | 2021-02-11 | COMP | 2021-02-11 | [16 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 7549.27 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117688713 | POLE _BROK _REPL_33249 CR224 4PN/6PW PVT | 35180022 |  |  | STS-POLE _BROK _REPL_33249 CR224 4PN/6PW | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2321 | -119.5332 |  | TIER 2 |  |  | 08224A |  | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | [6 empty] | 40.1 | 40.1 |  |  | 1 | 40 | 40 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101118316 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2020-12-23 | 2020-12-23 | COMP | 2020-12-23 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-08-27 | 2020-08-27 | B-Tag Addition 06.24.20 | 2020-07-31 | Fresno |  |  | 27495.6 | 6001.7 | 6001.7 | 1096.8 | 1096.8 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-06-29
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117691795 | POLE _ BROK _ REPL_33249 CR224 4PN/4PW/2 | 35209471 |  |  | STS-POLE _ BROK _ REPL_33249 CR224 4PN/4 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2329 | -119.5314 |  | TIER 2 |  |  | 08224A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.4 | 25.4 |  |  | 0 | 25.4 | 25.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103086667 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-01-29 | 2021-01-29 | COMP | 2021-01-29 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-10-27 | 2020-10-27 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 9177.55 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117692187 | POLE _ BROK _ REPL_31242 Willow Pond Ln, | 35209475 |  |  | STS-POLE _ BROK _ REPL_31242 WILLOW POND | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2005 | -119.6765 |  | TIER 2 |  |  | 0000821285 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.2 | 19.2 |  |  | 0 | 19.2 | 19.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103224707 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-02-02 | 2021-02-02 | COMP | 2021-02-02 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 6960.97 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Oakhurst | Oakhurst |  |  | OPEN | 118570488 | POLE_BROK_REPL - 39089 WASHBURN LN/2NOak | 35189140 |  |  | STS-POLE_BROK_REPL - 39089 WASHBURN LN/2 | UNSC | UNSC srdy | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3178 | -119.6391 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000721145 | 10407 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.8 | 21.8 |  |  | 0 | 21.8 | 21.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101020284 | RELW OH PRI INSP CLR REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-10-15 | 2020-10-15 | COMP | 2020-10-15 | [16 empty] | 2020-02-24 | 2021-02-24 |  | 2021-02-24 | 2021 CBP Plan | 2020-11-15 | TRC |  | 254421103 | 7719.33 | 1118.5 | -1385 | -1385 | -1385 |  |  |  | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117686778 | POLE _BROK _REPL_R/O 44810 DOUGLAS RD/2P | 35209272 |  |  | STS-POLE _BROK _REPL_R/O 44810 DOUGLAS R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2635 | -119.7311 |  | TIER 2 |  |  | 0000820014 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 44 | 44 |  |  | 0 | 44 | 44 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052867 | OH PRI ESTR TER2 PRTO FSRP RELW | Pole | 2021-01-25 | 2021-01-25 | COMP | 2021-01-25 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 17848.84 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117686820 | POLE _BROK _REPL_A/F 44700 DOUGLAS RD/1P | 35209276 |  |  | STS-POLE _BROK _REPL_A/F 44700 DOUGLAS R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.268 | -119.7311 |  | TIER 2 |  |  | 0000820011 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.8 | 42.8 |  |  | 0 | 42.8 | 42.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052969 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-01-14 | 2021-01-14 | COMP | 2021-01-14 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 16537.08 | 13.5 | 0 | 1104.5 | 1104.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687709 | POLE _BROK _REPL_28765 FLYING 0 RANCH RD | 35209368 |  |  | STS-POLE _BROK _REPL_28765 FLYING 0 RANC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1671 | -119.6698 |  | TIER 2 |  |  | 0000009211 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.9 | 15.9 |  |  | 0 | 15.9 | 15.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101062603 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-01-19 | 2021-01-19 | COMP | 2021-01-19 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-10-21 | 2020-10-21 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 6998.21 | 53.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687766 | POLE _BROK _REPL_51525 LONG GOLD RD/5PW | 35209383 |  |  | STS-POLE _BROK _REPL_51525 LONG GOLD RD/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1139 | -119.6171 |  | TIER 2 |  |  | 0000009226 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 16.2 | 16.2 |  |  | 0 | 16.2 | 16.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101063728 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-01-15 | 2021-01-15 | COMP | 2021-01-15 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 5680.47 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117688640 | POLE _BROK _REPL_55850 CR226 1PS/1PW PVT | 35209404 |  |  | STS-POLE _BROK _REPL_55850 CR226 1PS/1PW | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2393 | -119.5311 |  | TIER 2 |  |  | 08224A |  | Y | 311 |  |  | 2021-03-09 07:00 | 2021-03-09 15:00 | Scheduled | CLICK | [6 empty] | 0.8 | 0.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101117591 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-01-20 | COMP | 2021-01-20 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 20178.31 | 94.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117692189 | POLE _ BROK _ REPL_31242 Willow Pond Ln, | 35209500 |  |  | STS-POLE _ BROK _ REPL_31242 WILLOW POND | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2 | -119.6759 |  | TIER 2 |  |  | 0000821285 |  | Y | 311 |  |  | 2021-03-12 05:03 | 2021-03-12 10:43 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 0.8 | 0.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103224730 | RELW ESTR OH PRI TER2 PRTO FSRP | Pole | 2021-01-22 | 2021-01-22 | COMP | 2021-01-22 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 8798.72 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 116948406 | POLE_DECA_REPL - 53522[HSE]RD 800OAKHURS | 35208764 |  |  | STS-POLE_DECA_REPL - 53522[HSE]RD 800OAK | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3557 | -119.8292 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000007202 | 4646 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.9 | 37.9 |  |  | 0 | 37.9 | 37.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101068139 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-05 | 2021-01-05 | COMP | 2021-01-05 | [16 empty] | 2019-04-03 | 2020-04-03 | 2020-08-31 | 2020-08-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 15007.51 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117262969 | POLE_DECA_REPL - HWY 49 SKY VISTA PL 4NO | 35154088 |  |  | STS-POLE_DECA_REPL - HWY 49 SKY VISTA PL | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3495 | -119.714 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000721065 | 11740 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101027464 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-04-28 | 2020-04-28 | COMP | 2020-04-28 | [16 empty] | 2019-05-17 | 2020-05-17 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | PIKEENG |  | 254421101 | 17844.91 | 1095.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117686755 | POLE _BROK _REPL_CR2OO/WYLE RANCH RD 3PS | 35216242 |  |  | STS-POLE _BROK _REPL_CR2OO/WYLE RANCH RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2045 | -119.5425 |  | TIER 2 |  |  | 08225B |  | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Reserved | CLICK | [6 empty] | 17.6 | 17.6 |  |  | 0 | 17.6 | 17.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052580 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-02-10 | 2021-02-10 | COMP | 2021-02-10 | [16 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 6069.22 | 13.5 | 0 | 978 | 978 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117686773 | POLE _BROK _REPL_31040 WYLE RANCH WY 3PW | 35209267 |  |  | STS-POLE _BROK _REPL_31040 WYLE RANCH WY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1989 | -119.5447 |  | TIER 2 |  |  | 08225B |  | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052760 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2020-12-15 | 2020-12-15 | COMP | 2020-12-15 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 6471.9 | 53.8 | -380.1 | -199.1 | -199.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117686774 | POLE _BROK _REPL_31040 WYLE RANCH WY 1PS | 35217118 |  |  | STS-POLE _BROK _REPL_31040 WYLE RANCH WY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1978 | -119.545 |  | TIER 2 |  |  | 0000008225 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052764 | PRI RELW OH ESTR TER2 PRTO | Pole | 2021-01-15 | 2021-01-15 | COMP | 2021-01-14 | [16 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | Strike Force Work plan | 2021-02-28 | TRC |  |  | 21630.04 | 447 | 85.4 | 85.4 | 85.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-11-10
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117686918 | POLE_BURN_REPL - 32632[HSE]BLUFF DR/2PS/ | 35154791 |  |  | STS-POLE_BURN_REPL - 32632[HSE]BLUFF DR/ | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land Enviro |  |  | 37.2211 | -119.8119 |  | TIER 2 |  |  | 0000008203 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 101054223 | RELW OH PRI ESTR GO TER2 PRTO FSRP | Pole | 2020-05-08 | 2020-05-07 | COMP | 2020-05-07 | [16 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | PIKEENG |  |  | 26123.4 | 136.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687024 | POLE _BROK _REPL_30233 HOGANS MTN RD 1PS | 35216250 |  |  | STS-POLE _BROK _REPL_30233 HOGANS MTN RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1874 | -119.7092 |  | TIER 2 |  |  | 0000008216 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 9.6 | 9.6 |  |  | 0 | 9.6 | 9.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101055838 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-01-04 | 2021-01-04 | COMP | 2021-01-04 | [16 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 3453.4 | 13.5 | 0 | 525 | 525 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687026 | POLE _BROK _REPL_30564 HOGANS MTN RD 1PE | 35209286 |  |  | STS-POLE _BROK _REPL_30564 HOGANS MTN RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1946 | -119.7168 |  | TIER 2 |  |  | 0000008216 |  | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101055874 | PRI RELW OH ESTR TER2 PRTO FSRP | Pole | 2020-12-28 | 2020-12-28 | COMP | 2020-12-28 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-11-07 | 2020-11-07 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 24110.19 | 1121.4 | 1107.9 | 362 | 362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 117687047 | POLE_DECA_REPL - ERIE/HOPI 2PSE COARSEGO | 35209297 |  |  | STS-POLE_DECA_REPL - ERIE/HOPI 2PSE COAR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2036 | -119.6731 |  | TIER 2 |  |  | 0000821285 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 42.9 | 42.9 |  |  | 0 | 42.9 | 42.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056613 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-01-06 | 2021-01-06 | COMP | 2021-01-06 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-10-05 | 2020-10-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 16895.38 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | OAKHURST | Oakhurst |  |  | OPEN | 119095695 | TREE_DECA_INPL - RD 600 APACHE RANCH RD | 35154223 |  |  | STS-POLE_DECA_REPL - RD.600 APACHE RANCH | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3308 | -119.7724 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000007201 | 10357 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103212294 | POHW OH ESTR TER2 | Pole | 2020-05-11 | 2020-05-11 | COMP | 2020-05-11 | [16 empty] | 2020-06-02 | 2021-06-02 |  | 2021-06-02 | Per DOT Approved Request 28501 | 2020-05-01 | PIKEENG |  | 254421101 | 18838.4 | 8100.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2021-01-14
Bay/Central | YO | ONEALS | Oakhurst |  |  | OPEN | 117170626 | POLE_BROK_REPL - R\O 34528 RD 236\30PSWO | 35209330 |  |  | STS-POLE_BROK_REPL - R\O 34528 RD 236\30 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2379 | -119.5948 |  | TIER 2 | 385 | 25443-2102, COARSEGOLD | 0000008223 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.6 | 16.6 |  |  | 0 | 16.6 | 16.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101053740 | RELW OH PRI REMT SWRK ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-01 | 2021-02-01 | COMP | 2021-02-01 | [16 empty] | 2019-05-06 | 2020-05-06 | 2020-09-04 | 2020-09-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432102 | 6002.91 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | ONEALS | Oakhurst |  |  | OPEN | 117170628 | POLE_BROK_REPL - R\O 34528 RD 236\18PSWO | 35154448 |  |  | STS-POLE_BROK_REPL - R\O 34528 RD 236\18 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2411 | -119.5826 |  | TIER 2 | 385 | 25443-2102, COARSEGOLD | 0000008222 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.4 | 26.4 |  |  | 0 | 26.4 | 26.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101053696 | RELW OH PRI CLR REMT NOAC SPCR ESTR FMOB TER2 PRTO | Pole | 2020-05-13 | 2020-05-13 | COMP | 2020-05-13 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-05-01 | PIKEENG |  | 254432102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117065432 | POLE_DECA_REPL - 20280 CRIPPLE HILL RD P | 35188062 |  |  | STS-POLE_DECA_REPL - 20280 CRIPPLE HILL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9914 | -120.2869 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3505 | 8365 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 49.2 | 49.2 |  |  | 0 | 49.2 | 49.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101032905 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-01 | 2020-09-30 | COMP | 2020-09-30 | [16 empty] | 2019-04-19 | 2020-04-19 |  | 2020-04-19 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 21138.97 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117074490 | POLE_BROK_REPL - A/F 15274 CAMINO DEL PA | 35188157 |  |  | STS-POLE_BROK_REPL - A/F 15274 CAMINO DE | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land Enviro |  |  | 38.0075 | -120.3087 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3518 | 23253 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 66 | 65 | 1 |  | 0 | 66 | 65 | 1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046525 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-09-29 |  | COMP | 2020-09-29 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-04-22 | 2020-04-22 |  | 2020-04-22 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 29328.55 | 158.4 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117084695 | POLE_DECA_REPL - 14207 OAK KNOLL RD/1PSE | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 37.9887 | -120.3326 |  | TIER 2 | 157 | 16335-1704, CURTIS | U3405 | 4865 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101047356 | REGW OH PRI CLR JPOL RESD ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan |  | UNASSIGNED |  | 163351704 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117238143 | POLE_BROK_REPL - PHOENIX POWER HOUSE/1NE | 35189204 |  |  | STS-POLE_BROK_REPL - PHOENIX POWER HOUSE | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 38.0321 | -120.3258 |  | TIER 2 | 41 | 16335-1702, CURTIS | T34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 45.7 | 45.7 |  |  | 0 | 45.7 | 45.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030670 | RELW OH PRI REMT NOAC ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-28 |  | COMP | 2020-09-28 | [16 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 17477.94 | 3493.1 | 1068.7 | 1068.7 | 1068.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117238323 | POLE_BROK_REPL - PHOENIX POWER HOUSEPHOE | 35189207 |  |  | STS-POLE_BROK_REPL - PHOENIX POWER HOUSE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 38.0316 | -120.3262 |  | TIER 2 | 41 | 16335-1702, CURTIS | T34 | 435 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 52.6 | 52.6 |  |  | 0 | 52.6 | 52.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030668 | RELW OH PRI REMT NOAC ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-01 |  | COMP | 2020-10-01 | [16 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 21648.32 | 3686.9 | 1068.7 | 1068.7 | 1068.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117238388 | POLE_BROK_REPL - PHOENIX POWER HOUSE/1SW | 35189209 |  |  | STS-POLE_BROK_REPL - PHOENIX POWER HOUSE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 38.0312 | -120.3265 |  | TIER 2 | 41 | 16335-1702, CURTIS | T34 | 435 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 56.6 | 56.6 |  |  | 0 | 56.6 | 56.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030666 | RELW OH PRI REMT NOAC ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-09 | 2020-10-08 | COMP | 2020-10-08 | [16 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 20496.92 | 2271.5 | 1068.7 | 1068.7 | 1068.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117255143 | POLE_BROK_REPL - 21778 EL COYOTEPHOENIX | 35189429 |  |  | STS-POLE_BROK_REPL - 21778 EL COYOTEPHOE | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.017 | -120.3048 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3513 | 9111 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 51.9 | 51.9 |  |  | 0 | 51.9 | 51.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047306 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-09-25 |  | COMP | 2020-09-25 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 28596.32 | 256.6 | 213.5 | 213.5 | 213.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117256388 | POLE_BROK_REPL - 21600 MONTGOMERYPHOENIX | 35189451 |  |  | STS-POLE_BROK_REPL - 21600 MONTGOMERYPHO | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.0148 | -120.3142 |  | TIER 2 | 41 | 16335-1702, CURTIS | T35 | 20363 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.4 | 36.4 |  |  | 0 | 36.4 | 36.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047027 | RELW OH PRI CLR JPOL RESD NOAC ESTR USA FMOB TER2 PRTO | Pole | 2020-09-25 |  | COMP | 2020-09-25 | [16 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 16958.93 | 39.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | COMP | 117239647 | POLE_BROK_REPL - 14457 PHILLIP LNPHOENIX | 35154832 |  |  | STS-POLE_BROK_REPL - 14457 PHILLIP LNPHO | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.0081 | -120.3279 |  | TIER 2 | 157 | 16335-1704, CURTIS | T3420 | S1491 | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 55 | 53.1 | 1.9 |  | 0 | 55 | 53.1 | 1.9 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031219 | RELW OH PRI COMP JPOL RESD ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-06-04 | 2020-07-30 | COMP | 2020-06-04 | COMP | 2021-01-08 | 2020-07-30 | 2020-07-30 | [11 empty] | 2021-01-15 | 2021-01-08 | 2020-05-15 |  | 2020-05-15 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351704 | 27455.81 | 10708.2 | 10708.3 | 21320.3 | 21320.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117056801 | POLE_BROK_REPL - 19903 MONO WAY 1PN/1PEP | 35187968 |  |  | STS-POLE_BROK_REPL - 19903 MONO WAY 1PN/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9847 | -120.3037 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3508 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 11.8 | 11.8 |  |  | 0 | 11.8 | 11.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032613 | RELW OH SERV CLR NOAC JPOL RESD REMT ESTR USA FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-11-29 | COMP | 2020-10-15 | [16 empty] | 2019-04-18 | 2020-04-18 |  | 2020-04-18 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 5188.16 | 152.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117064463 | POLE_BROK_REPL - 1PE/O EPPHOENIX LAKE-CE | 35188009 |  |  | STS-POLE_BROK_REPL - 1PE/O EPPHOENIX LAK | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9886 | -120.2925 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3505 | S2263 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.7 | 36.7 |  |  | 0 | 36.7 | 36.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032877 | RELW OH PRI REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-02 | 2020-12-29 | COMP | 2020-10-02 | [16 empty] | 2019-04-18 | 2020-04-18 |  | 2020-04-18 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117064471 | POLE_BROK_REPL - 20119 HAYSTACK RDPHOENI | 35188015 |  |  | STS-POLE_BROK_REPL - 20119 HAYSTACK RDPH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9874 | -120.2996 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3504 | 20173 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 59.3 | 59.1 | 0.2 |  | 0 | 59.3 | 59.1 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032688 | RELW OH PRI REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-22 | 2020-09-22 | COMP | 2020-09-22 |  |  | 2020-08-28 | 2020-08-28 | [12 empty] | 2019-04-19 | 2020-04-19 |  | 2020-04-19 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 24953.45 | 476.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117064472 | POLE_BROK_REPL - 20259 HAYSTACK RD 2PW/O | 35188021 |  |  | STS-POLE_BROK_REPL - 20259 HAYSTACK RD 2 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9882 | -120.2996 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3504 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.5 | 17.5 |  |  | 0 | 17.5 | 17.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032689 | OH RELW PRI REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-22 | 2021-02-03 | COMP | 2020-09-22 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-19 | 2020-04-19 |  | 2020-04-19 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 8999.88 | 438.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117065421 | POLE_BROK_REPL - 20140 DOG PATCH LN. PHO | 35188050 |  |  | STS-POLE_BROK_REPL - 20140 DOG PATCH LN. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9897 | -120.2877 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3505 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.3 | 13.3 |  |  | 0 | 13.3 | 13.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032885 | RELW OH SERV CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-22 | 2020-09-22 | COMP | 2020-09-22 | [16 empty] | 2019-04-19 | 2020-04-19 |  | 2020-04-19 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 4080.77 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117067734 | POLE_DECA_REPL - WAIF MINE RD 1PN\O PHOE | 35188087 |  |  | STS-POLE_DECA_REPL - WAIF MINE RD 1PN\O | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.985 | -120.3096 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3508 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 16.7 | 16.7 |  |  | 0 | 16.7 | 16.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101032504 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-14 | 2020-09-14 | COMP | 2020-09-14 | [16 empty] | 2019-04-19 | 2020-04-19 |  | 2020-04-19 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 6300.68 | 321.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117069483 | POLE_BROK_REPL - 15399 DANATEPHOENIX LAK | 35188131 |  |  | STS-POLE_BROK_REPL - 15399 DANATEPHOENIX | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 38.0127 | -120.306 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3518 | 9111 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 45.5 | 45.5 |  |  | 0 | 45.5 | 45.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046608 | OH RELW PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-27 | 2020-11-23 | COMP | 2020-09-27 | [16 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117069918 | POLE_BROK_REPL - 21821 BELLVIEWPHOENIX L | 35188137 |  |  | STS-POLE_BROK_REPL - 21821 BELLVIEWPHOEN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0183 | -120.2853 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3611 | 111443 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.6 | 57.6 |  |  | 0 | 57.6 | 57.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101057255 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-12-14 | COMP | 2020-10-12 | [16 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117074306 | POLE_BROK_REPL - 19840 SOMMETTE DR/1PS/1 | 35154801 |  |  | STS-POLE_BROK_REPL - 19840 SOMMETTE DR/1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9831 | -120.3232 |  | TIER 2 | 157 | 16335-1704, CURTIS | U3506 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.9 | 27.9 |  |  | 0 | 27.9 | 27.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032211 | RELW OH PRI PGEA JPOL RESD FMOB ESTR BTKA USA TER2 PRTO FSRP | Pole | 2020-08-04 | 2020-08-21 | COMP | 2020-05-08 |  |  | 2020-07-31 | 2020-07-31 | [12 empty] | 2019-04-22 | 2020-04-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 163351704 | 14046.14 | 139.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117074468 | POLE_BROK_REPL - 15331 AVENIDA DEL SOL/3 | 35188151 |  |  | STS-POLE_BROK_REPL - 15331 AVENIDA DEL S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9902 | -120.3135 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3502 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13 | 13 |  |  | 0 | 13 | 13 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033546 | RELW OH PRI JPOL REMT NOAC ESTR USA FMOB TER2 PRTO | Pole | 2020-09-22 | 2020-11-24 | COMP | 2020-09-22 | [16 empty] | 2019-04-22 | 2020-04-22 |  | 2020-04-22 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 14297 | 477.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117084080 | POLE_BROK_REPL - 20097 PHOENIX LAKE RD/1 | 35189554 |  |  | STS-POLE_BROK_REPL - 20097 PHOENIX LAKE | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9872 | -120.3314 |  | TIER 2 | 157 | 16335-1704, CURTIS | U3405 | 4865 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 44.9 | 44.9 |  |  | 0 | 44.9 | 44.9 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101047550 | RELW RESD OH PRI JPOL ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-11-25 | 2020-12-03 | COMP | 2020-11-24 | [16 empty] | 2019-04-23 | 2020-04-23 | 2020-10-01 | 2020-10-01 | B-tag addition 8/4/2020 |  | Fresno |  | 163351704 | [9 empty] | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-08-04
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117231290 | POLE_DECA_REPL - 21593 PHOENIX LAKE RD./ | 35189176 |  |  | STS-POLE_DECA_REPL - 21593 PHOENIX LAKE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0127 | -120.2841 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3616 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.4 | 26.4 |  |  | 0 | 26.4 | 26.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056533 | RELW OH PRI INSP FIRE ESTR GO FMOB TER2 | Pole | 2020-10-07 | 2020-12-05 | COMP | 2020-10-06 | [16 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 10585.1 | 85 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117241491 | POLE_DECA_REPL - 22430 LYONS BALD MNT RD | 35154842 |  |  | STS-POLE_DECA_REPL - 22430 LYONS BALD MN | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0298 | -120.3295 |  | TIER 2 | 157 | 16335-1704, CURTIS | T34 | 11290 | Y | 311 |  |  | 2021-03-01 07:00 | 2021-03-01 16:00 | Dispatched | CLICK | [6 empty] | 41.6 | 41.6 |  |  | 0 | 41.6 | 41.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101030686 | RELW OH PRI REMT NOAC ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-04-23 | 2020-07-31 | COMP | 2020-04-23 |  |  | 2020-07-31 | 2020-07-31 | [12 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351704 | 27344.67 | 4681.2 | 3744.2 | 3744.2 | 3744.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117243132 | POLE_DECA_REPL - 22216 VILLA RDPHOENIX L | 35189298 |  |  | STS-POLE_DECA_REPL - 22216 VILLA RDPHOEN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0249 | -120.3262 |  | TIER 2 | 41 | 16335-1702, CURTIS | T34 | L543 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39 | 39 |  |  | 0 | 39 | 39 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101030680 | RELW OH PRI CLR NOAC FMOB ESTR REAR USA TER2 PRTO | Pole | 2020-10-06 | 2020-10-06 | COMP | 2020-10-06 | [16 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 20814.65 | 164.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117249845 | POLE_BROK_REPL - A/F 14836 LAKESIDE DRPH | 35154056 |  |  | STS-POLE_BROK_REPL - A/F 14836 LAKESIDE | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-01-09 | Renew Permit | 38.001 | -120.3188 |  | TIER 2 | 157 | 16335-1704, CURTIS | T3521 | 49231 | Y | 311 |  |  | 2021-03-12 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 48 | 48 |  |  | 0 | 48 | 48 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101045425 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-03-31 | 2020-06-10 | COMP | 2020-03-31 |  |  | 2021-02-21 | 2021-02-21 | [12 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351704 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117250966 | POLE_BROK_REPL - 20813 LAKESIDE CTPHOENI | 35154065 |  |  | STS-POLE_BROK_REPL - 20813 LAKESIDE CTPH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-01-09 | Renew Permit | 37.9998 | -120.3184 |  | TIER 2 | 157 | 16335-1704, CURTIS | T3521 | 49231 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 58.2 | 58 | 0.2 |  | 0 | 58.2 | 58 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101045416 | RELW OH PRI CLR JPOL RESD ESTR TER2 BTKA USA FMOB PRTO | Pole | 2020-04-28 | 2020-09-03 | COMP | 2020-04-28 |  |  | 2021-02-21 | 2021-02-21 | [12 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 163351704 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117251466 | POLE_DECA_REPL - 21925 LYONS BALD MTN SW | 35189382 |  |  | STS-POLE_DECA_REPL - 21925 LYONS BALD MT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0221 | -120.3216 |  | TIER 2 | 41 | 16335-1702, CURTIS | T35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.6 | 15.6 |  |  | 0 | 15.6 | 15.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101048825 | RELW OH PRI REMT FMOB ESTR BTKA TER2 PRTO | Pole | 2020-10-02 | 2020-10-02 | COMP | 2020-10-02 | [16 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117256378 | POLE_BROK_REPL - 22455[ENTR]VILASPHOENIX | 35189446 |  |  | STS-POLE_BROK_REPL - 22455[ENTR]VILASPHO | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0294 | -120.323 |  | TIER 2 | 41 | 16335-1702, CURTIS | T35 | 40153 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 52.6 | 52.4 | 0.2 |  | 0 | 52.6 | 52.4 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048909 | RELW OH PRI CLR RESD REMT ESTR USA FMOB TER2 PRTO | Pole | 2020-10-05 | 2020-10-05 | COMP | 2020-10-05 | [16 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 23594.5 | 76.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117256504 | POLE_BROK_REPL - 22455[ENTR]VILAS 1SPHOE | 35189454 |  |  | STS-POLE_BROK_REPL - 22455[ENTR]VILAS 1S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0289 | -120.3225 |  | TIER 2 | 41 | 16335-1702, CURTIS | T35 | 40153 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 63.3 | 63.1 | 0.2 |  | 0 | 63.3 | 63.1 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048906 | RELW OH PRI CLR RESD REMT ESTR PRTO USA FMOB TER2 | Pole | 2020-09-25 | 2020-09-25 | COMP | 2020-09-25 | [16 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117258453 | POLE_BROK_REPL - R/O 22265 VALISPHOENIX | 35189478 |  |  | STS-POLE_BROK_REPL - R/O 22265 VALISPHOE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0278 | -120.3215 |  | TIER 2 | 41 | 16335-1702, CURTIS | T35 | 40153 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.2 | 56 | 1.2 |  | 0 | 57.2 | 56 | 1.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048846 | RELW OH PRI JPOL RESD REMT ESTR USA FMOB TER2 PRTO | Pole | 2020-10-14 | 2020-10-14 | COMP | 2020-10-14 | [16 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117259449 | POLE_BROK_REPL - 21830 MONTGOMERY 3WPHOE | 35189490 |  |  | STS-POLE_BROK_REPL - 21830 MONTGOMERY 3W | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0185 | -120.316 |  | TIER 2 | 41 | 16335-1702, CURTIS | T35 | 63263 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.6 | 33.6 |  |  | 0 | 33.6 | 33.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048345 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-27 | 2020-09-27 | COMP | 2020-09-27 | [16 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 17186.91 | 191.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117268441 | POLE_BROK_REPL - 21755 ROBIN HILLPHOENIX | 35188775 |  |  | STS-POLE_BROK_REPL - 21755 ROBIN HILLPHO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0157 | -120.2902 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3515 | 2499 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.6 | 33.6 |  |  | 0 | 33.6 | 33.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047694 | RELW RESD OH PRI ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-06 | 2020-12-01 | COMP | 2020-10-06 | [16 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117269151 | POLE_BROK_REPL - 21925 LYONS BALD MTN SW | 35188808 |  |  | STS-POLE_BROK_REPL - 21925 LYONS BALD MT | UNSC | UNSC srdy | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0212 | -120.3195 |  | TIER 2 | 41 | 16335-1702, CURTIS | T35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.2 | 40.2 |  |  | 0 | 40.2 | 40.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048816 | OH PRI REMT NOAC PRTO RELW ESTR GO FMOB TER2 | Pole | 2020-10-13 | 2020-10-13 | COMP | 2020-10-13 | [16 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 28353.02 | 405.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117269187 | POLE_BROK_REPL - 22224[ENTR]FORTUNA MINE | 35188813 |  |  | STS-POLE_BROK_REPL - 22224[ENTR]FORTUNA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0264 | -120.2974 |  | TIER 2 | 41 | 16335-1702, CURTIS | T35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.6 | 18.6 |  |  | 0 | 18.6 | 18.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047910 | RELW OH PRI ESTR REMT GO BTKA FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-12-03 | COMP | 2020-10-12 | [16 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117269220 | POLE_BROK_REPL - R/O 22251 VALISPHOENIX | 35188819 |  |  | STS-POLE_BROK_REPL - R/O 22251 VALISPHOE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0261 | -120.3199 |  | TIER 2 | 41 | 16335-1702, CURTIS | T35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.8 | 22.8 |  |  | 0 | 22.8 | 22.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048381 | RELW OH PRI JPOL REMT ESTR USA FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-10-15 | COMP | 2020-10-15 | [16 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 7695.29 | 538.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117269232 | POLE_BROK_REPL - 21925 LYONS BALD MTN SW | 35188823 |  |  | STS-POLE_BROK_REPL - 21925 LYONS BALD MT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0207 | -120.3198 |  | TIER 2 | 41 | 16335-1702, CURTIS | T35 | 71773 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.9 | 26.9 |  |  | 0 | 26.9 | 26.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048818 | RELW OH PRI RESD ESTR BTKA PROG FMOB TER2 PRTO | Pole | 2020-09-28 | 2020-09-28 | COMP | 2020-09-28 | [16 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 11934.95 | 205.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117269591 | POLE_BROK_REPL - 22052 YERBA SANTA 1NPHO | 35188834 |  |  | STS-POLE_BROK_REPL - 22052 YERBA SANTA 1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0234 | -120.3174 |  | TIER 2 | 41 | 16335-1702, CURTIS | T35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.4 | 16.4 |  |  | 0 | 16.4 | 16.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048376 | RELW OH PRI REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-05 | 2020-10-05 | COMP | 2020-10-05 | [16 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 7493.12 | 42.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117269711 | POLE_BROK_REPL - A/F 16211[ENTR]HIDDEN V | 35154123 |  |  | STS-POLE_BROK_REPL - A/F 16211[ENTR]HIDD | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-01-09 | Renew Permit | 38.0101 | -120.2858 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3520 | 2497 | Y | 311 |  |  | 2021-03-11 07:00 | 2021-03-11 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 33 | 33 |  |  | 0 | 33 | 33 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047746 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO | Pole | 2020-06-10 | 2020-06-11 | COMP | 2020-03-30 |  |  | 2021-02-21 | 2021-02-21 | [12 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351702 | 19720.49 | 215.7 |  |  |  | 71.9 |  | 71.9 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117269766 | POLE_BROK_REPL - A/F 16211[ENTR]HIDDEN V | 35188839 |  |  | STS-POLE_BROK_REPL - A/F 16211[ENTR]HIDD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0104 | -120.2862 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3520 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.4 | 15.4 |  |  | 0 | 15.4 | 15.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047745 | RELW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-05 | 2020-11-25 | COMP | 2020-10-05 | [16 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117270325 | POLE_BROK_REPL - 14900[ENTR]LAKESIDEPHOE | 35184166 |  |  | B3 -POLE_BROK_REPL - 14900[ENTR]LAKESIDE | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0017 | -120.317 |  | TIER 2 | 157 | 16335-1704, CURTIS | T3522 | 49231 | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Dispatched | CLICK | [6 empty] | 41.7 | 41.7 |  |  | 0.5 | 41.2 | 41.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101045408 | PRI OH RELW CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-06 | 2020-10-23 | COMP | 2020-10-06 |  |  | 2020-10-21 | 2020-10-21 | [12 empty] | 2019-05-18 | 2020-05-18 | 2021-06-18 | 2021-06-18 | Work Plan Reconcilation (B-Tags) | 2020-05-18 | W. Sac |  | 163351704 | 21929.08 | 6280.8 | -4691 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-07-21
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117270377 | POLE_BROK_REPL - A/F 21886 FORTUNA MINE | 35188863 |  |  | STS-POLE_BROK_REPL - A/F 21886 FORTUNA M | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0209 | -120.2926 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3515 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 19.8 | 19.8 |  |  | 0 | 19.8 | 19.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047682 | RELW OH PRI RESD ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-10-08 | 2020-12-13 | COMP | 2020-10-06 | [16 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 10724.62 | 236.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117270569 | POLE_BROK_REPL - 15600[MB]BEAR CUB CTPHO | 35154139 |  |  | STS-POLE_BROK_REPL - 15600[MB]BEAR CUB C | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-12-31 |  | 38.0057 | -120.3016 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3519 | 23259 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.4 | 39.4 |  |  | 0 | 39.4 | 39.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046100 | RELW OH PRI CLR RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2021-01-28 | 2021-01-29 | COMP | 2020-05-05 |  |  | 2021-01-29 | 2021-01-29 | [12 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 163351702 | 21498 | 280.2 |  |  |  | 199.2 |  | 199.2 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117270713 | POLE_BROK_REPL - 15608 BEAR CUB CT[SERVI | 35188885 |  |  | STS-POLE_BROK_REPL - 15608 BEAR CUB CT[S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0055 | -120.2998 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3519 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.4 | 14.4 |  |  | 0 | 14.4 | 14.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046092 | OH PRI RESD ESTR REAR USA FMOB TER2 PRTO RELW | Pole | 2020-09-25 | 2020-09-25 | COMP | 2020-09-25 | [16 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117271614 | POLE_DECA_REPL - 16080[ENTR]HIDDEN VALLE | 35188901 |  |  | STS-POLE_DECA_REPL - 16080[ENTR]HIDDEN V | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0115 | -120.2894 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3520 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 41.1 | 41.1 |  |  | 0 | 41.1 | 41.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101047735 | RELW OH PRI ESTR GO BTKA PROG FMOB TER2 PRTO | Pole | 2021-01-19 | 2021-01-29 | COMP | 2020-10-07 |  |  | 2021-01-16 | 2021-01-16 | [12 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 20220.34 | 273.6 | 53.4 | 53.4 | 53.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117272542 | POLE_BROK_REPL - A/F 15970[ENTR]HIDDEN V | 35188924 |  |  | STS-POLE_BROK_REPL - A/F 15970[ENTR]HIDD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.011 | -120.292 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3520 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.8 | 20.8 |  |  | 0 | 20.8 | 20.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047726 | RELW OH GO PRI ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-30 | 2020-11-25 | COMP | 2020-09-30 | [16 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 16466.05 | 173.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117300361 | POLE_BROK_REPL - 15540[MB]BEAR CUB CT 1W | 35188993 |  |  | STS-POLE_BROK_REPL - 15540[MB]BEAR CUB C | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0047 | -120.3025 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3518 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.7 | 13.7 |  |  | 0 | 13.7 | 13.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046357 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-05 | 2020-10-05 | COMP | 2020-10-05 | [16 empty] | 2019-05-22 | 2020-05-22 |  | 2020-05-22 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 5710.46 | 157.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117069099 | POLE_BROK_REPL - 16071 AVENIDA DEL SOLPH | 35188124 |  |  | STS-POLE_BROK_REPL - 16071 AVENIDA DEL S | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.994 | -120.2931 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3505 | 22955 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 46 | 45.8 | 0.2 |  | 0 | 46 | 45.8 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033553 | RELW OH PRI CLR JPOL RESD REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-02 | 2021-01-16 | COMP | 2020-10-02 |  |  | 2021-01-16 | 2021-01-16 | [12 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 19686.49 | 544.9 | 106.7 | 106.7 | 106.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117075452 | POLE_BROK_REPL - 15409 CAMINO DEL PARQUE | 35188163 |  |  | STS-POLE_BROK_REPL - 15409 CAMINO DEL PA | CONS | CONS ERDY SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0079 | -120.3055 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3518 | 23253 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43.3 | 43.1 | 0.2 |  | 0 | 43.3 | 43.1 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046504 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-10-16 | 2021-01-19 | COMP | 2020-10-16 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-04-22 | 2020-04-22 |  | 2020-04-22 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 23052.88 | 201.5 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117076794 | POLE_BROK_REPL - 15559 DEL PARQUE CT PHO | 35188169 |  |  | STS-POLE_BROK_REPL - 15559 DEL PARQUE CT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0091 | -120.3023 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3518 | 23253 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37 | 37 |  |  | 0 | 37 | 37 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046480 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA USA PROG FMOB PRTO TER2 | Pole | 2020-10-01 | 2021-01-17 | COMP | 2020-10-01 |  |  | 2021-01-17 | 2021-01-17 | [12 empty] | 2019-04-22 | 2020-04-22 |  | 2020-04-22 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 21528.73 | 105.3 | 53.4 | 53.4 | 53.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117232923 | POLE_DECA_REPL - 16261 HIDDEN VALLEY RD/ | 35189188 |  |  | STS-POLE_DECA_REPL - 16261 HIDDEN VALLEY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0104 | -120.2844 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3616 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.4 | 15.4 |  |  | 0 | 15.4 | 15.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056545 | RELW OH PRI INSP CLR RESD FIRE ESTR FMOB TER2 | Pole | 2020-10-06 | 2021-01-16 | COMP | 2020-10-06 |  |  | 2021-01-16 | 2021-01-16 | [12 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 9438.29 | 53.4 | 53.4 | 53.4 | 53.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117249517 | POLE_DECA_REPL - 21922 EL COYOTE PHOENIX | 35189362 |  |  | STS-POLE_DECA_REPL - 21922 EL COYOTE PHO | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0196 | -120.3069 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3513 | 9111 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43.3 | 43.3 |  |  | 0 | 43.3 | 43.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101046996 | RELW OH PRI CLR JPOL RESD BTKA ESTR GO PROG FMOB TER2 PRTO | Pole | 2020-10-15 | 2021-01-19 | COMP | 2020-10-15 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 27555.32 | 390.5 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117258565 | POLE_BROK_REPL - 21783 EL LOBO CENTER PH | 35189481 |  |  | STS-POLE_BROK_REPL - 21783 EL LOBO CENTE | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0171 | -120.3083 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3513 | 821655 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 40 | 40 |  |  | 0 | 40 | 40 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046979 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-05 | 2021-01-16 | COMP | 2020-10-05 |  |  | 2021-01-16 | 2021-01-16 | [12 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 19100.91 | 53.4 | 53.4 | 53.4 | 53.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117262701 | POLE_BROK_REPL - 21302[ENTR]PHEONIX LAKE | 35189506 |  |  | STS-POLE_BROK_REPL - 21302[ENTR]PHEONIX | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0089 | -120.3004 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3519 | 8000 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.7 | 40 | 1.7 |  | 0 | 41.7 | 40 | 1.7 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047667 | RELW OH PRI CLR JPOL PUBL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-06 | 2021-01-16 | COMP | 2020-10-06 |  |  | 2021-01-16 | 2021-01-16 | [12 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 28310.96 | 101.4 | 53.4 | 53.4 | 53.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117267944 | POLE_BROK_REPL - 22382[ENTR]FORTUNA MINE | 35188699 |  |  | STS-POLE_BROK_REPL - 22382[ENTR]FORTUNA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0287 | -120.2951 |  | TIER 2 | 41 | 16335-1702, CURTIS | T35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.3 | 16.3 |  |  | 0 | 16.3 | 16.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047922 | RELW OH PRI BTKA REMT ESTR FMOB TER2 PRTO | Pole | 2020-10-02 | 2021-01-17 | COMP | 2020-10-02 |  |  | 2021-01-17 | 2021-01-17 | [12 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 10337.09 | 91.4 | 53.4 | 53.4 | 53.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117268141 | POLE_BROK_REPL - R/O 14904 SENA [500 FT | 35188768 |  |  | STS-POLE_BROK_REPL - R/O 14904 SENA [500 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0124 | -120.3131 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3517 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.8 | 27.8 |  |  | 0 | 27.8 | 27.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046320 | RELW OH PRI NOAC ESTR FMOB TER2 PRTO | Pole | 2020-09-27 | 2020-11-20 | COMP | 2020-09-27 | [16 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | PHOENIX LAKE-CEDAR RIDGE | Sonora |  |  | OPEN | 117268733 | POLE_BROK_REPL - 15378 POCO CALLE PHOENI | 35188792 |  |  | STS-POLE_BROK_REPL - 15378 POCO CALLE PH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0149 | -120.3072 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3513 | 9111 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 62.3 | 62.1 | 0.2 |  | 0 | 62.3 | 62.1 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046956 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-29 | 2021-01-15 | COMP | 2020-09-29 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 28449.09 | 233.2 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | RAYMOND | Mariposa |  |  | OPEN | 116815276 | POLE_BROK_REPL - A/F 34157[MB]RD 600/2PN | 35215567 |  |  | STS-POLE_BROK_REPL - A/F 34157[MB]RD 600 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2464 | -119.8828 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008191 | 5516 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101023365 | RELW OH PRI PUBL RESD REMT TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 1 | 53.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | RAYMOND | Mariposa |  |  | OPEN | 116815650 | POLE_DECA_REPL - 34149 RD 600/1PNRAYMOND | 35214479 |  |  | STS-POLE_DECA_REPL - 34149 RD 600/1PNRAY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.2483 | -119.8809 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008191 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101023361 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 1 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | RAYMOND | Mariposa |  |  | OPEN | 117149430 | POLE_DECA_REPL - 42037 RD800 3PS/ORAYMON | 35215124 |  |  | STS-POLE_DECA_REPL - 42037 RD800 3PS/ORA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3619 | -119.827 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000006206 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.6 | 16.6 |  |  | 0 | 16.6 | 16.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101068713 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-01 | 2021-02-01 | COMP | 2021-02-01 | [16 empty] | 2019-05-02 | 2020-05-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254452102 | 5984.51 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 116861738 | POLE_DECA_REPL - 37072 RD 606/3PNRAYMOND | 35215179 |  |  | STS-POLE_DECA_REPL - 37072 RD 606/3PNRAY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2318 | -119.8713 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008194 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059432 | RELW OH PRI CLR REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 116865694 | POLE_DECA_REPL - 33497 RD 415 #4 S/O RDR | 35215414 |  |  | STS-POLE_DECA_REPL - 33497 RD 415 #4 S/O | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2338 | -119.8836 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008194 | 5516 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059478 | RELW OH PRI CLR REMT ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 1 | 77.6 | 64.1 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 116808337 | POLE_DECA_REPL - 38868[HSE]RD 600/5PW/1P | 35083030 |  |  | STS-POLE_DECA_REPL - 38868[HSE]RD 600/5P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3108 | -119.7995 |  | TIER 2 | 256 | 25442-1101, OAKHURST | 0000007203 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 9.6 | 9.6 |  |  | 0 | 9.6 | 9.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101024705 | RELW OH SEC CLR REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-02 | 2020-12-02 | COMP | 2020-12-02 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-09-28 | 2020-09-28 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254421101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 116861903 | POLE_DECA_REPL - 37072 RD 606/2PNRAYMOND | 35083060 |  |  | STS-POLE_DECA_REPL - 37072 RD 606/2PNRAY | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2305 | -119.8711 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008194 |  | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-08 16:00 | Scheduled | CLICK | [6 empty] | 68.2 | 68.2 |  |  | 1.5 | 67.2 | 67.2 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101059431 | RELW OH PRI CLR REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-11-24 | 2020-11-24 | COMP | 2020-11-24 | [16 empty] | 2019-03-29 | 2019-09-29 | 2020-08-15 | 2020-08-15 | B-Tag Addition 06.24.20 | 2020-03-29 | W. Sac |  | 254432104 | 8701.71 | 1538.9 | 1495.8 | 1427 | 1427 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-06-29
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 116871743 | POLE_DECA_REPL - #1 W/O 36772 RD 606 #3 | 35178952 |  |  | STS-POLE_DECA_REPL - #1 W/O 36772 RD 606 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2236 | -119.8744 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008194 |  | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-15 16:00 | Dispatched | CLICK | [6 empty] | 41.1 | 41.1 |  |  | 0 | 41.1 | 41.1 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 103088055 | RELW OH PRI CLR REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-06-23 | 2020-06-23 | COMP | 2020-06-23 | [16 empty] | 2019-03-30 | 2020-03-30 | 2020-08-15 | 2020-08-15 | B-Tag Addition 06.24.20 |  | Bakersfield |  | 254432104 | 444957.75 | 11769.4 | -16503.6 | 9.4 | 9.4 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 116871837 | POLE_DECA_REPL - #1 W/O 36772 RD 606 #3 | 35178953 |  |  | STS-POLE_DECA_REPL - #1 W/O 36772 RD 606 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2233 | -119.8775 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008194 |  | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-15 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 19.5 | 40 | 40 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101059314 | RELW OH PRI CLR REMT ESTR GO USA FMOB TER2 PRTO FSRP | Pole | 2020-06-23 | 2020-06-23 | COMP | 2020-06-23 | [16 empty] | 2019-03-30 | 2020-03-30 | 2020-08-15 | 2020-08-15 | B-Tag Addition 06.24.20 |  | Bakersfield |  | 254432104 | 17518.31 | 13087.3 | 2725.8 | 762.9 | 762.9 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 116872472 | POLE_DECA_REPL - #1 W/O 36772 RD 606 #3 | 35178955 |  |  | STS-POLE_DECA_REPL - #1 W/O 36772 RD 606 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2207 | -119.88 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008194 |  | Y | 311 |  |  | 2021-03-16 07:00 | 2021-03-16 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 1 | 40 | 40 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101059320 | OH RELW NOAC PRI CLR REMT ESTR GO USA PROG FMOB TER2 PRTO FSRP | Pole | 2020-07-03 | 2020-07-16 | COMP | 2020-07-03 | [16 empty] | 2019-03-30 | 2020-03-30 | 2020-08-15 | 2020-08-15 | B-Tag Addition 06.24.20 |  | Bakersfield |  | 254432104 | 28770.43 | 9105.2 | 110.1 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 116881155 | POLE_DECA_REPL - 32632[HSE]BLUFF DR/2PS/ | 35086156 |  |  | STS-POLE_DECA_REPL - 32632[HSE]BLUFF DR/ | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.22 | -119.8353 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008194 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 18.2 | 18.2 |  |  | 0 | 18.2 | 18.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059581 | RELW OH PRI CLR REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-07-20 | 2020-07-20 | COMP | 2020-07-20 | [16 empty] | 2019-04-01 | 2019-10-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | QUES |  | 254432104 | 10647.23 | 45.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 116951931 | POLE_DECA_REPL - 41280[MB]RD 800/1PN/4PW | 35208794 |  |  | STS-POLE_DECA_REPL - 41280[MB]RD 800/1PN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.3475 | -119.8249 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000007202 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25 | 25 |  |  | 0 | 25 | 25 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101068123 | RELW OH PRI REMT FIRE ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-26 | 2021-01-25 | COMP | 2021-01-25 | [16 empty] | 2019-04-03 | 2020-04-03 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 11112.89 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 116954679 | POLE_DECA_REPL - 40717[HSE]RD 800/1PE/6P | 35208819 |  |  | STS-POLE_DECA_REPL - 40717[HSE]RD 800/1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3395 | -119.8137 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000007202 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.3 | 22.3 |  |  | 0 | 22.3 | 22.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101068232 | RELW OH PRI CLR REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-02-09 | 2021-02-11 | COMP | 2021-02-09 | [16 empty] | 2019-04-03 | 2020-04-03 | 2020-08-31 | 2020-08-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 8540.19 | 45.9 | 32.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 116963394 | POLE_DECA_REPL - 40170[HSE]BETSY JACOBS | 35178573 |  |  | STS-POLE_DECA_REPL - 40170[HSE]BETSY JAC | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3561 | -119.798 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000007202 |  | Y | 311 |  |  | 2021-03-09 07:00 | 2021-03-09 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 27.8 | 27.8 |  |  | 0 | 27.8 | 27.8 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101068148 | RELW OH PRI CLR REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-06-25 | 2020-06-25 | COMP | 2020-06-24 | [16 empty] | 2019-04-05 | 2020-04-05 | 2020-08-14 | 2020-08-14 | B-Tag Addition 06.24.20 |  | Santa Rosa |  | 254452102 | 13319.25 | 1547.3 | 122.6 | 122.6 | 122.6 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 117001340 | POLE_DECA_REPL - 36049 GRANITE RD/5PW/6P | 35178520 |  |  | STS-POLE_DECA_REPL - 36049 GRANITE RD/5P | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.211 | -119.8844 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008195 |  | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-15 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101059599 | RELW OH PRI REMT FIRE NOAC SWRK ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-06-04 | 2020-07-24 | COMP | 2020-06-04 | [16 empty] | 2019-04-10 | 2020-04-10 | 2020-08-16 | 2020-08-16 | B-Tag Clean Up 6/8/2020 |  | Fresno |  | 254432104 | 6462.81 | 7338.4 | -16849.4 | 865 | 865 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-06-08
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 117001395 | POLE_DECA_REPL - 36049 GRANITE RD/5PW/8P | 35178521 |  |  | STS-POLE_DECA_REPL - 36049 GRANITE RD/5P | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2123 | -119.8844 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008195 |  | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-15 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101059603 | RELW OH PRI REMT FIRE NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-07-01 | 2020-07-06 | COMP | 2020-06-09 | [16 empty] | 2019-04-10 | 2020-04-10 | 2020-08-16 | 2020-08-16 | Work Plan Reconcilation (B-Tags) |  | Fresno |  | 254432104 | 5717.02 | 8497.8 | -16598.7 | 865 | 865 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-07-21
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 117001744 | POLE_DECA_REPL - 32770 RD 600/2PN/2PERAY | 35209105 |  |  | STS-POLE_DECA_REPL - 32770 RD 600/2PN/2P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2242 | -119.9005 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008193 | 6201 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.6 | 39.6 |  |  | 0 | 39.6 | 39.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059238 | RELW OH PRI CLR JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-03 | 2021-02-03 | COMP | 2021-02-03 | [16 empty] | 2019-04-10 | 2020-04-10 | 2020-05-31 | 2020-05-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 18786.51 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Raymond | Oakhurst |  |  | OPEN | 119972958 | POLE_BROK_REPL - #2 W/O 36528 RD 606Raym | 35211323 |  |  | STS-POLE_BROK_REPL - #2 W/O 36528 RD 606 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-05 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2157 | -119.8806 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 0000008194 | 10576 | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101059273 | RELW OH PRI CREW CLR REMT FIRE NOAC SWRK ESTR USA FMOB TER2 | Pole | 2020-11-23 | 2020-11-23 | COMP | 2020-11-23 | [16 empty] | 2020-11-02 | 2021-02-02 |  | 2021-02-02 | B tag clean up 11/8/2020 |  | Fresno |  | 254432104 | 9591 | 698 | 684.6 | [5 empty] | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-11-08
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 116949885 | POLE_DECA_REPL - 41280[MB]RD 800/1PN/7PW | 35208774 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3545 | -119.8284 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000007202 |  | Y | 311 |  |  | 2021-03-03 06:35 | 2021-03-03 11:09 | Scheduled | CLICK | [6 empty] | 0.8 | 0.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101068137 | RELW OH PRI CLR REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-01-20 | COMP | 2021-01-20 | [16 empty] | 2019-04-03 | 2020-04-03 | 2020-09-22 | 2020-09-22 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 6145.27 | 1036.1 | 1022.6 | 978 | 978 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 116951086 | POLE_DECA_REPL - 41280[MB]RD 800/1PN/5PW | 35208781 |  |  | STS-POLE_DECA_REPL - 41280[MB]RD 800/1PN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3479 | -119.8258 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000007202 |  | Y | 311 |  |  | 2021-06-25 07:00 | 2021-06-25 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101068125 | RELW OH PRI CLR REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-04 | 2021-01-04 | COMP | 2021-01-04 | [16 empty] | 2019-04-03 | 2020-04-03 | 2020-08-31 | 2020-08-31 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 9398.36 | 13.5 | 0 | 624.5 | 624.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | RAYMOND | Oakhurst |  |  | OPEN | 116955199 | POLE_DECA_REPL - 40300[HSE]RD 800/2PNERA | 35208829 |  |  | STS-POLE_DECA_REPL - 40300[HSE]RD 800/2P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.3392 | -119.8216 |  | TIER 2 | 1210 | 25445-2102, MARIPOSA | 0000007202 |  | Y | 311 |  |  | 2021-06-29 07:00 | 2021-06-29 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101068172 | RELW OH PRI CLR REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-29 | 2020-12-29 | COMP | 2020-12-29 | [16 empty] | 2019-04-04 | 2020-04-04 | 2020-10-23 | 2020-10-23 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254452102 | 6274.53 | 943.5 | 930.1 | 362 | 362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SHILLING | Mariposa |  |  | OPEN | 117065993 | POLE_WOOD_REPL - 9090 LAKE MC CLURE RD/1 | [6 empty] | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 37.5466 | -120.2869 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 0000004155 |  | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Woodpecker Damage | Replace |  | 101196473 | REGW OH PRI CLR REMT JAR BTKA FMOB TER2 PRTO | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-04-19 | 2019-10-19 |  | 2019-10-19 | Tags converted to Pole Replacement |  | UNASSIGNED |  | 252811102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-03-23
Bay/Central | YO | SNELLING | Mariposa |  |  | OPEN | 117072766 | POLE_DECA_REPL - #22 S/O 9558 MCCLURE PT | 35215542 |  |  | STS-POLE_DECA_REPL - #22 S/O 9558 MCCLUR | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5823 | -120.2975 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 0000004154 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101195797 | RELW ESTR OH PRI REMT BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252811102 | 1 | 13.5 | 0 | 1304 | 1304 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SNELLING | Mariposa |  |  | OPEN | 117072206 | POLE_BROK_REPL - 9090 LAKE MC CLURE RD/1 | 35093803 |  |  | STS-POLE_BROK_REPL - 9090 LAKE MC CLURE | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5548 | -120.2891 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 0000004155 |  | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | [6 empty] | 61.6 | 61.6 |  |  | 0 | 61.6 | 61.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101196484 | RELW OH PRI CLR REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-04-27 | 2020-04-27 | COMP | 2020-04-27 | [16 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | circuit based plan 2.14 | 2020-05-20 | TRC |  | 252811102 | 23614.25 | 1701.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | SNELLING | Mariposa |  |  | OPEN | 117072246 | POLE_DECA_REPL - 9090 LAKE MC CLURE RD/1 | 35154782 |  |  | STS-POLE_DECA_REPL - 9090 LAKE MC CLURE | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5559 | -120.2898 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 0000004155 |  | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | [6 empty] | 19.3 | 19.3 |  |  | 0 | 19.3 | 19.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101196487 | RELW OH PRI CLR REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-05-07 | 2020-05-07 | COMP | 2020-05-07 | [16 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 252811102 | 6859.76 | 1368 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | SNELLING | Mariposa |  |  | OPEN | 117072760 | POLE_DECA_REPL - #22 S/O 9558 MCCLURE PT | 35209642 |  |  | STS-POLE_DECA_REPL - #22 S/O 9558 MCCLUR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5831 | -120.2968 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 0000004154 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.1 | 15.1 |  |  | 0 | 15.1 | 15.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101195795 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-23 | 2020-12-23 | COMP | 2020-12-23 | [16 empty] | 2019-04-21 | 2020-04-21 | 2020-09-29 | 2020-09-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252811102 | 7819.07 | 53.8 | 0 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SNELLING | Mariposa |  |  | OPEN | 117072749 | POLE_DECA_REPL - #22 S/O 9558 MCCLURE PT | 35093054 |  |  | STS-POLE_DECA_REPL - #22 S/O 9558 MCCLUR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.584 | -120.2946 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 0000004154 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101195790 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-08 | 2020-12-11 | COMP | 2020-12-07 | [16 empty] | 2019-04-21 | 2019-10-31 | 2020-09-29 | 2020-09-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 252811102 | 8906.81 |  | -868.8 | 652.2 | 652.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SNELLING | Oakhurst |  |  | OPEN | 117072355 | POLE_DECA_REPL - #22 S/O 9558 MCCLURE PT | 35215481 |  |  | STS-POLE_DECA_REPL - #22 S/O 9558 MCCLUR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.5643 | -120.2874 |  | TIER 2 | 163 | 25281-1102, MERCED FALLS | 0000004154 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101196348 | RELW OH PRI CLR REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252811102 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116979031 | POLE_BROK_REPL - 18150 CALLE OESTESONORA | 35187572 |  |  | STS-POLE_BROK_REPL - 18150 CALLE OESTESO | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.9518 | -120.3845 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3323 | 19686 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 63.7 | 62.9 | 0.8 |  | 0 | 63.7 | 62.9 | 0.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041601 | RELW ESTR OH PRI RESD BTKA USA FMOB TER2 PRTO | Pole | 2020-09-23 | 2021-02-03 | COMP | 2020-09-23 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 28046.77 | 119.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116979529 | POLE_DECA_REPL - 18180 CALLE OESTE SONOR | 35187588 |  |  | STS-POLE_DECA_REPL - 18180 CALLE OESTE S | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.9526 | -120.3832 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3323 | 19686 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 59.6 | 58.8 | 0.8 |  | 0 | 59.6 | 58.8 | 0.8 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101041594 | RELW OH PRI JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-26 | 2021-02-03 | COMP | 2020-08-26 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 33208.59 | 240.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116981872 | POLE_DECA_REPL - 18260 AVENIDA BONITA SO | 35187682 |  |  | STS-POLE_DECA_REPL - 18260 AVENIDA BONIT | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.9534 | -120.3854 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3323 | 19687 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 56.9 | 55.3 | 1.6 |  | 0 | 56.9 | 55.3 | 1.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101041521 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-18 | 2021-02-03 | COMP | 2020-09-18 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 27492.25 | 600.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116985584 | POLE_DECA_REPL - 11816 CAMPO SECO SONORA | 35187840 |  |  | STS-POLE_DECA_REPL - 11816 CAMPO SECO SO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9568 | -120.3868 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3323 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.7 | 31.9 | 0.8 |  | 0 | 32.7 | 31.9 | 0.8 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101041728 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-21 | 2021-02-03 | COMP | 2020-09-21 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 15419.24 | 257.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116986691 | POLE_BROK_REPL - 11762 CAMPO SECO RD/2PS | 35187918 |  |  | STS-POLE_BROK_REPL - 11762 CAMPO SECO RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9538 | -120.3892 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3322 | 1843 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.2 | 29.2 |  |  | 0 | 29.2 | 29.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041354 | RELW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-11-25 | 2020-11-23 | COMP | 2020-10-12 | [16 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 13099.51 | 452.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116990588 | POLE_DECA_REPL - 113 SUNSETSONORA95370 | 35209067 |  |  | STS-POLE_DECA_REPL - 113 SUNSETSONORA953 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land JointPole |  |  | 37.9768 | -120.3819 |  | TIER 2 | 492 | 16335-1701, CURTIS | U3313 | 4869 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 75 | 75 |  |  | 0 | 75 | 75 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101045009 | OH PRI PGEA CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP RELW | Pole | 2021-02-16 |  | COMP | 2021-02-16 | [16 empty] | 2019-04-09 | 2020-04-09 | 2020-10-19 | 2020-10-19 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163351701 | 36126.79 | 296.1 | 296.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116990823 | POLE_BROK_REPL - 18430 AVENIDA BONITA/1P | 35187949 |  |  | STS-POLE_BROK_REPL - 18430 AVENIDA BONIT | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.9593 | -120.377 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3324 | 1241 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.4 | 44.4 |  |  | 0 | 44.4 | 44.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041877 | RELW OH PRI NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2020-10-14 |  | COMP | 2020-10-14 | [16 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116990940 | POLE_DECA_REPL - 238 SUNSETSONORA95370 | 35209085 |  |  | STS-POLE_DECA_REPL - 238 SUNSETSONORA953 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Enviro JointPole |  |  | 37.9764 | -120.3836 |  | TIER 2 | 492 | 16335-1701, CURTIS | U3313 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.4 | 41.4 |  |  | 0 | 41.4 | 41.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101045017 | RELW OH PRI JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2019-04-09 | 2020-04-09 | 2020-10-19 | 2020-10-19 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163351701 | 21245.77 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117004000 | POLE_BROK_REPL - 18330 WARDS FERRY RD 1P | 35154327 |  |  | STS-POLE_BROK_REPL - 18330 WARDS FERRY R | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9565 | -120.3295 |  | TIER 2 | 318 | 16335-1705, CURTIS | U3425 | 20353 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 76.4 | 75.4 | 1 |  | 0 | 76.4 | 75.4 | 1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101043573 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 FSRP PRTO | Pole | 2020-05-29 |  | COMP | 2020-05-29 |  |  | 2021-01-14 | 2021-01-14 | [12 empty] | 2019-04-10 | 2020-04-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | CALENG |  | 163351705 | 35771.76 | 45.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117017052 | POLE_BROK_REPL - 15355 WARDS FERRYSONORA | 35188210 |  |  | STS-POLE_BROK_REPL - 15355 WARDS FERRYSO | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.9028 | -120.295 |  | TIER 2 | 72 | 16335-1703, CURTIS | W35 | 64799 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.9 | 39.9 |  |  | 0 | 39.9 | 39.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029525 | RELW PRI OH CLR RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-09-24 | 2021-02-03 | COMP | 2020-09-24 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-12 | 2020-04-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 16821.8 | 226.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117021430 | POLE_BROK_REPL - E\OF\ENT 17122 COUNTRY | 35188339 |  |  | STS-POLE_BROK_REPL - E\OF\ENT 17122 COUN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.9388 | -120.2668 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.5 | 14.5 |  |  | 0 | 14.5 | 14.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047263 | RELW OH PRI RESD REMT FLAG ESTR BTKA USA PRTO FMOB TER2 | Pole | 2020-09-16 |  | COMP | 2020-09-16 | [16 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 11808.53 | 302.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117021572 | POLE_BROK_REPL - E\OF\ENT 17070 COUNTRY | 35188355 |  |  | STS-POLE_BROK_REPL - E\OF\ENT 17070 COUN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.9383 | -120.2662 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 | L1765 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43.9 | 43.9 |  |  | 0 | 43.9 | 43.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047264 | RELW OH PRI CLR RESD REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-21 |  | COMP | 2020-09-21 | [16 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 21587.03 | 543 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117023332 | POLE_BROK_REPL - 25855 RICHARDS RANCH RD | 35209391 |  |  | STS-POLE_BROK_REPL - 25855 RICHARDS RANC | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.8787 | -120.3088 |  | TIER 2 | 72 | 16335-1703, CURTIS | W35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029705 | RELW OH PRI CLR REMT NOAC ESTR REAR USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2020-11-13 | 2020-11-13 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163351703 | 1 | 2717.5 | 2636.8 | 2636.8 | 2636.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117024745 | POLE_BROK_REPL - N\OF\ENT 17330 SPARROW | 35154548 |  |  | STS-POLE_BROK_REPL - N\OF\ENT 17330 SPAR | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD | 2021-01-09 | Renew Permit | 37.9379 | -120.277 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 | L1767 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047844 | RELW OH PRI CLR RESD REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2021-02-19 | 2021-02-19 | [12 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-12-31 | CALENG |  | 163351703 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117027024 | POLE_BROK_REPL - 26505 RICHARDS RANCH RD | 35188507 |  |  | STS-POLE_BROK_REPL - 26505 RICHARDS RANC | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.8879 | -120.3009 |  | TIER 2 | 72 | 16335-1703, CURTIS | W35 | S1965 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 179.1 | 179.1 |  |  | 0 | 179.1 | 179.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029610 | RELW OH PRI CLR JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-10-05 |  | COMP | 2020-10-05 | [16 empty] | 2019-04-14 | 2020-04-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 59399.8 | 397.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117064701 | POLE_BROK_REPL - 14925 LOS ROBLES RDSONO | 35188027 |  |  | STS-POLE_BROK_REPL - 14925 LOS ROBLES RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9852 | -120.3166 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3507 | 37150 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 82.7 | 80.8 | 1.9 |  | 0 | 82.7 | 80.8 | 1.9 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032389 | RELW OH PRI JPOL REMT TRAF ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-08-27 |  | COMP | 2020-08-27 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-19 | 2020-04-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 34159.6 | 162.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117069254 | POLE_BROK_REPL - 20150 WAIF MINE RD/1PW | 35215402 |  |  | STS-POLE_BROK_REPL - 20150 WAIF MINE RD/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9858 | -120.3112 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3507 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032413 | RELW OH SERV REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117111655 | POLE_BROK_REPL - 21700 SPRINGFIELD RD/2P | 35093022 |  |  | STS-POLE_BROK_REPL - 21700 SPRINGFIELD R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.0176 | -120.415 |  | TIER 2 | 165 | 16376-1703, RACETRACK | T3214 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101043175 | RELW OH PRI CLR JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-04-27 | 2019-08-27 |  | 2019-08-27 | 2021 CBP Plan | 2019-11-19 | TRC |  | 163761703 | 1 | 90.8 |  |  |  | 90.8 |  | 90.8 |  | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117118536 | POLE_BROK_REPL - 19357 BOSTWICK RD SONOR | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 37.9741 | -120.4391 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U32 | 97729 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103370704 | REGW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 163761704 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117120935 | POLE_BROK_REPL - HWY49/FRAGUEROSONORA953 | 35208815 |  |  | STS-POLE_BROK_REPL - HWY49/FRAGUEROSONOR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land Enviro JointPole |  |  | 37.9948 | -120.4349 |  | TIER 2 | 485 | 16376-1704, RACETRACK | T32 | 1001 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101044392 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163761704 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117121012 | POLE_DECA_REPL - 19615 BOSTWICK RD SONOR | 35214968 |  |  | STS-POLE_DECA_REPL - 19615 BOSTWICK RD S | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.9774 | -120.444 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U3206 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103370817 | RELW OH PRI JPOL GO RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163761704 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117122493 | POLE_DECA_REPL - 21203 CRYSTAL ROCK RDSO | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 38.0054 | -120.4187 |  | TIER 2 | 165 | 16376-1703, RACETRACK | T3219 |  | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101043058 | REGW OH PRI JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan |  | UNASSIGNED |  | 163761703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117135401 | POLE_BROK_REPL - S\OF\ENT 18920 RD\BLACK | 35154263 |  |  | STS-POLE_BROK_REPL - S\OF\ENT 18920 RD\B | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9659 | -120.2846 |  | TIER 2 | 318 | 16335-1705, CURTIS | U3616 | 27309 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 35.8 | 35.8 |  |  | 0 | 35.8 | 35.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033599 | RELW OH PRI INSP BTKA FIRE FLAG ESTR FSRP USA FMOB TER2 | Pole | 2020-05-13 |  | COMP | 2020-05-13 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-05-01 | 2020-05-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | CALENG |  | 163351705 | 24503.41 | 630.1 | 149.5 | 149.5 | 149.5 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117147427 | POLE_BROK_REPL - 18323 SHELLSONORA95370 | 35208987 |  |  | STS-POLE_BROK_REPL - 18323 SHELLSONORA95 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9561 | -120.4546 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U31 |  | Y | 311 |  |  | 2021-01-16 | 2021-01-16 | Completed | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101012491 | RELW OH SERV CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-02 | 2020-05-02 | 2020-10-21 | 2020-10-21 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163761704 | 1 | 1189.7 | 1180.9 | 1205 | 1205 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117151850 | POLE_DECA_REPL - AF 8581 WILCOX RANCH RD | 35209058 |  |  | STS-POLE_DECA_REPL - AF 8581 WILCOX RANC | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.9899 | -120.4603 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U3104 | L443 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.7 | 24.7 |  |  | 0 | 24.7 | 24.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101012741 | RELW OH PRI JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 |  | COMP | 2020-12-11 | [16 empty] | 2019-05-03 | 2020-05-03 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163761704 | 14324.44 |  | -1267 | -769.2 | -769.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117152298 | POLE_BROK_REPL - 19460 RAWHIDE ENT SONOR | 35215145 |  |  | STS-POLE_BROK_REPL - 19460 RAWHIDE ENT S | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land JointPole |  |  | 37.979 | -120.4482 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U3110 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101012319 | RELW OH PRI REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163761704 | 1 | 87 | 87 | 87 | 87 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117154706 | POLE_DECA_REPL - AF 8715 WILCOX RANCH RD | 35209078 |  |  | STS-POLE_DECA_REPL - AF 8715 WILCOX RANC | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9882 | -120.4581 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U3104 | L443 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101012752 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163761704 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117160145 | POLE_BROK_REPL - 3PS 15PE 1PN 11030 CAMP | 35187969 |  |  | STS-POLE_BROK_REPL - 3PS 15PE 1PN 11030 | UNSC | UNSC ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.9489 | -120.3903 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3302 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 14.1 | 14.1 |  |  | 0 | 14.1 | 14.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030909 | RELW OH PRI INSP JPOL REMT FIRE FLAG ESTR GO BTKA USA FMOB TER2 | Pole | 2020-10-14 | 2021-02-03 | COMP | 2020-10-14 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117160461 | POLE_DECA_REPL - 23083 HWY 49 SONORA | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 37.9924 | -120.4524 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U3105 | 299321 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101012646 | REGW OH PRI CLR RESD ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 163761704 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117162349 | POLE_DECA_REPL - 1PSE 18015 PLAZA ORIENT | 35188085 |  |  | STS-POLE_DECA_REPL - 1PSE 18015 PLAZA OR | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.9488 | -120.3813 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3304 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.1 | 31.7 | 0.4 |  | 0 | 32.1 | 31.7 | 0.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031011 | RELW OH SEC INSP RESD REMT FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-09-11 | 2021-02-03 | COMP | 2020-09-11 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 15970.27 | 452.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117168166 | POLE_BROK_REPL - 1PN 17865 VIA SERENA SO | 35188243 |  |  | STS-POLE_BROK_REPL - 1PN 17865 VIA SEREN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9456 | -120.3861 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3303 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.8 | 20.8 |  |  | 0 | 20.8 | 20.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030982 | RELW OH PRI INSP FLAG ESTR BTKA FMOB TER2 | Pole | 2020-09-27 |  | COMP | 2020-09-27 |  |  | 2020-08-04 | 2020-08-04 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 10691.96 | 520.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117168604 | POLE_BROK_REPL - 13600 KINKAID FLATS RDS | 35188264 |  |  | STS-POLE_BROK_REPL - 13600 KINKAID FLATS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.9424 | -120.3546 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3402 | 19714 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 80.9 | 68.5 | 12.4 |  | 0 | 80.9 | 68.5 | 12.4 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033129 | RELW OH PRI INSP JPOL RESD FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-09-22 |  | COMP | 2020-09-22 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 30695.84 | 181 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117168976 | POLE_BROK_REPL - 18050 CALLE OESTESONORA | 35188272 |  |  | STS-POLE_BROK_REPL - 18050 CALLE OESTESO | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.9506 | -120.3849 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3303 | 19686 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.7 | 36.7 |  |  | 0 | 36.7 | 36.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030999 | RELW OH PRI INSP JPOL RESD FIRE ESTR BTKA USA PROG FMOB TER2 | Pole | 2020-09-24 | 2021-02-03 | COMP | 2020-09-24 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 23832.95 | 481.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117169021 | POLE_BROK_REPL - 13570 KINKAID FLATS RDS | 35188278 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9424 | -120.3559 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3402 | 19714 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.1 | 31.1 |  |  | 0 | 31.1 | 31.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033128 | RELW OH PRI INSP JPOL RESD FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-09-14 | 2021-02-17 | COMP | 2020-09-14 |  |  | 2021-02-17 | 2021-02-17 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 17188.65 | 423.4 | -12069.3 | -12069.3 | -12069.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117169793 | POLE_BROK_REPL - 17945 VIA SERENA SONORA | 35188318 |  |  | STS-POLE_BROK_REPL - 17945 VIA SERENA SO | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.9485 | -120.383 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3303 | 19687 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 55.5 | 53.8 | 1.7 |  | 0 | 55.5 | 53.8 | 1.7 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031005 | RELW OH PRI INSP JPOL RESD FIRE ESTR BTKA FMOB TER2 | Pole | 2020-09-14 | 2021-02-03 | COMP | 2020-09-14 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 27206.01 | 426.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117169863 | POLE_BROK_REPL - 5PS 17951 OLD WARDS FER | 35188328 |  |  | STS-POLE_BROK_REPL - 5PS 17951 OLD WARDS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.9432 | -120.3368 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3404 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.5 | 28.5 |  |  | 0 | 28.5 | 28.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033239 | RELW OH PRI PGEA INSP RESD ESTR BTKA FMOB TER2 | Pole | 2020-09-23 | 2020-09-22 | COMP | 2020-09-22 | [16 empty] | 2019-05-06 | 2020-05-06 | 2021-07-14 | 2021-07-14 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 11517.47 | 437.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117172806 | POLE_DECA_REPL - 17960 OLD WARDS FERRY R | 35188421 |  |  | STS-POLE_DECA_REPL - 17960 OLD WARDS FER | UNSC | UNSC ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.9477 | -120.3432 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3403 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 27.6 | 27.6 |  |  | 0 | 27.6 | 27.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101033059 | RELW OH PRI INSP CLR JPOL REMT FIRE FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-09-17 | 2021-02-03 | COMP | 2020-09-17 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 13152.81 | 76.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117175743 | POLE_BROK_REPL - 2PS 17250 BLACKBIRD LNS | 35188474 |  |  | STS-POLE_BROK_REPL - 2PS 17250 BLACKBIRD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.9359 | -120.3912 |  | TIER 2 | 72 | 16335-1703, CURTIS | V33 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.5 | 19.5 |  |  | 0 | 19.5 | 19.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033125 | RELW OH PRI INSP CLR JPOL RESD FIRE ESTR GO BTKA USA PROG FMOB TER2 | Pole | 2020-09-11 |  | COMP | 2020-09-11 | [16 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 13638.82 | 486.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117180641 | POLE_BROK_REPL - 1PN 3PW 1PN 12701 ROUTE | 35188526 |  |  | STS-POLE_BROK_REPL - 1PN 3PW 1PN 12701 R | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.9447 | -120.3451 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3403 | 19706 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 63.3 | 59.7 | 3.6 |  | 0 | 63.3 | 59.7 | 3.6 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033217 | RELW OH PRI INSP JPOL RESD FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-09-21 | 2021-02-03 | COMP | 2020-09-21 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-07 | 2020-05-07 | 2021-07-13 | 2021-07-13 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117185371 | POLE_BROK_REPL - CRNR TIDWALL/RESERVOIR | 35154568 |  |  | STS-POLE_BROK_REPL - CRNR TIDWALL/RESERV | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.9995 | -120.3914 |  | TIER 2 | 165 | 16376-1703, RACETRACK | T3322 | 1637 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 72.2 | 72.2 |  |  | 0 | 72.2 | 72.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101056799 | RELW OH PRI JPOL ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-21 |  | COMP | 2021-01-21 | [16 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163761703 | 31212.49 | 135.8 | 45 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117189409 | POLE_DECA_REPL - 18415 BLUE BELLE RDSONO | 35209593 |  |  | STS-POLE_DECA_REPL - 18415 BLUE BELLE RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9574 | -120.3103 |  | TIER 2 | 318 | 16335-1705, CURTIS | U3522 | 40089 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101030611 | RELW OH PRI INSP CLR ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163351705 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117191112 | POLE_BROK_REPL - 17340 KENNEDY RDSONORA9 | 35188680 |  |  | STS-POLE_BROK_REPL - 17340 KENNEDY RDSON | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 37.9364 | -120.3506 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 | 19716 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 65 | 63.3 | 1.7 |  | 0 | 65 | 63.3 | 1.7 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031679 | RELW OH PRI INSP JPOL RESD FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-09-21 |  | COMP | 2020-09-21 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 32049.34 | 263.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117191204 | POLE_BROK_REPL - 1PW 2PS 17190 LIME KILN | 35188683 |  |  | STS-POLE_BROK_REPL - 1PW 2PS 17190 LIME | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.9354 | -120.3521 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.9 | 26.9 |  |  | 0 | 26.9 | 26.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031680 | RELW OH PRI INSP JPOL FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-09-16 | 2021-02-03 | COMP | 2020-09-16 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 18788.63 | 580.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117191915 | POLE_BROK_REPL - 1PE 6PN 7287 ES LA VIDA | 35188760 |  |  | STS-POLE_BROK_REPL - 1PE 6PN 7287 ES LA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land Enviro |  |  | 37.9405 | -120.3465 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.1 | 17.1 |  |  | 0 | 17.1 | 17.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033222 | RELW OH PRI INSP RESD REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-09-22 |  | COMP | 2020-09-22 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 8290.12 | 181 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117209709 | POLE_BROK_REPL - 11030 CAMPO SECO RDSONO | 35188947 |  |  | STS-POLE_BROK_REPL - 11030 CAMPO SECO RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9505 | -120.4056 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3301 | 91315 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 35.2 | 35.2 |  |  | 0 | 35.2 | 35.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030896 | RELW OH FIRE PRI INSP REMT TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-10-15 | 2021-02-03 | COMP | 2020-10-15 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 20643.78 | 156.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117209731 | POLE_DECA_REPL - 1PW 3PS 17084 LIME KILN | 35188952 |  |  | STS-POLE_DECA_REPL - 1PW 3PS 17084 LIME | UNSC | UNSC ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.9289 | -120.3535 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 | 19717 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 56.8 | 56.8 |  |  | 0 | 56.8 | 56.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031597 | RELW OH PRI INSP JPOL RESD REMT TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-12-03 | 2021-02-03 | COMP | 2020-10-05 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117214249 | POLE_DECA_REPL - 16840 OUTBACK TRAILSONO | 35189003 |  |  | STS-POLE_DECA_REPL - 16840 OUTBACK TRAIL | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.9213 | -120.361 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 17.1 | 17.1 |  |  | 0 | 17.1 | 17.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031528 | RELW OH PRI INSP JPOL REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-09-29 |  | COMP | 2020-09-29 | [16 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117217723 | POLE_DECA_REPL - 2PE 2PS 2PE 17140 MURPH | 35189069 |  |  | STS-POLE_DECA_REPL - 2PE 2PS 2PE 17140 M | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.9306 | -120.334 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.3 | 24.3 |  |  | 0 | 24.3 | 24.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031745 | RELW REMT OH PRI INSP FIRE NOAC ESTR USA FMOB TER2 | Pole | 2020-09-24 | 2020-09-23 | COMP | 2020-09-23 | [16 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117295277 | POLE_BROK_REPL - 8650 WILCOX RANCH RDSON | 35215545 |  |  | STS-POLE_BROK_REPL - 8650 WILCOX RANCH R | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9904 | -120.4585 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U3104 | L443 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 54.2 | 54.2 |  |  | 0 | 54.2 | 54.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101012747 | RELW OH PRI CLR JPOL RESD NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-11 | 2021-01-07 | COMP | 2021-01-07 | [16 empty] | 2019-05-21 | 2020-05-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163761704 | 20804.02 |  | 0 | 565.7 | 565.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117684863 | POLE _BROK _REPL_RO 20231 AZEVEDO DR PVT | 35216222 |  |  | STS-POLE _BROK _REPL_RO 20231 AZEVEDO DR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9891 | -120.4559 |  | TIER 2 |  |  | U3104 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 49.1 | 49.1 |  |  | 0 | 49.1 | 49.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101012722 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-02-01 |  | COMP | 2021-02-01 | [16 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 24893.66 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | COMP | 116983901 | POLE_BROK_REPL - 18288 AVENIDA BONITASON | 35154265 |  |  | STS-POLE_BROK_REPL - 18288 AVENIDA BONIT | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-11-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2021-01-09 | No Action | 37.9548 | -120.3839 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3323 | 19687 | Y | 311 |  |  | 2021-01-05 | 2021-01-05 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 66 | 66 |  |  | 0 | 66 | 66 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041532 | RELW OH PRI COMP FLAG ESTR BTKA USA CCNT FMOB TER2 PRTO | Pole | 2020-04-29 | 2020-07-12 | COMP | 2020-04-29 | COMP | 2021-01-05 | 2020-03-26 | 2020-03-26 | [11 empty] | 2021-01-15 | 2021-01-05 | 2020-04-09 |  | 2020-04-09 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351703 | 31744.4 | 18969.9 | 18587.2 | 27748.3 | 27748.3 | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 114887327 | POLE_BROK_REPL - 21271 APPLE VALLEY DR S | 35099894 |  |  | STS-POLE_BROK_REPL - 21271 APPLE VALLEY | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0077 | -120.333 |  | TIER 2 | 157 | 16335-1704, CURTIS | T3420 | L1607 | Y | 311 |  |  | 2021-03-10 07:00 | 2021-03-10 16:00 | Scheduled | CLICK | [6 empty] | 72.4 | 61 | 11.4 |  | 3.5 | 71.4 | 60 | 11.4 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031238 | RELW OH PRI INSP JPOL REMT GO BTKA REAR SCOP SCPA FMOB TER2 | Pole | 2020-04-06 | 2020-07-28 | COMP | 2020-04-05 |  |  | 2020-07-28 | 2020-07-28 | [12 empty] | 2018-08-14 | 2019-10-10 |  | 2019-10-10 | circuit based plan 2.14 | 2020-06-30 | Fresno |  | 163351704 | 35158.96 | 8191.5 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 114887493 | POLE_BROK_REPL - 21432 APPLE HILL DR SON | 35099902 |  |  | STS-POLE_BROK_REPL - 21432 APPLE HILL DR | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-01-09 | Renew Permit | 38.0098 | -120.3282 |  | TIER 2 | 157 | 16335-1704, CURTIS | T3420 | S1491 | Y | 311 |  |  | 2021-02-19 07:00 | 2021-02-19 16:00 | Completed | CLICK | [6 empty] | 53.9 | 53.9 |  |  | 0 | 53.9 | 53.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031213 | RELW OH PRI INSP JPOL REMT JAR BTKA SCOP SCPA FMOB TER2 | Pole | 2020-05-21 | 2020-07-15 | COMP | 2020-05-20 |  |  | 2021-02-21 | 2020-03-25 | [12 empty] | 2018-08-14 | 2019-10-17 |  | 2019-10-17 | circuit based plan 2.14 | 2020-05-31 | TRC |  | 163351704 | 24614.67 | 7296.2 | 4221.7 | 4221.7 | 4221.7 | 0 |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 115720061 | POLE_BROK_REPL - 26333 POWELL RANCH RD S | 35099905 |  |  | STS-POLE_BROK_REPL - 26333 POWELL RANCH | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8833 | -120.298 |  | TIER 2 | 72 | 16335-1703, CURTIS | W35 | S1965 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15 | 15 |  |  | 0 | 15 | 15 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029622 | RELW OH PRI SWRK SCOP SCPA TER2 FSRP | Pole | 2020-05-12 | 2020-05-12 | COMP | 2020-05-12 | [16 empty] | 2019-01-23 | 2019-10-23 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-20 | TRC |  | 163351703 | 5659.48 | 4727.7 | 1330.1 | 1330.1 | 1330.1 | 0 |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 115740991 | TREE_DECA_INPL - 11441 COVERED WAGON RD | 35073840 |  |  | STS-TREE_DECA_INPL - 11441 COVERED WAGON | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2020-06-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.0214 | -120.3964 |  | TIER 2 | 165 | 16376-1703, RACETRACK | T3312 | 26343 | Y | 311 |  |  | 2020-04-13 | 2020-04-17 | Completed | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 101053190 | RELW OH SERV TMAN ESTR USA TER2 | Pole | 2019-03-06 | 2019-03-06 | COMP | 2019-03-06 | [16 empty] | 2019-01-25 | 2019-09-25 |  | 2019-09-25 | Q1 Work Plan | 2019-03-06 | Fresno |  | 163761703 | 23650.02 | 84518.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116882413 | POLE_BROK_REPL - 16560 CORCORAN GRAY 2PN | 35178568 |  |  | B STS-POLE_BROK_REPL - 16560 CORCORAN G | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8678 | -120.3079 |  | TIER 2 | 72 | 16335-1703, CURTIS | W35 |  | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 1 | 1 |  |  | 1 | 0 | 0 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101029726 | OH RELW PRI REMT ESTR GO FMOB TER2 PRTO FSRP | Pole | 2020-06-12 | 2020-06-16 | COMP | 2020-06-12 | [16 empty] | 2019-04-01 | 2020-04-01 | 2020-08-13 | 2020-08-13 | B-Tag Addition 07.06.2020 |  | Bakersfield |  | 163351703 | 37490.01 | 4669.6 | -1850.5 | -1850.5 | -1850.5 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-07-06
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116885211 | POLE_BROK_REPL - 25855 RICHARDS RANCH RD | 35178569 |  |  | STS-POLE_BROK_REPL - 25855 RICHARDS RANC | CONS | CONS ERDY SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8729 | -120.3079 |  | TIER 2 | 72 | 16335-1703, CURTIS | W35 |  | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41 | 41 |  |  | 6 | 39 | 39 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101029716 | RELW OH NOAC PRI CLR REMT ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-06-23 | 2020-07-21 | COMP | 2020-06-23 | [16 empty] | 2019-04-01 | 2020-04-01 | 2020-08-13 | 2020-08-13 | B-Tag Addition 06.24.20 |  | Bakersfield |  | 163351703 | 42508.33 | 8761.1 | 679.3 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-06-29
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116979271 | POLE_DECA_REPL - 18164 CALLE OESTE SONOR | 35187584 |  |  | STS-POLE_DECA_REPL - 18164 CALLE OESTE S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.952 | -120.3837 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3323 | 19686 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.1 | 34.1 |  |  | 0 | 34.1 | 34.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101041597 | RELW OH PRI JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-17 | 2021-02-03 | COMP | 2020-09-17 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 19906.48 | 164.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116979866 | POLE_DECA_REPL - 18310 VIA SERENA SONORA | 35187594 |  |  | STS-POLE_DECA_REPL - 18310 VIA SERENA SO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9544 | -120.3822 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3323 | 19687 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48.7 | 48.7 |  |  | 0 | 48.7 | 48.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101041565 | RELW OH PRI RESD FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-17 | 2021-02-03 | COMP | 2020-09-17 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 25314.14 | 164.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116983584 | POLE_BROK_REPL - 18291 AVENIDA BONITASON | 35187713 |  |  | STS-POLE_BROK_REPL - 18291 AVENIDA BONIT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9542 | -120.3845 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3323 | 19687 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 52.8 | 52 | 0.8 |  | 0 | 52.8 | 52 | 0.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041525 | RELW OH PRI CLR RESD FLAG ESTR BTKA USA FMOB PRTO TER2 | Pole | 2020-10-01 | 2021-02-03 | COMP | 2020-10-01 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 25982.08 | 530.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116983881 | POLE_BROK_REPL - 11762 CAMPO SECO RD 1NS | 35187719 |  |  | STS-POLE_BROK_REPL - 11762 CAMPO SECO RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9547 | -120.388 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3323 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.9 | 16.9 |  |  | 0 | 16.9 | 16.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041403 | RELW OH PRI RESD REMT SPCR ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-09-24 | 2020-09-24 | COMP | 2020-09-24 | [16 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 7971.52 | 205.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116984790 | POLE_DECA_REPL - 11797 ESSEN LN. SONORA | 35187780 |  |  | STS-POLE_DECA_REPL - 11797 ESSEN LN. SON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9559 | -120.3876 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3323 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.2 | 15.2 |  |  | 0 | 15.2 | 15.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101041425 | OH RELW PRI RESD REMT ESTR REAR FMOB TER2 PRTO | Pole | 2020-09-21 | 2020-09-21 | COMP | 2020-09-21 | [16 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 7055.05 | 345.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116985133 | POLE_DECA_REPL - 18148 CAMPO SECO SONORA | 35154285 |  |  | STS-POLE_DECA_REPL - 18148 CAMPO SECO SO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9526 | -120.3892 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3322 | 1843 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 53.5 | 53.5 |  |  | 0 | 53.5 | 53.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101041365 | RELW OH PRI NOAC ESTR REAR PRTO FMOB TER2 | Pole | 2020-04-28 | 2020-06-14 | COMP | 2020-04-28 | [16 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351703 | 25875.74 | 389.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116985465 | POLE_DECA_REPL - 11829 CAMPO SECO RD/1PS | 35187803 |  |  | STS-POLE_DECA_REPL - 11829 CAMPO SECO RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9566 | -120.3864 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3323 | 19692 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.8 | 36.8 |  |  | 0 | 36.8 | 36.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101041729 | RELW OH PRI RESD ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-09-25 | 2020-09-25 | COMP | 2020-09-25 | [16 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 16524.46 | 172.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116987900 | POLE_BROK_REPL - 13010 LAKE VALLEY LN 1P | 35187924 |  |  | STS-POLE_BROK_REPL - 13010 LAKE VALLEY L | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.954 | -120.3605 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3421 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.9 | 14.9 |  |  | 0 | 14.9 | 14.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101043085 | RELW SERV OH CLR RESD NOAC ESTR USA FMOB TER2 PRTO | Pole | 2020-10-01 | 2020-11-22 | COMP | 2020-09-30 | [16 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 5703.63 | 259.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116989022 | POLE_BROK_REPL - 18181 VIA SERENA/1PW SO | 35187937 |  |  | STS-POLE_BROK_REPL - 18181 VIA SERENA/1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9522 | -120.3806 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3324 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16 | 16 |  |  | 0 | 16 | 16 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041978 | RELW OH PRI ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-09-10 | 2021-02-03 | COMP | 2020-09-10 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 8372.11 | 436 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116990123 | POLE_DECA_REPL - 18211 JACOBS RD 1PSW/1P | 35154299 |  |  | STS-POLE_DECA_REPL - 18211 JACOBS RD 1PS | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9519 | -120.3596 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3421 |  | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-04 16:00 | Dispatched | CLICK | [6 empty] | 22 | 22 |  |  | 0 | 22 | 22 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101043106 | RELW OH SERV CLR JPOL REMT NOAC ESTR USA FMOB TER2 PRTO | Pole | 2020-05-20 | 2020-08-07 | COMP | 2020-05-20 |  |  | 2020-07-27 | 2020-07-27 | [12 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351703 | 9082.85 | 1093.1 | 1093.1 | 523.7 | 523.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117000367 | POLE_DECA_REPL - 18430 AVENEDA BONITA/4P | 35187985 |  |  | STS-POLE_DECA_REPL - 18430 AVENEDA BONIT | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9564 | -120.377 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3324 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 31.7 | 31.7 |  |  | 0 | 31.7 | 31.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101041885 | RELW OH PRI NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2020-09-17 | 2020-11-17 | COMP | 2020-09-16 | [16 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117000909 | POLE_OVRL_TEST - 18381 CORTE DE MONTANA/ | 35188011 |  |  | STS-POLE_OVRL_TEST - 18381 CORTE DE MONT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9542 | -120.377 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3324 | 1241 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 32.4 | 32.4 |  |  | 0 | 32.4 | 32.4 |  |  | EC | E | Pole | Overloaded | Test |  | 101041888 | RELW OH PRI SPCR ESTR GO BTKA REAR FMOB TER2 PRTO | Pole | 2020-09-16 | 2020-09-21 | COMP | 2020-09-15 | [16 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 16084.79 | 184.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117000926 | POLE_BROK_REPL - JACOBS/OLD WARDS FERRY | 35188016 |  |  | STS-POLE_BROK_REPL - JACOBS/OLD WARDS FE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9531 | -120.3539 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3422 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.2 | 25.2 |  |  | 0 | 25.2 | 25.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101043134 | RELW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-13 | 2020-10-14 | COMP | 2020-10-02 | [16 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 10351.47 | 256.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117001500 | POLE_BROK_REPL - JACOBS/OLD WARDS FERRY | 35190146 |  |  | B STS-POLE_BROK_REPL - JACOBS/OLD WARDS | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9542 | -120.3515 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3422 | L1787 | Y | 311 |  |  | 2021-01-07 | 2021-01-07 | Completed | Order Operation | [6 empty] | 60 | 60 |  |  | 9.5 | 58.5 | 58.5 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101043157 | RELW OH PRI JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-08-31 | 2020-11-23 | COMP | 2020-08-21 |  |  | 2020-11-23 | 2020-11-23 | [12 empty] | 2019-04-10 | 2020-04-10 | 2020-10-13 | 2020-10-13 | B-tag addition 8/4/2020 |  | Bakersfield |  | 163351703 | 27363.56 | 15887.8 | 8924.4 | 25798.7 | 25798.7 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-08-04
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117002838 | POLE_BROK_REPL - 18280 CORTE DEL MONTANA | 35086237 |  |  | STS-POLE_BROK_REPL - 18280 CORTE DEL MON | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9532 | -120.3785 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3324 |  | Y | 311 |  |  | 2021-03-09 07:00 | 2021-03-09 16:00 | Scheduled | CLICK | [6 empty] | 36.7 | 36.7 |  |  | 0 | 36.7 | 36.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041865 | RELW OH PRI CLR REMT ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-05-12 | 2020-08-03 | COMP | 2020-05-12 | [16 empty] | 2019-04-10 | 2019-10-10 |  | 2019-10-10 | circuit based plan 2.14 | 2020-05-20 | TRC |  | 163351703 | 35638.23 | 8965 | 1447.5 | 1447.5 | 1447.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117003548 | POLE_WOOD_ASES - 18087 LIME KILN RD SONO | 35188052 |  |  | STS-POLE_WOOD_ASES - 18087 LIME KILN RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9513 | -120.3664 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3325 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 25.4 | 25.4 |  |  | 0 | 25.4 | 25.4 |  |  | EC | E | Pole | Woodpecker Damage | Assessment |  | 101042038 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-15 | 2021-02-03 | COMP | 2020-09-15 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117003933 | POLE_BROK_REPL - 18087 LIME KILN RD 1NES | 35188058 |  |  | STS-POLE_BROK_REPL - 18087 LIME KILN RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9517 | -120.3659 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3325 | 9765 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 30.2 | 30.2 |  |  | 0 | 30.2 | 30.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101042035 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-18 | 2020-12-12 | COMP | 2020-09-17 | [16 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 13876.03 | 114.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117008557 | POLE_BROK_REPL - 18422 AVENIDA BONITA/4P | 35188102 |  |  | STS-POLE_BROK_REPL - 18422 AVENIDA BONIT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9603 | -120.3767 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3319 | 6064 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 23.7 | 23.7 |  |  | 0 | 23.7 | 23.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101042513 | RELW PRI OH CLR RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-18 | 2020-10-20 | COMP | 2020-09-17 | [16 empty] | 2019-04-11 | 2020-04-11 |  | 2020-04-11 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117016489 | POLE_BROK_REPL - 16812 ANDERSON RD W/TRA | 35188178 |  |  | STS-POLE_BROK_REPL - 16812 ANDERSON RD W | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9415 | -120.2749 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 | 1729 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 60.4 | 56.8 | 3.6 |  | 0 | 60.4 | 56.8 | 3.6 |  | EC | E | Pole | Broken/Damaged | Replace |  | 103354746 | RELW OH PRI CLR RESD REMT ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-09-21 | 2020-09-21 | COMP | 2020-09-21 | [16 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 21758.87 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117016964 | POLE_BROK_REPL - SE\C\OF YOSEMITY RD\COU | 35188204 |  |  | STS-POLE_BROK_REPL - SE\C\OF YOSEMITY RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9397 | -120.2733 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.3 | 15.3 |  |  | 0 | 15.3 | 15.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047206 | RELW OH PRI REMT ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-09-14 | 2020-09-14 | COMP | 2020-09-14 | [16 empty] | 2019-04-12 | 2020-04-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 5208.71 | 316.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117017269 | POLE_BROK_REPL - 15910 WARDS FERRY 1PE/O | 35188221 |  |  | STS-POLE_BROK_REPL - 15910 WARDS FERRY 1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9119 | -120.2915 |  | TIER 2 | 72 | 16335-1703, CURTIS | V35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.4 | 19.4 |  |  | 0 | 19.4 | 19.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031034 | RELW OH PRI REMT ESTR TER2 BTKA REAR FMOB PRTO | Pole | 2020-09-21 | 2020-09-21 | COMP | 2020-09-21 | [16 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 6303.58 | 271.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117017820 | POLE_BROK_REPL - SE\C\OF YOSEMITY RD\COU | 35188250 |  |  | STS-POLE_BROK_REPL - SE\C\OF YOSEMITY RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9403 | -120.2731 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.3 | 17.3 |  |  | 0 | 17.3 | 17.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047212 | RELW OH PRI RESD REMT USA FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-09 | 2021-02-03 | COMP | 2020-10-09 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 9720.94 | 452.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117018753 | POLE_BROK_REPL - 15910 WARDS FERRY 1PE/O | 35188283 |  |  | STS-POLE_BROK_REPL - 15910 WARDS FERRY 1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9165 | -120.2936 |  | TIER 2 | 72 | 16335-1703, CURTIS | V35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.9 | 32.9 |  |  | 0 | 32.9 | 32.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031043 | RELW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-28 | 2020-09-28 | COMP | 2020-09-28 | [16 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 12644.68 | 316.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117019674 | POLE_BROK_REPL - FR\YD\OF\18301 HERSHEY | 35188314 |  |  | STS-POLE_BROK_REPL - FR\YD\OF\18301 HERS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9514 | -120.2639 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3623 | L2153 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.5 | 40.5 |  |  | 0 | 40.5 | 40.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033507 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-22 | 2020-09-22 | COMP | 2020-09-22 | [16 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 20487.01 | 300.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117021408 | POLE_BROK_REPL - 25855 RICHARDS RANCH RD | 35190148 |  |  | STS-POLE_BROK_REPL - 25855 RICHARDS RANC | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8836 | -120.3056 |  | TIER 2 | 72 | 16335-1703, CURTIS | W3513 |  | Y | 311 |  |  | 2021-03-26 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101029691 | RELW OH PRI RESD TER2 ESTR USA FMOB PRTO | Pole | 2020-08-21 | 2020-08-28 | COMP | 2020-08-21 | [16 empty] | 2019-04-13 | 2019-11-13 | 2020-10-15 | 2020-10-15 | B-tag addition 8/4/2020 |  | Bakersfield |  | 163351703 | 18857.85 | 819.5 | 819.5 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-08-04
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117021761 | POLE_DECA_REPL - E\OF\ENT 17130 COUNTRY | 35188360 |  |  | STS-POLE_DECA_REPL - E\OF\ENT 17130 COUN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9382 | -120.265 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 | L1765 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.6 | 57.4 | 0.2 |  | 0 | 57.6 | 57.4 | 0.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101047286 | RELW OH PRI RESD REMT FLAG ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-10-01 | 2020-10-23 | COMP | 2020-10-01 |  |  | 2020-09-29 | 2020-09-29 | [12 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 24653.6 | 126.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117022049 | POLE_BROK_REPL - SE\C\OF YOSEMITY RD\COU | 35188378 |  |  | STS-POLE_BROK_REPL - SE\C\OF YOSEMITY RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9383 | -120.2729 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 | 1729 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.5 | 27.5 |  |  | 0 | 27.5 | 27.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047364 | RELW OH PRI RESD REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-09 | 2021-02-03 | COMP | 2020-10-09 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 16392.96 | 42.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117023303 | POLE_BROK_REPL - FR\YD\OF\17315 YOSIMITE | 35188409 |  |  | STS-POLE_BROK_REPL - FR\YD\OF\17315 YOSI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.937 | -120.2753 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 | L1767 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 22.4 | 22.4 |  |  | 0 | 22.4 | 22.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047376 | RELW OH PRI RESD REMT REAR SPCR ESTR FMOB TER2 PRTO | Pole | 2020-09-21 | 2020-09-21 | COMP | 2020-09-21 | [16 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117024089 | POLE_BROK_REPL - S\OF\ENT 16186 YOSIMITE | 35188420 |  |  | STS-POLE_BROK_REPL - S\OF\ENT 16186 YOSI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9175 | -120.2818 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 23.2 | 23.2 |  |  | 0 | 23.2 | 23.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047793 | RELW OH PRI REMT NOAC ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-10-15 | COMP | 2020-10-15 | [16 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 8567.69 | 81.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117025502 | POLE_BROK_REPL - S\OF\ENT 16186 YOSIMITE | 35188440 |  |  | STS-POLE_BROK_REPL - S\OF\ENT 16186 YOSI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9169 | -120.2804 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 15.3 | 15.3 |  |  | 0 | 15.3 | 15.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047789 | RELW OH PRI REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-14 | 2020-09-14 | COMP | 2020-09-14 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 5852.83 | 76.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117025550 | POLE_BROK_REPL - S\OF\ENT 16255 YOSIMITE | 35188448 |  |  | STS-POLE_BROK_REPL - S\OF\ENT 16255 YOSI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9166 | -120.2797 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 27.4 | 27.4 |  |  | 0 | 27.4 | 27.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047787 | RELW OH PRI REMT NOAC ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-12-15 | 2020-12-17 | COMP | 2020-09-14 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117025892 | POLE_BROK_REPL - N\OF\ENT\16401 YOSIMITE | 35188458 |  |  | STS-POLE_BROK_REPL - N\OF\ENT\16401 YOSI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9184 | -120.2786 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 | 1729 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.3 | 28.3 |  |  | 0 | 28.3 | 28.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047784 | RELW OH PRI REMT ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-09-22 | 2020-09-22 | COMP | 2020-09-22 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 11992.15 | 181 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117026411 | POLE_BROK_REPL - SE\C\OF YOSEMITY RD\COU | 35188468 |  |  | STS-POLE_BROK_REPL - SE\C\OF YOSEMITY RD | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9343 | -120.271 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 | 1729 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 19.2 | 19.2 |  |  | 0 | 19.2 | 19.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047380 | RELW OH PRI CLR REMT ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-09-14 | 2020-09-14 | COMP | 2020-09-14 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 7499.07 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117026525 | POLE_BROK_REPL - E\OF\ENT\16346 YOSIMITE | 35188478 |  |  | STS-POLE_BROK_REPL - E\OF\ENT\16346 YOSI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9188 | -120.2816 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 15.3 | 15.3 |  |  | 0 | 15.3 | 15.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047781 | RELW OH PRI REMT ESTR BTKA PRTO USA FMOB TER2 | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117026784 | POLE_BROK_REPL - 26505 RICHARDS RANCH RD | 35188488 |  |  | STS-POLE_BROK_REPL - 26505 RICHARDS RANC | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8888 | -120.2966 |  | TIER 2 | 72 | 16335-1703, CURTIS | W35 | S1965 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 43.5 | 41.7 | 1.8 |  | 0 | 43.5 | 41.7 | 1.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029604 | RELW OH PRI CLR JPOL REMT ESTR TER2 BTKA USA FMOB PRTO FSRP | Pole | 2020-09-18 | 2021-01-27 | COMP | 2020-09-17 | [16 empty] | 2019-04-14 | 2020-04-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117027007 | POLE_DECA_REPL - N\OF\ENT\16401 YOSIMITE | 35188502 |  |  | STS-POLE_DECA_REPL - N\OF\ENT\16401 YOSI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9207 | -120.2772 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 | 1729 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 33.5 | 33.5 |  |  | 0.5 | 33 | 33 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101047772 | RELW OH PRI REMT SPCR ESTR BTKA PRTO REAR FMOB TER2 | Pole | 2020-09-25 | 2020-09-25 | COMP | 2020-09-25 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 9869.39 | 72.1 | 72.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117027066 | POLE_BROK_REPL - FR\YD\OF 17003 YOSIMITE | 35188512 |  |  | STS-POLE_BROK_REPL - FR\YD\OF 17003 YOSI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9321 | -120.2712 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 14.4 | 14.4 |  |  | 0 | 14.4 | 14.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047383 | RELW OH PRI REMT ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117027182 | POLE_BROK_REPL - FR\YD\OF 17003 YOSIMITE | 35188522 |  |  | STS-POLE_BROK_REPL - FR\YD\OF 17003 YOSI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9315 | -120.2693 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 | L1771 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 29.2 | 29.2 |  |  | 0 | 29.2 | 29.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047385 | RELW OH PRI CLR RESD REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117027313 | POLE_BROK_REPL - AF\ENT\TO\16895 YOSIMIT | 35188527 |  |  | STS-POLE_BROK_REPL - AF\ENT\TO\16895 YOS | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9259 | -120.2748 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 24 | 24 |  |  | 0 | 24 | 24 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047610 | RELW OH PRI REMT NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2020-09-08 | 2020-09-08 | COMP | 2020-09-08 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117027473 | POLE_BROK_REPL - 95370SONORA95370 | 35188537 |  |  | STS-POLE_BROK_REPL - 95370SONORA95370 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9016 | -120.3032 |  | TIER 2 | 72 | 16335-1703, CURTIS | W35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 19.3 | 19.3 |  |  | 0 | 19.3 | 19.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103185546 | RELW OH PRI CLR REMT ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-04-14 | 2020-04-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117027616 | POLE_BROK_REPL - FR\YD\OF\16875 YOSIMITE | 35188540 |  |  | STS-POLE_BROK_REPL - FR\YD\OF\16875 YOSI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9263 | -120.2736 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 25.6 | 25.6 |  |  | 0 | 25.6 | 25.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047611 | RELW OH PRI REMT NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2020-09-14 | 2020-09-14 | COMP | 2020-09-14 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117027683 | POLE_BROK_REPL - AF\ENT\TO\17150 YOSIMIT | 35188545 |  |  | STS-POLE_BROK_REPL - AF\ENT\TO\17150 YOS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9289 | -120.2737 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 13.5 | 13.5 |  |  | 0 | 13.5 | 13.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047617 | RELW OH PRI REMT ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 4707.35 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117027728 | POLE_BROK_REPL - N\OF\ENT\16875 YOSIMITE | 35188555 |  |  | STS-POLE_BROK_REPL - N\OF\ENT\16875 YOSI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9239 | -120.2733 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.6 | 18.6 |  |  | 0 | 18.6 | 18.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047609 | RELW OH PRI REMT NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 7785.44 | 311.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117030413 | POLE_DECA_REPL - 16678 BLACK OAK SONORA | 35188580 |  |  | STS-POLE_DECA_REPL - 16678 BLACK OAK SON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9745 | -120.2767 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3612 | 601 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43 | 43 |  |  | 0 | 43 | 43 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101033754 | RELW JPOL OH PRI REMT ESTR BTKA PROG FMOB TER2 PRTO | Pole | 2020-09-29 | 2020-09-29 | COMP | 2020-09-28 | [16 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 20135.36 | 262.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117032335 | POLE_BROK_REPL - FR\YD\OF 17011 COUNTRY | 35188615 |  |  | STS-POLE_BROK_REPL - FR\YD\OF 17011 COUN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9322 | -120.2669 |  | TIER 2 | 72 | 16335-1703, CURTIS | V36 | L1771 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.2 | 23.2 |  |  | 0 | 23.2 | 23.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047355 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 8042.45 | 316.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117032737 | POLE_BROK_REPL - 14800 ALGERINE SONORA | 35188633 |  |  | STS-POLE_BROK_REPL - 14800 ALGERINE SONO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8975 | -120.3156 |  | TIER 2 | 72 | 16335-1703, CURTIS | W35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.7 | 17.7 |  |  | 0 | 17.7 | 17.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029489 | RELW OH PRI CLR REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 7368.57 | 269.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117037241 | POLE_BROK_REPL - 18390 AVENIDA BONITA/1P | 35188667 |  |  | STS-POLE_BROK_REPL - 18390 AVENIDA BONIT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9554 | -120.3832 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3323 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.8 | 14.8 |  |  | 0 | 14.8 | 14.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101041533 | RELW OH PRI PGEA REMT ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-09-11 | 2021-02-03 | COMP | 2020-09-11 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 11090.41 | 537.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117039254 | POLE_BROK_REPL - 21008 MAURICE LN.@HOUSE | 35187597 |  |  | STS-POLE_BROK_REPL - 21008 MAURICE LN.@H | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0031 | -120.2656 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3623 | 10940 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.7 | 15.7 |  |  | 0 | 15.7 | 15.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103360371 | RELW OH SEC INSP JPOL RESD ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-09-17 | 2020-11-09 | COMP | 2020-09-16 | [16 empty] | 2019-04-16 | 2020-04-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 6922.92 | 340.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117043639 | POLE_BROK_REPL - 13373 TERRACE RD 1PS SO | 35187732 |  |  | STS-POLE_BROK_REPL - 13373 TERRACE RD 1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9712 | -120.3523 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3412 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.2 | 16.2 |  |  | 0 | 16.2 | 16.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101044999 | RELW REMT OH PRI NOAC ESTR FMOB TER2 PRTO | Pole | 2020-09-15 | 2020-11-16 | COMP | 2020-09-15 | [16 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 6034.19 | 316.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117056966 | POLE_BROK_REPL - 16730 PRIMROSE LN.SONOR | 35187986 |  |  | STS-POLE_BROK_REPL - 16730 PRIMROSE LN.S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9866 | -120.2768 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3602 | 23239 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 35.9 | 35.9 |  |  | 0 | 35.9 | 35.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101039526 | RELW OH PRI PGEA CLR RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-09-23 | 2020-11-20 | COMP | 2020-09-23 | [16 empty] | 2019-04-18 | 2020-04-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 16906.98 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117062017 | POLE_BROK_REPL - 15920 SERRANOSONORA9537 | 35154722 |  |  | STS-POLE_BROK_REPL - 15920 SERRANOSONORA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9761 | -120.3027 |  | TIER 2 | 318 | 16335-1705, CURTIS | U35 | UNKNOWN | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 58.3 | 58.3 |  |  | 0 | 58.3 | 58.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031563 | RELW OH PRI PGEA CLR JPOL REMT ESTR REAR USA FSRP FMOB TER2 PRTO | Pole | 2020-06-23 | 2020-06-23 | COMP | 2020-06-23 | [16 empty] | 2019-04-18 | 2020-04-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | CALENG |  | 163351705 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117062020 | POLE_BROK_REPL - 10530 SERRANO 1PSESONOR | 35215306 |  |  | STS-POLE_BROK_REPL - 10530 SERRANO 1PSES | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9766 | -120.3036 |  | TIER 2 | 318 | 16335-1705, CURTIS | U35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 12 | 12 |  |  | 0 | 12 | 12 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031565 | RELW OH PRI PGEA REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2021-02-02 | 2021-02-02 | COMP | 2021-02-02 | [16 empty] | 2019-04-18 | 2020-04-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163351705 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117068975 | COND_BROK_REPA - 16071 AVENIDA DEL SOL 2 | 35188110 |  |  | STS-COND_BROK_REPA - 16071 AVENIDA DEL S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9947 | -120.2912 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3505 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.5 | 16.5 |  |  | 0 | 16.5 | 16.5 |  |  | EC | E | Conductor | Broken/Damaged | Repair |  | 101033551 | RELW OH PRI CLR JPOL RESD REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-22 | 2020-11-25 | COMP | 2020-09-22 |  |  | 2020-08-19 | 2020-08-19 | [12 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 6440.98 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117069145 | POLE_BROK_REPL - 20150 WAIF MINE RD SONO | 35215397 |  |  | STS-POLE_BROK_REPL - 20150 WAIF MINE RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9858 | -120.3108 |  | TIER 2 |  |  | U3507 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 10.3 | 10.3 |  |  | 0 | 10.3 | 10.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101015690 | RELW OH SERV REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-26 | 2021-01-26 | COMP | 2021-01-26 | [16 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG | [11 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117088843 | POLE_BROK_REPL - 0LD WARDS FERRY RD 1PS/ | 35187681 |  |  | STS-POLE_BROK_REPL - 0LD WARDS FERRY RD | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9519 | -120.3495 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3422 | L1787 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 45.7 | 44 | 1.7 |  | 0 | 45.7 | 44 | 1.7 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101043242 | RELW OH PRI CLR JPOL RESD ESTR BTKA PRTO USA FMOB TER2 | Pole | 2020-10-15 | 2020-11-13 | COMP | 2020-10-15 | [16 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117115780 | POLE_BROK_REPL - 20955 JAMESTOWN RD 9PS/ | 35154178 |  |  | STS-POLE_BROK_REPL - 20955 JAMESTOWN RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9976 | -120.411 |  | TIER 2 | 165 | 16376-1703, RACETRACK | T3225 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18 | 18 |  |  | 0 | 18 | 18 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101043918 | RELW OH PRI JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-05-04 | 2020-08-07 | COMP | 2020-05-04 | [16 empty] | 2019-04-28 | 2020-04-28 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163761703 | 6638.13 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117123601 | POLE_BROK_REPL - 19230 CORDELIA AVESONOR | 35188297 |  |  | STS-POLE_BROK_REPL - 19230 CORDELIA AVES | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9715 | -120.3319 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3415 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.6 | 15.6 |  |  | 0 | 15.6 | 15.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103184598 | RELW OH SEC INSP JPOL RESD FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-11-25 | 2020-12-19 | COMP | 2020-09-28 | [16 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 9274.54 | 141.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117134953 | POLE_BROK_REPL - BL\YD\OF16310 MORRIS RD | 35154258 |  |  | STS-POLE_BROK_REPL - BL\YD\OF16310 MORRI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9645 | -120.2855 |  | TIER 2 | 318 | 16335-1705, CURTIS | U3616 | 5373 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.8 | 44.8 |  |  | 0 | 44.8 | 44.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033581 | RELW OH PRI INSP JPOL RESD REMT NOAC ESTR REAR USA FMOB TER2 FSRP | Pole | 2020-04-22 | 2020-04-22 | COMP | 2020-04-22 | [16 empty] | 2019-05-01 | 2020-05-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 163351705 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117136609 | POLE_BROK_REPL - FT\YD\OF 16111 BLACK OA | 35154267 |  |  | STS-POLE_BROK_REPL - FT\YD\OF 16111 BLAC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9672 | -120.2857 |  | TIER 2 | 318 | 16335-1705, CURTIS | U3520 | 21471 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 64.4 | 63.2 | 1.2 |  | 0 | 64.4 | 63.2 | 1.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033618 | RELW OH PRI INSP JPOL RESD REMT TRAF ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-08-21 | 2021-02-03 | COMP | 2020-08-20 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-01 | 2020-05-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351705 | 33355.98 | 561.6 |  |  |  | 127.7 |  | 127.7 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117143251 | POLE_DECA_REPL - BK\YD\OF 17220 ANDRA RD | 35188619 |  |  | STS-POLE_DECA_REPL - BK\YD\OF 17220 ANDR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9676 | -120.2782 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3616 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.6 | 13.6 |  |  | 0 | 13.6 | 13.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101033659 | RELW OH PRI INSP CLR JPOL REMT FIRE NOAC ESTR GO FMOB TER2 | Pole | 2020-09-18 | 2020-09-18 | COMP | 2020-09-18 | [16 empty] | 2019-05-02 | 2020-05-02 |  | 2020-05-02 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 5040.84 | 657.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117143560 | POLE_DECA_REPL - FR\YD\OF 15201 YOST RAN | 35188628 |  |  | STS-POLE_DECA_REPL - FR\YD\OF 15201 YOST | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9676 | -120.2771 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3617 | 601 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.6 | 36.6 |  |  | 0 | 36.6 | 36.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101033667 | RELW OH PRI INSP CLR JPOL REMT FIRE ESTR GO BTKA USA FMOB TER2 | Pole | 2020-10-05 | 2020-10-05 | COMP | 2020-10-05 | [16 empty] | 2019-05-02 | 2020-05-02 |  | 2020-05-02 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117157284 | POLE_DECA_REPL - 3PS 9PE 11030 CAMPO SEC | 35187865 |  |  | STS-POLE_DECA_REPL - 3PS 9PE 11030 CAMPO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9482 | -120.3981 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3301 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.6 | 26.6 |  |  | 0 | 26.6 | 26.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101030925 | RELW OH PRI PGEA INSP REMT ESTR BTKA FMOB TER2 | Pole | 2020-09-08 | 2020-09-08 | COMP | 2020-09-08 | [16 empty] | 2019-05-03 | 2020-05-03 |  | 2020-05-03 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 13334.06 | 316.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117159371 | POLE_DECA_REPL - 7PW 1722 KINKAID FLAT R | 35187915 |  |  | STS-POLE_DECA_REPL - 7PW 1722 KINKAID FL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.937 | -120.386 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3308 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.5 | 24.5 |  |  | 0 | 24.5 | 24.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101033119 | RELW OH PRI PGEA INSP REMT ESTR GO BTKA FMOB TER2 | Pole | 2020-08-25 | 2020-08-25 | COMP | 2020-08-25 | [16 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 11574.92 | 166.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117159764 | POLE_BROK_REPL - 2PE 17898 CAMPBELL FLAT | 35187940 |  |  | STS-POLE_BROK_REPL - 2PE 17898 CAMPBELL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9475 | -120.3898 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3302 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.7 | 22.7 |  |  | 0 | 22.7 | 22.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030938 | RELW OH PRI INSP JPOL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-10-09 | 2021-02-03 | COMP | 2020-10-09 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117160009 | POLE_BROK_REPL - 17898 CAMPBELLSB FLATS | 35187946 |  |  | STS-POLE_BROK_REPL - 17898 CAMPBELLSB FL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9479 | -120.3909 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3302 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.8 | 13.8 |  |  | 0 | 13.8 | 13.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030941 | RELW OH SEC INSP ESTR BTKA USA FMOB TER2 | Pole | 2020-09-30 | 2020-12-12 | COMP | 2020-09-30 | [16 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 5691.12 | 495.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117160036 | POLE_BROK_REPL - 9PW 1722 KINKAID FLAT R | 35187950 |  |  | STS-POLE_BROK_REPL - 9PW 1722 KINKAID FL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9362 | -120.3884 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3308 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 27.1 | 27.1 |  |  | 0 | 27.1 | 27.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033117 | RELW OH PRI PGEA INSP REMT ESTR BTKA USA FMOB TER2 | Pole | 2020-09-11 | 2020-09-11 | COMP | 2020-09-11 | [16 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 13971 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117160737 | POLE_BROK_REPL - 3PS 11PE 11030 CAMPO SE | 35188018 |  |  | STS-POLE_BROK_REPL - 3PS 11PE 11030 CAMP | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9482 | -120.3949 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3302 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.4 | 19.4 |  |  | 0 | 19.4 | 19.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030920 | RELW OH PRI INSP JPOL REMT FIRE NOAC ESTR USA FMOB TER2 | Pole | 2020-09-11 | 2020-09-11 | COMP | 2020-09-11 | [16 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 10725.36 | 495.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117160822 | POLE_BROK_REPL - 3PS 13PE 11030 CAMPO SE | 35188025 |  |  | STS-POLE_BROK_REPL - 3PS 13PE 11030 CAMP | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9482 | -120.3931 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3302 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.9 | 19.9 |  |  | 0 | 19.9 | 19.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030913 | RELW OH PRI INSP JPOL REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-09-11 | 2020-09-11 | COMP | 2020-09-11 | [16 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 8531.49 | 405.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117160855 | POLE_BROK_REPL - 3PS 12PE 11030 CAMPO SE | 35188031 |  |  | STS-POLE_BROK_REPL - 3PS 12PE 11030 CAMP | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9482 | -120.3941 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3302 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.3 | 16.3 |  |  | 0 | 16.3 | 16.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030914 | RELW INSP OH PRI REMT FIRE ESTR REAR USA FMOB TER2 | Pole | 2020-09-18 | 2020-09-18 | COMP | 2020-09-18 | [16 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 6860.86 | 543 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117161118 | POLE_BROK_REPL - 1PS 12055 APPEY WAYSONO | 35188049 |  |  | STS-POLE_BROK_REPL - 1PS 12055 APPEY WAY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9414 | -120.3818 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3308 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15 | 15 |  |  | 0 | 15 | 15 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033316 | RELW OH PRI PGEA PATR REMT FIRE ESTR BTKA REAR FMOB TER2 | Pole | 2020-09-28 | 2020-09-28 | COMP | 2020-09-28 | [16 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 5115.1 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117161296 | POLE_BROK_REPL - 3PS 14PE 11030 CAMPO SE | 35188067 |  |  | STS-POLE_BROK_REPL - 3PS 14PE 11030 CAMP | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9482 | -120.3914 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3302 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.4 | 17.4 |  |  | 0 | 17.4 | 17.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030911 | RELW OH PRI INSP ESTR FMOB TER2 | Pole | 2020-10-05 | 2020-10-15 | COMP | 2020-10-05 | [16 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 14809.97 | 249.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117162929 | POLE_BROK_REPL - 65 LOWER SUNSETSONORA95 | 35105898 |  |  | STS-POLE_BROK_REPL - 65 LOWER SUNSETSONO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.985 | -120.3862 |  | TIER 2 | 165 | 16376-1703, RACETRACK | U3308 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.4 | 18.4 |  |  | 0 | 18.4 | 18.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048236 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-07-15 | 2020-10-16 | COMP | 2020-05-19 |  |  | 2020-10-16 | 2020-10-16 | [12 empty] | 2019-05-05 | 2019-11-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-20 | TRC |  | 163761703 | 9948.82 | 1531.4 | 1531.4 | 1531.4 | 1531.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117166584 | POLE_BROK_REPL - 17991 AVENIDA BONITASON | 35188172 |  |  | STS-POLE_BROK_REPL - 17991 AVENIDA BONIT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9491 | -120.3877 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3303 | 19685 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 64.2 | 62.5 | 1.7 |  | 0 | 64.2 | 62.5 | 1.7 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030934 | RELW OH PRI INSP JPOL RESD FIRE FLAG ESTR BTKA USA PROG FMOB TER2 | Pole | 2020-09-22 | 2021-02-03 | COMP | 2020-09-22 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 23426.37 | 452.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117167058 | POLE_BROK_REPL - 1PS 17951 OLD WARDS FER | 35188208 |  |  | STS-POLE_BROK_REPL - 1PS 17951 OLD WARDS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.948 | -120.3401 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3404 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.8 | 27.8 |  |  | 0 | 27.8 | 27.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033053 | RELW OH PRI PGEA INSP CLR RESD REMT ESTR BTKA USA FMOB TER2 | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 9535.47 | 226.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117167617 | POLE_BROK_REPL - 13633 KINKAID FLATS RDS | 35188220 |  |  | STS-POLE_BROK_REPL - 13633 KINKAID FLATS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9423 | -120.3505 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3402 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.6 | 19.6 |  |  | 0 | 19.6 | 19.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033134 | RELW OH PRI INSP JPOL RESD FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-09-22 | 2020-11-17 | COMP | 2020-09-21 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 6772.12 | 226.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117167665 | POLE_DECA_REPL - 1PE 13661 KINKAID FLATS | 35188226 |  |  | STS-POLE_DECA_REPL - 1PE 13661 KINKAID F | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9436 | -120.3526 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3402 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.5 | 19.5 |  |  | 0 | 19.5 | 19.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101033137 | RELW OH PRI INSP CLR JPOL ESTR REMT FIRE NOAC GO BTKA REAR USA FMOB TER2 | Pole | 2020-09-22 | 2020-11-06 | COMP | 2020-09-22 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 6410.91 | 370.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117167964 | POLE_BURN_REPL - 2PS 2PE 17951 OLD WARDS | 35188237 |  |  | STS-POLE_BURN_REPL - 2PS 2PE 17951 OLD W | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9477 | -120.3383 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3404 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.2 | 20.2 |  |  | 0 | 20.2 | 20.2 |  |  | EC | E | Pole | Burnt | Replace |  | 101033056 | RELW OH PRI PGEA INSP CLR REMT NOAC ESTR REAR FMOB TER2 | Pole | 2020-09-16 | 2020-09-16 | COMP | 2020-09-15 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 20707.9 | 280.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117168333 | POLE_DECA_REPL - 17865 VVIA SERENA SONOR | 35154423 |  |  | STS-POLE_DECA_REPL - 17865 VVIA SERENA S | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9452 | -120.3861 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3303 | 19687 | Y | 311 |  |  | 2021-03-10 07:00 | 2021-03-10 16:00 | Scheduled | CLICK | [6 empty] | 66.8 | 65 | 1.8 |  | 0 | 66.8 | 65 | 1.8 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101030983 | RELW OH PRI INSP ESTR GO BTKA FMOB TER2 | Pole | 2020-04-27 | 2020-06-19 | COMP | 2020-04-27 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351703 | 27176.39 | 194.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117168451 | POLE_BROK_REPL - 18030 CALLE OESTE RDSON | 35188257 |  |  | STS-POLE_BROK_REPL - 18030 CALLE OESTE R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9498 | -120.3849 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3303 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14 | 14 |  |  | 0 | 14 | 14 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103187957 | RELW OH SEC INSP JPOL RESD FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-09-17 | 2020-11-24 | COMP | 2020-09-16 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 6372.48 | 269.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117169073 | POLE_BROK_REPL - 3PE 17976 LIME KILN RD | 35188289 |  |  | STS-POLE_BROK_REPL - 3PE 17976 LIME KILN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9486 | -120.3631 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3401 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 35.2 | 35.2 |  |  | 0 | 35.2 | 35.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033166 | RELW OH PRI INSP CLR JPOL RESD FIRE ESTR OTRG REAR FMOB TER2 | Pole | 2020-09-15 | 2020-11-10 | COMP | 2020-09-15 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 14756.22 | 211.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117169250 | POLE_DECA_REPL - 2PE 1PS 17976 LIME KILN | 35188294 |  |  | STS-POLE_DECA_REPL - 2PE 1PS 17976 LIME | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9479 | -120.3622 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3401 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 9.1 | 9.1 |  |  | 0 | 9.1 | 9.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101033168 | RELW OH PRI PGEA INSP RESD ESTR BTKA FMOB TER2 | Pole | 2020-10-06 | 2021-02-03 | COMP | 2020-10-05 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 7049.84 | 135.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117169327 | POLE_DECA_REPL - 3PE 13720 KINKAID FLATS | 35188299 |  |  | STS-POLE_DECA_REPL - 3PE 13720 KINKAID F | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9451 | -120.3523 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3402 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.6 | 20.6 |  |  | 0 | 20.6 | 20.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101033140 | RELW OH PRI INSP CLR JPOL REMT FIRE ESTR GO REAR USA FMOB TER2 | Pole | 2020-09-17 | 2020-11-13 | COMP | 2020-09-17 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 10374.2 | 543 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117169501 | POLE_BROK_REPL - 2PW 17775 PLAZA DEL SUR | 35154444 |  |  | STS-POLE_BROK_REPL - 2PW 17775 PLAZA DEL | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-01-09 | Renew Permit | 37.9455 | -120.384 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3303 |  | Y | 311 |  |  | 2021-03-10 07:00 | 2021-03-10 16:00 | Scheduled | CLICK | [6 empty] | 21.8 | 21.8 |  |  | 0 | 21.8 | 21.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030990 | RELW OH PRI INSP JPOL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-04-29 | 2020-06-23 | COMP | 2020-04-29 |  |  | 2021-02-19 | 2021-02-19 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351703 | 12967.81 | 822 |  |  |  | 282.6 |  | 282.6 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117169858 | POLE_BROK_REPL - 6PW 12670 ALGERINE RDSO | 35188323 |  |  | STS-POLE_BROK_REPL - 6PW 12670 ALGERINE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9081 | -120.3776 |  | TIER 2 | 72 | 16335-1703, CURTIS | V33 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.9 | 27.9 |  |  | 0 | 27.9 | 27.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030861 | RELW REMT OH PRI INSP FIRE NOAC ESTR REAR USA FMOB TER2 | Pole | 2020-09-16 | 2020-09-16 | COMP | 2020-09-16 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 9473.82 | 90.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117170020 | POLE_BROK_REPL - 4PW 12670 ALGERINE RDSO | 35188338 |  |  | STS-POLE_BROK_REPL - 4PW 12670 ALGERINE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9075 | -120.3746 |  | TIER 2 | 72 | 16335-1703, CURTIS | V33 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.7 | 20.7 |  |  | 0 | 20.7 | 20.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030860 | RELW OH PRI INSP REMT FIRE NOAC ESTR REAR USA FMOB TER2 | Pole | 2020-09-21 | 2020-09-21 | COMP | 2020-09-21 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 8907.54 | 133.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117170040 | POLE_DECA_REPL - 13720 KINKAID FLATS RDS | 35188348 |  |  | STS-POLE_DECA_REPL - 13720 KINKAID FLATS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9455 | -120.3541 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3402 | 19706 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 62.3 | 59.8 | 2.5 |  | 1 | 61.3 | 58.8 | 2.5 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101033145 | PRI RELW OH INSP CLR JPOL REMT FIRE ESTR GO BTKA USA FMOB TER2 | Pole | 2020-09-17 | 2020-11-13 | COMP | 2020-09-17 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 24355.42 | 382 | 144.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117170414 | POLE_BROK_REPL - 1P BELLA PLAZA CT/AT EN | 35188364 |  |  | STS-POLE_BROK_REPL - 1P BELLA PLAZA CT/A | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9472 | -120.3826 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3303 | 19687 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 35.8 | 35.8 |  |  | 0 | 35.8 | 35.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031003 | RELW OH PRI INSP JPOL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-10-14 | 2021-02-03 | COMP | 2020-10-14 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 17266.11 | 42.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117170650 | POLE_DECA_REPL - 13744 KINKAID FLATS RDS | 35188368 |  |  | STS-POLE_DECA_REPL - 13744 KINKAID FLATS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9456 | -120.3518 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3402 | 19706 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 29.2 | 29.2 |  |  | 0 | 29.2 | 29.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101033147 | RELW OH PRI INSP CLR JPOL GO REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-09-17 | 2020-11-16 | COMP | 2020-09-17 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 16877.52 | 157.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117171740 | POLE_BROK_REPL - 1PE 13520 ROUTE 5 RDSON | 35188416 |  |  | STS-POLE_BROK_REPL - 1PE 13520 ROUTE 5 R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9476 | -120.3468 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3403 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 23.6 | 23.6 |  |  | 0 | 23.6 | 23.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033203 | RELW OH PRI INSP JPOL RESD FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-11-10 | 2020-11-13 | COMP | 2020-09-21 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117174935 | POLE_BROK_REPL - 3PS 2PW PLAZA ORIENTESO | 35188454 |  |  | STS-POLE_BROK_REPL - 3PS 2PW PLAZA ORIEN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9433 | -120.3835 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3303 | 19688 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 61.6 | 61.4 | 0.2 |  | 6 | 55.6 | 55.4 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101030968 | RELW OH PRI INSP REMT FIRE ESTR REAR USA FMOB TER2 | Pole | 2020-09-21 | 2020-11-17 | COMP | 2020-09-21 | [16 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 24793.58 | -1010.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117174938 | POLE_BROK_REPL - 1PE 13540 TRES CASASSON | 35188459 |  |  | STS-POLE_BROK_REPL - 1PE 13540 TRES CASA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9476 | -120.3489 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3403 | 21073 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 36.7 | 36.7 |  |  | 0 | 36.7 | 36.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033198 | RELW OH PRI INSP JPOL RESD FIRE CGI ESTR BTKA REAR USA FMOB TER2 | Pole | 2020-10-15 | 2020-11-02 | COMP | 2020-10-15 | [16 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117181047 | POLE_BROK_REPL - 1PS 14403 ALGERINE WARD | 35154541 |  |  | STS-POLE_BROK_REPL - 1PS 14403 ALGERINE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9004 | -120.3311 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 | 21295 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 47 | 47 |  |  | 0 | 47 | 47 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029469 | RELW OH PRI INSP CLR JPOL RESD REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-06-18 | 2020-08-29 | COMP | 2020-04-30 | [16 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 163351703 | 21471.07 | 88.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117181048 | POLE_DECA_REPL - 14403 ALGERINE WARDS FE | 35188561 |  |  | STS-POLE_DECA_REPL - 14403 ALGERINE WARD | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.901 | -120.3315 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 | 21295 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.5 | 39.5 |  |  | 0 | 39.5 | 39.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101029471 | RELW OH PRI INSP JPOL RESD REMT FIRE ESTR BTKA FMOB TER2 | Pole | 2020-09-16 | 2020-11-05 | COMP | 2020-09-16 | [16 empty] | 2019-05-07 | 2020-05-07 | 2021-07-10 | 2021-07-10 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 18124.27 | 51.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117181276 | POLE_BROK_REPL - 2PW 1PN 73901 ALGERINE | 35188566 |  |  | STS-POLE_BROK_REPL - 2PW 1PN 73901 ALGER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9044 | -120.3391 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.4 | 12.4 |  |  | 0 | 12.4 | 12.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029446 | RELW OH PRI INSP RESD REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-09-16 | 2021-02-03 | COMP | 2020-09-16 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117184601 | POLE_DECA_REPL - 359 SARATOGA RD SONORA | 35154561 |  |  | STS-POLE_DECA_REPL - 359 SARATOGA RD SON | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-06-29 | Renew Permit | 37.9997 | -120.3927 |  | TIER 2 | 165 | 16376-1703, RACETRACK | T3322 |  | Y | 311 |  |  | 2021-03-11 07:00 | 2021-03-11 16:00 | Scheduled | CLICK | [6 empty] | 60.5 | 60.5 |  |  | 0 | 60.5 | 60.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101056813 | RELW OH PRI ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-04-28 | 2020-06-17 | COMP | 2020-04-28 |  |  | 2020-04-28 | 2020-05-04 | [12 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163761703 | 29959.92 | 966.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117184675 | POLE_BROK_REPL - 6PW 1PN/E 73901 ALGERIN | 35188606 |  |  | STS-POLE_BROK_REPL - 6PW 1PN/E 73901 ALG | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9059 | -120.3428 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 10.9 | 10.9 |  |  | 0 | 10.9 | 10.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029435 | RELW OH SEC INSP JPOL RESD REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-09-23 | 2021-02-03 | COMP | 2020-09-23 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 8371.68 | 303.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117186946 | POLE_BROK_REPL - 1PS 19715 LIME KILN RDS | 35188654 |  |  | STS-POLE_BROK_REPL - 1PS 19715 LIME KILN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9404 | -120.3575 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 | 19598 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.4 | 27.4 |  |  | 0 | 27.4 | 27.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033070 | RELW OH PRI INSP JPOL REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-09-30 | 2021-02-03 | COMP | 2020-09-30 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-08 | 2019-11-08 |  | 2019-11-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 15139.05 | 114.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117186981 | POLE_BROK_REPL - 13374 LIME KILN RDSONOR | 35188657 |  |  | STS-POLE_BROK_REPL - 13374 LIME KILN RDS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9399 | -120.3569 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16 | 16 |  |  | 0 | 16 | 16 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033071 | RELW OH PRI FIRE INSP JPOL REMT ESTR GO BTKA USA FMOB TER2 | Pole | 2020-09-30 | 2021-02-03 | COMP | 2020-09-30 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 12315.44 | 125.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117188128 | POLE_BROK_REPL - 7PS 19715 LIME KILN RDS | 35188666 |  |  | STS-POLE_BROK_REPL - 7PS 19715 LIME KILN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9323 | -120.354 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.4 | 15.4 |  |  | 0 | 15.4 | 15.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031607 | RELW OH PRI INSP REMT FIRE NOAC ESTR REAR USA FMOB TER2 | Pole | 2020-09-22 | 2020-11-20 | COMP | 2020-09-22 | [16 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 7171.69 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117188379 | POLE_DECA_REPL - 18177 KELLY RANCH RDSON | 35154604 |  |  | STS-POLE_DECA_REPL - 18177 KELLY RANCH R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9513 | -120.323 |  | TIER 2 | 318 | 16335-1705, CURTIS | U3521 | 890173 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 39.4 | 39.4 |  |  | 0 | 39.4 | 39.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101030496 | RELW OH PRI INSP CLR ESTR FMOB TER2 FSRP | Pole | 2020-04-20 | 2020-04-20 | COMP | 2020-04-20 | [16 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 163351705 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117190762 | POLE_DECA_REPL - 3PS 15859 LIME KILN RDS | 35188679 |  |  | STS-POLE_DECA_REPL - 3PS 15859 LIME KILN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9077 | -120.3501 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.1 | 15.1 |  |  | 0 | 15.1 | 15.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031271 | RELW OH PRI INSP JPOL RESD REMT NOAC ESTR USA FMOB TER2 | Pole | 2020-10-16 | 2020-12-03 | COMP | 2020-10-16 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117191113 | POLE_BROK_REPL - 17034 KENNEDY RDSONORA9 | 35188681 |  |  | STS-POLE_BROK_REPL - 17034 KENNEDY RDSON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9359 | -120.3507 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.6 | 17.6 |  |  | 0 | 17.6 | 17.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031681 | RELW OH REMT PRI INSP JPOL FIRE FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-10-15 | 2020-10-28 | COMP | 2020-09-23 |  |  | 2020-10-15 | 2020-10-15 | [12 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 16839.18 | 480.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117191125 | POLE_DECA_REPL - 1PS 15859 LIME KILN RDS | 35188682 |  |  | STS-POLE_DECA_REPL - 1PS 15859 LIME KILN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9093 | -120.3498 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 | 1715 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.5 | 34.5 |  |  | 0 | 34.5 | 34.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031268 | RELW OH PRI INSP JPOL RESD REMT NOAC ESTR USA FMOB TER2 | Pole | 2020-11-25 | 2020-11-25 | COMP | 2020-09-21 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 16113.69 | 257.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117191426 | POLE_DECA_REPL - 4PW LIME KILN RDSONORA9 | 35188685 |  |  | STS-POLE_DECA_REPL - 4PW LIME KILN RDSON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.912 | -120.3466 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18 | 18 |  |  | 0 | 18 | 18 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031406 | RELW OH PRI INSP JPOL RESD REMT NOAC ESTR USA FMOB TER2 | Pole | 2020-09-30 | 2020-11-23 | COMP | 2020-09-29 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 6058.3 | 135.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117191703 | POLE_DECA_REPL - 2PE 15PS MURPHY RDSONOR | 35188695 |  |  | STS-POLE_DECA_REPL - 2PE 15PS MURPHY RDS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9217 | -120.3441 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.3 | 18.3 |  |  | 0 | 18.3 | 18.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031198 | RELW OH PRI INSP CLR RESD FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 6032.67 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117191816 | POLE_DECA_REPL - 2PE 15PS 17140 MURPHY R | 35188698 |  |  | STS-POLE_DECA_REPL - 2PE 15PS 17140 MURP | UNSC | UNSC srdy | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9212 | -120.3442 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.4 | 29.4 |  |  | 0 | 29.4 | 29.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031458 | RELW OH PRI INSP CLR RESD FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-10-13 | 2020-10-15 | COMP | 2020-09-18 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 22387.96 | 400.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117192236 | POLE_BROK_REPL - 15900 LIME KILN RDSONOR | 35188762 |  |  | STS-POLE_BROK_REPL - 15900 LIME KILN RDS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.912 | -120.3512 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.2 | 19.2 |  |  | 0 | 19.2 | 19.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031251 | RELW OH PRI INSP REMT USA FIRE ESTR BTKA FMOB TER2 | Pole | 2020-09-30 | 2020-09-30 | COMP | 2020-09-30 | [16 empty] | 2019-05-09 | 2020-05-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 8096.62 | 224.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117192846 | POLE_BROK_REPL - 1PS/E 7287 ES LA VIDASO | 35188769 |  |  | STS-POLE_BROK_REPL - 1PS/E 7287 ES LA VI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9354 | -120.3467 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 9.7 | 9.7 |  |  | 0 | 9.7 | 9.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033246 | RELW OH SEC INSP JPOL REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-09-18 | 2020-09-18 | COMP | 2020-09-18 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 2995.1 | 226.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117193093 | POLE_DECA_REPL - 1PE 1PS 1PW 7287 ES LA | 35188777 |  |  | STS-POLE_DECA_REPL - 1PE 1PS 1PW 7287 ES | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9348 | -120.3472 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.2 | 21.2 |  |  | 0 | 21.2 | 21.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101033242 | RELW OH PRI INSP REMT FIRE ESTR USA FMOB TER2 | Pole | 2020-09-16 | 2020-09-16 | COMP | 2020-09-16 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 6742.3 | 543 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117193589 | POLE_DECA_REPL - 7PE 16800 JURY RANCH RD | 35188791 |  |  | STS-POLE_DECA_REPL - 7PE 16800 JURY RANC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9164 | -120.3509 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.1 | 21.1 |  |  | 0 | 21.1 | 21.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031225 | RELW OH PRI INSP JPOL REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-10-14 | 2020-12-14 | COMP | 2020-10-14 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117193624 | POLE_DECA_REPL - 8PE 16800 JURY RANCH RD | 35188796 |  |  | STS-POLE_DECA_REPL - 8PE 16800 JURY RANC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9166 | -120.3499 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 | 1715 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031217 | RELW OH PRI INSP CLR JPOL REMT NOAC ESTR REAR USA FMOB TER2 | Pole | 2020-10-16 | 2020-12-01 | COMP | 2020-10-13 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117193724 | POLE_DECA_REPL - 3PW 16121 MURPHY RDSONO | 35188811 |  |  | STS-POLE_DECA_REPL - 3PW 16121 MURPHY RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9178 | -120.3501 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.2 | 22.2 |  |  | 0 | 22.2 | 22.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031210 | RELW OH PRI INSP CLR JPOL REMT NOAC ESTR REAR USA FMOB TER2 | Pole | 2020-09-22 | 2020-11-24 | COMP | 2020-09-22 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117193942 | POLE_BROK_REPL - 1PE 2PS 17500 ROUTE 5 R | 35188826 |  |  | STS-POLE_BROK_REPL - 1PE 2PS 17500 ROUTE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9409 | -120.3465 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.9 | 20.9 |  |  | 0 | 20.9 | 20.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033221 | RELW OH PRI INSP CLR JPOL REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-09-29 | 2020-11-16 | COMP | 2020-09-28 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 7467.29 | 76.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117194751 | POLE_BROK_REPL - 21899[SGN]SAWMILL FLAT | 35154625 |  |  | STS-POLE_BROK_REPL - 21899[SGN]SAWMILL F | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0182 | -120.3879 |  | TIER 2 | 165 | 16376-1703, RACETRACK | T3313 | 26348 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.5 | 41.5 |  |  | 0 | 41.5 | 41.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101052699 | RELW OH PRI CLR JPOL RESD ESTR BTKA PRTO USA FMOB TER2 | Pole | 2020-05-28 | 2020-07-15 | COMP | 2020-05-27 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163761703 | 20301.12 | 44.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117206763 | POLE_BROK_REPL - 3PS 14484 ALGERINE WARD | 35188877 |  |  | STS-POLE_BROK_REPL - 3PS 14484 ALGERINE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9079 | -120.3268 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.1 | 21.1 |  |  | 0 | 21.1 | 21.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031128 | RELW OH PRI INSP JPOL REMT FIRE ESTR USA FMOB TER2 | Pole | 2020-10-13 | 2020-12-01 | COMP | 2020-10-12 | [16 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117213872 | POLE_DECA_REPL - 1PS 16840 OUTBACK TRAIL | 35188987 |  |  | STS-POLE_DECA_REPL - 1PS 16840 OUTBACK T | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.925 | -120.3632 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.2 | 15.2 |  |  | 0 | 15.2 | 15.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031537 | RELW JPOL OH PRI INSP REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-10-07 | 2020-12-01 | COMP | 2020-10-06 | [16 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 7145.92 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117217655 | POLE_BROK_REPL - 2PE 2PS 3PE 17140 MURPH | 35189064 |  |  | STS-POLE_BROK_REPL - 2PE 2PS 3PE 17140 M | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9304 | -120.333 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 30.8 | 30.8 |  |  | 0 | 30.8 | 30.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031104 | RELW OH PRI INSP ESTR GO FMOB TER2 | Pole | 2020-10-06 | 2020-10-13 | COMP | 2020-10-05 | [16 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 22709.01 | 148.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117217772 | POLE_BROK_REPL - 2PE 2PS 1PE 17140 MURPH | 35189075 |  |  | STS-POLE_BROK_REPL - 2PE 2PS 1PE 17140 M | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9308 | -120.3353 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.4 | 18.4 |  |  | 0 | 18.4 | 18.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101031743 | RELW OH PRI INSP ESTR FMOB TER2 | Pole | 2020-09-14 | 2020-09-14 | COMP | 2020-09-14 | [16 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 6365.54 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117217843 | POLE_DECA_REPL - 17080 MURPHY RD2PE 3PS | 35189080 |  |  | STS-POLE_DECA_REPL - 17080 MURPHY RD2PE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9248 | -120.3413 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 | 63519 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.9 | 31.9 |  |  | 0 | 31.9 | 31.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031159 | RELW OH PRI INSP REMT NOAC ESTR FMOB BTKA REAR USA TER2 | Pole | 2020-09-25 | 2020-09-25 | COMP | 2020-09-25 | [16 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 14596.05 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117217910 | POLE_DECA_REPL - 17080 MURPHY RD2PE 2PS | 35189085 |  |  | STS-POLE_DECA_REPL - 17080 MURPHY RD2PE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9261 | -120.3402 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.4 | 15.4 |  |  | 0 | 15.4 | 15.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031160 | RELW OH PRI REAR INSP REMT NOAC ESTR USA FMOB TER2 | Pole | 2020-09-29 | 2020-09-29 | COMP | 2020-09-29 | [16 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117218161 | POLE_DECA_REPL - 2PE 3PS 17140 MURPHY RD | 35189089 |  |  | STS-POLE_DECA_REPL - 2PE 3PS 17140 MURPH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9298 | -120.3374 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.4 | 18.4 |  |  | 0 | 18.4 | 18.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031741 | RELW OH PRI INSP REMT NOAC USA ESTR BTKA REAR FMOB TER2 | Pole | 2020-09-11 | 2020-09-11 | COMP | 2020-09-11 | [16 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 6365.54 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117218168 | POLE_DECA_REPL - 2PE 4PS 17140 MURPHY RD | 35189093 |  |  | STS-POLE_DECA_REPL - 2PE 4PS 17140 MURPH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9289 | -120.3381 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.7 | 29.7 |  |  | 0 | 29.7 | 29.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103112657 | OH PRI INSP CLR REMT NOAC TER2 RELW ESTR BTKA REAR USA FMOB | Pole | 2020-09-29 | 2020-10-02 | COMP | 2020-09-29 | [16 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 11272.7 | 44.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117218679 | POLE_DECA_REPL - 3PE 17140 MURPHY RDSONO | 35189111 |  |  | STS-POLE_DECA_REPL - 3PE 17140 MURPHY RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9319 | -120.336 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 | S1599 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29 | 29 |  |  | 0 | 29 | 29 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031733 | RELW OH PRI INSP CLR REMT NOAC ESTR REAR USA FMOB TER2 | Pole | 2020-10-05 | 2020-10-05 | COMP | 2020-10-05 | [16 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 10099.05 | 63.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117218815 | POLE_DECA_REPL - MURPHY RDSONORA95370 | 35189124 |  |  | STS-POLE_DECA_REPL - MURPHY RDSONORA9537 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9346 | -120.3338 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 | 1723 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 45.8 | 45 | 0.8 |  | 0 | 45.8 | 45 | 0.8 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031752 | RELW OH PRI INSP RESD REMT NOAC ESTR BTKA REAR USA FMOB TER2 | Pole | 2020-10-05 | 2020-10-05 | COMP | 2020-10-05 | [16 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 17995 | 51.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117219030 | POLE_DECA_REPL - 1PN 17255 MURPHY RDSONO | 35189131 |  |  | STS-POLE_DECA_REPL - 1PN 17255 MURPHY RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9376 | -120.3335 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 | 1723 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 55.5 | 55.3 | 0.2 |  | 0.5 | 55 | 54.8 | 0.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031766 | RELW OH PRI INSP CLR RESD REMT NOAC ESTR BTKA REAR USA FMOB TER2 | Pole | 2020-10-05 | 2020-10-05 | COMP | 2020-10-05 | [16 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 21696.39 | 206 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117219128 | POLE_DECA_REPL - 1PS 17447 MURPHY RDSONO | 35189139 |  |  | STS-POLE_DECA_REPL - 1PS 17447 MURPHY RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9383 | -120.3334 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 | 1723 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.3 | 29.3 |  |  | 0 | 29.3 | 29.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031770 | OH PRI INSP CLR RESD REMT TRAF FLAG ESTR BTKA USA FMOB TER2 RELW | Pole | 2020-10-01 | 2021-02-03 | COMP | 2020-10-01 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 12820.16 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117219185 | POLE_DECA_REPL - 1PS 2P S/W 17447 MURPHY | 35189143 |  |  | STS-POLE_DECA_REPL - 1PS 2P S/W 17447 MU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.94 | -120.3351 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.4 | 15.4 |  |  | 0 | 15.4 | 15.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031776 | RELW OH PRI INSP JPOL ESTR GO FMOB TER2 | Pole | 2020-10-09 | 2020-11-29 | COMP | 2020-10-09 | [16 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117219290 | POLE_DECA_REPL - 1PS 1PS/W 17447 MURPHY | 35189148 |  |  | STS-POLE_DECA_REPL - 1PS 1PS/W 17447 MUR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9394 | -120.3346 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 | 1723 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 1840.8 | 1840.8 |  |  | 0 | 1840.8 | 1840.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031771 | RELW OH PRI INSP CLR JPOL RESD FIRE ESTR GO BTKA FMOB TER2 | Pole | 2020-12-02 | 2020-12-02 | COMP | 2020-10-05 | [16 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 400035.64 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117323526 | POLE_BROK_REPL - 18045 OLD WARDS FERRY R | 35189384 |  |  | STS-POLE_BROK_REPL - 18045 OLD WARDS FER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9492 | -120.3462 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3403 | L1787 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 61.4 | 60.6 | 0.8 |  | 0 | 61.4 | 60.6 | 0.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 103354730 | RELW OH PRI INSP RESD FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-09-22 | 2021-02-03 | COMP | 2020-09-22 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-05-26 | 2020-05-26 |  | 2020-05-26 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117327508 | POLE_BROK_REPL - 14000 ALGERINE WARDS FE | 35189447 |  |  | STS-POLE_BROK_REPL - 14000 ALGERINE WARD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9032 | -120.3278 |  | TIER 2 | 72 | 16335-1703, CURTIS | W34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 9.2 | 9.2 |  |  | 0 | 9.2 | 9.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101029465 | RELW OH SERV RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-08 | 2020-09-08 | COMP | 2020-09-08 | [16 empty] | 2019-05-28 | 2020-05-28 |  | 2020-05-28 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 2964.09 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 119065733 | POLE_BROK_REPL - 21691 ACORN SONORA | 35179359 |  |  | B~S-POLE_BROK_REPL - 21691 ACORN SONORA | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0157 | -120.2817 |  | TIER 2 | 41 | 16335-1702, CURTIS | T3611 | 2505 | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Dispatched | CLICK | [6 empty] | 102.3 | 102.3 |  |  | 0.5 | 101.8 | 101.8 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101057279 | OH ESTR TER2 RELW | Pole | 2020-11-03 | 2020-11-13 | COMP | 2020-11-03 |  |  | 2020-11-04 | 2020-11-04 | [12 empty] | 2020-05-20 | 2020-06-20 |  | 2020-06-20 | B-Tag Addition 06.24.20 |  | Concord |  | 163351702 | 34513.75 | 8003.8 | -4018 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-06-29
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 119167150 | POLE_BROK_REPL - 18238 OLD WARDS FERRY R | 35182323 |  |  | STS-POLE_BROK_REPL - 18238 OLD WARDS FER | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9487 | -120.3412 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3422 | L1787 | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 29 | 29 |  |  | 7.75 | 28 | 28 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101043164 | RELW OH PRI TMAN CLR RESD NOAC ESTR TER2 | Pole | 2020-08-03 | 2020-08-03 | COMP | 2020-08-03 | [16 empty] | 2020-06-15 | 2020-09-15 |  | 2020-09-15 | B-Tag Addition 06.24.20 |  | Fresno |  | 163351703 | 32682.22 | 9521.5 | [7 empty] | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-06-29
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 116984278 | POLE_DECA_REPL - 11797 CAMPO SECO RD SON | 35187742 |  |  | STS-POLE_DECA_REPL - 11797 CAMPO SECO RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9553 | -120.3867 |  | TIER 2 | 72 | 16335-1703, CURTIS | U3323 | 19692 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39 | 39 |  |  | 0 | 39 | 39 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101041416 | OH RELW PRI CLR JPOL RESD ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-09-25 | 2020-11-19 | COMP | 2020-09-25 | [16 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 17707.67 | 224.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117182162 | POLE_BROK_REPL - 1PN 3PW 2PN 12701 ROUT | 35145805 |  |  | STS-POLE_BROK_REPL - 1PN 3PW 2PN 12701 R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9453 | -120.3458 |  | TIER 2 | 72 | 16335-1703, CURTIS | V3403 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 53.5 | 28.5 | 25 |  | 0 | 53.5 | 28.5 | 25 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033216 | RELW OH PRI INSP JPOL RESD FIRE ESTR BTKA USA FMOB TER2 | Pole | 2019-12-23 | 2021-01-16 | COMP | 2019-12-23 |  |  | 2021-01-16 | 2021-01-16 | [12 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan |  | UNASSIGNED |  | 163351703 | 19516.76 | 97.7 | 53.4 | 53.4 | 53.4 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117190738 | POLE_DECA_REPL - 3PS 15859 LIME KILN RDS | 35188678 |  |  | STS-POLE_DECA_REPL - 3PS 15859 LIME KILN | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9069 | -120.3503 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16 | 16 |  |  | 0 | 16 | 16 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031272 | RELW OH PRI INSP REMT FIRE NOAC ESTR USA FMOB TER2 | Pole | 2020-09-23 | 2021-01-15 | COMP | 2020-09-23 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117191590 | POLE_DECA_REPL - 2PW LIME KILN RDSONORA9 | 35188690 |  |  | STS-POLE_DECA_REPL - 2PW LIME KILN RDSON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9117 | -120.3446 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.6 | 13.6 |  |  | 0 | 13.6 | 13.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031395 | RELW OH PRI INSP JPOL RESD REMT NOAC ESTR REAR USA FMOB TER2 | Pole | 2020-09-25 | 2020-11-25 | COMP | 2020-09-25 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 5242.05 | 135.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SONORA | Sonora |  |  | OPEN | 117208119 | POLE_DECA_REPL - 1PW 1PS 16791 LIME KILN | 35188898 |  |  | STS-POLE_DECA_REPL - 1PW 1PS 16791 LIME | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9245 | -120.3515 |  | TIER 2 | 72 | 16335-1703, CURTIS | V34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 18.9 | 18.9 |  |  | 0 | 18.9 | 18.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101031478 | RELW OH PRI INSP CLR JPOL REMT NOAC TER2 ESTR REAR USA FMOB | Pole | 2020-09-25 | 2020-11-24 | COMP | 2020-09-25 | [16 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351703 | 8394.02 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SOULSBYVILLE | Sonora |  |  | OPEN | 117030304 | POLE_BROK_REPL - 19401 SOULSBYVILLE RD 3 | 35188570 |  |  | STS-POLE_BROK_REPL - 19401 SOULSBYVILLE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 37.9739 | -120.2761 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3612 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22 | 22 |  |  | 0 | 22 | 22 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033753 | RELW OH PRI JPOL FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-22 |  | COMP | 2020-09-22 |  |  | 2021-02-01 | [13 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 11604.62 | 304.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SOULSBYVILLE | Sonora |  |  | OPEN | 117042483 | POLE_BROK_REPL - 19760 SOULSBYVILLE RD. | 35154659 |  |  | STS-POLE_BROK_REPL - 19760 SOULSBYVILLE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 37.9813 | -120.2665 |  | TIER 2 | 318 | 16335-1705, CURTIS | U3608 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.5 | 15.5 |  |  | 0 | 15.5 | 15.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033996 | RELW OH SERV CLR JPOL PUBL FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-04-22 |  | COMP | 2020-04-22 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-04-16 | 2020-04-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 163351705 | 8343.72 | 193.9 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SOULSBYVILLE | Sonora |  |  | OPEN | 117051654 | POLE_BROK_REPL - 16703 ALLISON WAY 2SE 3 | 35215245 |  |  | STS-POLE_BROK_REPL - 16703 ALLISON WAY 2 | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9883 | -120.2741 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3602 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 8.2 | 8.2 |  |  | 0 | 8.2 | 8.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101039579 | RELW OH SERV PGEA RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-02 | 2021-02-01 | COMP | 2021-02-01 | [16 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SOULSBYVILLE | Sonora |  |  | OPEN | 117134585 | POLE_DECA_REPL - 17370 CARLOZZI DRSOULSB | 35154254 |  |  | STS-POLE_DECA_REPL - 17370 CARLOZZI DRSO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro JointPole |  |  | 37.9999 | -120.2604 |  | TIER 2 | 318 | 16335-1705, CURTIS | T3624 | L2057 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101055562 | RELW OH PRI INSP CLR JPOL RESD FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-08-24 |  | COMP | 2020-08-24 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-05-01 | 2020-05-01 |  | 2020-05-01 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351705 | 27215.9 | 837 | 320.2 | 320.2 | 320.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SOULSBYVILLE | Sonora |  |  | OPEN | 117027714 | POLE_BROK_REPL - 19580 JUBILEE 1PSSOULSB | 35188550 |  |  | STS-POLE_BROK_REPL - 19580 JUBILEE 1PSSO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9767 | -120.2767 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3612 | 23247 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.4 | 43.6 | 0.8 |  | 0 | 44.4 | 43.6 | 0.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033768 | RELW OH PRI REMT TRAF ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-21 | 2021-01-19 | COMP | 2020-09-21 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 17944.73 | 964.5 | 299.1 | 299.1 | 299.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SOULSBYVILLE | Sonora |  |  | OPEN | 117030658 | POLE_BROK_REPL - 19195 BLACK OAK RD. 1SE | 35188590 |  |  | STS-POLE_BROK_REPL - 19195 BLACK OAK RD. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9712 | -120.2782 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3611 | 601 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 63.1 | 62.9 | 0.2 |  | 0 | 63.1 | 62.9 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033774 | RELW OH PRI CLR RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-10-16 | COMP | 2020-10-15 | [16 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SOULSBYVILLE | Sonora |  |  | OPEN | 117038670 | POLE_BROK_REPL - 19380 AMERIO RD.SOULSBY | 35187592 |  |  | STS-POLE_BROK_REPL - 19380 AMERIO RD.SOU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9735 | -120.2736 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3612 | 54761 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.2 | 37.2 |  |  | 0 | 37.2 | 37.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033789 | RELW OH PRI REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-22 | 2020-09-22 | COMP | 2020-09-22 | [16 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 15750.3 | 181 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SOULSBYVILLE | Sonora |  |  | OPEN | 117041132 | POLE_BROK_REPL - 17057 MT. SIDE DR. SOUL | 35187657 |  |  | STS-POLE_BROK_REPL - 17057 MT. SIDE DR. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9748 | -120.2685 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3613 | 22180 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.2 | 28.2 |  |  | 0 | 28.2 | 28.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033857 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-01 | 2021-01-06 | COMP | 2020-10-01 | [16 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SOULSBYVILLE | Sonora |  |  | OPEN | 117041371 | POLE_BURN_REPL - 17115 MONTE GRANDE DR 1 | 35187662 |  |  | STS-POLE_BURN_REPL - 17115 MONTE GRANDE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9747 | -120.2673 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3613 | 97407 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.2 | 42.2 |  |  | 0 | 42.2 | 42.2 |  |  | EC | E | Pole | Burnt | Replace |  | 101033868 | RELW OH PRI PGEA CLR RESD TRAF FLAG FMOB ESTR BTKA USA TER2 PRTO | Pole | 2020-09-24 | 2021-02-01 | COMP | 2020-09-24 |  |  | 2021-02-01 | 2021-02-01 | [12 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 20248.88 | 352.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SOULSBYVILLE | Sonora |  |  | OPEN | 117041562 | POLE_BROK_REPL - 17083 MT. SIDE DR. SOUL | 35187680 |  |  | STS-POLE_BROK_REPL - 17083 MT. SIDE DR. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.974 | -120.2678 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3613 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 11.8 | 11.8 |  |  | 0 | 11.8 | 11.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033859 | RELW OH SEC JPOL REMT ESTR GO BTKA PROG FMOB TER2 PRTO | Pole | 2020-09-21 | 2020-09-22 | COMP | 2020-09-21 | [16 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 7188.16 | 257.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SOULSBYVILLE | Sonora |  |  | OPEN | 117217436 | POLE_DECA_REPL - 17341 LIVERMORE LN. SOU | 35154712 |  |  | STS-POLE_DECA_REPL - 17341 LIVERMORE LN. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-01-09 | Renew Permit | 37.9942 | -120.2612 |  | TIER 2 | 318 | 16335-1705, CURTIS | U3604 | L2061 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.4 | 57.4 |  |  | 0 | 57.4 | 57.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101048697 | OH PRI INSP RESD FIRE PROG RELW ESTR GO FMOB TER2 FSRP | Pole | 2020-07-03 | 2020-09-25 | COMP | 2020-05-05 |  |  | 2021-02-19 | 2020-04-11 | [12 empty] | 2019-05-12 | 2020-05-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 163351705 | 30051.86 | 562 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SOULSBYVILLE | Sonora |  |  | OPEN | 117219389 | POLE_DECA_REPL - 20111 SOULSBYVILLE RD S | 35154732 |  |  | STS-POLE_DECA_REPL - 20111 SOULSBYVILLE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9874 | -120.2645 |  | TIER 2 | 318 | 16335-1705, CURTIS | U3603 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.1 | 15.1 |  |  | 0 | 15.1 | 15.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101048884 | RELW OH SEC BTKA INSP RESD ESTR USA FMOB TER2 FSRP | Pole | 2020-04-28 | 2020-06-25 | COMP | 2020-04-28 | [16 empty] | 2019-05-12 | 2020-05-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 163351705 | 4659.06 | 44.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | SOULSBYVILLE | Sonora |  |  | OPEN | 119368760 | POLE_BROK_REPL - 19650 JUBILEE CT. 1N 1W | 35186519 |  |  | STS-POLE_BROK_REPL - 19650 JUBILEE CT. 1 | CONS | CONS ERDY SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9794 | -120.2762 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3607 | 9220SB | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 114.4 | 106 | 8.4 |  | 15 | 112.4 | 104 | 8.4 |  | EC | B | Pole | Broken/Damaged | Replace |  | 101034065 | RELW OH FMOB PRI INSP CLR ESTR TER2 | Pole | 2020-08-04 | 2020-08-20 | COMP | 2020-08-04 |  |  | 2020-08-20 | 2020-08-20 | [12 empty] | 2020-07-14 | 2020-10-14 |  | 2020-10-14 | Work Plan Reconcilation (B-Tags) |  | San Francisco |  | 163351702 | 100578.13 | 39446.7 | 3924.1 | 8553.9 | 8553.9 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-07-21
Bay/Central | YO | Soulsbyville | Sonora |  |  | OPEN | 120109950 | POLE_BROK_REPL - 20574 KINGS CTSoulsbyvi | 35218502 |  |  | STS-POLE_BROK_REPL - 20574 KINGS CTSOULS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-31 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9956 | -120.2653 |  | TIER 2 | 318 | 16335-1705, CURTIS | T3623 | 78181 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.3 | 33.3 |  |  | 0 | 33.3 | 33.3 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101055418 | RELW CLR OH PRI JPOL RESD FLAG ESTR BTKA OTHR USA FMOB TER2 | Pole | 2020-12-14 | 2020-12-17 | COMP | 2020-12-14 |  |  | 2020-12-15 | 2020-12-15 | [12 empty] | 2020-11-30 | 2021-02-28 |  | 2021-02-28 | B tag clean up 12/2/2020 |  | Fresno |  | 163351705 | 21212.06 | 131 | [7 empty] | N | Pulled from MPP Import File | N |  | Y | 2020-12-02
Bay/Central | YO | TOULUMNE | Sonora |  |  | OPEN | 117037369 | POLE_BROK_REPL - AF\17801 SILVER SPUR RD | 35188669 |  |  | STS-POLE_BROK_REPL - AF\17801 SILVER SPU | UNSC | UNSC srdy | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9454 | -120.2502 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.6 | 14.6 |  |  | 0 | 14.6 | 14.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048019 | RELW OH PRI RESD REMT ESTR BTKA PROG FMOB TER2 PRTO | Pole | 2020-09-21 | 2020-10-13 | COMP | 2020-09-21 | [16 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 7738.77 | 352.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TOULUMNE | Sonora |  |  | OPEN | 117037683 | POLE_BROK_REPL - FR\YD\OF 17801 SILVER S | 35187579 |  |  | STS-POLE_BROK_REPL - FR\YD\OF 17801 SILV | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9451 | -120.2486 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 | S1663 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 47.5 | 47.5 |  |  | 0 | 47.5 | 47.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048021 | RELW OH SERV CLR RESD REMT ESTR GO BTKA PROG FMOB TER2 PRTO | Pole | 2020-10-06 | 2020-10-06 | COMP | 2020-10-06 | [16 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 21166.53 | 225.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TOUUMNE | Sonora |  |  | OPEN | 117041640 | POLE_BROK_REPL - BK\YD\OF 17250 SILVER S | 35187685 |  |  | STS-POLE_BROK_REPL - BK\YD\OF 17250 SILV | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9443 | -120.259 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.6 | 28.6 |  |  | 0 | 28.6 | 28.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048050 | RELW OH PRI CLR REMT ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-09-30 | 2020-09-30 | COMP | 2020-09-30 | [16 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117210693 | POLE_DECA_REPL - 18834 MT.EATON RD 1ETUO | 35188978 |  |  | STS-POLE_DECA_REPL - 18834 MT.EATON RD 1 | ADER | ADER SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9516 | -120.2308 |  | TIER 2 | 41 | 16335-1702, CURTIS | U37 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 15 | 15 |  |  | 0 | 15 | 15 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101045999 | RELW OH SEC PGEA INSP REMT FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-10-15 | 2020-10-15 | COMP | 2020-10-15 | [16 empty] | 2019-05-10 | 2020-05-10 | 2024-05-08 | 2024-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 9120.88 | 157.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117017533 | POLE_BROK_REPL - AF\ENT\TO 18461 HERSHEY | 35188239 |  |  | STS-POLE_BROK_REPL - AF\ENT\TO 18461 HER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9538 | -120.2662 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3623 | L2153 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.7 | 34.7 |  |  | 1 | 33.7 | 33.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033506 | RELW OH PRI PGEA CLR RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-02 | 2020-11-16 | COMP | 2020-09-30 | [16 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 16040.09 | 760.1 | 144.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117018147 | POLE_BROK_REPL - AF\ENT\18301 HERSHEY EA | 35188255 |  |  | STS-POLE_BROK_REPL - AF\ENT\18301 HERSHE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9541 | -120.2629 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3623 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 23.5 | 23.5 |  |  | 0 | 23.5 | 23.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033514 | RELW OH PRI PGEA RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-09 | 2020-09-09 | COMP | 2020-09-09 |  |  | 2020-09-04 | 2020-09-04 | [12 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117018782 | POLE_BROK_REPL - 17600 APPLEGATE COLONY | 35188288 |  |  | STS-POLE_BROK_REPL - 17600 APPLEGATE COL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9435 | -120.2443 |  | TIER 2 | 41 | 16335-1702, CURTIS | V37 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.8 | 13.8 |  |  | 0 | 13.8 | 13.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103349072 | RELW OH PRI REMT NOAC ESTR USA FMOB TER2 PRTO | Pole | 2020-09-16 | 2020-09-16 | COMP | 2020-09-16 | [16 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 6269.65 | 268.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117019266 | POLE_BROK_REPL - AF\ENT\18301 HERSHEY EA | 35188303 |  |  | STS-POLE_BROK_REPL - AF\ENT\18301 HERSHE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9521 | -120.2624 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3623 | L2153 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 56.4 | 54.6 | 1.8 |  | 0 | 56.4 | 54.6 | 1.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033509 | RELW OH PRI PGEA CLR RESD ESTR PRTO BTKA USA FMOB TER2 | Pole | 2020-09-11 | 2021-02-01 | COMP | 2020-09-11 |  |  | 2021-02-01 | 2021-02-01 | [12 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 28202.12 | 498.7 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117021122 | POLE_BROK_REPL - E\OF\ENT 18507HERSHEY W | 35188319 |  |  | STS-POLE_BROK_REPL - E\OF\ENT 18507HERSH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9535 | -120.2672 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3623 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 15.1 | 15.1 |  |  | 0 | 15.1 | 15.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101033501 | RELW OH PRI PGEA RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 6649.14 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117024431 | POLE_BROK_REPL - 19361 CHEROKEE RD.TUOLU | 35188430 |  |  | STS-POLE_BROK_REPL - 19361 CHEROKEE RD.T | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9747 | -120.25 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3615 | S1793 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.6 | 41.6 |  |  | 0 | 41.6 | 41.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032857 | RELW OH PRI PGEA CLR RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-18 | 2020-09-18 | COMP | 2020-09-18 | [16 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 19207.56 | 401.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117027773 | POLE_BROK_REPL - 19400 CHEROKEE RD. 2NTU | 35188560 |  |  | STS-POLE_BROK_REPL - 19400 CHEROKEE RD. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9735 | -120.2593 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3614 | S1793 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.7 | 39.7 |  |  | 0 | 39.7 | 39.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032807 | RELW OH PRI PGEA CLR RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-30 | 2020-09-30 | COMP | 2020-09-30 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 19213.27 | 123.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117030392 | POLE_BROK_REPL - A\F\SW\C\O YOSIMITY RD\ | 35188575 |  |  | STS-POLE_BROK_REPL - A\F\SW\C\O YOSIMITY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9485 | -120.2663 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 | 23394 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.3 | 24.3 |  |  | 0 | 24.3 | 24.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047866 | RELW OH PRI RESD TRAF ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-28 | 2021-01-15 | COMP | 2020-09-28 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 13771.86 | 373.1 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117030591 | POLE_BROK_REPL - 19290 CHEROKEE RD.TUOLU | 35188585 |  |  | STS-POLE_BROK_REPL - 19290 CHEROKEE RD.T | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9728 | -120.2604 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3614 | S1793 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 59.9 | 59.1 | 0.8 |  | 0 | 59.9 | 59.1 | 0.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032789 | RELW OH PRI PGEA CLR COMM ESTR BTKA USA FMOB PRTO TER2 | Pole | 2020-10-05 | 2021-01-16 | COMP | 2020-10-05 |  |  | 2021-01-16 | 2021-01-16 | [12 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 25232.31 | 53.4 | 53.4 | 53.4 | 53.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117031956 | POLE_BROK_REPL - N\OF\ENT 17732 SADDLE R | 35188600 |  |  | STS-POLE_BROK_REPL - N\OF\ENT 17732 SADD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9446 | -120.2655 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 | 23394 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 45.9 | 45.9 |  |  | 0 | 45.9 | 45.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047907 | RELW CLR OH PRI REMT NOAC FLAG ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 |  |  | 2020-08-21 | 2020-08-21 | [12 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 19396.59 | 344.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117032441 | POLE_BROK_REPL - N\OF\ENT 17587 SADDLE R | 35188625 |  |  | STS-POLE_BROK_REPL - N\OF\ENT 17587 SADD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9422 | -120.2647 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.1 | 27.1 |  |  | 0 | 27.1 | 27.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047892 | RELW OH PRI BTKA REMT ESTR GO USA FMOB TER2 PRTO | Pole | 2020-09-17 | 2021-02-01 | COMP | 2020-09-17 |  |  | 2021-02-01 | 2021-02-01 | [12 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 16094.62 | 518.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117033723 | POLE_BROK_REPL - A\F\SW\C\O YOSIMITY RD\ | 35188643 |  |  | STS-POLE_BROK_REPL - A\F\SW\C\O YOSIMITY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9491 | -120.2659 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.5 | 20.5 |  |  | 0 | 20.5 | 20.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047917 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-11 | 2020-09-11 | COMP | 2020-09-11 | [16 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 9856.61 | 514.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117034755 | POLE_BROK_REPL - AF\ENT\TO 18097\ YOSIMI | 35188652 |  |  | STS-POLE_BROK_REPL - AF\ENT\TO 18097\ YO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9495 | -120.2515 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25 | 25 |  |  | 0 | 25 | 25 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047996 | RELW OH PRI CLR RESD REMT FLAG ESTR BTKA PRTO USA FMOB TER2 | Pole | 2020-10-01 | 2021-01-19 | COMP | 2020-10-01 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 14167.39 | 341.6 | 299.1 | 299.1 | 299.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117036994 | POLE_BROK_REPL - SE\CO YOSIMITY RD\HHERS | 35188664 |  |  | STS-POLE_BROK_REPL - SE\CO YOSIMITY RD\H | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9496 | -120.2622 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 39.7 | 39.7 |  |  | 0 | 39.7 | 39.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101047942 | RELW OH PRI FLAG ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-10-15 | 2021-01-19 | COMP | 2020-10-15 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 16245.16 | 373.9 | 373.9 | 373.9 | 373.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117037422 | POLE_BROK_REPL - AF\17801 SILVER SPUR RD | 35187575 |  |  | STS-POLE_BROK_REPL - AF\17801 SILVER SPU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9451 | -120.2494 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.1 | 22.1 |  |  | 0 | 22.1 | 22.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048020 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-18 | 2020-10-13 | COMP | 2020-09-17 | [16 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 10597.17 | 361.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117039613 | POLE_BROK_REPL - FR\YD\OF 17801 SILVER S | 35187628 |  |  | STS-POLE_BROK_REPL - FR\YD\OF 17801 SILV | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.944 | -120.2512 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 16.3 | 16.3 |  |  | 0 | 16.3 | 16.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048029 | RELW OH PRI FLAG ESTR BTKA PROG FMOB TER2 PRTO | Pole | 2020-10-08 | 2021-01-19 | COMP | 2020-10-08 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 11116.31 | 450 | 373.9 | 373.9 | 373.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117041495 | POLE_BROK_REPL - BK\YD\OF 17634 SILVER S | 35187673 |  |  | STS-POLE_BROK_REPL - BK\YD\OF 17634 SILV | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9459 | -120.255 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 | L2155 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34 | 34 |  |  | 0 | 34 | 34 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048035 | RELW OH PRI REMT NOAC ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-10-01 | 2020-10-01 | COMP | 2020-09-30 | [16 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117041810 | POLE_BROK_REPL - FR\YD\OF 17634 SILVER S | 35187698 |  |  | STS-POLE_BROK_REPL - FR\YD\OF 17634 SILV | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9472 | -120.2559 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.2 | 18.2 |  |  | 0 | 18.2 | 18.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048039 | RELW OH PRI REMT ESTR TER2 BTKA USA FMOB PRTO | Pole | 2020-09-28 | 2020-09-28 | COMP | 2020-09-28 | [16 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 7607.73 | 85.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117042017 | POLE_BROK_REPL - BK\YD\OF 18071 YOSEMITE | 35187704 |  |  | STS-POLE_BROK_REPL - BK\YD\OF 18071 YOSE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.946 | -120.2577 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 | L2155 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 55.6 | 54.6 | 1 |  | 0 | 55.6 | 54.6 | 1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048044 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-10-12 | COMP | 2020-10-12 | [16 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117042480 | POLE_BROK_REPL - FR\YD\OF 17301 SILVER S | 35187721 |  |  | STS-POLE_BROK_REPL - FR\YD\OF 17301 SILV | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9425 | -120.2604 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.9 | 26.9 |  |  | 0 | 26.9 | 26.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101048062 | RELW OH PRI REMT ESTR GO PRTO REAR FMOB TER2 | Pole | 2020-09-14 | 2020-09-14 | COMP | 2020-09-14 | [16 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 11834.4 | 362 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117046865 | POLE_BROK_REPL - S\OF\ENT 17600 APPLEGAT | 35187753 |  |  | STS-POLE_BROK_REPL - S\OF\ENT 17600 APPL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9422 | -120.2485 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18 | 18 |  |  | 0 | 18 | 18 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046601 | RELW OH PRI REMT NOAC ESTR REAR USA FMOB PRTO TER2 | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-04-17 | 2020-04-17 |  | 2020-04-17 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 9502.02 | 271.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117046870 | POLE_BROK_REPL - S\OF\ENT 17600 APPLEGAT | 35187759 |  |  | STS-POLE_BROK_REPL - S\OF\ENT 17600 APPL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9427 | -120.2483 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.4 | 14.4 |  |  | 0 | 14.4 | 14.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046599 | RELW OH PRI REMT ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-09-21 | 2020-09-21 | COMP | 2020-09-21 | [16 empty] | 2019-04-17 | 2020-04-17 |  | 2020-04-17 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 5056.97 | 314 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117047026 | POLE_BROK_REPL - S\OF\ENT 17600 APPLEGAT | 35187765 |  |  | STS-POLE_BROK_REPL - S\OF\ENT 17600 APPL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9408 | -120.2493 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18 | 18 |  |  | 0 | 18 | 18 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046694 | RELW OH PRI REMT NOAC ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-09-21 | 2020-09-21 | COMP | 2020-09-21 | [16 empty] | 2019-04-17 | 2020-04-17 |  | 2020-04-17 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 6002.02 | 271.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117049188 | POLE_BROK_REPL - S\OF\ENT 17600 APPLE CO | 35187782 |  |  | STS-POLE_BROK_REPL - S\OF\ENT 17600 APPL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9361 | -120.2519 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.2 | 20.2 |  |  | 0 | 20.2 | 20.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046706 | RELW OH PRI CLR REMT ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-09-17 | 2020-11-18 | COMP | 2020-09-16 | [16 empty] | 2019-04-17 | 2020-04-17 |  | 2020-04-17 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 7070.64 | 316.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117049329 | POLE_BROK_REPL - BK\YD\OF 17600 APPLE CO | 35187795 |  |  | STS-POLE_BROK_REPL - BK\YD\OF 17600 APPL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9354 | -120.2524 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 | 961393 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.2 | 31.2 |  |  | 0 | 31.2 | 31.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046709 | RELW OH PRI CLR REMT NOAC SPCR ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-10-07 | 2020-10-07 | COMP | 2020-10-07 | [16 empty] | 2019-04-17 | 2020-04-17 |  | 2020-04-17 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 14713.83 | 42.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Tuolumne | Sonora |  |  | OPEN | 117049632 | POLE_BROK_REPL - north of 17600 apple co | 35187801 |  |  | STS-POLE_BROK_REPL - NORTH OF 17600 APPL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9398 | -120.2498 |  | TIER 2 | 41 | 16335-1702, CURTIS | V36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.8 | 13.8 |  |  | 0 | 13.8 | 13.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046696 | RELW INSP OH PRI REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-09-14 | 2020-09-14 | COMP | 2020-09-14 | [16 empty] | 2019-04-17 | 2020-04-17 |  | 2020-04-17 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 11503.7 | 667.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117064953 | POLE_BROK_REPL - 18191 YOSEMITE RD TUOLU | 35188044 |  |  | STS-POLE_BROK_REPL - 18191 YOSEMITE RD T | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9512 | -120.247 |  | TIER 2 | 41 | 16335-1702, CURTIS | U36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.3 | 25.3 |  |  | 0 | 25.3 | 25.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103349006 | RELW OH PRI NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-09-22 | 2020-11-04 | COMP | 2020-09-22 | [16 empty] | 2019-04-19 | 2020-04-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 16931.73 | 422.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117152753 | POLE_DECA_REPL - 20170 TUOLUMNE RDTUOLUM | 35154314 |  |  | STS-POLE_DECA_REPL - 20170 TUOLUMNE RDTU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-01-09 | Renew Permit | 37.9887 | -120.2457 |  | TIER 2 | 318 | 16335-1705, CURTIS | U3701 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50.5 | 50.5 |  |  | 0 | 50.5 | 50.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101044323 | RELW OH PRI INSP CLR JPOL PUBL RESD FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-08-17 | 2020-08-17 | COMP | 2020-08-17 |  |  | 2021-02-21 | 2021-02-21 | [12 empty] | 2019-05-03 | 2020-05-03 |  | 2020-05-03 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351705 | 26425.85 | 550.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117209273 | POLE_BROK_REPL - REAR OF 18650 LAUREL AV | 35154666 |  |  | STS-POLE_BROK_REPL - REAR OF 18650 LAURE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.959 | -120.2317 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 | 79009 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 52.1 | 51.6 | 0.5 |  | 0 | 52.1 | 51.6 | 0.5 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046110 | RELW OH PRI INSP RESD FIRE NOAC ESTR GO REAR USA FMOB TER2 FSRP | Pole | 2020-06-02 | 2020-12-29 | COMP | 2020-06-01 | [16 empty] | 2019-05-10 | 2020-05-10 | 2024-05-08 | 2024-05-08 | 2021 CBP Plan | 2020-05-31 | CALENG |  | 163351702 | 20778.09 | 194.6 | 0 | 90.5 | 90.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117209358 | POLE_DECA_REPL - 18101 MT.EATON RDTUOLUM | 35188937 |  |  | STS-POLE_DECA_REPL - 18101 MT.EATON RDTU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9515 | -120.2326 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 | L1109 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.9 | 44.9 |  |  | 0 | 44.9 | 44.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101045968 | RELW OH PRI INSP CLR JPOL GO REMT FIRE FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-10-06 | 2020-12-03 | COMP | 2020-10-06 |  |  | 2020-08-18 | 2020-08-18 | [12 empty] | 2019-05-10 | 2020-05-10 | 2024-05-08 | 2024-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 20091.01 | 140.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117209832 | POLE_BROK_REPL - 18650 LAUREL AVE/1PSTUO | 35188968 |  |  | STS-POLE_BROK_REPL - 18650 LAUREL AVE/1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9581 | -120.2317 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 | 79009 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.1 | 38.1 |  |  | 0 | 38.1 | 38.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046113 | RELW OH PRI INSP RESD FIRE ESTR FMOB BTKA REAR USA TER2 FSRP | Pole | 2020-09-29 | 2020-09-29 | COMP | 2020-09-29 | [16 empty] | 2019-05-10 | 2020-05-10 | 2024-05-08 | 2024-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117214037 | POLE_BROK_REPL - 18641 SEQUIOA ST/1PNTUO | 35188998 |  |  | STS-POLE_BROK_REPL - 18641 SEQUIOA ST/1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9575 | -120.2318 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 | 79009 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50.2 | 50.2 |  |  | 0 | 50.2 | 50.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046027 | RELW OH PRI INSP RESD FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-09-29 | 2020-09-29 | COMP | 2020-09-29 | [16 empty] | 2019-05-11 | 2020-05-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 21956.68 | 118.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117214177 | POLE_BROK_REPL - 18641 SEQUIOA ST TUOLUM | 35209686 |  |  | STS-POLE_BROK_REPL - 18641 SEQUIOA ST TU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9572 | -120.2318 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 | 79009 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43.3 | 43.3 |  |  | 0 | 43.3 | 43.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046023 | RELW OH PRI INSP RESD FIRE ESTR BTKA USA FMOB FSRP TER2 | Pole | 2020-12-09 | 2020-12-09 | COMP | 2020-12-09 | [16 empty] | 2019-05-11 | 2020-05-11 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163351702 | 23049.41 | 273.7 | -1556.6 | -1194.6 | -1194.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE | Sonora |  |  | OPEN | 117223827 | POLE_BROK_REPL - 18355 APPLE COLONY RDTU | 35189159 |  |  | STS-POLE_BROK_REPL - 18355 APPLE COLONY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9527 | -120.2384 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3721 | 56337 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 64.5 | 63.8 | 0.7 |  | 0 | 64.5 | 63.8 | 0.7 |  | EC | E | Pole | Broken/Damaged | Replace |  | 103349062 | RELW OH PRI INSP CLR RESD REMT FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-09-25 | 2020-09-25 | COMP | 2020-09-25 | [16 empty] | 2019-05-13 | 2020-05-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 24737.04 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117017364 | POLE_BROK_REPL - FR\YD\OF\18034 APPLEGAT | 35188227 |  |  | STS-POLE_BROK_REPL - FR\YD\OF\18034 APPL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.9494 | -120.2378 |  | TIER 2 | 41 | 16335-1702, CURTIS | V37 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.9 | 20.2 | 1.7 |  | 0 | 21.9 | 20.2 | 1.7 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046435 | RELW OH SERV CLR RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-13 |  | COMP | 2020-10-13 | [16 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117026955 | POLE_BROK_REPL - MB 17955 APPLEGATE COLO | 35188497 |  |  | STS-POLE_BROK_REPL - MB 17955 APPLEGATE | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 37.9472 | -120.2332 |  | TIER 2 | 41 | 16335-1702, CURTIS | V37 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 13.2 | 13.2 |  |  | 0 | 13.2 | 13.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046407 | RELW OH PRI REMT NOAC ESTR USA FMOB TER2 PRTO | Pole | 2020-09-16 |  | COMP | 2020-09-16 | [16 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 12595.97 | 339.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117033718 | POLE_BROK_REPL - 18300 CARMACK LN. 1S\1W | 35154638 |  |  | STS-POLE_BROK_REPL - 18300 CARMACK LN. 1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9677 | -120.2395 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3716 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101043708 | RELW OH REMT SERV CLR RESD NOAC ESTR GO USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2024-04-13 | 2024-04-13 | 2021 CBP Plan | 2020-12-31 | CALENG |  | 163351702 | 1 | 45.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117033749 | POLE_BROK_REPL - 18300 CARMACK LN. 1S\1W | 35209511 |  |  | STS-POLE_BROK_REPL - 18300 CARMACK LN. 1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9679 | -120.2392 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3716 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101043713 | RELW OH PRI JPOL RESD NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163351702 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117039464 | POLE_BROK_REPL - 19011 CARTER/2PSW/1PW T | 35187622 |  |  | STS-POLE_BROK_REPL - 19011 CARTER/2PSW/1 | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9671 | -120.2356 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3717 | 2191 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 46.3 | 46.3 |  |  | 0 | 46.3 | 46.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101043364 | RELW OH RESD PRI CLR JPOL REMT NOAC ESTR GO USA FMOB TER2 PRTO | Pole | 2020-10-13 |  | COMP | 2020-10-13 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 27958.18 | 307.5 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117046537 | POLE_BROK_REPL - 18833 BIRCH ST TUOLUMNE | 35187749 |  |  | STS-POLE_BROK_REPL - 18833 BIRCH ST TUOL | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9644 | -120.2334 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3717 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 12.7 | 12.7 |  |  | 0 | 12.7 | 12.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101043507 | RELW OH SERV JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-09 | 2020-10-05 | COMP | 2020-10-05 | [16 empty] | 2019-04-17 | 2020-04-17 |  | 2020-04-17 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 3665.05 | 241 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117049997 | POLE_BROK_REPL - W\OF\ENT 17420 TUOLUMNE | 35187813 |  |  | STS-POLE_BROK_REPL - W\OF\ENT 17420 TUOL | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.9635 | -120.2588 |  | TIER 2 | 41 | 16335-1702, CURTIS | U36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.5 | 23.5 |  |  | 0 | 23.5 | 23.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032738 | RELW OH PRI JPOL TRAF ESTR BTKA FSRP PRTO FMOB TER2 | Pole | 2020-09-22 | 2021-02-01 | COMP | 2020-09-22 |  |  | 2021-02-01 | 2021-02-01 | [12 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 16096.74 | 565 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117214918 | POLE_DECA_REPL - 18247 APPLE COLONY RD-- | 35189045 |  |  | STS-POLE_DECA_REPL - 18247 APPLE COLONY | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9538 | -120.2352 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.3 | 12.3 |  |  | 0 | 12.3 | 12.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101045880 | RELW OH SEC PGEA INSP REMT FIRE FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-09-25 |  | COMP | 2020-09-25 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-05-11 | 2020-05-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 9359.64 | 256.6 | 213.5 | 213.5 | 213.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117215141 | POLE_DECA_REPL - 18217 APPLE COLONY RDTU | 35189049 |  |  | STS-POLE_DECA_REPL - 18217 APPLE COLONY | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 37.9529 | -120.236 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 | 396967 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 63.1 | 62.3 | 0.8 |  | 0 | 63.1 | 62.3 | 0.8 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101045888 | RELW OH PRI PGEA INSP CLR RESD FIRE FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole | 2021-01-15 | 2021-01-14 | COMP | 2020-09-30 |  |  | 2021-01-14 | 2021-01-14 | [12 empty] | 2019-05-11 | 2020-05-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 26888.92 | 356.4 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117215406 | POLE_BROK_REPL - 18555 MAPLETUOLUMNE CIT | 35214720 |  |  | STS-POLE_BROK_REPL - 18555 MAPLETUOLUMNE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.9567 | -120.234 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046008 | RELW OH SERV INSP RESD FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-11 | 2020-05-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163351702 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117218726 | POLE_BROK_REPL - 18333 APPLE COLONY/2PW/ | 35189119 |  |  | STS-POLE_BROK_REPL - 18333 APPLE COLONY/ | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9557 | -120.2351 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 | 48807 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 45.9 | 45.9 |  |  | 0 | 45.9 | 45.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101045854 | RELW OH PRI INSP RESD FIRE ESTR BTKA REAR USA FMOB TER2 FSRP | Pole | 2020-09-25 |  | COMP | 2020-09-25 | [16 empty] | 2019-05-12 | 2020-05-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 23380.05 | 85.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117218813 | POLE_BROK_REPL - 18333 APPLE COLONY/2PWT | 35209705 |  |  | STS-POLE_BROK_REPL - 18333 APPLE COLONY/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9552 | -120.2354 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 | 48807 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101045862 | RELW OH PRI INSP RESD FIRE NOAC USA ESTR BTKA REAR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-12 | 2020-05-12 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163351702 | 1 | 40.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117017503 | POLE_BROK_REPL - S\OF\DR\18056 APPLEGATE | 35188233 |  |  | STS-POLE_BROK_REPL - S\OF\DR\18056 APPLE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9498 | -120.2369 |  | TIER 2 | 41 | 16335-1702, CURTIS | V37 | 396967 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.3 | 13.3 |  |  | 0 | 13.3 | 13.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046431 | OH SERV CLR RESD ESTR BTKA USA FMOB TER2 PRTO RELW | Pole | 2020-10-12 | 2021-01-19 | COMP | 2020-10-12 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 8861.82 | 299.1 | 299.1 | 299.1 | 299.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117022437 | POLE_BROK_REPL - 19337 CHEROKEE RD 3WTUO | 35188389 |  |  | STS-POLE_BROK_REPL - 19337 CHEROKEE RD 3 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9703 | -120.2517 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3615 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.2 | 14.2 |  |  | 0 | 14.2 | 14.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032720 | RELW OH PRI PGEA RESD REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-24 | 2020-09-24 | COMP | 2020-09-24 | [16 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 6494.49 | 404.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117031814 | POLE_BROK_REPL - 19300 CHEROKEE RD 3S SP | 35188595 |  |  | STS-POLE_BROK_REPL - 19300 CHEROKEE RD 3 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9702 | -120.2582 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3614 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 10.7 | 10.7 |  |  | 0 | 10.7 | 10.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032800 | RELW OH PRI PGEA REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-21 | 2020-09-21 | COMP | 2020-09-21 | [16 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 4747.08 | 449.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117032674 | POLE_BROK_REPL - 18322 OAK ST./2PW\3N\1\ | 35188630 |  |  | STS-POLE_BROK_REPL - 18322 OAK ST./2PW\3 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9652 | -120.2388 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3716 | 1381 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.5 | 37.5 |  |  | 0 | 37.5 | 37.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101043678 | RELW OH PRI CLR COMM ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-09-29 | 2020-10-26 | COMP | 2020-09-17 | [16 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 20298.05 | 1726.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117042630 | POLE_BROK_REPL - 18646 CROCKERTUOLUMNE C | 35187726 |  |  | STS-POLE_BROK_REPL - 18646 CROCKERTUOLUM | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9664 | -120.2325 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3717 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.5 | 32.8 | 1.7 |  | 0 | 34.5 | 32.8 | 1.7 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101043544 | RELW OH SERV CLR RESD REMT NOAC ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-11-06 | COMP | 2020-10-12 | [16 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 14643.93 | 165.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117046418 | POLE_BROK_REPL - 18602 BAKER/1E 1SETUOLU | 35187743 |  |  | STS-POLE_BROK_REPL - 18602 BAKER/1E 1SET | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9638 | -120.2301 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3717 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.4 | 24.4 |  |  | 0 | 24.4 | 24.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101043526 | RELW OH PRI REMT NOAC ESTR USA FMOB TER2 PRTO | Pole | 2020-09-30 | 2020-12-31 | COMP | 2020-09-29 | [16 empty] | 2019-04-17 | 2020-04-17 |  | 2020-04-17 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 8901.5 | 271.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117046469 | POLE_BROK_REPL - 18833 BIRCH STTUOLUMNE | 35154665 |  |  | STS-POLE_BROK_REPL - 18833 BIRCH STTUOLU | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9645 | -120.2332 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3717 | 49177 | Y | 311 |  |  | 2021-03-03 07:00 | 2021-03-03 16:00 | Dispatched | CLICK | [6 empty] | 80.9 | 79.9 | 1 |  | 0 | 80.9 | 79.9 | 1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101043508 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-05-15 | 2020-07-24 | COMP | 2020-05-15 |  |  | 2020-07-24 | 2020-07-24 | [12 empty] | 2019-04-17 | 2020-04-17 |  | 2020-04-17 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351702 | 32977.31 | 5679.8 | 5635.5 | 5635.5 | 5635.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117049290 | POLE_BROK_REPL - FR\YD\OF\17420 TUOLUMNE | 35187788 |  |  | STS-POLE_BROK_REPL - FR\YD\OF\17420 TUOL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9652 | -120.2586 |  | TIER 2 | 41 | 16335-1702, CURTIS | U36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.6 | 20.4 | 0.2 |  | 0 | 20.6 | 20.4 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101032734 | RELW OH SEC NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-09-21 | 2020-09-21 | COMP | 2020-09-21 | [16 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351702 | 8581.47 | 316 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117159554 | POLE_BROK_REPL - TUOLUMNE RD/MI WU ST/1P | 35154342 |  |  | STS-POLE_BROK_REPL - TUOLUMNE RD/MI WU S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9752 | -120.241 |  | TIER 2 | 318 | 16335-1705, CURTIS | U3711 | 8110 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43.6 | 43.6 |  |  | 0 | 43.6 | 43.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101044556 | INSP OH PRI RELW JPOL REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-08-19 | 2021-01-15 | COMP | 2020-08-19 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351705 | 21716.85 | 481.1 | 74.8 | 74.8 | 74.8 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117208569 | POLE_BROK_REPL - 18306 YOSEMITETUOLUMNE | 35188905 |  |  | STS-POLE_BROK_REPL - 18306 YOSEMITETUOLU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9553 | -120.2406 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3721 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 25 | 25 |  |  | 0 | 25 | 25 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046228 | RELW OH SEC INSP RESD FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-10-15 | 2021-01-17 | COMP | 2020-10-15 |  |  | 2021-01-17 | 2021-01-17 | [12 empty] | 2019-05-10 | 2020-05-10 | 2024-05-08 | 2024-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 13238.04 | 95.9 | 53.4 | 53.4 | 53.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117209463 | POLE_BROK_REPL - 18317 YOSEMITE/3PSETUOL | 35188942 |  |  | STS-POLE_BROK_REPL - 18317 YOSEMITE/3PSE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.954 | -120.2393 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3721 | L1657 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 58.1 | 55.9 | 2.2 |  | 0 | 58.1 | 55.9 | 2.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046226 | RELW OH PRI FIRE INSP CLR RESD ESTR BTKA REAR USA FMOB TER2 FSRP | Pole | 2020-09-23 | 2020-09-23 | COMP | 2020-09-23 | [16 empty] | 2019-05-10 | 2020-05-10 | 2024-05-08 | 2024-05-08 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 22026.77 | 42.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117209733 | POLE_BROK_REPL - 18300#L YOSEMITETUOLUMN | 35188957 |  |  | STS-POLE_BROK_REPL - 18300#L YOSEMITETUO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9542 | -120.2413 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3721 | L1657 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.3 | 38.3 |  |  | 0 | 38.3 | 38.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046233 | RELW OH PRI INSP PUBL RESD TRAF USA FLAG ESTR BTKA FMOB TER2 FSRP | Pole | 2020-10-08 | 2021-01-19 | COMP | 2020-10-08 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 20808.77 | 405.2 | 320.2 | 320.2 | 320.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117213935 | POLE_BROK_REPL - 18610 ELM ST.1E TUOLUMN | 35188992 |  |  | STS-POLE_BROK_REPL - 18610 ELM ST.1E TUO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9577 | -120.2323 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.5 | 14.5 |  |  | 0 | 14.5 | 14.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101046029 | RELW OH SERV INSP JPOL RESD FIRE ESTR GO BTKA USA FMOB FSRP TER2 | Pole | 2020-10-05 | 2021-01-19 | COMP | 2020-10-05 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-05-11 | 2020-05-11 | 2024-05-09 | 2024-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 13173.14 | 416.4 | 373.9 | 373.9 | 373.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117214299 | POLE_DECA_REPL - 18148 MT.EATON RD 1NTUO | 35189009 |  |  | STS-POLE_DECA_REPL - 18148 MT.EATON RD 1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9525 | -120.2334 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 | L1109 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 35.7 | 35.7 |  |  | 0 | 35.7 | 35.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101045961 | RELW OH PRI INSP CLR JPOL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-09-29 | 2021-01-15 | COMP | 2020-09-29 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-05-11 | 2020-05-11 | 2024-05-09 | 2024-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 20124.01 | 281.6 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117214772 | POLE_DECA_REPL - 18256 APPLE COLONY RD-- | 35154694 |  |  | STS-POLE_DECA_REPL - 18256 APPLE COLONY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9541 | -120.2351 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 | 396967 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 45.3 | 45.3 |  |  | 0 | 45.3 | 45.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101045871 | RELW OH PRI PGEA INSP CLR REMT FIRE FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-07-21 | 2020-09-17 | COMP | 2020-07-21 |  |  | 2020-09-02 | 2020-09-02 | [12 empty] | 2019-05-11 | 2020-05-11 | 2024-05-09 | 2024-05-09 | 2021 CBP Plan | 2020-07-31 | CALENG |  | 163351702 | 25520.44 | 128.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117216288 | POLE_DECA_REPL - 18256 APPLE COLONY RDTU | 35189054 |  |  | STS-POLE_DECA_REPL - 18256 APPLE COLONY | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9535 | -120.2369 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.5 | 14.5 |  |  | 0 | 14.5 | 14.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101045922 | RELW OH PRI PGEA INSP CLR REMT FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-10-06 | 2020-10-06 | COMP | 2020-10-06 | [16 empty] | 2019-05-11 | 2020-05-11 | 2024-05-09 | 2024-05-09 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 9182.59 | 160.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117218506 | POLE_DECA_REPL - BOX FACTORY RD/BODENHAM | 35189100 |  |  | STS-POLE_DECA_REPL - BOX FACTORY RD/BODE | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.955 | -120.2445 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3721 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.9 | 25.9 |  |  | 0 | 25.9 | 25.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101046282 | RELW OH PRI INSP REMT FIRE FLAG ESTR GO BTKA USA FMOB TER2 FSRP | Pole | 2020-09-25 | 2020-11-25 | COMP | 2020-09-25 |  |  | 2020-08-27 | 2020-08-27 | [12 empty] | 2019-05-12 | 2020-05-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 11628.21 | 4119.3 | 1383 | 1383 | 1383 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117223815 | POLE_DECA_REPL - 18228 APPLE COLONY RD 2 | 35189156 |  |  | STS-POLE_DECA_REPL - 18228 APPLE COLONY | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9526 | -120.2378 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 13.2 | 13.2 |  |  | 0 | 13.2 | 13.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101045919 | RELW OH PRI INSP CLR RESD ESTR BTKA USA FMOB FSRP TER2 | Pole | 2020-09-29 | 2020-09-29 | COMP | 2020-09-29 | [16 empty] | 2019-05-13 | 2020-05-13 | 2024-05-11 | 2024-05-11 | 2021 CBP Plan | 2020-11-15 | CALENG |  | 163351702 | 6007.34 | 42.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUOLUMNE CITY | Sonora |  |  | OPEN | 117323466 | POLE_DECA_REPL - 18466 APPLE COLONY RD/1 | 35154360 |  |  | STS-POLE_DECA_REPL - 18466 APPLE COLONY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-01-09 | Renew Permit | 37.9516 | -120.2369 |  | TIER 2 | 41 | 16335-1702, CURTIS | U3722 | 396967 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 59.5 | 59.5 |  |  | 0 | 59.5 | 59.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101045930 | RELW OH PRI PGEA CLR RESD FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-05-05 | 2020-09-03 | COMP | 2020-05-04 |  |  | 2021-02-21 | 2021-02-21 | [12 empty] | 2019-05-26 | 2020-05-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 163351702 | 29016.77 | 625.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUTTLETOWN | Sonora |  |  | OPEN | 117152309 | POLE_DECA_REPL - 8565 WILCOX RANCH RD/1/ | 35215150 |  |  | STS-POLE_DECA_REPL - 8565 WILCOX RANCH R | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9894 | -120.4598 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U3104 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.5 | 18.5 |  |  | 0 | 18.5 | 18.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101012744 | RELW PRI OH JPOL RESD REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-01-19 | COMP | 2021-01-19 | [16 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163761704 | 7176.92 |  | 0 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUTTLETOWN | Sonora |  |  | OPEN | 117153091 | POLE_BROK_REPL - 20112 HWY 49 NEAR GARAG | 35209063 |  |  | STS-POLE_BROK_REPL - 20112 HWY 49 NEAR G | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.9883 | -120.461 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U3103 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.7 | 13.7 |  |  | 0 | 13.7 | 13.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101012759 | RELW OH SERV JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-08 | 2021-01-07 | COMP | 2021-01-07 | [16 empty] | 2019-05-03 | 2020-05-03 | 2020-10-09 | 2020-10-09 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 163761704 | 4417.68 | 8.8 | 0 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUTTLETOWN | Sonora |  |  | OPEN | 117160682 | POLE_BROK_REPL - 20420 HWY 49TUTTLETOWN | 35215249 |  |  | STS-POLE_BROK_REPL - 20420 HWY 49TUTTLET | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9927 | -120.4516 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U3105 | 299321 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101012645 | RELW OH PRI CLR JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163761704 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TUTTLTOWN | Sonora |  |  | OPEN | 117153084 | TREE_CLER_TRIM - 20112 HWY 49 TUTTLTOWN | 35215156 |  |  | STS-TREE_CLER_TRIM - 20112 HWY 49 TUTTLT | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.9881 | -120.4606 |  | TIER 2 | 485 | 16376-1704, RACETRACK | U3104 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Tree/Vine | Clearance Impaired | Trim |  | 101012758 | RELW OH SERV RESD NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 163761704 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | TWAIN HARTE | Sonora |  |  | OPEN | 117207504 | POLE_BROK_REPL - 21716 KNOX RD 1PSTWAIN | 35114989 |  |  | STS-POLE_BROK_REPL - 21716 KNOX RD 1PSTW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0163 | -120.2324 |  | TIER 2 | 64 | 16366-1701, MIWUK | T3712 | L1167 | Y | 311 |  |  | 2020-01-21 | 2020-01-21 | Completed | Order Operation | [6 empty] | 41.7 | 41 | 0.7 |  | 0 | 41.7 | 41 | 0.7 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101038659 | RELW OH PRI INSP RESD FIRE ESTR GO BTKA USA FMOB TER2 | Pole | 2019-08-28 | 2019-08-30 | COMP | 2019-08-27 | [16 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | Q1 Work Plan |  | UNASSIGNED |  | 163661701 | 14237.69 | 2480.9 |  |  |  | 7698.5 |  | 7698.5 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | WAWONA | Oakhurst |  |  | OPEN | 117122896 | TREE_DECA_INPL - NA WAWONA HIGHWAY 41 | 35174954 |  |  | BC7 STS-TREE_DECA_INPL - NA WAWONA HIGHW | PEND | PEND | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.538 | -119.6571 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000004215 |  | Y | 311 |  |  |  |  | Returned | Order Operation | [6 empty] | 0.8 | 0.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | B | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103228982 | RESD RELW OH PRI ESTR BTKA FMOB TER2 PRTO | Pole | 2020-05-22 |  | COMP | 2020-05-22 |  |  | 2020-05-22 | 2020-05-22 | [12 empty] | 2019-04-29 | 2020-04-29 | 2020-07-21 | 2020-07-21 | B-Tag Clean Up 5/14/20 |  | Fresno |  | 254421103 | 6910.35 | 4229.5 | 362 | 327.2 | 327.2 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-05-25
Bay/Central | YO | WSIP | Oakhurst |  |  | OPEN | 117344264 | POLE_DECA_REPL - 45068 GOLD CREEK RD/2PS | 35208924 |  |  | STS-POLE_DECA_REPL - 45068 GOLD CREEK RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2492 | -119.7248 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212C | 5683 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 72.7 | 71.6 | 1.1 |  | 0 | 72.7 | 71.6 | 1.1 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101061948 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-09 |  | COMP | 2021-02-09 | [16 empty] | 2019-05-30 | 2020-05-30 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 28700.42 | 403.6 | 390.1 | 182.9 | 182.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | WSIP | Oakhurst |  |  | OPEN | 117375541 | POLE_DECA_REPL - WSIPWSIP | 35208974 |  |  | STS-POLE_DECA_REPL - WSIPWSIP | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 37.2526 | -119.7212 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08212C | 5683 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 49.8 | 49.8 |  |  | 0 | 49.8 | 49.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103229086 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-09 | 2021-02-09 | COMP | 2021-02-09 | [16 empty] | 2019-05-31 | 2020-05-31 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 21212.21 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | WSIP | Sonora |  |  | OPEN | 116851331 | TIEW_LOOS_REPL - BK\OF\TOLE BOOTH TO YOS | 35188501 |  |  | STS-TIEW_LOOS_REPL - BK\OF\TOLE BOOTH TO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.7983 | -119.8657 |  | TIER 2 | 72 | 16335-1703, CURTIS | Y46 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.4 | 15.4 |  |  | 0 | 15.4 | 15.4 |  |  | EC | E | Tie Wire | Loose | Replace |  | 101038715 | RELW OH PRI PGEA CLR REMT ESTR TER2 BTKA USA FMOB PRTO | Pole | 2020-09-21 |  | COMP | 2020-09-21 |  |  | 2020-09-18 | 2020-09-18 | [12 empty] | 2019-03-27 | 2020-03-27 |  | 2020-03-27 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 6776.57 | 4693.8 | 1476.5 | 1476.5 | 1476.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | WSIP | Sonora |  |  | OPEN | 116866658 | POLE_BURN_REPL - R\OF\HS\11255 SAWMILL M | 35188549 |  |  | STS-POLE_BURN_REPL - R\OF\HS\11255 SAWMI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8265 | -119.964 |  | TIER 2 | 72 | 16335-1703, CURTIS | X44 | S1999 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.2 | 39.2 |  |  | 0 | 39.2 | 39.2 |  |  | EC | E | Pole | Burnt | Replace |  | 101038554 | RELW OH PRI PGEA CLR REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-10 | 2020-09-10 | COMP | 2020-09-10 | [16 empty] | 2019-03-29 | 2020-03-29 |  | 2020-03-29 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 20077.46 | 566.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | WSIP | Sonora |  |  | OPEN | 116875085 | POLE_BROK_REPL - R\OF\HS\11255 SAWMILL M | 35188607 |  |  | STS-POLE_BROK_REPL - R\OF\HS\11255 SAWMI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8337 | -119.9828 |  | TIER 2 | 72 | 16335-1703, CURTIS | X43 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.2 | 33.2 |  |  | 0 | 33.2 | 33.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101038497 | RELW OH PRI REMT ESTR USA FMOB TER2 PRTO | Pole | 2020-09-15 | 2020-11-12 | COMP | 2020-09-15 | [16 empty] | 2019-03-30 | 2020-03-30 |  | 2020-03-30 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 27594.32 | 2339.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | WSIP | Sonora |  |  | OPEN | 116875090 | POLE_BURN_REPL - R\OF\HS\11255 SAWMILL M | 35188612 |  |  | STS-POLE_BURN_REPL - R\OF\HS\11255 SAWMI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8318 | -119.979 |  | TIER 2 | 72 | 16335-1703, CURTIS | X43 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.7 | 31.7 |  |  | 0 | 31.7 | 31.7 |  |  | EC | E | Pole | Burnt | Replace |  | 101038501 | RELW OH PRI REMT TER2 ESTR USA FMOB PRTO | Pole | 2020-09-15 | 2020-11-19 | COMP | 2020-09-15 | [16 empty] | 2019-03-30 | 2020-03-30 |  | 2020-03-30 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 163351703 | 26842.52 | 2653.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | WSIP | Sonora |  |  | OPEN | 116885319 | POLE_BURN_REPL - 25855 RICHARDS RANCH RD | 35154064 |  |  | STS-POLE_BURN_REPL - 25855 RICHARDS RANC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8739 | -120.3091 |  | TIER 2 | 72 | 16335-1703, CURTIS | W35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 39.4 | 39.4 |  |  | 0 | 39.4 | 39.4 |  |  | EC | E | Pole | Burnt | Replace |  | 101029713 | RELW PRI OH REMT ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-03-30 | 2020-05-13 | COMP | 2020-03-30 | [16 empty] | 2019-04-01 | 2020-04-01 | 2024-03-30 | 2024-03-30 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 163351703 | 30632.59 | 4436.6 |  |  |  | 88.7 |  | 88.7 |  | Y | MPP File Only | N |  | Y | 2020-02-18
Bay/Central | YO | YOSEMITE LAKES | Madera |  |  | OPEN | 117385963 | POLE_DECA_REPL - A/F 31735 RD 400YOSEMIT | 35154624 |  |  | STS-POLE_DECA_REPL - A/F 31735 RD 400YOS | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-04-20 | Change Schedule/Request Extension | 37.2087 | -119.7858 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08206A |  | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Scheduled | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101062140 | RELW OH PRI JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-09-02 | 2020-09-02 | COMP | 2020-09-02 |  |  | 2020-04-16 | 2020-04-22 | [12 empty] | 2019-06-04 | 2020-06-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254432104 | 15250.52 | 910.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Merced |  |  | OPEN | 117363346 | POLE_BROK_REPL - ENT 31777 RD 400 1PE YO | 35154562 |  |  | STS-POLE_BROK_REPL - ENT 31777 RD 400 1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-03-05 |  | 37.2074 | -119.7827 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08206A | 10328 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.1 | 39.1 |  |  | 0 | 39.1 | 39.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101062137 | RELW OH PRI PGEA RESD FIRE FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-09-28 | 2020-09-28 | COMP | 2020-09-28 |  |  | 2020-03-05 | 2020-03-09 | [12 empty] | 2019-05-31 | 2020-05-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254432104 | 37508.46 | 2323.2 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Merced |  |  | OPEN | 117363458 | POLE_BURN_REPL - 31735 RD 400 1PW YOSEMI | 35154566 |  |  | STS-POLE_BURN_REPL - 31735 RD 400 1PW YO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-03-05 |  | 37.2088 | -119.7867 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08206A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.7 | 20.7 |  |  | 0 | 20.7 | 20.7 |  |  | EC | E | Pole | Burnt | Replace |  | 101062143 | RELW OH PRI PGEA RESD FIRE FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-08-29 | 2020-08-31 | COMP | 2020-08-27 |  |  | 2020-03-05 | 2020-03-09 | [12 empty] | 2019-05-31 | 2020-05-31 | 2024-05-29 | 2024-05-29 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254432104 | 11801.05 | 1168.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116837263 | POLE_DECA_REPL - 30665 SENTINELYOSEMITE | 35214838 |  |  | STS-POLE_DECA_REPL - 30665 SENTINELYOSEM | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1939 | -119.7519 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205D | 6165 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.5 | 41.5 |  |  | 0 | 41.5 | 41.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059812 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-04 |  | COMP | 2021-01-04 | [16 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 22279.37 | 165.3 | 0 | 407.5 | 407.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116861028 | POLE_DECA_REPL - 42848 RANGER CIR DR 1PS | 35209326 |  |  | STS-POLE_DECA_REPL - 42848 RANGER CIR DR | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2008 | -119.7636 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B | 5509 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101058707 | RELW OH PRI CLR FLAG ESTR BTKA USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116862706 | POLE_DECA_REPL - RANGER CIR DR/MOCCASSIN | 35209398 |  |  | STS-POLE_DECA_REPL - RANGER CIR DR/MOCCA | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.2015 | -119.7609 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B | 5509 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 49.9 | 47.5 | 2.4 |  | 0 | 49.9 | 47.5 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101058717 | RELW OH PRI FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-10 |  | COMP | 2021-02-10 | [16 empty] | 2019-03-29 | 2020-03-29 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 22586.1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116863083 | POLE_DECA_REPL - 43152 RANGER CIR DR 3PN | 35209422 |  |  | STS-POLE_DECA_REPL - 43152 RANGER CIR DR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2051 | -119.7602 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101058741 | RELW OH PRI JPOL FMOB REMT ESTR BTKA TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116863224 | POLE_DECA_REPL - 30270 CORRAL DR YOSEMIT | 35215227 |  |  | STS-POLE_DECA_REPL - 30270 CORRAL DR YOS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1899 | -119.7798 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205C | 6292 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101060063 | OH PRI CLR RESD FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116863959 | POLE_BROK_REPL - CORRAL/WINCHESTER WY YO | 35209443 |  |  | STS-POLE_BROK_REPL - CORRAL/WINCHESTER W | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1873 | -119.7794 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101058990 | RELW OH PRI CLR RESD FIRE TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 |  | 2020-03-28 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116864860 | POLE_BROK_REPL - 43283 RANGER CIR 1PS YO | 35209448 |  |  | STS-POLE_BROK_REPL - 43283 RANGER CIR 1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2038 | -119.755 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.6 | 36.6 |  |  | 0 | 36.6 | 36.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101058757 | RELW OH PRI JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-18 | 2021-02-18 | COMP | 2021-02-18 | [16 empty] | 2019-03-28 | 2020-03-28 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 12522.37 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116864897 | POLE_BROK_REPL - 42753 RANGER CIR DR 3PE | 35209454 |  |  | STS-POLE_BROK_REPL - 42753 RANGER CIR DR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2014 | -119.767 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B | 5509 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101058697 | RELW OH PRI FLAG ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116865109 | POLE_DECA_REPL - #1 S/O 43283 RANGER CIR | 35209462 |  |  | STS-POLE_DECA_REPL - #1 S/O 43283 RANGER | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2037 | -119.7549 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B | 5509 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102316195 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2020-11-06 | 2020-11-06 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116865157 | POLE_DECA_REPL - RANGER CIR DR/BEAR PAW | 35209468 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2028 | -119.7592 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.8 | 19.8 |  |  | 0 | 19.8 | 19.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101058737 | RELW OH SEC RESD ESTR BTKA FSRP PRTO FMOB TER2 | Pole | 2021-02-17 | 2021-02-17 | COMP | 2021-02-17 |  |  | 2021-02-17 | 2021-02-17 | [12 empty] | 2019-03-29 | 2020-03-29 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 6240.59 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116866550 | POLE_DECA_REPL - RANGER CIR DR/MOCCASSIN | 35209510 |  |  | STS-POLE_DECA_REPL - RANGER CIR DR/MOCCA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.2001 | -119.7613 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B | 5509 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101058719 | RELW OH PRI RESD ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116870950 | POLE_DECA_REPL - REVIS/RANGE CIR DR 4PEY | 35209541 |  |  | STS-POLE_DECA_REPL - REVIS/RANGE CIR DR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.1996 | -119.7671 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B | 5509 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101058668 | RELW OH PRI BTKA RESD FLAG ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2020-09-08 | 2020-09-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116871026 | POLE_DECA_REPL - REVIS/RANGE CIR DR 3PE/ | 35209546 |  |  | STS-POLE_DECA_REPL - REVIS/RANGE CIR DR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1995 | -119.7684 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101058666 | RELW OH SEC RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116871342 | POLE_DECA_REPL - 42816 BADGER CIR 6PNYOS | 35209555 |  |  | STS-POLE_DECA_REPL - 42816 BADGER CIR 6P | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro |  |  | 37.1992 | -119.7681 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101058667 | RELW OH PRI RESD ESTR BTKA FSRP PRTO FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2020-09-08 | 2020-09-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116871649 | POLE_DECA_REPL - REVIS/RANGE CIR DR 1PEY | 35209580 |  |  | STS-POLE_DECA_REPL - REVIS/RANGE CIR DR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1992 | -119.7687 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B | 5509 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101058662 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116877358 | POLE_DECA_REPL - BADGER CIR/BADGER CT 1P | 35215544 |  |  | STS-POLE_DECA_REPL - BADGER CIR/BADGER C | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1974 | -119.7657 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059061 | RELW OH SERV CLR JPOL RESD FIRE ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116877883 | POLE_DECA_REPL - STETSON/HOLIDAY 2PS/1PW | 35209662 |  |  | STS-POLE_DECA_REPL - STETSON/HOLIDAY 2PS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1899 | -119.7722 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205C | 10572 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101058920 | RELW OH PRI CLR RESD FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 |  | 2020-03-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116883377 | POLE_DECA_REPL - RANGER CIR/REVIS RDYOSE | 35215610 |  |  | STS-POLE_DECA_REPL - RANGER CIR/REVIS RD | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 37.196 | -119.7622 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059052 | RELW OH PRI CLR JPOL RESD FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2021-02-05 | 2021-02-05 | [12 empty] | 2019-04-01 | 2020-04-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 1 | 13.5 | 0 | 978 | 978 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116884729 | POLE_DECA_REPL - REVIS/YOSEMITE SPGS DR | 35214565 |  |  | STS-POLE_DECA_REPL - REVIS/YOSEMITE SPGS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1947 | -119.7639 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205C | 5525 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059046 | RELW OH PRI CLR JPOL RESD FIRE TRAF FLAG ESTR GO TER2 BTKA USA FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-01 | 2020-04-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116912001 | POLE_DECA_REPL - 30228 STETSON DR 1PNWYO | 35086165 |  |  | STS-POLE_DECA_REPL - 30228 STETSON DR 1P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 37.1877 | -119.7739 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205C | 10572 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101058931 | RELW OH PRI CLR JPOL RESD REMT FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-02 | 2020-04-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254432104 | 1 | 44.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116936643 | POLE_BROK_REPL - REVIS RD/W REVIS CIR 1P | 35209704 |  |  | STS-POLE_BROK_REPL - REVIS RD/W REVIS CI | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1943 | -119.7624 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 21.2 | 21.2 |  |  | 0 | 21.2 | 21.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101059132 | RELW OH PRI CLR JPOL RESD FIRE FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 |  | COMP | 2021-01-28 | [16 empty] | 2019-04-02 | 2020-04-02 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 11438.42 | 13.5 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116936954 | POLE_DECA_REPL - 30164 YOSRMITE SPGS PWY | 35214572 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1867 | -119.7675 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08205C | 24802 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.8 | 36.8 |  |  | 0 | 36.8 | 36.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059651 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2019-04-02 | 2020-04-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432103 | 22292.75 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116941565 | POLE_DECA_REPL - REVIS RD/REVIS CT 1PWYO | 35209741 |  |  | STS-POLE_DECA_REPL - REVIS RD/REVIS CT 1 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1897 | -119.7639 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205C | 10569 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 37.6 | 37.6 |  |  | 0 | 37.6 | 37.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059376 | RELW OH PRI CLR JPOL RESD FIRE FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 |  | COMP | 2021-01-28 | [16 empty] | 2019-04-03 | 2020-04-03 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 19476.77 | 13.5 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116949147 | POLE_DECA_REPL - 30300 REVIS RDYOSEMITE | 35208771 |  |  | STS-POLE_DECA_REPL - 30300 REVIS RDYOSEM | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1891 | -119.7627 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205C | 10569 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.2 | 32.2 |  |  | 0 | 32.2 | 32.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059399 | RELW OH PRI CLR JPOL RESD FIRE FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-21 |  | COMP | 2021-01-21 | [16 empty] | 2019-04-03 | 2020-04-03 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 18128.17 | 13.5 | 0 | 366.8 | 366.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116951085 | POLE_DECA_REPL - REVIS RD/REVIS CIR 1PSE | 35208777 |  |  | STS-POLE_DECA_REPL - REVIS RD/REVIS CIR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1876 | -119.7606 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205C | 10569 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059421 | RELW OH PRI CLR JPOL RESD FIRE FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-03 | 2020-04-03 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116951396 | POLE_DECA_REPL - REVIS RD/REVIS CIR 1PSE | 35208785 |  |  | STS-POLE_DECA_REPL - REVIS RD/REVIS CIR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1878 | -119.7602 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205C | 10569 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059423 | RELW OH PRI CLR JPOL RESD FIRE FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-03 | 2020-04-03 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116959028 | POLE_BROK_REPL - 42841 REVIS WY 1PE YOSE | 35208855 |  |  | STS-POLE_BROK_REPL - 42841 REVIS WY 1PE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1916 | -119.765 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08205C | 24802 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.3 | 40.3 |  |  | 0 | 40.3 | 40.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101059521 | RELW OH PRI CLR JPOL RESD REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 |  | COMP | 2021-01-28 | [16 empty] | 2019-04-04 | 2020-04-04 | 2020-09-08 | 2020-09-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 21064.74 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117011563 | POLE_BROK_REPL - 43500 CAVE STONE CT. YO | 35209229 |  |  | STS-POLE_BROK_REPL - 43500 CAVE STONE CT | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1706 | -119.7587 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B | 10574 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 60.8 | 60 | 0.8 |  | 0 | 60.8 | 60 | 0.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101106640 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-16 |  | COMP | 2021-02-16 |  |  | 2021-01-18 | [13 empty] | 2019-04-11 | 2020-04-11 | 2020-10-30 | 2020-10-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 23428.45 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117012157 | POLE_DECA_REPL - 1PN 29849 REVIS RD.YOSE | 35209250 |  |  | STS-POLE_DECA_REPL - 1PN 29849 REVIS RD. | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land |  |  | 37.1836 | -119.7585 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 09201B | 10569 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.9 | 42.3 | 0.6 |  | 0 | 42.9 | 42.3 | 0.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101107064 | RELW OH PRI CLR FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-05 |  | COMP | 2021-02-05 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 22518.75 | 60.2 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117012221 | POLE_DECA_REPL - 29103 YOSEMITE SPRG. PK | 35209255 |  |  | STS-POLE_DECA_REPL - 29103 YOSEMITE SPRG | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1712 | -119.7578 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106638 | RELW OH PRI FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-11 | 2020-04-11 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117015459 | POLE_BROK_REPL - 1PS 1PW 29739 YOSEMITE | 35209269 |  |  | STS-POLE_BROK_REPL - 1PS 1PW 29739 YOSEM | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land |  |  | 37.1822 | -119.7677 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 20.7 | 20.7 |  |  | 0 | 20.7 | 20.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101106462 | RELW OH PRI JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-29 |  | COMP | 2020-12-29 | [16 empty] | 2019-04-12 | 2020-04-12 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 13717.96 | 1113.9 | 1060.1 | 663.7 | 663.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117016164 | POLE_BROK_REPL - 1PN 29839 YOSEMITE LK. | 35209296 |  |  |  | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1817 | -119.7665 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B | 24802 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 46.5 | 46.5 |  |  | 0 | 46.5 | 46.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101106463 | RELW OH PRI CLR JPOL RESD ESTR USA FMOB TER2 PRTO FSRP | Pole | 2021-02-16 | 2021-02-16 | COMP | 2021-02-16 | [16 empty] | 2019-04-12 | 2020-04-12 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 20715.92 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117018293 | POLE_DECA_REPL - 1PS 29833 CORRAL DR.YOS | 35209306 |  |  | STS-POLE_DECA_REPL - 1PS 29833 CORRAL DR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1814 | -119.7703 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B | 10329 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.5 | 56.4 | 1.1 |  | 0 | 57.5 | 56.4 | 1.1 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106469 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 |  | COMP | 2021-01-19 | [16 empty] | 2019-04-12 | 2020-04-12 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 25581.01 | 13.5 | 0 | 366.8 | 366.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117018546 | POLE_BROK_REPL - 29239 GRAPEVINE TR.YOSE | 35209311 |  |  | STS-POLE_BROK_REPL - 29239 GRAPEVINE TR. | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1703 | -119.7541 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201A | 10574 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101107130 | RELW OH PRI RESD FIRE TRAF FLAG FMOB ESTR BTKA USA TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-12 | 2020-04-12 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 230.7 | 217.2 | 217.2 | 217.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117019198 | POLE_DECA_REPL - 29390 GLACIERYOSEMITE L | 35209331 |  |  | STS-POLE_DECA_REPL - 29390 GLACIERYOSEMI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1747 | -119.7644 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B | 10763 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106669 | RELW OH PRI CLR RESD FLAG ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-12 | 2020-04-12 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117021105 | POLE_DECA_REPL - 1PE 29043 ACORNYOSEMITE | 35209352 |  |  | STS-POLE_DECA_REPL - 1PE 29043 ACORNYOSE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1707 | -119.7739 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B | 10267 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106741 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2020-10-30 | 2020-10-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117021525 | POLE_DECA_REPL - 43463 CRYSTAL SPRINGS C | 35209357 |  |  | STS-POLE_DECA_REPL - 43463 CRYSTAL SPRIN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.1701 | -119.7597 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B | 10763 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 55.8 | 54.2 | 1.6 |  | 0 | 55.8 | 54.2 | 1.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106651 | RELW OH PRI CLR RESD ESTR REAR FMOB TER2 FSRP PRTO | Pole | 2021-02-10 |  | COMP | 2021-02-10 | [16 empty] | 2019-04-13 | 2020-04-13 | 2020-10-30 | 2020-10-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 22376.14 | 45.9 | 32.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117021609 | POLE_BROK_REPL - 1PW 29529 REVIS RD.YOSE | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 37.1775 | -119.7573 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 09201A | 10569 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101107103 | REGW OH PRI CLR JPOL RESD FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-04-13 | 2020-04-13 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan |  | UNASSIGNED |  | 254432104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117021772 | POLE_DECA_REPL - 42768 LONG HOLLOWYOSEMI | 35209366 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1711 | -119.7713 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B | 10267 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 81.9 | 80.7 | 1.2 |  | 0 | 81.9 | 80.7 | 1.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106733 | RELW OH PRI FLAG ESTR GO BTKA USA PROG FMOB TER2 PRTO FSRP | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2019-04-13 | 2020-04-13 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 35148.95 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117021815 | POLE_DECA_REPL - 2PS 41850 HORSESHOE BEN | 35209371 |  |  | STS-POLE_DECA_REPL - 2PS 41850 HORSESHOE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1839 | -119.7846 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 09201B | 6292 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106566 | RELW OH PRI CLR JPOL RESD FIRE ESTR BTKA USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 187.5 | 174 | 174 | 174 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117021944 | POLE_DECA_REPL - 2PS 1PE 41850 HORSESHOE | 35209375 |  |  | STS-POLE_DECA_REPL - 2PS 1PE 41850 HORSE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1838 | -119.7844 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 09201B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106567 | OH RELW PRI CLR JPOL RESD FIRE ESTR BTKA USA FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117022175 | POLE_DECA_REPL - 1PN 1PW 42800 LONG HOLL | 35209380 |  |  | STS-POLE_DECA_REPL - 1PN 1PW 42800 LONG | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1721 | -119.771 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B | 10267 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106731 | RELW OH PRI FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117022418 | POLE_DECA_REPL - 29618 JIM BOWIEYOSEMITE | 35209385 |  |  | STS-POLE_DECA_REPL - 29618 JIM BOWIEYOSE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1788 | -119.7723 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 09201B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106491 | RELW OH PRI CLR JPOL RESD REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2020-12-17 | 2020-12-17 | [12 empty] | 2019-04-13 | 2019-10-13 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117023873 | POLE_DECA_REPL - 29800 MARIPOSA CT.YOSEM | 35209401 |  |  | STS-POLE_DECA_REPL - 29800 MARIPOSA CT.Y | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1818 | -119.7732 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106480 | RELW OH PRI JPOL RESD USA FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117023926 | POLE_DECA_REPL - 1PN 29865 HORSESHOE DR. | 35214951 |  |  | STS-POLE_DECA_REPL - 1PN 29865 HORSESHOE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.182 | -119.7806 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 09201B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 9.3 | 9.3 |  |  | 0 | 9.3 | 9.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106550 | RELW OH SERV CLR JPOL RESD FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-17 | 2021-02-17 | COMP | 2021-02-16 | [16 empty] | 2019-04-13 | 2020-04-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 2996.54 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117023969 | POLE_BROK_REPL - A/F 29800 MARIPOSA CT. | 35209411 |  |  | STS-POLE_BROK_REPL - A/F 29800 MARIPOSA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1816 | -119.7734 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101106481 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2019-04-13 | 2020-04-13 | 2020-10-15 | 2020-10-15 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 20279.35 | 13.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117024215 | POLE_BROK_REPL - 1PS 29798 HORSESHOE DR. | 35209416 |  |  | STS-POLE_BROK_REPL - 1PS 29798 HORSESHOE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.1807 | -119.7816 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 09201B | 10614 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.3 | 39.3 |  |  | 0 | 39.3 | 39.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101106547 | RELW OH PRI CLR JPOL RESD FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-29 |  | COMP | 2021-01-29 | [16 empty] | 2019-04-13 | 2020-04-13 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 20309.04 | 136.1 | 46.8 | 169 | 169 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117024326 | POLE_DECA_REPL - LONG HOLLOWYOSEMITE LAK | 35209421 |  |  | STS-POLE_DECA_REPL - LONG HOLLOWYOSEMITE | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1754 | -119.7664 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 18.9 | 18.9 |  |  | 0 | 18.9 | 18.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106679 | RELW OH PRI FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-16 |  | COMP | 2021-02-16 | [16 empty] | 2019-04-13 | 2020-04-13 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 10424.59 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117024604 | POLE_DECA_REPL - 1PW 43515 CEDAR GROVE W | 35209426 |  |  | STS-POLE_DECA_REPL - 1PW 43515 CEDAR GRO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.1759 | -119.7592 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 09201B | 10569 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 42.8 | 42.8 |  |  | 0 | 42.8 | 42.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101107080 | RELW OH PRI CLR ESTR USA FMOB TER2 PRTO FSRP | Pole | 2021-02-01 | 2021-01-29 | COMP | 2021-01-29 | [16 empty] | 2019-04-13 | 2020-04-13 | 2020-09-05 | 2020-09-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 17399.74 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117024629 | POLE_BROK_REPL - 29795 KINGS CANYON S.YO | 35209431 |  |  | STS-POLE_BROK_REPL - 29795 KINGS CANYON | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.1818 | -119.7762 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B | 10329 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101106576 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117025915 | POLE_DECA_REPL - 29508 GLACIERYOSEMITE L | 35209435 |  |  | STS-POLE_DECA_REPL - 29508 GLACIERYOSEMI | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1763 | -119.7675 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B | 10267 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.5 | 41.5 |  |  | 0 | 41.5 | 41.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106683 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-10 |  | COMP | 2021-02-10 | [16 empty] | 2019-04-14 | 2020-04-14 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 21248.17 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117026034 | POLE_BROK_REPL - 42436 JOHN MUIR YOSEMIT | 35209440 |  |  | STS-POLE_BROK_REPL - 42436 JOHN MUIR YOS | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1791 | -119.7776 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 09201B | 10614 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 68.1 | 67.4 | 0.7 |  | 0 | 68.1 | 67.4 | 0.7 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101106517 | RELW OH PRI CLR JPOL RESD REMT FIRE ESTR TRAF FLAG BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-16 |  | COMP | 2021-02-16 | [16 empty] | 2019-04-14 | 2020-04-14 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 29291.9 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117026226 | POLE_DECA_REPL - 29511 YOSEMITE LK. PWKY | 35209447 |  |  | STS-POLE_DECA_REPL - 29511 YOSEMITE LK. | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1783 | -119.763 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B | 24802 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106616 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-14 | 2020-04-14 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117027146 | POLE_DECA_REPL - 29632 YOSEMITE SPGS. PW | 35209450 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 37.179 | -119.7659 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106606 | RELW OH PRI FLAG ESTR GO BTKA USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-14 | 2020-04-14 | 2020-10-05 | 2020-10-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117027398 | POLE_DECA_REPL - 29682 YOSEMITE LK. PWKY | 35209456 |  |  | STS-POLE_DECA_REPL - 29682 YOSEMITE LK. | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.1792 | -119.7666 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 09201B | 24802 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106603 | RELW OH PRI CLR ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-14 | 2020-04-14 | 2020-10-05 | 2020-10-05 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117226562 | POLE_DECA_REPL - 43794 RD415 YOSEMITE LA | 35214869 |  |  | STS-POLE_DECA_REPL - 43794 RD415 YOSEMIT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.23 | -119.7497 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204A | 5675 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19 | 18.2 | 0.8 |  | 0 | 19 | 18.2 | 0.8 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101050720 | RELW OH PRI ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2021-02-16 | 2021-02-16 | COMP | 2021-02-16 | [16 empty] | 2019-05-13 | 2020-05-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 6461.63 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117240512 | POLE_DECA_REPL - WATER GULCH RD/RD416 NW | 35215025 |  |  | STS-POLE_DECA_REPL - WATER GULCH RD/RD41 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.2283 | -119.7382 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101050274 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117325540 | POLE_BROK_REPL - 41714 LILLEY MT DRYOSEM | 35215744 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.199 | -119.7871 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08206A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101060242 | RELW OH PRI FIRE FLAG ESTR BTKA USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2021-01-22 | 2021-01-22 | [12 empty] | 2019-05-27 | 2020-05-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Yosemite Lakes | Oakhurst |  |  | OPEN | 117687230 | POLE _BROK _REPL_BEAR PAW WAY/BEAR PAW C | 35209328 |  |  | STS-POLE _BROK _REPL_BEAR PAW WAY/BEAR P | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1999 | -119.7592 |  | TIER 2 |  |  | 08205B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 52.5 | 52.5 |  |  | 0 | 52.5 | 52.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101058733 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2020-12-14 |  | COMP | 2020-12-14 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 25049.99 | 94.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Yosemite Lakes | Oakhurst |  |  | OPEN | 117688326 | POLE _BROK _REPL_42893 LONG HOLLOW PVTP | 35209399 |  |  | STS-POLE _BROK _REPL_42893 LONG HOLLOW P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 37.174 | -119.7703 |  | TIER 2 |  |  | 09201B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101106725 | PRI RELW OH ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2020-11-04 | 2020-11-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | COMP | 116952258 | POLE_DECA_REPL - 30501 YOSRMITE SPGS PWY | 35086058 |  |  | STS-POLE_DECA_REPL - 30501 YOSRMITE SPGS | DOCC | DOCC ERDY SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-14 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.1921 | -119.7691 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08205C | 24802 | Y | 311 |  |  | 2021-02-16 07:00 | 2021-02-16 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 43 | 41.8 | 1.2 |  | 9 | 42 | 40.8 | 1.2 |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101059508 | RELW OH COMP RESD PRI CLR JPOL REMT FIRE TRAF FLAG ESTR BTKA USA CCNT FMOB TER2 PRTO FSRP | Pole | 2020-06-17 | 2020-06-30 | COMP | 2020-06-17 | COMP | 2021-02-16 | 2020-06-30 | 2020-06-30 | [11 empty] | 2021-02-18 | 2021-02-16 | 2019-10-03 | 2020-08-11 | 2020-08-11 | Work Plan Reconcilation (B-Tags) |  | Fresno |  | 254432103 | 32873.66 | 13112.8 | -20297.1 | 222.6 | 222.6 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-07-21
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116847227 | POLE_DECA_REPL - STARLIGHT/STARLIGHT WY | 35209217 |  |  | STS-POLE_DECA_REPL - STARLIGHT/STARLIGHT | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2019 | -119.7795 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.2 | 12.2 |  |  | 0 | 12.2 | 12.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101058638 | OH RELW SEC RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-29 | 2021-01-29 | COMP | 2021-01-29 | [16 empty] | 2019-03-27 | 2020-03-27 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 4029.37 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116854695 | POLE_DECA_REPL - 42485 RANGER CIR WAY 2P | 35209277 |  |  | STS-POLE_DECA_REPL - 42485 RANGER CIR WA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2031 | -119.7715 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.2 | 34.2 |  |  | 0 | 34.2 | 34.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101058688 | RELW OH SERV ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-03 | 2021-02-03 | COMP | 2021-02-03 | [16 empty] | 2019-03-28 | 2020-03-28 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 10746.38 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116861669 | POLE_BROK_REPL - 42848 RANGER CIR DR 1PS | 35209372 |  |  | STS-POLE_BROK_REPL - 42848 RANGER CIR DR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.201 | -119.763 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.1 | 11.7 | 2.4 |  | 0 | 14.1 | 11.7 | 2.4 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101058709 | RELW SERV OH ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 | 2021-01-28 | COMP | 2021-01-28 | [16 empty] | 2019-03-29 | 2020-03-29 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 5112.12 | 13.5 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116861950 | POLE_BROK_REPL - 42848 RANGER CIR DR 1PS | 35209377 |  |  | STS-POLE_BROK_REPL - 42848 RANGER CIR DR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2013 | -119.7631 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.7 | 13.3 | 2.4 |  | 0 | 15.7 | 13.3 | 2.4 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101058710 | RELW OH SERV ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 | 2021-01-28 | COMP | 2021-01-28 | [16 empty] | 2019-03-29 | 2020-03-29 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 254432104 | 5059.31 | 13.5 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117017822 | POLE_BROK_REPL - 1PW 29777 TIOGA YOSEMIT | 35209302 |  |  | STS-POLE_BROK_REPL - 1PW 29777 TIOGA YOS | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1809 | -119.742 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 09201A | 6165 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 54.2 | 52.8 | 1.4 |  | 0 | 54.2 | 52.8 | 1.4 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101107988 | RELW OH PRI CLR JPOL REMT BTKA FIRE ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-09 | 2021-02-09 | COMP | 2021-02-09 | [16 empty] | 2019-04-12 | 2020-04-12 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 20772.39 | 503.3 | 489.9 | 182.9 | 182.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117023729 | POLE_DECA_REPL - 1PE 29525 JIM BOWIE YOS | 35209397 |  |  | STS-POLE_DECA_REPL - 1PE 29525 JIM BOWIE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1758 | -119.7709 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 09201B | 10614 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.9 | 38.9 |  |  | 0 | 38.9 | 38.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106498 | PRI OH RELW CLR JPOL RESD REMT FIRE ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-29 | 2021-01-29 | COMP | 2021-01-29 | [16 empty] | 2019-04-13 | 2020-04-13 | 2020-09-01 | 2020-09-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 16370.09 | 131.6 | 118.2 | 118.2 | 118.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117232006 | POLE_BROK_REPL - 33030 RD400YOSEMITE LAK | 35214942 |  |  | STS-POLE_BROK_REPL - 33030 RD400YOSEMITE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2286 | -119.7636 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08204B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 12.8 | 12.8 |  |  | 0 | 12.8 | 12.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101050844 | OH SERV JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP RELW | Pole | 2021-01-27 | 2021-01-27 | COMP | 2021-01-27 | [16 empty] | 2019-05-14 | 2019-10-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 5532.52 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Yosemite Lakes | Oakhurst |  |  | OPEN | 117687215 | POLE _BROK _REPL_RANGER CIR DR/MOCCASSIN | 35209312 |  |  | STS-POLE _BROK _REPL_RANGER CIR DR/MOCCA | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2017 | -119.7622 |  | TIER 2 |  |  | 08205B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 11 | 11 |  |  | 0 | 11 | 11 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101058714 | RELW PRI OH ESTR TER2 PRTO FSRP | Pole | 2020-12-10 | 2020-12-10 | COMP | 2020-12-10 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 3910.13 | 13.5 | -1737.6 | -1013.6 | -1013.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117687231 | POLE _BROK _REPL_BEAR PAW WAY/BEAR PAW C | 35209333 |  |  | STS-POLE _BROK _REPL_BEAR PAW WAY/BEAR P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1998 | -119.7595 |  | TIER 2 |  |  | 08205B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 11.1 | 11.1 |  |  | 0 | 11.1 | 11.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101058734 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2020-12-22 | 2020-12-22 | COMP | 2020-12-22 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 4929.24 | 983.5 | 970.1 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116827692 | POLE_BROK_REPL - 31606 ROAD 416YOSEMITE | 35214806 |  |  | STS-POLE_BROK_REPL - 31606 ROAD 416YOSEM | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2079 | -119.7294 |  | TIER 2 | 489 | 25443-2103, COARSEGOLD | 08205A | 5508 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.5 | 32.5 |  |  | 0 | 32.5 | 32.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103152845 | RELW ESTR OH PRI CLR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-01-20 | COMP | 2021-01-20 | [16 empty] | 2019-03-25 | 2020-03-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432103 | 14164.67 | 13.5 | 0 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116862822 | POLE_BURN_REPL - 43152 RANGER CIR DR 2PN | 35083632 |  |  | STS-POLE_BURN_REPL - 43152 RANGER CIR DR | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2048 | -119.7594 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B | 5509 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Burnt | Replace |  | 101058742 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-08-19 | 2020-10-28 | COMP | 2020-08-19 | [16 empty] | 2019-03-29 | 2020-03-29 | 2020-09-08 | 2020-09-08 | 2021 CBP Plan | 2020-09-30 | QUES |  | 254432104 | 19018.72 | 1326.2 | 1155.3 | 1155.3 | 1155.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116863032 | POLE_DECA_REPL - RANGER CIR DR/BEAR PAWY | 35177386 |  |  | BC3 STS-POLE_DECA_REPL - RANGER CIR DR/B | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-12-08 | No Action | 37.2023 | -119.7599 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205B | 5509 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 53.6 | 53.6 |  |  | 0 | 53.6 | 53.6 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101058718 | RELW OH PRI CLR FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-06-09 | 2020-06-30 | COMP | 2020-06-09 |  |  | 2020-12-23 | 2020-12-23 | [12 empty] | 2019-03-29 | 2020-03-29 | 2020-08-08 | 2020-08-08 | Work Plan Reconcilation (B-Tags) |  | W. Sac |  | 254432104 | 23529.75 | 2242.3 | 1155.3 | 1155.3 | 1155.3 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-07-21
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 116948397 | POLE_BROK_REPL - C/O CORRAL DR/YOSEMITE | 35214614 |  |  | STS-POLE_BROK_REPL - C/O CORRAL DR/YOSEM | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1988 | -119.7725 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08205C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.6 | 23.6 |  |  | 0 | 23.6 | 23.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101058856 | RELW OH SEC CLR RESD REMT BTKA FIRE ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-11 | 2021-01-11 | COMP | 2021-01-11 | [16 empty] | 2019-04-03 | 2020-04-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254432104 | 7015.05 | 13.5 | 0 | 407.5 | 407.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117018340 | POLE_DECA_REPL - 2PSW 29766 TIOGAYOSEMIT | 35178860 |  |  | STS-POLE_DECA_REPL - 2PSW 29766 TIOGAYOS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1794 | -119.7439 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 09201A |  | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101107983 | RELW OH PRI CLR JPOL REMT FIRE ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-06-04 | 2020-06-04 | COMP | 2020-06-04 | [16 empty] | 2019-04-12 | 2020-04-12 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan |  | Fresno |  | 254432104 | 15204.63 | 85.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117021586 | POLE_BROK_REPL - 1PS 41882 HORSESHOE BEN | 35209361 |  |  | STS-POLE_BROK_REPL - 1PS 41882 HORSESHOE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1831 | -119.7829 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 09201B | 6292 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 55.8 | 55.8 |  |  | 0 | 55.8 | 55.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101106563 | RELW OH PRI CLR JPOL RESD FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-05 | 2021-01-05 | COMP | 2021-01-05 | [16 empty] | 2019-04-13 | 2020-04-13 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 21730.27 | 13.5 | 0 | 489 | 489 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117025552 | POLE_DECA_REPL - 1PS 29452 KIT CARSONYOS | 35105443 |  |  | STS-POLE_DECA_REPL - 1PS 29452 KIT CARSO | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1761 | -119.776 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 09201B |  | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101106513 | RELW OH PRI CLR RESD REMT FIRE ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-11-25 | 2020-11-25 | COMP | 2020-11-25 | [16 empty] | 2019-04-14 | 2019-10-14 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254432104 | 7152.69 | 904.7 | 452.2 | 869.6 | 869.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117363326 | POLE_DECA_REPL - 30283 HORSESHOE DRYOSEM | 35154558 |  |  | STS-POLE_DECA_REPL - 30283 HORSESHOE DRY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-04-06 | Change Schedule/Request Extension | 37.1893 | -119.7831 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08206D | 6292 | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101059942 | RELW OH PRI CLR RESD FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-05-13 | 2020-05-13 | COMP | 2020-05-13 |  |  | 2020-04-03 | 2020-04-16 | [12 empty] | 2019-05-30 | 2020-05-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | PIKEENG |  | 254432104 | 26243.87 | 1287.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE LAKES | Oakhurst |  |  | OPEN | 117378364 | POLE_BROK_REPL - A/F 31430 BIG RIVER WAY | 35154611 |  |  | STS-POLE_BROK_REPL - A/F 31430 BIG RIVER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-04-20 | Change Schedule/Request Extension | 37.2053 | -119.7898 |  | TIER 2 | 442 | 25443-2104, COARSEGOLD | 08206A | 5512 | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101060323 | RELW OH PRI CLR RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-05-28 | 2020-05-28 | COMP | 2020-05-28 |  |  | 2020-04-16 | 2020-04-22 | [12 empty] | 2019-06-03 | 2020-06-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | PIKEENG |  | 254432104 | 17521.83 | 820.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Yosemite Lakes | Oakhurst |  |  | OPEN | 117687217 | POLE _BROK _REPL_RANGER CIR DR/BEAR PAW | 35209317 |  |  | STS-POLE _BROK _REPL_RANGER CIR DR/BEAR | PEND | PEND CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 37.2025 | -119.7601 |  | TIER 2 |  |  | 08205B |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 52.5 | 52.5 |  |  | 0 | 52.5 | 52.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101058723 | OH PRI ESTR TER2 PRTO FSRP RELW | Pole | 2021-01-08 | 2021-01-08 | COMP | 2020-12-08 |  |  | 2020-12-10 | 2020-12-15 | [12 empty] | 2019-07-31 | 2020-07-31 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 11430.28 | 860.5 | -1218.1 | -494.1 | -494.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Yosemite Lakes | Oakhurst |  |  | OPEN | 117687219 | POLE_DECA_REPL - BEAR PAW WAY/BEAR PAW C | 35209323 |  |  | STS-POLE_DECA_REPL - BEAR PAW WAY/BEAR P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2021 | -119.7587 |  | TIER 2 |  |  | 08205B |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 34.5 | 34.5 |  |  | 0 | 34.5 | 34.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101058728 | RELW OH PRI ESTR PROG TER2 PRTO FSRP | Pole | 2021-01-05 | 2021-01-05 | COMP | 2021-01-05 |  |  | 2020-12-16 | 2020-12-16 | [12 empty] | 2019-07-31 | 2020-07-31 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 15091.98 | 131.6 | 118.2 | 118.2 | 118.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | Yosemite Lakes | Oakhurst |  |  | OPEN | 117687324 | POLE _BROK _REPL_3O311 YOSRMITE SPGS PWY | 35209338 |  |  | STS-POLE _BROK _REPL_3O311 YOSRMITE SPGS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1892 | -119.7673 |  | TIER 2 |  |  | 08205C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.3 | 36.3 |  |  | 0 | 36.3 | 36.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101059580 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-01-06 | 2021-01-06 | COMP | 2021-01-06 |  |  | 2020-12-14 | 2020-12-14 | [12 empty] | 2019-07-31 | 2020-07-31 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-02-28 | CALENG |  |  | 16022.07 | 13.5 | 0 | 525 | 525 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE NATIONAL PARK | Oakhurst |  |  | OPEN | 117114095 | TREE_DECA_INPL - AF 8038 RACOON RDYOSEMI | 35187885 |  |  | STS-TREE_DECA_INPL - AF 8038 RACOON RDYO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.5478 | -119.6406 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000421352 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 7.7 | 7.7 |  |  | 0 | 7.7 | 7.7 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 101016660 | RELW OH SERV JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-23 |  | COMP | 2020-09-23 | [16 empty] | 2019-04-28 | 2020-04-28 |  | 2020-04-28 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 5098.86 | 3293.4 | 2634.6 | 1383 | 1383 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE NATIONAL PARK | Oakhurst |  |  | OPEN | 117114609 | TREE_DECA_INPL - 2PE1PN OF 2052 SPELT RD | 35187909 |  |  | STS-TREE_DECA_INPL - 2PE1PN OF 2052 SPEL | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.5496 | -119.648 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000421352 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 10 | 10 |  |  | 0 | 10 | 10 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103371359 | RELW OH PRI CLR NOAC ESTR USA FMOB TER2 PRTO | Pole | 2020-09-02 |  | COMP | 2020-09-02 |  |  | 2020-09-02 | 2020-09-02 | [12 empty] | 2019-04-28 | 2020-04-28 |  | 2020-04-28 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 18565.34 | 2912.9 | 2681.3 | 1429.7 | 1429.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE NATIONAL PARK | Oakhurst |  |  | OPEN | 117115719 | TREE_DECA_INPL - YOSEMITE NATIONAL PARKY | 35188007 |  |  | STS-TREE_DECA_INPL - YOSEMITE NATIONAL P | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.5481 | -119.6484 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000421352 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.7 | 12.7 |  |  | 0 | 12.7 | 12.7 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103218446 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-13 |  | COMP | 2020-10-13 | [16 empty] | 2019-04-28 | 2020-04-28 | 2020-08-31 | 2020-08-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 7836.82 | 1933.9 | 1240.2 | 140.2 | 140.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE NATIONAL PARK | Oakhurst |  |  | OPEN | 117118200 | POLE_DECA_REPL - 2650 ENGLISH LN.YOSEMIT | 35188063 |  |  | STS-POLE_DECA_REPL - 2650 ENGLISH LN.YOS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Enviro |  |  | 37.5511 | -119.6419 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000421352 | 5727 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 74.8 | 74.8 | 0 |  | 0 | 74.8 | 74.8 | 0 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016646 | RELW OH PRI FLAG ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-10-01 |  | COMP | 2020-10-01 | [16 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 28338.26 | 1674.5 | 1287 | 187 | 187 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE NATIONAL PARK | Oakhurst |  |  | OPEN | 117125759 | POLE_DECA_REPL - 1PS OF 7771 CHILNUALNA | 35188316 |  |  | STS-POLE_DECA_REPL - 1PS OF 7771 CHILNUA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.5398 | -119.6582 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000004215 | 5554 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.6 | 16.6 |  |  | 0 | 16.6 | 16.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016321 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-01 |  | COMP | 2020-10-01 | [16 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-11-15 | QUES |  | 254421103 | 9781.9 | 553.1 | 157.6 | 140.2 | 140.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE NATIONAL PARK | Oakhurst |  |  | OPEN | 117126556 | TREE_DECA_INPL - YOSEMITE NATIONAL PARKY | 35188336 |  |  | STS-TREE_DECA_INPL - YOSEMITE NATIONAL P | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.5427 | -119.6513 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000004215 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.5 | 27.5 |  |  | 0 | 27.5 | 27.5 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103206866 | OH PRI FLAG ESTR BTKA USA FMOB TER2 PRTO RELW | Pole | 2020-10-15 |  | COMP | 2020-10-15 |  |  | 2021-01-29 | 2021-02-01 | [12 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | QUES |  | 254421103 | 28754.81 | 2051.9 | 1838.5 | 1803.7 | 1803.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE NATIONAL PARK | Oakhurst |  |  | OPEN | 117130312 | TREE_DECA_INPL - 3 TREES SOUTH OF 8051 C | 35188410 |  |  | STS-TREE_DECA_INPL - 3 TREES SOUTH OF 80 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5475 | -119.6389 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000421351 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.6 | 24.6 |  |  | 0 | 24.6 | 24.6 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 101016655 | RELW OH SERV CLR FLAG ESTR GO REAR PROG FMOB TER2 PRTO | Pole | 2020-10-14 | 2021-02-01 | COMP | 2020-10-14 |  |  | 2021-01-29 | 2021-02-01 | [12 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-11-15 | QUES |  | 254421103 | 10818.9 | 191.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE NATIONAL PARK | Oakhurst |  |  | COMP | 117126956 | TREE_DECA_INPL - YOSEMITE NATIONAL PARKY | 35174955 |  |  | BC7 STS-TREE_DECA_INPL - YOSEMITE NATION | FICL | FICL SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-06-23 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.5421 | -119.6517 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000004215 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 0.8 | 0.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | B | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103206858 | PRI RELW OH COMP NOAC ESTR USA CPGE CPGD FMOB TER2 PRTO | Pole | 2020-05-15 | 2020-12-30 | COMP | 2020-05-15 | COMP | 2021-01-09 | 2020-05-13 | 2020-05-13 | [11 empty] | 2021-01-13 | 2021-01-09 | 2020-04-30 | 2020-07-21 | 2020-07-21 | B-Tag Clean Up 5/14/20 |  | Fresno |  | 254421103 | 17115.51 | 14160.7 | 8529.6 | 20670.1 | 20670.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-05-25
Bay/Central | YO | YOSEMITE NATIONAL PARK | Oakhurst |  |  | OPEN | 117113771 | POLE_DECA_REPL - 1PE OF 2697 SPELT RDYOS | 35187856 |  |  | STS-POLE_DECA_REPL - 1PE OF 2697 SPELT R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5515 | -119.6483 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000421352 | 10635 | Y | 311 |  |  | 2021-07-02 07:00 | 2021-07-02 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016537 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-10 | 2020-11-13 | COMP | 2020-09-10 | [16 empty] | 2019-04-28 | 2020-04-28 |  | 2020-04-28 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 17873.63 | 2744.8 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE NATIONAL PARK | Oakhurst |  |  | OPEN | 117115652 | POLE_DECA_REPL - 2PE OF 2052 SPELT RD. Y | 35188001 |  |  | STS-POLE_DECA_REPL - 2PE OF 2052 SPELT R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.5491 | -119.6473 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000421352 | 10635 | Y | 311 |  |  | 2021-06-29 07:00 | 2021-06-29 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101016543 | OH PRI CLR NOAC ESTR PROG FMOB TER2 PRTO RELW | Pole | 2020-09-15 | 2020-09-15 | COMP | 2020-09-15 | [16 empty] | 2019-04-28 | 2020-04-28 |  | 2020-04-28 | 2021 CBP Plan | 2020-10-31 | QUES |  | 254421103 | 15542.7 | 1600.2 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
Bay/Central | YO | YOSEMITE NATIONAL PARK | Oakhurst |  |  | OPEN | 117125637 | POLE_DECA_REPL - #1 NE/O 7993 S FORREST | 35097370 |  |  | STS-POLE_DECA_REPL - #1 NE/O 7993 S FORR | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-10-12 | No Action | 37.5444 | -119.6406 |  | TIER 2 | 22 | 25442-1103, OAKHURST | 0000421353 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 50.9 | 50.9 |  |  | 0 | 50.9 | 50.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102317616 | RELW OH PRI CLR RESD REMT FIRE BTKA TRAF FLAG ESTR USA FMOB TER2 PRTO | Pole | 2020-11-02 | 2020-12-17 | COMP | 2019-12-18 |  |  | 2020-05-20 | 2020-12-17 | [12 empty] | 2019-04-30 | 2019-10-27 |  | 2019-10-27 | Program Manager |  | Fresno |  | 254421103 | 8837.43 | 5119.5 | -7.9 | -7.9 | -7.9 | 1419.1 |  | 1419.1 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
North | HB |  | Clear Lake |  |  | COMP | 115597328 | REPL POLE NE/C/O PINE AVE/ DAVIS AVE | 35069524 |  |  | REPL POLE NE/C/O PINE AVE/ DAVIS AVE | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-07-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.9544 | -122.6216 |  | TIER 2 | 765 | 04336-1104, HIGHLANDS | X3009 |  | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 103.1 | 103.1 |  |  | 1 | 102.1 | 102.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102150919 | REGW OH COMP CCNT TER2 | Pole | 2019-08-07 | 2019-08-07 | COMP | 2019-04-28 | COMP | 2021-01-08 | 2019-08-06 | 2019-08-06 | [11 empty] | 2021-01-14 | 2021-01-08 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-06-30 | Santa Rosa |  | 043361104 | 24265.38 | 9931.3 | 2640.3 | 2640.3 | 2640.3 | 429.4 |  | 429.4 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB |  | Clear Lake |  |  | OPEN | 115597321 | NE/C/O EUREKA AVE / DAVIS AVE. | 35069643 |  |  | GC REPL POLE NE/C/O EUREKA AVE / DAVIS | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9544 | -122.6173 |  | TIER 2 | 765 | 04336-1104, HIGHLANDS | X3009 |  | Y | 311 |  |  | 2021-03-03 07:00 | 2021-03-03 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 78.6 | 78.6 |  |  | 3.5 | 75.1 | 75.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102150839 | REGW OH TER2 | Pole | 2019-04-25 | 2019-10-02 | COMP | 2019-04-25 |  |  | 2019-10-02 | 2019-10-02 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-06-30 | Santa Rosa |  | 043361104 | 26669.9 | 6172.4 | 1383.3 |  |  | 2663.2 |  | 2663.2 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB |  | Clear Lake |  |  | OPEN | 115597464 | GC REPL POLE 15866 23RD AVE.1P/E | 35070338 |  |  | GC REPL POLE 15866 23RD AVE.1P/E | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9394 | -122.6153 |  | TIER 2 | 765 | 04336-1104, HIGHLANDS | X3019 |  | Y | 311 |  |  |  |  | Returned | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 106.5 | 106.5 |  |  | 7.5 | 99.5 | 99.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102212692 | REGW OH TER2 | Pole | 2019-04-25 | 2019-10-02 | COMP | 2019-04-25 |  |  | 2019-10-02 | 2019-10-02 | [12 empty] | 2018-12-26 | 2019-12-31 | 2021-05-31 | 2021-05-31 | Q1 Work Plan | 2019-06-30 | Santa Rosa |  | 043361104 | 31515.17 | 41899.2 | 1850.9 |  |  | 9138.6 |  | 9138.6 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB |  | Clear Lake |  |  | OPEN | 115597468 | 1N/O 1E/O 10749 HWY 29 | 35069762 |  |  | POD 1N/O 1E/O 10749 HWY 29 | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9036 | -122.6119 |  | TIER 2 | 135 | 04336-1103, HIGHLANDS | Y30 |  | Y | 311 |  |  | 2021-04-13 07:00 | 2021-04-13 16:00 | Scheduled | CLICK | [6 empty] | 51.8 | 51.8 |  |  | 0 | 51.8 | 51.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102151371 | REGW OH TER2 | Pole | 2019-04-16 | 2019-05-01 | COMP | 2019-04-16 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-06-30 | QUES |  | 043361103 | 16402.23 | 35937.7 | 1986.9 |  |  | 34438.5 |  | 34438.5 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB |  | Eureka |  |  | OPEN | 115597305 | 1E/O C/O WALNUT DR / N. RIDGE DR | 35069292 |  |  | 1E/O C/O WALNUT DR / N. RIDGE DR | CONS | CONS CONT SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2019-12-31 | Renew Permit | 40.7503 | -124.1457 |  | TIER 2 | 96 | 19243-1108, HARRIS | Q0813 |  | Y | 311 |  |  | 2021-03-06 07:00 | 2021-03-06 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 43.5 | 43.5 |  |  | 14 | 42.5 | 42.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100997253 | REGW OH TER2 | Pole | 2019-04-28 | 2019-08-23 | COMP | 2019-04-28 |  |  | 2019-08-23 | 2019-08-23 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-06-30 | QUES |  | 192431108 | 17154.09 | 10091.2 | 4865.4 | 2602.7 | 2602.7 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB |  | Fort Bragg |  |  | OPEN | 115597143 | REPL POLE 32640 MILL CK DR | 35069842 |  |  | REPL POLE 32640 MILL CK DR*CC | CONS | CONS CONT SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 39.4874 | -123.7809 |  | TIER 2 | 430 | 04276-1101, FORT BRAGG A | K0222 |  | Y | 311 |  |  | 2021-05-25 06:26 | 2021-05-25 14:26 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 25.8 | 25.8 |  |  | 2.5 | 24.8 | 24.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102184634 | REGW OH TER2 | Pole | 2019-04-25 | 2019-06-03 | COMP | 2019-04-25 |  |  | 2019-03-26 | 2019-03-26 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-06-30 | QUES |  | 042761101 | 26590.79 | 21107.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB |  | Fort Bragg |  |  | OPEN | 115597346 | REPL POLE 32668 MILL CREEK DR | 35069199 |  |  | REPL POLE 32668 MILL CREEK DR | CONS | CONS CONT SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.4888 | -123.7785 |  | TIER 2 | 430 | 04276-1101, FORT BRAGG A | K0223 | 1379 | Y | 311 |  |  |  |  | Returned | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 25.8 | 25.8 |  |  | 1 | 24.8 | 24.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102203078 | REGW OH TER2 | Pole | 2019-04-25 | 2019-05-29 | COMP | 2019-04-25 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Per DOT Approved Request 45808 | 2019-06-30 | QUES |  | 042761101 | 21456.9 | 16138.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2021-02-06
North | HB |  | Garberville |  |  | OPEN | 115597146 | POLE_DECA_REPL - #9S\O 67402 HWY 271 | 35069403 |  |  | POLE_DECA_REPL - #9S\O 67402 HWY 271 | CONS | CONS CONT SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.8516 | -123.7182 |  | TIER 2 | 99 | 19222-1101, GARBERVILLE | KK1817 |  | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 41.8 | 41.8 |  |  | 8 | 40.8 | 40.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100987692 | REGW OH TER2 | Pole | 2019-04-25 | 2019-09-05 | COMP | 2019-04-25 |  |  | 2019-09-05 | 2019-09-05 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-02 | ENENG |  | 192221101 | 35656 | 10019.5 | 4297.8 | 4297.8 | 4297.8 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB |  | Garberville |  |  | OPEN | 115597375 | 2SW/O 83500 HWY 271 | 35069175 |  |  | 2SW/O 83500 HWY 271 | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.9962 | -123.7912 |  | TIER 2 | 99 | 19222-1101, GARBERVILLE | HH16 |  | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-28 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100992344 | REGW OH TER2 | Pole | 2019-04-09 | 2019-07-24 | COMP | 2019-04-09 |  |  | 2019-07-26 | 2019-07-26 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-02 | ENENG |  | 192221101 | 17607.92 | 3226.8 |  |  |  | 83.4 |  | 83.4 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB |  | Garberville |  |  | OPEN | 115597412 | #3W\O#1N\O 65750 HWY 271 | 35070362 |  |  | #3W\O#1N\O 65750 HWY 271 | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.8496 | -123.7092 |  | TIER 2 | 99 | 19222-1101, GARBERVILLE | KK1818 |  | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-28 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100987765 | REGW OH TER2 | Pole | 2019-06-04 | 2019-10-08 | COMP | 2019-06-04 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-02 | ENENG |  | 192221101 | 25809.33 | 1916.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB |  | Garberville |  |  | OPEN | 118593191 | POLE_DECA_REPL - | 35179978 |  |  | STS-POLE_DECA_REPL - | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.2279 | -124.1101 |  | TIER 2 |  |  | CC08 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.2 | 17.2 |  |  | 0 | 17.2 | 17.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100986338 | RELW TER2 | Pole | 2020-12-09 | 2021-02-02 | COMP | 2020-12-09 | [16 empty] | 2020-02-28 | 2020-12-31 | 2021-05-31 | 2021-05-31 | Email from [REDACTED] 3.3.20 | 2020-09-30 | QUES |  |  | 8845.54 | 3505 | 3245.1 | 2002.8 | 2002.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-03-09
North | HB |  | Lakeport |  |  | COMP | 115597376 | REPL POLE 2E/O 8040 HWY 29 MB | 35069977 |  |  | REPL POLE 2E/O 8040 HWY 29 MB | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.9292 | -122.7379 |  | TIER 2 | 32 | 04331-1102, KONOCTI | X27 |  | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 2 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102162195 | REGW OH COMP CCNT TER2 | Pole | 2019-12-04 | 2020-06-26 | COMP | 2019-04-25 | COMP | 2021-01-13 | 2019-09-05 | 2019-09-05 | [11 empty] | 2021-01-20 | 2021-01-13 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-06-30 | QUES |  | 043311102 | 12782.21 | 3636.4 | 1572.6 | 680.2 | 680.2 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | ALDERPOINT | Garberville |  |  | OPEN | 117068850 | POLE_BROK_REPL - 3N/O 1057 CASTERLIN RDA | 35215353 |  |  | STS-POLE_BROK_REPL - 3N/O 1057 CASTERLIN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.2348 | -123.6047 |  | TIER 2 | 393 | 19232-1122, FORT SEWARD | CC21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100995249 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192321122 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | ALDERPOINT | Garberville |  |  | OPEN | 117070187 | POLE_BROK_REPL - 1SE/O 19N/O 1409 CASTER | 35215407 |  |  | STS-POLE_BROK_REPL - 1SE/O 19N/O 1409 CA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.2436 | -123.5842 |  | TIER 2 | 393 | 19232-1122, FORT SEWARD | BB21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100995289 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192321122 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | ALDERPOINT | Garberville |  |  | OPEN | 117072289 | POLE_BROK_REPL - 9267 FORT SEWARD RDALDE | 35215466 |  |  | STS-POLE_BROK_REPL - 9267 FORT SEWARD RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.2381 | -123.6254 |  | TIER 2 | 393 | 19232-1122, FORT SEWARD | CC20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100995390 | RELW OH PRI JPOL TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2021-01-20 | 2021-01-20 | [12 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192321122 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | ALDERPOINT | Garberville |  |  | OPEN | 117072315 | POLE_BROK_REPL - 1N/O 4W/O 9397 FORT SEW | 35215471 |  |  | STS-POLE_BROK_REPL - 1N/O 4W/O 9397 FORT | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.2368 | -123.6201 |  | TIER 2 | 393 | 19232-1122, FORT SEWARD | CC20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100995357 | RELW OH PRI ESTR FSRP PRTO FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192321122 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | ALDERPOINT | Garberville |  |  | OPEN | 117068184 | POLE_BROK_REPL - 1S/O 1N/O 22660 ALDERPO | 35202386 |  |  | STS-POLE_BROK_REPL - 1S/O 1N/O 22660 ALD | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.2219 | -123.6035 |  | TIER 2 | 393 | 19232-1122, FORT SEWARD | CC21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.7 | 24.7 |  |  | 0 | 24.7 | 24.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100995117 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-21 |  | COMP | 2021-01-21 | [16 empty] | 2019-04-18 | 2020-04-18 | 2020-10-11 | 2020-10-11 | 2021 CBP Plan | 2021-02-28 | QUES |  | 192321122 | 8703.34 | 176.7 | 0 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | ALDERPOINT | Garberville |  |  | OPEN | 117068191 | POLE_DECA_REPL - 2SW/O 4S/O 4E/O 1409 CA | 35202391 |  |  | STS-POLE_DECA_REPL - 2SW/O 4S/O 4E/O 140 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.2238 | -123.5959 |  | TIER 2 | 393 | 19232-1122, FORT SEWARD | CC21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.7 | 32.7 |  |  | 0 | 32.7 | 32.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100995152 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-22 | 2021-01-22 | COMP | 2021-01-22 | [16 empty] | 2019-04-19 | 2020-04-19 | 2020-10-11 | 2020-10-11 | 2021 CBP Plan | 2021-02-28 | QUES |  | 192321122 | 25791.89 | 206.5 | 85.4 | 85.4 | 85.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | ALDERPOINT | Garberville |  |  | OPEN | 117190607 | POLE_BROK_REPL - #8S\O 870 ALDERPOINT RD | 35202555 |  |  | STS-POLE_BROK_REPL - #8S\O 870 ALDERPOIN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.1522 | -123.624 |  | TIER 2 | 253 | 19232-1121, FORT SEWARD | DD20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 22.7 | 22.7 |  |  | 0 | 22.7 | 22.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100995867 | RELW OH PRI CLR RESD REMT ESTR GO REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-10 | 2020-12-10 | COMP | 2020-12-10 | [16 empty] | 2019-05-09 | 2020-05-09 | 2020-09-26 | 2020-09-26 | 2021 CBP Plan | 2021-01-31 | QUES |  | 192321121 | 9329.16 | 1242.3 | 1242.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | ANNAPOLIS | Point Arena |  |  | OPEN | 117178692 | POLE_DECA_REPL - 25100 SODA SPRINGS RDAN | 35202523 |  |  | STS-POLE_DECA_REPL - 25100 SODA SPRINGS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land JointPole |  |  | 38.7318 | -123.3423 |  | TIER 2 | 252 | 04286-1101, ANNAPOLIS | BB12 | 65889 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102180495 | RELW OH PRI INSP FIRE ESTR USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2020-05-07 | 2020-10-11 | 2020-10-11 | 2021 CBP Plan | 2021-02-28 | QUES |  | 042861101 | 1 | 151.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | BLOCKSBURG | Garberville |  |  | OPEN | 117072371 | POLE_BROK_REPL - 4W/O 786 CASTERLIN RDBL | 35215486 |  |  | STS-POLE_BROK_REPL - 4W/O 786 CASTERLIN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.239 | -123.6326 |  | TIER 2 | 393 | 19232-1122, FORT SEWARD | CC20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100995404 | RELW OH PRI REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192321122 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | BLOCKSBURG | Garberville |  |  | OPEN | 117072382 | POLE_BROK_REPL - 3N/O 4W/O 1N/O 9397 FOR | 35215491 |  |  | STS-POLE_BROK_REPL - 3N/O 4W/O 1N/O 9397 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.2397 | -123.6341 |  | TIER 2 | 393 | 19232-1122, FORT SEWARD | CC20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100995406 | RELW OH PRI REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192321122 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | BLOCKSBURG | Garberville |  |  | OPEN | 117075934 | POLE_BROK_REPL - 1N/O 26175 ALDERPOINT R | 35215552 |  |  | STS-POLE_BROK_REPL - 1N/O 26175 ALDERPOI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.2592 | -123.6299 |  | TIER 2 | 393 | 19232-1122, FORT SEWARD | BB20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100995418 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-22 | 2020-04-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192321122 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | BLOCKSBURG | Garberville |  |  | OPEN | 117088102 | POLE_DECA_REPL - 1SW/O 89 CHURCH ST BLOC | 35215867 |  |  | STS-POLE_DECA_REPL - 1SW/O 89 CHURCH ST | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.275 | -123.6348 |  | TIER 2 | 393 | 19232-1122, FORT SEWARD | BB20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100995443 | RELW OH PRI MINR JAR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-22 | 2020-04-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192321122 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | BLOCKSBURG | Garberville |  |  | OPEN | 117094222 | POLE_BROK_REPL - 4NW/O 28019 CEMENTARY R | 35214684 |  |  | STS-POLE_BROK_REPL - 4NW/O 28019 CEMENTA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.2774 | -123.6402 |  | TIER 2 | 393 | 19232-1122, FORT SEWARD | BB20 | 8113 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100995460 | RELW OH PRI JPOL REMT TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2021-02-09 | 2021-02-09 | [12 empty] | 2019-04-24 | 2020-04-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192321122 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | BOONVILLE | Ukiah |  |  | OPEN | 116878679 | POLE_BROK_REPL - 16100 HWY 128 BOONVILLE | 35202585 |  |  | STS-POLE_BROK_REPL - 16100 HWY 128 BOONV | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.9845 | -123.3509 |  | TIER 2 | 184 | 04260-1101, PHILO | W12 | 3700 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102203467 | RELW OH SEC RESD FLAG REMT TRAF ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2020-12-03 | 2020-12-03 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042601101 | 1 | 584.6 | 113.1 | 113.1 | 113.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | BOONVILLE | Ukiah |  |  | OPEN | 116976353 | POLE_DECA_REPL - #3 S/O #2 W/O 20500 TUM | 35214759 |  |  | STS-POLE_DECA_REPL - #3 S/O #2 W/O 20500 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.0506 | -123.4409 |  | TIER 2 | 184 | 04260-1101, PHILO | V10 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102213725 | RELW OH PRI REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-07 | 2020-04-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042601101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | BOONVILLE | Ukiah |  |  | OPEN | 116879583 | POLE_BROK_REPL - A/F HWY 253 ON HWY 128 | 35215602 |  |  | STS-POLE_BROK_REPL - A/F HWY 253 ON HWY | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land JointPole |  |  | 38.9992 | -123.3586 |  | TIER 2 | 184 | 04260-1101, PHILO | W1207 | 2435 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 63.6 | 63.6 |  |  | 0 | 63.6 | 63.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102214077 | RELW OH PRI JPOL RESD REMT TRAF FLAG ESTR BTKA FSRP PRTO FMOB TER2 | Pole | 2021-01-27 |  | COMP | 2021-01-27 |  |  | 2020-12-29 | 2020-12-29 | [12 empty] | 2019-04-01 | 2020-04-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042601101 | 29637.05 | 105.2 | 64.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | BURNT RANCH | Willow Creek |  |  | OPEN | 118593551 | POLE_BROK_REPL - | 35179274 |  |  | STS-POLE_BROK_REPL_121 HORSESHOE LANE, B | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Permit |  |  | 40.8149 | -123.4965 |  | TIER 2 |  |  | P24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.7 | 36.7 |  |  | 0 | 36.7 | 36.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100974214 | RELW TER2 | Pole | 2020-09-02 |  | COMP | 2020-09-02 | [16 empty] | 2020-02-28 | 2020-12-31 |  | 2020-12-31 | Email from[REDATED] 3.3.20 | 2020-09-30 | QUES |  |  | 19262.7 | 1970.2 | 1216.8 | [5 empty] | Electric Distribution | N | MPP File Only | N |  | Y | 2020-03-09
North | HB | CAZADERO | Point Arena |  |  | OPEN | 117103508 | POLE_BROK_REPL - 45200 SODA SPRINGS RD C | 35202209 |  |  | STS-POLE_BROK_REPL - 45200 SODA SPRINGS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.7646 | -123.3652 |  | TIER 2 | 252 | 04286-1101, ANNAPOLIS | BB12 | 4599 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102185352 | RELW OH PRI INSP CLR FIRE ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 | 2020-10-11 | 2020-10-11 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042861101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | CAZADERO | Point Arena |  |  | OPEN | 117105272 | POLE_BROK_REPL - #7 N/O 24700 SODA SPRIN | 35202212 |  |  | STS-POLE_BROK_REPL - #7 N/O 24700 SODA S | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.7561 | -123.3534 |  | TIER 2 | 252 | 04286-1101, ANNAPOLIS | BB12 | 4599 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102185343 | RELW OH PRI INSP FIRE ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-26 | 2020-04-26 | 2020-10-11 | 2020-10-11 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042861101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | CAZADERO | Point Arena |  |  | COMP | 117938168 | REPL POLE:ROUTE C12 G61 #24E/O,Cazadero | 35181745 |  |  | OCGC7/21B REPLPOLE HWY12 G61#24E/OCAZ*BD | MAPP | MAPP SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-06-23 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7353 | -123.2922 |  | TIER 2 | 252 | 04286-1101, ANNAPOLIS | BB14 |  | Y | 311 |  |  | 2021-02-09 06:00 | 2021-02-09 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 77.3 | 76.1 | 1.2 |  | 171 | 2 | 0.8 | 1.2 |  | EC | B | Pole | Decayed/Rotten | Replace |  | 102201559 | RELW OH TNT COMP CPGG TER2 FSRP | Pole | 2020-09-16 | 2020-10-21 | COMP | 2020-09-15 | COMP | 2021-02-09 | [13 empty] | 2021-02-10 | 2021-02-09 | 2020-06-11 | 2020-07-21 | 2020-07-21 | B-Tag Addition 06.24.20 |  | Santa Rosa |  | 042861101 | 12017.32 | 23635.3 | 8162.2 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Access/Customer Issue | Y | 2020-06-29
North | HB | CLEARLAKE | Clear Lake |  |  | OPEN | 116986228 | POLE_DECA_REPL - 11173 PIONEER CLEARLAKE | 35150157 |  |  | STS-POLE_DECA_REPL - 11173 PIONEER | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.9961 | -122.7037 |  | TIER 2 | 179 | 04319-1102, REDBUD | W2809 | 2339 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24 | 24 |  |  | 0 | 24 | 24 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102202058 | RELW OH PRI JPOL RESD REMT ESTR GO BTKA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-09 | 2020-04-09 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 31430 | 2020-12-31 | QUES |  | 043191102 | [9 empty] | Y | MPP File Only | N |  | Y | 2021-01-28
North | HB | CLEARLAKE | Lakeport |  |  | OPEN | 115597227 | REPL POLE 3067 WILLOW RD | 35069217 |  |  | POD REPL POLE 3067 WILLOW RD | CONS | CONS CONT SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0064 | -122.7864 |  | TIER 2 | 300 | 04214-1101, CLEAR LAKE | W2603 |  | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 91 | 91 |  |  | 0 | 91 | 91 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102160001 | REGW OH TER2 | Pole | 2019-05-18 | 2019-10-02 | COMP | 2019-05-18 |  |  | 2019-10-02 | 2019-10-02 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-06-30 | Santa Rosa |  | 042141101 | 17757.03 | 6016 | 802.1 |  |  | 1531.5 |  | 1531.5 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | CLEARLAKE OAKS | Clear Lake |  |  | OPEN | 116873974 | POLE_BURN_REPL - 1NW/O 13200 HWY 20CLEAR | 35209626 |  |  | STS-POLE_BURN_REPL - 1NW/O 13200 HWY 20C | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land Enviro JointPole |  |  | 39.0269 | -122.663 |  | TIER 2 | 111 | 04319-1101, REDBUD | V2919 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.3 | 28.3 |  |  | 0 | 28.3 | 28.3 |  |  | EC | E | Pole | Burnt | Replace |  | 102154194 | OH PRI JPOL PUBL FIRE TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP RELW | Pole | 2021-02-22 |  | COMP | 2021-02-22 | [16 empty] | 2019-03-30 | 2019-10-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043191101 | 16416.85 | 43.5 | 43.5 | 43.5 | 43.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | CLEARLAKE OAKS | Clear Lake |  |  | COMP | 118995498 | POLE_DECA_REPL - 6N/O 15698 HWY 20 Clear | 35181968 |  |  | 8/7 B REPL POLE 6N/O 15698 HWY 20 C | DOCC | DOCC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-10 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.0344 | -122.6279 |  | TIER 2 | 179 | 04319-1102, REDBUD | V30 |  | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 46.3 | 42.7 | 3.6 |  | 2 | 45.3 | 41.7 | 3.6 |  | EC | B | Pole | Decayed/Rotten | Replace |  | 102155368 | PRI OH RELW INSP COMP CLR REMT FIRE BTKA USA CCNT FMOB TER2 | Pole | 2020-07-15 | 2020-07-15 | COMP | 2020-07-15 | COMP | 2021-01-13 | [13 empty] | 2021-01-21 | 2021-01-13 | 2020-08-07 |  | 2020-08-07 | B-Tag Addition 06.24.20 |  | Santa Rosa |  | 043191102 | 13806.5 | 6356.6 | 3587.1 | 3587.1 | 3587.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Access/Customer Issue - ACCESS ISSUES LOCKED GATE NO CONTACT INFO | Y | 2020-06-29
North | HB | DEL LOMA | Willow Creek |  |  | OPEN | 109272226 | POLE_LEAN_REPL - 808 BIG MTN RD 1S/O 1W/ | 35120878 |  |  | STS-POLE_LEAN_REPL - 808 BIG MTN RD 1S/O | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 40.7896 | -123.3477 |  | TIER 2 | 126 | 19217-1103, WILLOW CREEK | P27 | 3079 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.5 | 44.5 |  |  | 10.5 | 34 | 34 |  |  | EC | E | Pole | Leaning | Replace |  | 100975295 | RELW OH PRI INSP REMT NOAC GO PTPF SCOP SCPA TER2 | Pole | 2020-09-10 |  | COMP | 2020-09-10 | [16 empty] | 2014-09-17 | 2019-09-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 192171103 | 37797.19 | 7717.2 | 1216.8 | [5 empty] | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | EUREKA | Eureka |  |  | OPEN | 116740627 | POLE_BROK_REPL - C/O 2463 FRESHWATER KNE | 35082050 |  |  | STS-POLE_BROK_REPL - C/O 2463 FRESHWATER | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.7605 | -124.057 |  | TIER 2 | 287 | 19243-1109, HARRIS | Q1009 |  | Y | 311 |  |  | 2021-03-26 07:03 | 2021-03-26 15:00 | Dispatched | CLICK | [6 empty] | 24.2 | 24.2 |  |  | 0.25 | 23.95 | 23.95 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100984169 | RELW OH SEC ESTR FMOB TER2 PRTO | Pole | 2019-04-16 | 2019-05-03 | COMP | 2019-04-16 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-03-15 | 2020-03-15 | 2021-05-31 | 2021-05-31 | Q1 Work Plan |  | UNASSIGNED |  | 192431109 | 8948.32 | 3328.7 | 740 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | EUREKA | Eureka |  |  | OPEN | 116664865 | POLE_DECA_REPL - 192 GRANGE RDEUREKA9550 | 35089932 |  |  | STS-POLE_DECA_REPL - 192 GRANGE RDEUREKA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-12-31 |  | 40.7587 | -124.0631 |  | TIER 2 | 287 | 19243-1109, HARRIS | Q1008 | 6265 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 47.2 | 47.2 |  |  | 0 | 47.2 | 47.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100984256 | RELW OH FLAG PRI JPOL RESD ESTR PROG FMOB TER2 PRTO FSRP | Pole | 2020-04-01 | 2021-02-02 | COMP | 2020-04-01 |  |  | 2021-02-05 | 2021-02-05 | [12 empty] | 2019-03-06 | 2020-03-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-31 | PIKEENG |  | 192431109 | 18540.87 | 1045.9 | 1045.9 | 1045.9 | 1045.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | EUREKA | Eureka |  |  | OPEN | 116673758 | POLE_DECA_REPL - 1SE/O 100 LANGLOIS LN E | 35089953 |  |  | STS-POLE_DECA_REPL - 1SE/O 100 LANGLOIS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.7579 | -124.0529 |  | TIER 2 | 287 | 19243-1109, HARRIS | Q1009 | 5577 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.4 | 42.2 | 0.2 |  | 0 | 42.4 | 42.2 | 0.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100984236 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-02-25 | 2020-04-14 | COMP | 2020-02-24 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-03-06 | 2020-03-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-04-17 | PIKEENG |  | 192431109 | 20284.82 | 1478.7 | 1437 | 1437 | 1437 | 41.7 |  | 41.7 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | EUREKA | Eureka |  |  | OPEN | 116681298 | POLE_DECA_REPL - 7852 ELK RIVER RD EUREK | 35214591 |  |  | STS-POLE_DECA_REPL - 7852 ELK RIVER RD E | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 40.7037 | -124.15 |  | TIER 2 | 307 | 19234-1102, HUMBOLDT BAY | R0812 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.3 | 16.3 |  |  | 0 | 16.3 | 16.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101002894 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-27 |  | COMP | 2021-01-27 | [16 empty] | 2019-03-07 | 2020-03-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192341102 | 11479.4 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | FERNDALE | Fortuna |  |  | OPEN | 116685654 | POLE_DECA_REPL - 10S/O 720 CENTERVILLE R | 35214624 |  |  | STS-POLE_DECA_REPL - 10S/O 720 CENTERVIL | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 40.5662 | -124.336 |  | TIER 2 | 637 | 19238-1103, EEL RIVER | U03 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100999254 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-08 | 2020-03-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192381103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | FERNDALE | Garberville |  |  | OPEN | 117116346 | POLE_BROK_REPL - 1506 NORTH FORK RDFERND | 35214908 |  |  | STS-POLE_BROK_REPL - 1506 NORTH FORK RDF | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.3554 | -124.2914 |  | TIER 2 | 49 | 19222-1102, GARBERVILLE | Z04 | 176634 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100987454 | RELW REMT OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-28 | 2020-04-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192221102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | FERNDALE | Garberville |  |  | OPEN | 117116347 | POLE_BROK_REPL - 2S/O 1506 NORTH FORK RD | 35202284 |  |  | STS-POLE_BROK_REPL - 2S/O 1506 NORTH FOR | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.3534 | -124.293 |  | TIER 2 | 49 | 19222-1102, GARBERVILLE | Z04 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100987452 | RELW PRI OH ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-28 | 2020-04-28 | 2020-09-08 | 2020-09-08 | 2021 CBP Plan | 2021-01-31 | QUES |  | 192221102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | FERNDALE | Garberville |  |  | OPEN | 113035729 | POLE_BROK_REPL - 27145 MATTOLE RD FERNDA | 35149544 |  |  | STS-POLE_DECA_REPL - IRO 27145 MATTOLE R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.3394 | -124.313 |  | TIER 2 | 49 | 19222-1102, GARBERVILLE | Z04 | 2501 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.8 | 37.8 |  |  | 0 | 37.8 | 37.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100987470 | RELW OH PRI INSP RESD REMT ESTR GO TER2 FSRP | Pole | 2020-06-15 | 2020-06-15 | COMP | 2020-06-15 | [16 empty] | 2017-06-08 | 2020-05-23 | 2020-10-18 | 2020-10-18 | 2021 CBP Plan | 2020-12-31 | TRC |  | 192221102 | 22026.89 | 1843.1 | 1296 | 1296 | 1296 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | FORT BRAGG | Fort Bragg |  |  | OPEN | 117073482 | POLE_DECA_REPL - 27200 HWY 1 FORT BRAGG | 35209646 |  |  | STS-POLE_DECA_REPL - 27200 HWY 1 FORT BR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 39.5249 | -123.7608 |  | TIER 2 | 430 | 04276-1101, FORT BRAGG A | K02 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102185048 | PRI RELW OH CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 042761101 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | FORT BRAGG | Fort Bragg |  |  | OPEN | 117300441 | POLE_BROK_REPL - #2W/O #10 S/O 30901 GUT | 35209547 |  |  | STS-POLE_BROK_REPL - #2W/O #10 S/O 30901 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.491 | -123.7328 |  | TIER 2 | 430 | 04276-1101, FORT BRAGG A | L03 | 3227 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102185638 | RELW OH PRI JPOL REMT CGI ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-22 | 2020-05-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 042761101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | FORT BRAGG | Fort Bragg |  |  | OPEN | 117302114 | POLE_DECA_REPL - R/O 32551 CLEONE HEIGHT | 35209590 |  |  | STS-POLE_DECA_REPL - R/O 32551 CLEONE HE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.4856 | -123.7804 |  | TIER 2 | 430 | 04276-1101, FORT BRAGG A | K0222 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.3 | 34.3 |  |  | 0 | 34.3 | 34.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102184641 | OH RELW SEC RESD REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2019-05-22 | 2020-05-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 042761101 | 16492.21 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | FORT BRAGG | Fort Bragg |  |  | OPEN | 117304180 | POLE_BROK_REPL - #25 S/O 30901 GUTHRIE R | 35209604 |  |  | STS-POLE_BROK_REPL - #25 S/O 30901 GUTHR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Enviro JointPole |  |  | 39.4784 | -123.7315 |  | TIER 2 | 430 | 04276-1101, FORT BRAGG A | L03 | 3227 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.8 | 14.8 |  |  | 0 | 14.8 | 14.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102185655 | RELW OH PRI REMT CGI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-12 |  | COMP | 2021-02-12 | [16 empty] | 2019-05-22 | 2020-05-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 042761101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | FORT BRAGG | Fort Bragg |  |  | OPEN | 117310699 | POLE_BROK_REPL - 24300 RAMSEY RIDGE RDFO | 35209659 |  |  | STS-POLE_BROK_REPL - 24300 RAMSEY RIDGE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 39.4723 | -123.7198 |  | TIER 2 | 430 | 04276-1101, FORT BRAGG A | L03 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102185668 | OH RELW PRI JPOL REMT CGI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-23 | 2020-05-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 042761101 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | FORT BRAGG | Fort Bragg |  |  | OPEN | 117072520 | POLE_DECA_REPL - 6N/O 28301 N HWY 1 FORT | 35155018 |  |  | STS-POLE_DECA_REPL-6N/O 28301N HWY 1F*BD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5415 | -123.7566 |  | TIER 2 | 430 | 04276-1101, FORT BRAGG A | K02 | 3127 | Y | 311 |  |  |  |  | Returned | Order Operation | [6 empty] | 30.8 | 30 | 0.8 |  | 0 | 30.8 | 30 | 0.8 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102185118 | RELW PRI OH INSP CLR JPOL PUBL FLAG ESTR GO BTKA PROG FMOB TER2 | Pole | 2020-09-17 | 2020-11-29 | COMP | 2020-09-17 |  |  | 2020-09-24 | 2020-09-24 | [12 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | Per DOT Approved Request 8419 | 2020-12-31 | QUES |  | 042761101 | 21998.44 | 5769.6 | 1219.8 | 3 | 3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-09-13
North | HB | FORT BRAGG | Fort Bragg |  |  | OPEN | 117233806 | POLE_DECA_REPL - 22000 PETALUMA AVFORT B | 35202818 |  |  | STS-POLE_DECA_REPL - 22000 PETALUMA AVFO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.4566 | -123.7905 |  | TIER 2 | 238 | 04276-1104, FORT BRAGG A | M0104 | 3119 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 55 | 55 | 0 |  | 0 | 55 | 55 | 0 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102190094 | RELW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-28 |  | COMP | 2020-12-28 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-09-07 | 2020-09-07 | 2021 CBP Plan | 2021-02-28 | QUES |  | 042761104 | 26071.18 |  | 0 | 1784.4 | 1784.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | FORTUNA | Fortuna |  |  | OPEN | 116679602 | POLE_DECA_REPL - 1W/O 1900 SUNNY HTS RD | 35214579 |  |  | STS-POLE_DECA_REPL - 1W/O 1900 SUNNY HTS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 40.608 | -124.1422 |  | TIER 2 | 636 | 19215-1132, NEWBURG | T0813 | 4051 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100993672 | RELW OH PRI JPOL ESTR RTRN FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-07 | 2020-03-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192151132 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | FORTUNA | Fortuna |  |  | OPEN | 116680122 | POLE_DECA_REPL - 3S/O 1N/O 3750 NEWBURG | 35214583 |  |  | STS-POLE_DECA_REPL - 3S/O 1N/O 3750 NEWB | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 40.6003 | -124.1258 |  | TIER 2 | 636 | 19215-1132, NEWBURG | T08 | 3425 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100993347 | RELW OH PRI JPOL RESD REMT FLAG ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-07 | 2020-03-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192151132 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | GARBERVILLE | Garberville |  |  | OPEN | 116814443 | POLE_BROK_REPL - AT HOUSE 7608 OACREST D | 35215510 |  |  | STS-POLE_BROK_REPL - AT HOUSE 7608 OACRE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.0749 | -123.7868 |  | TIER 2 | 99 | 19222-1101, GARBERVILLE | FF1619 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100988260 | RELW OH SEC RESD FIRE ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192221101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | GARBERVILLE | Garberville |  |  | OPEN | 116814972 | POLE_LEAN_REPL - 1N\O 1W\O 754O BENBOW D | 35215551 |  |  | STS-POLE_LEAN_REPL - 1N\O 1W\O 754O BENB | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 40.075 | -123.788 |  | TIER 2 | 99 | 19222-1101, GARBERVILLE | FF1619 | 80367 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Leaning | Replace |  | 100988262 | RELW OH PRI CLR RESD FIRE ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192221101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | GARBERVILLE | Garberville |  |  | OPEN | 116822423 | POLE_BROK_REPL - 1NE\O 1SE\O AT HOUSE 52 | 35214687 |  |  | STS-POLE_BROK_REPL - 1NE\O 1SE\O AT HOUS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 40.0965 | -123.7911 |  | TIER 2 | 99 | 19222-1101, GARBERVILLE | FF1603 | 5473 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100989007 | RELW RESD OH SEC CLR REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192221101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | GARBERVILLE | Garberville |  |  | OPEN | 117154117 | POLE_BROK_REPL - 8W/O KINSEY HOUSE RANCH | 35215166 |  |  | STS-POLE_BROK_REPL - 8W/O KINSEY HOUSE R | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.0645 | -123.744 |  | TIER 2 | 99 | 19222-1101, GARBERVILLE | FF17 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100988539 | RELW OH PRI CLR RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192221101 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | GARBERVILLE | Garberville |  |  | OPEN | 117154331 | POLE_BROK_REPL - 11W/O KINSEY RANCH HOUS | 35202469 |  |  | STS-POLE_BROK_REPL - 11W/O KINSEY RANCH | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.0642 | -123.7478 |  | TIER 2 | 99 | 19222-1101, GARBERVILLE | FF17 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100988536 | RELW OH PRI CLR RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2020-09-12 | 2020-09-12 | 2021 CBP Plan | 2021-01-31 | QUES |  | 192221101 | 1 | 380.5 | 121.3 | 121.3 | 121.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | GARBERVILLE | Garberville |  |  | OPEN | 117157000 | POLE_BROK_REPL - 6E/O 3450 E.BRANCH RDGA | 35215189 |  |  | STS-POLE_BROK_REPL - 6E/O 3450 E.BRANCH | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.0633 | -123.7491 |  | TIER 2 | 99 | 19222-1101, GARBERVILLE | FF17 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100988535 | RELW OH PRI CLR REMT ESTR GO REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192221101 | 1 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | GARBERVILLE | Garberville |  |  | OPEN | 114761639 | POLE_BROK_REPL - 2SW/O 8E/O 3S/O HOU | 35048036 |  |  | REPL POLE 2SW/8E/3S 2500 HWY 101 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | Poles | 2.4 |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.0325 | -123.7875 |  | TIER 2 | 99 | 19222-1101, GARBERVILLE | GG16 | 1565 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-03 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100994752 | RELW OH PRI CREW REMT FIRE NOAC SWRK ESTR GO USA XMPT XDOC TER2 | Pole | 2020-09-30 | 2020-09-30 | COMP | 2018-09-18 |  |  | 2020-06-30 | 2020-06-30 | [12 empty] | 2018-06-28 | 2019-06-28 | 2019-08-27 | 2019-08-27 | Q1 Work Plan |  | Chico |  | 192221101 | 5377.35 | 10483.3 | [7 empty] | Y | Crticial Work MPP Owned and pulled from MPP Import File | N | Internal Timeliness - Consturction | Y | 2020-02-18
North | HB | GARBERVILLE | Garberville |  |  | OPEN | 117240241 | POLE_BROK_REPL - #12N\O#12W\O 160 PEAK R | 35202838 |  |  | STS-POLE_BROK_REPL - #12N\O#12W\O 160 PE | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 40.1968 | -123.5901 |  | TIER 2 | 253 | 19232-1121, FORT SEWARD | DD21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100994815 | RELW OH PRI CLR REMT SPCR ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-11 | 2020-12-10 | COMP | 2020-12-10 | [16 empty] | 2019-05-15 | 2020-05-15 | 2020-10-11 | 2020-10-11 | 2021 CBP Plan | 2021-02-28 | QUES |  | 192321121 | 33634.6 | 1700.8 | 1352 | 109.7 | 109.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | GARBERVILLE | Garberville |  |  | OPEN | 119803229 | POLE_BROK_REPL - 26NE/O 1N/O 542 STANLEY | 35212548 |  |  | STS-POLE_BROK_REPL - 26NE/O 1N/O 542 STA | CONS | CONS SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | S9 Prior to 11/2 Static File | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.0469 | -123.8916 |  | TIER 2 | 99 | 19222-1101, GARBERVILLE | GG14 |  | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100994784 | RELW OH PRI INSP REMT NOAC ESTR FMOB TER2 USA | Pole | 2020-12-17 | 2020-12-17 | COMP | 2020-12-17 | [16 empty] | 2020-09-23 | 2020-12-23 |  | 2020-12-23 | B tag clean up 11/15/2020 |  | Chico |  | 192221101 | 21805.11 | 261 | 261 | 261 | 261 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-11-15
North | HB | HIDDEN VALLEY LAKE | Clear Lake |  |  | OPEN | 117302641 | POLE_BROK_REPL - #30E #12SE HOUSE @ 2133 | 35209799 |  |  | STS-POLE_BROK_REPL - #30E #12SE HOUSE @ | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.7752 | -122.474 |  | TIER 2 | 386 | 04314-1103, MIDDLETOWN | BB34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.7 | 20.7 |  |  | 0 | 20.7 | 20.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103319650 | RELW OH PRI REMT FIRE JAR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-16 | 2021-02-12 | COMP | 2021-02-12 | [16 empty] | 2019-05-22 | 2020-05-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043141103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | HIDDEN VALLEY LAKE | Clear Lake |  |  | OPEN | 117696822 | POLE_BROK_REPL - R/O 24382 GRANGE RD W/T | 35154821 |  |  | STS-POLE_BROK_REPL - R/O 24382 GRANGE RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.7739 | -122.4885 |  | TIER 2 | 386 | 04314-1103, MIDDLETOWN | BB33 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102204912 | RELW OH PRI INSP REMT FIRE SWRK ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD |  |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-08-01 | 2020-01-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 043141103 | 1 | 333.6 |  |  |  | 333.6 |  | 333.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | HIDDEN VALLEY LAKE | Clear Lake |  |  | OPEN | 117010434 | POLE_LEAN_REPL - 17053 KNOLLVIEW DR HIDD | 35202186 |  |  | STS-POLE_LEAN_REPL - 17053 KNOLLVIEW DR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.8133 | -122.571 |  | TIER 2 | 221 | 04314-1102, MIDDLETOWN | AA32D | 1312 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.1 | 39.1 |  |  | 0 | 39.1 | 39.1 |  |  | EC | E | Pole | Leaning | Replace |  | 102208531 | RELW OH PRI JPOL RESD FLAG FMOB TER2 PRTO FSRP | Pole | 2020-12-07 |  | COMP | 2020-12-07 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-09-12 | 2020-09-12 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043141102 | 25063.76 | 1454.7 | 699.3 | -271.5 | -271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | Hidden Valley Lake | Clear Lake |  |  | OPEN | 120450896 | POLE_DECA_REPL - 18364 LAKE RIDGE CIR.Hi | 35227590 |  |  |  | PEND | PEND ERDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  |  | 1 | 2021-03-23 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.8086 | -122.5675 |  | TIER 2 | 221 | 04314-1102, MIDDLETOWN | AA32D | 514 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 2 | 0 | 70.7 | 70.1 | 0.6 |  | 0 | 70.7 | 70.1 | 0.6 |  | EC | B | Pole | Decayed/Rotten | Replace |  | 102208627 | RELW OH PRI CREW CLR JPOL RESD ESTR FIRE TRAF FLAG GO BTKA USA PROG FMOB TER2 | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2021-01-20 | 2021-04-20 |  | 2021-04-20 | B tag clean up 1/21/2021 |  | Santa Rosa |  | 043141102 | [9 empty] | N | MPP File Only | N |  | Y | 2021-01-21
North | HB | HONEYDEW | Garberville |  |  | OPEN | 119362488 | POLE_DECA_REPL - 5SW/O 20N/O 3950 WILDER | 35220970 |  |  | STS-POLE_DECA_REPL - 5SW/O 20N/O 3950 WI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.2146 | -124.1133 |  | TIER 2 | 49 | 19222-1102, GARBERVILLE | CC08 | 2553 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 49.4 | 49.4 |  |  | 0 | 49.4 | 49.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100986332 | OH RELW PRI INSP ESTR FMOB TER2 | Pole | 2021-02-01 | 2021-02-11 | COMP | 2021-01-31 | [16 empty] | 2020-07-13 | 2021-07-13 |  | 2021-07-13 | Work Plan Reconcilation (B-Tags) |  | Chico |  | 192221102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-07-21
North | HB | HOOPA | Willow Creek |  |  | OPEN | 116871728 | POLE_DECA_REPL - 3W/O 10N/O LCO3153 COMM | 35215448 |  |  | STS-POLE_DECA_REPL - 3W/O 10N/O LCO3153 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 41.0657 | -123.6793 |  | TIER 2 | 65 | 19240-1101, HOOPA | J1915 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101011398 | RELW OH PRI JPOL REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192401101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | HOOPA | Willow Creek |  |  | OPEN | 116872124 | POLE_DECA_REPL - GP AT 5E/O LCO 4681 COM | 35215453 |  |  | STS-POLE_DECA_REPL - GP AT 5E/O LCO 4681 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 41.068 | -123.6768 |  | TIER 2 | 65 | 19240-1101, HOOPA | J1915 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101011415 | RELW OH PRI PGEA RESD ESTR REAR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2021-03-21 | 2021-03-21 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192401101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | HOOPA | Willow Creek |  |  | OPEN | 116872493 | POLE_DECA_REPL - 1S/O LCO 4681 COMM.SERV | 35215472 |  |  | STS-POLE_DECA_REPL - 1S/O LCO 4681 COMM. | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 41.0689 | -123.6806 |  | TIER 2 | 65 | 19240-1101, HOOPA | J1915 | 4681 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101011423 | RELW PRI OH JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192401101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | HOOPA | Willow Creek |  |  | OPEN | 116872770 | POLE_DECA_REPL - 1W/O LCO 4681 COMM.SERV | 35215477 |  |  | STS-POLE_DECA_REPL - 1W/O LCO 4681 COMM. | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 41.0695 | -123.6816 |  | TIER 2 | 65 | 19240-1101, HOOPA | J1915 | 3323 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101011425 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192401101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | HOOPA | Willow Creek |  |  | OPEN | 116875217 | POLE_DECA_REPL - 1S/O 24W/O C/O#6793 ON | 35150370 |  |  | 11/11 B REPL POLE 1S/O 24W/O C/O#6793 ON | UNSC | UNSC | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 41.1974 | -123.743 |  | TIER 2 | 65 | 19240-1101, HOOPA | G18 | 37202 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-08 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 48 | 48 |  |  | 8 | 40 | 40 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101011842 | RELW OH PRI ESTR PROG FMOB TER2 PRTO | Pole | 2020-07-07 | 2021-02-22 | COMP | 2020-07-07 | [16 empty] | 2019-03-30 | 2020-03-30 | 2020-11-11 | 2020-11-11 | B tag clean up 8/29/2020 | 2020-12-31 | TRC |  | 192401101 | 18691.73 | 13844.5 | 221.8 | 187 | 187 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-08-29
North | HB | HOOPA | Willow Creek |  |  | OPEN | 116872378 | POLE_BROK_REPL - 3E/O LCO 3153 COMM.SERV | 35225608 |  |  | STS-POLE_BROK_REPL - 3E/O LCO 3153 COMM. | ADER | ADER | Poles | MPP | Not Funded as 2020 Wildfire OII | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 41.0695 | -123.6778 |  | TIER 2 | 65 | 19240-1101, HOOPA | J1915 | 3323 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101011418 | RELW OH PRI JPOL RESD BTKA FMOB TER2 PRTO FSRP SCOP SCPA | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2021-05-31 | 2021-05-31 | work plan year cleanup 01/21/2021 | 2021-03-01 | Chico |  | 192401101 | [9 empty] | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-21
North | HB | HOOPA | Willow Creek |  |  | OPEN | 114686690 | POLE_BROK_REPL - 2616 hwy 169Hoopa | 35048939 |  |  | POD T2 REPL POLE 2616 HWY 169HOOPA | PEND | PEND ERDY CONT | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 41.198 | -123.7442 |  | TIER 2 | 65 | 19240-1101, HOOPA | G18 | 37202 | Y | 311 |  |  |  |  | Returned | Order Operation | [6 empty] | 26 | 26 |  |  | 0 | 26 | 26 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103315267 | REGW OH PRI INSP CLR FLAG ESTR BTKA USA XMPT XDOC FMOB TER2 | Pole | 2018-11-07 |  | COMP | 2018-11-07 |  |  | 2018-10-08 | 2018-10-08 | [12 empty] | 2018-06-09 | 2019-06-09 | 2019-08-09 | 2019-08-09 | 2021 CBP Plan |  | Chico |  | 192401101 | 15477.08 | 6816.2 | 2608.8 | 2608.8 | 2608.8 | 619.7 |  | 619.7 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | HOOPA | Willow Creek |  |  | OPEN | 116828720 | POLE_BROK_REPL - S/P 1W/O 6S/O POLE NO 8 | 35202488 |  |  | STS-POLE_BROK_REPL - S/P 1W/O 6S/O POLE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 41.0939 | -123.6942 |  | TIER 2 | 65 | 19240-1101, HOOPA | I1923 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 12.4 | 12.4 |  |  | 0 | 12.4 | 12.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100969231 | RELW OH SERV ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-25 |  | COMP | 2021-01-25 | [16 empty] | 2019-03-25 | 2020-03-25 | 2020-10-03 | 2020-10-03 | 2021 CBP Plan | 2021-01-31 | QUES |  | 192401101 | 6624.16 | 1836.6 | 1383 | 1383 | 1383 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | HOPLAND | Ukiah |  |  | OPEN | 116948246 | POLE_DECA_REPL - #3EO 14550 EAST SIDE RD | 35214605 |  |  | STS-POLE_DECA_REPL - #3EO 14550 EAST SID | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.9591 | -123.1003 |  | TIER 2 | 33 | 04225-1101, HOPLAND | X18 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102212015 | RELW OH PRI INSP REMT ESTR GO USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-03 | 2020-04-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042251101 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | HOPLAND | Ukiah |  |  | OPEN | 117303171 | POLE_DECA_REPL - #1N #1W 11700 HEWLETT R | 35215616 |  |  | STS-POLE_DECA_REPL - #1N #1W 11700 HEWLE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 38.9925 | -123.1271 |  | TIER 2 | 33 | 04225-1101, HOPLAND | W18 | 635 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102194907 | RELW OH PRI CLR JPOL RESD COMM FIRE NOAC ESTR BTKA REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-22 | 2020-05-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042251101 | 1 | 227.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | HOPLAND | Ukiah |  |  | OPEN | 108877066 | POLE_BROK_REPL - 1800 OLD TOLL RD HOPLAN | 35145868 |  |  | GC-POLE_BROK_REPL - 1800 OLD TOLL RD HO | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9768 | -123.0669 |  | TIER 2 | 33 | 04225-1101, HOPLAND | W1923 | 1231 | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | [6 empty] | 51 | 51 |  |  | 2.5 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102214493 | RELW OH PRI INSP MINR GO BTKA TER2 SCOP SCPA | Pole | 2020-06-04 | 2020-07-16 | COMP | 2020-06-04 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2014-08-04 | 2019-08-04 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-06-08 | CALENG |  | 042251101 | 21613.06 | 3468.5 | 1529.4 | 1529.4 | 1529.4 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | HYDESVILLE | Fortuna |  |  | OPEN | 117254707 | POLE_DECA_REPL - #1W\O 6551 ROHNERVILLE | 35224484 |  |  | STS-POLE_DECA_REPL - #1W\O 6551 ROHNERVI | PEND | PEND | Poles | MPP | Not Funded as 2020 Wildfire OII | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.5513 | -124.1061 |  | TIER 2 | 100 | 19229-1121, CARLOTTA | U0922 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19 | 19 |  |  | 0 | 19 | 19 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100994109 | OH PRI INSP REAR SCOP SCPA FMOB TER2 FSRP RELW | Pole | 2021-01-27 |  | COMP | 2021-01-27 |  |  | 2021-02-02 | 2021-02-02 | [12 empty] | 2019-05-17 | 2021-06-23 | 2021-05-31 | 2021-05-31 | work plan year cleanup 01/21/2021 |  | Chico |  | 192291121 | 6633.17 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-21
North | HB | KELSEYVILLE | Clear Lake |  |  | OPEN | 116724428 | POLE_DECA_REPL - 8922 FAIRWAY DR KELSEYV | 35208763 |  |  | STS-POLE_DECA_REPL - 8922 FAIRWAY DR KEL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.963 | -122.7423 |  | TIER 2 | 649 | 04331-1108, KONOCTI | X2704 | 7419 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.3 | 39.3 |  |  | 0 | 39.3 | 39.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102162511 | RELW OH PRI JPOL RESD FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-22 |  | COMP | 2021-02-22 | [16 empty] | 2019-03-13 | 2020-03-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043311108 | 16714.62 | 152.4 | 152.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | KELSEYVILLE | Clear Lake |  |  | OPEN | 116752184 | POLE_DECA_REPL - ENT 9921 SODA BAY RD/4P | 35208773 |  |  | STS-POLE_DECA_REPL - ENT 9921 SODA BAY R | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land Enviro |  |  | 38.9451 | -122.7346 |  | TIER 2 | 649 | 04331-1108, KONOCTI | X2715 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.4 | 15.4 |  |  | 0 | 15.4 | 15.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102162164 | RELW OH PRI JPOL REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-08 |  | COMP | 2021-02-08 | [16 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043311108 | 8934.05 | 43.5 | 43.5 | 43.5 | 43.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | KELSEYVILLE | Clear Lake |  |  | OPEN | 116757236 | POLE_DECA_REPL - 2N/O 9011 SODA BAY RD K | 35208806 |  |  | STS-POLE_DECA_REPL - 2N/O 9011 SODA BAY | UNSC | UNSC ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 38.9698 | -122.7406 |  | TIER 2 | 649 | 04331-1108, KONOCTI | W2724 | 1278 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.4 | 38.4 |  |  | 0 | 38.4 | 38.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102156589 | RELW OH PRI JPOL RESD ESTR GO BTKA REAR FMOB TER2 PRTO FSRP | Pole | 2021-02-19 | 2021-02-19 | COMP | 2021-02-19 | [16 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043311108 | 18357.87 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | KELSEYVILLE | Clear Lake |  |  | OPEN | 116764540 | POLE_DECA_REPL - 8946/SODA/BAY/RD/1N/O1E | 35208827 |  |  | STS-POLE_DECA_REPL - 8946/SODA/BAY/RD/1N | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 38.9736 | -122.7427 |  | TIER 2 | 649 | 04331-1108, KONOCTI | W2724 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102156549 | RELW OH SEC JPOL RESD REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043311108 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | KELSEYVILLE | Clear Lake |  |  | OPEN | 116767823 | POLE_DECA_REPL - 1S/O ENT 9275 /BASS/RD | 35208853 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.981 | -122.7373 |  | TIER 2 | 649 | 04331-1108, KONOCTI | W2719 | 1278 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 59.5 | 59.5 |  |  | 0 | 59.5 | 59.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102155568 | RELW OH PRI JPOL RESD REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043311108 | 35441.79 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | KELSEYVILLE | Clear Lake |  |  | OPEN | 116843659 | POLE_DECA_REPL - RO 4664 KAWEAH RD/1PNEK | 35209177 |  |  | STS-POLE_DECA_REPL - RO 4664 KAWEAH RD/1 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.9595 | -122.7213 |  | TIER 2 | 649 | 04331-1108, KONOCTI | X2801 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12 | 12 |  |  | 0 | 12 | 12 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102162401 | RELW OH ESTR PRI CLR NOAC FMOB TER2 PRTO FSRP | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043311108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | KELSEYVILLE | Clear Lake |  |  | OPEN | 116938491 | POLE_BROK_REPL - N/W C/O POINT LAKE VIEW | 35209775 |  |  | STS-POLE_BROK_REPL - N/W C/O POINT LAKE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 38.9531 | -122.6989 |  | TIER 2 | 649 | 04331-1108, KONOCTI | X2809 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102162848 | RELW PRI OH CLR JAR NOAC FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-02 | 2020-04-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043311108 | 1 | 59.7 | 59.7 | 43.5 | 43.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | KELSEYVILLE | Clear Lake |  |  | OPEN | 116759540 | POLE_DECA_REPL - AT 8988SODA/BAY/RD KELS | 35209752 |  |  | STS-POLE_DECA_REPL - AT 8988SODA/BAY/RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.9685 | -122.7434 |  | TIER 2 | 649 | 04331-1108, KONOCTI | W2724 | 1278 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 54.5 | 54.5 |  |  | 0 | 54.5 | 54.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102156584 | RELW OH PRI JPOL REMT JAR NOAC REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-29 |  | COMP | 2021-01-29 | [16 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043311108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | KELSEYVILLE | Lakeport |  |  | OPEN | 117155279 | POLE_BROK_REPL - 5490 KONOCTI RD.@HOUSE | 35209083 |  |  | STS-POLE_BROK_REPL - 5490 KONOCTI RD.@HO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 38.9786 | -122.8147 |  | TIER 2 | 32 | 04331-1102, KONOCTI | W25 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102145116 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043311102 | 1 | 43.5 | 43.5 | 43.5 | 43.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | KELSEYVILLE | Lakeport |  |  | OPEN | 117293300 | POLE_DECA_REPL - R/O 5300 SODA BAY RD 5/ | 35202942 |  |  | STS-POLE_DECA_REPL - R/O 5300 SODA BAY R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.0176 | -122.8037 |  | TIER 2 | 300 | 04214-1101, CLEAR LAKE | V26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102143833 | RELW OH SEC CLR NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-21 | 2020-05-21 | 2020-10-13 | 2020-10-13 | 2021 CBP Plan | 2021-02-28 | QUES |  | 042141101 | 1 | 129.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | KELSEYVILLE | Lakeport |  |  | COMP | 117027229 | POD REPL POLE - A/F 8780 WIGHT WAY 2PS/ | 35089426 |  |  | STS-POD REPL POLE - A/F 8720 WIGHT WAY 2 | DOCC | DOCC SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-10-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.936 | -122.8661 |  | TIER 2 | 32 | 04331-1102, KONOCTI | X24 |  | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 1 | 39.8 | 39.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102146040 | RELW OH PRI COMP JPOL REMT FLAG ESTR BTKA USA CCNT FMOB TER2 PRTO | Pole | 2020-05-08 | 2020-07-16 | COMP | 2020-05-08 | COMP | 2021-01-06 | 2020-06-04 | 2020-06-04 | [11 empty] | 2021-01-11 | 2021-01-06 | 2019-08-27 |  | 2019-08-27 | circuit based plan 2.14 | 2020-06-08 | CALENG |  | 043311102 | 11113.44 | 6743.8 | 2296 | 2296 | 2296 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | KELSEYVILLE | Lakeport |  |  | OPEN | 115089409 | POLE_BROK_REPL - 9495 KELSEY CREEK RD KE | 35069340 |  |  | POD T2 REPL POLE 9495 KELSEY CREEK R | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.925 | -122.8588 |  | TIER 2 | 32 | 04331-1102, KONOCTI | X24 | 2395 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 32.8 | 32.8 |  |  | 0 | 32.8 | 32.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102146290 | RELW OH PRI CREW JPOL REMT SPCR ESTR USA TER2 | Pole | 2019-02-12 | 2019-04-08 | COMP | 2019-02-12 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-08-30 | 2019-08-30 |  | 2019-08-30 | Q1 Work Plan |  | UNASSIGNED |  | 043311102 | 12017.71 | 11557.6 | 1448.5 | 1378.8 | 1378.8 | 0 |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | KELSEYVILLE | Lakeport |  |  | OPEN | 117052171 | POLE_BROK_REPL - A/F ENTR. 1525 WEST LAK | 35202445 |  |  | STS-POLE_BROK_REPL - A/F ENTR. 1525 WEST | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.0214 | -122.7576 |  | TIER 2 | 27 | 04335-1106, LUCERNE | V2722 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.8 | 22.8 |  |  | 0 | 22.8 | 22.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102144187 | RELW OH PRI INSP JAR FMOB TER2 FSRP | Pole | 2021-01-22 |  | COMP | 2021-01-22 | [16 empty] | 2019-04-17 | 2020-04-17 | 2020-10-09 | 2020-10-09 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043351106 | 12630.64 | 335.7 | -362 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | KELSEYVILLE | Lakeport |  |  | OPEN | 117096363 | POLE_BROK_REPL - CLEAR LAKE STATE PARK S | 35202190 |  |  | STS-POLE_BROK_REPL - CLEAR LAKE STATE PA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Enviro |  |  | 39.0134 | -122.8101 |  | TIER 2 | 300 | 04214-1101, CLEAR LAKE | V25 | 4231 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.4 | 32.8 | 0.6 |  | 0 | 33.4 | 32.8 | 0.6 |  | EC | E | Pole | Broken/Damaged | Replace |  | 102143827 | RELW OH PRI ESTR BTKA USA PROG FMOB TER2 PRTO FSRP | Pole | 2020-12-21 |  | COMP | 2020-12-21 | [16 empty] | 2019-04-25 | 2020-04-25 | 2020-10-14 | 2020-10-14 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042141101 | 22675.58 | 3834.6 | 3245 | 2229 | 2229 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | KELSEYVILLE | Lakeport |  |  | OPEN | 117183363 | POLE_DECA_REPL - 5567 MAIN ST KELSEYVILL | 35100850 |  |  | STS POLE_DECA_REPL - 5567 MAIN ST KELSEY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9737 | -122.8309 |  | TIER 2 | 32 | 04331-1102, KONOCTI | W2523 | 315171 | Y | 311 |  |  | 2021-03-25 07:00 | 2021-03-25 16:00 | Scheduled | CLICK | [6 empty] | 57.1 | 57.1 |  |  | 0 | 57.1 | 57.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102211436 | RELW OH SEC JPOL PUBL TRAF BTKA FLAG ESTR GO PROG FMOB TER2 PRTO FSRP | Pole | 2020-08-14 | 2021-01-27 | COMP | 2020-08-14 |  |  | 2021-01-27 | 2021-01-27 | [12 empty] | 2019-05-08 | 2019-09-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-09-30 | CALENG |  | 043311102 | 31924.27 | 1259.7 | 1259.7 | [5 empty] | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | LAKEPORT | Lakeport |  |  | OPEN | 117039691 | POLE_BROK_REPL - R/O 1487 SANDY LN LAKEP | 35209539 |  |  | STS-POLE_BROK_REPL - R/O 1487 SANDY LN L | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.0249 | -122.9345 |  | TIER 2 | 777 | 04214-1102, CLEAR LAKE | V22 | 2895 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102158333 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2020-12-28 | 2020-12-28 | [12 empty] | 2019-04-16 | 2020-04-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 042141102 | 1 | 303.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | LAKEPORT | Lakeport |  |  | OPEN | 117095728 | POLE_BROK_REPL - 2805 SCOTTS CREEK RD 2E | 35209687 |  |  | STS-POLE_BROK_REPL - 2805 SCOTTS CREEK R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land JointPole |  |  | 39.0439 | -122.9617 |  | TIER 2 | 258 | 04321-1101, HARTLEY | V22 | 1113 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102158021 | RELW REMT OH PRI JPOL FLAG ESTR GO BTKA USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043211101 | 1 | 176.3 | 176.3 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | LAKEPORT | Lakeport |  |  | OPEN | 117400577 | POLE_BROK_REPL - 2364 SCOTTS CREEK RD LA | 35203111 |  |  | STS-POLE_BROK_REPL - 2364 SCOTTS CREEK R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.0464 | -122.9545 |  | TIER 2 | 258 | 04321-1101, HARTLEY | V2208 | 695 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102158047 | RELW CLR OH PRI CREW REMT ESTR BTKA USA TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-03 | 2020-06-03 | 2020-10-16 | 2020-10-16 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043211101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | LAKEPORT | Lakeport |  |  | OPEN | 117620555 | POLE_BROK_REPL - MB 1150 BOGGS LN 1/WLAK | 35209223 |  |  | STS-POLE_BROK_REPL - MB 1150 BOGGS LN 1/ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 39.0572 | -122.9287 |  | TIER 2 | 258 | 04321-1101, HARTLEY | U2321 | 2369 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102147132 | OH RELW PRI INSP CLR JPOL RESD FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-19 | 2020-07-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043211101 | 1 | 92.8 | 92.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | LAKEPORT | Lakeport |  |  | OPEN | 117106051 | POLE_BROK_REPL - 3719 SCOTTS CK RD/5PN/1 | 35202222 |  |  | STS-POLE_BROK_REPL - 3719 SCOTTS CK RD/5 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0415 | -122.9802 |  | TIER 2 | 258 | 04321-1101, HARTLEY | V21 |  | Y | 311 |  |  |  |  | Started | Order Operation | [6 empty] | 37 | 37 |  |  | 0 | 37 | 37 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102157975 | OH PRI ESTR FMOB TER2 PRTO FSRP RELW | Pole | 2020-12-07 | 2020-12-07 | COMP | 2020-12-07 | [16 empty] | 2019-04-26 | 2020-04-26 | 2020-10-17 | 2020-10-17 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043211101 | 30847.39 | 2674.2 | 1475.2 | 594.9 | 594.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | LAKEPORT | Lakeport |  |  | OPEN | 117112550 | POLE_BROK_REPL - 8625 SCOTTS VALLEY RD @ | 35202246 |  |  | STS-POLE_BROK_REPL - 8625 SCOTTS VALLEY | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.1503 | -123.0004 |  | TIER 2 | 134 | 04287-1101, UPPER LAKE | S21 | 717 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 73.7 | 73.7 |  |  | 0 | 73.7 | 73.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102161215 | RELW OH PRI INSP CLR RESD GO BTKA FMOB TER2 FSRP SCOP SCPA | Pole | 2020-11-16 |  | COMP | 2020-11-16 | [16 empty] | 2019-04-27 | 2019-11-07 | 2020-10-13 | 2020-10-13 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042871101 | 44874.7 | 2345.2 | 1621.9 | 1621.9 | 1621.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | LAKEPORT | Lakeport |  |  | OPEN | 117113680 | POLE_BROK_REPL - 3719 SCOTTS CK RD/5PNLA | 35208786 |  |  | STS-POLE_BROK_REPL - 3719 SCOTTS CK RD/5 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0408 | -122.9831 |  | TIER 2 | 258 | 04321-1101, HARTLEY | V21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.6 | 25.6 |  |  | 0 | 25.6 | 25.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102157973 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-29 | 2021-02-09 | COMP | 2020-12-29 | [16 empty] | 2019-04-27 | 2020-04-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043211101 | 12181.19 | 1876.9 | 1715.5 | 2068 | 2068 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | LAKEPORT | Lakeport |  |  | OPEN | 117286808 | POLE_BROK_REPL - SE/C/O CRYSTAL LAKE WY/ | 35203171 |  |  | STS-POLE_BROK_REPL - SE/C/O CRYSTAL LAKE | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.073 | -122.929 |  | TIER 2 | 737 | 04321-1102, HARTLEY | U2316 | 1475 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.3 | 34.3 |  |  | 0 | 34.3 | 34.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103312336 | OH PRI JPOL FIRE JAR TRAF FLAG BTKA FMOB TER2 PRTO FSRP RELW | Pole | 2020-12-09 |  | COMP | 2020-12-09 | [16 empty] | 2019-05-20 | 2020-05-20 | 2020-10-17 | 2020-10-17 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043211102 | 23545.94 | 1242.3 | 717.4 | -72.4 | -72.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | Lakeport | Lakeport |  |  | OPEN | 117691135 | POLE _ BROK _ REPL_5405 SCOTTS VLY RD | 35124807 |  |  | STS-POLE _ BROK _ REPL_5405 SCOTTS VLY R | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.107 | -122.9773 |  | TIER 2 | 134 | 04287-1101, UPPER LAKE | T21 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 38.3 | 37 | 1.3 |  | 0 | 38.3 | 37 | 1.3 |  | EC | E | Pole | Broken/Damaged | Replace |  | 102206287 | RELW OH PRI ESTR TER2 PRTO | Pole | 2020-02-13 | 2020-05-07 | COMP | 2020-02-13 |  |  | 2020-05-07 | 2020-05-07 | [12 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 |  | Fresno |  | 042871101 | 8666.82 | 1372.6 | 1299 | 1310.8 | 1310.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | LAYTONVILLE | Willits |  |  | OPEN | 117046751 | POLE_BROK_REPL - 1000 BAUER RDLAYTONVILL | 35215194 |  |  | STS-POLE_BROK_REPL - 1000 BAUER RDLAYTON | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.6877 | -123.4992 |  | TIER 2 | 299 | 04268-1101, LAYTONVILLE | G0825 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102183195 | RELW OH SEC JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042681101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | LAYTONVILLE | Willits |  |  | OPEN | 117047104 | POLE_DECA_REPL - A/F 1001 BAUER RD LAYTO | 35215199 |  |  | STS-POLE_DECA_REPL - A/F 1001 BAUER RD L | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 39.6876 | -123.5 |  | TIER 2 | 299 | 04268-1101, LAYTONVILLE | G0825 | 2577 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102183192 | RELW OH PRI JPOL RESD ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042681101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | LAYTONVILLE | Willits |  |  | OPEN | 117047194 | POLE_DECA_REPL - 1001 BAUER RDLAYTONVILL | 35215205 |  |  | STS-POLE_DECA_REPL - 1001 BAUER RDLAYTON | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 39.6875 | -123.5 |  | TIER 2 | 299 | 04268-1101, LAYTONVILLE | G0825 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102183193 | RELW OH SEC JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042681101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | LAYTONVILLE | Willits |  |  | OPEN | 117049072 | POLE_DECA_REPL - 1S/O 44801 HARMON DR O/ | 35202314 |  |  | STS-POLE_DECA_REPL - 1S/O 44801 HARMON D | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro JointPole |  |  | 39.6862 | -123.4792 |  | TIER 2 | 299 | 04268-1101, LAYTONVILLE | G0923 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102195637 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2020-09-25 | 2020-09-25 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042681101 | 1 | 955.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | LAYTONVILLE | Willits |  |  | OPEN | 117072467 | POLE_DECA_REPL - ENT 46740 RD 307 LAYTON | 35092669 |  |  | STS-POLE_DECA_REPL - ENT 46740 RD 307 LA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.7105 | -123.4903 |  | TIER 2 | 299 | 04268-1101, LAYTONVILLE | G09 | 402 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102195792 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2019-06-21 | 2019-06-21 | [12 empty] | 2019-04-21 | 2019-09-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | Santa Rosa |  | 042681101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | LAYTONVILLE | Willits |  |  | OPEN | 117072523 | POLE_DECA_REPL - 12 S\O 1E\O HOUSE 651 W | 35215500 |  |  | STS-POLE_DECA_REPL - 12 S\O 1E\O HOUSE 6 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 39.7131 | -123.4893 |  | TIER 2 | 299 | 04268-1101, LAYTONVILLE | G09 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102195801 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042681101 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | LAYTONVILLE | Willits |  |  | OPEN | 117096796 | POLE_BROK_REPL - 1660 BRANSCOMB RD LAYTO | 35214701 |  |  | STS-CRSS_BROK_REPA - 1660 BRANSCOMB RD L | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.6733 | -123.5016 |  | TIER 2 | 216 | 04268-1102, LAYTONVILLE | H0810 | 7083 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102194752 | RELW OH PRI JPOL RESD ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042681102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | LAYTONVILLE | Willits |  |  | OPEN | 117138230 | POLE_BROK_REPL - 1S\O 2W\O HOUSE 48001 W | 35215085 |  |  | STS-POLE_BROK_REPL - 1S\O 2W\O HOUSE 480 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 39.7308 | -123.5072 |  | TIER 2 | 299 | 04268-1101, LAYTONVILLE | F08 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102182883 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-01 | 2020-05-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042681101 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | Laytonville | Willits |  |  | OPEN | 118438491 | POLE_BROK_REPL - 42501 MATHER LN.Laytonv | 35224228 |  |  | STS-POLE_BROK_REPL - 42501 MATHER LN.LAY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.6529 | -123.4858 |  | TIER 2 | 216 | 04268-1102, LAYTONVILLE | H09 | 5259 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102194087 | OH PRI INSP ESTR TER2 RELW FMOB | Pole |  |  | REQD | [17 empty] | 2020-01-16 | 2021-01-16 |  | 2021-01-16 | Q1 Work Plan | 2021-03-31 | UNASSIGNED |  | 042681102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | LEGGETT | Garberville |  |  | OPEN | 117071279 | POLE_BROK_REPL - #8S\O 65250 HWY 271LEGG | 35215441 |  |  | STS-POLE_BROK_REPL - #8S\O 65250 HWY 271 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.8393 | -123.6859 |  | TIER 2 | 299 | 04268-1101, LAYTONVILLE | KK1825 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.6 | 37.6 |  |  | 0 | 37.6 | 37.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100987967 | RELW OH PRI CLR JPOL RESD FIRE ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-25 |  | COMP | 2021-01-25 | [16 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042681101 | 29988.82 | 590.8 | 590.8 | 590.8 | 590.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | Lower Lake | Clear Lake |  |  | OPEN | 115277244 | POLE_DECA_REPL - 6451 Sunrise Dr Lower L | 35149629 |  |  | STS-POLE_DECA_REPL - 6451 SUNRISE DR LOW | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 38.9354 | -122.6589 |  | TIER 2 | 32 | 04331-1102, KONOCTI | X29 | 948 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.8 | 27.8 |  |  | 0 | 27.8 | 27.8 |  |  | EC | F | Pole | Decayed/Rotten | Replace |  | 102147970 | RELW OH PRI INSP REMT NOAC USA SCOP SCPA FMOB TER2 | Pole | 2020-10-07 | 2020-10-05 | COMP | 2020-10-05 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-11-06 | 2023-11-06 | 2019-12-31 | 2019-12-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 043311102 | 31579.37 | 1406.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | LOWER LAKE | Clear Lake |  |  | OPEN | 116721716 | POLE_BROK_REPL - 5360 SUNRISE RD LOWER L | 35208761 |  |  | STS-POLE_BROK_REPL - 5360 SUNRISE RD LOW | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.9442 | -122.6532 |  | TIER 2 | 32 | 04331-1102, KONOCTI | X29 | 2297 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48.8 | 48.8 |  |  | 0 | 48.8 | 48.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102216328 | OH PRI CLR ESTR BTKA FMOB TER2 PRTO FSRP RELW | Pole | 2021-01-27 |  | COMP | 2021-01-27 | [16 empty] | 2019-03-13 | 2020-03-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043311102 | 20360 | 95.9 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | LOWER LAKE | Clear Lake |  |  | OPEN | 116765996 | POLE_BROK_REPL - 13449 ANDERSON RD LOWER | 35208838 |  |  | STS-POLE_BROK_REPL - 13449 ANDERSON RD L | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 38.9407 | -122.6632 |  | TIER 2 | 32 | 04331-1102, KONOCTI | X29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 19.9 | 19.9 |  |  | 0 | 19.9 | 19.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103928075 | OH RELW PRI CLR NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-28 |  | COMP | 2021-01-28 | [16 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 043311102 | 8612.76 | 102.3 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | LOWER LAKE | Clear Lake |  |  | OPEN | 116862439 | POLE_OVRL_REPL - 15898 KUGLMAN RD SP LOW | 35202542 |  |  | STS-POLE_OVRL_REPL - 15898 KUGLMAN RD SP | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.9144 | -122.6158 |  | TIER 2 | 135 | 04336-1103, HIGHLANDS | Y30 | 639309 | Y | 311 |  |  |  |  | Started | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 74.6 | 74.6 |  |  | 0 | 74.6 | 74.6 |  |  | EC | E | Pole | Overloaded | Replace |  | 102151382 | RELW OH PRI ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-30 |  | COMP | 2020-12-30 | [16 empty] | 2019-03-29 | 2020-03-29 | 2020-09-17 | 2020-09-17 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043361103 | 39226.31 | 3486.6 | 3442.1 | 5602.2 | 5602.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | MAD RIVER | Fortuna |  |  | OPEN | 118593205 | POLE_DECA_REPL -1S CO43847 MAD RIVER RD | 35184647 |  |  | STS-POLE_DECA_REPL -1S CO43847 MAD RIVER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4389 | -123.49 |  | TIER 2 | 205 | 19241-1101, LOW GAP | X24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 23 | 22.6 | 0.4 |  | 0 | 23 | 22.6 | 0.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101009545 | RELW TER2 | Pole | 2020-08-12 | 2020-11-07 | COMP | 2020-08-12 | [16 empty] | 2020-02-28 | 2020-12-31 |  | 2020-12-31 | Email from [REDACTED] 3.3.20 | 2020-09-30 | CALENG |  | 192411101 | 10888.89 | 61.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-03-09
North | HB | MENDOCINO | Fort Bragg |  |  | OPEN | 110643860 | POLE_DECA_REPL - 42265 LITTLE LAKE RD ME | 35194922 |  |  | POLE_DECA_REPL - 42255 LITTLE LAKE R | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.3096 | -123.748 |  | TIER 2 | 178 | 04308-1101, BIG RIVER | P02 | 3291 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 47.9 | 47.9 |  |  | 0 | 47.9 | 47.9 |  |  | EC | F | Pole | Decayed/Rotten | Replace |  | 102188166 | RELW OH PRI INSP RESD FLAG ESTR GO BTKA TER2 | Pole | 2020-12-29 |  | COMP | 2020-12-29 |  |  | 2021-02-17 | 2021-02-17 | [12 empty] | 2015-08-04 | 2020-08-04 |  | 2020-08-04 | Per DOT Approved Request 45760 | 2020-12-31 | ENENG |  | 043081101 | 27223.31 | 501 | 27.8 | 1940 | 1940 |  |  |  | Electric Distribution | N | MPP Owned but exists in DO Pull | N |  | Y | 2021-02-06
North | HB | MENDOCINO | Fort Bragg |  |  | OPEN | 117010866 | POLE_DECA_REPL - 42375 LITTLE LAKE RD ME | 35191851 |  |  | GC 12/31 REPL POLE 42375 LITTLE LAKE RD | CONS | CONS SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3095 | -123.7527 |  | TIER 2 | 178 | 04308-1101, BIG RIVER | P02 |  | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 39.1 | 39.1 |  |  | 0.5 | 39 | 39 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 102188162 | RELW OH PRI JPOL RESD BTKA FLAG ESTR GO PROG FMOB TER2 PRTO | Pole | 2020-12-24 | 2021-01-06 | COMP | 2020-12-24 |  |  | 2021-01-04 | 2021-01-04 | [12 empty] | 2019-04-11 | 2020-04-11 | 2020-12-31 | 2020-12-31 | B-tag addition 8/12/2020 | 2021-02-28 | ENENG |  | 043081101 | 26176.64 | 3011 | 2970.7 | 4771.3 | 4771.3 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N | Tag Duration Set Inappropriate For Work | Y | 2020-08-18
North | HB | MIDDLETOWN | Clear Lake |  |  | COMP | 117097399 | POLE_BROK_REPL - 1918 RANCHERIA RD 3E 1S | 35117479 |  |  | STS-POLE_BROK_REPL - 1918 RANCHERIA RD 3 | DOCC | DOCC SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7302 | -122.6238 |  | TIER 2 | 67 | 04314-1101, MIDDLETOWN | CC30 | 1314 | Y | 311 |  |  | 2021-01-14 | 2021-01-14 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 43.5 | 43.5 |  |  | 1.75 | 42.5 | 42.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102166475 | RELW OH PRI INSP COMP JPOL PUBL ESTR GO BTKA CCNT PROG FMOB TER2 | Pole | 2020-07-27 | 2020-07-29 | COMP | 2020-01-30 | COMP | 2021-01-14 | 2019-10-15 | 2019-10-15 | [11 empty] | 2021-01-20 | 2021-01-14 | 2020-04-25 | 2021-05-31 | 2021-05-31 | Q1 Work Plan | 2020-01-30 | EEI |  | 043141101 | 21123.6 | 10774.2 | 2142.3 | 618.3 | 618.3 | 3068.2 |  | 3068.2 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | MIDDLETOWN | Clear Lake |  |  | OPEN | 117068916 | POLE_DECA_REPL - NW C/O HWY 29/RANCHERIA | 35118001 |  |  | STS-POLE_DECA_REPL - NW C/O HWY 29/RANCH | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.731 | -122.6236 |  | TIER 2 | 67 | 04314-1101, MIDDLETOWN | CC30 |  | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 44.4 | 44.4 |  |  | 7.5 | 43.4 | 43.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102166472 | RELW OH PRI INSP JPOL RESD FIRE TRAF CGI FLAG ESTR GO BTKA FMOB TER2 | Pole | 2019-08-12 | 2020-01-31 | COMP | 2019-08-12 |  |  | 2019-08-19 | 2019-08-19 | [12 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | Q1 Work Plan | 2019-08-12 | EEI |  | 043141101 | 28934.41 | 8450.2 | 3086.3 | 5236.4 | 5236.4 | 1073.6 |  | 1073.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | MIDDLETOWN | Clear Lake |  |  | OPEN | 117270156 | POLE_DECA_REPL - 21300 SANTA CLARA RD.C/ | 35117905 |  |  | STS-POLE_DECA_REPL - 21300 SANTA CLARA R | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7493 | -122.6232 |  | TIER 2 | 67 | 04314-1101, MIDDLETOWN | BB3024 | 99071 | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 2 | 40.8 | 40.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102151935 | RELW OH PRI CLR ESTR FMOB TER2 PRTO | Pole | 2019-09-06 | 2019-11-19 | COMP | 2019-09-06 |  |  | 2019-11-19 | 2019-11-19 | [12 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | Q1 Work Plan | 2019-09-06 | CALENG |  | 043141101 | 23188.55 | 9434.4 | 233.6 | 55.6 | 55.6 | 372.5 |  | 372.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | MIDDLETOWN | Clear Lake |  |  | OPEN | 117273723 | POLE_DECA_REPL - 15525 LAKE AVE.E/O MIDD | 35118062 |  |  | STS-POLE_DECA_REPL - 15525 LAKE AVE.E/O | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7473 | -122.6198 |  | TIER 2 | 67 | 04314-1101, MIDDLETOWN | BB3024 |  | Y | 311 |  |  | 2021-03-06 07:00 | 2021-03-06 16:00 | Dispatched | CLICK | [6 empty] | 1.8 | 1.8 |  |  | 4.5 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102151917 | RELW OH PRI CLR ESTR GO FMOB TER2 PRTO | Pole | 2019-09-13 | 2019-11-19 | COMP | 2019-09-13 |  |  | 2019-11-19 | 2019-11-19 | [12 empty] | 2019-05-19 | 2020-05-19 | 2021-05-31 | 2021-05-31 | Q1 Work Plan | 2019-09-13 | EEI |  | 043141101 | 24712.81 | 9937.9 | 3375.4 | 562.7 | 562.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | MIDDLETOWN | Clear Lake |  |  | OPEN | 117011462 | POLE_BROK_REPL - 21760 HWY 29 @ HOUSE W/ | 35117971 |  |  | STS-POLE_BROK_REPL - 21760 HWY 29 @ HOUS | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7387 | -122.6243 |  | TIER 2 | 67 | 04314-1101, MIDDLETOWN | CC30 | 64881 | Y | 311 |  |  | 2021-03-24 07:00 | 2021-03-24 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102166651 | RELW OH PRI INSP JPOL REMT FIRE SPCR SWRK ESTR GO BTKA FMOB TER2 | Pole | 2019-08-16 | 2019-10-15 | COMP | 2019-08-16 |  |  | 2019-10-15 | 2019-10-15 | [12 empty] | 2019-04-11 | 2020-04-11 | 2021-05-31 | 2021-05-31 | Q1 Work Plan | 2019-08-16 | EEI |  | 043141101 | 18673.48 | 6251 | 3339.4 | 1975.2 | 1975.2 | 2686.6 |  | 2686.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | MYERS FLAT | Garberville |  |  | OPEN | 117161423 | POLE_BURN_REPL - 17119 AVE OF THE GIANTS | 35215264 |  |  | STS-POLE_BURN_REPL - 17119 AVE OF THE GI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.3085 | -123.9069 |  | TIER 2 | 251 | 19231-1141, FRUITLAND | AA13 | 3987 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 100990440 | RELW OH PRI JPOL RESD COMM REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192311141 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | MYERS FLAT | Garberville |  |  | OPEN | 117164268 | TREE_DECA_INPL - 3S\O 3W\O 1S\O HOUSE 65 | 35215308 |  |  | STS-TREE_DECA_INPL - 3S\O 3W\O 1S\O HOUS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.2317 | -123.8253 |  | TIER 2 | 195 | 19231-1142, FRUITLAND | CC1505 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100989629 | SEC RELW OH ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192311142 | 1 | 129.6 | 129.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | MYERS FLAT | Garberville |  |  | OPEN | 117166211 | POLE_DECA_REPL - 1E\O HOUSE 5 ORCHARD LN | 35215333 |  |  | STS-POLE_DECA_REPL - 1E\O HOUSE 5 ORCHAR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 40.2348 | -123.8215 |  | TIER 2 | 195 | 19231-1142, FRUITLAND | CC1505 | 3783 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100989689 | RELW OH PRI JPOL RESD REMT FLAG SWRK ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-06 | 2020-05-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192311142 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | MYERS FLAT | Garberville |  |  | OPEN | 117171781 | POLE_BROK_REPL - 3N\O 3W\O 1S\O HOUSE 65 | 35215356 |  |  | STS-POLE_BROK_REPL - 3N\O 3W\O 1S\O HOUS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.2337 | -123.8256 |  | TIER 2 | 195 | 19231-1142, FRUITLAND | CC1505 | NA | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100989709 | SEC RELW OH PGEA PUBL RESD FIRE ESTR GO USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-06 | 2020-05-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192311142 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | MYERS FLAT | Garberville |  |  | OPEN | 117171782 | POLE_BROK_REPL - 1S\O @6W\O 1S\O HOUSE 6 | 35215381 |  |  | STS-POLE_BROK_REPL - 1S\O @6W\O 1S\O HOU | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.2322 | -123.8265 |  | TIER 2 | 195 | 19231-1142, FRUITLAND | CC1505 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100989645 | RELW OH SEC JPOL ESTR FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-06 | 2019-10-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192311142 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | MYERS FLAT | Garberville |  |  | OPEN | 117162524 | POLE_DECA_REPL - 2E\O 1S\O 17119 AVE OF | 35224486 |  |  | STS-POLE_DECA_REPL - 2E\O 1S\O 17119 AVE | PEND | PEND | Poles | MPP | Not Funded as 2020 Wildfire OII | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Land JointPole |  |  | 40.308 | -123.9049 |  | TIER 2 | 251 | 19231-1141, FRUITLAND | AA13 | 3987 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 56.5 | 56.5 |  |  | 1.25 | 55.25 | 55.25 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100990459 | RELW OH PRI JPOL REMT NOAC SPCR FSRP REAR FMOB TER2 PRTO SCOP SCPA | Pole | 2021-02-01 |  | COMP | 2021-02-01 | [16 empty] | 2019-05-04 | 2021-06-11 |  | 2021-06-11 | work plan year cleanup 01/21/2021 |  | Chico |  | 192311141 | 35306.05 | 716.8 | 716.8 | 498.9 | 498.9 |  |  |  | FRMMA/WMPMA - Electric | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-21
North | HB | Nice | Lakeport |  |  | OPEN | 120048112 | POLE_BROK_REPL - SW C/O LAKEVIEW DR/MONO | 35216675 |  |  | B3-POLE_BROK_REPL - SW C/O LAKEVIEW DR/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-20 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1273 | -122.8572 |  | TIER 2 | 532 | 04335-1103, LUCERNE | T2415 | 1539 | Y | 311 |  |  | 2021-04-09 07:00 | 2021-04-09 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 39.1 | 39.1 |  |  | 0 | 39.1 | 39.1 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 102164023 | RELW OH PRI CLR JPOL RESD FLAG ESTR GO BTKA USA CTMN FMOB TER2 | Pole | 2020-12-23 | 2020-12-31 | COMP | 2020-12-22 |  |  | 2020-12-23 | 2020-12-23 | [12 empty] | 2020-11-17 | 2021-02-17 |  | 2021-02-17 | B tag clean up 11/19/2020 |  | Santa Rosa |  | 043351103 | 18869.74 | 941.5 | 770.2 | 770.2 | 770.2 |  |  |  | Electric Distribution | N | Pulled from MPP Import File | N |  | Y | 2020-11-19
North | HB | PETROLIA | Garberville |  |  | OPEN | 117124774 | POLE_BROK_REPL - A/F #1N/O 1321 LIGHT HO | 35214992 |  |  | STS-POLE_BROK_REPL - A/F #1N/O 1321 LIGH | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.3002 | -124.2977 |  | TIER 2 | 49 | 19222-1102, GARBERVILLE | AA04 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100987259 | RELW OH PRI TER2 ESTR BTKA FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192221102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PETROLIA | Garberville |  |  | OPEN | 117124778 | POLE_DECA_REPL - 115 EVERGREEN WAY PETRO | 35214997 |  |  | STS-POLE_DECA_REPL - 115 EVERGREEN WAY P | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.3005 | -124.2947 |  | TIER 2 | 49 | 19222-1102, GARBERVILLE | AA04 | 2551 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100987265 | RELW OH PRI ESTR PRTO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192221102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PETROLIA | Garberville |  |  | OPEN | 117124781 | POLE_BROK_REPL - 7W/O 29 CHAMBERS RDPETR | 35215002 |  |  | STS-POLE_BROK_REPL - 7W/O 29 CHAMBERS RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.3231 | -124.2594 |  | TIER 2 | 49 | 19222-1102, GARBERVILLE | Z05 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100987177 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192221102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PETROLIA | Garberville |  |  | OPEN | 117139566 | POLE_DECA_REPL - #2W 141 TOBACCO RD PETR | 35215093 |  |  | STS-POLE_DECA_REPL - #2W 141 TOBACCO RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.3154 | -124.2793 |  | TIER 2 | 49 | 19222-1102, GARBERVILLE | AA0405 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100987351 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-01 | 2020-05-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192221102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PETROLIA | Garberville |  |  | OPEN | 117158420 | POLE_BROK_REPL - 10W/O 36328 MATTOLE RD | 35215208 |  |  | STS-POLE_BROK_REPL - 10W/O 36328 MATTOLE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 40.2793 | -124.246 |  | TIER 2 | 49 | 19222-1102, GARBERVILLE | AA05 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100987026 | RELW OH PRI FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192221102 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PETROLIA | Garberville |  |  | OPEN | 117184770 | POLE_BROK_REPL - 3N/O 1E/O 42101 MATTOLE | 35202541 |  |  | STS-POLE_BROK_REPL - 3N/O 1E/O 42101 MAT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.2381 | -124.1598 |  | TIER 2 | 49 | 19222-1102, GARBERVILLE | BB07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100986452 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2019-11-08 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | QUES |  | 192221102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PETROLIA | Garberville |  |  | OPEN | 117320767 | POLE_BROK_REPL - 1S/O 2E/O 36328 MATTOLE | 35215677 |  |  | STS-POLE_BROK_REPL - 1S/O 2E/O 36328 MAT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 40.277 | -124.2328 |  | TIER 2 | 49 | 19222-1102, GARBERVILLE | AA05 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100986880 | RELW OH PRI REMT TER2 NOAC ESTR FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-25 | 2020-05-25 | 2021-03-09 | 2021-03-09 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192221102 | 1 | 348 | 348 | 348 | 348 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PETROLIA | Garberville |  |  | OPEN | 117116271 | POLE_BROK_REPL - 1SE/O 3E/O 2S/O C/O MAT | 35202279 |  |  | STS-POLE_BROK_REPL - 1SE/O 3E/O 2S/O C/O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.3229 | -124.2835 |  | TIER 2 | 49 | 19222-1102, GARBERVILLE | Z0424 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.3 | 18.3 |  |  | 0 | 18.3 | 18.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100987398 | PRI RELW OH ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-03 | 2021-02-03 | COMP | 2021-02-03 | [16 empty] | 2019-04-28 | 2020-04-28 | 2020-09-08 | 2020-09-08 | 2021 CBP Plan | 2021-02-28 | QUES |  | 192221102 | 19913.92 | 87.1 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PHILO | Ukiah |  |  | OPEN | 116838584 | POLE_DECA_REPL - S/O 3970 HWY 128PHILO95 | 35202499 |  |  | STS-POLE_DECA_REPL - S/O 3970 HWY 128PHI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 39.1103 | -123.5066 |  | TIER 2 | 88 | 04260-1102, PHILO | T08 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | F | Pole | Decayed/Rotten | Replace |  | 102169737 | RELW OH SEC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 |  | 2020-03-26 | 2021 CBP Plan | 2021-02-28 | QUES |  | 042601102 | 1 | 40.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PHILO | Ukiah |  |  | OPEN | 116838605 | POLE_DECA_REPL - #2SE/O 3970 HWY 128PHIL | 35214848 |  |  | STS-POLE_DECA_REPL - #2SE/O 3970 HWY 128 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.1094 | -123.5054 |  | TIER 2 | 88 | 04260-1102, PHILO | T08 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102169729 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042601102 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PHILO | Ukiah |  |  | OPEN | 116854473 | POLE_DECA_REPL - 185 HOLMES RANCH RDPHIL | 35215023 |  |  | STS-POLE_DECA_REPL - 185 HOLMES RANCH RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 39.1491 | -123.5091 |  | TIER 2 | 88 | 04260-1102, PHILO | T08 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102170042 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042601102 | 1 | 38 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PHILO | Ukiah |  |  | OPEN | 116862432 | POLE_LEAN_REPL - #2W/O #9N/O 4201 HWY 12 | 35215204 |  |  | STS-POLE_LEAN_REPL - #2W/O #9N/O 4201 HW | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.1149 | -123.5021 |  | TIER 2 | 88 | 04260-1102, PHILO | T08 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Leaning | Replace |  | 102169675 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042601102 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PHILO | Ukiah |  |  | OPEN | 116863353 | POLE_BROK_REPL - #2NW/O 560 SMITH HILL R | 35215231 |  |  | STS-POLE_BROK_REPL - #2NW/O 560 SMITH HI | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.1445 | -123.5142 |  | TIER 2 | 88 | 04260-1102, PHILO | T08 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 38.4 | 38.4 |  |  | 0 | 38.4 | 38.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102170209 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-16 |  | COMP | 2021-02-16 | [16 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042601102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PHILO | Ukiah |  |  | OPEN | 116873186 | POLE_DECA_REPL - S/O #3NW/O 6501 CLOW RI | 35215487 |  |  | STS-POLE_DECA_REPL - S/O #3NW/O 6501 CLO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.1245 | -123.4905 |  | TIER 2 | 88 | 04260-1102, PHILO | T09 | 3713 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102170699 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042601102 | 1 | 313 | 313.1 | 236.5 | 236.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PHILO | Ukiah |  |  | OPEN | 116876538 | POLE_DECA_REPL - 66001 NASH MILL RDPHILO | 35215509 |  |  | STS-POLE_DECA_REPL - 66001 NASH MILL RDP | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.1239 | -123.4937 |  | TIER 2 | 88 | 04260-1102, PHILO | T09 | 3713 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102170707 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042601102 | 1 |  | 0 | 1304 | 1304 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PHILO | Ukiah |  |  | OPEN | 116876865 | POLE_DECA_REPL - #2W/O 66200 NASH MILL R | 35215514 |  |  | STS-POLE_DECA_REPL - #2W/O 66200 NASH MI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.1241 | -123.4999 |  | TIER 2 | 88 | 04260-1102, PHILO | T08 | 3713 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102170356 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042601102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PHILO | Ukiah |  |  | OPEN | 116949411 | CONN_INCR_REPL - 13970 NASH MILL RD PHIL | 35214620 |  |  | STS-CONN_INCR_REPL - 13970 NASH MILL RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.1254 | -123.4845 |  | TIER 2 | 88 | 04260-1102, PHILO | T09 | 9075 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Connector | Incorrectly Installed | Replace |  | 102170683 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-03 | 2020-04-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042601102 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | PHILO | Ukiah |  |  | OPEN | 115144896 | POLE_BROK_REPL - FRANKS FIREWOOD PHILO G | 35072251 |  |  | ROK REPL POLE FRANKS FIREWOOD PHI | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0823 | -123.4914 |  | TIER 2 | 88 | 04260-1102, PHILO | U09 | 2600 | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 41 | 41 |  |  | 1 | 40 | 40 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102216133 | RELW CLR OH PRI CREW REMT SPCR ESTR BTKA USA TER2 | Pole | 2019-02-25 | 2019-02-25 | COMP | 2019-02-25 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-10-26 | 2019-10-26 |  | 2019-10-26 | Q1 Work Plan |  | UNASSIGNED |  | 042601102 | 12731.65 | 2179.8 | 235.1 | 235.1 | 235.1 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | PIERCY | Garberville |  |  | OPEN | 114646755 | POD POLE_BROK_REPL - 81404 HWY 271 PIERC | 35044779 |  |  | POLE_BROK_REPL - 81404 HWY 271 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.9756 | -123.8016 |  | TIER 2 | 99 | 19222-1101, GARBERVILLE | HH16 | 1763 | Y | 311 |  |  | 2021-03-03 07:00 | 2021-03-03 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 40.1 | 40.1 |  |  | 11.5 | 40 | 40 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100991715 | POHW OH PRI SEC SERV CREW TRAF CLR JPOL RESD FLAG ESTR GO OTRG XMPT TER2 | Pole | 2018-09-14 | 2018-10-25 | COMP | 2018-09-14 |  |  | 2018-07-27 | 2018-07-27 | [12 empty] | 2018-05-18 | 2019-05-18 | 2021-05-31 | 2021-05-31 | Q1 Work Plan |  | UNASSIGNED |  | 192221101 | 22938.11 | 39727 | 87 | 87 | 87 | 825.6 |  | 825.6 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | PIERCY | Garberville |  |  | OPEN | 114647621 | POD POLE_BROK_REPL - 82912 DIMMICK RD PI | 35044780 |  |  | POD STS-POLE_BROK_REPL - 82912 DIMMICK | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.9796 | -123.8052 |  | TIER 2 | 99 | 19222-1101, GARBERVILLE | HH16 | 1571 | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-04 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 40.1 | 40.1 |  |  | 0 | 40.1 | 40.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100991681 | POHW OH PRI CREW CLR JPOL REMT SWRK ESTR USA XMPT TER2 | Pole | 2018-09-26 | 2018-11-12 | COMP | 2018-09-26 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-05-18 | 2019-05-18 | 2019-07-17 | 2019-07-17 | Q1 Work Plan |  | UNASSIGNED |  | 192221101 | 8729.92 | 6842.1 | 174 | 174 | 174 |  |  |  | Electric Distribution | Y | MPP File Only | N | Access/Customer Issue | Y | 2020-02-18
North | HB | PIERCY | Garberville |  |  | OPEN | 115597451 | REPL POLE 1SE\O 60681 HWY 271 | 35070377 |  |  | GC REPL POLE 1SE\O 60681 HWY 271 PIERCY | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.8335 | -123.6207 |  | TIER 2 | 299 | 04268-1101, LAYTONVILLE | LL20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101010326 | REGW OH TER2 | Pole | 2019-05-03 | 2019-07-31 | COMP | 2019-05-02 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-02 | ENENG |  | 042681101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | POTTER VALLEY | Ukiah |  |  | OPEN | 117019598 | POLE_BURN_REPL - 2N/O 8177 GIBSON LNPOTT | 35214930 |  |  | STS-POLE_BURN_REPL - 2N/O 8177 GIBSON LN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 39.3432 | -123.1442 |  | TIER 2 | 1017 | 04228-1104, POTTER VALLEY P H | O17 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 102173652 | RELW OH PRI JPOL REMT FLAG ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-12 | 2020-04-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042281104 | 1 | 16.2 | 16.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | POTTER VALLEY | Ukiah |  |  | OPEN | 119965886 | POLE_BROK_REPL - 2N/O R/O 14001 N. BUSCH | 35211046 |  |  | GC POLE_BROK_REPL - 2N/O R/O 14001 N. B | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-01-02 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3566 | -123.1368 |  | TIER 2 | 147 | 04228-1105, POTTER VALLEY P H | O17 | 64118 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 61.2 | 61.2 |  |  | 0 | 61.2 | 61.2 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 102173540 | RELW OH PRI CLR COMM REMT FIRE SWRK ESTR GO BTKA USA CTMN FMOB TER2 | Pole | 2020-11-20 | 2020-12-11 | COMP | 2020-11-19 | [16 empty] | 2020-10-30 | 2021-01-30 |  | 2021-01-30 | B tag clean up 11/1/2020 |  | Santa Rosa |  | 042281105 | 26754.59 | 4324.6 | 1468.3 | 1468.3 | 1468.3 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N |  | Y | 2020-11-01
North | HB | REDCREST | Garberville |  |  | OPEN | 116708678 | POLE_BROK_REPL - 2999 DYERVILLE LOOP RD. | 35214661 |  |  | STS-POLE_BROK_REPL - 2999 DYERVILLE LOOP | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.3401 | -123.8923 |  | TIER 2 | 251 | 19231-1141, FRUITLAND | Z14 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100989997 | RELW OH PRI JPOL REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-11 | 2020-03-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192311141 | 1 | 129.6 | 129.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | REDCREST | Garberville |  |  | OPEN | 116712687 | POLE_DECA_REPL - 1W\O HOUSE 178 WEOTT HG | 35214690 |  |  | STS-POLE_DECA_REPL - 1W\O HOUSE 178 WEOT | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 40.3207 | -123.9238 |  | TIER 2 | 251 | 19231-1141, FRUITLAND | AA1303 | 3923 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100988985 | RELW OH PRI JPOL COMM ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-11 | 2020-03-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192311141 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | Redcrest | Garberville |  |  | OPEN | 117684709 | POLE _BROK _REPL_1EO 1SO 5WO 1SO HOUSE 1 | 35216218 |  |  | STS-POLE _BROK _REPL_1EO 1SO 5WO 1SO HOU | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.32 | -123.9148 |  | TIER 2 | 251 | 19231-1141, FRUITLAND | AA1304 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100989208 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192311141 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | REDWAY | Garberville |  |  | OPEN | 116851536 | POLE_DECA_REPL - 3E/O 4301 BRICELAND RD. | 35176807 |  |  | STS-POLE_DECA_REPL - 3E/O 4301 BRICELAND | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.1236 | -123.8761 |  | TIER 2 | 49 | 19222-1102, GARBERVILLE | EE14 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 74.4 | 74.4 |  |  | 0 | 74.4 | 74.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100985091 | OH RELW PRI JPOL TRAF FLAG ESTR USA FMOB TER2 PRTO | Pole | 2020-08-12 | 2021-02-02 | COMP | 2020-08-12 |  |  | 2021-02-05 | 2021-02-05 | [12 empty] | 2019-03-27 | 2020-03-27 |  | 2020-03-27 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 192221102 | 14333.32 | 296.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | REDWOOD VALLEY | Ukiah |  |  | OPEN | 116807263 | POLE_BROK_REPL - 875 LENNIX DR REDWOOD V | 35215350 |  |  | STS-POLE_BROK_REPL - 875 LENNIX DR REDWO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 39.2548 | -123.2322 |  | TIER 2 | 335 | 04341-1101, CALPELLA | Q15 | 7505 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103058384 | RELW OH PRI CREW CLR JPOL PUBL RESD FIRE TRAF FLAG ESTR BTKA USA PROG TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-12 | 2020-03-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 043411101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | REDWOOD VALLEY | Ukiah |  |  | OPEN | 117208021 | POLE_DECA_REPL - 680 E SCHOOL WAY REDWOO | 35214627 |  |  | STS-POLE_DECA_REPL - 680 E SCHOOL WAY RE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 39.2667 | -123.2139 |  | TIER 2 | 128 | 04295-1101, MENDOCINO | Q1602 | 45290 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102169997 | RELW OH PRI CREW JPOL REMT ESTR USA TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042951101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | REDWOOD VALLEY | Ukiah |  |  | OPEN | 117299439 | POLE_DECA_REPL - #32W #5N 9 MAPLE LN RED | 35215601 |  |  | STS-POLE_DECA_REPL - #32W #5N 9 MAPLE LN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.3209 | -123.3493 |  | TIER 2 | 335 | 04341-1101, CALPELLA | P12 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102178289 | RELW OH PRI PGEA REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-22 | 2020-05-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 043411101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | REDWOOD VALLEY | Ukiah |  |  | OPEN | 117335176 | POLE_BROK_REPL - 3203 REEVES CANYON RD W | 35215771 |  |  | STS-POLE_BROK_REPL - 3203 REEVES CANYON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.281 | -123.3034 |  | TIER 2 | 335 | 04341-1101, CALPELLA | Q13 | 6657 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.6 | 39.6 | 0 |  | 0 | 39.6 | 39.6 | 0 |  | EC | E | Pole | Broken/Damaged | Replace |  | 102201923 | RELW OH PRI CLR REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-17 | 2021-02-17 | COMP | 2021-02-17 | [16 empty] | 2019-05-28 | 2020-05-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 043411101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | REDWOOD VALLEY | Ukiah |  |  | OPEN | 117337598 | POLE_BROK_REPL - #1S/R/O 656 FINNE RD RE | 35215786 |  |  | STS-POLE_BROK_REPL - #1S/R/O 656 FINNE R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.2442 | -123.224 |  | TIER 2 | 335 | 04341-1101, CALPELLA | Q15 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102178009 | RELW OH PRI CLR JPOL REMT ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-29 | 2020-05-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 043411101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | REDWOOD VALLEY | Ukiah |  |  | OPEN | 117344351 | POLE_BROK_REPL - 10801 BAKERS CREEK RDRE | 35215798 |  |  | STS-POLE_BROK_REPL - 10801 BAKERS CREEK | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land JointPole |  |  | 39.2913 | -123.2339 |  | TIER 2 | 335 | 04341-1101, CALPELLA | P15 | 399765 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102177855 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-30 | 2020-05-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 043411101 | 1 | 146.1 | 146.1 | 146.1 | 146.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | Redwood Valley | Ukiah |  |  | OPEN | 117938169 | REPL POLE:R/O 9021 COLONY DR,Redwood Val | 35216018 |  |  | STS-REPL POLE:R/O 9021 COLONY DR,REDWOOD | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.2754 | -123.1798 |  | TIER 2 | 128 | 04295-1101, MENDOCINO | Q16 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102202206 | RELW OH TNT TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-04 | 2020-06-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042951101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | Redwood Valley | Ukiah |  |  | OPEN | 117938171 | REPL POLE:#1E 2900 RD B,Redwood Valley | 35216023 |  |  | STS-REPL POLE:#1E 2900 RD B,REDWOOD VALL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.2514 | -123.1791 |  | TIER 2 | 128 | 04295-1101, MENDOCINO | Q16 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102202654 | RELW OH TNT JPOL TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-18 | 2020-06-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042951101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | REDWOOD VALLEY | Ukiah |  |  | OPEN | 117338582 | POLE_BROK_REPL - #1S #2W A/F 11501 HWY 1 | 35203070 |  |  |  | CONS | CONS ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2822 | -123.2616 |  | TIER 2 | 335 | 04341-1101, CALPELLA | Q14 |  | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 14.1 | 14.1 |  |  | 0 | 14.1 | 14.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102205703 | RELW OH PRI INSP CLR JPOL ESTR REMT NOAC BTKA REAR FMOB TER2 FSRP | Pole | 2020-11-13 | 2021-01-07 | COMP | 2020-11-13 | [16 empty] | 2019-05-29 | 2020-05-29 | 2020-12-15 | 2020-12-15 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043411101 | 8070.96 | 2012.9 | 1348.6 | 1057.4 | 1057.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | REDWOOD VALLEY | Ukiah |  |  | OPEN | 117771520 | REPL POLE:ENTRANCE TO 8555 CAVE CREEK RD | 35145947 |  |  | STS-REPL POLE:ENTRANCE TO 8555 CAVE CREE | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 39.384 | -123.2171 |  | TIER 2 | 128 | 04295-1101, MENDOCINO | N15 |  | Y | 311 |  |  | 2021-03-01 07:00 | 2021-03-01 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 29.1 | 29.1 |  |  | 1 | 29 | 29 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102198758 | RELW OH TNT TER2 | Pole | 2020-07-31 | 2020-09-16 | COMP | 2020-07-31 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-29 | 2019-11-29 |  | 2019-11-29 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 042951101 | 17160.88 | 5235.5 | 2010.9 | 1934.8 | 1934.8 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | Redwood Valley | Willits |  |  | OPEN | 120535808 | POLE_DECA_REPL - #1N 2090 RD BRedwood Va | 35233464 |  |  | B3-POLE_DECA_REPL - #1N 2090 RD BREDWOO | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-04-16 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 39.2594 | -123.1835 |  | TIER 2 | 335 | 04341-1101, CALPELLA | Q16 | 967425 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 102202509 | RELW OH PRI PATR CLR JPOL RESD TRAF ESTR BTKA USA WATR FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2021-02-14 | 2021-05-14 |  | 2021-05-14 | B tag clean up 2/19/2021 |  | Santa Rosa |  | 043411101 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | HB | ROCKPORT | Fort Bragg |  |  | OPEN | 115325408 | POLE_DECA_REPL - 46866 HWY 1 ROCKPORT S | 35072252 |  |  | STS-POLE_DECA_REPL-46866HWY 1 ROCKPOR*BD | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.729 | -123.8104 |  | TIER 2 | 430 | 04276-1101, FORT BRAGG A | F01 | 1775 | Y | 311 |  |  | 2021-03-24 07:00 | 2021-03-24 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 27.9 | 27.9 |  |  | 22.75 | 5.15 | 5.15 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102200030 | RELW OH PRI CREW CLR JPOL REMT NOAC ESTR USA TER2 | Pole | 2019-02-25 | 2019-04-12 | COMP | 2019-02-25 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-11-09 | 2019-11-09 |  | 2019-11-09 | Q1 Work Plan |  | UNASSIGNED |  | 042761101 | 15288.71 | 25675.9 | 21732.1 | [5 empty] | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | SCOTIA | Fortuna |  |  | OPEN | 118593309 | REPL POLE 1W/9S BARKDULL RD @HWY 101 | 35185270 |  |  | REPL POLE 1W/9S BARKDULL RD @HWY 101 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4279 | -123.9868 |  | TIER 2 | 176 | 19225-1102, RIO DELL | X12 | 1563 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.6 | 34.6 |  |  | 0 | 34.6 | 34.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101006447 | RELW TER2 | Pole | 2020-08-07 | 2020-10-21 | COMP | 2020-08-07 | [16 empty] | 2020-02-28 | 2020-12-31 |  | 2020-12-31 | Email from [REDACTED] 3.3.20 | 2020-09-30 | CALENG |  | 192251102 | 29358.27 | 4531 | [7 empty] | N | MPP File Only | N |  | Y | 2020-03-09
North | HB | UKIAH | Ukiah |  |  | OPEN | 116769533 | POLE_DECA_REPL - 2605 VICHY SPRINGS RD W | 35202194 |  |  | STS-POLE_DECA_REPL - 2605 VICHY SPRINGS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 39.1658 | -123.1619 |  | TIER 2 | 607 | 04277-1115, UKIAH | S1708 | 731 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102197995 | RELW OH PRI RESD TRAF FLAG ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042771115 | 1 | 6526.2 | 1575.4 | 1575.4 | 1575.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | UKIAH | Ukiah |  |  | OPEN | 116877525 | POLE_DECA_REPL - #3E/O 1500 NASH MILL RD | 35215549 |  |  | STS-POLE_DECA_REPL - #3E/O 1500 NASH MIL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.1309 | -123.4785 |  | TIER 2 | 88 | 04260-1102, PHILO | T09 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102170725 | OH RELW PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042601102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | UKIAH | Ukiah |  |  | OPEN | 116939336 | POLE_DECA_REPL - 1501 NASH MILL RDUKIAH9 | 35214584 |  |  | STS-POLE_DECA_REPL - 1501 NASH MILL RDUK | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land JointPole |  |  | 39.1287 | -123.4771 |  | TIER 2 | 88 | 04260-1102, PHILO | T09 | 9077 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102170734 | RELW OH PRI TER2 REMT ESTR FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-02 | 2020-04-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042601102 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | UKIAH | Ukiah |  |  | OPEN | 116947059 | POLE_BROK_REPL - R/O 12831 NASH MILL RD | 35214592 |  |  | STS-POLE_BROK_REPL - R/O 12831 NASH MILL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.1289 | -123.4749 |  | TIER 2 | 88 | 04260-1102, PHILO | T09 | 9077 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102170746 | RELW OH PRI REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-02 | 2020-04-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042601102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | UKIAH | Ukiah |  |  | OPEN | 117143842 | POLE_DECA_REPL - 681 SANEL DRUKIAH95418 | 35215107 |  |  |  | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land JointPole |  |  | 39.05 | -123.1444 |  | TIER 2 | 33 | 04225-1101, HOPLAND | V17 | 5555 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102192419 | RELW OH PRI INSP CNCL JPOL REMT ESTR GO USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-02 | 2020-05-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042251101 | 1 | 43.5 | 43.5 | 43.5 | 43.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | UKIAH | Ukiah |  |  | OPEN | 117272034 | POLE_BROK_REPL - 8 S/O 5210 BURKE HILL D | 35215329 |  |  | STS-POLE_BROK_REPL - 8 S/O 5210 BURKE HI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.0694 | -123.1951 |  | TIER 2 | 144 | 04277-1114, UKIAH | U16 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102197541 | RELW OH PRI JPOL NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-19 | 2020-05-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042771114 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | UKIAH | Ukiah |  |  | OPEN | 117343341 | POLE_BROK_REPL - #2 ON LINE S/O 2500 VIS | 35215948 |  |  | STS-POLE_BROK_REPL - #2 ON LINE S/O 2500 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2287 | -123.1369 |  | TIER 2 | 335 | 04341-1101, CALPELLA | R17 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 28.6 | 28.6 |  |  | 0 | 28.6 | 28.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103819602 | PRI OH RELW REMT JAR SPCR FMOB TER2 PRTO FSRP | Pole | 2021-02-16 | 2021-02-16 | COMP | 2021-02-16 | [16 empty] | 2019-05-30 | 2020-05-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 043411101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | UKIAH | Ukiah |  |  | OPEN | 117322509 | POLE_DECA_REPL - 770 CANYON CT UKIAH | 35203162 |  |  | STS-POLE_DECA_REPL - 770 CANYON CT UKIAH | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit FAA Enviro |  |  | 39.112 | -123.2122 |  | TIER 2 | 610 | 04277-1113, UKIAH | T1621 | 7545 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 2 | 0 | 50.2 | 50.2 |  |  | 0 | 50.2 | 50.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102178778 | OH SERV JPOL MINR RESD JAR TRAF FLAG BTKA FMOB TER2 PRTO FSRP RELW | Pole | 2020-12-07 |  | COMP | 2020-12-07 | [16 empty] | 2019-05-26 | 2020-05-26 | 2020-12-14 | 2020-12-14 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042771113 | 27497.89 | 1282.6 | 1242.3 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | UKIAH | Ukiah |  |  | OPEN | 120081171 | TREE_DECA_INPL - 770 CANYON CRT UKIAH S | 35203162 |  |  | STS-POLE_DECA_REPL - 770 CANYON CT UKIAH | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit FAA Enviro |  |  | 39.112 | -123.2122 |  | TIER 2 | 610 | 04277-1113, UKIAH | T1621 | 7545 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 2 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 102178778 | POHW OH ESTR TER2 | Pole | 2020-12-07 |  | COMP | 2020-12-07 | [16 empty] | 2020-10-20 | 2021-10-20 |  | 2021-10-20 | Per DOT Approved Request 28554 | 2021-01-31 | QUES |  | 042771113 | 27497.89 | 1282.6 | 1242.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
North | HB | UKIAH/HOPLAND | Ukiah |  |  | COMP | 119815101 | TREE_DECA_INPL - 4400 MOOSE RD UKIAH/HOP | 35204251 |  |  | OCGC B3-TREE_DECA_INPL- 4400 MOOSE RD UK | FICL | FICL SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-11-27 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.9973 | -123.1935 |  | TIER 2 | 33 | 04225-1101, HOPLAND | W16 | 7449 | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 2 | 0 | 0 | 2 | 0 |  |  |  | 16 | 0 |  |  |  | EC | B | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103601582 | RELW OH SERV CUST COMP REMT FIRE NOAC ESTR CTMN CPGG TER2 FMOB | Pole | 2020-11-20 | 2020-11-20 | COMP | 2020-11-20 | COMP | 2021-01-08 | [13 empty] | 2021-01-08 | 2021-01-08 | 2020-12-25 |  | 2020-12-25 | B tag clean up 10/4/2020 |  | Santa Rosa |  | 042251101 | 14840.56 | 14629.6 | 11799.4 | 11799.4 | 11799.4 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N |  | Y | 2020-10-04
North | HB | UPPER LAKE | Lakeport |  |  | OPEN | 117144380 | POLE_BROK_REPL - 9707 WITTER SRINGS RD @ | 35208961 |  |  | STS-POLE_BROK_REPL - 9707 WITTER SRINGS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 39.168 | -122.9669 |  | TIER 2 | 134 | 04287-1101, UPPER LAKE | S220 | 579 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102161035 | RELW OH PRI INSP REMT ESTR FMOB FSRP TER2 | Pole |  |  | REQD | [17 empty] | 2019-05-02 | 2020-05-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | ENENG |  | 042871101 | 1 | 807.6 | 64.8 | 271.5 | 271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | UPPER LAKE | Lakeport |  |  | OPEN | 117205681 | POLE_DECA_REPL - 12134 ELK MTN RD @ 1S U | 35202571 |  |  | STS-POLE_DECA_REPL - 12134 ELK MTN RD @ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2139 | -122.9141 |  | TIER 2 | 134 | 04287-1101, UPPER LAKE | R23 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 32.1 | 32.1 |  |  | 0 | 32.1 | 32.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102160551 | RELW OH PRI INSP CLR JPOL ESTR BTKA FMOB TER2 FSRP | Pole | 2020-12-03 | 2021-01-23 | COMP | 2020-12-03 | [16 empty] | 2019-05-09 | 2020-05-09 | 2020-10-09 | 2020-10-09 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042871101 | 16070.8 | 1793.7 | 1477.6 | -271.5 | -271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | WHITETHORN | Garberville |  |  | OPEN | 114840337 | POLE_BROK_REPL - 9 SPANS LOAD SIDE SSD 1 | 35058331 |  |  | T2 REPL POLE 9 LS SSD 1510 OAKRIDGE RD | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.126 | -123.8401 |  | TIER 2 | 49 | 19222-1102, GARBERVILLE | EE1513 | 1510 | Y | 311 |  |  |  |  | Returned | Order Operation | [6 empty] | 35.8 | 35.8 |  |  | 4 | 34.8 | 34.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100985498 | POHW OH PRI CREW CLR JPOL REMT NOAC ESTR GO XMPT XDOC TER2 | Pole | 2019-01-24 | 2019-09-23 | COMP | 2019-01-24 |  |  | 2020-06-30 | 2020-06-30 | [12 empty] | 2018-07-18 | 2019-07-18 | 2019-10-15 | 2019-10-15 | Q1 Work Plan | 2019-02-28 | EEI |  | 192221102 | 26155.3 | 5303.7 |  |  |  | 931.9 |  | 931.9 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | WHITETHORN | Garberville |  |  | OPEN | 115098548 | REPL POLE:4W/O 6S/O HUNTERS CABIN(WAGNER | 35064151 |  |  | STS-REPL POLE:4W/O 6S/O HUNTERS CABIN(WA | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.0585 | -123.8793 |  | TIER 2 | 99 | 19222-1101, GARBERVILLE | GG14 |  | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 51.8 | 51.8 |  |  | 25 | 26.8 | 26.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100987868 | POHW OH TNT TER2 | Pole | 2019-05-07 | 2019-05-07 | COMP | 2019-05-07 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-10-29 | 2019-10-29 | 2021-05-31 | 2021-05-31 | Q1 Work Plan | 2019-07-01 | EEI |  | 192221101 | 22897.54 | 17187.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | WHITETHORN | Garberville |  |  | OPEN | 115098563 | POLE_DECA_REPL - 8E/O 6S/O HUNTERS CABIN | 35064153 |  |  | GC-REPL POLE:8E/O 6S/O HUNTERS CABIN (W | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2019-12-31 | Renew Permit | 40.0619 | -123.8575 |  | TIER 2 | 99 | 19222-1101, GARBERVILLE | FF14 |  | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 51 | 51 |  |  | 12 | 42.5 | 42.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100987828 | POHW OH TNT TER2 | Pole | 2019-04-09 | 2019-04-09 | COMP | 2019-04-09 |  |  | 2019-04-09 | 2019-04-09 | [12 empty] | 2018-10-29 | 2019-10-29 |  | 2019-10-29 | Q1 Work Plan | 2019-07-01 | EEI |  | 192221101 | 18725.24 | 9346.2 | 235.1 | 235.1 | 235.1 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | WILLITS | Willits |  |  | OPEN | 117072146 | POLE_DECA_REPL - #1N #2SE 99 N LENORE ST | 35215461 |  |  | STS-POLE_DECA_REPL - #1N #2SE 99 N LENOR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.4149 | -123.3468 |  | TIER 2 | 138 | 04266-1103, WILLITS | N1204 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102170633 | OH SERV RESD FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042661103 | 1 | 233.7 | 233.7 | 233.7 | 233.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | OPEN | 117113761 | POLE_DECA_REPL - 591 SEQUOIA BL W/TRANS | 35214883 |  |  | STS-POLE_DECA_REPL - 591 SEQUOIA BL W/TR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 39.4096 | -123.3633 |  | TIER 2 | 416 | 04266-1102, WILLITS | N1202 | 3785 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102171736 | RELW OH PRI CLR JPOL RESD ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-28 | 2020-04-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042661102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | OPEN | 117115169 | POLE_DECA_REPL - R/O 100 EASY ST W/TRANS | 35168632 |  |  | STS-POLE_DECA_REPL - R/O 100 EASY ST W/T | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.4108 | -123.3622 |  | TIER 2 | 416 | 04266-1102, WILLITS | N1202 | 3781 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102171512 | RELW OH PRI CLR JPOL RESD ESTR REAR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-28 | 2020-04-28 | 2020-05-31 | 2020-05-31 | 2021 CBP Plan | 2021-02-28 | QUES |  | 042661102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | OPEN | 117127265 | POLE_DECA_REPL - #1W #1N 60 MAIN ST (HWY | 35215021 |  |  | STS-POLE_DECA_REPL - #1W #1N 60 MAIN ST | UNSE | UNSE HOLD | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.4137 | -123.3564 |  | TIER 2 | 416 | 04266-1102, WILLITS | N1203 | 9607 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102171350 | RELW OH PRI CLR ESTR REAR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042661102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | OPEN | 117130402 | POLE_DECA_REPL - A/F ENTRANCE 796 RAILRO | 35215877 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.403 | -123.3486 |  | TIER 2 | 416 | 04266-1102, WILLITS | N1209 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102170380 | RELW OH SEC REMT JAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042661102 | 1 | 394.8 | 394.8 | 394.8 | 394.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | OPEN | 117275357 | POLE_DECA_REPL - #1W A/F 1100 EXLEY ST W | 35215389 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 39.416 | -123.3717 |  | TIER 2 | 416 | 04266-1102, WILLITS | M12 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102302344 | RELW OH PRI JPOL RESD FIRE TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-20 | 2020-05-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042661102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | Willits | Willits |  |  | OPEN | 117690892 | POLE _ BROK _ REPL_#3E #1N E COMMERCIAL | 35216323 |  |  | STS-POLE _ BROK _ REPL_#3E #1N E COMMERC | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 39.414 | -123.3457 |  | TIER 2 | 138 | 04266-1103, WILLITS | N1204 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102170620 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042661103 | 1 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | OPEN | 117691042 | POLE_DECA_REPL - 26 S/E/O 41401 HWY 101 | 35216327 |  |  | STS-POLE_DECA_REPL - 26 S/E/O 41401 HWY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.6357 | -123.426 |  | TIER 2 | 216 | 04268-1102, LAYTONVILLE | I10 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102196098 | RELW OH PRI ESTR USA TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042681102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | COMP | 117093912 | POLE_DECA_REPL - #1N/O ENTRANCE 23785 RE | 35132757 |  |  | STS-POLE_DECA_REPL - #1N/O ENTRANCE 2378 | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-11-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2020-12-31 | No Action | 39.4374 | -123.3174 |  | TIER 2 | 138 | 04266-1103, WILLITS | M13 | 696 | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 27.8 | 27.8 |  |  | 6.5 | 26.8 | 26.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102193380 | RELW OH PRI INSP COMP RESD REMT BTKA CCNT SCOP SCPA FMOB TER2 | Pole | 2020-03-24 | 2020-06-23 | COMP | 2020-03-24 | COMP | 2021-01-08 | 2020-06-23 | 2020-06-23 | [11 empty] | 2021-01-13 | 2021-01-08 | 2019-10-24 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-01-03 | EEI |  | 042661103 | 15551.2 | 27043.2 | 5039.8 | 3318.6 | 3318.6 | 466.6 |  | 466.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | HB | WILLITS | Willits |  |  | COMP | 117134977 | POLE_DECA_REPL - #1S DELLA AV ON VIOLA S | 35132787 |  |  | OCGC STS-POLE_DECA_REPL -#1S DELLA AV ON | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2020-12-31 | No Action | 39.3975 | -123.358 |  | TIER 2 | 103 | 04266-1104, WILLITS | N1212 |  | Y | 311 |  |  | 2021-01-11 | 2021-01-11 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 50 | 50 |  |  | 38 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102169627 | COMP JPOL RELW OH PRI RESD ESTR CPGG FMOB TER2 PRTO | Pole | 2020-05-12 | 2020-08-24 | COMP | 2020-05-12 | COMP | 2021-01-11 | 2020-08-24 | 2020-08-24 | [11 empty] | 2021-01-11 | 2021-01-11 | 2020-05-01 |  | 2020-05-01 | 2021 CBP Plan | 2020-01-03 | EEI |  | 042661104 | 13596.81 | 11308.8 | 9911.4 | 9911.4 | 9911.4 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | COMP | 117152595 | POLE_BROK_REPL - #2E 21290 LOCUST ST WIL | 35132770 |  |  | OCGCSTSRECL_BROKREPL-#2E 21290LOCUST*DIV | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.3951 | -123.354 |  | TIER 2 | 103 | 04266-1104, WILLITS | N1213 |  | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 50 | 50 |  |  | 45.25 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102169594 | RELW OH SEC COMP JPOL RESD ESTR CPGG FMOB TER2 PRTO FSRP | Pole | 2020-09-28 | 2020-11-07 | COMP | 2020-09-27 | COMP | 2021-01-06 | [13 empty] | 2021-01-06 | 2021-01-06 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | EEI |  | 042661104 | 6567.4 | 12923.3 | 11835.9 | 11835.9 | 11835.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | COMP | 117171478 | POLE_DECA_REPL - #1S #1W 20020 HOLLAND L | 35132824 |  |  | OCGCSTSPOLE_DECA_REPL-#1S #1W20020 HOLLA | MAPP | MAPP SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.3767 | -123.3392 |  | TIER 2 | 103 | 04266-1104, WILLITS | N12 |  | Y | 311 |  |  | 2021-02-08 07:00 | 2021-02-08 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 20.1 | 20.1 |  |  | 54.5 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102172382 | RELW OH SEC COMP JPOL RESD ESTR CPGG PRTO REAR FMOB TER2 | Pole | 2020-06-01 | 2020-08-04 | COMP | 2020-06-01 | COMP | 2021-02-08 | 2020-06-04 | 2020-06-04 | [11 empty] | 2021-02-10 | 2021-02-08 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-12-31 | EEI |  | 042661104 | 8550.56 | 5063.3 | 3898.8 | 219.2 | 219.2 | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | COMP | 117178170 | POLE_DECA_REPL - #2 ON LINE E/O HOUSE @ | 35132827 |  |  | OCGCSTSPOLE_DECA_REPL-#2 ONLINE E/O HOUS | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.3727 | -123.3383 |  | TIER 2 | 103 | 04266-1104, WILLITS | N12 |  | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 17.1 | 17.1 |  |  | 54 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102172626 | RELW OH PRI COMP JPOL RESD ESTR CPGD FMOB TER2 PRTO | Pole | 2020-07-23 | 2020-08-30 | COMP | 2020-07-23 | COMP | 2021-02-17 | 2020-06-04 | 2020-06-04 | [11 empty] | 2021-02-19 | 2021-02-17 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-10-31 | EEI |  | 042661104 | 9826.34 | 5024.9 | 3674.3 | -5.3 | -5.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | OPEN | 117110304 | POLE_DECA_REPL - 498 MILL ST W/TRANS WIL | 35132709 |  |  | STS-TRAN_CORR_REPL - 498 MILL ST W/TRANS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 39.4066 | -123.3563 |  | TIER 2 | 103 | 04266-1104, WILLITS | N1208 | 34006 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 93.1 | 90.5 | 2.6 |  | 0 | 93.1 | 90.5 | 2.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102169904 | RELW OH RESD PRI CLR JPOL ESTR PROG FMOB TER2 PRTO FSRP | Pole | 2020-04-16 |  | COMP | 2020-04-16 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2019-04-27 | 2020-04-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-03 | EEI |  | 042661104 | 38293 | 411.3 | 74.8 | 74.8 | 74.8 | 291.8 |  | 291.8 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | OPEN | 117129233 | TREE_DECA_INPL - R/O 53 W OAK AVWILLITS9 | 35132780 |  |  | STS-TREE_DECA_INPL - R/O 53 W OAK AVWILL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.4048 | -123.3537 |  | TIER 2 | 103 | 04266-1104, WILLITS | N1208 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.1 | 19.1 |  |  | 0 | 19.1 | 19.1 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 102170280 | RELW OH SEC RESD ESTR FMOB TER2 PRTO FSRP | Pole | 2020-04-22 | 2021-01-17 | COMP | 2020-04-22 |  |  | 2021-01-17 | 2021-01-17 | [12 empty] | 2019-04-30 | 2020-04-30 | 2020-09-09 | 2020-09-09 | 2021 CBP Plan | 2020-01-03 | EEI |  | 042661104 | 6883.99 | 2437.2 | 625.3 | 213.5 | 213.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | OPEN | 117178203 | +OLE_DECA_REPL - #1 ON LINE E/O HOUSE @ | 35132828 |  |  | OCGCSTSPOLE_DECA_REPL-#1 ONLINE E/O HOUS | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.3725 | -123.3389 |  | TIER 2 | 103 | 04266-1104, WILLITS | N12 | 8679 | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | [6 empty] | 40.9 | 40.9 |  |  | 47.5 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102172623 | RELW OH PRI JPOL REMT ESTR FMOB TER2 PRTO | Pole | 2020-03-10 | 2020-04-04 | COMP | 2020-03-10 | COMP | 2021-02-17 | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-01-03 | EEI |  | 042661104 | 18259.86 | 7441.1 | 3274.9 | -7.9 | -7.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | OPEN | 117330014 | POLE_DECA_REPL - 26790 HWY 101 1PEWILLIT | 35132887 |  |  | STS-POLE_DECA_REPL - 26790 HWY 101 1PEWI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.4597 | -123.3513 |  | TIER 2 | 138 | 04266-1103, WILLITS | M12 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 27.7 | 27.7 |  |  | 0 | 27.7 | 27.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102211369 | RELW OH PRI CLR JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-04-15 | 2020-06-18 | COMP | 2020-03-05 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-28 | 2020-05-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-03 | EEI |  | 042661103 | 27345.15 | 1816 | -3.9 | -3.9 | -3.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | OPEN | 117340032 | POLE_DECA_REPL - #3E/O HOUSE 5320 BERRY | 35149785 |  |  | STS-POLE_DECA_REPL - #3E/O HOUSE 5320 BE | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.4304 | -123.2748 |  | TIER 2 | 138 | 04266-1103, WILLITS | M14 |  | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 47.1 | 47.1 |  |  | 0 | 47.1 | 47.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102192456 | RELW OH PRI CLR JPOL REMT NOAC ESTR GO PRTO FMOB TER2 | Pole | 2020-11-12 | 2020-11-12 | COMP | 2020-06-02 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-29 | 2020-05-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-31 | TRC |  | 042661103 | 29711.11 | 3038.2 | 1350.7 | 1350.7 | 1350.7 | 88.6 |  | 88.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLITS | Willits |  |  | OPEN | 119598248 | POLE_DECA_REPL - #2 W/O PEPPERWOO WAY/ON | 35192802 |  |  | GC-POLE_DECA_REPL - #2 W/O PEPPERWOO WA | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.4058 | -123.3718 |  | TIER 2 | 103 | 04266-1104, WILLITS | N12 | 7397 | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 31.2 | 31.2 |  |  | 0 | 31.2 | 31.2 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 102193062 | RELW OH PRI INSP JPOL RESD FIRE SPCR SWRK ESTR BTKA REAR USA FMOB TER2 | Pole | 2020-11-21 | 2020-12-23 | INPR | 2020-11-21 |  |  | 2020-11-23 | 2020-11-23 | [12 empty] | 2020-08-11 | 2020-11-11 |  | 2020-11-11 | B-tag addition 8/12/2020 |  | Santa Rosa |  | 042661104 | 14411.74 | 1828 | 1027.4 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Tag Duration Set Inappropriate For Work | Y | 2020-08-18
North | HB | WILLOW CREEK | Willow Creek |  |  | OPEN | 116733063 | POLE_DECA_REPL - 6S/E/O 2E/O LCO 5809 RI | 35214745 |  |  | STS-POLE_DECA_REPL - 6S/E/O 2E/O LCO 580 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.9605 | -123.6366 |  | TIER 2 | 277 | 19217-1102, WILLOW CREEK | L2025 | 5809 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100962923 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-14 | 2020-03-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192171102 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLOW CREEK | Willow Creek |  |  | OPEN | 116741576 | POLE_BROK_REPL - CO-5389 BIGGFOOT AVE 1E | 35214827 |  |  | STS-POLE_BROK_REPL - CO-5389 BIGGFOOT AV | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.9507 | -123.6232 |  | TIER 2 | 180 | 19217-1101, WILLOW CREEK | M2101 | 2905 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100969261 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-15 | 2020-03-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 192171101 | 1 | 702.6 | 702.6 | 472.9 | 472.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | WILLOW CREEK | Willow Creek |  |  | OPEN | 116751038 | POLE_DECA_REPL - 1S\O 1N\O R\O 45139 HWY | 35189884 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.908 | -123.6135 |  | TIER 2 | 126 | 19217-1103, WILLOW CREEK | N2102 |  | Y | 311 |  |  | 2021-03-12 07:00 | 2021-03-12 16:00 | Dispatched | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100962062 | RELW CLR OH PRI REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-09 | 2020-10-14 | COMP | 2020-08-31 |  |  | 2020-10-14 | 2020-10-14 | [12 empty] | 2019-03-17 | 2020-03-17 | 2020-10-14 | 2020-10-14 | B-tag addition 8/4/2020 |  | Chico |  | 192171103 | 13630.89 | 6202.5 | 3100.4 | 3100.4 | 3100.4 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Internal Timeliness - Consturction | Y | 2020-08-04
North | HB | WILLOW CREEK | Willow Creek |  |  | OPEN | 119032263 | POLE_BROK_REPL - #3N BRANNAN MOUNTAIN RD | 35220966 |  |  | STS-POLE_BROK_REPL - #3N BRANNAN MOUNTAI | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Land Enviro |  |  | 40.9462 | -123.6356 |  | TIER 2 | 180 | 19217-1101, WILLOW CREEK | M2005 | 5002 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 52.2 | 44.8 | 7.4 |  | 0 | 52.2 | 44.8 | 7.4 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100970766 | RELW OH PRI INSP ESTR FMOB TER2 | Pole | 2021-01-31 |  | COMP | 2021-01-31 | [16 empty] | 2020-05-14 | 2021-05-14 |  | 2021-05-14 | Work Plan Reconcilation (B-Tags) |  | Chico |  | 192171101 | 23876.21 | 882.9 | 882.9 | 522.5 | 522.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-07-21
North | HB | YORKVILLE | Ukiah |  |  | OPEN | 117154589 | POLE_BROK_REPL - #1W/O #1S/O ENTRANCE 19 | 35227754 |  |  | STS-POLE_BROK_REPL - #1W/O #1S/O ENTRANC | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.9474 | -123.3198 |  | TIER 2 | 184 | 04260-1101, PHILO | X13 | 1409 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103990936 | OH PRI ESTR RELW INSP CLR REMT GO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-04-30 | UNASSIGNED |  | 042601101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | HB | YORKVILLE | Ukiah |  |  | COMP | 117188999 | POLE_DECA_REPL - #1E/O #4N/O HOUSE 21669 | 35192005 |  |  | OCGC11/6 B REPL POLE #1E/O #4N/O HOUSE 2 | MAPP | MAPP SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-10-09 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.9153 | -123.2744 |  | TIER 2 | 184 | 04260-1101, PHILO | Y14 |  | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 30 | 30 |  |  | 54 | 1 | 1 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 102203706 | RELW OH PRI INSP COMP CLR REMT FIRE NOAC ESTR USA CPGG FMOB TER2 | Pole | 2020-11-21 | 2020-11-21 | REQD | 2020-11-21 | COMP | 2021-02-09 | [13 empty] | 2021-02-09 | 2021-02-09 | 2020-05-08 | 2020-11-06 | 2020-11-06 | B-tag addition 8/12/2020 |  | Santa Rosa |  | 042601101 | 13670.94 | 6160.5 | 4414.3 | 734.7 | 734.7 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-08-18
North | HB | YORKVILLE | Ukiah |  |  | COMP | 117189074 | POLE_DECA_REPL - #2E/O #4N/O HOUSE 21669 | 35218550 |  |  | OCGCSTSPOLE_DECAREPL-#2E/O #4N/O HOUSE 2 | FICL | FICL SRDY | Poles | MPP |  | 07D | Critical Work | WSIP | 6.1 |  |  | 6 |  | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.9151 | -123.2734 |  | TIER 2 | 184 | 04260-1101, PHILO | Y14 |  | Y | 311 |  |  | 2021-01-05 | 2021-01-05 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 51.9 | 51.9 |  |  | 54 | 1.9 | 1.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102212323 | RELW OH PRI INSP COMP CLR REMT FIRE NOAC ESTR USA CPGG FMOB TER2 | Pole | 2020-12-21 | 2020-12-21 | COMP | 2020-12-18 | COMP | 2021-01-05 | [13 empty] | 2021-01-05 | 2021-01-03 | 2020-05-08 |  | 2020-05-08 | Per DOT Approved Request 19097 |  | UNASSIGNED |  | 042601101 | 15638.82 | 15379.1 | 14941.1 | 14941.1 | 14941.1 |  |  |  | FRMMA/WMPMA - Electric | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2020-12-10
North | NB |  | San Rafael |  |  | COMP | 115597197 | REPL POLE C/O MAPLE ST/PINO AVE | 35069523 |  |  | REPL POLE C/O MAPLE ST/PINO AVE | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-07-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2020-12-31 | No Action | 37.8799 | -122.5383 |  | TIER 2 | 97 | 04203-1125, ALTO | VV3209 | 1256 | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 43.5 | 43.5 |  |  | 0 | 42.5 | 42.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102275615 | REGW OH COMP CCNT TER2 | Pole | 2019-04-10 | 2019-09-17 | COMP | 2019-04-10 | COMP | 2021-01-13 | 2019-09-05 | 2019-09-09 | [11 empty] | 2021-01-15 | 2021-01-13 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-04-10 | Santa Rosa |  | 042031125 | 23168.73 | 5905.2 | 4507.2 | 4251.2 | 4251.2 | 344.6 |  | 344.6 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB |  | San Rafael |  |  | COMP | 115597338 | POLE_DECA_REPL - | 35070289 |  |  | REPL POLE 236 MT VIEW AVE | FICL | FICL SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-06-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2021-02-28 | No Action | 37.9854 | -122.5133 |  | TIER 2 | 473 | 04201-1109, SAN RAFAEL | SS3322 |  | Y | 311 |  |  | 2021-01-07 | 2021-01-07 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 50.9 | 50.5 | 0.4 |  | 7.25 | 2.9 | 2.5 | 0.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102223268 | REGW OH COMP CCNT TER2 | Pole | 2019-04-09 | 2019-04-24 | COMP | 2019-04-09 | COMP | 2021-01-07 | 2020-06-03 | 2020-06-03 | [11 empty] | 2021-01-11 | 2021-01-07 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-02 | QUES |  | 042011109 | 23391.17 | 27911.7 | -572.5 | -621.7 | -621.7 | -5954.6 |  | -5954.6 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB |  | San Rafael |  |  | OPEN | 115597224 | REPL POLE R/O 2545 CENTER RD | 35069887 |  |  | REPL POLE R/O 2545 CENTER RD | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-30 | Renew Permit | 38.1114 | -122.6192 |  | TIER 2 | 174 | 04320-1101, STAFFORD | QQ3004 |  | Y | 311 |  |  | 2021-04-27 07:00 | 2021-04-27 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 45.2 | 45.2 |  |  | 0.5 | 44.7 | 44.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102230830 | REGW OH TER2 | Pole | 2019-04-25 | 2019-05-02 | COMP | 2019-04-25 |  |  | 2019-02-15 | 2019-02-19 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-02 | QUES |  | 043201101 | 34601.53 | 27854.7 | 74.8 | 74.8 | 74.8 | 3871.2 |  | 3871.2 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB |  | San Rafael |  |  | OPEN | 115597230 | REPL POLE 514 SHORELINE HWY 1S | 35069631 |  |  | REPL POLE 514 SHORELINE HWY 1S | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.8815 | -122.5383 |  | TIER 2 | 97 | 04203-1125, ALTO | VV3209 | 1256 | Y | 311 |  |  | 2021-03-20 07:00 | 2021-03-20 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 98.3 | 98.3 |  |  | 5.5 | 92.8 | 92.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102295878 | REGW OH TER2 | Pole | 2019-04-25 | 2019-10-23 | COMP | 2019-04-25 |  |  | 2019-09-24 | 2019-09-24 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-02 | Santa Rosa |  | 042031125 | 28189.93 | 11572.9 | 1664.2 | 957.6 | 957.6 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | CALISTOGA | Napa |  |  | OPEN | 116623445 | POLE_BROK_REPL - 14560 STATE HWY 128 A/F | 35149632 |  |  | STS-POLE_BROK_REPL - 14560 STATE HWY 128 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6424 | -122.7025 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE28 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.7 | 17.7 |  |  | 0 | 17.7 | 17.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219112 | RELW OH PRI GO RTRN FMOB TER2 PRTO JPOL | Pole | 2020-12-22 | 2021-02-14 | COMP | 2020-04-09 |  |  | 2020-12-22 | 2020-12-22 | [12 empty] | 2019-03-01 | 2020-03-01 |  | 2020-03-01 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 13572.11 | 2147.9 | 597.9 | 597.9 | 597.9 | 250.2 |  | 250.2 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117068509 | POLE_BROK_REPL - M/B 16701 STATE HWY 128 | 35149944 |  |  | STS-POLE_BROK_REPL - M/B 16701 STATE HWY | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 38.6301 | -122.6697 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 | 890 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 30.8 | 30.8 |  |  | 0 | 30.8 | 30.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219251 | RELW OH PRI INSP FLAG REMT FIRE TRAF ESTR BTKA USA FMOB TER2 | Pole | 2020-04-01 |  | COMP | 2020-04-01 |  |  | 2020-04-09 | 2020-04-09 | [12 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 17392.92 | 3516 |  |  |  | 655.9 |  | 655.9 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117068965 | POLE_BROK_REPL - M/B 16865 STATE HWY 128 | 35149953 |  |  | STS-POLE_BROK_REPL - M/B 16865 STATE HWY | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 38.6292 | -122.668 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 | 890 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.2 | 39.2 |  |  | 0 | 39.2 | 39.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219263 | RELW OH PRI INSP CLR JPOL REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-05-27 |  | COMP | 2020-05-27 |  |  | 2020-12-22 | 2020-12-22 | [12 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2020-07-31 | CALENG |  | 042711101 | 21971.17 | 4670 | 523.6 | 523.6 | 523.6 | 166.8 |  | 166.8 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117098197 | POLE_BROK_REPL - M/B 17104 SPENCER LN 1N | 35150014 |  |  | STS-POLE_BROK_REPL - M/B 17104 SPENCER L | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-03-31 | No Action | 38.6178 | -122.6703 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 |  | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-04 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219413 | RELW OH PRI INSP REMT FIRE FLAG ESTR BTKA FMOB TER2 | Pole | 2020-04-16 | 2020-12-22 | COMP | 2020-04-16 |  |  | 2020-12-22 | 2020-12-22 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 9165.48 | 2088.9 | 911.5 | 785.4 | 785.4 | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117098416 | POLE_BROK_REPL - 17000 SPENCER LN 1NWCAL | 35150017 |  |  | STS-POLE_BROK_REPL - 17000 SPENCER LN 1N | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-03-31 | No Action | 38.6187 | -122.6723 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 |  | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-04 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219420 | RELW OH PRI INSP JPOL REMT FIRE FLAG ESTR BTKA FMOB TER2 | Pole | 2020-04-03 | 2020-12-22 | COMP | 2020-04-03 |  |  | 2020-12-22 | 2020-12-22 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 16014.76 | 2795.4 | 1618 | 785.4 | 785.4 | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117165948 | POLE_DECA_REPL - 3120 OLD LAWLEY TOLL RD | 35149790 |  |  | STS-POLE_DECA_REPL - 3120 OLD LAWLEY TOL | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.6118 | -122.5925 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE31 | 89150 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 45.8 | 45.8 |  |  | 0 | 45.8 | 45.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102248413 | OH PRI INSP JPOL REMT FIRE FLAG ESTR GO BTKA FMOB TER2 RELW | Pole | 2021-01-15 |  | COMP | 2021-01-15 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-09-30 | CALENG |  | 042711101 | 24468.81 | 437.6 | 0 | 1467 | 1467 | 437.7 |  | 437.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117192689 | POLE_BROK_REPL - 16585 STATE HWY 128 A/F | 35149862 |  |  | STS-POLE_BROK_REPL - 16585 STATE HWY 128 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 38.6316 | -122.6727 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE2907 | 890 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29 | 29 |  |  | 0 | 29 | 29 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219242 | RELW OH PRI INSP JPOL FIRE BTKA TRAF FLAG ESTR USA FMOB TER2 | Pole | 2020-04-09 |  | COMP | 2020-04-09 |  |  | 2020-12-22 | 2020-12-22 | [12 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 20247.84 | 6155.9 | 523.6 | 523.6 | 523.6 | 697.7 |  | 697.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117193340 | POLE_DECA_REPL - R/O 3000 PALISADES RDCA | 35149865 |  |  | STS-POLE_DECA_REPL - R/O 3000 PALISADES | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 38.6024 | -122.5838 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | FF31 | 487029 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 97.6 | 96.4 | 1.2 |  | 0 | 97.6 | 96.4 | 1.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102223398 | RELW OH PRI INSP ESTR GO FMOB TER2 | Pole | 2020-05-28 | 2020-05-27 | COMP | 2020-04-03 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 21446.06 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117194445 | POLE_BROK_REPL - C/O FRANZ VALLEY RD/ ST | 35149868 |  |  | STS-POLE_BROK_REPL - C/O FRANZ VALLEY RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 38.6323 | -122.6737 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE2907 | 890 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 81.9 | 81.1 | 0.8 |  | 0 | 81.9 | 81.1 | 0.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219238 | RELW OH PRI INSP CLR JPOL RESD FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-04-16 |  | COMP | 2020-04-16 |  |  | 2020-09-17 | 2020-09-17 | [12 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 38508.9 | 6382.2 |  |  |  | 689.1 |  | 689.1 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117013044 | POLE_BROK_REPL - 1218 BENNETT LN R/OCALI | 35149864 |  |  | STS-POLE_BROK_REPL - 1218 BENNETT LN R/O | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6031 | -122.6231 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | FF30 | 4917 | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102220565 | RELW OH PRI REMT JPOL RESD COMM FIRE ESTR FMOB TER2 PRTO | Pole | 2020-06-01 | 2020-07-24 | COMP | 2020-06-01 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-04-11 | 2020-04-11 |  | 2020-04-11 | circuit based plan 2.14 | 2020-05-31 | CALENG |  | 042711101 | 12995.1 | 4631.9 | 3471.7 | 10278 | 10278 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | CALISTOGA | Napa |  |  | OPEN | 117027978 | POLE_DECA_REPL - 3265 HWY 29 W/TRANS HOU | 35149904 |  |  | STS-POLE_DECA_REPL - 3265 HWY 29 W/TRANS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6089 | -122.5957 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | F31 | 2307 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 40.4 | 40.4 |  |  | 0 | 40.4 | 40.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102313178 | RELW OH PRI INSP JPOL RESD REMT FIRE SWRK ESTR BTKA REAR USA FMOB TER2 | Pole | 2020-05-27 | 2020-06-01 | COMP | 2020-05-27 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | circuit based plan 2.14 | 2020-07-31 | CALENG |  | 042711101 | 16236.25 | 2326.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | CALISTOGA | Napa |  |  | OPEN | 117028009 | POLE_DECA_REPL - #2W 3307 HWY 29CALISTOG | 35149907 |  |  | STS-POLE_DECA_REPL - #2W 3307 HWY 29CALI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6096 | -122.5967 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | F31 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 42.4 | 42.4 |  |  | 0 | 42.4 | 42.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102313176 | RELW OH PRI INSP JPOL RESD REMT FIRE TRAF SWRK ESTR BTKA USA FMOB TER2 | Pole | 2020-04-06 | 2020-10-20 | COMP | 2020-04-06 |  |  | 2020-10-20 | 2020-10-20 | [12 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 15456.08 | 136.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117044309 | POLE_DECA_REPL - 11080 FRANZ VALLEY RD ( | 35149916 |  |  | STS-POLE_DECA_REPL - 11080 FRANZ VALLEY | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6182 | -122.6828 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 |  | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102219449 | RELW OH PRI INSP FLAG JPOL RESD FIRE TRAF ESTR BTKA USA FMOB TER2 | Pole | 2020-04-02 | 2020-08-20 | COMP | 2020-04-02 |  |  | 2020-08-20 | 2020-08-20 | [12 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117047054 | POLE_DECA_REPL - 10880 FRANZ VALLEY RD @ | 35149929 |  |  | STS-POLE_DECA_REPL - 10880 FRANZ VALLEY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6147 | -122.6857 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.5 | 32.5 |  |  | 0 | 32.5 | 32.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102219469 | RELW OH PRI INSP REMT FIRE ESTR BTKA FMOB TER2 | Pole | 2020-04-02 | 2020-08-20 | COMP | 2020-04-02 |  |  | 2020-08-20 | 2020-08-20 | [12 empty] | 2019-04-17 | 2020-04-17 |  | 2020-04-17 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117068923 | POLE_DECA_REPL - M/B 16865 STATE HWY 128 | 35149950 |  |  | STS-POLE_DECA_REPL - M/B 16865 STATE HWY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6298 | -122.669 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.8 | 20.8 |  |  | 0 | 20.8 | 20.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102219262 | RELW OH PRI INSP JPOL REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-09-14 | 2020-09-15 | COMP | 2020-04-06 |  |  | 2020-09-10 | 2020-09-10 | [12 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 14083.68 | 2778.5 |  |  |  | 510.9 |  | 510.9 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117068998 | POLE_BROK_REPL - M/B 16865 STATE HWY 128 | 35104572 |  |  | STS-POLE_BROK_REPL - M/B 16865 STATE HWY | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6293 | -122.668 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 |  | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Dispatched | Order Operation | [6 empty] | 41 | 41 |  |  | 1 | 40 | 40 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219264 | RELW OH PRI INSP REMT FIRE TRAF FLAG ESTR BTKA FMOB TER2 | Pole | 2020-01-13 | 2020-03-03 | COMP | 2019-09-17 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-04-20 | 2019-10-20 |  | 2019-10-20 | Q1 Work Plan |  | Santa Rosa |  | 042711101 | 9879.71 | 7950.3 | 174 | 174 | 174 | 407.2 |  | 407.2 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | CALISTOGA | Napa |  |  | OPEN | 117072151 | POLE_DECA_REPL - 16970 STATE HWY 128 @ H | 35149962 |  |  | REPL POLE 16970 HWY 128 W/35181201 | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6274 | -122.667 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 |  | Y | 311 |  |  | 2021-03-05 07:00 | 2021-03-05 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102219281 | SEC OH RELW INSP RESD FIRE ESTR BTKA FMOB TER2 | Pole | 2020-07-03 | 2020-08-18 | COMP | 2020-06-19 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | 2021 CBP Plan | 2020-07-31 | CALENG |  | 042711101 | 4995.25 | 2213 | 409.4 |  |  | 333.6 |  | 333.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117072349 | POLE_BROK_REPL - 17100 STATE HWY 128 3NC | 35149965 |  |  | STS-POLE_BROK_REPL - 17100 STATE HWY 128 | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.623 | -122.6635 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 |  | Y | 311 |  |  | 2021-02-19 07:00 | 2021-02-19 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 10.5 | 40.8 | 40.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219391 | RELW OH PRI INSP JPOL REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-09-18 | 2020-09-18 | COMP | 2020-04-22 |  |  | 2020-09-17 | 2020-09-17 | [12 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 15644.49 | 5001.4 | 3605 | 3258.1 | 3258.1 | 453.1 |  | 453.1 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117074155 | POLE_DECA_REPL - 17050 STATE HWY 128 (GA | 35149968 |  |  | STS-POLE_DECA_REPL - 17050 STATE HWY 128 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6256 | -122.6672 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24 | 24 |  |  | 0 | 24 | 24 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102219369 | RELW OH PRI INSP JPOL REMT FIRE ESTR BTKA FMOB TER2 | Pole | 2020-04-16 | 2020-07-23 | COMP | 2020-04-16 |  |  | 2020-04-13 | 2020-04-13 | [12 empty] | 2019-04-22 | 2020-04-22 |  | 2020-04-22 | circuit based plan 2.14 | 2020-04-10 | CALENG |  | 042711101 | 10153.67 | 1460.9 | 87 | 87 | 87 | 166.8 |  | 166.8 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | CALISTOGA | Napa |  |  | OPEN | 117082799 | POLE_DECA_REPL - 17801 STATE HWY 128 @ H | 35097238 |  |  | STS-POLE_DECA_REPL - 17801 STATE HWY 128 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6205 | -122.654 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.4 | 18.4 |  |  | 0 | 18.4 | 18.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102219706 | RELW OH PRI INSP JPOL REMT FIRE ESTR BTKA FMOB TER2 | Pole | 2020-06-11 | 2020-10-15 | COMP | 2020-06-09 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-04-23 | 2019-10-20 |  | 2019-10-20 | 2021 CBP Plan | 2020-06-08 | CALENG |  | 042711101 | 6615.76 | 64.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117083976 | POLE_BROK_REPL - 18079 STATE HWY 128 (GA | 35149982 |  |  | STS-POLE_BROK_REPL - 18079 STATE HWY 128 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6151 | -122.654 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 | 8319 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219634 | RELW OH PRI INSP CLR REMT FIRE ESTR BTKA FMOB TER2 | Pole | 2020-04-06 | 2020-05-26 | COMP | 2020-04-06 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | circuit based plan 2.14 | 2020-04-10 | CALENG |  | 042711101 | 14730.45 | 3771.1 | 194.6 |  |  | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | CALISTOGA | Napa |  |  | OPEN | 117098627 | POLE_DECA_REPL - 16850 SPENCER LN 1ECALI | 35150020 |  |  | STS-POLE_DECA_REPL - 16850 SPENCER LN 1E | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6197 | -122.6743 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15 | 15 |  |  | 0 | 15 | 15 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102219422 | RELW OH PRI INSP JPOL REMT FIRE FLAG ESTR BTKA FMOB TER2 | Pole | 2020-04-17 | 2020-10-26 | COMP | 2020-04-17 |  |  | 2020-10-26 | 2020-10-26 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 11411.39 | 767.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117098789 | POLE_DECA_REPL - 16800 SPENCER LN 1ECALI | 35151092 |  |  | STS-POLE_DECA_REPL - 16800 SPENCER LN 1E | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 38.6205 | -122.6759 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.7 | 15.7 |  |  | 0 | 15.7 | 15.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102219424 | RELW OH SEC INSP JPOL REMT FIRE FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-10-27 | 2020-11-10 | COMP | 2020-05-05 |  |  | 2020-10-26 | 2020-10-26 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 9310.01 | 256 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117099088 | POLE_BROK_REPL - M/B 16700 SPENCER LN 1S | 35150024 |  |  | STS-POLE_BROK_REPL - M/B 16700 SPENCER L | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 38.6209 | -122.6768 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 17.9 | 17.9 |  |  | 0 | 17.9 | 17.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219430 | RELW OH PRI INSP JPOL REMT FIRE ESTR BTKA FMOB TER2 | Pole | 2020-06-23 | 2020-10-12 | COMP | 2020-04-09 |  |  | 2020-10-12 | 2020-10-15 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 7430.97 | 287.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117099229 | POLE_DECA_REPL - M/B 16700 SPENCER LN 1W | 35150027 |  |  | STS-POLE_DECA_REPL - M/B 16700 SPENCER L | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6213 | -122.6774 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.5 | 16.5 |  |  | 0 | 16.5 | 16.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102219433 | RELW OH PRI INSP CUST JPOL REMT FIRE FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-09-14 | 2020-09-30 | COMP | 2020-04-06 |  |  | 2020-09-11 | 2020-09-11 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 10995.88 | 623.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117099347 | POLE_DECA_REPL - 16670 SPENCER LN W/TRAN | 35150030 |  |  | STS-POLE_DECA_REPL - 16670 SPENCER LN W/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6219 | -122.6786 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 | 8355 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 40.8 | 39.2 | 1.6 |  | 0 | 40.8 | 39.2 | 1.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102219436 | RELW OH PRI INSP CLR JPOL REMT FIRE FLAG ESTR BTKA FMOB TER2 | Pole | 2020-10-07 | 2020-11-03 | COMP | 2020-04-17 |  |  | 2020-09-11 | 2020-09-11 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 22190.4 | 1782 |  |  |  | 265.9 |  | 265.9 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117166195 | POLE_BROK_REPL - 3093 OLD LAWLEY TOLL RD | 35149793 |  |  | STS-POLE_BROK_REPL - 3093 OLD LAWLEY TOL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-02-20 | Renew Permit | 38.6114 | -122.5922 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE31 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26 | 26 |  |  | 0 | 26 | 26 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102248411 | RELW OH PRI INSP JPOL REMT FIRE FLAG ESTR BTKA USA SMTR FMOB TER2 | Pole | 2020-04-13 | 2020-10-26 | COMP | 2020-04-13 |  |  | 2020-10-26 | 2020-10-26 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 15564.4 | 108.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117166327 | POLE_DECA_REPL - 3082 OLD LAWLEY TOLL RD | 35149797 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-02-20 | Renew Permit | 38.6104 | -122.5917 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE31 |  | Y | 311 |  |  | 2021-02-27 07:00 | 2021-02-27 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102248409 | RELW OH PRI INSP FLAG JPOL REMT FIRE ESTR GO BTKA USA FMOB TER2 | Pole | 2020-04-20 | 2020-10-26 | COMP | 2020-04-20 |  |  | 2020-10-26 | 2020-10-26 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 13504.9 | 1721.5 | 1174.5 |  |  | 62.8 |  | 62.8 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117169224 | POLE_DECA_REPL - 94515CALISTOGA94515 | 35149810 |  |  | STS-POLE_DECA_REPL - 94515CALISTOGA94515 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6177 | -122.6073 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE31 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.8 | 23.8 |  |  | 0 | 23.8 | 23.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103593374 | RELW OH PRI INSP JPOL REMT FIRE ESTR BTKA FMOB TER2 | Pole | 2020-04-20 | 2020-08-13 | COMP | 2020-04-20 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 11338.55 | 88.7 |  |  |  | 88.7 |  | 88.7 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117196378 | POLE_BROK_REPL - 3452 HWY 128 @ 2NCALIST | 35149895 |  |  | STS-POLE_BROK_REPL - 3452 HWY 128 @ 2NCA | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6019 | -122.6232 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | FF30 |  | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102220563 | RELW OH PRI INSP JPOL FIRE ESTR FMOB TER2 | Pole | 2020-07-15 | 2020-08-28 | COMP | 2020-05-26 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | circuit based plan 2.14 | 2020-07-31 | CALENG |  | 042711101 | 23474.51 | 3670.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | CALISTOGA | Napa |  |  | OPEN | 117196518 | POLE_BROK_REPL - 12207 FRANZ VALLEY RD A | 35149898 |  |  | STS-POLE_BROK_REPL - 12207 FRANZ VALLEY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-03-31 | No Action | 38.6306 | -122.6751 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE2907 |  | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-04 16:00 | Scheduled | CLICK | [6 empty] | 56.1 | 56.1 |  |  | 0 | 56.1 | 56.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219603 | RELW OH PRI INSP JPOL FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-04-06 | 2020-12-22 | COMP | 2020-04-06 |  |  | 2020-12-22 | 2020-12-22 | [12 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 9782.8 | 2610.4 | 1521.6 | 1521.6 | 1521.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117221605 | POLE_DECA_REPL - 3149 OLD LAWLEY TOLL RD | 35149980 |  |  | STS-POLE_DECA_REPL - 3149 OLD LAWLEY TOL | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-02-20 | Renew Permit | 38.6135 | -122.593 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE3117 | 89150 | Y | 311 |  |  | 2021-03-01 07:00 | 2021-03-01 16:00 | Dispatched | CLICK | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102248416 | RELW PRI OH INSP JPOL REMT FIRE FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-04-23 | 2020-10-26 | COMP | 2020-04-23 |  |  | 2020-10-26 | 2020-10-26 | [12 empty] | 2019-05-13 | 2020-05-13 |  | 2020-05-13 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 16194.74 | 1787.5 | 683.1 |  |  | 533.5 |  | 533.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117222222 | REPL POLE HWY 128@IDA CLAYTON | 35104808 |  |  | CTP REPL POLE HWY 128@IDA CLAYTON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6334 | -122.6757 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE2907 | 8339 | Y | 311 |  |  | 2021-03-03 07:00 | 2021-03-03 16:00 | Scheduled | CLICK | [6 empty] | 66.5 | 66.5 |  |  | 0 | 66.5 | 66.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219220 | RELW OH PRI INSP JPOL FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-10-27 | 2020-12-21 | COMP | 2020-10-27 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-13 | 2019-11-13 |  | 2019-11-13 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 042711101 | 16575.62 | 436.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117223396 | POLE_BROK_REPL - C/O FRANZ VALLEY RD/ ST | 35149994 |  |  | STS-POLE_BROK_REPL - C/O FRANZ VALLEY RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6329 | -122.6748 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE2907 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 19.4 | 19.4 |  |  | 0 | 19.4 | 19.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219236 | RELW OH REMT PRI INSP JPOL FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-05-05 | 2020-09-10 | COMP | 2020-05-05 |  |  | 2020-09-10 | 2020-09-10 | [12 empty] | 2019-05-13 | 2020-05-13 |  | 2020-05-13 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 13470.09 | 933.5 |  |  |  | 255.4 |  | 255.4 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117223495 | POLE_BROK_REPL - 5223 OLD LAWLEY TOLL RD | 35149997 |  |  | STS-POLE_BROK_REPL - 5223 OLD LAWLEY TOL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-02-20 | Renew Permit | 38.616 | -122.5938 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE3117 | 89150 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 78.4 | 78.4 |  |  | 0 | 78.4 | 78.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102248429 | RELW OH PRI INSP CLR JPOL FLAG RESD REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-06-25 | 2020-10-26 | COMP | 2020-06-25 |  |  | 2020-10-26 | 2020-10-26 | [12 empty] | 2019-05-13 | 2020-05-13 |  | 2020-05-13 | 2021 CBP Plan | 2020-07-31 | CALENG |  | 042711101 | 36696.74 | 818.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117229000 | POLE_BROK_REPL - 12207 FRANZ VALLEY RD A | 35150031 |  |  | STS-POLE_BROK_REPL - 12207 FRANZ VALLEY | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 38.63 | -122.6756 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE2907 |  | Y | 311 |  |  | 2021-03-05 07:00 | 2021-03-05 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219602 | RELW OH PRI JPOL REMT FIRE FLAG ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-10-27 | 2020-11-30 | COMP | 2020-04-13 |  |  | 2020-10-26 | 2020-10-26 | [12 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 12321.18 | 1301.6 | 789.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117229095 | POLE_BROK_REPL - 12207 FRANZ VALLEY RD A | 35150034 |  |  | STS-POLE_BROK_REPL - 12207 FRANZ VALLEY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6295 | -122.676 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE2907 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 16.5 | 16.5 |  |  | 0 | 16.5 | 16.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219601 | OH PRI JPOL REMT FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO RELW | Pole | 2020-09-15 | 2020-10-29 | COMP | 2020-04-10 |  |  | 2020-09-11 | 2020-09-11 | [12 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 10244.45 | 256.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117230118 | POLE_DECA_REPL - 3149 OLD LAWLEY TOLL RD | 35150042 |  |  | STS-POLE_DECA_REPL - 3149 OLD LAWLEY TOL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6139 | -122.5907 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE3117 |  | Y | 311 |  |  | 2021-03-16 07:00 | 2021-03-16 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102248421 | RELW OH SEC INSP JPOL RESD REMT FIRE ESTR REAR USA FMOB TER2 | Pole | 2020-05-07 | 2020-08-14 | COMP | 2020-05-07 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 7515.21 | 334.1 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117230206 | POLE_DECA_REPL - 3149 OLD LAWLEY TOLL RD | 35150043 |  |  | STS-POLE_DECA_REPL - 3149 OLD LAWLEY TOL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6142 | -122.5908 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE3117 | 606388 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 36.8 | 36.8 |  |  | 0 | 36.8 | 36.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102248422 | RELW INSP OH PRI CLR JPOL RESD REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-04-09 | 2020-10-23 | COMP | 2020-04-09 |  |  | 2020-10-23 | 2020-10-23 | [12 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 20357.98 | 394.5 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117246941 | POLE_DECA_REPL - 3214 OLD LAWLEY TOLL RD | 35150064 |  |  | STS-POLE_DECA_REPL - 3214 OLD LAWLEY TOL | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-02-20 | Renew Permit | 38.6155 | -122.5939 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE3117 |  | Y | 311 |  |  | 2021-03-01 07:00 | 2021-03-01 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103160031 | RELW GO OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-04-20 | 2020-10-23 | COMP | 2020-04-20 |  |  | 2020-10-23 | 2020-10-23 | [12 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 8125.94 | 804.9 | 310.3 |  |  | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117263862 | POLE_BROK_REPL - 1SE/O 2490 SILVERADO TR | 35150067 |  |  | STS-POLE_BROK_REPL - 1SE/O 2490 SILVERAD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5938 | -122.5803 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | FF3109 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 24.1 | 24.1 |  |  | 0 | 24.1 | 24.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102225611 | RELW OH PRI JPOL REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-04-30 | 2020-10-01 | COMP | 2020-04-30 |  |  | 2020-10-01 | 2020-10-01 | [12 empty] | 2019-05-17 | 2020-05-17 | 2024-05-15 | 2024-05-15 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 15140.37 | 2395.5 |  |  |  | 459.1 |  | 459.1 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117364136 | POLE_DECA_REPL - 2490 STATE HWY 29CALIS | 35149788 |  |  | STS-POLE_DECA_REPL - 2490 STATE HWY 29C | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5945 | -122.5809 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | FF3109 | 445 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.6 | 31.6 |  |  | 0 | 31.6 | 31.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102223426 | RELW OH PRI INSP JPOL RESD FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-05-15 | 2020-10-15 | COMP | 2020-05-15 |  |  | 2020-10-01 | 2020-10-01 | [12 empty] | 2019-05-31 | 2020-05-31 |  | 2020-05-31 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 20397.39 | 2641.8 | 272.4 | 257.4 | 257.4 | 255.4 |  | 255.4 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117691227 | POLE _ BROK _ REPL_3452 HWY 128 @ 2N 1E | 35149920 |  |  | STS-POLE _ BROK _ REPL_3452 HWY 128 @ 2N | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6022 | -122.6217 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | FF30 |  | Y | 311 |  |  |  |  | Returned | Order Operation | [6 empty] | 61 | 61 |  |  | 0 | 61 | 61 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102220566 | RELW OH PRI ESTR TER2 PRTO | Pole | 2020-04-02 | 2020-05-28 | COMP | 2020-04-02 |  |  | 2020-07-17 | 2020-07-17 | [12 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | circuit based plan 2.14 | 2020-04-10 | CALENG |  | 042711101 | 25838.85 | 3482 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | CALISTOGA | Napa |  |  | OPEN | 117890829 | POLE_BROK_REPL - 12207 FRANZ VALLEY RD A | 35150035 |  |  | STS-POLE_BROK_REPL - 12207 FRANZ VALLEY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 38.6312 | -122.6746 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE2907 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 21.2 | 21.2 |  |  | 0 | 21.2 | 21.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219605 | RELW OH PRI JPOL RESD REMT FIRE TRAF FLAG ESTR BTKA OTHR USA FMOB TER2 | Pole | 2020-11-04 | 2020-11-06 | COMP | 2020-04-16 |  |  | 2020-10-26 | 2020-10-26 | [12 empty] | 2019-09-17 | 2020-09-17 |  | 2020-09-17 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 13177.56 | 1908.9 |  |  |  | 214.2 |  | 214.2 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | CALISTOGA | Napa |  |  | OPEN | 117005818 | POLE_DECA_REPL - 1N/O 3582 HWY 128[OF HO | 35093348 |  |  | STS-POLE_DECA_REPL - 1N/O 3582 HWY 128[O | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6045 | -122.6271 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | FF30 |  | Y | 311 |  |  | 2021-06-30 06:00 | 2021-06-30 16:00 | Scheduled | CLICK | [6 empty] | 34 | 34 |  |  | 0 | 34 | 34 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102220684 | RELW OH PRI JPOL SPCR REMT FIRE NOAC ESTR FMOB PRTO TER2 | Pole | 2019-08-07 | 2019-08-22 | COMP | 2019-08-07 |  |  | 2019-08-20 | 2019-08-20 | [12 empty] | 2019-04-10 | 2019-10-07 |  | 2019-10-07 | Q1 Work Plan |  | Concord |  | 042711101 | 16776.2 | -3133.1 |  |  |  | 130.2 |  | 130.2 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | CALISTOGA | Napa |  |  | OPEN | 117097735 | POLE_BROK_REPL - 17104 SPENCER LN (HOUSE | 35150011 |  |  | STS-POLE_BROK_REPL - 17104 SPENCER LN (H | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6168 | -122.6714 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.7 | 15.7 |  |  | 0 | 15.7 | 15.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102219731 | RELW OH PRI FIRE INSP JPOL REMT ESTR BTKA FMOB TER2 | Pole | 2020-04-20 | 2020-06-16 | COMP | 2020-04-20 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | circuit based plan 2.14 | 2020-04-10 | CALENG |  | 042711101 | 7192.42 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | GREENBRAE | San Rafael |  |  | OPEN | 117208060 | POLE_DECA_REPL - 2 FERN RD GREENBRAE | 35215886 |  |  | STS-POLE_DECA_REPL - 2 FERN RD GREENBRAE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land JointPole |  |  | 37.9429 | -122.5487 |  | TIER 2 | 31 | 04201-1107, SAN RAFAEL | TT3223 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102230910 | RELW OH SEC JPOL MINR RESD FIRE JAR TRAF FLAG BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042011107 | 1 | 1668 | 261 | 261 | 261 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | GREENBRAE | San Rafael |  |  | OPEN | 117215935 | POLE_DECA_REPL - R/O 2 BUCKEYE WAY GREEN | 35214735 |  |  | STS-POLE_DECA_REPL - R/O 2 BUCKEYE WAY G | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro JointPole |  |  | 37.9532 | -122.558 |  | TIER 2 | 31 | 04201-1107, SAN RAFAEL | TT3217 | 4189 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102234166 | RELW OH PRI ESTR RESD GO BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-11 | 2020-05-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042011107 | 1 | 945.8 | 945.8 | 945.8 | 945.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | HEALDSBURG | Napa |  |  | OPEN | 117234420 | POLE_DECA_REPL - M/B 10880 FRANZ VALLEY | 35150055 |  |  | REPL POLE 10880 FRANZ VLY W/35183176 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.6151 | -122.6886 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE28 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.7 | 33.7 |  |  | 0 | 33.7 | 33.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102219510 | RELW OH PRI ESTR GO FMOB TER2 PRTO | Pole | 2020-09-11 |  | COMP | 2020-09-11 | [16 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 042711101 | 19863.38 | 920.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | HEALDSBURG | Napa |  |  | OPEN | 117231653 | POLE_DECA_REPL - 13856 STATE HWY 128 @ H | 35150048 |  |  | STS-POLE_DECA_REPL - 13856 STATE HWY 128 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.65 | -122.7104 |  | TIER 2 | 35 | 04271-1101, CALISTOGA | EE28 | 791 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 27.8 | 27.8 |  |  | 0 | 27.8 | 27.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102219079 | RELW OH PRI ESTR GO PRTO FMOB TER2 | Pole | 2020-05-18 | 2020-09-14 | COMP | 2020-05-18 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 042711101 | 14362.59 | 498 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | INVERNESS | San Rafael |  |  | OPEN | 117253337 | POLE_DECA_REPL - #2W/O A/F 13275 SIR FRA | 35215162 |  |  | STS-POLE_DECA_REPL - #2W/O A/F 13275 SIR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.1092 | -122.8706 |  | TIER 2 | 488 | 04229-1101, OLEMA | PP2422 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102293997 | RELW OH PRI JPOL FLAG ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042291101 | 1 | 80.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | INVERNESS | San Rafael |  |  | OPEN | 117253342 | POLE_BROK_REPL - A/F #2W/O A/F 13275 SIR | 35215167 |  |  | STS-POLE_BROK_REPL - A/F #2W/O A/F 13275 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.109 | -122.8708 |  | TIER 2 | 488 | 04229-1101, OLEMA | PP2422 | 602 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102293998 | RELW OH PRI JPOL FLAG ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-03-18 | 2021-03-18 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042291101 | 1 | 232.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | INVERNESS | San Rafael |  |  | OPEN | 117254139 | POLE_DECA_REPL - A/F 142120 SIR FRANCIS | 35215172 |  |  | STS-POLE_DECA_REPL - A/F 142120 SIR FRAN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.1092 | -122.8836 |  | TIER 2 | 488 | 04229-1101, OLEMA | PP2421 | 602 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102293915 | OH RELW PRI JPOL RESD FIRE TRAF FLAG ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042291101 | 1 | 174 | 174 | 174 | 174 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | LARKSPUR | San Rafael |  |  | OPEN | 117208059 | POLE_DECA_REPL - 77 BRIAR RD LARKSPUR | 35214632 |  |  | STS-POLE_DECA_REPL - 77 BRIAR RD LARKSPU | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.944 | -122.548 |  | TIER 2 | 31 | 04201-1107, SAN RAFAEL | TT3223 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102230906 | RELW OH SEC JPOL RESD FIRE TRAF FLAG ESTR BTKA FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042011107 | 1 | 80.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | Larkspur | San Rafael |  |  | OPEN | 118260958 | POLE_BROK_REPL - 1 MURRAY AVE-GUY POLELa | 35202701 |  |  | STS-POLE_BROK_REPL - 1 MURRAY AVE-GUY PO | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.9462 | -122.5459 |  | TIER 2 | 31 | 04201-1107, SAN RAFAEL | TT3223 | 10062 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.8 | 37.8 |  |  | 0 | 37.8 | 37.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103148624 | RELW SERV OH JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-08 |  | COMP | 2020-12-08 | [16 empty] | 2019-12-11 | 2020-12-11 | 2020-10-18 | 2020-10-18 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042011107 | 19234.17 | 1331.3 | 518.3 | -543 | -543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | MARSHALL | San Rafael |  |  | OPEN | 114848522 | REPL POLE 19180 HIGHWAY 1 MARSHALL | 35052243 |  |  | REPL POLE 19180 HIGHWAY 1 MARSHALL | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1521 | -122.8876 |  | TIER 2 | 488 | 04229-1101, OLEMA | OO23 | 3473 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 91 | 91 |  |  | 1 | 90 | 90 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102294051 | REGW OH PRI INSP JPOL PUBL RESD FIRE ESTR BTKA REAR USA PROG FMOB TER2 | Pole | 2019-02-20 | 2019-02-20 | COMP | 2019-02-20 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-08-02 | 2019-08-02 |  | 2019-08-02 | Q1 Work Plan | 2019-02-28 | EEI |  | 042291101 | 77523.43 | 17358 | -9614.1 | 1885.9 | 1885.9 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | MILL VALLEY | San Rafael |  |  | OPEN | 117060727 | POLE_DECA_REPL - 43 LOMITA DR MILL VALLE | 35215302 |  |  | STS-POLE_DECA_REPL - 43 LOMITA DR MILL V | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.9074 | -122.5192 |  | TIER 2 | 1398 | 04203-1123, ALTO | UU3316 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102234193 | RELW OH PRI INSP JPOL RESD FIRE TRAF FLAG USA ESTR GO BTKA PROG FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-18 | 2020-04-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042031123 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | Mill Valley | San Rafael |  |  | OPEN | 117772263 | POLE_DECA_REPL - 482 GREEN GLEN WAY,Mill | 35202461 |  |  | STS-POLE_DECA_REPL - 482 GREEN GLEN WAY, | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 37.8755 | -122.5358 |  | TIER 2 | 614 | 04203-1120, ALTO | VV3214 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102277268 | RELW OH TNT JPOL TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-03 | 2020-04-03 | 2020-10-10 | 2020-10-10 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042031120 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116749616 | POLE_DECA_REPL - #2 ON LINE W/O CO#2389 | 35208765 |  |  | STS-POLE_DECA_REPL - #2 ON LINE W/O CO#2 | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 38.3608 | -122.2679 |  | TIER 2 | 313 | 04329-1104, PUEBLO | KK3913 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.2 | 32.2 |  |  | 0 | 32.2 | 32.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102284379 | RELW OH RTRN PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-19 | 2021-02-03 | COMP | 2021-01-19 | [16 empty] | 2019-03-16 | 2020-03-16 | 2021-03-12 | 2021-03-12 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043291104 | 12014.09 | 151.9 | 0 | 1711.2 | 1711.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116751904 | POLE_BURN_REPL - 2 E/O 2245 ATLAS PEAK R | 35208770 |  |  | STS-POLE_BURN_REPL - 2 E/O 2245 ATLAS PE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.367 | -122.2635 |  | TIER 2 | 313 | 04329-1104, PUEBLO | KK3908 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 58.5 | 55.3 | 3.2 |  | 0 | 58.5 | 55.3 | 3.2 |  | EC | E | Pole | Burnt | Replace |  | 102286048 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-01-19 | COMP | 2021-01-19 | [16 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043291104 | 18148.81 |  | 0 | 1711.2 | 1711.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116754500 | POLE_BURN_REPL - 2 W/O 2560 ATLAS PEAK R | 35208780 |  |  | STS-POLE_BURN_REPL - 2 W/O 2560 ATLAS PE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.3715 | -122.2509 |  | TIER 2 | 313 | 04329-1104, PUEBLO | KK39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.8 | 34.8 |  |  | 0 | 34.8 | 34.8 |  |  | EC | E | Pole | Burnt | Replace |  | 102286002 | RELW OH PRI CLR JPOL RESD NOAC ESTR PRTO USA FMOB TER2 FSRP | Pole | 2021-01-29 |  | COMP | 2021-01-29 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043291104 | 16941.99 |  | 0 | 1466.7 | 1466.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116754719 | POLE_BURN_REPL - 1 W/O 2560 ATLAS PEAK R | 35208784 |  |  | STS-POLE_BURN_REPL - 1 W/O 2560 ATLAS PE | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.3711 | -122.2499 |  | TIER 2 | 313 | 04329-1104, PUEBLO | KK39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 29.9 | 29.9 |  |  | 0 | 29.9 | 29.9 |  |  | EC | E | Pole | Burnt | Replace |  | 102285984 | RELW OH PRI CLR JPOL RESD NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2021-02-22 |  | COMP | 2021-02-22 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043291104 | 14519.86 |  | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116755194 | POLE_BROK_REPL - #1N/O HOUSE 2590 MONTIC | 35209746 |  |  | STS-POLE_BROK_REPL - #1N/O HOUSE 2590 MO | APPR | APPR ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.346 | -122.2399 |  | TIER 2 | 313 | 04329-1104, PUEBLO | KK40 | 1213 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102289245 | RELW OH PRI JPOL RESD JAR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | INPR | [17 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043291104 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116755198 | POLE_DECA_REPL - 1 R/O 2463 ATLAS PEAK R | 35208787 |  |  | STS-POLE_DECA_REPL - 1 R/O 2463 ATLAS PE | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.3701 | -122.2523 |  | TIER 2 | 313 | 04329-1104, PUEBLO | KK39 | 1304 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 44.8 | 44.8 |  |  | 0 | 44.8 | 44.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102285981 | RELW OH PRI RESD ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-19 | 2021-01-15 | COMP | 2021-01-15 | [16 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043291104 | 20509.18 | 13.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116755446 | POLE_BURN_REPL - 2 R/O 2463 ATLAS PEAK R | 35208791 |  |  | STS-POLE_BURN_REPL - 2 R/O 2463 ATLAS PE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3697 | -122.2519 |  | TIER 2 | 313 | 04329-1104, PUEBLO | KK39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.4 | 20.4 |  |  | 0 | 20.4 | 20.4 |  |  | EC | E | Pole | Burnt | Replace |  | 102285979 | OH RELW PRI CLR JPOL ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-30 | 2021-02-16 | COMP | 2020-12-30 | [16 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043291104 | 7551.66 | 13.4 | 0 | 1724.5 | 1724.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116755784 | POLE_BROK_REPL - 1 W/O 2477 ATLAS PEAK R | 35209762 |  |  | STS-POLE_BROK_REPL - 1 W/O 2477 ATLAS PE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.3714 | -122.253 |  | TIER 2 | 313 | 04329-1104, PUEBLO | KK39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102285934 | RELW OH PRI CLR JPOL RESD JAR NOAC USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043291104 | 1 | 662.7 | 435 | 435 | 435 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116760061 | POLE_BURN_REPL - W/O 2500 ATLAS PEAK RDN | 35208818 |  |  | STS-POLE_BURN_REPL - W/O 2500 ATLAS PEAK | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.3667 | -122.2538 |  | TIER 2 | 313 | 04329-1104, PUEBLO | KK39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 102286010 | RELW OH PRI CUST CLR ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043291104 | 1 | 553.6 | 174 | 1600 | 1600 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116764751 | POLE_BROK_REPL - 2441 ATLAS PEAK RD.@HOU | 35209765 |  |  | STS-POLE_BROK_REPL - 2441 ATLAS PEAK RD. | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3706 | -122.2534 |  | TIER 2 | 313 | 04329-1104, PUEBLO | KK39 | 4059 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102285959 | PRI OH RELW JAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043291104 | 1 | 13.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116792754 | POLE_BROK_REPL - #5NE/O ENTRANCE 6800 GO | 35202211 |  |  | STS-POLE_BROK_REPL - #5NE/O ENTRANCE 680 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.3541 | -122.1264 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | KK42 | 2659 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 30.7 | 30.7 |  |  | 0 | 30.7 | 30.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102289775 | RELW OH PRI JPOL GO REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-28 |  | COMP | 2020-12-28 | [16 empty] | 2019-03-20 | 2020-03-20 | 2020-11-23 | 2020-11-23 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043051101 | 18626.65 | 593.7 | -760.2 | 900.8 | 900.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116803441 | POLE_BROK_REPL - 5NW/O 7200 WILD HORSE V | 35202229 |  |  | STS-POLE_BROK_REPL - 5NW/O 7200 WILD HOR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.3132 | -122.2124 |  | TIER 2 |  | 202-1112, NAPA | LL40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102288909 | RELW OH PRI JPOL REMT FIRE NOAC ESTR GO FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-01-31 | QUES | [11 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116805109 | POLE_BROK_REPL - 1NW/O 7200 WILD HORSE V | 35208902 |  |  | STS-POLE_BROK_REPL - 1NW/O 7200 WILD HOR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.31 | -122.2042 |  | TIER 2 |  | 202-1112, NAPA | LL40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.2 | 57.2 |  |  | 0 | 57.2 | 57.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102288896 | RELW OH PRI JPOL REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-07 |  | COMP | 2021-01-07 | [16 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  |  | 25778.25 |  | 0 | 987.7 | 987.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116807465 | POLE_BROK_REPL - 2W/O 6301 WILD HORSE VL | 35208918 |  |  | STS-POLE_BROK_REPL - 2W/O 6301 WILD HORS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.2964 | -122.2154 |  | TIER 2 |  | 202-1112, NAPA | LL40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.4 | 28.4 |  |  | 0 | 28.4 | 28.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102288801 | RELW OH PRI JPOL REMT FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-13 |  | COMP | 2021-01-13 |  |  | 2021-02-22 | 2021-02-22 | [12 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  |  | 14171.25 | 55.7 | 55.7 | 1619.9 | 1619.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116808187 | POLE_DECA_REPL - 343 CIRCLE OAKS DR NAPA | 35154353 |  |  | STS-POLE_DECA_REPL - 343 CIRCLE OAKS DRN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.4136 | -122.2166 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | JJ4009 | 226821 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.9 | 37.9 |  |  | 0 | 37.9 | 37.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102292210 | RELW OH PRI JPOL RESD REMT FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-09 |  | COMP | 2021-02-09 | [16 empty] | 2019-03-21 | 2020-03-21 | 2024-03-19 | 2024-03-19 | 2021 CBP Plan | 2020-10-31 | QUES |  | 043051101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116816842 | POLE_DECA_REPL - R/O 6052 WILD HORSE VLY | 35208963 |  |  | STS-POLE_DECA_REPL - R/O 6052 WILD HORSE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2933 | -122.2175 |  | TIER 2 |  | 202-1112, NAPA | LL40 | 3405 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102288774 | RELW OH PRI JPOL RESD REMT FIRE ESTR TER2 BTKA USA FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI | [11 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116817858 | POLE_BROK_REPL - 18N/O 1W/O 5425 HWY.121 | 35208968 |  |  | STS-POLE_BROK_REPL - 18N/O 1W/O 5425 HWY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.265 | -122.3752 |  | TIER 2 | 186 | 04246-1106, BASALT | MM36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102256133 | RELW OH PRI CLR JPOL RESD REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 042461106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116819534 | POLE_DECA_REPL - 63O7 WOLD HORSE VLY RDN | 35202422 |  |  | STS-POLE_DECA_REPL - 63O7 WOLD HORSE VLY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.2963 | -122.2122 |  | TIER 2 |  | 202-1112, NAPA | LL40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102288812 | RELW OH PRI JPOL RESD REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 | 2020-12-22 | 2020-12-22 | 2021 CBP Plan | 2021-01-31 | QUES | [11 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116819649 | POLE_BURN_REPL - 6300 WILD HORSE VALLEY | 35202431 |  |  | STS-POLE_BURN_REPL - 6300 WILD HORSE VAL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.2964 | -122.2138 |  | TIER 2 |  | 202-1112, NAPA | LL40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 103336349 | RELW OH PRI JPOL RESD REMT FIRE NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-02-28 | QUES | [11 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116821290 | POLE_BURN_REPL - 3683 ATLAS PEAK RD 1S @ | 35208996 |  |  | STS-POLE_BURN_REPL - 3683 ATLAS PEAK RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.4151 | -122.2489 |  | TIER 2 | 313 | 04329-1104, PUEBLO | JJ39 | 861209 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 103770852 | RELW OH PRI JPOL FLAG RESD REMT FIRE ESTR BTKA USA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043291104 | 1 | 13.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116821291 | POLE_DECA_REPL - 3683 ATLAS PEAK RD 8SNA | 35209001 |  |  | STS-POLE_DECA_REPL - 3683 ATLAS PEAK RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.4111 | -122.2473 |  | TIER 2 | 313 | 04329-1104, PUEBLO | JJ39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102292425 | RELW OH PRI JPOL RESD REMT FIRE FLAG ESTR BTKA USA FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043291104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116825613 | POLE_DECA_REPL - 42 COUNTRY LN NAPA | 35209081 |  |  | STS-POLE_DECA_REPL - 42 COUNTRY LN NAPA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3038 | -122.223 |  | TIER 2 |  | 202-1112, NAPA | LL40 | 2455 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102288325 | RELW OH PRI RESD REMT FIRE ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-25 | 2020-03-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI | [11 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116852361 | POLE_BURN_REPL - 2500 SODA CANYON RD R/O | 35154639 |  |  | STS-POLE_BURN_REPL - 2500 SODA CANYON RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.415 | -122.2943 |  | TIER 2 | 408 | 04329-1105, PUEBLO | JJ38 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 102291800 | RELW OH SEC ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 043291105 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116852373 | POLE_DECA_REPL - 4088 ATLAS PEAK RD (HOU | 35209772 |  |  | STS-POLE_DECA_REPL - 4088 ATLAS PEAK RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.4308 | -122.2434 |  | TIER 2 | 313 | 04329-1104, PUEBLO | II40 | 9595 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102291384 | RELW OH PRI JPOL RESD REMT FIRE ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2019-09-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043291104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116867760 | POLE_OVRL_TEST - 1981 CAPELL VALLEY ROAD | 35209515 |  |  | STS-POLE_OVRL_TEST - 1981 CAPELL VALLEY | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.4785 | -122.2363 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | HH4022 | 310269 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.3 | 23.3 |  |  | 0 | 23.3 | 23.3 |  |  | EC | E | Pole | Overloaded | Test |  | 103158775 | OH PRI JPOL RESD REMT FIRE FLAG ESTR BTKA FMOB FSRP PRTO RELW TER2 | Pole | 2021-01-25 |  | COMP | 2021-01-25 | [16 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043051101 | 14606.21 | 746.8 | 46.7 | 1146.7 | 1146.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116867761 | POLE_BROK_REPL - 1981 CAPELL VALLEY ROAD | 35209520 |  |  | STS-POLE_BROK_REPL - 1981 CAPELL VALLEY | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.4786 | -122.2361 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | HH4022 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.9 | 23.9 |  |  | 0 | 23.9 | 23.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103158798 | RELW OH PRI JPOL RESD REMT FIRE FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-25 |  | COMP | 2021-01-25 | [16 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043051101 | 8672.19 |  | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116868231 | POLE_BROK_REPL - R/O 1962 CAPELL VALLEY | 35209525 |  |  | STS-POLE_BROK_REPL - R/O 1962 CAPELL VAL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.471 | -122.2344 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | HH4022 | 720 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 56 | 56 |  |  | 0 | 56 | 56 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102287722 | RELW OH PRI RESD CLR JPOL REMT FIRE ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 |  | COMP | 2021-01-19 | [16 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043051101 | 27388.63 | 1165.9 | 1071.9 | 1898.3 | 1898.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116872613 | POLE_DECA_REPL - HOUSE 4450 ATLAS PEAK | 35209605 |  |  | STS-POLE_DECA_REPL - HOUSE 4450 ATLAS P | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.4429 | -122.2467 |  | TIER 2 | 313 | 04329-1104, PUEBLO | II39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.7 | 13.7 |  |  | 0 | 13.7 | 13.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102291445 | RELW RESD OH PRI JPOL REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-25 |  | COMP | 2021-01-25 | [16 empty] | 2019-03-30 | 2020-03-30 | 2021-03-21 | 2021-03-21 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043291104 | 5888.67 | 236.3 | 236.3 | 1336.3 | 1336.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116876976 | POLE_BROK_REPL - 1981 CAPELL VALLEY ROAD | 35209636 |  |  | STS-POLE_BROK_REPL - 1981 CAPELL VALLEY | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Enviro JointPole |  |  | 38.4794 | -122.2368 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | HH40 | 310269 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.8 | 31.8 |  |  | 0 | 31.8 | 31.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103119542 | RELW OH PRI JPOL RESD REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-25 |  | COMP | 2021-01-25 | [16 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043051101 | 19081.97 | 554.3 | 348 | 1448 | 1448 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116935859 | POLE_BROK_REPL - NE C/O CAPELL CROSS RD | 35209699 |  |  | STS-POLE_BROK_REPL - NE C/O CAPELL CROS | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Enviro JointPole |  |  | 38.4718 | -122.2278 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | HH4023 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14 | 14 |  |  | 0 | 14 | 14 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103158790 | RELW OH PRI JPOL RESD REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 |  | COMP | 2021-01-28 | [16 empty] | 2019-04-01 | 2020-04-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043051101 | 8642.79 | 491.3 | 339.4 | 1439.4 | 1439.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116955618 | POLE_DECA_REPL - 1981 CAPELL VALLEY ROAD | 35208834 |  |  | STS-POLE_DECA_REPL - 1981 CAPELL VALLEY | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.4786 | -122.2352 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | HH4022 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103158799 | RELW OH PRI JPOL RESD REMT FIRE FMOB FLAG ESTR BTKA TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043051101 | 1 |  | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 117018878 | POLE_BURN_REPL - 2931 ATLAS PECK RD MP 4 | 35209316 |  |  | STS-POLE_BURN_REPL - 2931 ATLAS PECK RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3808 | -122.2473 |  | TIER 2 | 313 | 04329-1104, PUEBLO | KK39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 103156124 | RELW OH SEC REMT FIRE ESTR BTKA FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-04-12 | 2020-04-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043291104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 117154097 | POLE_DECA_REPL - KNOXVILLE RD ENT (BLUE | 35209073 |  |  | STS-POLE_DECA_REPL - KNOXVILLE RD ENT (B | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.5787 | -122.2536 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | FF39 | 630 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102264268 | RELW OH PRI INSP ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 043051101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 117154675 | POLE_DECA_REPL - 4301 KNOXVILLE RD 1NNAP | 35154338 |  |  | STS-POLE_DECA_REPL - 4301 KNOXVILLE RD 1 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.5334 | -122.2293 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | GG40 | 654 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 100.4 | 100.4 |  |  | 0 | 100.4 | 100.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102264396 | RELW OH PRI INSP CLR REMT FIRE NOAC ESTR FMOB TER2 FSRP | Pole | 2021-02-02 | 2021-02-01 | COMP | 2021-02-01 | [16 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 043051101 | 24782.93 | 45.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 117158300 | POLE_BROK_REPL - #1N/O ENTRANCE 6261 GOR | 35202475 |  |  | STS-POLE_BROK_REPL - #1N/O ENTRANCE 6261 | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3201 | -122.1166 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | LL43 | 7261 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102289991 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2020-10-27 | 2020-10-27 | 2021 CBP Plan | 2021-02-28 | QUES |  | 043051101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 117304631 | POLE_DECA_REPL - 20N/O 8300 WILD HORSE V | 35209611 |  |  | STS-POLE_DECA_REPL - 20N/O 8300 WILD HOR | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land JointPole |  |  | 38.3229 | -122.192 |  | TIER 2 |  | 202-1112, NAPA | LL41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.3 | 26.3 |  |  | 0 | 26.3 | 26.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102289046 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-29 |  | COMP | 2021-01-29 | [16 empty] | 2019-05-22 | 2020-05-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  |  | 25569.46 | 84.6 | 84.6 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | Napa | Napa |  |  | OPEN | 117691414 | POLE _ BROK _ REPL_4S/2W/O 6301 WILD HOR | 35202359 |  |  | STS-POLE _ BROK _ REPL_4S/2W/O 6301 WILD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.2947 | -122.2157 |  | TIER 2 | 502 | 04202-1112, NAPA | LL40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25 | 25 |  |  | 0 | 25 | 25 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102288795 | RELW OH TER2 PRI ESTR GO PRTO FSRP | Pole | 2021-02-10 |  | COMP | 2021-02-10 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042021112 | 13341.26 |  | -1013.6 | -651.6 | -651.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | COMP | 114829325 | POD POLE_BROK_REPL - 2000 WOODEN VALLEY | 35052106 |  |  | POD POLE_BROK_REPL - 2000 WOODEN VALLEY | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.3334 | -122.1264 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | LL42 |  | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 7.5 | 40.8 | 40.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102289633 | REGW OH PRI INSP COMP JPOL NOAC ESTR REAR CCNT FMOB TER2 | Pole | 2018-12-10 | 2018-12-10 | COMP | 2018-12-10 | COMP | 2021-02-17 | 2020-06-04 | 2020-06-04 | [11 empty] | 2021-02-22 | 2021-02-17 | 2019-07-27 |  | 2019-07-27 | Q1 Work Plan |  | UNASSIGNED |  | 043051101 | 27659.68 | 10461.5 | 8946 |  |  | 922.4 |  | 922.4 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | NAPA | Napa |  |  | COMP | 114829326 | POD POLE_BROK_REPL - 2040 NAPA GORDON VA | 35052107 |  |  | POD-POLE_BROK_REPL - 2040 NAPA GORDON VA | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.3336 | -122.1253 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | LL42 |  | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102289635 | REGW OH PRI INSP COMP JPOL NOAC ESTR REAR CCNT FMOB TER2 | Pole | 2018-12-10 | 2018-12-10 | COMP | 2018-12-10 | COMP | 2021-02-17 | 2020-06-04 | 2020-06-04 | [11 empty] | 2021-02-22 | 2021-02-17 | 2019-07-27 |  | 2019-07-27 | Q1 Work Plan |  | UNASSIGNED |  | 043051101 | 31551.11 | 20514.5 | 7905.8 |  |  | 10111.8 |  | 10111.8 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | NAPA | Napa |  |  | COMP | 116790498 | POLE_DECA_REPL - 2 S/O 74 SUNNY HILL LN | 35154251 |  |  | STS-POLE_DECA_REPL - 2 S/O 74 SUNNY HILL | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2021-02-20 | No Action | 38.4081 | -122.2117 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | JJ4009 |  | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 81.8 | 81.8 |  |  | 3.25 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102292159 | RELW OH PRI COMP CLR FLAG ESTR BTKA CCNT FSRP PRTO FMOB TER2 | Pole | 2020-05-12 | 2020-10-30 | COMP | 2020-05-12 | COMP | 2021-02-11 | 2020-10-30 | 2020-10-30 | [11 empty] | 2021-02-17 | 2021-02-11 | 2020-03-20 | 2024-03-18 | 2024-03-18 | 2021 CBP Plan | 2020-05-01 | QUES |  | 043051101 | 12427.22 | 3138.6 | 2521.6 | 1012.9 | 1012.9 | 166.8 |  | 166.8 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | COMP | 117174105 | POLE_BROK_REPL - R/O HOUSE 10 VALLE VIST | 35107529 |  |  | REPL POLE R/O HOUSE 10 VALLE VISTA AVE | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.3399 | -122.1136 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | KK4322 | 4909 | Y | 311 |  |  | 2021-01-15 | 2021-01-15 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102291171 | RELW OH COMP CCNT TER2 PRI JAR FMOB PRTO FSRP | Pole | 2020-06-02 | 2020-07-20 | COMP | 2020-06-02 | COMP | 2021-01-15 | [13 empty] | 2021-02-01 | 2021-01-15 | 2019-11-06 | 2024-05-04 | 2024-05-04 | circuit based plan 2.14 | 2020-06-08 | CALENG |  | 043051101 | 21750.99 | 11059.6 | 7346.3 | 27622.9 | 27622.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | NAPA | Napa |  |  | COMP | 119537322 | POLE_BROK_REPL - 3 N/O 8000 WILD HORSE V | 35191529 |  |  | STS-POLE_BROK_REPL - 3 N/O 8000 WILD HOR | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-09-29 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.3238 | -122.1989 |  | TIER 2 | 502 | 04202-1112, NAPA | LL41 | 2259 | Y | 311 |  |  | 2021-01-12 | 2021-01-12 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 43.7 | 43.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 102288992 | RELW OH COMP ESTR CCNT TER2 | Pole | 2020-10-03 | 2020-10-07 | COMP | 2020-10-03 | COMP | 2021-01-14 | [13 empty] | 2021-01-20 | 2021-01-14 | 2020-10-27 |  | 2020-10-27 | B-tag addition 8/12/2020 |  | Santa Rosa |  | 042021112 | 18207.46 | 8787.7 | 4410.7 | 12585.7 | 12585.7 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Internal Timeliness - Consturction - [REDACTED] capacity issues | Y | 2020-08-18
North | NB | NAPA | Napa |  |  | COMP | 119794659 | POLE_BROK_REPL - 11080 EAST SIDE RD 23NE | 35204197 |  |  | STS-POLE_BROK_REPL - 11080 EAST SIDE RD | UNSC | UNSC | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-09-21 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 38.6583 | -122.2217 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | DD40 |  | Y | 311 |  |  | 2020-09-12 | 2020-09-12 | Scheduled | Order Operation | POLRPL | # of Poles Replaced | 1 | 1 | 0 | 0 | 40.2 | 40.2 |  |  | 0 | 40.2 | 40.2 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 102254711 | RELW OH PRI COMP CLR REMT NOAC ESTR OTHR USA CCNT FMOB TER2 | Pole | 2020-12-23 | 2021-01-04 | COMP | 2020-12-23 | [15 empty] | 2021-01-25 | 2020-09-21 | 2020-12-21 |  | 2020-12-21 | B tag clean up 10/4/2020 |  | Santa Rosa |  | 043051101 | 20380.99 | 1077.4 | 1037 | 187 | 187 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Tag in Closure Status | Y | 2020-10-04
North | NB | NAPA | Napa |  |  | OPEN | 116762917 | POLE_BROK_REPL - 2 R/O 2391 ATLAS PEAK R | 35165588 |  |  | STS-POLE_BROK_REPL - 2 R/O 2391 ATLAS PE | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3754 | -122.2563 |  | TIER 2 | 313 | 04329-1104, PUEBLO | KK39 | 4059 | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 45.1 | 42.7 | 2.4 |  | 0 | 45.1 | 42.7 | 2.4 |  | EC | E | Pole | Broken/Damaged | Replace |  | 102285948 | RELW OH TER2 PRI ESTR FMOB PRTO FSRP | Pole | 2020-04-06 | 2020-05-21 | COMP | 2020-04-06 | [16 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 043291104 | 12377.58 | 440.9 | 440.9 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116766688 | POLE_DECA_REPL - A/F 40 RIDGECREST DR NA | 35154227 |  |  | STS-POLE_DECA_REPL - A/F 40 RIDGECREST D | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4117 | -122.2148 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | JJ4009 | 226821 | Y | 311 |  |  | 2021-03-05 07:00 | 2021-03-05 16:00 | Scheduled | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102292237 | OH RELW PRI JPOL RESD REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-06-17 | 2020-10-30 | COMP | 2020-06-17 |  |  | 2020-10-30 | 2020-10-30 | [12 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | QUES |  | 043051101 | 18320.74 | 1105.9 | 1041.9 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116806527 | POLE_BROK_REPL - 6440 WILD HORSE VLY RDN | 35202267 |  |  | STS-POLE_BROK_REPL - 6440 WILD HORSE VLY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2968 | -122.2087 |  | TIER 2 |  | 202-1112, NAPA | LL40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.5 | 17.5 |  |  | 0 | 17.5 | 17.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102288814 | RELW OH PRI JPOL RESD REMT FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-07 | 2021-01-21 | COMP | 2020-12-07 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-12-22 | 2020-12-22 | 2021 CBP Plan | 2021-01-31 | QUES |  |  | 6767.02 | 1242.3 | 699.3 | -271.5 | -271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116825022 | POLE_BURN_REPL - R/O 6270 SILVERADO TRAI | 35145878 |  |  | STS-POLE_BURN_REPL - R/O 6270 SILVERADO | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4255 | -122.3292 |  | TIER 2 | 16 | 04329-2102, PUEBLO | JJ37 |  | Y | 311 |  |  | 2021-02-18 07:00 | 2021-02-18 16:00 | Completed | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 1.5 | 40.8 | 40.8 |  |  | EC | E | Pole | Burnt | Replace |  | 102280184 | RELW OH PRI JPOL REMT FIRE ESTR USA PRTO FMOB TER2 | Pole | 2020-07-08 | 2020-07-16 | COMP | 2020-06-04 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | circuit based plan 2.14 | 2020-06-08 | CALENG |  | 043292102 | 27104.75 | 13545.3 | 1896 | 7446 | 7446 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | NAPA | Napa |  |  | OPEN | 116827693 | POLE_BROK_REPL - #1E/O ENTRANCE 3801 MON | 35154551 |  |  | STS-POLE_BROK_REPL - #1E/O ENTRANCE 3801 | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3757 | -122.2021 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | KK41 | 2443 | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 10.5 | 40.8 | 40.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102290521 | RELW OH PRI JPOL RESD REMT FIRE FLAG ESTR BTKA OTRG FMOB TER2 PRTO FSRP | Pole | 2020-05-13 | 2020-10-30 | COMP | 2020-05-13 |  |  | 2020-10-30 | 2020-10-30 | [12 empty] | 2019-03-25 | 2020-03-25 | 2024-03-23 | 2024-03-23 | 2021 CBP Plan | 2020-05-01 | QUES |  | 043051101 | 14822.07 | 3589.2 | 2621.9 | 2541 | 2541 | 489.1 |  | 489.1 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116870932 | POLE_DECA_REPL - 3570 SODA CANYON RD. 3P | 35202566 |  |  | STS-POLE_DECA_REPL - 3570 SODA CANYON RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4403 | -122.28 |  | TIER 2 | 408 | 04329-1105, PUEBLO | II39 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26 | 26 |  |  | 0 | 26 | 26 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102291528 | RELW OH PRI JPOL RESD REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-08 | 2021-01-26 | COMP | 2020-12-08 | [16 empty] | 2019-03-30 | 2020-03-30 | 2020-10-27 | 2020-10-27 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043291105 | 11571.85 | 1286.9 | 536.4 | -389.1 | -389.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 116875482 | POLE_DECA_REPL - 191 RIDGE DR R/O 1SE NA | 35132269 |  |  | STS-POLE_DECA_REPL - 191 RIDGE DR R/O 1S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3967 | -122.3032 |  | TIER 2 | 16 | 04329-2102, PUEBLO | JJ38 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102291933 | RELW OH PRI CLR NOAC ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-01-10 | 2020-03-27 | COMP | 2020-01-10 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-03-31 | 2020-03-31 |  | 2020-03-31 | circuit based plan 2.14 |  | Concord |  | 043292102 | 18918.33 | 2097.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | NAPA | Napa |  |  | OPEN | 116875812 | POLE_DECA_REPL - A/F 1001 KNOXVILLE RD N | 35223299 |  |  | STS-POLE_DECA_REPL - A/F 1001 KNOXVILLE | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.4953 | -122.2453 |  | TIER 2 | 160 | 04343-2102, SILVERADO | HH39 | 6741 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102287246 | RELW OH PRI JPOL REMT FIRE FLAG BTKA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 |  | 2020-03-31 | Per DOT Approved Request 25876 | 2021-05-31 | UNASSIGNED |  | 043432102 | [9 empty] | N | MPP Owned but exists in DO Pull | N |  | Y | 2021-01-11
North | NB | NAPA | Napa |  |  | OPEN | 116950464 | POLE_DECA_REPL - 1061 STEELE CANYON RD A | 35104357 |  |  | STS-POLE_DECA_REPL - 1061 STEELE CANYON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5184 | -122.1887 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | GG4123 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 49.3 | 49.3 |  |  | 0 | 49.3 | 49.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102263361 | RELW OH PRI REMT FIRE NOAC ESTR FMOB TER2 PRTO | Pole | 2019-10-01 | 2019-12-22 | COMP | 2019-10-01 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-04-03 | 2019-07-30 |  | 2019-07-30 | circuit based plan 2.14 |  | Santa Rosa |  | 043051101 | 21897.57 | 3308.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | NAPA | Napa |  |  | OPEN | 117122849 | POLE_DECA_REPL - 2 N/O 3194 REDWOOD RDNA | 35149677 |  |  | STS-POLE_DECA_REPL - 2 N/O 3194 REDWOOD | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-02-20 | Renew Permit | 38.3234 | -122.3499 |  | TIER 2 | 2 | 04329-2103, PUEBLO | LL370 |  | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102273091 | RELW OH PRI INSP JPOL RESD FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-04-15 | 2020-09-16 | COMP | 2020-04-15 |  |  | 2020-09-16 | 2020-09-16 | [12 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 043292103 | 22949.96 | 6139.9 | 5530.4 | 1159 | 1159 | 116.3 |  | 116.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 117302581 | POLE_BROK_REPL - 28N/O 8300 WILD HORSE V | 35202958 |  |  | STS-POLE_BROK_REPL - 28N/O 8300 WILD HOR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land Enviro JointPole |  |  | 38.3267 | -122.1903 |  | TIER 2 |  | 202-1112, NAPA | LL41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.8 | 22.8 |  |  | 0 | 22.8 | 22.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103916685 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-13 |  | COMP | 2021-01-13 | [16 empty] | 2019-05-22 | 2020-05-22 | 2020-10-21 | 2020-10-21 | 2021 CBP Plan | 2021-01-31 | QUES |  |  | 22000.63 | 134.8 | 134.8 | 1403.5 | 1403.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NAPA | Napa |  |  | OPEN | 119698502 | POLE_BURN_REPL - 11080 EAST SIDE RD 26NE | 35198211 |  |  | 12/1 B REPL POLE 11080 EAST SIDE RD | DOCC | DOCC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6579 | -122.2176 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | DD40 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 31 | 31 |  |  | 0 | 31 | 31 |  |  | EC | B | Pole | Burnt | Replace |  | 102254716 | RELW OH PRI COMP ESTR OTHR CCNT FMOB TER2 | Pole | 2020-09-08 | 2020-09-11 | COMP | 2020-09-05 | [16 empty] | 2020-09-01 | 2020-12-01 |  | 2020-12-01 | B tag clean up 9/5/2020 |  | UNASSIGNED |  | 043051101 | 9954.53 | 1731 | [7 empty] | N | 11/2 in MPP Import File | N |  | Y | 2020-09-05
North | NB | Napa | Napa |  |  | OPEN | 119698663 | POLE_BURN_REPL - 11080 Berryessa Knoxvil | 35198213 |  |  | STS-POLE_BURN_REPL - 11080 BERRYESSA KNO | DOCC | DOCC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6541 | -122.2382 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | DD40 |  | Y | 311 |  |  | 2020-09-11 | 2020-09-11 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 15.1 | 15.1 |  |  | 0 | 15.1 | 15.1 |  |  | EC | B | Pole | Burnt | Replace |  | 102254683 | PRI OH RELW ESTR OTHR FMOB TER2 | Pole | 2020-09-08 | 2020-11-13 | COMP | 2020-09-05 | COMP | 2020-09-11 | [14 empty] | 2020-09-01 | 2020-12-01 |  | 2020-12-01 | B tag clean up 9/5/2020 |  | UNASSIGNED |  | 043051101 | 7214.98 | 2194.2 | [7 empty] | N | 11/2 in MPP Import File | N | Estimating Delays | Y | 2020-09-05
North | NB | NAPA | Napa |  |  | OPEN | 119698732 | POLE_BROK_REPL - 11080 EAST SIDE RD 9NE | 35198214 |  |  | POLE_BROK_REPL - 11080 EAST SIDE RD | DOCC | DOCC | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6546 | -122.2361 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | DD40 |  | Y | 311 |  |  |  |  | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 24.8 | 24.8 |  |  | 24 | 0.9 | 0.9 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 102254679 | RELW OH PRI ESTR OTHR FMOB TER2 | Pole | 2020-11-16 | 2020-11-17 | COMP | 2020-11-13 | COMP | 2020-09-13 | [14 empty] | 2020-09-01 | 2020-12-01 |  | 2020-12-01 | B tag clean up 9/5/2020 |  | UNASSIGNED |  | 043051101 | 8480.32 | 6314.6 | 6314.6 | 6314.6 | 6314.6 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Estimating Delays | Y | 2020-09-05
North | NB | NAPA | Napa |  |  | OPEN | 119698820 | POLE_BROK_REPL - 11080 EAST SIDE RD 6NEN | 35198215 |  |  | STS-POLE_BROK_REPL - 11080 EAST SIDE RD | DOCC | DOCC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6538 | -122.2392 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | DD40 |  | Y | 311 |  |  | 2020-11-20 | 2020-11-20 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 102254684 | OH PRI COMP ESTR OTHR FMOB TER2 CCNT RELW | Pole | 2020-09-08 | 2020-10-02 | COMP | 2020-09-05 | [16 empty] | 2020-09-01 | 2020-12-01 |  | 2020-12-01 | B tag clean up 9/5/2020 |  | UNASSIGNED |  | 043051101 | 7376.53 | 2324 | 16.4 | 16.4 | 16.4 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N |  | Y | 2020-09-05
North | NB | Napa | Napa |  |  | OPEN | 119701681 | POLE_BROK_REPL - 11080 EAST SIDE RD 11NE | 35198216 |  |  | STS-POLE_BROK_REPL - 11080 EAST SIDE RD | DOCC | DOCC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6552 | -122.2329 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | DD40 |  | Y | 311 |  |  | 2020-09-13 | 2020-09-13 | Scheduled | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 26.2 | 26.2 |  |  | 0 | 26.1 | 26.1 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 102254688 | RELW OH PRI ESTR OTHR FMOB TER2 | Pole | 2020-09-08 | 2020-10-26 | COMP | 2020-09-07 | COMP | 2020-09-13 | [14 empty] | 2020-09-01 | 2020-12-01 |  | 2020-12-01 | B tag clean up 9/5/2020 |  | Santa Rosa |  | 043051101 | 8872.55 | 13.4 | [7 empty] | N | 11/2 in MPP Import File | N |  | Y | 2020-09-05
North | NB | NAPA | Napa |  |  | OPEN | 119825568 | POLE_BROK_REPL - 11080 EAST SIDE RD Napa | 35205567 |  |  | STS-POLE_BROK_REPL - 11080 EAST SIDE RD | POST | POST | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | Out of PEND |  |  | 38.6553 | -122.2382 |  | TIER 2 | 264 | 04305-1101, MONTICELLO | DD40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.2 | 40.2 |  |  | 0 | 40.2 | 40.2 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 102254681 | RELW OH PRI REMT FIRE NOAC ESTR BTKA OTHR USA FMOB TER2 | Pole | 2020-11-29 | 2020-11-29 | COMP | 2020-11-29 | [16 empty] | 2020-09-28 | 2020-12-28 |  | 2020-12-28 | B tag clean up 10/4/2020 |  | UNASSIGNED |  | 043051101 | 8147.84 | -20.7 | [7 empty] | N | 11/2 in MPP Import File | N | Tag in Closure Status | Y | 2020-10-04
North | NB | NICASIO | San Rafael |  |  | OPEN | 117047205 | POLE_DECA_REPL - 11 N/O 101 NICASIO VALL | 35116646 |  |  | STS-POLE_DECA_REPL - 11 N/O 101 NICASIO | PEND | PEND SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 38.0201 | -122.6634 |  | TIER 2 | 185 | 04302-1101, WOODACRE | SS2908 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 34.7 | 34.7 |  |  | 0 | 34.7 | 34.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102257838 | RELW OH PRI REMT FIRE ESTR BTKA FMOB TER2 PRTO | Pole | 2019-10-03 | 2019-08-28 | COMP | 2019-08-27 |  |  | 2020-08-03 | 2020-08-03 | [12 empty] | 2019-04-17 | 2020-04-17 |  | 2020-04-17 | 2021 CBP Plan |  | UNASSIGNED |  | 043021101 | 14162.57 | 273.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | NICASIO | San Rafael |  |  | OPEN | 117069420 | POLE_DECA_REPL - 4749 NICASIO VALLEY RDN | 35116648 |  |  | STS-POLE_DECA_REPL - 4749 NICASIO VALLEY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD | 2019-12-31 | Renew Permit | 38.0626 | -122.6999 |  | TIER 2 | 185 | 04302-1101, WOODACRE | RR2809 | DISCONNECT 5729 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 29 | 29 |  |  | 0 | 29 | 29 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102229358 | RELW OH PRI CLR RESD FLAG ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-09-02 | 2019-09-05 | [12 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2021-01-31 | Bakersfield |  | 043021101 | 1 | 1605.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | NICASIO | San Rafael |  |  | OPEN | 117157589 | POLE_DECA_REPL - 14500 P.T.REYES PETALUM | 35215198 |  |  | STS-POLE_DECA_REPL - 14500 P.T.REYES PET | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.0801 | -122.7846 |  | TIER 2 | 488 | 04229-1101, OLEMA | QQ26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.8 | 12.8 |  |  | 0 | 12.8 | 12.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102227599 | OH PRI JPOL RESD REMT FIRE FLAG ESTR BTKA PRTO RELW FMOB TER2 FSRP | Pole | 2021-02-19 |  | COMP | 2021-02-19 | [16 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042291101 | 9835.02 | 134.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NICASIO | San Rafael |  |  | OPEN | 117157606 | POLE_DECA_REPL - #5S/O 14000 P.T.REYES P | 35215203 |  |  | STS-POLE_DECA_REPL - #5S/O 14000 P.T.REY | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Enviro JointPole |  |  | 38.0796 | -122.7781 |  | TIER 2 | 488 | 04229-1101, OLEMA | QQ26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 17.4 | 17.4 |  |  | 0 | 17.4 | 17.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102227582 | RELW OH PRI JPOL RESD REMT FIRE FLAG REAR ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-01 |  | COMP | 2021-02-01 | [16 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 042291101 | 13257.17 | 80.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | NICASIO | San Rafael |  |  | OPEN | 117161455 | POLE_DECA_REPL - #2N/O R/O 5720 NICASIO | 35154371 |  |  | STS-POLE_DECA_REPL - #2N/O R/O 5720 NICA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.0864 | -122.6945 |  | TIER 2 | 185 | 04302-1101, WOODACRE | QQ28 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102229283 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 043021101 | 1 | 89.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | NICASIO | San Rafael |  |  | OPEN | 117153051 | POLE_BROK_REPL - #2E/O #2S/O #3W/O R/O 1 | 35155558 |  |  | STS-POLE_BROK_REPL - #2E/O #2S/O #3W/O R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0766 | -122.6745 |  | TIER 2 | 185 | 04302-1101, WOODACRE | QQ29 | 5729 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 24.2 | 24.2 |  |  | 0 | 24.2 | 24.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102229503 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-11-30 | 2020-11-30 | COMP | 2020-11-30 | [16 empty] | 2019-05-03 | 2020-05-03 |  | 2020-05-03 | 2021 CBP Plan | 2020-10-31 | QUES |  | 043021101 | 10876.39 | 1731.4 | 1242.3 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | NICASIO | San Rafael |  |  | OPEN | 117157045 | POLE_DECA_REPL - #1E/O R/O 1290 OLD RANC | 35116650 |  |  | STS-POLE_DECA_REPL - #1E/O R/O 1290 OLD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0784 | -122.6726 |  | TIER 2 | 185 | 04302-1101, WOODACRE | QQ29 |  | Y | 311 |  |  | 2021-03-12 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102229476 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-09-15 | 2020-09-15 | COMP | 2020-06-29 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-03 | 2020-05-03 |  | 2020-05-03 | 2021 CBP Plan | 2020-08-31 | Bakersfield |  | 043021101 | 16175.08 | 53.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | NOVATO | San Rafael |  |  | OPEN | 117273239 | POLE_DECA_REPL - # 1754 INDIAN VALLEY RD | 35150077 |  |  | STS-POLE_DECA_REPL - # 1754 INDIAN VALLE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0892 | -122.5897 |  | TIER 2 | 98 | 04320-1102, STAFFORD | QQ3117 | 5265 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50.5 | 50.3 | 0.2 |  | 0 | 50.5 | 50.3 | 0.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102220483 | RELW OH PRI JPOL REMT FIRE TRAF ESTR BTKA PROG FMOB TER2 PRTO | Pole | 2020-05-01 | 2020-10-30 | COMP | 2020-05-01 |  |  | 2020-10-30 | 2020-10-30 | [12 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | 2021 CBP Plan | 2020-04-10 | EEI |  | 043201102 | 20348.61 | 128 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | POPE VALLEY | Napa |  |  | OPEN | 116967502 | POLE_DECA_REPL - ENTRANCE TO 2700 POPE C | 35134370 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6455 | -122.3766 |  | TIER 2 | 7 | 04343-2104, SILVERADO | EE36 |  | Y | 311 |  |  | 2021-02-27 07:00 | 2021-02-27 16:00 | Dispatched | CLICK | [6 empty] | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102253472 | RELW OH PRI INSP CLR JPOL REMT NOAC SWRK ESTR USA FMOB TER2 FSRP | Pole | 2020-02-06 | 2020-03-31 | COMP | 2020-02-06 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-04-05 | 2020-04-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | Concord |  | 043432104 | 12172.14 | 3955 | 2713.3 |  |  | 1241.8 |  | 1241.8 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | POPE VALLEY | Napa |  |  | OPEN | 117078029 | POLE_BROK_REPL - F/O 2709 HARNESS DRPOPE | 35104588 |  |  | STS-POLE_BROK_REPL - F/O 2709 HARNESS DR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-02-20 | Renew Permit | 38.69 | -122.376 |  | TIER 2 | 7 | 04343-2104, SILVERADO | DD3604 | 3245 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 42.8 | 42.8 |  |  | 0 | 42.8 | 42.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102254986 | RELW OH PRI INSP JPOL RESD FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-09-10 | 2020-10-16 | COMP | 2020-07-03 |  |  | 2020-10-16 | 2020-10-16 | [12 empty] | 2019-04-22 | 2019-10-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | CALENG |  | 043432104 | 23267 | 874.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | POPE VALLEY | Napa |  |  | OPEN | 117691320 | POLE_BROK_REPL - 2249 JAMES CREEK RD POP | 35225232 |  |  | STS-POLE_BROK_REPL - 2249 JAMES CREEK RD | ADER | ADER ERDY | Poles | MPP | Not Funded as 2020 Wildfire OII | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.6649 | -122.468 |  | TIER 2 | 7 | 04343-2104, SILVERADO | DD34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102251339 | RELW OH PRI SCOP SCPA TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | work plan year cleanup 01/21/2021 | 2021-02-28 | Santa Rosa |  | 043432104 | [9 empty] | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-21
North | NB | SAINT HELENA | Napa |  |  | OPEN | 116863413 | POLE_DECA_REPL - 1000 SAGE CANYON RD RO | 35154682 |  |  | STS-POLE_DECA_REPL - 1000 SAGE CANYON RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.4823 | -122.38 |  | TIER 2 | 160 | 04343-2102, SILVERADO | HH36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.2 | 20.2 |  |  | 0 | 20.2 | 20.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102256034 | RELW OH PRI CLR FMOB REMT ESTR BTKA TER2 PRTO | Pole | 2021-02-16 |  | COMP | 2021-02-16 | [16 empty] | 2019-03-29 | 2020-03-29 |  | 2020-03-29 | 2021 CBP Plan | 2020-10-31 | QUES |  | 043432102 | 10420.02 | 296.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 116866034 | POLE_BROK_REPL - 990 SAGE CANYON RD 5PNW | 35154711 |  |  | STS-POLE_BROK_REPL - 990 SAGE CANYON RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.4858 | -122.3864 |  | TIER 2 | 160 | 04343-2102, SILVERADO | HH36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.4 | 18.4 |  |  | 0 | 18.4 | 18.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102256023 | RELW OH PRI RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-05-15 |  | COMP | 2020-05-15 |  |  | 2020-04-06 | 2020-04-06 | [12 empty] | 2019-03-29 | 2020-03-29 |  | 2020-03-29 | 2021 CBP Plan | 2020-05-01 | QUES |  | 043432102 | 11989.95 | 775.7 | 273.2 | 258.2 | 258.2 | 166.8 |  | 166.8 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 116838848 | POLE_DECA_REPL - R/O 2371 POPE CANYON RD | 35134341 |  |  | STS-POLE_DECA_REPL - R/O 2371 POPE CANYO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6342 | -122.3935 |  | TIER 2 | 7 | 04343-2104, SILVERADO | EE36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.3 | 24.3 |  |  | 0 | 24.3 | 24.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102253427 | RELW OH PRI INSP JPOL REMT ESTR BTKA USA FMOB TER2 FSRP | Pole | 2019-12-24 | 2020-02-06 | COMP | 2019-12-24 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | Concord |  | 043432104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 116841937 | POLE_DECA_REPL - R/O 2371 POPE CANYON RD | 35134345 |  |  | STS-POLE_DECA_REPL - R/O 2371 POPE CANYO | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6362 | -122.3985 |  | TIER 2 | 7 | 04343-2104, SILVERADO | EE36 | 7313 | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102253437 | RELW OH PRI INSP CLR JPOL REMT SWRK ESTR GO FMOB TER2 FSRP | Pole | 2020-01-10 | 2020-03-03 | COMP | 2020-01-10 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | Concord |  | 043432104 | 9786.93 | 1712.5 | 1704.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 116848405 | POLE_DECA_REPL - #1E/O #2N/O HOUSE 2483 | 35134349 |  |  | STS-POLE_DECA_REPL - #1E/O #2N/O HOUSE 2 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6375 | -122.3862 |  | TIER 2 | 7 | 04343-2104, SILVERADO | EE36 |  | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102253452 | RELW OH PRI INSP CLR JPOL REMT NOAC ESTR GO FMOB TER2 FSRP | Pole | 2020-01-10 | 2020-02-21 | COMP | 2020-01-10 |  |  | 2019-12-23 | 2019-12-23 | [12 empty] | 2019-03-27 | 2020-03-27 | 2024-03-25 | 2024-03-25 | 2021 CBP Plan |  | Concord |  | 043432104 | 9616.36 | 1706.9 | 1388.7 |  |  | 310.3 |  | 310.3 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 116970513 | POLE_DECA_REPL - 4 N/O A/F 1030 SILVERAD | 35092958 |  |  | STS-POLE_DECA_REPL - 4 N/O A/F 1030 SILV | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5192 | -122.467 |  | TIER 2 | 7 | 04343-2104, SILVERADO | GG3423 |  | Y | 311 |  |  | 2021-03-05 07:00 | 2021-03-05 16:00 | Dispatched | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 10 | 41.7 | 41.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102262350 | RELW OH PRI JPOL PUBL FIRE TRAF ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2019-11-20 | 2019-11-20 | COMP | 2019-11-20 |  |  | 2019-07-30 | 2019-07-31 | [12 empty] | 2019-04-06 | 2019-10-03 |  | 2019-10-03 | circuit based plan 2.14 |  | Santa Rosa |  | 043432104 | 16191.59 | 2615.2 | 843.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117139605 | POLE_DECA_REPL - F/O 4890 CHILES POPE VA | 35134504 |  |  | STS-POLE_DECA_REPL - F/O 4890 CHILES POP | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5873 | -122.3997 |  | TIER 2 | 7 | 04343-2104, SILVERADO | FF36 |  | Y | 311 |  |  | 2021-02-20 07:00 | 2021-02-20 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102262401 | INSP RELW OH PRI JPOL SPCR FLAG SWRK ESTR BTKA REAR USA FMOB TER2 | Pole | 2020-03-24 | 2020-05-04 | COMP | 2020-03-24 |  |  | 2019-12-11 | 2019-12-11 | [12 empty] | 2019-05-01 | 2020-05-01 |  | 2020-05-01 | 2021 CBP Plan |  | Concord |  | 043432104 | 8681.71 | 1127.6 | 1127.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117150087 | POLE_DECA_REPL - 4553 CHILES POPE VALLEY | 35134508 |  |  | STS-POLE_DECA_REPL - 4553 CHILES POPE VA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.57 | -122.3904 |  | TIER 2 | 7 | 04343-2104, SILVERADO | FF36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.5 | 26.5 |  |  | 0 | 26.5 | 26.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102262464 | RELW OH PRI INSP JPOL RESD REMT FIRE FLAG SWRK ESTR BTKA REAR USA FMOB TER2 | Pole | 2019-12-24 | 2020-02-24 | COMP | 2019-12-24 |  |  | 2019-12-11 | 2019-12-11 | [12 empty] | 2019-05-02 | 2020-05-02 |  | 2020-05-02 | 2021 CBP Plan |  | UNASSIGNED |  | 043432104 | 9081.77 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117150101 | POLE_DECA_REPL - 4140 CHILES POPE VALLEY | 35134548 |  |  | STS-POLE_DECA_REPL - 4140 CHILES POPE VA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5641 | -122.3814 |  | TIER 2 | 7 | 04343-2104, SILVERADO | FF36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.1 | 32.1 |  |  | 0 | 32.1 | 32.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103810425 | RELW OH PRI INSP JPOL RESD REMT FIRE FMOB ESTR REAR USA TER2 | Pole | 2020-01-10 | 2020-03-03 | COMP | 2020-01-10 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-02 | 2020-05-02 |  | 2020-05-02 | 2021 CBP Plan |  | UNASSIGNED |  | 043432104 | 9096.37 | 133 |  |  |  | 133 |  | 133 |  | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117150102 | POLE_DECA_REPL - MB 4553 CHILES POPE VAL | 35134514 |  |  | STS-POLE_DECA_REPL - MB 4553 CHILES POPE | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5719 | -122.394 |  | TIER 2 | 7 | 04343-2104, SILVERADO | FF36 |  | Y | 311 |  |  | 2021-02-20 07:00 | 2021-02-20 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 1 | 40.8 | 40.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102262438 | RELW OH PRI INSP JPOL RESD REMT FIRE FLAG SWRK ESTR BTKA REAR USA FMOB TER2 | Pole | 2020-01-10 | 2020-03-02 | COMP | 2020-01-10 |  |  | 2019-12-11 | 2019-12-11 | [12 empty] | 2019-05-02 | 2020-05-02 |  | 2020-05-02 | 2021 CBP Plan |  | UNASSIGNED |  | 043432104 | 8033.75 | 1517.3 | 1517.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117150103 | POLE_DECA_REPL - MB 4553 CHILES POPE VAL | 35134356 |  |  | STS-POLE_DECA_REPL - MB 4553 CHILES POPE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5722 | -122.395 |  | TIER 2 | 7 | 04343-2104, SILVERADO | FF36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.5 | 39.5 |  |  | 0 | 39.5 | 39.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102262435 | RELW OH PRI INSP RESD REMT FIRE FLAG ESTR BTKA USA FMOB TER2 | Pole | 2019-12-24 | 2019-12-24 | COMP | 2019-12-24 |  |  | 2019-12-11 | 2019-12-11 | [12 empty] | 2019-05-02 | 2019-09-30 |  | 2019-09-30 | 2021 CBP Plan |  | UNASSIGNED |  | 043432104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117150104 | POLE_DECA_REPL - GATE TO 4553 CHILES POP | 35134515 |  |  | STS-POLE_DECA_REPL - GATE TO 4553 CHILES | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5713 | -122.3928 |  | TIER 2 | 7 | 04343-2104, SILVERADO | FF36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.9 | 25.9 |  |  | 0 | 25.9 | 25.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102262451 | RELW OH PRI INSP JPOL RESD REMT FIRE SPCR FLAG SWRK ESTR BTKA USA FMOB TER2 | Pole | 2020-01-13 | 2020-03-10 | COMP | 2020-01-13 |  |  | 2019-12-11 | 2019-12-11 | [12 empty] | 2019-05-02 | 2020-05-02 |  | 2020-05-02 | 2021 CBP Plan |  | UNASSIGNED |  | 043432104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117150105 | POLE_DECA_REPL - 4553 CHILES POPE VALLEY | 35134518 |  |  | STS-POLE_DECA_REPL - 4553 CHILES POPE VA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5706 | -122.3915 |  | TIER 2 | 7 | 04343-2104, SILVERADO | FF36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.4 | 24.4 |  |  | 0 | 24.4 | 24.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102262452 | RELW OH PRI INSP JPOL RESD REMT FIRE FLAG ESTR BTKA REAR USA FMOB TER2 | Pole | 2019-12-24 | 2020-02-24 | COMP | 2019-12-24 |  |  | 2019-12-11 | 2019-12-11 | [12 empty] | 2019-05-02 | 2020-05-02 |  | 2020-05-02 | 2021 CBP Plan |  | UNASSIGNED |  | 043432104 | 8854.07 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117150107 | POLE_DECA_REPL - 4340 CHILES POPE VALLEY | 35134520 |  |  | STS-POLE_DECA_REPL - 4340 CHILES POPE VA | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5674 | -122.3861 |  | TIER 2 | 7 | 04343-2104, SILVERADO | FF36 |  | Y | 311 |  |  | 2021-03-11 07:00 | 2021-03-11 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102262471 | RELW OH PRI INSP JPOL RESD REMT FIRE NOAC ESTR REAR USA FMOB TER2 | Pole | 2020-01-13 | 2020-03-02 | COMP | 2020-01-13 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-02 | 2020-05-02 |  | 2020-05-02 | 2021 CBP Plan |  | Concord |  | 043432104 | 12701.03 | 2025.3 | 1906.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117154809 | POLE_DECA_REPL - 4140 CHILES POPE VALLEY | 35134522 |  |  | STS-POLE_DECA_REPL - 4140 CHILES POPE VA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5644 | -122.3803 |  | TIER 2 | 7 | 04343-2104, SILVERADO | FF36 | 525 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 48.6 | 48.6 |  |  | 0 | 48.6 | 48.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102262481 | RELW OH PRI INSP JPOL RESD REMT FIRE NOAC ESTR BTKA REAR USA FMOB TER2 | Pole | 2020-01-13 | 2020-03-10 | COMP | 2020-01-13 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-03 | 2020-05-03 |  | 2020-05-03 | 2021 CBP Plan |  | UNASSIGNED |  | 043432104 | 23527.52 | 2457.9 | 2371.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117154841 | POLE_DECA_REPL - 4140 CHILES POPE VALLEY | 35134525 |  |  | STS-POLE_DECA_REPL - 4140 CHILES POPE VA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5629 | -122.3782 |  | TIER 2 | 7 | 04343-2104, SILVERADO | FF36 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.7 | 24.7 |  |  | 0 | 24.7 | 24.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102262486 | RELW OH PRI INSP JPOL RESD REMT FIRE NOAC SPCR SWRK ESTR REAR USA FMOB TER2 | Pole | 2020-01-10 | 2020-02-24 | COMP | 2020-01-10 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-03 | 2020-05-03 |  | 2020-05-03 | 2021 CBP Plan |  | Concord |  | 043432104 | 7672.79 | 88.7 |  |  |  | 88.7 |  | 88.7 |  | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117155821 | POLE_DECA_REPL - 4128 CHILES POPE VALLEY | 35134527 |  |  | STS-POLE_DECA_REPL - 4128 CHILES POPE VA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5603 | -122.3714 |  | TIER 2 | 7 | 04343-2104, SILVERADO | FF36 | 525 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.2 | 38.2 |  |  | 0 | 38.2 | 38.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102262496 | RELW OH PRI INSP JPOL RESD REMT FIRE NOAC SPCR SWRK ESTR REAR USA WATR FMOB TER2 | Pole | 2020-01-13 | 2020-03-17 | COMP | 2020-01-13 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-03 | 2020-05-03 |  | 2020-05-03 | 2021 CBP Plan |  | Concord |  | 043432104 | 16149.94 | 352.3 |  |  |  | 265.9 |  | 265.9 |  | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117155830 | POLE_DECA_REPL - 4140 CHILES POPE VALLEY | 35134529 |  |  | STS-POLE_DECA_REPL - 4140 CHILES POPE VA | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.562 | -122.3757 |  | TIER 2 | 7 | 04343-2104, SILVERADO | FF36 |  | Y | 311 |  |  | 2021-02-18 07:00 | 2021-02-18 16:00 | Completed | CLICK | [6 empty] | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102262488 | RELW OH PRI INSP JPOL RESD REMT FIRE SPCR SWRK ESTR BTKA REAR USA FMOB TER2 | Pole | 2019-12-18 | 2020-03-31 | COMP | 2019-12-18 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-03 | 2020-05-03 |  | 2020-05-03 | 2021 CBP Plan |  | Concord |  | 043432104 | 9024.6 | 1522.7 | 1436.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117155831 | POLE_DECA_REPL - 4140 CHILES POPE VALLEY | 35134531 |  |  | STS-POLE_DECA_REPL - 4140 CHILES POPE VA | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5625 | -122.3771 |  | TIER 2 | 7 | 04343-2104, SILVERADO | FF36 |  | Y | 311 |  |  | 2021-02-18 07:00 | 2021-02-18 16:00 | Completed | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0.5 | 41.3 | 41.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102262487 | RELW OH PRI INSP JPOL RESD REMT SWRK FIRE NOAC SPCR ESTR REAR USA FMOB TER2 | Pole | 2020-01-10 | 2020-02-24 | COMP | 2020-01-10 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-03 | 2020-05-03 |  | 2020-05-03 | 2021 CBP Plan |  | UNASSIGNED |  | 043432104 | 8033.75 | 126.7 | 38.1 |  |  | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117156820 | POLE_DECA_REPL - 4128 CHILES POPE VALLEY | 35134533 |  |  | STS-POLE_DECA_REPL - 4128 CHILES POPE VA | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5597 | -122.3718 |  | TIER 2 | 7 | 04343-2104, SILVERADO | GG36 |  | Y | 311 |  |  | 2021-02-20 07:00 | 2021-02-20 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102262495 | RELW OH PRI INSP JPOL RESD REMT FIRE NOAC SWRK ESTR BTKA REAR USA WATR FMOB TER2 | Pole | 2020-01-16 | 2020-03-17 | COMP | 2020-01-16 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-03 | 2020-05-03 |  | 2020-05-03 | 2021 CBP Plan |  | UNASSIGNED |  | 043432104 | 8245.15 | 539.9 |  |  |  | 531.9 |  | 531.9 |  | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117177259 | POLE_BROK_REPL - AT HOUSE 2300 BARNETT R | 35225234 |  |  | STS-POLE_BROK_REPL - AT HOUSE 2300 BARNE | ADER | ADER ERDY | Poles | MPP | Not Funded as 2020 Wildfire OII | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.6353 | -122.415 |  | TIER 2 | 7 | 04343-2104, SILVERADO | EE35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102253247 | JAR OH PRI INSP RELW FMOB TER2 SCPA SCOP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | work plan year cleanup 01/21/2021 | 2021-04-30 | Santa Rosa |  | 043432104 | [9 empty] | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-21
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117177272 | POLE_BROK_REPL - ENTRANCE TO 2322 BARNE | 35225233 |  |  |  | ADER | ADER ERDY | Poles | MPP | Not Funded as 2020 Wildfire OII | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.6359 | -122.4189 |  | TIER 2 | 7 | 04343-2104, SILVERADO | EE35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103160184 | OH PRI INSP JAR FMOB TER2 SCPA RELW SCOP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | work plan year cleanup 01/21/2021 | 2021-04-30 | Santa Rosa |  | 043432104 | [9 empty] | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-21
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117260788 | POLE_DECA_REPL - 2W/O ROSSI RD ON CONN V | 35197492 |  |  | 11/7 B REPL POLE 2W/O ROSSI RD ON CO | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5145 | -122.418 |  | TIER 2 | 160 | 04343-2102, SILVERADO | HH35 |  | Y | 311 |  |  | 2021-03-03 07:00 | 2021-03-03 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 45.1 | 42.7 | 2.4 |  | 0 | 45.1 | 42.7 | 2.4 |  | EC | B | Pole | Decayed/Rotten | Replace |  | 102261802 | OH PRI CLR JPOL RESD BTKA RELW REMT ESTR FMOB TER2 PRTO | Pole | 2020-11-18 | 2020-11-24 | COMP | 2020-11-18 | [16 empty] | 2019-05-17 | 2020-05-17 | 2020-11-07 | 2020-11-07 | B tag clean up 8/29/2020 |  | Santa Rosa |  | 043432102 | 16014.61 | 4097.2 | 1566.8 | 1502 | 1502 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Access/Customer Issue | Y | 2020-08-29
North | NB | SAINT HELENA | Napa |  |  | OPEN | 117272836 | POLE_DECA_REPL - F/O 4647 CHILES POPE VA | 35134605 |  |  | STS-POLE_DECA_REPL - F/O 4647 CHILES POP | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5815 | -122.397 |  | TIER 2 | 7 | 04343-2104, SILVERADO | FF36 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 24.6 | 24.6 |  |  | 0 | 24.6 | 24.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102262412 | RELW OH PRI CLR JPOL FIRE ESTR BTKA FMOB TER2 PRTO | Pole | 2020-01-13 | 2020-02-24 | COMP | 2020-01-13 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | 2021 CBP Plan |  | UNASSIGNED |  | 043432104 | 8063.95 | 227.2 | 227.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NB | SAN RAFAEL | San Rafael |  |  | OPEN | 116686335 | POLE_BROK_REPL - 11 DEER PARK AVSAN RAFA | 35090081 |  |  | STS-POLE_BROK_REPL - 11 DEER PARK AVSAN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.9776 | -122.5089 |  | TIER 2 | 473 | 04201-1109, SAN RAFAEL | TT3303 | 5655 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 47.7 | 47.7 |  |  | 0 | 47.7 | 47.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102238006 | RELW OH PRI INSP CLR JPOL RESD FIRE ESTR BTKA REAR USA FMOB TER2 | Pole | 2019-08-20 | 2020-03-02 | COMP | 2019-08-20 |  |  | 2020-02-17 | 2020-03-02 | [12 empty] | 2019-03-08 | 2020-03-08 |  | 2020-03-08 | Q1 Work Plan | 2020-01-31 | QUES |  | 042011109 | 31724.92 | 3373.4 | 74.8 | 74.8 | 74.8 | 1186.6 |  | 1186.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NB | SAN RAFAEL | San Rafael |  |  | OPEN | 117085534 | POLE_BROK_REPL - A/F C/O LAS RAPOSAS RD/ | 35154041 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.0196 | -122.5637 |  | TIER 2 | 219 | 04299-1105, LAS GALLINAS A | SS3206 | 4663 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 61.3 | 61.3 |  |  | 2 | 59.3 | 59.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102246496 | RELW OH PRI CLR JPOL RESD REMT FIRE ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2020-06-15 | 2020-11-06 | COMP | 2020-06-15 |  |  | 2020-11-02 | 2020-11-05 | [12 empty] | 2019-04-23 | 2020-04-23 | 2024-04-21 | 2024-04-21 | 2021 CBP Plan | 2020-05-01 | QUES |  | 042991105 | 28899.58 | 2632.9 |  |  |  | 166.8 |  | 166.8 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | OPEN | 113036918 | POLE_OVRL_REPL - 16578 LAVERNE LN ANDERS | 35233124 |  |  | STS-POLE_OVRL_REPL - 16578 LAVERNE LN AN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-04-19 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.4711 | -122.4427 |  | TIER 2 | 391 | 10344-1101, JESSUP | R2803 | 6955 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | B | Pole | Overloaded | Replace |  | 101465530 | RELW OH PRI INSP RESD ESTR BTKA FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2017-07-11 | 2022-03-15 | 2021-05-17 | 2021-05-17 | B tag clean up 2/19/2021 | 2021-03-14 | Chico |  | 103441101 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | NV | ANDERSON | Redding |  |  | COMP | 116710160 | POLE_BROK_REPL - 19220 HILL STANDERSON96 | 35090832 |  |  | STS-POLE_BROK_REPL - 19220 HILL STANDERS | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-07-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.4632 | -122.3396 |  | TIER 2 | 946 | 10344-1103, JESSUP | R3010 | 728460 | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 24 | 24 |  |  | 60 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101502787 | PRI RELW OH COMP JPOL RESD REMT ESTR BTKA CPGG FMOB TER2 PRTO | Pole | 2019-10-24 | 2019-11-12 | COMP | 2019-10-23 | COMP | 2021-01-06 | [13 empty] | 2021-01-07 | 2021-01-06 | 2020-03-11 |  | 2020-03-11 | Program Manager | 2020-01-31 | EEI |  | 103441103 | 11594.53 | 17846.1 | 15786.4 | 15786.4 | 15786.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
North | NV | ANDERSON | Redding |  |  | COMP | 116718757 | POLE_DECA_REPL - R/O 14895 COBBLESTONE L | 35154062 |  |  | STS-POLE_DECA_REPL - R/O 14895 COBBLESTO | MAPP | MAPP SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.4727 | -122.5091 |  | TIER 2 | 391 | 10344-1101, JESSUP | R26 | 872879 | Y | 311 |  |  | 2021-02-05 | 2021-02-05 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 32.8 | 32.8 |  |  | 40 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101480973 | RELW OH PRI COMP JPOL REMT NOAC ESTR CPGG FMOB TER2 PRTO FSRP | Pole | 2020-04-30 | 2020-04-30 | COMP | 2020-04-30 | COMP | 2021-02-05 | [13 empty] | 2021-02-05 | 2021-02-05 | 2020-03-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | QUES |  | 103441101 | 29339.9 | 3586.6 | 3586.6 | 861 | 861 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | COMP | 116741657 | POLE_BROK_REPL - P\A 15074 HI LO LN.ANDE | 35170987 |  |  | STS-POLE_BROK_REPL - P\A 15074 HI LO LN. | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.4679 | -122.4946 |  | TIER 2 | 391 | 10344-1101, JESSUP | R27 | 4253 | Y | 311 |  |  | 2021-01-14 | 2021-01-14 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 31 | 31 |  |  | 31.5 | 0.9 | 0.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101480951 | RELW OH PRI COMP JPOL ESTR BTKA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-04-17 | 2020-04-17 | COMP | 2020-04-17 | COMP | 2021-01-14 | [13 empty] | 2021-01-15 | 2021-01-14 | 2020-03-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 103441101 | 17098.19 | 9271 | 9271 | 9271 | 9271 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | COMP | 116754652 | POLE_BROK_REPL - 17404 HAWTHORNE AVE AND | 35154173 |  |  | STS-POLE_BROK_REPL - 17404 HAWTHORNE AVE | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.4781 | -122.4104 |  | TIER 2 | 391 | 10344-1101, JESSUP | Q2922 | 1496 | Y | 311 |  |  | 2021-01-07 | 2021-01-07 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 2 | 53 | 53 |  |  | 11 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101464607 | RELW OH PRI JPOL REMT FLAG ESTR BTKA PROG FMOB TER2 PRTO FSRP COMP CPGG | Pole | 2020-10-21 | 2020-12-18 | COMP | 2020-10-21 | COMP | 2021-01-07 | 2020-12-18 | 2020-12-18 | [11 empty] | 2021-01-08 | 2021-01-07 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103441101 | 17499.49 | 20727.5 | 18513.8 | 16374.7 | 16374.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | COMP | 116762201 | POLE_BROK_REPL - 17240 HAWTHORNE AVE 1/W | 35154202 |  |  | STS-POLE_BROK_REPL - 17240 HAWTHORNE AVE | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.4783 | -122.4176 |  | TIER 2 | 391 | 10344-1101, JESSUP | Q2921 | 1496 | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-26 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 44.4 | 44.4 |  |  | 20 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101464589 | RELW OH PRI JPOL REMT FLAG ESTR BTKA PROG FMOB TER2 PRTO FSRP COMP CPGG | Pole | 2020-09-28 | 2020-12-18 | COMP | 2020-09-28 | COMP | 2021-01-07 | 2020-12-18 | 2020-12-18 | [11 empty] | 2021-01-12 | 2021-01-07 | 2020-03-19 |  | 2020-03-19 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103441101 | 10278.6 | 10052.6 | 7096.9 | 7096.9 | 7096.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | COMP | 116792826 | POLE_BROK_REPL - C/O CHINA GULCH DR / SY | 35154292 |  |  | STS-POLE_BROK_REPL - C/O CHINA GULCH DR | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.4901 | -122.4007 |  | TIER 2 | 391 | 10344-1101, JESSUP | Q2918 | 4379 | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-26 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 30.1 | 30.1 |  |  | 60 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101464350 | RELW OH PRI COMP JPOL REMT FLAG ESTR BTKA PROG CPGG FMOB TER2 FSRP PRTO | Pole | 2020-09-10 | 2020-12-17 | COMP | 2020-09-10 | COMP | 2021-01-15 | 2020-12-17 | 2020-12-17 | [11 empty] | 2021-01-15 | 2021-01-15 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103441101 | 15705.76 | 21322.4 | 20602 | 19385.2 | 19385.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | COMP | 116817394 | POLE_BROK_REPL - 15214 CLOVERDALE RD 1PN | 35154432 |  |  | STS-POLE_BROK_REPL - 15214 CLOVERDALE RD | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.4771 | -122.494 |  | TIER 2 | 391 | 10344-1101, JESSUP | Q27 | 5467 | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-26 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 30.1 | 30.1 |  |  | 40 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101460319 | RELW OH PRI PGEA COMP RESD REMT FLAG ESTR BTKA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-09-29 | 2020-12-17 | COMP | 2020-09-29 | COMP | 2021-01-13 | 2020-12-17 | 2020-12-17 | [11 empty] | 2021-01-15 | 2021-01-13 | 2020-03-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103441101 | 8628.41 | 17312.8 | 17312.8 | 12190.4 | 12190.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | COMP | 116824423 | POLE_DECA_REPL - C/O CHINA GULCH RD / KA | 35154479 |  |  | STS-POLE_DECA_REPL - C/O CHINA GULCH RD | MAPP | MAPP SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.4884 | -122.4403 |  | TIER 2 | 391 | 10344-1101, JESSUP | Q2818 | 6959 | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-26 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 30.1 | 30.1 |  |  | 40 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101461655 | RELW PRI OH PGEA COMP RESD ESTR BTKA PROG CPGG FMOB TER2 PRTO FSRP | Pole | 2020-08-18 | 2020-08-18 | COMP | 2020-08-18 | COMP | 2021-02-04 | [13 empty] | 2021-02-05 | 2021-02-04 | 2020-03-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103441101 | 8233.33 | 5043.2 | 3586.6 | 861 | 861 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | COMP | 116877535 | POLE_BROK_REPL - 17041 HAWTHORNE AVEANDE | 35154819 |  |  | STS-POLE_BROK_REPL - 17041 HAWTHORNE AVE | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.4784 | -122.4247 |  | TIER 2 | 391 | 10344-1101, JESSUP | Q2825 | 1496 | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-26 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 58.8 | 58.8 |  |  | 27.5 | 0.8 | 0.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101462369 | RELW OH PRI PGEA JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP CPGG COMP | Pole | 2020-08-25 | 2020-12-18 | COMP | 2020-08-25 | COMP | 2021-01-08 | 2020-12-18 | 2020-12-18 | [11 empty] | 2021-01-08 | 2021-01-08 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103441101 | 21932.4 | 14287.4 | 13799.1 | 12582.3 | 12582.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | COMP | 116877736 | POLE_BROK_REPL - 17240 HAWTHORNE AVE 4/W | 35154831 |  |  | STS-POLE_BROK_REPL - 17240 HAWTHORNE AVE | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.4783 | -122.4205 |  | TIER 2 | 391 | 10344-1101, JESSUP | Q2825 | 1496 | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-26 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 46.1 | 46.1 |  |  | 25 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101462416 | RELW OH PRI PGEA JPOL RESD FLAG ESTR BTKA PROG FMOB TER2 PRTO FSRP COMP CPGG | Pole | 2020-10-28 | 2020-12-18 | COMP | 2020-10-28 | COMP | 2021-01-08 | 2020-12-18 | 2020-12-18 | [11 empty] | 2021-01-08 | 2021-01-08 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103441101 | 11172.71 | 11015.1 | 10134.8 | 10134.8 | 10134.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | COMP | 117113416 | POLE_BROK_REPL - 17113 BLUE HORSE RD.AND | 35170997 |  |  | STS-POLE_BROK_REPL - 17113 BLUE HORSE RD | MAPP | MAPP SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.4636 | -122.4245 |  | TIER 2 | 490 | 10344-1102, JESSUP | R28 | 6951 | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 30.1 | 30.1 |  |  | 25 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101465847 | OH PRI COMP REMT ESTR CPGG FMOB RELW GO BTKA USA TER2 PRTO FSRP | Pole | 2020-04-20 | 2020-04-20 | COMP | 2020-04-20 | COMP | 2021-02-09 | [13 empty] | 2021-02-10 | 2021-02-09 | 2020-04-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 103441102 | 20155.61 | 5479.4 | 5479.5 | 726.6 | 726.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | OPEN | 116637380 | POLE_BROK_REPL - 17638 ANDREA WY.ANDERSO | 35078201 |  |  | STS-POLE_BROK_REPL - 17638 ANDREA WY.AND | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4575 | -122.3939 |  | TIER 2 | 490 | 10344-1102, JESSUP | R2909 | 2377 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 31 | 31 |  |  | 0 | 31 | 31 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101490139 | RELW OH PRI INSP REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-04-16 | 2020-04-16 | COMP | 2020-04-16 | [16 empty] | 2019-03-05 | 2019-09-05 | 2020-09-25 | 2020-09-25 | 2021 CBP Plan |  | Chico |  | 103441102 | 4909.14 | 1070.8 | 1070.8 | 869 | 869 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | OPEN | 116690647 | POLE_DECA_REPL - 5858 HAPPY VALLEY RD AN | 35171172 |  |  | STS-POLE_DECA_REPL - 5858 HAPPY VALLEY R | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4557 | -122.4022 |  | TIER 2 | 490 | 10344-1102, JESSUP | R2913 | 76068 | Y | 311 |  |  | 2021-03-03 07:00 | 2021-03-03 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101490302 | RELW OH PRI JPOL RESD FLAG ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2020-04-29 | 2020-12-18 | COMP | 2020-04-27 |  |  | 2020-12-18 | 2020-12-18 | [12 empty] | 2019-03-09 | 2020-03-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 103441102 | 19736.65 | 1409.5 | 1147.5 | 1147.5 | 1147.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | OPEN | 116691639 | POLE_BROK_REPL - G/P AT 5747 HAPPY VALLE | 35090693 |  |  | STS-POLE_BROK_REPL - G/P AT 5747 HAPPY V | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4518 | -122.4022 |  | TIER 2 | 490 | 10344-1102, JESSUP | R2913 | 76068 | Y | 311 |  |  | 2021-03-03 07:00 | 2021-03-03 16:00 | Scheduled | CLICK | [6 empty] | 31.8 | 31.8 |  |  | 0 | 31.8 | 31.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101490275 | RELW RESD OH SEC PGEA ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-03-16 | 2020-03-16 | COMP | 2020-03-06 |  |  | 2019-05-14 | 2019-05-14 | [12 empty] | 2019-03-09 | 2020-03-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-31 | EEI |  | 103441102 | 3276.79 | 915.6 | 391.1 | 391.1 | 391.1 | 524.5 |  | 524.5 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | OPEN | 116692854 | POLE_LEAN_REPL - 7480 HAPPY VALLEY RD AN | 35153797 |  |  | STS-POLE_LEAN_REPL - 7480 HAPPY VALLEY R | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land JointPole |  |  | 40.4875 | -122.3758 |  | TIER 2 | 391 | 10344-1101, JESSUP | Q3016 | 4429 | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-21 16:00 | Scheduled | CLICK | [6 empty] | 75 | 75 |  |  | 0 | 75 | 75 |  |  | EC | E | Pole | Leaning | Replace |  | 101502752 | RELW OH PRI JPOL REMT ESTR REAR PROG FMOB TER2 PRTO FSRP | Pole | 2021-02-11 |  | COMP | 2021-02-11 | [16 empty] | 2019-03-09 | 2020-03-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103441101 | 29655.82 | 522 | 522 | 522 | 522 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | OPEN | 116709575 | POLE_BROK_REPL - 16218 CLOVERDALE RD.1SA | 35090823 |  |  | STS-POLE_BROK_REPL - 16218 CLOVERDALE RD | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.474 | -122.4559 |  | TIER 2 | 391 | 10344-1101, JESSUP | R2801 | 41356 | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101465431 | RELW OH BTKA PRI REMT ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-02-18 | 2020-02-19 | COMP | 2020-02-14 |  |  | 2019-05-14 | 2019-05-14 | [12 empty] | 2019-03-11 | 2020-03-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-31 | EEI |  | 103441101 | 11835.92 | 1480.2 | 1480.2 | 1480.2 | 1480.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | OPEN | 116734648 | POLE_BROK_REPL - ENT 7070 HWY 273 1/NEAN | 35154091 |  |  | STS-POLE_BROK_REPL - ENT 7070 HWY 273 1/ | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 40.4901 | -122.3599 |  | TIER 2 | 391 | 10344-1101, JESSUP | Q3018 | 68362 | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-21 16:00 | Scheduled | CLICK | [6 empty] | 46.8 | 46.8 |  |  | 0 | 46.8 | 46.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101501538 | RELW PRI OH JPOL REMT TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-22 |  | COMP | 2021-02-22 | [16 empty] | 2019-03-14 | 2020-03-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103441101 | 12318.38 | 1498.3 | 129.6 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | OPEN | 116735018 | POLE_DECA_REPL - A\F 15795 CLOVER DALE R | 35170990 |  |  | STS-POLE_DECA_REPL - A\F 15795 CLOVER DA | CONS | CONS ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4738 | -122.4716 |  | TIER 2 | 391 | 10344-1101, JESSUP | R2704 | 5343 | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101481279 | RELW PRI OH RESD REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-04-17 | 2020-12-18 | COMP | 2020-04-17 |  |  | 2020-12-18 | 2020-12-18 | [12 empty] | 2019-03-14 | 2020-03-14 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan |  | UNASSIGNED |  | 103441101 | 19227.7 | 4280.9 | 4018.9 | 4018.9 | 4018.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | OPEN | 116741206 | POLE_DECA_REPL - 7N/0 3E/O 7186 RENSHAW | 35154125 |  |  | STS-POLE_DECA_REPL - 7N/0 3E/O 7186 RENS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4918 | -122.4526 |  | TIER 2 | 391 | 10344-1101, JESSUP | Q2817 | 4215 | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | [6 empty] | 31.8 | 31.8 |  |  | 0 | 31.8 | 31.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101461612 | RELW OH PRI PGEA REMT NOAC ESTR PROG FMOB FSRP PRTO TER2 | Pole | 2020-04-29 | 2020-04-29 | COMP | 2020-04-29 | [16 empty] | 2019-03-15 | 2020-03-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | QUES |  | 103441101 | 5319.98 | 726.6 | 726.6 | 726.6 | 726.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | OPEN | 116751622 | POLE_BROK_REPL - 6574 HWY 273.ANDERSON96 | 35202130 |  |  | STS-POLE_BROK_REPL - 6574 HWY 273.ANDERS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.4779 | -122.3419 |  | TIER 2 | 391 | 10344-1101, JESSUP | Q3025 | 9002 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | [6 empty] | 56.7 | 56.7 |  |  | 0 | 56.7 | 56.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101500178 | RELW OH PRI JPOL REMT TRAF FLAG ESTR TER2 BTKA PROG FMOB PRTO FSRP | Pole | 2021-01-25 |  | COMP | 2021-01-25 |  |  |  | 2021-02-01 | [12 empty] | 2019-03-17 | 2020-03-17 | 2020-11-17 | 2020-11-17 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103441101 | 17109.73 | 995.6 | 651.6 | 522 | 522 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | OPEN | 116861462 | POLE_BROK_REPL - A/T16337 HAWTHORNE AVE | 35154658 |  |  | STS-POLE_BROK_REPL - A/T16337 HAWTHORNE | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4779 | -122.4496 |  | TIER 2 | 391 | 10344-1101, JESSUP | Q2822 | 10851 | Y | 311 |  |  | 2021-04-12 07:00 | 2021-04-16 16:00 | Reserved | CLICK | [6 empty] | 62.4 | 62.4 |  |  | 0 | 62.4 | 62.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101461824 | RELW OH PRI PGEA JPOL FMOB RESD ESTR BTKA TER2 PRTO FSRP | Pole | 2020-07-17 | 2020-09-10 | COMP | 2020-07-17 |  |  | 2020-05-18 | 2020-05-18 | [12 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-07-31 | QUES |  | 103441101 | 17829.77 | 489.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | ANDERSON | Redding |  |  | OPEN | 117227279 | POLE_BURN_REPL - SE C/O CANYON RD / CHIN | 35154785 |  |  | STS-POLE_BURN_REPL - SE C/O CANYON RD / | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4884 | -122.3933 |  | TIER 2 | 391 | 10344-1101, JESSUP | Q2919 | 9753 | Y | 311 |  |  | 2021-04-07 07:00 | 2021-04-07 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Burnt | Replace |  | 101464424 | RELW OH PRI FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-08-25 | 2020-12-18 | COMP | 2020-08-25 |  |  | 2020-12-18 | 2020-12-18 | [12 empty] | 2019-05-12 | 2019-11-12 | 2024-05-10 | 2024-05-10 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103441101 | 23160.45 | 4796.5 | 4048.2 | 2831.4 | 2831.4 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | ANDERSON | Redding |  |  | OPEN | 117297184 | POLE_BROK_REPL - 4786 ST.YNEZ/LASSEN @HO | 35215565 |  |  | STS-POLE_BROK_REPL - 4786 ST.YNEZ/LASSEN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4273 | -122.4448 |  | TIER 2 | 490 | 10344-1102, JESSUP | S28 | 6379 | Y | 311 |  |  | 2021-04-19 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 68.5 | 68.5 |  |  | 0 | 68.5 | 68.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101492174 | RELW OH PRI REMT ESTR BTKA USA FSRP FMOB TER2 PRTO | Pole | 2021-02-02 | 2021-02-02 | COMP | 2021-02-02 | [16 empty] | 2019-05-21 | 2020-05-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103441102 | 16278.42 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | BANGOR | Oroville |  |  | OPEN | 117841747 | POLE_DECA_REPL - 278 SUNNY HILLS RD W/TR | 35216472 |  |  | STS-POLE_DECA_REPL - 278 SUNNY HILLS RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.3797 | -121.4203 |  | TIER 2 | 115 | 10319-1101, BANGOR | J2717 | 661 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100381238 | OH PRI PATR ESTR BTKA FSRP RELW PROG FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-09-04 | 2020-09-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103191101 | 1 | 102.3 | 93.5 | 93.5 | 93.5 |  |  |  | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | BANGOR | Oroville |  |  | OPEN | 115010456 | POLE_BROK_REPL - 1 POLE EAST OF 15811 VI | 35205305 |  |  | STS-POLE_BROK_REPL - 1 POLE EAST OF 1581 | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-12-09 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.4182 | -121.3402 |  | TIER 2 | 115 | 10319-1101, BANGOR | I29 | 1875 | Y | 311 |  |  | 2021-06-09 07:00 | 2021-06-09 16:00 | Dispatched | CLICK | [6 empty] | 24.1 | 24.1 |  |  | 0 | 24.1 | 24.1 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100360513 | PRI OH RELW INSP CLR JPOL RESD GO BTKA FMOB TER2 | Pole | 2020-11-12 | 2020-11-14 | COMP | 2020-11-11 |  |  | 2020-10-29 | 2020-10-29 | [12 empty] | 2018-09-29 | 2019-09-29 | 2021-01-06 | 2021-01-06 | B tag clean up 10/18/2020 |  | Chico |  | 103191101 | 12779.09 | 108679.9 | 2843.2 | 1944.2 | 1944.2 |  |  |  | Electric Distribution | N | 11/2 in MPP Import File | N | Previous Reason Code Submitted - No Action | Y | 2020-10-18
North | NV | BELDEN | Chico |  |  | OPEN | 117127559 | POLE_BROK_REPL - #4N ON LINE A/F CO#7051 | 35215026 |  |  | STS-POLE_BROK_REPL - #4N ON LINE A/F CO# | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.9188 | -121.3239 |  | TIER 2 | 284 | 10221-1102, BUCKS CREEK | P40K | 1245BP | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100403772 | RELW OH PRI CLR REMT SPCR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 102211102 | 1 | 1870.9 | 1870.9 | 701.3 | 701.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | BELDEN | Chico |  |  | OPEN | 117066398 | POLE_BROK_REPL - #1E TABLE MOUNTIAN/HWY | 35137607 |  |  | STS-POLE_BROK_REPL - #1E TABLE MOUNTIAN/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.9379 | -121.3125 |  | TIER 2 | 284 | 10221-1102, BUCKS CREEK | O40 | 1245BP | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.4 | 25.4 |  |  | 80 | 0.8 | 0.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100391578 | RELW OH PRI CLR REMT ESTR FMOB TER2 PRTO | Pole | 2020-03-23 | 2020-06-24 | COMP | 2020-03-23 | [16 empty] | 2019-04-19 | 2019-10-16 | 2020-12-29 | 2020-12-29 | 2021 CBP Plan | 2020-01-29 | ENENG |  | 102211102 | 26031.67 | 27548.5 | 7045.1 | 7045.1 | 7045.1 | 177.3 |  | 177.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | BELLA VISTA | Burney |  |  | COMP | 117183820 | POLE_DECA_REPL - 5NE/O 28103 HWY 299 2 P | 35181255 |  |  | STS-POLE_DECA_REPL - 5NE/O 28103 HWY 299 | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-23 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.7775 | -121.9999 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | K39 | 1649 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 2 | 52.7 | 52.7 |  |  | 15.5 | 51.7 | 51.7 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101474178 | RELW OH PRI INSP COMP NOAC SPCR ESTR CCNT FMOB TER2 | Pole | 2020-07-06 | 2020-07-16 | COMP | 2020-07-06 | COMP | 2021-02-05 | [13 empty] | 2021-02-16 | 2021-02-05 | 2020-05-08 | 2020-08-20 | 2020-08-20 | Per DOT Approved Request ID# 847 from [REDACTED] | 2020-06-23 | Chico |  | 103321101 | 38762.48 | 52697.5 | 38348.9 | 31115.1 | 31115.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-22
North | NV | BELLA VISTA | Burney |  |  | COMP | 117183863 | POLE_DECA_REPL - 5NE/O 28103 HWY 299 2 P | 35181255 |  |  | STS-POLE_DECA_REPL - 5NE/O 28103 HWY 299 | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.7775 | -121.9999 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | K39 | 1649 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 2 | 0 |  |  |  | 15.5 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101474179 | REGW OH PRI INSP COMP CLR CCNT PROG MINR JAR GO FMOB TER2 | Pole | 2020-07-06 | 2020-07-16 | COMP | 2020-07-06 | COMP | 2021-02-05 | [13 empty] | 2021-02-16 | 2021-02-10 | 2020-05-08 |  | 2020-05-08 | Per DOT Approved Request 28586 | 2020-06-23 | Chico |  | 103321101 | 38762.48 | 52697.5 | 38348.9 | 31115.1 | 31115.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2021-01-14
North | NV | BELLA VISTA | Burney |  |  | COMP | 117184298 | POLE_DECA_REPL - 3NE/O 28103 HWY 299BELL | 35179981 |  |  | STS-POLE_DECA_REPL - 3NE/O 28103 HWY 299 | MAPP | MAPP SRDY REDL | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.776 | -122.0028 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | K39 | 1649 | Y | 311 |  |  | 2021-01-16 | 2021-01-16 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 40.8 | 40.8 |  |  | 0 | 0 |  |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101474182 | OH RELW PRI INSP COMP REMT NOAC ESTR CCNT TER2 FMOB | Pole | 2020-06-26 | 2020-06-29 | COMP | 2020-06-26 | COMP | 2021-01-16 | [13 empty] | 2021-01-25 | 2021-01-16 | 2020-05-08 | 2020-08-27 | 2020-08-27 | Per DOT Approved Request ID# 835 from [REDACTED] |  | Chico |  | 103321101 | 23633.4 | 2711.1 | 1222.5 | 1222.5 | 1222.5 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-22
North | NV | BELLA VISTA | Burney |  |  | OPEN | 117153002 | POLE_DECA_REPL - A/F 15900 OAKRUN RDBELL | 35154318 |  |  | STS-POLE_DECA_REPL - A/F 15900 OAKRUN RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.7486 | -122.0207 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | K38 | 1173 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101547159 | RELW OH PRI INSP FIRE TRAF FLAG ESTR FMOB TER2 FSRP | Pole | 2020-09-11 | 2020-10-30 | COMP | 2020-09-11 |  |  | 2020-08-31 | 2020-08-31 | [12 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103321101 | 9295.26 | 1373.8 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | BELLA VISTA | Burney |  |  | OPEN | 117153480 | POLE_DECA_REPL - 16076 OAK RUN RD 1PNBEL | 35154326 |  |  | STS-POLE_DECA_REPL - 16076 OAK RUN RD 1P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.7539 | -122.0237 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | K38 | 1639 | Y | 311 |  |  | 2021-04-19 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 68.7 | 68.7 |  |  | 0 | 68.7 | 68.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101547163 | RELW OH PRI GO INSP RESD ESTR BTKA FMOB TER2 FSRP | Pole | 2021-02-01 | 2021-02-01 | COMP | 2021-02-01 | [16 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103321101 | 16736.02 | 1739.1 |  |  |  | 177.3 |  | 177.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | BELLA VISTA | Burney |  |  | OPEN | 117161327 | POLE_BROK_REPL - 1SE/O C O 6063 BUZZARD | 35154366 |  |  | STS-POLE_BROK_REPL - 1SE/O C O 6063 BUZZ | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.7674 | -121.97 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | K39 | 6573 | Y | 311 |  |  | 2021-04-19 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 62.4 | 62.4 |  |  | 0 | 62.4 | 62.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101474251 | RELW OH PRI INSP CLR ESTR FMOB TER2 | Pole | 2021-01-29 |  | COMP | 2021-01-29 | [16 empty] | 2019-05-04 | 2019-11-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103321101 | 12099.62 | 88.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | BELLA VISTA | Burney |  |  | OPEN | 117165078 | POLE_DECA_REPL - 27274 299 BELLA VISTA | 35154395 |  |  | STS-POLE_DECA_REPL - 27274 299BELLA VIST | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.7511 | -122.0411 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | K38 | 1639 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101548086 | RELW OH PRI INSP RESD FIRE ESTR GO REAR FMOB TER2 FSRP | Pole | 2020-09-17 | 2020-09-17 | COMP | 2020-09-17 | [16 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103321101 | 18943.99 | 3565.7 | 1279.2 | 32.4 | 32.4 | 628.5 |  | 628.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | BELLA VISTA | Redding |  |  | OPEN | 116751510 | POLE_BROK_REPL - 1N/O 11603 DESCHUTES RD | 35145235 |  |  | STS-POLE_BROK_REPL - 1N/O 11603 DESCHUTE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.6262 | -122.2339 |  | TIER 2 | 226 | 10335-1104, DESCHUTES | N3318 | 3657 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101459179 | RELW OH PRI JPOL FIRE TRAF FLAG ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2020-01-02 | 2020-01-03 | [12 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28593 | 2020-12-31 | QUES |  | 103351104 | 1 | 44.3 | 0 | 978 | 978 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
North | NV | BELLA VISTA | Redding |  |  | OPEN | 117144348 | POLE_DECA_REPL - 16057 OAK RUN RD @ HOUE | 35154298 |  |  | STS-POLE_DECA_REPL - 16057 OAK RUN RD @ | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.7526 | -122.0222 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | K38 | 1631 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101547147 | RELW OH PRI INSP RESD REMT ESTR REAR FMOB TER2 FSRP | Pole | 2020-08-28 | 2020-08-28 | COMP | 2020-08-28 | [16 empty] | 2019-05-02 | 2020-05-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103321101 | 23266.32 | 1778.1 | 1216.8 |  |  | 561.4 |  | 561.4 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | BLAIRSDEN-GRAEAGLE | Grass Valley |  |  | OPEN | 117400175 | POLE_BROK_REPL - 24N/O 3NE/O C/O 7971MM | 35154637 |  |  | STS-POLE_BROK_REPL - 24N/O 3NE/O C/O 797 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.7172 | -120.6568 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | B18 | 9045 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.8 | 41.8 |  |  | 10 | 40.8 | 40.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100111888 | RELW OH PRI CLR REMT FIRE ESTR FMOB TER2 PRTO | Pole | 2020-06-09 | 2020-08-21 | COMP | 2020-06-09 | [16 empty] | 2019-06-05 | 2020-06-05 |  | 2020-06-05 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 152101101 | 25065.97 | 10789.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | BLAIRSDEN-GRAEAGLE | Grass Valley |  |  | OPEN | 117400205 | POLE_BROK_REPL - 24N/O 3NE/O C/O 7971MM | 35154643 |  |  | STS-POLE_BROK_REPL - 24N/O 3NE/O C/O 797 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.7181 | -120.6569 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | B18 | 9045 | Y | 311 |  |  | 2021-06-01 07:00 | 2021-06-01 16:00 | Scheduled | CLICK | [6 empty] | 40.9 | 40.9 |  |  | 0 | 40.9 | 40.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100103525 | RELW CLR OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-06-30 | 2020-08-21 | COMP | 2020-06-30 | [16 empty] | 2019-06-05 | 2020-06-05 |  | 2020-06-05 | 2021 CBP Plan | 2020-12-31 | CALENG |  | 152101101 | 28376.42 | 2522.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | BURNEY | Burney |  |  | OPEN | 110772467 | POLE_LEAN_REPL - 17 POLES E/O HIGH WATER | 35198934 |  |  | STS-POLE_LEAN_REPL - 17 POLES E/O HIGH W | UNSC | UNSC SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-27 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 41.0102 | -121.7041 |  | TIER 2 | 655 | 10373-2101, PIT NO 3 | F46 | 354683 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 30.3 | 30.3 |  |  | 0 | 30.3 | 30.3 |  |  | EC | B | Pole | Leaning | Replace |  | 101515031 | RELW OH PRI INSP REMT NOAC TER2 FSRP | Pole | 2020-12-17 | 2021-01-12 | COMP | 2020-12-17 | [16 empty] | 2015-10-16 | 2020-04-11 | 2021-02-24 | 2021-02-24 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103732101 | 26822.13 | 2478.5 | 1429.3 | 549 | 549 |  |  |  | FRMMA/WMPMA - Electric | Y | Pulled from MPP Import File | N |  | Y | 2020-08-25
North | NV | BURNEY | Burney |  |  | OPEN | 117033350 | POLE_DECA_REPL - 5N/O A/F 20806 BLACK RA | 35202245 |  |  | STS-POLE_DECA_REPL - 5N/O A/F 20806 BLAC | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 40.895 | -121.6499 |  | TIER 2 | 1978 | 10331-1102, BURNEY | H47 | 7731 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101520754 | RELW OH PRI PGEA REMT TRAF ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103311102 | 1 | 4122.7 | 1423.3 | 1423.3 | 1423.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | BURNEY | Burney |  |  | OPEN | 117121065 | POLE_DECA_REPL - 9 W/O SECT 1442BURNEY96 | 35202315 |  |  | STS-POLE_DECA_REPL - 9 W/O SECT 1442BURN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.9274 | -121.6717 |  | TIER 2 | 1978 | 10331-1102, BURNEY | G47 | 1442 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 50.6 | 50.6 |  |  | 0 | 50.6 | 50.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103018181 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-09 | 2021-02-09 | COMP | 2021-02-09 | [16 empty] | 2019-04-29 | 2020-04-29 | 2020-11-08 | 2020-11-08 | 2021 CBP Plan | 2021-02-28 | QUES |  | 103311102 | 11999.69 | 467.9 | 0 | 203.7 | 203.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | BURNEY | Burney |  |  | OPEN | 117178613 | POLE_DECA_REPL - 14W/O C/O#8829 ON APPLE | 35202521 |  |  | STS-POLE_DECA_REPL - 14W/O C/O#8829 ON A | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.9262 | -121.6762 |  | TIER 2 | 1978 | 10331-1102, BURNEY | G46 | 8829 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 52.2 | 52.2 |  |  | 0 | 52.2 | 52.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101515691 | RELW OH PRI PGEA REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-18 | 2021-02-18 | COMP | 2021-02-18 | [16 empty] | 2019-05-07 | 2020-05-07 | 2020-11-22 | 2020-11-22 | 2021 CBP Plan | 2021-02-28 | QUES |  | 103311102 | 9713.72 | 242.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | BURNEY | Burney |  |  | OPEN | 117214521 | POLE_DECA_REPL - R/OBURNEY96013 | 35202591 |  |  | STS-POLE_DECA_REPL - R/OBURNEY96013 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.9999 | -121.6327 |  | TIER 2 | 655 | 10373-2101, PIT NO 3 | F4710 | 7903 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101516487 | RELW OH PRI JPOL REMT ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-11 | 2020-05-11 | 2020-11-22 | 2020-11-22 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103732101 | 1 | 80.7 | 0 | 271.5 | 271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | BURNEY | Burney |  |  | OPEN | 117221883 | POLE_DECA_REPL - R/O 21658 COTTONWOOD ST | 35214826 |  |  | STS-POLE_DECA_REPL - R/O 21658 COTTONWOO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.9175 | -121.6249 |  | TIER 2 | 1978 | 10331-1102, BURNEY | H4801 | 1340 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 90.1 | 90.1 |  |  | 0 | 90.1 | 90.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101515566 | RELW OH PRI JPOL RESD ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-25 |  | COMP | 2021-01-25 | [16 empty] | 2019-05-13 | 2020-05-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103311102 | 25394.19 |  | 0 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | BURNEY | Burney |  |  | OPEN | 117271520 | POLE_BROK_REPL - 1N/O 4S/O CO#4789 BURNE | 35202918 |  |  | STS-POLE_BROK_REPL - 1N/O 4S/O CO#4789 B | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 41.2001 | -121.6839 |  | TIER 2 | 655 | 10373-2101, PIT NO 3 | A4619 | 479 | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-21 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101517607 | RELW OH PRI REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2020-12-24 | 2020-12-24 | [12 empty] | 2019-05-18 | 2020-05-18 | 2020-11-30 | 2020-11-30 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103732101 | 1 |  | 0 | 271.5 | 271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | Burney | Burney |  |  | OPEN | 119054144 | POLE_DECA_REPL - A/F 20238 COVE RDBurney | 35220967 |  |  | STS-POLE_DECA_REPL - A/F 20238 COVE RDBU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.8726 | -121.9275 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | I40 | 8159 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 73.7 | 72.5 | 1.2 |  | 0 | 73.7 | 72.5 | 1.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101547718 | OH RELW PRI INSP ESTR FMOB TER2 | Pole | 2021-01-19 | 2021-01-27 | COMP | 2021-01-14 | [16 empty] | 2020-05-21 | 2021-05-21 |  | 2021-05-21 | Work Plan Reconcilation (B-Tags) |  | Chico |  | 103321101 | 31385.72 | 267.5 | 267.5 | 267.5 | 267.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-07-21
North | NV | CHICO | Chico |  |  | OPEN | 116984717 | POLE_DECA_REPL - 9106 COHASSET CHICO | 35154273 |  |  | STS-POLE_DECA_REPL - 9106 COHASSET CHICO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-01-20 | Renew Permit | 39.8987 | -121.7424 |  | TIER 2 | 123 | 10297-1111, SYCAMORE CREEK | P3022 | 16859 | Y | 311 |  |  | 2021-03-16 07:00 | 2021-03-16 16:00 | Scheduled | CLICK | [6 empty] | 51.1 | 51.1 |  |  | 0 | 51.1 | 51.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100432693 | RELW OH PRI INSP CLR JPOL FIRE FLAG ESTR GO BTKA USA PROG FMOB TER2 | Pole | 2020-05-13 | 2020-10-20 | COMP | 2020-05-13 |  |  | 2020-06-09 | 2020-10-20 | [12 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 102971111 | 29757.1 | 548.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | CORNING | Red Bluff |  |  | OPEN | 117229975 | POLE_BROK_REPL - 12NW/O 7S/O 6600 BOGGS | 35150041 |  |  | STS-POLE_BROK_REPL - 12NW/O 7S/O 6600 BO | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.9893 | -122.4046 |  | TIER 2 | 60 | 10333-1101, CORNING | BB29 | 850063 | Y | 311 |  |  | 2021-03-18 07:00 | 2021-03-18 16:00 | Scheduled | CLICK | [6 empty] | 56.5 | 56.5 |  |  | 0 | 56.5 | 56.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101522961 | RELW OH PRI REMT FIRE NOAC SWRK ESTR GO FMOB TER2 PRTO | Pole | 2020-04-28 | 2020-04-28 | COMP | 2020-04-28 | [16 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | circuit based plan 2.14 | 2020-04-10 | QUES |  | 103331101 | 10919.93 | 1061.1 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | CORNING | Red Bluff |  |  | OPEN | 117276148 | POLE_DECA_REPL - 16400 PASKENTA RD. CORN | 35150081 |  |  | STS-POLE_DECA_REPL - 16400 PASKENTA RD. | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 39.9253 | -122.4273 |  | TIER 2 | 29 | 10333-1102, CORNING | DD28 | 1893 | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-21 16:00 | Reserved | CLICK | [6 empty] | 31 | 31 |  |  | 0 | 31 | 31 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101522266 | RELW OH PRI JPOL REMT FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-20 | 2020-05-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103331102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | CORNING | Red Bluff |  |  | OPEN | 117281030 | POLE_DECA_REPL - #2 ON LINE E/O #3S 1664 | 35215447 |  |  | STS-POLE_DECA_REPL - #2 ON LINE E/O #3S | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.9178 | -122.4098 |  | TIER 2 | 29 | 10333-1102, CORNING | DD29 | 6185 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 65.2 | 65.2 |  |  | 0 | 65.2 | 65.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101521981 | RELW OH PRI REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-21 | 2021-01-21 | COMP | 2021-01-21 | [16 empty] | 2019-05-20 | 2020-05-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103331102 | 12483.14 | 348 | 348 | 1326 | 1326 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | Corning | Red Bluff |  |  | OPEN | 119116144 | POLE_BROK_REPL - 1N/O C/O ROBIN HILL RD. | 35220968 |  |  | STS-POLE_BROK_REPL - 1N/O C/O ROBIN HILL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.0113 | -122.4013 |  | TIER 2 | 60 | 10333-1101, CORNING | BB2907 | 4275 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 55.2 | 54 | 1.2 |  | 0 | 55.2 | 54 | 1.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101523987 | OH RELW PRI INSP ESTR FMOB TER2 | Pole | 2021-01-16 | 2021-01-16 | COMP | 2021-01-16 |  |  | 2021-01-15 | 2021-01-15 | [12 empty] | 2020-06-02 | 2021-06-02 |  | 2021-06-02 | B-Tag Addition 06.24.20 |  | Chico |  | 103331101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-06-29
North | NV | COTTONWOOD | Red Bluff |  |  | OPEN | 116735401 | POLE_BROK_REPL-1S/W 17455 BIG BEAR LNC | 35202129 |  |  | STS-POLE_BROK_REPL-1S/W 17455 BIG BEAR L | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 40.3009 | -122.3659 |  | TIER 2 | 372 | 10293-1103, COTTONWOOD | U3022 | 1927 | Y | 311 |  |  | 2021-03-18 07:00 | 2021-03-18 16:00 | Scheduled | CLICK | [6 empty] | 44.8 | 44.8 |  |  | 0 | 44.8 | 44.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101509584 | RELW OH PRI INSP REMT FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2021-01-13 |  | COMP | 2021-01-13 | [16 empty] | 2019-03-14 | 2020-03-14 | 2020-11-04 | 2020-11-04 | 2021 CBP Plan | 2021-02-28 | QUES |  | 102931103 | 7057.82 | 1104.9 | 680 | 1744.1 | 1744.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Red Bluff |  |  | OPEN | 116964220 | POLE_BROK_REPL - 17400 HOOKER CRK RD (@ | 35202135 |  |  | STS-POLE_BROK_REPL - 17400 HOOKER CRK RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.3056 | -122.3229 |  | TIER 2 | 372 | 10293-1103, COTTONWOOD | U31 | 9639 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 31.1 | 31.1 |  |  | 0 | 31.1 | 31.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101510705 | RELW OH PRI INSP CLR REMT FIRE NOAC SPCR ESTR GO FSRP TER2 USA FMOB | Pole | 2020-12-10 | 2020-12-10 | COMP | 2020-12-10 | [16 empty] | 2019-04-05 | 2020-04-05 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-02-28 | QUES |  | 102931103 | 29826.83 | 2439 | 582.9 | -116.4 | -116.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Red Bluff |  |  | OPEN | 117001223 | POLE_BROK_REPL - 17100 12 S/O HOKEER CK | 35202178 |  |  | STS-POLE_BROK_REPL - 17100 12 S/O HOKEER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.294 | -122.3086 |  | TIER 2 | 372 | 10293-1103, COTTONWOOD | V31 | 9643 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101510904 | RELW OH PRI INSP REMT NOAC ESTR FSRP TER2 FMOB | Pole | 2021-01-11 | 2021-01-11 | COMP | 2021-01-11 | [16 empty] | 2019-04-10 | 2020-04-10 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-02-28 | QUES |  | 102931103 | 4855.44 | 680 | 680 | 1474.8 | 1474.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Red Bluff |  |  | OPEN | 117116096 | POLE_BROK_REPL - 19 W/0 8361 HWY36 COTTO | 35214898 |  |  | STS-POLE_BROK_REPL - 19 W/0 8361 HWY36 C | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 40.3303 | -122.8422 |  | TIER 2 | 358 | 10361-1101, WILDWOOD | U18 | 3253 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 44.6 | 44.6 |  |  | 0 | 44.6 | 44.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101497326 | RELW OH PRI INSP JPOL REMT ESTR FMOB TER2 FSRP | Pole | 2021-01-27 | 2021-01-26 | COMP | 2021-01-26 | [16 empty] | 2019-04-27 | 2020-04-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103611101 | 6149.2 | 433.3 | 129.6 | 978 | 978 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Red Bluff |  |  | OPEN | 117116164 | POLE_DECA_REPL - 20 W/02255 HWY 36 COTTO | 35214903 |  |  | STS-POLE_DECA_REPL - 20 W/02255 HWY 36 C | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.3203 | -122.8215 |  | TIER 2 | 358 | 10361-1101, WILDWOOD | U19 | 3253 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 56 | 56 |  |  | 0 | 56 | 56 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101497029 | PRI RELW OH INSP JPOL REMT ESTR FMOB TER2 FSRP | Pole | 2021-02-17 | 2021-02-19 | COMP | 2021-02-16 |  |  | 2021-02-19 | 2021-02-19 | [12 empty] | 2019-04-27 | 2020-04-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103611101 | 13451.34 | 677.6 | 374 | 374 | 374 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Redding |  |  | OPEN | 120535072 | TREE_DECA_INPL - 3341 MANSEE DR COTTONWO | 35233126 |  |  | STS-TREE_DECA_INPL - 3341 MANSEE DR COTT | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-04-17 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.3841 | -122.4657 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | T2705 | 10045 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | B | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 101491875 | RELW OH SERV TMAN JPOL RESD REMT ESTR BTKA USA TER2 | Pole |  |  | REQD | [17 empty] | 2021-02-15 | 2021-05-15 |  | 2021-05-15 | B tag clean up 2/19/2021 | 2021-03-14 | Chico |  | 102931102 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | NV | COTTONWOOD | Redding |  |  | COMP | 116679420 | POLE_DECA_REPL - 17 E/O 4309 BLACK PINE | 35090783 |  |  | STS-POLE_DECA_REPL - 17 E/O 4309 BLACK P | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.4134 | -122.5071 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | S26 | 9479 | Y | 311 |  |  |  |  | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 25.8 | 25.8 |  |  | 34 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101491567 | RELW OH PRI COMP JPOL CPGG FMOB REMT ESTR BTKA TER2 PRTO FSRP | Pole | 2019-10-16 | 2020-12-30 | COMP | 2019-10-15 | COMP | 2021-01-07 | 2020-12-30 | 2020-12-30 | [11 empty] | 2021-01-08 | 2021-01-07 | 2020-03-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-31 | EEI |  | 102931102 | 10510.58 | 11604.8 | 9763.5 | 9763.5 | 9763.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Redding |  |  | COMP | 119820145 | POLE_BROK_REPL - 21953 STONEY CREEK PLAC | 35204359 |  |  | STS-POLE_BROK_REPL - 21953 STONEY CREEK | FICL | FICL SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-11-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.3592 | -122.2193 |  | TIER 2 | 372 | 10293-1103, COTTONWOOD | T3320 | 2045 | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 31.8 | 31.8 |  |  | 68.5 | 0.8 | 0.8 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101510213 | OH RELW PRI JPOL PUBL RESD FIRE ESTR BTKA USA CTMN FMOB TER2 CPGG COMP | Pole | 2020-11-25 | 2020-12-14 | COMP | 2020-11-24 | COMP | 2021-01-06 | 2020-11-30 | 2020-11-30 | [11 empty] | 2021-01-08 | 2021-01-06 | 2020-12-28 |  | 2020-12-28 | B tag clean up 10/4/2020 |  | Chico |  | 102931103 | 19320.75 | 24733.4 | 20927.5 | 20927.5 | 20927.5 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N |  | Y | 2020-10-04
North | NV | COTTONWOOD | Redding |  |  | OPEN | 116628697 | POLE_BROK_REPL - 2N/O 3958 HAPPY VALLEY | 35078139 |  |  | STS-POLE_BROK_REPL - 2N/O 3958 HAPPY VAL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.4026 | -122.4081 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | S2917 | 1693 | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Scheduled | CLICK | [6 empty] | 32 | 32 |  |  | 0 | 32 | 32 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101482110 | RELW OH PRI PGEA JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2019-05-14 | 2019-05-14 | [12 empty] | 2019-03-03 | 2019-09-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | QUES |  | 102931102 | 1 | 1282.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Redding |  |  | OPEN | 116629604 | POLE_BROK_REPL - 3W /O 2SW/O C/O HAPPY V | 35078128 |  |  | STS-POLE_BROK_REPL - 3W /O 2SW/O C/O HAP | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.4021 | -122.4106 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | S2917 | 8645 | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Dispatched | CLICK | [6 empty] | 32 | 32 |  |  | 0 | 32 | 32 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101482116 | RELW OH PRI JPOL REMT ESTR BTKA FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-03-03 | 2019-09-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Chico |  | 102931102 | 1 | 1566.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Redding |  |  | OPEN | 116630992 | POLE_BROK_REPL - N/O 7952 ETIWANDA RDCOT | 35090552 |  |  | STS-POLE_BROK_REPL - N/O 7952 ETIWANDA R | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.3971 | -122.3894 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | S2919 | 2065 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101482150 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-04 | 2020-03-04 | 2020-07-09 | 2020-07-09 | 2021 CBP Plan | 2020-10-31 | EEI |  | 102931102 | 1 | 41.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Redding |  |  | OPEN | 116631388 | POLE_BROK_REPL - PG-E POLE .P1518COTTONW | 35202092 |  |  | STS-POLE_BROK_REPL - PG-E POLE .P1518COT | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.397 | -122.3877 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | S2919 | 2065 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 70.4 | 70.4 |  |  | 0 | 70.4 | 70.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101482147 | RELW OH PRI JPOL REMT ESTR GO BTKA RTRN FMOB TER2 PRTO FSRP | Pole | 2021-02-08 |  | COMP | 2021-02-08 |  |  | 2021-02-10 | 2021-02-10 | [12 empty] | 2019-03-04 | 2020-03-04 | 2020-07-09 | 2020-07-09 | 2021 CBP Plan | 2021-01-31 | QUES |  | 102931102 | 19929.1 | 1037.1 | 1037.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Redding |  |  | OPEN | 116632449 | POLE_DECA_REPL - 3469 CARRIAGE/GAS PT RD | 35214560 |  |  | STS-POLE_DECA_REPL - 3469 CARRIAGE/GAS P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.3869 | -122.4476 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | S2822 | 1578 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101491931 | RELW OH PRI JPOL REMT ESTR FMOB BTKA RTRN PROG TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-04 | 2020-03-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 102931102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Redding |  |  | OPEN | 116639454 | POLE_DECA_REPL - C/O 8 W/O FOSTER RDCOTT | 35090666 |  |  | STS-POLE_DECA_REPL - C/O 8 W/O FOSTER RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.397 | -122.5276 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | S26 | 2625 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101491446 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2019-05-14 | 2019-05-14 | [12 empty] | 2019-03-05 | 2020-03-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | EEI |  | 102931102 | 1 | 2940.4 | 1480.3 | 1480.3 | 1480.3 | 953.6 |  | 953.6 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Redding |  |  | OPEN | 116639455 | POLE_DECA_REPL - C/O 10 W/O 1 S/O COX RD | 35090670 |  |  | STS-POLE_DECA_REPL - C/O 10 W/O 1 S/O CO | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.3955 | -122.5294 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | S26 | 2625 | Y | 311 |  |  | 2021-03-18 07:00 | 2021-03-18 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 32.8 | 32.8 |  |  | 0 | 32.8 | 32.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101491449 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2019-10-29 | 2019-12-19 | COMP | 2019-10-28 | [16 empty] | 2019-03-05 | 2020-03-05 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2020-01-31 | EEI |  | 102931102 | 13041.29 | 2433 | 1480.3 | 1480.3 | 1480.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Redding |  |  | OPEN | 116672870 | POLE_BROK_REPL - 4 E/O 14170 BLACK PINE | 35214564 |  |  | STS-POLE_BROK_REPL - 4 E/O 14170 BLACK P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.4133 | -122.5177 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | S26 | 9479 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101491601 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-06 | 2020-03-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 102931102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Redding |  |  | OPEN | 116672871 | POLE_BROK_REPL - 5E/0 14170 GAS PT RD CO | 35214567 |  |  | STS-POLE_BROK_REPL - 5E/0 14170 GAS PT R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.4147 | -122.5228 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | S26 | 9479 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101491613 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-06 | 2020-03-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 102931102 | 1 | 129.6 | 129.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Redding |  |  | OPEN | 116678970 | POLE_BROK_REPL - 14460 GAS PT RD COTTONW | 35214570 |  |  | STS-POLE_BROK_REPL - 14460 GAS PT RD COT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.4058 | -122.5149 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | S26 | 10049 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 28.5 | 30 | 30 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101491493 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-06 | 2020-03-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 102931102 | 1 | 14307.3 | 129.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Redding |  |  | OPEN | 116736048 | POLE_DECA_REPL - . COTTONWOOD | 35110570 |  |  | STS-POLE_DECA_REPL - . COTTONWOOD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.392 | -122.3164 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | S3123 | 11033 | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Dispatched | CLICK | [6 empty] | 67.2 | 67.2 |  |  | 0 | 67.2 | 67.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103161363 | RELW OH PRI JPOL REMT NOAC ESTR GO REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-31 |  | COMP | 2021-01-31 |  |  | 2019-06-24 | 2019-06-24 | [12 empty] | 2019-03-14 | 2019-09-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | Chico |  | 102931102 | 14898.98 | 1923 | 906.3 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Redding |  |  | OPEN | 116747010 | POLE_DECA_REPL - 18362 CHERYL LN 1SE COT | 35137656 |  |  | STS-POLE_DECA_REPL - 18362 CHERYL LN 1SE | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.327 | -122.4202 |  | TIER 2 | 372 | 10293-1103, COTTONWOOD | U2810 | 4797 | Y | 311 |  |  | 2021-04-19 07:00 | 2021-04-23 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 31.8 | 31.8 |  |  | 0 | 31.8 | 31.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101511442 | RELW OH PRI INSP JPOL REMT SPCR ESTR BTKA REAR USA FMOB TER2 FSRP | Pole | 2020-04-06 | 2020-06-09 | COMP | 2020-04-06 | [16 empty] | 2019-03-14 | 2020-03-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-29 | ENENG |  | 102931103 | 4841.35 | 726.6 | 726.6 | 726.6 | 726.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Redding |  |  | OPEN | 116792268 | POLE_BROK_REPL - 15773 GAS POINT RDCOTTO | 35137666 |  |  | STS-POLE_BROK_REPL - 15773 GAS POINT RDC | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.3846 | -122.4684 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | T2705 | 10045 | Y | 311 |  |  | 2021-04-19 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 31.8 | 31.8 |  |  | 0 | 31.8 | 31.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101491865 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-03-04 | 2020-05-01 | COMP | 2020-03-04 |  |  | 2020-01-02 | 2020-01-02 | [12 empty] | 2019-03-20 | 2020-03-20 |  | 2020-03-20 | Program Manager | 2020-01-29 | ENENG |  | 102931102 | 21956.56 | 1597.8 |  |  |  | 536.5 |  | 536.5 |  | Y | MPP File Only | N |  | Y | 2020-02-20
North | NV | COTTONWOOD | Redding |  |  | OPEN | 116900427 | POLE_DECA_REPL - 3 E/O 14170 BLACK PINE | 35214568 |  |  | STS-POLE_DECA_REPL - 3 E/O 14170 BLACK P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.4128 | -122.5182 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | S26 | 9479 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101491602 | RELW OH PRI REMT SWRK ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-01 | 2020-04-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 102931102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | COTTONWOOD | Redding |  |  | OPEN | 116937300 | POLE_BROK_REPL - #11W 20250 LAKE CALIFOR | 35214576 |  |  | STS-POLE_BROK_REPL - #11W 20250 LAKE CAL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 40.3674 | -122.2482 |  | TIER 2 | 372 | 10293-1103, COTTONWOOD | T33 | 11371 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101510556 | RELW OH PRI INSP JPOL FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-02 | 2020-04-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 102931103 | 1 | 976.9 | 129.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | EAST TEHAMA COUNTY | Red Bluff |  |  | OPEN | 117227453 | POLE_DECA_REPL - 25W/O 1S/O 37785 HWY 36 | 35143596 |  |  | STS-POLE_DECA_REPL - 25W/O 1S/O 37785 HW | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.345 | -121.6428 |  | TIER 2 | 90 | 10254-1101, VOLTA | T47 | 6471 | Y | 311 |  |  | 2021-03-20 07:00 | 2021-03-20 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101556176 | OH RELW PRI INSP JPOL REMT ESTR BTKA FMOB TER2 | Pole | 2020-03-02 | 2020-03-18 | COMP | 2020-03-02 |  |  | 2020-03-18 | 2020-03-18 | [12 empty] | 2019-05-13 | 2020-02-13 | 2020-09-29 | 2020-09-29 | Work Plan Reconcilation (B-Tags) | 2020-02-28 | TRC |  | 102541101 | 8401.31 | 20923.2 | -33345.6 | 1961 | 1961 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-07-21
North | NV | ELK CREEK | Willows |  |  | OPEN | 116849066 | POLE_DECA_REPL - 2833 RD306/SPELK CREEK9 | 35214928 |  |  | STS-POLE_DECA_REPL - 2833 RD306/SPELK CR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.6096 | -122.5352 |  | TIER 2 | 244 | 10278-1101, ELK CREEK | W10K | 37334 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100339517 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 102781101 | 1 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | ELK CREEK | Willows |  |  | OPEN | 115251765 | POLE_BROK_REPL - 1 P S/O C/O 4403 | 35071774 |  |  | STS-POLE_BROK_REPL - 1 P S/O C/O 4403 | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-04-11 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.4241 | -122.532 |  | TIER 2 | 244 | 10278-1101, ELK CREEK | AA11 | 4403 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 62.9 | 62.9 |  |  | 1.5 | 61.4 | 61.4 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100407667 | RELW OH PRI INSP CLR JPOL REMT NOAC ESTR USA FMOB TER2 | Pole | 2019-03-19 | 2019-06-13 | COMP | 2019-03-15 |  |  | 2019-09-24 | 2019-09-24 | [12 empty] | 2018-11-05 | 2019-11-05 | 2021-05-09 | 2021-05-09 | Q1 Work Plan | 2019-03-15 | UNASSIGNED |  | 102781101 | 19426.07 | 4818.7 |  |  |  | 1850.7 |  | 1850.7 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | ELK CREEK | Willows |  |  | COMP | 117025488 | POLE_DECA_REPL - A\F RD 410 ON RD 306 2N | 35154556 |  |  | STS-POLE_DECA_REPL - A\F RD 410 ON RD 30 | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.4859 | -122.5183 |  | TIER 2 | 244 | 10278-1101, ELK CREEK | Z11 | 2002 | Y | 311 |  |  | 2020-11-20 | 2020-11-20 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 30.8 | 30.8 |  |  | 4 | 26.8 | 26.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100407434 | OH RELW PRI COMP CLR JPOL REMT ESTR BTKA CCNT FMOB TER2 PRTO FSRP | Pole | 2020-05-05 | 2020-08-05 | COMP | 2020-05-04 | COMP | 2021-01-14 | 2020-04-27 | 2020-04-27 | [11 empty] | 2021-01-21 | 2021-01-14 | 2020-04-14 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | QUES |  | 102781101 | 12929.24 | 11754.6 | 7871.6 | 7871.6 | 7871.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | FALL RIVER MILLS | Burney |  |  | OPEN | 117066860 | POLE_DECA_REPL - 1NE/0 0/F 2359 FORT CRO | 35215323 |  |  | STS-POLE_DECA_REPL - 1NE/0 0/F 2359 FORT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 41.0042 | -121.4475 |  | TIER 2 | 1973 | 10372-1101, PIT NO 1 | F5203 | 2359 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | [6 empty] | 72.6 | 72.6 |  |  | 0 | 72.6 | 72.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101521495 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-28 | 2021-02-08 | COMP | 2021-01-28 | [16 empty] | 2019-04-19 | 2020-04-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103721101 | 16617.92 | 46.7 | 46.7 | 1024.7 | 1024.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | FALL RIVER MILLS | Burney |  |  | OPEN | 117068656 | POLE_DECA_REPL - A/F 43088 BRIDGE STFALL | 35175187 |  |  | STS-POLE_DECA_REPL - A/F 43088 BRIDGE ST | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 41.0009 | -121.4426 |  | TIER 2 | 1973 | 10372-1101, PIT NO 1 | F5203 | 70952 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | [6 empty] | 32 | 32 |  |  | 1 | 31 | 31 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101521460 | RELW OH PRI FLAG ESTR BTKA REAR FSRP FMOB TER2 PRTO | Pole | 2020-05-15 | 2020-12-30 | COMP | 2020-05-15 |  |  | 2020-12-30 | 2020-12-30 | [12 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | Chico |  | 103721101 | 15379.58 | 221.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | FALL RIVER MILLS | Burney |  |  | OPEN | 117068725 | POLE_DECA_REPL - G/P E/O 43088 BRIDGE ST | 35202401 |  |  | STS-POLE_DECA_REPL - G/P E/O 43088 BRIDG | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 41.0011 | -121.4426 |  | TIER 2 | 1973 | 10372-1101, PIT NO 1 | F5203 | 70952 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | [6 empty] | 39.8 | 39.8 |  |  | 0 | 39.8 | 39.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101521458 | RELW OH SERV FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-14 |  | COMP | 2021-01-14 |  |  | 2021-02-04 | 2021-02-04 | [12 empty] | 2019-04-20 | 2020-04-20 | 2020-11-26 | 2020-11-26 | 2021 CBP Plan | 2021-02-28 | QUES |  | 103721101 | 9809.98 | 80.7 | 0 | 1537.3 | 1537.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | FOREST RANCH | Chico |  |  | OPEN | 116822769 | POLE_DECA_REPL - 10 N\O DEER CDEEK HWY A | 35149696 |  |  | STS-POLE_DECA_REPL - 10 N\O DEER CDEEK H | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.9363 | -121.6472 |  | TIER 2 | 43 | 10303-1102, ORO FINO | P32 | 2040 | Y | 311 |  |  | 2021-04-01 07:00 | 2021-04-01 16:00 | Dispatched | CLICK | [6 empty] | 40.2 | 40.2 |  |  | 3.5 | 40 | 40 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100402120 | RELW OH PRI INSP CLR REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-06-09 | 2020-06-10 | COMP | 2020-04-09 |  |  | 2020-06-09 | 2020-06-09 | [12 empty] | 2019-03-24 | 2020-03-24 |  | 2020-03-24 | circuit based plan 2.14 | 2020-04-10 | CALENG |  | 103031102 | 28634.7 | 5908.9 | 4775.8 | 2798 | 2798 | 315.5 |  | 315.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | FOREST RANCH | Chico |  |  | OPEN | 116822939 | POLE_DECA_REPL - 11N\O C\O DEER CREEK HW | 35149699 |  |  | STS-POLE_DECA_REPL - 11N\O C\O DEER CREE | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.9372 | -121.6478 |  | TIER 2 | 43 | 10303-1102, ORO FINO | P32 | 2040 | Y | 311 |  |  | 2021-04-01 07:00 | 2021-04-01 16:00 | Dispatched | CLICK | [6 empty] | 40.2 | 40.2 |  |  | 0 | 40.2 | 40.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100430949 | RELW OH PRI INSP CLR JPOL REMT FIRE NOAC ESTR USA FMOB TER2 | Pole | 2020-04-09 | 2020-06-09 | COMP | 2020-04-09 |  |  | 2020-06-09 | 2020-06-09 | [12 empty] | 2019-03-24 | 2020-03-24 |  | 2020-03-24 | circuit based plan 2.14 | 2020-04-10 | CALENG |  | 103031102 | 29907.43 | 3007.3 | 1814.9 | 1233.4 | 1233.4 | 240.6 |  | 240.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | FOREST RANCH | Chico |  |  | OPEN | 117142267 | POLE_DECA_REPL - 52S/O C/O HUMBOLDT RD O | 35149707 |  |  | STS-POLE_DECA_REPL - 52S/O C/O HUMBOLDT | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Land |  |  | 40.0006 | -121.6305 |  | TIER 2 | 43 | 10303-1102, ORO FINO | N33 | 38698 | Y | 311 |  |  |  |  | Returned | Order Operation | [6 empty] | 27.1 | 27.1 |  |  | 0 | 27.1 | 27.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100431346 | RELW OH PRI INSP CLR REMT NOAC TRAF FLAG ESTR TER2 REAR USA FMOB | Pole | 2020-04-09 |  | COMP | 2020-04-09 |  |  | 2020-09-20 | 2020-09-20 | [12 empty] | 2019-05-01 | 2020-05-01 |  | 2020-05-01 | circuit based plan 2.14 | 2020-04-10 | CALENG |  | 103031102 | 28755.14 | 1510.4 |  |  |  | 427.5 |  | 427.5 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | FOREST RANCH | Chico |  |  | OPEN | 117161613 | POLE_BROK_REPL - 7262 NO. 10 HUBOLT RDFO | 35149763 |  |  | STS-POLE_BROK_REPL - 7262 NO. 10 HUBOLT | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.078 | -121.5616 |  | TIER 2 | 43 | 10303-1102, ORO FINO | L3424 | 1943 | Y | 311 |  |  | 2021-02-13 07:00 | 2021-02-13 16:00 | Completed | CLICK | [6 empty] | 40.1 | 40.1 |  |  | 0 | 40.1 | 40.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103357382 | RELW OH SEC PGEA INSP RESD REMT ESTR BTKA RTRN FMOB TER2 | Pole | 2020-04-13 | 2020-05-27 | COMP | 2020-04-13 | [16 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | circuit based plan 2.14 | 2020-04-10 | CALENG |  | 103031102 | 6684.91 | 4509.1 | 913.6 | 76.8 | 76.8 | 133 |  | 133 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | FOREST RANCH | Chico |  |  | OPEN | 117173979 | POLE_BROK_REPL - 22 BUTTE CREEK FLAT RD | 35149822 |  |  | STS-POLE_BROK_REPL - 22 BUTTE CREEK FLAT | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.0776 | -121.5604 |  | TIER 2 | 43 | 10303-1102, ORO FINO | L3424 | 1943 | Y | 311 |  |  | 2021-02-13 07:00 | 2021-02-13 16:00 | Completed | CLICK | [6 empty] | 40.1 | 40.1 |  |  | 0 | 40.1 | 40.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100342665 | RELW OH PRI INSP JPOL PUBL REMT FIRE SWRK ESTR BTKA USA FMOB TER2 | Pole | 2020-03-31 | 2020-07-16 | COMP | 2020-03-31 | [16 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | circuit based plan 2.14 | 2020-04-10 | CALENG |  | 103031102 | 23953.35 | 12315.6 | 7975.7 | 5671 | 5671 | 383.3 |  | 383.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | FOREST RANCH | Chico |  |  | OPEN | 117175115 | POLE_BROK_REPL - 3E/O 2SE/O 1W/O 9091 HU | 35149831 |  |  | STS-POLE_BROK_REPL - 3E/O 2SE/O 1W/O 909 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.1132 | -121.4643 |  | TIER 2 | 43 | 10303-1102, ORO FINO | L3701 | 82201 | Y | 311 |  |  |  |  | Returned | Order Operation | [6 empty] | 91.1 | 91.1 |  |  | 10 | 91 | 91 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100429812 | RELW OH PRI INSP REMT ESTR BTKA FMOB TER2 | Pole | 2020-05-27 | 2020-12-30 | COMP | 2020-05-27 |  |  | 2020-04-24 | 2020-04-24 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | circuit based plan 2.14 | 2020-07-31 | CALENG |  | 103031102 | 39045.43 | 1264.2 | 561.9 | -90.5 | -90.5 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | FOREST RANCH | Chico |  |  | OPEN | 117025072 | POLE_BROK_REPL - 27 S/O 18171 HWY 32FORE | 35110578 |  |  | STS-POLE_BROK_REPL - 27 S/O 18171 HWY 32 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.9589 | -121.6481 |  | TIER 2 | 43 | 10303-1102, ORO FINO | O32 | 2407 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 85.7 | 85.7 |  |  | 0 | 85.7 | 85.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100339737 | RELW OH PRI PATR CLR REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-12-10 | 2020-12-10 | COMP | 2020-12-10 |  |  | 2019-06-06 | 2019-06-06 | [12 empty] | 2019-04-13 | 2019-09-13 |  | 2019-09-13 | 2021 CBP Plan | 2021-01-31 | Chico |  | 103031102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | FOREST RANCH | Chico |  |  | OPEN | 117025092 | POLE_BROK_REPL - 31S/O 18171 HWY 32FORES | 35110353 |  |  | STS-POLE_BROK_REPL - 31S/O 18171 HWY 32F | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.9566 | -121.6506 |  | TIER 2 | 43 | 10303-1102, ORO FINO | O32 | 2407 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 65.4 | 65.4 |  |  | 0 | 65.4 | 65.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100339735 | RELW OH PRI PATR REMT FIRE ESTR BTKA USA FMOB TER2 | Pole | 2020-11-28 | 2020-11-28 | COMP | 2020-11-28 |  |  | 2019-06-06 | 2019-06-06 | [12 empty] | 2019-04-13 | 2019-08-27 |  | 2019-08-27 | 2021 CBP Plan | 2020-07-31 | Chico |  | 103031102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | FRENCH GULCH | Redding |  |  | OPEN | 117260264 | POLE_BROK_REPL - 55S/O C/O HWY 299/CRYST | 35154080 |  |  | STS-POLE_BROK_REPL - 55S/O C/O HWY 299/C | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6464 | -122.6693 |  | TIER 2 | 285 | 10338-1102, FRENCH GULCH | N23 | 800623 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101460717 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-09-24 | 2020-12-08 | COMP | 2020-09-24 | [16 empty] | 2019-05-17 | 2020-05-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103381102 | 22413.6 | 3777.8 | 2599.8 | 1383 | 1383 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | GREENVILLE | Quincy |  |  | OPEN | 117185656 | POLE_DECA_REPL - R/O 3450 DIAMOND MTN. R | 35215460 |  |  | STS-POLE_DECA_REPL - R/O 3450 DIAMOND MT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.1381 | -120.821 |  | TIER 2 | 650 | 10313-2101, CRESCENT MILLS | K52 | 3127 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100383808 | RELW OH PRI CLR JPOL REMT ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2019-11-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103132101 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | GREENVILLE | Quincy |  |  | OPEN | 117205292 | POLE_DECA_REPL - 240' N/O C/O THOMPSON R | 35154636 |  |  | STS-POLE_DECA_REPL - 240' N/O C/O THOMPS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.1451 | -120.9076 |  | TIER 2 | 401 | 10281-2101, BIG MEADOWS | K5009 | 3177 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 20.2 | 20.2 |  |  | 1 | 19.2 | 19.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100388654 | RELW OH PRI JPOL RESD FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-09-25 |  | COMP | 2020-09-25 |  |  | 2021-01-12 | 2021-01-12 | [12 empty] | 2019-05-09 | 2020-05-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 102812101 | 13265.19 | 2515.4 | 1366.3 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | GREENVILLE | Quincy |  |  | OPEN | 117213013 | POLE_DECA_REPL - 4643 N VALLEY RD 2P/S 4 | 35154678 |  |  | STS-POLE_DECA_REPL - 4643 N VALLEY RD 2P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 40.1488 | -120.8753 |  | TIER 2 | 401 | 10281-2101, BIG MEADOWS | K5108 | 18607 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103020562 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 102812101 | 1 | 44.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | GREENVILLE | Quincy |  |  | OPEN | 117182048 | POLE_DECA_REPL - A/F 3494 NORTH VALLEY R | 35154549 |  |  | STS-POLE_DECA_REPL - A/F 3494 NORTH VALL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.1456 | -120.8955 |  | TIER 2 | 401 | 10281-2101, BIG MEADOWS | K5106 | 3177 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.1 | 21.1 |  |  | 1 | 20.1 | 20.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102301635 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-08-13 | 2021-01-12 | COMP | 2020-08-13 |  |  | 2021-01-12 | 2021-01-12 | [12 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 102812101 | 12986.05 | 375.9 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | GREENVILLE | Quincy |  |  | OPEN | 117190001 | POLE_DECA_REPL - C/O N. VALLEY AND GREEN | 35154613 |  |  | STS-POLE_DECA_REPL - C/O N. VALLEY AND G | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.1463 | -120.8926 |  | TIER 2 | 401 | 10281-2101, BIG MEADOWS | K5106 | 3177 | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | [6 empty] | 15.5 | 15.5 |  | 0 | 32 | 5 | 5 |  | 0 | EC | E | Pole | Decayed/Rotten | Replace |  | 102301631 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-05-06 | 2020-05-09 | COMP | 2020-05-06 |  |  | 2020-04-27 | 2020-04-27 | [12 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | QUES |  | 102812101 | 10537.14 | 6678.4 | 5184.7 | 3643.4 | 3643.4 | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | GREENVILLE | Quincy |  |  | OPEN | 117205294 | POLE_DECA_REPL - 2371 NORTH VALLEY RDGRE | 35154640 |  |  | STS-POLE_DECA_REPL - 2371 NORTH VALLEY R | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.1465 | -120.9152 |  | TIER 2 | 401 | 10281-2101, BIG MEADOWS | K50 | 2979BP | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 18.5 | 18.5 |  | 0 | 30 | 8 | 8 |  | 0 | EC | E | Pole | Decayed/Rotten | Replace |  | 102301160 | RELW OH PRI CLR JPOL RESD FIRE NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-04-27 | 2020-04-27 | COMP | 2020-04-27 | [16 empty] | 2019-05-09 | 2020-05-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | QUES |  | 102812101 | 8759.95 | 5824.2 | 5006.2 | 3643.4 | 3643.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | IGO | Redding |  |  | COMP | 116745970 | POLE_BROK_REPL - 11641 PLATINA RD 1NW/O. | 35204596 |  |  | STS-POLE_BROK_REPL - 10 W/0 11647 PLATIN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 40.4542 | -122.6322 |  | TIER 2 | 354 | 10340-1101, GIRVAN | R23 | 1837 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 5 | 0 | 0 | 0 |  |  |  | 27.3 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101487266 | PRI REGW OH COMP JPOL RESD REMT ESTR BTKA PROG CPGD FMOB TER2 PRTO FSRP | Pole | 2020-10-12 | 2020-10-10 | REQD | 2020-10-10 | [15 empty] | 2021-02-18 | 2020-10-29 | 2020-03-15 |  | 2020-03-15 | Per DOT Approved Request 28452 |  | UNASSIGNED |  | 103401101 | 71265.57 | 74948.8 | 1555.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
North | NV | IGO | Redding |  |  | COMP | 116754287 | POLE_BROK_REPL - 5W/0 14161 PLATINA RDIG | 35204596 |  |  | STS-POLE_BROK_REPL - 10 W/0 11647 PLATIN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 40.4515 | -122.635 |  | TIER 2 | 354 | 10340-1101, GIRVAN | R23 | 1837 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 5 | 0 | 0 | 0 |  |  |  | 27.3 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101487275 | REGW OH PRI COMP JPOL REMT ESTR BTKA PROG CPGD FMOB TER2 PRTO FSRP | Pole | 2020-10-12 | 2020-10-10 | REQD | 2020-10-10 | [15 empty] | 2021-02-18 | 2020-10-27 | 2020-03-18 |  | 2020-03-18 | Per DOT Approved Request 28453 |  | UNASSIGNED |  | 103401101 | 71265.57 | 74948.8 | 1555.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
North | NV | IGO | Redding |  |  | COMP | 116754583 | POLE_BROK_REPL - 2W/0 14161 PLATINA RDIG | 35204596 |  |  | STS-POLE_BROK_REPL - 10 W/0 11647 PLATIN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 40.4533 | -122.6342 |  | TIER 2 | 354 | 10340-1101, GIRVAN | R23 | 1837 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 5 | 0 | 0 | 0 |  |  |  | 27.3 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101487272 | OH REGW PRI COMP JPOL REMT NOAC ESTR PROG CPGD FMOB TER2 PRTO FSRP | Pole | 2020-10-12 | 2020-10-10 | REQD | 2020-10-10 | [15 empty] | 2021-02-17 | 2020-10-27 | 2020-03-18 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28454 |  | UNASSIGNED |  | 103401101 | 71265.57 | 74948.8 | 1555.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
North | NV | IGO | Redding |  |  | COMP | 116754680 | POLE_BROK_REPL - 1W/0 14161 PLATINA RD I | 35204596 |  |  | STS-POLE_BROK_REPL - 10 W/0 11647 PLATIN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 40.4539 | -122.6336 |  | TIER 2 | 354 | 10340-1101, GIRVAN | R23 | 1837 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 5 | 0 | 0 | 0 |  |  |  | 27.3 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101487265 | REGW OH PRI COMP JPOL REMT NOAC ESTR CPGD FMOB TER2 PRTO FSRP | Pole | 2020-10-12 | 2020-10-10 | REQD | 2020-10-10 | [15 empty] | 2021-02-17 | 2020-10-27 | 2020-03-18 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28455 |  | UNASSIGNED |  | 103401101 | 71265.57 | 74948.8 | 1555.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
North | NV | IGO | Redding |  |  | COMP | 116755336 | POLE_BROK_REPL - 5W/O 11514 PLATINA RDIG | 35204596 |  |  | STS-POLE_BROK_REPL - 10 W/0 11647 PLATIN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 40.4583 | -122.6312 |  | TIER 2 | 354 | 10340-1101, GIRVAN | R23 | 323094 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 5 | 0 | 0 | 0 |  |  |  | 27.3 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101487257 | RELW OH PRI COMP JPOL REMT NOAC ESTR CPGD FMOB TER2 PRTO FSRP | Pole | 2020-10-12 | 2020-10-10 | REQD | 2020-10-10 | [15 empty] | 2021-02-18 | 2020-10-28 | 2020-03-18 | 2020-11-09 | 2020-11-09 | 2021 CBP Plan |  | UNASSIGNED |  | 103401101 | 71265.57 | 74948.8 | 1555.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | IGO | Redding |  |  | OPEN | 116682768 | POLE_BROK_REPL - 12 W/O 4272 LOWER GAS P | 35214611 |  |  | STS-POLE_BROK_REPL - 12 W/O 4272 LOWER G | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.4192 | -122.5343 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | S26 | 1397 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101491679 | RELW PRI OH ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-07 | 2020-03-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 102931102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | IGO | Redding |  |  | OPEN | 116684180 | POLE_DECA_REPL - 4879 LOWER GAS PT RDIGO | 35090590 |  |  | STS-POLE_DECA_REPL - 4879 LOWER GAS PT R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4277 | -122.5414 |  | TIER 2 | 601 | 10293-1102, COTTONWOOD | S26 | 1757 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101491703 | JPOL RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2019-11-27 | 2020-01-15 | COMP | 2019-11-26 | [16 empty] | 2019-03-07 | 2020-03-07 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2020-01-31 | EEI |  | 102931102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | IGO | Redding |  |  | OPEN | 116716612 | POLE_BROK_REPL - 7 E/O 14451 SMALL FARMS | 35154054 |  |  | STS-POLE_BROK_REPL - 7 E/O 14451 SMALL F | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4672 | -122.5196 |  | TIER 2 | 391 | 10344-1101, JESSUP | R26 | 2023 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 66.8 | 66.8 |  |  | 0 | 66.8 | 66.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101480616 | OH PRI REMT PRTO RELW ESTR BTKA FMOB TER2 FSRP | Pole | 2021-02-11 | 2021-02-11 | COMP | 2021-02-11 | [16 empty] | 2019-03-12 | 2020-03-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103441101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | IGO | Redding |  |  | OPEN | 116755199 | POLE_BROK_REPL - 4W/0 11514 PLATINA RDIG | 35204596 |  |  | STS-POLE_BROK_REPL - 10 W/0 11647 PLATIN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 40.4586 | -122.6305 |  | TIER 2 | 354 | 10340-1101, GIRVAN | R23 | 323094 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 5 | 0 | 0 | 171.2 | 171.2 |  |  |  | 34.7 | 34.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101487256 | REGW OH PRI JPOL REMT NOAC ESTR PROG FMOB TER2 PRTO FSRP | Pole | 2020-10-12 | 2020-10-10 | REQD | 2020-10-10 | [16 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28456 |  | UNASSIGNED |  | 103401101 | 71265.57 | 74948.8 | 1555.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
North | NV | IGO | Redding |  |  | OPEN | 116755538 | POLE_BROK_REPL - 7W/0 11514 PLATINA RDIG | 35204596 |  |  | STS-POLE_BROK_REPL - 10 W/0 11647 PLATIN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 40.4576 | -122.6326 |  | TIER 2 | 354 | 10340-1101, GIRVAN | R23 | 323094 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 5 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101487259 | REGW OH PRI JPOL REMT NOAC ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-10-12 | 2020-10-10 | REQD | 2020-10-10 | [16 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28457 |  | UNASSIGNED |  | 103401101 | 71265.57 | 74948.8 | 1555.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
North | NV | IGO | Redding |  |  | OPEN | 116756573 | POLE_BROK_REPL - 5N/0 11514 PLATINA RDIG | 35204596 |  |  | STS-POLE_BROK_REPL - 10 W/0 11647 PLATIN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 40.4623 | -122.632 |  | TIER 2 | 354 | 10340-1101, GIRVAN | R23 | 3507 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 5 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101487244 | REGW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-10-12 | 2020-10-10 | REQD | 2020-10-10 | [16 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28458 |  | UNASSIGNED |  | 103401101 | 71265.57 | 74948.8 | 1555.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
North | NV | IGO | Redding |  |  | OPEN | 116812083 | POLE_DECA_REPL - 2N/O 13976 S FORK RD IG | 35154365 |  |  | STS-POLE_DECA_REPL - 2N/O 13976 S FORK R | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 40.5074 | -122.5423 |  | TIER 2 | 354 | 10340-1101, GIRVAN | Q2606 | 6885 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 51.8 | 51.8 |  |  | 0 | 51.8 | 51.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101493916 | RELW PRI OH JPOL REMT ESTR BTKA REAR PROG FMOB TER2 PRTO FSRP | Pole | 2021-02-18 | 2021-02-18 | COMP | 2021-02-18 | [16 empty] | 2019-03-22 | 2020-03-22 | 2024-03-20 | 2024-03-20 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103401101 | 9343.17 | 1664.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | IGO | Redding |  |  | OPEN | 116875355 | POLE_BROK_REPL - 5N/0 7741 ZIGG MINE RD | 35202573 |  |  | STS-POLE_BROK_REPL - 5N/0 7741 ZIGG MINE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.5153 | -122.5514 |  | TIER 2 | 354 | 10340-1101, GIRVAN | Q25 | 3489 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 44.4 | 44.4 |  |  | 0 | 44.4 | 44.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101494806 | RELW OH PRI RESD REMT NOAC SWRK FMOB TER2 PRTO FSRP | Pole | 2021-02-19 | 2021-02-19 | COMP | 2021-02-19 | [16 empty] | 2019-03-30 | 2020-03-30 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103401101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | LAKEHEAD | Redding |  |  | OPEN | 117296048 | POLE_DECA_REPL - R/0 17239 CHAPMAN DR 6 | 35121388 |  |  | STS-POLE_DECA_REPL - R/0 17239 CHAPMAN D | UNSC | UNSC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.7819 | -122.3158 |  | TIER 2 | 556 | 10327-1101, ANTLER | K3103 | 3385 | Y | 311 |  |  | 2021-03-05 07:00 | 2021-03-05 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101459355 | RELW OH PRI INSP CLR ESTR FMOB TER2 FSRP | Pole | 2021-02-08 | 2021-02-08 | COMP | 2020-07-31 | [16 empty] | 2019-05-21 | 2020-05-21 | 2020-08-28 | 2020-08-28 | Per DOT Approved Request ID# 863 from [REDACTED] | 2020-08-31 | EEI |  | 103271101 | 29084.32 | 9581.4 | 604.6 | 516.7 | 516.7 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permit Delay - To [REDACTED]: Please see the below issues that came up for job 35121388; it looks like we need permits for the railroad, and Cal Trans, look into this job and if you see fit put it back to PEND Status or let us know if we will be able t | Y | 2020-06-22
North | NV | LAKEHEAD | Redding |  |  | OPEN | 116825517 | POLE_BROK_REPL - 4N\O 20923 TAWNY WY LAK | 35121423 |  |  | STS-POLE_BROK_REPL - 4N\O 20923 TAWNY WY | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.8781 | -122.2828 |  | TIER 2 | 556 | 10327-1101, ANTLER | H32 | 3849 | Y | 311 |  |  | 2021-04-12 07:00 | 2021-04-16 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 31 | 31 |  |  | 0 | 31 | 31 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101456022 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2019-09-18 | 2020-06-29 | COMP | 2019-09-18 | [16 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | Program Manager | 2019-09-18 | EEI |  | 103271101 | 13162.49 | 1399.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-20
North | NV | LAKEHEAD | Redding |  |  | OPEN | 117072906 | POLE_BROK_REPL - 8E/O CO-1955 STATTON RD | 35121496 |  |  | STS-POLE_BROK_REPL - 8E/O CO-1955 STATTO | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.8542 | -122.3241 |  | TIER 2 | 556 | 10327-1101, ANTLER | I3112 | 1376 | Y | 311 |  |  | 2021-04-12 07:00 | 2021-04-16 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 31.8 | 31.8 |  |  | 0 | 31.8 | 31.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101455696 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-04-13 | 2020-04-13 | COMP | 2019-09-17 |  |  | 2020-04-13 | 2019-11-05 | [12 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | Program Manager | 2019-09-17 | EEI |  | 103271101 | 21756.34 | 4132 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-20
North | NV | LAKEHEAD | Redding |  |  | OPEN | 117129197 | POLE_BROK_REPL - 18241 SKYLINE DR LAKEHE | 35202712 |  |  | STS-POLE_BROK_REPL - 18241 SKYLINE DR LA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.8152 | -122.3075 |  | TIER 2 | 556 | 10327-1101, ANTLER | J31 | 3333 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101456400 | OH PRI JPOL MINR REMT JAR BTKA FMOB TER2 PRTO FSRP RELW | Pole | 2020-12-17 | 2021-02-04 | COMP | 2020-12-17 | [16 empty] | 2019-04-30 | 2020-04-30 | 2020-11-22 | 2020-11-22 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103271101 | 22289.99 | 1363.4 | 482.1 | -398.2 | -398.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | LAKEHEAD | Redding |  |  | OPEN | 117687134 | POLE_BROK_REPL - 2NO CO 386 ANTLER RD LA | 35215922 |  |  | STS-POLE_BROK_REPL - 2NO CO 386 ANTLER R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 40.8928 | -122.3814 |  | TIER 2 | 556 | 10327-1101, ANTLER | H2920 | 1384 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101473392 | RELW OH PRI MINR GO PROG TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103271101 | 1 | 1013.1 | 1013.1 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MANTON | Red Bluff |  |  | OPEN | 117189819 | POLE_BROK_REPL - 21115 ROLLINGS HILLS DR | 35143565 |  |  | STS-POLE_BROK_REPL - 21115 ROLLINGS HILL | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4119 | -121.8454 |  | TIER 2 | 90 | 10254-1101, VOLTA | S42 | 850263 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-22 16:00 | Dispatched | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0.5 | 42.2 | 42.2 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101552717 | PRI RELW OH INSP REMT FIRE ESTR BTKA PROG FMOB TER2 | Pole | 2020-03-03 | 2020-05-01 | COMP | 2020-03-03 | [16 empty] | 2019-05-08 | 2020-05-08 | 2020-11-07 | 2020-11-07 | B-tag addition 8/12/2020 | 2020-02-28 | TRC |  | 102541101 | 17679.44 | 16449.4 | -28149.8 | 535.2 | 535.2 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-08-18
North | NV | MANTON | Red Bluff |  |  | COMP | 117251774 | POLE_BROK_REPL - 10E\O 35070 FORWARDS MI | 35143515 |  |  | STS-POLE_BROK_REPL - 10E\O 35070 FORWARD | MAPP | MAPP SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.4355 | -121.734 |  | TIER 2 | 90 | 10254-1101, VOLTA | R45 | 1571 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 51 | 51 |  |  | 66 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101556392 | RELW COMP REMT OH PRI INSP ESTR CPGG FMOB TER2 FSRP | Pole | 2020-03-09 | 2020-03-09 | COMP | 2020-03-09 | COMP | 2021-02-10 | [13 empty] | 2021-02-11 | 2021-02-10 | 2020-05-15 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2020-02-28 | TRC |  | 102541101 | 25079.16 | 15149.2 | 12924 | 9130.1 | 9130.1 | 1102.7 |  | 1102.7 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MANTON | Red Bluff |  |  | COMP | 117254122 | POLE_DECA_REPL - 1E\O 35070 FORWARDS MIL | 35143516 |  |  | STS-POLE_DECA_REPL - 1E\O 35070 FORWARDS | FICL | FICL SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.4385 | -121.7395 |  | TIER 2 | 90 | 10254-1101, VOLTA | R45 | 1571 | Y | 311 |  |  | 2021-01-19 | 2021-01-19 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 30.1 | 30.1 |  |  | 50 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101556379 | RELW OH PRI INSP COMP RESD REMT ESTR BTKA CPGG FMOB TER2 FSRP | Pole | 2020-03-05 | 2020-03-05 | COMP | 2020-03-05 | COMP | 2021-01-19 | 2020-01-02 | 2020-01-02 | [11 empty] | 2021-01-21 | 2021-01-19 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-02-28 | TRC |  | 102541101 | 6804.29 | 14474.7 | 14263.4 | 14263.4 | 14263.4 | 166.8 |  | 166.8 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MANTON | Red Bluff |  |  | OPEN | 117227514 | POLE_DECA_REPL - 6E\O 34344 FORWARDS MIL | 35143610 |  |  | STS-POLE_DECA_REPL - 6E\O 34344 FORWARDS | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4412 | -121.7617 |  | TIER 2 | 90 | 10254-1101, VOLTA | R44 | 1563 | Y | 311 |  |  | 2021-04-19 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 32 | 32 |  |  | 0 | 32 | 32 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101553313 | RELW OH PRI INSP TER2 REMT ESTR FMOB FSRP | Pole | 2020-07-02 | 2020-07-02 | COMP | 2020-06-30 |  |  | 2020-01-02 | 2020-01-02 | [12 empty] | 2019-05-13 | 2020-05-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | TRC |  | 102541101 | 8348.6 | 3544.2 | 836.5 | 836.5 | 836.5 | 1206.6 |  | 1206.6 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MARYSVILLE | Oroville |  |  | OPEN | 117101076 | POLE_DECA_REPL - 4870 KINGS RANCH RD 2PL | 35202200 |  |  | STS-POLE_DECA_REPL - 4870 KINGS RANCH RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.3504 | -121.4313 |  | TIER 2 | 115 | 10319-1101, BANGOR | K27 | 665 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.9 | 13.9 |  |  | 0 | 13.9 | 13.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100415591 | RELW OH PRI CLR JPOL SWRK ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-17 |  | COMP | 2021-02-17 | [16 empty] | 2019-04-25 | 2020-04-25 | 2020-10-30 | 2020-10-30 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103191101 | 6458.33 | 89.3 | -452.6 | -226.3 | -226.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MARYSVILLE | Oroville |  |  | OPEN | 117101078 | POLE_DECA_REPL - 4870 KINGS RANCH RD 1PL | 35214770 |  |  | STS-POLE_DECA_REPL - 4870 KINGS RANCH RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 39.3514 | -121.4318 |  | TIER 2 | 115 | 10319-1101, BANGOR | K27 | 673 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100381993 | RELW OH PRI CLR JPOL RESD REMT SWRK ESTR GO BTKA USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103191101 | 1 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MARYSVILLE | Oroville |  |  | OPEN | 117101080 | POLE_DECA_REPL - 4870 KINGS RANCH RD W/T | 35202203 |  |  | STS-POLE_DECA_REPL - 4870 KINGS RANCH RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.3525 | -121.4325 |  | TIER 2 | 115 | 10319-1101, BANGOR | K27 | 665 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.4 | 29.4 |  |  | 0 | 29.4 | 29.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100415590 | RELW JPOL OH PRI CLR RESD REMT SWRK USA ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-22 |  | COMP | 2021-02-22 | [16 empty] | 2019-04-25 | 2020-04-25 | 2020-10-30 | 2020-10-30 | 2021 CBP Plan | 2021-02-28 | QUES |  | 103191101 | 12671.76 | 321.3 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MARYSVILLE | Oroville |  |  | OPEN | 117101085 | POLE_DECA_REPL - 4870 KINGS RANCH RD W/T | 35202206 |  |  | STS-POLE_DECA_REPL - 4870 KINGS RANCH RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.3492 | -121.4299 |  | TIER 2 | 115 | 10319-1101, BANGOR | K27 | 665 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.9 | 37.9 |  |  | 0 | 37.9 | 37.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100415592 | RELW OH PRI JPOL RESD REMT SWRK ESTR BTKA FMOB FSRP TER2 PRTO | Pole | 2021-01-15 |  | COMP | 2021-01-15 | [16 empty] | 2019-04-25 | 2020-04-25 | 2020-10-30 | 2020-10-30 | 2021 CBP Plan | 2021-02-28 | QUES |  | 103191101 | 16137.47 |  | 0 | 1583.6 | 1583.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MARYSVILLE | Oroville |  |  | OPEN | 117101084 | POLE_DECA_REPL - 4778 LA PORTE RD 7PL SM | 35145773 |  |  | STS-POLE_DECA_REPL - 4778 LA PORTE RD 7P | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3476 | -121.4384 |  | TIER 2 | 115 | 10319-1101, BANGOR | K26 | 665 | Y | 311 |  |  | 2021-03-10 07:00 | 2021-03-10 16:00 | Dispatched | CLICK | [6 empty] | 40.1 | 40.1 |  |  | 0.5 | 40 | 40 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100381878 | RELW OH PRI CLR JPOL RESD REMT NOAC SWRK ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-01-22 | 2020-01-29 | COMP | 2020-01-21 | [16 empty] | 2019-04-25 | 2019-10-25 |  | 2019-10-25 | circuit based plan 2.14 |  | Chico |  | 103191101 | 13625.61 | 3506.8 | 111.2 | 111.2 | 111.2 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | MARYSVILLE | Oroville |  |  | OPEN | 117078080 | POLE_BROK_REPL - #1S 133 TENNESSE LN W/T | 35202148 |  |  | STS-POLE_BROK_REPL - #1S 133 TENNESSE LN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3573 | -121.4222 |  | TIER 2 | 115 | 10319-1101, BANGOR | K27 | 6695 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.8 | 33.8 |  |  | 0 | 33.8 | 33.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100382012 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-15 | 2020-12-15 | COMP | 2020-12-15 |  |  | 2020-12-10 | 2020-12-10 | [12 empty] | 2019-04-22 | 2020-04-22 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103191101 | 15107.4 | 1331.5 | 645 | -190 | -190 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MCARTHUR | Burney |  |  | OPEN | 117128277 | POLE_DECA_REPL - 6NE/O 9E/O C.O.SWITCHB | 35215036 |  |  | STS-POLE_DECA_REPL - 6NE/O 9E/O C.O.SWIT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 41.0628 | -121.2679 |  | TIER 2 | 681 | 10349-1101, MC ARTHUR | D56 | 1544 | Y | 311 |  |  | 2021-05-03 07:00 | 2021-05-08 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101549610 | OH PRI JPOL RESD ESTR FSRP PRTO RELW BTKA FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103491101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MILL CREEK | Red Bluff |  |  | OPEN | 117273943 | POLE_BROK_REPL - #29 ON LINE E/O #10E HW | 35143810 |  |  | STS-POLE_BROK_REPL - #29 ON LINE E/O #10 | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.3479 | -121.5508 |  | TIER 2 | 90 | 10254-1101, VOLTA | T50 | 1141 | Y | 311 |  |  | 2021-01-27 | 2021-01-27 | Dispatched | Order Operation | [6 empty] | 40.9 | 40.9 |  |  | 10 | 40.8 | 40.8 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101532359 | RELW OH PRI PATR REMT SWRK ESTR FMOB TER2 | Pole | 2020-11-24 | 2020-12-05 | COMP | 2020-08-31 | [16 empty] | 2019-05-19 | 2020-05-19 | 2020-10-02 | 2020-10-02 | B-tag addition 8/4/2020 | 2020-12-31 | TRC |  | 102541101 | 11144.62 | 4722.5 | 140.2 | 140.2 | 140.2 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-08-04
North | NV | MILL CREEK | Red Bluff |  |  | OPEN | 117273945 | POLE_BROK_REPL - 38N/O R/O 40306 PINE WA | 35137758 |  |  | STS-POLE_BROK_REPL - 38N/O R/O 40306 PIN | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.3467 | -121.5367 |  | TIER 2 | 90 | 10254-1101, VOLTA | T50 | 6087 | Y | 311 |  |  | 2021-03-18 07:00 | 2021-03-18 16:00 | Scheduled | CLICK | [6 empty] | 55.6 | 55.6 |  |  | 0 | 55.6 | 55.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101554648 | RELW OH PRI INSP SWRK TER2 ESTR FMOB | Pole | 2020-06-25 | 2020-07-15 | COMP | 2020-06-25 | [16 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | 2021 CBP Plan | 2020-12-31 | ENENG |  | 102541101 | 13068.08 | 3346 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117188977 | POLE_BROK_REPL - 29839 HWY.299 [AT HOUSE | 35233122 |  |  | STS-POLE_BROK_REPL - 29839 HWY.299 [AT H | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-04-13 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.8152 | -121.937 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | J4009 | 4523 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101478949 | RELW PRI OH INSP CLR ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-11 | 2021-05-11 | B tag clean up 2/19/2021 | 2021-03-10 | Chico |  | 103321101 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | NV | MONTGOMERY CREEK | Burney |  |  | COMP | 117036380 | POLE_BROK_REPL - CUTOUT 209 BIG BEND RD | 35110347 |  |  | STS-POLE_BROK_REPL - CUTOUT 209 BIG BEND | FICL | FICL SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 41.0202 | -121.9101 |  | TIER 2 | 218 | 10132-1101, PIT NO 5 | E4117 | 1606 | Y | 311 |  |  | 2021-01-15 | 2021-01-15 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 46.6 | 46.6 |  |  | 5.5 | 4.6 | 4.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101513437 | RELW OH PRI PGEA COMP REMT ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-06-29 | 2020-07-01 | COMP | 2020-02-19 | COMP | 2021-01-15 | 2019-06-24 | 2019-06-24 | [11 empty] | 2021-01-20 | 2021-01-15 | 2019-08-27 |  | 2019-08-27 | circuit based plan 2.14 |  | Chico |  | 101321101 | 30507.81 | 24695.3 | 14032.1 | 14032.1 | 14032.1 | 1935.5 |  | 1935.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | MONTGOMERY CREEK | Burney |  |  | COMP | 117170762 | POLE_DECA_REPL - 2E/O C/O PATTERSON RANC | 35154452 |  |  | STS-POLE_DECA_REPL - 2E/O C/O PATTERSON | MAPP | MAPP SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.8137 | -121.9224 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | J4111 | 4523 | Y | 311 |  |  | 2021-01-11 | 2021-01-11 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101479247 | RELW OH PRI INSP COMP ESTR GO CCNT FMOB TER2 FSRP | Pole | 2020-05-06 | 2020-06-30 | COMP | 2020-05-05 | COMP | 2021-01-11 | [13 empty] | 2021-01-15 | 2021-01-11 | 2020-05-06 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | QUES |  | 103321101 | 6171.05 | 3340.1 | 1829.7 | 1829.7 | 1829.7 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117116209 | POLE_DECA_REPL - 17E/O 8SE/O C/O#5663 @P | 35180302 |  |  | STS-POLE_DECA_REPL - 17E/O 8SE/O C/O#566 | CONS | CONS ERDY SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.9965 | -121.7315 |  | TIER 2 | 655 | 10373-2101, PIT NO 3 | F45 | 5663 | Y | 311 |  |  | 2021-04-24 07:00 | 2021-04-24 16:00 | Dispatched | CLICK | [6 empty] | 40.3 | 40.3 |  |  | 0 | 40.3 | 40.3 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101514846 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-06-16 | 2021-01-26 | COMP | 2020-06-16 | [16 empty] | 2019-04-28 | 2020-04-28 | 2020-08-30 | 2020-08-30 | Per DOT Approved Request ID# 839 from [REDACTED] |  | Chico |  | 103732101 | 26741.39 | 3033.4 | 233.7 | 233.7 | 233.7 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-06-22
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117162670 | POLE_DECA_REPL - 20E/O 8SE/O C/O#5663 @P | 35180301 |  |  | STS-POLE_DECA_REPL - 20E/O 8SE/O C/O#566 | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.9969 | -121.7297 |  | TIER 2 | 655 | 10373-2101, PIT NO 3 | F45 | 5663 | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Dispatched | CLICK | [6 empty] | 40.8 | 40.8 |  |  | 0 | 40.8 | 40.8 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101514836 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-06-16 | 2021-01-26 | COMP | 2020-06-16 | [16 empty] | 2019-04-29 | 2020-04-29 | 2020-08-30 | 2020-08-30 | Per DOT Approved Request ID# 840 from [REDACTED] |  | Chico |  | 103732101 | 27236.92 | 2349.7 | 280.5 | 280.5 | 280.5 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-06-22
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117162671 | POLE_BROK_REPL - 40S/O 1E/O SWITCH #6553 | 35180300 |  |  | STS-POLE_BROK_REPL - 40S/O 1E/O SWITCH # | CONS | CONS ERDY SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.9996 | -121.7257 |  | TIER 2 | 655 | 10373-2101, PIT NO 3 | F45 | 2101 | Y | 311 |  |  | 2021-04-22 07:00 | 2021-04-22 16:00 | Dispatched | CLICK | [6 empty] | 40.3 | 40.3 |  |  | 0 | 40.3 | 40.3 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101514863 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-06-16 | 2021-01-26 | COMP | 2020-06-16 | [16 empty] | 2019-04-29 | 2020-04-29 | 2020-08-30 | 2020-08-30 | Per DOT Approved Request ID# 846 from [REDACTED] |  | Chico |  | 103732101 | 27941.39 | 2855.4 | 374 | 374 | 374 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-06-22
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117185849 | POLE_BROK_REPL - 30022 JACKSON LN 1N/OMO | 35154579 |  |  | B STS-POLE_BROK_REPL-30022 JACKSON LN 1N | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.8517 | -121.9315 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | I40 | 6449 | Y | 311 |  |  | 2021-03-23 07:00 | 2021-03-23 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 51.8 | 51.8 |  |  | 0 | 51.8 | 51.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103145908 | RELW OH PRI INSP REMT ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-05-06 | 2020-05-06 | COMP | 2020-05-06 | [16 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | QUES |  | 103321101 | 16333.94 | 11933.5 | 2.2 | 2.2 | 2.2 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 116948239 | POLE_BROK_REPL - 7S/O CO-9315 S/O PIT 5 | 35214599 |  |  | STS-POLE_BROK_REPL - 7S/O CO-9315 S/O PI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.981 | -121.9684 |  | TIER 2 | 218 | 10132-1101, PIT NO 5 | F39 | 9315 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101513516 | RELW OH PRI PGEA REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-03 | 2020-04-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 101321101 | 1 | 374 | 374 | 374 | 374 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 116975545 | POLE_DECA_REPL - 11W/O SW-1711 PIT 5 RD | 35088156 |  |  | STS-POLE_DECA_REPL - 11W/O SW-1711 PIT 5 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 41.0004 | -121.9549 |  | TIER 2 | 218 | 10132-1101, PIT NO 5 | F40 | 1658 | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Dispatched | CLICK | [6 empty] | 59.4 | 59.4 |  |  | 0 | 59.4 | 59.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101512613 | RELW OH PRI PGEA JPOL REMT NOAC ESTR PROG FMOB TER2 PRTO FSRP | Pole | 2020-12-02 | 2021-01-07 | COMP | 2020-12-02 | [16 empty] | 2019-04-07 | 2019-09-27 | 2020-11-26 | 2020-11-26 | 2021 CBP Plan | 2020-09-30 | QUES |  | 101321101 | 26202.79 | 2144.9 | 1061.3 | 271.5 | 271.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117006444 | POLE_DECA_REPL - 2E/O SW-4831 BIG BEND R | 35154359 |  |  | STS-POLE_DECA_REPL - 2E/O SW-4831 BIG BE | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.9969 | -121.9176 |  | TIER 2 | 218 | 10132-1101, PIT NO 5 | F41 | 1660 | Y | 311 |  |  | 2021-04-12 07:00 | 2021-04-16 16:00 | Reserved | CLICK | [6 empty] | 43 | 43 |  |  | 0 | 43 | 43 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101512384 | RELW OH PRI PGEA REMT NOAC ESTR PROG FMOB TER2 PRTO FSRP | Pole | 2020-10-14 | 2020-10-14 | COMP | 2020-10-13 | [16 empty] | 2019-04-10 | 2019-10-10 | 2020-12-04 | 2020-12-04 | 2021 CBP Plan | 2020-12-31 | QUES |  | 101321101 | 12048.23 | 3764.8 |  |  |  | 631.5 |  | 631.5 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117036369 | POLE_DECA_REPL - CUTOUT 209 BIG BEND RDM | 35110346 |  |  | STS-POLE_DECA_REPL - CUTOUT 209 BIG BEND | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 41.0201 | -121.9104 |  | TIER 2 | 218 | 10132-1101, PIT NO 5 | E4117 | 1606 | Y | 311 |  |  | 2021-04-12 07:00 | 2021-04-16 16:00 | Reserved | CLICK | [6 empty] | 45.8 | 45.8 |  |  | 0 | 45.8 | 45.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101513433 | RELW OH SEC PGEA JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-11-17 | 2020-11-18 | COMP | 2020-09-16 |  |  | 2019-06-24 | 2019-06-24 | [12 empty] | 2019-04-15 | 2019-08-27 | 2020-11-14 | 2020-11-14 | 2021 CBP Plan | 2020-09-30 | QUES |  | 101321101 | 6263.17 | 1532.4 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117036381 | POLE_DECA_REPL - 30617 SOUTHWIND DR 1W/O | 35110134 |  |  | STS-POLE_DECA_REPL - 30617 SOUTHWIND DR | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 41.0201 | -121.9093 |  | TIER 2 | 218 | 10132-1101, PIT NO 5 | E4117 | 3073 | Y | 311 |  |  | 2021-04-19 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 53.9 | 53.9 |  |  | 0 | 53.9 | 53.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101513442 | RELW OH SEC PGEA REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-11-30 | 2020-12-02 | COMP | 2020-08-24 |  |  | 2019-06-24 | 2019-06-24 | [12 empty] | 2019-04-15 | 2019-08-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 101321101 | 10419.66 | 2971.9 | -412.2 | -1629 | -1629 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117112884 | POLE_BROK_REPL - 78S/O 1E/O SWITCH #5663 | 35202258 |  |  | STS-POLE_BROK_REPL - 78S/O 1E/O SWITCH # | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 41.0082 | -121.7089 |  | TIER 2 | 655 | 10373-2101, PIT NO 3 | F46 | 354683 | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101515019 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-02 |  | COMP | 2020-12-02 |  |  | 2021-02-09 | 2021-02-09 | [12 empty] | 2019-04-27 | 2020-04-27 | 2020-11-22 | 2020-11-22 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103732101 | 26744.18 | 3637.8 | 2388.6 | 1292.5 | 1292.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117112892 | POLE_DECA_REPL - 12E/O 8SE/O SWITCH # 56 | 35202262 |  |  | STS-POLE_DECA_REPL - 12E/O 8SE/O SWITCH | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 40.9957 | -121.7345 |  | TIER 2 | 655 | 10373-2101, PIT NO 3 | F45 | 5663 | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101514830 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-11-24 |  | COMP | 2020-11-24 | [16 empty] | 2019-04-27 | 2020-04-27 | 2020-11-30 | 2020-11-30 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103732101 | 27256.55 | 4773.7 | 2519.9 | 1298.5 | 1298.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117112895 | POLE_BROK_REPL - 11E/O 8SE/O SWITCH # 56 | 35202266 |  |  | STS-POLE_BROK_REPL - 11E/O 8SE/O SWITCH | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 40.9955 | -121.7351 |  | TIER 2 | 655 | 10373-2101, PIT NO 3 | F45 | 5663 | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101514829 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-04 |  | COMP | 2020-12-04 | [16 empty] | 2019-04-27 | 2020-04-27 | 2020-11-30 | 2020-11-30 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103732101 | 27567.42 | 4269.5 | 2700.9 | 1479.5 | 1479.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117116203 | POLE_DECA_REPL - 15E/0 8SE/O SWITCH # 56 | 35202274 |  |  | STS-POLE_DECA_REPL - 15E/0 8SE/O SWITCH | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 40.9962 | -121.7328 |  | TIER 2 | 655 | 10373-2101, PIT NO 3 | F45 | 5663 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101514843 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-28 | 2020-04-28 | 2020-11-30 | 2020-11-30 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103732101 | 1 | 3012 | 1698.3 | 1935 | 1935 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117178790 | POLE_BROK_REPL - 1N/O 1E/O C/O DUNN-MOOD | 35215425 |  |  | STS-POLE_BROK_REPL - 1N/O 1E/O C/O DUNN- | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.8185 | -121.9224 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | J4106 | 4523 | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | [6 empty] | 58.6 | 58.6 |  |  | 0 | 58.6 | 58.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103018632 | OH RELW PRI INSP ESTR GO PROG FMOB TER2 FSRP | Pole | 2021-01-27 | 2021-02-09 | COMP | 2021-01-27 |  |  | 2021-02-09 | 2021-02-09 | [12 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103321101 | 15733.14 | 552.9 | 552.9 | 441.5 | 441.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117187210 | POLE_BROK_REPL - 18182 DUNN-MOODY RDMONT | 35154596 |  |  | STS-POLE_BROK_REPL - 18182 DUNN-MOODY RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.8143 | -121.9318 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | J4014 | 4523 | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Dispatched | CLICK | [6 empty] | 70 | 70 |  |  | 0 | 70 | 70 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101478982 | RELW OH PRI INSP CLR ESTR FMOB TER2 FSRP | Pole | 2021-02-01 |  | COMP | 2021-02-01 | [16 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103321101 | 18040.52 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117225417 | POLE_BROK_REPL - R/O 30145 JACKSON LN 1S | 35214856 |  |  | STS-POLE_BROK_REPL - R/O 30145 JACKSON L | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.8462 | -121.9229 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | I4020 | 6449 | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | [6 empty] | 65.5 | 65.5 |  |  | 0 | 65.5 | 65.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101519910 | INSP RELW OH PRI REMT NOAC ESTR FMOB TER2 FSRP | Pole | 2021-01-20 |  | COMP | 2021-01-20 | [16 empty] | 2019-05-13 | 2020-05-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103321101 | 18139.57 |  | 0 | 978 | 978 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117243867 | POLE_DECA_REPL - 3N/O 21153 BIG BEND RDM | 35154848 |  |  | STS-POLE_DECA_REPL - 3N/O 21153 BIG BEND | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.903 | -121.9009 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | H41 | 1633 | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Dispatched | CLICK | [6 empty] | 44.2 | 44.2 |  |  | 0 | 44.2 | 44.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101547283 | RELW OH PRI INSP JPOL REMT FIRE NOAC ESTR REAR FMOB TER2 FSRP | Pole | 2021-01-27 | 2021-01-27 | COMP | 2021-01-27 | [16 empty] | 2019-05-15 | 2019-10-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103321101 | 6100.95 | 3172.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117274532 | POLE_BROK_REPL - 5S/O CO-9315 S/O PIT 5 | 35215384 |  |  | STS-POLE_BROK_REPL - 5S/O CO-9315 S/O PI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 40.9819 | -121.9697 |  | TIER 2 | 218 | 10132-1101, PIT NO 5 | F39 | 3019 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101513528 | RELW OH PRI CLR JPOL REMT FIRE NOAC ESTR FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-19 | 2020-05-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 101321101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | MONTGOMERY CREEK | Burney |  |  | OPEN | 117322197 | POLE_BROK_REPL - 16S/O CO 2955 IRON CANY | 35215703 |  |  | STS-POLE_BROK_REPL - 16S/O CO 2955 IRON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 41.0096 | -121.9654 |  | TIER 2 | 218 | 10132-1101, PIT NO 5 | F39 | 3019 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Scheduled | CLICK | [6 empty] | 71.8 | 71.8 |  |  | 0 | 71.8 | 71.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101513551 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-18 | 2021-02-18 | COMP | 2021-02-18 | [16 empty] | 2019-05-24 | 2020-05-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 101321101 | 21761.47 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OAK RUN | Redding |  |  | OPEN | 116615234 | POLE_BROK_REPL - 1W/O 10602 OAK RUN RDOA | 35091325 |  |  | STS-POLE_BROK_REPL - 1W/O 10602 OAK RUN | CONS | CONS ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.5968 | -122.1711 |  | TIER 2 | 664 | 10335-1101, DESCHUTES | O35 | 2711 | Y | 311 |  |  | 2021-03-20 07:00 | 2021-03-30 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 42.9 | 42.9 |  |  | 0 | 42.9 | 42.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101470339 | RELW OH PRI BTKA JPOL FIRE ESTR USA FMOB TER2 PRTO | Pole | 2020-06-01 | 2020-07-21 | COMP | 2019-05-30 |  |  | 2019-09-24 | 2019-09-24 | [12 empty] | 2019-02-27 | 2020-02-27 |  | 2020-02-27 | Q1 Work Plan | 2020-02-27 | EEI |  | 103351101 | 9615.5 | 2302.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OAK RUN | Redding |  |  | OPEN | 116592069 | POLE_DECA_REPL - 1W/O 11203 OAK RUN RD O | 35090533 |  |  | STS-POLE_DECA_REPL - 1W/O 11203 OAK RUN | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6147 | -122.1352 |  | TIER 2 | 664 | 10335-1101, DESCHUTES | N35 | 2711 | Y | 311 |  |  | 2021-04-19 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 31.8 | 31.8 |  |  | 0 | 31.8 | 31.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101459614 | JPOL RELW OH PRI REMT FIRE ESTR FMOB TER2 PRTO | Pole | 2020-04-02 | 2020-04-02 | COMP | 2019-08-19 |  |  | 2019-05-14 | 2019-05-14 | [12 empty] | 2019-02-25 | 2020-02-25 |  | 2020-02-25 | Program Manager | 2020-02-25 | EEI |  | 103351101 | 11194.6 | 3428.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-20
North | NV | OAK RUN | Redding |  |  | OPEN | 116593213 | POLE_DECA_REPL - 3E/O 11203 OAK RUN RD O | 35090549 |  |  | GC-POLE_DECA_REPL - 3E/O 11203 OAK RUN | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6165 | -122.1325 |  | TIER 2 | 664 | 10335-1101, DESCHUTES | N35 | 2711 | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 40.1 | 40.1 |  |  | 0 | 40.1 | 40.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101459606 | RELW OH PRI JPOL FIRE TRAF FLAG ESTR PROG FMOB TER2 PRTO | Pole | 2019-05-08 | 2020-06-13 | COMP | 2019-05-08 |  |  | 2019-05-14 | 2019-05-14 | [12 empty] | 2019-02-25 | 2020-02-25 |  | 2020-02-25 | Q1 Work Plan | 2020-02-25 | EEI |  | 103351101 | 6711.83 | 237.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OAK RUN | Redding |  |  | OPEN | 116614891 | POLE_DECA_REPL - 7SW/O 14096 OAK RUN TO | 35090648 |  |  | STS-POLE_DECA_REPL - 7SW/O 14096 OAK RUN | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6937 | -122.0106 |  | TIER 2 | 664 | 10335-1101, DESCHUTES | M38 | 2591 | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | [6 empty] | 31 | 31 |  |  | 0 | 31 | 31 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101458730 | RELW PUBL OH PRI CUST REMT TRAF FLAG ESTR BTKA USA PROG FMOB TER2 PRTO | Pole | 2020-05-29 | 2020-06-01 | COMP | 2019-08-08 |  |  | 2019-05-14 | 2019-05-14 | [12 empty] | 2019-02-27 | 2020-02-27 |  | 2020-02-27 | Q1 Work Plan | 2020-02-27 | EEI |  | 103351101 | 19343.92 | 82.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OAK RUN | Redding |  |  | OPEN | 116746938 | POLE_BURN_REPL - 4N/O 12608 OAK RUN RD O | 35137456 |  |  | STS-POLE_BURN_REPL - 4N/O 12608 OAK RUN | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6559 | -122.0742 |  | TIER 2 | 664 | 10335-1101, DESCHUTES | M37 | 5281 | Y | 311 |  |  | 2021-04-12 07:00 | 2021-04-16 16:00 | Reserved | CLICK | [6 empty] | 17 | 17 |  |  | 0 | 17 | 17 |  |  | EC | E | Pole | Burnt | Replace |  | 101459332 | RELW OH PRI REMT NOAC ESTR PROG FMOB TER2 PRTO | Pole | 2020-02-04 | 2020-02-04 | COMP | 2020-02-04 |  |  | 2020-01-02 | 2020-01-03 | [12 empty] | 2019-03-15 | 2019-10-23 |  | 2019-10-23 | Program Manager | 2020-01-29 | ENENG |  | 103351101 | 11637.2 | 915.4 |  |  |  | 915.4 |  | 915.4 |  | Y | MPP File Only | N |  | Y | 2020-02-20
North | NV | OROVILLE | Chico |  |  | OPEN | 116744143 | POLE_DECA_REPL - 3245 CLARK RD/1PE (HWY | 35214847 |  |  | STS-POLE_DECA_REPL - 3245 CLARK RD/1PE ( | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.6697 | -121.6282 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V3301 | 17941 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.9 | 16.9 |  |  | 0 | 16.9 | 16.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100397894 | OH RELW PRI CLR JPOL REMT ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2019-03-15 | 2020-03-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103091102 | 7342.74 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116748977 | POLE_BURN_REPL - 2N/O C/O CLARK RDOROVIL | 35154157 |  |  | STS-POLE_BURN_REPL - 2N/O C/O CLARK RDOR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land JointPole |  |  | 39.6494 | -121.6336 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V3311 | 17871 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.9 | 34.9 |  |  | 1 | 33.9 | 33.9 |  |  | EC | E | Pole | Burnt | Replace |  | 100398014 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole | 2020-04-20 |  | COMP | 2020-04-20 |  |  | 2020-12-28 | 2020-12-28 | [12 empty] | 2019-03-16 | 2020-03-16 | 2024-03-14 | 2024-03-14 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 103091102 | 16824.63 | 253.9 | 0 | 111.7 | 111.7 | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116752081 | POLE_BROK_REPL - TRANS AT 3390 DRY CREEK | 35214940 |  |  | STS-POLE_BROK_REPL - TRANS AT 3390 DRY C | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.6745 | -121.5816 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V34 | 815317 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100375457 | RELW OH PRI CLR JPOL REMT SWRK ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103091102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116752415 | POLE_DECA_REPL - 3693 RUNAWAY RD/1PE ORO | 35214945 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.6637 | -121.6357 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V3306 | 17951 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100397971 | RELW OH SEC JPOL RTRN REMT ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103091102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116757241 | POLE_DECA_REPL - 1E/O 3784 W.BRANCH LN O | 35082465 |  |  | STS-POLE_DECA_REPL - 1E/O 3784 W.BRANCH | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.6664 | -121.632 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V3306 | 17945 | Y | 311 | [5 empty] | Order Operation | [6 empty] | 73.4 | 73.4 |  |  | 0 | 73.4 | 73.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100397960 | RELW OH PRI JPOL RESD FIRE ESTR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-31 |  | COMP | 2021-01-31 | [16 empty] | 2019-03-18 | 2019-09-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | Chico |  | 103091102 | 10596.43 | 110.9 | 110.9 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116759235 | POLE_DECA_REPL - T-PL#06/07 ON LINE R/O | 35154177 |  |  | STS-POLE_DECA_REPL - T-PL#06/07 ON LINE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 39.6103 | -121.5923 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | W34 | 5171 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.5 | 37.5 |  |  | 0 | 37.5 | 37.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100331790 | RELW OH PRI RESD REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-07-29 | 2020-07-28 | COMP | 2020-07-28 | [16 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 103091102 | 29072.5 | 927.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116764184 | POLE_DECA_REPL - DURHAM PENTZ RD ON CIRC | 35215079 |  |  | STS-POLE_DECA_REPL - DURHAM PENTZ RD ON | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 39.6412 | -121.6433 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V3220 | 1375 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.3 | 15.3 |  |  | 0 | 15.3 | 15.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100397715 | RELW OH PRI CLR JPOL FLAG RESD FIRE TRAF ESTR GO USA FMOB TER2 PRTO FSRP | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103091102 | 11657.69 | 110.9 | 110.9 | 1071.5 | 1071.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116766363 | POLE_DECA_REPL - 2/N/O/175 BUCKHORN TR.O | 35215115 |  |  | STS-POLE_DECA_REPL - 2/N/O/175 BUCKHORN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.5911 | -121.5133 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | W36 | 1527 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100331772 | RELW OH PRI JPOL BTKA RESD REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103091102 | 1 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116766450 | POLE_DECA_REPL - 3/N/O/175 BUCKHORN TR.O | 35215120 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | FAA JointPole |  |  | 39.5925 | -121.5136 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | W36 | 1527 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 18.8 | 18.8 |  |  | 0 | 18.8 | 18.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100437401 | OH RELW PRI JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103091102 | 7786.1 | 140.2 | 140.2 | 140.2 | 140.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116805776 | POLE_DECA_REPL - #2 A/F 2772 PENTZ RD @ | 35215335 |  |  | STS-POLE_DECA_REPL - #2 A/F 2772 PENTZ R | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.6519 | -121.5637 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V34 | 7109 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100427431 | RELW ESTR OH PRI REMT GO BTKA REAR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103091102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116820173 | POLE_BROK_REPL - 3606 CORY CANYON/1PS/3P | 35214621 |  |  | STS-POLE_BROK_REPL - 3606 CORY CANYON/1P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.6557 | -121.6565 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V32 | 5297 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100397794 | RELW OH PRI JPOL RESD REMT FIRE SPCR ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103091102 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116851977 | POLE_DECA_REPL - 3143 WILLIAMS RD 4PN/3P | 35154631 |  |  | STS-POLE_DECA_REPL - 3143 WILLIAMS RD 4P | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 39.6682 | -121.6563 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V32 | 368837 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 23.2 | 23.2 |  |  | 0 | 23.2 | 23.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100397846 | RELW OH PRI CLR JPOL REMT FIRE ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-05-19 |  | COMP | 2020-05-19 | [16 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | CALENG |  | 103091102 | 23830.23 | 385.8 |  |  |  | 177.3 |  | 177.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116864546 | POLE_BROK_REPL - 3078 DURHAM PENTZ/6PE O | 35215336 |  |  | STS-POLE_BROK_REPL - 3078 DURHAM PENTZ/6 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 39.6407 | -121.6604 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V32 | 133679 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100397743 | RELW OH PRI CLR RESD FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103091102 | 1 | 34.8 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 117338804 | POLE_BROK_REPL - OFF CHEROKEE RD | 35203073 |  |  | STS-POLE_BROK_REPL - OFF CHEROKEE RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.6099 | -121.5391 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | W35 | 17483 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 16.3 | 16.3 |  |  | 0 | 16.3 | 16.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103653477 | RELW OH PRI ESTR JPOL RESD BTKA REAR FMOB TER2 PRTO FSRP | Pole | 2021-02-22 |  | COMP | 2021-02-22 | [16 empty] | 2019-05-29 | 2020-05-29 | 2020-11-02 | 2020-11-02 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103091102 | 10727.73 | 372.3 | 202.1 | 202.1 | 202.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | COMP | 116822491 | POLE_BROK_REPL - 5E/O 3343 C0RY CANYON R | 35111429 |  |  | STS-POLE_BROK_REPL - 5E/O 3343 C0RY CANY | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.6598 | -121.6503 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V32 | 5297 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 40.1 | 40.1 |  |  | 0 | 40.1 | 40.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100397810 | RELW OH PRI COMP JPOL RESD FIRE FLAG ESTR USA CCNT FMOB TER2 PRTO FSRP | Pole | 2020-04-16 | 2020-06-08 | COMP | 2020-04-16 | COMP | 2021-02-10 | 2019-06-24 | 2019-06-24 | [11 empty] | 2021-02-16 | 2021-02-10 | 2020-03-24 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-07-31 | Bakersfield |  | 103091102 | 16545.04 | 2607.1 | 715.4 | -4.6 | -4.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Chico |  |  | COMP | 116825457 | POLE_BROK_REPL - 3500 CORY CANYON RD 4P | 35111430 |  |  | STS-POLE_BROK_REPL - 3500 COREY CANYON R | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.6622 | -121.6496 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V32 | 5297 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 40.1 | 40.1 |  |  | 0 | 40.1 | 40.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103123851 | RELW OH PRI COMP JPOL RESD ESTR USA CCNT FMOB TER2 PRTO FSRP | Pole | 2020-04-16 | 2020-07-06 | COMP | 2020-04-16 | COMP | 2021-02-10 | 2019-06-24 | 2019-06-24 | [11 empty] | 2021-02-16 | 2021-02-10 | 2020-03-25 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-07-31 | Bakersfield |  | 103091102 | 11104.36 | 4374.9 | 863.8 | -4.6 | -4.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Chico |  |  | OPEN | 116812803 | POLE_BROK_REPL - 3078 AT HOME JACKSON RA | 35202316 |  |  | STS-POLE_BROK_REPL - 3078 AT HOME JACKSO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.6485 | -121.6663 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V32 | 17247 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 46.7 | 46.7 |  |  | 0 | 46.7 | 46.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103123841 | RELW OH PRI JPOL RESD FIRE ESTR USA FSRP PRTO FMOB TER2 | Pole | 2020-12-01 | 2021-01-19 | COMP | 2020-12-01 | [16 empty] | 2019-03-22 | 2020-03-22 | 2020-09-28 | 2020-09-28 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103091102 | 20243.87 | 1242.3 | 744.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | COMP | 116804710 | POLE_DECA_REPL - 2671 WILLIAMS RD/1PN OR | 35111554 |  |  | STS-POLE_DECA_REPL - 2671 WILLIAMS RD/1P | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2019-10-11 | No Action | 39.6494 | -121.6601 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V32 | 5057 | Y | 311 |  |  | 2021-01-05 | 2021-01-05 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 61.7 | 61.7 |  |  | 60 | 1.7 | 1.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100397767 | RELW OH PRI COMP JPOL RESD FIRE TRAF FLAG ESTR USA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-08-12 | 2020-08-13 | COMP | 2020-08-11 | COMP | 2021-01-05 | 2019-06-21 | 2019-08-15 | [11 empty] | 2021-01-11 | 2021-01-05 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-07-31 | Bakersfield |  | 103091102 | 15811.4 | 20988.6 | 18135.3 | 18135.3 | 18135.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | COMP | 116822147 | POLE_DECA_REPL - A/F 3405 CORY CANYON RD | 35154471 |  |  | STS-POLE_DECA_REPL - A/F 3405 CORY CANYO | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.6591 | -121.652 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V32 | 5297 | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 51.6 | 51.6 |  |  | 43 | 1.6 | 1.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100397806 | RELW OH PRI COMP CLR RESD FIRE SPCR FLAG ESTR USA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-08-14 | 2020-08-14 | COMP | 2020-08-14 | COMP | 2021-01-13 | 2020-03-24 | 2020-03-24 | [11 empty] | 2021-02-18 | 2021-01-13 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 103091102 | 27598.45 | 22215.6 | 19313.1 | 19442.8 | 19442.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | COMP | 116827157 | POLE_BROK_REPL - 3606 COREY/CANYON 1PN O | 35111561 |  |  | STS-POLE_BROK_REPL - 3606 COREY/CANYON 1 | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.6646 | -121.6478 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V32 | 5297 | Y | 311 |  |  | 2021-01-12 | 2021-01-12 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 56.1 | 56.1 |  |  | 73.5 | 0.8 | 0.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103123859 | RELW OH PRI COMP CLR JPOL RESD FIRE JAR SPCR USA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-08-11 | 2020-08-11 | COMP | 2020-08-11 | COMP | 2021-01-12 | 2019-06-24 | 2019-06-24 | [11 empty] | 2021-02-18 | 2021-01-12 | 2020-03-25 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-07-31 | Bakersfield |  | 103091102 | 9484.22 | 22748.8 | 20713 | 20713 | 20713 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Chico |  |  | COMP | 116845276 | POLE_DECA_REPL - 3143 WILLIAMS RD/1PN OR | 35111540 |  |  | STS-POLE_DECA_REPL - 3143 WILLIAMS RD/1P | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.6662 | -121.6587 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V32 | 368837 | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 48.1 | 48.1 |  |  | 20 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100397828 | RELW OH PRI COMP CLR JPOL RESD FIRE SPCR FLAG ESTR BTKA USA PROG CPGG FMOB TER2 PRTO FSRP | Pole | 2020-08-11 | 2020-09-23 | COMP | 2020-08-11 | COMP | 2021-01-06 | 2019-06-24 | 2019-06-24 | [11 empty] | 2021-01-11 | 2021-01-06 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-07-31 | Bakersfield |  | 103091102 | 6626.33 | 7036.2 | 5572.9 | 5572.9 | 5572.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | COMP | 116851664 | POLE_DECA_REPL - 3143 WILLIAMS RD/3PN OR | 35111439 |  |  | STS-POLE_DECA_REPL - 3143 WILLIAMS RD/3P | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.6676 | -121.6583 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V32 | 368837 | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 52.1 | 52.1 |  |  | 30 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100397825 | RELW OH PRI COMP CLR JPOL RESD FIRE SPCR FLAG ESTR BTKA USA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-09-02 | 2020-11-10 | COMP | 2020-09-01 | COMP | 2021-01-06 | 2019-06-24 | 2019-06-24 | [11 empty] | 2021-01-11 | 2021-01-06 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-07-31 | Bakersfield |  | 103091102 | 8697.43 | 14854.8 | 8355.3 | 8355.3 | 8355.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116748391 | POLE_BURN_REPL - R/O 3813 STEAMBOAT ROCK | 35154149 |  |  | STS-POLE_BURN_REPL - R/O 3813 STEAMBOAT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.6741 | -121.6309 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V3301 | 17937 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 64.2 | 63.1 | 1.1 |  | 0 | 64.2 | 63.1 | 1.1 |  | EC | E | Pole | Burnt | Replace |  | 100397865 | RELW OH PRI JPOL RESD REMT ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-06-15 | 2020-10-20 | COMP | 2020-06-15 | [16 empty] | 2019-03-16 | 2020-03-16 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2020-12-31 | CALENG |  | 103091102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116817423 | POLE_BROK_REPL - 2871 WILLIAMS RD/3PN/2P | 35111555 |  |  | STS-POLE_BROK_REPL - 2871 WILLIAMS RD/3P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.6587 | -121.6586 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V32 | 5057 | Y | 311 |  |  | 2021-03-08 06:00 | 2021-03-08 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 53.1 | 53.1 |  |  | 27.5 | 30.9 | 30.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100397815 | RELW OH PRI JPOL RESD REMT FIRE ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-06 | 2021-01-06 | COMP | 2021-01-06 |  |  | 2019-06-24 | 2019-06-24 | [12 empty] | 2019-03-23 | 2020-03-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Bakersfield |  | 103091102 | 7377.62 | 12738.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116818041 | POLE_BROK_REPL - 2871 WILLIAMS RD/ 3PN/4 | 35111556 |  |  | STS-POLE_BROK_REPL - 2871 WILLIAMS RD/ 3 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.6594 | -121.6563 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V32 | 5057 | Y | 311 |  |  | 2021-03-08 06:00 | 2021-03-08 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100397817 | RELW OH PRI CLR JPOL RESD REMT FIRE ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2019-06-24 | 2019-06-24 | [12 empty] | 2019-03-23 | 2020-03-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Bakersfield |  | 103091102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Chico |  |  | OPEN | 116845277 | POLE_DECA_REPL - 3143 WILLIAMS RD/1PEORO | 35111541 |  |  | STS-POLE_DECA_REPL - 3143 WILLIAMS RD/1P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.6654 | -121.6588 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | V32 | 368837 | Y | 311 |  |  | 2021-03-08 06:00 | 2021-03-08 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100397829 | RELW OH PRI CLR JPOL RESD FIRE BTKA SPCR FLAG ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2019-06-24 | 2019-06-24 | [12 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Bakersfield |  | 103091102 | 1 | 4259 |  |  |  | 4259 |  | 4259 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Oroville |  |  | OPEN | 116826178 | POLE_DECA_REPL - C/O DACK WY AND DACK CT | 35227177 |  |  | STS-POLE_DECA_REPL - C/O DACK WY AND DAC | ADER | ADER | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.4168 | -121.4999 |  | TIER 2 | 161 | 10291-1109, WYANDOTTE | I25 | 6521 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100375298 | OH PRI INSP JPOL MINR RESD REMT BTKA FMOB TER2 RELW | Pole |  |  | REQD | [17 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | Per DOT Approved Request 45770 |  | Chico |  | 102911109 | 1 | 34.8 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-02-06
North | NV | OROVILLE | Oroville |  |  | OPEN | 116854726 | POLE_DECA_REPL - 2E\O 1N\O 185 CANYON DR | 35202530 |  |  | STS-POLE_DECA_REPL - 2E\O 1N\O 185 CANYO | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.5193 | -121.4838 |  | TIER 2 | 394 | 10291-1110, WYANDOTTE | G25G | 345 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.8 | 27.8 |  |  | 0 | 27.8 | 27.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100392708 | OH PRI CLR JPOL RESD ESTR BTKA FMOB FSRP PRTO RELW TER2 | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2019-03-28 | 2020-03-28 | 2020-07-08 | 2020-07-08 | 2021 CBP Plan | 2021-01-31 | QUES |  | 102911110 | 14272.97 |  | -1230.8 | -687.8 | -687.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Oroville |  |  | OPEN | 116920792 | POLE_BROK_REPL - 8065 RESERVOIR RD 3PL S | 35202599 |  |  | STS-POLE_BROK_REPL - 8065 RESERVOIR RD 3 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.4085 | -121.5144 |  | TIER 2 | 161 | 10291-1109, WYANDOTTE | I2521 | 81581 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100430349 | RELW OH PRI INSP RESD REMT NOAC ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-02 | 2020-04-02 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-01-31 | QUES |  | 102911109 | 1 | 250.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Oroville |  |  | OPEN | 117207820 | POLE_DECA_REPL - 1S\O 253 PALERMO DR ORO | 35214622 |  |  | STS-POLE_DECA_REPL - 1S\O 253 PALERMO DR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.5168 | -121.5005 |  | TIER 2 | 394 | 10291-1110, WYANDOTTE | G25F | 13363 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100427727 | RELW OH PRI JPOL RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 102911110 | 1 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Oroville |  |  | OPEN | 117683208 | POLE_BROK_REPL - 66 THOMPSON FLAT RD ORO | 35202465 |  |  | STS-POLE_BROK_REPL - 66 THOMPSON FLAT RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 39.537 | -121.5512 |  | TIER 2 | 616 | 10291-1102, WYANDOTTE | G2401 | 13029 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100423489 | RELW OH PRI MINR GO TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-02-28 | QUES |  | 102911102 | 1 |  | 0 | 244.5 | 244.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Oroville |  |  | CNCL | 116849885 | POLE_DECA_REPL - 91 TOYON HILL DR 3PEORO | 35154626 |  |  | *CNCL*POLE_DECA_RPL-91 TOYON HILL DR | DOCC | DOCC | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.5603 | -121.3522 |  | TIER 2 | 181 | 10322-1101, KANAKA | F28 | 303 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100373527 | RELW OH PRI CNCL JPOL REMT NOAC ESTR GO REAR CPGD FMOB TER2 PRTO | Pole | 2020-06-02 | 2020-07-24 | COMP | 2020-06-02 | [15 empty] | 2021-02-17 | 2021-02-17 | 2020-03-27 |  | 2020-03-27 | circuit based plan 2.14 | 2020-05-01 | CALENG |  | 103221101 | 33020.81 | 2527.5 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | COMP | 114895774 | POLE_DECA_REPL - 155 DISTRICT CENTER DR | 35144604 |  |  | STS-POLE_DECA_REPL - 155 DISTRICT CENTER | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.4488 | -121.4841 |  | TIER 2 | 161 | 10291-1109, WYANDOTTE | I2504 | 13495 | Y | 311 |  |  | 2021-01-11 | 2021-01-11 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 81 | 81 |  |  | 0.5 | 80.5 | 80.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100425240 | OH PRI INSP CLR JPOL RESD REMT NOAC GO PROG FMOB TER2 CCNT RELW COMP | Pole | 2020-02-20 | 2020-04-17 | COMP | 2020-02-20 | COMP | 2021-01-11 | [13 empty] | 2021-02-02 | 2021-01-11 | 2019-08-16 |  | 2019-08-16 | circuit based plan 2.14 |  | Chico |  | 102911109 | 14967.03 | 42820.9 | 2282.7 | 2282.7 | 2282.7 | 44.3 |  | 44.3 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | COMP | 116839582 | POLE_DECA_REPL - C/O RIVERVEIW DR./HERIT | 35115251 |  |  | STS-POLE_DECA_REPL - C/O RIVERVEIW DR./H | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.5067 | -121.4704 |  | TIER 2 | 13 | 10291-1103, WYANDOTTE | G25H | 915 | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 40.1 | 40.1 |  |  | 2.5 | 40 | 40 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100425374 | RELW OH PRI PGEA COMP CLR ESTR JPOL RESD BTKA CCNT FMOB TER2 PRTO FSRP | Pole | 2020-03-10 | 2020-03-12 | COMP | 2020-03-10 | COMP | 2021-01-13 | [13 empty] | 2021-02-02 | 2021-01-13 | 2020-03-26 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-03-10 | EEI |  | 102911103 | 7549.03 | 3406.4 | 1492.2 | 1492.2 | 1492.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | COMP | 116863500 | TRAN_SEEP_REPL - 172 WARD BLVD OROVILLE | 35115267 |  |  | STS-TRAN_SEEP_REPL - 172 WARD BLVD OROVI | DOCC | DOCC ERDY SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-06-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2019-12-02 | No Action | 39.5141 | -121.4938 |  | TIER 2 | 13 | 10291-1103, WYANDOTTE | G25G | 1511 | Y | 311 |  |  | 2021-01-15 | 2021-01-15 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 51.5 | 50.1 | 1.4 |  | 16.5 | 51.4 | 50 | 1.4 |  | EC | E | Transformer | Leaks/Seeps/Weeps | Replace |  | 100392828 | RELW OH PRI COMP CLR JPOL RESD FLAG ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2019-08-20 | 2019-08-23 | COMP | 2019-08-20 | COMP | 2021-01-15 | 2019-08-20 | 2019-08-23 | [11 empty] | 2021-01-19 | 2021-01-15 | 2019-10-24 |  | 2019-10-24 | Q1 Work Plan | 2019-08-20 | EEI |  | 102911103 | 32315.46 | 24790.1 | -11267.6 | 4232.4 | 4232.4 | 7379.5 |  | 7379.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | COMP | 116949007 | POLE_DECA_REPL - 5790 ORO-QUINCY HWYOROV | 35115309 |  |  | STS-POLE_DECA_REPL - 5790 ORO-QUINCY HWY | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-06-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.5133 | -121.4458 |  | TIER 2 | 13 | 10291-1103, WYANDOTTE | G260 | 1508 | Y | 311 |  |  | 2021-01-19 | 2021-01-19 | Dispatched | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 40.1 | 40.1 |  |  | 0 | 40.1 | 40.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100375637 | RELW OH PRI COMP CLR JPOL RESD ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2019-08-28 | 2020-01-15 | COMP | 2019-08-28 | COMP | 2021-01-19 | [13 empty] | 2021-01-26 | 2021-01-19 | 2020-04-03 |  | 2020-04-03 | circuit based plan 2.14 | 2019-08-28 | EEI |  | 102911103 | 7474.77 | 1832.4 | 1832.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | COMP | 117014782 | POLE_DECA_REPL - 245 FORTUNE WY OROVILLE | 35144603 |  |  | STS-POLE_DECA_REPL - 245 FORTUNE WY OROV | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.4409 | -121.4873 |  | TIER 2 | 161 | 10291-1109, WYANDOTTE | I2509 | 13497 | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 40.1 | 40.1 |  |  | 0 | 40.1 | 40.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100375920 | RELW PRI OH INSP COMP JPOL RESD ESTR BTKA CCNT FMOB TER2 | Pole | 2020-01-31 | 2020-03-25 | COMP | 2020-01-31 | COMP | 2021-01-13 | [13 empty] | 2021-02-02 | 2021-01-13 | 2019-09-15 |  | 2019-09-15 | circuit based plan 2.14 |  | Chico |  | 102911109 | 12838.4 | 4086.1 | 1409.8 | 1409.8 | 1409.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | COMP | 117017610 | POLE_BROK_REPL - 231 BRYDEN WAY OROVILLE | 35144602 |  |  | STS-POLE_BROK_REPL - 231 BRYDEN WAY OROV | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-07-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.4406 | -121.482 |  | TIER 2 | 161 | 10291-1109, WYANDOTTE | I2510 | 23603 | Y | 311 |  |  | 2021-01-16 | 2021-01-16 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 40.2 | 40.2 |  |  | 0 | 40.2 | 40.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103649172 | RELW OH PRI INSP COMP JPOL RESD ESTR REAR CCNT FMOB TER2 | Pole | 2020-01-08 | 2020-02-07 | COMP | 2020-01-08 | COMP | 2021-01-16 | [13 empty] | 2021-01-20 | 2021-01-16 | 2019-11-17 |  | 2019-11-17 | circuit based plan 2.14 |  | Chico |  | 102911109 | 14695.87 | 6011.4 | 2673.1 | 2673.1 | 2673.1 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | OPEN | 116847453 | POLE_DECA_REPL - 55 QUINCY PLACE R/0OROV | 35115263 |  |  | STS-POLE_DECA_REPL - 55 QUINCY PLACE R/0 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5153 | -121.4787 |  | TIER 2 | 13 | 10291-1103, WYANDOTTE | G25H | 9621 | Y | 311 |  |  | 2021-03-13 07:00 | 2021-03-13 16:00 | Dispatched | CLICK | [6 empty] | 40.1 | 40.1 |  |  | 1 | 40 | 40 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100392095 | RELW OH PRI CLR JPOL RESD ESTR REAR FMOB TER2 PRTO | Pole | 2019-10-29 | 2019-11-25 | COMP | 2019-10-28 | [16 empty] | 2019-03-27 | 2020-03-27 |  | 2020-03-27 | circuit based plan 2.14 | 2019-10-28 | EEI |  | 102911103 | 26024.35 | 4637.4 | 4545.2 | 4519.5 | 4519.5 | 54.6 |  | 54.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | OPEN | 116852390 | POLE_DECA_REPL - F\O 370 MT.IDA RDOROVIL | 35149740 |  |  | STS-POLE_DECA_REPL - F\O 370 MT.IDA RDOR | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-10-06 | Renew Permit | 39.4887 | -121.4911 |  | TIER 2 | 38 | 10291-1107, WYANDOTTE | G25M | 77578 | Y | 311 |  |  | 2021-03-03 07:00 | 2021-03-03 16:00 | Dispatched | CLICK | [6 empty] | 40.1 | 40.1 |  |  | 1.5 | 40 | 40 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100392289 | RELW OH PRI RESD NOAC FLAG ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-04-28 | 2020-07-06 | COMP | 2020-04-28 |  |  | 2020-03-16 | 2020-07-06 | [12 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-04-10 | CALENG |  | 102911107 | 17571.32 | 5389.8 | 334.2 | 334.2 | 334.2 | 288.9 |  | 288.9 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | OPEN | 116873950 | POLE_DECA_REPL - 140 MISTY VEIW LN AT HO | 35144539 |  |  | STS-POLE_DECA_REPL - 140 MISTY VEIW LN A | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.45 | -121.4559 |  | TIER 2 | 38 | 10291-1107, WYANDOTTE | I2603 | 13509 | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 40.1 | 40.1 |  |  | 1 | 40 | 40 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100398744 | PRI OH RELW CLR JPOL RESD FIRE ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-01-07 | 2020-02-07 | COMP | 2020-01-07 | [16 empty] | 2019-03-30 | 2019-12-16 |  | 2019-12-16 | circuit based plan 2.14 |  | Chico |  | 102911107 | 13521 | 4078.3 | 217.9 | 217.9 | 217.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | OPEN | 116875742 | POLE_BROK_REPL - 209 OAKVALE AVE 1PS ORO | 35149756 |  |  | STS-POLE_BROK_REPL - 209 OAKVALE AVE 1PS | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-07-20 | Renew Permit | 39.4989 | -121.4932 |  | TIER 2 | 38 | 10291-1107, WYANDOTTE | G25M | 517 | Y | 311 |  |  | 2021-02-20 07:00 | 2021-02-20 16:00 | Dispatched | CLICK | [6 empty] | 40.3 | 40.3 |  |  | 1.5 | 40 | 40 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100392348 | RELW OH PRI RESD TRAF FLAG ESTR FMOB TER2 PRTO FSRP | Pole | 2020-04-21 | 2020-07-02 | COMP | 2020-04-20 |  |  | 2020-03-31 | 2020-04-13 | [12 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-04-10 | CALENG |  | 102911107 | 13600.58 | 3215.5 | 325.7 | 325.7 | 325.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | OPEN | 116948651 | POLE_DECA_REPL - R/O 515 BUTTE OAKS RD O | 35228375 |  |  | STS-POLE_DECA_REPL - R/O 515 BUTTE OAKS | UNSC | UNSC | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 39.3875 | -121.4489 |  | TIER 2 | 115 | 10319-1101, BANGOR | J26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.5 | 29.5 |  |  | 0 | 29.5 | 29.5 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 103021690 | RELW OH PRI PGEA COMP REMT ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2021-02-01 | 2021-02-01 | COMP | 2021-02-01 | [16 empty] | 2019-04-03 | 2019-06-30 |  | 2019-06-30 | B tag clean up 2/19/2021 |  | Chico |  | 103191101 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | NV | OROVILLE | Oroville |  |  | OPEN | 116954951 | POLE_DECA_REPL - C/O LOST HORIZON DR/LOS | 35115313 |  |  | STS-POLE_DECA_REPL - C/O LOST HORIZON DR | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5032 | -121.4481 |  | TIER 2 | 13 | 10291-1103, WYANDOTTE | G26P | 5423 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 40.1 | 40.1 |  |  | 1 | 40 | 40 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100375813 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-03-10 | 2020-06-09 | COMP | 2020-03-10 |  |  | 2020-06-09 | 2020-06-09 | [12 empty] | 2019-04-04 | 2020-04-04 |  | 2020-04-04 | circuit based plan 2.14 | 2020-03-10 | EEI |  | 102911103 | 14388.26 | 3626.6 | -3.3 | -3.3 | -3.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | OPEN | 116954984 | POLE_DECA_REPL - QOROVILLE95915 | 35115314 |  |  | STS-POLE_DECA_REPL - QOROVILLE95915 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5033 | -121.4483 |  | TIER 2 | 13 | 10291-1103, WYANDOTTE | G26P | 5423 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 40.2 | 40.2 |  |  | 0 | 40.2 | 40.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103649530 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-03-11 | 2020-05-01 | COMP | 2020-03-11 | [16 empty] | 2019-04-04 | 2020-04-04 |  | 2020-04-04 | circuit based plan 2.14 | 2020-03-11 | EEI |  | 102911103 | 16646.07 | 5308 | 1635.2 | 1330.4 | 1330.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | OPEN | 116976731 | POLE_DECA_REPL - 420 DUNSTONE RD 4PL W O | 35144601 |  |  | STS-POLE_DECA_REPL - 420 DUNSTONE RD 4PL | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.4365 | -121.4728 |  | TIER 2 | 161 | 10291-1109, WYANDOTTE | I26 | 13501 | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 40.1 | 40.1 |  |  | 1 | 40 | 40 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100398767 | OH PRI JPOL RESD FIRE ESTR BTKA USA PRTO RELW FMOB TER2 | Pole | 2020-01-30 | 2020-02-07 | COMP | 2020-01-30 | [16 empty] | 2019-04-06 | 2019-10-06 |  | 2019-10-06 | circuit based plan 2.14 |  | Chico |  | 102911109 | 12722.22 | 3511.9 | 217.9 | 217.9 | 217.9 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | COMP | 116949015 | POLE_DECA_REPL - C/O FOREBSTOWN RD/ORO-Q | 35115310 |  |  | STS-POLE_DECA_REPL - C/O FOREBSTOWN RD/O | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.5136 | -121.445 |  | TIER 2 | 13 | 10291-1103, WYANDOTTE | G260 | 1508 | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 20.1 | 20.1 |  |  | 31 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100424722 | RELW OH PRI COMP CLR JPOL REMT ESTR REAR CPGG FMOB TER2 PRTO | Pole | 2019-08-29 | 2020-05-11 | COMP | 2019-08-29 | COMP | 2021-01-08 | 2020-05-11 | 2020-05-11 | [11 empty] | 2021-02-18 | 2021-01-08 | 2020-04-03 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2019-08-29 | EEI |  | 102911103 | 7931.19 | 12805.2 | 9778.7 | 9781.4 | 9781.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | OPEN | 116877104 | POLE_DECA_REPL - C/O MISSION OLIVE BLAZE | 35149762 |  |  | STS-POLE_DECA_REPL - C/O MISSION OLIVE B | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-11-03 | Renew Permit | 39.4346 | -121.4504 |  | TIER 2 | 38 | 10291-1107, WYANDOTTE | I2608 | 5817 | Y | 311 |  |  | 2021-06-09 07:00 | 2021-06-09 16:00 | Scheduled | CLICK | [6 empty] | 59 | 59 |  |  | 0 | 59 | 59 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100398614 | RELW OH PRI CLR JPOL RESD FIRE TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-06-15 | 2020-06-20 | COMP | 2020-04-09 |  |  | 2020-02-20 | 2020-03-02 | [12 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-04-10 | CALENG |  | 102911107 | 27536.66 | 5358.3 | -7.9 | -7.9 | -7.9 | 109 |  | 109 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | OROVILLE | Oroville |  |  | OPEN | 116949866 | POLE_DECA_REPL - AT 972 HURLETON RDOROVI | 35149783 |  |  | STS-POLE_DECA_REPL - AT 972 HURLETON RDO | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole | 2020-06-09 | Renew Permit | 39.4989 | -121.3914 |  | TIER 2 | 38 | 10291-1107, WYANDOTTE | G2821 | 83161 | Y | 311 |  |  | 2021-03-08 06:00 | 2021-03-08 16:00 | Scheduled | CLICK | [6 empty] | 73.9 | 73.9 |  |  | 0 | 73.9 | 73.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100380871 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2021-01-21 |  | COMP | 2021-01-21 |  |  | 2020-02-24 | 2020-03-11 | [12 empty] | 2019-04-03 | 2020-04-03 | 2020-12-13 | 2020-12-13 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 102911107 | 22935.24 | 662.8 | 0 | 978 | 978 | 197.7 |  | 197.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Oroville |  |  | OPEN | 116953720 | POLE_DECA_REPL - C/O LOST HORIZON DR/ORO | 35115311 |  |  | STS-POLE_DECA_REPL - C/O LOST HORIZON DR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5056 | -121.4512 |  | TIER 2 | 13 | 10291-1103, WYANDOTTE | G26J | 865 | Y | 311 |  |  | 2021-07-01 06:00 | 2021-07-01 16:00 | Scheduled | CLICK | [6 empty] | 13.1 | 13.1 |  |  | 1 | 13 | 13 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100425811 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2019-12-09 | 2020-12-28 | COMP | 2019-11-22 |  |  | 2020-12-28 | 2020-12-28 | [12 empty] | 2019-04-04 | 2020-04-04 |  | 2020-04-04 | 2021 CBP Plan | 2019-11-22 | EEI |  | 102911103 | 7503.58 | 290.5 | 0 | 109 | 109 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | OROVILLE | Oroville |  |  | OPEN | 117121191 | POLE_DECA_REPL - 5519 ORO BANGOR HWY 1PN | 35149675 |  |  | STS-POLE_DECA_REPL - 5519 ORO BANGOR HWY | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 39.4575 | -121.4413 |  | TIER 2 | 38 | 10291-1107, WYANDOTTE | H26 | 5545 | Y | 311 |  |  | 2021-07-01 06:00 | 2021-07-01 16:00 | Scheduled | CLICK | [6 empty] | 15.2 | 15.2 |  |  | 0 | 15.2 | 15.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100395784 | RELW OH PRI CLR JPOL RESD FIRE ESTR GO BTKA REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-04-14 |  | COMP | 2020-04-14 | [16 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-04-10 | CALENG |  | 102911107 | 6744.53 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | PALO CEDRO | Redding |  |  | COMP | 116759648 | POLE_DECA_REPL - C/O 7932 DESCHUTES RD. | 35145281 |  |  | STS-POLE_DECA_REPL - C/O 7932 DESCHUTES | MAPP | MAPP SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.5186 | -122.2386 |  | TIER 2 | 226 | 10335-1104, DESCHUTES | Q3302 | 9718 | Y | 311 |  |  | 2021-02-12 07:00 | 2021-02-12 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 32.8 | 32.8 |  |  | 40 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101468077 | RELW OH PRI COMP BTKA JPOL REMT ESTR OTRG CPGG FMOB TER2 PRTO FSRP | Pole | 2020-04-10 | 2020-07-16 | COMP | 2020-04-09 | COMP | 2021-02-05 | 2020-01-02 | 2020-01-03 | [11 empty] | 2021-02-05 | 2021-02-05 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-03-05 | QUES |  | 103351104 | 11703.24 | 5620.1 | 5086.6 | 1287.4 | 1287.4 | 533.5 |  | 533.5 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | PALO CEDRO | Redding |  |  | COMP | 119996738 | POLE_DECA_REPL - 9444 SILVER BRIDGE RD P | 35214185 |  |  | STS-POLE_DECA_REPL - 9444 SILVER BRIDGE | FICL | FICL SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-10 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.562 | -122.2198 |  | TIER 2 | 226 | 10335-1104, DESCHUTES | P3305 | 1477 | Y | 311 |  |  | 2021-01-19 | 2021-01-19 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 30.1 | 30.1 |  |  | 20 | 0 |  |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101488927 | RELW OH SERV TMAN COMP REMT BTKA USA CPGG TER2 ESTR | Pole | 2020-12-04 | 2020-12-04 | COMP | 2020-12-04 | COMP | 2021-01-19 | [13 empty] | 2021-01-20 | 2021-01-19 | 2021-02-07 |  | 2021-02-07 | B tag clean up 11/15/2020 |  | Chico |  | 103351104 | 4465 | 5952 | 5952 | 5952 | 5952 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-11-15
North | NV | PALO CEDRO | Redding |  |  | OPEN | 116753070 | POLE_BROK_REPL - 2S/O RUSTIC OAKS LN. ON | 35145256 |  |  | STS-POLE_BROK_REPL - 2S/O RUSTIC OAKS LN | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6105 | -122.2378 |  | TIER 2 | 226 | 10335-1104, DESCHUTES | N3323 | 7503 | Y | 311 |  |  | 2021-04-12 07:00 | 2021-04-16 16:00 | Reserved | CLICK | [6 empty] | 84.4 | 84.4 |  |  | 0 | 84.4 | 84.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101458966 | RELW OH PRI JPOL REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-03 | 2020-12-03 | COMP | 2020-10-13 |  |  | 2020-01-02 | 2020-01-02 | [12 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | Pole Notification Clean Up 05.29.20 | 2020-09-30 | QUES |  | 103351104 | 25590.06 | 2464 | 2255 |  |  | 418 |  | 418 | Electric Distribution | N | MPP File Only | N |  | Y | 2020-06-02
North | NV | Paradise | Chico |  |  | OPEN | 117240568 | POLE_BROK_REPL - #4N 3800 PENTZ RD PARAD | 35215035 |  |  | STS-POLE_BROK_REPL - #4N 3800 PENTZ RD P | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.6917 | -121.5736 |  | TIER 2 | 293 | 10309-1102, CLARK ROAD | U3418 | 17749 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100404287 | RELW OH PRI INSP JPOL REMT FIRE ESTR GO BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103091102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | PAYNES CREEK | Red Bluff |  |  | OPEN | 117688360 | POLE_BROK_REPL - 28025 MANTON RD PVTP PA | 35195992 |  |  | STS-POLE_BROK _ REPL_28025 MANTON RD P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4053 | -121.99 |  | TIER 2 | 90 | 10254-1101, VOLTA | S39 | 2607 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 55.3 | 55.3 |  |  | 0 | 55.3 | 55.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101551985 | PRI RELW OH TER2 PRTO | Pole | 2020-12-03 | 2021-02-16 | COMP | 2020-12-03 | [16 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | Per DOT Approved Request 45809 | 2020-12-31 | ENENG |  | 102541101 | 26268.31 | 162 | -420.1 | 1354 | 1354 |  |  |  | FRMMA/WMPMA - Electric | N | MPP Owned but exists in DO Pull | N |  | Y | 2021-02-06
North | NV | PAYNES CREEK | Red Bluff |  |  | OPEN | 117191713 | POLE_DECA_REPL - #2N #2E 30990 MANTON RD | 35143595 |  |  | STS-POLE_DECA_REPL - #2N #2E 30990 MANTO | CONS | CONS SRDY JEAP | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4296 | -121.881 |  | TIER 2 | 90 | 10254-1101, VOLTA | S42 | 85533 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-22 16:00 | Dispatched | CLICK | [6 empty] | 81.8 | 81.8 |  |  | 0 | 81.8 | 81.8 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101553085 | RELW OH PRI INSP REMT ESTR BTKA FMOB TER2 | Pole | 2020-04-21 | 2020-04-23 | COMP | 2020-04-21 | [16 empty] | 2019-05-09 | 2020-05-09 | 2020-09-26 | 2020-09-26 | Work Plan Reconcilation (B-Tags) | 2020-02-28 | EEI |  | 102541101 | 7953.74 | 16576 | -35771 |  |  | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Tag in Closure Status | Y | 2020-07-21
North | NV | PAYNES CREEK | Red Bluff |  |  | OPEN | 117250725 | POLE_BURN_REPL - PONDEROSA WY 2.8MLS S\O | 35143731 |  |  | STS-POLE_BURN_REPL - PONDEROSA WY 2.8MLS | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.373 | -121.8039 |  | TIER 2 | 90 | 10254-1101, VOLTA | T43 | 6441 | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-15 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 40.1 | 40.1 |  |  | 5 | 40 | 40 |  |  | EC | B | Pole | Burnt | Replace |  | 101555051 | RELW OH PRI INSP ESTR CLR REMT FIRE REAR FMOB TER2 | Pole | 2020-05-12 | 2020-06-05 | COMP | 2020-05-12 | [16 empty] | 2019-05-16 | 2020-05-16 | 2020-09-24 | 2020-09-24 | B-Tag Addition 07.06.2020 | 2020-02-28 | EEI |  | 102541101 | 27922.18 | 40905.5 | 18924.3 | 18924.3 | 18924.3 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-07-06
North | NV | PLATINA | Red Bluff |  |  | OPEN | 117123931 | POLE_BROK_REPL - 1W/O C/O SUNDAY GULCH O | 35214978 |  |  | STS-POLE_BROK_REPL - 1W/O C/O SUNDAY GUL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 40.3625 | -122.9443 |  | TIER 2 | 358 | 10361-1101, WILDWOOD | T16 | 98896 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101499625 | RELW OH PRI INSP ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103611101 | 1 | 1753.5 | 1753.5 | 514.2 | 514.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | PLATINA | Red Bluff |  |  | OPEN | 117123958 | POLE_BROK_REPL - 2E/O C/O SUNDAY GULCH R | 35214983 |  |  | STS-POLE_BROK_REPL - 2E/O C/O SUNDAY GUL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 40.3638 | -122.94 |  | TIER 2 | 358 | 10361-1101, WILDWOOD | T16 | 98896 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 60 | 60 |  |  | 0 | 60 | 60 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101499668 | RELW OH PRI INSP REMT FIRE NOAC ESTR FMOB TER2 FSRP | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103611101 | 28612.89 | 1940.5 | 1940.6 | 701.3 | 701.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | PLATINA | Red Bluff |  |  | OPEN | 117124638 | POLE_BROK_REPL - 1 N/0 HWY 36 BY HARRISO | 35214987 |  |  | STS-POLE_BROK_REPL - 1 N/0 HWY 36 BY HAR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 40.3628 | -122.9602 |  | TIER 2 | 358 | 10361-1101, WILDWOOD | T15 | 85981 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101501605 | RELW OH PRI INSP REMT ESTR REAR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 103611101 | 1 | 1659.1 | 1659.1 | 280.5 | 280.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | PLATINA | Red Bluff |  |  | OPEN | 117132089 | POLE_BROK_REPL - 13 E/O HWY 36 OFF HWY 3 | 35202406 |  |  | STS-POLE_BROK_REPL - 13 E/O HWY 36 OFF H | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.3576 | -122.9007 |  | TIER 2 | 358 | 10361-1101, WILDWOOD | T17 | 98896 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101498974 | RELW OH PRI INSP REMT FMOB NOAC SWRK ESTR TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-30 | 2020-11-05 | 2020-11-05 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103611101 | 1 | 165.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | PLATINA | Red Bluff |  |  | OPEN | 117134255 | POLE_DECA_REPL - HWY 36 6040-7190 TAP PL | 35215074 |  |  | STS-POLE_DECA_REPL - HWY 36 6040-7190 TA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.3509 | -122.864 |  | TIER 2 | 358 | 10361-1101, WILDWOOD | T18 | 1454 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101497996 | RELW INSP OH PRI GO FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-01 | 2020-05-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103611101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | Red Bluff | Red Bluff |  |  | OPEN | 119073222 | POLE_BROK_REPL - 1NO 21754 ADOBE RD RED | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-31 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 40.2015 | -122.226 |  | TIER 2 | 694 | 10354-1105, RED BLUFF | X3304 | 146070 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101544289 | REGW OH PRI JPOL RESD ESTR BTKA OTHR FMOB TER2 | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2020-05-28 | 2021-05-28 |  | 2021-05-28 | Per DOT Approved Request 50355 |  | UNASSIGNED |  | 103541105 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117136404 | POLE_BROK_REPL - 21242 SHANGRI WAYRED BL | 35176592 |  |  | STS-POLE_BROK_REPL - 21242 SHANGRI WAYRE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.2811 | -122.2528 |  | TIER 2 | 595 | 10354-1104, RED BLUFF | V33 | 2039 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.9 | 36.7 | 1.2 |  | 0 | 37.9 | 36.7 | 1.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101527105 | RELW OH PRI INSP CLR REMT FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-11-05 | 2020-11-05 | COMP | 2020-11-05 | [16 empty] | 2019-05-01 | 2020-05-01 | 2021-05-31 | 2021-05-31 | B-Tag Clean Up 5/14/20 | 2020-09-30 | Chico |  | 103541104 | 16899.7 | 85.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-05-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117138316 | POLE_BROK_REPL - 1S/0 2E/0 16250 PENNER | 35176593 |  |  | STS-POLE_BROK_REPL - 1S/0 2E/0 16250 PEN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.2655 | -122.2537 |  | TIER 2 | 595 | 10354-1104, RED BLUFF | V33 | 85291 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.7 | 40.5 | 1.2 |  | 0 | 41.7 | 40.5 | 1.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101526554 | RELW OH PRI INSP CLR REMT FIRE SPCR ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-09-12 | 2020-09-12 | COMP | 2020-09-12 | [16 empty] | 2019-05-01 | 2020-05-01 | 2021-05-31 | 2021-05-31 | B-Tag Clean Up 5/14/20 | 2020-09-30 | Chico |  | 103541104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-05-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117169395 | POLE_BROK_REPL - A/F C/O GREEN OAK DR. A | 35226693 |  |  |  | ADER | ADER | Poles | MPP | Not Funded as 2020 Wildfire OII | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | Permit |  |  | 40.0188 | -122.4097 |  | TIER 2 | 60 | 10333-1101, CORNING | BB2906 | 85211 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101523476 | OH PRI RESD JAR FLAG GO BTKA FMOB TER2 PRTO RELW | Pole |  |  | REQD | [17 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | work plan year cleanup 01/21/2021 | 2021-05-31 | Chico |  | 103331101 | [9 empty] | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-21
North | NV | RED BLUFF | Red Bluff |  |  | COMP | 117069428 | POLE_DECA_REPL - #1N 14975 PLEASANT VALL | 35137503 |  |  | STS-POLE_DECA_REPL - #1N 14975 PLEASANT | FICL | FICL SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.2292 | -122.3566 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | W3013 | 85361 | Y | 311 |  |  | 2021-01-19 | 2021-01-19 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 32 | 32 |  |  | 52.5 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101539466 | RELW OH PRI COMP JPOL REMT CITY ESTR BTKA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-04-01 | 2020-04-01 | COMP | 2020-04-01 | COMP | 2021-01-19 | [13 empty] | 2021-01-22 | 2021-01-19 | 2019-10-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-29 | ENENG |  | 103541101 | 17073.36 | 14961.1 | 14877.7 | 14877.7 | 14877.7 | 83.4 |  | 83.4 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | COMP | 117081352 | POLE_DECA_REPL - #10W 17525 HWY 36 E/O K | 35137610 |  |  | STS-POLE_DECA_REPL - #10W 17525 HWY 36 E | FICL | FICL SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.222 | -122.4039 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | W29 | 85811 | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 32.8 | 32.8 |  |  | 35 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101527115 | RELW OH PRI COMP JPOL REMT ESTR BTKA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | COMP | 2021-01-13 | [13 empty] | 2021-01-21 | 2021-01-13 | 2020-04-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-29 | ENENG |  | 103541101 | 7882.6 | 10114.1 | 10069.7 | 10069.7 | 10069.7 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | COMP | 117081353 | POLE_DECA_REPL - #1S 17535 HWY 36 W/TRAN | 35202160 |  |  | STS-POLE_DECA_REPL - #1S 17535 HWY 36 W/ | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.2195 | -122.3887 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | W29 | 85811 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 30.1 | 30.1 |  |  | 27.5 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101527144 | RELW COMP JPOL OH PRI REMT ESTR BTKA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-12-30 | 2020-12-30 | COMP | 2020-12-30 | COMP | 2021-02-10 | [13 empty] | 2021-02-12 | 2021-02-10 | 2020-04-22 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103541101 | 20692.84 | 3244.4 | 2787.6 | 3097.2 | 3097.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | COMP | 117088862 | POLE_DECA_REPL - A/F 15360 FRONTIER DR W | 35137727 |  |  | STS-POLE_DECA_REPL - A/F 15360 FRONTIER | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.2295 | -122.3477 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | W3014 | 4189 | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 35 | 35 |  |  | 56.5 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101539486 | RELW OH PRI COMP RESD REMT ESTR BTKA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-04-24 | 2021-01-05 | COMP | 2020-04-24 | COMP | 2021-02-09 | 2021-01-05 | 2021-01-05 | [11 empty] | 2021-02-12 | 2021-02-09 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-29 | ENENG |  | 103541101 | 22025.95 | 9322.7 | 6484.9 | 2854.8 | 2854.8 | 211.1 |  | 211.1 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | COMP | 120177471 | POLE_DECA_REPL - IN BACK OF 14525 CARRIA | 35220121 |  |  | STS-POLE_DECA_REPL - IN BACK OF 14525 CA | FICL | FICL SRDY CRDY REDL | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-02-11 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.2157 | -122.2063 |  | TIER 2 | 694 | 10354-1105, RED BLUFF | W3421 | 9367 | Y | 311 |  |  | 2021-01-15 | 2021-01-15 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 30.1 | 30.1 |  |  | 60 | 0 |  |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101527818 | OH PRI CREW CLR RESD ESTR GO RELW COMP FIRE SWRK BTKA REAR CPGG FMOB TER2 | Pole | 2021-01-06 | 2021-01-06 | COMP | 2021-01-06 | COMP | 2021-01-15 | [13 empty] | 2021-01-15 | 2021-01-15 | 2021-03-11 |  | 2021-03-11 | B tag clean up 12/15/2020 |  | Chico |  | 103541105 | 8634.94 | 20574.6 | 20574.6 | 20574.6 | 20574.6 |  |  |  | Electric Distribution | N | Pulled from MPP Import File | N |  | Y | 2020-12-15
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 116971464 | POLE_BROK_REPL - A/F 21760 WILCOX RD RED | 35214732 |  |  | STS-POLE_BROK_REPL - A/F 21760 WILCOX RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 40.2042 | -122.2279 |  | TIER 2 | 694 | 10354-1105, RED BLUFF | X3304 | 85631 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101544298 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-06 | 2020-04-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103541105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 116973973 | POLE_BROK_REPL - 1S/0 14235 NOBLE 0AK RD | 35202141 |  |  | STS-POLE_BROK_REPL - 1S/0 14235 NOBLE 0A | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.2057 | -122.2356 |  | TIER 2 | 694 | 10354-1105, RED BLUFF | X3303 | 3895 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 86.9 | 86.3 | 0.6 |  | 0 | 86.9 | 86.3 | 0.6 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101544180 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-14 |  | COMP | 2021-01-14 |  |  | 2020-12-14 | 2020-12-14 | [12 empty] | 2019-04-07 | 2020-04-07 | 2020-11-07 | 2020-11-07 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103541105 | 21765.94 | 859.3 | 859.3 | 3407.3 | 3407.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117018900 | POLE_BROK_REPL - C\O THE OAK DR.\WILLOW | 35214915 |  |  | STS-POLE_BROK_REPL - C\O THE OAK DR.\WIL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.2443 | -122.2723 |  | TIER 2 | 595 | 10354-1104, RED BLUFF | W3203 | 85303 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101526883 | RELW OH PRI ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-12 | 2020-04-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103541104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117020271 | POLE_BROK_REPL - 6E/O 10N/O 17430 SNIVEL | 35214941 |  |  | STS-POLE_BROK_REPL - 6E/O 10N/O 17430 SN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 40.3088 | -122.262 |  | TIER 2 | 595 | 10354-1104, RED BLUFF | U32 | 2039 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101508271 | RELW OH PRI INSP REMT FIRE NOAC ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-12 | 2020-04-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103541104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117032649 | POLE_BROK_REPL - 18171 REEDS CRK RD RED | 35202242 |  |  | STS-POLE_BROK_REPL - 18171 REEDS CRK RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.1579 | -122.3641 |  | TIER 2 | 440 | 10357-1105, TYLER | Y30 | 1721 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 72.3 | 72.3 |  |  | 0 | 72.3 | 72.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101553542 | RELW OH PRI GO JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-09 |  | COMP | 2021-02-09 | [16 empty] | 2019-04-15 | 2020-04-15 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103571105 | 19502.03 | 558.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117037702 | POLE_BROK_REPL - 18350 JOHNSON RED BLUFF | 35202261 |  |  | STS-POLE_BROK_REPL - 18350 JOHNSON RED B | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.1547 | -122.3574 |  | TIER 2 | 440 | 10357-1105, TYLER | Y30 | 1536 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103645962 | RELW OH SERV JPOL REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-31 |  | COMP | 2020-12-31 | [16 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2021-02-28 | QUES |  | 103571105 | 4258.54 | 811.4 | 632.9 | 1968.8 | 1968.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117044709 | POLE_DECA_REPL - #1N 17750 CLEARWATER DR | 35137604 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.2233 | -122.3759 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | W30 | 85367 | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 30.1 | 30.1 |  |  | 50 | 5 | 5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101539692 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-04-06 | 2020-05-28 | COMP | 2020-04-06 | [16 empty] | 2019-04-16 | 2019-10-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-29 | ENENG |  | 103541101 | 12618.95 | 10887.4 | 9287.4 | 7583.9 | 7583.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117046019 | POLE_DECA_REPL - #6 ON LINE S/O 5890 LOW | 35149925 |  |  | STS-POLE_DECA_REPL - #6 ON LINE S/O 5890 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.969 | -122.5522 |  | TIER 2 | 29 | 10333-1102, CORNING | CC25 | 1917 | Y | 311 |  |  | 2021-03-18 07:00 | 2021-03-18 16:00 | Scheduled | CLICK | [6 empty] | 48.3 | 48.3 |  |  | 0 | 48.3 | 48.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101528405 | RELW OH PRI REMT FIRE NOAC ESTR FMOB TER2 PRTO | Pole | 2020-10-28 | 2020-10-28 | COMP | 2020-10-28 | [16 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103331102 | 8353.69 | 3978.2 | 1313.3 | 1313.3 | 1313.3 | 1304.6 |  | 1304.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117069061 | POLE_BURN_REPL - 5800 OSBORN RD 8E/O HOU | 35149956 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.9536 | -122.4913 |  | TIER 2 | 29 | 10333-1102, CORNING | CC27 | 850337 | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-21 16:00 | Reserved | CLICK | [6 empty] | 47.9 | 47.9 |  |  | 0 | 47.9 | 47.9 |  |  | EC | E | Pole | Burnt | Replace |  | 101530264 | RELW OH PRI REMT FIRE NOAC ESTR FMOB TER2 PRTO | Pole | 2021-02-16 | 2021-02-16 | COMP | 2021-02-16 | [16 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103331102 | 6324.19 | 879.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117069409 | POLE_DECA_REPL - 18210 HWY 36/SPRED BLUF | 35137722 |  |  | STS-POLE_DECA_REPL - 18210 HWY 36/SPRED | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.2216 | -122.36 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | W3018 | 85837 | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101539338 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | [16 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-29 | ENENG |  | 103541101 | 11787.25 | 292 | 292 | 292 | 292 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117081354 | POLE_DECA_REPL - #1N #4W 17691 HWY 36RED | 35215611 |  |  | STS-POLE_DECA_REPL - #1N #4W 17691 HWY 3 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.2201 | -122.381 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | W29 | 85811 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101527157 | JPOL OH PRI RELW REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-22 | 2020-04-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103541101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117088853 | POLE_DECA_REPL - 17525 HWY 36 W/TRANSRED | 35214618 |  |  | STS-POLE_DECA_REPL - 17525 HWY 36 W/TRAN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.2202 | -122.3912 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | W29 | 85811 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101527137 | RELW OH SWRK PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-22 | 2020-04-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103541101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117088855 | POLE_DECA_REPL - 17535 HWY 36RED BLUFF96 | 35202168 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.22 | -122.3888 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | W29 | 85811 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 25 | 5.1 | 5.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101527142 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-30 | 2021-02-17 | COMP | 2020-12-30 |  |  | 2021-02-04 | 2021-02-04 | [12 empty] | 2019-04-22 | 2020-04-22 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103541101 | 15523.51 | 3034.7 | 2698.9 | 2694.8 | 2694.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117088865 | POLE_DECA_REPL - 14615 HANKS DRRED BLUFF | 35214623 |  |  | STS-POLE_DECA_REPL - 14615 HANKS DRRED B | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 40.219 | -122.3404 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | W3020 | 8291 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101539426 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-23 | 2020-04-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103541101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117088866 | POLE_DECA_REPL - AC/F 16450 LABRADOR DR | 35137611 |  |  | STS-POLE_DECA_REPL - AC/F 16450 LABRADOR | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 40.2242 | -122.4121 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | W29 | 85811 | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 30.1 | 30.1 |  |  | 4 | 30 | 30 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101526944 | RELW OH ESTR PRI REMT NOAC FMOB TER2 PRTO FSRP | Pole | 2020-04-13 |  | COMP | 2020-04-13 |  |  | 2021-01-05 | 2021-01-05 | [12 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-29 | ENENG |  | 103541101 | 13186.35 | 5080.9 | 1448.8 | 1448.8 | 1448.8 | 127.7 |  | 127.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117088871 | POLE_DECA_REPL - #1W 17535 HWY 36RED BLU | 35214630 |  |  | STS-POLE_DECA_REPL - #1W 17535 HWY 36RED | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.2201 | -122.3897 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | W29 | 85811 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101527140 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-22 | 2020-04-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103541101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117089714 | POLE_BROK_REPL - GP AT 11W/O 18040 JOHNS | 35214634 |  |  | STS-POLE_BROK_REPL - GP AT 11W/O 18040 J | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.1518 | -122.3802 |  | TIER 2 | 440 | 10357-1105, TYLER | Y29 | 9163 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101555748 | RELW OH SERV JPOL FMOB REMT NOAC ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103571105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117089754 | POLE_BROK_REPL - 12W/O 18040 JOHNSON RD | 35214638 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.1505 | -122.3819 |  | TIER 2 | 440 | 10357-1105, TYLER | Y29 | 9163 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101555749 | RELW OH PRI JPOL REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103571105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117090161 | POLE_BROK_REPL - 21W/O 18040 JOHNSON RDR | 35202174 |  |  | STS-POLE_BROK_REPL - 21W/O 18040 JOHNSON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.1512 | -122.3916 |  | TIER 2 | 440 | 10357-1105, TYLER | Y29 | 9163 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 51.2 | 51.2 |  |  | 0 | 51.2 | 51.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101555758 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-01 | 2021-02-01 | COMP | 2021-02-01 | [16 empty] | 2019-04-24 | 2020-04-24 | 2020-11-12 | 2020-11-12 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103571105 | 7732.28 | 335.7 | 0 | 226.3 | 226.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117090275 | POLE_BROK_REPL - 17 P W/O PVT P 18040 JO | 35214649 |  |  | STS-POLE_BROK_REPL - 17 P W/O PVT P 1804 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 40.1512 | -122.3928 |  | TIER 2 | 440 | 10357-1105, TYLER | Y29 | 9163 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103832426 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103571105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117091368 | POLE_DECA_REPL - #1W 14450 CRAMER RDRED | 35202177 |  |  | STS-POLE_DECA_REPL - #1W 14450 CRAMER RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 40.2134 | -122.3422 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | W3025 | 8291 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101539396 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-02-28 | QUES |  | 103541101 | 1 | 773 | 348 | 592.5 | 592.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117091386 | POLE_DECA_REPL - A/F 14591 BRIAN RDRED B | 35202180 |  |  | STS-POLE_DECA_REPL - A/F 14591 BRIAN RDR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.2154 | -122.3396 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | W3025 | 8291 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 50.2 | 50.2 |  |  | 0 | 50.2 | 50.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101539403 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-09 |  | COMP | 2021-02-09 |  |  | 2021-02-11 | 2021-02-11 | [12 empty] | 2019-04-24 | 2020-04-24 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103541101 | 8177.62 | 303.6 | 0 | 226.3 | 226.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117098607 | POLE_BROK_REPL - GPW/O 1S/O C/O LIVE OAK | 35214722 |  |  | STS-POLE_BROK_REPL - GPW/O 1S/O C/O LIVE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.1467 | -122.337 |  | TIER 2 | 440 | 10357-1105, TYLER | Y30 | 85409 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101553428 | RELW OH SEC JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103571105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117110706 | POLE_BROK_REPL - 1NE/O 1N/O 18900 RED BA | 35214861 |  |  | STS-POLE_BROK_REPL - 1NE/O 1N/O 18900 RE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.1205 | -122.3363 |  | TIER 2 | 440 | 10357-1105, TYLER | Y30 | 85132 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101554112 | RELW OH PRI JPOL REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-27 | 2020-04-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103571105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117153149 | POLE_BROK_REPL - 1E/AT HOUSE 1310 MONTEC | 35215161 |  |  | STS-POLE_BROK_REPL - 1E/AT HOUSE 1310 MO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.1679 | -122.3236 |  | TIER 2 | 392 | 10354-1103, RED BLUFF | X3122 | 85761 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101539212 | RELW OH NOAC PRI JPOL REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103541103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117159450 | POLE_BROK_REPL - 6E/O 2S/O 15400 AWERY R | 35215229 |  |  | STS-POLE_BROK_REPL - 6E/O 2S/O 15400 AWE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.0834 | -122.4632 |  | TIER 2 | 440 | 10357-1105, TYLER | Z27 | 2803 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101555906 | OH RELW PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103571105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117162742 | POLE_BROK_REPL - 1RED BLUFF96080 | 35202483 |  |  | STS-POLE_BROK_REPL - 1RED BLUFF96080 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.1047 | -122.4908 |  | TIER 2 | 440 | 10357-1105, TYLER | Z27 | 2153 | Y | 311 |  |  | 2021-03-18 07:00 | 2021-03-18 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103702115 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-15 | 2020-12-15 | COMP | 2020-12-15 | [16 empty] | 2019-05-04 | 2020-05-04 | 2020-11-21 | 2020-11-21 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103571105 | 12599.54 | 5100.6 | 3593.4 | 2969.5 | 2969.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117163765 | POLE_BROK_REPL - A/H2W/O 15400O RED BANK | 35154382 |  |  | STS-POLE_BROK_REPL - A/H2W/O 15400O RED | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.1112 | -122.468 |  | TIER 2 | 440 | 10357-1105, TYLER | Z27 | 2153 | Y | 311 |  |  | 2021-04-19 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 31.8 | 31.8 |  |  | 0 | 31.8 | 31.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101554433 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-08-17 | 2020-10-06 | COMP | 2020-08-17 | [16 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103571105 | 9413.81 | 1048.3 | 867.3 | 873.7 | 873.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117164392 | POLE_BROK_REPL - 19705 5W/O DEER VALLEY | 35202491 |  |  | STS-POLE_BROK_REPL - 19705 5W/O DEER VAL | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.1977 | -122.3078 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | X31 | 7953 | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101538890 | OH PRI JPOL REMT ESTR BTKA FSRP RELW FMOB TER2 PRTO | Pole | 2020-12-23 | 2021-02-16 | COMP | 2020-12-23 | [16 empty] | 2019-05-05 | 2020-05-05 | 2020-11-04 | 2020-11-04 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103541101 | 28543.95 | 2697.1 | 1766.8 | 941.3 | 941.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117164562 | POLE_BROK_REPL - 19705 4W/0 DEER VALLEY | 35215322 |  |  | STS-POLE_BROK_REPL - 19705 4W/0 DEER VAL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 40.1985 | -122.3075 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | X31 | 770129 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101538888 | RELW OH ESTR PRI JPOL REMT BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103541101 | 1 | 488.3 | 488.3 | 488.3 | 488.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117164563 | POLE_BROK_REPL - 19705 1N/O 7W/O DEER VA | 35202493 |  |  | STS-POLE_BROK_REPL - 19705 1N/O 7W/O DEE | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.1986 | -122.3079 |  | TIER 2 | 375 | 10354-1101, RED BLUFF | X31 | 770129 | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101538896 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-09 | 2021-02-03 | COMP | 2020-12-09 |  |  | 2021-01-29 | 2021-01-29 | [12 empty] | 2019-05-05 | 2020-05-05 | 2020-11-04 | 2020-11-04 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103541101 | 9528.82 | 2356.8 | 1529.8 | 611.6 | 611.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117176240 | POLE_BROK_REPL - 8W/O RIDGE RD RED BANK | 35178410 |  |  | STS-POLE_BROK_REPL - 8W/O RIDGE RD RED B | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.1122 | -122.4521 |  | TIER 2 | 440 | 10357-1105, TYLER | Z28 | 2151 | Y | 311 |  |  | 2021-04-19 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 31.9 | 31.9 |  |  | 0 | 31.9 | 31.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101553737 | PRI OH RELW JPOL REMT TER2 NOAC ESTR FMOB PRTO FSRP | Pole | 2020-06-11 | 2020-06-11 | COMP | 2020-06-11 | [16 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-06-16 | Chico |  | 103571105 | 7133.54 | 1002.8 | 1002.8 | 1010.1 | 1010.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117193916 | POLE_BROK_REPL - 16575 JULIE LNRED BLUFF | 35215570 |  |  | STS-POLE_BROK_REPL - 16575 JULIE LNRED B | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.2619 | -122.2406 |  | TIER 2 | 595 | 10354-1104, RED BLUFF | V33 | 850055 | Y | 311 |  |  | 2021-05-10 07:00 | 2021-05-14 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101526433 | RELW OH PRI INSP JPOL REMT FIRE NOAC SPCR ESTR REAR USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-09 | 2020-05-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103541104 | 1 | 129.6 | 129.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117223472 | POLE_BROK_REPL - 4N/O POLE 1727 GALLATIN | 35154761 |  |  | STS-POLE_BROK_REPL - 4N/O POLE 1727 GALL | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.0861 | -122.3969 |  | TIER 2 | 440 | 10357-1105, TYLER | Z29 | 1727 | Y | 311 |  |  | 2021-03-18 07:00 | 2021-03-18 16:00 | Scheduled | CLICK | [6 empty] | 31.8 | 31.8 |  |  | 0 | 31.8 | 31.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101554318 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-08-19 | 2020-08-19 | COMP | 2020-08-19 | [16 empty] | 2019-05-13 | 2020-05-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103571105 | 6885.43 | 1093.6 | 867.4 | 873.7 | 873.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | RED BLUFF | Red Bluff |  |  | OPEN | 117260117 | POLE_BROK_REPL - AT 18500 REDBANK RD. RE | 35154077 |  |  | STS-POLE_BROK_REPL - AT 18500 REDBANK RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.1076 | -122.3523 |  | TIER 2 | 440 | 10357-1105, TYLER | Z30 | 1725 | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101554053 | RELW OH SEC JPOL REAR REMT ESTR GO PROG FMOB TER2 PRTO FSRP | Pole | 2020-11-04 | 2020-12-18 | COMP | 2020-11-04 | [16 empty] | 2019-05-17 | 2020-05-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103571105 | 10992.39 | 1898 | 1519 | 1522.8 | 1522.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | Red Bluff | Red Bluff |  |  | OPEN | 119118754 | POLE_BROK_REPL - 7480 RED OAK RD.Red Blu | 35220969 |  |  | STS-POLE_BROK_REPL - 7480 RED OAK RD.RED | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.0158 | -122.4115 |  | TIER 2 | 60 | 10333-1101, CORNING | BB2906 | 85152 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 77.1 | 76 | 1.1 |  | 0 | 77.1 | 76 | 1.1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101523487 | RELW OH PRI INSP ESTR FMOB TER2 | Pole | 2021-01-16 | 2021-01-16 | COMP | 2021-01-16 | [16 empty] | 2020-06-06 | 2021-06-06 |  | 2021-06-06 | B-Tag Addition 06.24.20 |  | Chico |  | 103331101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-06-29
North | NV | Redding | Redding |  |  | OPEN | 119741561 | POLE_DECA_REPL - 424 LAKE BLVD-C.O.RRedd | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-31 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 40.6132 | -122.3847 |  | TIER 2 | 552 | 10352-1103, OREGON TRAIL | N2925 |  | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101476286 | REGW OH PRI JPOL RESD FLAG ESTR BTKA OTHR FMOB TER2 | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2020-09-10 | 2021-09-10 |  | 2021-09-10 | Per DOT Approved Request 50356 |  | UNASSIGNED |  | 103521103 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | NV | REDDING | Redding |  |  | OPEN | 116687155 | POLE_BROK_REPL - 7893 EASTSIDE RD REDDIN | 35080071 |  |  | STS-POLE_BROK_REPL - 7893 EASTSIDE RDRED | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.5016 | -122.3752 |  | TIER 2 | 354 | 10340-1101, GIRVAN | Q3011 | 1873 | Y | 311 |  |  | 2021-03-12 07:00 | 2021-03-12 16:00 | Dispatched | CLICK | [6 empty] | 40.1 | 40.1 |  |  | 0 | 40.1 | 40.1 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101503099 | RELW OH PRI JPOL FMOB REMT ESTR BTKA PROG TER2 PRTO FSRP | Pole | 2020-09-03 | 2020-09-04 | COMP | 2020-06-26 |  |  | 2020-07-31 | 2020-08-21 | [12 empty] | 2019-03-08 | 2019-09-08 | 2020-08-19 | 2020-08-19 | Per DOT Approved Request ID# 855 from [REDACTED] |  | Chico |  | 103401101 | 16535.78 | 5659.7 | 882.1 | [5 empty] | FRMMA/WMPMA - Electric | Y | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-22
North | NV | REDDING | Redding |  |  | OPEN | 116751652 | POLE_BROK_REPL - 1W/O 1N/O 11603 DESCHUT | 35145239 |  |  | STS-POLE_BROK_REPL - 1W/O 1N/O 11603 DES | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6258 | -122.2348 |  | TIER 2 | 226 | 10335-1104, DESCHUTES | N3318 | 3657 | Y | 311 |  |  | 2021-02-27 07:00 | 2021-02-27 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101459171 | RELW OH PRI JPOL FIRE NOAC ESTR REAR FMOB FSRP TER2 PRTO | Pole | 2020-03-19 | 2020-06-10 | COMP | 2020-03-19 |  |  | 2020-01-02 | 2020-01-02 | [12 empty] | 2019-03-17 | 2020-03-17 | 2020-10-30 | 2020-10-30 | B-tag addition 8/4/2020 | 2020-03-05 | QUES |  | 103351104 | 26428.75 | 3269.4 | 3225.1 |  |  | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-08-04
North | NV | REDDING | Redding |  |  | COMP | 116970808 | POLE_DECA_REPL - SWITCH POLE 1943 OLD OA | 35219548 |  |  | STS-POLE_DECA_REPL - SWITCH POLE 1943 OL | CONS | CONS SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-02-01 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6389 | -122.3673 |  | TIER 2 | 693 | 10352-1102, OREGON TRAIL | N3007 | 2957 | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 30.1 | 30.1 |  |  | 66.5 | 10 | 10 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101476723 | RELW OH PRI COMP JPOL REMT ESTR GO BTKA CPGG FMOB TER2 PRTO FSRP | Pole | 2021-01-08 | 2021-01-13 | COMP | 2021-01-06 | [15 empty] | 2021-02-19 | 2021-02-17 | 2020-04-06 | 2021-03-01 | 2021-03-01 | B tag clean up 12/3/2020 |  | Chico |  | 103521102 | 13737.71 | 8942.4 | 8579.2 | 1113 | 1113 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-12-03
North | NV | REDDING | Redding |  |  | OPEN | 116692087 | POLE_BROK_REPL - 2W/O 1E/O C/O DRIFTWOOD | 35202096 |  |  | STS-POLE_BROK_REPL - 2W/O 1E/O C/O DRIFT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6988 | -122.2684 |  | TIER 2 | 641 | 10356-1102, STILLWATER | L3224 | 6141 | Y | 311 |  |  | 2021-04-05 07:00 | 2021-04-09 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101475173 | RELW OH PRI REMT ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2020-12-14 | 2021-02-04 | COMP | 2020-12-14 | [16 empty] | 2019-03-09 | 2020-03-09 |  | 2020-03-09 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103561102 | 16150.49 | 1242.3 | 699.3 | -362 | -362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | REDDING | Redding |  |  | OPEN | 116722017 | POLE_BROK_REPL - R/O 13721 KITTY HAWK LN | 35202099 |  |  | STS-POLE_BROK_REPL - R/O 13721 KITTY HAW | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.6876 | -122.2972 |  | TIER 2 | 641 | 10356-1102, STILLWATER | M3110 | 6695 | Y | 311 |  |  | 2021-04-05 07:00 | 2021-04-09 16:00 | Reserved | CLICK | [6 empty] | 68 | 68 |  |  | 0 | 68 | 68 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101479020 | RELW OH PRI CLR JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-22 |  | COMP | 2021-01-22 | [16 empty] | 2019-03-13 | 2020-03-13 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103561102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | REDDING | Redding |  |  | OPEN | 116723987 | POLE_DECA_REPL - 2NW/O 1E/O 21931 HIDDEN | 35137512 |  |  | STS-POLE_DECA_REPL - 2NW/O 1E/O 21931 HI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6304 | -122.2432 |  | TIER 2 | 552 | 10352-1103, OREGON TRAIL | N3312 | 6557 | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Dispatched | CLICK | [6 empty] | 31 | 31 |  |  | 0 | 31 | 31 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101459988 | RELW OH PRI FIRE ESTR BTKA FMOB TER2 PRTO | Pole | 2020-02-05 | 2021-02-16 | COMP | 2020-02-05 |  |  | 2020-01-02 | 2020-01-02 | [12 empty] | 2019-03-13 | 2019-11-10 |  | 2019-11-10 | Program Manager | 2020-01-29 | ENENG |  | 103521103 | 11141.27 | 5609 | 64.8 |  |  | 2684.3 |  | 2684.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
North | NV | REDDING | Redding |  |  | OPEN | 116724384 | POLE_BROK_REPL - R/O 19200 FELLOWSHIP WA | 35154087 |  |  | STS-POLE_BROK_REPL - R/O 19200 FELLOWSHI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6855 | -122.3463 |  | TIER 2 | 317 | 10356-1101, STILLWATER | M3010 | 2557 | Y | 311 |  |  | 2021-03-29 07:00 | 2021-04-02 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101462543 | RELW OH PRI JPOL REMT ESTR BTKA OTRG FMOB TER2 PRTO FSRP | Pole | 2020-09-08 | 2020-10-28 | COMP | 2020-09-08 | [16 empty] | 2019-03-13 | 2020-03-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103561101 | 22784.25 | 2812.7 | 1216.8 |  |  | 276.9 |  | 276.9 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | REDDING | Redding |  |  | OPEN | 116725309 | POLE_DECA_REPL - 1SW/O 13981 PRADO LN RE | 35202127 |  |  | STS-POLE_DECA_REPL - 1SW/O 13981 PRADO L | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 40.6946 | -122.3102 |  | TIER 2 | 317 | 10356-1101, STILLWATER | M3104 | 4697 | Y | 311 |  |  | 2021-04-05 07:00 | 2021-04-09 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 31.1 | 31.1 |  |  | 0 | 31.1 | 31.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101478359 | RELW OH PRI CLR JPOL REMT ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2020-12-14 | 2021-02-01 | COMP | 2020-12-14 | [16 empty] | 2019-03-13 | 2020-02-20 | 2020-10-10 | 2020-10-10 | 2021 CBP Plan | 2021-01-31 | QUES |  | 103561101 | 24265.22 | 1578 | 1061.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | REDDING | Redding |  |  | OPEN | 116734735 | POLE_DECA_REPL - 20198 CASA DR. REDDING | 35154095 |  |  | STS-POLE_DECA_REPL - 20198 CASA DR. REDD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6917 | -122.3093 |  | TIER 2 | 317 | 10356-1101, STILLWATER | M3104 | 4697 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 33.8 | 33.8 |  |  | 0 | 33.8 | 33.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101478855 | PRI OH RELW CLR JPOL REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2020-09-24 | 2020-11-22 | COMP | 2020-09-24 |  |  | 2020-09-11 | 2020-09-11 | [12 empty] | 2019-03-14 | 2019-10-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103561101 | 8144.79 | 1578.8 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | REDDING | Redding |  |  | OPEN | 116735168 | POLE_DECA_REPL - #1N 19295 UNION SCHOOL | 35154103 |  |  | STS-POLE_DECA_REPL - #1N 19295 UNION SCH | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.6854 | -122.3439 |  | TIER 2 | 317 | 10356-1101, STILLWATER | M3010 | 4697 | Y | 311 |  |  | 2021-03-29 07:00 | 2021-04-02 16:00 | Reserved | CLICK | [6 empty] | 55.3 | 55.3 |  |  | 0 | 55.3 | 55.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101462485 | RELW OH PRI JPOL PUBL FLAG ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2021-02-01 |  | COMP | 2021-02-01 |  |  | 2021-01-28 | 2021-01-28 | [12 empty] | 2019-03-14 | 2020-03-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103561101 | 16453.02 | 2079.2 |  |  |  | 166.8 |  | 166.8 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | REDDING | Redding |  |  | OPEN | 116793487 | POLE_DECA_REPL - 14737 MARIN DR. REDDING | 35215228 |  |  | STS-POLE_DECA_REPL - 14737 MARIN DR. RED | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.7164 | -122.2337 |  | TIER 2 | 641 | 10356-1102, STILLWATER | L3313 | 6667 | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-21 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101474685 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2019-09-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103561102 | 1 | 234.1 | 234.1 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | NV | REDDING | Redding |  |  | OPEN | 116823236 | POLE_LEAN_REPL - 2W\O 1S\O 12450 MARIA D | 35214728 |  |  | STS-POLE_LEAN_REPL - 2W\O 1S\O 12450 MAR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.65 | -122.3123 |  | TIER 2 | 693 | 10352-1102, OREGON TRAIL | N3104 | 7003 | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-21 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Leaning | Replace |  | 101467148 | RELW REMT OH PRI JPOL ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103521102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | REDDING | Redding |  |  | OPEN | 116862431 | POLE_DECA_REPL - 21150 ALPHA 1 PE 1 PN R | 35215200 |  |  | STS-POLE_DECA_REPL - 21150 ALPHA 1 PE 1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.644 | -122.3003 |  | TIER 2 | 552 | 10352-1103, OREGON TRAIL | N3110 | 4843 | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-21 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101467257 | RELW OH PRI JPOL REMT ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103521103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | REDDING | Redding |  |  | OPEN | 116862520 | POLE_DECA_REPL - 1E/O 17690 COWGILL LN R | 35137585 |  |  | STS-POLE_DECA_REPL - 1E/O 17690 COWGILL | CONS | CONS ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6375 | -122.4033 |  | TIER 2 | 552 | 10352-1103, OREGON TRAIL | N2908 | 2361 | Y | 311 |  |  | 2021-04-12 07:00 | 2021-04-16 16:00 | Reserved | CLICK | [6 empty] | 54.4 | 54.4 |  |  | 0 | 54.4 | 54.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101475713 | PRI RELW OH JPOL FIRE NOAC ESTR GO FMOB TER2 PRTO FSRP | Pole | 2020-04-27 | 2020-07-23 | COMP | 2020-04-27 |  |  | 2020-01-02 | 2020-01-03 | [12 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | Program Manager | 2020-01-29 | ENENG |  | 103521103 | 20963.21 | 4298.1 |  |  |  | 489.1 |  | 489.1 |  | Y | MPP File Only | N |  | Y | 2020-02-20
North | NV | REDDING | Redding |  |  | OPEN | 116863625 | POLE_DECA_REPL - 12425 ALPHA LN. REDDING | 35215242 |  |  | STS-POLE_DECA_REPL - 12425 ALPHA LN. RED | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.6477 | -122.2979 |  | TIER 2 | 552 | 10352-1103, OREGON TRAIL | N3105 | 4843 | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-21 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101467237 | RELW OH PRI JPOL REMT SWRK ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-28 | 2020-03-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103521103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | REDDING | Redding |  |  | OPEN | 116864462 | POLE_BROK_REPL - C/O EVANS VIEW LN / CO | 35137685 |  |  | STS-POLE_BROK_REPL - C/O EVANS VIEW LN | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6371 | -122.4053 |  | TIER 2 | 552 | 10352-1103, OREGON TRAIL | N2907 | 11127 | Y | 311 |  |  | 2021-04-12 07:00 | 2021-04-16 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 58.3 | 58.3 |  |  | 0 | 58.3 | 58.3 |  |  | EC | F | Pole | Broken/Damaged | Replace |  | 101475728 | RELW OH SERV JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-10-12 | 2020-10-13 | COMP | 2020-08-03 |  |  | 2020-01-02 | 2020-01-03 | [12 empty] | 2019-03-28 | 2020-03-28 | 2022-04-19 | 2022-04-19 | Program Manager | 2020-09-30 | ENENG |  | 103521103 | 12074.75 | 647.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-20
North | NV | REDDING | Redding |  |  | OPEN | 116865208 | POLE_DECA_REPL - F/O 20462 SUNNYCREST LN | 35202554 |  |  | STS-POLE_DECA_REPL - F/O 20462 SUNNYCRES | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 40.6441 | -122.2982 |  | TIER 2 | 552 | 10352-1103, OREGON TRAIL | N3110 | 4843 | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-21 16:00 | Reserved | CLICK | [6 empty] | 74.6 | 74.6 | 0 |  | 0 | 74.6 | 74.6 | 0 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101467278 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-11 |  | COMP | 2021-02-11 | [16 empty] | 2019-03-29 | 2019-11-05 |  | 2019-11-05 | 2021 CBP Plan | 2021-02-28 | QUES |  | 103521103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | REDDING | Redding |  |  | OPEN | 116950396 | POLE_DECA_REPL - R\O 19698 WINTU WYREDDI | 35214635 |  |  | STS-POLE_DECA_REPL - R\O 19698 WINTU WYR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 40.6369 | -122.3292 |  | TIER 2 | 693 | 10352-1102, OREGON TRAIL | N3107 | 4623 | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-21 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101466391 | OH PRI JPOL REMT ESTR REAR FSRP RELW FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-03 | 2020-04-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103521102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | REDDING | Redding |  |  | OPEN | 116975554 | POLE_DECA_REPL - 18439 OLD OASIS RDREDDI | 35214754 |  |  | STS-POLE_DECA_REPL - 18439 OLD OASIS RDR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 40.6369 | -122.3762 |  | TIER 2 | 693 | 10352-1102, OREGON TRAIL | N3006 | 1943 | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-21 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101476518 | RELW OH PRI JPOL REMT ESTR REAR WATR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-07 | 2020-04-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103521102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | REDDING | Redding |  |  | OPEN | 116978507 | POLE_DECA_REPL - 2N/O F/O 9673 YUKI-YAMA | 35137697 |  |  | STS-POLE_DECA_REPL - 2N/O F/O 9673 YUKI- | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.5704 | -122.2767 |  | TIER 2 | 621 | 10352-1104, OREGON TRAIL | O3223 | 8881 | Y | 311 |  |  | 2021-04-12 07:00 | 2021-04-16 16:00 | Reserved | CLICK | [6 empty] | 31.8 | 31.8 |  |  | 0 | 31.8 | 31.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101469929 | RELW OH PRI REMT FIRE FMOB ESTR BTKA TER2 PRTO FSRP | Pole | 2020-05-22 | 2020-05-26 | COMP | 2020-05-05 |  |  | 2020-01-02 | 2020-01-03 | [12 empty] | 2019-04-08 | 2020-04-08 | 2021-05-31 | 2021-05-31 | Program Manager | 2020-01-29 | ENENG |  | 103521104 | 8738.2 | 883.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-20
North | NV | REDDING | Redding |  |  | OPEN | 116980403 | POLE_DECA_REPL - F/O 18552 CANDY LN REDD | 35214809 |  |  | STS-POLE_DECA_REPL - F/O 18552 CANDY LN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.6379 | -122.3734 |  | TIER 2 | 693 | 10352-1102, OREGON TRAIL | N3006 | 1943 | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-21 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101476523 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-08 | 2020-04-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103521102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | REDDING | Redding |  |  | OPEN | 117005463 | POLE_DECA_REPL - C/O SANDSTONE DR/RED WA | 35170719 |  |  | STS-POLE_DECA_REPL - C/O SANDSTONE DR/RE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6436 | -122.3714 |  | TIER 2 | 693 | 10352-1102, OREGON TRAIL | N3006 | 5391 | Y | 311 |  |  | 2021-04-05 07:00 | 2021-04-09 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101476397 | RELW OH PRI JPOL REMT ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2020-04-28 | 2020-06-19 | COMP | 2020-04-27 | [16 empty] | 2019-04-10 | 2020-04-10 | 2020-09-27 | 2020-09-27 | 2021 CBP Plan |  | UNASSIGNED |  | 103521102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | REDDING | Redding |  |  | OPEN | 117007686 | POLE_DECA_REPL - 12307 SANDSTONE DR REDD | 35214860 |  |  | STS-POLE_DECA_REPL - 12307 SANDSTONE DR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 40.6446 | -122.3714 |  | TIER 2 | 693 | 10352-1102, OREGON TRAIL | N3006 | 5391 | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-21 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101476401 | RELW OH SEC JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-11 | 2020-04-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 103521102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | ROUND MOUNTAIN | Burney |  |  | OPEN | 114903592 | POLE_DECA_REPL - 29230 FENDERS FERRY ROU | 35119287 |  |  | STS-POLE_DECA_REPL - 29230 FENDERS FERRY | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.8222 | -121.961 |  | TIER 2 | 283 | 10332-1101, CEDAR CREEK | J4006 | 1611 | Y | 311 |  |  | 2021-04-12 07:00 | 2021-04-16 16:00 | Reserved | CLICK | [6 empty] | 31.9 | 31.9 |  |  | 0 | 31.9 | 31.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101478622 | RELW OH PRI PATR FIRE JAR PROG SCOP SCPA FMOB TER2 | Pole | 2019-12-10 | 2019-12-10 | COMP | 2019-12-10 |  |  | 2019-09-24 | 2019-09-24 | [12 empty] | 2018-08-18 | 2019-08-18 |  | 2019-08-18 | circuit based plan 2.14 |  | UNASSIGNED |  | 103321101 | 7883.28 | 6733.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | SHINGLETOWN | Redding |  |  | COMP | 116753053 | POLE_BROK_REPL - 29462 INWOOD RD 1W SHIN | 35137659 |  |  | CSTS-POLE_BROK_REPL - 29462 INWOOD RD | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-11-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.5267 | -121.9565 |  | TIER 2 | 62 | 10254-1102, VOLTA | P40 | 7701 | Y | 311 |  |  | 2021-02-08 07:00 | 2021-02-12 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 32.7 | 32.7 |  |  | 15 | 1.7 | 1.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101481511 | RELW OH PRI COMP RESD REMT NOAC ESTR BTKA CPGG FMOB TER2 PRTO | Pole | 2020-03-23 | 2020-03-23 | COMP | 2020-03-23 | COMP | 2021-01-08 | 2020-01-02 | 2020-01-02 | [11 empty] | 2021-01-08 | 2021-01-08 | 2020-03-17 |  | 2020-03-17 | circuit based plan 2.14 | 2020-01-29 | ENENG |  | 102541102 | 18808.21 | 7549.6 | 6515.1 | 6515.1 | 6515.1 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | SHINGLETOWN | Redding |  |  | COMP | 116872622 | POLE_BURN_REPL - 28442 MORAINE WAY 1PW S | 35137689 |  |  | STS-POLE_BURN_REPL - 28442 MORAINE WAY 1 | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-07-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.478 | -121.9963 |  | TIER 2 | 62 | 10254-1102, VOLTA | Q39 | 7605 | Y | 311 |  |  | 2021-01-14 | 2021-01-14 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 32.9 | 32.7 | 0 | 0.2 | 22 | 1.7 | 1.7 |  |  | EC | E | Pole | Burnt | Replace |  | 101484151 | RELW COMP RESD OH PRI JPOL FLAG ESTR BTKA CPGG FMOB TER2 PRTO | Pole | 2020-02-26 | 2020-02-26 | COMP | 2020-02-26 | COMP | 2021-01-14 | 2020-01-02 | 2020-01-02 | [11 empty] | 2021-01-15 | 2021-01-14 | 2020-03-30 |  | 2020-03-30 | circuit based plan 2.14 | 2020-01-29 | ENENG |  | 102541102 | 25973.25 | 11333 | 10476.6 | 10476.6 | 10476.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | SHINGLETOWN | Redding |  |  | COMP | 116956928 | POLE_DECA_REPL - R/O 7825 BUNYA WY 6PNE/ | 35137595 |  |  | STS-POLE_DECA_REPL - R/O 7825 BUNYA WY 6 | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-11-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.5137 | -121.784 |  | TIER 2 | 62 | 10254-1102, VOLTA | Q4402 | 93418 | Y | 311 |  |  | 2021-02-08 07:00 | 2021-02-12 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 31.8 | 31.8 |  |  | 22 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101481978 | RELW OH PRI COMP ESTR BTKA CPGG FMOB TER2 PRTO | Pole | 2020-03-24 | 2020-03-24 | COMP | 2020-03-24 | COMP | 2021-01-05 | 2020-01-02 | 2020-01-02 | [11 empty] | 2021-01-07 | 2021-01-05 | 2020-04-04 |  | 2020-04-04 | circuit based plan 2.14 | 2020-01-29 | ENENG |  | 102541102 | 8106.83 | 9608.7 | 8420.3 | 8420.3 | 8420.3 | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | SHINGLETOWN | Redding |  |  | OPEN | 116877475 | POLE_BROK_REPL - #1S 27111 LACK CREEK DR | 35137490 |  |  | STS-POLE_BROK_REPL - #1S 27111 LACK CREE | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.4786 | -122.0364 |  | TIER 2 | 664 | 10335-1101, DESCHUTES | Q38 | 5401 | Y | 311 |  |  | 2021-03-18 07:00 | 2021-03-18 16:00 | Scheduled | CLICK | [6 empty] | 31 | 31 |  |  | 0 | 31 | 31 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101483802 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-02-14 | 2020-03-04 | COMP | 2020-02-14 |  |  | 2020-01-02 | 2020-01-03 | [12 empty] | 2019-03-31 | 2019-12-09 | 2020-10-30 | 2020-10-30 | Program Manager | 2020-01-29 | ENENG |  | 103351101 | 9374.43 | 1073.6 |  |  |  | 83.4 |  | 83.4 |  | Y | MPP File Only | N |  | Y | 2020-02-20
North | NV | WHITMORE | Redding |  |  | COMP | 117102935 | POLE_DECA_REPL - 10W/O 30520 MORELLI RAN | 35154113 |  |  | STS-POLE_DECA_REPL - 10W/O 30520 MORELLI | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.5887 | -121.9249 |  | TIER 2 | 282 | 10360-1101, WHITMORE | O40 | 6699 | Y | 311 |  |  | 2021-01-14 | 2021-01-14 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101480797 | RELW INSP OH PRI COMP REMT FIRE ESTR CCNT FMOB TER2 FSRP | Pole | 2020-04-27 | 2020-04-27 | COMP | 2020-04-27 | COMP | 2021-01-14 | [13 empty] | 2021-01-28 | 2021-01-14 | 2019-10-25 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | QUES |  | 103601101 | 8349.22 | 3910.9 | 2644.2 | 2644.2 | 2644.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | WHITMORE | Redding |  |  | COMP | 117121259 | POLE_DECA_REPL - 1N/O 11879 FERN RD SVC | 35154221 |  |  |  | MAPP | MAPP SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 40.6354 | -121.8871 |  | TIER 2 | 282 | 10360-1101, WHITMORE | N41 | 2217 | Y | 311 |  |  | 2021-01-14 | 2021-01-14 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0 | 1 | 1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101476544 | RELW OH SEC INSP REMT ESTR GO PROG FMOB TER2 FSRP COMP CCNT | Pole | 2020-09-30 | 2020-09-30 | COMP | 2020-09-30 | COMP | 2021-01-14 | 2020-09-24 | 2020-09-24 | [11 empty] | 2021-01-28 | 2021-01-14 | 2020-04-29 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-09-30 | QUES |  | 103601101 | 9012.42 | 1867.8 | 806 | 806 | 806 | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | NV | WHITMORE | Redding |  |  | OPEN | 117128456 | POLE_BROK_REPL - 1W/O 13106 FERN RD EAST | 35179326 |  |  | STS-POLE_BROK_REPL - 1W/O 13106 FERN RD | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6649 | -121.8959 |  | TIER 2 | 282 | 10360-1101, WHITMORE | M41 | 2113 | Y | 311 |  |  | 2021-02-18 07:00 | 2021-02-18 16:00 | Dispatched | CLICK | [6 empty] | 40.1 | 40.1 |  |  | 0 | 40.1 | 40.1 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101476169 | RELW OH PRI INSP CLR REMT NOAC ESTR GO FMOB TER2 | Pole | 2020-06-25 | 2020-06-25 | COMP | 2020-06-25 | [16 empty] | 2019-04-30 | 2019-10-30 | 2020-08-21 | 2020-08-21 | Per DOT Approved Request ID# 851 from [REDACTED] |  | Chico |  | 103601101 | 14743.05 | 4345.2 | 1862.7 | 1862.7 | 1862.7 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-22
North | NV | WHITMORE | Redding |  |  | OPEN | 117111021 | POLE_BROK_REPL - 2E/O 3N/O 10707 HUFORD | 35202240 |  |  | STS-POLE_BROK_REPL - 2E/O 3N/O 10707 HUF | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 40.5996 | -121.9621 |  | TIER 2 | 282 | 10360-1101, WHITMORE | O40 | 1521 | Y | 311 |  |  | 2021-05-17 07:00 | 2021-05-21 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101480893 | RELW OH PRI INSP CLR REMT ESTR FMOB FSRP TER2 | Pole |  |  | REQD | [17 empty] | 2019-04-27 | 2020-04-27 | 2020-11-13 | 2020-11-13 | 2021 CBP Plan | 2021-02-28 | QUES |  | 103601101 | 1 | 532.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | NV | WHITMORE | Redding |  |  | OPEN | 117120893 | POLE_BROK_REPL - 3W/O 4SW/O 12730 FERN R | 35154218 |  |  | STS-POLE_BROK_REPL - 3W/O 4SW/O 12730 FE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 40.6572 | -121.9524 |  | TIER 2 | 282 | 10360-1101, WHITMORE | M40 | 1413 | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Dispatched | CLICK | [6 empty] | 47.6 | 47.6 |  |  | 0 | 47.6 | 47.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101475249 | OH PRI INSP REMT JAR BTKA OTRG FMOB TER2 RELW | Pole | 2021-02-01 | 2021-02-01 | COMP | 2021-02-01 | [16 empty] | 2019-04-29 | 2019-10-29 |  | 2019-10-29 | 2021 CBP Plan | 2020-10-31 | QUES |  | 103601101 | 7836.8 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA |  | Marysville |  |  | OPEN | 118593330 | POLE_OVRL_REPL - 7864 MARYSVILLE RD 3PE | 35178939 |  |  | STS-POLE_OVRL_REPL -7864 MARYSVILLE RD 3 | UNSC | UNSC | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 39.3617 | -121.316 |  | TIER 2 | 115 | 10319-1101, BANGOR | J2925 | 7446 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.7 | 17.7 |  |  | 0 | 17.7 | 17.7 |  |  | EC | E | Pole | Overloaded | Replace |  | 101288252 | RELW TER2 | Pole | 2020-11-06 | 2021-02-19 | COMP | 2020-09-18 |  |  | 2021-02-19 | 2021-02-19 | [12 empty] | 2020-02-28 | 2020-12-31 |  | 2020-12-31 | Email from [REDACTED] 3.3.20 | 2020-09-30 | QUES |  | 103191101 | 11835.79 | 1804.4 | 1216.8 | [5 empty] | Electric Distribution | N | MPP File Only | N |  | Y | 2020-03-09
North | SA | BROWNS VALLEY | Marysville |  |  | OPEN | 116803204 | POLE_BROK_REPL - WSIP BROWNS VALLEY | 35200475 |  |  | STS-POLE_BROK_REPL - WSIP BROWNS VALLEY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro JointPole |  |  | 39.2511 | -121.3388 |  | TIER 2 | 743 | 15313-2101, NARROWS | M2912 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103686241 | RELW OH PRI JPOL ESTR RESD REMT BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-03-28 | 2021-03-28 | 2021 CBP Plan | 2021-03-31 | QUES |  | 153132101 | 1 | 1240.2 | 1240.2 | 140.2 | 140.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | BROWNS VALLEY | Marysville |  |  | OPEN | 116806117 | POLE_BROK_REPL - WSIP BROWNS VALLEY | 35200471 |  |  | STS-POLE_BROK_REPL - WSIP BROWNS VALLEY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 39.2457 | -121.3351 |  | TIER 2 | 743 | 15313-2101, NARROWS | M2913 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103682204 | RELW OH PRI JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-03-29 | 2021-03-29 | 2021 CBP Plan | 2021-03-31 | QUES |  | 153132101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | BROWNS VALLEY | Marysville |  |  | OPEN | 116808769 | POLE_BROK_REPL - WSIP BROWNS VALLEY | 35200473 |  |  | STS-POLE_BROK_REPL - WSIP BROWNS VALLEY | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.2479 | -121.3339 |  | TIER 2 | 743 | 15313-2101, NARROWS | M2913 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 23.5 | 23.5 |  |  | 0 | 23.5 | 23.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103682410 | RELW OH PRI JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-03 |  | COMP | 2021-02-03 | [16 empty] | 2019-03-21 | 2020-03-21 | 2021-03-29 | 2021-03-29 | 2021 CBP Plan | 2021-03-31 | QUES |  | 153132101 | 11466.06 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | BROWNS VALLEY | Marysville |  |  | OPEN | 116813335 | POLE_BROK_REPL - 11PW/O 7558 FORBES RD B | 35204638 |  |  | STS-POLE_BROK_REPL - 11PW/O 7558 FORBES | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.2513 | -121.3447 |  | TIER 2 | 743 | 15313-2101, NARROWS | M2912 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101287391 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-04-11 | 2021-04-11 | 2021 CBP Plan | 2021-03-31 | QUES |  | 153132101 | 1 | 378.5 | 378.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | BROWNS VALLEY | Marysville |  |  | OPEN | 116813637 | POLE_BROK_REPL - 15PW/O 7558 FORBES RD B | 35200356 |  |  | STS-POLE_BROK_REPL - 15PW/O 7558 FORBES | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.2512 | -121.3481 |  | TIER 2 | 743 | 15313-2101, NARROWS | M2911 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101333683 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-04-11 | 2021-04-11 | 2021 CBP Plan | 2021-03-31 | QUES |  | 153132101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | BROWNS VALLEY | Marysville |  |  | OPEN | 116825218 | POLE_BROK_REPL - WSIPBROWNS VALLEY95918 | 35200469 |  |  | STS-POLE_BROK_REPL - WSIPBROWNS VALLEY95 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.2568 | -121.3514 |  | TIER 2 | 743 | 15313-2101, NARROWS | M2906 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103672162 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-25 | 2020-03-25 | 2021-03-27 | 2021-03-27 | 2021 CBP Plan | 2021-03-31 | QUES |  | 153132101 | 1 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | BROWNS VALLEY | Marysville |  |  | OPEN | 116842009 | POLE_DECA_REPL - 6463 OFF BALD MTN.RD. B | 35202503 |  |  | STS-POLE_DECA_REPL - 6463 OFF BALD MTN.R | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.2655 | -121.3729 |  | TIER 2 | 644 | 15292-1101, BROWNS VALLEY | M2803 | 1861 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101329687 | RELW OH PRI CREW JPOL RESD REMT ESTR BTKA RTRN FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | VPI |  | 152921101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | BROWNS VALLEY | Marysville |  |  | OPEN | 116851970 | POLE_DECA_REPL - 9191 BYRON WY.BROWNS VA | 35200468 |  |  | STS-POLE_DECA_REPL - 9191 BYRON WY.BROWN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 39.2275 | -121.3688 |  | TIER 2 | 743 | 15313-2101, NARROWS | N2804 | 17405 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103029406 | RELW JPOL OH PRI CLR RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-04-04 | 2021-04-04 | 2021 CBP Plan | 2021-03-31 | QUES |  | 153132101 | 1 | 316.7 | 316.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | BROWNS VALLEY | Marysville |  |  | OPEN | 116865168 | POLE_BROK_REPL - 1PNW/O 6995 STEPHAN TRA | 35202552 |  |  | STS-POLE_BROK_REPL - 1PNW/O 6995 STEPHAN | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.2332 | -121.3532 |  | TIER 2 | 743 | 15313-2101, NARROWS | M2921 | 18485 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101288213 | RELW OH PRI JPOL REMT ESTR BTKA PRTO USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-01-31 | VPI |  | 153132101 | 1 | 151.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | BROWNS VALLEY | Marysville |  |  | OPEN | 117005012 | POLE_BROK_REPL - 8032 MARYSVILLE RD OR 1 | 35160215 |  |  | STS-POLE_BROK_REPL - 8032 MARYSVILLE RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3617 | -121.3117 |  | TIER 2 | 115 | 10319-1101, BANGOR | J3021 | 7446 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.1 | 20.1 |  |  | 0 | 20.1 | 20.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101288258 | OH PRI INSP JPOL REMT TRAF FLAG ESTR BTKA FMOB TER2 RELW | Pole | 2021-01-13 | 2021-02-17 | COMP | 2020-06-19 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 103191101 | 21965.26 | 871.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | BROWNS VALLEY | Marysville |  |  | OPEN | 117338293 | POLE_BROK_REPL - 7304 FRONTIER PL/1PW BR | 35204639 |  |  | STS-POLE_BROK_REPL - 7304 FRONTIER PL/1P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.2403 | -121.3413 |  | TIER 2 | 743 | 15313-2101, NARROWS | M2917 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101288169 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-29 | 2020-05-29 | 2021-04-09 | 2021-04-09 | 2021 CBP Plan | 2021-03-31 | QUES |  | 153132101 | 1 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | BROWNS VALLEY | Marysville |  |  | COMP | 117186948 | POLE_DECA_REPL - #15N/O SMARTSVILLE SUB | 35175453 |  |  | B3 STS-POLE_DECA_REP-#15N/O SMARTSVILLE | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-06-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.2225 | -121.3033 |  | TIER 2 | 743 | 15313-2101, NARROWS | N03 |  | Y | 311 |  |  | 2021-01-16 | 2021-01-16 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 83 | 83 |  |  | 0 | 83 | 83 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101339816 | RELW OH PRI COMP JPOL REMT NOAC ESTR GO CCNT PROG FMOB TER2 PRTO FSRP | Pole | 2020-11-18 | 2020-11-19 | COMP | 2020-11-10 | COMP | 2021-01-16 | [13 empty] | 2021-01-28 | 2021-01-16 | 2020-05-08 | 2020-07-28 | 2020-07-28 | B-Tag Clean Up 5/14/20 |  | W. Sac |  | 153132101 | 22592.19 | 21849.7 | 19818.2 | 19038 | 19038 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-05-25
North | SA | BROWNS VALLEY | Marysville |  |  | OPEN | 116986249 | POLE_DECA_REPL - SE C/O WILLOW GLEN RD/M | 35160213 |  |  | STS-POLE_DECA_REPL - SE C/O WILLOW GLEN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3626 | -121.3229 |  | TIER 2 | 115 | 10319-1101, BANGOR | J2924 | 7446 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 65.9 | 65.9 |  |  | 0 | 65.9 | 65.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101334274 | RELW OH PRI INSP CLR JPOL REMT FIRE TRAF FLAG ESTR BTKA USA TER2 FMOB | Pole | 2020-06-19 | 2021-01-08 | COMP | 2020-06-19 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 103191101 | 37143.64 | 335.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | BROWNS VALLEY | Marysville |  |  | OPEN | 117023634 | POLE_BROK_REPL - 7864 MARYSVILLE RD/4PE | 35109265 |  |  | STS-POLE_BROK_REPL - 7864 MARYSVILLE RD/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3617 | -121.3147 |  | TIER 2 | 115 | 10319-1101, BANGOR | J2925 | 7446 | Y | 311 |  |  | 2021-04-01 07:00 | 2021-04-01 16:00 | Scheduled | CLICK | [6 empty] | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101288253 | RELW OH PRI INSP JPOL REMT NOAC ESTR FMOB TER2 | Pole | 2020-06-24 | 2020-08-24 | COMP | 2020-06-24 |  |  | 2019-06-04 | 2019-06-04 | [12 empty] | 2019-04-13 | 2019-10-13 |  | 2019-10-13 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 103191101 | 28266.98 | 2695.4 | 1694.4 | 1164.4 | 1164.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | BROWNS VALLEY | Marysville |  |  | COMP | 120070456 | POLE_DECA_REPL - 1P SO PO BOX 300 OREGON | 35218042 |  |  | STS-POLE_DECA_REPL - 1P SO PO BOX 300 OR | MAPP | MAPP ERDY SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-21 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.3371 | -121.3269 |  | TIER 2 | 115 | 10319-1101, BANGOR | K29 | 391907 | Y | 311 |  |  | 2021-03-30 08:00 | 2021-03-30 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 48 | 48 |  |  | 37.5 | 24 | 24 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101324630 | RELW OH PRI COMP JPOL PUBL FIRE SWRK ESTR BTKA USA CTMN CPGE FMOB TER2 | Pole | 2020-12-02 | 2020-12-08 | COMP | 2020-12-01 | COMP | 2021-02-16 | [13 empty] | 2021-02-17 | 2021-02-16 | 2021-02-18 |  | 2021-02-18 | B tag clean up 12/2/2020 |  | UNASSIGNED |  | 103191101 | 6464.24 | 4363.3 | 4242.2 | 1393.4 | 1393.4 |  |  |  | Electric Distribution | N | Pulled from MPP Import File | N |  | Y | 2020-12-02
North | SA | BROWNS VALLEY | Marysville |  |  | OPEN | 116976264 | POLE_DECA_REPL - 9204 WESTWOOD TRL. BROW | 35216855 |  |  | STS-POLE_DECA_REPL - 9204 WESTWOOD TRL. | ADER | ADER ERDY | Poles | MPP | Not Funded as 2020 Wildfire OII | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 39.3214 | -121.271 |  | TIER 2 | 177 | 15374-1101, DOBBINS | K3121 | 9671 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101301982 | OH PRI CLR JPOL RESD FIRE BTKA FMOB TER2 PRTO RELW | Pole |  |  | REQD | [17 empty] | 2019-04-07 | 2020-04-07 | 2021-02-05 | 2021-02-05 | work plan year cleanup 01/21/2021 |  | W. Sac |  | 153741101 | [9 empty] | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-21
North | SA | DOBBINS | Marysville |  |  | OPEN | 117031335 | POLE_BROK_REPL - 10486 TEXAS HILL ROAD D | 35144195 |  |  | STS-POLE_BROK_REPL - 10486 TEXAS HILL RO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.3631 | -121.2195 |  | TIER 2 | 177 | 15374-1101, DOBBINS | J3222 | 18449 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101286194 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | Per DOT Approved Request 45773 | 2020-06-30 | W. Sac |  | 153741101 | [9 empty] | Y | MPP File Only | N |  | Y | 2021-02-06
North | SA | DOBBINS | Marysville |  |  | OPEN | 117294260 | POLE_BURN_REPL - A/F 15313 INDAINA SCH. | 35144274 |  |  | STS-POLE_BURN_REPL - A/F 15313 INDAINA S | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 39.3987 | -121.2273 |  | TIER 2 | 177 | 15374-1101, DOBBINS | J3201 | 16019 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.6 | 29.6 |  |  | 0 | 29.6 | 29.6 |  |  | EC | E | Pole | Burnt | Replace |  | 101287945 | RELW OH PRI INSP CLR JPOL REMT FIRE TRAF ESTR BTKA USA FMOB TER2 | Pole | 2021-01-08 | 2021-01-08 | COMP | 2020-06-25 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-05-21 | 2020-05-21 |  | 2020-05-21 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153741101 | 14693.06 | 168.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | DOBBINS | Marysville |  |  | OPEN | 117084989 | POLE_BROK_REPL - 4P/N/O 9011 MARYSVILLE | 35171117 |  |  | STS-POLE_BROK_REPL - 4P/N/O 9011 MARYSVI | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3631 | -121.2616 |  | TIER 2 | 115 | 10319-1101, BANGOR | J3122 |  | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 67.3 | 67.3 |  |  | 0 | 67.3 | 67.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101286906 | RELW OH PRI JPOL REMT ESTR GO BTKA USA SCOP SCPA FMOB TER2 PRTO | Pole | 2021-01-07 | 2021-01-07 | COMP | 2021-01-07 | [16 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 103191101 | 8311.72 | 835.6 | 666.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | DOBBINS | Marysville |  |  | OPEN | 117312967 | POLE_BROK_REPL - F/O 13971 GRINDROCK WY. | 35144277 |  |  | STS-POLE_BROK_REPL - F/O 13971 GRINDROCK | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3665 | -121.2198 |  | TIER 2 | 177 | 15374-1101, DOBBINS | J3222 | 9817 | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 37.1 | 37.1 |  |  | 1 | 37 | 37 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101286205 | RELW OH PRI JPOL ESTR RESD REMT GO BTKA PROG FMOB TER2 PRTO | Pole | 2020-10-26 | 2020-12-17 | COMP | 2020-10-25 | [16 empty] | 2019-05-23 | 2020-05-23 |  | 2020-05-23 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153741101 | 15307.98 | 2830 | 2642.3 | 2625 | 2625 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | DUNNIGAN | Woodland |  |  | OPEN | 116881076 | POLE_DECA_REPL - 20W/O 8S/O 23945 BALD M | 35144187 |  |  | STS-POLE_DECA_REPL - 20W/O 8S/O 23945 BA | POST | POST ERDY IDOC IDCR | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Out of PEND |  |  | 38.7932 | -122.0857 |  | TIER 2 | 119 | 06317-2101, MADISON | G09 | 13372 | Y | 311 |  |  |  |  | Completed | Order Operation | [6 empty] | 50.1 | 50.1 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101660001 | RELW OH PRI INSP REMT ESTR BTKA USA FMOB TER2 | Pole |  |  | REQD |  | COMP | 2020-11-20 | [14 empty] | 2019-04-01 | 2020-04-01 |  | 2020-04-01 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 063172101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | DUNNIGAN | Woodland |  |  | COMP | 116882301 | POLE_DECA_REPL - 24W/O 8S/O 23945 BALD M | 35205610 |  |  | STS-POLE_DECA_REPL - 24W/O 8S/O 23945 BA | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7948 | -122.0904 |  | TIER 2 | 119 | 06317-2101, MADISON | G09 | 13372 | Y | 311 |  |  | 2021-02-14 07:00 | 2021-02-14 16:00 | Dispatched | CLICK | [6 empty] | 42.8 | 42.8 |  |  | 0.5 | 42.3 | 42.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101590900 | RELW OH PRI INSP COMP REMT GO BTKA CCNT FMOB TER2 SCPA SCOP | Pole | 2020-10-25 | 2020-10-25 | COMP | 2020-10-25 | COMP | 2021-02-14 | [13 empty] | 2021-02-22 | 2021-02-14 | 2019-10-01 |  | 2019-10-01 | Q1 Work Plan File |  | UNASSIGNED |  | 063172101 | 10187.69 | 1693.4 | 1693.3 | 111.2 | 111.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-07
North | SA | FAIRFIELD | Vacaville |  |  | OPEN | 117027399 | POLE_BROK_REPL - 6S/O SW C/O LAGOON VALL | 35160300 |  |  | STS-POLE_BROK_REPL - 6S/O SW C/O LAGOON | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.3217 | -122.0246 |  | TIER 2 | 212 | 06360-1104, VACAVILLE | R11 | 2811 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101663436 | RELW OH PRI JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 063601104 | 1 | 755.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | FAIRFIELD | Vacaville |  |  | OPEN | 117070294 | POLE_BROK_REPL - 2E/O 4500 GREEN VALLEY | 35200465 |  |  | STS-POLE_BROK_REPL - 2E/O 4500 GREEN VAL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.2624 | -122.1626 |  | TIER 2 | 341 | 06380-1102, JAMESON | S0816 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101659112 | RELW OH PRI JPOL ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 063801102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | FAIRFIELD | Vacaville |  |  | OPEN | 117070691 | POLE_DECA_REPL - 4406 GREEN VALLEY RD FA | 35200359 |  |  | STS-POLE_DECA_REPL - 4406 GREEN VALLEY R | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2569 | -122.1618 |  | TIER 2 | 341 | 06380-1102, JAMESON | S0816 | 1799 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101559193 | RELW OH PRI JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 063801102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | FAIRFIELD | Vacaville |  |  | OPEN | 117071923 | POLE_DECA_REPL - 4415 GREEN VALLEY RDFAI | 35200420 |  |  | STS-POLE_DECA_REPL - 4415 GREEN VALLEY R | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2581 | -122.1621 |  | TIER 2 | 341 | 06380-1102, JAMESON | S0816 | 1799 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101559213 | RELW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-21 | 2020-04-21 | 2020-09-14 | 2020-09-14 | 2021 CBP Plan | 2021-02-28 | VPI |  | 063801102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | FAIRFIELD | Vacaville |  |  | OPEN | 117115449 | POLE_BROK_REPL - 1/E R/O 2161 JOYCE LN F | 35200467 |  |  | STS-POLE_BROK_REPL - 1/E R/O 2161 JOYCE | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3046 | -122.1314 |  | TIER 2 | 79 | 06380-1105, JAMESON | R08 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101668359 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-28 | 2020-04-28 |  | 2020-04-28 | 2021 CBP Plan | 2021-02-28 | VPI |  | 063801105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | FAIRFIELD | Vacaville |  |  | OPEN | 117183884 | POLE_DECA_REPL - AT HOUSE 4606 OBERTY LN | 35144233 |  |  | STS-POLE_DECA_REPL - AT HOUSE 4606 OBERT | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2669 | -122.1624 |  | TIER 2 | 341 | 06380-1102, JAMESON | S08 | 11633 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101658867 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | VPI |  | 063801102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | FAIRFIELD | Vacaville |  |  | OPEN | 117186580 | POLE_BROK_REPL - 18W R/O 4361 MC GREGOR | 35144237 |  |  | STS-POLE_BROK_REPL - 18W R/O 4361 MC GRE | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2524 | -122.1842 |  | TIER 2 | 502 | 04202-1112, NAPA | S0723 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101558305 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 042021112 | 1 | 687.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | FAIRFIELD | Vacaville |  |  | OPEN | 117347196 | POLE_BROK_REPL - 1420 ROCKVILLE RD FAIRF | 35200464 |  |  | STS-POLE_BROK_REPL - 1420 ROCKVILLE RD F | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.264 | -122.1726 |  | TIER 2 | 341 | 06380-1102, JAMESON | S0719 | 10307 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101655478 | RELW OH PRI JPOL RESD REMT ESTR GO BTKA REAR FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-05-30 | 2020-05-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 063801102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | FAIRFIELD | Vacaville |  |  | OPEN | 117027317 | POLE_BROK_REPL - 5S/O SW C/O LAGOON VALL | 35160219 |  |  | STS-POLE_BROK_REPL - 5S/O SW C/O LAGOON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3224 | -122.0246 |  | TIER 2 | 212 | 06360-1104, VACAVILLE | R11 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 17.5 | 17.5 |  |  | 0 | 17.5 | 17.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101564220 | RELW OH PRI JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-14 | 2021-01-29 | COMP | 2020-10-14 |  |  | 2021-01-25 | 2021-01-29 | [12 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2020-07-31 | W. Sac |  | 063601104 | 12020.69 | 2530.1 | 1379.1 | 5379.1 | 5379.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | FAIRFIELD | Vacaville |  |  | OPEN | 117107086 | POLE_DECA_REPL - OPP/O 2136 TWIN SISTERS | 35150038 |  |  | STS-POLE_DECA_REPL - OPP/O 2136 TWIN SIS | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2978 | -122.1355 |  | TIER 2 | 79 | 06380-1105, JAMESON | R0824 | 3577 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 48.4 | 48.4 |  |  | 0 | 48.4 | 48.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101559892 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-10-23 | 2021-01-30 | COMP | 2020-04-09 |  |  | 2020-10-22 | 2020-10-22 | [12 empty] | 2019-04-26 | 2020-04-26 |  | 2020-04-26 | 2021 CBP Plan | 2020-04-10 | ENENG |  | 063801105 | 25877.47 | 5515.6 | 2266.5 | 5766.5 | 5766.5 | 333.6 |  | 333.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | FAIRFIELD | Vacaville |  |  | OPEN | 117179464 | POLE_BROK_REPL - 1E A/F 1954 ROCKVILLE R | 35172184 |  |  | NR3 STS-POLE_REPL - 1E A/F 1954 ROCKVIL | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-14 | Renew Permit | 38.2516 | -122.1464 |  | TIER 2 | 79 | 06380-1105, JAMESON | S0823 | 4193 | Y | 311 |  |  |  |  | Returned | Order Operation | [6 empty] | 41.2 | 41.2 |  |  | 0 | 41.2 | 41.2 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101559355 | OH PRI RELW FMOB FSRP TER2 PRTO | Pole | 2020-05-18 | 2020-06-18 | COMP | 2020-05-18 |  |  | 2020-05-27 | 2020-06-18 | [12 empty] | 2019-05-07 | 2020-05-07 | 2020-09-18 | 2020-09-18 | B-Tag Clean Up 5/14/20 |  | W. Sac |  | 063801105 | 25931.22 | 9507.3 | 4770.1 | 6035.3 | 6035.3 |  |  |  | FRMMA/WMPMA - Electric | Y | 11/2 in MPP Import File | N | Internal Timeliness – Construction | Y | 2020-05-25
North | SA | LOMA RICA | Marysville |  |  | OPEN | 119600375 | POLE_BROK_REPL - 12126 SCOTT GRANT RD LO | 35192586 |  |  | B3STS-POLE_BROK_REPL-12126 SCOTT GRANT R | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3133 | -121.373 |  | TIER 2 | 115 | 10319-1101, BANGOR | L2803 | 16993 | Y | 311 |  |  | 2021-02-21 07:00 | 2021-02-21 16:00 | Dispatched | CLICK | [6 empty] | 42.8 | 42.8 |  |  | 0 | 42.8 | 42.8 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 103029731 | RELW OH PRI TMAN CLR ESTR BTKA TER2 | Pole | 2020-12-07 | 2020-12-11 | COMP | 2020-12-07 | [16 empty] | 2020-08-11 | 2020-11-11 |  | 2020-11-11 | B-tag addition 8/12/2020 |  | W. Sac |  | 103191101 | 12700.38 | 1956.6 | 1835.5 | 1164.4 | 1164.4 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Tag in Closure Status | Y | 2020-08-18
North | SA | MARYSVILLE | Marysville |  |  | OPEN | 116968285 | POLE_BROK_REPL - 12760 LONE TREE WY | 35217606 |  |  | NR12 B3-POLE_BROK_REPL-12760 LONE TREE W | UNSC | UNSC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3307 | -121.3947 |  | TIER 2 | 115 | 10319-1101, BANGOR | K2720 | 693385 | Y | 311 |  |  | 2021-04-15 07:00 | 2021-04-15 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 53.7 | 53.7 |  |  | 0 | 53.7 | 53.7 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101293178 | OH PRI CLR JPOL RESD BTKA USA FMOB TER2 PRTO RELW | Pole | 2020-12-24 | 2020-12-29 | COMP | 2020-12-24 | [16 empty] | 2019-04-05 | 2020-04-05 | 2020-09-30 | 2020-09-30 | B tag clean up 11/24/2020 |  | W. Sac |  | 103191101 | [9 empty] | N | Not Assigned 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-11-24
North | SA | MARYSVILLE | Marysville |  |  | OPEN | 116971518 | POLE_BROK_REPL - 6P E\O 12180 KIMBERLY W | 35143931 |  |  | STS-POLE_BROK_REPL - 6P E\O 12180 KIMBER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 39.3123 | -121.3892 |  | TIER 2 | 115 | 10319-1101, BANGOR | L2801 |  | Y | 311 |  |  | 2021-03-10 07:00 | 2021-03-10 16:00 | Scheduled | CLICK | [6 empty] | 20 | 20 |  |  | 0 | 20 | 20 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101287469 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-06-25 | 2020-08-18 | COMP | 2020-06-25 |  |  | 2020-06-10 | 2020-06-10 | [12 empty] | 2019-04-06 | 2020-04-06 |  | 2020-04-06 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 103191101 | 11930.84 | 1409.1 | 1216.1 | 873.7 | 873.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | MARYSVILLE | Marysville |  |  | OPEN | 116974216 | POLE_BURN_REPL - 11710 LOMA RICA RD. MAR | 35143933 |  |  | STS-POLE_BURN_REPL - 11710 LOMA RICA RD. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3198 | -121.3998 |  | TIER 2 | 115 | 10319-1101, BANGOR | K2725 | 40133 | Y | 311 |  |  | 2021-03-10 07:00 | 2021-03-10 16:00 | Scheduled | CLICK | [6 empty] | 37.6 | 37.6 |  |  | 5 | 32.6 | 32.6 |  |  | EC | E | Pole | Burnt | Replace |  | 101292654 | PRI RELW OH CLR JPOL RESD REMT SWRK ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-06-25 | 2020-06-25 | COMP | 2020-06-25 | [16 empty] | 2019-04-07 | 2020-04-07 |  | 2020-04-07 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 103191101 | 17366.08 | 3422.4 | 2253.1 | 873.7 | 873.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | MARYSVILLE | Marysville |  |  | OPEN | 119210786 | POLE_BROK_REPL - 3W/O 6180 STONEHEDGE DR | 35183928 |  |  | B3STS-POLE_BROK_REPL-3W/O 6180 STONEHEDG | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3412 | -121.3857 |  | TIER 2 | 115 | 10319-1101, BANGOR | K2811 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101324325 | RELW OH PRI INSP JPOL REMT FIRE SWRK ESTR BTKA USA FMOB TER2 | Pole | 2020-09-08 | 2020-09-10 | COMP | 2020-07-09 | [16 empty] | 2020-06-25 | 2020-09-25 |  | 2020-09-25 | Work Plan Reconcilation (B-Tags) |  | W. Sac |  | 103191101 | 7329.04 | 3740.6 | [7 empty] | N | 11/2 in MPP Import File | N | Access/Customer Issue - Unable to reach customer | Y | 2020-07-21
North | SA | MARYSVILLE | Marysville |  |  | COMP | 116876067 | POLE_DECA_REPL - 12970 DOUGLAS WAY S/S | 35217608 |  |  | B2STS-POLE_DECA_REPL-12970 DOUGLAS WY S/ | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  |  | 1 | 2021-01-01 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.3366 | -121.4 |  | TIER 2 | 115 | 10319-1101, BANGOR | K27 | 1887 | Y | 311 |  |  | 2021-01-20 | 2021-01-20 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 23.1 | 23.1 |  |  | 42 | 23 | 23 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101293288 | OH PRI COMP CLR JPOL RESD REMT FIRE NOAC GO REAR CPGE CPGD FMOB TER2 PRTO RELW | Pole | 2020-12-17 | 2020-12-22 | COMP | 2020-12-17 | COMP | 2021-01-20 | [13 empty] | 2021-01-21 | 2021-01-20 | 2020-03-31 | 2021-01-29 | 2021-01-29 | Per DOT Approved Request 17958 |  | W. Sac |  | 103191101 | 10256.93 | 17659 | 17658.9 | 12886.3 | 12886.3 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-11-30
North | SA | MARYSVILLE | Marysville |  |  | OPEN | 116875402 | POLE_BROK_REPL - 1/P S/O 5650 WOLF TRAIL | 35216851 |  |  | STS-POLE_BROK_REPL - 1/P S/O 5650 WOLF T | ADER | ADER ERDY | Poles | MPP | Not Funded as 2020 Wildfire OII | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.3274 | -121.4044 |  | TIER 2 | 115 | 10319-1101, BANGOR | K2719 | 16933 | Y | 311 |  |  | 2021-05-21 07:00 | 2021-05-21 16:00 | Scheduled | CLICK | [6 empty] | 50.1 | 50.1 |  |  | 0 | 50.1 | 50.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101293455 | RELW OH PRI CLR JPOL RESD REMT FIRE NOAC REAR FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 |  | 2020-03-31 | work plan year cleanup 01/21/2021 |  | W. Sac |  | 103191101 | 1 | 121.1 | [7 empty] | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-21
North | SA | SMARTSVILLE | Marysville |  |  | OPEN | 117041831 | POLE_BROK_REPL - 4PS/O 7660 WALSH LN SMA | 35202276 |  |  | STS-POLE_BROK_REPL - 4PS/O 7660 WALSH LN | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.1799 | -121.3197 |  | TIER 2 | 967 | 15379-1101, SMARTVILLE | O2905 | 39137 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101309249 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-16 | 2020-04-16 | 2020-10-30 | 2020-10-30 | 2021 CBP Plan | 2021-01-31 | VPI |  | 153791101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | SMARTSVILLE | Marysville |  |  | OPEN | 117049841 | POLE_DECA_REPL - 4P N/O CUT OUT 2021 A/S | 35200357 |  |  | STS-POLE_DECA_REPL - 4P N/O CUT OUT 2021 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.1973 | -121.3162 |  | TIER 2 | 967 | 15379-1101, SMARTVILLE | N2920 | 17339 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101335218 | RELW OH PRI INSP ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 153791101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | SMARTSVILLE | Marysville |  |  | OPEN | 117067167 | POLE_DECA_REPL - 8111 HAMMONTON SMARTSVI | 35200470 |  |  | STS-POLE_DECA_REPL - 8111 HAMMONTON SMAR | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.1982 | -121.3126 |  | TIER 2 | 967 | 15379-1101, SMARTVILLE | N3016 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103678448 | RELW OH SEC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-19 | 2020-04-19 | 2020-10-30 | 2020-10-30 | 2021 CBP Plan | 2021-01-31 | VPI |  | 153791101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | STONYFORD | Sacramento |  |  | OPEN | 117159486 | POLE_BROK_REPL - 1 S/O 4195 MAXWELL SITE | 35200460 |  |  | STS-POLE_BROK_REPL - 1 S/O 4195 MAXWELL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 39.3078 | -122.3366 |  | TIER 2 | 427 | 06288-1105, MAXWELL | L0409 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101644352 | RELW OH PRI JPOL ESTR BTKA USA FSRP FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 062881105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | STONYFORD | Sacramento |  |  | OPEN | 117159852 | POLE_DECA_REPL - #1S/O #1W/O 4195 MAXWEL | 35200431 |  |  | STS-POLE_DECA_REPL - #1S/O #1W/O 4195 MA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.3065 | -122.3371 |  | TIER 2 | 427 | 06288-1105, MAXWELL | L0409 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101617266 | RELW OH SEC REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 062881105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | STONYFORD | Sacramento |  |  | OPEN | 117160103 | POLE_BROK_REPL - #1 W/O 4195 MAXWELL SIT | 35200430 |  |  | STS-POLE_BROK_REPL - #1 W/O 4195 MAXWELL | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.3087 | -122.3375 |  | TIER 2 | 427 | 06288-1105, MAXWELL | L0409 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101617264 | RELW OH SEC ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 062881105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | STONYFORD | Sacramento |  |  | OPEN | 117187079 | POLE_BROK_REPL - #2N/O FU#3883 ON HUFFMA | 35200462 |  |  | STS-POLE_BROK_REPL - #2N/O FU#3883 ON HU | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 39.2549 | -122.3563 |  | TIER 2 | 427 | 06288-1105, MAXWELL | M04 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101644396 | OH RELW PRI REMT ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | QUES |  | 062881105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | VACAVILLE | Vacaville |  |  | OPEN | 116714131 | POLE_BROK_REPL - 1A/F 6884 STIEGER HILL | 35200425 |  |  | STS-POLE_BROK_REPL - 1A/F 6884 STIEGER H | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3935 | -122.0023 |  | TIER 2 | 495 | 06359-1105, VACA DIXON | P1120 | 3589 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101580846 | RELW OH PRI INSP JPOL REMT ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-12 | 2020-03-12 | 2020-11-14 | 2020-11-14 | 2021 CBP Plan | 2021-01-31 | VPI |  | 063591105 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | VACAVILLE | Vacaville |  |  | OPEN | 116810533 | POLE_BROK_REPL - 2IN PVPT 6973 PLEASANTS | 35200424 |  |  | STS-POLE_BROK_REPL - 2IN PVPT 6973 PLEAS | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3982 | -122.0416 |  | TIER 2 | 348 | 06360-1108, VACAVILLE | P1116 | 56665 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101578516 | RELW OH PRI INSP CLR SWRK ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-04-10 | 2021-04-10 | 2021 CBP Plan | 2021-03-31 | TRC |  | 063601108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | VACAVILLE | Vacaville |  |  | OPEN | 116714480 | POLE_DECA_REPL - 1W/O 1S/O 1A/F 6948 GIB | 35081645 |  |  | STS-POLE_DECA_REPL - 1W/O 1S/O 1A/F 6948 | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.3958 | -122.0008 |  | TIER 2 | 495 | 06359-1105, VACA DIXON | P1216 | 3589 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 18.5 | 18.5 |  |  | 0 | 18.5 | 18.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101668293 | RELW OH PRI INSP JPOL REMT ESTR FMOB TER2 FSRP | Pole | 2021-01-06 |  | COMP | 2021-01-06 | [16 empty] | 2019-03-12 | 2020-03-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 063591105 | 7025.58 | 1732.5 | 1214.4 | 1221.7 | 1221.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | VACAVILLE | Vacaville |  |  | OPEN | 117035475 | POLE_DECA_REPL - 4W/O POLE AT 3780 CANTE | 35088945 |  |  | STS-POLE_DECA_REPL - 4W/O POLE AT 3780 C | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4227 | -122.0288 |  | TIER 2 | 495 | 06359-1105, VACA DIXON | P11 | 15779 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 80.7 | 80.7 |  |  | 0 | 80.7 | 80.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101579666 | RELW OH PRI INSP ESTR BTKA FMOB TER2 FSRP | Pole | 2021-02-02 | 2021-02-02 | COMP | 2021-02-02 | [16 empty] | 2019-04-15 | 2019-09-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 063591105 | 15531.76 | 345.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SA | VACAVILLE | Woodland |  |  | OPEN | 117246307 | POLE_BROK_REPL - 8261 PLEASANT VLY RD.1P | 35200423 |  |  | STS-POLE_BROK_REPL - 8261 PLEASANT VLY R | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.47 | -122.041 |  | TIER 2 | 441 | 06368-1102, PUTAH CREEK | O11 | 20797 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101571236 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | TRC |  | 063681102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | Winters | Woodland |  |  | OPEN | 117688596 | POLE _ BROK _ REPL_8140 OLIVE SCHOOL LN. | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 38.4714 | -122.011 |  | TIER 2 | 479 | 06368-1103, PUTAH CREEK | N1125 |  | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101576213 | OH PRI ESTR TER2 PRTO FSRP POHW | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-07-31 | 2020-07-31 | 2020-09-29 | 2020-09-29 | 2021 CBP Plan |  | UNASSIGNED |  | 063681103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SA | WINTERS | Woodland |  |  | OPEN | 117318245 | POLE_DECA_REPL - C/O CO RD 34/ELCAMINO R | 35143971 |  |  | STS-POLE_DECA_REPL - C/O CO RD 34/ELCAMI | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.5231 | -122.0226 |  | TIER 2 | 441 | 06368-1102, PUTAH CREEK | M11 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 39.5 | 39.5 |  |  | 0 | 39.5 | 39.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101574767 | RELW OH PRI JPOL RESD NOAC ESTR GO FMOB TER2 PRTO FSRP | Pole | 2021-01-06 | 2021-01-05 | COMP | 2021-01-05 | [16 empty] | 2019-05-24 | 2020-05-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | EEI |  | 063681102 | 18462.68 | 3441 | 3440.9 | 5017.8 | 5017.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI |  | Placerville |  |  | OPEN | 115597202 | 616 CANAL ST. | 35069237 |  |  | 616 CANAL ST. | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-06-26 | Renew Permit | 38.731 | -120.8098 |  | TIER 2 | 322 | 15308-1112, PLACERVILLE | I4104 |  | Y | 311 |  |  | 2021-03-11 07:00 | 2021-03-11 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 133 | 133 |  |  | 24.75 | 120 | 120 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101406550 | REGW OH TER2 | Pole | 2019-07-23 | 2019-10-18 | COMP | 2019-06-12 |  |  | 2019-07-24 | 2019-08-27 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-02 | CALENG |  | 153081112 | 82966.58 | 60306.3 | -9000.4 | 2499.6 | 2499.6 | 14402.9 |  | 14402.9 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI |  | Placerville |  |  | OPEN | 115597378 | POLE_DECA_REPL - | 35069162 |  |  | SW/O HOUSE 2855 CANAL CT | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7333 | -120.8198 |  | TIER 2 | 322 | 15308-1112, PLACERVILLE | H4122 |  | Y | 311 |  |  | 2020-11-01 | 2020-11-01 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 89 | 89 |  |  | 8 | 81 | 81 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101385518 | REGW OH TER2 CCNT COMP | Pole | 2019-07-22 | 2019-07-23 | COMP | 2019-07-22 | [16 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-02 | CALENG |  | 153081112 | 30135.1 | 74207 | -35000 |  |  | 25832.1 |  | 25832.1 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | APPLEGATE | Auburn |  |  | OPEN | 116623973 | POLE_DECA_REPL - A\F 521 APPLEGATE SCHOO | 35091361 |  |  | STS-POLE_DECA_REPL - A\F 521 APPLEGATE S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9986 | -120.9889 |  | TIER 2 | 374 | 15224-1102, HALSEY | S1101 | 6225 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48.8 | 48.8 |  |  | 10 | 38.8 | 38.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100026239 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-07-28 | 2020-09-11 | COMP | 2020-07-28 |  |  | 2019-09-05 | 2019-09-05 | [12 empty] | 2019-03-01 | 2020-03-01 | 2024-02-28 | 2024-02-28 | Per DOT Approved Request 28448 | 2020-12-31 | QUES |  | 152241102 | 23017.86 | 3323.7 | 843.8 |  |  | 10 |  | 10 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
North | SI | APPLEGATE | Auburn |  |  | OPEN | 116635349 | POLE_DECA_REPL - P/D 1N/O 1NW/O AT 35 PI | 35091404 |  |  | STS-POLE_DECA_REPL - P/D 1N/O 1NW/O AT 3 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9911 | -121.0024 |  | TIER 2 | 374 | 15224-1102, HALSEY | S1009 |  | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100032905 | RELW OH SERV PGEA CLR JPOL RESD TRAF FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2019-10-31 | 2019-11-22 | COMP | 2019-10-31 | [16 empty] | 2019-03-05 | 2020-03-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-31 | QUES |  | 152241102 | 9176.11 | 4533.2 | 3216.7 | 730.4 | 730.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | APPLEGATE | Auburn |  |  | OPEN | 116636626 | POLE_BROK_REPL - AT 140 GILBERT RD APPLE | 35090963 |  |  | STS-POLE_BROK_REPL - AT 140 GILBERT RD A | CONS | CONS ERDY SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9873 | -121.0023 |  | TIER 2 | 374 | 15224-1102, HALSEY | S1009 |  | Y | 311 |  |  | 2021-03-19 07:00 | 2021-03-19 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100030359 | OH RELW SEC CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2019-11-04 | 2019-11-21 | COMP | 2019-11-04 |  |  | 2019-05-13 | 2019-05-14 | [12 empty] | 2019-03-05 | 2020-03-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-31 | QUES |  | 152241102 | 5263.3 | 858.2 | 858.3 | 516.1 | 516.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | APPLEGATE | Auburn |  |  | OPEN | 117732292 | TREE_DECA_INPL - 471 APPLEGATE SCHOOL RD | 35091361 |  |  | STS-POLE_DECA_REPL - A\F 521 APPLEGATE S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9986 | -120.9889 |  | TIER 2 | 374 | 15224-1102, HALSEY | S1101 | 6225 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100026239 | POHW OH ESTR TER2 FSRP | Pole | 2020-07-28 | 2020-09-11 | COMP | 2020-07-28 |  |  | 2019-09-05 | 2019-09-05 | [12 empty] | 2019-05-15 | 2020-03-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | QUES |  | 152241102 | 23017.86 | 3323.7 | 843.8 |  |  | 10 |  | 10 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116688295 | POLE_BROK_REPL - R\O 16105 BASS LAKE RD | 35080105 |  |  | STS-POLE_BROK_REPL - R\O 16105 BASS LAKE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9731 | -121.0051 |  | TIER 2 | 374 | 15224-1102, HALSEY | S1019 | 6123 | Y | 311 | [5 empty] | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 75.4 | 75.4 |  |  | 0 | 75.4 | 75.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100034388 | RELW OH PRI PGEA CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-23 | 2021-02-12 | COMP | 2020-12-22 | [16 empty] | 2019-03-08 | 2019-09-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152241102 | 19218.21 |  | -1684.3 | 91.7 | 91.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116692033 | POLE_BROK_REPL - #1W 3020 AYERS HOLMES R | 35163385 |  |  | STS-POLE_BROK_REPL - #1W 3020 AYERS HOLM | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 38.927 | -121.177 |  | TIER 2 | 129 | 15227-1102, WISE | T0618 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.7 | 19.7 |  |  | 0 | 19.7 | 19.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100073242 | RELW OH PRI CLR JPOL REMT NOAC ESTR GO REAR FMOB TER2 PRTO FSRP | Pole | 2020-10-28 |  | COMP | 2020-10-28 | [16 empty] | 2019-03-09 | 2020-03-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152271102 | 7938.2 | 766.2 | 25 | 25 | 25 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116720150 | POLE_DECA_REPL - 4NE/O 12285 RIO OSO RD | 35088493 |  |  | STS-POLE_DECA_REPL - 4NE/O 12285 RIO OSO | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.0109 | -121.1005 |  | TIER 2 | 306 | 15270-1108, BELL | R0822 | 5773 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100090271 | RELW OH PRI CLR JPOL RESD ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-13 | 2019-09-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 152701108 | 1 | 16.4 | 16.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116727807 | POLE_DECA_REPL - 20395 MONTANA LN. AUBUR | 35085009 |  |  | STS-POLE_DECA_REPL - 20395 MONTANA LN. A | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.9712 | -121.0681 |  | TIER 2 | 68 | 15224-1101, HALSEY | R1103 | 95573 | Y | 311 | [5 empty] | Order Operation | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100024767 | OH RELW PRI ESTR GO PROG TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-13 | 2019-09-13 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2020-09-30 | QUES |  | 152241101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116737013 | POLE_BROK_REPL - #2N ON LINE @ 12435 LON | 35214814 |  |  | STS-POLE_BROK_REPL - #2N ON LINE @ 12435 | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.9978 | -121.1046 |  | TIER 2 | 306 | 15270-1108, BELL | S0802 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100032749 | RELW OH PRI JPOL RESD ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-14 | 2020-03-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | VPI |  | 152701108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116764612 | POLE_BROK_REPL - 1W/O R/O 10405 BELL RD | 35202184 |  |  | STS-POLE_BROK_REPL - 1W/O R/O 10405 BELL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.001 | -121.1318 |  | TIER 2 | 306 | 15270-1108, BELL | S0703 | 6853 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100027864 | RELW OH PRI JPOL REMT ESTR REAR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152701108 | 1 |  | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116767805 | POLE_BROK_REPL - AT 1489 CHRISTIAN VALLE | 35225172 |  |  | STS-POLE_BROK_REPL - AT 1489 CHRISTIAN V | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.9725 | -121.049 |  | TIER 2 | 68 | 15224-1101, HALSEY | S0919 | 94889 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100031648 | CLR OH PRI RELW JPOL RESD BTKA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 |  | 2020-03-19 | Per DOT Approved Request 45769 | 2021-02-28 | Auburn |  | 152241101 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-06
North | SI | AUBURN | Auburn |  |  | OPEN | 116773331 | POLE_DECA_REPL - 1W/O 3733 OTTO WAY AUBU | 35215140 |  |  | STS-POLE_DECA_REPL - 1W/O 3733 OTTO WAY | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.9884 | -121.0814 |  | TIER 2 | 306 | 15270-1108, BELL | S0810 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100031253 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | VPI |  | 152701108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116790246 | POLE_DECA_REPL - A/F 4609 BELL RD AUBURN | 35202197 |  |  | STS-POLE_DECA_REPL - A/F 4609 BELL RD AU | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.9602 | -121.1352 |  | TIER 2 | 463 | 15270-1107, BELL | S0723 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27 | 27 |  |  | 0 | 27 | 27 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100028019 | RELW OH PRI CLR JPOL REMT FIRE FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-13 |  | COMP | 2021-01-13 | [16 empty] | 2019-03-20 | 2020-03-20 | 2020-10-23 | 2020-10-23 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152701107 | 13157.17 |  | -1991.9 | 791.8 | 791.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116791420 | POLE_DECA_REPL - #1NW 6385 BARBARA LN W/ | 35215197 |  |  | STS-POLE_DECA_REPL - #1NW 6385 BARBARA L | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.9858 | -121.0892 |  | TIER 2 | 306 | 15270-1108, BELL | S0809 | 6247 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100030677 | RELW OH PRI CLR JPOL RESD BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | VPI |  | 152701108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116793233 | POLE_DECA_REPL - #1 ON LINE S/O 3700 CHR | 35215221 |  |  | STS-POLE_DECA_REPL - #1 ON LINE S/O 3700 | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.989 | -121.0737 |  | TIER 2 | 306 | 15270-1108, BELL | S0810 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100034194 | RELW OH PRI JPOL COMM NOAC ESTR GO FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | VPI |  | 152701108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116817799 | POLE_DECA_REPL - 11600 CRAMER RD AUBURN | 35202388 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.9853 | -121.1145 |  | TIER 2 | 306 | 15270-1108, BELL | S07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.1 | 19.6 | 0.5 |  | 0 | 20.1 | 19.6 | 0.5 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100032476 | RELW OH PRI JPOL REMT BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2019-03-23 | 2020-03-23 | 2020-11-30 | 2020-11-30 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152701108 | 10611.1 |  | -210 | 850 | 850 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116818705 | POLE_DECA_REPL - R/O 13085 DRY CREEK RD | 35214589 |  |  | STS-POLE_DECA_REPL - R/O 13085 DRY CREEK | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.9632 | -121.0817 |  | TIER 2 | 981 | 15270-1109, BELL | S0824 | 5783 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100033075 | OH PRI CLR REMT ESTR REAR FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | VPI |  | 152701109 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116822874 | POLE_DECA_REPL - R/O 5210 MEADOW VIEW DR | 35214713 |  |  | STS-POLE_DECA_REPL - R/O 5210 MEADOW VIE | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.9812 | -121.1121 |  | TIER 2 | 306 | 15270-1108, BELL | S0811 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100089207 | RELW OH PRI CLR RESD REMT GO REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | VPI |  | 152701108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116836961 | POLE_BROK_REPL - R/O 11861 JOEGER RD W/T | 35214833 |  |  | STS-POLE_BROK_REPL - R/O 11861 JOEGER RD | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.9649 | -121.1072 |  | TIER 2 | 306 | 15270-1108, BELL | S0821 | 39511 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100031872 | RELW OH PRI CLR REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | VPI |  | 152701108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116842207 | POLE_BROK_REPL - AT 10170 MT VERNON RDAU | 35214872 |  |  | STS-POLE_BROK_REPL - AT 10170 MT VERNON | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.9295 | -121.1231 |  | TIER 2 | 463 | 15270-1107, BELL | T0719 | 433 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100070077 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2021-04-18 | 2021-04-18 | 2021 CBP Plan | 2021-03-31 | VPI |  | 152701107 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116842968 | POLE_DECA_REPL - 1W/O 1550 OLD AIRPORT R | 35088772 |  |  | STS-POLE_DECA_REPL - 1W/O 1550 OLD AIRPO | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 38.9484 | -121.0688 |  | TIER 2 | 456 | 15246-1103, PLACER | T0906 | 6057 | Y | 311 | [5 empty] | Order Operation | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100040600 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2019-11-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152461103 | 1 | 1535.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116879416 | POLE_BROK_REPL - 9490 CRATER HILL RD AUB | 35163394 |  |  | STS-POLE_BROK_REPL - 9490 CRATER HILL RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-12-31 |  | 38.9042 | -121.1259 |  | TIER 2 | 129 | 15227-1102, WISE | U0709 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.8 | 20.8 |  |  | 0 | 20.8 | 20.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100078295 | RELW OH PRI CLR JPOL RESD FIRE ESTR BTKA FMOB TER2 PRTO | Pole | 2021-02-18 | 2021-02-18 | COMP | 2020-08-28 |  |  | 2021-02-18 | 2021-02-18 | [12 empty] | 2019-04-01 | 2020-04-01 |  | 2020-04-01 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152271102 | 13315.58 | 304.7 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 117032282 | POLE_BROK_REPL - 1990 VADA RANCH RD AUBU | 35088907 |  |  | STS-POLE_BROK_REPL - 1990 VADA RANCH RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.9094 | -121.1071 |  | TIER 2 | 456 | 15246-1103, PLACER | U0801 | 35265 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 80.3 | 80.3 |  |  | 0 | 80.3 | 80.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100075249 | RELW OH PRI CREW JPOL RESD NOAC SWRK ESTR TER2 FSRP | Pole | 2020-06-25 |  | COMP | 2020-06-25 |  |  | 2019-05-13 | 2019-05-14 | [12 empty] | 2019-03-27 | 2019-09-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | TRC |  | 152461103 | 17734.89 | 1872.3 | 1447.5 | 1447.5 | 1447.5 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 117098625 | POLE_DECA_REPL - 1SW/O A/F 5090 SWEET WA | 35214726 |  |  | STS-POLE_DECA_REPL - 1SW/O A/F 5090 SWEE | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.0033 | -121.0854 |  | TIER 2 | 306 | 15270-1108, BELL | R0824 | 9715 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100023464 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | VPI |  | 152701108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 117098716 | POLE_DECA_REPL - A/F 5090 SWEET WATER DR | 35214731 |  |  | STS-POLE_DECA_REPL - A/F 5090 SWEET WATE | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.0035 | -121.0849 |  | TIER 2 | 306 | 15270-1108, BELL | R0824 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100023465 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-25 | 2020-04-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152701108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 117104981 | GUY_OVRG_TRIM - AF 5245 CEDAR RIDGE DR A | 35214820 |  |  | STS-GUY_OVRG_TRIM - AF 5245 CEDAR RIDGE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 39.0058 | -121.0853 |  | TIER 2 | 306 | 15270-1108, BELL | R0824 | 9715 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.5 | 38.5 |  |  | 0 | 38.5 | 38.5 |  |  | EC | E | Guy | Overgrown | Trim |  | 100023488 | RELW ESTR OH PRI FMOB TER2 PRTO FSRP | Pole | 2021-02-10 |  | COMP | 2021-02-10 | [16 empty] | 2019-04-26 | 2020-04-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152701108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 117337896 | POLE_DECA_REPL - #1E ON LINE @ R/O 8311 | 35203065 |  |  | STS-POLE_DECA_REPL - #1E ON LINE @ R/O 8 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.9979 | -121.1512 |  | TIER 2 | 306 | 15270-1108, BELL | S07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 19.8 | 19.8 |  |  | 0 | 19.8 | 19.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100078003 | RELW OH SEC CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-05 |  | COMP | 2021-01-05 | [16 empty] | 2019-05-29 | 2020-05-29 | 2020-10-27 | 2020-10-27 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152701108 | 12057.18 |  | -1092.6 | 292.4 | 292.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | COMP | 116791323 | POLE_DECA_REPL - 1E/O R/O 1740 CHRISTIAN | 35149666 |  |  | STS-POLE_DECA_REPL - 1E/O R/O 1740 CHRIS | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.9745 | -121.0515 |  | TIER 2 | 68 | 15224-1101, HALSEY | S0918 | 2414 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0.5 | 40.5 | 40.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100033528 | PRI RELW OH COMP CLR JPOL RESD NOAC ESTR USA CCNT FMOB TER2 PRTO | Pole | 2020-04-24 | 2020-08-06 | COMP | 2020-04-24 | COMP | 2021-02-10 | [13 empty] | 2021-02-11 | 2021-02-10 | 2020-03-20 |  | 2020-03-20 | circuit based plan 2.14 | 2020-04-10 | PIKEENG |  | 152241101 | 14605.08 | 8304.1 | 1553.3 | 111.2 | 111.2 | 41.7 |  | 41.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | AUBURN | Auburn |  |  | COMP | 116834577 | POLE_DECA_REPL - 1S/O 10180 JOEGER RDAUB | 35083473 |  |  | STS-POLE_DECA_REPL - 1S/O 10180 JOEGER R | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.943 | -121.124 |  | TIER 2 | 463 | 15270-1107, BELL | T0709 |  | Y | 311 |  |  | 2021-01-12 | 2021-01-12 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.9 | 41.9 |  |  | 3.5 | 0.9 | 0.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100078470 | OH RELW PRI COMP CLR JPOL REMT ESTR USA CCNT FMOB TER2 PRTO FSRP | Pole | 2020-08-25 | 2020-09-11 | COMP | 2020-04-19 | COMP | 2021-01-12 | 2019-05-13 | 2019-05-14 | [11 empty] | 2021-01-15 | 2021-01-12 | 2019-09-26 | 2021-05-31 | 2021-05-31 | Program Manager | 2020-07-31 | W. Sac |  | 152701107 | 12039.93 | 8294.6 | 5981.1 | 5993.8 | 5993.8 | 84.6 |  | 84.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
North | SI | AUBURN | Auburn |  |  | OPEN | 116589554 | POLE_DECA_REPL - 2N/O 6430 FAIR OAKS LNA | 35090476 |  |  | STS-POLE_DECA_REPL - 2N/O 6430 FAIR OAKS | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0051 | -121.1286 |  | TIER 2 | 306 | 15270-1108, BELL | R07 | 6563 | Y | 311 |  |  | 2021-04-12 07:00 | 2021-04-12 16:00 | Dispatched | CLICK | [6 empty] | 49.5 | 41.8 | 7.7 |  | 0.5 | 49 | 41.3 | 7.7 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100113962 | RELW OH PRI CLR JPOL REMT ESTR BTKA RTRN USA FMOB TER2 PRTO FSRP | Pole | 2019-11-25 | 2019-12-16 | COMP | 2019-11-25 | [16 empty] | 2019-02-23 | 2020-02-23 | 2021-04-01 | 2021-04-01 | 2021 CBP Plan | 2019-10-31 | QUES |  | 152701108 | 14908.86 | 3544.2 | 3113.4 | 1112 | 1112 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116686086 | POLE_BROK_REPL - 1W\O 3N\O 15850 APPLEGA | 35142802 |  |  | STS-POLE_BROK_REPL - 1W\O 3N\O 15850 APP | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9725 | -121.0145 |  | TIER 2 | 374 | 15224-1102, HALSEY | S1018 |  | Y | 311 |  |  | 2021-04-14 07:00 | 2021-04-14 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 4.5 | 40 | 40 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100034512 | RELW OH PRI INSP CLR JPOL REMT SCOP REAR PROG SCPA FMOB TER2 PRTO | Pole | 2020-01-19 | 2020-06-30 | COMP | 2020-01-19 |  |  | 2020-06-30 | 2020-06-30 | [12 empty] | 2019-03-08 | 2019-09-08 |  | 2019-09-08 | circuit based plan 2.14 | 2020-03-08 | Auburn |  | 152241102 | 17362.67 | 3973.2 | 77.7 | 58.7 | 58.7 | 1706.5 |  | 1706.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | AUBURN | Auburn |  |  | OPEN | 116686226 | POLE_DECA_REPL - 6N\O 15850 APPLEGATE RD | 35091610 |  |  | STS-POLE_DECA_REPL - 6N\O 15850 APPLEGAT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9733 | -121.0141 |  | TIER 2 | 374 | 15224-1102, HALSEY | S1018 | 56793BP | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-22 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100034313 | RELW OH PRI PGEA CLR JPOL REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2019-12-27 | 2020-01-24 | COMP | 2019-12-27 |  |  | 2019-05-13 | 2019-05-14 | [12 empty] | 2019-03-08 | 2020-03-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-31 | QUES |  | 152241102 | 15779.03 | 290.3 |  |  |  | 19.3 |  | 19.3 |  | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116692231 | POLE_DECA_REPL - R/O 6737 WISE RD AUBURN | 35163386 |  |  | STS-POLE_DECA_REPL - R/O 6737 WISE RD AU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9247 | -121.1753 |  | TIER 2 | 129 | 15227-1102, WISE | T0618 |  | Y | 311 |  |  | 2021-03-24 07:00 | 2021-03-24 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100073254 | RELW OH SEC JPOL REMT NOAC ESTR REAR PROG FMOB TER2 PRTO FSRP | Pole | 2020-09-10 | 2020-10-28 | COMP | 2020-09-10 | [16 empty] | 2019-03-09 | 2020-03-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152271102 | 7407.56 |  | -1385 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116722705 | POLE_BROK_REPL - 2E/O 6460 WISE RD[OF HO | 35163388 |  |  | STS-POLE_BROK_REPL - 2E/O 6460 WISE RD[O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9226 | -121.1808 |  | TIER 2 | 129 | 15227-1102, WISE | T0622 | 5381 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.6 | 44.6 |  |  | 0 | 44.6 | 44.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100036632 | RELW OH PRI CLR JPOL REMT ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2020-05-21 | 2020-07-15 | COMP | 2020-05-21 | [16 empty] | 2019-03-13 | 2020-03-13 |  | 2020-03-13 | circuit based plan 2.14 | 2020-07-16 | TRC |  | 152271102 | 21068.67 | 308.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | AUBURN | Auburn |  |  | OPEN | 116759068 | POLE_DECA_REPL - 2580 ROSS CT AUBURN | 35149659 |  |  | STS-POLE_DECA_REPL - 2580 ROSS CT AUBURN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9763 | -121.0654 |  | TIER 2 | 68 | 15224-1101, HALSEY | S0911 | 89241 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 49.1 | 49.1 |  |  | 0 | 49.1 | 49.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100033427 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-04-14 | 2020-06-08 | COMP | 2020-04-14 |  |  | 2020-02-28 | 2020-02-28 | [12 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-04-10 | PIKEENG |  | 152241101 | 24418.08 | 125.1 |  |  |  | 125.1 |  | 125.1 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | AUBURN | Auburn |  |  | OPEN | 116834447 | POLE_BROK_REPL - 1WO 11925 FRESH AIR LN | 35088749 |  |  | / STS-POLE_BROK_REPL - 1WO 11925 FRESH A | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9661 | -121.1054 |  | TIER 2 | 306 | 15270-1108, BELL | S0822 | 39511 | Y | 311 |  |  | 2021-03-25 07:00 | 2021-03-25 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100032931 | RELW OH PRI CLR REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2019-11-14 | 2020-08-28 | COMP | 2019-11-14 | [16 empty] | 2019-03-26 | 2019-11-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | W. Sac |  | 152701108 | 28782.94 | 81.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116872377 | POLE_DECA_REPL - #1S 9603 WISE RD W/T AU | 35163392 |  |  | STS-POLE_DECA_REPL - #1S 9603 WISE RD W/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 38.8993 | -121.1271 |  | TIER 2 | 129 | 15227-1102, WISE | U0709 | 38617 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 47.7 | 47.7 |  |  | 0 | 47.7 | 47.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100045270 | RELW OH PRI FIRE CLR JPOL RESD TRAF FLAG ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-09-04 | 2020-11-02 | COMP | 2020-08-28 |  |  | 2020-06-18 | 2020-06-18 | [12 empty] | 2019-03-30 | 2020-03-30 |  | 2020-03-30 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152271102 | 20836.06 | 598.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 117431419 | POLE_DECA_REPL - #4W ON LINE A/F 585 PER | 35121855 |  |  | STS-POLE_DECA_REPL - #4W ON LINE A/F 585 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8785 | -121.1021 |  | TIER 2 | 900 | 15227-1101, WISE | U0817 | 46739 | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100044945 | RELW OH PRI INSP JPOL FIRE ESTR BTKA FMOB TER2 FSRP | Pole | 2020-04-17 | 2020-06-09 | COMP | 2020-04-17 |  |  | 2019-09-05 | 2019-09-05 | [12 empty] | 2019-06-11 | 2020-06-11 |  | 2020-06-11 | 2021 CBP Plan |  | Auburn |  | 152271101 | 9523.12 | 1362.6 | 1362.6 | 1180.6 | 1180.6 |  |  |  | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | COMP | 116704923 | POLE_BROK_REPL - R/O 7045 MT. VERNON RDA | 35163387 |  |  | STS-POLE_BROK_REPL - R/O 7045 MT. VERNON | MAPP | MAPP SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.9399 | -121.1712 |  | TIER 2 | 129 | 15227-1102, WISE | T0614 | 697216 | Y | 311 |  |  | 2021-02-16 07:00 | 2021-02-16 16:00 | Completed | CLICK | [6 empty] | 28.1 | 28.1 |  |  | 74 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100036958 | RELW OH PRI COMP CLR JPOL REMT NOAC ESTR GO REAR USA CPGG PRTO FMOB TER2 | Pole | 2020-08-28 | 2020-12-21 | COMP | 2020-08-28 | COMP | 2021-02-16 | [13 empty] | 2021-02-22 | 2021-02-16 | 2020-03-10 |  | 2020-03-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152271102 | 13036.11 | 7304.3 | 5919.3 | 1147.5 | 1147.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | COMP | 120010510 | COND_CLER_INPL - 69O CHUBB RD W/TAuburn | 35213160 |  |  | B3 - STS-COND_CLER_INPL - 69O CHUBB RD W | MAPP | MAPP SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-13 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.9438 | -121.0411 |  | TIER 2 | 374 | 15224-1102, HALSEY | T0910 | 34205 | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 14.1 | 14.1 |  |  | 40.5 | 0 |  |  |  | EC | B | Conductor | Clearance Impaired | Install CL Pole |  | 100088637 | RELW ESTR COMP OH SERV INSP GO PROG CPGG FMOB TER2 | Pole | 2020-12-09 | 2020-12-09 | COMP | 2020-12-09 | COMP | 2021-02-09 | [13 empty] | 2021-02-10 | 2021-02-09 | 2021-02-10 |  | 2021-02-10 | B tag clean up 11/15/2020 |  | Auburn |  | 152241102 | 13165.61 | 4005.5 | 3455.8 | 730.2 | 730.2 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-11-15
North | SI | AUBURN | Auburn |  |  | OPEN | 116764426 | POLE_DECA_REPL - R/O 10025 BELL RD AUBUR | 35202176 |  |  | STS-POLE_DECA_REPL - R/O 10025 BELL RD A | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0012 | -121.1328 |  | TIER 2 | 306 | 15270-1108, BELL | S0703 | 8317 | Y | 311 |  |  | 2021-03-03 07:00 | 2021-03-03 16:00 | Scheduled | CLICK | [6 empty] | 50.1 | 50.1 |  |  | 0 | 50.1 | 50.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100027863 | PRI OH RELW JPOL REMT FMOB ESTR REAR TER2 PRTO FSRP | Pole | 2020-11-30 | 2021-01-21 | COMP | 2020-11-30 | [16 empty] | 2019-03-19 | 2020-03-19 | 2020-11-04 | 2020-11-04 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152701108 | 21937.12 | 2858.3 | 1111.3 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 116809882 | POLE_BROK_REPL - R/O 1NO 2000 CHRISTIANV | 35149676 |  |  | STS-POLE_BROK_REPL - R/O 1NO 2000 CHRIST | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9747 | -121.0566 |  | TIER 2 | 68 | 15224-1101, HALSEY | S0918 |  | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 36 | 36 |  |  | 6 | 30 | 30 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100033806 | RELW OH PRI JPOL RESD REMT NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2020-04-16 | 2020-12-08 | COMP | 2020-04-16 | [16 empty] | 2019-03-21 | 2020-03-21 |  | 2020-03-21 | 2021 CBP Plan | 2020-04-10 | PIKEENG |  | 152241101 | 21898.91 | 5984 | 2764.5 | 2764.5 | 2764.5 | 333.6 |  | 333.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 117868702 | POLE_BROK_REPL - 400 BALTIMORE RD AUBURN | 35224799 |  |  | B3 - STS-POLE_BROK_REPL - 400 BALTIMORE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-05-03 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8862 | -121.0851 |  | TIER 2 | 1199 | 15246-1101, PLACER | U0819 | 106534 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 46.4 | 46.4 |  |  | 0 | 46.4 | 46.4 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100098545 | RELW CLR OH PRI TMAN JPOL REMT ESTR BTKA USA PROG TER2 FSRP | Pole | 2021-02-04 |  | COMP | 2021-02-04 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-09-10 | 2020-09-10 | 2021-05-31 | 2021-05-31 | B tag clean up 1/12/2021 |  | Auburn |  | 152461101 | [9 empty] | N | MPP File Only | N |  | Y | 2021-01-12
North | SI | AUBURN | Auburn |  |  | OPEN | 118022365 | TREE_DECA_INPL - 11925 FRESH AIR LN AUBU | 35088749 |  |  | / STS-POLE_BROK_REPL - 1WO 11925 FRESH A | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 |  | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9661 | -121.1054 |  | TIER 2 | 306 | 15270-1108, BELL | S0822 | 39511 | Y | 311 |  |  | 2021-03-25 07:00 | 2021-03-25 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100032931 | POHW OH ESTR TER2 FSRP | Pole | 2019-11-14 | 2020-08-28 | COMP | 2019-11-14 | [16 empty] | 2019-10-03 | 2020-10-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | W. Sac |  | 152701108 | 28782.94 | 81.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Auburn |  |  | OPEN | 120482065 | POLE_BROK_REPL - EOL POLE, 300' SOUTH OF | 35228974 |  |  | B3 - STS-POLE_BROK_REPL - EOL POLE, 300' | PEND | PEND | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  |  | 1 | 2021-04-02 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.9037 | -121.1173 |  | TIER 2 | 463 | 15270-1107, BELL | U0705 | 4549 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 93.2 | 92.5 | 0.7 |  | 0 | 93.2 | 92.5 | 0.7 |  | EC | B | Pole | Broken/Damaged | Replace |  | 100050368 | RELW OH PRI SERV TMAN CLR RESD FLAG ESTR BTKA PROG TER2 | Pole | 2021-02-22 |  | COMP | 2021-02-22 | [16 empty] | 2021-01-30 | 2021-04-30 |  | 2021-04-30 | B tag clean up 2/19/2021 |  | Auburn |  | 152701107 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | SI | AUBURN | Grass Valley |  |  | OPEN | 116822599 | POLE_BROK_REPL - 2S/O 4W/O A/F 11000 GAU | 35214692 |  |  | STS-POLE_BROK_REPL - 2S/O 4W/O A/F 11000 | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.0237 | -121.1128 |  | TIER 2 | 432 | 15269-1109, HIGGINS | R0811 | 5775 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100025178 | RELW OH PRI CLR RESD TER2 ESTR BTKA FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | VPI |  | 152691109 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Grass Valley |  |  | OPEN | 116590914 | POLE_BROK_REPL - R/O 11187 STREETER RD A | 35090587 |  |  | STS-CUTO_BROK_REPL - R/O 11187 STREETER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0321 | -121.1149 |  | TIER 2 | 432 | 15269-1109, HIGGINS | R07 | 172971 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 44.2 | 44.2 |  |  | 0 | 44.2 | 44.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100022218 | RELW OH PRI CLR JPOL REMT ESTR BTKA RTRN USA FMOB TER2 PRTO FSRP | Pole | 2020-06-29 | 2020-08-23 | COMP | 2020-06-26 | [16 empty] | 2019-02-24 | 2020-02-24 | 2021-04-04 | 2021-04-04 | 2021 CBP Plan | 2020-12-31 | QUES |  | 152691109 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | AUBURN | Grass Valley |  |  | OPEN | 116590916 | POLE_BROK_REPL - 11187 STREETER RD AUBUR | 35090596 |  |  | STS-POLE_BROK_REPL - 11187 STREETER RD A | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0339 | -121.1149 |  | TIER 2 | 432 | 15269-1109, HIGGINS | R07 | 172971 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 42.6 | 42.6 | 0 |  | 0 | 42.6 | 42.6 | 0 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100022214 | RELW OH PRI CLR JPOL REMT FLAG ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2019-11-20 | 2019-12-05 | COMP | 2019-11-20 |  |  | 2021-02-01 | 2021-02-01 | [12 empty] | 2019-02-24 | 2020-02-24 | 2024-02-23 | 2024-02-23 | Per 7.22.20 email from [REDACTED], job needs to be done with 31365299 | 2019-10-31 | QUES |  | 152691109 | 20693.45 | 215.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-07-28
North | SI | BLAIRSDEN-GRAEAGLE | Grass Valley |  |  | OPEN | 117396609 | POLE_BROK_REPL - 4N/O 3SW/O C/O 7971 AT | 35154629 |  |  | STS-POLE_BROK_REPL - 4N/O 3SW/O C/O 7971 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.6966 | -120.6619 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | C18 | 7971 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 91.3 | 91.3 |  |  | 0 | 91.3 | 91.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100091055 | OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP RELW | Pole | 2020-09-04 | 2020-10-26 | COMP | 2020-06-30 |  |  | 2020-10-26 | 2020-10-26 | [12 empty] | 2019-06-05 | 2020-06-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | CALENG |  | 152101101 | 29958.1 | 6682.4 | 2702.3 | 1004.7 | 1004.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | BLAIRSDEN-GRAEAGLE | Grass Valley |  |  | OPEN | 117399382 | POLE_BROK_REPL - 12N/O 3NE/O C/O 7971MM | 35154633 |  |  | STS-POLE_BROK_REPL - 12N/O 3NE/O C/O 797 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.7078 | -120.658 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | C18 | 9045 | Y | 311 |  |  | 2021-04-01 07:00 | 2021-04-01 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100091030 | RELW OH PRI CLR JPOL REMT SWRK ESTR FMOB TER2 PRTO FSRP | Pole | 2020-06-26 | 2020-08-21 | COMP | 2020-06-26 | [16 empty] | 2019-06-05 | 2020-06-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | CALENG |  | 152101101 | 21771.18 | 2731.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | BLAIRSDEN-GRAEAGLE | Grass Valley |  |  | OPEN | 117403581 | POLE_BROK_REPL - 14N/O 3NE/O C/O 7971MM | 35154655 |  |  | STS-POLE_BROK_REPL - 14N/O 3NE/O C/O 797 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.7097 | -120.6572 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | C18 | 9045 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.8 | 41.8 |  |  | 0.5 | 41.3 | 41.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100091032 | RELW OH PRI CLR JPOL REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-07-14 | 2020-08-21 | COMP | 2020-07-14 | [16 empty] | 2019-06-05 | 2020-06-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | CALENG |  | 152101101 | 30929.03 | 2742.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | CALPINE | Grass Valley |  |  | OPEN | 117400308 | POLE_BROK_REPL - #12 ON LINE N/O CO#7933 | 35163724 |  |  | STS-POLE_BROK_REPL - #12 ON LINE N/O CO# | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.6948 | -120.6537 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | C19 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.7 | 31.7 |  |  | 0 | 31.7 | 31.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100088319 | RELW OH PRI CLR JPOL REMT NOAC ESTR FMOB TER2 FSRP PRTO | Pole | 2020-10-02 | 2020-12-10 | COMP | 2020-10-02 | [16 empty] | 2019-06-05 | 2020-06-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152101101 | 25532.84 | 5897.6 | 1383 | 1383 | 1383 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | CALPINE | Grass Valley |  |  | COMP | 117341623 | POLE_BROK_REPL - 322 PATRICA LN CALPINE | 35133899 |  |  | STS-POLE_BROK_REPL - 322 PATRICA LN CALP | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2020-12-31 | No Action | 39.6164 | -120.5868 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | E2004 |  | Y | 311 |  |  | 2021-01-09 | 2021-01-09 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 42.7 | 42.7 |  |  | 4.75 | 41.7 | 41.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100086666 | RELW OH PRI COMP CLR JPOL RESD FIRE ESTR GO BTKA CCNT FMOB TER2 PRTO | Pole | 2020-03-05 | 2020-05-08 | COMP | 2020-03-05 | COMP | 2021-01-19 | 2020-01-10 | 2020-01-10 | [11 empty] | 2021-01-19 | 2021-01-09 | 2020-05-29 |  | 2020-05-29 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 15347.18 | 37059.6 | 9949.7 | 9816.4 | 9816.4 | 54.3 |  | 54.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | CALPINE | Grass Valley |  |  | OPEN | 117279939 | POLE_DECA_REPL - #1E ON LINE @ R/O 306 O | 35133815 |  |  | STS-POLE_DECA_REPL - #1E ON LINE @ R/O 3 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5696 | -120.6145 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F2001 | 1731 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100105486 | RELW OH PRI PGEA CLR RESD REMT FIRE ESTR PRTO BTKA FMOB TER2 | Pole | 2020-06-22 | 2020-08-22 | COMP | 2020-06-22 | [16 empty] | 2019-05-20 | 2020-05-20 |  | 2020-05-20 | 2021 CBP Plan | 2020-05-31 | PIKEENG |  | 152101101 | 17689.57 | 2865.9 |  |  |  | 701.4 |  | 701.4 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | CALPINE | Grass Valley |  |  | OPEN | 117340517 | POLE_DECA_REPL - 11SW/O C/O 30317 AT GOL | 35133897 |  |  | STS-POLE_DECA_REPL - 11SW/O C/O 30317 AT | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.6147 | -120.5985 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | E20 |  | Y | 311 |  |  | 2021-08-24 07:00 | 2021-08-24 16:00 | Reserved | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100090176 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-01-22 | 2020-02-24 | COMP | 2020-01-22 | [16 empty] | 2019-05-29 | 2020-05-29 |  | 2020-05-29 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 23797.7 | 22321.3 | 18262.7 | 15122.8 | 15122.8 | 953.6 |  | 953.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | CALPINE | Grass Valley |  |  | OPEN | 117340523 | POLE_BROK_REPL - 3N/O C/O 30317 AT GOLD | 35133898 |  |  | STS-POLE_BROK_REPL - 3N/O C/O 30317 AT G | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.6196 | -120.5945 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | E20 |  | Y | 311 |  |  | 2021-04-01 07:00 | 2021-04-01 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100103962 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-04-30 | 2020-08-25 | COMP | 2020-03-02 | [16 empty] | 2019-05-29 | 2020-05-29 |  | 2020-05-29 | 2021 CBP Plan | 2020-01-09 | PIKEENG |  | 152101101 | 16451.9 | 1514.6 |  |  |  | 1115.1 |  | 1115.1 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | CAMERON PARK | Placerville |  |  | OPEN | 117699601 | POLE_BROK_REPL - R/O 3911 ARCHWOOD RD. C | 35218786 |  |  | B3 - STS-POLE_BROK_REPL - R/O 3911 ARCHW | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6609 | -120.9917 |  | TIER 2 | 435 | 15365-2108, SHINGLE SPRINGS | J3716 | 13751 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101375624 | OH SEC TMAN JPOL MINR RESD GO REAR PROG TER2 RELW | Pole | 2020-12-29 | 2021-01-05 | COMP | 2020-12-29 | [16 empty] | 2019-08-01 | 2019-11-01 |  | 2019-11-01 | B tag clean up 12/7/2020 |  | Auburn |  | 153652108 | [9 empty] | Y | Not Assigned 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-12-07
North | SI | CAMINO | Placerville |  |  | OPEN | 110655587 | POLE_DECA_REPL - 2700 DOGWOOD LN CAMINO | 35148135 |  |  | STS-POLE_DECA_REPL - 2700 DOGWOOD LN CAM | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.7505 | -120.6903 |  | TIER 2 | 81 | 15366-1104, APPLE HILL | H4413 | F20849 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 62.3 | 62.3 |  |  | 0 | 62.3 | 62.3 |  |  | EC | F | Pole | Decayed/Rotten | Replace |  | 101401221 | RELW OH PRI INSP JPOL MINR RESD GO REAR TER2 | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2015-09-06 | 2020-09-06 | 2020-09-20 | 2020-09-20 | 2021 CBP Plan | 2020-10-31 | QUES |  | 153661104 | 30196.39 | 383.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | CAMINO | Placerville |  |  | OPEN | 116685723 | POLE_DECA_REPL - 2370 APPLE TREE LN.CAMI | 35091575 |  |  | STS-POLE_DECA_REPL - 2370 APPLE TREE LN. | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.7564 | -120.673 |  | TIER 2 | 81 | 15366-1104, APPLE HILL | H44 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101417320 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-08 | 2020-03-08 |  | 2020-03-08 | 2021 CBP Plan | 2020-10-31 | QUES |  | 153661104 | 1 | 257.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | CAMINO | Placerville |  |  | OPEN | 116714096 | POLE_DECA_REPL - 1P N/O 3211 RIO VISTA W | 35148137 |  |  | STS-POLE_DECA_REPL - 1P N/O 3211 RIO VIS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 38.7692 | -120.723 |  | TIER 2 | 81 | 15366-1104, APPLE HILL | H43 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.4 | 16.4 |  |  | 0 | 16.4 | 16.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101400886 | RELW OH PRI JAR PROG FMOB TER2 PRTO | Pole | 2020-08-31 |  | COMP | 2020-08-31 | [16 empty] | 2019-03-12 | 2020-03-12 |  | 2020-03-12 | 2021 CBP Plan | 2020-10-31 | QUES |  | 153661104 | 8313 | 1262.2 | 1216.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | CAMINO | Placerville |  |  | OPEN | 116811721 | POLE_BROK_REPL - 3705 CARSON RD. CAMINO | 35215454 |  |  | STS-POLE_BROK_REPL - 3705 CARSON RD. CAM | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.7408 | -120.6924 |  | TIER 2 | 248 | 15366-1103, APPLE HILL | H4418 | 11035 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101400975 | RELW OH PRI CLR JPOL PUBL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-04-01 | 2021-04-01 | 2021 CBP Plan | 2021-03-31 | EEI |  | 153661103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | CAMINO | Placerville |  |  | OPEN | 116848775 | POLE_BROK_REPL - 3079 MEYERS RD. CAMINO | 35148180 |  |  | STS-POLE_BROK_REPL - 3079 MEYERS RD.CAMI | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 38.743 | -120.6587 |  | TIER 2 | 81 | 15366-1104, APPLE HILL | H4517 | 1441 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51.6 | 51.6 |  |  | 0 | 51.6 | 51.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101405127 | RELW OH PRI TRAF CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO RTRN | Pole | 2020-11-18 |  | COMP | 2020-11-18 |  |  | 2021-02-18 | 2021-02-18 | [12 empty] | 2019-03-27 | 2020-03-27 |  | 2020-03-27 | 2021 CBP Plan | 2020-12-31 | QUES |  | 153661104 | 39142.28 | 25482.6 | 1172.7 | 1172.7 | 1172.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | CAMINO | Placerville |  |  | OPEN | 118197144 | POLE_DECA_REPL - 2058 CABLE RD,CAMINO CA | 35189453 |  |  | STS-REPL POLE:2058 CABLE RD,CAMINO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 38.7537 | -120.6564 |  | TIER 2 | 81 | 15366-1104, APPLE HILL | H4512 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.3 | 14.3 |  |  | 0 | 14.3 | 14.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101417607 | RELW OH TNT TER2 | Pole | 2021-01-08 | 2021-01-08 | COMP | 2020-10-06 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-10-15 | 2020-10-15 |  | 2020-10-15 | 2021 CBP Plan | 2020-11-15 | TRC |  | 153661104 | 8434.44 | 1289.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | CAMINO | Placerville |  |  | COMP | 116682706 | POLE_BROK_REPL - 2260 LARSEN DR.CAMINO95 | 35091530 |  |  | STS-POLE_BROK_REPL - 2260 LARSEN DR.CAMI | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7547 | -120.6746 |  | TIER 2 | 81 | 15366-1104, APPLE HILL | H44 | 10893 | Y | 311 |  |  | 2021-02-08 07:00 | 2021-02-08 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 6 | 40.8 | 40.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101402259 | RELW OH PRI COMP ESTR RTRN CCNT FMOB TER2 PRTO | Pole | 2020-05-04 | 2020-06-30 | COMP | 2020-05-04 | COMP | 2021-02-08 | 2019-05-08 | 2019-05-08 | [11 empty] | 2021-02-11 | 2021-02-08 | 2020-03-07 |  | 2020-03-07 | circuit based plan 2.14 | 2020-01-31 | QUES |  | 153661104 | 28910.1 | 9742.3 | 4376.4 | 2455 | 2455 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | CAMINO | Placerville |  |  | COMP | 116692536 | POLE_BROK_REPL - 2/P/W/O/SER.P AT HOUSE | 35086871 |  |  | STS-POLE_BROK_REPL - 2/P/W/O/SER.P AT HO | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7492 | -120.6797 |  | TIER 2 | 81 | 15366-1104, APPLE HILL | H44 |  | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 56.1 | 56.1 |  |  | 0 | 56.1 | 56.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101418714 | SEC RELW OH COMP ESTR GO CCNT FMOB TER2 PRTO | Pole | 2020-09-14 | 2020-10-27 | COMP | 2020-09-09 | COMP | 2021-02-10 | [13 empty] | 2021-02-12 | 2021-02-10 | 2019-10-10 |  | 2019-10-10 | 2021 CBP Plan | 2020-10-31 | QUES |  | 153661104 | 7840.22 | 3691.2 | 3645.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | CAMINO | Placerville |  |  | COMP | 117937998 | REPL POLE:C/O DUTCHMAN DR. HAPPY HOLLOW | 35189416 |  |  | STS-REPL POLE:C/O DUTCHMAN DR. HAPPY HOL | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7453 | -120.6745 |  | TIER 2 | 81 | 15366-1104, APPLE HILL | H44 |  | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 45.1 | 42.7 | 2.4 |  | 0.75 | 44.35 | 41.95 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101402113 | RELW COMP CCNT TER2 OH TNT JPOL | Pole | 2020-10-13 | 2020-12-02 | COMP | 2020-10-13 | COMP | 2021-02-11 | [13 empty] | 2021-02-16 | 2021-02-11 | 2020-07-01 |  | 2020-07-01 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153661104 | 10920.16 | 3072 | 2737.2 | [5 empty] | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | CAMINO | Placerville |  |  | OPEN | 116683008 | POLE_BROK_REPL - TRANS.P OFF OFF GUIDE P | 35091533 |  |  | STS-POLE_BROK_REPL - TRANS.P OFF OFF GUI | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7545 | -120.6714 |  | TIER 2 | 81 | 15366-1104, APPLE HILL | H4511 | 10893 | Y | 311 |  |  | 2021-03-24 07:00 | 2021-03-24 16:00 | Dispatched | CLICK | [6 empty] | 87.1 | 87.1 |  |  | 19.5 | 67.6 | 67.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101406937 | RELW OH TER2 PRI ESTR FMOB PRTO | Pole | 2020-04-16 | 2020-06-12 | COMP | 2020-04-16 | [16 empty] | 2019-03-07 | 2020-03-07 |  | 2020-03-07 | circuit based plan 2.14 | 2020-01-31 | QUES |  | 153661104 | 33117.72 | 29905.1 | 2584 | 2431.7 | 2431.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | CAMINO | Placerville |  |  | OPEN | 116706002 | POLE_DECA_REPL - 1P N/O 1P S/O 3141 HASS | 35148136 |  |  | STS-POLE_DECA_REPL - 1P N/O 1P S/O 3141 | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7614 | -120.7298 |  | TIER 2 | 81 | 15366-1104, APPLE HILL | H4308 | 1451 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-22 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101400492 | RELW OH PRI JPOL GO FMOB TER2 PRTO | Pole | 2020-09-15 | 2020-11-02 | COMP | 2020-09-10 | [16 empty] | 2019-03-10 | 2020-03-10 |  | 2020-03-10 | 2021 CBP Plan | 2020-10-31 | QUES |  | 153661104 | 24503.84 | 6251.8 | 5843.6 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | CAMINO | Placerville |  |  | OPEN | 116812657 | POLE_DECA_REPL - R/O/2815 SENIC CIRCLE C | 35169948 |  |  | STS-POLE_DECA_REPL - R/O/2815 SENIC CIRC | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-02-13 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7427 | -120.6897 |  | TIER 2 | 248 | 15366-1103, APPLE HILL | H4418 | 9695 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 42 | 42 |  |  | 0.25 | 41.75 | 41.75 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101419634 | RELW OH PRI CLR JPOL RESD ESTR PRTO REAR FMOB TER2 FSRP | Pole | 2020-06-05 | 2020-06-05 | COMP | 2020-04-23 | [16 empty] | 2019-03-22 | 2020-03-22 | 2021-03-13 | 2021-03-13 | B Tag Assignment 3.30.20 |  | W. Sac |  | 153661103 | 27362.46 | 13550.4 | [7 empty] | N | 11/2 in MPP Import File | N | Access/Customer Issue - Customer won't let crews access | Y | 2020-03-30
North | SI | CAMINO | Placerville |  |  | OPEN | 116821242 | POLE_DECA_REPL - 2/P/E/O/P/A/F/2956 SNOW | 35188261 |  |  | STS-POLE_DECA_REPL - 2/P/E/O/P/A/F/2956 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7365 | -120.6748 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | H4425 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 13.6 | 13.6 |  |  | 0 | 13.6 | 13.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101400043 | RELW OH SERV CLR JPOL RESD ESTR BTKA REAR FMOB TER2 PRTO | Pole | 2020-09-24 | 2020-09-24 | COMP | 2020-09-24 | [16 empty] | 2019-03-24 | 2020-03-24 |  | 2020-03-24 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | CAMINO | Placerville |  |  | OPEN | 116827326 | POLE_DECA_REPL - 1P E/O 2801 GARDELLA LN | 35148138 |  |  | STS-POLE_DECA_REPL - 1P E/O 2801 GARDELL | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.745 | -120.6652 |  | TIER 2 | 81 | 15366-1104, APPLE HILL | H4516 | 1471 | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | [6 empty] | 42 | 41.8 | 0.2 |  | 0 | 42 | 41.8 | 0.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101404907 | RELW OH PRI CLR JPOL RESD ESTR REAR FMOB TER2 PRTO | Pole | 2020-09-16 | 2020-11-02 | COMP | 2020-09-11 | [16 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | 2021 CBP Plan | 2020-10-31 | QUES |  | 153661104 | 23827.43 | 5513.6 | 4982.2 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | CAMINO | Placerville |  |  | OPEN | 117938002 | POLE_DECA_REPL - A/F C/O AUDUBON DR AND | 35189428 |  |  | STS-REPL POLE:A/F C/O AUDUBON DR AND KIN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7545 | -120.6977 |  | TIER 2 | 81 | 15366-1104, APPLE HILL | H4412 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.1 | 31.7 | 2.4 |  | 0 | 34.1 | 31.7 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101418308 | RELW OH TNT JPOL TER2 | Pole | 2021-01-11 | 2021-01-11 | COMP | 2020-10-14 |  |  | 2021-01-11 | 2021-01-08 | [12 empty] | 2019-06-26 | 2020-06-26 |  | 2020-06-26 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153661104 | 19457.79 | 935.8 | 448.6 | 448.6 | 448.6 |  |  |  | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | CAMINO | Placerville |  |  | OPEN | 119898101 | POLE_BROK_REPL - IN FRONT OF 2746 KINGFI | 35207263 |  |  | B3 STS-POLE_BROK_REPL - IN FRONT OF 2746 | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-12-16 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7487 | -120.6979 |  | TIER 2 | 81 | 15366-1104, APPLE HILL | H4417 | 18545 | Y | 311 |  |  | 2021-03-01 07:00 | 2021-03-01 16:00 | Dispatched | CLICK | [6 empty] | 40.2 | 40.2 |  |  | 0 | 40.2 | 40.2 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101401493 | RELW OH PRI SERV TMAN JPOL BTKA USA TER2 ESTR | Pole | 2020-12-14 | 2020-12-15 | COMP | 2020-11-19 | [16 empty] | 2020-10-13 | 2021-01-13 |  | 2021-01-13 | B tag clean up 10/18/2020 |  | Auburn |  | 153661104 | 17430.79 | 584.9 | [7 empty] | N | 11/2 in MPP Import File | N |  | Y | 2020-10-18
North | SI | CAMINO | Placerville |  |  | OPEN | 116957576 | POLE_DECA_REPL - 1E/O R/O 5010 PONY EXPR | 35087239 |  |  | STS-POLE_DECA_REPL - 1E/O R/O 5010 PONY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7439 | -120.6341 |  | TIER 2 | 81 | 15366-1104, APPLE HILL | H4520 | 7029 | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 47.2 | 47.2 |  |  | 0 | 47.2 | 47.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101406397 | RELW OH PRI CLR JPOL ESTR BTKA REAR FMOB TER2 PRTO | Pole | 2021-02-10 | 2021-02-10 | COMP | 2021-02-10 | [16 empty] | 2019-04-04 | 2019-10-04 |  | 2019-10-04 | 2021 CBP Plan | 2020-10-31 | QUES |  | 153661104 | 19243.91 | 1020.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | CAMINO | Placerville |  |  | OPEN | 116966783 | POLE_BROK_REPL - 5 E/O 4949 EIGHT MILE R | 35087260 |  |  | STS-POLE_BROK_REPL - 5 E/O 4949 EIGHT MI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.742 | -120.6334 |  | TIER 2 | 81 | 15366-1104, APPLE HILL | H4520 | 1525 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 53.9 | 53.9 |  |  | 0 | 53.9 | 53.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101406024 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA REAR FMOB TER2 PRTO | Pole | 2020-10-21 | 2020-12-31 | COMP | 2020-10-21 | [16 empty] | 2019-04-05 | 2019-10-05 |  | 2019-10-05 | 2021 CBP Plan | 2020-10-31 | QUES |  | 153661104 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | COLFAX | Auburn |  |  | OPEN | 116617942 | POLE_BROK_REPL - #3 ON LINE E/O 730 BRID | 35091008 |  |  | STS-POLE_BROK_REPL - #3 ON LINE E/O 730 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0322 | -120.9942 |  | TIER 2 | 999 | 15249-1102, WEIMAR | R1010 |  | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-05 16:00 | Scheduled | CLICK | [6 empty] | 25.1 | 25.1 |  |  | 1 | 25 | 25 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102354095 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2019-10-28 | 2019-11-19 | COMP | 2019-10-28 | [16 empty] | 2019-02-28 | 2020-02-28 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 50346 | 2019-12-31 | QUES |  | 152491102 | 11147.19 | 1785.5 | 1785.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-02-19
North | SI | COLFAX | Auburn |  |  | OPEN | 116634083 | POLE_BROK_REPL - 970 COYOTE MOUNTAIN RDC | 35091676 |  |  | STS-POLE_BROK_REPL - 970 COYOTE MOUNTAIN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0353 | -121.0031 |  | TIER 2 | 999 | 15249-1102, WEIMAR | R1009 | 2021 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51.3 | 51.3 |  |  | 0 | 51.3 | 51.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100069417 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2019-10-21 | 2019-12-24 | COMP | 2019-10-21 | [16 empty] | 2019-03-04 | 2020-03-04 | 2024-03-02 | 2024-03-02 | Per DOT Approved Request 50347 | 2020-01-31 | QUES |  | 152491102 | 23573.11 | 549.3 |  |  |  | 25.6 |  | 25.6 |  | N | MPP File Only | N |  | Y | 2021-02-19
North | SI | COLFAX | Auburn |  |  | OPEN | 116709109 | POLE_BROK_REPL - 166 BARTON DR COLFAX | 35191025 |  |  |  | UNSC | UNSC | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 39.0122 | -120.9855 |  | TIER 2 | 420 | 15249-1101, WEIMAR | R1116 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 25.9 | 25.9 |  |  | 0 | 25.9 | 25.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100023723 | OH PRI INSP CLR JPOL RESD REMT BTKA PRTO RELW FMOB TER2 | Pole | 2020-09-08 | 2021-02-19 | COMP | 2020-09-08 |  |  | 2021-02-19 | 2021-02-19 | [12 empty] | 2019-03-11 | 2020-03-11 |  | 2020-03-11 | Work Plan Reconcilation (B-Tags) |  | Auburn |  | 152491101 | 16704.87 | 5780.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-07-21
North | SI | COLFAX | Auburn |  |  | OPEN | 117164776 | POLE_DECA_REPL - 1505 HILLCREST BLVD. CO | 35202495 |  |  | STS-POLE_DECA_REPL - 1505 HILLCREST BLVD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 39.1066 | -120.973 |  | TIER 2 | 304 | 15243-1101, SHADY GLEN | P1118 | 30269 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48.1 | 44.3 | 3.8 |  | 0 | 48.1 | 44.3 | 3.8 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100015679 | RELW OH PRI JPOL FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-11 |  | COMP | 2021-01-11 | [16 empty] | 2019-05-05 | 2020-05-05 | 2020-08-15 | 2020-08-15 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152431101 | 21788.7 | 883.7 | -1231.8 | 1135.7 | 1135.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | COLFAX | Auburn |  |  | OPEN | 117167869 | POLE_BROK_REPL - 6W/O 24145 TOKAYANA WY | 35202498 |  |  | STS-POLE_BROK_REPL - 6W/O 24145 TOKAYANA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.0969 | -120.969 |  | TIER 2 | 304 | 15243-1101, SHADY GLEN | P1123 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.9 | 27.9 |  |  | 0 | 27.9 | 27.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100015731 | RELW OH PRI JPOL RESD REMT ESTR GO BTKA REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-21 | 2021-01-19 | COMP | 2021-01-19 | [16 empty] | 2019-05-06 | 2020-05-06 | 2020-10-27 | 2020-10-27 | 2021 CBP Plan | 2021-02-28 | TRC |  | 152431101 | 24465.14 |  | -210 | 1371 | 1371 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | COLFAX | Auburn |  |  | OPEN | 117167884 | POLE_DECA_REPL - #1 ON LINE N/O 22140 PL | 35215343 |  |  | STS-POLE_DECA_REPL - #1 ON LINE N/O 2214 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.0636 | -120.9807 |  | TIER 2 | 420 | 15249-1101, WEIMAR | Q1117 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100020580 | RELW OH PRI CLR JPOL RESD REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-06 | 2020-05-06 | 2021-04-03 | 2021-04-03 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152491101 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | COLFAX | Auburn |  |  | OPEN | 117169726 | POLE_BROK_REPL - 1140 PINECROFT RD COLFA | 35202502 |  |  | STS-POLE_BROK_REPL - 1140 PINECROFT RD C | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 39.1008 | -120.9635 |  | TIER 2 | 304 | 15243-1101, SHADY GLEN | P1119 | 41527 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100017665 | RELW OH PRI CLR RESD FIRE ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-06 | 2020-05-06 | 2020-10-20 | 2020-10-20 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152431101 | 1 |  | -210 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | COLFAX | Auburn |  |  | OPEN | 117249103 | POLE_BROK_REPL - 1N/O 545 WASHINGTON IRV | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-31 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 39.0576 | -120.96 |  | TIER 2 | 420 | 15249-1101, WEIMAR | Q1119 | 30847 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100018671 | REGW OH PRI CLR JPOL RESD GO REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-05-16 | 2020-05-16 | 2024-05-14 | 2024-05-14 | Per DOT Approved Request 50353 |  | UNASSIGNED |  | 152491101 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | SI | COLFAX | Auburn |  |  | OPEN | 117255851 | POLE_BROK_REPL - 407 WASHINGTON IRVING D | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-31 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 39.0574 | -120.9617 |  | TIER 2 | 420 | 15249-1101, WEIMAR | Q1119 | 30847 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100018647 | REGW OH PRI CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-05-17 | 2020-05-17 | 2024-05-15 | 2024-05-15 | Per DOT Approved Request 50354 |  | UNASSIGNED |  | 152491101 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | SI | COLFAX | Auburn |  |  | OPEN | 117935430 | POLE_BROK_REPL - 1W/O HOUSE 1125 TAWNY L | 35215661 |  |  | STS-POLE_BROK_REPL - 1W/O HOUSE 1125 TAW | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.0661 | -120.9853 |  | TIER 2 | 420 | 15249-1101, WEIMAR | Q11 | 6139 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100104077 | INSP RELW OH PRI CLR REMT FIRE NOAC ESTR REAR PROG FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-10-01 | 2020-10-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152491101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | COLFAX | Auburn |  |  | COMP | 116628968 | POLE_DECA_REPL - 2 E/O 2024 PEACEFUL VAL | 35091529 |  |  | STS-POLE_DECA_REPL - 2 E/O 2024 PEACEFUL | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.0449 | -121.0156 |  | TIER 2 | 999 | 15249-1102, WEIMAR | R10 |  | Y | 311 |  |  | 2021-01-25 | 2021-01-25 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100023793 | RELW OH PRI COMP CLR REMT ESTR BTKA CCNT FMOB TER2 PRTO FSRP | Pole | 2020-04-08 | 2020-05-16 | COMP | 2020-04-08 | COMP | 2021-01-25 | [13 empty] | 2021-01-27 | 2021-01-25 | 2020-03-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-31 | QUES |  | 152491102 | 5423.32 | 1750.9 | 1750.8 | 1205 | 1205 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | COLFAX | Auburn |  |  | OPEN | 116617526 | POLE_BROK_REPL - 880 BRIDAL PATH RDCOLFA | 35090968 |  |  | STS-POLE_BROK_REPL - 880 BRIDAL PATH RDC | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0364 | -120.9978 |  | TIER 2 | 999 | 15249-1102, WEIMAR | R1010 | 6111 | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 42 | 41.8 | 0.2 |  | 1 | 41 | 40.8 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100024579 | RELW OH PRI CLR JPOL REMT FIRE ESTR FMOB TER2 PRTO FSRP | Pole | 2020-01-23 | 2020-02-07 | COMP | 2020-01-23 | [16 empty] | 2019-02-27 | 2020-02-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-12-31 | QUES |  | 152491102 | 18812.73 | 3661.6 | 3260.8 | 1376.1 | 1376.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | COLFAX | Auburn |  |  | OPEN | 116626965 | POLE_BROK_REPL - AT 20870 INDIAN DR COLF | 35090130 |  |  | STS-POLE_BROK_REPL - AT 20870 INDIAN DRC | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0413 | -120.9922 |  | TIER 2 | 420 | 15249-1101, WEIMAR | R1005 | 6145 | Y | 311 |  |  | 2021-02-27 07:00 | 2021-02-27 16:00 | Dispatched | CLICK | [6 empty] | 43 | 41.8 | 1.2 |  | 0 | 43 | 41.8 | 1.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100026054 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-01-06 | 2020-02-07 | COMP | 2020-01-06 | [16 empty] | 2019-03-02 | 2020-03-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-31 | QUES |  | 152491101 | 17555.89 | 3405.9 | 3405.9 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | COLFAX | Auburn |  |  | OPEN | 116628394 | POLE_DECA_REPL - 20881 PLACER HILLS RD C | 35091481 |  |  | STS-POLE_DECA_REPL - 20881 PLACER HILLS | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0418 | -120.9981 |  | TIER 2 | 999 | 15249-1102, WEIMAR | R1005 |  | Y | 311 |  |  | 2021-04-12 07:00 | 2021-04-12 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0.75 | 41.05 | 41.05 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100109427 | RELW OH PRI CLR JPOL RESD REMT FLAG ESTR PRTO BTKA FMOB TER2 FSRP | Pole | 2020-04-22 | 2020-06-22 | COMP | 2020-02-25 |  |  | 2019-05-13 | 2019-05-14 | [12 empty] | 2019-03-03 | 2020-03-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-31 | QUES |  | 152491102 | 14860.5 | 323.2 | 130.2 | 111.2 | 111.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | COLFAX | Auburn |  |  | OPEN | 116631612 | POLE_BROK_REPL - A/F 19350 BLACK OAK RD | 35091303 |  |  | STS-POLE_BROK_REPL - A/F 19350 BLACK OAK | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0314 | -121.0027 |  | TIER 2 | 999 | 15249-1102, WEIMAR | R1009 | 6113 | Y | 311 |  |  | 2021-03-20 07:00 | 2021-03-20 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100024558 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2019-11-18 | 2019-12-06 | COMP | 2019-11-18 |  |  | 2019-05-13 | 2019-05-14 | [12 empty] | 2019-03-04 | 2020-03-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-01-31 | QUES |  | 152491102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | COLFAX | Auburn |  |  | OPEN | 118976960 | POLE_BROK_REPL - 2S/O 22460 CANYON WY CO | 35181267 |  |  | B3 STS-POLE_BROK_REPL - 2S/O 22460 CANYO | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0633 | -120.9555 |  | TIER 2 | 420 | 15249-1101, WEIMAR | Q1120 | 30771 | Y | 311 |  |  | 2021-03-23 07:00 | 2021-03-23 16:00 | Dispatched | CLICK | [6 empty] | 52.8 | 52.8 |  |  | 7 | 51.8 | 51.8 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100019817 | RELW OH PRI NOAC CREW CLR REMT ESTR RTRN USA PROG FMOB TER2 | Pole | 2020-06-26 | 2020-07-07 | COMP | 2020-06-26 | [16 empty] | 2020-05-02 | 2020-08-02 |  | 2020-08-02 | B-Tag Addition 06.24.20 |  | Auburn |  | 152491101 | 31946.06 | 28978.6 | 2580.1 | 2561.1 | 2561.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-29
North | SI | COLFAX | Auburn |  |  | OPEN | 120041393 | POLE_BROK_REPL - 845 NEW VALLEY RD #2 N/ | 35214175 |  |  | B2 - STS-POLE_BROK_REPL - 845 NEW VALLEY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-08 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0516 | -120.9944 |  | TIER 2 | 999 | 15249-1102, WEIMAR | Q1025 | 9505 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 47.8 | 39.1 | 8.7 |  | 0 | 47.8 | 39.1 | 8.7 |  | EC | B | Pole | Broken/Damaged | Replace |  | 102354041 | RELW OH ESTR TER2 | Pole | 2020-12-23 | 2020-12-30 | COMP | 2020-12-23 | [16 empty] | 2020-11-05 | 2021-02-05 |  | 2021-02-05 | B tag clean up 11/19/2020 |  | Auburn |  | 152491102 | 23521.27 | 220.8 | [7 empty] | N | Pulled from MPP Import File | N |  | Y | 2020-11-19
North | SI | COLFAX | Auburn |  |  | OPEN | 120218220 | POLE_BROK_REPL - 24281 TOKAYANA WAY COLF | 35222001 |  |  | B2 - STS-POLE_BROK_REPL - 24281 TOKAYANA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-11 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0976 | -120.9631 |  | TIER 2 | 304 | 15243-1101, SHADY GLEN | P1124 | 41527 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.2 | 18.2 |  |  | 0 | 18.2 | 18.2 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100089274 | RELW OH ESTR TER2 | Pole | 2021-01-12 | 2021-01-14 | COMP | 2021-01-12 |  |  | 2021-01-14 | 2021-01-14 | [12 empty] | 2020-12-08 | 2021-02-08 |  | 2021-02-08 | B tag clean up 12/21/2020 |  | Auburn |  | 152431101 | [9 empty] | N | Pulled from MPP Import File | N |  | Y | 2020-12-21
North | SI | COLFAX | Auburn |  |  | OPEN | 116617837 | POLE_DECA_REPL - #1N 775 BRIDAL PATH RDC | 35090985 |  |  | STS-POLE_DECA_REPL - #1N 775 BRIDAL PATH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0354 | -120.9984 |  | TIER 2 | 999 | 15249-1102, WEIMAR | R1010 | 40965 | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-05 16:00 | Scheduled | CLICK | [6 empty] | 25.1 | 25.1 |  |  | 0.5 | 25 | 25 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100024568 | RELW OH PRI CLR JPOL REMT FIRE ESTR FMOB TER2 PRTO FSRP | Pole | 2019-10-23 | 2019-12-19 | COMP | 2019-10-23 | [16 empty] | 2019-02-28 | 2020-02-28 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 27550 | 2019-12-31 | QUES |  | 152491102 | 13526.18 | 3838.8 | 3447.3 | [5 empty] | FRMMA/WMPMA - Electric | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-11
North | SI | COLFAX | Auburn |  |  | OPEN | 116617845 | POLE_BROK_REPL - #7 ON LINE E/O 730 BRID | 35090990 |  |  | STS-POLE_BROK_REPL - #7 ON LINE E/O 730 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0337 | -120.9927 |  | TIER 2 | 999 | 15249-1102, WEIMAR | R1010 | 30387 | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-05 16:00 | Scheduled | CLICK | [6 empty] | 53.1 | 53.1 |  |  | 0.5 | 53 | 53 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102354100 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2019-11-05 | 2019-11-22 | COMP | 2019-11-05 | [16 empty] | 2019-02-28 | 2020-02-28 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 27551 | 2019-12-31 | QUES |  | 152491102 | 19523.46 | 2865.7 | 2865.7 | [5 empty] | FRMMA/WMPMA - Electric | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-11
North | SI | COLFAX | Auburn |  |  | OPEN | 116617857 | POLE_BROK_REPL - #5 ON LINE E/O 730 BRID | 35090997 |  |  | STS-POLE_BROK_REPL - #5 ON LINE E/O 730 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0329 | -120.993 |  | TIER 2 | 999 | 15249-1102, WEIMAR | R1010 |  | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-05 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 23.1 | 23.1 |  |  | 0 | 23.1 | 23.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102354098 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-03-02 | 2020-04-27 | COMP | 2020-03-02 | [16 empty] | 2019-02-28 | 2020-02-28 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 27552 | 2019-12-31 | QUES |  | 152491102 | 11871.78 | 3064.5 | 3064.5 | [5 empty] | FRMMA/WMPMA - Electric | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-11
North | SI | COLFAX | Auburn |  |  | OPEN | 116618055 | POLE_BROK_REPL - A/F 730 BRIDAL PATH RDC | 35091020 |  |  | STS-POLE_BROK_REPL - A/F 730 BRIDAL PATH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0324 | -120.9966 |  | TIER 2 | 999 | 15249-1102, WEIMAR | R1010 | 30387 | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-05 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 42.9 | 42.9 |  |  | 0.5 | 42.8 | 42.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100024576 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-01-16 | 2020-10-23 | COMP | 2019-11-19 | INPR | [15 empty] | 2019-02-28 | 2020-02-28 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 27553 | 2019-12-31 | QUES |  | 152491102 | 17187.52 | 2046.9 | 1994.5 |  |  | 10 |  | 10 | FRMMA/WMPMA - Electric | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-11
North | SI | COLFAX | Auburn |  |  | OPEN | 116631124 | POLE_BROK_REPL - AT 19740 PLACER HILLS R | 35078637 |  |  | STS-POLE_BROK_REPL - AT 19740 PLACER HIL | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0343 | -121.0042 |  | TIER 2 | 999 | 15249-1102, WEIMAR | R1009 |  | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 16.1 | 16.1 |  |  | 0 | 16.1 | 16.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100022269 | RELW OH SEC JPOL RESD FIRE ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-15 | 2020-12-15 | COMP | 2020-12-14 |  |  | 2020-12-15 | 2020-12-15 | [12 empty] | 2019-03-04 | 2019-09-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152491102 | 8359.88 | 940.3 | -673 | 922 | 922 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | COLFAX | Auburn |  |  | OPEN | 116683869 | POLE_BROK_REPL - AT 890 SWANSON LN COLFA | 35078704 |  |  | STS-POLE_BROK_REPL - AT 890 SWANSON LNCO | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.031 | -120.9567 |  | TIER 2 | 420 | 15249-1101, WEIMAR | R1110 | 33933 | Y | 311 |  |  | 2021-03-09 07:00 | 2021-03-09 16:00 | Scheduled | CLICK | [6 empty] | 33.9 | 33.9 |  |  | 0.5 | 33.8 | 33.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100024436 | PRI RELW OH CLR REMT FIRE NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-14 | 2021-01-20 | COMP | 2020-12-11 | [16 empty] | 2019-03-07 | 2019-09-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152491101 | 18095.47 | 2752.9 | 137.1 | -1710.8 | -1710.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | COLFAX | Auburn |  |  | OPEN | 116722473 | POLE_BROK_REPL - 3W/O HOUSE 600 MOONRISE | 35202146 |  |  | STS-POLE_BROK_REPL - 3W/O HOUSE 600 MOON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0857 | -120.9394 |  | TIER 2 | 304 | 15243-1101, SHADY GLEN | Q12 |  | Y | 311 |  |  | 2021-04-20 07:00 | 2021-04-20 16:00 | Scheduled | CLICK | [6 empty] | 21.1 | 21.1 |  |  | 0.5 | 21 | 21 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100110794 | OH PRI CLR MINR RESD REMT TER2 RELW JAR GO BTKA FMOB PRTO FSRP | Pole | 2020-12-11 | 2021-01-20 | COMP | 2020-12-10 | [16 empty] | 2019-03-13 | 2020-03-13 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152431101 | 9758.44 | 2254.3 | 362.5 | -1710.8 | -1710.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | COLFAX | Auburn |  |  | OPEN | 116963193 | POLE_DECA_REPL - R/O 24380 GRAND VIEW AV | 35220578 |  |  | B1 - STS-POLE_DECA_REPL - R/O 24380 GRAN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-05-03 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0951 | -120.9421 |  | TIER 2 | 304 | 15243-1101, SHADY GLEN | P1221 | 30845 | Y | 311 |  |  | 2021-03-03 07:00 | 2021-03-03 16:00 | Scheduled | CLICK | [6 empty] | 13.1 | 13.1 |  |  | 0 | 13.1 | 13.1 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100016581 | RELW OH SEC PGEA INSP REMT ESTR REAR FMOB TER2 FSRP | Pole | 2020-12-31 | 2021-01-26 | COMP | 2020-12-31 | [16 empty] | 2019-04-05 | 2020-04-05 | 2021-05-31 | 2021-05-31 | B tag clean up 12/21/2020 |  | Auburn |  | 152431101 | 9810.91 | 552.4 | 552.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-12-21
North | SI | COLFAX | Auburn |  |  | OPEN | 117017258 | POLE_BROK_REPL - 1P/S/O C/O 33225 COLFAX | 35202207 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1265 | -120.9537 |  | TIER 2 | 215 | 15243-1102, SHADY GLEN | P1110 | 48894 | Y | 311 |  |  | 2021-04-08 07:00 | 2021-04-08 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 54.1 | 54.1 |  |  | 0 | 54.1 | 54.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103675985 | RELW OH PRI INSP CUST CLR RESD FIRE NOAC ESTR REAR FMOB TER2 FSRP | Pole | 2021-01-25 | 2021-02-01 | COMP | 2021-01-25 | [16 empty] | 2019-04-12 | 2020-04-12 | 2020-10-14 | 2020-10-14 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152431102 | 22453.68 | 129.6 | 129.6 | 1092 | 1092 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | COLFAX | Auburn |  |  | OPEN | 117068716 | POLE_DECA_REPL - R/O 234 COLFAX CEMETERY | 35202396 |  |  | STS-POLE_DECA_REPL - R/O 234 COLFAX CEME | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0985 | -120.9452 |  | TIER 2 | 304 | 15243-1101, SHADY GLEN | P1221 | 30845 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 45.1 | 45.1 |  |  | 0.5 | 45 | 45 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100015914 | RELW OH PRI PGEA INSP RESD REMT ESTR REAR FSRP FMOB TER2 | Pole | 2020-12-15 | 2020-12-15 | COMP | 2020-12-15 | [16 empty] | 2019-04-20 | 2020-04-20 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152431101 | 17979.39 | 2923.9 | 1185.4 | -381.1 | -381.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | COOL | Auburn |  |  | COMP | 117086790 | POLE_DECA_REPL - 1S/O 4320 HWY 49COOL956 | 35149985 |  |  | STS-POLE_DECA_REPL - 1S/O 4320 HWY 49COO | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8426 | -121.0151 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | V1013 | 1145 | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 13 | 40 | 40 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100056830 | RELW OH PRI COMP JPOL REMT ESTR REAR CCNT FMOB TER2 PRTO | Pole | 2020-04-16 | 2020-07-29 | COMP | 2020-04-16 | COMP | 2021-02-09 | [13 empty] | 2021-02-11 | 2021-02-09 | 2020-04-23 |  | 2020-04-23 | circuit based plan 2.14 | 2020-04-10 | PIKEENG |  | 152282101 | 9629.37 | 9481.3 | 6133.4 | 1862.4 | 1862.4 | 238.9 |  | 238.9 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | COOL | Auburn |  |  | COMP | 117116060 | POLE_DECA_REPL - 1S/O 3601 BIRD HAVEN LO | 35149667 |  |  | STS-POLE_DECA_REPL - 1S/O 3601 BIRD HAVE | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-11-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8659 | -121.0004 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | V1005 | 7497 | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 43 | 41.8 | 1.2 |  | 6 | 2 | 0.8 | 1.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100054753 | RELW PRI OH COMP JPOL REMT ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-04-13 | 2020-06-10 | COMP | 2020-04-13 | COMP | 2021-01-13 | [13 empty] | 2021-01-19 | 2021-01-13 | 2020-04-28 |  | 2020-04-28 | circuit based plan 2.14 | 2020-04-10 | PIKEENG |  | 152282101 | 21096.6 | 6228.2 | 4900.5 | 4448.2 | 4448.2 | 83.4 |  | 83.4 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | COOL | Auburn |  |  | COMP | 117304594 | POLE_BROK_REPL - 11N/O C/O HWY 49 AND AA | 35149706 |  |  | STS-POLE_BROK_REPL - 11N/O C/O HWY 49 AN | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-11-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8985 | -121.0164 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | U10 |  | Y | 311 |  |  | 2021-01-09 | 2021-01-09 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 43.5 | 43.5 |  |  | 13 | 42.5 | 42.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100049989 | RELW OH PRI COMP CLR JPOL REMT FIRE NOAC ESTR GO CCNT FMOB TER2 PRTO | Pole | 2020-04-21 | 2020-04-21 | COMP | 2020-04-21 | COMP | 2021-01-09 | [13 empty] | 2021-01-13 | 2021-01-09 | 2020-05-22 |  | 2020-05-22 | circuit based plan 2.14 | 2020-04-10 | PIKEENG |  | 152282101 | 24312.93 | 31893.8 | 25983.5 | 16241 | 16241 | 125.1 |  | 125.1 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | COOL | Auburn |  |  | COMP | 117304686 | POLE_BROK_REPL - 8N/O C/O AARON COOL DR | 35149709 |  |  | STS-POLE_BROK_REPL - 8N/O C/O AARON COOL | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-11-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8961 | -121.0163 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | U10 |  | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 43.5 | 43.5 |  |  | 0.5 | 43 | 43 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100049986 | RELW OH PRI COMP CLR JPOL REMT NOAC ESTR CCNT PRTO FMOB TER2 | Pole | 2020-04-15 | 2020-07-29 | COMP | 2020-04-15 | COMP | 2021-01-09 | [13 empty] | 2021-01-14 | 2021-01-09 | 2020-05-22 |  | 2020-05-22 | circuit based plan 2.14 | 2020-04-10 | PIKEENG |  | 152282101 | 13633.99 | 5138.9 | 543.3 | 410 | 410 | 166.8 |  | 166.8 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | COOL | Auburn |  |  | OPEN | 114849627 | POLE_BROK_REPL - 3276 TOMAHAWK RD COOL | 35106644 |  |  | STS-POLE_BROK_REPL - 3276 TOMAHAWK RD CO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8566 | -120.9885 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | V1106 | 3331 | Y | 311 |  |  | 2019-04-29 | 2019-04-29 | Completed | Order Operation | [6 empty] | 42.8 | 42.8 |  |  | 0 | 42.8 | 42.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100056644 | RELW OH PRI INSP JPOL REMT BTKA SCOP SCPA FMOB TER2 | Pole | 2019-07-24 | 2020-12-22 | COMP | 2019-07-23 | INPR |  | 2019-06-04 | 2019-06-04 | [12 empty] | 2018-08-02 | 2019-08-02 |  | 2019-08-02 | Q1 Work Plan |  | W. Sac |  | 152282101 | 18975.16 | 5387.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | COOL | Auburn |  |  | OPEN | 115076554 | POLE_DECA_REPL - 3785 Catecroft LnCool | 35069578 |  |  | STS-POLE_DECA_REPL - 3785 CATECROFT LNCO | UNSC | UNSC CONT SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8598 | -121.0222 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | V1002 | 5821 | Y | 311 |  |  |  |  | Returned | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 41.8 | 41.8 |  |  | 10 | 40.8 | 40.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100057483 | REGW OH PRI INSP JPOL RESD ESTR BTKA USA FMOB TER2 | Pole | 2019-03-27 | 2020-07-21 | COMP | 2019-03-27 | [16 empty] | 2018-10-21 | 2019-10-21 |  | 2019-10-21 | Q1 Work Plan | 2019-06-23 | CALENG |  | 152282101 | 8007.98 | 3176.9 |  |  |  | 515.2 |  | 515.2 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | COOL | Auburn |  |  | OPEN | 116767250 | POLE_BROK_REPL - 1SO 1901 SWEET WATER CT | 35150238 |  |  | STS-TRAN_CORR_REPL - 1SO 1901 SWEET WATE | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 38.9026 | -120.9792 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | U1107 | 30913 | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | [6 empty] | 41.6 | 41 | 0.6 |  | 1 | 40.6 | 40 | 0.6 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100046232 | RELW OH PRI JPOL RESD ESTR FIRE FLAG GO BTKA PROG FMOB TER2 PRTO | Pole | 2020-04-16 | 2020-06-16 | COMP | 2020-04-16 |  |  | 2020-04-08 | 2020-04-08 | [12 empty] | 2019-03-19 | 2020-03-19 |  | 2020-03-19 | 2021 CBP Plan | 2020-04-10 | PIKEENG |  | 152282101 | 25607.04 | 5168.6 | 4684.8 | 1309.8 | 1309.8 | 416.9 |  | 416.9 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | COOL | Auburn |  |  | OPEN | 116950835 | POLE_CLER_REPL - A/F 2500 BIG NUGGET TR | 35150413 |  |  | STS-TRAN_CORR_REPL - A/F 2500 BIG NUGGET | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9139 | -120.9665 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | T1124 | 9245 | Y | 311 |  |  | 2021-03-19 07:00 | 2021-03-19 16:00 | Dispatched | CLICK | [6 empty] | 81 | 81 |  |  | 0 | 81 | 81 |  |  | EC | E | Pole | Clearance Impaired | Replace |  | 100039723 | RELW OH PRI CLR JPOL REMT FLAG PROG ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-04-13 | 2020-11-30 | COMP | 2020-04-13 |  |  | 2020-02-20 | 2020-02-20 | [12 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2020-04-10 | PIKEENG |  | 152282101 | 13094.18 | 2151.8 | 2151.8 | 1147.5 | 1147.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | DIAMOND SPRINGS | Placerville |  |  | OPEN | 116747489 | POLE_DECA_REPL - 1NE/O 4600 RINGOLD RD.F | 35187722 |  |  | STS-POLE_DECA_REPL - 1NE/O 4600 RINGOLD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6892 | -120.7888 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I4221 | 12581 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 38.2 | 38.2 |  |  | 0 | 38.2 | 38.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101403448 | RELW OH PRI TER2 RESD ESTR BTKA FMOB PRTO | Pole | 2021-01-11 | 2021-02-12 | COMP | 2020-10-07 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-03-16 | 2020-03-16 |  | 2020-03-16 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 14802.25 | 149.5 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | DIAMOND SPRINGS | Placerville |  |  | OPEN | 116747691 | POLE_BROK_REPL - 1NE/O 4612 RINGOLD RD. | 35187734 |  |  | STS-POLE_BROK_REPL - 1NE/O 4612 RINGOLD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6883 | -120.7896 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I4221 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.6 | 18.6 |  |  | 0 | 18.6 | 18.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101403451 | RELW OH PRI ESTR BTKA PROG FMOB TER2 PRTO | Pole | 2020-09-04 | 2021-02-18 | COMP | 2020-09-04 |  |  | 2021-02-18 | 2021-02-18 | [12 empty] | 2019-03-16 | 2020-03-16 |  | 2020-03-16 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | DIAMOND SPRINGS | Placerville |  |  | OPEN | 116748685 | POLE_DECA_REPL - UNKNOWNDIAMOND SPRINGS9 | 35187758 |  |  | STS-POLE_DECA_REPL - UNKNOWNDIAMOND SPRI | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.6999 | -120.8085 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I4119 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.9 | 13.9 |  |  | 0 | 13.9 | 13.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103663321 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-08-27 | 2020-08-26 | COMP | 2020-08-26 | [16 empty] | 2019-03-16 | 2020-03-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | DIAMOND SPRINGS | Placerville |  |  | OPEN | 117123237 | POLE_DECA_REPL - 2N/O 1045 PLEASANT VALL | 35188267 |  |  | 201038VTCONST_REPL - 2N/O 1045 PLEASANT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6944 | -120.794 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I4221 | 13097 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 71.4 | 71.4 |  |  | 0 | 71.4 | 71.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101415913 | RELW OH PRI PATR JPOL FIRE ESTR BTKA FMOB TER2 | Pole | 2020-09-08 | 2021-02-18 | COMP | 2020-09-08 |  |  | 2021-02-18 | 2021-02-18 | [12 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | DIAMOND SPRINGS | Placerville |  |  | OPEN | 116734357 | POLE_DECA_REPL - AF 1090 PLEASANT VALLEY | 35160204 |  |  | STS-POLE_DECA_REPL - AF 1090 PLEASANT VA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6923 | -120.7931 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I4221 | 2107 | Y | 311 |  |  |  |  | Started | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 22.7 | 22.7 |  |  | 0 | 22.7 | 22.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101416191 | RELW OH PRI REMT ESTR GO REAR FMOB TER2 PRTO | Pole | 2020-09-21 | 2020-11-19 | COMP | 2020-09-21 |  |  | 2020-09-21 | 2020-09-21 | [12 empty] | 2019-03-14 | 2020-03-14 |  | 2020-03-14 | 2021 CBP Plan | 2020-10-31 | QUES |  | 152261106 | 11586.78 | 3677.2 | 2293.3 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | DOWNEYVILLE | Grass Valley |  |  | OPEN | 117918691 | POLE_BROK_REPL - 1/P/W/O C/O'S 32483 DOW | 35130375 |  |  | STS-POLE_BROK_REPL - 1/P/W/O C/O'S 32483 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5717 | -120.7361 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F17 | 2730 | Y | 311 |  |  | 2021-08-25 07:00 | 2021-08-25 16:00 | Dispatched | CLICK | [6 empty] | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100104682 | RELW OH JPOL ESTR TER2 | Pole | 2019-12-11 | 2020-04-24 | COMP | 2019-12-11 |  |  | 2019-10-15 | 2019-10-15 | [12 empty] | 2019-09-22 | 2019-11-22 |  | 2019-11-22 | Q1 Work Plan |  | Auburn |  | 152101101 | 35729.02 | 4565.3 | 2.8 |  |  | 127.7 |  | 127.7 | FRMMA/WMPMA - Electric | Y | 11/2 in MPP Import File | N | Clearance/Loading Issue - Helicopter set/weather | Y | 2020-02-18
North | SI | EL DORADO | Placerville |  |  | OPEN | 117130269 | POLE_DECA_REPL - R/O 1121 SAND RIDGE RDE | 35215055 |  |  | STS-POLE_DECA_REPL - R/O 1121 SAND RIDGE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.5948 | -120.8117 |  | TIER 2 | 360 | 15226-1105, DIAMOND SPRINGS | L41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101385452 | RELW OH PRI CLR TER2 REMT ESTR FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152261105 | 1 | 488.3 | 488.3 | 488.3 | 488.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | EL DORADO | Placerville |  |  | OPEN | 117142849 | POLE_BROK_REPL - 4P W/O 1P S/O 1800 WYNO | 35215099 |  |  | STS-POLE_BROK_REPL - 4P W/O 1P S/O 1800 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.5943 | -120.8202 |  | TIER 2 | 360 | 15226-1105, DIAMOND SPRINGS | L41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101413431 | RELW OH PRI REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-01 | 2020-05-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152261105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | EL DORADO | Placerville |  |  | OPEN | 117150936 | POLE_BROK_REPL - 1P S/O 1P E/O 1800 WYKN | 35215134 |  |  | STS-POLE_BROK_REPL - 1P S/O 1P E/O 1800 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.5944 | -120.8152 |  | TIER 2 | 360 | 15226-1105, DIAMOND SPRINGS | L41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101412006 | RELW OH PRI REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-02 | 2020-05-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152261105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | EL DORADO | Placerville |  |  | OPEN | 117150937 | POLE_BROK_REPL - 1P W/O 1P N/O 830 SAND | 35215139 |  |  | STS-POLE_BROK_REPL - 1P W/O 1P N/O 830 S | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.595 | -120.8246 |  | TIER 2 | 360 | 15226-1105, DIAMOND SPRINGS | L41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101384942 | RELW OH PRI JPOL REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-02 | 2020-05-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152261105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | EL DORADO | Placerville |  |  | OPEN | 117173340 | POLE_BROK_REPL - R/O 830 SAND RIDGE RD.E | 35188426 |  |  | STS-POLE_BROK_REPL - R/O 830 SAND RIDGE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5939 | -120.8236 |  | TIER 2 | 360 | 15226-1105, DIAMOND SPRINGS | L41 | 13785 | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-15 16:00 | Scheduled | CLICK | [6 empty] | 42.8 | 41.8 | 1 |  | 0 | 42.8 | 41.8 | 1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101384944 | RELW OH PRI JPOL RESD FSRP PRTO ESTR FMOB TER2 | Pole | 2020-10-14 | 2020-10-14 | COMP | 2020-10-14 | [16 empty] | 2019-05-06 | 2020-05-06 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2020-11-15 | EEI |  | 152261105 | 19591.34 | 123.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | EL DORADO | Placerville |  |  | OPEN | 117335065 | POLE_DECA_REPL - L42 EL DORADO | 35189468 |  |  | STS-POLE_DECA_REPL - L42 EL DORADO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5975 | -120.7813 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L42 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.6 | 20.2 | 2.4 |  | 0 | 22.6 | 20.2 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103663976 | RELW OH PRI PGEA CLR RESD REMT FIRE FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-11 | 2021-01-11 | COMP | 2020-10-14 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-05-28 | 2020-05-28 |  | 2020-05-28 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 11053.15 | 361.4 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | EL DORADO HILLS | Placerville |  |  | OPEN | 120528071 | POLE_BROK_REPL - 1473 LOMITA WAY EL DORA | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-04-13 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 38.7333 | -121.0756 |  | TIER 2 | 522 | 15361-2109, CLARKSVILLE | I35 | 78156 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101378596 | REGW OH PRI SEC TMAN JPOL ESTR BTKA USA TER2 | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2021-02-11 | 2021-05-11 |  | 2021-05-11 | B tag clean up 2/19/2021 |  | UNASSIGNED |  | 153612109 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | SI | EL DORADO HILLS | Placerville |  |  | OPEN | 120528078 | POLE_BROK_REPL - 1450 LOMITA WAY EL DORA | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-04-13 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 38.7338 | -121.0755 |  | TIER 2 | 522 | 15361-2109, CLARKSVILLE | H3521 | 78156 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 103667401 | REGW OH PRI SEC SERV TMAN JPOL ESTR BTKA USA PROG TER2 | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2021-02-11 | 2021-05-11 |  | 2021-05-11 | B tag clean up 2/19/2021 |  | UNASSIGNED |  | 153612109 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | SI | EL DORADO HILLS | Placerville |  |  | OPEN | 117771524 | POLE_DECA_REPL - SVC TO 3920 BASS LAKE R | 35189364 |  |  | STS-REPL POLE:SVC TO 3920 BASS LAKE RD., | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6672 | -121.0338 |  | TIER 2 | 133 | 15361-2104, CLARKSVILLE | J36 |  | Y | 311 |  |  | 2021-03-13 07:00 | 2021-03-13 16:00 | Scheduled | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101380499 | RELW OH TNT TER2 JPOL | Pole | 2020-10-08 | 2020-12-03 | COMP | 2020-10-08 | [16 empty] | 2019-06-26 | 2020-06-26 |  | 2020-06-26 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153612104 | 17578.55 | 629.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | El Dorado Hills | Placerville |  |  | OPEN | 117771591 | REPL POLE:2161 VALLEY SPRINGS RD,El Dora | 35189370 |  |  | STS-REPL POLE:2161 VALLEY SPRINGS RD,EL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7111 | -121.0513 |  | TIER 2 | 133 | 15361-2104, CLARKSVILLE | I3514 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101374490 | RELW OH TNT JPOL TER2 | Pole | 2021-01-11 | 2021-01-12 | COMP | 2020-10-15 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-06-05 | 2020-06-05 |  | 2020-06-05 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153612104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | El Dorado Hills | Placerville |  |  | OPEN | 117771592 | REPL POLE:2/P/E/O 2161 GREEN VALLEY RD,E | 35189373 |  |  | STS-REPL POLE:2/P/E/O 2161 GREEN VALLEY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7111 | -121.0501 |  | TIER 2 | 133 | 15361-2104, CLARKSVILLE | I3514 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.7 | 15.7 |  |  | 0 | 15.7 | 15.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101374492 | RELW OH TNT JPOL TER2 | Pole | 2020-10-05 | 2021-01-08 | COMP | 2020-10-05 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-06-11 | 2020-06-11 |  | 2020-06-11 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153612104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | El Dorado Hills | Placerville |  |  | OPEN | 117771593 | REPL POLE:1/P/A/F 1920 GREEN SPRINGS RD, | 35189376 |  |  | STS-REPL POLE:1/P/A/F 1920 GREEN SPRINGS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7118 | -121.0483 |  | TIER 2 | 133 | 15361-2104, CLARKSVILLE | I3514 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.7 | 26.7 |  |  | 0 | 26.7 | 26.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101374557 | RELW OH TNT JPOL TER2 | Pole | 2021-01-11 | 2021-01-12 | COMP | 2020-10-14 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-06-03 | 2020-06-03 |  | 2020-06-03 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153612104 | 16035.89 | 762.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | El Dorado Hills | Placerville |  |  | OPEN | 117771596 | REPL POLE:C/O VALLEY SPRINGS RD AND VERD | 35189383 |  |  | STS-REPL POLE:C/O VALLEY SPRINGS RD AND | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7095 | -121.0482 |  | TIER 2 | 133 | 15361-2104, CLARKSVILLE | I3514 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.9 | 39.9 |  |  | 0 | 39.9 | 39.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101409929 | RELW OH TNT JPOL TER2 | Pole | 2021-01-12 | 2021-01-20 | COMP | 2020-10-15 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-06-03 | 2020-06-03 |  | 2020-06-03 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153612104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | FIDDLETOWN | Placerville |  |  | OPEN | 117079250 | POLE_DECA_REPL - ENTRANCE 4221 EDEN LNFI | 35147914 |  |  | STS-POLE_DECA_REPL - ENTRANCE 4221 EDEN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.542 | -120.7042 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | M44 |  | Y | 311 |  |  | 2021-03-24 07:00 | 2021-03-24 16:00 | Scheduled | CLICK | [6 empty] | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101393360 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-06-19 | 2020-08-23 | COMP | 2020-06-19 | [16 empty] | 2019-04-22 | 2020-04-22 |  | 2020-04-22 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153662102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | FIDDLETOWN | Placerville |  |  | OPEN | 117079518 | POLE_BROK_REPL - 4SE/O 3040 BRIDGEPORT S | 35188205 |  |  | STS-POLE_BROK_REPL - 4SE/O 3040 BRIDGEPO | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5402 | -120.713 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | M44 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 28.5 | 28.5 |  |  | 0 | 28.5 | 28.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101393184 | RELW OH PRI REMT ESTR FMOB TER2 PRTO | Pole | 2020-08-24 | 2020-08-24 | COMP | 2020-08-24 | [16 empty] | 2019-04-22 | 2020-04-22 |  | 2020-04-22 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | FIDDLETOWN | Placerville |  |  | OPEN | 117079519 | POLE_BROK_REPL - 1N/O 3280 BRIDGEPORT SC | 35188212 |  |  | STS-POLE_BROK_REPL - 1N/O 3280 BRIDGEPOR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5363 | -120.7065 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | M44 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.2 | 28.2 |  |  | 4 | 24.2 | 24.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101393197 | RELW NOAC OH PRI REMT ESTR GO FMOB TER2 PRTO | Pole | 2020-08-24 | 2020-08-24 | COMP | 2020-08-24 | [16 empty] | 2019-04-22 | 2020-04-22 |  | 2020-04-22 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 9652.18 | 1312.1 | 1303.3 | 1303.3 | 1303.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | FIDDLETOWN | Placerville |  |  | OPEN | 117086286 | POLE_DECA_REPL - ENTRANCE 4321 EDEN LNFI | 35187647 |  |  | STS-POLE_DECA_REPL - ENTRANCE 4321 EDEN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5407 | -120.7068 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | M44 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 30.9 | 28.5 | 2.4 |  | 0 | 30.9 | 28.5 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101393367 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-08-26 | 2020-10-19 | COMP | 2020-08-26 | [16 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 12319.03 | 81.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | FIDDLETOWN | Placerville |  |  | OPEN | 117086291 | POLE_DECA_REPL - 1E/O ENTRANCE 4301 EDEN | 35187653 |  |  | STS-POLE_DECA_REPL - 1E/O ENTRANCE 4301 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5407 | -120.7055 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | M44 | 11667 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 59.1 | 59.1 |  |  | 0 | 59.1 | 59.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101393366 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-08-24 | 2020-10-13 | COMP | 2020-08-24 | [16 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | FIDDLETOWN | Placerville |  |  | OPEN | 117086300 | POLE_DECA_REPL - 1W/O ENTRANCE 4321 EDEN | 35187658 |  |  | STS-POLE_DECA_REPL - 1W/O ENTRANCE 4321 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5407 | -120.7073 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | M44 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25 | 22.6 | 2.4 |  | 0 | 25 | 22.6 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101393370 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-20 | 2020-10-27 | COMP | 2020-08-24 | [16 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | FIDDLETOWN | Placerville |  |  | OPEN | 117086324 | POLE_BROK_REPL - EL DORADO FIDDLETOWN | 35187664 |  |  | STS-POLE_BROK_REPL - EL DORADO FIDDLETOW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5447 | -120.7165 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | M44 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.5 | 16.5 |  |  | 0 | 16.5 | 16.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103662287 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-08-27 | 2020-08-27 | COMP | 2020-08-27 | [16 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | FIDDLETOWN | Placerville |  |  | OPEN | 117086326 | POLE_BROK_REPL - 2W/O HOUSE 3041 BRIDGEP | 35187670 |  |  | STS-POLE_BROK_REPL - 2W/O HOUSE 3041 BRI | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5414 | -120.7129 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | M44 |  | Y | 311 |  |  | 2021-03-12 07:00 | 2021-03-12 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101393181 | RELW OH PRI NOAC ESTR FMOB TER2 PRTO | Pole | 2020-08-25 | 2020-08-25 | COMP | 2020-08-25 | [16 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | FIDDLETOWN | Placerville |  |  | OPEN | 117158770 | POLE_BROK_REPL - 7460 RANCH CAMP RDFIDDL | 35187890 |  |  | STS-POLE_BROK_REPL - 7460 RANCH CAMP RDF | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5601 | -120.7044 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L44 |  | Y | 311 |  |  | 2021-03-09 07:00 | 2021-03-09 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103662087 | RELW OH PRI CLR RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-10-08 | 2020-10-08 | COMP | 2020-10-08 | [16 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 6249.38 | 1210.5 | 1210.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | FIDDLETOWN | Placerville |  |  | OPEN | 117158783 | POLE_BROK_REPL - 95684FIDDLETOWN95629 | 35187896 |  |  | STS-POLE_BROK_REPL - 95684FIDDLETOWN9562 | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5602 | -120.7051 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L44 |  | Y | 311 |  |  | 2021-03-09 07:00 | 2021-03-09 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103661854 | RELW OH PRI CLR RESD REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-09-30 | 2020-09-30 | COMP | 2020-09-30 | [16 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 5711.84 | 967.5 | 967.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | FIDDLETOWN | Placerville |  |  | OPEN | 117060749 | POLE_DECA_REPL - 1S/O F/O 2921 CEDAR CRE | 35187992 |  |  | STS-POLE_DECA_REPL - 1S/O F/O 2921 CEDAR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5482 | -120.7126 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | M44 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27 | 27 |  |  | 0 | 27 | 27 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101393429 | RELW OH PRI JPOL REMT FLAG ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-08-27 | 2021-01-12 | COMP | 2020-08-27 |  |  | 2021-01-12 | 2021-01-12 | [12 empty] | 2019-04-18 | 2020-04-18 |  | 2020-04-18 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 18352.56 | 534.6 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | FIDDLETOWN | Placerville |  |  | OPEN | 117060850 | POLE_DECA_REPL - 1S/O 1E/O 3021 CEDAR CR | 35187997 |  |  | STS-POLE_DECA_REPL - 1S/O 1E/O 3021 CEDA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5473 | -120.7086 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | M44 | 21355 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 45.1 | 45.1 |  |  | 0 | 45.1 | 45.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101393447 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-08-31 | 2021-01-19 | COMP | 2020-08-31 |  |  | 2021-01-19 | 2021-01-19 | [12 empty] | 2019-04-18 | 2020-04-18 |  | 2020-04-18 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 23645.45 | 537.5 | 442.5 | 363 | 363 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | FIDDLETOWN | Placerville |  |  | OPEN | 117112726 | POLE_DECA_REPL - 3310 CEDAR CREEK RD 3PS | 35187844 |  |  | STS-POLE_DECA_REPL - 3310 CEDAR CREEK RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5469 | -120.6975 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | M44 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32 | 29.6 | 2.4 |  | 0 | 32 | 29.6 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101414505 | RELW OH PRI JPOL REMT ESTR TER2 REAR USA FMOB PRTO | Pole | 2020-10-15 | 2021-01-02 | COMP | 2020-10-15 | [16 empty] | 2019-04-27 | 2020-04-27 |  | 2020-04-27 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 18486.36 | 414 | -181 | -181 | -181 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 115005611 | POLE_DECA_REPL - 8258 FAIR PINES LN GARD | 35113507 |  |  | STS-POLE_DECA_REPL - 8258 FAIR PINES LN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.8458 | -120.8325 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V15 | 1253 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 3 | 47 | 47 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100108142 | RELW OH PRI INSP JPOL REMT NOAC SCOP SCPA FMOB TER2 | Pole |  |  | REQD |  |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2018-09-27 | 2019-09-27 |  | 2019-09-27 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 874.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117053297 | POLE_BROK_REPL - 5155 GLENN CT GARDEN VA | 35141935 |  |  | STS-POLE_BROK_REPL - 5155 GLENN CT GARDE | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8454 | -120.859 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1412 | 4159 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.7 | 44.7 |  |  | 0 | 44.7 | 44.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100108718 | RELW OH PRI CREW JPOL RESD TRAF ESTR TER2 | Pole | 2021-01-14 |  | COMP | 2021-01-14 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 35531.73 | 14242.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117056903 | POLE_BROK_REPL - AT 5820 JOHNTWON CREEK | 35142114 |  |  | STS-POLE_BROK_REPL - AT 5820 JOHNTWON CR | ADER | ADER ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.831 | -120.8713 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1421 | 6053 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055910 | RELW OH PRI CLR JPOL RESD ESTR REAR FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-18 | 2020-04-18 |  | 2020-04-18 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117057104 | POLE_DECA_REPL - ENTRANCE AT 5856 JOHNTW | 35142114 |  |  | STS-POLE_BROK_REPL - AT 5820 JOHNTWON CR | ADER | ADER ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.8297 | -120.8705 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1421 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100055912 | REGW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-18 | 2020-04-18 |  | 2020-04-18 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117083535 | POLE_DECA_REPL - R/O 6571 JOHNSTOWN CREE | 35142503 |  |  | STS-POLE_BROK_REPL - 6657 JOHNSTOWN CREE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 38.8156 | -120.8714 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1401 | 18875 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 125.8 | 125.8 |  |  | 0 | 125.8 | 125.8 |  |  | EC | F | Pole | Decayed/Rotten | Replace |  | 100098701 | REGW OH PRI CLR JPOL REMT ESTR REAR FMOB TER2 PRTO | Pole | 2021-01-08 | 2021-01-08 | COMP | 2020-09-27 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-23 | 2020-04-23 | 2024-04-23 | 2024-04-23 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117086604 | POLE_BROK_REPL - A/F 6180 JOHNSTOWN RD G | 35142502 |  |  | STS-POLE_BROK_REPL - 6340 CHRYSLER CIR G | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8194 | -120.8682 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1401 | 18875 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 66 | 66 |  |  | 0 | 66 | 66 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100063097 | REGW OH PRI CLR JPOL REMT FLAG ESTR REAR FMOB TER2 PRTO | Pole | 2021-01-15 | 2021-01-14 | COMP | 2021-01-14 | [16 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117086853 | POLE_BROK_REPL - AT HOUSE RANCH 5191 MAR | 35171136 |  |  | STS-POLE_BROK_REPL - AT HOUSE RANCH 5191 | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8444 | -120.8728 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1411 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.6 | 24.6 |  |  | 0 | 24.6 | 24.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100111044 | OH PRI CLR JPOL REMT ESTR REAR PROG FMOB TER2 PRTO RELW | Pole | 2021-02-08 |  | COMP | 2021-02-08 | [16 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117093325 | POLE_DECA_REPL - 1NO C/O JOHNSTOWN CHRYS | 35142502 |  |  | STS-POLE_BROK_REPL - 6340 CHRYSLER CIR G | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8197 | -120.8672 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1401 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100063098 | REGW OH PRI FLAG CLR JPOL REMT ESTR GO BTKA REAR FMOB TER2 PRTO | Pole | 2021-01-15 | 2021-01-14 | COMP | 2021-01-14 | [16 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117093329 | POLE_DECA_REPL - A/F 6301 ROLLER COASTER | 35159296 |  |  | STS-POLE_DECA_REPL - A/F 6301 ROLLER COA | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8142 | -120.8608 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1402 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.2 | 22.2 |  |  | 0 | 22.2 | 22.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100078926 | RELW OH PRI CLR JPOL REMT FLAG ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2021-01-04 |  | COMP | 2021-01-04 |  |  | 2021-02-19 | 2021-02-19 | [12 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117095226 | POLE_BROK_REPL - F/O 5521 HOLLOW OAK CT/ | 35141960 |  |  | STS-POLE_BROK_REPL - 1S/O ENTRANCE AT 55 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8393 | -120.8721 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1416 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.7 | 24.7 |  |  | 0 | 24.7 | 24.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055849 | REGW OH SEC RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2021-01-10 | 2021-02-19 | COMP | 2021-01-10 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 9372.74 | 645.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117095251 | POLE_BROK_REPL - 1S/O ENTRANCE AT 5511 H | 35141960 |  |  | STS-POLE_BROK_REPL - 1S/O ENTRANCE AT 55 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8391 | -120.8701 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1416 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055872 | RELW FIRE OH PRI RESD ESTR FMOB TER2 PRTO | Pole | 2021-01-10 | 2021-02-19 | COMP | 2021-01-10 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 9372.74 | 645.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117095252 | POLE_BROK_REPL - S/O W/O AT HOUSE 5520 B | 35141960 |  |  | STS-POLE_BROK_REPL - 1S/O ENTRANCE AT 55 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8398 | -120.8712 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1416 | 31165 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100087428 | REGW OH PRI CLR RESD FIRE ESTR PROG FMOB TER2 PRTO | Pole | 2021-01-10 | 2021-02-19 | COMP | 2021-01-10 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 9372.74 | 645.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117100998 | POLE_DECA_REPL - 1WO 1NO 6657 JOHNSTOWN | 35142503 |  |  | STS-POLE_BROK_REPL - 6657 JOHNSTOWN CREE | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 38.8158 | -120.8724 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1401 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100110569 | REGW OH PRI CLR JPOL REMT ESTR GO REAR USA FMOB TER2 PRTO | Pole | 2021-01-08 | 2021-01-08 | COMP | 2020-09-27 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117103080 | POLE_DECA_REPL - F/O 6611 HANCOCK RD/JOH | 35141961 |  |  | STS-POLE_DECA_REPL - F/O 6611 HANCOCK RD | UNSC | UNSC | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 38.8373 | -120.8678 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1416 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.7 | 20.7 |  |  | 0 | 20.7 | 20.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100055879 | RELW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2021-01-10 | 2021-02-22 | COMP | 2021-01-10 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 8486.82 | 645.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117106251 | POLE_BROK_REPL - N/O 6811 OLYMPUS DR/GAR | 35142203 |  |  | STS-POLE_BROK_REPL - N/O 6811 OLYMPUS DR | ADER | ADER | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.8242 | -120.8557 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1423 | 4127 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100056116 | RELW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-26 | 2020-04-26 |  | 2020-04-26 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 4019.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117106252 | POLE_BROK_REPL - F/O 6789 OLYMPUS DR/GAR | 35142203 |  |  | STS-POLE_BROK_REPL - N/O 6811 OLYMPUS DR | ADER | ADER | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.8243 | -120.8564 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1423 | 4127 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100056112 | REGW OH PRI RESD FMOB FIRE ESTR TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-26 | 2020-04-26 |  | 2020-04-26 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 4019.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117110515 | POLE_BROK_REPL - ENTRANCE 5742 MC KINLEY | 35142204 |  |  | STS-POLE_BROK_REPL - ENTRANCE 5742 MC KI | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8309 | -120.8569 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1423 | 5981 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 188.9 | 188.9 |  |  | 0 | 188.9 | 188.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055982 | RESD RELW OH PRI FIRE ESTR FMOB TER2 PRTO | Pole | 2021-01-20 | 2021-01-14 | COMP | 2021-01-14 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-27 | 2020-04-27 |  | 2020-04-27 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 84938.26 | 144.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117110528 | POLE_DECA_REPL - AT ENTRANCE 5800 MC KIN | 35142204 |  |  | STS-POLE_BROK_REPL - ENTRANCE 5742 MC KI | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8283 | -120.8556 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1423 | 5981 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100056104 | REGW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2021-01-20 | 2021-01-14 | COMP | 2021-01-14 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-27 | 2020-04-27 |  | 2020-04-27 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 84938.26 | 144.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117110529 | POLE_DECA_REPL - ENTRANCE AT 5764 MC KIN | 35142204 |  |  | STS-POLE_BROK_REPL - ENTRANCE 5742 MC KI | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8297 | -120.8564 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1423 | 5981 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100056108 | REGW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2021-01-20 | 2021-01-14 | COMP | 2021-01-14 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-27 | 2020-04-27 |  | 2020-04-27 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 84938.26 | 144.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117110530 | POLE_BROK_REPL - F/O 5851 MC KINLEY DR/H | 35142204 |  |  | STS-POLE_BROK_REPL - ENTRANCE 5742 MC KI | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8268 | -120.8551 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1423 | 5981 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100056101 | REGW OH PRI RESD FIRE ESTR GO FMOB TER2 PRTO | Pole | 2021-01-20 | 2021-01-14 | COMP | 2021-01-14 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-27 | 2020-04-27 |  | 2020-04-27 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 84938.26 | 144.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117116588 | POLE_BROK_REPL - 6336 GARDEN PARK DR GAR | 35137215 |  |  | STS-POLE_BROK_REPL - 6336 GARDEN PARK DR | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8149 | -120.8459 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1404 | 5987 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 63.4 | 63.4 |  |  | 0 | 63.4 | 63.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100079037 | RELW OH PRI CLR JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-12 | 2021-01-10 | COMP | 2021-01-10 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-28 | 2020-04-28 |  | 2020-04-28 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117116589 | POLE_BROK_REPL - G/P 6336 GARDEN PARK DR | 35137215 |  |  | STS-POLE_BROK_REPL - 6336 GARDEN PARK DR | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8148 | -120.8462 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1404 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100079045 | REGW OH PRI CLR JPOL REMT TRAF ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-12 | 2021-01-10 | COMP | 2021-01-10 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-28 | 2020-04-28 |  | 2020-04-28 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117168159 | POLE_DECA_REPL - 1N/O AT 5081 OAK LN/GAR | 35141935 |  |  | STS-POLE_BROK_REPL - 5155 GLENN CT GARDE | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8452 | -120.8612 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1412 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100108724 | REGW OH PRI CLR RESD REMT ESTR GO BTKA FMOB TER2 PRTO | Pole | 2021-01-14 |  | COMP | 2021-01-14 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-06 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 35531.73 | 14242.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117179063 | POLE_BROK_REPL - R/O 3SO 3EO 8385 FAI PI | 35142152 |  |  | STS-POLE_DECA_REPL - AT 1WO 8260 PORTER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8414 | -120.8223 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1512 | 31155 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100108834 | REGW OH PRI CLR JPOL FMOB RESD ESTR BTKA TER2 PRTO | Pole | 2020-12-03 | 2021-02-17 | COMP | 2020-10-25 |  |  | 2021-02-17 | 2021-02-17 | [12 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 27383.68 | 3379.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117187962 | POLE_BROK_REPL - 2E/O AT HOUSE 5700 HACK | 35206344 |  |  |  | UNSC | UNSC | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 38.8327 | -120.833 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V14 | 1171 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 1 | 0 | 0 | 58.9 | 58.9 |  |  | 0 | 58.9 | 58.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100056769 | OH PRI CLR JPOL REMT JAR BTKA SCOP SCPA FMOB TER2 PRTO RELW | Pole | 2020-12-28 | 2021-02-19 | COMP | 2020-12-28 |  |  | 2021-01-13 | 2021-01-13 | [12 empty] | 2019-05-08 | 2020-05-08 | 2020-12-31 | 2020-12-31 | work plan date cleanup on 10/25/2020 |  | Auburn |  | 153082106 | 25464.83 | 676.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-10-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117229387 | POLE_BROK_REPL - 1SO 6410 JOHNSTOWN CREE | 35135365 |  |  | STS-POLE_BROK_REPL - 1SO 6410 JOHNSTOWN | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.811 | -120.8673 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W14 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100063072 | CLR RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 484.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117256454 | POLE_BROK_REPL - 95633 GARDEN VALLEY | 35137220 |  |  | STS-POLE_BROK_REPL - 95633 GARDEN VALLEY | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.812 | -120.8799 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W13 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 24.8 | 24.8 |  |  | 0 | 24.8 | 24.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103662925 | RELW OH PRI INSP CLR JPOL REMT ESTR BTKA REAR FMOB TER2 | Pole | 2021-01-11 |  | COMP | 2021-01-11 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 12229.77 | 27.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117267900 | POLE_BROK_REPL - 6160 LYXN RIDGE RDGARDE | 35175502 |  |  | STS-POLE_BROK_REPL - 6160 LYXN RIDGE RDG | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.8199 | -120.875 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W13 | 31135 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100072372 | RELW OH PRI INSP CLR JPOL RESD REMT TRAF FLAG ESTR GO BTKA FMOB TER2 | Pole |  |  | REQD |  |  |  | 2020-06-11 | 2020-06-11 | [12 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 164.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117328813 | POLE_DECA_REPL - 1PLS 7101 BAYNE RD GARD | 35137227 |  |  | STS-POLE_DECA_REPL - 1PLS 7101 BAYNE RD | UNSC | UNSC | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 38.8061 | -120.8463 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 20.2 | 20.2 |  |  | 0 | 20.2 | 20.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101387801 | RELW OH PRI NOAC JPOL REMT ESTR FMOB TER2 PRTO | Pole | 2020-12-31 | 2021-02-18 | COMP | 2020-12-31 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-28 | 2020-05-28 |  | 2020-05-28 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 15017.13 | 233 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117336545 | POLE_BROK_REPL - 3NO 1WO 5680 YELLOW BRI | 35142157 |  |  | STS-POLE_BROK_REPL - 3NO 1WO 5680 YELLOW | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8208 | -120.8278 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1501 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19 | 19 |  |  | 0 | 19 | 19 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100062667 | RELW OH PRI JPOL REMT NOAC ESTR GO FMOB TER2 PRTO | Pole | 2020-12-31 |  | COMP | 2020-12-31 | [16 empty] | 2019-05-29 | 2020-05-29 |  | 2020-05-29 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 20213.18 | 9087.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | Garden Valley | Auburn |  |  | OPEN | 117681968 | POLE _BROK _REPL_1N/W ENTRANCE AT 6035 C | 35148064 |  |  | STS-POLE _BROK _REPL_1N/W ENTRANCE AT 60 | PEND | PEND ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.8244 | -120.8641 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1422 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.5 | 25.5 |  |  | 0 | 25.5 | 25.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055927 | OH RELW PRI ESTR GO TER2 PRTO | Pole | 2020-12-29 |  | COMP | 2020-12-29 | [16 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 14440.48 | 17.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | Garden Valley | Auburn |  |  | OPEN | 117682467 | POLE_BROK_REPL - GP AT HOUSE 5501 GARDEN | 35148069 |  |  | STS-POLE_BROK_REPL - GP AT HOUSE 5501 GA | PEND | PEND ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8365 | -120.8493 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1418 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.3 | 17.3 |  |  | 0 | 17.3 | 17.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100108444 | RELW OH PRI ESTR GO TER2 PRTO | Pole | 2020-12-28 | 2020-12-24 | COMP | 2020-12-24 | [16 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | COMP | 117074484 | POLE_BROK_REPL - 5520 HANCOCK CT GARDEN | 35141932 |  |  | STS-POLE_BROK_REPL - 5520 HANCOCK CT GAR | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8404 | -120.8716 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1411 | 31165 | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 2 | 54.6 | 54.6 |  |  | 2.5 | 3.6 | 3.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100108715 | COMP CLR RELW OH PRI CREW JPOL RESD REMT NOAC ESTR CCNT TER2 | Pole | 2020-05-08 | 2020-07-16 | COMP | 2020-05-08 | COMP | 2021-01-13 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-01-19 | 2021-01-13 | 2020-04-11 |  | 2020-04-11 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 153082106 | 35443.55 | 17405.4 | 4877.2 | 4743.9 | 4743.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | COMP | 117097869 | POLE_DECA_REPL - AT HOUSE 4942 MULE TAIL | 35153314 |  |  | STS-POLE_DECA_REPL - AT HOUSE 4942 MULE | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8525 | -120.8471 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1409 | 5833 | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 42.2 | 41.9 | 0.3 |  | 1 | 41.2 | 40.9 | 0.3 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100108679 | OH PRI COMP CLR RESD REMT ESTR GO BTKA CCNT FMOB TER2 PRTO RELW | Pole | 2020-04-07 | 2020-06-04 | COMP | 2020-04-07 | COMP | 2021-01-08 | [13 empty] | 2021-01-13 | 2021-01-08 | 2020-04-25 | 2021-07-06 | 2021-07-06 | circuit based plan 2.14 | 2020-05-31 | Auburn |  | 153082106 | 26308.14 | 8559.3 | 2210.8 | 2210.8 | 2210.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | COMP | 117099979 | POLE_DECA_REPL - AT F/O HOUSE 4940 SCOTC | 35153315 |  |  | STS-POLE_DECA_REPL - AT F/O HOUSE 4940 S | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8537 | -120.8434 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1409 | 5833 | Y | 311 |  |  | 2021-01-05 | 2021-01-05 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 43.7 | 43.7 |  |  | 5 | 2.7 | 2.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100111316 | RELW OH PRI COMP CLR RESD REMT ESTR GO REAR CCNT PROG FMOB PRTO TER2 | Pole | 2020-04-11 | 2020-06-09 | COMP | 2020-04-11 | COMP | 2021-01-05 | [13 empty] | 2021-01-08 | 2021-01-05 | 2020-04-25 |  | 2020-04-25 | circuit based plan 2.14 | 2020-05-31 | Auburn |  | 153082106 | 25958.56 | 25609.5 | 12292.5 | 3383.6 | 3383.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | COMP | 117112478 | POLE_DECA_REPL - 6160 GARDEN PARK DRGARD | 35142500 |  |  | STS-POLE_DECA_REPL - 6160 GARDEN PARK DR | DOCC | DOCC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.82 | -120.8494 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1403 | 5983 | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 42.8 | 42.8 |  |  | 2.25 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100078964 | RELW OH PRI COMP CLR JPOL REMT FLAG ESTR BTKA USA CCNT FMOB TER2 PRTO | Pole | 2020-10-01 | 2020-10-01 | COMP | 2020-07-20 | COMP | 2021-02-11 | 2020-07-30 | 2020-07-30 | [11 empty] | 2021-02-16 | 2021-02-11 | 2020-04-27 |  | 2020-04-27 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 18229.74 | 2415.1 | 1613.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | COMP | 117112504 | POLE_BROK_REPL - 6390 PIKES PEAK CR GARD | 35137224 |  |  | STS-POLE_BROK_REPL - 6390 PIKES PEAK CR | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8131 | -120.8472 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1409 | 5987 | Y | 311 |  |  |  |  | Cancelled | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 28.5 | 27.8 | 0.7 |  | 1.75 | 27.5 | 26.8 | 0.7 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100079060 | RELW OH PRI COMP CLR JPOL REMT FLAG ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-06-17 | 2020-07-30 | COMP | 2020-06-12 | COMP | 2021-01-12 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-01-15 | 2021-01-12 | 2020-04-27 |  | 2020-04-27 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 153082106 | 19746.72 | 11422.8 | 7908.5 | 5311.4 | 5311.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | COMP | 117156283 | POLE_BROK_REPL - F/O ENTRANCE AT 5620 GA | 35141907 |  |  | STS-POLE_BROK_REPL - N/O ENTRANCE AT 558 | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8341 | -120.848 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V14 |  | Y | 311 |  |  | 2021-01-12 | 2021-01-12 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 42.8 | 42.8 |  |  | 1.5 | 1.8 | 1.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100056143 | REGW OH PRI COMP RESD FIRE CCNT PRTO ESTR FMOB TER2 | Pole | 2020-06-04 | 2020-06-10 | COMP | 2020-04-14 | COMP | 2021-01-12 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-01-15 | 2021-01-12 | 2020-05-03 |  | 2020-05-03 | circuit based plan 2.14 | 2020-05-31 | Auburn |  | 153082106 | 14995.17 | 6276.3 | 3268.6 | 2350.2 | 2350.2 | 56.3 |  | 56.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | COMP | 117163053 | POLE_BROK_REPL - AT 5770 GARDEN PARK DR | 35142205 |  |  | STS-POLE_BROK_REPL - AT 5770 GARDEN PARK | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8294 | -120.8534 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1423 |  | Y | 311 |  |  | 2021-01-12 | 2021-01-12 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100068510 | RELW OH SEC COMP RESD FIRE ESTR CCNT FMOB TER2 PRTO | Pole | 2020-05-08 | 2020-06-30 | COMP | 2020-05-08 | COMP | 2021-01-12 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-01-15 | 2021-01-12 | 2020-05-04 |  | 2020-05-04 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 153082106 | 9992.85 | 892.5 | 173.6 | 173.6 | 173.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | COMP | 117164781 | POLE_BROK_REPL - 1N/O 1N/E AT HOUSE 5782 | 35142149 |  |  | STS-POLE_BROK_REPL - 1N/O 1N/E AT HOUSE | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8277 | -120.8449 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1424 | 2518 | Y | 311 |  |  | 2021-01-14 | 2021-01-14 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 32.8 | 32.8 |  |  | 7.5 | 1.8 | 1.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100108973 | RELW OH PRI COMP RESD FIRE ESTR CCNT FMOB TER2 PRTO | Pole | 2020-05-02 | 2020-07-30 | COMP | 2020-05-02 | COMP | 2021-01-14 | [13 empty] | 2021-01-19 | 2021-01-14 | 2020-05-05 |  | 2020-05-05 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 153082106 | 20617.31 | 8126.4 | 4671.2 | 4671.2 | 4671.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | COMP | 117182264 | POLE_BROK_REPL - AT HOUSE 5501 HOLLOW OA | 35141932 |  |  | STS-POLE_BROK_REPL - 5520 HANCOCK CT GAR | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8404 | -120.8726 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1411 | 31165 | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 2 | 0 |  |  |  | 2.5 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100111635 | REGW OH PRI COMP CLR RESD REMT ESTR GO BTKA CCNT FMOB TER2 PRTO | Pole | 2020-05-08 | 2020-07-16 | COMP | 2020-05-08 | COMP | 2021-01-13 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-01-19 | 2021-01-13 | 2020-05-08 |  | 2020-05-08 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 153082106 | 35443.55 | 17405.4 | 4877.2 | 4743.9 | 4743.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | COMP | 117192535 | POLE_BROK_REPL - 2S/O 5331 GARDEN VALLEY | 35142112 |  |  | STS-POLE_BROK_REPL - 2S/O 5331 GARDEN VA | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.84 | -120.854 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1413 | 4163 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 19.25 | 40 | 40 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055971 | RELW OH PRI COMP RESD FIRE ESTR CCNT FMOB TER2 PRTO | Pole | 2020-07-01 | 2020-07-07 | COMP | 2020-06-20 | COMP | 2021-02-10 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-02-12 | 2021-02-10 | 2020-05-09 |  | 2020-05-09 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 153082106 | 19111.91 | 9887.9 | 6310.3 | 3525.8 | 3525.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | COMP | 117255293 | POLE_BROK_REPL - 6340 MT MURPHY RD GARDE | 35137219 |  |  |  | MAPP | MAPP SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8151 | -120.8783 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W13 |  | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 43.7 | 43.7 |  |  | 2.5 | 2.7 | 2.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101382438 | RELW OH PRI INSP COMP CLR JPOL ESTR REMT TRAF FLAG BTKA CCNT FMOB TER2 | Pole | 2020-06-25 | 2020-08-12 | COMP | 2020-06-25 | COMP | 2021-01-08 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-01-13 | 2021-01-08 | 2020-05-17 |  | 2020-05-17 | circuit based plan 2.14 | 2020-06-30 | W. Sac |  | 153082106 | 15567.68 | 5988.7 | 3113.2 | 2710.9 | 2710.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | COMP | 117267926 | POLE_DECA_REPL - G/P 6160 LYXN RIDGE RD | 35137221 |  |  | STS-POLE_BROK_REPL - 6160 LYXN RIDGE RDG | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8199 | -120.8747 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W13 |  | Y | 311 |  |  | 2021-04-06 07:00 | 2021-04-06 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 3 | 102 | 102 |  |  | 0 | 102 | 102 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100072371 | REGW OH SEC INSP COMP CLR JPOL RESD ESTR BTKA CCNT FMOB TER2 | Pole | 2020-08-11 | 2020-08-27 | COMP | 2020-08-11 | COMP | 2021-02-09 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-02-11 | 2021-02-09 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 153082106 | 66210.94 | 7333.8 | 1442.1 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | COMP | 117268093 | POLE_BROK_REPL - 6521 LAZY BROOK TRAIL G | 35137221 |  |  | STS-POLE_BROK_REPL - 6160 LYXN RIDGE RDG | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.817 | -120.875 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W13 |  | Y | 311 |  |  | 2021-04-06 07:00 | 2021-04-06 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 3 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103664143 | REGW OH PRI INSP COMP CLR JPOL RESD REMT ESTR BTKA CCNT FMOB TER2 | Pole | 2020-08-11 | 2020-08-27 | COMP | 2020-08-11 | COMP | 2021-02-09 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-02-12 | 2021-02-09 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 153082106 | 66210.94 | 7333.8 | 1442.1 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | COMP | 117268181 | POLE_BROK_REPL - G/P 6491 LAZY BROOK TR | 35137221 |  |  | STS-POLE_BROK_REPL - 6160 LYXN RIDGE RDG | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8165 | -120.8749 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W13 |  | Y | 311 |  |  | 2021-04-06 07:00 | 2021-04-06 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 3 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100072384 | REGW OH SEC INSP COMP CLR JPOL RESD REMT ESTR BTKA REAR CCNT FMOB TER2 | Pole | 2020-08-11 | 2020-08-27 | COMP | 2020-08-11 | COMP | 2021-02-09 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-02-12 | 2021-02-09 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 153082106 | 66210.94 | 7333.8 | 1442.1 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | COMP | 117508095 | POLE_BROK_REPL - 2500 WAKEFIELD PL GARDE | 35148105 |  |  | STS-POLE_BROK_REPL - 2500 WAKEFIELD PL G | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8569 | -120.8553 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1408 | 1127 | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100110432 | RELW OH ESTR TER2 CCNT COMP | Pole | 2020-07-27 | 2020-07-27 | COMP | 2020-07-27 | COMP | 2021-01-08 | [13 empty] | 2021-01-28 | 2021-01-08 | 2020-06-11 |  | 2020-06-11 | circuit based plan 2.14 | 2020-09-30 | W. Sac |  | 153082106 | 25649.82 | 24457.2 | 21065.6 | 3648.5 | 3648.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 114590648 | POLE_BROK_REPL - 6340 CHRYSLER CIR GARDE | 35142879 |  |  | STS-POLE_BROK_REPL - 6340 CHRYSLER CIR G | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8193 | -120.8662 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1401 | 3049 | Y | 311 |  |  | 2021-02-19 07:00 | 2021-02-19 16:00 | Completed | CLICK | [6 empty] | 42.8 | 42.8 |  |  | 0 | 42.8 | 42.8 |  |  | EC | F | Pole | Broken/Damaged | Replace |  | 100078922 | RELW OH PRI INSP REMT SCOP GO BTKA SCPA FMOB TER2 | Pole | 2020-06-23 | 2020-08-11 | COMP | 2020-06-23 | [16 empty] | 2018-05-10 | 2023-05-10 | 2019-12-31 | 2019-12-31 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 153082106 | 17494.42 | 5562.1 | 313.4 | 313.4 | 313.4 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 114934281 | POLE_DECA_REPL - 4921 MARSHALL RD GARDEN | 35062674 |  |  | STS-POLE_DECA_REPL - 4921 MARSHALL RDGAR | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8531 | -120.8574 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1407 | 1135 | Y | 311 |  |  | 2021-03-20 07:00 | 2021-03-20 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 40.1 | 40.1 |  |  | 19.5 | 40 | 40 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100093058 | INSP REGW OH PRI JPOL RESD REMT FIRE ESTR BTKA FMOB TER2 | Pole | 2019-09-27 | 2019-09-27 | COMP | 2019-09-27 |  |  | 2019-03-25 | 2019-03-25 | [12 empty] | 2018-08-31 | 2019-08-31 | 2020-10-09 | 2020-10-09 | Q1 Work Plan | 2019-09-27 | EEI |  | 153082106 | 11660.51 | 23797.7 | -31671.2 | -31671.2 | -31671.2 |  |  |  | Electric Distribution | Y | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117069776 | POLE_BURN_REPL - 4SO 1WO 5610 MT MURPHY | 35141693 |  |  | STS-POLE_DECA_REPL - AT ENTRANCE 5801/58 | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8354 | -120.8772 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1320 | 31131 | Y | 311 |  |  | 2020-07-31 | 2020-07-31 | Completed | Order Operation | POLRPL | # of Poles Replaced | 2 | 1 | 0 | 0 | 54.6 | 54.6 |  |  |  | 54.1 | 54.1 |  |  | EC | B | Pole | Burnt | Replace |  | 100108033 | REGW OH PRI JPOL REMT ESTR BTKA REAR FMOB TER2 PRTO | Pole | 2020-02-04 | 2020-03-30 | COMP | 2020-02-04 | COMP | 2020-07-31 | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-20 | 2019-10-20 | 2020-10-10 | 2020-10-10 | circuit based plan 2.14 | 2020-04-17 | Auburn |  | 153082106 | 32633.66 | 25668.1 |  |  |  | 11970 |  | 11970 |  | Y | 11/2 in MPP Import File | N | Tag in Closure Status | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117071722 | POLE_BROK_REPL - GP AT 6061 JOHNTWON CRE | 35142119 |  |  | STS-POLE_BROK_REPL - GP AT 6061 JOHNTWON | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8228 | -120.8686 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1421 |  | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 59.6 | 59.6 |  |  | 0 | 59.6 | 59.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100087426 | RELW OH SEC RESD FIRE ESTR PROG FMOB TER2 PRTO | Pole | 2020-05-28 | 2020-07-30 | COMP | 2020-05-28 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 153082106 | 9683.8 | 3296.1 | 460.1 | 460.1 | 460.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117072820 | POLE_DECA_REPL - 1N/O 6001 JOHNTWON CREE | 35142117 |  |  | STS-POLE_DECA_REPL - 1N/O 6001 JOHNTWON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8249 | -120.8697 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1421 | 6053 | Y | 311 |  |  | 2021-04-07 07:00 | 2021-04-07 16:00 | Scheduled | CLICK | [6 empty] | 78.7 | 78.7 |  |  | 0 | 78.7 | 78.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100055923 | RELW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-07-06 | 2020-09-04 | COMP | 2020-07-06 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 58778.3 | 329.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117073434 | POLE_BROK_REPL - 1S/O ENTRANCE AT 5960 J | 35142117 |  |  | STS-POLE_DECA_REPL - 1N/O 6001 JOHNTWON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8257 | -120.8694 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1421 | 6053 | Y | 311 |  |  | 2021-04-07 07:00 | 2021-04-07 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055922 | REGW OH PRI RESD FIRE TER2 ESTR FMOB PRTO | Pole | 2020-07-06 | 2020-09-04 | COMP | 2020-07-06 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 58778.3 | 329.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117073435 | POLE_BROK_REPL - GP AT 5960 JOHNTWON CRE | 35142117 |  |  | STS-POLE_DECA_REPL - 1N/O 6001 JOHNTWON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8258 | -120.8698 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1421 |  | Y | 311 |  |  | 2021-04-07 07:00 | 2021-04-07 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055921 | REGW OH SEC RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-07-06 | 2020-09-04 | COMP | 2020-07-06 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 58778.3 | 329.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117075660 | POLE_DECA_REPL - 1W/O HOUSE 5601 MT MURP | 35141694 |  |  | STS-POLE_DECA_REPL - 1N/O ENTRANCE 5501 | FICL | FICL SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8427 | -120.874 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1315 |  | Y | 311 |  |  | 2020-06-11 | 2020-06-11 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 4 | 0 | 0 | 151 | 151 |  |  |  | 150 | 150 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100111381 | REGW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-02-19 | 2020-04-15 | COMP | 2020-02-19 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-22 | 2020-04-22 |  | 2020-04-22 | circuit based plan 2.14 | 2020-04-20 | Auburn |  | 153082106 | 98262.82 | 102130.1 |  |  |  | 16712.2 |  | 16712.2 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117076725 | POLE_BROK_REPL - 5601 JOHNTOWN RD GARDEN | 35141938 |  |  | STS-POLE_BROK_REPL - 5601 JOHNTOWN RD GA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8371 | -120.8726 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1416 | 6053 | Y | 311 |  |  | 2021-04-09 07:00 | 2021-04-09 16:00 | Scheduled | CLICK | [6 empty] | 76.3 | 76.3 |  |  | 10 | 76 | 76 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055845 | RELW OH PRI INSP CLR JPOL RESD REMT ESTR TER2 | Pole | 2020-10-30 | 2020-10-30 | COMP | 2020-10-30 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-11 | 2020-04-11 |  | 2020-04-11 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 46290.05 | 2516.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117084187 | POLE_BROK_REPL - R/O HOUSE 5151 A BAR A | 35141695 |  |  | STS-POLE_BROK_REPL - R/O HOUSE 5151 A BA | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.847 | -120.8728 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1411 | 31125 | Y | 311 |  |  | 2020-08-25 | 2020-08-25 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 4 | 0 | 0 | 106.6 | 106.6 |  |  |  | 106.1 | 106.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100108709 | RELW OH PRI CLR JPOL REMT ESTR REAR FMOB TER2 PRTO | Pole | 2020-07-09 | 2020-07-09 | COMP | 2020-02-13 | COMP | 2020-08-21 | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | circuit based plan 2.14 | 2020-04-22 | Auburn |  | 153082106 | 60777.75 | 128594.8 | -58800 | -58800 | -58800 | 37005.3 |  | 37005.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117086611 | POLE_BROK_REPL - 6321 JOHNSTOWN CREEK RD | 35142505 |  |  | POLE_BROK_REPL - 6321 JOHNSTOWN CREE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.816 | -120.8685 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1401 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 117.7 | 117.7 |  |  | 0 | 117.7 | 117.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100063089 | RELW OH PRI CLR JPOL REMT FLAG ESTR BTKA REAR FMOB TER2 PRTO | Pole | 2021-01-12 | 2021-01-12 | COMP | 2020-10-03 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117086613 | POLE_BROK_REPL - AT 6241 JOHNSTON CREEK | 35142505 |  |  | POLE_BROK_REPL - 6321 JOHNSTOWN CREE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8173 | -120.868 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1401 | 18875 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100063093 | REGW OH PRI CLR JPOL REMT FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2021-01-12 | 2021-01-12 | COMP | 2020-10-03 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117095227 | POLE_BROK_REPL - 2S/W 1S/O C/O HANCOCK C | 35141938 |  |  | STS-POLE_BROK_REPL - 5601 JOHNTOWN RD GA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8367 | -120.8711 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1416 | 6053 | Y | 311 |  |  | 2021-04-09 07:00 | 2021-04-09 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055836 | REGW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-10-30 | 2020-10-30 | COMP | 2020-10-30 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 46290.05 | 2516.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117100768 | POLE_BROK_REPL - 1N/E ENTRANCE AT 4972 H | 35143939 |  |  | STS-POLE_BROK_REPL - 1N/E ENTRANCE AT 49 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8522 | -120.8446 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1409 |  | Y | 311 |  |  | 2021-04-08 07:00 | 2021-04-08 16:00 | Scheduled | CLICK | [6 empty] | 42.8 | 42.8 |  |  | 0 | 42.8 | 42.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100108683 | RELW OH PRI CLR RESD REMT REAR SCOP SCPA FMOB TER2 PRTO | Pole | 2020-01-03 | 2020-02-03 | COMP | 2020-01-03 | [16 empty] | 2019-04-25 | 2019-12-31 |  | 2019-12-31 | 2021 CBP Plan | 2020-04-25 | Auburn |  | 153082106 | 20740.86 | 14175.8 |  |  |  | 110.3 |  | 110.3 |  | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117100999 | POLE_BROK_REPL - AT 6650 PROVIDECE HILL | 35137212 |  |  | STS-POLE_DECA_REPL - A/F 6301 ROLLER COA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8222 | -120.865 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1402 | 3047 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 101.4 | 101.4 |  |  | 0 | 101.4 | 101.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100078954 | REGW OH REMT PRI CLR JPOL FLAG ESTR BTKA REAR USA FMOB TER2 PRTO | Pole | 2020-06-04 | 2020-08-18 | COMP | 2020-06-04 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 43744.96 | 347 |  |  |  | 46.2 |  | 46.2 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117101023 | POLE_BROK_REPL - 1NWO 6230 ROLLER COASTE | 35137212 |  |  | STS-POLE_DECA_REPL - A/F 6301 ROLLER COA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8172 | -120.8623 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1402 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100078933 | REGW OH PRI CLR JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-06-04 | 2020-08-18 | COMP | 2020-06-04 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 43744.96 | 347 |  |  |  | 46.2 |  | 46.2 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117101025 | POLE_BROK_REPL - 6151 CHRYSLER CIRGARDEN | 35137212 |  |  | STS-POLE_DECA_REPL - A/F 6301 ROLLER COA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8204 | -120.8639 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1402 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100078949 | REGW OH PRI CLR JPOL REMT FLAG USA ESTR BTKA REAR FMOB TER2 PRTO | Pole | 2020-06-04 | 2020-08-18 | COMP | 2020-06-04 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 43744.96 | 347 |  |  |  | 46.2 |  | 46.2 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117103081 | POLE_BROK_REPL - AT 6740 HANCOCK RD/JOHN | 35141962 |  |  | STS-POLE_BROK_REPL - 2N/O F/O 6740 HANCO | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8333 | -120.8651 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1416 | 8577 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 54.6 | 54.6 |  |  | 1 | 53.6 | 53.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055892 | REGW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-07-06 | 2020-09-09 | COMP | 2020-07-06 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 37792.73 | 428.6 | 57.6 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117103093 | POLE_BROK_REPL - 2N/O F/O 6740 HANCOCK R | 35141962 |  |  | STS-POLE_BROK_REPL - 2N/O F/O 6740 HANCO | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8347 | -120.8649 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1417 | 8577 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055893 | RELW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-07-06 | 2020-09-09 | COMP | 2020-07-06 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-25 | 2020-04-25 |  | 2020-04-25 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 37792.73 | 428.6 | 57.6 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117106957 | POLE_BROK_REPL - 1NEO 6888 TAMALPAIS RD | 35142158 |  |  | STS-POLE_BROK_REPL - 1NEO 6888 TAMALPAIS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8175 | -120.8542 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1403 | 5985 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 62.2 | 62.2 |  |  | 10 | 52.2 | 52.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100078968 | RELW OH PRI CLR JPOL REMT TRAF FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-07-02 | 2020-08-29 | COMP | 2020-07-02 |  |  | 2020-07-09 | 2020-07-09 | [12 empty] | 2019-04-26 | 2020-04-26 |  | 2020-04-26 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 153082106 | 29427.26 | 5704.6 | 652.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117106964 | POLE_DECA_REPL - G/P 6895 TAMALPAIS RD G | 35142158 |  |  | STS-POLE_BROK_REPL - 1NEO 6888 TAMALPAIS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8181 | -120.8542 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1403 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100078970 | REGW OH PRI CLR JPOL REMT ESTR REAR FMOB TER2 PRTO | Pole | 2020-07-02 | 2020-08-29 | COMP | 2020-07-02 |  |  | 2020-07-09 | 2020-07-09 | [12 empty] | 2019-04-26 | 2020-04-26 |  | 2020-04-26 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 153082106 | 29427.26 | 5704.6 | 652.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117106971 | POLE_DECA_REPL - 6811 GARDEN PARK DR GAR | 35142159 |  |  | STS-POLE_DECA_REPL - 6811 GARDEN PARK DR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8219 | -120.8499 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1403 | 5983 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 54.7 | 54.7 |  |  | 0 | 54.7 | 54.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100079003 | RELW OH PRI CLR JPOL REMT FLAG ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-09-27 | 2021-01-08 | COMP | 2020-09-27 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-26 | 2020-04-26 |  | 2020-04-26 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 23878 | 45.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117112479 | POLE_DECA_REPL - 6256 PIKES PEAK CIR GAR | 35142501 |  |  | STS-POLE_DECA_REPL - 6256 PIKES PEAK CIR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8168 | -120.8495 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1403 | 5987 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 107.4 | 107.4 |  |  | 0 | 107.4 | 107.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100078960 | RELW OH PRI CLR JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-06-02 | 2020-08-19 | COMP | 2020-06-02 |  |  | 2020-07-09 | 2020-07-09 | [12 empty] | 2019-04-27 | 2020-04-27 |  | 2020-04-27 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 50417.3 | 1933.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117112505 | POLE_DECA_REPL - 6120 TAMALPAIS RDGARDEN | 35142501 |  |  | STS-POLE_DECA_REPL - 6256 PIKES PEAK CIR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8211 | -120.8498 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1403 | 5983 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100078965 | REGW OH PRI CLR ESTR JPOL REMT FLAG BTKA USA FMOB TER2 PRTO | Pole | 2020-06-02 | 2020-08-19 | COMP | 2020-06-02 |  |  | 2020-07-09 | 2020-07-09 | [12 empty] | 2019-04-27 | 2020-04-27 |  | 2020-04-27 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 50417.3 | 1933.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117120171 | POLE_BROK_REPL - 6207 SHASTA DR GARDEN V | 35137216 |  |  | STS-POLE_BROK_REPL - 6207 SHASTA DR GARD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8184 | -120.8465 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1404 |  | Y | 311 |  |  | 2021-04-05 07:00 | 2021-04-05 16:00 | Scheduled | CLICK | [6 empty] | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100079027 | PRI RELW OH CLR JPOL REMT FLAG ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-06-29 | 2020-08-22 | COMP | 2020-06-29 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 13350.55 | 4871.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117120174 | POLE_BROK_REPL - G/P 7075 PYRAMID CT GAR | 35137217 |  |  | STS-POLE_BROK_REPL - G/P 7075 PYRAMID CT | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8221 | -120.8474 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1404 |  | Y | 311 |  |  | 2021-02-19 07:00 | 2021-02-19 16:00 | Completed | CLICK | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100079016 | RELW OH PRI CLR JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-05 | 2020-08-07 | COMP | 2020-06-15 |  |  | 2020-08-07 | 2020-08-07 | [12 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | circuit based plan 2.14 | 2020-06-30 | W. Sac |  | 153082106 | 9655.63 | 8999.7 | 626.9 | 626.9 | 626.9 | 338.8 |  | 338.8 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117152558 | POLE_BROK_REPL - 1S/O 5331 GARDEN VALLEY | 35141937 |  |  | STS-POLE_BROK_REPL - 1S/O 5331 GARDEN VA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8406 | -120.8541 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1413 |  | Y | 311 |  |  | 2021-03-18 07:00 | 2021-03-18 16:00 | Scheduled | CLICK | [6 empty] | 53.8 | 53.8 |  |  | 0.5 | 53.3 | 53.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055970 | RELW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-08-25 | 2020-11-05 | COMP | 2020-08-22 |  |  | 2020-10-28 | 2020-10-28 | [12 empty] | 2019-05-03 | 2020-05-03 |  | 2020-05-03 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 46755.16 | 25.7 | 25.7 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117152576 | POLE_BROK_REPL - AT 5331 GARDEN VALLEY R | 35141937 |  |  | STS-POLE_BROK_REPL - 1S/O 5331 GARDEN VA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8415 | -120.8545 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1413 | 4163 | Y | 311 |  |  | 2021-03-18 07:00 | 2021-03-18 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055967 | REGW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-08-25 | 2020-11-05 | COMP | 2020-08-22 |  |  | 2020-10-28 | 2020-10-28 | [12 empty] | 2019-05-03 | 2020-05-03 | 2021-06-30 | 2021-06-30 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 46755.16 | 25.7 | 25.7 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117164787 | POLE_BROK_REPL - AT ENTRANCE 5845 BARTON | 35142150 |  |  | STS-POLE_BROK_REPL - AT ENTRANCE 5845 BA | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8284 | -120.8422 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1424 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Dispatched | CLICK | [6 empty] | 42.8 | 42.8 |  |  | 0 | 42.8 | 42.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100110638 | RELW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-07-02 | 2020-09-19 | COMP | 2020-07-02 | [16 empty] | 2019-05-05 | 2020-05-05 |  | 2020-05-05 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 153082106 | 11794.25 | 1364.4 | 1364.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117181617 | POLE_DECA_REPL - AT HOUSE 5301 A BAR A/M | 35141933 |  |  | STS-POLE_DECA_REPL - AT HOUSE 5301 A BAR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8461 | -120.8708 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1411 | 1713 | Y | 311 |  |  | 2021-04-08 07:00 | 2021-04-08 16:00 | Scheduled | CLICK | [6 empty] | 43.7 | 43.7 |  |  | 0 | 43.7 | 43.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100108705 | RELW OH PRI CLR RESD REMT ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-06-29 | 2020-08-24 | COMP | 2020-06-29 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117182569 | POLE_BROK_REPL - ETRANCE AT 5000 MARSHAL | 35141929 |  |  | STS-POLE_BROK_REPL - ETRANCE AT 5000 MAR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 38.8533 | -120.8587 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1407 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.8 | 42.8 |  |  | 0 | 42.8 | 42.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100108402 | RELW OH PRI CLR RESD REMT ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-04-21 | 2020-07-03 | COMP | 2020-04-20 |  |  | 2020-04-24 | 2020-04-24 | [12 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-31 | Auburn |  | 153082106 | 14490.08 | 2167.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117206867 | POLE_BROK_REPL - N/O ENTRANCE AT 5583 GA | 35153327 |  |  | STS-POLE_BROK_REPL - N/O ENTRANCE AT 558 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8348 | -120.8489 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V14 | 2518 | Y | 311 |  |  | 2021-03-19 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 44.6 | 44.6 |  |  | 0 | 44.6 | 44.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100056145 | RELW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-05-01 | 2020-09-04 | COMP | 2020-03-05 |  |  | 2020-02-27 | 2020-02-27 | [12 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan |  | Auburn |  | 153082106 | 25792.64 | 2957.1 |  |  |  | 80.3 |  | 80.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117220649 | POLE_BROK_REPL - AT R/O HOUSE 5159 GARDE | 35141937 |  |  | STS-POLE_BROK_REPL - 1S/O 5331 GARDEN VA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8468 | -120.8554 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1413 | 4161 | Y | 311 |  |  | 2021-03-18 07:00 | 2021-03-18 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100111047 | REGW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-08-25 | 2020-11-05 | COMP | 2020-08-22 |  |  | 2020-10-28 | 2020-10-28 | [12 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 46755.16 | 25.7 | 25.7 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117220653 | POLE_BROK_REPL - AT R/O HOUSE 5201 TOWNZ | 35141936 |  |  | -POLE_DECA_REPL - 2E/O 3S/O AT 514 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8441 | -120.8578 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1412 | 4159 | Y | 311 |  |  | 2021-04-09 07:00 | 2021-04-09 16:00 | Scheduled | CLICK | [6 empty] | 52.8 | 52.8 |  |  | 0 | 52.8 | 52.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100108717 | REGW OH PRI ESTR RESD FIRE RTRN FMOB TER2 PRTO | Pole | 2020-11-24 | 2020-11-25 | COMP | 2020-09-25 |  |  | 2020-11-24 | 2020-11-24 | [12 empty] | 2019-05-12 | 2020-05-12 |  | 2020-05-12 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 35986.67 | 811.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117255112 | POLE_BROK_REPL - 4-P-W OF 6221 MT MURPHY | 35137218 |  |  | STS-POLE_BROK_REPL - 4-P-W OF 6221 MT MU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8174 | -120.8793 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W13 | 18875 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 128 | 128 |  |  | 10 | 122.8 | 122.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101382444 | RELW OH PRI INSP CLR JPOL RESD REMT TRAF FLAG ESTR BTKA USA FMOB TER2 | Pole | 2020-08-19 | 2020-08-27 | COMP | 2020-06-30 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 153082106 | 46230.5 | 652.4 | 652.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117255257 | POLE_BROK_REPL - 7-P-W OF 6221 MT MURPHY | 35137218 |  |  | STS-POLE_BROK_REPL - 4-P-W OF 6221 MT MU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8157 | -120.8783 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W13 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101382441 | REGW OH PRI REMT INSP CLR JPOL TRAF FLAG ESTR GO BTKA USA FMOB TER2 | Pole | 2020-08-19 | 2020-08-27 | COMP | 2020-06-30 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 153082106 | 46230.5 | 652.4 | 652.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117255568 | POLE_BROK_REPL - 1-P ON PROP 6340 MT MUR | 35137218 |  |  | STS-POLE_BROK_REPL - 4-P-W OF 6221 MT MU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8156 | -120.8792 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W13 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101382437 | REGW OH PRI INSP CLR JPOL REMT ESTR BTKA REAR FMOB TER2 | Pole | 2020-08-19 | 2020-08-27 | COMP | 2020-06-30 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 153082106 | 46230.5 | 652.4 | 652.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117269141 | POLE_BROK_REPL - 1NO 3WO 2SO 6441 LAZY B | 35137221 |  |  | STS-POLE_BROK_REPL - 6160 LYXN RIDGE RDG | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8141 | -120.8769 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W13 |  | Y | 311 |  |  | 2021-04-06 07:00 | 2021-04-06 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 3 | 102 | 102 |  |  |  | 102 | 102 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100100848 | OH REGW PRI INSP CLR JPOL REMT ESTR GO REAR FMOB TER2 | Pole | 2020-08-11 | 2020-08-27 | COMP | 2020-08-11 | COMP | 2021-02-09 | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 153082106 | 66210.94 | 7333.8 | 1442.1 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117269707 | POLE_BROK_REPL - G/P 1NO 3WO 3SO 6441 LA | 35137222 |  |  | STS-POLE_BROK_REPL - G/P 1NO 3WO 3SO 644 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8134 | -120.8766 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W13 |  | Y | 311 |  |  | 2021-04-06 07:00 | 2021-04-06 16:00 | Scheduled | CLICK | [6 empty] | 66 | 66 |  |  | 0 | 66 | 66 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100100850 | RELW OH SEC INSP CLR JPOL REMT ESTR REAR FMOB TER2 | Pole | 2020-07-20 | 2020-09-16 | COMP | 2020-07-20 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117305857 | POLE_BROK_REPL - G/P AT 5550 POOHS PATH | 35142155 |  |  | STS-POLE_BROK_REPL - G/P AT 5550 POOHS P | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8193 | -120.8327 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W14 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100110565 | RELW OH SEC RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-09-04 | 2020-09-04 | COMP | 2020-09-04 | [16 empty] | 2019-05-23 | 2020-05-23 |  | 2020-05-23 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 10477.46 | 535.3 | 535.3 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117336671 | POLE_BROK_REPL - 5601 JOHNTOWN CREEK RD | 35141938 |  |  | STS-POLE_BROK_REPL - 5601 JOHNTOWN RD GA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8369 | -120.8727 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1416 |  | Y | 311 |  |  | 2021-04-09 07:00 | 2021-04-09 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055846 | REGW OH SEC JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-30 | 2020-10-30 | COMP | 2020-10-30 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-29 | 2020-05-29 |  | 2020-05-29 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 46290.05 | 2516.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | Garden Valley | Auburn |  |  | OPEN | 117682112 | POLE_DECA_REPL - G/P 6860 OLYMPUS DR GAR | 35148078 |  |  | STS-POLE_DECA_REPL - G/P 6860 OLYMPUS DR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8225 | -120.853 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1403 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.5 | 18.5 |  |  | 0 | 18.5 | 18.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100078992 | RELW OH PRTO PRI ESTR TER2 | Pole | 2020-07-02 | 2020-09-25 | COMP | 2020-07-02 | [16 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 12681.56 | 94.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117682468 | POLE_BROK_REPL - 1N/O 1N/W AT HOUSE 5100 | 35148079 |  |  | STS-POLE _BROK _REPL_1N/O 1N/W AT HOUSE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8435 | -120.8515 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1413 |  | Y | 311 |  |  | 2021-04-05 07:00 | 2021-04-05 16:00 | Scheduled | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100108752 | RELW OH PRI ESTR TER2 PRTO | Pole | 2020-08-08 | 2020-09-16 | COMP | 2020-08-08 | [16 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 22796.6 | 550.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117071699 | POLE_DECA_REPL - GP AT 6029 JOHNTWON CRE | 35142116 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8233 | -120.8691 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1421 |  | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 64.1 | 64.1 |  |  | 0 | 64.1 | 64.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100056016 | RELW OH SEC RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2021-01-31 | 2021-01-31 | COMP | 2020-09-27 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 30024.59 | 21.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117071756 | POLE_DECA_REPL - F/O 6001 JOHNTWON CREEK | 35142116 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.824 | -120.8697 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1421 | 18875 | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100055924 | REGW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2021-01-31 | 2021-01-31 | COMP | 2020-09-27 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 30024.59 | 21.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117072814 | POLE_BROK_REPL - GP AT 6001 JOHNTWON CRE | 35142116 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.824 | -120.8693 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1421 |  | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100055925 | REGW OH SEC RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2021-01-31 | 2021-01-31 | COMP | 2020-09-27 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 30024.59 | 21.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117074477 | POLE_DECA_REPL - AT ENTRANCE 5941 CHRYSL | 35142200 |  |  | STS-POLE_DECA_REPL - AT ENTRANCE 5941 CH | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8263 | -120.8664 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1421 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | [6 empty] | 33.1 | 33.1 |  |  | 21 | 13 | 13 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100055932 | RELW OH PRI JPOL RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-07-13 | 2020-12-12 | COMP | 2020-07-13 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-22 | 2020-04-22 |  | 2020-04-22 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 15737.14 | 4672 | 4672 | 3309.2 | 3309.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117086603 | POLE_BROK_REPL - 2NO 6115JOHNSTOWN CREEK | 35142504 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8217 | -120.8683 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1401 |  | Y | 311 |  |  | 2021-04-22 07:00 | 2021-04-22 16:00 | Scheduled | CLICK | [6 empty] | 19.1 | 19.1 |  |  | 0 | 19.1 | 19.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100063105 | RELW OH PRI CLR JPOL REMT ESTR BTKA PRTO FMOB TER2 | Pole | 2020-10-02 | 2021-01-22 | COMP | 2020-07-26 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 11952.88 | 90.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117109366 | POLE_DECA_REPL - 3074 CONIFER CT GARDEN | 35141697 |  |  | STS-POLE_DECA_REPL - 3074 CONIFER CT GAR | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8712 | -120.8716 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | U1421 |  | Y | 311 |  |  | 2020-06-25 | 2020-06-25 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 4 | 0 | 0 | 129 | 129 |  |  |  | 127 | 127 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100049022 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-01-12 | 2020-03-25 | COMP | 2020-01-12 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-26 | 2020-04-26 |  | 2020-04-26 | Per DOT Approved Request 45778 | 2020-04-24 | Auburn |  | 153082106 | 61611.13 | 60113.4 | -20921.7 | -20921.7 | -20921.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2021-02-06
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117116586 | POLE_DECA_REPL - A/F 1EO C/O SAN GORGONI | 35137214 |  |  | STS-POLE_DECA_REPL - A/F 1EO C/O SAN GOR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8191 | -120.8472 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1404 |  | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 25.1 | 25.1 |  |  | 0 | 25.1 | 25.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100079014 | RELW OH PRI CLR JPOL REMT BTKA FLAG ESTR USA FMOB TER2 PRTO | Pole | 2020-07-03 | 2021-02-10 | COMP | 2020-06-25 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-28 | 2020-04-28 |  | 2020-04-28 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117146146 | POLE_DECA_REPL - 1S/O 5485 RAINIER DR/GA | 35142110 |  |  | STS-POLE_DECA_REPL - 1S/O 5485 RAINIER D | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8367 | -120.8568 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1418 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 68.5 | 68.5 |  |  | 0 | 68.5 | 68.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100055998 | RESD RELW OH PRI FIRE ESTR GO FMOB TER2 PRTO | Pole | 2020-12-31 | 2020-12-31 | COMP | 2020-11-02 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-02 | 2020-05-02 |  | 2020-05-02 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 32236.28 | 10052.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117146163 | POLE_DECA_REPL - F/O 5655 GARDEN PARK DR | 35142111 |  |  | STS-POLE_DECA_REPL - F/O ENTRANCE AT 551 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8323 | -120.8554 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1418 | 6921 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 132.9 | 132.9 |  |  | 0 | 132.9 | 132.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100055990 | REGW OH PRI RESD FIRE ESTR GO FMOB TER2 PRTO | Pole | 2020-11-02 | 2020-12-23 | COMP | 2020-10-30 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-02 | 2020-05-02 |  | 2020-05-02 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 65653.81 | 8060.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117159502 | POLE_BROK_REPL - GP AT HOUSE 4131 GARDEN | 35208520 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8289 | -120.8466 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1424 |  | Y | 311 |  |  | 2021-04-27 07:00 | 2021-04-27 16:00 | Scheduled | CLICK | [6 empty] | 37.1 | 37.1 |  |  | 0 | 37.1 | 37.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100108972 | RELW OH SEC RESD FIRE GO SCOP FMOB TER2 PRTO SCPA | Pole | 2020-11-24 | 2021-01-12 | COMP | 2020-11-24 | [16 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | Per DOT Approved Request 31409 |  | Auburn |  | 153082106 | 20038.04 | 5364.7 | [7 empty] | N | MPP File Only | N |  | Y | 2021-01-28
North | SI | GARDEN VALLEY | Auburn |  |  | OPEN | 117164778 | POLE_DECA_REPL - 1S/O AT 5485 RAINIER DR | 35142110 |  |  | STS-POLE_DECA_REPL - 1S/O 5485 RAINIER D | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8375 | -120.8567 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1418 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100055999 | REGW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-12-31 | 2020-12-31 | COMP | 2020-11-02 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-05 | 2020-05-05 |  | 2020-05-05 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 32236.28 | 10052.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | Garden Valley | Auburn |  |  | OPEN | 117681971 | POLE _BROK _REPL_R/O 5755 GARDEN PARK DR | 35148107 |  |  | STS-POLE _BROK _REPL_R/O 5755 GARDEN PAR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8302 | -120.8525 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1423 |  | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 19.1 | 19.1 |  |  | 0 | 19.1 | 19.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100056137 | RELW OH PRI ESTR TER2 PRTO | Pole | 2020-07-02 | 2021-02-05 | COMP | 2020-07-02 | [16 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 8242.13 | 38.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GARDEN VALLEY | Placerville |  |  | OPEN | 117682111 | POLE _BROK _REPL_A/F 6295 ROLLER COASTER | 35148109 |  |  | STS-POLE _BROK _REPL_A/F 6295 ROLLER COA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8155 | -120.8607 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1402 |  | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 25.2 | 25.2 |  |  | 0 | 25.2 | 25.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100078928 | RELW OH PRI ESTR GO TER2 PRTO | Pole | 2020-10-14 | 2021-02-09 | COMP | 2020-10-14 |  |  | 2020-07-09 | 2020-07-09 | [12 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 14091.48 | 3154.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | Missing COMP / CNCL | 117682392 | POLE_BROK_REPL - 4N/O WILD OAK CAMP GRAS | 35216207 |  |  | STS-POLE_BROK_REPL - 4N/O WILD OAK CAMP | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 |  | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.1428 | -121.1115 |  | TIER 2 | 544 | 15203-1103, GRASS VALLEY | O07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 1 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100103375 | PRI OH RELW ESTR TER2 PRTO FSRP ERR | Pole |  |  | REQD | [16 empty] | 2020-12-09 | 2020-12-09 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152031103 | 1 | 129.6 | 129.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 110433702 | POLE_BROK_REPL - 15615 HUMMER LN (C/O PO | 35165557 |  |  | STS-POLE_BROK_REPL - 15615 HUMMER LN (C/ | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.143 | -121.0891 |  | TIER 2 | 544 | 15203-1103, GRASS VALLEY | O08 | 2180 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24 | 24 |  |  | 0 | 24 | 24 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100112575 | RELW OH PRI CREW JPOL REMT NOAC ESTR GO TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2015-06-01 | 2020-06-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 152031103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116636901 | POLE_DECA_REPL - 15186 1W/O KIWE RDGRASS | 35090981 |  |  | STS-POLE_DECA_REPL - 15186 1W/O KIWE RDG | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 39.14 | -121.0824 |  | TIER 2 | 544 | 15203-1103, GRASS VALLEY | O08 | 7787 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.6 | 38.6 |  |  | 0 | 38.6 | 38.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100114037 | RELW OH PRI CLR JPOL FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2019-12-10 |  | COMP | 2019-12-10 | [16 empty] | 2019-03-05 | 2020-03-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-30 | QUES |  | 152031103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116721727 | POLE_BROK_REPL - NW/0 16290 LOWER COLFAX | 35133830 |  |  | STS-POLE_BROK_REPL - NW/0 16290 LOWER CO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.1594 | -120.9785 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1112 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 60.3 | 60.3 |  |  | 0 | 60.3 | 60.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100106768 | RELW OH PRI JPOL FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-22 |  | COMP | 2021-02-22 |  |  | 2019-12-03 | 2019-12-03 | [12 empty] | 2019-03-13 | 2020-03-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 152481106 | 14858.74 | 320 |  |  |  | 50.4 |  | 50.4 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116746892 | POLE_DECA_REPL - 16551 PERIMETER RDGRASS | 35187709 |  |  | STS-POLE_DECA_REPL - 16551 PERIMETER RDG | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.0765 | -121.1848 |  | TIER 2 | 432 | 15269-1109, HIGGINS | Q0607 | 32873 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.7 | 38.7 |  |  | 0 | 38.7 | 38.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100092154 | RELW OH PRI JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-10-27 |  | COMP | 2020-10-27 | [16 empty] | 2019-03-15 | 2020-03-15 | 2020-11-10 | 2020-11-10 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 152691109 | 19650.69 | 1450.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116747611 | POLE_BROK_REPL - 1/S C/0 7087 MT LION DR | 35133866 |  |  | STS-POLE_BROK_REPL - 1/S C/0 7087 MT LIO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1369 | -120.9815 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1122 | 50015 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 61 | 61 | 0 |  | 0 | 61 | 61 | 0 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100012661 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-11-03 | 2020-12-16 | COMP | 2020-11-03 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-03-16 | 2020-03-16 |  | 2020-03-16 | 2021 CBP Plan | 2020-10-31 | QUES |  | 152481106 | 9274.18 | 1537.3 | 1175.3 | 1175.3 | 1175.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116752677 | POLE_BROK_REPL - 24354 RESTIVE WAYGRASS | 35214950 |  |  | STS-POLE_BROK_REPL - 24354 RESTIVE WAYGR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.0687 | -121.17 |  | TIER 2 | 432 | 15269-1109, HIGGINS | Q0613 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100094751 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152691109 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116817437 | POLE_BROK_REPL - A/F 18178 RETRAC WY CO# | 35188213 |  |  | STS-POLE_BROK_REPL - A/F 18178 RETRAC WY | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.1089 | -121.0906 |  | TIER 2 | 395 | 15269-1103, HIGGINS | P0818 | 9895 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 40.3 | 40.3 |  |  | 0 | 40.3 | 40.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100013760 | RELW OH PRI CLR RESD FIRE ESTR FMOB TER2 PRTO FSRP | Pole | 2020-11-16 |  | COMP | 2020-11-16 | [16 empty] | 2019-03-23 | 2020-03-23 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 152691103 | 28191.54 | 1697.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116819157 | POLE_DECA_REPL - 11351 SQUIRREL CREEK RD | 35083465 |  |  | STS-POLE_DECA_REPL - 11351 SQUIRREL CREE | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.2224 | -121.0859 |  | TIER 2 | 342 | 15248-1110, BRUNSWICK | N0804 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100076569 | RELW OH SEC JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2019-05-14 | 2019-05-14 | [12 empty] | 2019-03-23 | 2019-09-23 | 2021-04-16 | 2021-04-16 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 152481110 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116826962 | POLE_DECA_REPL - 3PN 22445 PERIMETER RD | 35188351 |  |  | STS-POLE_DECA_REPL - 3PN 22445 PERIMETER | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.0532 | -121.246 |  | TIER 2 | 432 | 15269-1109, HIGGINS | Q04 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.8 | 17.8 |  |  | 0 | 17.8 | 17.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103828645 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-09-02 |  | COMP | 2020-09-02 | [16 empty] | 2019-03-25 | 2020-03-25 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 152691109 | 7620.9 | 1203.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116847529 | POLE_DECA_REPL - 2W/O 11550 MUSHROOM TRA | 35188477 |  |  | STS-POLE_DECA_REPL - 2W/O 11550 MUSHROOM | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 39.2102 | -121.1424 |  | TIER 2 | 109 | 15313-2105, NARROWS | N07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.3 | 16.3 |  |  | 0 | 16.3 | 16.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100076801 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-10-05 |  | COMP | 2020-10-05 | [16 empty] | 2019-03-27 | 2020-03-27 |  | 2020-03-27 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 11247.76 | 1024 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116848992 | POLE_BROK_REPL - 11288 ALPINE LN GRASS V | 35188496 |  |  | STS-POLE_BROK_REPL - 11288 ALPINE LN GRA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.216 | -121.0832 |  | TIER 2 | 342 | 15248-1110, BRUNSWICK | N0809 | 3907 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.7 | 38.7 |  |  | 0 | 38.7 | 38.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100076534 | RELW PRI OH JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-10-28 |  | COMP | 2020-10-28 | [16 empty] | 2019-03-27 | 2020-03-27 | 2020-10-16 | 2020-10-16 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 152481110 | 19599.76 | 1530.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116853374 | POLE_BROK_REPL - R/O 11322 BUTLER RD GRA | 35188509 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2151 | -121.0846 |  | TIER 2 | 342 | 15248-1110, BRUNSWICK | N0809 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 23.8 | 23.8 |  |  | 0 | 23.8 | 23.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100107922 | RELW OH SEC JPOL RESD NOAC ESTR GO FMOB TER2 PRTO FSRP | Pole | 2020-10-20 | 2020-12-12 | COMP | 2020-10-20 | [16 empty] | 2019-03-27 | 2020-03-27 | 2020-10-16 | 2020-10-16 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 152481110 | 13192.73 | 1349 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116865223 | POLE_BROK_REPL - A/F 11830 PADDOCK LNGRA | 35215404 |  |  | STS-POLE_BROK_REPL - A/F 11830 PADDOCK L | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.2016 | -121.0954 |  | TIER 2 | 544 | 15203-1103, GRASS VALLEY | N0812 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100087926 | RELW OH PRI RESD ESTR BTKA FMOB FSRP TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-04-11 | 2021-04-11 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152031103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116875104 | POLE_BROK_REPL - 4N/O 12206 MARA SERENA | 35215497 |  |  | STS-POLE_BROK_REPL - 4N/O 12206 MARA SER | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.1991 | -121.0994 |  | TIER 2 | 544 | 15203-1103, GRASS VALLEY | N0817 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100087979 | RELW OH PRI JPOL REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2021-04-11 | 2021-04-11 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152031103 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116938830 | POLE_BROK_REPL - E/0 13101 TWIN ESTAR LN | 35215938 |  |  | STS-POLE_BROK_REPL - E/0 13101 TWIN ESTA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.1831 | -121.09 |  | TIER 2 | 544 | 15203-1103, GRASS VALLEY | N0823 | 6579 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100080090 | OH PRI JPOL RESD REMT JAR FSRP RELW BTKA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-02 | 2020-04-02 | 2021-04-17 | 2021-04-17 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152031103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116972611 | POLE_BROK_REPL - WSIP GRASS VALLEY | 35214741 |  |  | STS-POLE_BROK_REPL - WSIP GRASS VALLEY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.069 | -121.0598 |  | TIER 2 | 596 | 15269-1104, HIGGINS | Q09 | 4281 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103686957 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-06 | 2020-04-06 | 2021-03-27 | 2021-03-27 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152691104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116972736 | POLE_DECA_REPL - 2SW/O ENT 19865 APPLEJA | 35214749 |  |  | STS-POLE_DECA_REPL - 2SW/O ENT 19865 APP | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.0895 | -121.0323 |  | TIER 2 | 596 | 15269-1104, HIGGINS | Q09 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103822428 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-06 | 2020-04-06 | 2021-03-29 | 2021-03-29 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152691104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116972742 | POLE_DECA_REPL - 3S/O 20721 SALT CRK RD | 35188490 |  |  | STS-POLE_DECA_REPL - 3S/O 20721 SALT CRK | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.0727 | -121.0557 |  | TIER 2 | 596 | 15269-1104, HIGGINS | Q09 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31 | 31 |  |  | 0 | 31 | 31 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100019308 | RELW OH PRI JPOL PUBL RESD TRAF ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-15 |  | COMP | 2020-12-15 | [16 empty] | 2019-04-06 | 2020-04-06 | 2020-06-27 | 2020-06-27 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 152691104 | 18117.55 | 1604.8 | -2013.4 | 158.6 | 158.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 117021125 | POLE_BROK_REPL - 1N/O ENTRANCE 16500 RAT | 35134068 |  |  | STS-POLE_BROK_REPL - 1N/O ENTRANCE 16500 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.1508 | -121.0331 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O0920 | 9059 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100101133 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-12-31 | QUES |  | 152481106 | 1 | 510.4 |  |  |  | 182.4 |  | 182.4 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 117064973 | POLE_BROK_REPL - 1N/O 1A/F 12108 E.BENNE | 35134083 |  |  | STS-POLE_BROK_REPL - 1N/O 1A/F 12108 E.B | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.2146 | -121.0254 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | N10 | 9789 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100080641 | RELW OH PRI CLR JPOL REMT FIRE ESTR REAR FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-19 | 2020-04-19 |  | 2020-04-19 | 2021 CBP Plan | 2020-10-31 | QUES |  | 152481106 | 1 | 961.1 | 266.5 |  |  | 243.4 |  | 243.4 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 117319195 | POLE_BROK_REPL - 2N/0 12733 0FF SCHR0EDE | 35134168 |  |  | STS-POLE_BROK_REPL - 2N/0 12733 0FF SCHR | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.1828 | -121.0543 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | N0923 | 9723 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 79.9 | 79.9 |  |  | 0 | 79.9 | 79.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100075752 | RELW OH PRI CLR JPOL RESD ESTR FMOB TER2 PRTO | Pole | 2021-01-12 |  | COMP | 2021-01-12 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-24 | 2020-05-24 |  | 2020-05-24 | 2021 CBP Plan | 2020-10-31 | QUES |  | 152481106 | 16520.67 |  | 0 | 1508 | 1508 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 118258601 | TREE_DECA_INPL - 14130 FREDERICK WAY GRA | 35189113 |  |  | STS-TREE_DECA_INPL - 14130 FREDERICK WAY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1686 | -120.9546 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O11 | 33279 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 9.4 | 9.4 |  |  | 0 | 9.4 | 9.4 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103388071 | RELW OH ESTR TER2 FSRP | Pole | 2020-10-19 | 2020-12-18 | COMP | 2020-10-16 | [16 empty] | 2019-11-26 | 2020-11-26 | 2024-11-24 | 2024-11-24 | 2021 CBP Plan | 2020-10-31 | VPI |  | 152481106 | 6486.64 | 1230.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 118404845 | TREE_DECA_INPL - 16500 RATTLESNAKE RD G | 35134068 |  |  | STS-POLE_BROK_REPL - 1N/O ENTRANCE 16500 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.1508 | -121.0331 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O0920 | 9059 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100101133 | POHW OH ESTR TER2 | Pole |  |  | REQD |  |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-11-12 | 2020-11-12 |  | 2020-11-12 | Pole Notification Clean Up 05.29.20 | 2020-12-31 | QUES |  | 152481106 | 1 | 510.4 |  |  |  | 182.4 |  | 182.4 |  | Y | MPP File Only | N |  | Y | 2020-06-02
North | SI | GRASS VALLEY | Grass Valley |  |  | COMP | 115778539 | POLE_BROK_REPL - 12263 APPALOOSA CT GRAS | 35075533 |  |  | STS-POLE_BROK_REPL - 12263 APPALOOSA CT | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.088 | -121.0436 |  | TIER 2 | 596 | 15269-1104, HIGGINS | Q09 | 7583 | Y | 311 |  |  | 2021-01-21 | 2021-01-21 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41 | 0.8 |  | 0 | 41.8 | 41 | 0.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 103822355 | RELW OH PRI CREW COMP CLR JPOL RESD NOAC ESTR CCNT TER2 FSRP | Pole | 2020-04-22 | 2020-06-18 | COMP | 2020-04-22 | COMP | 2021-01-21 | [13 empty] | 2021-02-01 | 2021-01-21 | 2019-12-03 | 2021-05-31 | 2021-05-31 | Program Manager | 2020-06-30 | Bakersfield |  | 152691104 | 24642.95 | 7744.7 | 4709.6 | 2239.3 | 2239.3 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-20
North | SI | GRASS VALLEY | Grass Valley |  |  | COMP | 116690872 | POLE_BROK_REPL - C/0 CLAIM JUMPR LN 0N S | 35133373 |  |  | STS-POLE_BROK_REPL - C/0 CLAIM JUMPR LN | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.155 | -120.9593 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1114 |  | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100012777 | OH RELW PRI COMP JPOL REMT FLAG ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-02-03 | 2020-06-05 | COMP | 2020-02-03 | COMP | 2021-01-08 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-01-19 | 2021-01-08 | 2020-03-09 |  | 2020-03-09 | circuit based plan 2.14 | 2020-01-09 | QUES |  | 152481106 | 16034.92 | 8193.5 | 4456.7 | 4073.5 | 4073.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | COMP | 116691006 | POLE_BROK_REPL - E/0 18206 SPRINGS VALLE | 35133376 |  |  | STS-POLE_BROK_REPL - E/0 18206 SPRINGS V | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.1564 | -120.9589 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1114 | 6455 | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0 | 1 | 1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100012781 | COMP RELW OH PRI REMT ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-07-07 | 2020-07-07 | COMP | 2020-02-06 | COMP | 2021-01-08 | 2020-01-22 | 2020-01-22 | [11 empty] | 2021-01-19 | 2021-01-08 | 2020-03-09 |  | 2020-03-09 | circuit based plan 2.14 | 2020-01-09 | QUES |  | 152481106 | 25590.69 | 14191 | 461.7 | 461.7 | 461.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | COMP | 116747312 | POLE_DECA_REPL - 1SW/0 14090 WAYLAND GRA | 35133863 |  |  |  | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.1645 | -120.9825 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1106 | 8671 | Y | 311 |  |  | 2021-01-07 | 2021-01-07 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 2 | 51 | 51 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100106498 | RELW OH PRI COMP JPOL RESD FIRE ESTR GO BTKA CCNT FMOB TER2 PRTO | Pole | 2020-01-24 | 2020-06-30 | COMP | 2020-01-24 | COMP | 2021-01-07 | 2020-06-30 | 2020-06-30 | [11 empty] | 2021-01-15 | 2021-01-07 | 2020-03-16 |  | 2020-03-16 | circuit based plan 2.14 | 2020-01-09 | QUES |  | 152481106 | 18882.23 | 13032.7 | 3771.1 | 3771.1 | 3771.1 | 269.6 |  | 269.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | COMP | 116789286 | POLE_BROK_REPL - S/P N/0 16214 MT OLIVE | 35133909 |  |  | STS-POLE_BROK_REPL - S/P N/0 16214 MT OL | DOCC | DOCC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.1453 | -120.9693 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1118 |  | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100012747 | RELW OH SERV COMP JPOL RESD FIRE ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-01-24 | 2020-09-08 | COMP | 2020-01-24 | COMP | 2021-02-11 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-02-18 | 2021-02-11 | 2020-03-20 |  | 2020-03-20 | 2021 CBP Plan | 2020-01-09 | QUES |  | 152481106 | 4467.64 | 982.2 | 895.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | COMP | 116879455 | POLE_DECA_REPL - 1W/O 1N/O A/F 18622 DOG | 35133943 |  |  | STS-POLE_DECA_REPL - 1W/O 1N/O A/F 18622 | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.1135 | -121.0017 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | P1014 |  | Y | 311 |  |  | 2021-01-21 | 2021-01-21 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 4 | 40.8 | 40.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100097788 | RELW OH PRI COMP CLR ESTR CCNT FMOB TER2 PRTO | Pole | 2020-06-04 | 2020-07-28 | COMP | 2020-03-23 | COMP | 2021-01-21 | 2019-12-03 | 2019-12-03 | [11 empty] | 2021-02-02 | 2021-01-21 | 2020-03-31 |  | 2020-03-31 | circuit based plan 2.14 | 2020-01-09 | QUES |  | 152481106 | 12226.12 | 7591.8 | 5716 | 3103.1 | 3103.1 | 133.6 |  | 133.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | COMP | 116978156 | POLE_BROK_REPL - 12844 S.MACK RD GRASS V | 35133972 |  |  | STS-POLE_BROK_REPL - 12844 S.MACK RD GRA | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.1803 | -121.0544 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O0903 | 9723 | Y | 311 |  |  | 2021-01-09 | 2021-01-09 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100067297 | RELW OH PRI COMP JPOL REMT ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-01-06 | 2020-07-27 | COMP | 2020-01-06 | COMP | 2021-01-09 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-01-19 | 2021-01-09 | 2020-04-08 |  | 2020-04-08 | circuit based plan 2.14 | 2020-01-09 | QUES |  | 152481106 | 18320.73 | 22813.1 | 18715.2 | 6823.6 | 6823.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | COMP | 117009874 | POLE_BROK_REPL - #2 ON LINE S/O 10106 FO | 35134046 |  |  | POLE_BROK_REPL - #2 ON LINE S/O 1010 | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.1756 | -121.0508 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O0903 |  | Y | 311 |  |  | 2021-02-08 07:00 | 2021-02-08 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0 | 1 | 1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103028673 | RELW OH PRI COMP JPOL REMT ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-06-05 | 2020-08-03 | COMP | 2020-06-05 | COMP | 2021-02-08 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-02-16 | 2021-02-08 | 2020-04-11 |  | 2020-04-11 | circuit based plan 2.14 | 2020-06-30 | QUES |  | 152481106 | 9490.15 | 7000.1 | 4719.2 | 3292.9 | 3292.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | COMP | 117064994 | POLE_BROK_REPL - 12477 OLD MINE RD GRASS | 35096072 |  |  | STS-POLE_BROK_REPL - 4W/O 12190 LOMA RIC | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.2131 | -121.0225 |  | TIER 2 | 139 | 15248-1102, BRUNSWICK | N10 | 30163 | Y | 311 |  |  | 2021-02-05 | 2021-02-05 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 4 | 0 |  |  |  | 4 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100080654 | REGW OH PRI COMP CLR JPOL REMT FIRE ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-01-10 | 2020-02-04 | COMP | 2020-01-10 | COMP | 2021-01-14 | 2019-10-15 | 2019-10-15 | [11 empty] | 2021-02-16 | 2021-02-05 | 2020-04-19 |  | 2020-04-19 | Pole Notification Clean Up 05.29.20 |  | Auburn |  | 152481102 | 62947.66 | 33134.5 | 13278.9 | 9798 | 9798 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-06-02
North | SI | GRASS VALLEY | Grass Valley |  |  | COMP | 117067794 | POLE_BROK_REPL - R/O 14214 WILBUR RIDGE | 35093275 |  |  | STS-POLE_BROK_REPL - R/O 14214 WILBUR RI | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.1598 | -121.0426 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O0914 | 33753 | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 1.8 | 1.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100104214 | RELW OH PRI COMP JPOL RESD CCNT TER2 ESTR BTKA FMOB PRTO | Pole | 2020-03-17 | 2020-05-19 | COMP | 2020-03-17 | COMP | 2021-01-13 | [13 empty] | 2021-01-21 | 2021-01-13 | 2019-10-14 |  | 2019-10-14 | circuit based plan 2.14 | 2020-01-09 | QUES |  | 152481106 | 18353.65 | 14398 | 10252.1 | 9889.9 | 9889.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | COMP | 117086082 | POLE_BROK_REPL - 11342 HIDDEN HAVEN LN G | 35134100 |  |  | STS-POLE_BROK_REPL - 11342 HIDDEN HAVEN | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-10-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.1565 | -121.0448 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O0914 | 7667 | Y | 311 |  |  | 2021-01-12 | 2021-01-12 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.2 | 41 | 0.2 |  | 3.5 | 0.2 |  | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100104144 | RELW OH PRI COMP JPOL RESD ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-03-20 | 2020-06-03 | COMP | 2020-03-20 | COMP | 2021-01-12 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-01-20 | 2021-01-12 | 2020-04-23 |  | 2020-04-23 | circuit based plan 2.14 | 2020-01-09 | QUES |  | 152481106 | 21103.2 | 19358.5 | 14715.6 | 14315.8 | 14315.8 | 166.8 |  | 166.8 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | COMP | 118009406 | TREE_DECA_INPL - 12368 E BENNETT RD GRAS | 35096072 |  |  | STS-POLE_BROK_REPL - 4W/O 12190 LOMA RIC | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.2131 | -121.0225 |  | TIER 2 | 139 | 15248-1102, BRUNSWICK | N10 | 30163 | Y | 311 |  |  | 2021-02-05 | 2021-02-05 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 4 | 0 |  |  |  | 4 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100080654 | POHW OH COMP ESTR CCNT TER2 | Pole | 2020-01-10 | 2020-02-04 | COMP | 2020-01-10 | COMP | 2021-01-14 | 2019-10-15 | 2019-10-15 | [11 empty] | 2021-02-16 | 2021-02-05 | 2020-10-14 |  | 2020-10-14 | Pole Notification Clean Up 05.29.20 |  | Auburn |  | 152481102 | 62947.66 | 33134.5 | 13278.9 | 9798 | 9798 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-06-02
North | SI | GRASS VALLEY | Grass Valley |  |  | COMP | 118149624 | TREE_DECA_INPL - 14090 WAYLAND RD GRASS | 35133863 |  |  |  | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 |  | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.1645 | -120.9825 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1106 | 8671 | Y | 311 |  |  | 2021-01-07 | 2021-01-07 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 2 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 0 | POHW OH COMP ESTR CCNT TER2 FSRP | Pole | 2020-01-24 | 2020-06-30 | COMP | 2020-01-24 | COMP | 2021-01-07 | 2020-06-30 | 2020-06-30 | [11 empty] | 2021-01-15 | 2021-01-07 | 2020-03-16 | 2024-10-19 | 2024-10-19 | Pole Notification Clean Up 05.29.20 | 2020-01-09 | QUES |  | 152481106 | 18882.23 | 13032.7 | 3771.1 | 3771.1 | 3771.1 | 269.6 |  | 269.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-06-02
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 115477173 | POLE_DECA_REPL - 15200 CLOVER VALLEY RD | 35210247 |  |  | B3 STS-POLE_DECA_REPL - 15200 CLOVER VAL | CONS | CONS SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-02-13 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1324 | -121.0314 |  | TIER 2 | 596 | 15269-1104, HIGGINS | P0905 | 4739 | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Scheduled | CLICK | [6 empty] | 41.6 | 40.2 | 1.4 |  | 0 | 41.6 | 40.2 | 1.4 |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100078043 | RELW OH PRI INSP JPOL REMT JAR NOAC REAR FMOB TER2 FSRP | Pole | 2020-11-19 | 2020-12-11 | COMP | 2020-11-19 | [16 empty] | 2018-12-06 | 2019-12-06 | 2021-03-13 | 2021-03-13 | B tag clean up 10/25/2020 |  | Auburn |  | 152691104 | 22617.31 | 4191.3 | 3641.6 | 1150.2 | 1150.2 |  |  |  | Electric Distribution | Y | Pulled from MPP Import File | N |  | Y | 2020-10-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 115781860 | POLE_BROK_REPL - 20514 OXBOW WAY GRASS V | 35075529 |  |  | STS-POLE_BROK_REPL - 20514 OXBOW WAY GRA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0768 | -121.0513 |  | TIER 2 | 596 | 15269-1104, HIGGINS | Q09 | 34063 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103822421 | RELW OH PRI CREW JPOL COMM NOAC ESTR TER2 FSRP | Pole | 2020-07-01 | 2020-08-28 | COMP | 2020-06-29 | [16 empty] | 2019-01-12 | 2019-10-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-07-31 | Bakersfield |  | 152691104 | 13659.75 | 1809.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116591276 | POLE_DECA_REPL - R/O 22998 MEYER RAVINE | 35090769 |  |  | STS-POLE_DECA_REPL - R/O 22998 MEYER RAV | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.043 | -121.1322 |  | TIER 2 | 432 | 15269-1109, HIGGINS | R07 | 32845 | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100090392 | RELW OH PRI CLR JPOL REMT CGI ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-02-24 | 2020-04-13 | COMP | 2020-02-24 | [16 empty] | 2019-02-24 | 2020-02-24 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2019-10-31 | QUES |  | 152691109 | 18150.61 | 2581.5 | 2507.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116626520 | POLE_DECA_REPL - AT 12540 SUTHERLAND DR | 35091393 |  |  | STS-POLE_DECA_REPL - AT 12540 SUTHERLAND | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1585 | -121.1073 |  | TIER 2 | 544 | 15203-1103, GRASS VALLEY | O08 | 8753 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 36.6 | 36.6 |  |  | 0 | 36.6 | 36.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100103050 | RELW OH PRI CLR FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2019-10-28 | 2019-11-15 | COMP | 2019-10-28 | [16 empty] | 2019-03-01 | 2020-03-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-30 | QUES |  | 152031103 | 15370.69 | 145.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116626870 | POLE_DECA_REPL - AT 12187 GILLHAM CT GRA | 35090124 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1553 | -121.1009 |  | TIER 2 | 544 | 15203-1103, GRASS VALLEY | O08 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 23.8 | 23.8 |  |  | 0 | 23.8 | 23.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100103083 | RELW OH SERV FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-01-06 | 2020-02-04 | COMP | 2020-01-06 | [16 empty] | 2019-03-02 | 2020-03-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-30 | QUES |  | 152031103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116626902 | POLE_DECA_REPL - 12177 GILLHAM CTGRASS V | 35090125 |  |  | STS-POLE_DECA_REPL - 12177 GILLHAM CTGRA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1549 | -121.1007 |  | TIER 2 | 544 | 15203-1103, GRASS VALLEY | O08 |  | Y | 311 |  |  | 2021-03-23 07:00 | 2021-03-23 16:00 | Scheduled | CLICK | [6 empty] | 22.8 | 22.8 |  |  | 0 | 22.8 | 22.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100114067 | RELW OH PRI CLR FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-01-08 | 2020-02-04 | COMP | 2020-01-08 | [16 empty] | 2019-03-02 | 2020-03-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-30 | QUES |  | 152031103 | 7341.7 | 867.8 | 788 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116627016 | POLE_DECA_REPL - 12199 AT GILLHAM CTGRAS | 35090139 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1546 | -121.1013 |  | TIER 2 | 544 | 15203-1103, GRASS VALLEY | O08 | 6927 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 41.5 | 41.5 |  |  | 0 | 41.5 | 41.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100103086 | RELW OH PRI CLR FIRE ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2020-01-24 | 2020-02-07 | COMP | 2020-01-24 | [16 empty] | 2019-03-02 | 2020-03-02 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2019-11-30 | QUES |  | 152031103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116628400 | POLE_BROK_REPL - 1S/O 11251 GOODRIDGE RD | 35091487 |  |  | STS-POLE_BROK_REPL - 1S/O 11251 GOODRIDG | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1447 | -121.0931 |  | TIER 2 | 544 | 15203-1103, GRASS VALLEY | O08 |  | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41 | 41 |  |  | 1 | 40 | 40 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100112578 | RELW OH PRI JPOL FIRE ESTR BTKA PRTO PROG FMOB TER2 FSRP | Pole | 2020-05-26 | 2020-05-26 | COMP | 2020-05-26 | [16 empty] | 2019-03-03 | 2020-03-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | QUES |  | 152031103 | 8364.65 | 1468.8 | 982.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116639948 | POLE_BROK_REPL - AT 15842 OLD AUBURN RD | 35091091 |  |  | STS-POLE_BROK_REPL - AT 15842 OLD AUBURN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1431 | -121.0775 |  | TIER 2 | 544 | 15203-1103, GRASS VALLEY | O0825 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.9 | 13.9 |  |  | 38 | 0.8 | 0.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100114202 | RELW OH SERV FIRE ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-01-21 | 2020-03-06 | COMP | 2020-01-21 | [16 empty] | 2019-03-06 | 2020-03-06 | 2024-03-04 | 2024-03-04 | Per DOT Approved Request 28449 | 2019-11-30 | QUES |  | 152031103 | 5981.62 | 7444.5 | [7 empty] | N | MPP File Only | N |  | Y | 2021-01-14
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116692092 | POLE_BROK_REPL - 3.S 17841 ROLLIN VIEW D | 35133823 |  |  | STS-POLE_BROK_REPL - 3.S 17841 ROLLIN VI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1596 | -120.9543 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1115 | 6455 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 82.1 | 81.9 | 0.2 |  | 0 | 82.1 | 81.9 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100099307 | RELW OH PRI INSP JPOL REMT ESTR BTKA RTRN FMOB TER2 FSRP | Pole | 2020-06-26 | 2020-08-26 | COMP | 2020-06-26 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-03-09 | 2020-03-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-31 | QUES |  | 152481106 | 23432.51 | 5429.6 |  |  |  | 4919.5 |  | 4919.5 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116742000 | POLE_DECA_REPL - 1.W 14865 CITDEL WAY GR | 35133861 |  |  | STS-POLE_DECA_REPL - 1.W 14865 CITDEL WA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1437 | -120.9879 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O11 | 8545 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.2 | 41 | 0.2 |  | 0 | 41.2 | 41 | 0.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100083809 | RELW OH PRI JPOL REMT ESTR REAR FMOB TER2 PRTO | Pole | 2020-01-31 | 2020-06-20 | COMP | 2020-01-31 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-03-15 | 2020-03-15 |  | 2020-03-15 | circuit based plan 2.14 | 2020-01-09 | QUES |  | 152481106 | 18599.18 | 4664 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116752410 | POLE_BROK_REPL - A/F 15538 MT OLIVE RD G | 35133877 |  |  | STS-POLE_BROK_REPL - A/F 15538 MT OLIVE | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1451 | -120.9813 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1117 |  | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100110784 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-07-30 | 2020-08-03 | COMP | 2020-03-25 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-03-17 | 2020-03-17 | 2024-03-15 | 2024-03-15 | circuit based plan 2.14 | 2020-01-09 | QUES |  | 152481106 | 25229.64 | 6524.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116755865 | POLE_BROK_REPL - NE/0 14045 OLD COACH WA | 35133901 |  |  | STS-POLE_BROK_REPL - NE/0 14045 OLD COAC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1517 | -120.9775 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1117 | 31251 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100110785 | RELW OH PRI REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-06-26 | 2020-06-26 | COMP | 2020-06-26 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-03-18 | 2020-03-18 | 2024-03-16 | 2024-03-16 | 2021 CBP Plan | 2020-05-31 | QUES |  | 152481106 | 15787.33 | 4298.6 | 1935.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116757322 | POLE_DECA_REPL - 1W/O 14012 WIGGINS WAY | 35178185 |  |  | B3 STS-POLE_DECA_REPL - 1W/O 14012 WIGGI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0682 | -121.1563 |  | TIER 2 | 432 | 15269-1109, HIGGINS | Q0615 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100092732 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-06-09 | 2020-06-09 | COMP | 2020-06-01 | [16 empty] | 2019-03-18 | 2020-03-18 | 2020-08-12 | 2020-08-12 | B-Tag Clean Up 6/8/2020 |  | Auburn |  | 152691109 | 14938.14 | 2658.9 | [7 empty] | N | 11/2 in MPP Import File | N | Access/Customer Issue - Unable to contact home owner | Y | 2020-06-08
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116804387 | POLE_BROK_REPL - 1NW/0 15563 ORCHARD SPR | 35133916 |  |  | STS-POLE_BROK_REPL - 1NW/0 15563 ORCHARD | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1488 | -120.9584 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1119 | 30541 | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100106065 | RELW OH PRI JPOL ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-06-15 | 2020-06-19 | COMP | 2020-03-25 |  |  | 2020-06-19 | 2020-06-19 | [12 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-01-09 | QUES |  | 152481106 | 17807.84 | 11588.5 | 7787.1 | 7507.9 | 7507.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116805403 | POLE_BROK_REPL - SSD C/0 31253 0FF HWY 1 | 35081341 |  |  | STS-POLE_BROK_REPL - SSD C/0 31253 0FF H | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1492 | -120.9667 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1118 | 779 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100012721 | RELW OH PRI JPOL RESD FIRE TRAF FMOB FLAG ESTR BTKA TER2 PRTO FSRP | Pole | 2020-06-30 | 2020-08-16 | COMP | 2020-06-30 |  |  | 2020-07-15 | 2020-07-15 | [12 empty] | 2019-03-21 | 2019-09-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 152481106 | 16347.88 | 1017.7 |  |  |  | 874.9 |  | 874.9 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116807386 | POLE_BROK_REPL - 10229 TURKEY TROT PL GR | 35178188 |  |  | B3 STS-POLE_BROK_REPL - 10229 TURKEY TRO | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1183 | -121.083 |  | TIER 2 | 395 | 15269-1103, HIGGINS | P0814 | 1711 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-08 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.9 | 41.9 |  |  | 6 | 40.9 | 40.9 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100017655 | RELW OH PRI CREW JPOL RESD ESTR REAR TER2 FSRP | Pole | 2020-07-24 | 2020-09-14 | COMP | 2020-06-05 | [16 empty] | 2019-02-26 | 2020-02-26 | 2020-08-15 | 2020-08-15 | B-Tag Clean Up 6/8/2020 |  | Auburn |  | 152691103 | 11296.46 | 13122.2 | 6676.7 | 6676.7 | 6676.7 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-06-08
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116811690 | POLE_DECA_REPL - 1SW/O GARDEN BAR RD ON | 35188134 |  |  | STS-POLE_DECA_REPL - 1SW/O GARDEN BAR RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0614 | -121.1607 |  | TIER 2 | 432 | 15269-1109, HIGGINS | Q0620 | 8985 | Y | 311 |  |  |  |  | Scheduled | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 39.4 | 39.4 |  |  | 0 | 39.4 | 39.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100094830 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-10-06 | 2020-10-06 | COMP | 2020-10-06 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 152691109 | 17824.83 | 1813.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116820151 | POLE_BROK_REPL - 3PE 20548 PERIMETER RD | 35188246 |  |  | STS-POLE_BROK_REPL - 3PE 20548 PERIMETER | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0534 | -121.2432 |  | TIER 2 | 432 | 15269-1109, HIGGINS | Q04 |  | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103828650 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-10-05 | 2020-11-24 | COMP | 2020-10-05 | [16 empty] | 2019-03-23 | 2020-03-23 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 152691109 | 9925.95 | 2239.5 | 1192.2 | 863 | 863 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116868551 | POLE_DECA_REPL - 4NWO 19755 MOUNTAIN MEA | 35188569 |  |  | STS-POLE_DECA_REPL - 4NWO 19755 MOUNTAIN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0988 | -121.0124 |  | TIER 2 | 596 | 15269-1104, HIGGINS | P10 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.8 | 19.8 |  |  | 0 | 19.8 | 19.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100105624 | RELW OH PRI REMT ESTR GO REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-11-14 | 2021-01-02 | COMP | 2020-11-10 | [16 empty] | 2019-03-29 | 2020-03-29 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 152691104 | 15597.25 | 1470 | -271.5 | -271.5 | -271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116957324 | POLE_BROK_REPL - 16571 DOG BAR RD GRASS | 35133954 |  |  | STS-POLE_BROK_REPL - 16571 DOG BAR RD GR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1376 | -121.0217 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1022 | 7645 | Y | 311 |  |  | 2021-03-23 07:00 | 2021-03-23 16:00 | Scheduled | CLICK | [6 empty] | 41.2 | 41 | 0.2 |  | 0 | 41.2 | 41 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100067764 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-10-26 | COMP | 2020-07-01 |  |  | 2020-09-03 | 2020-09-08 | [12 empty] | 2019-04-04 | 2020-04-04 |  | 2020-04-04 | 2021 CBP Plan | 2020-12-31 | QUES |  | 152481106 | 22540.24 | 2627 | 1620.5 |  |  | 130.4 |  | 130.4 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116957383 | POLE_BROK_REPL - A/F 16571 DOG BAR RD GR | 35133956 |  |  | STS-POLE_BROK_REPL - A/F 16571 DOG BAR R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1375 | -121.022 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1022 | 7645 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 90.7 | 90.5 | 0.2 |  | 0 | 90.7 | 90.5 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100067767 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-10-15 | COMP | 2020-08-18 |  |  | 2020-10-12 | 2020-10-15 | [12 empty] | 2019-04-04 | 2020-04-04 |  | 2020-04-04 | 2021 CBP Plan | 2020-10-31 | QUES |  | 152481106 | 25862.07 | 756.9 |  |  |  | 166.8 |  | 166.8 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116972612 | POLE_BROK_REPL - ENT 21310 PIONEER WAY G | 35188485 |  |  | STS-POLE_BROK_REPL - ENT 21310 PIONEER W | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0688 | -121.0616 |  | TIER 2 | 596 | 15269-1104, HIGGINS | Q09 | 4281 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.3 | 40.3 |  |  | 0 | 40.3 | 40.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103822408 | RELW OH PRI JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-11-12 | 2021-01-04 | COMP | 2020-11-12 | [16 empty] | 2019-04-06 | 2020-04-06 | 2020-09-27 | 2020-09-27 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 152691104 | 18189.37 | 941 | -316.7 | -316.7 | -316.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116973617 | POLE_BROK_REPL - R/O 15115 LORIE DR GRAS | 35133960 |  |  | STS-POLE_BROK_REPL - R/O 15115 LORIE DRG | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1419 | -121.0298 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1021 | 6753 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100067715 | PRI RELW OH CLR JPOL REMT ESTR REAR FMOB TER2 PRTO | Pole | 2020-06-22 | 2020-08-23 | COMP | 2020-06-22 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-07 | 2020-04-07 |  | 2020-04-07 | 2021 CBP Plan | 2020-12-31 | QUES |  | 152481106 | 17600.15 | 417.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 117015564 | POLE_BROK_REPL - #1S A/F 12857 SIERRA VI | 35134056 |  |  | STS-POLE_BROK_REPL - #1S A/F 12857 SIERR | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1682 | -120.9983 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1009 |  | Y | 311 |  |  | 2021-03-17 07:00 | 2021-03-17 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103801879 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-05-06 | 2020-07-30 | COMP | 2020-05-06 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | circuit based plan 2.14 | 2020-01-09 | QUES |  | 152481106 | 8377.81 | 267.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 117018172 | POLE_DECA_REPL - 1SE/O ALTA SIERRA DR ON | 35134062 |  |  | STS-POLE_DECA_REPL - 1SE/O ALTA SIERRA D | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1497 | -121.0353 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O0920 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100101166 | RELW OH PRI CLR JPOL REMT FMOB NOAC ESTR TER2 PRTO | Pole | 2020-07-01 | 2020-09-24 | COMP | 2020-07-01 |  |  | 2019-12-03 | 2019-12-03 | [12 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-12-31 | QUES |  | 152481106 | 12926.49 | 654.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 117084957 | POLE_BROK_REPL - R/O 14371 DOG BAR RD 1E | 35134096 |  |  | STS-POLE_BROK_REPL - R/O 14371 DOG BAR R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1545 | -121.0373 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O0915 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100114053 | RELW OH PRI JPOL RESD ESTR REAR FMOB TER2 PRTO | Pole | 2020-06-18 | 2020-08-11 | COMP | 2020-06-18 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | circuit based plan 2.14 | 2020-05-31 | QUES |  | 152481106 | 5618.8 | 1478.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 117089089 | POLE_BROK_REPL - 2N/O 10767 WELSH LN GRA | 35134105 |  |  | STS-POLE_BROK_REPL - 2N/O 10767 WELSH LN | FICL | FICL SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.1577 | -121.0498 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O0913 |  | Y | 311 |  |  | 2020-06-24 | 2020-06-24 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 1 | 0 | 0 | 41.8 | 41.8 | 0 |  | 0 | 40.8 | 40.8 | 0 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100105335 | RELW OH PRI JPOL RESD REMT ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-04-30 | 2020-05-04 | COMP | 2020-03-03 | COMP | 2020-06-24 | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | circuit based plan 2.14 | 2020-01-09 | QUES |  | 152481106 | 20077.44 | 16366.7 |  |  |  | 75.9 |  | 75.9 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 117089137 | POLE_BROK_REPL - R/O 14516 PENN RD 1SW/O | 35134106 |  |  | STS-POLE_BROK_REPL - R/O 14516 PENN RD 1 | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1587 | -121.0477 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O0913 |  | Y | 311 |  |  |  |  | Returned | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41 | 41 |  |  | 3 | 40 | 40 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100105322 | RELW OH PRI JPOL RESD NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2020-02-03 | 2020-02-25 | COMP | 2020-02-03 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | circuit based plan 2.14 | 2020-01-09 | QUES |  | 152481106 | 13278.68 | 41607 | 1760.2 | 1727.8 | 1727.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 117089182 | POLE_BROK_REPL - R/O 14516 PENN RD GRASS | 35134108 |  |  | STS-POLE_BROK_REPL - R/O 14516 PENN RD G | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1589 | -121.0474 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O0913 | 7667 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100105324 | RELW OH PRI JPOL RESD NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2020-03-24 | 2020-05-08 | COMP | 2020-03-24 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | circuit based plan 2.14 | 2020-01-09 | QUES |  | 152481106 | 24713.22 | 61208.2 | 53715.4 | 53650.6 | 53650.6 | 88.6 |  | 88.6 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 117319196 | POLE_BROK_REPL - 12779 SCHROEDER WAYGRAS | 35134169 |  |  | STS-POLE_BROK_REPL - 12779 SCHROEDER WAY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1816 | -121.0543 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O0902 |  | Y | 311 |  |  | 2021-04-17 07:00 | 2021-04-17 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100067294 | RELW OH PRI CLR JPOL RESD REMT ESTR FMOB TER2 PRTO | Pole | 2020-06-12 | 2020-10-11 | COMP | 2020-05-22 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-24 | 2020-05-24 |  | 2020-05-24 | 2021 CBP Plan | 2020-05-31 | QUES |  | 152481106 | 16850.26 | 1201 |  |  |  | 959.7 |  | 959.7 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 117319203 | POLE_BROK_REPL - 1S0 2W/0 12626 0FF HWY | 35134170 |  |  | STS-POLE_BROK_REPL - 1S0 2W/0 12626 0FF | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1842 | -121.0542 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | N0922 |  | Y | 311 |  |  | 2021-03-17 07:00 | 2021-03-17 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100097028 | RELW OH PRI CLR JPOL RESD REMT ESTR FMOB TER2 PRTO | Pole | 2020-03-06 | 2020-07-30 | COMP | 2020-03-06 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-24 | 2020-05-24 |  | 2020-05-24 | circuit based plan 2.14 | 2020-01-09 | QUES |  | 152481106 | 9973.38 | 15830.7 | 13667.2 | 13667.2 | 13667.2 | 127.8 |  | 127.8 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 117842214 | TREE_DECA_INPL - 15814 AUBURN RD GRASS V | 35091091 |  |  | STS-POLE_BROK_REPL - AT 15842 OLD AUBURN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.143 | -121.0773 |  | TIER 2 | 544 | 15203-1103, GRASS VALLEY | O0825 | 7787 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100114202 | RELW OH ESTR TER2 FSRP | Pole | 2020-01-21 | 2020-03-06 | COMP | 2020-01-21 | [16 empty] | 2019-08-08 | 2020-03-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-30 | QUES |  | 152031103 | 5981.62 | 7444.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 118186083 | TREE_DECA_INPL - 14516 PENN RD GRASS VAL | 35134108 |  |  | STS-POLE_BROK_REPL - R/O 14516 PENN RD G | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1589 | -121.0477 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O0913 | 7667 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100105324 | TER2 FSRP POHW OH ESTR | Pole | 2020-03-24 | 2020-05-08 | COMP | 2020-03-24 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-11-12 | 2020-11-12 | 2024-11-10 | 2024-11-10 | Pole Notification Clean Up 05.29.20 | 2020-01-09 | QUES |  | 152481106 | 24713.22 | 61208.2 | 53715.4 | 53650.6 | 53650.6 | 88.6 |  | 88.6 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-06-02
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 115036507 | POLE_BROK_REPL - 19739 wolf creek rdGras | 35069272 |  |  | STS-POLE_BROK_REPL - 19739 WOLF CREEK RD | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.1038 | -121.0206 |  | TIER 2 | 596 | 15269-1104, HIGGINS | P1017 | 4173 | Y | 311 |  |  |  |  | Cancelled | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100097864 | REGW OH PRI INSP CLR JPOL REMT NOAC ESTR TER2 USA FMOB | Pole |  |  | REQD | [17 empty] | 2018-10-09 | 2019-10-09 |  | 2019-10-09 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152691104 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 115055008 | POLE_BROK_REPL - 20525 Dog Bar RdGrass V | 35070122 |  |  | STS-POLE_BROK_REPL - 20525 DOG BAR *CANC | DOCC | DOCC ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2020-05-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.0933 | -121.0002 |  | TIER 2 | 501 | 15269-1110, HIGGINS | P1024 | 4879 | Y | 311 |  |  |  |  | Cancelled | Order Operation | [6 empty] | 81 | 81 |  |  | 0 | 81 | 81 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100097423 | REGW OH PRI INSP CLR JPOL REMT NOAC ESTR USA FMOB TER2 | Pole |  |  | REQD | 2020-06-03 |  | 2020-06-03 | 2019-05-14 | 2019-05-14 | [12 empty] | 2018-10-12 | 2019-10-12 |  | 2019-10-12 | Q1 Work Plan | 2019-02-28 | W. Sac |  | 152691110 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 115467322 | POLE_BROK_REPL - 16249 DAVID WAY GRASS V | 35074272 |  |  | STS-POLE_BROK_REPL - 16249 DAVID WAY GRA | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land JointPole |  |  | 39.1227 | -121.0605 |  | TIER 2 | 596 | 15269-1104, HIGGINS | P0907 | 842642 | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 128.7 | 128.7 |  |  | 0 | 128.7 | 128.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100095921 | RELW OH PRI INSP CLR JPOL RESD ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-12-22 |  | COMP | 2020-12-22 |  |  | 2020-12-23 | 2021-01-04 | [12 empty] | 2018-12-07 | 2019-12-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152691104 | 39496.65 | 1073.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 115477965 | POLE_BROK_REPL - 15956 Annie DrGrass Val | 35069505 |  |  | STS-POLE_BROK_REPL - 15956 ANNIE DRGRASS | UNSE | UNSE ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.1271 | -121.0454 |  | TIER 2 | 596 | 15269-1104, HIGGINS | P0909 | 8721 | Y | 311 |  |  | 2020-02-07 | 2020-02-07 | Completed | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100014721 | REGW OH PRI INSP JPOL RESD ESTR BTKA FMOB TER2 | Pole |  |  | REQD |  |  |  | 2019-05-14 | 2019-05-14 | [12 empty] | 2018-12-10 | 2019-12-10 |  | 2019-12-10 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152691104 | 1 | 84.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 115480193 | POLE_BROK_REPL - 19004 CONNIE DR GRASS V | 35074156 |  |  | STS-POLE_BROK_REPL - 19004 CONNIE DR GRA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.1227 | -121.0473 |  | TIER 2 | 596 | 15269-1104, HIGGINS | P0909 | 8721 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103703809 | RELW OH PRI INSP JPOL RESD NOAC ESTR REAR FSRP TER2 FMOB | Pole |  |  | REQD | [17 empty] | 2018-12-10 | 2019-12-10 | 2023-12-09 | 2023-12-09 | 2021 CBP Plan | 2021-01-31 | Auburn |  | 152691104 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116503155 | POLE_BROK_REPL - 21702 BREWER RD GRASS V | 35090431 |  |  | STS-POLE_BROK_REPL - 21702 BREWER RD GRA | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 39.0575 | -121.0843 |  | TIER 2 | 395 | 15269-1103, HIGGINS | Q0819 | 2295 | Y | 311 |  |  | 2021-04-12 07:00 | 2021-04-12 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 112.1 | 112.1 |  |  | 0 | 112.1 | 112.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100018474 | RELW OH PRI CREW CLR JPOL RESD TRAF FLAG ESTR BTKA USA TER2 | Pole | 2020-12-04 | 2021-02-22 | COMP | 2020-12-04 |  |  | 2021-02-22 | 2021-02-22 | [12 empty] | 2019-01-30 | 2020-01-30 |  | 2020-01-30 | Q1 Work Plan | 2019-09-20 | QUES |  | 152691103 | 90186.4 | 1067.1 | 75 | 75 | 75 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GRASS VALLEY | Grass Valley |  |  | OPEN | 116735404 | POLE_DECA_REPL - 18154 JUSTICE CT GRASS | 35081117 |  |  | STS-POLE_DECA_REPL - 18154 JUSTICE CT GR | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1549 | -120.9907 |  | TIER 2 | 19 | 15248-1106, BRUNSWICK | O1111 | 8677 | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 42.8 | 42.8 |  |  | 0 | 42.8 | 42.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100109401 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-01-22 | 2021-02-09 | COMP | 2019-12-18 | [16 empty] | 2019-03-14 | 2019-09-10 |  | 2019-09-10 | 2021 CBP Plan |  | W. Sac |  | 152481106 | 23375.46 | 37.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | Greenwood | Auburn |  |  | OPEN | 120511930 | TREE_DECA_INPL - 1S/O 1E/O AT 1028 FOX G | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-04-11 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 38.9409 | -120.9231 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | T12 | 6881 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | B | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100075192 | REGW OH SEC INSP JPOL RESD ESTR BTKA FMOB TER2 | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2021-02-09 | 2021-05-09 |  | 2021-05-09 | B tag clean up 2/19/2021 |  | UNASSIGNED |  | 152282101 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | SI | GREENWOOD | Auburn |  |  | COMP | 117272756 | POLE_DECA_REPL - 4000 ALDER GLEN WY 1SW/ | 35150076 |  |  | STS-POLE_DECA_REPL - 4000 ALDER GLEN WY | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-11-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8942 | -120.9039 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | U13 | 5195 | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 1.8 | 1.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100082614 | RELW OH PRI COMP CLR JPOL RESD ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-04-15 | 2020-07-14 | COMP | 2020-04-15 | COMP | 2021-01-06 | 2020-07-14 | 2020-07-14 | [11 empty] | 2021-01-08 | 2021-01-06 | 2020-05-19 |  | 2020-05-19 | circuit based plan 2.14 | 2020-04-10 | PIKEENG |  | 152282101 | 17406.46 | 18912.6 | 13458.3 | 2272.6 | 2272.6 | 20.5 |  | 20.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | GREENWOOD | Auburn |  |  | OPEN | 117291502 | POLE_BROK_REPL - A/F C/O HWY 193 RICCI R | 35217339 |  |  | B1 STS-POLE_BROK_REPL - A/F C/O HWY 193 | CONS | CONS SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.899 | -120.9099 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | U1306 | 1103 | Y | 311 |  |  | 2021-04-02 07:00 | 2021-04-02 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 43.7 | 43.7 |  |  | 0 | 43.7 | 43.7 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100073510 | RELW OH PRI CLR JPOL RESD ESTR GO REAR FMOB TER2 PRTO | Pole | 2021-01-19 | 2021-01-19 | COMP | 2020-12-01 |  |  | 2020-12-02 | 2020-12-02 | [12 empty] | 2019-05-21 | 2020-05-21 | 2020-12-23 | 2020-12-23 | B tag clean up 11/30/2020 |  | Auburn |  | 152282101 | 32228.23 | 1051.7 | 648.9 | 648.9 | 648.9 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N | Permitting_Delays | Y | 2020-11-30
North | SI | GREENWOOD | Auburn |  |  | COMP | 119567446 | POLE_BROK_REPL - AT 5200 LONGVIEW LN 1E/ | 35192338 |  |  | B3 - STS-POLE_BROK_REPL - AT 5200 LONGVI | FICL | FICL SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-10-09 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8999 | -120.8728 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | U1310 | 8569 | Y | 311 |  |  | 2020-12-01 | 2020-12-01 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 22 | 22 |  |  | 42 | 0 |  |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100050519 | RELW OH PRI INSP COMP CLR JPOL REMT CCNT FMOB FIRE NOAC ESTR TER2 | Pole | 2020-10-21 | 2020-10-26 | COMP | 2020-10-21 | COMP | 2020-12-01 | 2020-10-14 | 2020-10-14 | [11 empty] | 2021-01-20 | 2021-01-15 | 2020-11-06 |  | 2020-11-06 | B-tag addition 8/12/2020 |  | Auburn |  | 152282101 | 11320.68 | 18321.2 | 1954.1 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Tag in Closure Status | Y | 2020-08-18
North | SI | KELSEY | Placerville |  |  | OPEN | 117565457 | POLE_BROK_REPL - 7045 STEWART MINE RD. K | 35233970 |  |  | STS-POLE_BROK_REPL - 7045 STEWART MINE R | ESTS | ESTS ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.7813 | -120.8364 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G40 | 1443 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101388005 | RELW OH PRI TMAN JPOL REMT GO BTKA PROG TER2 | Pole |  |  | REQD | [17 empty] | 2019-07-05 | 2020-07-05 |  | 2020-07-05 | Per DOT Approved Request 31435 |  | UNASSIGNED |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2021-01-28
North | SI | KYBURZ | Placerville |  |  | OPEN | 116978362 | POLE_BROK_REPL - E/0 13305 HWY 50 KYBURZ | 35143873 |  |  | STS-POLE_BROK_REPL - E/0 13305 HWY 50 KY | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 38.7706 | -120.3113 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | H5305 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 30.4 | 30.4 |  |  | 0 | 30.4 | 30.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101398169 | RELW OH SERV JPOL RESD ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-02-07 |  | COMP | 2020-02-07 |  |  | 2020-06-30 | 2020-06-30 | [12 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-04-08 | Auburn |  | 152762101 | 16077.11 | 795.3 |  |  |  | 555.5 |  | 555.5 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | KYBURZ | Placerville |  |  | OPEN | 117262534 | POLE_DECA_REPL - #1E CO#2521 LOT 9 HWY 5 | 35144271 |  |  | STS-POLE_DECA_REPL - #1E CO#2521 LOT 9 H | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 38.7754 | -120.2815 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G54 | 13139 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 75.7 | 75.7 |  |  | 0 | 75.7 | 75.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101407039 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-07-28 |  | COMP | 2020-07-28 | [16 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-06-30 | Auburn |  | 152762101 | 48867.12 | 2915.2 | 187 | 187 | 187 | 763 |  | 763 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | KYBURZ | Placerville |  |  | OPEN | 120525649 | TREE_DECA_INPL - LOT 27 RIVERSIDE TRACT/ | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-04-12 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 38.7737 | -120.2834 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G54 | 13532 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | B | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 101407025 | REGW OH SERV REMT SWRK ESTR GO BTKA CTMN PROG FMOB TER2 | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2021-02-10 | 2021-05-10 |  | 2021-05-10 | B tag clean up 2/19/2021 |  | UNASSIGNED |  | 152762101 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | SI | KYBURZ | Placerville |  |  | COMP | 117249937 | TREE_DECA_INPL - SP/AT LOT 4 36MILESTONE | 35143989 |  |  | STS-TREE_DECA_INPL - SP/AT LOT 4 36MILES | MAPP | MAPP SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7787 | -120.2425 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G55 |  | Y | 311 |  |  | 2021-01-16 | 2021-01-16 | Completed | Order Operation | POLRPL | # of Poles Replaced | 2 | 0 | 0 | 2 | 54.6 | 54.6 |  |  | 0 | 3.6 | 3.6 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 101407255 | RELW OH SEC JPOL REMT NOAC ESTR FMOB TER2 PRTO CCNT COMP | Pole | 2020-01-31 | 2020-06-02 | COMP | 2020-01-31 | COMP | 2021-01-16 | [13 empty] | 2021-01-29 | 2021-01-16 | 2020-05-16 |  | 2020-05-16 | circuit based plan 2.14 | 2020-05-16 | Auburn |  | 152762101 | 42055.74 | 31745.4 | 19014.4 | 2970.1 | 2970.1 | 715 |  | 715 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | KYBURZ | Placerville |  |  | COMP | 117250630 | POLE_DECA_REPL - #2S CO#2523 LOT 9 RIVER | 35143994 |  |  | STS-POLE_DECA_REPL - #2S CO#2523 LOT 9 R | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7761 | -120.2794 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G54 |  | Y | 311 |  |  | 2021-01-09 | 2021-01-09 | Completed | Order Operation | POLRPL | # of Poles Replaced | 2 | 0 | 0 | 2 | 52.8 | 52.8 |  |  | 0 | 1.8 | 1.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101407070 | RELW OH SERV COMP JPOL REMT ESTR CCNT FMOB TER2 PRTO | Pole | 2020-01-24 | 2020-05-13 | COMP | 2020-01-24 | COMP | 2021-01-09 | [13 empty] | 2021-01-27 | 2021-01-09 | 2020-05-16 |  | 2020-05-16 | circuit based plan 2.14 | 2020-05-16 | Auburn |  | 152762101 | 50851.49 | 64196.8 | 52068.9 | 17327.3 | 17327.3 | 2467.6 |  | 2467.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | KYBURZ | Placerville |  |  | COMP | 117262700 | POLE_DECA_REPL - #1E CO#2521 LOT 13 RIVE | 35144000 |  |  | STS-POLE_DECA_REPL - #1E CO#2521 LOT 13 | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7754 | -120.2811 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G54 |  | Y | 311 |  |  | 2021-01-09 | 2021-01-09 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 41 | 41 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101419667 | RELW OH SEC COMP JPOL REMT NOAC ESTR GO CCNT FMOB TER2 PRTO | Pole | 2020-01-25 | 2020-05-13 | COMP | 2020-01-25 | COMP | 2021-01-09 | [13 empty] | 2021-01-13 | 2021-01-09 | 2020-05-17 |  | 2020-05-17 | circuit based plan 2.14 | 2020-05-17 | Auburn |  | 152762101 | 38653.63 | 28678.3 | 21326.1 | 4316.4 | 4316.4 | 133 |  | 133 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | KYBURZ | Placerville |  |  | COMP | 118426585 | TREE_DECA_INPL - LOT 4 - 36 MILE STONE K | 35143989 |  |  | STS-TREE_DECA_INPL - SP/AT LOT 4 36MILES | MAPP | MAPP SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 |  | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7787 | -120.2425 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G55 | 18157 | Y | 311 |  |  | 2021-01-16 | 2021-01-16 | Completed | Order Operation | POLRPL | # of Poles Replaced | 2 | 0 | 0 | 2 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 101407255 | POHW OH COMP ESTR CCNT TER2 | Pole | 2020-01-31 | 2020-06-02 | COMP | 2020-01-31 | COMP | 2021-01-16 | [13 empty] | 2021-01-22 | 2021-01-16 | 2020-05-16 |  | 2020-05-16 | Pole Notification Clean Up 05.29.20 | 2020-05-16 | Auburn |  | 152762101 | 42055.74 | 31745.4 | 19014.4 | 2970.1 | 2970.1 | 715 |  | 715 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-06-02
North | SI | KYBURZ | Placerville |  |  | COMP | 118434856 | TREE_DECA_INPL - LOT 9, RIVERSIDE TRACT | 35143994 |  |  | STS-POLE_DECA_REPL - #2S CO#2523 LOT 9 R | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 |  | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.776 | -120.2797 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G54 | 2523 | Y | 311 |  |  | 2021-01-09 | 2021-01-09 | Completed | Order Operation | POLRPL | # of Poles Replaced | 2 | 0 | 0 | 2 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103844529 | POHW OH ESTR TER2 COMP CCNT | Pole | 2020-01-24 | 2020-05-13 | COMP | 2020-01-24 | COMP | 2021-01-09 | [13 empty] | 2021-01-27 | 2021-01-09 | 2021-01-13 |  | 2021-01-13 | Pole Notification Clean Up 05.29.20 | 2020-05-16 | Auburn |  | 152762101 | 50851.49 | 64196.8 | 52068.9 | 17327.3 | 17327.3 | 2467.6 |  | 2467.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-06-02
North | SI | KYBURZ | Placerville |  |  | OPEN | 117248728 | POLE_DECA_REPL - #3S CO#2527 34 MILE STO | 35143987 |  |  | STS-POLE_DECA_REPL - #3S CO#2527 34 MILE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7754 | -120.2701 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G54 |  | Y | 311 |  |  | 2021-04-15 07:00 | 2021-04-15 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 42.8 | 42.8 |  |  | 0 | 42.8 | 42.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101419672 | RELW OH SEC JPOL REMT ESTR PRTO FMOB TER2 | Pole | 2020-07-13 | 2020-07-21 | COMP | 2020-07-13 | [16 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | circuit based plan 2.14 | 2020-05-31 | Auburn |  | 152762101 | 33254.52 | 3569.3 |  |  |  | 1571.2 |  | 1571.2 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | KYBURZ | Placerville |  |  | OPEN | 117248733 | POLE_DECA_REPL - #1S CO#2527 34 MILE STO | 35143988 |  |  | STS-POLE_DECA_REPL - #1S CO#2527 34 MILE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7759 | -120.2692 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G54 | 2527 | Y | 311 |  |  | 2021-04-15 07:00 | 2021-04-15 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 42.6 | 41.9 | 0.7 |  | 0 | 42.6 | 41.9 | 0.7 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101407161 | RELW OH PRI JPOL REMT ESTR GO FMOB TER2 PRTO | Pole | 2020-07-28 | 2020-11-30 | COMP | 2020-07-28 | [16 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-06-30 | Auburn |  | 152762101 | 50263.41 | 2385 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | KYBURZ | Placerville |  |  | OPEN | 117257145 | TREE_DECA_INPL - 6211 41 MILE STONE TRAC | 35116130 |  |  | STS-TREE_DECA_INPL - 6211 41 MILE STONE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7858 | -120.1584 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G57 | 13801 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 17.4 | 17.4 |  |  | 0 | 17.4 | 17.4 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 101407503 | RELW OH SERV JPOL REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-07-02 | 2020-09-24 | COMP | 2020-07-02 |  |  | 2019-09-24 | 2019-09-24 | [12 empty] | 2019-05-17 | 2020-05-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 152762101 | 10520.15 | 1595.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | KYBURZ | Placerville |  |  | OPEN | 117261263 | POLE_BROK_REPL - A/F LOT 34 41 MILE TRAC | 35116145 |  |  | STS-POLE_BROK_REPL - A/F LOT 34 41 MILE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7874 | -120.1637 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G57 | 13801 | Y | 311 |  |  |  |  | Started | Order Operation | [6 empty] | 41.4 | 41.4 |  |  | 0 | 41.4 | 41.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101407492 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-07-02 | 2020-09-13 | COMP | 2020-07-02 |  |  | 2019-09-24 | 2019-09-24 | [12 empty] | 2019-05-17 | 2020-05-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | CALENG |  | 152762101 | 19498.03 | 5560.4 | 2978.3 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | KYBURZ | Placerville |  |  | OPEN | 117268755 | POLE_BROK_REPL - 22NE/0 LOT 25 36MILE TR | 35144002 |  |  | STS-POLE_BROK_REPL - 22NE/0 LOT 25 36MIL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7858 | -120.2143 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G56 | 18157 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 65.3 | 64.6 | 0.7 |  | 0 | 65.3 | 64.6 | 0.7 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101407358 | RELW OH PRI CLR JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-01-15 | 2021-01-08 | COMP | 2020-01-15 | [16 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-05-18 | Auburn |  | 152762101 | 32289.39 | 2365.3 | 187 | 187 | 187 | 1781.9 |  | 1781.9 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | Kyburz | Placerville |  |  | OPEN | 117771526 | REPL POLE:CO#2511 E/O MM 43.50 HWY 50,Ky | 35148050 |  |  | STS-REPL POLE:CO#2511 E/O MM 43.50 HWY 5 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7734 | -120.3023 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G54 |  | Y | 311 |  |  |  |  | Started | Order Operation | [6 empty] | 28.4 | 28.4 |  |  | 0 | 28.4 | 28.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101406934 | RELW OH TNT JPOL TER2 | Pole | 2020-06-25 | 2020-08-19 | COMP | 2020-06-25 |  |  | 2020-06-03 | 2020-06-03 | [12 empty] | 2019-07-15 | 2020-07-15 |  | 2020-07-15 | 2021 CBP Plan | 2020-05-31 | CALENG |  | 152762101 | 13827.22 | 3727.9 | 2990.1 | [5 empty] | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | KYBURZ | Placerville |  |  | OPEN | 118490248 | TREE_DECA_INPL - LOT 4, 34 MILESTONE KYB | 35184083 |  |  | STS-TREE_DECA_INPL - LOT 4, 34 MILESTONE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7762 | -120.2712 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G54 | 2527 | Y | 311 |  |  | 2021-04-15 07:00 | 2021-04-15 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 0 | RELW OH ESTR GO TER2 | Pole | 2020-07-28 | 2020-10-16 | COMP | 2020-07-28 | [16 empty] | 2020-01-29 | 2021-01-29 |  | 2021-01-29 | 2021 CBP Plan |  | Auburn |  | 152762101 | 26682.33 | 3031.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | KYBURZ | Placerville |  |  | OPEN | 117893826 | POLE_BROK_REPL - R/O 1384 SILVER FORK RD | 35148051 |  |  | STS-POLE_BROK_REPL - R/O 1384 SILVER FOR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7728 | -120.2946 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G5422 | 2493 | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 25.1 | 25.1 |  |  | 0 | 25.1 | 25.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101406848 | RELW OH SEC INSP JPOL RESD ESTR BTKA FMOB TER2 | Pole | 2021-01-11 | 2021-02-09 | COMP | 2020-07-22 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-09-18 | 2020-09-18 |  | 2020-09-18 | 2021 CBP Plan | 2020-10-31 | CALENG |  | 152762101 | 14772.14 | 294.2 | 149.5 | 149.5 | 149.5 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | LINCOLN | Auburn |  |  | OPEN | 116608526 | POLE_BROK_REPL - A/F 1706 KILAGA SPRINGS | 35090895 |  |  | STS-POLE_BROK_REPL - A/F 1706 KILAGA SPR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9703 | -121.2517 |  | TIER 2 | 499 | 15370-1104, LINCOLN | S04 | 5331 | Y | 311 |  |  | 2021-04-13 07:00 | 2021-04-13 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100027042 | RELW OH PRI ESTR CLR REMT BTKA FMOB TER2 PRTO FSRP | Pole | 2019-10-18 | 2019-12-09 | COMP | 2019-10-17 |  |  | 2019-05-13 | 2019-05-14 | [12 empty] | 2019-02-26 | 2020-02-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-10-29 | CALENG |  | 153701104 | 8009.19 | 78.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | LINCOLN | Auburn |  |  | OPEN | 116682449 | POLE_BROK_REPL - 2W/O 1N/O 4177 PLEASANT | 35091526 |  |  | STS-POLE_BROK_REPL - 2W/O 1N/O 4177 PLEA | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9464 | -121.1875 |  | TIER 2 | 129 | 15227-1102, WISE | T0606 | 30527 | Y | 311 |  |  | 2021-02-20 07:00 | 2021-02-20 16:00 | Completed | CLICK | [6 empty] | 41.2 | 41 | 0.2 |  | 3.75 | 40.2 | 40 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100078391 | RELW OH PRI CLR JPOL REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-01-06 | 2020-02-04 | COMP | 2020-01-06 |  |  | 2019-08-15 | 2019-08-15 | [12 empty] | 2019-03-07 | 2020-03-07 | 2020-11-14 | 2020-11-14 | 2021 CBP Plan | 2019-11-08 | CALENG |  | 152271102 | 21723.2 | 501.2 | 501.3 | 278.2 | 278.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | LINCOLN | Auburn |  |  | COMP | 116591204 | POLE_BROK_REPL - #1N/O HOUSE @ 4620 GARD | 35090734 |  |  | STS-POLE_BROK_REPL - #1N/O HOUSE @ 4620 | MAPP | MAPP SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.9599 | -121.2286 |  | TIER 2 | 499 | 15370-1104, LINCOLN | S05 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 25.2 | 25.2 |  |  | 51.25 | 0.8 | 0.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100028774 | RELW OH PRI COMP CLR JPOL REMT ESTR BTKA RTRN CPGG FMOB TER2 PRTO | Pole | 2019-10-31 | 2019-11-13 | COMP | 2019-10-31 | COMP | 2021-02-17 | [13 empty] | 2021-02-19 | 2021-02-17 | 2020-02-24 |  | 2020-02-24 | Program Manager | 2019-10-31 | CALENG |  | 153701104 | 10628.9 | 10420.3 | 3691.7 | 117.6 | 117.6 | 2238.2 |  | 2238.2 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
North | SI | LINCOLN | Auburn |  |  | COMP | 116616579 | POLE_DECA_REPL - 2 S/O 1 W/O 3 N/O 5500 | 35090952 |  |  | STS-POLE_DECA_REPL - 2 S/O 1 W/O 3 N/O 5 | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-07-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.9721 | -121.2498 |  | TIER 2 | 499 | 15370-1104, LINCOLN | S04 |  | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 21.9 | 21.9 |  |  | 60 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100028356 | RELW OH PRI COMP CLR REMT NOAC ESTR GO USA CPGG FMOB TER2 PRTO | Pole | 2019-11-01 | 2019-11-01 | COMP | 2019-11-01 | COMP | 2021-01-08 | [13 empty] | 2021-01-13 | 2021-01-08 | 2020-02-27 |  | 2020-02-27 | Program Manager | 2019-11-01 | CALENG |  | 153701104 | 8260.45 | 17373.7 | 15786.4 | 15786.4 | 15786.4 | 736.6 |  | 736.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
North | SI | LINCOLN | Auburn |  |  | COMP | 116619230 | POLE_DECA_REPL - R/O 5610 N.KILAGA SPRIN | 35091071 |  |  | STS-POLE_DECA_REPL - R/O 5610 N.KILAGA S | MAPP | MAPP ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.9778 | -121.2529 |  | TIER 2 | 499 | 15370-1104, LINCOLN | S04 | 5395 | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 41.3 | 41.1 | 0.2 |  | 21 | 1 | 0.8 | 0.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100027669 | RELW OH PRI COMP CLR REMT NOAC ESTR CPGG TER2 BTKA USA FMOB PRTO | Pole | 2019-09-23 | 2019-10-11 | COMP | 2019-09-23 | COMP | 2021-02-11 | [13 empty] | 2021-02-22 | 2021-02-11 | 2020-02-28 |  | 2020-02-28 | Program Manager | 2019-10-31 | CALENG |  | 153701104 | 16661.23 | 5920.6 | 1452 |  |  | 1491.2 |  | 1491.2 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
North | SI | LINCOLN | Auburn |  |  | OPEN | 116592578 | POLE_BROK_REPL - #2S #19W ON LINE @ R/O | 35090824 |  |  | STS-POLE_BROK_REPL - #2S #19W ON LINE @ | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0024 | -121.2273 |  | TIER 2 | 129 | 15227-1102, WISE | S05 |  | Y | 311 |  |  | 2021-04-10 07:00 | 2021-04-10 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 20.4 | 20.4 |  |  | 0 | 20.4 | 20.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100027911 | RELW OH SERV JPOL REMT ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2019-10-25 | 2019-11-14 | COMP | 2019-10-25 | [16 empty] | 2019-02-25 | 2020-02-25 |  | 2020-02-25 | circuit based plan 2.14 | 2019-10-31 | QUES |  | 152271102 | 8933.22 | 817.6 |  |  |  | 620.6 |  | 620.6 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | LINCOLN | Auburn |  |  | OPEN | 116614953 | POLE_BROK_REPL - 3 E/O R/O 5028 MC COURT | 35090927 |  |  | STS-POLE_BROK_REPL - 3 E/O R/O 5028 MC C | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9716 | -121.2696 |  | TIER 2 | 499 | 15370-1104, LINCOLN | S04 | 15305 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | [6 empty] | 67 | 67 |  |  | 2.25 | 64.75 | 64.75 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100109116 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2019-10-22 | 2019-10-22 | COMP | 2019-10-22 | [16 empty] | 2019-02-27 | 2020-02-27 |  | 2020-02-27 | Program Manager | 2019-10-30 | CALENG |  | 153701104 | 30275.36 | 5371.3 | 158.4 |  |  | 5173.9 |  | 5173.9 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
North | SI | LINCOLN | Auburn |  |  | OPEN | 116615381 | POLE_DECA_REPL - 1 S/O 3 E/O R/O 5028 MC | 35090936 |  |  | STS-POLE_DECA_REPL - 1 S/O 3 E/O R/O 502 | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9714 | -121.2694 |  | TIER 2 | 499 | 15370-1104, LINCOLN | S04 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | [6 empty] | 16.3 | 16.3 |  |  | 23 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100109117 | RELW OH SERV REMT SPCR ESTR BTKA USA FMOB TER2 PRTO | Pole | 2019-11-01 | 2019-11-01 | COMP | 2019-11-01 | [16 empty] | 2019-02-27 | 2020-02-27 |  | 2020-02-27 | Program Manager | 2019-11-01 | CALENG |  | 153701104 | 12087.86 | 3141.6 | 1815.2 |  |  | 1287.4 |  | 1287.4 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
North | SI | LINCOLN | Auburn |  |  | OPEN | 116617773 | POLE_BROK_REPL - R/O 5200 GARDEN BAR RD | 35090976 |  |  | STS-POLE_BROK_REPL - R/O 5200 GARDEN BAR | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9788 | -121.2117 |  | TIER 2 | 129 | 15227-1102, WISE | S05 | 8149 | Y | 311 |  |  | 2021-03-12 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | [6 empty] | 67.9 | 67.1 | 0.8 |  | 0 | 67.9 | 67.1 | 0.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100028791 | RELW OH PRI CLR JPOL REMT CGI ESTR FMOB TER2 PRTO | Pole | 2019-11-05 | 2019-11-05 | COMP | 2019-11-04 | [16 empty] | 2019-02-28 | 2020-02-28 |  | 2020-02-28 | circuit based plan 2.14 | 2019-11-04 | CALENG |  | 152271102 | 26593.22 | 4550.7 |  |  |  | 1016.8 |  | 1016.8 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | LINCOLN | Auburn |  |  | OPEN | 120140616 | POLE_DECA_REPL - 1796 KILAGA SPRINGS RD | 35219191 |  |  | B3 STS-POLE_DECA_REPL - 1796 KILAGA SPRI | CONS | CONS SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-22 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.9655 | -121.2412 |  | TIER 2 | 499 | 15370-1104, LINCOLN | S04 | 5389 | Y | 311 |  |  | 2021-02-19 07:00 | 2021-02-19 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 22.1 | 22.1 |  |  | 0 | 22.1 | 22.1 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100028351 | RELW OH ESTR TER2 | Pole | 2020-12-17 | 2020-12-17 | COMP | 2020-12-17 | [16 empty] | 2020-11-19 | 2021-02-19 |  | 2021-02-19 | B tag clean up 12/10/2020 |  | Auburn |  | 153701104 | 14158.07 | 1278.9 | 1278.9 | 1278.9 | 1278.9 |  |  |  | Electric Distribution | N | Pulled from MPP Import File | N |  | Y | 2020-12-10
North | SI | LOOMIS | Auburn |  |  | OPEN | 117109756 | POLE_DECA_REPL - #1 ON LINE N/O 7577 BAR | 35202234 |  |  | STS-POLE_DECA_REPL - #1 ON LINE N/O 7577 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.8232 | -121.1626 |  | TIER 2 | 447 | 15256-1107, PENRYN | W0605 | 32073 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100062431 | RELW OH PRI INSP CLR JPOL REMT ESTR REAR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-27 | 2019-11-27 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152561107 | 1 |  | -1092.6 | -0.6 | -0.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | LOOMIS | Auburn |  |  | OPEN | 117110449 | POLE_DECA_REPL - A/F 3920 HICKEY LN/GP L | 35202237 |  |  | STS-POLE_DECA_REPL - A/F 3920 HICKEY LN/ | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land |  |  | 38.8132 | -121.1617 |  | TIER 2 | 447 | 15256-1107, PENRYN | W0610 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.1 | 21.1 |  |  | 0 | 21.1 | 21.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100100879 | RELW OH SERV INSP RESD ESTR BTKA FMOB TER2 FSRP | Pole | 2021-02-01 |  | COMP | 2021-02-01 | [16 empty] | 2019-04-27 | 2020-04-27 | 2020-09-01 | 2020-09-01 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152561107 | 12194.09 |  | -1060 | 32 | 32 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | LOTUS | Placerville |  |  | OPEN | 117847336 | POLE_BROK_REPL - 995 LOTUS RDLOTUS95651 | 35160321 |  |  | STS-POLE_BROK_REPL - 995 LOTUS RDLOTUS95 | PEND | PEND ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.8003 | -120.9093 |  | TIER 2 | 110 | 15365-2109, SHINGLE SPRINGS | G3911 | 11092 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 56.6 | 56.6 |  |  | 0 | 56.6 | 56.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101381206 | RELW OH PRI INSP CUST CLR BTKA RESD FLAG ESTR FMOB TER2 | Pole | 2020-10-28 |  | COMP | 2020-10-28 | [16 empty] | 2019-09-05 | 2020-09-05 |  | 2020-09-05 | 2021 CBP Plan | 2020-10-31 | QUES |  | 153652109 | 24756.22 | 2131.1 | 1425.4 | 1425.4 | 1425.4 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | LOTUS | Placerville |  |  | OPEN | 117249795 | POLE_DECA_REPL - 6489 PROSPECTORS RD-SER | 35160312 |  |  | STS-POLE_DECA_REPL - 6489 PROSPECTORS RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8214 | -120.8965 |  | TIER 2 | 110 | 15365-2109, SHINGLE SPRINGS | G39 | 22945 | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-04 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101414062 | RELW OH PRI INSP CLR JPOL RESD REMT ESTR REAR PROG FMOB TER2 | Pole | 2020-08-14 | 2020-10-13 | COMP | 2020-08-14 | [16 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-09-30 | QUES |  | 153652109 | 32061.78 | 2069.5 | 2024.1 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | MARYSVILLE | Grass Valley |  |  | OPEN | 116956669 | POLE_BROK_REPL - 1W/O R/O 13214 HUTTO RD | 35187947 |  |  | STS-POLE_BROK_REPL - 1W/O R/O 13214 HUTT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1659 | -121.2833 |  | TIER 2 | 109 | 15313-2105, NARROWS | O03 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 15.2 | 15.2 |  |  | 0 | 15.2 | 15.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100013168 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-10-12 | COMP | 2020-10-12 | [16 empty] | 2019-04-04 | 2020-04-04 |  | 2020-04-04 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 7450.22 | 1873.8 | 681.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | MARYSVILLE | Grass Valley |  |  | OPEN | 116957193 | POLE_BROK_REPL - 4W/O R/O 13214 HUTTO RD | 35187983 |  |  | STS-POLE_BROK_REPL - 4W/O R/O 13214 HUTT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1659 | -121.2864 |  | TIER 2 | 109 | 15313-2105, NARROWS | O03 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 28.4 | 28.4 |  |  | 0 | 28.4 | 28.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100013171 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-10-14 | COMP | 2020-10-12 | [16 empty] | 2019-04-04 | 2020-04-04 | 2021-07-22 | 2021-07-22 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 13506.65 | 1168.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | MEADOW VISTA | Auburn |  |  | OPEN | 116628403 | POLE_BROK_REPL - 2S/O AT 1215 GRANGE RD | 35091491 |  |  | STS-POLE_BROK_REPL - 2S/O AT 1215 GRANGE | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.9881 | -121.0282 |  | TIER 2 | 68 | 15224-1101, HALSEY | S1006 | 5731 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100032331 | RELW OH PRI JPOL REMT ESTR REAR FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-03 | 2020-03-03 |  | 2020-03-03 | 2021 CBP Plan | 2020-10-31 | QUES |  | 152241101 | 1 | 1409.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | MEADOW VISTA | Auburn |  |  | OPEN | 116742427 | POLE_DECA_REPL - AT 17320 PLACER HILLS R | 35214837 |  |  | STS-POLE_DECA_REPL - AT 17320 PLACER HIL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.0041 | -121.0145 |  | TIER 2 | 999 | 15249-1102, WEIMAR | R1023 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100025913 | RELW PRI OH CLR RESD ESTR BTKA CPGD FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-15 | 2020-03-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152491102 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | MEADOW VISTA | Auburn |  |  | COMP | 116636087 | POLE_BROK_REPL - 18939 MOONLIGHT CTMEADO | 35091435 |  |  | STS-POLE_BROK_REPL - 18939 MOONLIGHT CTM | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.0234 | -121.016 |  | TIER 2 | 999 | 15249-1102, WEIMAR | R1012 | 6241 | Y | 311 |  |  | 2021-02-06 | 2021-02-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100025925 | COMP JPOL RELW OH PRI CLR RESD FIRE ESTR CCNT FMOB TER2 PRTO FSRP | Pole | 2020-10-21 | 2020-10-22 | COMP | 2019-11-22 | COMP | 2021-02-06 | 2020-10-22 | 2020-10-22 | [11 empty] | 2021-02-10 | 2021-02-06 | 2020-03-05 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 28588 | 2020-01-31 | QUES |  | 152491102 | 17653.73 | 6402.3 | 4578.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-14
North | SI | MEADOW VISTA | Auburn |  |  | COMP | 116636102 | POLE_BROK_REPL - 18960 MOONLIGHT CT MEAD | 35091439 |  |  | STS-POLE_BROK_REPL - 18960 MOONLIGHT CTM | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.0228 | -121.0165 |  | TIER 2 | 999 | 15249-1102, WEIMAR | R1012 | 6241 | Y | 311 |  |  | 2021-02-06 | 2021-02-06 | Dispatched | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.2 | 41 | 0.2 |  | 0 | 41.2 | 41 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100025924 | RELW OH PRI COMP CLR JPOL RESD FIRE ESTR CCNT FMOB TER2 PRTO FSRP | Pole | 2019-11-13 | 2019-11-27 | COMP | 2019-10-30 | COMP | 2021-02-06 | 2019-05-13 | 2019-05-14 | [11 empty] | 2021-02-10 | 2021-02-06 | 2020-03-05 |  | 2020-03-05 | 2021 CBP Plan | 2020-01-31 | QUES |  | 152491102 | 21354.91 | 9686.9 | 9612.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | MEADOW VISTA | Auburn |  |  | COMP | 116680614 | POLE_DECA_REPL - 3 S/O A/F 800 HAYWIRE R | 35091254 |  |  | STS-POLE_DECA_REPL - 3 S/O A/F 800 HAYWI | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.0249 | -120.9967 |  | TIER 2 | 999 | 15249-1102, WEIMAR | R1015 |  | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100024582 | RELW OH PRI COMP CLR JPOL RESD REMT ESTR GO BTKA CCNT PRTO FMOB TER2 FSRP | Pole | 2020-02-25 | 2020-05-19 | COMP | 2020-02-25 | [15 empty] | 2021-02-01 | 2021-01-22 | 2020-03-07 |  | 2020-03-07 | 2021 CBP Plan | 2020-01-31 | QUES |  | 152491102 | 6041.01 | 9383.3 | 9383.3 | 1180.6 | 1180.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | MEADOW VISTA | Auburn |  |  | OPEN | 116720262 | POLE_BROK_REPL - 1 W/O 2160 SIERRA DRMEA | 35149642 |  |  | STS-POLE_BROK_REPL - 1 W/O 2160 SIERRA D | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 39.0125 | -121.0302 |  | TIER 2 | 68 | 15224-1101, HALSEY | R1016 | 5723 | Y | 311 |  |  | 2020-09-29 | 2020-09-29 | Completed | Order Operation | [6 empty] | 29.8 | 29.8 |  |  | 0 | 29.8 | 29.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100072308 | RELW OH PRI CLR JPOL RESD REMT ESTR REAR PROG FMOB PRTO TER2 | Pole | 2020-04-23 | 2020-06-13 | COMP | 2020-04-22 |  |  | 2020-02-20 | 2020-02-20 | [12 empty] | 2019-03-13 | 2020-03-13 |  | 2020-03-13 | circuit based plan 2.14 | 2020-04-10 | PIKEENG |  | 152241101 | 16564.75 | 9786.5 | -11943.8 | -11943.8 | -11943.8 | 32.4 |  | 32.4 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | MEADOW VISTA | Auburn |  |  | OPEN | 116751105 | POLE_BROK_REPL - A/F 1610 COMBIE RD MEAD | 35149650 |  |  | STS-POLE_BROK_REPL - A/F 1610 COMBIE RD | CONS | CONS ERDY SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 39.0051 | -121.0283 |  | TIER 2 | 68 | 15224-1101, HALSEY | R1021 | 5723 | Y | 311 |  |  | 2021-04-01 07:00 | 2021-04-01 16:00 | Dispatched | CLICK | [6 empty] | 44.4 | 44.4 |  |  | 7.75 | 43.4 | 43.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100021575 | RELW CLR OH PRI JPOL PUBL ESTR BTKA FMOB TER2 PRTO | Pole | 2020-07-10 | 2020-07-14 | COMP | 2020-05-07 |  |  | 2020-02-27 | 2020-02-27 | [12 empty] | 2019-03-17 | 2020-03-17 |  | 2020-03-17 | circuit based plan 2.14 | 2020-04-10 | PIKEENG |  | 152241101 | 36453.77 | 9921.3 | 1013.4 | 668.1 | 668.1 | 416.9 |  | 416.9 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | MEADOW VISTA | Auburn |  |  | OPEN | 116751271 | POLE_BROK_REPL - AT 1610 COMBIE RD MEADO | 35149652 |  |  | STS-POLE_BROK_REPL - AT 1610 COMBIE RD M | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 39.0052 | -121.0281 |  | TIER 2 | 68 | 15224-1101, HALSEY | R1021 |  | Y | 311 |  |  | 2021-04-01 07:00 | 2021-04-01 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0.5 | 40.5 | 40.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100025282 | RELW OH SEC CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-04-14 | 2020-06-13 | COMP | 2020-04-14 |  |  | 2020-02-27 | 2020-02-27 | [12 empty] | 2019-03-17 | 2020-03-17 |  | 2020-03-17 | circuit based plan 2.14 | 2020-04-10 | PIKEENG |  | 152241101 | 8381.21 | 7167.7 | 762.2 | 762.2 | 762.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 116988774 | POLE_DECA_REPL - 615 E BROAD ST NEVADA C | 35086862 |  |  | STS-POLE_DECA_REPL - 1SE/O 616 BECKMAN L | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land | 2020-12-26 | Renew Permit | 39.2668 | -121.0222 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1001 | 42931 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 101 | 101 |  |  | 0 | 101 | 101 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100009118 | REGW OH PRI CLR TRAF FLAG ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-07-19 | 2020-01-17 | [12 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 1 | 2564.8 |  |  |  | 1832.6 |  | 1832.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 116989538 | POLE_BROK_REPL - 1SE/O 119 NIVENS STNEVA | 35086862 |  |  | STS-POLE_DECA_REPL - 1SE/O 616 BECKMAN L | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land | 2020-12-26 | Renew Permit | 39.2668 | -121.0223 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1001 | 42931 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100113269 | REGW OH PRI CLR TRAF FLAG ESTR GO BTKA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-07-19 | 2020-01-17 | [12 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 1 | 2564.8 |  |  |  | 1832.6 |  | 1832.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 116989716 | POLE_DECA_REPL - 119 NIVENS ST NEVADA CI | 35086862 |  |  | STS-POLE_DECA_REPL - 1SE/O 616 BECKMAN L | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land | 2020-12-26 | Renew Permit | 39.2672 | -121.0225 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1001 | 33165 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100106876 | REGW OH PRI CLR TRAF FLAG ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-07-19 | 2020-01-17 | [12 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 1 | 2564.8 |  |  |  | 1832.6 |  | 1832.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117004232 | POLE_BROK_REPL - #5 ON LINE SE/O 13596 J | 35127504 |  |  | STS-POLE_DECA_REPL - R/O 13596 JOE DAY R | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.2468 | -121.0047 |  | TIER 2 | 24 | 15248-1105, BRUNSWICK | M1013 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 4 | 0 | 209.7 | 209.7 |  |  | 0 | 209.7 | 209.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100085027 | REGW OH PRI CLR REMT NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2021-01-14 |  | COMP | 2021-01-14 |  |  | 2021-01-20 | 2021-01-25 | [12 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481105 | 63505.57 | 4128.7 | 183 |  |  | 1064.5 |  | 1064.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117005407 | POLE_DECA_REPL - 1N/O R/O 1871 PITTSGBUR | 35127505 |  |  | STS-POLE_DECA_REPL - 1N/O R/O 12466 OLD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.2425 | -121.0199 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1017 | 8918 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100008800 | REGW OH PRI RESD REMT ESTR FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-10-17 | 2019-10-17 | [12 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 1 | 607.9 |  |  |  | 122.9 |  | 122.9 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117005413 | POLE_DECA_REPL - 1N/O R/O 12466 OLD FREN | 35127505 |  |  | STS-POLE_DECA_REPL - 1N/O R/O 12466 OLD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.2419 | -121.0248 |  | TIER 2 | 24 | 15248-1105, BRUNSWICK | M1016 | 2100 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100000183 | RELW OH PRI JPOL RESD ESTR BTKA REAR USA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-10-17 | 2019-10-17 | [12 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481105 | 1 | 607.9 |  |  |  | 122.9 |  | 122.9 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117005559 | POLE_DECA_REPL - #2 ON LINE SE/O 13596 J | 35127504 |  |  | STS-POLE_DECA_REPL - R/O 13596 JOE DAY R | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.2479 | -121.0058 |  | TIER 2 | 24 | 15248-1105, BRUNSWICK | M1013 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 4 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100085024 | REGW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-14 |  | COMP | 2021-01-14 |  |  | 2021-01-20 | 2021-01-25 | [12 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481105 | 63505.57 | 4128.7 | 183 |  |  | 1064.5 |  | 1064.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117005594 | POLE_DECA_REPL - R/O 13596 JOE DAY RANCH | 35127504 |  |  | STS-POLE_DECA_REPL - R/O 13596 JOE DAY R | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.2485 | -121.0065 |  | TIER 2 | 24 | 15248-1105, BRUNSWICK | M1013 | 7301 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 4 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100076102 | RELW OH ESTR PRI CLR REMT BTKA FMOB TER2 PRTO | Pole | 2021-01-14 |  | COMP | 2021-01-14 |  |  | 2021-01-20 | 2021-01-25 | [12 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481105 | 63505.57 | 4128.7 | 183 |  |  | 1064.5 |  | 1064.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117007660 | POLE_DECA_REPL - 1SE/O 616 BECKMAN LNNEV | 35086862 |  |  | STS-POLE_DECA_REPL - 1SE/O 616 BECKMAN L | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land | 2020-12-26 | Renew Permit | 39.2675 | -121.0215 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1001 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100113893 | RELW OH PRI CLR TRAF FLAG ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-07-19 | 2020-01-17 | [12 empty] | 2019-04-11 | 2019-09-11 |  | 2019-09-11 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 1 | 2564.8 |  |  |  | 1832.6 |  | 1832.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117021146 | POLE_DECA_REPL - 2SW/O AF 206 SACRAMENTO | 35127257 |  |  | STS-POLE_DECA_REPL - 2SW/O AF 206 SACRAM | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 39.261 | -121.0166 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1007 | 2175 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 101 | 101 |  |  | 0 | 101 | 101 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100009007 | CLR RELW OH PRI PUBL RESD TRAF ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 1 | 3746.8 | 2613.9 | 2613.9 | 2613.9 | 422.5 |  | 422.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117021614 | POLE_DECA_REPL - 1SW/O 228 PROSPECT ST N | 35127257 |  |  | STS-POLE_DECA_REPL - 2SW/O AF 206 SACRAM | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 39.2599 | -121.0174 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1007 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100008968 | REGW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 1 | 3746.8 | 2613.9 | 2613.9 | 2613.9 | 422.5 |  | 422.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117021668 | POLE_DECA_REPL - R/O 310 NEVADA ST NEVAD | 35127254 |  |  | STS-POLE_DECA_REPL - R/O 310 NEVADA STNE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.2651 | -121.0142 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1002 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 246.4 | 246.4 |  |  | 0 | 246.4 | 246.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100091895 | RELW OH SERV CLR ESTR FMOB TER2 PRTO | Pole | 2020-12-28 |  | COMP | 2020-12-28 |  |  | 2021-02-18 | [13 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 72763.62 | 1159.7 |  |  |  | 1116.5 |  | 1116.5 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117022136 | POLE_BROK_REPL - R/O 208 CLAY ST NEVADA | 35127257 |  |  | STS-POLE_DECA_REPL - 2SW/O AF 206 SACRAM | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 39.26 | -121.0156 |  | TIER 2 | 24 | 15248-1105, BRUNSWICK | M1007 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100084912 | REGW OH SEC CLR RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481105 | 1 | 3746.8 | 2613.9 | 2613.9 | 2613.9 | 422.5 |  | 422.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117027148 | POLE_DECA_REPL - R/O 242 NEVADA STNEVADA | 35127254 |  |  | STS-POLE_DECA_REPL - R/O 310 NEVADA STNE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.2647 | -121.0143 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1002 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100091736 | REGW OH SEC CLR ESTR GO BTKA PRTO FMOB TER2 | Pole | 2020-12-28 |  | COMP | 2020-12-28 |  |  | 2021-02-18 | [13 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 72763.62 | 1159.7 |  |  |  | 1116.5 |  | 1116.5 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117027535 | TREE_DECA_INPL - 1N/O 13397 GRACIE RDNEV | 35101199 |  |  | STS-POLE_DECA_REPL - #3 ON LINE E/O 1352 | ESTS | ESTS HOLD | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.2525 | -121.0078 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1008 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 76 | 76 |  |  | 0 | 76 | 76 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100067135 | REGW OH SEC CLR JPOL REMT ESTR GO BTKA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-10-17 | 2019-10-17 | [12 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | Pole Notification Clean Up 05.29.20 | 2021-01-31 | W. Sac |  | 152481103 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-06-02
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117027935 | POLE_DECA_REPL - A/F 13463 GRACIE RD/GPN | 35101199 |  |  | STS-POLE_DECA_REPL - #3 ON LINE E/O 1352 | ESTS | ESTS HOLD | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.2516 | -121.0068 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1013 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100085011 | REGW OH PRI JPOL REMT ESTR GO BTKA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-10-17 | 2019-10-17 | [12 empty] | 2019-04-14 | 2020-04-14 |  | 2020-04-14 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117030153 | POLE_BROK_REPL - 327 CLAY STNEVADA CITY9 | 35127257 |  |  | STS-POLE_DECA_REPL - 2SW/O AF 206 SACRAM | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 39.2582 | -121.0148 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1007 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100008958 | REGW OH SEC CLR RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2024-04-13 | 2024-04-13 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 1 | 3746.8 | 2613.9 | 2613.9 | 2613.9 | 422.5 |  | 422.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117031143 | POLE_DECA_REPL - 140 GROVE STNEVADA CITY | 35127254 |  |  | STS-POLE_DECA_REPL - R/O 310 NEVADA STNE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.2637 | -121.0137 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1002 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100083338 | CLR REGW OH PRI RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-12-28 |  | COMP | 2020-12-28 |  |  | 2021-02-18 | [13 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 72763.62 | 1159.7 |  |  |  | 1116.5 |  | 1116.5 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117033018 | POLE_DECA_REPL - 211 NEVADA STNEVADA CIT | 35127254 |  |  | STS-POLE_DECA_REPL - R/O 310 NEVADA STNE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.2635 | -121.0155 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1002 | 1963 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100072974 | RELW OH PRI CLR RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-12-28 |  | COMP | 2020-12-28 |  |  | 2021-02-18 | [13 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 72763.62 | 1159.7 |  |  |  | 1116.5 |  | 1116.5 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117042865 | POLE_BROK_REPL - R/O 520 SILVA AVE NEVAD | 35093264 |  |  | STS-POLE_BROK_REPL - 1S/O 225 PARK AVE N | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.2577 | -121.0101 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1008 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 101 | 101 |  |  | 0 | 101 | 101 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100067072 | REGW OH SEC CLR REMT ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-10-15 | 2019-10-15 | [12 empty] | 2019-04-16 | 2020-04-16 |  | 2020-04-16 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 1 | 1138.2 |  |  |  | 371.6 |  | 371.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117061019 | POLE_BROK_REPL - 1S/O 225 PARK AVE NEVAD | 35093264 |  |  | STS-POLE_BROK_REPL - 1S/O 225 PARK AVE N | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.2614 | -121.0128 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1002 | 50005 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100072986 | RELW OH PRI INSP CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 | Pole |  |  | REQD |  |  |  | 2019-10-15 | 2019-10-15 | [12 empty] | 2019-04-18 | 2019-10-18 |  | 2019-10-18 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 1 | 1138.2 |  |  |  | 371.6 |  | 371.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117076335 | POLE_DECA_REPL - AF 217 BOULDER ST NEVAD | 35093264 |  |  | STS-POLE_BROK_REPL - 1S/O 225 PARK AVE N | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.2623 | -121.0125 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1002 | 7385 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100083322 | REGW OH PRI CLR ESTR TRAF FLAG BTKA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-10-15 | 2019-10-15 | [12 empty] | 2019-04-22 | 2020-04-22 |  | 2020-04-22 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 1 | 1138.2 |  |  |  | 371.6 |  | 371.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117076344 | POLE_DECA_REPL - 1SW/O 210 PARK AVENEVAD | 35093264 |  |  | STS-POLE_BROK_REPL - 1S/O 225 PARK AVE N | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.2618 | -121.0135 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1002 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100083355 | REGW OH GO SERV CLR ESTR REAR FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-10-15 | 2019-10-15 | [12 empty] | 2019-04-22 | 2020-04-22 |  | 2020-04-22 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 1 | 1138.2 |  |  |  | 371.6 |  | 371.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117077302 | POLE_DECA_REPL - 2R/O 549 UREN ST NEVADA | 35172445 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.2688 | -121.0125 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1002 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 37.6 | 37.6 |  |  | 0 | 37.6 | 37.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100072994 | RELW OH PRI CLR ESTR REAR FMOB TER2 PRTO | Pole | 2021-02-10 | 2021-02-08 | COMP | 2021-02-08 | [16 empty] | 2019-04-22 | 2020-04-22 |  | 2020-04-22 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152481103 | 13687.94 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117179820 | POLE_DECA_REPL - C/O PLEASANT VALLEY RD | 35163569 |  |  | STS-POLE_DECA_REPL - C/O PLEASANT VALLEY | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.3192 | -121.1517 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100099070 | RELW OH PRI FIRE INSP JPOL RESD TRAF ESTR BTKA USA FMOB TER2 | Pole | 2020-08-24 |  | COMP | 2020-08-24 | [16 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 10981.82 | 508.7 | -1385 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117180158 | POLE_DECA_REPL - #1NE ON LINE @ #1E HWY | 35163573 |  |  | STS-POLE_DECA_REPL - #1NE ON LINE @ #1E | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.3204 | -121.1001 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K08 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.4 | 57.4 |  |  | 0 | 57.4 | 57.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100104907 | RELW OH PRI CLR REMT FIRE NOAC FMOB ESTR REAR USA TER2 PRTO | Pole | 2020-08-28 | 2020-08-27 | COMP | 2020-08-27 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 13237.36 | 249.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117186095 | POLE_BROK_REPL - 1E/O 10909 LEE CREST CT | 35102111 |  |  | STS-POLE_BROK_REPL - 1SW/O 11150 WILLOW | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.2711 | -120.9971 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | L1024 | 31841 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100004670 | REGW OH PRI INSP JPOL RESD ESTR BTKA FMOB TER2 | Pole |  |  | REQD |  |  |  | 2019-10-17 | 2019-10-17 | [12 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 1 | 3286.9 |  |  |  | 1742.4 |  | 1742.4 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117186951 | POLE_DECA_REPL - R/O 10961 SUTTER DRNEVA | 35102111 |  |  | STS-POLE_BROK_REPL - 1SW/O 11150 WILLOW | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.2703 | -120.9991 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | L1024 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100004653 | REGW OH PRI INSP CLR JPOL REMT ESTR REAR FMOB TER2 | Pole |  |  | REQD |  |  |  | 2019-10-17 | 2019-10-17 | [12 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 1 | 3286.9 |  |  |  | 1742.4 |  | 1742.4 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117187182 | POLE_DECA_REPL - R/O 10976 SUTTER RDNEVA | 35102111 |  |  | STS-POLE_BROK_REPL - 1SW/O 11150 WILLOW | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.2702 | -121.0004 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | L1024 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100105744 | REGW OH PRI INSP CLR JPOL REMT ESTR REAR FMOB TER2 | Pole |  |  | REQD |  |  |  | 2019-10-17 | 2019-10-17 | [12 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 152481103 | 1 | 3286.9 |  |  |  | 1742.4 |  | 1742.4 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117210382 | POLE_BROK_REPL - R/O 10664 CORFLOWER CT | 35163707 |  |  | STS-POLE_BROK_REPL - R/O 10664 CORFLOWER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3235 | -121.1221 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 30307 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.7 | 41 | 0.7 |  | 0 | 41.7 | 41 | 0.7 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100107401 | RELW OH PRI CLR RESD ESTR FMOB TER2 PRTO | Pole | 2020-10-20 | 2020-12-11 | COMP | 2020-10-20 | [16 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 18501.75 | 1341.8 | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117210385 | POLE_BROK_REPL - #3S 10664 BIRCHVILLE RD | 35163711 |  |  | STS-POLE_BROK_REPL - #3S 10664 BIRCHVILL | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 39.3219 | -121.1199 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 23.3 | 23.3 |  |  | 0 | 23.3 | 23.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100107394 | RELW FMOB OH PRI ESTR TER2 PRTO | Pole | 2021-02-08 | 2021-02-05 | COMP | 2021-02-05 |  |  | 2020-05-11 | 2020-07-02 | [12 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 12586.24 | 1030.1 | -1029.9 | -49.3 | -49.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117210392 | POLE_BROK_REPL - #2S 10664 BIRCHVILLE RD | 35163717 |  |  | STS-POLE_BROK_REPL - #2S 10664 BIRCHVILL | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Enviro |  |  | 39.3225 | -121.1199 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 18.9 | 18.9 |  |  | 0 | 18.9 | 18.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100099111 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-09-23 |  | COMP | 2020-09-23 | [16 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 10911.65 |  | -1385 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117210393 | POLE_BROK_REPL - 10664 BIRCHVILLE RDNEVA | 35163719 |  |  | STS-POLE_BROK_REPL - 10664 BIRCHVILLE RD | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 39.3233 | -121.1196 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 26.5 | 26.5 |  |  | 0 | 26.5 | 26.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100099112 | RELW OH PRI CLR ESTR FMOB TER2 PRTO | Pole | 2020-09-29 | 2020-09-28 | COMP | 2020-09-28 | [16 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 10430.17 |  | -1385 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117216391 | POLE_BROK_REPL - R/O 11699 BIRCHVILLE RD | 35163801 |  |  | STS-POLE_BROK_REPL - R/O 11699 BIRCHVILL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.3166 | -121.1325 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100066808 | RELW OH PRI RESD REMT ESTR REAR FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117216393 | POLE_BROK_REPL - #3E 11427 BIRCHVILLE RD | 35163802 |  |  | STS-POLE_BROK_REPL - #3E 11427 BIRCHVILL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 39.3176 | -121.1298 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 3131 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.1 | 39.1 |  |  | 0 | 39.1 | 39.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100001874 | RELW OH PRI JPOL REMT ESTR FMOB TER2 PRTO | Pole | 2020-10-28 |  | COMP | 2020-10-28 | [16 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 19940.15 | 1443.3 | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117231605 | POLE_BROK_REPL - R/O 10644 READER RANCH | 35163664 |  |  | STS-POLE_BROK_REPL - R/O 10644 READER RA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.3163 | -121.1117 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100107426 | OH SEC ESTR REAR FMOB TER2 PRTO RELW | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117268832 | POLE_DECA_REPL - AT 13418 MCKITRICK RANC | 35229032 |  |  | STS-POLE_DECA_REPL - AT 13418 MCKITRICK | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.2867 | -121.1175 |  | TIER 2 | 154 | 15313-2102, NARROWS | L07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100003838 | OH PRI CLR JPOL MINR GO REAR FMOB TER2 PRTO RELW | Pole |  |  | REQD | [17 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | Per DOT Approved Request 31433 | 2021-02-28 | UNASSIGNED |  | 153132102 | [9 empty] | Y | MPP File Only | N |  | Y | 2021-01-28
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117272573 | POLE_DECA_REPL - #1W 15873 BITNEY SPRING | 35216681 |  |  | STS-POLE_DECA_REPL - #1W 15873 BITNEY SP | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 39.2585 | -121.1822 |  | TIER 2 | 154 | 15313-2102, NARROWS | M0607 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.1 | 28.1 |  |  | 0 | 28.1 | 28.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100007172 | RELW OH PRI JPOL RESD FLAG BTKA FMOB PRTO TER2 | Pole | 2020-12-31 |  | COMP | 2020-12-31 |  |  | 2021-01-12 | [13 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | Per DOT Approved Request 45786 |  | Auburn |  | 153132102 | 15276.12 | 422.4 | 243 | 243 | 243 |  |  |  | FRMMA/WMPMA - Electric | N | MPP Owned but exists in DO Pull | N |  | Y | 2021-02-06
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117384692 | POLE_BROK_REPL - 1S/O 1E/O 11827 BIRCHVI | 35163718 |  |  | STS-POLE_BROK_REPL - 1S/O 1E/O 11827 BIR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro | 2020-11-01 | Renew Permit | 39.3193 | -121.1356 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 3131 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 58.8 | 58.6 | 0.2 |  | 0 | 58.8 | 58.6 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 103828215 | RELW OH PRI CLR JPOL RESD REMT NOAC CGI ESTR REAR FMOB TER2 PRTO | Pole | 2020-09-01 | 2020-08-31 | COMP | 2020-08-31 |  |  | 2020-05-05 | 2020-05-07 | [12 empty] | 2019-06-04 | 2020-06-04 |  | 2020-06-04 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 29921.89 | 3774.1 | 391.4 | 374 | 374 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117393002 | POLE_BROK_REPL - R/O 11699 BIRCHVILLE RD | 35163722 |  |  | STS-POLE_BROK_REPL - R/O 11699 BIRCHVILL | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.3155 | -121.1312 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | L07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100066806 | RELW OH PRI CLR JPOL REMT NOAC ESTR GO REAR FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-06-05 | 2020-06-05 |  | 2020-06-05 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117396670 | POLE_DECA_REPL - 14304 BITNEY SPRINGS RD | 35229029 |  |  | STS-POLE_DECA_REPL - 14304 BITNEY SPRING | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.2542 | -121.1564 |  | TIER 2 | 154 | 15313-2102, NARROWS | M0610 | 1597 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100007164 | RELW OH PRI INSP CLR JPOL REMT FIRE NOAC GO FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-06-05 | 2019-12-05 |  | 2019-12-05 | Per DOT Approved Request 31442 | 2021-02-28 | UNASSIGNED |  | 153132102 | [9 empty] | Y | MPP File Only | N |  | Y | 2021-01-28
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117880314 | POLE_BROK_REPL - AT 23294 HWY 49 [ LAST | 35163776 |  |  | STS-POLE_BROK_REPL - AT 23294 HWY 49 [ L | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3107 | -121.1142 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | L07 | 4203 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.4 | 42.4 |  |  | 0 | 42.4 | 42.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100004249 | RELW PRI OH INSP CLR JPOL REMT FIRE NOAC ESTR FMOB TER2 | Pole | 2020-10-14 | 2021-02-12 | COMP | 2020-10-14 | [16 empty] | 2019-09-13 | 2020-09-13 |  | 2020-09-13 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 21347.73 | 1547.4 | 17.4 | [5 empty] | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117882057 | POLE_BROK_REPL - R/O 11699 BIRCHVILLE RD | 35163777 |  |  | STS-POLE_BROK_REPL - R/O 11699 BIRCHVILL | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.3152 | -121.1306 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | L07 | 3101 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100066805 | RELW OH PRI INSP CLR REMT FIRE NOAC ESTR TER2 FMOB | Pole |  |  | REQD | [17 empty] | 2019-09-13 | 2020-06-15 |  | 2020-06-15 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 1 | 474 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 118389213 | TREE_DECA_INPL - A/F 1 NE/O 21605 PLACER | 35101199 |  |  | STS-POLE_DECA_REPL - #3 ON LINE E/O 1352 | ESTS | ESTS HOLD | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.2525 | -121.0078 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1008 | 33113 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100067135 | POHW OH ESTR TER2 | Pole |  |  | REQD |  |  |  | 2019-10-17 | 2019-10-17 | [12 empty] | 2019-12-31 | 2020-04-14 |  | 2020-04-14 | Pole Notification Clean Up 05.29.20 | 2021-01-31 | W. Sac |  | 152481103 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-06-02
North | SI | NEVADA CITY | Grass Valley |  |  | COMP | 117190343 | POLE_DECA_REPL - #3S BIRCHVILLE RD ON PL | 35163659 |  |  | STS-POLE_DECA_REPL - #3S BIRCHVILLE RD O | DOCC | DOCC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2021-12-31 | No Action | 39.3174 | -121.1527 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K06 |  | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 56.3 | 56.3 |  |  | 0 | 56.3 | 56.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100103953 | RELW OH PRI COMP REMT NOAC ESTR GO REAR USA CCNT FMOB TER2 PRTO | Pole | 2020-10-23 | 2020-10-23 | COMP | 2020-10-23 | COMP | 2021-02-11 | 2021-02-01 | 2021-02-03 | [11 empty] | 2021-02-18 | 2021-02-11 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 9233.35 | 2951.5 | 833.9 | 213.5 | 213.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 116860212 | POLE_BROK_REPL - AF 13325 NEWTOWN RDNEVA | 35163389 |  |  | STS-POLE_BROK_REPL - AF 13325 NEWTOWN RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-12-30 |  | 39.2532 | -121.1035 |  | TIER 2 | 154 | 15313-2102, NARROWS | M08 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 60.1 | 60.1 |  |  | 0 | 60.1 | 60.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100109356 | OH PRI JPOL FLAG ESTR BTKA FMOB TER2 PRTO RELW | Pole | 2020-08-31 | 2020-10-13 | COMP | 2020-08-27 |  |  | 2021-02-08 | 2021-02-11 | [12 empty] | 2019-03-28 | 2020-03-28 |  | 2020-03-28 | 2021 CBP Plan | 2020-10-31 | TRC |  | 153132102 | 11116.96 | 472.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 116969720 | POLE_DECA_REPL - 1S/O 475 SPRING ST NEVA | 35127448 |  |  | STS-POLE_DECA_REPL - 1S/O 475 SPRING ST | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-06-12 | No Action | 39.2634 | -121.0218 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1001 | 9117 | Y | 311 |  |  | 2021-04-01 07:00 | 2021-04-01 16:00 | Scheduled | CLICK | [6 empty] | 108.7 | 103.5 | 5 | 0.2 | 0 | 108.7 | 103.5 | 5 | 0.2 | EC | E | Pole | Decayed/Rotten | Replace |  | 100106843 | RELW OH PRI CLR GO TRAF FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-11-30 | 2020-12-29 | COMP | 2020-07-15 |  |  | 2020-05-12 | 2020-06-01 | [12 empty] | 2019-04-06 | 2020-04-06 |  | 2020-04-06 | Q1 Work Plan | 2020-05-31 | W. Sac |  | 152481103 | 114480.63 | 1600.6 | 275.9 | 275.9 | 275.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 116973715 | POLE_DECA_REPL - 321 DRUMMON ST NEVADA C | 35127448 |  |  | STS-POLE_DECA_REPL - 1S/O 475 SPRING ST | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-06-12 | No Action | 39.2625 | -121.0241 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1001 | 9117 | Y | 311 |  |  | 2021-04-01 07:00 | 2021-04-01 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100009159 | REGW OH PRI CLR TRAF FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-11-30 | 2020-12-29 | COMP | 2020-07-15 |  |  | 2020-05-12 | 2020-06-01 | [12 empty] | 2019-04-07 | 2020-04-07 |  | 2020-04-07 | Q1 Work Plan | 2020-05-31 | W. Sac |  | 152481103 | 114480.63 | 1600.6 | 275.9 | 275.9 | 275.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 116985458 | POLE_BROK_REPL - SP R/O 334 JORDAN STNEV | 35127448 |  |  | STS-POLE_DECA_REPL - 1S/O 475 SPRING ST | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-06-12 | No Action | 39.2601 | -121.0233 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1006 |  | Y | 311 |  |  | 2021-04-01 07:00 | 2021-04-01 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100094088 | REGW OH PRI CLR RESD NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-11-30 | 2020-12-29 | COMP | 2020-07-15 |  |  | 2020-05-12 | 2020-06-01 | [12 empty] | 2019-04-09 | 2020-04-09 | 2021-05-31 | 2021-05-31 | Q1 Work Plan | 2020-05-31 | W. Sac |  | 152481103 | 114480.63 | 1600.6 | 275.9 | 275.9 | 275.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117005536 | POLE_BROK_REPL - 22N/O 10738 RIDGE RD. N | 35149855 |  |  | STS-POLE_BROK_REPL - 22N/O 10738 RIDGE R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2576 | -121.0387 |  | TIER 2 | 59 | 15248-1104, BRUNSWICK | M0909 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100103150 | OH PRI ESTR REAR FMOB TER2 PRTO RELW | Pole | 2020-04-13 | 2020-04-13 | COMP | 2020-04-13 | [16 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | circuit based plan 2.14 | 2020-04-10 | PIKEENG |  | 152481104 | 26623.42 | 9271.7 | 7068.2 | 7068.2 | 7068.2 | 90.4 |  | 90.4 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117008411 | POLE_DECA_REPL - SP 582 MAIN ST NEVADA C | 35086863 |  |  | B2STS-POLE_DECA_REP-SP 582 MAIN STNEVAD | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2673 | -121.0209 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1001 |  | Y | 311 |  |  | 2021-03-06 07:00 | 2021-03-06 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 3 | 0 | 0 | 126 | 126 |  |  |  | 126 | 126 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100009057 | RELW OH SERV CLR TRAF FLAG ESTR BTKA PRTO FMOB TER2 | Pole | 2020-06-05 | 2020-06-27 | COMP | 2020-05-08 |  |  | 2019-10-15 | 2019-10-15 | [12 empty] | 2019-04-11 | 2019-09-11 |  | 2019-09-11 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 152481103 | 41611.84 | 22717.7 | -9970.9 | 9779.3 | 9779.3 | 926.2 |  | 926.2 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117015810 | POLE_BROK_REPL - 3S/O 527 JORDAN ST NEVA | 35127448 |  |  | STS-POLE_DECA_REPL - 1S/O 475 SPRING ST | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-06-12 | No Action | 39.2578 | -121.0279 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1006 | 5737 | Y | 311 |  |  | 2021-04-01 07:00 | 2021-04-01 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100094091 | REGW OH PRI CLR JPOL RESD REAR REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-11-30 | 2020-12-29 | COMP | 2020-07-15 |  |  | 2020-05-12 | 2020-06-01 | [12 empty] | 2019-04-12 | 2020-04-12 | 2024-04-10 | 2024-04-10 | Q1 Work Plan | 2020-05-31 | W. Sac |  | 152481103 | 114480.63 | 1600.6 | 275.9 | 275.9 | 275.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117017709 | POLE_DECA_REPL - SP R/O 337 ALEXANDER ST | 35086863 |  |  | B2STS-POLE_DECA_REP-SP 582 MAIN STNEVAD | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2676 | -121.019 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1002 |  | Y | 311 |  |  | 2021-03-06 07:00 | 2021-03-06 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 3 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100009053 | REGW OH SERV CLR ESTR BTKA USA PROG FMOB TER2 PRTO | Pole | 2020-06-05 | 2020-06-27 | COMP | 2020-05-08 |  |  | 2019-10-15 | 2019-10-15 | [12 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 152481103 | 41611.84 | 22717.7 | -9970.9 | 9779.3 | 9779.3 | 926.2 |  | 926.2 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117018324 | POLE_BROK_REPL - R/O 211 REWARD STNEVADA | 35127450 |  |  | STS-POLE_BROK_REPL - R/O 211 REWARD STNE | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2543 | -121.0271 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1006 |  | Y | 311 |  |  | 2021-03-13 07:00 | 2021-03-13 16:00 | Scheduled | CLICK | [6 empty] | 68.7 | 68.7 |  |  | 0 | 68.7 | 68.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100008891 | RELW OH SEC CLR ESTR JPOL RESD REMT BTKA REAR FMOB TER2 PRTO FSRP | Pole | 2020-10-01 | 2020-11-28 | COMP | 2020-10-01 |  |  | 2019-10-15 | 2019-10-15 | [12 empty] | 2019-04-12 | 2020-04-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-07-31 | Auburn |  | 152481103 | 21381.74 | 1397.5 | 666.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117024750 | POLE_BROK_REPL - R/O 12484 NEVADA CITY H | 35163451 |  |  | STS-POLE_BROK_REPL - R/O 12484 NEVADA CI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2463 | -121.0316 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M0915 | 7341 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 43.5 | 42.8 | 0.7 |  | 0 | 43.5 | 42.8 | 0.7 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100104523 | JPOL OH PRI RELW ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-06-12 | 2020-06-12 | COMP | 2020-06-12 | [16 empty] | 2019-04-13 | 2020-04-13 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-07-31 | Auburn |  | 152481103 | 34464.67 | 23046 | 18667.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117068926 | POLE_BROK_REPL - AF 10340 WILLOW VALLEY | 35127251 |  |  | STS-POLE_BROK_REPL - 1E/O 11735 BOURBON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-12-30 | No Action | 39.2677 | -121.0079 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1003 | 50003 | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 81.5 | 81.5 |  |  | 0 | 81.5 | 81.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100008619 | REGW OH PRI CLR RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-10-15 | COMP | 2020-05-02 |  |  | 2021-02-08 | 2021-02-10 | [12 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 152481103 | 54993.61 | 33193.3 | 20770 | 7004.5 | 7004.5 | 674.5 |  | 674.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117069132 | POLE_DECA_REPL - 1SE/O 14700 HEARTER PL | 35127251 |  |  | STS-POLE_BROK_REPL - 1E/O 11735 BOURBON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-12-30 | No Action | 39.2668 | -121.0072 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1003 |  | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100009102 | PRI REGW OH CLR RESD ESTR BTKA REAR FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-10-15 | COMP | 2020-05-02 |  |  | 2021-02-08 | 2021-02-10 | [12 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 152481103 | 54993.61 | 33193.3 | 20770 | 7004.5 | 7004.5 | 674.5 |  | 674.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117070625 | POLE_BROK_REPL - 1E/O 11735 BOURBON HILL | 35127251 |  |  | STS-POLE_BROK_REPL - 1E/O 11735 BOURBON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-12-30 | No Action | 39.2687 | -121.0069 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1003 |  | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100083409 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-10-15 | COMP | 2020-05-02 |  |  | 2021-02-08 | 2021-02-10 | [12 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 152481103 | 54993.61 | 33193.3 | 20770 | 7004.5 | 7004.5 | 674.5 |  | 674.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117070823 | POLE_DECA_REPL - AF 650 MANZANITA LN NEV | 35127250 |  |  | STS-POLE_DECA_REPL - AF 650 MANZANITA LN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2697 | -121.0115 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1003 | 33513 | Y | 311 |  |  | 2021-03-12 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | [6 empty] | 76.9 | 76.9 |  |  | 0 | 76.9 | 76.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100072993 | RELW OH PRI CLR JPOL RESD ESTR BTKA PROG FMOB TER2 PRTO | Pole | 2020-07-01 | 2020-09-04 | COMP | 2020-07-01 |  |  | 2020-07-05 | 2020-07-08 | [12 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 152481103 | 61318.76 | 736.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117070987 | POLE_BROK_REPL - AF 155 BOURBON HILL RDN | 35127250 |  |  | STS-POLE_DECA_REPL - AF 650 MANZANITA LN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2686 | -121.0107 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | M1003 |  | Y | 311 |  |  | 2021-03-12 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100008603 | REGW OH SEC CLR RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-07-01 | 2020-09-04 | COMP | 2020-07-01 |  |  | 2020-07-05 | 2020-07-08 | [12 empty] | 2019-04-20 | 2020-04-20 |  | 2020-04-20 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 152481103 | 61318.76 | 736.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117161088 | POLE_BROK_REPL - 16922 WASHINGTON RDNEVA | 35127247 |  |  | STS-POLE_BROK_REPL - 15255 ONE MILE WY N | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-30 | Renew Permit | 39.2731 | -121.008 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | L1023 |  | Y | 311 |  |  | 2021-04-21 07:00 | 2021-04-21 16:00 | Scheduled | CLICK | [6 empty] | 80.6 | 80.6 |  |  | 0 | 80.6 | 80.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100005616 | SERV RELW OH INSP JPOL RESD ESTR BTKA FMOB TER2 | Pole | 2020-03-20 | 2020-09-18 | COMP | 2020-03-20 |  |  | 2020-07-10 | 2020-07-13 | [12 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 152481103 | 67081.59 | 2798.8 |  |  |  | 1113 |  | 1113 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117175646 | POLE_BROK_REPL - 15232 LEWIS RD NEVADA C | 35127247 |  |  | STS-POLE_BROK_REPL - 15255 ONE MILE WY N | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-30 | Renew Permit | 39.2723 | -121.0049 |  | TIER 2 | 34 | 15248-1103, BRUNSWICK | L1023 | 31321 | Y | 311 |  |  | 2021-04-21 07:00 | 2021-04-21 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100005366 | REGW OH PRI INSP JPOL RESD FLAG ESTR GO BTKA OTRG FMOB TER2 | Pole | 2020-03-20 | 2020-09-18 | COMP | 2020-03-20 |  |  | 2020-07-10 | 2020-07-13 | [12 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 152481103 | 67081.59 | 2798.8 |  |  |  | 1113 |  | 1113 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117180149 | POLE_DECA_REPL - #3NE ON LINE @ #1E HWY | 35163571 |  |  | STS-POLE_DECA_REPL - #3NE ON LINE @ #1E | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3216 | -121.098 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K08 |  | Y | 311 |  |  | 2021-03-16 07:00 | 2021-03-16 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100104909 | RELW OH PRI CLR REMT FIRE NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2020-08-18 | 2020-08-18 | COMP | 2020-08-18 | [16 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 19376.19 | 2436.3 | 164.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117184159 | POLE_BROK_REPL - 21581 PLEASANT VALLEY R | 35163600 |  |  | STS-POLE_BROK_REPL - 21581 PLEASANT VALL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-12-30 |  | 39.3148 | -121.154 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | L06 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 63 | 63 |  |  | 0 | 63 | 63 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100003729 | RELW OH REMT PRI CLR JPOL TRAF FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-26 | 2020-08-26 | COMP | 2020-08-26 |  |  | 2021-02-10 | 2021-02-16 | [12 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 13611.95 | 670.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117210383 | POLE_BROK_REPL - SP/O 1W/O 7145 CAVITT S | 35163709 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3238 | -121.1196 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 13.3 | 13.3 |  |  | 0 | 13.3 | 13.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103688974 | OH RELW PRI RESD ESTR FMOB TER2 PRTO | Pole | 2020-08-17 | 2020-08-18 | COMP | 2020-08-17 | [16 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 6517.39 | 725.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117210387 | POLE_BROK_REPL - #1E #1S 16474 CORNFLOWE | 35163713 |  |  | STS-POLE_BROK_REPL - #1E #1S 16474 CORNF | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3237 | -121.1207 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  | 2021-03-11 07:00 | 2021-03-11 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100107400 | RELW OH PRI RESD ESTR FMOB TER2 PRTO | Pole | 2020-09-15 | 2020-11-17 | COMP | 2020-09-14 | [16 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 6962.2 | 796 | -722.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117210388 | POLE_BROK_REPL - #1N 10664 BIRCHVILLE RD | 35163715 |  |  | STS-POLE_BROK_REPL - #1N 10664 BIRCHVILL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3237 | -121.1196 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.7 | 23.7 |  |  | 0 | 23.7 | 23.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100099113 | RELW OH PRI RESD RTRN ESTR FMOB TER2 PRTO | Pole | 2020-08-25 | 2020-10-27 | COMP | 2020-08-24 | [16 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-09-30 | TRC |  | 152471101 | 10597.91 | 129.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117216386 | POLE_DECA_REPL - 1W/O ENT 11438 BIRCHVIL | 35163773 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 39.3191 | -121.1333 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 17.6 | 17.6 |  |  | 0 | 17.6 | 17.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103828213 | RELW OH PRI JPOL REMT ESTR FMOB TER2 PRTO | Pole | 2020-12-01 | 2020-12-02 | COMP | 2020-09-25 |  |  | 2020-12-01 | 2020-12-02 | [12 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 9349.21 | 2176.9 | 64.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117216396 | POLE_BROK_REPL - A/F 11427 BIRCHVILLE RD | 35163803 |  |  | STS-POLE_BROK_REPL - A/F 11427 BIRCHVILL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-11-30 | Renew Permit | 39.3182 | -121.1319 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 3131 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 26 | 26 |  |  | 0 | 26 | 26 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100001877 | RELW OH PRI CLR JPOL REMT ESTR FMOB TER2 PRTO | Pole | 2020-08-21 | 2020-10-16 | COMP | 2020-08-20 |  |  | 2020-05-04 | 2020-05-06 | [12 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 15618.39 | 2019.7 | 1233.3 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117216397 | POLE_BROK_REPL - #1E 11427 BIRCHVILLE RD | 35163804 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-11-30 | Renew Permit | 39.3176 | -121.1315 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100001876 | RELW OH PRI CLR JPOL REMT ESTR FMOB TER2 PRTO | Pole | 2020-08-21 | 2020-10-11 | COMP | 2020-08-21 |  |  | 2020-05-05 | 2020-05-07 | [12 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 11075.56 | 566.8 | 64.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117231602 | POLE_BROK_REPL - #1S CO#4203 @ #3 ON LIN | 35163660 |  |  | STS-POLE_BROK_REPL - #1S CO#4203 @ #3 ON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3166 | -121.1094 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K08 | 4203 | Y | 311 |  |  | 2021-03-16 07:00 | 2021-03-16 16:00 | Scheduled | CLICK | [6 empty] | 14.2 | 14.2 |  |  | 0 | 14.2 | 14.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100109316 | RELW OH PRI REMT ESTR WATR FMOB TER2 PRTO | Pole | 2020-08-31 | 2020-11-03 | COMP | 2020-08-31 | [16 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 441610.39 | 2025.1 | 662.2 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117231604 | POLE_BROK_REPL - #2S CO#4203 @ #3 ON LIN | 35163662 |  |  | STS-POLE_BROK_REPL - #2S CO#4203 @ #3 ON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3163 | -121.11 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 4203 | Y | 311 |  |  | 2021-03-16 07:00 | 2021-03-16 16:00 | Scheduled | CLICK | [6 empty] | 40.2 | 40.2 |  |  | 0 | 40.2 | 40.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100109317 | RELW OH PRI CLR JPOL REMT ESTR FMOB PRTO TER2 | Pole | 2020-09-14 | 2020-11-18 | COMP | 2020-09-11 | [16 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 20634.7 | 451.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117243458 | POLE_BROK_REPL - #2W ON LINE A/F 25563 H | 35163676 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3366 | -121.1174 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K0715 | 1529 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100104966 | RELW OH PRI CLR NOAC ESTR FMOB PRTO TER2 | Pole | 2020-08-27 | 2020-08-27 | COMP | 2020-08-27 | [16 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 20074.54 | 5706.3 | 4913.2 | 863 | 863 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117243542 | POLE_BROK_REPL - #3 S/O ENTRANCE @ PACHE | 35163678 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3333 | -121.115 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 17.5 | 17.5 |  |  | 0 | 17.5 | 17.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100107451 | RELW OH PRI CLR NOAC ESTR FMOB TER2 PRTO | Pole | 2020-08-27 | 2020-10-16 | COMP | 2020-08-27 | [16 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 12417.33 | 252.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117243553 | POLE_BROK_REPL - #1S ENTRANCE TO PACHECO | 35163680 |  |  | STS-POLE_BROK_REPL - #1S ENTRANCE TO PAC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3344 | -121.116 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K0715 | 1529 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 52.3 | 52.3 |  |  | 0 | 52.3 | 52.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100099130 | RELW OH PRI CLR ESTR FMOB TER2 PRTO | Pole | 2020-10-21 | 2020-12-29 | COMP | 2020-10-21 | [16 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 20964.92 | 1105.1 | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117250272 | POLE_DECA_REPL - #1 ON LINE W/O 16000 PL | 35163688 |  |  | STS-POLE_DECA_REPL - #1 ON LINE W/O 1600 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3382 | -121.1258 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 6081 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 45.3 | 45.3 |  |  | 0 | 45.3 | 45.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100107492 | RELW OH PRI CLR JPOL ESTR RESD REMT FMOB TER2 PRTO | Pole | 2020-09-11 | 2020-11-17 | COMP | 2020-09-11 | [16 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 22266.77 | 2362.6 | 681.6 | 40.8 | 40.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117270628 | POLE_DECA_REPL - 1E/O 2N/O 15880 BEITLER | 35163696 |  |  | STS-POLE_DECA_REPL - 1E/O 2N/O 15880 BEI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2574 | -121.1823 |  | TIER 2 | 154 | 15313-2102, NARROWS | M0607 | 1595 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.3 | 27.3 |  |  | 0 | 27.3 | 27.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100007176 | RELW OH PRI JPOL RESD REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-11 | 2021-01-11 | COMP | 2020-08-10 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-09-30 | TRC |  | 153132102 | 16551.75 | 1768.4 | 299.1 | 299.1 | 299.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117273745 | POLE_DECA_REPL - 2E/O 1S/O 18053 E.STARD | 35163704 |  |  | STS-POLE_DECA_REPL - 2E/O 1S/O 18053 E.S | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.264 | -121.1725 |  | TIER 2 | 154 | 15313-2102, NARROWS | M0603 |  | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100106885 | RELW OH PRI JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-21 | 2020-10-12 | COMP | 2020-08-06 | [16 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | 2021 CBP Plan | 2020-09-30 | TRC |  | 153132102 | 13205.32 | 5059.6 | 3725.4 | 997.8 | 997.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117278969 | POLE_DECA_REPL - 15326 FAWNBROOK ACCESS | 35163706 |  |  | STS-POLE_DECA_REPL - 15326 FAWNBROOK ACC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3303 | -121.1153 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | [6 empty] | 34.5 | 34.5 |  |  | 0 | 34.5 | 34.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100113328 | RELW OH PRI JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-28 | 2020-10-08 | COMP | 2020-08-28 | [16 empty] | 2019-05-20 | 2020-05-20 |  | 2020-05-20 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 13277.6 | 1373.8 | -146.9 | -146.9 | -146.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117385226 | POLE_BROK_REPL - #1N ENTRANCE TO PACHECO | 35163720 |  |  | STS-POLE_BROK_REPL - #1N ENTRANCE TO PAC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3355 | -121.1167 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K0715 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.8 | 18.8 |  |  | 0 | 18.8 | 18.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100104967 | RELW OH PRI CUST CLR RESD REMT NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2020-09-22 | 2020-09-23 | COMP | 2020-09-21 | [16 empty] | 2019-06-04 | 2020-06-04 |  | 2020-06-04 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 23861.98 | 335.7 | -1385 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEVADA CITY | Grass Valley |  |  | OPEN | 117216388 | POLE_DECA_REPL - ENT 11438 BIRCHVILLE RD | 35163800 |  |  | STS-POLE_DECA_REPL - ENT 11438 BIRCHVILL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-11-30 |  | 39.3191 | -121.1327 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.4 | 14.4 |  |  | 0 | 14.4 | 14.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103828212 | RELW OH PRI JPOL REMT ESTR FMOB TER2 PRTO | Pole | 2021-01-28 | 2021-02-02 | COMP | 2020-10-20 |  |  | 2021-01-28 | 2020-05-29 | [12 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 9688.54 | 2588.8 | -1385 | -1385 | -1385 | 3146.9 |  | 3146.9 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEWCASTLE | Auburn |  |  | OPEN | 116750726 | POLE_BROK_REPL - 1S/O 1E/O 6320 SCHINDLE | 35214892 |  |  | STS-POLE_BROK_REPL - 1S/O 1E/O 6320 SCHI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.9156 | -121.1852 |  | TIER 2 | 129 | 15227-1102, WISE | T0622 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100050438 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152271102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEWCASTLE | Auburn |  |  | OPEN | 116981931 | POLE_BROK_REPL - C/O SPRING LN & ARMES L | 35214813 |  |  | STS-POLE_BROK_REPL - C/O SPRING LN & ARM | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.8751 | -121.16 |  | TIER 2 | 761 | 15256-1105, PENRYN | U0625 | 9461 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100044153 | OH PRI INSP JPOL RESD REMT FIRE ESTR GO FMOB RELW BTKA USA TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-08 | 2020-04-08 | 2021-04-09 | 2021-04-09 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152561105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEWCASTLE | Auburn |  |  | OPEN | 117219010 | POLE_BROK_REPL - AT 2050 GOLD HILL RD NE | 35202647 |  |  | STS-POLE_BROK_REPL - AT 2050 GOLD HILL R | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 38.9123 | -121.1866 |  | TIER 2 | 761 | 15256-1105, PENRYN | U0602 | 5399 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.4 | 29.4 |  |  | 0 | 29.4 | 29.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100099482 | RELW OH PRI JPOL ESTR RESD REMT BTKA RTRN FMOB TER2 PRTO FSRP | Pole | 2020-12-15 |  | COMP | 2020-12-15 | [16 empty] | 2019-05-12 | 2020-05-12 | 2020-10-11 | 2020-10-11 | 2021 CBP Plan | 2021-02-28 | TRC |  | 152561105 | 14341.89 |  | -1648.1 | -1376.6 | -1376.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEWCASTLE | Auburn |  |  | OPEN | 116870959 | POLE_BROK_REPL - 425 UNCLE JOES LN NEWCA | 35163391 |  |  | STS-POLE_BROK_REPL - 425 UNCLE JOES LNNE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 38.8913 | -121.1545 |  | TIER 2 | 129 | 15227-1102, WISE | U0711 |  | Y | 311 |  |  | 2021-03-27 07:00 | 2021-03-27 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100050481 | OH PRI CLR FMOB RELW JPOL RESD ESTR BTKA TER2 PRTO | Pole | 2020-09-01 | 2020-10-20 | COMP | 2020-09-01 |  |  | 2020-04-08 | 2020-04-08 | [12 empty] | 2019-03-30 | 2020-03-30 |  | 2020-03-30 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152271102 | 14239.82 | 1495.2 | -1385 | -1385 | -1385 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEWCASTLE | Auburn |  |  | OPEN | 116873027 | POLE_BROK_REPL - A/F 460 REAMS RDNEWCAST | 35163393 |  |  | STS-POLE_BROK_REPL - A/F 460 REAMS RDNEW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8906 | -121.1522 |  | TIER 2 | 129 | 15227-1102, WISE | U0711 |  | Y | 311 |  |  | 2021-03-26 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100080244 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-24 | 2020-10-19 | COMP | 2020-08-24 |  |  | 2020-05-27 | 2020-05-27 | [12 empty] | 2019-03-30 | 2020-03-30 |  | 2020-03-30 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152271102 | 10410.04 | 32.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEWCASTLE | Auburn |  |  | OPEN | 116875880 | POLE_BROK_REPL - AT 1NO 5520 VIRGINIA TO | 35134820 |  |  | STS-POLE_BROK_REPL - AT 1NO 5520 VIRGINI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.902 | -121.1998 |  | TIER 2 | 714 | 15370-1101, LINCOLN | U0510 |  | Y | 311 |  |  | 2021-03-26 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100049516 | RELW OH PRI JPOL RESD BTKA FMOB TER2 PRTO FSRP | Pole | 2020-06-22 | 2020-08-11 | COMP | 2020-06-22 | [16 empty] | 2019-03-31 | 2020-03-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | TRC |  | 153701101 | 12404.89 | 5115.3 | 1395.8 | 1395.8 | 1395.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEWCASTLE | Auburn |  |  | OPEN | 116940833 | POLE_BROK_REPL - 997 LOZANOS RDNEWCASTLE | 35163397 |  |  | STS-POLE_BROK_REPL - 997 LOZANOS RDNEWCA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 38.8915 | -121.1256 |  | TIER 2 | 129 | 15227-1102, WISE | U0714 |  | Y | 311 |  |  | 2021-03-26 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100044249 | OH PRI CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO RELW | Pole | 2020-09-03 | 2020-09-04 | COMP | 2020-09-03 |  |  | 2020-06-24 | 2020-06-24 | [12 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152271102 | 31232.08 | 9023.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEWCASTLE | Auburn |  |  | OPEN | 116945857 | POLE_BROK_REPL - 1091 LOZANOS RDNEWCASTL | 35163398 |  |  | STS-POLE_BROK_REPL - 1091 LOZANOS RDNEWC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 38.8928 | -121.1251 |  | TIER 2 | 129 | 15227-1102, WISE | U0714 | 38617 | Y | 311 |  |  | 2021-04-03 07:00 | 2021-04-03 16:00 | Scheduled | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100044224 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-31 | 2020-10-27 | COMP | 2020-08-31 |  |  | 2020-06-24 | 2020-06-24 | [12 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152271102 | 20699.95 | 198.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NEWCASTLE | Auburn |  |  | OPEN | 117001354 | POLE_BROK_REPL - 8957 RIDGE RDNEWCASTLE9 | 35163399 |  |  | STS-POLE_BROK_REPL - 8957 RIDGE RDNEWCAS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8823 | -121.1375 |  | TIER 2 | 129 | 15227-1102, WISE | U0718 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.6 | 23.6 |  |  | 0 | 23.6 | 23.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100050409 | RELW OH SEC CLR JPOL RESD ESTR REAR FMOB TER2 PRTO | Pole | 2020-08-31 | 2020-11-09 | COMP | 2020-08-31 | [16 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152271102 | 8696.7 | 1145.9 | -239.1 | -239.1 | -239.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORDEN | Auburn |  |  | OPEN | 117771756 | POLE_DECA_REPL - ,NORDEN NORDEN | 35202449 |  |  | STS-POLE_DECA_REPL - ,NORDEN NORDEN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.3175 | -120.3525 |  | TIER 2 | 778 | 15259-1102, SUMMIT | K2619 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.7 | 34.7 |  |  | 0 | 34.7 | 34.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103704984 | RELW OH TNT TER2 FSRP | Pole | 2020-12-28 |  | COMP | 2020-12-28 | [16 empty] | 2019-06-18 | 2020-06-18 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | TRC |  | 152591102 | 20060.8 | 80.7 | -1141.3 | 786.7 | 786.7 |  |  |  | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117196230 | POLE_BROK_REPL - 22676 PLEASANT VALLEY R | 35163693 |  |  | STS-POLE_BROK_REPL - 22676 PLEASANT VALL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.3255 | -121.1474 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.8 | 28.8 |  |  | 0 | 28.8 | 28.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100001717 | RELW OH PRI JPOL PUBL FLAG ESTR BTKA FMOB PRTO TER2 | Pole | 2020-10-06 |  | COMP | 2020-10-06 |  |  | 2021-02-18 | [13 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 11141.24 | 838 | -1385 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117211463 | POLE_DECA_REPL - 22752 PLEASANT VALLEY R | 35163735 |  |  | STS-POLE_DECA_REPL - 22752 PLEASANT VALL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole | 2020-12-30 | Renew Permit | 39.3268 | -121.146 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 90730 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.3 | 25.3 |  |  | 0 | 25.3 | 25.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001728 | RELW JPOL OH PRI PUBL RESD FLAG ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-08-31 |  | COMP | 2020-08-31 |  |  | 2020-04-29 | 2020-04-30 | [12 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 14153.53 | 643.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117211465 | POLE_DECA_REPL - A/F 12212 VICKI DRNORTH | 35163739 |  |  | STS-POLE_DECA_REPL - A/F 12212 VICKI DRN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.3248 | -121.1439 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.1 | 14.1 |  |  | 0 | 14.1 | 14.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001724 | RELW OH PRI JPOL RESD REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-01 |  | COMP | 2020-09-01 | [16 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 6094.89 | 90.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117211474 | POLE_DECA_REPL - #1S 22935 PLEASANT VALL | 35163743 |  |  | STS-POLE_DECA_REPL - #1S 22935 PLEASANT | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.3275 | -121.1445 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 90730 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.6 | 33.6 |  |  | 0 | 33.6 | 33.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001730 | RELW OH PRI JPOL PUBL RESD BTKA FLAG ESTR GO USA FMOB TER2 PRTO | Pole | 2020-08-26 |  | COMP | 2020-08-26 | [16 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 19916.18 | 226.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117216517 | POLE_DECA_REPL - #2N ON LINE @ #1W 23548 | 35163806 |  |  | STS-POLE_DECA_REPL - #2N ON LINE @ #1W 2 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.3365 | -121.1396 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 90730 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100107480 | RELW OH PRI REMT NOAC ESTR GO REAR USA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117216536 | POLE_DECA_REPL - 23155 PLEASANT VALLEY R | 35163562 |  |  | STS-POLE_DECA_REPL - 23155 PLEASANT VALL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.3321 | -121.1416 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 62 | 62 |  |  | 0 | 62 | 62 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001692 | RELW OH PRI RESD REMT FLAG ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-09-02 |  | COMP | 2020-09-02 |  |  | 2020-06-11 | [13 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 12256.01 | 90.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117216538 | POLE_DECA_REPL - #1 ON LINE N/O 23550 PL | 35163566 |  |  | STS-POLE_DECA_REPL - #1 ON LINE N/O 2355 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.3357 | -121.1374 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100107483 | RELW OH SEC RESD REMT ESTR BTKA USA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117250261 | POLE_DECA_REPL - #1W #5S CO#6081 @ #1E R | 35163682 |  |  | STS-POLE_DECA_REPL - #1W #5S CO#6081 @ # | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.3393 | -121.1277 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100107490 | RELW OH PRI JPOL REMT ESTR GO FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117346238 | POLE_BROK_REPL - #1 ON LINE N/O 16296 PL | 35163712 |  |  | STS-POLE_BROK_REPL - #1 ON LINE N/O 1629 | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 39.3399 | -121.1239 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K0714 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 18.4 | 18.4 |  |  | 0 | 18.4 | 18.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100001915 | RELW OH PRI CLR JPOL RESD REMT NOAC ESTR REAR PROG FMOB TER2 PRTO | Pole | 2020-11-12 | 2020-11-10 | COMP | 2020-09-15 | [16 empty] | 2019-05-30 | 2020-05-30 |  | 2020-05-30 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 20185.25 | 1923.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117610876 | POLE_BROK_REPL - R/O 12212 VICKI DR W/TN | 35163758 |  |  | STS-POLE_BROK_REPL - R/O 12212 VICKI DR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land JointPole |  |  | 39.3267 | -121.1449 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 90730 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50.7 | 49.4 | 1.3 |  | 0 | 50.7 | 49.4 | 1.3 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100001895 | RELW OH PRI INSP CLR REMT FIRE ESTR BTKA FMOB TER2 | Pole | 2021-01-08 | 2021-01-08 | COMP | 2020-08-20 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-07-17 | 2020-07-17 |  | 2020-07-17 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 22501.57 | 135.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | COMP | 117211461 | POLE_DECA_REPL - 22822 PLEASANT VALLEY R | 35163733 |  |  | STS-POLE_DECA_REPL - 22822 PLEASANT VALL | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2021-12-30 | No Action | 39.3278 | -121.1448 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  | 2021-02-12 07:00 | 2021-02-12 16:00 | Completed | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001729 | RELW OH SEC COMP JPOL PUBL RESD FLAG ESTR BTKA USA CCNT FMOB TER2 PRTO | Pole | 2020-11-30 | 2020-12-02 | COMP | 2020-09-01 | COMP | 2021-02-12 | 2021-02-08 | 2021-02-09 | [11 empty] | 2021-02-22 | 2021-02-12 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 8202.23 | 2977.7 | 1333.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | COMP | 117216529 | POLE_DECA_REPL - R/O 23381 PLEASANT VALL | 35163549 |  |  | STS-POLE_DECA_REPL - R/O 23381 PLEASANT | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.3341 | -121.1389 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  | 2021-02-06 | 2021-02-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001698 | RELW OH SEC COMP JPOL REMT NOAC ESTR REAR USA CCNT FMOB TER2 PRTO | Pole | 2020-09-03 | 2020-10-26 | COMP | 2020-09-03 | COMP | 2021-02-06 | [13 empty] | 2021-02-16 | 2021-02-06 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 5475.06 | 3530.9 | 2859 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | COMP | 117216535 | POLE_DECA_REPL - 23927 PLEASANT VALLEY R | 35163558 |  |  | STS-POLE_DECA_REPL - 23927 PLEASANT VALL | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2021-12-30 | No Action | 39.3407 | -121.1319 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | [6 empty] | 51.6 | 51.6 |  |  | 0 | 51.6 | 51.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001710 | RELW OH PRI COMP RESD REMT FLAG ESTR BTKA USA CCNT FMOB TER2 PRTO | Pole | 2020-08-31 | 2020-10-22 | COMP | 2020-08-26 | COMP | 2021-02-12 | 2021-02-01 | 2021-02-03 | [11 empty] | 2021-02-22 | 2021-02-12 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 9786.27 | 3053.8 | 2814.3 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117184072 | POLE_BROK_REPL - A/F 21266 PLEASANT VALL | 35163596 |  |  | STS-POLE_BROK_REPL - A/F 21266 PLEASANT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3078 | -121.1519 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | L06 | 90730 | Y | 311 |  |  | 2021-12-31 07:00 | 2021-12-31 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100003737 | RELW OH PRI JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-03 | 2020-09-03 | COMP | 2020-09-03 |  |  | 2020-07-16 | 2020-07-16 | [12 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 18460.84 | 258.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117184157 | POLE_BROK_REPL - 21581 PLEASANT VALLEY R | 35163598 |  |  | STS-POLE_BROK_REPL - 21581 PLEASANT VALL | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-11-30 | Renew Permit | 39.3127 | -121.1531 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | L06 |  | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100003727 | RELW OH PRI CLR JPOL REMT ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-09-01 | 2020-10-21 | COMP | 2020-09-01 |  |  | 2021-02-08 | 2021-02-08 | [12 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 17117.45 | 2653.3 | -1844.8 | -2526.3 | -2526.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117190114 | POLE_BROK_REPL - 21045 PLEASANT VALLEY R | 35163657 |  |  | STS-POLE_BROK_REPL - 21045 PLEASANT VALL | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.303 | -121.1564 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | L06 |  | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100003717 | RELW OH SERV BTKA JPOL REMT ESTR FMOB TER2 PRTO | Pole | 2020-09-09 | 2020-11-17 | COMP | 2020-09-09 | [16 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 6085.33 | 150.8 | -1385 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117194746 | POLE_DECA_REPL - AT 21266 PLEASANT VALLE | 35163677 |  |  | STS-POLE_DECA_REPL - AT 21266 PLEASANT V | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3067 | -121.1542 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | L06 | 8865 | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 41.4 | 41 |  | 0.4 | 0 | 41.4 | 41 |  | 0.4 | EC | E | Pole | Decayed/Rotten | Replace |  | 100003740 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-02 | 2020-10-23 | COMP | 2020-09-02 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 18097.36 | 2348.3 | 691.6 | -96.4 | -96.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117196220 | POLE_DECA_REPL - 12333 BIRCHVILLE RDNORT | 35163687 |  |  | STS-POLE_DECA_REPL - 12333 BIRCHVILLE RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3191 | -121.1495 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 90730 | Y | 311 |  |  | 2021-03-29 07:00 | 2021-03-29 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 36.8 | 36.8 |  |  | 0 | 36.8 | 36.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001879 | RELW OH PRI JPOL REMT NOAC ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-10-09 | 2020-11-22 | COMP | 2020-09-29 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 14764.18 | 1233.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117196221 | POLE_DECA_REPL - #1N 22551 PLEASANT VALL | 35163689 |  |  | STS-POLE_DECA_REPL - #1N 22551 PLEASANT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-30 | Renew Permit | 39.325 | -121.1476 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 90730 | Y | 311 |  |  | 2021-03-11 07:00 | 2021-03-11 16:00 | Scheduled | CLICK | [6 empty] | 43.5 | 43.5 |  |  | 0 | 43.5 | 43.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001892 | RELW OH PRI PUBL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-11-18 | 2020-11-18 | COMP | 2020-11-18 |  |  | 2020-05-29 | 2020-06-01 | [12 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 22879.58 | 4945.8 | 2309.9 | 449.6 | 449.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117196228 | POLE_DECA_REPL - #1S 22551 PLEASANT VALL | 35163691 |  |  | STS-POLE_DECA_REPL - #1S 22551 PLEASANT | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-12-30 | No Action | 39.3244 | -121.1487 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  | 2021-03-12 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001888 | PRI RELW OH PUBL REMT FLAG ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-10-08 | 2020-10-08 | COMP | 2020-10-08 |  |  | 2021-02-01 | 2021-02-03 | [12 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 10713.56 | 2523.2 | 788.6 | 213.5 | 213.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117211456 | POLE_DECA_REPL - 12101 VICKI DR NORTH SA | 35163731 |  |  | STS-POLE_DECA_REPL - 12101 VICKI DR NORT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3245 | -121.1432 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  | 2021-03-11 07:00 | 2021-03-11 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001725 | RELW OH PRI JPOL RESD REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-01 | 2020-10-23 | COMP | 2020-09-01 | [16 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 10252.67 | 1991.8 | 1837 | 1003.1 | 1003.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117211464 | POLE_DECA_REPL - #1S 12101 VICKI DRNORTH | 35163737 |  |  | STS-POLE_DECA_REPL - #1S 12101 VICKI DRN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3234 | -121.1439 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 90730 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 54.1 | 54.1 |  |  | 0 | 54.1 | 54.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001726 | RELW OH PRI JPOL RESD REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-11 | 2020-11-04 | COMP | 2020-09-11 | [16 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 19899.37 | 181 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117211471 | POLE_DECA_REPL - 11888 VICKI DR NORTH SA | 35163741 |  |  | STS-POLE_DECA_REPL - 11888 VICKI DRNORTH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3267 | -121.1397 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 30477 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.5 | 31.5 |  |  | 0 | 31.5 | 31.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001903 | OH RELW PRI JPOL RESD REMT ESTR BTKA PRTO USA FMOB TER2 | Pole | 2020-08-20 | 2021-01-08 | COMP | 2020-08-20 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 20745.96 | 381.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117211476 | POLE_DECA_REPL - #1W 22752 PLEASANT VALL | 35163745 |  |  | STS-POLE_DECA_REPL - #1W 22752 PLEASANT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3268 | -121.1465 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  | 2021-03-24 07:00 | 2021-03-24 16:00 | Scheduled | CLICK | [6 empty] | 51.8 | 51.8 |  |  | 10 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001864 | RELW OH PRI JPOL RESD REMT ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-08-25 | 2020-10-14 | COMP | 2020-08-25 | [16 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 18584.34 | 5223.5 | 2884.9 | 1003.1 | 1003.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117211479 | POLE_DECA_REPL - C/O VICKI DR/PLEASANT V | 35163747 |  |  | STS-POLE_DECA_REPL - C/O VICKI DR/PLEASA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-11-30 | Renew Permit | 39.3254 | -121.1472 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001718 | RELW OH PRI JPOL RESD REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-08-25 | 2020-10-14 | COMP | 2020-08-25 |  |  | 2020-05-07 | 2020-05-13 | [12 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 7402.99 | 4660.8 | 4113.4 | 1290.5 | 1290.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117211484 | POLE_DECA_REPL - 22935 PKEASANT VALLEY R | 35163749 |  |  | STS-POLE_DECA_REPL - 22935 PKEASANT VALL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-11-01 | Renew Permit | 39.3279 | -121.1438 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 90730 | Y | 311 |  |  | 2021-03-23 07:00 | 2021-03-23 16:00 | Scheduled | CLICK | [6 empty] | 43.3 | 42.7 | 0.2 | 0.4 | 0 | 43.3 | 42.7 | 0.2 | 0.4 | EC | E | Pole | Decayed/Rotten | Replace |  | 100001732 | RELW OH PRI PUBL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-08-24 | 2020-10-21 | COMP | 2020-08-24 |  |  | 2020-04-29 | 2020-04-30 | [12 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 20368.88 | 2441 | 2081.9 | 1003.1 | 1003.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117216516 | POLE_DECA_REPL - #1NE 23700 PLEASANT VAL | 35163805 |  |  | STS-POLE_DECA_REPL - #1NE 23700 PLEASANT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-11-01 | Renew Permit | 39.3386 | -121.1336 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  | 2021-03-23 07:00 | 2021-03-23 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001706 | RELW OH PRI REMT FLAG ESTR TER2 BTKA USA FMOB PRTO | Pole | 2020-08-20 | 2020-08-20 | COMP | 2020-08-20 |  |  | 2020-04-29 | 2020-04-30 | [12 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 10072.61 | 2088.6 | 1109.1 | 732.1 | 732.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117216522 | POLE_DECA_REPL - #1W 23548 PLEASANT VALL | 35163807 |  |  | STS-POLE_DECA_REPL - #1W 23548 PLEASANT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3348 | -121.1383 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  | 2021-04-06 07:00 | 2021-04-06 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001700 | RELW OH PRI REMT ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-08-22 | 2020-11-24 | COMP | 2020-08-20 | [16 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 8101.07 | 362 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117216523 | POLE_DECA_REPL - #2 ON LINE E/O 23155 PL | 35163808 |  |  | STS-POLE_DECA_REPL - #2 ON LINE E/O 2315 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3321 | -121.1409 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 90730 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 35.4 | 35.4 |  |  | 0 | 35.4 | 35.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001741 | RELW PRI OH JPOL RESD REMT NOAC ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-08-26 | 2020-10-20 | COMP | 2020-08-25 | [16 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 15583.77 | 362 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117216527 | POLE_DECA_REPL - 23746 PLEASANT VALLEY R | 35163809 |  |  | STS-POLE_DECA_REPL - 23746 PLEASANT VALL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3393 | -121.1331 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 90730 | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-04 16:00 | Scheduled | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001707 | RELW OH PRI RESD REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-08-27 | 2020-08-27 | COMP | 2020-08-27 | [16 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 12901.09 | 407.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117216531 | POLE_DECA_REPL - 23837 PLEASANT VALLEY R | 35163551 |  |  | STS-POLE_DECA_REPL - 23837 PLEASANT VALL | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3398 | -121.1321 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 90730 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001708 | RELW OH PRI RESD REMT ESTR BTKA PRTO USA FMOB TER2 | Pole | 2020-08-24 | 2020-10-15 | COMP | 2020-08-24 | [16 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 17612.92 | 45.4 | -1385 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117216532 | POLE_DECA_REPL - 23254 PLEASANT VALLEY R | 35163553 |  |  | STS-POLE_DECA_REPL - 23254 PLEASANT VALL | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2021-12-30 | No Action | 39.3334 | -121.141 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001694 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-08-20 | 2020-11-09 | COMP | 2020-08-17 |  |  | 2021-02-10 | 2021-02-10 | [12 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 12049.53 | 1291.4 | 666.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117216533 | POLE_DECA_REPL - 23033 PLEASANT VALLEY R | 35163555 |  |  | STS-POLE_DECA_REPL - 23033 PLEASANT VALL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-11-30 | Renew Permit | 39.3301 | -121.1424 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 90730 | Y | 311 |  |  | 2021-04-06 07:00 | 2021-04-06 16:00 | Scheduled | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001738 | RELW OH PRI JPOL PUBL FLAG ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-08-26 | 2020-11-02 | COMP | 2020-08-26 |  |  | 2020-05-04 | 2020-05-07 | [12 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 21307.53 | 579.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117216534 | POLE_DECA_REPL - #2NW ON LINE A/F 23381 | 35163557 |  |  | STS-POLE_DECA_REPL - #2NW ON LINE A/F 23 | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3345 | -121.1392 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 90730 | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001697 | RELW OH PRI JPOL REMT ESTR GO BTKA RTRN USA FMOB TER2 PRTO | Pole | 2020-09-04 | 2020-11-02 | COMP | 2020-09-03 |  |  |  | 2021-02-17 | [12 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 12855.09 | 1109.6 | 883.3 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117227526 | POLE_DECA_REPL - 16296 PLEASANT VALLEY R | 35163629 |  |  | STS-POLE_DECA_REPL - 16296 PLEASANT VALL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3393 | -121.1239 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K0714 | 30597 | Y | 311 |  |  | 2021-04-06 07:00 | 2021-04-06 16:00 | Scheduled | CLICK | [6 empty] | 41.6 | 41 | 0.6 |  | 0 | 41.6 | 41 | 0.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001916 | RELW OH PRI JPOL REMT ESTR BTKA USA PRTO FMOB TER2 | Pole | 2020-08-20 | 2020-11-16 | COMP | 2020-08-20 | [16 empty] | 2019-05-13 | 2020-05-13 |  | 2020-05-13 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 22847.04 | 1459.7 | -61.1 | -61.1 | -61.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117227553 | POLE_DECA_REPL - #4 ON LINE N/O 16296 PL | 35163631 |  |  | STS-POLE_DECA_REPL - #4 ON LINE N/O 1629 | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 39.3413 | -121.1244 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K0714 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 69.8 | 69.8 |  |  | 0 | 69.8 | 69.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001912 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-08-14 | 2020-10-14 | COMP | 2020-08-14 | [16 empty] | 2019-05-13 | 2020-05-13 |  | 2020-05-13 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 12612.69 | 704.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117227555 | POLE_DECA_REPL - #5 ON LINE N/O 16296 PL | 35163633 |  |  | STS-POLE_DECA_REPL - #5 ON LINE N/O 1629 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3418 | -121.1244 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K0714 |  | Y | 311 |  |  | 2021-03-24 07:00 | 2021-03-24 16:00 | Scheduled | CLICK | [6 empty] | 57 | 57 |  |  | 0 | 57 | 57 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001911 | RELW OH PRI JPOL REMT ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-08-19 | 2020-10-29 | COMP | 2020-08-19 | [16 empty] | 2019-05-13 | 2020-05-13 |  | 2020-05-13 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 6201.19 | 1084.1 | 948.2 | 765 | 765 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117243456 | POLE_BROK_REPL - R/O 25706 HWY 49 W/T NO | 35163674 |  |  | STS-POLE_BROK_REPL - R/O 25706 HWY 49 W/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3383 | -121.1184 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K0714 | 1529 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 30.2 | 30.2 |  |  | 0 | 30.2 | 30.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100104947 | OH PRI CLR REMT ESTR FMOB TER2 PRTO RELW | Pole | 2020-08-21 | 2020-08-21 | COMP | 2020-08-21 | [16 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 18024.94 | 1165.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117250263 | POLE_DECA_REPL - #2 ON LINE W/O 16000 PL | 35163684 |  |  | STS-POLE_DECA_REPL - #2 ON LINE W/O 1600 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3386 | -121.1268 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.1 | 28.1 |  |  | 0 | 28.1 | 28.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100112312 | RELW OH REMT PRI CLR JPOL ESTR FMOB TER2 PRTO | Pole | 2020-09-01 | 2020-10-16 | COMP | 2020-08-26 | [16 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 13196.77 | 13.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117250271 | POLE_BROK_REPL - #2W #5S CO#6081 @ #1E R | 35163686 |  |  | STS-POLE_BROK_REPL - #2W #5S CO#6081 @ # | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3393 | -121.1285 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 6081 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 34.9 | 34.9 |  |  | 0 | 34.9 | 34.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100112449 | RELW OH PRI CLR JPOL REMT ESTR FMOB TER2 PRTO | Pole | 2020-08-14 | 2020-10-21 | COMP | 2020-08-14 | [16 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 16347.49 | 181 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117250273 | POLE_DECA_REPL - #5S CO#6081 @ #1E R/O 2 | 35163690 |  |  | STS-POLE_DECA_REPL - #5S CO#6081 @ #1E R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3394 | -121.1269 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 6081 | Y | 311 |  |  | 2021-04-06 07:00 | 2021-04-06 16:00 | Scheduled | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100107489 | RELW OH PRI JPOL REMT ESTR FMOB TER2 PRTO | Pole | 2020-09-03 | 2020-10-21 | COMP | 2020-09-01 | [16 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 21465.23 | 374.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117267552 | POLE_DECA_REPL - #2E R/O 24223 PLEASANT | 35163692 |  |  | STS-POLE_DECA_REPL - #2E R/O 24223 PLEAS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.3422 | -121.1252 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K0714 |  | Y | 311 |  |  | 2021-04-06 07:00 | 2021-04-06 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100104954 | RELW OH PRI JPOL REMT NOAC ESTR REAR USA FMOB TER2 PRTO | Pole | 2020-09-10 | 2020-10-29 | COMP | 2020-09-09 | [16 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 13121.22 | 237.6 | -1385 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117267553 | POLE_DECA_REPL - #1E R/O 24223 PLEASANT | 35163694 |  |  | STS-POLE_DECA_REPL - #1E R/O 24223 PLEAS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.342 | -121.126 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 | 90730 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 21.2 | 21.2 |  |  | 0 | 21.2 | 21.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100001715 | RELW OH PRI JPOL REMT ESTR GO BTKA USA FMOB TER2 PRTO | Pole | 2020-08-19 | 2020-10-11 | COMP | 2020-08-19 | [16 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 10945.8 | 241.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117588587 | POLE_BROK_REPL - #1N 23927 PLEASANT VALL | 35163779 |  |  | STS-POLE_BROK_REPL - #1N 23927 PLEASANT | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 39.3411 | -121.131 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | K07 |  | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100001711 | RELW OH PRI INSP REMT FIRE JAR FLAG BTKA FMOB TER2 | Pole | 2020-11-30 | 2020-12-01 | COMP | 2020-09-25 |  |  | 2020-11-30 | 2020-12-01 | [12 empty] | 2019-07-11 | 2020-07-11 |  | 2020-07-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 10905.69 | 2410.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | NORTH SAN JUAN | Grass Valley |  |  | OPEN | 117733719 | POLE_DECA_REPL - #1E CRESCENT ST ON MAIN | 35163766 |  |  | STS-POLE_DECA_REPL - #1E CRESCENT ST ON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-11-30 | Renew Permit | 39.3077 | -121.1654 |  | TIER 2 | 121 | 15247-1101, COLUMBIA HILL | L0604 | 8865 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13 | 13 |  |  | 0 | 13 | 13 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100004412 | RELW OH PRI INSP CLR JPOL RESD TRAF ESTR BTKA USA FMOB TER2 | Pole | 2020-10-06 | 2020-10-13 | COMP | 2020-08-20 |  |  | 2020-05-07 | 2020-05-13 | [12 empty] | 2019-08-09 | 2020-03-01 |  | 2020-03-01 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152471101 | 8265.43 | 624.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116721083 | POLE_BROK_REPL - AF 10149 PARK VIEW LNPE | 35187640 |  |  | STS-POLE_BROK_REPL - AF 10149 PARK VIEW | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 39.1997 | -121.2414 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0419 | 5257 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 47.2 | 47.2 |  |  | 0 | 47.2 | 47.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100010595 | RELW OH PRI CLR RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-08 |  | COMP | 2020-10-08 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-03-13 | 2020-03-13 |  | 2020-03-13 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 21510.55 | 1297.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116748380 | POLE_DECA_REPL - 2/N/O 1/A/F 19504 TARA | 35187746 |  |  | STS-POLE_DECA_REPL - 2/N/O 1/A/F 19504 T | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2041 | -121.215 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0513 | 4643 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.5 | 40.5 |  |  | 0 | 40.5 | 40.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100010304 | RELW OH PRI CLR ESTR FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-12-11 | COMP | 2020-10-15 | [16 empty] | 2019-03-16 | 2020-03-16 |  | 2020-03-16 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 16055.58 | 1335.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116749418 | POLE_DECA_REPL - 20975 HWY 20PENN VALLEY | 35187787 |  |  | STS-POLE_DECA_REPL - 20975 HWY 20PENN VA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 39.2071 | -121.2387 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0415 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.8 | 29.8 |  |  | 0 | 29.8 | 29.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100011543 | RELW OH PRI CLR PUBL FIRE ESTR BTKA PRTO FMOB TER2 | Pole | 2020-09-24 |  | COMP | 2020-09-24 |  |  | 2021-02-03 | 2021-02-03 | [12 empty] | 2019-03-16 | 2020-03-16 |  | 2020-03-16 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 17294.13 | 2286.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116791018 | POLE_BROK_REPL - 10200 MEADOW SPRINGS LN | 35188028 |  |  | STS-POLE_BROK_REPL - 10200 MEADOW SPRING | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 39.1965 | -121.2175 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0517 | 4331 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38 | 38 |  |  | 0 | 38 | 38 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100076363 | RELW OH PRI CLR ESTR BTKA FMOB TER2 PRTO | Pole | 2020-11-12 | 2020-11-10 | COMP | 2020-09-18 | [16 empty] | 2019-03-20 | 2020-03-20 |  | 2020-03-20 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 16431.78 | 2225.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116806366 | POLE_BROK_REPL - INDIAN SPRINGS RD PENN | 35188101 |  |  | STS-POLE_BROK_REPL - INDIAN SPRINGS RD P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1838 | -121.1991 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0525 | 3487 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.5 | 20.5 |  |  | 0 | 20.5 | 20.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100088521 | RELW OH PRI CLR JPOL PUBL FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-09 | 2021-02-18 | COMP | 2020-10-09 |  |  | 2021-02-18 | 2021-02-18 | [12 empty] | 2019-03-21 | 2020-03-21 |  | 2020-03-21 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 17004.49 | 1996.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116812287 | POLE_DECA_REPL - 2NE/O OAK CANYON DR PEN | 35188150 |  |  | STS-POLE_DECA_REPL - 2NE/O OAK CANYON DR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.1998 | -121.2257 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0516 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.9 | 26.9 |  |  | 0 | 26.9 | 26.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100069089 | RELW OH PRI CLR ESTR GO FMOB TER2 PRTO | Pole | 2020-10-14 |  | COMP | 2020-10-14 | [16 empty] | 2019-03-22 | 2020-03-22 |  | 2020-03-22 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 13123.17 | 1491 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116877023 | POLE_BROK_REPL - A/F 11247 SPENCEVILLE R | 35188641 |  |  | STS-POLE_BROK_REPL - A/F 11247 SPENCEVIL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.1871 | -121.1863 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0621 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100088818 | RELW OH PRI CLR RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-10-08 |  | COMP | 2020-10-08 | [16 empty] | 2019-03-31 | 2020-03-31 | 2024-03-29 | 2024-03-29 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 17568.96 | 1868 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116985505 | POLE_DECA_REPL - 2SE/0 15341 INDIAN CT P | 35187809 |  |  | STS-POLE_DECA_REPL - 2SE/0 15341 INDIAN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.1445 | -121.1902 |  | TIER 2 | 109 | 15313-2105, NARROWS | O06 | 4201 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 60.2 | 60.2 |  |  | 0 | 60.2 | 60.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100097280 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-14 | 2020-12-29 | COMP | 2020-10-29 | [16 empty] | 2019-04-09 | 2020-04-09 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 27055.62 | 2137.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 117002256 | POLE_DECA_REPL - R/O 16614 INDIAN SPRING | 35214830 |  |  | STS-POLE_DECA_REPL - R/O 16614 INDIAN SP | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.1747 | -121.1788 |  | TIER 2 | 109 | 15313-2105, NARROWS | O06 | 7203 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103028457 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-10 | 2020-04-10 | 2021-04-29 | 2021-04-29 | 2021 CBP Plan | 2021-03-31 | EEI |  | 153132105 | 1 | 97.2 | 97.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 117788027 | POLE_BROK_REPL - 13058 MOONEY FLATS RDPE | 35201820 |  |  | STS-POLE_BROK_REPL - 13058 MOONEY FLATS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2351 | -121.2475 |  | TIER 2 | 154 | 15313-2102, NARROWS | M0424 | 5277 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.8 | 42.8 |  |  | 0 | 42.8 | 42.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100000097 | RELW OH PRI INSP CLR REMT FMOB FIRE ESTR GO BTKA TER2 | Pole | 2020-10-13 | 2020-11-25 | COMP | 2020-10-13 | [16 empty] | 2019-08-22 | 2020-08-22 |  | 2020-08-22 | Per DOT Approved Request 20340 |  | Auburn |  | 153132102 | 17695.2 | 209.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-12-16
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 117788033 | POLE_BROK_REPL - 1/S 13058 MOONEYFLATS R | 35201858 |  |  | STS-POLE_BROK_REPL - 1/S 13058 MOONEYFLA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2348 | -121.2478 |  | TIER 2 | 109 | 15313-2105, NARROWS | M0424 | 5277 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43.7 | 43.7 |  |  | 0 | 43.7 | 43.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100000096 | RELW OH PRI INSP CLR REMT FIRE ESTR GO BTKA FMOB TER2 | Pole | 2020-10-13 | 2020-10-13 | COMP | 2020-10-13 | [16 empty] | 2019-08-22 | 2020-08-22 |  | 2020-08-22 | Per DOT Approved Request 20341 |  | Auburn |  | 153132105 | 17543.05 | 125.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-12-16
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116723425 | POLE_BROK_REPL - 11124 BLACKLEDGE RD. PE | 35187646 |  |  | STS-POLE_BROK_REPL - 11124 BLACKLEDGE RD | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 39.2176 | -121.2052 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0509 | 4357 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.9 | 39.9 |  |  | 0 | 39.9 | 39.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100011049 | OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP RELW | Pole | 2020-10-02 | 2021-01-08 | COMP | 2020-10-02 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-03-13 | 2020-03-13 | 2024-03-11 | 2024-03-11 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 24649.73 | 2192.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116735648 | POLE_BROK_REPL - 19289 LOS ROBLESPENN VA | 35187683 |  |  | STS-POLE_BROK_REPL - 19289 LOS ROBLESPEN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2178 | -121.2095 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0508 | 4357 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.6 | 28.6 |  |  | 0 | 28.6 | 28.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100011619 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-12-01 | COMP | 2020-10-12 | [16 empty] | 2019-03-14 | 2020-03-14 |  | 2020-03-14 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 12110.39 | 1045 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116748406 | POLE_BROK_REPL - 1/N/O 1/A/F 19504 TARA | 35187752 |  |  | STS-POLE_BROK_REPL - 1/N/O 1/A/F 19504 T | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2033 | -121.215 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0513 |  | Y | 311 |  |  | 2021-03-01 07:00 | 2021-03-01 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100010303 | RELW OH PRI CLR ESTR FMOB TER2 PRTO | Pole | 2020-10-07 | 2020-12-08 | COMP | 2020-10-07 | [16 empty] | 2019-03-16 | 2020-03-16 |  | 2020-03-16 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 7739.35 | 2610.5 | 1334.7 | 863 | 863 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116759438 | POLE_DECA_REPL - R/O 10499 PLEASANT VALL | 35187925 |  |  | STS-POLE_DECA_REPL - R/O 10499 PLEASANT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2119 | -121.201 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0509 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.6 | 16.6 |  |  | 0 | 16.6 | 16.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100107613 | RELW OH SERV JPOL REMT ESTR BTKA RTRN FMOB TER2 PRTO FSRP | Pole | 2020-09-24 | 2020-12-31 | COMP | 2020-09-24 | [16 empty] | 2019-03-18 | 2020-03-18 | 2024-03-16 | 2024-03-16 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 10235.95 | 1178.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116791024 | POLE_BROK_REPL - AF 10758 EAGLESHAM CT P | 35188035 |  |  | STS-POLE_BROK_REPL - AF 10758 EAGLESHAM | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1949 | -121.2036 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0519 | 7765 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 37.4 | 37.4 |  |  | 0 | 37.4 | 37.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100099263 | RELW OH PRI JPOL REMT TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-10-05 | 2021-01-08 | COMP | 2020-10-05 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-03-20 | 2020-03-20 | 2024-03-18 | 2024-03-18 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 20920.58 | 1596.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116803527 | POLE_DECA_REPL - 95946PENN VALLEY95946 | 35188064 |  |  | STS-POLE_DECA_REPL - 95946PENN VALLEY959 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.192 | -121.2192 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0517 | 31487 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.1 | 28.1 |  |  | 0 | 28.1 | 28.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103676247 | RELW OH PRI CLR ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-11 | 2021-01-12 | COMP | 2020-10-05 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-03-21 | 2020-03-21 |  | 2020-03-21 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 13845.62 | 1313.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116811274 | POLE_BROK_REPL - 13646 LUPINE CT. PENN V | 35188122 |  |  | STS-POLE_BROK_REPL - 13646 LUPINE CT. PE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1861 | -121.139 |  | TIER 2 | 109 | 15313-2105, NARROWS | N07 |  | Y | 311 |  |  | 2021-03-16 07:00 | 2021-03-16 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103680684 | RELW OH SERV ESTR FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-12-02 | COMP | 2020-10-12 | [16 empty] | 2019-03-22 | 2020-03-22 |  | 2020-03-22 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 10431.6 | 6399.8 | 4789.6 | 4304.3 | 4304.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116811978 | POLE_DECA_REPL - 2R/O 18401 INDIAN SPRIN | 35188144 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1875 | -121.2052 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0524 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 27.6 | 27.6 |  |  | 0 | 27.6 | 27.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100086551 | RELW OH PRI CLR REMT FIRE NOAC ESTR FMOB TER2 PRTO | Pole | 2020-10-02 | 2020-11-20 | COMP | 2020-10-02 | [16 empty] | 2019-03-22 | 2020-03-22 |  | 2020-03-22 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 10755.38 | 1054.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116825799 | POLE_DECA_REPL - ANGIE CT.PENN VALLEY959 | 35188320 |  |  | STS-POLE_DECA_REPL - ANGIE CT.PENN VALLE | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1912 | -121.1422 |  | TIER 2 | 109 | 15313-2105, NARROWS | N07 |  | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103680130 | RELW FMOB OH PRI ESTR TER2 PRTO | Pole | 2020-10-02 | 2020-10-02 | COMP | 2020-10-02 | [16 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 12866.99 | 1572.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116825807 | POLE_BROK_REPL - 11530 LONGVALLEY RD PEN | 35188325 |  |  | STS-POLE_BROK_REPL - 11530 LONGVALLEY RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1896 | -121.1435 |  | TIER 2 | 109 | 15313-2105, NARROWS | N07 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 20.4 | 20.4 |  |  | 0 | 20.4 | 20.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103674562 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-09-28 | 2020-09-28 | COMP | 2020-09-28 | [16 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 9396.89 | 27114.2 | 25646.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116826192 | POLE_DECA_REPL - 11441 LONG VALLEY RDPEN | 35188330 |  |  | STS-POLE_DECA_REPL - 11441 LONG VALLEY R | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1913 | -121.1459 |  | TIER 2 | 109 | 15313-2105, NARROWS | N07 | 9083 | Y | 311 |  |  | 2021-02-19 07:00 | 2021-02-19 16:00 | Completed | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103676056 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-09-17 | 2020-11-16 | COMP | 2020-09-17 | [16 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 19140.3 | 2947.4 | 914.7 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116826677 | POLE_BROK_REPL - 11380 LONG VALLEY RDPEN | 35188335 |  |  | STS-POLE_BROK_REPL - 11380 LONG VALLEY R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1894 | -121.147 |  | TIER 2 | 109 | 15313-2105, NARROWS | N07 | 7205 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43.9 | 42.9 | 1 |  | 0 | 43.9 | 42.9 | 1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 103676053 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-10-01 | 2020-11-24 | COMP | 2020-09-30 | [16 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 17167.53 | 1485.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116880491 | POLE_BROK_REPL - 11544 EL NORA DR PENN V | 35187571 |  |  | STS-POLE_BROK_REPL - 11544 EL NORA DR PE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1881 | -121.1895 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0621 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13 | 13 |  |  | 0 | 13 | 13 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100088837 | RELW OH PRI CLR RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-12 | 2021-01-20 | COMP | 2020-10-12 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-01 | 2020-04-01 | 2024-03-30 | 2024-03-30 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 6790.44 | 1303 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116954845 | POLE_BROK_REPL - 13243 SIMPLE JUSTICE RD | 35187860 |  |  | STS-POLE_BROK_REPL - 13243 SIMPLE JUSTIC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1688 | -121.1507 |  | TIER 2 | 109 | 15313-2105, NARROWS | O0706 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.5 | 18.5 |  |  | 0 | 18.5 | 18.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100012881 | RELW OH PRI CLR JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-05 | 2021-01-08 | COMP | 2020-10-05 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-04 | 2020-04-04 |  | 2020-04-04 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 8576.61 | 1277.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 116972887 | POLE_BROK_REPL - 1 S/O A/F 14906 MAIDU T | 35188495 |  |  | STS-POLE_BROK_REPL - 1 S/O A/F 14906 MAI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1558 | -121.1706 |  | TIER 2 | 109 | 15313-2105, NARROWS | O06 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.2 | 14.2 |  |  | 0 | 14.2 | 14.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103820704 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-09-18 | 2020-11-09 | COMP | 2020-09-18 | [16 empty] | 2019-04-07 | 2020-04-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 5876.56 | 1766.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 117001379 | POLE_DECA_REPL - 1SW/O 1S/O 14341 INDIAN | 35188020 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.163 | -121.1425 |  | TIER 2 | 109 | 15313-2105, NARROWS | O0712 | 8757 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-08 16:00 | Scheduled | CLICK | [6 empty] | 43.5 | 43.5 |  |  | 0 | 43.5 | 43.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100012918 | RELW OH PRI CLR JPOL REMT ESTR BTKA PROG FMOB TER2 PRTO | Pole | 2020-09-29 | 2020-11-25 | COMP | 2020-09-29 | [16 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 19358.33 | 1730.3 | 128.7 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | OPEN | 117001742 | POLE_BROK_REPL - 2N/O 14144 INDIAN SPRIN | 35188026 |  |  | STS-POLE_BROK_REPL - 2N/O 14144 INDIAN S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1655 | -121.1397 |  | TIER 2 | 109 | 15313-2105, NARROWS | O0707 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.8 | 16.8 |  |  | 0 | 16.8 | 16.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100012608 | RELW OH SEC JPOL RESD NOAC ESTR USA FMOB TER2 PRTO | Pole | 2021-01-08 | 2021-01-12 | COMP | 2020-10-12 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 8102.16 | 1291.5 | 413.5 | 413.5 | 413.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PENN VALLEY | Grass Valley |  |  | COMP | 119598325 | POLE_BROK_REPL - 16708 DEL MARY WAY PENN | 35192909 |  |  | B3 - STS-POLE_BROK_REPL - 16708 DEL MARY | FICL | FICL SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-10-02 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.2744 | -121.2102 |  | TIER 2 | 154 | 15313-2102, NARROWS | L05 | 32973 | Y | 311 |  |  | 2021-01-15 | 2021-01-15 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 26.9 | 26.9 |  |  | 84 | 0.9 | 0.9 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100003942 | RELW OH COMP ESTR CPGG TER2 | Pole | 2020-10-23 | 2020-11-10 | COMP | 2020-10-23 | COMP | 2021-01-15 | 2020-10-15 | 2020-10-15 | [11 empty] | 2021-01-15 | 2021-01-15 | 2020-10-30 |  | 2020-10-30 | B-tag addition 8/12/2020 |  | Auburn |  | 153132102 | 25306.45 | 33165.9 | 30590.7 | 21322 | 21322 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-08-18
North | SI | PENRYN | Auburn |  |  | OPEN | 117132355 | POLE_BROK_REPL - AT 7249 ALLEN LNPENRYN9 | 35215065 |  |  | STS-POLE_BROK_REPL - AT 7249 ALLEN LNPEN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.87 | -121.1677 |  | TIER 2 | 761 | 15256-1105, PENRYN | U0624 | 4077 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100105236 | RELW OH PRI INSP JPOL RESD REMT FIRE ESTR GO USA PROG FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-30 | 2021-04-09 | 2021-04-09 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152561105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PILOT HILL | Auburn |  |  | OPEN | 115189958 | POLE_DECA_REPL - 295 Pine Tree CirPilot | 35075486 |  |  | STS-POLE_DECA_REPL - 295 PINE TREE CIRPI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8533 | -121.0377 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | V0910 | 4065 | Y | 311 | [5 empty] | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 67.8 | 67.8 |  |  | 0 | 67.8 | 67.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100054615 | RELW OH PRI INSP JPOL RESD REMT FIRE ESTR BTKA USA TER2 FMOB | Pole | 2020-05-28 | 2020-05-28 | COMP | 2020-05-28 | [16 empty] | 2018-11-04 | 2019-11-04 |  | 2019-11-04 | 2021 CBP Plan | 2019-02-28 | Auburn |  | 152282101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PILOT HILL | Auburn |  |  | OPEN | 115416948 | POLE_BROK_REPL - 4771 SALMON FALLS RD PI | 35075490 |  |  | STS-POLE_BROK_REPL - 4771 SALMON FALLS R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8289 | -121.0136 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | V1023 | 9311 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 37.3 | 37.3 |  |  | 0 | 37.3 | 37.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100054664 | RELW OH PRI INSP JPOL REMT TRAF FLAG ESTR GO BTKA USA FMOB TER2 | Pole | 2020-03-27 | 2020-06-02 | COMP | 2020-03-27 |  |  | 2019-05-08 | 2019-05-08 | [12 empty] | 2018-11-28 | 2019-11-28 |  | 2019-11-28 | 2021 CBP Plan | 2019-02-28 | Auburn |  | 152282101 | 9652.79 | 41.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PILOT HILL | Auburn |  |  | OPEN | 115449340 | POLE_DECA_REPL - 5150 Meadow Croft LnPil | 35074274 |  |  | STS-POLE_DECA_REPL - 5150 MEADOW CROFT L | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8279 | -121.0046 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | V1024 | 7085 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 69.7 | 69.7 |  |  | 0 | 69.7 | 69.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100056624 | RELW OH PRI INSP CLR REMT CGI ESTR BTKA USA FMOB TER2 | Pole | 2020-04-22 | 2020-04-22 | COMP | 2020-04-22 | [16 empty] | 2018-12-05 | 2019-12-05 |  | 2019-12-05 | 2021 CBP Plan | 2019-03-06 | Bakersfield |  | 152282101 | 16036.32 | 410.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PILOT HILL | Auburn |  |  | OPEN | 115453216 | POLE_DECA_REPL - 5260 MEADOW CROFT LN PI | 35218785 |  |  | B3 - STS-POLE_DECA_REPL - 5260 MEADOW CR | CONS | CONS SRDY | Poles | MPP | Veg+CONST - OH | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8251 | -121.0019 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | V10 | 6395 | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 40.1 | 40.1 |  |  | 0 | 40.1 | 40.1 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100107506 | OH PRI INSP REMT BTKA FMOB TER2 RELW | Pole | 2020-12-21 | 2020-12-21 | COMP | 2020-12-21 | [16 empty] | 2018-12-06 | 2019-12-06 | 2020-09-22 | 2020-09-22 | B tag clean up 12/7/2020 |  | Auburn |  | 152282101 | 18526.07 | 1245.2 | 1245.2 | [5 empty] | Electric Distribution | N | Not Assigned 11/2 in MPP Import File | N | Tag in Closure Status | Y | 2020-12-07
North | SI | PILOT HILL | Auburn |  |  | OPEN | 117086791 | POLE_DECA_REPL - AT HOUSE 3941 ACORN LNP | 35149987 |  |  | STS-POLE_DECA_REPL - AT HOUSE 3941 ACORN | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8555 | -121.0273 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | V1006 | 4065 | Y | 311 |  |  | 2021-03-29 07:00 | 2021-03-29 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 2.5 | 40.8 | 40.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100055116 | RELW OH PRI JPOL REMT ESTR REAR PROG FMOB TER2 PRTO | Pole | 2020-04-17 | 2020-06-13 | COMP | 2020-04-17 | [16 empty] | 2019-04-23 | 2020-04-23 |  | 2020-04-23 | circuit based plan 2.14 | 2020-04-10 | PIKEENG |  | 152282101 | 17188.21 | 4467.3 | 394.7 | 394.7 | 394.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | PILOT HILL | Auburn |  |  | OPEN | 117160823 | POLE_BROK_REPL - 2N/O 2E/O 5201 MEADOW C | 35148989 |  |  | STS-TRAN_CORR_REPL - 2N/O 2E/O 5201 MEAD | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.828 | -121.0013 |  | TIER 2 | 69 | 15228-2101, MOUNTAIN QUARRIES | V10 | 6395 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0.5 | 40.5 | 40.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100100882 | RELW OH PRI JPOL REMT ESTR REAR PROG FMOB TER2 PRTO | Pole | 2020-04-16 | 2020-11-03 | COMP | 2020-04-16 | [16 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-04-10 | PIKEENG |  | 152282101 | 19382.61 | 156.1 | 156.1 | 156.1 | 156.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PILOT HILL | Auburn |  |  | OPEN | 120014944 | POLE_BROK_REPL - 14 S/O 7107 LIME QUARRY | 35213312 |  |  | B2 - STS-POLE_BROK_REPL - 14 S/O 7107 LI | CONS | CONS SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | S9 Prior to 11/2 Static File | 1 | 2020-12-23 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7804 | -121.0886 |  | TIER 2 | 429 | 15256-1103, PENRYN | W08 | 5285 | Y | 311 |  |  | 2021-02-19 07:00 | 2021-02-19 16:00 | Dispatched | CLICK | [6 empty] | 52.1 | 52.1 |  |  | 0 | 52.1 | 52.1 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100060308 | RELW OH ESTR TER2 | Pole | 2020-12-09 | 2020-12-09 | COMP | 2020-12-09 |  |  | 2021-01-28 | 2021-02-12 | [12 empty] | 2020-10-20 | 2021-01-20 |  | 2021-01-20 | B tag clean up 11/15/2020 |  | Auburn |  | 152561103 | 29813.86 | 8211 | 7631.9 | 3120.1 | 3120.1 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-11-15
North | SI | PLACERVILLE | Auburn |  |  | OPEN | 117180613 | POLE_DECA_REPL - G/P 1WO 8581 HWY 193PLA | 35142153 |  |  | STS-POLE_BROK_REPL - A/F 8581 HWY 193 PL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8315 | -120.8211 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1517 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 110.9 | 110.9 |  |  | 10 | 100.9 | 100.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100108917 | SEC RELW OH CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-05 | 2020-11-28 | COMP | 2020-10-03 | [16 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 43879.89 | 1045.9 | 652.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Auburn |  |  | OPEN | 117180644 | POLE_DECA_REPL - A/F 1WO 8581 HWY 193 PL | 35142153 |  |  | STS-POLE_BROK_REPL - A/F 8581 HWY 193 PL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8315 | -120.8205 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1517 | 30839 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100108916 | REGW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-05 | 2020-11-28 | COMP | 2020-10-03 | [16 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 43879.89 | 1045.9 | 652.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Auburn |  |  | OPEN | 117185888 | POLE_BROK_REPL - A/F 8581 HWY 193 PLACER | 35142153 |  |  | STS-POLE_BROK_REPL - A/F 8581 HWY 193 PL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8312 | -120.82 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | V1517 | 30839 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100108914 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-05 | 2020-11-28 | COMP | 2020-10-03 | [16 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 43879.89 | 1045.9 | 652.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Auburn |  |  | OPEN | 117655261 | POLE_BROK_REPL - 1NO 6393 GARDEN VALLEY | 35148077 |  |  | STS-POLE_BROK_REPL - 1NO 6393 GARDEN VAL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8194 | -120.8247 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | W1501 | 7522 | Y | 311 |  |  | 2021-04-07 07:00 | 2021-04-07 16:00 | Scheduled | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100062660 | RELW OH PRI INSP JPOL FIRE ESTR BTKA TER2 FMOB | Pole | 2020-08-08 | 2020-10-03 | COMP | 2020-08-08 | [16 empty] | 2019-07-29 | 2020-07-29 |  | 2020-07-29 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 24606.36 | 767.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116690915 | POLE_BROK_REPL - 2740 MOSQUITO RD, PVILL | 35081191 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD | 2020-05-11 | Renew Permit | 38.7376 | -120.7828 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H4222 | 77273 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 102.1 | 102.1 |  |  | 0 | 102.1 | 102.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101386223 | RELW OH PRI CLR JPOL ESTR GO FMOB PRTO TER2 | Pole | 2021-02-19 | 2021-02-18 | COMP | 2020-12-22 |  |  | 2021-02-19 | 2020-02-13 | [12 empty] | 2019-03-09 | 2019-09-09 |  | 2019-09-09 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 28526.76 | 2637.4 |  |  |  | 2489 |  | 2489 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116705695 | POLE_BROK_REPL - C/O 1386 CARSON RD PLAC | 35137203 |  |  | STS-POLE_BROK_REPL - C/O 1386 CARSON RD | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole | 2020-12-31 | Renew Permit | 38.7355 | -120.7836 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H4222 | 18381 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 25.9 | 25.9 |  |  | 0 | 25.9 | 25.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101386582 | RELW OH SERV CLR JPOL SPCR ESTR FMOB TER2 PRTO | Pole | 2021-01-11 |  | COMP | 2021-01-11 |  |  | 2020-06-17 | 2020-06-17 | [12 empty] | 2019-03-10 | 2020-03-10 |  | 2020-03-10 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 11787.66 | 838.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116747284 | POLE_DECA_REPL - 3048 MONTEREY RD PLACER | 35160205 |  |  | STS-POLE_DECA_REPL - 3048 MONTEREY RD PL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.7304 | -120.7594 |  | TIER 2 | 248 | 15366-1103, APPLE HILL | I4205 | 7225 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101415914 | RELW OH PRI ESTR FSRP PRTO FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-03-16 | 2020-03-16 | 2024-03-14 | 2024-03-14 | 2021 CBP Plan | 2020-10-31 | QUES |  | 153661103 | 1 | 2254.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116751412 | POLE_DECA_REPL - A\F 899 SPRING ST. PLAC | 35233972 |  |  | STS-POLE_DECA_REPL - A\F 899 SPRING ST. | UNSE | UNSE ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.7317 | -120.8032 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | I4104 | 22441 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101406502 | RELW RESD OH PRI JPOL BTKA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 |  | 2020-03-17 | Per DOT Approved Request 31434 |  | UNASSIGNED |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2021-01-28
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116751629 | POLE_DECA_REPL - 895 UNION ST. PLACERVIL | 35137205 |  |  | STS-POLE_DECA_REPL - 895 UNION ST. PLACE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole | 2021-07-01 |  | 38.7305 | -120.8004 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | I4105 | 1319 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 66.2 | 66.2 |  |  | 0 | 66.2 | 66.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101404683 | RELW OH PRI ESTR GO FMOB TER2 PRTO | Pole | 2021-01-11 |  | COMP | 2021-01-11 |  |  | 2021-01-25 | 2021-01-25 | [12 empty] | 2019-03-17 | 2020-03-17 |  | 2020-03-17 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 32438.55 | 518.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116754685 | POLE_BROK_REPL - 3230 CLARK ST. PLACERVI | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-04-17 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 38.7227 | -120.7976 |  | TIER 2 | 940 | 15308-1111, PLACERVILLE | I4110 | 13117 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101405758 | REGW OH PRI CLR ESTR FSRP PRTO FMOB TER2 | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-03-18 | 2020-03-18 | 2021-05-15 | 2021-05-15 | B tag clean up 2/19/2021 |  | UNASSIGNED |  | 153081111 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116807791 | POLE_DECA_REPL - 1P/A/F 4772 CHARPARRAL | 35188108 |  |  | STS-POLE_DECA_REPL - 1P/A/F 4772 CHARPAR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.695 | -120.7287 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I4324 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.1 | 17.1 |  |  | 0 | 17.1 | 17.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101396588 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-09-09 |  | COMP | 2020-09-09 | [16 empty] | 2019-03-21 | 2020-03-21 | 2024-03-19 | 2024-03-19 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 13207.01 | 85.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116827426 | POLE_DECA_REPL - 4561 PARK HILL DR PLACE | 35188366 |  |  | STS-POLE_DECA_REPL - 4561 PARK HILL DR P | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 38.6891 | -120.6469 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | I45 | 11427 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 43.2 | 43.2 |  |  | 0 | 43.2 | 43.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101408245 | RELW OH PRI PGEA CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-11 | 2021-01-08 | COMP | 2020-10-02 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116867130 | POLE_DECA_REPL - 1S/O 1756 MATTIE CT PLA | 35188559 |  |  | STS-POLE_DECA_REPL - 1S/O 1756 MATTIE CT | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.6745 | -120.8021 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | J41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.8 | 40.8 |  |  | 0 | 40.8 | 40.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101393093 | RELW OH PRI JPOL RESD REMT FIRE ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-02 |  | COMP | 2020-09-02 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-03-29 | 2020-03-29 |  | 2020-03-29 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 20268.85 | 85.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116875641 | POLE_BROK_REPL - 4661 GREENHILLS DR PLAC | 35160208 |  |  | STS-POLE_BROK_REPL - 4661 GREENHILLS DR | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.691 | -120.7319 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I43 | 10429 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101396501 | RELW OH PRI CLR RESD REMT RTRN ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-31 | 2020-03-31 |  | 2020-03-31 | 2021 CBP Plan | 2020-12-31 | QUES |  | 152261106 | 1 | 1360.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116880621 | POLE_DECA_REPL - 1P/A/F 4978 WOODLAND DR | 35187573 |  |  | STS-POLE_DECA_REPL - 1P/A/F 4978 WOODLAN | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 38.6908 | -120.7413 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I43 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.8 | 21.8 |  |  | 0 | 21.8 | 21.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101396930 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-11 | 2021-02-22 | COMP | 2020-09-29 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-01 | 2020-04-01 |  | 2020-04-01 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 11918.09 | 213.5 | 213.5 | 213.5 | 213.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116880865 | POLE_BROK_REPL - 4926 CEDAR RAVINE RD BY | 35187591 |  |  | STS-POLE_BROK_REPL - 4926 CEDAR RAVINE R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6882 | -120.7522 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I43 | 20383 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.2 | 32.9 | 1.3 |  | 0 | 34.2 | 32.9 | 1.3 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101397259 | RELW OH PRI CLR RESD REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2021-01-13 | 2021-02-19 | COMP | 2020-09-29 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-01 | 2020-04-01 |  | 2020-04-01 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116984538 | POLE_DECA_REPL - A/F 4732 DUSTY LN PLACE | 35160212 |  |  | STS-POLE_DECA_REPL - A/F 4732 DUSTY LN P | PEND | PEND ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.6767 | -120.7674 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | J4209 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.4 | 32.4 |  |  | 0 | 32.4 | 32.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101394159 | RELW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-12-18 |  | COMP | 2020-12-18 |  |  | 2021-02-18 | 2021-02-18 | [12 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | QUES |  | 152261106 | 17256.93 | 1827.6 | 102 | -687.8 | -687.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117004073 | POLE_BROK_REPL - 3740 SPRINGER RD PLACER | 35188065 |  |  | STS-POLE_BROK_REPL - 3740 SPRINGER RD PL | UNSC | UNSC ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 38.6726 | -120.6941 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J44 | 21289 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.6 | 37.6 |  |  | 0 | 37.6 | 37.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101416918 | RELW OH PRI CLR JPOL REMT FLAG ESTR GO BTKA PROG FMOB TER2 PRTO | Pole | 2020-09-21 | 2021-02-18 | COMP | 2020-09-21 |  |  | 2021-02-18 | 2021-02-18 | [12 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 18905.9 | 2048.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117008909 | POLE_DECA_REPL - A/F 1962 PLEASANT VALLE | 35188107 |  |  | STS-POLE_DECA_REPL - A/F 1962 PLEASANT V | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6775 | -120.7612 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | J4210 | 18027 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 205.4 | 204.8 | 0.6 |  | 0 | 205.4 | 204.8 | 0.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101415987 | OH PRI CLR RESD FIRE ESTR PROG FMOB TER2 PRTO RELW | Pole | 2020-09-14 | 2021-02-18 | COMP | 2020-09-14 |  |  | 2021-02-18 | 2021-02-18 | [12 empty] | 2019-04-11 | 2020-04-11 |  | 2020-04-11 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 237308.41 | 766.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117070757 | POLE_BROK_REPL - 1S/O 2828 POPLAR LN PLA | 35215426 |  |  | STS-POLE_BROK_REPL - 1S/O 2828 POPLAR LN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.7348 | -120.8239 |  | TIER 2 | 322 | 15308-1112, PLACERVILLE | H4122 | 21657 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101414391 | RELW OH PRI INSP CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2021-04-19 | 2021-04-19 | 2021 CBP Plan | 2021-03-31 | EEI |  | 153081112 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117072513 | POLE_BROK_REPL - 1900 COLD SPRINGS RD PL | 35215495 |  |  | STS-POLE_BROK_REPL - 1900 COLD SPRINGS R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.7403 | -120.8616 |  | TIER 2 | 273 | 15226-1103, DIAMOND SPRINGS | H4022 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101410696 | RELW OH PRI INSP CUST RESD REMT TRAF FLAG GO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152261103 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117093397 | POLE_DECA_REPL - 1W/O 2935 BEDFORD AVE P | 35137185 |  |  | STS-POLE_DECA_REPL - 1W/O 2935 BEDFORD A | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.7326 | -120.7994 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H4125 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101387101 | RELW OH SERV ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 333 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117093421 | POLE_BROK_REPL - 959 SPRING ST.PLACERVIL | 35137185 |  |  | STS-POLE_DECA_REPL - 1W/O 2935 BEDFORD A | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.7325 | -120.8008 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | I4105 | 22441 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101404695 | REGW OH PRI JPOL FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 333 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117093425 | POLE_BROK_REPL - 2914 BEDFORD AVEPLACERV | 35137185 |  |  | STS-POLE_DECA_REPL - 1W/O 2935 BEDFORD A | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.7335 | -120.7991 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H4125 | 1319 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101413254 | REGW OH PRI CLR JPOL FLAG ESTR GO BTKA USA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 333 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117121959 | POLE_BROK_REPL - 1PLS 6PLW 7265 BAYNE RD | 35137226 |  |  | STS-POLE_BROK_REPL - 1PLS 6PLW 7265 BAYN | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.805 | -120.8444 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 37.9 | 37.9 |  |  | 0 | 37.9 | 37.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101387816 | RELW OH PRI CLR JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-11 |  | COMP | 2021-01-11 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 19727.43 | 3550.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117129300 | POLE_BROK_REPL - 1P N/O 1P E/O 3221 YEAR | 35188395 |  |  | STS-POLE_BROK_REPL - 1P N/O 1P E/O 3221 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 38.6202 | -120.7686 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K42 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 10.3 | 10.3 |  |  | 0 | 10.3 | 10.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101386083 | RELW OH SEC CLR JPOL REMT ESTR REAR FMOB TER2 PRTO | Pole | 2020-12-02 | 2020-12-01 | COMP | 2020-10-09 |  |  | 2021-02-18 | 2021-02-18 | [12 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117131949 | POLE_BROK_REPL - #1W 2615 SANDRIDGE RDPL | 35188441 |  |  | STS-POLE_BROK_REPL - #1W 2615 SANDRIDGE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.6076 | -120.7795 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K42 | 13267 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.2 | 40.2 |  |  | 0 | 40.2 | 40.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101385858 | RELW OH PRI CLR JPOL REMT ESTR FMOB TER2 PRTO | Pole | 2020-10-06 |  | COMP | 2020-10-06 | [16 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117131965 | POLE_BROK_REPL - 1P E/O 2315 SANDRIDGE R | 35188451 |  |  | STS-POLE_BROK_REPL - 1P E/O 2315 SANDRID | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 38.605 | -120.7821 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K4222 | 13267 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 45.6 | 45.6 |  |  | 0 | 45.6 | 45.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101385827 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-13 | 2021-02-11 | COMP | 2020-10-13 | [16 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117143598 | POLE_DECA_REPL - 3450 SAND RIDGE RD. PLA | 35188635 |  |  | STS-POLE_DECA_REPL - 3450 SAND RIDGE RD. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.626 | -120.7447 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 | 12025 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 62.9 | 59.2 | 3.7 |  | 0 | 62.9 | 59.2 | 3.7 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101400494 | RELW OH PRI TRAF FLAG ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-09-10 | 2021-02-18 | COMP | 2020-09-10 |  |  | 2021-02-18 | 2021-02-18 | [12 empty] | 2019-05-02 | 2020-05-02 |  | 2020-05-02 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 27285.94 | 369 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117151539 | POLE_DECA_REPL - 1E/O 3771 STARBURST LN. | 35187718 |  |  | STS-POLE_DECA_REPL - 1E/O 3771 STARBURST | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 38.6204 | -120.7421 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.6 | 21.6 |  |  | 0 | 21.6 | 21.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101400634 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2021-01-11 | 2021-01-08 | COMP | 2020-09-28 |  |  | 2021-02-19 | 2021-02-19 | [12 empty] | 2019-05-03 | 2020-05-03 |  | 2020-05-03 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 13878.8 |  | 0 | 122.2 | 122.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117151553 | POLE_DECA_REPL - 1P W/O 4142 SANDRIDGE R | 35187724 |  |  | STS-POLE_DECA_REPL - 1P W/O 4142 SANDRID | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.633 | -120.7196 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 14.6 | 14.6 |  |  | 0 | 14.6 | 14.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101401196 | RELW OH PRI TRAF FLAG ESTR BTKA FMOB PRTO TER2 | Pole | 2020-09-11 | 2021-02-18 | COMP | 2020-09-11 |  |  | 2021-02-18 | 2021-02-18 | [12 empty] | 2019-05-03 | 2020-05-03 |  | 2020-05-03 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117210219 | POLE_BROK_REPL - 922 HILLCREST ST PLACER | 35137184 |  |  | STS-POLE_BROK_REPL - 922 HILLCREST ST PL | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.738 | -120.8074 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H4124 | 55525 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101386932 | RELW OH PRI JPOL REMT ESTR GO BTKA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-12-05 | 2019-12-05 | [12 empty] | 2019-05-10 | 2020-05-10 |  | 2020-05-10 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 3631.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117225604 | POLE_DECA_REPL - AT 9561 HWY 193 PLACERV | 35136902 |  |  | STS-POLE_DECA_REPL - AT 9561 HWY 193 PLA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.8021 | -120.8191 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G4112 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101383480 | RELW OH SEC JPOL RESD FIRE NOAC ESTR GO FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-13 | 2020-05-13 |  | 2020-05-13 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 772.4 |  |  |  | 355.5 |  | 355.5 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117225609 | POLE_BROK_REPL - 1WO 9461 HWY 193 (MOBIL | 35136903 |  |  | STS-POLE_BROK_REPL - 1WO 9461 HWY 193 (M | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8034 | -120.82 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G4112 | 20731 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 53.6 | 53.3 | 0.3 |  | 0 | 53.6 | 53.3 | 0.3 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101383485 | RELW OH PRI JPOL RESD FIRE NOAC ESTR PROG FMOB TER2 PRTO | Pole | 2021-01-11 |  | COMP | 2021-01-11 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-13 | 2020-05-13 |  | 2020-05-13 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117225610 | POLE_BROK_REPL - 9461 HWY 193 (MOBILE HO | 35136900 |  |  | STS-POLE_BROK_REPL - C/O RUNNING SPRING | ESTS | ESTS ERDY HOLD | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.8035 | -120.8191 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G4112 | 20731 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101413748 | JPOL REGW OH PRI RESD FIRE ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-13 | 2020-05-13 |  | 2020-05-13 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 2604.3 |  |  |  | 250.2 |  | 250.2 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117234037 | POLE_BROK_REPL - 4SE/O 5360 BASSI RDPLAC | 35160305 |  |  | STS-POLE_BROK_REPL - 4SE/O 5360 BASSI RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.7999 | -120.9157 |  | TIER 2 | 110 | 15365-2109, SHINGLE SPRINGS | G38 | 1239 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 71 | 71 |  |  | 0 | 71 | 71 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101388492 | RELW OH PRI CLR JPOL RESD REMT CGI ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-12-17 |  | COMP | 2020-12-17 |  |  | 2020-06-30 | 2020-06-30 | [12 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | QUES |  | 153652109 | 37746.88 | 1242.3 | 337.3 | -90.5 | -90.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117238719 | POLE_DECA_REPL - 6570 KELSEY CANYON RD P | 35137419 |  |  | STS-POLE_DECA_REPL - 6570 KELSEY CANYON | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.7862 | -120.8284 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 | 11313 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.1 | 41.1 |  |  | 0 | 41.1 | 41.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101383569 | RELW OH PRI CLR RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2021-01-05 |  | COMP | 2021-01-05 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117241247 | POLE_BROK_REPL - AT 6105 HWY 193 PLACERV | 35137361 |  |  | STS-POLE_BROK_REPL - AT 6105 HWY 193PLAC | APPR | APPR | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.8056 | -120.8222 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 | 1447 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101388061 | RELW OH PRI JPOL ESTR FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 9979.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117241248 | POLE_BROK_REPL - 1SE\O 6105 HWY 193 [IN | 35137362 |  |  | STS-POLE_BROK_REPL - 1SE\O 6105 HWY 193 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 38.8077 | -120.8264 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 21.4 | 21.4 |  |  | 0 | 21.4 | 21.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101388066 | PRI RELW OH PGEA RESD FIRE ESTR BTKA FMOB TER2 PRTO | Pole | 2020-12-29 | 2020-12-28 | COMP | 2020-12-28 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 9594.35 | 12185.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117241264 | POLE_BROK_REPL - 1NWO 6105 HWY 193PLACER | 35137363 |  |  | STS-POLE_BROK_REPL - 1NWO 6105 HWY 193PL | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.8055 | -120.8235 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 33 | 33 |  |  | 0 | 33 | 33 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101414547 | RELW OH PRI PGEA REMT FIRE NOAC ESTR FMOB TER2 PRTO | Pole | 2021-01-11 |  | COMP | 2021-01-11 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 14928.73 | 5952.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117249793 | POLE_BROK_REPL - 3N\O 9980 HWY 193 PLACE | 35137366 |  |  | STS-POLE_BROK_REPL - 3N\O 9980 HWY 193 P | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.792 | -120.8176 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101383653 | RELW OH PRI CLR RESD FIRE ESTR FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 5626.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117249828 | POLE_BROK_REPL - C/O KELSEY RD/BRIGHT HO | 35137425 |  |  | STS-POLE_BROK_REPL - C/O KELSEY RD/BRIGH | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.7938 | -120.819 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 | 10879 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101416112 | RELW OH PRI CLR RESD FIRE ESTR GO FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 5489.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117249844 | POLE_BROK_REPL - 6566 KELSEY RD PLACERVI | 35137373 |  |  | STS-POLE_BROK_REPL - 6566 KELSEY RD PLAC | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.7943 | -120.8192 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 | 10879 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101387618 | PRI RELW OH CLR RESD FIRE ESTR FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 243.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117249864 | POLE_BROK_REPL - 1N\O 6534 KELSEY RD PLA | 35137373 |  |  | STS-POLE_BROK_REPL - 6566 KELSEY RD PLAC | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.795 | -120.8193 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G4112 | 10879 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101383430 | REGW OH PRI CLR RESD FIRE ESTR FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 1 | 243.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117327774 | POLE_BROK_REPL - 2PLN 7405 BAYNE RD PLAC | 35135370 |  |  | STS-POLE_BROK_REPL - 2PLN 7405 BAYNE RD | PEND | PEND ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.7992 | -120.8358 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G40 | 1443 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 30.9 | 30.9 |  |  | 0 | 30.9 | 30.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101413751 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2021-01-25 |  | COMP | 2021-01-25 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-28 | 2020-05-28 |  | 2020-05-28 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 18626.64 | 1576.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117480859 | POLE_DECA_REPL - 977 OAK TERRACE PLACERV | 35148075 |  |  | STS-POLE_DECA_REPL - 977 OAK TERRACE PLA | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.7399 | -120.806 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H4124 | 10617 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 47.3 | 47.3 |  |  | 0 | 47.3 | 47.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101387019 | RELW OH PRI INSP CUST RESD FLAG ESTR BTKA PROG FMOB TER2 | Pole | 2020-12-28 |  | COMP | 2020-12-28 | [16 empty] | 2019-06-22 | 2020-06-22 |  | 2020-06-22 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117480888 | POLE_DECA_REPL - ENTRANCE 985 OAK TERRAC | 35148061 |  |  | STS-POLE_DECA_REPL - ENTRANCE 985 OAK TE | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.7396 | -120.8053 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H4124 | 10617 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51.3 | 51.3 |  |  | 0 | 51.3 | 51.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101387021 | RELW OH PRI INSP CUST RESD FLAG ESTR BTKA PROG FMOB TER2 | Pole | 2021-01-07 |  | COMP | 2021-01-07 | [16 empty] | 2019-06-22 | 2020-06-22 |  | 2020-06-22 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 21951.65 | 235.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117481951 | POLE_BROK_REPL - R/O 2721 EDGEWOOD DR PL | 35148076 |  |  | STS-POLE_BROK_REPL - R/O 2721 EDGEWOOD D | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 38.7389 | -120.8075 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H4124 | 55525 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101387025 | RELW OH SEC INSP CUST RESD NOAC ESTR REAR FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-06-23 | 2020-06-23 |  | 2020-06-23 | 2021 CBP Plan | 2021-01-31 | TRC |  | 153082106 | 1 | 335.7 | -1060 | [5 empty] | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117483822 | POLE_BROK_REPL - 921 MARIA VISTA WY PLAC | 35148067 |  |  | STS-POLE_BROK_REPL - 921 MARIA VISTA WY | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.7331 | -120.8034 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H4124 | 80693 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.1 | 18.1 |  |  | 0 | 18.1 | 18.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101386633 | RELW OH SEC INSP CUST RESD FLAG ESTR BTKA FMOB TER2 | Pole | 2021-01-05 |  | COMP | 2021-01-05 | [16 empty] | 2019-06-24 | 2020-06-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 12026.64 | 425.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117489100 | POLE_DECA_REPL - 873 HILLCREST ST PLACER | 35148104 |  |  | STS-POLE_DECA_REPL - 873 HILLCREST ST PL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.7373 | -120.8077 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H4124 | 80693 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.1 | 41.1 |  |  | 0 | 41.1 | 41.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101386905 | RELW OH SEC INSP CUST RESD FLAG ESTR BTKA FMOB TER2 | Pole | 2021-01-05 |  | COMP | 2021-01-05 | [16 empty] | 2019-06-25 | 2020-06-25 |  | 2020-06-25 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 15708.81 | 2082.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | Placerville | Placerville |  |  | OPEN | 117686554 | POLE_DECA_REPL - SP 5046 NEWTOWN RD #2 E | 35188788 |  |  | STS-POLE_DECA_REPL - SP 5046 NEWTOWN RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 38.7037 | -120.677 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | I44 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.8 | 12.8 |  |  | 0 | 12.8 | 12.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101422952 | RELW OH PRI ESTR USA TER2 PRTO | Pole | 2021-01-14 | 2021-01-08 | COMP | 2020-09-24 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116819220 | POLE_BROK_REPL - 4671 CHROME RIDGE CT PL | 35219238 |  |  | STS-POLE_BROK_REPL - 4671 CHROME RIDGE C | PEND | PEND | Poles | MPP | Not Funded as 2020 Wildfire OII | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Permit Enviro JointPole |  |  | 38.6993 | -120.7153 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | I4320 | 2173 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 47.9 | 47.9 |  |  | 0 | 47.9 | 47.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101398057 | RELW OH PRI JPOL MINR RESD REMT JAR BTKA PROG FSRP FMOB TER2 PRTO | Pole | 2021-02-09 |  | COMP | 2021-02-09 | [16 empty] | 2019-03-23 | 2020-03-23 | 2021-05-31 | 2021-05-31 | work plan year cleanup 01/21/2021 |  | Auburn |  | 153662102 | 24433.41 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-21
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116979541 | POLE_BROK_REPL - A\F 4181 LEISURE LN. PL | 35219239 |  |  | STS-POLE_BROK_REPL - A\F 4181 LEISURE LN | PEND | PEND | Poles | MPP | Not Funded as 2020 Wildfire OII | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.6801 | -120.6802 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J44 | 2661 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101417762 | RELW OH PRI JPOL RESD BTKA FMOB TER2 PRTO | Pole | 2021-02-01 |  | COMP | 2021-02-01 | [16 empty] | 2019-04-08 | 2020-04-08 | 2021-05-31 | 2021-05-31 | work plan year cleanup 01/21/2021 |  | Auburn |  | 153662102 | 24817.37 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-21
North | SI | PLACERVILLE | Placerville |  |  | COMP | 116691914 | POLE_DECA_REPL - #1E #1S 9389 MOSQUIITO | 35137200 |  |  | STS-POLE_DECA_REPL - #1E #1S 9389 MOSQUI | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2020-12-31 | No Action | 38.7493 | -120.78 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H4217 | 99439 | Y | 311 |  |  | 2021-01-15 | 2021-01-15 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 42.8 | 42.8 |  |  | 6 | 1.8 | 1.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103033980 | RELW OH PRI COMP JPOL RESD ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-05-12 | 2020-07-27 | COMP | 2020-05-12 | COMP | 2021-01-15 | 2020-04-08 | 2020-04-08 | [11 empty] | 2021-01-22 | 2021-01-15 | 2020-03-09 |  | 2020-03-09 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 153082106 | 21865.52 | 10850.1 | 4737.4 | 3974.7 | 3974.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | PLACERVILLE | Placerville |  |  | COMP | 116876248 | POLE_BROK_REPL - 4731 WOODLAND DR. PLACE | 35188622 |  |  | STS-POLE_BROK_REPL - 4731 WOODLAND DR. P | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6959 | -120.7434 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I43 |  | Y | 311 |  |  | 2021-02-12 07:00 | 2021-02-12 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 4.5 | 40.8 | 40.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101396967 | RELW COMP JPOL OH PRI REMT ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-10-06 | 2020-11-30 | COMP | 2020-10-05 | COMP | 2021-02-12 | [13 empty] | 2021-02-18 | 2021-02-12 | 2020-03-31 |  | 2020-03-31 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 9221.34 | 3911.4 | 3911.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | COMP | 116955411 | POLE_DECA_REPL - R/O 5167 MT AUKUM RDPLA | 35147910 |  |  | STS-POLE_DECA_REPL - R/O 5167 MT AUKUM R | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6676 | -120.6689 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J45 |  | Y | 311 |  |  | 2021-01-19 | 2021-01-19 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 25 | 25 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101397379 | RELW OH SERV COMP JPOL RESD ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-06-19 | 2020-08-19 | COMP | 2020-06-19 | COMP | 2021-01-19 | [13 empty] | 2021-01-22 | 2021-01-19 | 2020-04-04 |  | 2020-04-04 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153662102 | 5256.54 | 1689.1 | 1644.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | COMP | 116974914 | POLE_DECA_REPL - R/O 4914 BUCKS BAR RD P | 35188624 |  |  |  | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6717 | -120.7258 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J43 |  | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 66.8 | 66.8 |  |  | 3.5 | 65.8 | 65.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101404227 | RELW OH PRI COMP JPOL ESTR CCNT FMOB TER2 PRTO | Pole | 2020-10-14 | 2020-12-05 | COMP | 2020-10-13 | COMP | 2021-02-13 | [13 empty] | 2021-02-19 | 2021-02-13 | 2020-04-07 |  | 2020-04-07 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 5933.63 | 1708.5 | 1708.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | COMP | 117110742 | POLE_BROK_REPL - * PLACERVILLE | 35187794 |  |  | STS-POLE_BROK_REPL - * PLACERVILLE | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6412 | -120.7607 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | K42 |  | Y | 311 |  |  | 2021-02-12 07:00 | 2021-02-12 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103664022 | OH RELW PRI COMP CLR JPOL REMT ESTR REAR CCNT FMOB TER2 PRTO | Pole | 2020-10-08 | 2020-12-03 | COMP | 2020-10-07 | COMP | 2021-02-12 | [13 empty] | 2021-02-18 | 2021-02-12 | 2020-04-27 |  | 2020-04-27 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 6179.28 | 2508.3 | 1515.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | COMP | 117115791 | POLE_BROK_REPL - 5813 OAK HILL RD PLACER | 35188013 |  |  |  | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6425 | -120.7831 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | K42 |  | Y | 311 |  |  | 2021-02-08 07:00 | 2021-02-08 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103664958 | RELW OH SEC CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO CCNT COMP | Pole | 2020-10-09 | 2020-12-01 | COMP | 2020-10-09 | COMP | 2021-02-08 | [13 empty] | 2021-02-10 | 2021-02-08 | 2020-04-28 |  | 2020-04-28 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 9316.07 | 1379.4 | 1379.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | COMP | 117118752 | POLE_BROK_REPL - 3P W/O 5800 OAKHILL RD | 35188092 |  |  |  | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6417 | -120.7868 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | K42 |  | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101416744 | RELW OH PRI COMP CLR JPOL REMT ESTR GO BTKA CCNT FMOB TER2 PRTO | Pole | 2020-10-09 | 2020-12-01 | COMP | 2020-10-08 | COMP | 2021-02-11 | [13 empty] | 2021-02-16 | 2021-02-11 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 5370.26 | 686.3 | 686.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | COMP | 117119660 | POLE_DECA_REPL - 1P E/O 5070 OAKHILL RDP | 35188128 |  |  | STS-POLE_DECA_REPL - 1P E/O 5070 OAKHILL | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6341 | -120.7864 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | K42 |  | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101386627 | OH RELW PRI COMP JPOL RESD NOAC ESTR CCNT FMOB TER2 PRTO | Pole | 2020-10-08 | 2020-12-03 | COMP | 2020-10-08 | COMP | 2021-02-10 | [13 empty] | 2021-02-18 | 2021-02-10 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 9902.9 | 800.4 | 800.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | COMP | 117120908 | POLE_BROK_REPL - 2P E/O 6260 ARCH LN PLA | 35188188 |  |  | STS-POLE_BROK_REPL - 2P E/O 6260 ARCH LN | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6351 | -120.782 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | K42 |  | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101386589 | RELW PRI OH COMP CLR JPOL RESD ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-12-06 | COMP | 2020-10-15 | COMP | 2021-02-11 | [13 empty] | 2021-02-16 | 2021-02-11 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 9075.95 | 2258.2 | 2258.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | COMP | 117125925 | POLE_DECA_REPL - 3121 SAND RIDGE RDPLACE | 35147916 |  |  | STS-POLE_DECA_REPL - 3121 SAND RIDGE RDP | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2020-12-31 | No Action | 38.6222 | -120.7592 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K42 | 12025 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 42.8 | 42.8 |  |  | 5 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101386266 | RELW OH PRI COMP CLR JPOL RESD ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-06-25 | 2020-08-20 | COMP | 2020-06-25 | COMP | 2021-02-10 | 2020-06-25 | 2020-06-25 | [11 empty] | 2021-02-16 | 2021-02-10 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153662102 | 16532.78 | 4474 | 4409.5 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | COMP | 117240373 | POLE_BROK_REPL - 1P W/O P IN R/O HOUSE 1 | 35160306 |  |  | STS-POLE_BROK_REPL - 1P W/O P IN R/O HOU | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7943 | -120.934 |  | TIER 2 | 110 | 15365-2109, SHINGLE SPRINGS | G38 |  | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101388770 | RELW OH PRI COMP CLR JPOL RESD ESTR REAR CCNT FMOB TER2 PRTO | Pole | 2020-09-10 | 2020-11-02 | COMP | 2020-09-10 | COMP | 2021-02-11 | [13 empty] | 2021-02-16 | 2021-02-11 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-12-31 | QUES |  | 153652109 | 11622.63 | 5297.9 | 4684.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | COMP | 117252857 | POLE_DECA_REPL - OPP 337 BAYNE CT PLACER | 35135367 |  |  | STS-POLE_DECA_REPL - OPP 337 BAYNE CT PL | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8008 | -120.857 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G40 | 12223 | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 7.5 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101387736 | RELW OH PRI COMP CLR RESD REMT ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-04-19 | 2020-06-09 | COMP | 2020-04-19 | COMP | 2021-01-06 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-01-13 | 2021-01-06 | 2020-05-15 |  | 2020-05-15 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 153082106 | 15390.13 | 14547 | 10394.4 | 2742.4 | 2742.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | PLACERVILLE | Placerville |  |  | COMP | 117267465 | POLE_BROK_REPL - #1PLS C/O WILD TURKEY L | 35135369 |  |  | STS-POLE_BROK_REPL - #1PLS C/O WILD TURK | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7946 | -120.8412 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G40 | 1443 | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 44.4 | 43.7 | 0.7 |  | 3 | 2.7 | 2.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101387861 | RELW OH PRI COMP RESD FIRE ESTR CCNT FMOB TER2 PRTO | Pole | 2020-03-20 | 2020-06-20 | COMP | 2020-03-20 | COMP | 2021-01-08 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-01-13 | 2021-01-08 | 2020-05-17 |  | 2020-05-17 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 153082106 | 26241.19 | 26796.4 | 20731.6 | 2104.3 | 2104.3 | 22.1 |  | 22.1 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | PLACERVILLE | Placerville |  |  | COMP | 117321685 | POLE_DECA_REPL - 1 PLACERVILLE | 35137439 |  |  | STS-POLE_DECA_REPL - 1 PLACERVILLE | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7951 | -120.8213 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 | 1491 | Y | 311 |  |  | 2021-01-05 | 2021-01-05 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103667738 | PRI RELW OH COMP CLR RESD REMT ESTR BTKA REAR CCNT FMOB TER2 PRTO | Pole | 2020-05-22 | 2020-07-16 | COMP | 2020-05-22 | COMP | 2021-01-05 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-01-08 | 2021-01-05 | 2020-05-25 |  | 2020-05-25 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 153082106 | 22518.88 | 6051 | 2360.8 | 2360.8 | 2360.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | PLACERVILLE | Placerville |  |  | COMP | 117321686 | POLE_DECA_REPL - #4W KELSEY RD ON BRIGHT | 35137440 |  |  | STS-POLE_DECA_REPL - #4W KELSEY RD ON BR | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7942 | -120.8216 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 | 1491 | Y | 311 |  |  | 2021-01-14 | 2021-01-14 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.9 | 41.9 |  |  | 0 | 0.9 | 0.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101387573 | RELW OH PRI COMP CLR RESD REMT NOAC ESTR REAR CCNT FMOB TER2 PRTO | Pole | 2020-05-22 | 2020-05-22 | COMP | 2020-05-22 | COMP | 2021-01-14 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-01-20 | 2021-01-14 | 2020-05-25 |  | 2020-05-25 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 153082106 | 19513 | 5238.6 | 2302 | 2302 | 2302 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | Placerville | Placerville |  |  | COMP | 118085580 | POLE_DECA_REPL - 4351 Leisure LnPlacervi | 35189052 |  |  |  | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6843 | -120.672 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J45 | 15366-2102, APPLE HILL | Y | 311 |  |  | 2021-02-15 07:00 | 2021-02-15 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103669716 | SEC RELW OH COMP RESD ESTR BTKA USA CCNT FMOB TER2 PRTO | Pole | 2020-09-30 | 2020-09-30 | COMP | 2020-09-30 | COMP | 2021-02-15 | [13 empty] | 2021-02-19 | 2021-02-15 | 2020-10-22 |  | 2020-10-22 | 2021 CBP Plan | 2020-11-15 | TRC |  | 153662102 | 3328.15 | 1688.7 | 642.9 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116692579 | POLE_BROK_REPL - R/O 2697 MOSQUITO RD PL | 35137202 |  |  | STS-POLE_BROK_REPL - R/O 2697 MOSQUITO R | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7397 | -120.781 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H4222 | 77273 | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0.25 | 40.75 | 40.75 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101413643 | RELW OH PRI CLR JPOL ESTR FMOB TER2 PRTO | Pole | 2020-07-20 | 2020-10-06 | COMP | 2020-07-20 |  |  | 2019-12-05 | 2019-12-05 | [12 empty] | 2019-03-09 | 2020-03-09 |  | 2020-03-09 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 18563.19 | 3078.9 | 3078.9 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116708200 | POLE_BROK_REPL - 1P.SW.1590 CARSON RD PL | 35185802 |  |  | B3 STS-POLE_BROK_REPL - 1P.SW.1590 CARSO | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7391 | -120.7786 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H4222 | 77273 | Y | 311 |  |  | 2021-04-08 07:00 | 2021-04-08 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 42 | 42 |  |  | 0 | 42 | 42 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101386117 | OH PRI CLR JAR PROG FMOB TER2 PRTO RELW | Pole | 2020-07-22 | 2020-11-23 | COMP | 2020-07-22 |  |  | 2020-07-28 | 2020-07-28 | [12 empty] | 2019-03-11 | 2020-03-11 | 2020-09-21 | 2020-09-21 | Work Plan Reconcilation (B-Tags) |  | Auburn |  | 153082106 | 27111.56 | 10429.6 | 457.8 | 457.8 | 457.8 |  |  |  | FRMMA/WMPMA - Electric | Y | 11/2 in MPP Import File | N | Customer/Third Party Delay | Y | 2020-07-21
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116789313 | POLE_BROK_REPL - 4NE/O R/O 1741 UARRY RD | 35188017 |  |  | STS-POLE_BROK_REPL - 4NE/O R/O 1741 UARR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6951 | -120.7626 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I4225 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34 | 34 |  |  | 0 | 34 | 34 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101403958 | RELW OH PRI PGEA CLR JPOL REMT NOAC ESTR GO REAR FMOB TER2 PRTO | Pole | 2020-08-28 | 2020-11-18 | COMP | 2020-08-27 | [16 empty] | 2019-03-20 | 2020-03-20 |  | 2020-03-20 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 19396.98 | 42.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116791603 | POLE_BROK_REPL - 2R/O .1821 QUARRY RD.PL | 35188048 |  |  | STS-POLE_BROK_REPL - 2R/O .1821 QUARRY R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6929 | -120.766 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I4224 | 2100 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.1 | 32.1 |  |  | 0 | 32.1 | 32.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101416171 | RELW OH PRI JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-27 | 2020-10-21 | COMP | 2020-08-26 | [16 empty] | 2019-03-20 | 2020-03-20 |  | 2020-03-20 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116805269 | POLE_BROK_REPL - SERV TO 4680 SANDRIDGE | 35188088 |  |  | STS-POLE_BROK_REPL - SERV TO 4680 SANDRI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6434 | -120.6986 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J4423 | 2001 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.6 | 34.6 |  |  | 0 | 34.6 | 34.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101421065 | RELW OH PRI JPOL RESD ESTR REAR FMOB TER2 PRTO | Pole | 2020-09-09 | 2020-10-26 | COMP | 2020-09-08 | [16 empty] | 2019-03-21 | 2020-03-21 |  | 2020-03-21 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N | Access/Customer Issue | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116807092 | POLE_DECA_REPL - 2 W/O 3540 SYLVAN LNPLA | 35160206 |  |  | STS-POLE_DECA_REPL - 2 W/O 3540 SYLVAN L | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7114 | -120.8877 |  | TIER 2 | 113 | 15226-1107, DIAMOND SPRINGS | I3914 | 1402 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 60 | 60 |  |  | 0 | 60 | 60 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101411027 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-10-14 | 2020-12-01 | COMP | 2020-10-14 | [16 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 152261107 | 21357.25 | 244.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116822099 | POLE_BROK_REPL - 3536 MINING BROOK RD PL | 35160207 |  |  | STS-POLE_BROK_REPL - 3536 MINING BROOK R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7244 | -120.7314 |  | TIER 2 | 248 | 15366-1103, APPLE HILL | I4303 | 18463 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50.9 | 50.9 |  |  | 0 | 50.9 | 50.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101397951 | RELW OH PRI PGEA CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-11 | 2021-01-12 | COMP | 2020-10-16 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 153661103 | 26233.93 | 15721.1 | 2442.7 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116828097 | POLE_BROK_REPL - 4606 PARK HILL DR PLACE | 35188388 |  |  | STS-POLE_BROK_REPL - 4606 PARK HILL DR P | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6887 | -120.6476 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | I45 | 11427 | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101408237 | RELW OH PRI REMT PGEA CLR JPOL ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-28 | 2020-11-30 | COMP | 2020-09-28 |  |  | 2020-09-04 | 2020-09-04 | [12 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 18093.21 | 2394.5 | 2352 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116873401 | POLE_BROK_REPL - #1W 4200 WOODLAND CT PL | 35188588 |  |  | STS-POLE_BROK_REPL - #1W 4200 WOODLAND C | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7006 | -120.7503 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I43 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.4 | 15.4 |  |  | 0 | 15.4 | 15.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101396987 | RELW OH PRI JPOL RESD REMT JAR BTKA FMOB TER2 PRTO SCPA SCOP | Pole | 2020-08-25 | 2020-10-21 | COMP | 2020-08-25 | [16 empty] | 2019-03-30 | 2020-03-30 |  | 2020-03-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116877273 | POLE_DECA_REPL - 2P/E/O 4805 WOODLAND DR | 35188646 |  |  | STS-POLE_DECA_REPL - 2P/E/O 4805 WOODLAN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6947 | -120.7373 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I43 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.7 | 32.7 |  |  | 0 | 32.7 | 32.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101418131 | RELW OH PRI JPOL REMT NOAC ESTR FMOB PRTO TER2 | Pole | 2020-08-27 | 2020-10-26 | COMP | 2020-08-27 | [16 empty] | 2019-03-31 | 2020-03-31 |  | 2020-03-31 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116879216 | POLE_DECA_REPL - 1P/NW/O 4588 WOODLAND D | 35187563 |  |  | STS-POLE_DECA_REPL - 1P/NW/O 4588 WOODLA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.698 | -120.7476 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I43 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.5 | 16.5 |  |  | 0 | 16.5 | 16.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101396977 | RELW OH PRI JPOL REMT SWRK ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-02 | 2021-01-08 | COMP | 2020-10-02 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-01 | 2020-04-01 |  | 2020-04-01 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 5959.72 | 170.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116937142 | POLE_DECA_REPL - 1W/O 1380 1401 COSENS L | 35187697 |  |  | STS-POLE_DECA_REPL - 1W/O 1380 1401 COSE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6556 | -120.7836 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | J42 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.6 | 14.6 |  |  | 0 | 14.6 | 14.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101393408 | RELW OH PRI JPOL RESD REMT FIRE ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-11 | 2021-01-12 | COMP | 2020-10-13 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-02 | 2020-04-02 |  | 2020-04-02 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116937759 | POLE_BROK_REPL - R/O 4927 LAKESIDE DR.PL | 35187703 |  |  | STS-POLE_BROK_REPL - R/O 4927 LAKESIDE D | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6854 | -120.7482 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | J43 |  | Y | 311 |  |  | 2021-02-15 07:00 | 2021-02-15 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101403967 | RELW OH SEC JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-13 | 2020-12-05 | COMP | 2020-10-13 | [16 empty] | 2019-04-02 | 2020-04-02 |  | 2020-04-02 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 3257.73 | 329.2 | 329.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116938838 | POLE_DECA_REPL - 4930 OAK LEAF CIR PLACE | 35187708 |  |  | STS-POLE_DECA_REPL - 4930 OAK LEAF CIR P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6745 | -120.6647 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J45 | 8971 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 31.9 | 31.9 |  |  | 0 | 31.9 | 31.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101418758 | RELW OH PRI JPOL TER2 RESD NOAC ESTR FMOB PRTO | Pole | 2020-10-07 | 2020-12-02 | COMP | 2020-10-07 | [16 empty] | 2019-04-02 | 2020-04-02 |  | 2020-04-02 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116941248 | POLE_BROK_REPL - ENTRANCE 2161 PLEASANT | 35160210 |  |  | STS-POLE_BROK_REPL - ENTRANCE 2161 PLEAS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6758 | -120.7542 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | J4306 |  | Y | 311 |  |  | 2021-04-06 07:00 | 2021-04-06 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101403705 | RELW OH PRI CLR RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-24 | 2020-11-19 | COMP | 2020-09-24 | [16 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2020-10-31 | QUES |  | 152261106 | 11662.31 | 3521.4 | 3121.1 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116948589 | POLE_DECA_REPL - R/O 4000 WINTERHILL DR. | 35187760 |  |  | STS-POLE_DECA_REPL - R/O 4000 WINTERHILL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.685 | -120.7156 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J43 |  | Y | 311 |  |  | 2021-03-06 07:00 | 2021-03-06 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101404114 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-10-08 | 2020-12-02 | COMP | 2020-10-08 | [16 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 3569.99 | 428.8 | 428.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116948854 | POLE_DECA_REPL - SERV TO 1452 BADGER HIL | 35160211 |  |  | STS-POLE_DECA_REPL - SERV TO 1452 BADGER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7735 | -120.9498 |  | TIER 2 | 110 | 15365-2109, SHINGLE SPRINGS | H3801 | 4655 | Y | 311 |  |  | 2021-03-17 07:00 | 2021-03-17 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.2 | 41 | 0.2 |  | 0 | 41.2 | 41 | 0.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101414244 | OH RELW PRI INSP JPOL RESD FIRE ESTR BTKA REAR FMOB TER2 | Pole | 2020-08-05 | 2020-10-02 | COMP | 2020-08-05 | [16 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2020-09-30 | QUES |  | 153652109 | 21493.78 | 515.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116960648 | POLE_DECA_REPL - 1PE A/F 1401 COSENS LN | 35188014 |  |  | STS-POLE_DECA_REPL - 1PE A/F 1401 COSENS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6556 | -120.7846 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | J42 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.5 | 18.5 |  |  | 0 | 18.5 | 18.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101415806 | RELW OH PRI JPOL RESD REMT FIRE ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-28 | 2020-11-06 | COMP | 2020-08-27 | [16 empty] | 2019-04-04 | 2020-04-04 |  | 2020-04-04 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 8411.21 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116966659 | POLE_BROK_REPL - 2N/O 2NW/O 4925 BUCKSBA | 35188222 |  |  | STS-POLE_BROK_REPL - 2N/O 2NW/O 4925 BUC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6758 | -120.7264 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J43 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.4 | 14.4 |  |  | 0 | 14.4 | 14.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101404196 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-08-24 | 2020-11-06 | COMP | 2020-08-24 | [16 empty] | 2019-04-05 | 2020-04-05 |  | 2020-04-05 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 10011.24 | 100.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116973622 | POLE_BROK_REPL - R/O 5361 GOLD DUST DR P | 35188572 |  |  | STS-POLE_BROK_REPL - R/O 5361 GOLD DUST | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6797 | -120.7305 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J43 | 1333 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 62.7 | 60.3 | 2.4 |  | 0 | 62.7 | 60.3 | 2.4 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101404062 | OH PRI ESTR FMOB TER2 PRTO RELW | Pole | 2020-08-27 | 2020-10-23 | COMP | 2020-08-27 | [16 empty] | 2019-04-07 | 2020-04-07 |  | 2020-04-07 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116974573 | POLE_DECA_REPL - 5301 MOONSHNE RD. AT HO | 35188608 |  |  | STS-POLE_DECA_REPL - 5301 MOONSHNE RD. A | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6845 | -120.7713 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | J4203 | 20351 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48.4 | 47.8 | 0.6 |  | 0 | 48.4 | 47.8 | 0.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101393764 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-10-06 | 2020-12-01 | COMP | 2020-10-06 | [16 empty] | 2019-04-07 | 2020-04-07 |  | 2020-04-07 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116978779 | POLE_DECA_REPL - 1/N/O 1/W/O 4701 HAPPY | 35187566 |  |  | STS-POLE_DECA_REPL - 1/N/O 1/W/O 4701 HA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6796 | -120.6788 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J44 | 2661 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37 | 37 |  |  | 0 | 37 | 37 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101405423 | RELW OH PRI CLR JPOL ESTR GO BTKA REAR FMOB TER2 PRTO | Pole | 2020-10-09 | 2020-11-30 | COMP | 2020-10-08 | [16 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 17178.09 | 42.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116984635 | POLE_BROK_REPL - 2E/O R/O 2222 SAM HILL | 35187766 |  |  | STS-POLE_BROK_REPL - 2E/O R/O 2222 SAM H | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6867 | -120.7479 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | J43 |  | Y | 311 |  |  |  |  | Started | Order Operation | [6 empty] | 13.3 | 13.3 |  |  | 0 | 13.3 | 13.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101404030 | RELW OH PRI CLR RESD REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-10-09 | 2020-12-01 | COMP | 2020-10-08 | [16 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 7848.17 | 1153.4 | 1153.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117001763 | POLE_DECA_REPL - 1P E\O 3601 SPRINGER RD | 35188032 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6744 | -120.6991 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J44 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 16.5 | 16.5 |  |  | 0 | 16.5 | 16.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101405973 | OH RELW PRI CLR JPOL REMT NOAC ESTR FMOB PRTO TER2 | Pole | 2020-10-14 | 2020-12-02 | COMP | 2020-10-13 | [16 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 5492.19 | 793.5 | 793.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117007775 | POLE_DECA_REPL - 5333 ROCKY RIDGE RD PLA | 35188089 |  |  | STS-POLE_DECA_REPL - 5333 ROCKY RIDGE RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6589 | -120.7746 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | J42 | 2591 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.4 | 28.1 | 1.3 |  | 0 | 29.4 | 28.1 | 1.3 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101395335 | RELW OH PRI JPOL RESD REMT ESTR BTKA PROG FMOB TER2 PRTO | Pole | 2020-09-01 | 2020-10-23 | COMP | 2020-08-31 | [16 empty] | 2019-04-11 | 2020-04-11 |  | 2020-04-11 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 15469.05 | 324.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117021390 | POLE_DECA_REPL - 2S/O 2555 RIMROCK RD. P | 35188334 |  |  | STS-POLE_DECA_REPL - 2S/O 2555 RIMROCK R | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6614 | -120.738 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | J43 |  | Y | 311 |  |  | 2021-03-12 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101416800 | OH RELW PRI CLR RESD REMT NOAC ESTR GO FMOB TER2 PRTO | Pole | 2020-10-09 | 2020-10-09 | COMP | 2020-10-09 | [16 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 9393.14 | 1341 | 411.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117114039 | POLE_DECA_REPL - R/O 1281 MOCCASIN TRAIL | 35187874 |  |  | STS-POLE_DECA_REPL - R/O 1281 MOCCASIN T | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6388 | -120.7819 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | K42 | 5275 | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101416759 | RELW OH PRI CLR JPOL REMT ESTR REAR FMOB TER2 PRTO | Pole | 2020-10-09 | 2020-12-01 | COMP | 2020-10-09 | [16 empty] | 2019-04-28 | 2020-04-28 |  | 2020-04-28 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 19288.02 | 1209.2 | 1056.8 | 142.1 | 142.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117115287 | POLE_DECA_REPL - 1P E/O 1225 MOCCASIN TR | 35187966 |  |  | STS-POLE_DECA_REPL - 1P E/O 1225 MOCCASI | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.637 | -120.7843 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | K42 |  | Y | 311 |  |  | 2021-02-12 07:00 | 2021-02-12 16:00 | Completed | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101386458 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-12-02 | 2020-12-03 | COMP | 2020-10-15 |  |  | 2020-12-15 | 2020-12-15 | [12 empty] | 2019-04-28 | 2020-04-28 |  | 2020-04-28 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 13110.61 | 1459.7 | 1459.7 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117117435 | POLE_DECA_REPL - 5071 CLAN RAMSAY LNPLAC | 35188053 |  |  | STS-POLE_DECA_REPL - 5071 CLAN RAMSAY LN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6272 | -120.7867 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | K42 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.4 | 18.4 |  |  | 0 | 18.4 | 18.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103664990 | RELW OH PRI ESTR CLR JPOL RESD BTKA FMOB TER2 PRTO | Pole | 2020-10-09 | 2020-12-02 | COMP | 2020-10-09 | [16 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117125630 | POLE_DECA_REPL - 1W/O 3970 HIGH VIEW DR. | 35188311 |  |  | STS-POLE_DECA_REPL - 1W/O 3970 HIGH VIEW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6364 | -120.723 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 35.8 | 35.8 |  |  | 0 | 35.8 | 35.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101401254 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-11 | 2021-01-11 | COMP | 2020-10-13 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 15190.52 | 728.2 | 299.1 | 299.1 | 299.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117131948 | POLE_BROK_REPL - 2361 SANDRIDGE RDPLACER | 35188436 |  |  | STS-POLE_BROK_REPL - 2361 SANDRIDGE RDPL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6068 | -120.78 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K42 | 13267 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48.6 | 48.6 |  |  | 5 | 43.6 | 43.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101415396 | RELW OH PRI CLR JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-11 | 2021-01-11 | COMP | 2020-09-29 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 22711.36 | 1544.3 | 213.5 | 213.5 | 213.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117193130 | POLE_BROK_REPL - AT HOUSE 4700 SCHIRLE D | 35160304 |  |  | STS-POLE_BROK_REPL - AT HOUSE 4700 SCHIR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7879 | -120.9296 |  | TIER 2 | 110 | 15365-2109, SHINGLE SPRINGS | G38 | 11039 | Y | 311 |  |  | 2021-03-20 07:00 | 2021-03-20 16:00 | Scheduled | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101388786 | RELW OH PRI CLR JPOL REAR RESD ESTR FMOB TER2 PRTO | Pole | 2020-10-02 | 2020-12-01 | COMP | 2020-10-02 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | 2021 CBP Plan | 2020-10-31 | QUES |  | 153652109 | 22366.87 | 540.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117225611 | POLE_BROK_REPL - 1W\O 7860 BAYNE RD PLAC | 35136904 |  |  | STS-POLE_BROK_REPL - 1W\O 7860 BAYNE RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.798 | -120.8219 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G4112 | 1443 | Y | 311 |  |  | 2021-03-23 07:00 | 2021-03-23 16:00 | Scheduled | CLICK | [6 empty] | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101413741 | RELW OH PRI JPOL RESD FIRE ESTR BTKA FMOB TER2 PRTO | Pole | 2020-07-10 | 2020-09-10 | COMP | 2020-07-10 |  |  | 2020-05-12 | 2020-05-12 | [12 empty] | 2019-05-13 | 2020-05-13 |  | 2020-05-13 | 2021 CBP Plan | 2020-05-31 | W. Sac |  | 153082106 | 32955.27 | 1320.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117232588 | POLE_BROK_REPL - R\O 7740 TEXAS CANYON R | 35137053 |  |  | STS-POLE_BROK_REPL - 7740 TEXAS CANYON R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7834 | -120.8185 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 | 11313 | Y | 311 |  |  | 2021-03-27 07:00 | 2021-03-27 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101383527 | REGW OH PRI CLR RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-09-01 | 2020-09-15 | COMP | 2020-09-01 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 143713.29 | 2316.5 | 652.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117232646 | POLE_BROK_REPL - 7660 TXS CNYN RD PLACER | 35137053 |  |  | STS-POLE_BROK_REPL - 7740 TEXAS CANYON R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7829 | -120.8194 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 | 11313 | Y | 311 |  |  | 2021-03-27 07:00 | 2021-03-27 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101383534 | REGW OH PRI CLR RESD FIRE ESTR PROG FMOB TER2 PRTO | Pole | 2020-09-01 | 2020-09-15 | COMP | 2020-09-01 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 143713.29 | 2316.5 | 652.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117237264 | POLE_BROK_REPL - 7540 TEXAS CANYON RD. P | 35137053 |  |  | STS-POLE_BROK_REPL - 7740 TEXAS CANYON R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7834 | -120.8218 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 |  | Y | 311 |  |  | 2021-03-27 07:00 | 2021-03-27 16:00 | Scheduled | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101417147 | REGW OH PRI CLR ESTR RESD FIRE FMOB TER2 PRTO | Pole | 2020-09-01 | 2020-09-15 | COMP | 2020-09-01 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 143713.29 | 2316.5 | 652.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117246412 | POLE_BROK_REPL - 2P S/O 1400 MCKEE DR. P | 35160307 |  |  | STS-POLE_BROK_REPL - 2P S/O 1400 MCKEE D | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7825 | -120.9279 |  | TIER 2 | 110 | 15365-2109, SHINGLE SPRINGS | G38 |  | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-08 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0.25 | 40.75 | 40.75 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101388693 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-11-04 | 2020-11-05 | COMP | 2020-09-11 |  |  | 2020-11-05 | 2020-11-05 | [12 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-10-31 | QUES |  | 153652109 | 14662.94 | 4065.5 | 3062.1 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117249251 | POLE_DECA_REPL - 1S/O 1336 HIDDEN LAKE D | 35160308 |  |  | STS-POLE_DECA_REPL - 1S/O 1336 HIDDEN LA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7755 | -120.9642 |  | TIER 2 | 110 | 15365-2109, SHINGLE SPRINGS | H37 | 11477 | Y | 311 |  |  | 2021-03-10 07:00 | 2021-03-10 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101409414 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-05 | 2020-11-24 | COMP | 2020-10-05 | [16 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-12-31 | QUES |  | 153652109 | 15497.47 | 271.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117249354 | POLE_DECA_REPL - 1W/O 6NE/O 4320 LARKIN | 35160310 |  |  | STS-POLE_DECA_REPL - 1W/O 6NE/O 4320 LAR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6972 | -120.7918 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I42 |  | Y | 311 |  |  |  |  | Started | Order Operation | [6 empty] | 17.4 | 17.4 |  |  | 0 | 17.4 | 17.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101416887 | RELW OH PRI CLR JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-09-10 | 2020-09-10 | COMP | 2020-09-10 | [16 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-12-31 | QUES |  | 152261106 | 19534.17 | 2886.4 | 2135.7 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117249918 | POLE_BROK_REPL - R\O 4180 BRIGHT HOPE MI | 35137426 |  |  | STS-POLE_BROK_REPL - R\O 4180 BRIGHT HOP | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7929 | -120.8209 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 | 1491 | Y | 311 |  |  | 2021-03-30 07:00 | 2021-03-30 16:00 | Scheduled | CLICK | [6 empty] | 42.8 | 42.8 |  |  | 0 | 42.8 | 42.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101387570 | RELW OH PRI CLR RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-09-04 | 2020-11-17 | COMP | 2020-09-04 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117262890 | POLE_BROK_REPL - 2250 SANDRIDGE RD PLACE | 35189507 |  |  | STS-POLE_BROK_REPL - 2250 SANDRIDGE RD P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6083 | -120.7776 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K42 | 13267 | Y | 311 |  |  | 2021-03-16 07:00 | 2021-03-16 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103702329 | OH RELW PRI CREW CLR JPOL REMT NOAC SPCR ESTR REAR USA TER2 | Pole | 2020-09-08 | 2020-11-06 | COMP | 2020-09-08 | [16 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 12775.2 | 43.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117267962 | POLE_OVRL_REPL - 4001 BRIGHT HOPE MINE R | 35188763 |  |  | STS-POLE_OVRL_REPL - 4001 BRIGHT HOPE MI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7922 | -120.8273 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 |  | Y | 311 |  |  | 2021-03-06 07:00 | 2021-03-06 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Overloaded | Replace |  | 103032385 | SEC OH RELW CLR RESD FIRE ESTR GO FMOB TER2 PRTO SCPA SCOP | Pole | 2020-10-07 | 2020-11-30 | COMP | 2020-10-07 | [16 empty] | 2019-05-18 | 2020-05-18 |  | 2020-05-18 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153082106 | 8038.58 | 595.5 | 544.2 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117293045 | POLE_DECA_REPL - 407 COLOMA HEIGHT RD PL | 35160314 |  |  | STS-POLE_DECA_REPL - 407 COLOMA HEIGHT R | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7984 | -120.8867 |  | TIER 2 | 110 | 15365-2109, SHINGLE SPRINGS | G3914 |  | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101381506 | RELW OH PRI INSP CLR JPOL RESD ESTR BTKA REAR USA FMOB TER2 | Pole | 2020-09-15 | 2020-11-09 | COMP | 2020-09-15 |  |  | 2020-07-06 | 2020-07-06 | [12 empty] | 2019-05-21 | 2020-05-21 |  | 2020-05-21 | 2021 CBP Plan | 2020-10-31 | QUES |  | 153652109 | 19866.73 | 3757.6 | 3205.1 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117307681 | POLE_BROK_REPL - 2E\O R\O 4320 RAINBOW R | 35189193 |  |  | STS-POLE_BROK_REPL - 2E\O R\O 4320 RAINB | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6989 | -120.6575 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | I4517 |  | Y | 311 |  |  | 2021-03-05 07:00 | 2021-03-05 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101421528 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-30 | 2020-09-30 | COMP | 2020-09-30 | [16 empty] | 2019-05-23 | 2020-05-23 |  | 2020-05-23 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 6952.37 | 166.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117320092 | POLE_DECA_REPL - 4210 BRIGHT HOPE MINE R | 35137376 |  |  | STS-POLE_DECA_REPL - 4210 BRIGHT HOPE MI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.793 | -120.8201 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 | 1491 | Y | 311 |  |  |  |  | Started | Order Operation | [6 empty] | 89.6 | 89.6 |  |  | 0 | 89.6 | 89.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101387568 | RELW OH PRI CLR RESD REMT ESTR BTKA REAR FMOB TER2 PRTO | Pole | 2020-06-24 | 2020-08-19 | COMP | 2020-06-23 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-25 | 2020-05-25 |  | 2020-05-25 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 49692.94 | 4324 | 4324 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117322499 | POLE_DECA_REPL - 3N\O 4025 BRIGHT HOPE M | 35137376 |  |  | STS-POLE_DECA_REPL - 4210 BRIGHT HOPE MI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7954 | -120.827 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 |  | Y | 311 |  |  |  |  | Started | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101387592 | REGW OH PRI RESD FIRE ESTR GO FMOB TER2 PRTO | Pole | 2020-06-24 | 2020-08-19 | COMP | 2020-06-23 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-26 | 2020-05-26 |  | 2020-05-26 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 49692.94 | 4324 | 4324 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117322519 | POLE_DECA_REPL - 2N\O 4025 BRIGHT HOPE M | 35137376 |  |  | STS-POLE_DECA_REPL - 4210 BRIGHT HOPE MI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7948 | -120.8271 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 |  | Y | 311 |  |  |  |  | Started | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101416633 | REGW OH PRI RESD FIRE ESTR GO FMOB TER2 PRTO | Pole | 2020-06-24 | 2020-08-19 | COMP | 2020-06-23 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-26 | 2020-05-26 |  | 2020-05-26 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153082106 | 49692.94 | 4324 | 4324 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117329692 | POLE_DECA_REPL - #7 ON LINE W/O KELSEY R | 35137441 |  |  | STS-POLE_DECA_REPL - #7 ON LINE W/O KELS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7942 | -120.8262 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 |  | Y | 311 |  |  | 2021-03-19 07:00 | 2021-03-19 16:00 | Scheduled | CLICK | [6 empty] | 45.8 | 41.9 | 3.9 |  | 0 | 45.8 | 41.9 | 3.9 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101387576 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-09-28 | 2020-11-02 | COMP | 2020-09-28 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-28 | 2020-05-28 |  | 2020-05-28 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 32857.12 | 196 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117335069 | POLE_BROK_REPL - WSIP PLACERVILLE | 35189471 |  |  | STS-POLE_BROK_REPL - WSIP PLACERVILLE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5982 | -120.7825 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K4222 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 20.1 | 20.1 |  |  | 0 | 20.1 | 20.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103663115 | RELW OH PRI CLR JPOL RESD TRAF ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-11 | 2021-01-12 | COMP | 2020-08-27 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-05-28 | 2020-05-28 |  | 2020-05-28 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 9887.16 | 192.6 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117335087 | POLE_DECA_REPL - 2186 SAND RIDGE RDPLACE | 35189474 |  |  | STS-POLE_DECA_REPL - 2186 SAND RIDGE RDP | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5975 | -120.7778 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L42 | 13267 | Y | 311 |  |  | 2021-03-17 07:00 | 2021-03-17 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103688495 | PRI RELW OH CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-28 | 2020-10-21 | COMP | 2020-08-28 | [16 empty] | 2019-05-28 | 2020-05-28 |  | 2020-05-28 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117485683 | POLE_DECA_REPL - R/O 2821 MANOR DR PLACE | 35148062 |  |  | STS-POLE_DECA_REPL - R/O 2821 MANOR DR P | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7354 | -120.8057 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H4124 | 92871 | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 44.4 | 44.4 |  |  | 0 | 44.4 | 44.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101386527 | RELW OH PRI INSP CUST RESD FLAG ESTR BTKA FMOB TER2 | Pole | 2020-07-28 | 2020-10-06 | COMP | 2020-07-28 |  |  | 2020-07-30 | 2020-07-30 | [12 empty] | 2019-06-24 | 2020-06-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-09-30 | W. Sac |  | 153082106 | 27629.42 | 2963.5 | 2789.6 | [5 empty] | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117999860 | POLE_BROK_REPL - 1PLW 2PLS C/O RIVER BEN | 35188980 |  |  | STS-POLE_BROK_REPL - 1PLW 2PLS C/O RIVER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7803 | -120.8382 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G40 | 1443 | Y | 311 |  |  | 2021-03-29 07:00 | 2021-03-29 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101388008 | RELW OH PRI INSP CLR JPOL REMT ESTR BTKA REAR FMOB TER2 | Pole | 2020-10-07 | 2020-12-03 | COMP | 2020-10-06 | [16 empty] | 2019-10-15 | 2020-10-15 |  | 2020-10-15 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153082106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | Placerville | Placerville |  |  | OPEN | 118058851 | POLE_DECA_REPL - 1P S\O OPP\O 5255 BUCKS | 35189047 |  |  | STS-POLE_DECA_REPL - 1P S\O OPP\O 5255 B | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6612 | -120.7069 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J44 | 15366-2102, APPLE HILL | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | [6 empty] | 122.7 | 122.7 |  |  | 0 | 122.7 | 122.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101406725 | RELW OH PRI CLR JPOL RESD FMOB REMT ESTR BTKA USA TER2 PRTO | Pole | 2020-10-05 | 2020-11-30 | COMP | 2020-10-05 | [16 empty] | 2019-10-21 | 2020-10-21 |  | 2020-10-21 | 2021 CBP Plan | 2020-11-15 | TRC |  | 153662102 | 14372.97 | 3464.4 | 2368.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 119909380 | POLE_DECA_REPL - 1340 ARROWBEE DR PLACER | 35207266 |  |  | B3 STS-POLE_DECA_REPL - 1340 ARROWBEE DR | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7825 | -120.9347 |  | TIER 2 | 110 | 15365-2109, SHINGLE SPRINGS | G38 | 20543 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-08 16:00 | Dispatched | CLICK | [6 empty] | 66 | 66 |  |  | 0 | 66 | 66 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101388679 | ESTR RELW OH TER2 | Pole | 2020-11-23 | 2020-11-25 | COMP | 2020-11-23 |  |  | 2020-11-20 | 2020-11-20 | [12 empty] | 2020-09-14 | 2020-12-14 |  | 2020-12-14 | B tag clean up 10/18/2020 |  | Auburn |  | 153652109 | 31573.54 | 8408.5 | 3078.9 | -9.3 | -9.3 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Construction_Did_Not_Execute_Timely | Y | 2020-10-18
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 119909667 | POLE_BROK_REPL - #4 S/O 1141 WALLACE RD | 35207268 |  |  | B3 STS-POLE_BROK_REPL - #4 S/O 1141 WALL | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.753 | -120.8556 |  | TIER 2 | 586 | 15308-1110, PLACERVILLE | H40 | 421358 | Y | 311 |  |  | 2021-03-12 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | [6 empty] | 51.1 | 40.1 | 11 |  | 2 | 51 | 40 | 11 |  | EC | B | Pole | Broken/Damaged | Replace |  | 101389529 | RELW OH ESTR TER2 | Pole | 2020-11-22 | 2020-11-22 | INPR | 2020-11-22 | [16 empty] | 2020-09-16 | 2020-12-16 |  | 2020-12-16 | B tag clean up 10/18/2020 |  | Auburn |  | 153081110 | 38659.03 | 13042 | 2214.2 | 2214.2 | 2214.2 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-10-18
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 119944441 | POLE_BROK_REPL - 2684 COLOMA CT PLACERVI | 35210250 |  |  | B3 STS-POLE_BROK_REPL - 2684 COLOMA CT P | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-12-10 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7372 | -120.8131 |  | TIER 2 | 586 | 15308-1110, PLACERVILLE | H4123 | 21673 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Dispatched | CLICK | [6 empty] | 40.2 | 40.2 |  |  | 0 | 40.2 | 40.2 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101386227 | RELW OH ESTR TER2 | Pole | 2020-12-17 | 2020-12-17 | COMP | 2020-11-30 |  |  | 2020-12-03 | 2020-12-03 | [12 empty] | 2020-10-07 | 2021-01-07 |  | 2021-01-07 | B tag clean up 11/1/2020 |  | Auburn |  | 153081110 | 16066.43 | 743 | [7 empty] | N | 11/2 in MPP Import File | N |  | Y | 2020-11-01
North | SI | PLACERVILLE | Placerville |  |  | COMP | 117014719 | POLE_BROK_REPL - 1660 COUNTRY LN PLACERV | 35160216 |  |  | STS-POLE_BROK_REPL - 1660 COUNTRY LN PLA | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6662 | -120.7734 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | J4213 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 11.1 | 11.1 |  |  | 30 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101394902 | RELW OH PRI COMP CLR RESD FIRE ESTR CPGG FMOB TER2 PRTO | Pole | 2020-10-21 | 2020-12-17 | COMP | 2020-10-21 | COMP | 2021-01-10 | 2020-10-12 | 2020-10-12 | [11 empty] | 2021-01-13 | 2021-01-10 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | QUES |  | 152261106 | 9392.82 | 10527.4 | 10336.2 | 10336.2 | 10336.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | COMP | 117118875 | POLE_DECA_REPL - 2P W/O 5800 OAKHILL RD | 35188113 |  |  | STS-POLE_DECA_REPL - 2P W/O 5800 OAKHILL | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6418 | -120.7858 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | K42 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 15.1 | 15.1 |  |  | 40 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101386418 | RELW OH PRI CLR JPOL PUBL REMT ESTR GO BTKA FMOB TER2 PRTO CPGD COMP | Pole | 2020-10-09 | 2020-12-04 | COMP | 2020-10-08 | COMP | 2021-01-10 | [13 empty] | 2021-01-28 | 2021-01-10 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 5141.23 | 13781.6 | 13781.6 | 13781.6 | 13781.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | COMP | 117241286 | POLE_BROK_REPL - 5PLW 2PLS 9461 HWY 193 | 35137364 |  |  | STS-POLE_BROK_REPL - 5PLW 2PLS 9461 HWY | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-09-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8054 | -120.8257 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 |  | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 18.1 | 18.1 |  |  | 31 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103032360 | RELW OH SEC PGEA COMP ESTR CPGG FMOB TER2 PRTO | Pole | 2020-04-06 | 2020-06-16 | COMP | 2020-04-03 | COMP | 2021-01-13 | 2019-12-02 | 2019-12-02 | [11 empty] | 2021-01-17 | 2021-01-13 | 2020-05-15 |  | 2020-05-15 | circuit based plan 2.14 | 2020-05-31 | W. Sac |  | 153082106 | 10423.87 | 12375.4 | 7893.2 | 7893.2 | 7893.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | PLACERVILLE | Placerville |  |  | COMP | 119637880 | POLE_BROK_REPL - 2PS 2PE A/F 5641 CALAMI | 35198068 |  |  | B3 STS-POLE_BROK_REPL - 2PS 2PE A/F 5641 | FICL | FICL SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-10-22 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6465 | -120.7634 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | J42 |  | Y | 311 |  |  | 2021-01-05 | 2021-01-05 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 35.1 | 35.1 |  |  | 52.5 | 0 |  |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101396381 | RELW INSP OH PRI COMP CLR JPOL REMT FIRE NOAC ESTR GO REAR CPGD FMOB TER2 | Pole | 2020-10-01 | 2020-10-23 | COMP | 2020-10-01 | COMP | 2021-01-05 | [13 empty] | 2021-01-06 | 2021-01-05 | 2020-11-19 |  | 2020-11-19 | B tag clean up 8/29/2020 |  | Auburn |  | 152261106 | 29527.77 | 29943.9 | 24399.2 | 24399.2 | 24399.2 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N |  | Y | 2020-08-29
North | SI | PLACERVILLE | Placerville |  |  | COMP | 119993947 | COND_CLER_INPL - 3442 Excalibar Rd.Place | 35213116 |  |  | B3 - STS-COND_CLER_INPL - 3442 EXCALIBAR | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-09 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7207 | -120.8201 |  | TIER 2 | 940 | 15308-1111, PLACERVILLE | I4107 | 11287 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 11.1 | 11.1 |  |  | 30 | 0 |  |  |  | EC | B | Conductor | Clearance Impaired | Install CL Pole |  | 101406882 | RELW OH SERV COMP RESD ESTR GO BTKA USA CTMN PROG FMOB TER2 | Pole | 2020-12-04 | 2020-12-11 | COMP | 2020-12-04 | COMP | 2021-01-12 | [13 empty] | 2021-01-13 | 2021-01-12 | 2021-02-06 |  | 2021-02-06 | B tag clean up 11/15/2020 |  | Auburn |  | 153081111 | 6078.23 | 9304.5 | 8704.6 | 8704.6 | 8704.6 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-11-15
North | SI | PLACERVILLE | Placerville |  |  | COMP | 119994729 | POLE_DECA_REPL - 4190 OLIVE RIDGE RD PLA | 35212831 |  |  | B3 - STS-POLE_DECA_REPL - 4190 OLIVE RID | MAPP | MAPP SRDY REDL | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-10 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7462 | -120.9377 |  | TIER 2 | 110 | 15365-2109, SHINGLE SPRINGS | H3818 |  | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 40.1 | 40.1 |  |  | 62 | 0 |  |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101376533 | RELW OH PRI SERV TMAN COMP JPOL BTKA USA CPGE CPGD TER2 PROG ESTR | Pole | 2020-12-07 | 2020-12-15 | COMP | 2020-12-07 | COMP | 2021-02-17 | [13 empty] | 2021-02-18 | 2021-02-17 | 2021-02-07 |  | 2021-02-07 | B tag clean up 11/15/2020 |  | Auburn |  | 153652109 | 21158.49 | 6208.5 | 5271.6 | 1004.7 | 1004.7 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-11-15
North | SI | PLACERVILLE | Placerville |  |  | COMP | 120009614 | POLE_DECA_REPL - REAR OF 1220 SOURDOUGH | 35213117 |  |  | B3 - STS-POLE_DECA_REPL - REAR OF 1220 S | MAPP | MAPP SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-13 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7579 | -120.8671 |  | TIER 2 | 586 | 15308-1110, PLACERVILLE | H40 | 21713 | Y | 311 |  |  | 2021-02-18 07:00 | 2021-02-18 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 47.1 | 47.1 |  |  | 40 | 0 |  |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101414358 | OH RELW PRI SERV TMAN COMP BTKA USA CPGG TER2 PROG ESTR | Pole | 2020-12-01 | 2020-12-04 | COMP | 2020-12-01 | COMP | 2021-02-18 | [13 empty] | 2021-02-19 | 2021-02-18 | 2021-02-10 |  | 2021-02-10 | B tag clean up 11/15/2020 |  | Auburn |  | 153081110 | 24404.33 | 5866.8 | 5445.6 | 1490 | 1490 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-11-15
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116686414 | POLE_BROK_REPL - 1P.FO.1851 UNION RIDGE | 35214240 |  |  | STS-POLE_BROK_REPL - 1P.FO.1851 UNION RI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7543 | -120.7645 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H4214 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 15.7 | 15.7 |  |  | 0 | 15.7 | 15.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101387296 | SEC OH RELW JAR FMOB TER2 PRTO SCPA SCOP | Pole | 2020-12-02 | 2021-01-19 | COMP | 2020-12-02 | [16 empty] | 2019-03-08 | 2020-03-08 |  | 2020-03-08 | Per DOT Approved Request 31416 |  | Auburn |  | 153082106 | 6360.13 | 223.4 | -765.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2021-01-28
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116720269 | POLE_DECA_REPL - A/F 498 CANAL ST PLACER | 35088704 |  |  | STS-POLE_DECA_REPL - A/F 498 CANAL ST PL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7328 | -120.8141 |  | TIER 2 | 322 | 15308-1112, PLACERVILLE | H4123 |  | Y | 311 | [5 empty] | Order Operation | [6 empty] | 81.2 | 81.2 |  |  | 0 | 81.2 | 81.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101385905 | RELW OH PRI JPOL PUBL ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-01-26 | COMP | 2020-12-01 |  |  | 2021-01-25 | 2021-01-26 | [12 empty] | 2019-03-13 | 2019-11-14 | 2024-03-11 | 2024-03-11 | 2021 CBP Plan | 2021-01-31 | TRC |  | 153081112 | 16917.07 | 299.1 | -1538.4 | -90.4 | -90.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116821692 | POLE_DECA_REPL - 2/E/O/1/N/0 4546 CHAPAR | 35188276 |  |  | STS-POLE_DECA_REPL - 2/E/O/1/N/0 4546 CH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6987 | -120.7199 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | I4320 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | [6 empty] | 20.1 | 20.1 |  |  | 0 | 20.1 | 20.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101398077 | OH PRI JPOL REMT NOAC GO FMOB TER2 PRTO RELW | Pole | 2020-09-11 | 2020-11-06 | COMP | 2020-09-10 | [16 empty] | 2019-03-24 | 2020-03-24 |  | 2020-03-24 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 8797.04 | 2869.2 | 714.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116948726 | POLE_DECA_REPL - 1S/O A/F 4026 WINTERHIL | 35147909 |  |  | STS-POLE_DECA_REPL - 1S/O A/F 4026 WINTE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.685 | -120.717 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J43 |  | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 26.1 | 26.1 |  |  | 0 | 26.1 | 26.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101404115 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-12-21 | 2021-02-04 | COMP | 2020-12-21 | [16 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153662102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116949028 | POLE_BROK_REPL - 2 W/O R/O 5461 MT AUKUM | 35187767 |  |  | STS-POLE_BROK_REPL - 2 W/O R/O 5461 MT A | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6567 | -120.6682 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J45 | 3297 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.8 | 28.8 |  |  | 0 | 28.8 | 28.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101397456 | RELW OH PRI JPOL RESD REMT ESTR REAR FMOB TER2 PRTO | Pole | 2020-10-05 | 2021-01-29 | COMP | 2020-10-05 | [16 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 18486.87 | 1867.6 | 187 | 187 | 187 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 116955797 | POLE_DECA_REPL - 1 S/O 4807 WOODLAND RD | 35187905 |  |  | STS-POLE_DECA_REPL - 1 S/O 4807 WOODLAND | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6993 | -120.7375 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | I43 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | [6 empty] | 33.1 | 33.1 |  |  | 0 | 33.1 | 33.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101397031 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-10-13 | 2020-12-05 | COMP | 2020-10-13 | [16 empty] | 2019-04-04 | 2020-04-04 |  | 2020-04-04 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 14430.77 | 666.8 | 666.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117003271 | POLE_BROK_REPL - 2/E/O 6068 SILVER RIDGE | 35188045 |  |  | STS-POLE_BROK_REPL - 2/E/O 6068 SILVER R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6664 | -120.6745 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J44 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.1 | 33.1 |  |  | 0 | 33.1 | 33.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101406435 | RELW CLR OH PRI JPOL REMT NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2020-11-20 | 2020-11-20 | COMP | 2020-09-28 | [16 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 25778.77 | 166.1 | 85.4 | 85.4 | 85.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117003961 | POLE_BROK_REPL - 1S/O 4081 NEWTOWN RD. P | 35160214 |  |  | STS-POLE_BROK_REPL - 1S/O 4081 NEWTOWN R | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7126 | -120.7129 |  | TIER 2 | 248 | 15366-1103, APPLE HILL | I44 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | [6 empty] | 30.1 | 30.1 |  |  | 0 | 30.1 | 30.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101401722 | RELW OH PRI JPOL FMOB REMT NOAC ESTR TER2 PRTO | Pole | 2020-10-08 | 2020-11-24 | COMP | 2020-10-01 | [16 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2020-10-31 | QUES |  | 153661103 | 16477.31 | 1565.5 | 1479.2 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117032369 | POLE_BROK_REPL - 2/N/O 4481 DOWN THE HIL | 35188620 |  |  | STS-POLE_BROK_REPL - 2/N/O 4481 DOWN THE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6887 | -120.7141 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | I43 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.4 | 23.4 |  |  | 0 | 23.4 | 23.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101418863 | RELW OH PRI CLR ESTR JPOL REMT BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-08 | 2021-01-19 | COMP | 2020-10-15 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 13479.46 | 3105.2 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117065535 | POLE_DECA_REPL - 4 S/O R/O 5605 BUCKS BA | 35188068 |  |  | STS-POLE_DECA_REPL - 4 S/O R/O 5605 BUCK | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6549 | -120.7025 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J44 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | [6 empty] | 22.1 | 22.1 |  |  | 0 | 22.1 | 22.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101418093 | RELW OH PRI CLR JPOL REMT NOAC ESTR GO FMOB TER2 PRTO | Pole | 2020-10-14 | 2020-12-06 | COMP | 2020-10-14 | [16 empty] | 2019-04-19 | 2020-04-19 |  | 2020-04-19 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 9199.4 | 1581.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117118381 | POLE_DECA_REPL - 4P W/O 4P S/O 5951 OAKH | 35188074 |  |  | STS-POLE_DECA_REPL - 4P W/O 4P S/O 5951 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6342 | -120.7902 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | K42 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | [6 empty] | 16.1 | 16.1 |  |  | 0 | 16.1 | 16.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101386769 | RELW OH PRI ESTR CLR JPOL RESD BTKA FMOB TER2 PRTO | Pole | 2020-10-16 | 2020-12-07 | COMP | 2020-10-15 | [16 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117121047 | POLE_DECA_REPL - 3P E/O 6260 ARCH LNPLAC | 35188199 |  |  | STS-POLE_DECA_REPL - 3P E/O 6260 ARCH LN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6356 | -120.7812 |  | TIER 2 | 106 | 15226-1106, DIAMOND SPRINGS | K42 | 5275 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | [6 empty] | 35.1 | 35.1 |  |  | 0 | 35.1 | 35.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101386590 | PRI RELW OH CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-12-06 | COMP | 2020-10-15 | [16 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | EEI |  | 152261106 | 15647.5 | 666.8 | 666.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117122130 | POLE_DECA_REPL - R/O 6680 MARY ANN LN.PL | 35188245 |  |  | STS-POLE_DECA_REPL - R/O 6680 MARY ANN L | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.626 | -120.7173 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | [6 empty] | 10.1 | 10.1 |  |  | 0 | 10.1 | 10.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101413416 | RELW OH SEC ESTR FMOB TER2 PRTO | Pole | 2020-10-16 | 2020-12-07 | COMP | 2020-10-15 | [16 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 6766.83 | 481.8 | 481.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117125366 | POLE_DECA_REPL - 1P S/O 3244 WILLOW GLEN | 35188306 |  |  | STS-POLE_DECA_REPL - 1P S/O 3244 WILLOW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6208 | -120.7577 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K42 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.2 | 18.2 |  |  | 0 | 18.2 | 18.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101386273 | RELW OH SERV JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-14 | 2020-12-05 | COMP | 2020-10-14 | [16 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117126009 | POLE_BROK_REPL - 3121 SAND RIDGE RDPLACE | 35188321 |  |  | STS-POLE_BROK_REPL - 3121 SAND RIDGE RDP | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.622 | -120.7579 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K42 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18 | 18 |  |  | 0 | 18 | 18 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103664842 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-14 | 2021-01-08 | COMP | 2020-10-14 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 9285.79 | 149.5 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117132599 | POLE_BROK_REPL - 1S/O 3461 ALMOSTA RD. P | 35188461 |  |  | STS-POLE_BROK_REPL - 1S/O 3461 ALMOSTA R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6199 | -120.7511 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 | 21305 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 54.6 | 50.8 | 3.8 |  | 0 | 54.6 | 50.8 | 3.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101400347 | RELW OH PRI REMT SWRK ESTR FMOB TER2 PRTO | Pole | 2020-10-13 | 2021-01-04 | COMP | 2020-10-13 | [16 empty] | 2019-05-01 | 2020-05-01 |  | 2020-05-01 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | Placerville | Placerville |  |  | OPEN | 117172785 | POLE_BROK_REPL - 2S/O HOUSE 2040 HWY 49 | 35069588 |  |  | 2S/O HOUSE 2040 HWY 49 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7549 | -120.8244 |  | TIER 2 | 586 | 15308-1110, PLACERVILLE | H41 | 21689 | Y | 311 |  |  |  |  | Returned | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 43.5 | 43.5 |  |  | 0 | 43.5 | 43.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101388331 | POHW OH PRI JPOL ESTR BTKA OTHR TER2 | Pole | 2019-07-15 | 2021-01-21 | COMP | 2019-07-13 |  |  | 2019-06-04 | 2019-06-04 | [12 empty] | 2018-12-26 | 2019-12-26 |  | 2019-12-26 | Q1 Work Plan | 2019-09-02 | CALENG |  | 153081110 | 23278.6 | 6080.4 | 128.3 | 93.5 | 93.5 | 6871.6 |  | 6871.6 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117228752 | POLE_BROK_REPL - 1PLN 7090 STEWART MINE | 35135359 |  |  | 8 POLES-POLE_BROK_REPL-1PLN 7090 STEWART | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7805 | -120.8371 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 206 | 206 |  |  | 0 | 206 | 206 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101388009 | RELW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-11-09 | 2021-01-02 | COMP | 2020-11-09 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 113369.47 | 451.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117228754 | POLE_BROK_REPL - 1PLS 7025 STEWART MINE | 35135359 |  |  | 8 POLES-POLE_BROK_REPL-1PLN 7090 STEWART | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7817 | -120.8368 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101413779 | REGW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-11-09 | 2021-01-02 | COMP | 2020-11-09 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 113369.47 | 451.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117232995 | POLE_BROK_REPL - 7571 TEXAS CANYON RD PL | 35172449 |  |  | STS-POLE_BROK_REPL - 7571 TEXAS CANYON R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7834 | -120.8229 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.2 | 23.2 |  |  | 0 | 23.2 | 23.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101383547 | OH PRI CLR RESD FIRE ESTR FMOB TER2 PRTO RELW | Pole | 2020-12-02 | 2021-01-21 | COMP | 2020-12-02 | [16 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2021-01-31 | TRC |  | 153082106 | 13171.56 |  | -1928 | -1566 | -1566 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117267377 | POLE_BROK_REPL - 1PLN 6790 STEWART MINE | 35135359 |  |  | 8 POLES-POLE_BROK_REPL-1PLN 7090 STEWART | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.788 | -120.8369 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G40 | 1443 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101387987 | REGW OH PRI RESD FIRE ESTR FMOB TER2 PRTO | Pole | 2020-11-09 | 2021-01-02 | COMP | 2020-11-09 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 113369.47 | 451.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117267378 | POLE_BROK_REPL - 1PLS 6560 STEWART MINE | 35135359 |  |  | 8 POLES-POLE_BROK_REPL-1PLN 7090 STEWART | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7947 | -120.8392 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101387853 | REGW OH PRI RESD FIRE ESTR FMOB PRTO TER2 | Pole | 2020-11-09 | 2021-01-02 | COMP | 2020-11-09 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-17 | 2020-05-17 |  | 2020-05-17 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 113369.47 | 451.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117305771 | POLE_BROK_REPL - 2485 KINGSGATE RD PLACE | 35137499 |  |  | STS-POLE_BROK_REPL - 2485 KINGSGATE RD P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7494 | -120.7692 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | H42 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.6 | 13.6 |  |  | 0 | 13.6 | 13.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103667466 | RELW OH SERV CLR JPOL REMT ESTR REAR FMOB TER2 PRTO | Pole | 2021-01-07 | 2021-01-07 | COMP | 2021-01-07 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-23 | 2020-05-23 |  | 2020-05-23 | 2021 CBP Plan | 2021-01-31 | W. Sac |  | 153082106 | 7245.52 | 6322.7 | 1350.3 | 1350.3 | 1350.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117325222 | POLE_DECA_REPL - 6680 STEWART MINE RD PL | 35135359 |  |  | 8 POLES-POLE_BROK_REPL-1PLN 7090 STEWART | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7909 | -120.8388 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101387964 | REGW OH PRI JPOL REMT SWRK ESTR BTKA FMOB TER2 PRTO | Pole | 2020-11-09 | 2021-01-02 | COMP | 2020-11-09 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-27 | 2020-05-27 |  | 2020-05-27 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 113369.47 | 451.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117325259 | POLE_DECA_REPL - 1PLW 6680 STEWART MINE | 35135359 |  |  | 8 POLES-POLE_BROK_REPL-1PLN 7090 STEWART | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7908 | -120.8392 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101413770 | REGW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-11-09 | 2021-01-02 | COMP | 2020-11-09 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-27 | 2020-05-27 |  | 2020-05-27 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 113369.47 | 451.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117325322 | POLE_DECA_REPL - 6621 STEWART MINE RD PL | 35135359 |  |  | 8 POLES-POLE_BROK_REPL-1PLN 7090 STEWART | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7933 | -120.8383 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G40 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101387961 | RELW OH PRI JPOL REMT FMOB ESTR BTKA TER2 PRTO | Pole | 2020-11-09 | 2021-01-02 | COMP | 2020-11-09 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-27 | 2020-05-27 |  | 2020-05-27 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 113369.47 | 451.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 117328101 | POLE_BROK_REPL - 2PLE 6546 STEWART MINE | 35135359 |  |  | 8 POLES-POLE_BROK_REPL-1PLN 7090 STEWART | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7982 | -120.8385 |  | TIER 2 | 10 | 15308-2106, PLACERVILLE | G40 | 1443 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101387846 | REGW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-11-09 | 2021-01-02 | COMP | 2020-11-09 |  |  | 2019-12-02 | 2019-12-02 | [12 empty] | 2019-05-28 | 2020-05-28 |  | 2020-05-28 | 2021 CBP Plan | 2020-08-31 | W. Sac |  | 153082106 | 113369.47 | 451.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | Placerville | Placerville |  |  | OPEN | 117771489 | REPL POLE:#1 ON LINE W/O 3451 MINING BRO | 35160316 |  |  | STS-REPL POLE:#1 ON LINE W/O 3451 MINING | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7257 | -120.7344 |  | TIER 2 | 248 | 15366-1103, APPLE HILL | I4303 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.2 | 28.2 |  |  | 0 | 28.2 | 28.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101397942 | RELW TNT OH JPOL TER2 FSRP | Pole | 2020-11-30 | 2021-01-21 | COMP | 2020-11-30 | [16 empty] | 2019-07-12 | 2020-07-12 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2020-12-31 | QUES |  | 153661103 | 15025.37 | 1777.3 | 699.3 | -362 | -362 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 119774990 | POLE_BROK_REPL - R/O 3452 FORT JIM PLACE | 35202113 |  |  | B2 STS-POLE_BROK_REPL - R/O 3452 FORT JI | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7022 | -120.708 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | I44 | 22417 | Y | 311 |  |  | 2021-03-12 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | [6 empty] | 47.1 | 47.1 |  |  | 25.25 | 27 | 27 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101401052 | RELW OH ESTR TER2 | Pole | 2020-10-27 | 2020-10-29 | COMP | 2020-10-19 | [16 empty] | 2020-09-03 | 2020-11-03 |  | 2020-11-03 | B tag clean up 9/26/2020 |  | Auburn |  | 153662102 | 31933.45 | 15382 | 271.5 | 176.3 | 176.3 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-09-26
North | SI | PLACERVILLE | Placerville |  |  | OPEN | 120095980 | POLE_BROK_REPL - 2E/O 3151 WILTSE RD PLA | 35217539 |  |  | B3 STS-POLE_BROK_REPL - 2E/O 3151 WILTSE | CONS | CONS SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7288 | -120.775 |  | TIER 2 | 721 | 15308-1109, PLACERVILLE | I4203 | 284071 | Y | 311 |  |  | 2021-02-25 07:00 | 2021-02-25 16:00 | Dispatched | CLICK | [6 empty] | 63.1 | 63.1 |  |  | 1.5 | 63 | 63 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101405202 | RELW OH ESTR TER2 | Pole | 2020-12-17 | 2020-12-22 | COMP | 2020-12-17 | [16 empty] | 2020-11-12 | 2021-02-12 |  | 2021-02-12 | B tag clean up 11/30/2020 |  | Auburn |  | 153081109 | 34818.65 | 4116.2 | 3491.7 | [5 empty] | Electric Distribution | N | Pulled from MPP Import File | N |  | Y | 2020-11-30
North | SI | POLLOCK PINES | Placerville |  |  | OPEN | 116985238 | POLE_BURN_REPL - 2NE/O SSD C/0 2441 LOT | 35144189 |  |  | STS-POLE_BURN_REPL - 2NE/O SSD C/0 2441 | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.7633 | -120.3329 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | H53 | 8637 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.2 | 37.2 |  |  | 0 | 37.2 | 37.2 |  |  | EC | E | Pole | Burnt | Replace |  | 101398139 | RELW OH PRI CLR JPOL REMT NOAC ESTR PROG FMOB TER2 PRTO | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2021-01-31 | Auburn |  | 152762101 | 34688.15 | 2356.1 |  |  |  | 781.3 |  | 781.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | POLLOCK PINES | Placerville |  |  | OPEN | 116986910 | POLE_DECA_REPL - HWY 50 @ 30 MILE TRACT | 35144190 |  |  | STS-POLE_DECA_REPL - HWY 50 @ 30 MILE TR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.7645 | -120.3383 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | H53 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103034858 | RELW OH SEC CLR JPOL REMT NOAC ESTR GO REAR FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2021-01-31 | Auburn |  | 152762101 | 1 | 3821.3 |  |  |  | 3387 |  | 3387 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | POLLOCK PINES | Placerville |  |  | OPEN | 117251545 | POLE_BROK_REPL - #4 ON LINE W/O MM 43.50 | 35144269 |  |  | STS-POLE_BROK_REPL - #4 ON LINE W/O MM 4 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.7737 | -120.3892 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G52 | 52456 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101402202 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | 2021 CBP Plan | 2021-01-31 | Auburn |  | 152762101 | 1 | 2412.4 |  |  |  | 1207.5 |  | 1207.5 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | POLLOCK PINES | Placerville |  |  | COMP | 117023781 | POLE_BROK_REPL - 1S/O 21 ALDER CR.RD. PO | 35144194 |  |  | STS-POLE_BROK_REPL - 1S/O 21 ALDER CR.RD | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7649 | -120.3779 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | H52 | 2435 | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 44.6 | 44.6 |  |  | 0 | 44.6 | 44.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101398095 | RELW OH PRI COMP REMT NOAC ESTR REAR CCNT FMOB TER2 PRTO | Pole | 2020-02-28 | 2020-05-14 | COMP | 2020-02-28 | COMP | 2021-02-09 | [13 empty] | 2021-02-12 | 2021-02-09 | 2020-04-13 |  | 2020-04-13 | circuit based plan 2.14 | 2020-04-13 | Auburn |  | 152762101 | 28241.47 | 9147.7 | 1566.9 |  |  | 383.5 |  | 383.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | POLLOCK PINES | Placerville |  |  | OPEN | 117006478 | POLE_BROK_REPL - 1E/O LOT 43 30 MILE TRA | 35143875 |  |  | STS-POLE_BROK_REPL - 1E/O LOT 43 30 MILE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7631 | -120.3348 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | H53 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.7 | 44.7 |  |  | 0 | 44.7 | 44.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101398138 | RELW OH PRI REMT NOAC ESTR GO REAR FMOB TER2 PRTO | Pole | 2020-09-08 | 2020-11-07 | COMP | 2020-09-08 | [16 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2020-06-30 | Auburn |  | 152762101 | 33754.92 | 3101.4 |  |  |  | 125.6 |  | 125.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | POLLOCK PINES | Placerville |  |  | OPEN | 117031566 | POLE_DECA_REPL - 11W/O 10121 HWY 50.POLL | 35116106 |  |  | STS-POLE_DECA_REPL - 11W/O 10121 HWY 50. | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7703 | -120.4454 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | H50 |  | Y | 311 |  |  | 2019-11-12 | 2019-11-12 | Completed | Order Operation | [6 empty] | 69.2 | 67.9 | 1.3 |  | 0 | 69.2 | 67.9 | 1.3 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101419646 | RELW OH SERV CLR JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2019-09-12 | 2020-12-22 | COMP | 2019-09-11 |  |  | 2019-09-24 | 2019-09-24 | [12 empty] | 2019-04-15 | 2020-04-15 |  | 2020-04-15 | Q1 Work Plan |  | Fresno |  | 152762101 | 18775.38 | 90315.9 | 1281 | 6281 | 6281 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | POLLOCK PINES | Placerville |  |  | OPEN | 117227726 | POLE_BROK_REPL - #3 ON LINE W/O 3021 RIV | 35116124 |  |  | STS-POLE_BROK_REPL - #3 ON LINE W/O 3021 | CONS | CONS ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7754 | -120.406 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G51 |  | Y | 311 |  |  | 2021-02-02 | 2021-02-02 | Dispatched | Order Operation | [6 empty] | 43.5 | 43.5 |  |  | 0 | 43.5 | 43.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101402107 | RELW OH SEC JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2019-08-27 | 2019-09-12 | COMP | 2019-08-27 |  |  | 2019-09-24 | 2019-09-24 | [12 empty] | 2019-05-13 | 2020-05-13 |  | 2020-05-13 | Q1 Work Plan |  | Fresno |  | 152762101 | 14532.33 | 14853.7 | 2037 |  |  | 3976.5 |  | 3976.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | POLLOCK PINES | Placerville |  |  | OPEN | 117250408 | POLE_BROK_REPL - 10960 HWY 50 POLLOCK PI | 35143990 |  |  | STS-POLE_BROK_REPL - 10960 HWY 50 POLLOC | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7745 | -120.4008 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G5124 |  | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101402120 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-02-21 | 2020-06-16 | COMP | 2020-02-21 |  |  | 2020-02-25 | 2020-02-25 | [12 empty] | 2019-05-16 | 2020-05-16 | 2021-06-23 | 2021-06-23 | circuit based plan 2.14 | 2020-05-16 | Auburn |  | 152762101 | 13571.17 | 6722 |  |  |  | 898.2 |  | 898.2 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | POLLOCK PINES | Placerville |  |  | OPEN | 117250508 | POLE_BROK_REPL - 10946 HWY 50 W/T POLLOC | 35143992 |  |  | STS-POLE_BROK_REPL - 10946 HWY 50 W/T PO | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.774 | -120.4013 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | G5124 | 2461 | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 42.8 | 42.8 |  |  | 10 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101402121 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-04-11 | 2020-07-09 | COMP | 2020-04-11 |  |  | 2020-07-09 | 2020-07-09 | [12 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | circuit based plan 2.14 | 2020-05-31 | Auburn |  | 152762101 | 25310.3 | 9317.9 | 60 |  |  | 683.3 |  | 683.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | POLLOCK PINES | Placerville |  |  | OPEN | 117014857 | POLE_DECA_REPL - LOT 27 30MILE TRACT POL | 35144191 |  |  | STS-POLE_DECA_REPL - LOT 27 30MILE TRACT | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.764 | -120.341 |  | TIER 2 | 6 | 15276-2101, EL DORADO PH | H53 | 8637 | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 76.1 | 76.1 |  |  | 0 | 76.1 | 76.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101398130 | RELW OH SEC CLR JPOL REMT NOAC ESTR GO FMOB TER2 PRTO | Pole | 2020-12-17 | 2021-02-08 | COMP | 2020-12-17 | [16 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | 2021 CBP Plan | 2021-01-31 | Auburn |  | 152762101 | 53674.65 | 6486.8 |  |  |  | 6386.8 |  | 6386.8 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | RESCUE | Placerville |  |  | OPEN | 110399634 | POLE_BROK_REPL - 2425 CLARKSVILLE RD RES | 35219177 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.7 | -121.0389 |  | TIER 2 | 133 | 15361-2104, CLARKSVILLE | I3520 | 11499 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | F | Pole | Broken/Damaged | Replace |  | 101375173 | RELW OH PRI INSP RESD TRAF ESTR GO BTKA TER2 USA | Pole |  |  | REQD | [17 empty] | 2015-05-06 | 2020-05-06 |  | 2020-05-06 | Per DOT Approved Request 31427 | 2021-02-28 | Auburn |  | 153612104 | [9 empty] | Y | MPP File Only | N |  | Y | 2021-01-28
North | SI | RESCUE | Placerville |  |  | OPEN | 116628507 | POLE_DECA_REPL - C/O GREENSPINGS CT AND | 35233973 |  |  | STS-POLE_DECA_REPL - C/O GREENSPINGS CT | ESTS | ESTS ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.6984 | -121.0459 |  | TIER 2 | 133 | 15361-2104, CLARKSVILLE | I3519 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101377269 | RELW OH PRI JPOL RESD JAR BTKA FMOB PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-03-03 | 2020-03-03 |  | 2020-03-03 | Per DOT Approved Request 31440 |  | UNASSIGNED |  | 153612104 | [9 empty] | N | MPP File Only | N |  | Y | 2021-01-28
North | SI | Rescue | Placerville |  |  | OPEN | 117771508 | REPL POLE:DEER VALLEY/GREEN VALLEY RD,Re | 35189355 |  |  | STS-REPL POLE:DEER VALLEY/GREEN VALLEY R | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.7009 | -121.0283 |  | TIER 2 | 133 | 15361-2104, CLARKSVILLE | I3617 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 18.3 | 18.3 |  |  | 0 | 18.3 | 18.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101382187 | RELW OH TNT JPOL TER2 | Pole | 2020-09-24 |  | COMP | 2020-09-24 | [16 empty] | 2019-06-04 | 2020-06-04 |  | 2020-06-04 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153612104 | 10916.52 | 42.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | RESCUE | Placerville |  |  | OPEN | 117771893 | POLE_DECA_REPL - #2 ON LINE NE/O 2748 BA | 35160317 |  |  | STS-REPL POLE:#2 ON LINE NE/O 2748 BASS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 38.686 | -121.0123 |  | TIER 2 | 133 | 15361-2104, CLARKSVILLE | J3603 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101380143 | TNT OH RELW JPOL TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-17 | 2020-06-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | QUES |  | 153612104 | 1 | 749.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | Rescue | Placerville |  |  | OPEN | 117771755 | REPL POLE:,Rescue | 35189393 |  |  | STS-REPL POLE:,RESCUE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7053 | -121.0377 |  | TIER 2 | 133 | 15361-2104, CLARKSVILLE | I3520 |  | Y | 311 |  |  | 2021-03-06 07:00 | 2021-03-06 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103667354 | OH RELW TNT TER2 | Pole | 2020-10-15 | 2020-10-15 | COMP | 2020-10-15 | [16 empty] | 2019-06-05 | 2020-06-05 |  | 2020-06-05 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153612104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | Rescue | Placerville |  |  | OPEN | 117771509 | REPL POLE:AC/F 2321 GREEN VALLEY RD,Resc | 35189358 |  |  | STS-REPL POLE:AC/F 2321 GREEN VALLEY RD, | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6999 | -121.0267 |  | TIER 2 | 133 | 15361-2104, CLARKSVILLE | I3617 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | [6 empty] | 18.1 | 18.1 |  |  | 0 | 18.1 | 18.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101382189 | RELW OH TNT JPOL TER2 | Pole | 2020-10-02 | 2020-12-05 | COMP | 2020-10-02 |  |  | 2020-09-04 | 2020-09-04 | [12 empty] | 2019-06-04 | 2020-06-04 |  | 2020-06-04 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153612104 | 10790.18 | 85.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | ROUGH AND READY | Grass Valley |  |  | OPEN | 116826448 | POLE_DECA_REPL - A/F 16505 GLEKO RD ROUG | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-31 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 39.2147 | -121.1633 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0609 |  | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100081832 | REGW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-03-25 | 2020-03-25 |  | 2020-03-25 | Per DOT Approved Request 50352 |  | UNASSIGNED |  | 153132105 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | SI | ROUGH AND READY | Grass Valley |  |  | OPEN | 116842251 | POLE_BROK_REPL - 1W/O 10300 MATAS WECKS | 35208638 |  |  | STS-POLE_BROK_REPL - 1W/O 10300 MATAS WE | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.2135 | -121.1554 |  | TIER 2 | 109 | 15313-2105, NARROWS | N06 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100086072 | OH SEC JPOL REMT JAR BTKA FMOB TER2 PRTO SCPA RELW SCOP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 |  | 2020-03-26 | Per DOT Approved Request 31426 |  | Auburn |  | 153132105 | 1 | 7441.1 | [7 empty] | N | MPP File Only | N |  | Y | 2021-01-28
North | SI | ROUGH AND READY | Grass Valley |  |  | OPEN | 116876275 | POLE_DECA_REPL - 2S/O R/O 14851 ROUNGH A | 35188627 |  |  | STS-POLE_DECA_REPL - 2S/O R/O 14851 ROUN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.2247 | -121.1406 |  | TIER 2 | 109 | 15313-2105, NARROWS | N07 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38 | 38 |  |  | 0 | 38 | 38 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100072120 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-10-05 |  | COMP | 2020-10-05 | [16 empty] | 2019-03-31 | 2020-03-31 |  | 2020-03-31 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 31488.26 | 1380 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | ROUGH AND READY | Grass Valley |  |  | OPEN | 117162218 | POLE_BROK_REPL - R/O 13414 ROUNGH AND RE | 35163547 |  |  | STS-POLE_BROK_REPL - R/O 13414 ROUNGH AN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.2332 | -121.1208 |  | TIER 2 | 109 | 15313-2105, NARROWS | M0724 | 1051 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100007938 | RELW OH PRI INSP CLR JPOL RESD ESTR GO REAR USA FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-09-30 | TRC |  | 153132105 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | ROUGH AND READY | Grass Valley |  |  | OPEN | 117319429 | POLE_BROK_REPL - 1N/O 12937 ROUGH AND RE | 35229031 |  |  | STS-POLE_BROK_REPL - 1N/O 12937 ROUGH AN | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.2349 | -121.1787 |  | TIER 2 | 109 | 15313-2105, NARROWS | M0622 | 2750 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100107319 | OH SERV JPOL REMT JAR BTKA OTRG FMOB TER2 PRTO RELW | Pole |  |  | REQD | [17 empty] | 2019-05-24 | 2020-05-24 |  | 2020-05-24 | Per DOT Approved Request 31439 | 2021-02-28 | UNASSIGNED |  | 153132105 | [9 empty] | N | MPP File Only | N |  | Y | 2021-01-28
North | SI | ROUGH AND READY | Grass Valley |  |  | OPEN | 117321040 | POLE_BROK_REPL - 1E/O 15595 BRANDT LN RO | 35229030 |  |  | STS-POLE_BROK_REPL - 1E/O 15595 BRANDT L | ESTS | ESTS | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-30 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.231 | -121.1521 |  | TIER 2 | 109 | 15313-2105, NARROWS | M0625 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100008426 | RELW OH PRI CLR GO FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-25 | 2020-05-25 |  | 2020-05-25 | Per DOT Approved Request 31438 | 2021-02-28 | UNASSIGNED |  | 153132105 | [9 empty] | N | MPP File Only | N |  | Y | 2021-01-28
North | SI | ROUGH AND READY | Grass Valley |  |  | OPEN | 116834421 | POLE_BROK_REPL - 2E/O A/F 16775 PIONEER | 35188408 |  |  | STS-POLE_BROK_REPL - 2E/O A/F 16775 PION | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2108 | -121.165 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0609 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 20.1 | 20.1 |  |  | 0 | 20.1 | 20.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100081777 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-12 | 2021-01-20 | COMP | 2020-10-12 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-03-26 | 2020-03-26 |  | 2020-03-26 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 12121.89 | 1672.1 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | ROUGH AND READY | Grass Valley |  |  | OPEN | 115545752 | POLE_DECA_REPL - 16351 HILLAIRE RD ROUGH | 35074151 |  |  | STS-POLE_DECA_REPL - 16351 HILLAIRE RD R | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2282 | -121.1615 |  | TIER 2 | 109 | 15313-2105, NARROWS | M0624 | 4409 | Y | 311 |  |  | 2021-02-19 07:00 | 2021-02-19 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 22.9 | 22.9 |  |  | 0 | 22.9 | 22.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100008282 | RELW OH PRI CLR JPOL REMT FLAG ESTR BTKA OTHR USA TER2 | Pole | 2020-03-27 | 2020-05-18 | COMP | 2020-03-27 | [16 empty] | 2018-12-11 | 2019-12-11 |  | 2019-12-11 | Q1 Work Plan | 2020-06-30 | Bakersfield |  | 153132105 | 10617.01 | 2016.1 | 2016.1 | 1494.1 | 1494.1 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | ROUGH AND READY | Grass Valley |  |  | OPEN | 117303997 | POLE_BROK_REPL - 10396 BONANZA WAY ROUGH | 35163708 |  |  | STS-POLE_BROK_REPL - 10396 BONANZA WAY R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2358 | -121.133 |  | TIER 2 | 109 | 15313-2105, NARROWS | M0718 | 7291 | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 33 | 33 |  |  | 0.5 | 32.5 | 32.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103814579 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-14 | 2021-02-10 | COMP | 2020-08-10 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-05-22 | 2020-05-22 |  | 2020-05-22 | 2021 CBP Plan | 2020-09-30 | TRC |  | 153132105 | 21341.94 | 1021.6 | 111.2 | 111.2 | 111.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | ROUGH AND READY | Grass Valley |  |  | OPEN | 117456932 | POLE_BURN_REPL - A/F 11285 PROSPECTOR RD | 35113628 |  |  | STS-POLE_BURN_REPL - A/F 11285 PROSPECTO | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2373 | -121.1543 |  | TIER 2 | 109 | 15313-2105, NARROWS | M0620 | 7609 | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 31.8 | 31.8 |  |  | 0 | 31.8 | 31.8 |  |  | EC | E | Pole | Burnt | Replace |  | 100006959 | RELW OH PRI INSP CLR JPOL REMT FLAG ESTR BTKA FMOB TER2 | Pole | 2019-08-18 | 2020-07-28 | COMP | 2019-08-18 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2019-06-17 | 2019-12-17 |  | 2019-12-17 | Q1 Work Plan |  | W. Sac |  | 153132105 | 17989.55 | 4676.7 | 4676.7 | 4725.7 | 4725.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SHINGLE SPRINGS | Placerville |  |  | OPEN | 115095081 | POLE_BROK_REPL - 6581 Mitchell RdShingle | 35069751 |  |  | STS-POLE_BROK_REPL - 6581 MITCHELL RDSHI | DOCC | DOCC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 |  | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.5845 | -120.9772 |  | TIER 2 | 527 | 15361-2103, CLARKSVILLE | L3708 | 12849 | Y | 311 |  |  | 2020-02-06 | 2020-02-06 | Completed | Order Operation | [6 empty] | 29.1 | 27.9 | 1.2 |  | 0 | 29.1 | 27.9 | 1.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101377396 | REGW OH PRI INSP CLR JPOL REMT TRAF FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole | 2019-02-07 | 2019-05-02 | COMP | 2019-02-07 | COMP | 2020-02-06 | [14 empty] | 2018-10-27 | 2019-10-27 | 2021-05-31 | 2021-05-31 | Q1 Work Plan |  | UNASSIGNED |  | 153612103 | 13201.46 | 43665.4 |  |  |  | 1369.5 |  | 1369.5 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117243616 | POLE_DECA_REPL - 2SW/O 3NW/O 117 WILD PL | 35133728 |  |  | STS-POLE_DECA_REPL - 2SW/O 3NW/O 117 WIL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 39.5692 | -120.6217 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1910 | 827 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100093858 | RELW OH PRI PGEA CLR RESD REMT FIRE ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-08-04 | 2020-07-28 | COMP | 2020-01-22 | [16 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | 2021 CBP Plan | 2020-01-09 | PIKEENG |  | 152101101 | 27320.42 | 43.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | SIERRA CITY | Grass Valley |  |  | COMP | 117129070 | POLE_BROK_REPL - 35 SIERRA BUTTES RD SIE | 35133558 |  |  | STS-POLE_BROK_REPL - 35 SIERRA BUTTES RD | MAPP | MAPP SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-11-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.5661 | -120.641 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1908 | 7905 | Y | 311 |  |  | 2021-01-07 | 2021-01-07 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 321.8 | 321.8 |  |  | 0 | 40.8 | 40.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100094696 | RELW OH PRI SERV CREW COMP CLR JPOL REMT ESTR BTKA USA CCNT TER2 | Pole | 2020-05-27 | 2020-07-23 | COMP | 2020-05-27 | COMP | 2021-01-07 | [13 empty] | 2021-01-22 | 2021-01-07 | 2020-04-16 |  | 2020-04-16 | circuit based plan 2.14 | 2020-05-31 | PIKEENG |  | 152101101 | 23995.12 | 25819.2 | 19658.6 | 19658.6 | 19658.6 | 386.8 |  | 386.8 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | COMP | 117243633 | POLE_DECA_REPL - 1S/O 2SW/O 3NW/O 117 WI | 35133732 |  |  | STS-POLE_DECA_REPL - 1S/O 2SW/O 3NW/O 11 | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.5686 | -120.6217 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1910 |  | Y | 311 |  |  | 2021-01-11 | 2021-01-11 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 42.7 | 42.7 |  |  | 5 | 1.7 | 1.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100093862 | RELW OH SEC PGEA COMP RESD REMT FIRE ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-02-12 | 2020-03-04 | COMP | 2020-02-11 | COMP | 2021-01-11 | [13 empty] | 2021-02-01 | 2021-01-11 | 2020-05-15 |  | 2020-05-15 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 8469.1 | 11078.6 | 3568.5 | 3568.5 | 3568.5 | 479.7 |  | 479.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | COMP | 117243666 | POLE_DECA_REPL - 118 WILD PLUM RD SIERRA | 35133742 |  |  | STS-POLE_DECA_REPL - 118 WILD PLUM RD SI | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-07-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2020-12-31 | No Action | 39.5685 | -120.6193 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1910 |  | Y | 311 |  |  | 2021-01-11 | 2021-01-11 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100093883 | RELW OH SERV COMP JPOL RESD REMT FIRE ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-01-17 | 2020-02-10 | COMP | 2020-01-17 | COMP | 2021-01-11 | 2020-01-10 | 2020-01-10 | [11 empty] | 2021-01-29 | 2021-01-11 | 2020-05-15 |  | 2020-05-15 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 10549.07 | 11487.8 | 2616.1 | 2616.1 | 2616.1 | 135.2 |  | 135.2 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | COMP | 117246028 | POLE_DECA_REPL - 200FT NORTH OF INSECTIO | 35133745 |  |  | STS-POLE_DECA_REPL - 200FT NORTH OF INSE | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2020-12-31 | No Action | 39.5678 | -120.6282 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1909 |  | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0.5 | 40.5 | 40.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103672955 | RELW OH SERV COMP RESD TRAF FLAG ESTR GO BTKA CCNT FMOB TER2 PRTO | Pole | 2019-12-31 | 2020-01-22 | COMP | 2019-12-30 | COMP | 2021-02-09 | 2019-12-11 | 2019-12-11 | [11 empty] | 2021-02-17 | 2021-02-09 | 2020-05-15 |  | 2020-05-15 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 5735.79 | 13397.8 | 1702.7 |  |  | 364.9 |  | 364.9 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | COMP | 117250176 | POLE_DECA_REPL - 1NE/O 119 MAIN ST SIERR | 35133757 |  |  | STS-POLE_DECA_REPL - 1NE/O 119 MAIN ST S | DOCC | DOCC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.5636 | -120.641 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1908 |  | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 43.7 | 43.5 | 0.2 |  | 3 | 42.7 | 42.5 | 0.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100090816 | RELW OH PRI COMP CLR JPOL RESD REMT FIRE FLAG ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-07-15 | 2020-07-23 | COMP | 2020-02-11 | COMP | 2021-02-09 | 2020-06-29 | 2020-06-29 | [11 empty] | 2021-02-17 | 2021-02-09 | 2020-05-16 |  | 2020-05-16 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 15586.34 | 6744.6 | 2408.4 | 273 | 273 | 292.5 |  | 292.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | COMP | 117267505 | POLE_BROK_REPL - 1NW/O AF 17 CEMENTERY R | 35133782 |  |  | STS-POLE_BROK_REPL - 1NW/O AF 17 CEMENTE | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.5655 | -120.6406 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1908 |  | Y | 311 |  |  | 2021-01-23 | 2021-01-23 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 42.7 | 42.7 |  |  | 0 | 1.7 | 1.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100094694 | RELW OH PRI COMP CLR JPOL RESD REMT FIRE NOAC ESTR CCNT FMOB TER2 PRTO | Pole | 2020-04-23 | 2020-06-22 | COMP | 2020-04-23 | COMP | 2021-01-23 | [13 empty] | 2021-02-01 | 2021-01-23 | 2020-05-17 |  | 2020-05-17 | circuit based plan 2.14 | 2020-02-28 | PIKEENG |  | 152101101 | 12188.77 | 19950.1 | 15925.5 | 2126.6 | 2126.6 | 974.7 |  | 974.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | COMP | 117270917 | POLE_DECA_REPL - R/O 114 BUTTER ST SIERR | 35133777 |  |  | STS-POLE_DECA_REPL - R/O 114 BUTTER ST S | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-07-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.5665 | -120.6353 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1908 |  | Y | 311 |  |  | 2021-01-09 | 2021-01-09 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 2.5 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100090844 | RELW OH SERV PGEA COMP RESD REMT FIRE NOAC ESTR CCNT FMOB TER2 PRTO | Pole | 2020-01-15 | 2020-02-10 | COMP | 2020-01-15 | COMP | 2021-01-09 | [13 empty] | 2021-01-25 | 2021-01-09 | 2020-05-18 |  | 2020-05-18 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 8591.1 | 32221.2 | 1730.8 | 1730.8 | 1730.8 | 167.2 |  | 167.2 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | COMP | 117270923 | POLE_DECA_REPL - HWY 49 ANDWILD PLUM DR | 35133783 |  |  | STS-POLE_DECA_REPL - HWY 49 ANDWILD PLUM | DOCC | DOCC SRDY IDOC | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2020-12-31 | No Action | 39.5683 | -120.627 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1909 |  | Y | 311 |  |  | 2021-01-14 | 2021-01-14 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0 | 1 | 1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103672957 | RELW OH SERV COMP JPOL RESD REMT FIRE FLAG ESTR GO BTKA CCNT FMOB TER2 PRTO | Pole | 2020-02-05 | 2020-04-15 | COMP | 2020-02-05 | COMP | 2021-01-14 | 2020-04-15 | 2020-04-15 | [11 empty] | 2021-01-25 | 2021-01-14 | 2020-05-18 |  | 2020-05-18 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 11457.27 | 36889.3 | 31647.1 | 3782.1 | 3782.1 | 195.3 |  | 195.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | COMP | 117279932 | POLE_DECA_REPL - 319 OSTROM WAY RD SIERR | 35133811 |  |  | STS-POLE_DECA_REPL - 319 OSTROM WAY RD S | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.5712 | -120.6155 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F2001 | 1731 | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 10.25 | 40.8 | 40.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100105481 | OH RELW PRI COMP CLR JPOL RESD REMT FIRE FLAG ESTR GO BTKA CCNT FMOB TER2 PRTO | Pole | 2020-01-17 | 2020-06-29 | COMP | 2020-01-17 | COMP | 2021-01-13 | 2020-06-29 | 2020-06-29 | [11 empty] | 2021-01-21 | 2021-01-13 | 2020-05-20 |  | 2020-05-20 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 19755.89 | 6342.1 | 847.2 | 519.7 | 519.7 | 62.8 |  | 62.8 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | COMP | 117279940 | POLE_DECA_REPL - R/O 129 WILD PLUM RD SI | 35133816 |  |  | STS-POLE_DECA_REPL - R/O 129 WILD PLUM R | MAPP | MAPP SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-11-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.5692 | -120.6165 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1910 |  | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 1.8 | 1.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100093903 | RELW OH PRI COMP CLR JPOL RESD REMT FIRE ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-03-25 | 2020-05-21 | COMP | 2020-03-25 | COMP | 2021-01-06 | [13 empty] | 2021-01-12 | 2021-01-06 | 2020-05-20 |  | 2020-05-20 | circuit based plan 2.14 | 2020-06-30 | PIKEENG |  | 152101101 | 4528.75 | 29180.4 | 21273.2 | 3829 | 3829 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | COMP | 117279941 | POLE_DECA_REPL - #1N 129 WILD PLUM RDSIE | 35133817 |  |  | STS-POLE_DECA_REPL - #1N 129 WILD PLUM R | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-07-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.5695 | -120.6165 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1905 | 1731 | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 42.7 | 42.7 |  |  | 0 | 2.7 | 2.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100102370 | RELW OH PRI COMP CLR JPOL RESD REMT FIRE NOAC ESTR GO CCNT FMOB TER2 PRTO | Pole | 2020-01-07 | 2020-01-22 | COMP | 2020-01-07 | COMP | 2021-01-06 | [13 empty] | 2021-01-12 | 2021-01-06 | 2020-05-20 |  | 2020-05-20 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 15281.36 | 49581.2 | 46391.3 | 3396.6 | 3396.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117235248 | POLE_BROK_REPL - 21SE/0 0FF SSD 2707 STA | 35133705 |  |  | STS-POLE_BROK_REPL - 21SE/0 0FF SSD 2707 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5661 | -120.7089 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F17 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100113298 | RELW OH PRI CLR JPOL REMT NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2020-04-28 | 2020-08-18 | COMP | 2020-04-28 | [16 empty] | 2019-05-14 | 2020-05-14 |  | 2020-05-14 | 2021 CBP Plan | 2020-02-28 | PIKEENG |  | 152101101 | 13752.11 | 1820.1 |  |  |  | 221.6 |  | 221.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117243617 | POLE_DECA_REPL - 40 WILD PLUM LN SIERRA | 35226329 |  |  | STS-POLE_DECA_REPL - 40 WILD PLUM LN SIE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 39.568 | -120.6203 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1910 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100093870 | RELW OH PRI PGEA CLR RESD REMT FIRE ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | circuit based plan 2.14 |  | Auburn |  | 152101101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117250171 | POLE_DECA_REPL - R/O 125 MAIN ST SIERRA | 35133753 |  |  | STS-POLE_DECA_REPL - R/O 125 MAIN ST SIE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5642 | -120.6404 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1908 | 875BP | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.4 | 44.4 |  |  | 0 | 44.4 | 44.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100090811 | RELW OH PRI CLR JPOL RESD REMT FIRE NOAC ESTR FMOB TER2 PRTO | Pole | 2020-02-13 | 2020-03-05 | COMP | 2020-02-13 | [16 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 25974.26 | 6334.2 | 865.2 | 395.4 | 395.4 | 650.5 |  | 650.5 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117250173 | POLE_DECA_REPL - 1SW/O 12 CEMENTERY RDSI | 35133755 |  |  | STS-POLE_DECA_REPL - 1SW/O 12 CEMENTERY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5649 | -120.6392 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1908 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100090804 | OH RELW PRI CLR JPOL RESD REMT FIRE NOAC ESTR FMOB TER2 PRTO | Pole | 2020-06-11 | 2020-06-11 | COMP | 2020-01-15 | [16 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 12587.34 | 3219.3 | 21.1 | 21.1 | 21.1 | 48.7 |  | 48.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117250177 | POLE_DECA_REPL - SP/O 125 MAIN ST SIERRA | 35133758 |  |  | STS-POLE_DECA_REPL - SP/O 125 MAIN ST SI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5645 | -120.64 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1908 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100090809 | RELW OH SERV PGEA RESD REMT FIRE FLAG ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-01-28 | 2020-06-29 | COMP | 2020-01-28 |  |  | 2020-06-29 | 2020-06-29 | [12 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 11564.93 | 3965.3 | 112.1 |  |  | 1532 |  | 1532 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117252452 | POLE_DECA_REPL - 2E/O R/O 125 MAIN ST SI | 35133765 |  |  | STS-POLE_DECA_REPL - 2E/O R/O 125 MAIN S | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 39.5644 | -120.6392 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1908 | 875BP | Y | 311 |  |  |  |  | Returned | Order Operation | [6 empty] | 41 | 41 |  |  | 3.75 | 40 | 40 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100090805 | RELW OH PRI CLR ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-01-23 | 2020-02-18 | COMP | 2020-01-23 |  |  | 2020-01-10 | 2020-01-10 | [12 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 33047.9 | 39499.5 |  |  |  | 730.9 |  | 730.9 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117252461 | POLE_BROK_REPL - #1SW 101 WILD PLUM DR S | 35133766 |  |  | STS-POLE_BROK_REPL - #1SW 101 WILD PLUM | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-12-31 | Renew Permit | 39.5686 | -120.627 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1909 | 789 | Y | 311 |  |  | 2021-04-01 07:00 | 2021-04-01 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100104504 | RELW OH PRI CLR ESTR BTKA FMOB TER2 PRTO | Pole | 2020-03-18 | 2020-07-28 | COMP | 2020-03-18 |  |  | 2020-01-15 | 2020-01-15 | [12 empty] | 2019-05-16 | 2020-05-16 |  | 2020-05-16 | circuit based plan 2.14 | 2020-06-30 | PIKEENG |  | 152101101 | 38792.66 | 46032.4 | 37374.8 | 36874.6 | 36874.6 | 541.3 |  | 541.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117267516 | POLE_DECA_REPL - 32 SACRED MOUND RDSIERR | 35133784 |  |  | STS-POLE_DECA_REPL - 32 SACRED MOUND RDS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5685 | -120.6331 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1908 |  | Y | 311 |  |  | 2020-04-01 | 2020-04-01 | Completed | Order Operation | [6 empty] | 210.5 | 41.7 |  | 168.8 | 0 | 210.5 | 41.7 |  | 168.8 | EC | E | Pole | Decayed/Rotten | Replace |  | 100094713 | RELW OH PRI CLR JPOL RESD REMT FIRE ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-31 | 2020-10-21 | COMP | 2020-08-31 | [16 empty] | 2019-05-17 | 2020-05-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 152101101 | 8836.55 | 1482.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117267519 | POLE_DECA_REPL - 6NW/O 25 SIERRA BUTTER | 35133786 |  |  | STS-POLE_DECA_REPL - 6NW/O 25 SIERRA BUT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5665 | -120.641 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1908 |  | Y | 311 |  |  | 2021-04-01 07:00 | 2021-04-01 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | F | Pole | Decayed/Rotten | Replace |  | 100090829 | RELW OH PRI CLR JPOL RESD REMT FIRE FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-20 | 2020-10-30 | COMP | 2020-01-16 |  |  | 2020-06-29 | 2020-06-29 | [12 empty] | 2019-05-17 | 2020-05-17 | 2024-05-17 | 2024-05-17 | 2021 CBP Plan | 2020-01-09 | PIKEENG |  | 152101101 | 9555.73 | 882.8 | 793.5 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117270920 | POLE_DECA_REPL - #60 ON LINE S/O 220 SAL | 35133779 |  |  | STS-POLE_DECA_REPL - 100 KENTUCKY MINE R | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5739 | -120.6213 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1905 | 9079 | Y | 311 |  |  | 2021-08-19 07:00 | 2021-08-19 16:00 | Dispatched | CLICK | [6 empty] | 54.6 | 43.6 | 11 |  | 0 | 54.6 | 43.6 | 11 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100102377 | RELW OH PRI CLR JPOL RESD REMT FIRE ESTR BTKA PROG FMOB TER2 PRTO | Pole | 2020-03-02 | 2020-06-20 | COMP | 2020-02-27 | [16 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 27615.11 | 8086.2 | 500.8 | 374 | 374 | 2153.7 |  | 2153.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117273976 | POLE_BROK_REPL - 16SE/0 0FF SSD 2707 STA | 35133787 |  |  | STS-POLE_BROK_REPL - 16SE/0 0FF SSD 2707 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5663 | -120.7131 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F17 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 1 | 1 |  |  | 0 | 1 | 1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100104641 | RELW OH PRI CLR JPOL REMT NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2020-04-30 | 2020-06-24 | COMP | 2020-04-30 | [16 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | circuit based plan 2.14 | 2020-02-28 | PIKEENG |  | 152101101 | 20693.13 | 3181.9 |  |  |  | 177.4 |  | 177.4 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117274379 | POLE_DECA_REPL - #52 ON LINE S/O 220 SAL | 35133797 |  |  | STS-POLE_DECA_REPL - #52 ON LINE S/O 220 | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5764 | -120.6177 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1905 |  | Y | 311 |  |  | 2021-08-19 07:00 | 2021-08-19 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103916797 | RELW OH PRI CLR JPOL REMT FIRE NOAC ESTR FMOB TER2 PRTO | Pole | 2020-06-01 | 2020-07-30 | COMP | 2020-03-13 | [16 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | circuit based plan 2.14 | 2020-02-28 | PIKEENG |  | 152101101 | 42580.17 | 3012.8 |  |  |  | 365.7 |  | 365.7 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117274393 | POLE_BROK_REPL - #2NE ON LINE @ R/O 521 | 35133798 |  |  | STS-POLE_BROK_REPL - #2NE ON LINE @ R/O | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5703 | -120.6257 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F19 |  | Y | 311 |  |  | 2021-08-19 07:00 | 2021-08-19 16:00 | Dispatched | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100094719 | RELW OH PRI CLR JPOL REMT FIRE NOAC ESTR GO FMOB TER2 PRTO | Pole | 2020-05-18 | 2020-05-18 | COMP | 2020-03-16 | [16 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | circuit based plan 2.14 | 2020-02-28 | PIKEENG |  | 152101101 | 22946.71 | 3245.4 | 585 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117274394 | POLE_DECA_REPL - #57 ON LINE S/O 220 SAL | 35133799 |  |  | STS-POLE_DECA_REPL - #57 ON LINE S/O 220 | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5747 | -120.6203 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1905 |  | Y | 311 |  |  | 2021-08-19 07:00 | 2021-08-19 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100102379 | RELW OH PRI CLR JPOL REMT FIRE NOAC ESTR GO FMOB TER2 PRTO | Pole | 2020-01-21 | 2020-03-09 | COMP | 2020-01-21 | [16 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 12394.79 | 6219.4 | 3052.4 |  |  | 1600 |  | 1600 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117274395 | POLE_DECA_REPL - #3 on line NE/O 100 Ke | 35133800 |  |  | STS-POLE_DECA_REPL -#3 ON LINE NE/O 100 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5743 | -120.6208 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1905 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100102378 | RELW OH PRI CLR JPOL REMT FIRE NOAC ESTR FMOB TER2 PRTO | Pole | 2020-02-05 | 2020-02-24 | COMP | 2020-02-05 | [16 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 28990.57 | 3065.6 |  |  |  | 1339.6 |  | 1339.6 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117274396 | POLE_DECA_REPL - #54 ON LINE S/O 220 SAL | 35133801 |  |  | STS-POLE_DECA_REPL - #54 ON LINE S/O 220 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5757 | -120.619 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1905 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 1 | 1 |  |  | 0 | 1 | 1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100102382 | RELW OH PRI CLR JPOL REMT FIRE NOAC ESTR FMOB TER2 PRTO | Pole | 2020-06-01 | 2020-06-02 | COMP | 2020-03-16 |  |  | 2020-02-06 | 2020-02-06 | [12 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | circuit based plan 2.14 | 2020-02-28 | PIKEENG |  | 152101101 | 24343.8 | 3484 |  |  |  | 221.7 |  | 221.7 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117274397 | POLE_DECA_REPL - #55 ON LINE S/O 220 SAL | 35133802 |  |  | STS-POLE_DECA_REPL - #55 ON LINE S/O 220 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5754 | -120.6194 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1905 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 1 | 1 |  |  | 0 | 1 | 1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100102381 | RELW OH PRI CLR JPOL REMT FMOB FIRE NOAC ESTR TER2 PRTO | Pole | 2020-03-03 | 2020-06-02 | COMP | 2020-03-03 | [16 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | circuit based plan 2.14 | 2020-02-28 | PIKEENG |  | 152101101 | 28375.68 | 3783.2 |  |  |  | 398.9 |  | 398.9 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117274399 | POLE_DECA_REPL - #5NE ON LINE @ R/O 521 | 35133803 |  |  | STS-POLE_DECA_REPL - #5NE ON LINE @ R/O | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.571 | -120.6243 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1905 |  | Y | 311 |  |  | 2021-08-19 07:00 | 2021-08-19 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.8 | 41.8 |  |  | 3 | 40.8 | 40.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100112093 | RELW OH PRI CLR JPOL REMT FIRE NOAC ESTR FMOB TER2 PRTO | Pole | 2020-03-04 | 2020-05-01 | COMP | 2020-03-04 | [16 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | circuit based plan 2.14 | 2020-02-28 | PIKEENG |  | 152101101 | 28083.34 | 2652.5 | 446.5 | 117.6 | 117.6 | 246.2 |  | 246.2 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117274559 | POLE_BROK_REPL - 11W/O 101 HWY 49 SIERRA | 35133804 |  |  | STS-POLE_BROK_REPL - 11W/O 101 HWY 49 SI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5635 | -120.6538 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F19 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100095430 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-03-16 | 2020-07-29 | COMP | 2020-03-16 | [16 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | circuit based plan 2.14 | 2020-02-28 | PIKEENG |  | 152101101 | 22255.38 | 2282.6 |  |  |  | 177.3 |  | 177.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117274570 | POLE_BROK_REPL - 14W/O 101 HWY 49 SIERRA | 35133805 |  |  | STS-POLE_BROK_REPL - 14W/O 101 HWY 49 SI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5637 | -120.656 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F19 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100095433 | RELW OH PRI JPOL REMT NOAC ESTR GO FMOB TER2 PRTO | Pole | 2020-03-05 | 2020-06-25 | COMP | 2020-03-05 | [16 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | circuit based plan 2.14 | 2020-02-28 | PIKEENG |  | 152101101 | 22523.82 | 2084.1 |  |  |  | 349.4 |  | 349.4 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117274571 | POLE_BROK_REPL - 10W/O 101 HWY 49 SIERRA | 35133806 |  |  | STS-POLE_BROK_REPL - 10W/O 101 HWY 49 SI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5634 | -120.653 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F19 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100095429 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-03-04 | 2020-07-31 | COMP | 2020-03-04 |  |  | 2020-06-29 | 2020-06-29 | [12 empty] | 2019-05-19 | 2020-05-19 |  | 2020-05-19 | circuit based plan 2.14 | 2020-02-28 | PIKEENG |  | 152101101 | 22220.74 | 2228.7 |  |  |  | 480.2 |  | 480.2 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117279930 | POLE_DECA_REPL - #1 ON LINE S/O 316 OSTR | 35133810 |  |  | STS-POLE_DECA_REPL - #1 ON LINE S/O 316 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5717 | -120.615 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F2001 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 29.9 | 29.9 |  |  | 0 | 29.9 | 29.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100105480 | RELW OH PRI CLR JPOL RESD REMT FIRE NOAC ESTR FMOB TER2 PRTO | Pole | 2021-02-02 | 2021-02-11 | COMP | 2021-02-02 | [16 empty] | 2019-05-20 | 2020-05-20 |  | 2020-05-20 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 14230.7 | 1735.1 | 400.6 |  |  | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117279933 | POLE_DECA_REPL - 316 OSTROM WAY RDSIERRA | 35133812 |  |  | STS-POLE_DECA_REPL - 316 OSTROM WAY RDSI | PEND | PEND SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | DMD | 2020-12-31 | Renew Permit | 39.5718 | -120.6151 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F2001 | 1731 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.5 | 21.5 |  |  | 0 | 21.5 | 21.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100111811 | RELW OH PRI CLR JPOL RESD REMT FIRE ESTR GO BTKA PROG FMOB TER2 PRTO | Pole | 2021-02-01 | 2020-04-07 | COMP | 2021-02-01 |  |  | 2020-01-16 | 2020-01-16 | [12 empty] | 2019-05-20 | 2020-05-20 |  | 2020-05-20 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 14175.72 | 27186.6 |  |  |  | 86 |  | 86 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117279945 | POLE_DECA_REPL - 304OSTROM WAY RDSIERRA | 35133840 |  |  | STS-POLE_DECA_REPL - 304OSTROM WAY RDSIE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.569 | -120.6158 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F20 | 1731 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 1 | 1 |  |  | 0 | 1 | 1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100105545 | RELW OH PRI CLR JPOL RESD REMT FIRE FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-05-19 | 2020-07-15 | COMP | 2020-05-19 |  |  | 2020-07-13 | 2020-07-13 | [12 empty] | 2019-05-20 | 2020-05-20 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-07-31 | PIKEENG |  | 152101101 | 22997.66 | 4070.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117281660 | POLE_BROK_REPL - #2E CAVIN 23 ON MYA WAY | 35133843 |  |  | STS-POLE_BROK_REPL - #2E CAVIN 23 ON MYA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5758 | -120.6133 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F2001 | 1731 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100111807 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-01-14 | 2020-03-25 | COMP | 2020-01-14 |  |  | 2020-01-27 | 2020-01-27 | [12 empty] | 2019-05-20 | 2020-05-20 |  | 2020-05-20 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 18041.64 | 84954.2 | 77940.5 | 77940.5 | 77940.5 | 1552.1 |  | 1552.1 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117331610 | POLE_BROK_REPL - 25S/O 220 AT SALMON CRE | 35133892 |  |  | STS-POLE_BROK_REPL - 25S/O 220 AT SALMON | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5911 | -120.6133 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | E20 |  | Y | 311 |  |  | 2021-08-19 07:00 | 2021-08-19 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100087907 | RELW OH PRI JPOL REMT FIRE SWRK ESTR GO PROG FMOB TER2 PRTO | Pole | 2020-01-23 | 2020-07-09 | COMP | 2020-01-23 | [16 empty] | 2019-05-28 | 2020-05-28 |  | 2020-05-28 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 25977.67 | 9250.9 | 5534.7 |  |  | 1334.1 |  | 1334.1 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117331614 | POLE_DECA_REPL - 45S/O 220 AT SALMON CRE | 35133893 |  |  | STS-POLE_DECA_REPL - 45S/O 220 AT SALMON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5792 | -120.6114 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | E20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100103877 | RELW OH PRI JPOL REMT FIRE NOAC SWRK ESTR GO FMOB TER2 PRTO | Pole | 2020-04-30 | 2020-11-10 | COMP | 2020-04-30 | [16 empty] | 2019-05-28 | 2020-05-28 |  | 2020-05-28 | 2021 CBP Plan | 2020-02-28 | PIKEENG |  | 152101101 | 30132.79 | 4543.4 | 2057.6 | 1365.2 | 1365.2 | 1154 |  | 1154 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117331620 | POLE_BROK_REPL - 41S/O 220 AT SALMON CRE | 35133894 |  |  | STS-POLE_BROK_REPL - 41S/O 220 AT SALMON | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5817 | -120.6104 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | E20 |  | Y | 311 |  |  | 2021-08-19 07:00 | 2021-08-19 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100103883 | RELW OH PRI JPOL REMT FIRE ESTR NOAC SWRK GO PROG FMOB TER2 PRTO | Pole | 2020-03-11 | 2020-06-16 | COMP | 2020-03-11 | [16 empty] | 2019-05-28 | 2020-05-28 |  | 2020-05-28 | circuit based plan 2.14 | 2020-02-28 | PIKEENG |  | 152101101 | 30523.7 | 4187.8 |  |  |  | 349.4 |  | 349.4 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117331622 | POLE_DECA_REPL - 30S/O 220 AT SALMON CRE | 35133895 |  |  | STS-POLE_DECA_REPL - 30S/O 220 AT SALMON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5888 | -120.6121 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | E20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.8 | 41.8 |  |  | 0.5 | 41.3 | 41.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100087912 | RELW OH PRI JPOL REMT FIRE NOAC SWRK ESTR FMOB TER2 PRTO | Pole | 2020-01-22 | 2020-02-21 | COMP | 2020-01-22 | [16 empty] | 2019-05-28 | 2020-05-28 |  | 2020-05-28 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 22286.83 | 3459.5 |  |  |  | 1295.2 |  | 1295.2 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117331623 | POLE_BROK_REPL - 34S/O 220 AT SALMON CRE | 35133896 |  |  | STS-POLE_BROK_REPL - 34S/O 220 AT SALMON | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5862 | -120.6108 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | E20 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100087729 | RELW OH PRI JPOL REMT FIRE NOAC SWRK ESTR GO FMOB TER2 PRTO | Pole | 2020-03-09 | 2020-06-16 | COMP | 2020-03-09 | [16 empty] | 2019-05-28 | 2020-05-28 |  | 2020-05-28 | circuit based plan 2.14 | 2020-02-28 | PIKEENG |  | 152101101 | 24029.29 | 3989.3 |  |  |  | 266 |  | 266 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117348007 | POLE_BROK_REPL - 2SE/0 0FF SSD 2707 STAT | 35133921 |  |  | STS-POLE_BROK_REPL - 2SE/0 0FF SSD 2707 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5686 | -120.7212 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F17 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.8 | 41.8 |  |  | 10 | 40.8 | 40.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100104659 | RELW OH PRI CLR JPOL REMT NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2020-03-20 | 2020-07-10 | COMP | 2020-03-20 | [16 empty] | 2019-05-30 | 2020-05-30 |  | 2020-05-30 | circuit based plan 2.14 | 2020-02-28 | PIKEENG |  | 152101101 | 29531.3 | 6352.7 |  |  |  | 295.4 |  | 295.4 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117348009 | POLE_BROK_REPL - 12SE/0 0FF SSD 2707 STA | 35133922 |  |  | STS-POLE_BROK_REPL - 12SE/0 0FF SSD 2707 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5664 | -120.7161 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F17 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100104646 | RELW OH PRI CLR JPOL REMT NOAC ESTR REAR FMOB TER2 PRTO | Pole | 2020-04-30 | 2020-06-25 | COMP | 2020-04-30 | [16 empty] | 2019-05-30 | 2020-05-30 |  | 2020-05-30 | circuit based plan 2.14 | 2020-02-28 | PIKEENG |  | 152101101 | 27966.84 | 2592.4 |  |  |  | 205.5 |  | 205.5 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SIERRA CITY | Grass Valley |  |  | OPEN | 117246211 | POLE_BROK_REPL - R/O 445 MAIN ST SIERRA | 35133750 |  |  | GC-POLE_BROK_REPL - R/O 445 MAIN ST SIE | CONS | CONS SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over HSCA |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.5676 | -120.6291 |  | TIER 2 | 150 | 15210-1101, ALLEGHANY | F1909 | 949 | Y | 311 |  |  | 2021-05-11 07:00 | 2021-05-11 16:00 | Scheduled | CLICK | [6 empty] | 45.2 | 45.2 |  |  | 0 | 45.2 | 45.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100104488 | PRI RELW OH JPOL RESD TRAF ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-04-23 | 2020-07-16 | COMP | 2020-04-23 |  |  | 2020-01-22 | 2020-01-22 | [12 empty] | 2019-05-15 | 2020-05-15 |  | 2020-05-15 | circuit based plan 2.14 | 2020-01-09 | PIKEENG |  | 152101101 | 25438.35 | 5949.2 | 464.1 | 414.3 | 414.3 | 247.6 |  | 247.6 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116691979 | POLE_DECA_REPL - 11684 MOONEY FLAT RD SM | 35187562 |  |  | STS-POLE_DECA_REPL - 11684 MOONEY FLAT R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2265 | -121.2671 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0401 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 11.2 | 11.2 |  |  | 0 | 11.2 | 11.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100010828 | RELW OH PRI CLR JPOL REMT ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-09-08 | 2021-02-18 | COMP | 2020-09-08 |  |  | 2021-02-18 | 2021-02-18 | [12 empty] | 2019-03-09 | 2020-03-09 |  | 2020-03-09 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 7701.95 | 1880.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116705384 | POLE_DECA_REPL - A/F 10212 MELODY RD SMA | 35187570 |  |  | STS-POLE_DECA_REPL - A/F 10212 MELODY RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.206 | -121.2499 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0413 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.5 | 20.5 |  |  | 0 | 20.5 | 20.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100010972 | RELW OH RESD PRI CLR JPOL REMT ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-09-18 | 2021-02-18 | COMP | 2020-09-18 |  |  | 2021-02-18 | 2021-02-18 | [12 empty] | 2019-03-10 | 2020-03-10 |  | 2020-03-10 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 12205.69 | 2039.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116707376 | POLE_DECA_REPL - A/F 10550 MOONEY FLAT R | 35187574 |  |  | STS-POLE_DECA_REPL - A/F 10550 MOONEY FL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.2115 | -121.2758 |  | TIER 2 | 109 | 15313-2105, NARROWS | N301 | 1227 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 25.5 | 25.5 |  |  | 0 | 25.5 | 25.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100087067 | RELW OH PRI CLR ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-15 |  | COMP | 2020-10-15 | [16 empty] | 2019-03-11 | 2020-03-11 |  | 2020-03-11 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 8898.06 | 1171 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116707743 | POLE_DECA_REPL - 10743 MOONEY FLAT RD. S | 35187578 |  |  | STS-POLE_DECA_REPL - 10743 MOONEY FLAT R | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.2125 | -121.2751 |  | TIER 2 | 109 | 15313-2105, NARROWS | N301 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.8 | 15.8 |  |  | 0 | 15.8 | 15.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100087065 | RELW OH PRI CLR ESTR GO BTKA FMOB TER2 PRTO | Pole | 2020-10-14 |  | COMP | 2020-10-14 | [16 empty] | 2019-03-11 | 2020-03-11 |  | 2020-03-11 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 15681.54 | 1934 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116707922 | POLE_BROK_REPL - 1N/O 10645 MOONEY FLAT | 35187582 |  |  | STS-POLE_BROK_REPL - 1N/O 10645 MOONEY F | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 39.2136 | -121.2746 |  | TIER 2 | 109 | 15313-2105, NARROWS | N301 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.6 | 18.6 |  |  | 0 | 18.6 | 18.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100087060 | RELW OH PRI CLR ESTR BTKA PROG FMOB TER2 PRTO | Pole | 2020-10-06 |  | COMP | 2020-10-06 | [16 empty] | 2019-03-11 | 2020-03-11 |  | 2020-03-11 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 10945.48 | 1382.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116763897 | POLE_DECA_REPL - 21580 MOREL CTSMARTSVIL | 35187964 |  |  | STS-POLE_DECA_REPL - 21580 MOREL CTSMART | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.184 | -121.2527 |  | TIER 2 | 109 | 15313-2105, NARROWS | N04 | 3503 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.6 | 44.6 |  |  | 0 | 44.6 | 44.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100011223 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-16 | 2020-12-11 | COMP | 2020-10-16 | [16 empty] | 2019-03-19 | 2020-03-19 |  | 2020-03-19 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 17449.24 | 1905.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116883437 | POLE_DECA_REPL - 4S/O C/O CABRILLO WY./L | 35187649 |  |  | STS-POLE_DECA_REPL - 4S/O C/O CABRILLO W | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1694 | -121.3017 |  | TIER 2 | 109 | 15313-2105, NARROWS | O03 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24 | 24 |  |  | 0 | 24 | 24 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100013227 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2021-01-13 | 2021-02-19 | COMP | 2020-10-15 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-01 | 2020-04-01 |  | 2020-04-01 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 14474.47 | 1454.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116941530 | POLE_DECA_REPL - 1N/O 1E/O 23067 PATINO | 35187735 |  |  | STS-POLE_DECA_REPL - 1N/O 1E/O 23067 PAT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1776 | -121.2707 |  | TIER 2 | 109 | 15313-2105, NARROWS | O04 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.8 | 18.8 |  |  | 0 | 18.8 | 18.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100013360 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-14 | 2021-02-11 | COMP | 2020-10-14 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 10675.23 | 1252.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116961127 | POLE_DECA_REPL - 1W/O 12040 SHEPARD RD.S | 35188022 |  |  | STS-POLE_DECA_REPL - 1W/O 12040 SHEPARD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 39.1806 | -121.2497 |  | TIER 2 | 109 | 15313-2105, NARROWS | O04 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.8 | 31.8 |  |  | 0 | 31.8 | 31.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100013380 | RELW RESD OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-10-15 |  | COMP | 2020-10-15 | [16 empty] | 2019-04-05 | 2020-04-05 |  | 2020-04-05 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 12234.83 | 961 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | COMP | 116691899 | POLE_DECA_REPL - 4R/O 12347 HIDRAULC WY | 35187319 |  |  | STS-POLE_DECA_REPL - 4R/O 12347 HIDRAULC | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.2262 | -121.2723 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0401 |  | Y | 311 |  |  | 2021-02-04 | 2021-02-04 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100010839 | RELW OH PRI COMP CLR FIRE ESTR GO CCNT FMOB TER2 PRTO | Pole | 2020-10-13 | 2020-11-30 | COMP | 2020-10-12 | COMP | 2021-02-04 | [13 empty] | 2021-02-11 | 2021-02-04 | 2020-03-09 |  | 2020-03-09 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 5818.76 | 3096.2 | 1813.7 | 728.3 | 728.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | COMP | 116706297 | POLE_WOOD_ASES - SP R/O 10530 MELODY RDS | 35091648 |  |  | STS-POLE_WOOD_ASES - SP R/O 10530 MELODY | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.2017 | -121.2525 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0413 |  | Y | 311 |  |  | 2021-02-13 07:00 | 2021-02-13 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Woodpecker Damage | Assessment |  | 100010988 | RELW OH SEC COMP CLR JPOL RESD REMT ESTR BTKA REAR CCNT FMOB TER2 PRTO | Pole | 2019-12-02 | 2020-05-27 | COMP | 2019-12-02 | COMP | 2021-02-13 | [13 empty] | 2021-02-22 | 2021-02-13 | 2020-03-10 |  | 2020-03-10 | 2021 CBP Plan | 2019-11-30 | QUES |  | 153132105 | 4839.92 | 2566.5 | 2566.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | COMP | 116933775 | POLE_DECA_REPL - 7194 CHIPMUNK TR.SMARTS | 35187692 |  |  | STS-POLE_DECA_REPL - 7194 CHIPMUNK TR.SM | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.1649 | -121.2941 |  | TIER 2 | 109 | 15313-2105, NARROWS | O03 |  | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100013283 | OH RELW PRI COMP ESTR CCNT FMOB TER2 PRTO | Pole | 2020-10-14 | 2020-11-30 | COMP | 2020-10-14 | COMP | 2021-02-11 | [13 empty] | 2021-02-18 | 2021-02-11 | 2020-04-02 |  | 2020-04-02 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 7366.66 | 3513.8 | 2268.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | COMP | 116955433 | POLE_BROK_REPL - 7317 NUGGET TR. SMARTSV | 35187892 |  |  | STS-POLE_BROK_REPL - 7317 NUGGET TR. SMA | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.1674 | -121.2882 |  | TIER 2 | 109 | 15313-2105, NARROWS | O03 |  | Y | 311 |  |  | 2021-02-04 | 2021-02-04 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0.5 | 41.3 | 41.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100013178 | RELW OH PRI ESTR FMOB TER2 PRTO COMP CCNT | Pole | 2020-10-15 | 2020-12-04 | COMP | 2020-10-15 | COMP | 2021-02-04 | [13 empty] | 2021-02-11 | 2021-02-04 | 2020-04-04 |  | 2020-04-04 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 7866.66 | 2818.3 | 1624.9 | 111.2 | 111.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116691857 | POLE_DECA_REPL - 23000–23098 HYDRAULIC W | 35187318 |  |  | STS-POLE_DECA_REPL - 23000–23098 HYDRAUL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2252 | -121.2703 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0401 |  | Y | 311 |  |  | 2021-04-01 07:00 | 2021-04-01 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103675574 | RELW OH PRI CLR RESD REMT ESTR GO BTKA REAR FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-11-28 | COMP | 2020-10-12 | [16 empty] | 2019-03-09 | 2020-03-09 |  | 2020-03-09 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 4698.83 | 2218 | 1331.2 | 1116.7 | 1116.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116692224 | POLE_DECA_REPL - 1E/O 1S/O 11226 CHANTER | 35091636 |  |  | STS-POLE_DECA_REPL - 1E/O 1S/O 11226 CHA | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.187 | -121.2768 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0325 |  | Y | 311 |  |  | 2021-02-27 07:00 | 2021-02-27 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100071888 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2019-12-02 | 2019-12-27 | COMP | 2019-12-02 | [16 empty] | 2019-03-09 | 2020-03-09 |  | 2020-03-09 | 2021 CBP Plan | 2019-11-30 | QUES |  | 153132105 | 7707.82 | 765.2 | 686.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116692642 | POLE_BROK_REPL - 11101 MOONEY FLAT RDSMA | 35187564 |  |  | STS-POLE_BROK_REPL - 11101 MOONEY FLAT R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2179 | -121.2696 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0406 | 1227 | Y | 311 |  |  | 2021-03-17 07:00 | 2021-03-17 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103676701 | RELW PRI OH CLR JPOL RESD REMT ESTR BTKA REAR FMOB TER2 PRTO | Pole | 2020-09-23 | 2020-11-29 | COMP | 2020-09-23 | [16 empty] | 2019-03-09 | 2020-03-09 |  | 2020-03-09 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 16886.61 | 4177.5 | 3132.6 | 1014.1 | 1014.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116741452 | POLE_BROK_REPL - 1R/O 22236 MC. DANIEL H | 35187695 |  |  | STS-POLE_BROK_REPL - 1R/O 22236 MC. DANI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1932 | -121.2501 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0418 | 5215 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 42.9 | 42.9 |  |  | 0 | 42.9 | 42.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100010525 | OH PRI CLR RESD FIRE ESTR BTKA FMOB TER2 PRTO RELW | Pole | 2020-10-15 | 2020-11-29 | COMP | 2020-10-15 | [16 empty] | 2019-03-15 | 2020-03-15 |  | 2020-03-15 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 18447.42 | 2185.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116742315 | POLE_DECA_REPL - 1S/O 11025 VAGABOND LNS | 35187702 |  |  | STS-POLE_DECA_REPL - 1S/O 11025 VAGABOND | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1954 | -121.2523 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0418 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.2 | 12.2 |  |  | 0 | 12.2 | 12.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100010568 | RELW OH PRI CLR ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-13 | 2021-01-08 | COMP | 2020-10-13 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-03-15 | 2020-03-15 |  | 2020-03-15 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 6963.32 | 1075.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116748991 | POLE_BROK_REPL - A/F 11509 MC DANIEL RD | 35187764 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1864 | -121.2394 |  | TIER 2 | 109 | 15313-2105, NARROWS | N04 | 3503 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 41.7 | 41.7 |  |  | 0 | 41.7 | 41.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100011515 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-05 | 2020-12-02 | COMP | 2020-10-05 |  |  | 2020-09-29 | 2020-09-29 | [12 empty] | 2019-03-16 | 2020-03-16 |  | 2020-03-16 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 16212.48 | 1505.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116749368 | POLE_BROK_REPL - 21962 MCDANIEL RD SMART | 35187781 |  |  | STS-POLE_BROK_REPL - 21962 MCDANIEL RD S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1886 | -121.2455 |  | TIER 2 | 109 | 15313-2105, NARROWS | N04 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 20 | 20 |  |  | 0 | 20 | 20 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103677500 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA FMOB PRTO TER2 | Pole | 2020-10-05 | 2020-11-24 | COMP | 2020-10-05 | [16 empty] | 2019-03-16 | 2020-03-16 |  | 2020-03-16 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 8137.81 | 1152.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116750231 | POLE_BROK_REPL - 21955 MC DANIEL RD SMAR | 35187793 |  |  | STS-POLE_BROK_REPL - 21955 MC DANIEL RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1894 | -121.247 |  | TIER 2 | 109 | 15313-2105, NARROWS | N04 | 3503 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.5 | 37.5 |  |  | 0 | 37.5 | 37.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100011508 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-08 | 2021-01-08 | COMP | 2020-10-15 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-03-16 | 2020-03-16 |  | 2020-03-16 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 153132105 | 16919.37 | 1338.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116941433 | POLE_DECA_REPL - C/O WHITE FIR WY./MOSSW | 35187723 |  |  | STS-POLE_DECA_REPL - C/O WHITE FIR WY./M | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1733 | -121.2952 |  | TIER 2 | 109 | 15313-2105, NARROWS | O0308 |  | Y | 311 |  |  | 2021-03-03 07:00 | 2021-03-03 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100013253 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-12-03 | COMP | 2020-10-15 | [16 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 7913.96 | 1218.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116941434 | POLE_DECA_REPL - 1S/O C/O MOSSWOOD LN/WH | 35187729 |  |  | STS-POLE_DECA_REPL - 1S/O C/O MOSSWOOD L | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1731 | -121.2951 |  | TIER 2 | 109 | 15313-2105, NARROWS | O0308 |  | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100013260 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-10-13 | 2020-11-30 | COMP | 2020-10-13 | [16 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 6648.37 | 1672.8 | 575.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116942893 | POLE_DECA_REPL - 12241 PATINO RD.SMARTSV | 35187755 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.18 | -121.2702 |  | TIER 2 | 109 | 15313-2105, NARROWS | O04 | 6371 | Y | 311 |  |  |  |  | Scheduled | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 62.3 | 61.9 |  | 0.4 | 0 | 62.3 | 61.9 |  | 0.4 | EC | E | Pole | Decayed/Rotten | Replace |  | 100013355 | PRI OH RELW JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-13 | 2020-12-03 | COMP | 2020-10-13 | [16 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 23870.09 | 1402.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116949481 | POLE_DECA_REPL - 8716 MOSSWOOD LN. SMART | 35187779 |  |  | STS-POLE_DECA_REPL - 8716 MOSSWOOD LN.SM | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1739 | -121.2935 |  | TIER 2 | 109 | 15313-2105, NARROWS | O03 | 3393 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100013189 | RELW PRI OH ESTR FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-11-30 | COMP | 2020-10-15 | [16 empty] | 2019-04-03 | 2020-04-03 |  | 2020-04-03 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 18965.96 | 3575.7 | 2122.1 | 1008.6 | 1008.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116954827 | POLE_DECA_REPL - 1S/O 7326 NUGGET TR. SM | 35187855 |  |  | STS-POLE_DECA_REPL - 1S/O 7326 NUGGET TR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1686 | -121.2886 |  | TIER 2 | 109 | 15313-2105, NARROWS | O03 |  | Y | 311 |  |  | 2021-03-18 07:00 | 2021-03-18 16:00 | Scheduled | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100013180 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-11-30 | COMP | 2020-10-12 | [16 empty] | 2019-04-04 | 2020-04-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 7299.58 | 2312.9 | 1203.8 | 867.6 | 867.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116957985 | POLE_DECA_REPL - JUDAS EAR CT SMARTSVILL | 35187996 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1823 | -121.2511 |  | TIER 2 | 109 | 15313-2105, NARROWS | N04 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 59.9 | 59.9 |  |  | 0 | 59.9 | 59.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103677502 | RELW OH PRI JPOL RESD REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-10-13 | 2020-12-04 | COMP | 2020-10-13 | [16 empty] | 2019-04-04 | 2020-04-04 |  | 2020-04-04 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 20831.3 | 1045 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116962370 | POLE_DECA_REPL - A/F 23395 ST. HELENA DR | 35188114 |  |  | STS-POLE_DECA_REPL - A/F 23395 ST. HELEN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.171 | -121.2766 |  | TIER 2 | 109 | 15313-2105, NARROWS | O03 | 6371 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 29.1 | 29.1 |  |  | 0 | 29.1 | 29.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100013143 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2021-01-11 | 2021-01-12 | COMP | 2020-10-08 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-05 | 2020-04-05 |  | 2020-04-05 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 17002.28 | 1659.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116968888 | POLE_DECA_REPL - 12606 BLACK RDSMARTSVIL | 35188296 |  |  | STS-POLE_DECA_REPL - 12606 BLACK RDSMART | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1718 | -121.2495 |  | TIER 2 | 109 | 15313-2105, NARROWS | O04 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.8 | 15.8 |  |  | 0 | 15.8 | 15.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103847706 | RELW OH SEC JPOL RESD REMT NOAC PRTO ESTR FMOB TER2 | Pole | 2020-09-25 | 2020-12-01 | COMP | 2020-09-25 | [16 empty] | 2019-04-06 | 2020-04-06 |  | 2020-04-06 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 7730.81 | 878 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 116970835 | POLE_BROK_REPL - R/O 12009 HUTTO RD. SMA | 35188413 |  |  | STS-POLE_BROK_REPL - R/O 12009 HUTTO RD. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.1813 | -121.2773 |  | TIER 2 | 109 | 15313-2105, NARROWS | O0305 | 6371 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 26.5 | 26.5 |  |  | 0 | 26.5 | 26.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100013295 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-10-13 | 2020-11-30 | COMP | 2020-10-13 | [16 empty] | 2019-04-06 | 2020-04-06 |  | 2020-04-06 | 2021 CBP Plan | 2020-11-15 | ENENG |  | 153132105 | 17105.93 | 1519.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 117193577 | POLE_BROK_REPL - 5/W C/01737 MOONEY FLAT | 35163671 |  |  | STS-POLE_BROK_REPL - 5/W C/01737 MOONEY | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2356 | -121.2377 |  | TIER 2 | 154 | 15313-2102, NARROWS | M04 |  | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-08 16:00 | Dispatched | CLICK | [6 empty] | 42.8 | 42.8 |  |  | 0.25 | 42.55 | 42.55 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100083151 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-04 | 2020-08-04 | COMP | 2020-08-04 | [16 empty] | 2019-05-09 | 2020-05-09 |  | 2020-05-09 | circuit based plan 2.14 | 2020-09-30 | TRC |  | 153132102 | 9637.08 | 2365.4 | 483.5 | 58.7 | 58.7 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SMARTSVILLE | Grass Valley |  |  | OPEN | 117367004 | POLE_DECA_REPL - 2NE/O N/O 10289 WILDTUR | 35163714 |  |  | STS-POLE_DECA_REPL - 2NE/O N/O 10289 WIL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 39.2029 | -121.2662 |  | TIER 2 | 109 | 15313-2105, NARROWS | N04 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.8 | 19.8 |  |  | 0 | 19.8 | 19.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100011311 | RELW OH PRI CLR ESTR FMOB TER2 PRTO | Pole | 2020-09-08 | 2020-09-08 | COMP | 2020-09-08 | [16 empty] | 2019-05-31 | 2020-05-31 |  | 2020-05-31 | 2021 CBP Plan | 2020-09-30 | TRC |  | 153132105 | 23429.47 | 793.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | SMARTVILLE | Grass Valley |  |  | COMP | 119561468 | POLE_BROK_REPL - 22236 BLACK RD SMARTVIL | 35191716 |  |  | B3 - STS-POLE_BROK_REPL - 22236 BLACK RD | FICL | FICL SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-09-24 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 39.1938 | -121.2497 |  | TIER 2 | 109 | 15313-2105, NARROWS | N0418 | 5215 | Y | 311 |  |  | 2021-01-19 | 2021-01-19 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 50.1 | 50.1 |  |  | 42 | 50 | 50 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100010526 | RELW OH COMP JPOL ESTR CPGD TER2 | Pole | 2020-10-13 | 2020-11-03 | COMP | 2020-10-13 | COMP | 2021-01-19 | [13 empty] | 2021-01-20 | 2021-01-19 | 2020-10-22 |  | 2020-10-22 | B-tag addition 8/12/2020 |  | Auburn |  | 153132105 | 18499.26 | 12950.3 | 11213.4 | 11213.4 | 11213.4 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Insufficient Construction Resources | Y | 2020-08-18
North | SI | SOMERSET | Placerville |  |  | OPEN | 117022744 | POLE_DECA_REPL - N/O 5951 MT AUKUM RD SO | 35188393 |  |  | STS-POLE_DECA_REPL - N/O 5951 MT AUKUM R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6469 | -120.6863 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J44 | 21137 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 66 | 64.4 | 1.6 |  | 0 | 66 | 64.4 | 1.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101405793 | RELW OH PRI TEST JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO | Pole | 2021-01-11 | 2021-02-12 | COMP | 2020-09-28 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 30944.45 | 920.6 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117120068 | POLE_BROK_REPL - 1W/O 7591 BUZZARDS GULC | 35188146 |  |  | STS-POLE_BROK_REPL - 1W/O 7591 BUZZARDS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 38.5982 | -120.7365 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.2 | 30.8 | 2.4 |  | 0 | 33.2 | 30.8 | 2.4 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101401781 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-09 |  | COMP | 2020-10-09 | [16 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117166905 | POLE_BROK_REPL - R/O 3021 WINTER CREEK R | 35188190 |  |  | STS-POLE_BROK_REPL - R/O 3021 WINTER CRE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.5817 | -120.712 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L44 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 11 | 11 |  |  | 0 | 11 | 11 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101395360 | RELW OH PRI CLR RESD REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-10-07 |  | COMP | 2020-10-07 | [16 empty] | 2019-05-06 | 2020-05-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117323203 | POLE_DECA_REPL - SERV TO 7041 FAIRPLAY R | 35215709 |  |  | STS-POLE_DECA_REPL - SERV TO 7041 FAIRPL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.6034 | -120.6936 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K44 | 21469 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101420922 | RELW OH PRI PGEA CLR RESD REMT FIRE ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-26 | 2020-05-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 116975489 | POLE_BROK_REPL - 1S/O 6930 CASA CONTENTA | 35219341 |  |  | STS-POLE_BROK_REPL - 1S/O 6930 CASA CONT | PEND | PEND | Poles | MPP | Not Funded as 2020 Wildfire OII | 07D | Critical Work | WSIP | 6.1 |  |  | 6 | 2021-08-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.6392 | -120.6466 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K45 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21 | 21 |  |  | 0 | 21 | 21 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101396143 | OH PRI JPOL RESD REMT BTKA PRTO RELW FMOB TER2 | Pole | 2021-02-22 |  | COMP | 2021-02-22 | [16 empty] | 2019-04-07 | 2020-04-07 | 2021-05-31 | 2021-05-31 | work plan year cleanup 01/21/2021 | 2021-04-30 | Auburn |  | 153662102 | [9 empty] | N | Crticial Work MPP Owned and pulled from MPP Import File | N |  | Y | 2021-01-21
North | SI | SOMERSET | Placerville |  |  | COMP | 114976212 | POLE_BROK_REPL - 6460 Slug Gulch RdSomer | 35062875 |  |  | STS-POLE_BROK_REPL - 6460 SLUG GULCH RDS | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-06-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6003 | -120.6404 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K4525 | 2017 | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 11 | 40.8 | 40.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101420595 | REGW OH PRI INSP COMP CLR REMT NOAC ESTR CCNT FMOB TER2 | Pole | 2019-02-07 | 2019-03-20 | COMP | 2019-02-07 | COMP | 2021-01-13 | [13 empty] | 2021-01-20 | 2021-01-13 | 2019-09-15 |  | 2019-09-15 | Q1 Work Plan | 2019-02-28 | EEI |  | 153662102 | 20347.84 | 56159.7 | -21837.7 | -5337.7 | -5337.7 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SOMERSET | Placerville |  |  | COMP | 115346437 | POLE_DECA_REPL - 6520 MT AUKUM RD SOMERS | 35075488 |  |  | STS-POLE_DECA_REPL - 6520 MT AUKUM RDSOM | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.623 | -120.7 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K44 | 1341 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 72.8 | 72.8 |  |  | 23.25 | 49.55 | 49.55 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101421805 | RELW OH PRI INSP COMP JPOL REMT NOAC ESTR USA CCNT FMOB TER2 | Pole | 2019-04-09 | 2019-11-15 | COMP | 2019-04-09 | COMP | 2021-02-10 | 2019-04-16 | 2019-04-16 | [11 empty] | 2021-02-17 | 2021-02-10 | 2019-11-14 |  | 2019-11-14 | Q1 Work Plan | 2019-04-09 | W. Sac |  | 153662102 | 21142.22 | 22366 | -9834.2 | -347 | -347 | 6595.4 |  | 6595.4 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SOMERSET | Placerville |  |  | COMP | 115346478 | POLE_DECA_REPL - 6520 MT AUKUM RD SOMERS | 35075484 |  |  | STS-POLE_DECA_REPL - 6520 MT AUKUM RDSOM | DOCC | DOCC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6237 | -120.6998 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K44 | 1341 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.9 | 41.9 |  |  | 0 | 41.9 | 41.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101393634 | RELW OH PRI INSP COMP JPOL REMT NOAC ESTR USA CCNT FMOB TER2 | Pole | 2019-04-08 | 2019-11-15 | COMP | 2019-04-08 | COMP | 2021-02-10 | 2019-04-16 | 2019-04-16 | [11 empty] | 2021-02-17 | 2021-02-10 | 2019-11-14 |  | 2019-11-14 | Q1 Work Plan | 2019-04-08 | W. Sac |  | 153662102 | 20216.02 | 12957.1 | -11847 | -347 | -347 | 1881.8 |  | 1881.8 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SOMERSET | Placerville |  |  | COMP | 117123494 | POLE_BROK_REPL - 1S/O A/F 3757 OMO RANCH | 35188282 |  |  | STS-POLE_BROK_REPL - 1S/O A/F 3757 OMO R | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.5733 | -120.6682 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L45 |  | Y | 311 |  |  | 2021-02-08 07:00 | 2021-02-08 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101402832 | OH RELW PRI COMP ESTR REAR CCNT FMOB TER2 PRTO | Pole | 2020-10-06 | 2020-11-30 | COMP | 2020-10-06 | COMP | 2021-02-08 | [13 empty] | 2021-02-12 | 2021-02-08 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 6755.74 | 2599.5 | 2232.7 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | COMP | 117127577 | POLE_DECA_REPL - 1SW/O 4W/O 6001 LONE BA | 35188354 |  |  | STS-POLE_DECA_REPL - 1SW/O 4W/O 6001 LON | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.5988 | -120.7544 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 |  | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101401751 | RELW OH PRI COMP CLR JPOL REMT ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-11-30 | COMP | 2020-10-12 | COMP | 2021-02-11 | [13 empty] | 2021-02-16 | 2021-02-11 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 5430.95 | 2538.9 | 2496.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | COMP | 117127806 | POLE_DECA_REPL - 1SW/O 4W/O 6001 LONE BA | 35188359 |  |  |  | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.5983 | -120.7552 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 |  | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 41.8 | 41.8 |  |  | 4 | 40.8 | 40.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101401752 | RELW OH PRI CLR JPOL REMT NOAC SWRK ESTR BTKA REAR FMOB TER2 PRTO CCNT COMP | Pole | 2020-10-12 | 2020-12-01 | COMP | 2020-10-12 | COMP | 2021-02-09 | [13 empty] | 2021-02-12 | 2021-02-09 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 6050.12 | 2690.4 | 2605.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | COMP | 117164671 | POLE_DECA_REPL - 1E/O R/O 2981 OMO RANCH | 35188133 |  |  | STS-POLE_DECA_REPL - 1E/O R/O 2981 OMO R | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.5701 | -120.7011 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L44 |  | Y | 311 |  |  | 2021-02-16 07:00 | 2021-02-16 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 43.4 | 41 | 2.4 |  | 0 | 43.4 | 41 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101395615 | RELW OH PRI CUST COMP CLR RESD REMT CGI ESTR BTKA CCNT FMOB TER2 PRTO FSRP | Pole | 2020-09-23 | 2020-09-23 | COMP | 2020-09-23 | COMP | 2021-02-16 | [13 empty] | 2021-02-19 | 2021-02-16 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 10496.72 | 686.3 | 686.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | COMP | 117164675 | POLE_BROK_REPL - 1S/O 1E/O R/O 2981 OMO | 35188139 |  |  | STS-POLE_BROK_REPL - 1S/O 1E/O R/O 2981 | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.5696 | -120.7014 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L44 |  | Y | 311 |  |  | 2021-02-16 07:00 | 2021-02-16 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 43.4 | 41 | 2.4 |  | 0 | 43.4 | 41 | 2.4 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101395613 | RELW OH PRI CUST COMP CLR RESD REMT CGI ESTR BTKA CCNT FMOB TER2 PRTO FSRP | Pole | 2020-09-23 | 2020-09-23 | COMP | 2020-09-23 | COMP | 2021-02-16 | [13 empty] | 2021-02-19 | 2021-02-16 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 5756.18 | 505.5 | 505.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | COMP | 117165446 | POLE_BROK_REPL - 1S/O 1500 PARCEL RD SOM | 35188161 |  |  | STS-POLE_BROK_REPL - 1S/O 1500 PARCEL RD | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.5975 | -120.7171 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K4325 |  | Y | 311 |  |  | 2021-01-11 | 2021-01-11 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 81.8 | 81.8 |  |  | 0 | 0.8 | 0.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101395990 | RELW OH PRI COMP CLR JPOL REMT FIRE ESTR BTKA CCNT FMOB TER2 PRTO FSRP | Pole | 2020-10-13 | 2020-10-13 | COMP | 2020-10-13 | COMP | 2021-01-11 | [13 empty] | 2021-01-14 | 2021-01-11 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 2862.82 | 2018 | 2018 | 2018 | 2018 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | COMP | 117169876 | POLE_DECA_REPL - R/O 8521 CHARDONNAY LN | 35188333 |  |  | STS-POLE_DECA_REPL - R/O 8521 CHARDONNAY | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.5782 | -120.6718 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L45 | 10041 | Y | 311 |  |  | 2021-02-08 07:00 | 2021-02-08 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 42.7 | 42.7 |  |  | 3.75 | 41.7 | 41.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101417955 | RELW OH PRI COMP JPOL REMT ESTR BTKA FMOB TER2 PRTO CCNT | Pole | 2020-10-13 | 2020-10-19 | COMP | 2020-10-13 | COMP | 2021-02-08 | [13 empty] | 2021-02-12 | 2021-02-08 | 2020-05-06 |  | 2020-05-06 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 13324.5 | 3308.8 | 3052.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | COMP | 117323210 | POLE_DECA_REPL - #1/S/O SERV POLE TO 704 | 35189378 |  |  | STS-CRSS_BROK_REPL - #1/S/O SERV POLE TO | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6028 | -120.6942 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K44 |  | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 29.2 | 26.8 | 2.4 |  | 5 | 3.2 | 0.8 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101394643 | RELW OH PRI PGEA COMP CLR RESD REMT FIRE ESTR GO CCNT FMOB TER2 PRTO FSRP | Pole | 2020-10-06 | 2020-10-06 | COMP | 2020-10-06 | COMP | 2021-02-09 | [13 empty] | 2021-02-12 | 2021-02-09 | 2020-05-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 10740.77 | 527.5 | 527.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 114976195 | POLE_BROK_REPL - 6460 Slug Gulch RdSomer | 35062879 |  |  | STS-POLE_BROK_REPL - 6460 SLUG GULCH RDS | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6003 | -120.6405 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K4525 | 2017 | Y | 311 |  |  | 2021-03-05 07:00 | 2021-03-05 16:00 | Dispatched | CLICK | [6 empty] | 81.8 | 81.8 |  |  | 0.5 | 81.3 | 81.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101395771 | REGW OH PRI INSP CLR REMT ESTR FMOB TER2 | Pole | 2019-01-25 | 2019-01-25 | COMP | 2019-01-25 | [16 empty] | 2018-09-15 | 2019-09-15 |  | 2019-09-15 | Q1 Work Plan | 2019-02-28 | EEI |  | 153662102 | 11732.84 | 13284.2 | -10877.9 | 622.1 | 622.1 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SI | SOMERSET | Placerville |  |  | OPEN | 115524732 | POLE_BROK_REPL - 4001 Meyers CtSomerset | 35074277 |  |  | STS-POLE_BROK_REPL - 4001 MEYERS CTSOMER | ESTS | ESTS ERDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.6366 | -120.68 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K44 | 2005 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101394850 | RELW OH PRI INSP CLR JPOL REMT FMOB ESTR GO BTKA TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2018-12-17 | 2019-12-17 | 2020-10-25 | 2020-10-25 | 2021 CBP Plan | 2021-01-31 | Auburn |  | 153662102 | 1 | 168.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 116970818 | POLE_DECA_REPL - 1E/O 6620 SLUG GULCH RD | 35188407 |  |  | STS-POLE_DECA_REPL - 1E/O 6620 SLUG GULC | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6054 | -120.6366 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K4525 | 21483 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 47.9 | 45.5 | 2.4 |  | 0.5 | 47.4 | 45 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101395849 | OH PRI RESD ESTR FMOB TER2 PRTO RELW | Pole | 2020-10-13 | 2020-10-13 | COMP | 2020-10-13 | [16 empty] | 2019-04-06 | 2020-04-06 |  | 2020-04-06 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 18942.44 | 432.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 116979101 | POLE_BROK_REPL - AT 7741 BOONDOCK TR SOM | 35187576 |  |  | STS-POLE_BROK_REPL - AT 7741 BOONDOCK TR | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5991 | -120.649 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K4524 |  | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101395650 | RELW RESD OH SERV ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-06 | 2020-10-06 | COMP | 2020-10-06 | [16 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 4674.16 | 1460.4 | 1079.4 | 1080.7 | 1080.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 116979875 | POLE_BROK_REPL - 1E/O 6401 IRISH ACRES R | 35187599 |  |  | STS-POLE_BROK_REPL - 1E/O 6401 IRISH ACR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6027 | -120.6484 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K4524 | 21153 | Y | 311 |  |  | 2021-03-10 07:00 | 2021-03-10 16:00 | Scheduled | CLICK | [6 empty] | 43.5 | 43.5 |  |  | 0 | 43.5 | 43.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101419598 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-06 | 2020-10-06 | COMP | 2020-10-06 | [16 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 20377.29 | 3662.1 | 3376.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 116991767 | POLE_DECA_REPL - 1E/0 6960 MEHWALD LN. S | 35187955 |  |  | STS-POLE_DECA_REPL - 1E/0 6960 MEHWALD L | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6376 | -120.6374 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K45 |  | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-08 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101421092 | OH RELW PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-10-12 | COMP | 2020-10-12 | [16 empty] | 2019-04-09 | 2020-04-09 |  | 2020-04-09 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 5590.93 | 1018.3 | 1018.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117016225 | POLE_DECA_REPL - 1SW/O 1S/O AT 7601 FAIR | 35188174 |  |  | STS-POLE_DECA_REPL - 1SW/O 1S/O AT 7601 | CONS | CONS ERDY SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6018 | -120.6699 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K4521 |  | Y | 311 |  |  | 2021-03-01 07:00 | 2021-03-01 16:00 | Dispatched | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101395017 | RELW OH SERV RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-10-12 | 2020-12-01 | COMP | 2020-10-12 | [16 empty] | 2019-04-12 | 2020-04-12 | 2024-04-10 | 2024-04-10 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 3378.67 | 733.5 | 733.6 | 737.3 | 737.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117016750 | POLE_BROK_REPL - 2N/O AT 7531 FAIRPLAY R | 35188191 |  |  | STS-POLE_BROK_REPL - 2N/O AT 7531 FAIRPL | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6031 | -120.6733 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K4521 | 20599 | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101394989 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-10-13 | 2020-10-13 | COMP | 2020-10-13 | [16 empty] | 2019-04-12 | 2020-04-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 17872.79 | 3207.9 | 3208 | 737.3 | 737.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117021989 | POLE_BROK_REPL - 7184 PERRY CREEK RDSOME | 35188374 |  |  | STS-POLE_BROK_REPL - 7184 PERRY CREEK RD | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.611 | -120.6692 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K4516 | 1345 | Y | 311 |  |  | 2021-02-27 07:00 | 2021-02-27 16:00 | Dispatched | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 1.5 | 41.7 | 41.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101395179 | PRI RELW OH RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-09 | 2020-10-09 | COMP | 2020-10-09 | [16 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 18264.19 | 7079 | 6714.1 | 873.7 | 873.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117022749 | POLE_DECA_REPL - 2W/O 7184 PERRY CREEK R | 35188400 |  |  | STS-POLE_DECA_REPL - 2W/O 7184 PERRY CRE | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6117 | -120.671 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K4516 |  | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0.75 | 41.05 | 41.05 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101420638 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-09 | 2020-10-09 | COMP | 2020-10-09 | [16 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 7312.42 | 1675.3 | 1675.3 | 907.6 | 907.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117023053 | POLE_BROK_REPL - 3S/O 6628 GRIZZLY FLAT | 35188404 |  |  | STS-POLE_BROK_REPL - 3S/O 6628 GRIZZLY F | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6399 | -120.6594 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K45 |  | Y | 311 |  |  | 2021-03-09 07:00 | 2021-03-09 16:00 | Scheduled | CLICK | [6 empty] | 46.6 | 41.8 | 4.8 |  | 0 | 46.6 | 41.8 | 4.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101419901 | OH RELW PRI ESTR FMOB TER2 PRTO | Pole | 2020-10-13 | 2020-12-01 | COMP | 2020-10-13 | [16 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 13390.75 | 1127 | 894 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117114941 | POLE_DECA_REPL - 2S\O R/O 4041 SCREECH O | 35187938 |  |  | STS-POLE_DECA_REPL - 2S\O R/O 4041 SCREE | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5998 | -120.7023 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K44 |  | Y | 311 |  |  | 2021-03-16 07:00 | 2021-03-16 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101394545 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-10-13 | 2020-10-13 | COMP | 2020-10-13 | [16 empty] | 2019-04-28 | 2020-04-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 5354.47 | 1219.2 | 1138.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117115193 | POLE_DECA_REPL - 5969 OUTINGDALE RD.SOME | 35187958 |  |  | STS-POLE_DECA_REPL - 5969 OUTINGDALE RD. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6186 | -120.7221 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 | 41349 | Y | 311 |  |  | 2021-04-01 07:00 | 2021-04-01 16:00 | Scheduled | CLICK | [6 empty] | 41.2 | 41 | 0.2 |  | 0 | 41.2 | 41 | 0.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101401913 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-09-25 | 2020-09-25 | COMP | 2020-09-25 | [16 empty] | 2019-04-28 | 2020-04-28 |  | 2020-04-28 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 18858.04 | 1779.1 | 1779.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117123479 | POLE_BROK_REPL - R/O 3800 OMO RANCH RD S | 35188273 |  |  | STS-POLE_BROK_REPL - R/O 3800 OMO RANCH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5719 | -120.6681 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L45 | 11669 | Y | 311 |  |  | 2021-03-15 07:00 | 2021-03-15 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101402834 | RELW OH PRI JPOL ESTR GO REAR FMOB TER2 PRTO | Pole | 2020-10-01 | 2020-11-30 | COMP | 2020-10-01 | [16 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 18617.29 | 3502 | 3502 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117123492 | POLE_BROK_REPL - 1N/O 7314 JOHNSONS MINE | 35188277 |  |  | STS-POLE_BROK_REPL - 1N/O 7314 JOHNSONS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5704 | -120.6744 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L45 | 9955 | Y | 311 |  |  | 2021-03-13 07:00 | 2021-03-13 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101402918 | RELW OH PRI CLR ESTR REAR FMOB TER2 PRTO | Pole | 2020-09-21 | 2020-09-21 | COMP | 2020-09-21 | [16 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117126542 | POLE_DECA_REPL - 1N/O 6001 LONE BARN RD. | 35188331 |  |  | STS-POLE_DECA_REPL - 1N/O 6001 LONE BARN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5989 | -120.7504 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 |  | Y | 311 |  |  | 2021-03-25 07:00 | 2021-03-25 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101401761 | RELW OH RESD PRI CLR JPOL ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-06 | 2020-12-01 | COMP | 2020-10-06 |  |  | 2020-09-09 | 2020-09-09 | [12 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117126997 | POLE_BROK_REPL - R/O 6195 LONE BARN RD. | 35188341 |  |  | STS-POLE_BROK_REPL - R/O 6195 LONE BARN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5981 | -120.7499 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 | 22759 | Y | 311 |  |  | 2021-03-12 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | [6 empty] | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101401758 | RELW OH PRI CLR JPOL REMT NOAC SWRK ESTR BTKA REAR FMOB TER2 PRTO | Pole | 2020-12-02 | 2020-12-04 | COMP | 2020-10-06 | [16 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 16940.91 | 42.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117127362 | POLE_BROK_REPL - 3W/O 6001 LONE BARN RD. | 35188350 |  |  | STS-POLE_BROK_REPL - 3W/O 6001 LONE BARN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.599 | -120.7527 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 | 22759 | Y | 311 |  |  |  |  | Started | Order Operation | [6 empty] | 57.6 | 56 | 1.6 |  | 0 | 57.6 | 56 | 1.6 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101401753 | RELW OH PRI CLR JPOL REMT NOAC REAR SWRK ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-12-01 | COMP | 2020-10-09 | [16 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 23128.37 | 2732.1 | 2732.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117129655 | POLE_BROK_REPL - 5766 VACATION BLVD SOME | 35188399 |  |  | STS-POLE_BROK_REPL - 5766 VACATION BLVD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6146 | -120.726 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K4319 |  | Y | 311 |  |  | 2021-03-13 07:00 | 2021-03-13 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101401605 | RELW OH SERV CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-12 | 2020-10-12 | COMP | 2020-10-12 | [16 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 7141.49 | 556.5 | 428.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117129733 | POLE_BROK_REPL - R/O 5758 VACATION BLVD. | 35188405 |  |  | STS-POLE_BROK_REPL - R/O 5758 VACATION B | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6145 | -120.7262 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K4319 |  | Y | 311 |  |  | 2021-03-13 07:00 | 2021-03-13 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101401604 | RELW OH SERV CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO CCNT COMP | Pole | 2020-10-14 | 2020-10-14 | COMP | 2020-10-14 | [16 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 4993.72 | 2170.2 | 1865.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117159434 | POLE_BROK_REPL - 2S/O 7920 FAIRPLAY RDSO | 35147962 |  |  | STS-POLE_BROK_REPL - 2S/O 7920 FAIRPLAY | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5915 | -120.6613 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L45 |  | Y | 311 |  |  | 2021-02-19 07:00 | 2021-02-19 16:00 | Dispatched | CLICK | [6 empty] | 41.9 | 41.9 |  |  | 0.25 | 41.65 | 41.65 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101403155 | RELW REMT OH PRI JPOL ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-28 | 2020-09-28 | COMP | 2020-09-28 | [16 empty] | 2019-05-04 | 2020-05-04 |  | 2020-05-04 | 2021 CBP Plan | 2020-06-30 | W. Sac |  | 153662102 | 11168.91 | 1601.9 | 1385.6 | 1068.9 | 1068.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117161120 | POLE_BROK_REPL - HOUSE 3200 RENDEZVUOS L | 35188055 |  |  | STS-POLE_BROK_REPL - HOUSE 3200 RENDEZVU | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5687 | -120.6912 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L44 | 20879 | Y | 311 |  |  | 2021-03-12 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0 | 42.7 | 42.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101417810 | RELW OH PRI CUST CLR RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-10-06 | 2020-10-06 | COMP | 2020-10-06 | [16 empty] | 2019-05-04 | 2020-05-04 | 2024-05-02 | 2024-05-02 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 16814.95 | 42.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117163416 | POLE_BROK_REPL - 2S/O C/O MELLOWOOD DR/O | 35188103 |  |  | STS-POLE_BROK_REPL - 2S/O C/O MELLOWOOD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5666 | -120.7032 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L44 |  | Y | 311 |  |  | 2021-03-24 07:00 | 2021-03-24 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 44.2 | 41.8 | 2.4 |  | 0 | 44.2 | 41.8 | 2.4 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101395564 | RELW CLR OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-09-10 | 2020-09-10 | COMP | 2020-09-10 | [16 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117167045 | POLE_DECA_REPL - 2321 APACHE PASS RDSOME | 35188202 |  |  | STS-POLE_DECA_REPL - 2321 APACHE PASS RD | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5945 | -120.713 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L44 | 20899 | Y | 311 |  |  | 2021-02-26 07:00 | 2021-02-26 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101395965 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-10-06 | 2020-10-06 | COMP | 2020-10-06 | [16 empty] | 2019-05-06 | 2020-05-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 16301.73 | 3094.5 | 2770.2 | 737.3 | 737.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117171439 | POLE_DECA_REPL - 2S/O 2W/O R/O 3160 OMO | 35188375 |  |  | STS-POLE_DECA_REPL - 2S/O 2W/O R/O 3160 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5672 | -120.6951 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L44 |  | Y | 311 |  |  | 2021-03-11 07:00 | 2021-03-11 16:00 | Dispatched | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101417799 | RELW OH PRI CUST CLR RESD REMT ESTR GO REAR FMOB TER2 PRTO FSRP | Pole | 2020-10-06 | 2020-10-06 | COMP | 2020-10-06 | [16 empty] | 2019-05-06 | 2020-05-06 | 2020-07-30 | 2020-07-30 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 5472.76 | 360.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117179873 | POLE_BROK_REPL - 400SOMERSET95684 | 35188516 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5529 | -120.6936 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L44 |  | Y | 311 |  |  | 2021-03-05 07:00 | 2021-03-05 16:00 | Scheduled | CLICK | [6 empty] | 41.8 | 41.8 |  |  | 0 | 41.8 | 41.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103915442 | RELW PRI OH CLR RESD REMT NOAC ESTR FMOB TER2 PRTO | Pole | 2020-10-13 | 2020-10-13 | COMP | 2020-10-13 | [16 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 4372.31 | 579.1 | 579.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117252871 | POLE_DECA_REPL - 1\N\O 7216 TIGER EYE LN | 35189419 |  |  | STS-POLE_DECA_REPL - 1\N\O 7216 TIGER EY | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6341 | -120.6886 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K44 |  | Y | 311 |  |  | 2021-02-27 07:00 | 2021-02-27 16:00 | Dispatched | CLICK | [6 empty] | 45.1 | 42.7 | 2.4 |  | 0 | 45.1 | 42.7 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101393586 | PRI OH RELW PRTO ESTR FMOB TER2 FSRP | Pole | 2020-10-13 | 2020-12-01 | COMP | 2020-10-13 | [16 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 9790.7 | 335.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117322023 | POLE_DECA_REPL - 2W/O 5374 DAGOSTINI DR | 35189366 |  |  | STS-POLE_DECA_REPL - 2W/O 5374 DAGOSTINI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5549 | -120.7363 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L4323 | 11661 | Y | 311 |  |  | 2021-03-08 07:00 | 2021-03-08 16:00 | Scheduled | CLICK | [6 empty] | 44.2 | 41.8 | 2.4 |  | 0 | 44.2 | 41.8 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101393833 | RELW OH PRI CLR ESTR BTKA USA FMOB PRTO TER2 | Pole | 2020-10-13 | 2020-12-01 | COMP | 2020-10-13 | [16 empty] | 2019-05-25 | 2020-05-25 |  | 2020-05-25 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117322026 | POLE_DECA_REPL - 1W/O 2S/O 5374 DAGOSTIN | 35189369 |  |  | STS-POLE_DECA_REPL - 1W/O 2S/O 5374 DAGO | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.554 | -120.7335 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L4323 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24 | 21.6 | 2.4 |  | 0 | 24 | 21.6 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101393828 | RELW OH PRI CLR ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-10-05 | 2021-01-08 | COMP | 2020-10-05 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-05-25 | 2020-05-25 |  | 2020-05-25 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117326094 | POLE_BROK_REPL - 3S/O 6360 MEYERS LN SOM | 35189427 |  |  | STS-POLE_BROK_REPL - 3S/O 6360 MEYERS LN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6338 | -120.6842 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K44 |  | Y | 311 |  |  |  |  | Started | Order Operation | [6 empty] | 28.9 | 27.7 | 1.2 |  | 0 | 28.9 | 27.7 | 1.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101394772 | RELW OH PRI CLR JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-11-20 | 2020-11-20 | COMP | 2020-11-10 | [16 empty] | 2019-05-27 | 2020-05-27 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | 25907.36 | 1254.7 | -558.3 | -452.5 | -452.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 118236461 | POLE_BROK_REPL - 7695 PERRY CREEK RD SOM | 35189102 |  |  | STS-POLE_BROK_REPL - 7695 PERRY CREEK RD | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5996 | -120.6575 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K4523 | 1383 | Y | 311 |  |  | 2021-02-23 07:00 | 2021-02-23 16:00 | Dispatched | CLICK | [6 empty] | 42.7 | 42.7 |  |  | 0.75 | 41.95 | 41.95 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101395581 | OH ESTR TER2 FSRP RELW | Pole | 2020-10-02 | 2020-10-02 | COMP | 2020-10-02 | [16 empty] | 2019-07-08 | 2020-07-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-11-15 | TRC |  | 153662102 | 13574.85 | 3292.3 | 2094.1 | 854.8 | 854.8 |  |  |  | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 116971137 | POLE_BROK_REPL - A/F 6440 LADYHAWKE DR S | 35188423 |  |  | STS-POLE_BROK_REPL - A/F 6440 LADYHAWKE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6412 | -120.6649 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J45 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.9 | 12.9 |  |  | 0 | 12.9 | 12.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101396303 | PRI RELW OH JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-09-25 | 2021-01-08 | COMP | 2020-09-25 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-06 | 2020-04-06 |  | 2020-04-06 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117021927 | POLE_BROK_REPL - 2521 OMO RANCH RD SOMER | 35188369 |  |  | STS-POLE_BROK_REPL - 2521 OMO RANCH RD S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5656 | -120.7201 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | L43 | 10015 | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Scheduled | CLICK | [6 empty] | 14.1 | 14.1 |  |  | 0 | 14.1 | 14.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101394408 | RELW OH PRI TNT CLR JPOL REMT TRAF FLAG ESTR BTKA USA TER2 FSRP | Pole | 2021-01-11 | 2021-02-09 | COMP | 2020-10-15 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-03-28 | 2019-10-31 | 2024-03-26 | 2024-03-26 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 9683.86 | 149.5 | 149.5 | 149.5 | 149.5 |  |  |  | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117022417 | POLE_BROK_REPL - 5951 MT AUKUM RDSOMERSE | 35188384 |  |  | STS-POLE_BROK_REPL - 5951 MT AUKUM RDSOM | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 38.6462 | -120.6868 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | J44 | 21137 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 53.8 | 53.8 |  |  | 0 | 53.8 | 53.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101417550 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO | Pole | 2020-09-25 | 2021-01-08 | COMP | 2020-09-25 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 25867.95 | 316.2 | 213.5 | 213.5 | 213.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117119667 | POLE_BROK_REPL - 7650 BUZZARDS GULCH RD. | 35188138 |  |  | STS-POLE_BROK_REPL - 7650 BUZZARDS GULCH | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6041 | -120.7386 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | [6 empty] | 33.9 | 33.9 |  |  | 0 | 33.9 | 33.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101401789 | RELW OH SERV CLR REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2020-10-15 | 2020-12-11 | COMP | 2020-10-15 | [16 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 9819.17 | 407.5 | 407.5 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117127105 | POLE_BROK_REPL - 1W/O 6001 LONE BARN RD. | 35188346 |  |  | STS-POLE_BROK_REPL - 1W/O 6001 LONE BARN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5982 | -120.751 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12 | 12 |  |  | 0 | 12 | 12 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101401755 | RELW OH PRI CLR JPOL REMT NOAC SWRK ESTR BTKA REAR FMOB TER2 PRTO | Pole | 2020-12-04 | 2021-01-08 | COMP | 2020-10-13 |  |  | 2021-01-08 | 2021-01-08 | [12 empty] | 2019-04-30 | 2020-04-30 |  | 2020-04-30 | 2021 CBP Plan | 2020-10-31 | EEI |  | 153662102 | 8579.36 | 234.6 | 149.5 | 149.5 | 149.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOMERSET | Placerville |  |  | OPEN | 117136894 | POLE_DECA_REPL - 5615 VACATION BLVD SOME | 35188548 |  |  | STS-POLE_DECA_REPL - 5615 VACATION BLVD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6146 | -120.7317 |  | TIER 2 | 3 | 15366-2102, APPLE HILL | K43 | 21327 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 30.9 | 30.9 |  |  | 0 | 30.9 | 30.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101415783 | RELW JPOL OH PRI CLR RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2021-01-11 | 2021-01-13 | COMP | 2020-10-12 |  |  | 2021-01-13 | 2021-01-13 | [12 empty] | 2019-05-01 | 2020-05-01 |  | 2020-05-01 | 2021 CBP Plan | 2020-11-15 | EEI |  | 153662102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | SOUTH LAKE TAHOE | Placerville |  |  | OPEN | 117219777 | POLE_BROK_REPL - 1N/O AT LOT 39 ECHO SUM | 35214812 |  |  | STS-POLE_BROK_REPL - 1N/O AT LOT 39 ECHO | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.8095 | -120.0282 |  | TIER 2 | 918 | 15803-1101, ECHO SUMMIT | G60 | 8922 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101396573 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-12 | 2020-05-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 158031101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SI | TRUCKEE | Auburn |  |  | OPEN | 117409548 | POLE_DECA_REPL - #4NW #5W/O 300 SUGAR BO | 35215906 |  |  | STS-POLE_DECA_REPL - #4NW #5W/O 300 SUGA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 39.3123 | -120.3371 |  | TIER 2 | 778 | 15259-1102, SUMMIT | K2721 | 6813 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100000889 | OH RELW PRI CLR JPOL RESD ESTR GO REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-07 | 2020-06-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 152591102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CAZADERO | Geyserville |  |  | COMP | 120047534 | POLE_DECA_REPL - Lake Sonoma Wildlife Ar | 35216352 |  |  | B3-POLE_DECA_REPL - LAKE SONOMA WILDLIF | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-20 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7005 | -123.0924 |  | TIER 2 | 125 | 04289-1101, GEYSERVILLE | CC18 |  | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 46.2 | 41 | 5.2 |  | 12 | 45.2 | 40 | 5.2 |  | EC | B | Pole | Decayed/Rotten | Replace |  | 103606885 | RELW OH PRI INSP COMP SPCR ESTR GO REAR CCNT FMOB TER2 | Pole | 2020-12-15 | 2021-01-28 | COMP | 2020-12-15 | COMP | 2021-02-17 | [13 empty] | 2021-02-18 | 2021-02-17 | 2021-02-17 |  | 2021-02-17 | B tag clean up 11/19/2020 |  | Santa Rosa |  | 042891101 | 36273.8 | 8854.6 | 7097.6 | 1336 | 1336 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-11-19
North | SO | CAZADERO | Santa Rosa |  |  | OPEN | 116748505 | POLE_DECA_REPL - 27801 SKAGGS SPRINGS RD | 35214878 |  |  | STS-POLE_DECA_REPL - 27801 SKAGGS SPRING | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.6713 | -123.2898 |  | TIER 2 | 252 | 04286-1101, ANNAPOLIS | DD13 | 4585 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101968295 | RELW OH PRI CLR ESTR RTRN FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-16 | 2020-03-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042861101 | 1 | 13.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CAZADERO | Santa Rosa |  |  | OPEN | 116749066 | POLE_BROK_REPL - #7E #13S STEWARTS PT-SK | 35214887 |  |  | STS-POLE_BROK_REPL - #7E #13S STEWARTS P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.6559 | -123.2831 |  | TIER 2 | 252 | 04286-1101, ANNAPOLIS | DD14 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102199992 | RELW OH PRI CLR REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-16 | 2020-03-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042861101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CAZADERO | Santa Rosa |  |  | OPEN | 116751169 | POLE_BROK_REPL - 29564 SKYLINE DR 2PNE C | 35214901 |  |  | STS-POLE_BROK_REPL - 29564 SKYLINE DR 2P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.659 | -123.2621 |  | TIER 2 | 252 | 04286-1101, ANNAPOLIS | DD14 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101968278 | RELW OH PRI CLR REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042861101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CAZADERO | Santa Rosa |  |  | OPEN | 116751220 | POLE_DECA_REPL - 29564 SKYLINE DR 1PNECA | 35214906 |  |  | STS-POLE_DECA_REPL - 29564 SKYLINE DR 1P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.658 | -123.2627 |  | TIER 2 | 252 | 04286-1101, ANNAPOLIS | DD14 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101968277 | RELW OH PRI PGEA CLR REMT ESTR RTRN FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042861101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CAZADERO | Santa Rosa |  |  | OPEN | 116751800 | POLE_DECA_REPL - 29564 SKYLINE DR 7PNE C | 35214936 |  |  | STS-POLE_DECA_REPL - 29564 SKYLINE DR 7P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.6638 | -123.2529 |  | TIER 2 | 252 | 04286-1101, ANNAPOLIS | DD14 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101968283 | RELW OH PRI PGEA CLR REMT NOAC ESTR RTRN FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042861101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CAZADERO | Santa Rosa |  |  | OPEN | 116763415 | POLE_BROK_REPL - #13S STEWARTS PT-SKAGGS | 35215061 |  |  | STS-POLE_BROK_REPL - #13S STEWARTS PT-SK | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.6601 | -123.2928 |  | TIER 2 | 252 | 04286-1101, ANNAPOLIS | DD13 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102213264 | RELW OH PRI CLR RESD REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042861101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CAZADERO | Santa Rosa |  |  | OPEN | 116792585 | POLE_BROK_REPL - 29564 SKYLINE DR 9PNE/1 | 35215211 |  |  | STS-POLE_BROK_REPL - 29564 SKYLINE DR 9P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.6641 | -123.2509 |  | TIER 2 | 252 | 04286-1101, ANNAPOLIS | DD14 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101968288 | RELW OH PRI CLR REMT NOAC ESTR REAR RTRN FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042861101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CAZADERO | Santa Rosa |  |  | OPEN | 116792586 | POLE_BROK_REPL - 29564 SKYLINE DR 9PNE/2 | 35215215 |  |  | STS-POLE_BROK_REPL - 29564 SKYLINE DR 9P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.664 | -123.2501 |  | TIER 2 | 252 | 04286-1101, ANNAPOLIS | DD14 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101968289 | RELW OH PRI CLR REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042861101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CAZADERO | Santa Rosa |  |  | OPEN | 114894614 | POLE_BROK_REPL - Morhardt ridge rdCa | 35062494 |  |  | POLE_BROK_REPL - MORHARDT RIDG | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.5649 | -123.1216 |  | TIER 2 | 201 | 04285-1121, FORT ROSS | FF18 | 2967 | Y | 311 |  |  |  |  | Returned | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 62.8 | 62.8 |  |  | 0.25 | 62.55 | 62.55 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102038954 | REGW OH PRI INSP CLR REMT FIRE NOAC ESTR GO REAR USA FMOB TER2 | Pole | 2019-02-01 | 2019-03-07 | COMP | 2019-02-01 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-07-30 | 2019-07-30 |  | 2019-07-30 | Q1 Work Plan | 2019-02-28 | QUES |  | 042851121 | 18215.35 | 9400 | -9614.1 | 1885.9 | 1885.9 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SO | CAZADERO | Santa Rosa |  |  | OPEN | 115098301 | REPL POLE:1E/O 30930 KING RIDGE RD,Cazad | 35064163 |  |  | REPL POLE:1E/O 30930 KING RIDGE RD C | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6209 | -123.2392 |  | TIER 2 | 201 | 04285-1121, FORT ROSS | EE15 |  | Y | 311 |  |  |  |  | Returned | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 15.7 | 15.7 |  |  | 0 | 15.7 | 15.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102039363 | POHW OH TNT JPOL TER2 | Pole | 2019-03-28 | 2019-04-08 | COMP | 2019-03-28 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-10-29 | 2019-10-29 |  | 2019-10-29 | Q1 Work Plan | 2019-07-01 | PIKEENG |  | 042851121 | 6680.06 | 1580.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | SO | CAZADERO | Santa Rosa |  |  | OPEN | 116759722 | POLE_BROK_REPL - 4NW/O 22677 SKGS SPR RD | 35202156 |  |  | STS-POLE_BROK_REPL - 4NW/O 22677 SKGS SP | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6633 | -123.2383 |  | TIER 2 | 252 | 04286-1101, ANNAPOLIS | DD15 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 54.7 | 53.5 | 1.2 |  | 0 | 54.7 | 53.5 | 1.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 102039237 | RELW OH PRI CLR REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-13 | 2021-01-13 | COMP | 2021-01-13 | [16 empty] | 2019-03-18 | 2020-03-18 | 2020-10-07 | 2020-10-07 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042861101 | 27535.31 | 1237.5 | 0 | 1680.1 | 1680.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CLOVERDALE | Geyserville |  |  | OPEN | 116803091 | POLE_DECA_REPL - 23900 OAK HOLLOW RDCLOV | 35202226 |  |  | STS-POLE_DECA_REPL - 23900 OAK HOLLOW RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land JointPole |  |  | 38.728 | -122.9683 |  | TIER 2 | 125 | 04289-1101, GEYSERVILLE | CC22 | 12669 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 55.8 | 54.4 | 1.4 |  | 0 | 55.8 | 54.4 | 1.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102036406 | RELW OH PRI CLR JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-03 |  | COMP | 2021-02-03 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-09-26 | 2020-09-26 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042891101 | 24655.88 | 472.7 | 472.7 | 472.7 | 472.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CLOVERDALE | Geyserville |  |  | OPEN | 117117864 | POLE_BROK_REPL - 1255 HIATT RD CLOVERDAL | 35214923 |  |  | STS-POLE_BROK_REPL - 1255 HIATT RD CLOVE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.7661 | -123.0169 |  | TIER 2 | 37 | 04282-1102, CLOVERDALE | BB20 | 429006 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101965972 | RELW OH PRI ESTR GO FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042821102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CLOVERDALE | Geyserville |  |  | OPEN | 117119083 | POLE_DECA_REPL - #6S/O 1255 HIATT RDCLOV | 35202289 |  |  | STS-POLE_DECA_REPL - #6S/O 1255 HIATT RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.7636 | -123.0203 |  | TIER 2 | 37 | 04282-1102, CLOVERDALE | BB20 | 429006 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102037954 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2020-09-11 | 2020-09-11 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042821102 | 1 | 116.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CLOVERDALE | Geyserville |  |  | OPEN | 117119291 | POLE_DECA_REPL - #1N/ #4S/O 1255 HIATT R | 35214934 |  |  | STS-POLE_DECA_REPL - #1N/ #4S/O 1255 HIA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.7647 | -123.0199 |  | TIER 2 | 37 | 04282-1102, CLOVERDALE | BB20 | 429006 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102037614 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042821102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CLOVERDALE | Geyserville |  |  | OPEN | 117120516 | POLE_DECA_REPL - #8W/O 26747 DUTCHER CRE | 35202299 |  |  | STS-POLE_DECA_REPL - #8W/O 26747 DUTCHER | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.761 | -123.0026 |  | TIER 2 | 125 | 04289-1101, GEYSERVILLE | BB21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.6 | 13.6 |  |  | 0 | 13.6 | 13.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102038745 | RELW OH PRI CLR BTKA JPOL REMT ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-05 |  | COMP | 2021-02-05 | [16 empty] | 2019-04-29 | 2020-04-29 | 2020-09-18 | 2020-09-18 | 2021 CBP Plan | 2021-02-28 | QUES |  | 042891101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CLOVERDALE | Geyserville |  |  | OPEN | 117124915 | POLE_BROK_REPL - #1W/O #1S/O 1490 HOT SP | 35215006 |  |  | STS-POLE_BROK_REPL - #1W/O #1S/O 1490 HO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.7799 | -123.034 |  | TIER 2 | 37 | 04282-1102, CLOVERDALE | BB20 | 752613 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102037941 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042821102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CLOVERDALE | Geyserville |  |  | OPEN | 117126975 | POLE_DECA_REPL - #5W/O #3S/O 28243 CLOBE | 35202373 |  |  | STS-POLE_DECA_REPL - #5W/O #3S/O 28243 C | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land JointPole |  |  | 38.7755 | -123.0073 |  | TIER 2 | 37 | 04282-1102, CLOVERDALE | BB2101 | 736078 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 46.9 | 46.9 |  |  | 0 | 46.9 | 46.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101965792 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-12 |  | COMP | 2021-02-12 | [16 empty] | 2019-04-30 | 2020-04-30 | 2020-09-12 | 2020-09-12 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042821102 | 19796.45 | 238.8 | 238.8 | 174 | 174 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CLOVERDALE | Geyserville |  |  | COMP | 116985619 | POLE_DECA_REPL - 1NO 3SE/O 484 CLOVERCRE | 35087762 |  |  |  | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.8171 | -123.0258 |  | TIER 2 | 104 | 04282-1101, CLOVERDALE | AA2008 | 2813 | Y | 311 |  |  | 2021-02-16 07:00 | 2021-02-16 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 78.9 | 78.9 |  |  | 12.5 | 40 | 40 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103051704 | RELW OH PRI INSP COMP CLR JPOL RESD FIRE ESTR REAR CCNT PROG FMOB TER2 | Pole | 2019-08-05 | 2019-08-13 | COMP | 2019-08-02 | COMP | 2021-02-16 | 2020-06-04 | 2020-06-04 | [11 empty] | 2021-02-18 | 2021-02-16 | 2019-08-28 |  | 2019-08-28 | Q1 Work Plan |  | Santa Rosa |  | 042821101 | 15173.93 | 25331.9 | 2818.5 | 2594 | 2594 | 0 |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SO | CLOVERDALE | Geyserville |  |  | OPEN | 117117069 | POLE_DECA_REPL - R/O 900 HIATT RDCLOVERD | 35170225 |  |  | STS-POLE_DECA_REPL - R/O 900 HIATT RDCLO | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7692 | -123.0117 |  | TIER 2 | 37 | 04282-1102, CLOVERDALE | BB20 | 429006 | Y | 311 |  |  | 2021-02-22 07:00 | 2021-02-22 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 45.4 | 42.8 | 2.6 |  | 0 | 45.4 | 42.8 | 2.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101965968 | RELW OH PRI ESTR GO FMOB TER2 PRTO FSRP | Pole | 2020-04-29 | 2020-08-22 | COMP | 2020-04-29 | [16 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-02 | Santa Rosa |  | 042821102 | 36618.35 | 2925.3 | 2925.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | CLOVERDALE | Geyserville |  |  | OPEN | 117123308 | POLE_BROK_REPL - #12E/O#3S/O R/O 16430 C | 35145904 |  |  | STS-POLE_BROK_REPL - #12E/O#3S/O R/O 164 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.7842 | -123.0983 |  | TIER 2 | 37 | 04282-1102, CLOVERDALE | BB18 | 993 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 53.7 | 52.4 | 1.3 |  | 0 | 53.7 | 52.4 | 1.3 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101965694 | PRI OH RELW JAR GO REAR FMOB TER2 PRTO | Pole | 2020-06-17 | 2020-09-01 | COMP | 2020-03-06 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-04-29 | 2019-10-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 042821102 | 28585.02 | 18279.7 |  |  |  | 221.6 |  | 221.6 |  | Y | MPP File Only | N |  | Y | 2020-08-25
North | SO | COTATI | Petaluma |  |  | OPEN | 117016989 | POLE_DECA_REPL - 9150 WATER RDCOTATI9492 | 35202204 |  |  | STS-POLE_DECA_REPL - 9150 WATER RDCOTATI | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.3133 | -122.7104 |  | TIER 2 | 773 | 04227-1104, COTATI | LL2812 | 14631 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 47.1 | 46.1 | 1 |  | 0 | 47.1 | 46.1 | 1 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101996494 | RELW OH PRI INSP CLR JPOL REMT FIRE SWRK ESTR TER2 BTKA USA FMOB FSRP | Pole | 2021-02-01 |  | COMP | 2021-02-01 | [16 empty] | 2019-04-12 | 2020-04-12 | 2020-08-22 | 2020-08-22 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042271104 | 34871.66 | 532.1 | 125.7 | 125.7 | 125.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | COTATI | Petaluma |  |  | OPEN | 117071464 | POLE_BROK_REPL - #2 W/O MB 807 W SIERRA | 35202425 |  |  | STS-POLE_BROK_REPL - #2 W/O MB 807 W SIE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.323 | -122.7208 |  | TIER 2 | 773 | 04227-1104, COTATI | LL2806 | 3319 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101996052 | RELW OH PRI INSP JPOL REMT FIRE FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2020-09-08 | 2020-09-08 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042271104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | COTATI | Petaluma |  |  | OPEN | 115098504 | REPL POLE:#3 E/O GROVE ST ON MADRONE AVE | 35063572 |  |  |  | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3294 | -122.7268 |  | TIER 2 | 773 | 04227-1104, COTATI | LL2705 |  | Y | 311 |  |  | 2021-05-15 07:00 | 2021-05-15 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 69.9 | 50.1 | 19.8 |  | 0 | 69.9 | 50.1 | 19.8 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101991062 | POHW OH TNT JPOL TER2 | Pole | 2019-04-18 | 2019-07-05 | COMP | 2019-04-18 |  |  | 2019-05-16 | 2019-05-16 | [12 empty] | 2018-10-29 | 2019-10-29 |  | 2019-10-29 | Q1 Work Plan | 2019-07-01 | Santa Rosa |  | 042271104 | 29877.81 | 5799 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
North | SO | Forestville | Santa Rosa |  |  | OPEN | 117690532 | POLE _ BROK _ REPL_#1WEST 7050 GLOVANETT | 35216318 |  |  | STS-POLE _ BROK _ REPL_#1WEST 7050 GLOVA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.4678 | -122.909 |  | TIER 2 | 146 | 04209-1101, MIRABEL | HH2323 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102001641 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042091101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | GEYSERVILLE | Geyserville |  |  | OPEN | 116722742 | POLE_BROK_REPL - #3 ON LINE N/O CO#2493 | 35202121 |  |  | STS-POLE_BROK_REPL - #3 ON LINE N/O CO#2 | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6939 | -122.8181 |  | TIER 2 | 145 | 04289-1102, GEYSERVILLE | DD25 |  | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 15.4 | 15.4 |  |  | 0 | 15.4 | 15.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101977425 | RELW OH PRI PGEA CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-11 | 2020-12-11 | COMP | 2020-12-11 | [16 empty] | 2019-03-13 | 2020-03-13 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042891102 | 6141 | 2217.4 | 1837.2 | -244.4 | -244.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | GEYSERVILLE | Geyserville |  |  | COMP | 114747548 | REPL POLE - 12805 SKAGGS SPRING | 35050607 |  |  | REPL POLE - 12805 SKAGGS SPRGS | DOCC | DOCC CONT SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.6973 | -123.0984 |  | TIER 2 | 125 | 04289-1101, GEYSERVILLE | DD18 | 8795 | Y | 311 |  |  | 2021-02-17 07:00 | 2021-02-17 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 85.1 | 85.1 |  |  | 42.5 | 40 | 40 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103615047 | POHW OH PRI COMP CLR NOAC ESTR OTHR XMPT CCNT XDOC TER2 | Pole | 2018-11-07 | 2018-11-07 | COMP | 2018-11-07 | COMP | 2021-02-17 | 2019-10-09 | 2019-10-09 | [11 empty] | 2021-02-18 | 2021-02-17 | 2019-06-18 | 2019-08-16 | 2019-08-16 | Q1 Work Plan |  | UNASSIGNED |  | 042891101 | 26108.32 | 24391.3 | 6174.5 |  |  | 230.3 |  | 230.3 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SO | GEYSERVILLE | Geyserville |  |  | OPEN | 116819593 | POLE_DECA_REPL - 1W/O 2S/O HOUSE 3400 GE | 35136808 |  |  | REPL 6 POLES - 4000 GEYSERS RD | DOCC | DOCC ERDY SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-07-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7075 | -122.841 |  | TIER 2 | 145 | 04289-1102, GEYSERVILLE | CC25 |  | Y | 311 |  |  | 2020-12-08 | 2020-12-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 3 | 0 | 0 | 218.8 | 218.8 |  |  |  | 67.2 | 67.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102037663 | REGW OH PRI REMT SWRK ESTR BTKA FMOB TER2 PRTO | Pole | 2019-11-04 | 2020-03-06 | COMP | 2019-11-02 | [16 empty] | 2019-03-23 | 2020-03-23 |  | 2020-03-23 | circuit based plan 2.14 |  | UNASSIGNED |  | 042891102 | 71646.98 | 51762.6 | 22156 | 100341.1 | 100341.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SO | GEYSERVILLE | Geyserville |  |  | OPEN | 116819595 | POLE_DECA_REPL - 3S/O 4000 GEYSERS RDGEY | 35136808 |  |  | REPL 6 POLES - 4000 GEYSERS RD | DOCC | DOCC ERDY SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-07-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7098 | -122.8425 |  | TIER 2 | 145 | 04289-1102, GEYSERVILLE | CC25 |  | Y | 311 |  |  | 2020-12-08 | 2020-12-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 3 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101957559 | REGW OH PRI REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2019-11-04 | 2020-03-06 | COMP | 2019-11-02 | [16 empty] | 2019-03-23 | 2020-03-23 | 2020-10-05 | 2020-10-05 | circuit based plan 2.14 |  | UNASSIGNED |  | 042891102 | 71646.98 | 51762.6 | 22156 | 100341.1 | 100341.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SO | GEYSERVILLE | Geyserville |  |  | OPEN | 116819596 | POLE_BROK_REPL - 4S/O 4000 GEYSERS RD GE | 35136808 |  |  | REPL 6 POLES - 4000 GEYSERS RD | DOCC | DOCC ERDY SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-07-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.7093 | -122.8425 |  | TIER 2 | 145 | 04289-1102, GEYSERVILLE | CC25 | 12069 | Y | 311 |  |  | 2020-12-08 | 2020-12-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 3 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101957561 | REGW OH PRI REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2019-11-04 | 2020-03-06 | COMP | 2019-11-02 | [16 empty] | 2019-03-23 | 2020-03-23 |  | 2020-03-23 | circuit based plan 2.14 |  | UNASSIGNED |  | 042891102 | 71646.98 | 51762.6 | 22156 | 100341.1 | 100341.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SO | GLEN ELLEN | Santa Rosa |  |  | OPEN | 116155547 | POLE_BROK_REPL - 4052 Lakeside RdGlen El | 35091192 |  |  | STS-POLE_BROK_REPL - 4052 LAKESIDE RDGLE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-04-20 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3694 | -122.5362 |  | TIER 2 | 57 | 04307-1102, DUNBAR | KK3209 | 5285 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 53.7 | 53.7 |  |  | 0 | 53.7 | 53.7 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 102004362 | RELW OH PRI PATR FIRE TRAF ESTR RTRN FMOB TER2 | Pole | 2019-11-24 | 2019-12-23 | COMP | 2019-11-24 |  |  | 2019-07-30 | 2019-07-30 | [12 empty] | 2019-02-07 | 2020-02-07 | 2021-05-18 | 2021-05-18 | B tag clean up 2/19/2021 | 2019-09-10 | PIKEENG |  | 043071102 | [9 empty] | N | MPP File Only | N |  | Y | 2021-02-19
North | SO | GLEN ELLEN | Santa Rosa |  |  | OPEN | 117023108 | POLE_DECA_REPL - EAST 13651 HILL RDGLEN | 35214946 |  |  | STS-POLE_DECA_REPL - EAST 13651 HILL RDG | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.3653 | -122.5223 |  | TIER 2 | 57 | 04307-1102, DUNBAR | KK3306 | 16621 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102031691 | RELW OH PRI CLR JPOL RESD REMT TRAF FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043071102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | GLEN ELLEN | Santa Rosa |  |  | OPEN | 117025890 | POLE_DECA_REPL - WSIPGLEN ELLEN95442 | 35214982 |  |  | STS-POLE_DECA_REPL - WSIPGLEN ELLEN95442 | ESTS | ESTS HOLD | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.3643 | -122.5243 |  | TIER 2 | 57 | 04307-1102, DUNBAR | KK3306 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103600814 | RELW OH PRI CLR JPOL RESD REMT NOAC FLAG ESTR BTKA USA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-14 | 2020-04-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043071102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | GLEN ELLEN | Santa Rosa |  |  | COMP | 117035163 | POLE_DECA_REPL - 1900 MORNINGSIDE MNT DR | 35089432 |  |  | STS-POLE_DECA_REPL - 1900 MORNINGSIDE MN | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.3389 | -122.5243 |  | TIER 2 | 57 | 04307-1102, DUNBAR | KK3321 | 12383 | Y | 311 |  |  | 2021-02-12 07:00 | 2021-02-12 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 93.1 | 93.1 |  |  | 1.75 | 40.8 | 40.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101992664 | RELW OH PRI COMP CLR JPOL RESD REMT TRAF FLAG ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2019-06-21 | 2019-07-03 | COMP | 2019-06-20 | COMP | 2021-02-12 | 2020-06-04 | 2020-06-04 | [11 empty] | 2021-02-16 | 2021-02-12 | 2019-08-27 |  | 2019-08-27 | Q1 Work Plan |  | Santa Rosa |  | 043071102 | 22786.7 | 16118.5 | -7820.5 | 3679.5 | 3679.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
North | SO | GLEN ELLEN | Santa Rosa |  |  | OPEN | 116835464 | POLE_DECA_REPL - 11990 HENNO RDGLEN ELLE | 35085305 |  |  | GC POLE_DECA_REPL - 11990 HENNO RDGLEN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3847 | -122.5315 |  | TIER 2 | 14 | 04307-1101, DUNBAR | JJ3225 | 14279 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 80 | 80 |  |  | 0 | 80 | 80 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102030617 | RELW OH PRI INSP JPOL REMT FIRE SWRK ESTR BTKA USA FMOB TER2 FSRP | Pole | 2020-06-11 | 2021-01-26 | COMP | 2020-06-11 |  |  | 2021-01-26 | 2021-01-26 | [12 empty] | 2019-03-26 | 2019-09-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | CALENG |  | 043071101 | 17621.28 | 307.4 | 27.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
North | SO | HEALDSBURG | Geyserville |  |  | OPEN | 116713859 | POLE_BROK_REPL - 4151 WESTSIDE RD HEALDS | 35214693 |  |  | STS-POLE_BROK_REPL - 4151 WESTSIDE RD HE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 38.5638 | -122.8758 |  | TIER 2 | 40 | 04275-1113, FITCH MOUNTAIN | FF2422 | 2211 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101958912 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-12 | 2020-03-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042751113 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | HEALDSBURG | Geyserville |  |  | OPEN | 116719593 | POLE_DECA_REPL - #2W/O #3N/O 1195 WESTSI | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 38.6021 | -122.8872 |  | TIER 2 | 40 | 04275-1113, FITCH MOUNTAIN | FF2401 |  | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101958530 | OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP POHW | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-03-12 | 2020-03-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 042751113 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | HEALDSBURG | Geyserville |  |  | OPEN | 116736142 | POLE_BROK_REPL - 1501 WESTSIDE RDHEALDSB | 35202131 |  |  | STS-POLE_BROK_REPL - 1501 WESTSIDE RDHEA | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.5968 | -122.8833 |  | TIER 2 | 40 | 04275-1113, FITCH MOUNTAIN | FF24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101958747 | RELW OH SEC CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-14 | 2020-03-14 |  | 2020-03-14 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042751113 | 1 | 349.4 | 0 | 362 | 362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | HEALDSBURG | Geyserville |  |  | OPEN | 116736261 | POLE_DECA_REPL - #1W/O HOUSE 3069 WEST D | 35214774 |  |  | STS-POLE_DECA_REPL - #1W/O HOUSE 3069 WE | ESTS | ESTS ERDY HOLD | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.6395 | -122.9137 |  | TIER 2 | 40 | 04275-1113, FITCH MOUNTAIN | EE2302 | 48927 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101971003 | RELW OH PRI CLR JPOL PUBL RESD CGI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-14 | 2020-03-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042751113 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | HEALDSBURG | Geyserville |  |  | OPEN | 116754253 | POLE_DECA_REPL - #4W/O #1N/O 4395 WESTSI | 35214969 |  |  | STS-POLE_DECA_REPL - #4W/O #1N/O 4395 WE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.5584 | -122.8745 |  | TIER 2 | 40 | 04275-1113, FITCH MOUNTAIN | FF2422 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102030444 | RELW OH PRI CLR JPOL REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042751113 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | HEALDSBURG | Geyserville |  |  | OPEN | 116754274 | POLE_BROK_REPL - #1NE/O 1090 GRANT AVE H | 35214974 |  |  | STS-POLE_BROK_REPL - #1NE/O 1090 GRANT A | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.6001 | -122.8385 |  | TIER 2 | 677 | 04275-1111, FITCH MOUNTAIN | FF2502 | 855 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101959067 | RELW OH PRI CLR JPOL PUBL RESD TRAF FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042751111 | 1 | 153.1 | 153.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | HEALDSBURG | Geyserville |  |  | OPEN | 116754603 | POLE_BROK_REPL - 735 GRANT RD.HEALDSBURG | 35214984 |  |  | STS-POLE_BROK_REPL - 735 GRANT RD.HEALDS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.6015 | -122.8405 |  | TIER 2 | 677 | 04275-1111, FITCH MOUNTAIN | FF2501 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102032900 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042751111 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | HEALDSBURG | Geyserville |  |  | OPEN | 116757804 | POLE_DECA_REPL - #6W\O 5285 WESTSIDE RDH | 35215019 |  |  | STS-POLE_DECA_REPL - #6W\O 5285 WESTSIDE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.5484 | -122.8762 |  | TIER 2 | 40 | 04275-1113, FITCH MOUNTAIN | GG24 | 2209 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102029476 | RELW OH PRI CLR JPOL RESD REMT NOAC SWRK ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042751113 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | HEALDSBURG | Geyserville |  |  | OPEN | 116833459 | POLE_BROK_REPL - #1N/O 1021 OLD WAGON RD | 35214822 |  |  | STS-POLE_BROK_REPL - #1N/O 1021 OLD WAGO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.6053 | -122.8897 |  | TIER 2 | 40 | 04275-1113, FITCH MOUNTAIN | EE2325 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101963579 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042751113 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | HEALDSBURG | Geyserville |  |  | OPEN | 116842144 | POLE_DECA_REPL - 1890 FELTA RDHEALDSBURG | 35214862 |  |  | STS-POLE_DECA_REPL - 1890 FELTA RDHEALDS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.5821 | -122.8959 |  | TIER 2 | 40 | 04275-1113, FITCH MOUNTAIN | FF23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101963556 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 11571 | 2021-03-31 | EEI |  | 042751113 | [9 empty] | N | MPP File Only | N |  | Y | 2020-11-01
North | SO | HEALDSBURG | Geyserville |  |  | OPEN | 118171036 | POLE_DECA_REPL - #4S #4SE R/O 3220 PASSA | 35215727 |  |  | STS-POLE_DECA_REPL - #4S #4SE R/O 3220 P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.6339 | -122.8507 |  | TIER 2 | 145 | 04289-1102, GEYSERVILLE | EE24 | 858093 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101960403 | RELW OH PRI CLR REMT ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-11-13 | 2020-11-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042891102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | Healdsburg | Geyserville |  |  | OPEN | 118172493 | POLE_BROK_REPL - #1W #10N R/O 3220 PASSA | 35202746 |  |  | STS-POLE_BROK_REPL - #1W #10N R/O 3220 P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6473 | -122.8525 |  | TIER 2 | 145 | 04289-1102, GEYSERVILLE | EE24 | 858093 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.2 | 13.2 |  |  | 0 | 13.2 | 13.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101960409 | RELW OH PRI CLR ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-17 | 2021-02-17 | COMP | 2021-02-17 | [16 empty] | 2019-11-14 | 2020-11-14 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042891102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | HEALDSBURG | Geyserville |  |  | OPEN | 118128236 | POLE_BROK_REPL - #3E T-PL#11/17 N/O 1864 | 35222206 |  |  | NR21 REPL POLE 1864 POPPY HILL HLDS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-10 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.6336 | -122.8585 |  | TIER 2 | 145 | 04289-1102, GEYSERVILLE | EE24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 25.7 | 25.7 |  |  | 0 | 25.7 | 25.7 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 102030495 | RELW OH PRI CLR REMT FIRE NOAC ESTR REAR USA FMOB PSPS FSRP TER2 | Pole | 2021-01-05 | 2021-01-05 | COMP | 2021-01-05 | [16 empty] | 2019-10-31 | 2020-10-31 | 2021-02-07 | 2021-02-07 | B tag clean up 12/22/2020 |  | Santa Rosa |  | 042891102 | 9884.45 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | Electric Distribution | N | Pulled from MPP Import File | N |  | Y | 2020-12-22
North | SO | HOPLAND | Geyserville |  |  | OPEN | 117112283 | POLE_DECA_REPL-1E/O 7S/O R/O 33771 S | 35092850 |  |  | B3- REPL POLE 33771 HWY 128 HOPLAND | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-02-22 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.8749 | -123.1004 |  | TIER 2 | 104 | 04282-1101, CLOVERDALE | Z18 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.6 | 32 | 2.6 |  | 0 | 34.6 | 32 | 2.6 |  | EC | B | Pole | Decayed/Rotten | Replace |  | 102038706 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2021-01-17 | 2021-01-19 | COMP | 2021-01-17 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-04-27 | 2019-09-30 | 2021-03-22 | 2021-03-22 | B tag clean up 12/24/2020 |  | Santa Rosa |  | 042821101 | [9 empty] | N | Pulled from MPP Import File | N |  | Y | 2020-12-24
North | SO | KENWOOD | Santa Rosa |  |  | OPEN | 116974432 | POLE_DECA_REPL - 103592401KENWOOD95409 | 35202145 |  |  | STS-POLE_DECA_REPL - 103592401KENWOOD954 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.4192 | -122.5666 |  | TIER 2 | 14 | 04307-1101, DUNBAR | JJ3105 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 11 | 11 |  |  | 0 | 11 | 11 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103592401 | RELW OH SERV PGEA RESD FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-25 |  | COMP | 2021-01-25 | [16 empty] | 2019-04-07 | 2020-04-07 | 2020-09-25 | 2020-09-25 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043071101 | 5377.66 | 291.2 | 0 | 181 | 181 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | KENWOOD | Santa Rosa |  |  | OPEN | 117185954 | POLE_LEAN_REPL - 317 MERVIN AV KENWOOD | 35215465 |  |  | STS-POLE_LEAN_REPL - 317 MERVIN AV KENWO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.413 | -122.5531 |  | TIER 2 | 14 | 04307-1101, DUNBAR | JJ3207 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Leaning | Replace |  | 102033252 | RELW OH PRI JPOL RESD BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043071101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | MARSHALL | Petaluma |  |  | OPEN | 117211317 | POLE_DECA_REPL - #5SOUTH WEST 25500 HWAY | 35214658 |  |  | STS-POLE_DECA_REPL - #5SOUTH WEST 25500 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2262 | 122.9124 |  | TIER 2 | 327 | 04227-1103, COTATI | NN23 | 148 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101996872 | RELW OH PRI PGEA RESD FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042271103 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | MARSHALL | Petaluma |  |  | OPEN | 117445498 | POLE_BROK_REPL - #1NORTH 25500 HWAY 1MAR | 35216007 |  |  | STS-POLE_BROK_REPL - #1NORTH 25500 HWAY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2299 | -122.9097 |  | TIER 2 | 327 | 04227-1103, COTATI | NN23 | 148 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101996866 | RELW OH PRI INSP REMT FIRE NOAC ESTR USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-13 | 2020-06-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042271103 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | MARSHALL | Petaluma |  |  | OPEN | 117445579 | POLE_BROK_REPL - #8NORTH EAST 24800 HWAY | 35216012 |  |  | STS-POLE_BROK_REPL - #8NORTH EAST 24800 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2187 | -122.9165 |  | TIER 2 | 327 | 04227-1103, COTATI | NN23 | 87587 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102011876 | RELW OH PRI INSP REMT FIRE NOAC ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-13 | 2019-12-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042271103 | 1 | 34.8 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | MARSHALL | Petaluma |  |  | OPEN | 117456907 | POLE_BURN_REPL - #11NORTH #5EAST 22890 S | 35216034 |  |  | STS-POLE_BURN_REPL - #11NORTH #5EAST 228 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2013 | -122.9122 |  | TIER 2 | 327 | 04227-1103, COTATI | NN23 | 4289 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 101996911 | RELW OH PRI INSP REMT FIRE NOAC SWRK ESTR GO USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-17 | 2020-06-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042271103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | MARSHALL | Petaluma |  |  | OPEN | 114645752 | REPL POLE:22755 HWY 1,Marshall | 35044991 |  |  | GC REPL POLE:22755 HWY 1 MARSHALL | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1943 | -122.9189 |  | TIER 2 | 327 | 04227-1103, COTATI | NN23 | 2441 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Dispatched | CLICK | [6 empty] | 33.5 | 33.5 |  |  | 0 | 33.5 | 33.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101996925 | POHW OH TNT XMPT XDOC TER2 | Pole | 2019-05-09 | 2019-06-13 | COMP | 2018-09-18 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-05-30 | 2019-05-30 | 2019-07-29 | 2019-07-29 | Q1 Work Plan |  | UNASSIGNED |  | 042271103 | 14872.85 | 12296.3 |  |  |  | 83.4 |  | 83.4 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SO | MARSHALL | Petaluma |  |  | OPEN | 120080841 | POLE_DECA_REPL - 19485 SHORELINE HWY #1 | 35218476 |  |  | NR6 CTP REPL POLE 19485 SHORELINE HWY 1 | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-23 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.1782 | -122.9055 |  | TIER 2 | 327 | 04227-1103, COTATI | OO23 | 4131 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 62 | 58.1 | 3.9 |  | 0 | 62 | 58.1 | 3.9 |  | EC | B | Pole | Decayed/Rotten | Replace |  | 102013068 | OH PRI RESD RELW TMAN CLR JPOL REMT TRAF FLAG ESTR BTKA USA TER2 | Pole | 2020-12-17 | 2021-02-03 | COMP | 2020-12-17 |  |  | 2020-12-18 | 2020-12-18 | [12 empty] | 2020-11-20 | 2021-02-20 |  | 2021-02-20 | B tag clean up 11/24/2020 |  | Santa Rosa |  | 042271103 | 36231.29 | 259.3 | 113.1 | 113.1 | 113.1 |  |  |  | Electric Distribution | N | Pulled from MPP Import File | N |  | Y | 2020-11-24
North | SO | PENNGROVE | Petaluma |  |  | OPEN | 117066607 | POLE_DECA_REPL - #1 N/O 5644 HILLSBOROUG | 35215312 |  |  | STS-POLE_DECA_REPL - #1 N/O 5644 HILLSBO | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3209 | -122.6141 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | LL30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101953532 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-19 | 2020-04-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043371102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 114667104 | POLE_BROK_REPL - 1400 MARSHALL PETALUMA | 35145871 |  |  | STS-POLE_BROK_REPL - 1400 MARSHALL PETAL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.1593 | -122.7814 |  | TIER 2 | 297 | 04263-1109, PETALUMA C | OO26 | 1509 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 20.2 | 20.2 |  |  | 0 | 20.2 | 20.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101995792 | RELW OH PRI INSP JPOL REMT GO XMPT SCOP SCPA XDOC FMOB TER2 FSRP | Pole | 2021-01-15 |  | COMP | 2021-01-15 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-06-05 | 2019-06-05 | 2023-06-04 | 2023-06-04 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042631109 | 8719.49 | 4712.8 | 0 | 1226.5 | 1226.5 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 116990358 | POLE_DECA_REPL - #1 E/O #1 S/O 3272 ADOB | 35214825 |  |  | STS-POLE_DECA_REPL - #1 E/O #1 S/O 3272 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2924 | -122.5855 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | LL31 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101953351 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-09 | 2020-04-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043371102 | 1 | 30.8 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117019749 | POLE_DECA_REPL - #1NW/O 750 SONOMA MTN R | 35214935 |  |  | STS-POLE_DECA_REPL - #1NW/O 750 SONOMA M | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.3237 | -122.5903 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | LL31 | 5721 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101953609 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-12 | 2020-04-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043371102 | 1 | 13.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117024091 | POLE_DECA_REPL - #5 S/W O #1 N/O 829 MAN | 35214956 |  |  | STS-POLE_DECA_REPL - #5 S/W O #1 N/O 829 | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2846 | -122.5865 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | MM31 | 1299 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102007687 | RELW OH PRI CLR RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043371102 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117033972 | POLE_DECA_REPL - #1/E/O/A/F 175 PEPPER L | 35215052 |  |  | STS-POLE_DECA_REPL - #1/E/O/A/F 175 PEPP | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.2808 | -122.7243 |  | TIER 2 | 327 | 04227-1103, COTATI | MM2806 | 989 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101985525 | RELW OH PRI TER2 ESTR PROG FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042271103 | 1 | 52.2 | 52.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117037093 | POLE_BROK_REPL - #1/NW/O 696 OLD KING RD | 35215117 |  |  | STS-POLE_BROK_REPL - #1/NW/O 696 OLD KIN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.2807 | -122.7139 |  | TIER 2 | 327 | 04227-1103, COTATI | MM2807 | 2167 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101985565 | RELW OH PRI ESTR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-16 | 2020-04-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042271103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117038883 | POLE_DECA_REPL - A/F85 QUEEN LN PETALUMA | 35215142 |  |  | STS-POLE_DECA_REPL - A/F85 QUEEN LN PETA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.275 | -122.7199 |  | TIER 2 | 327 | 04227-1103, COTATI | MM2806 | 2883 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101985539 | RELW OH PRI ESTR GO FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-16 | 2020-04-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042271103 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117041767 | POLE_DECA_REPL - 197 QUEENS LNPETALUMA94 | 35215153 |  |  | STS-POLE_DECA_REPL - 197 QUEENS LNPETALU | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.275 | -122.7241 |  | TIER 2 | 327 | 04227-1103, COTATI | MM2806 | 2883 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101985532 | RELW OH PRI ESTR GO PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-16 | 2020-04-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042271103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117041917 | POLE_DECA_REPL - 500 QUEENS LNPETALUMA94 | 35202281 |  |  | STS-POLE_DECA_REPL - 500 QUEENS LNPETALU | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.2749 | -122.7151 |  | TIER 2 | 327 | 04227-1103, COTATI | MM2807 | 2883 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.7 | 27.7 |  |  | 0 | 27.7 | 27.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101985546 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-14 |  | COMP | 2020-12-14 | [16 empty] | 2019-04-16 | 2020-04-16 | 2020-10-13 | 2020-10-13 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042271103 | 14678.83 | 1242.3 | 228.7 | -334.8 | -334.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117049390 | POLE_DECA_REPL - #1 N/W #15 N O MB 4191 | 35215220 |  |  | STS-POLE_DECA_REPL - #1 N/W #15 N O MB 4 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2594 | -122.5507 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | MM32 | 503 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102006460 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043371102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117058692 | POLE_DECA_REPL - #11 E 300A HARDIN LANE | 35215283 |  |  | STS-POLE_DECA_REPL - #11 E 300A HARDIN L | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3003 | -122.625 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | LL30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102025647 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-18 | 2020-04-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043371102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117058695 | POLE_DECA_REPL - #8 N/O 700 HARDIN LNPET | 35215287 |  |  | STS-POLE_DECA_REPL - #8 N/O 700 HARDIN L | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3125 | -122.6143 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | LL30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102026597 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-18 | 2020-04-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043371102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117058696 | POLE_DECA_REPL - 700 HARDIN LNPETALUMA94 | 35215292 |  |  | STS-POLE_DECA_REPL - 700 HARDIN LNPETALU | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3076 | -122.6186 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | LL30 | 3341 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102026236 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-18 | 2020-04-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043371102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117058697 | POLE_DECA_REPL - #5 N/O 700 HARDIN LNPET | 35215297 |  |  | STS-POLE_DECA_REPL - #5 N/O 700 HARDIN L | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3107 | -122.6159 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | LL30 | 3341 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101953392 | OH PRI JPOL ESTR FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-04-18 | 2020-04-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043371102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117064649 | POLE_BROK_REPL - 230 EUCALYPTUS RD PETAL | 35194921 |  |  | STS-POLE_BROK_REPL - A/F 210 EUCALYPTUS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.2523 | -122.7052 |  | TIER 2 | 116 | 04263-1108, PETALUMA C | MM2823 | 3941 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101985974 | REGW OH PRI ESTR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-19 | 2020-04-19 |  | 2020-04-19 | 2021 CBP Plan | 2021-01-31 | ENENG |  | 042631108 | 1 | 212 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117066608 | POLE_DECA_REPL - #2 N/O 850 LYNCH RD PET | 35215317 |  |  | STS-POLE_DECA_REPL - #2 N/O 850 LYNCH RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.313 | -122.6057 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | LL30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101953400 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-19 | 2020-04-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043371102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117068889 | POLE_DECA_REPL - #7 S/O 850 LINCH RDPETA | 35215357 |  |  | STS-POLE_DECA_REPL - #7 S/O 850 LINCH RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3056 | -122.6086 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | LL30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101953409 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043371102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117068901 | POLE_DECA_REPL - #8 S/O 850 LINCH RDPETA | 35215382 |  |  | STS-POLE_DECA_REPL - #8 S/O 850 LINCH RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3045 | -122.6083 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | LL30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102030067 | RELW PRI OH ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043371102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117068903 | POLE_DECA_REPL - #6 S/O 850 LINCH RDPETA | 35215388 |  |  | STS-POLE_DECA_REPL - #6 S/O 850 LINCH RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3067 | -122.6088 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | LL30 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102030672 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043371102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117070868 | POLE_DECA_REPL - 5 POLES N/CUTOUTS 11371 | 35215431 |  |  | STS-POLE_DECA_REPL - 5 POLES N/CUTOUTS 1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2662 | -122.5565 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | MM32 | 11371 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102008049 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043371102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117071541 | POLE_DECA_REPL - 3274 ADOBE RDPETALUMA94 | 35202430 |  |  | STS-POLE_DECA_REPL - 3274 ADOBE RDPETALU | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.2877 | -122.5604 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | MM32 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102008040 | RELW OH PRI CLR RESD GO REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2020-11-28 | 2020-11-28 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043371102 | 1 | 40.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117079869 | POLE_DECA_REPL - #4EAST 1750 MARSHALL PE | 35215605 |  |  | STS-POLE_DECA_REPL - #4EAST 1750 MARSHAL | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.181 | -122.8368 |  | TIER 2 | 327 | 04227-1103, COTATI | OO25 | 7465 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101995849 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-22 | 2020-04-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042271103 | 1 | 30.8 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117081243 | POLE_DECA_REPL - #11SO/E 1803 MARSHALL P | 35215608 |  |  | STS-POLE_DECA_REPL - #11SO/E 1803 MARSHA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.1693 | -122.7937 |  | TIER 2 | 327 | 04227-1103, COTATI | OO26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102015295 | RELW OH PRI CLR REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-22 | 2020-04-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042271103 | 1 | 13.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117087117 | POLE_DECA_REPL - #10WEST 5600 MARSHALL P | 35214587 |  |  | STS-POLE_DECA_REPL - #10WEST 5600 MARSHA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.1491 | -122.8337 |  | TIER 2 | 327 | 04227-1103, COTATI | PP25 | 1509 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102014103 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-23 | 2020-04-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042271103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117094951 | POLE_DECA_REPL - #7WEST 5600 MARSHALL PE | 35214688 |  |  | STS-POLE_DECA_REPL - #7WEST 5600 MARSHAL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.1493 | -122.8308 |  | TIER 2 | 327 | 04227-1103, COTATI | PP25 | 87402 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101995442 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042271103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117214779 | POLE_DECA_REPL - #2 SW/O MB 1515 STONY P | 35214710 |  |  | STS-POLE_DECA_REPL - #2 SW/O MB 1515 STO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 38.2923 | -122.7039 |  | TIER 2 | 422 | 04227-1102, COTATI | LL28 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102030127 | RELW OH PRI CLR JPOL RESD REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-11 | 2020-05-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042271102 | 1 | 321.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | Petaluma | Petaluma |  |  | OPEN | 117938076 | REPL POLE:#1 S/W O #5 S/O 829 MANOR LN,P | 35202752 |  |  | STS-REPL POLE:#1 S/W O #5 S/O 829 MANOR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.2827 | -122.5833 |  | TIER 2 | 423 | 04337-1102, LAKEVILLE | MM31 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101990154 | RELW OH TNT JPOL TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-19 | 2020-06-19 | 2020-10-15 | 2020-10-15 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043371102 | 1 | 201.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 117087556 | POLE_BROK_REPL - 5303 REDWOOD HIGHWAY\10 | 35191421 |  |  | REPL POLE - 5303 REDWOOD HWY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.1917 | -122.5939 |  | TIER 2 | 297 | 04263-1109, PETALUMA C | OO31 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101994966 | RELW OH PRI JPOL RESD FIRE FLAG ESTR GO FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2020-08-06 | 2020-08-06 | [12 empty] | 2019-04-23 | 2020-04-23 | 2021-05-31 | 2021-05-31 | Per DOT Approved Request 31050 | 2021-03-31 | QUES |  | 042631109 | 1 | 42.5 | [7 empty] | N | MPP File Only | N |  | Y | 2021-01-22
North | SO | PETALUMA | Petaluma |  |  | COMP | 115098505 | POLE_DECA_REPL - #3EAST 5600 MARSHALL PE | 35063573 |  |  | STS-REPL POLE:#3EAST 5600 MARSHALL PETA | DOCC | DOCC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.1483 | -122.8219 |  | TIER 2 | 327 | 04227-1103, COTATI | PP25 | 4319 | Y | 311 |  |  | 2021-02-10 07:00 | 2021-02-10 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 41 | 41 |  |  | 0 | 41 | 41 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101995432 | POHW OH TNT COMP CCNT TER2 JPOL | Pole | 2019-09-27 | 2019-10-02 | COMP | 2019-09-26 | COMP | 2021-02-10 | 2020-06-04 | 2020-06-04 | [11 empty] | 2021-02-11 | 2021-02-10 | 2019-10-29 |  | 2019-10-29 | circuit based plan 2.14 | 2019-09-26 | CALENG |  | 042271103 | 25147.92 | 7507.4 | 3970.5 | 4577.3 | 4577.3 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SO | PETALUMA | Petaluma |  |  | OPEN | 115098904 | REPL POLE:#7/SW/O/MB 465 CHILENO VALLEY | 35064171 |  |  | STS-REPL POLE:#7/SW/O/MB 465 CHILENO VAL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2099 | -122.67 |  | TIER 2 | 116 | 04263-1108, PETALUMA C | NN29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 67.6 | 67.6 |  |  | 0 | 67.6 | 67.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101981326 | POHW OH TNT JPOL TER2 | Pole | 2020-11-18 | 2020-11-24 | COMP | 2019-10-03 |  |  | 2019-07-30 | 2019-07-30 | [12 empty] | 2018-10-29 | 2019-10-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-10-03 | CALENG |  | 042631108 | 11930.21 | 1995 | 1068.7 | 1068.7 | 1068.7 | 166.8 |  | 166.8 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
North | SO | PETALUMA | Petaluma |  |  | OPEN | 115098907 | REPL POLE:HOUSE 5360 BODEGA AVE,Petaluma | 35063908 |  |  | GC-REPL POLE:HOUSE 5360 BODEGA AVE,PETA | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2671 | -122.7242 |  | TIER 2 | 116 | 04263-1108, PETALUMA C | MM2811 |  | Y | 311 |  |  | 2021-05-15 07:00 | 2021-05-15 16:00 | Dispatched | CLICK | [6 empty] | 50.2 | 50.2 |  |  | 0 | 50.2 | 50.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101985676 | POHW OH TNT TER2 | Pole | 2019-10-02 | 2019-10-02 | COMP | 2019-10-01 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-10-29 | 2019-10-29 |  | 2019-10-29 | Q1 Work Plan | 2019-10-01 | CALENG |  | 042631108 | 3767.9 | 446.3 |  |  |  | 406.2 |  | 406.2 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 116803037 | POLE_DECA_REPL - F/O 5330 MONTE VERDE DR | 35202223 |  |  | STS-POLE_DECA_REPL - F/O 5330 MONTE VERD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land JointPole |  |  | 38.4723 | -122.6511 |  | TIER 2 | 56 | 04332-1103, RINCON | HH2925 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101966487 | RELW OH PRI INSP JPOL PUBL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043321103 | 1 | 196.8 | 196.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 116803620 | POLE_DECA_REPL - A\F MB 5342 MONTE VISTA | 35215266 |  |  | STS-POLE_DECA_REPL - A\F MB 5342 MONTE V | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.4724 | -122.65 |  | TIER 2 | 56 | 04332-1103, RINCON | HH2925 | 472 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101966486 | RELW OH PRI INSP JPOL PUBL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043321103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 116803822 | POLE_BROK_REPL - R/O 5329 MONTE VERDE AV | 35215816 |  |  | STS-POLE_BROK_REPL - R/O 5329 MONTE VERD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.4725 | -122.6511 |  | TIER 2 | 56 | 04332-1103, RINCON | HH2925 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102022199 | RELW OH SERV INSP JPOL PUBL RESD FIRE GO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043321103 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 116804681 | POLE_DECA_REPL - 5434 MONTE VERDE AVESAN | 35215299 |  |  | STS-POLE_DECA_REPL - 5434 MONTE VERDE AV | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.4725 | -122.6487 |  | TIER 2 | 56 | 04332-1103, RINCON | HH2925 | 472 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101966485 | RELW OH PUBL PRI INSP JPOL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043321103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 116805105 | POLE_DECA_REPL - 5446 M0NTE VERDE AVESAN | 35202244 |  |  | STS-POLE_DECA_REPL - 5446 M0NTE VERDE AV | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.4725 | -122.6481 |  | TIER 2 | 56 | 04332-1103, RINCON | HH2925 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102022197 | RELW JPOL OH PRI INSP PUBL RESD FIRE FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | QUES |  | 043321103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 116841968 | POLE_DECA_REPL - 4801 SADDLE CLUB LN SAN | 35202501 |  |  | STS-POLE_DECA_REPL - 4801 SADDLE CLUB LN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land JointPole |  |  | 38.4854 | -122.6699 |  | TIER 2 | 237 | 04332-1102, RINCON | HH2918 | 15249 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102023132 | RELW OH PRI INSP CLR JPOL RESD FIRE ESTR GO BTKA PROG FSRP FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-03-26 | 2020-03-26 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | QUES |  | 043321102 | 1 | 1037.6 | -430.6 | -101 | -101 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 116848176 | POLE_DECA_REPL - 5040 RINCON AVE SANTA R | 35214918 |  |  | STS-POLE_DECA_REPL - 5040 RINCON AVE SAN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.4861 | -122.6632 |  | TIER 2 | 237 | 04332-1102, RINCON | HH2918 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101994351 | RELW OH PRI INSP CLR JPOL RESD REMT FLAG ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043321102 | 1 | 64.8 | 64.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 116860958 | POLE_DECA_REPL - 5440 BADER RD SANTA ROS | 35215138 |  |  | STS-POLE_DECA_REPL - 5440 BADER RD SANTA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.454 | -122.6471 |  | TIER 2 | 237 | 04332-1102, RINCON | II2910 | 14029 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101949645 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043321102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 116865103 | POLE_BROK_REPL - #1S A/F 1439 BAIRD RD S | 35215393 |  |  | STS-POLE_BROK_REPL - #1S A/F 1439 BAIRD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.4879 | -122.6678 |  | TIER 2 | 323 | 04332-1104, RINCON | HH2913 | 4433 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101966538 | RELW OH PRI INSP JPOL REMT FIRE ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043321104 | 1 | 60.1 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 116867174 | POLE_DECA_REPL - #1/SE/O 4476 BENNET VIE | 35202558 |  |  | STS-POLE_DECA_REPL - #1/SE/O 4476 BENNET | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4169 | -122.6722 |  | TIER 2 | 12 | 04215-1111, SANTA ROSA A | JJ2902 | 55443 | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | [6 empty] | 122.7 | 122.7 |  |  | 0 | 122.7 | 122.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101969133 | RELW OH PRI CLR REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-14 | 2020-12-14 | COMP | 2020-12-14 | [16 empty] | 2019-03-29 | 2020-03-29 | 2020-10-10 | 2020-10-10 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042151111 | 27439.66 | 3994.3 | 2542.1 | -597.3 | -597.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 116872938 | POLE_BROK_REPL - R/O 1565 BAIRD RD SANTA | 35202570 |  |  | STS-POLE_BROK_REPL - R/O 1565 BAIRD RD S | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.4902 | -122.6693 |  | TIER 2 | 237 | 04332-1102, RINCON | HH2913 | 15265 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102025743 | RELW OH PRI INSP JPOL REMT FIRE SWRK ESTR GO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-30 | 2020-03-30 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043321102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 116941784 | POLE_BROK_REPL - C/O BAIRD RD & HARVILLE | 35215848 |  |  | STS-POLE_BROK_REPL - C/O BAIRD RD & HARV | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.4896 | -122.6672 |  | TIER 2 | 237 | 04332-1102, RINCON | HH2913 | 4433 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102025358 | RELW OH PRI INSP JPOL REMT FIRE JAR FLAG GO BTKA OTRG TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-29 | 2020-03-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043321102 | 1 | 13.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 117019186 | POLE_BROK_REPL - 7708 SONOMA HWY 12SANTA | 35214920 |  |  | STS-POLE_BROK_REPL - 7708 SONOMA HWY 12S | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.4327 | -122.5742 |  | TIER 2 | 14 | 04307-1101, DUNBAR | II3124 | 14251 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 66.1 | 66.1 |  |  | 0 | 66.1 | 66.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102031384 | RELW OH PRI INSP JPOL REMT FIRE ESTR GO BTKA REAR FMOB TER2 FSRP | Pole | 2021-02-11 |  | COMP | 2021-02-11 | [16 empty] | 2019-04-12 | 2020-04-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043071101 | 30256.87 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 117049180 | POLE_DECA_REPL - 7760 SONOMA HWY 12SANTA | 35215214 |  |  | STS-POLE_DECA_REPL - 7760 SONOMA HWY 12S | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.4299 | -122.5729 |  | TIER 2 | 14 | 04307-1101, DUNBAR | II3125 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101957880 | RELW OH SEC INSP CLR JPOL RESD REMT ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 043071101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 119985983 | POLE_BROK_REPL - #1 N/O 55 PYTHIAN RDSan | 35212265 |  |  | NR5 REPL POLE 7424 RANCHO ;PS GUILI | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-08 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4401 | -122.5814 |  | TIER 2 | 14 | 04307-1101, DUNBAR | II3119 | 15393 | Y | 311 |  |  | 2021-03-11 07:00 | 2021-03-11 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 52.6 | 41 | 11.6 |  | 0 | 52.6 | 41 | 11.6 |  | EC | B | Pole | Broken/Damaged | Replace |  | 103849012 | RELW OH PRI CREW CLR JPOL BTKA FIRE ESTR USA FMOB TER2 | Pole | 2020-12-18 | 2020-12-21 | COMP | 2020-11-27 | [16 empty] | 2020-11-05 | 2021-02-05 |  | 2021-02-05 | B tag clean up 11/8/2020 |  | Santa Rosa |  | 043071101 | 25063.14 | 3740.6 | 3655.6 | 175.6 | 175.6 |  |  |  | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-11-08
North | SO | SANTA ROSA | Santa Rosa |  |  | COMP | 114689776 | POLE_DECA_REPL - 4825 PRESSLEY RD SANTA | 35079503 |  |  | REPL POLE - 4825 PRESSLEY RD SA | DOCC | DOCC SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-07-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 38.3585 | -122.6377 |  | TIER 2 | 182 | 04318-2103, BELLEVUE | KK3011 | 15367 | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 36.2 | 36.2 |  |  | 0 | 36.1 | 36.1 |  |  | EC | F | Pole | Decayed/Rotten | Replace |  | 101986469 | RELW OH PRI COMP GO INSP RESD ESTR BTKA USA CCNT FMOB TER2 | Pole | 2019-11-27 | 2019-12-30 | COMP | 2019-11-27 | COMP | 2021-01-06 | 2020-06-04 | 2020-06-04 | [11 empty] | 2021-01-11 | 2021-01-06 | 2023-06-11 | 2019-12-31 | 2019-12-31 | circuit based plan 2.14 |  | UNASSIGNED |  | 043182103 | 15215.17 | 6748.1 | 2734.5 | 609.4 | 609.4 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 116842079 | POLE_DECA_REPL - 4840 SADDLE CLUB RD SAN | 35202507 |  |  | STS-POLE_DECA_REPL - 4840 SADDLE CLUB RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4848 | -122.6699 |  | TIER 2 | 237 | 04332-1102, RINCON | HH2918 | 15249 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.5 | 25.5 |  |  | 0 | 25.5 | 25.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101966566 | RELW OH SEC GO INSP RESD ESTR BTKA PROG FMOB TER2 FSRP | Pole | 2020-11-16 | 2021-01-12 | COMP | 2020-11-16 | [16 empty] | 2019-03-26 | 2020-03-26 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043321102 | 8985.44 | 1046.5 | 594 | 594 | 594 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SANTA ROSA | Santa Rosa |  |  | OPEN | 114625473 | GC REPL POLE 1654 WARM SPRINGS RD | 35058191 |  |  |  | CONS | CONS CONT SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.4002 | -122.5525 |  | TIER 2 | 14 | 04307-1101, DUNBAR | JJ3217 | 65797 | Y | 311 |  |  | 2021-05-15 07:00 | 2021-05-15 16:00 | Dispatched | CLICK | [6 empty] | 50.9 | 50.9 |  |  | 0 | 50.9 | 50.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102035105 | REGW OH PRI SEC SERV TMAN CLR JPOL RESD FIRE FLAG BTKA USA XMPT SCOP SCPA TER2 | Pole | 2019-02-23 | 2019-07-30 | COMP | 2019-02-23 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2018-05-22 | 2019-05-22 | 2019-07-21 | 2019-07-21 | Q1 Work Plan | 2019-02-23 | Santa Rosa |  | 043071101 | 19656.46 | 3406.3 |  |  |  | 3406.2 |  | 3406.2 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SO | SEBASTOPOL | Santa Rosa |  |  | OPEN | 116971478 | POLE_BROK_REPL - A/F 5796 BLANK RDSEBAST | 35214736 |  |  | STS-POLE_BROK_REPL - A/F 5796 BLANK RDSE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.3395 | -122.7898 |  | TIER 2 | 272 | 04227-1105, COTATI | KK2622 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101970884 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-06 | 2019-10-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042271105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SEBASTOPOL | Santa Rosa |  |  | OPEN | 117074715 | POLE_BURN_REPL - #1E/O 1967 GREEN HILL R | 35215860 |  |  | STS-POLE_BURN_REPL - #1E/O 1967 GREEN HI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.4166 | -122.8946 |  | TIER 2 | 5 | 04257-1102, MOLINO | JJ2305 | 9779 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 102008983 | RELW OH PRI CLR JAR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-22 | 2020-04-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042571102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117003143 | POLE_DECA_REPL - #1N/O 5251 GROVE STSONO | 35214835 |  |  | STS-POLE_DECA_REPL - #1N/O 5251 GROVE ST | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.3118 | -122.5465 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL32 | 14345 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102028309 | RELW OH PRI CLR JPOL REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-10 | 2020-04-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117003409 | POLE_DECA_REPL - R/O 5251 GROVE ST SONOM | 35214841 |  |  | STS-POLE_DECA_REPL - R/O 5251 GROVE ST S | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.3109 | -122.5463 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL32 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103141001 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-10 | 2020-04-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117004277 | POLE_DECA_REPL - #1 SE/O 5340 GROVE STSO | 35214845 |  |  | STS-POLE_DECA_REPL - #1 SE/O 5340 GROVE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.3133 | -122.5528 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3212 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102025237 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-10 | 2020-04-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117017189 | POLE_DECA_REPL - 5059 GROVE STSONOMA9547 | 35214894 |  |  | STS-POLE_DECA_REPL - 5059 GROVE STSONOMA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3109 | -122.5526 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3212 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102025236 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-12 | 2020-04-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117017211 | POLE_DECA_REPL - 18970 SWEET WILLIAMS CT | 35214900 |  |  | STS-POLE_DECA_REPL - 18970 SWEET WILLIAM | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3091 | -122.5548 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3212 | 12407 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101992776 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-12 | 2020-04-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117019451 | POLE_DECA_REPL - #1 SE/O 19292 SPRING DR | 35214925 |  |  | STS-POLE_DECA_REPL - #1 SE/O 19292 SPRIN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3099 | -122.5515 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3212 | 14345 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101992781 | RELW OH PRI CLR JPOL RESD FMOB ESTR GO BTKA TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-12 | 2020-04-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117025061 | POLE_DECA_REPL - 4878 GROVE STSONOMA9547 | 35214961 |  |  | STS-POLE_DECA_REPL - 4878 GROVE STSONOMA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3076 | -122.5524 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3217 | 12407 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101992768 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117025062 | POLE_DECA_REPL - #1 N/O 18920 CRESTVIEW | 35214966 |  |  | STS-POLE_DECA_REPL - #1 N/O 18920 CRESTV | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3008 | -122.5532 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3217 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101992754 | RELW OH PRI CLR JPOL RESD ESTR PRTO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117025063 | POLE_DECA_REPL - #1 E/O 4879 GROVE STSON | 35202218 |  |  | STS-POLE_DECA_REPL - #1 E/O 4879 GROVE S | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.3076 | -122.5516 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3217 | 12407 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48.6 | 48.6 | 0 |  | 0 | 48.6 | 48.6 | 0 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102026161 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-15 |  | COMP | 2021-01-15 | [16 empty] | 2019-04-13 | 2020-04-13 | 2020-10-09 | 2020-10-09 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042721104 | 26555.65 | 380.3 | 0 | 2005.4 | 2005.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117025065 | POLE_DECA_REPL - 4863 GROVE STSONOMA9547 | 35214971 |  |  | STS-POLE_DECA_REPL - 4863 GROVE STSONOMA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.3074 | -122.5511 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3217 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101992766 | RELW OH PRI CLR JPOL RESD ESTR GO PRTO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117025066 | POLE_DECA_REPL - 4611 GROVE STSONOMA9547 | 35214976 |  |  | STS-POLE_DECA_REPL - 4611 GROVE STSONOMA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land JointPole |  |  | 38.3034 | -122.5512 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3217 | 12407 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101992760 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-13 | 2020-04-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117025314 | POLE_DECA_REPL - #1W/O 1998 SOBRE VISTA | 35202221 |  |  | STS-POLE_DECA_REPL - #1W/O 1998 SOBRE VI | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 38.3222 | -122.5228 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3306 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 45.1 | 45.1 |  |  | 0 | 45.1 | 45.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101992838 | RELW OH PRI CLR REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-18 |  | COMP | 2020-12-18 | [16 empty] | 2019-04-13 | 2020-04-13 | 2020-10-09 | 2020-10-09 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042721104 | 21934.73 | 1514.9 | 518.3 | -181 | -181 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117027092 | POLE_DECA_REPL - 17914 CARRIGER RD SONOM | 35214991 |  |  | STS-POLE_DECA_REPL - 17914 CARRIGER RD S | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.3071 | -122.5172 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3316 | 6505 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102014348 | RELW OH PRI CLR JPOL REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-14 | 2020-04-14 | 2021-05-21 | 2021-05-21 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117030930 | CRSS_BROK_REPL - #1E/O 19105 KENSLEIGH D | 35215012 |  |  | STS-CRSS_BROK_REPL - #1E/O 19105 KENSLEI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 38.2996 | -122.545 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3223 | 6503 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Crossarm | Broken/Damaged | Replace |  | 102028353 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117033364 | POLE_DECA_REPL - R/O 17570 CARRIGER RD N | 35215027 |  |  | STS-POLE_DECA_REPL - R/O 17570 CARRIGER | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.314 | -122.5164 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3312 | 5661 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101983550 | RELW OH PRI CLR REMT CGI ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117033370 | POLE_BROK_REPL - #1 NE/O #3 N/O 17500 CA | 35215032 |  |  | STS-POLE_BROK_REPL - #1 NE/O #3 N/O 1750 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3156 | -122.5155 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3312 | 17019 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102014853 | RELW REMT OH PRI CLR CGI ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117034030 | POLE_DECA_REPL - 18566 WHITE OAK DRSONOM | 35215057 |  |  | STS-POLE_DECA_REPL - 18566 WHITE OAK DRS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.303 | -122.539 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3219 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101992681 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117034032 | POLE_DECA_REPL - 18684 WHITE OAK DRSONOM | 35215063 |  |  | STS-POLE_DECA_REPL - 18684 WHITE OAK DRS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3036 | -122.5403 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3218 | 14341 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101992682 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117038648 | POLE_DECA_REPL - 18794 DEER PARK DR SONO | 35215127 |  |  | STS-POLE_DECA_REPL - 18794 DEER PARK DR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3008 | -122.5365 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3219 | 11473 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102026103 | RELW OH PRI CLR JPOL RESD ESTR GO BTKA REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-16 | 2020-04-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117038656 | POLE_DECA_REPL - A/F 18799 DEER PARK DRS | 35215132 |  |  | STS-POLE_DECA_REPL - A/F 18799 DEER PARK | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3014 | -122.5372 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3219 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102026102 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-16 | 2020-04-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117038657 | POLE_DECA_REPL - 1811 DEER PARK DR.SONOM | 35215137 |  |  | STS-POLE_DECA_REPL - 1811 DEER PARK DR.S | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3011 | -122.5382 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3219 | 11473 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102026101 | RELW JPOL OH PRI CLR RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-16 | 2020-04-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117043569 | POLE_BROK_REPL - A/F 18871 CANYON RD SON | 35215163 |  |  | STS-POLE_BROK_REPL - A/F 18871 CANYON RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3003 | -122.5347 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3219 | 6551 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102026110 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-16 | 2020-04-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117043574 | POLE_BROK_REPL - #2SE/O 5251 GROVE ST SO | 35215168 |  |  | STS-POLE_BROK_REPL - #2SE/O 5251 GROVE S | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3103 | -122.545 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL32 | 14345 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102028311 | RELW OH PRI CLR JPOL BTKA RESD SWRK ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-16 | 2020-04-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117043576 | POLE_BROK_REPL - 18730 CANYON RD SONOMA | 35215173 |  |  | STS-POLE_BROK_REPL - 18730 CANYON RD SON | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.3048 | -122.5387 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3219 | 11473 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101992676 | RELW OH PRI CLR JPOL REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-16 | 2020-04-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117043577 | POLE_BROK_REPL - 18803 CANYON RD SONOMA | 35202287 |  |  | STS-POLE_BROK_REPL - 18803 CANYON RD SON | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.2995 | -122.5346 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3224 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21.4 | 21.4 |  |  | 0 | 21.4 | 21.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101992723 | OH PRI CLR JPOL BTKA RELW RESD ESTR FMOB TER2 PRTO FSRP | Pole | 2020-11-25 |  | COMP | 2020-11-25 | [16 empty] | 2019-04-16 | 2020-04-16 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042721104 | 11862.9 | 1242.3 | 880.3 | -271.5 | -271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117043580 | POLE_DECA_REPL - 18710 CANYON RDSONOMA95 | 35089355 |  |  | STS-POLE_DECA_REPL - 18710 CANYON RDSONO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.3091 | -122.539 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL32 | 13127 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 34.3 | 29.1 | 5.2 |  | 0 | 34.3 | 29.1 | 5.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101992805 | RELW OH PRI CLR JPOL REMT SWRK ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole | 2021-02-10 | 2021-02-09 | COMP | 2021-02-09 |  |  | 2020-06-04 | 2020-06-04 | [12 empty] | 2019-04-16 | 2019-10-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | Santa Rosa |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117049813 | POLE_DECA_REPL - 3771 CORY LNSONOMA95476 | 35215225 |  |  | STS-POLE_DECA_REPL - 3771 CORY LNSONOMA9 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2985 | -122.5332 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3224 | 6551 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101992722 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117050999 | POLE_DECA_REPL - #1S/O #1W/O 3000 HAWKS | 35202335 |  |  | STS-POLE_DECA_REPL - #1S/O #1W/O 3000 HA | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 38.2928 | -122.5282 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3225 | 10545 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.2 | 34.2 |  |  | 0 | 34.2 | 34.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102028337 | RELW OH PRI CLR JPOL REMT SWRK ESTR GO BTKA REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-08 |  | COMP | 2021-01-08 | [16 empty] | 2019-04-17 | 2020-04-17 | 2020-10-09 | 2020-10-09 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042721104 | 13375.73 |  | -1013.6 | 1163 | 1163 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117051000 | POLE_DECA_REPL - #1S/O 3000 HAWKS BEARDS | 35215232 |  |  | STS-POLE_DECA_REPL - #1S/O 3000 HAWKS BE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2931 | -122.5276 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3225 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102030058 | RELW OH PRI CLR JPOL REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117051001 | POLE_DECA_REPL - #1S/W/O 3150 HAWKS BEAR | 35215236 |  |  | STS-POLE_DECA_REPL - #1S/W/O 3150 HAWKS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2945 | -122.5316 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3225 | 10545 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101992736 | OH NOAC RELW PRI CLR JPOL REMT SWRK ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117051003 | POLE_DECA_REPL - #1SW/O 3000 HAWKS BEARD | 35215240 |  |  | STS-POLE_DECA_REPL - #1SW/O 3000 HAWKS B | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 38.2932 | -122.5286 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3225 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102028336 | RELW OH PRI CLR JPOL REMT SWRK ESTR BTKA REAR FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117051659 | POLE_DECA_REPL - #1NW/O 3480 HAWKS BEARD | 35215250 |  |  | STS-POLE_DECA_REPL - #1NW/O 3480 HAWKS B | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2964 | -122.5362 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3224 | 10545 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102028349 | RELW OH PRI CLR JPOL RESD REMT SWRK ESTR BTKA REAR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117056614 | POLE_DECA_REPL - 1229 SOBRE VISTA DR 3S | 35202371 |  |  | STS-POLE_DECA_REPL - 1229 SOBRE VISTA DR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 38.3325 | -122.5133 |  | TIER 2 | 57 | 04307-1102, DUNBAR | LL3302 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 10.4 | 10.4 |  |  | 0 | 10.4 | 10.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101966097 | RELW OH SERV CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-14 |  | COMP | 2020-12-14 | [16 empty] | 2019-04-18 | 2020-04-18 | 2020-06-30 | 2020-06-30 | 2021 CBP Plan | 2021-01-31 | QUES |  | 043071102 | 7427.49 | 1358.8 | 699.3 | -181 | -181 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117067425 | POLE_BROK_REPL - 1/P R/O 19400 WYATT RD | 35215326 |  |  | STS-POLE_BROK_REPL - 1/P R/O 19400 WYATT | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2895 | -122.5073 |  | TIER 2 | 305 | 04272-1104, SONOMA | MM3303 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102004934 | RELW PRI OH CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-19 | 2020-04-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117067426 | POLE_BROK_REPL - 1/P NW/F 1590 FOWLER CR | 35215331 |  |  | STS-POLE_BROK_REPL - 1/P NW/F 1590 FOWLE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.2881 | -122.5068 |  | TIER 2 | 305 | 04272-1104, SONOMA | MM3303 | 2539 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101992645 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-19 | 2020-04-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117067628 | POLE_DECA_REPL - #4 2399 THORNSBERY RD.S | 35215337 |  |  | STS-POLE_DECA_REPL - #4 2399 THORNSBERY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.2843 | -122.4183 |  | TIER 2 | 550 | 04272-1105, SONOMA | MM3504 | 91357 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101993328 | RELW OH PRI CLR JPOL FIRE TRAF FLAG ESTR BTKA PRTO USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-19 | 2020-04-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117068714 | POLE_BURN_REPL - #4 NE/O R/O 2270 THORNS | 35215346 |  |  | STS-POLE_BURN_REPL - #4 NE/O R/O 2270 TH | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 38.2882 | -122.417 |  | TIER 2 | 550 | 04272-1105, SONOMA | MM3504 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 101993318 | RELW PRI OH CLR JPOL FIRE NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117068938 | POLE_DECA_REPL - 2151 LOVALL VALLEY RD S | 35215392 |  |  | STS-POLE_DECA_REPL - 2151 LOVALL VALLEY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.2958 | -122.4233 |  | TIER 2 | 550 | 04272-1105, SONOMA | LL3523 | 11627 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102032993 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117070395 | POLE_DECA_REPL - R/O 1872 THORNSBERRY RD | 35215417 |  |  | STS-POLE_DECA_REPL - R/O 1872 THORNSBERR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.2934 | -122.421 |  | TIER 2 | 550 | 04272-1105, SONOMA | LL3523 | 6375 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102032637 | RELW OH PRI CLR JPOL RESD ESTR BTKA USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2019-11-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117070396 | POLE_DECA_REPL - #1 E/O 1870 THORNSBERRY | 35202415 |  |  | STS-POLE_DECA_REPL - #1 E/O 1870 THORNSB | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 38.2934 | -122.422 |  | TIER 2 | 550 | 04272-1105, SONOMA | LL3523 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14 | 14 |  |  | 0 | 14 | 14 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101995241 | OH RELW PRI CLR JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-01 |  | COMP | 2021-02-01 | [16 empty] | 2019-04-20 | 2020-04-20 | 2020-11-19 | 2020-11-19 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042721105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117070725 | POLE_DECA_REPL - 3303 WOOD VALLEY RDSONO | 35215422 |  |  | STS-POLE_DECA_REPL - 3303 WOOD VALLEY RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.2926 | -122.4133 |  | TIER 2 | 550 | 04272-1105, SONOMA | LL3524 | 229588 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101995221 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117071091 | POLE_BROK_REPL - R/O/2140 GROVE ST PVT S | 35215436 |  |  | STS-POLE_BROK_REPL - R/O/2140 GROVE ST P | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 38.2904 | -122.5187 |  | TIER 2 | 305 | 04272-1104, SONOMA | MM3301 | 6469 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 102008292 | RELW OH PRI CLR JPOL REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-20 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721104 | 1 | 34.8 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117077023 | POLE_DECA_REPL - #4 W/O 1590 STAGE GULCH | 35215568 |  |  | STS-POLE_DECA_REPL - #4 W/O 1590 STAGE G | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land JointPole |  |  | 38.2354 | -122.5116 |  | TIER 2 | 329 | 04272-1107, SONOMA | NN33 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101997216 | RELW OH PRI CLR JPOL RESD REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-22 | 2020-04-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721107 | 1 | 40.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117077025 | POLE_DECA_REPL - #1 N/O #4 W/O 1590 STAG | 35202144 |  |  | STS-POLE_DECA_REPL - #1 N/O #4 W/O 1590 | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2356 | -122.5117 |  | TIER 2 | 329 | 04272-1107, SONOMA | NN33 | 4437 | Y | 311 |  |  |  |  | Scheduled | Order Operation | [6 empty] | 24.1 | 24.1 |  |  | 2 | 22.1 | 22.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101997217 | RELW OH PRI CLR JPOL REMT SWRK ESTR GO BTKA REAR PROG FMOB TER2 PRTO FSRP | Pole | 2020-12-10 | 2020-12-10 | COMP | 2020-12-10 | [16 empty] | 2019-04-22 | 2020-04-22 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042721107 | 12332.46 | 4353.9 | 2998.6 | -506.8 | -506.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 118179326 | POLE_BROK_REPL - A/F 3440 WOOD VALLEY RD | 35215928 |  |  | STS-POLE_BROK_REPL - A/F 3440 WOOD VALLE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 38.2911 | -122.4126 |  | TIER 2 | 550 | 04272-1105, SONOMA | MM3504 | 229588 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101993345 | OH PRI JAR FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-11-16 | 2020-11-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042721105 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117013059 | POLE_BROK_REPL - #2 E/O 2500 GROVE ST SO | 35202195 |  |  | STS-POLE_BROK_REPL - #2 E/O 2500 GROVE S | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2936 | -122.5198 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3321 | 127933 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 45.8 | 45.8 |  |  | 0 | 45.8 | 45.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101982941 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-07 | 2021-01-22 | COMP | 2020-12-07 | [16 empty] | 2019-04-11 | 2020-04-11 | 2020-10-10 | 2020-10-10 | 2021 CBP Plan | 2021-02-28 | QUES |  | 042721104 | 24079.11 | 1286.9 | 427.8 | -271.5 | -271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117027089 | POLE_DECA_REPL - #1 N/O 17914 CARRIGER R | 35202227 |  |  | STS-POLE_DECA_REPL - #1 N/O 17914 CARRIG | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3079 | -122.5168 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3316 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.7 | 22.7 |  |  | 0 | 22.7 | 22.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101983527 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-10 | 2021-01-30 | COMP | 2020-12-10 | [16 empty] | 2019-04-14 | 2020-04-14 | 2020-11-18 | 2020-11-18 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042721104 | 14023.91 | 1591.7 | 735.5 | -325.8 | -325.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117050985 | POLE_DECA_REPL - #2S/O #1SW/O 3000 HAWKS | 35202330 |  |  | STS-POLE_DECA_REPL - #2S/O #1SW/O 3000 H | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2923 | -122.528 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3225 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15 | 15 |  |  | 0 | 15 | 15 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101992734 | RELW OH PRI CLR JPOL REMT SWRK ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole | 2020-12-07 | 2021-01-26 | COMP | 2020-12-07 | [16 empty] | 2019-04-17 | 2020-04-17 | 2020-10-09 | 2020-10-09 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042721104 | 5974.74 | 1242.3 | -422.9 | -941.2 | -941.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 117069260 | POLE_DECA_REPL - R/O 2190 THORNSBERRY RD | 35202405 |  |  | STS-POLE_DECA_REPL - R/O 2190 THORNSBERR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2897 | -122.4176 |  | TIER 2 | 550 | 04272-1105, SONOMA | MM3504 | 229588 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.4 | 40.4 |  |  | 0 | 40.4 | 40.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101993362 | RELW OH PRI CLR JPOL FIRE NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-09 | 2021-02-04 | COMP | 2020-12-09 | [16 empty] | 2019-04-20 | 2020-04-20 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-01-31 | QUES |  | 042721105 | 21280.52 | 1533.4 | 445.9 | -434.4 | -434.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | SONOMA | Petaluma |  |  | OPEN | 115597126 | REPL POLE 13410 W ARNOLD DR | 35069775 |  |  | GC REPL POLE 13410 W ARNOLD DR | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.3681 | -122.5244 |  | TIER 2 | 57 | 04307-1102, DUNBAR | KK3306 |  | Y | 311 |  |  | 2021-03-31 06:00 | 2021-03-31 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 74.1 | 74.1 |  |  | 14.5 | 59.6 | 59.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102004433 | REGW OH TER2 | Pole | 2019-08-09 | 2019-11-12 | COMP | 2019-06-05 |  |  | 2019-11-11 | 2019-11-11 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-02 | Santa Rosa |  | 043071102 | 27697.32 | 11861.8 |  |  |  | 3527.3 |  | 3527.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
North | SO | SONOMA | Petaluma |  |  | OPEN | 117030214 | POLE_DECA_REPL - #2 E/O 2151 GROVE ST SO | 35202230 |  |  | STS-POLE_DECA_REPL - #2 E/O 2151 GROVE S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 38.2947 | -122.5154 |  | TIER 2 | 305 | 04272-1104, SONOMA | LL3322 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.4 | 15.4 |  |  | 0 | 15.4 | 15.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101982935 | RELW OH PRI CLR REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-03 | 2020-12-03 | COMP | 2020-12-03 | [16 empty] | 2019-04-14 | 2020-04-14 | 2020-11-18 | 2020-11-18 | 2021 CBP Plan | 2021-02-28 | QUES |  | 042721104 | 6140.65 | 1242.3 | 789.8 | -90.5 | -90.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | TOMALES | Petaluma |  |  | OPEN | 117206429 | POLE_DECA_REPL - 500 CERINI RD TOMALES | 35214597 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 38.2343 | -122.8833 |  | TIER 2 | 327 | 04227-1103, COTATI | NN24 | 2437 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 102011230 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 042271103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
North | SO | TOMALES | Petaluma |  |  | OPEN | 117417346 | POLE_BURN_REPL - IRO 2365 TOMALES-PETALU | 35203121 |  |  | STS-POLE_BURN_REPL - IRO 2365 TOMALES-PE | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 38.2363 | -122.8559 |  | TIER 2 | 327 | 04227-1103, COTATI | NN24 | 2437 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 31.5 | 31.5 |  |  | 0 | 31.5 | 31.5 |  |  | EC | E | Pole | Burnt | Replace |  | 101996837 | RELW OH PRI INSP REMT FIRE SWRK ESTR BTKA FMOB TER2 FSRP | Pole | 2021-02-22 | 2021-02-22 | COMP | 2021-02-22 | [16 empty] | 2019-06-07 | 2020-06-07 | 2020-10-15 | 2020-10-15 | 2021 CBP Plan | 2021-02-28 | QUES |  | 042271103 | 14547.36 | 80.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC |  | Monterey |  |  | OPEN | 115597320 | +POLE_DECA_REPL- R/O 575 MAR VISTA PVTP | 35070209 |  |  | POLE_DECA_REPL R/O 575 MAR VISTA PVTP | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-01-09 | Renew Permit | 36.5903 | -121.9139 |  | TIER 2 |  |  | I0220 |  | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 52.2 | 52.2 |  |  | 2.5 | 50.6 | 50.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101734588 | REGW OH TER2 | Pole | 2020-03-24 | 2019-07-23 | COMP | 2019-06-07 |  |  | 2019-06-03 | 2019-07-09 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-06-30 | San Jose |  |  | 35650.56 | 14676.9 | -15840.9 | 14286.8 | 14286.8 | -9826.2 |  | -9826.2 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
South | CC |  | Monterey |  |  | OPEN | 115597119 | POLE_DECA_REPL - NWC\O RONDA RD @ ATAJO | 35069714 |  |  | POLE DECA REPLNWC\O RONDA RD @ ATAJO WAY | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.579 | -121.9279 |  | TIER 2 |  |  | J0203 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 53.5 | 53.5 |  |  | 44.5 | 37 | 37 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101736645 | REGW OH TER2 | Pole | 2019-06-04 | 2019-09-05 | COMP | 2019-06-04 |  |  | 2019-09-05 | 2019-09-05 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-06-30 | San Jose |  |  | 33523.26 | 38027.2 |  |  |  | 9016.3 |  | 9016.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
South | CC |  | Watsonville |  |  | OPEN | 115597139 | POLE_DECA_REPL - NW\C\O MAR MONTE AVE @ | 35069519 |  |  | POLE DECA REPL NW\C\O MAR MONTE AVE | UNSC | UNSC CONT SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.9517 | -121.8502 |  | TIER 2 |  |  | P1807 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 51.8 | 51.8 |  |  | 0 | 51.8 | 51.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101788513 | REGW OH TER2 FSRP | Pole | 2020-05-26 | 2020-10-21 | COMP | 2020-05-26 |  |  | 2020-10-21 | 2020-10-21 | [12 empty] | 2018-12-26 | 2019-12-31 | 2023-12-25 | 2023-12-25 | 2021 CBP Plan | 2020-05-26 | PIKEENG |  |  | 25089.15 | 934.4 | 37.4 | 37.4 | 37.4 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
South | CC | APTOS | Santa Cruz |  |  | OPEN | 117052327 | POLE_DECA_REPL - 46555 DAISY LANEAPTOS95 | 35202351 |  |  | STS-POLE_DECA_REPL - 46555 DAISY LANEAPT | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.9836 | -121.8339 |  | TIER 2 | 232 | 08369-2104, ROB ROY | O1814 | 1939 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.6 | 31.6 |  |  | 0 | 31.6 | 31.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101692155 | RELW OH PRI INSP JPOL FIRE NOAC SWRK ESTR REAR USA FMOB TER2 FSRP | Pole | 2020-12-04 | 2020-12-03 | COMP | 2020-12-03 | [16 empty] | 2019-04-17 | 2020-04-17 | 2020-11-03 | 2020-11-03 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 083692104 | 19141.78 | 409.1 | -814.5 | -271.5 | -271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | APTOS | Santa Cruz |  |  | OPEN | 117269051 | POLE_DECA_REPL - 529 ENCINO DRAPTOS95001 | 35202909 |  |  | STS-POLE_DECA_REPL - 529 ENCINO DRAPTOS9 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 36.9703 | -121.8801 |  | TIER 2 | 86 | 08369-2105, ROB ROY | O1718 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.2 | 16.2 |  |  | 0 | 16.2 | 16.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101692821 | RELW OH SEC JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-04 |  | COMP | 2020-12-04 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-09-02 | 2020-09-02 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 083692105 | 9546.37 | 17.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | APTOS | Santa Cruz |  |  | OPEN | 117328613 | POLE_DECA_REPL - MARTHA AVE 1/P/N/O 1200 | 35203050 |  |  | STS-POLE_DECA_REPL - MARTHA AVE 1/P/N/O | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.9846 | -121.8765 |  | TIER 2 | 86 | 08369-2105, ROB ROY | O1714 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.7 | 16.7 |  |  | 0 | 16.7 | 16.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101694624 | RELW OH SEC JPOL RESD ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-12 |  | COMP | 2021-01-12 | [16 empty] | 2019-05-28 | 2020-05-28 | 2020-11-03 | 2020-11-03 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 083692105 | 8487.97 | 195.8 | 187 | 676 | 676 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | APTOS | Watsonville |  |  | OPEN | 117337016 | POLE_DECA_REPL - 3460 VALENCIA RDAPTOS95 | 35203056 |  |  | STS-POLE_DECA_REPL - 3460 VALENCIA RDAPT | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 36.9872 | -121.8656 |  | TIER 2 | 232 | 08369-2104, ROB ROY | O1715 | 2563 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 58.2 | 58.2 |  |  | 0 | 58.2 | 58.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101690509 | RELW OH PRI JPOL RESD FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-20 |  | COMP | 2021-01-20 | [16 empty] | 2019-05-29 | 2020-05-29 | 2020-11-04 | 2020-11-04 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 083692104 | 25965.47 | 346.8 | 123.1 | 612.1 | 612.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | APTOS | Watsonville |  |  | OPEN | 117337112 | POLE_DECA_REPL - 1SE/O 3460 VALENCIA RDA | 35203059 |  |  | STS-POLE_DECA_REPL - 1SE/O 3460 VALENCIA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 36.9867 | -121.8654 |  | TIER 2 | 232 | 08369-2104, ROB ROY | O1715 | 2563 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 65.6 | 62 | 3.6 |  | 0 | 65.6 | 62 | 3.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103128226 | RELW OH PRI JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-03 |  | COMP | 2021-02-03 | [16 empty] | 2019-05-29 | 2020-05-29 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 083692104 | 29535.26 | 410.8 | 85.4 | 137.1 | 137.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | APTOS | Watsonville |  |  | COMP | 116988588 | POLE_DECA_REPL - 160 SIESTA DR APTOS VA | 35104305 |  |  | STS-POLE_DECA_REPL - 160 SIESTA DR APTOS | DOCC | DOCC | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-09 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 36.9779 | -121.8925 |  | TIER 2 | 86 | 08369-2105, ROB ROY | O1717 | 1153 | Y | 311 |  |  | 2021-02-08 07:00 | 2021-02-08 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 40.1 | 40.1 |  |  | 0 | 0 |  |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 103829739 | RELW OH PRI CREW COMP CLR JPOL RESD TRAF FLAG ESTR USA CCNT TER2 FSRP | Pole | 2020-12-07 | 2020-12-08 | COMP | 2020-11-23 | COMP | 2021-02-08 | 2020-12-08 | 2020-12-08 | [11 empty] | 2021-02-09 | 2021-02-08 | 2019-11-20 | 2020-08-06 | 2020-08-06 | B-Tag Addition 06.24.20 |  | Fresno |  | 083692105 | 22525.97 | 4830.1 | 4541.3 | 4476.1 | 4476.1 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-06-29
South | CC | AROMAS | Watsonville |  |  | OPEN | 117184437 | POLE_BROK_REPL - 1PN/CO/CARR AVE.-PERSER | 35215440 |  |  | STS-POLE_BROK_REPL - 1PN/CO/CARR AVE.-PE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 36.8866 | -121.634 |  | TIER 2 | 719 | 18274-2104, SAN BENITO | Q2320 | 3383 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101699568 | RELW OH PRI JPOL RESD ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182742104 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | BIG SUR | Monterey |  |  | OPEN | 117317749 | POLE_BROK_REPL - N/O ANDREW MOLERA ST PK | 35202994 |  |  | STS-POLE_BROK_REPL - N/O ANDREW MOLERA S | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.2933 | -121.8602 |  | TIER 2 | 888 | 18294-1102, OTTER | P03 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101672173 | RELW OH PRI REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-24 | 2020-05-24 | 2020-10-20 | 2020-10-20 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182941102 | 1 | 97.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | BIG SUR | Monterey |  |  | OPEN | 117344109 | POLE_DECA_REPL - END/O PARTINGTON CYN RD | 35203081 |  |  | STS-POLE_DECA_REPL - END/O PARTINGTON CY | DOCC | DOCC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 36.1939 | -121.7004 |  | TIER 2 | 888 | 18294-1102, OTTER | R07 | 6947 | Y | 311 | [12 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | H | Pole | Decayed/Rotten | Replace |  | 101677095 | RELW OH PRI CLR JPOL REAR REMT FIRE ESTR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-30 | 2020-05-30 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182941102 | 1 | 670 | 149.9 | 149.9 | 149.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | BIG SUR | Monterey |  |  | OPEN | 117346364 | POLE_DECA_REPL - EL SUR RCH HWY 1 13NW 5 | 35215811 |  |  | STS-POLE_DECA_REPL - EL SUR RCH HWY 1 13 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 36.3079 | -121.8725 |  | TIER 2 | 888 | 18294-1102, OTTER | P03 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.3 | 19.3 |  |  | 0 | 19.3 | 19.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101672196 | OH PRI JPOL REMT FIRE NOAC ESTR USA FSRP PRTO RELW FMOB TER2 | Pole | 2021-01-28 |  | COMP | 2021-01-28 | [16 empty] | 2019-05-30 | 2020-05-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182941102 | 21424.73 | 242.6 | 233.7 | 233.7 | 233.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | BIG SUR | Monterey |  |  | OPEN | 117418215 | POLE_DECA_REPL - ANDREW MOLERA ST PK HWY | 35215929 |  |  | STS-POLE_DECA_REPL - ANDREW MOLERA ST PK | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 36.2887 | -121.8389 |  | TIER 2 | 888 | 18294-1102, OTTER | P04 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.2 | 18.2 |  |  | 0 | 18.2 | 18.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101776079 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-01 |  | COMP | 2021-02-01 | [16 empty] | 2019-06-07 | 2020-06-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182941102 | 8414.3 | 563.1 | 554.2 | 280.5 | 280.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | BIG SUR | Monterey |  |  | OPEN | 117346365 | POLE_DECA_REPL - EL SUR RCH HWY 1 13NW 4 | 35215814 |  |  | STS-POLE_DECA_REPL - EL SUR RCH HWY 1 13 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.3071 | -121.8732 |  | TIER 2 | 888 | 18294-1102, OTTER | P03 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20 | 20 |  |  | 0 | 20 | 20 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101776083 | RELW OH PRI JPOL REMT FIRE NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-29 | 2021-02-02 | COMP | 2021-01-28 | [16 empty] | 2019-05-30 | 2020-05-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182941102 | 20971.79 | 122.2 | 113.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | CARMEL | Monterey |  |  | OPEN | 116842796 | POLE_BROK_REPL - R/O 25315 ARRIBA DEL MU | 35202512 |  |  | STS-POLE_BROK_REPL - R/O 25315 ARRIBA DE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 36.5557 | -121.8986 |  | TIER 2 | 867 | 18229-1102, HATTON | J0311 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.6 | 20.6 |  |  | 0 | 20.6 | 20.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101754823 | RELW OH PRI JPOL RESD ESTR TER2 BTKA PROG FMOB PRTO FSRP | Pole | 2020-12-29 |  | COMP | 2020-12-29 | [16 empty] | 2019-03-26 | 2020-03-26 | 2020-10-21 | 2020-10-21 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182291102 | 14740.99 | 58 | -1100 | 485.2 | 485.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | CARMEL | Monterey |  |  | OPEN | 115098895 | +REPL POLE:R\O 28182 ROBINSON CYN RD PV | 35063994 |  |  | XSTS-REPL POLE:R\O 28182 ROBINSON CYN. | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.5055 | -121.8099 |  | TIER 2 |  |  | K05 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 51.1 | 51.1 |  |  | 0.5 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101743577 | POHW OH TNT JPOL TER2 | Pole | 2019-05-03 | 2019-06-12 | COMP | 2019-05-03 | [16 empty] | 2018-10-29 | 2019-10-29 |  | 2019-10-29 | Q1 Work Plan | 2019-07-01 | QUES |  |  | 37077.78 | 8823.7 | -1677.8 |  |  | 138.8 |  | 138.8 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
South | CC | CARMEL | Monterey |  |  | OPEN | 115098896 | +POLE_DECA_REPL- 1W/R/O 27590 MOONCREST | 35064277 |  |  | XSTS-REPL POLE:1W/R/O 27590 MOONCREST DR | UNSC | UNSC CONT SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.526 | -121.8026 |  | TIER 2 |  |  | K0509 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 51.1 | 51.1 |  |  | 2 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101743728 | POHW OH TNT TER2 | Pole | 2020-03-24 | 2020-05-21 | COMP | 2019-04-18 | [16 empty] | 2018-10-29 | 2019-10-29 |  | 2019-10-29 | Q1 Work Plan | 2019-07-01 | QUES |  |  | 25989.26 | 3980.1 | -643.4 | [5 empty] | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
South | CC | CARMEL | Monterey |  |  | OPEN | 120106376 | POLE_BROK_REPL - 579 VIEJO RD CARMEL AGU | 35218323 |  |  | STS-POLE_BROK_REPL - 579 VIEJO RD CARMEL | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-31 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.5767 | -121.8965 |  | TIER 2 | 1757 | 18285-2204, VIEJO | J0302 | 7567 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Dispatched | CLICK | [6 empty] | 50.9 | 50.9 |  |  | 1 | 49.9 | 49.9 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 103870555 | RELW OH PRI TMAN RESD FIRE FLAG BTKA USA CCNT TER2 ESTR | Pole | 2021-01-12 | 2021-01-12 | COMP | 2020-12-21 |  |  | 2020-12-23 | 2020-12-23 | [12 empty] | 2020-11-28 | 2021-02-28 |  | 2021-02-28 | B tag clean up 12/2/2020 |  | Fresno |  | 182852204 | 22774.44 | 1694.6 | 1694.6 | 224.3 | 224.3 |  |  |  | Electric Distribution | N | Pulled from MPP Import File | N |  | Y | 2020-12-02
South | CC | CARMEL VALLEY | King City |  |  | OPEN | 117107606 | POLE_DECA_REPL - 42250 CARMEL VALLEY RDC | 35209763 |  |  | STS-POLE_DECA_REPL - 42250 CARMEL VALLEY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro |  |  | 36.3114 | -121.4818 |  | TIER 2 | 710 | 18208-2103, LOS OSITOS | P13 | 9551 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101777207 | RELW OH PRI INSP REMT TRAF ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-26 | 2020-04-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 182082103 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | CARMEL VALLEY | Monterey |  |  | OPEN | 116951194 | POLE_DECA_REPL - R/O 64 E CARMEL VLY RD | 35202613 |  |  | STS-POLE_DECA_REPL - R/O 64 E CARMEL VLY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.4756 | -121.7186 |  | TIER 2 | 713 | 18237-1111, LAURELES | L0714 | 2943 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101777581 | RELW OH SEC JPOL RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-03 | 2020-04-03 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182371111 | 1 | 73.3 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | CARMEL VALLEY | Monterey |  |  | OPEN | 117033490 | POLE_BROK_REPL - 3/P/S 62 HILLTOP RANCHC | 35215037 |  |  | STS-POLE_BROK_REPL - 3/P/S 62 HILLTOP RA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 36.4793 | -121.7135 |  | TIER 2 | 713 | 18237-1111, LAURELES | L07 | 2943 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101750574 | RELW OH PRI JPOL RESD REMT ESTR GO REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182371111 | 1 | 64.4 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | CARMEL VALLEY | Monterey |  |  | OPEN | 117264524 | POLE_BROK_REPL - 411–425 EL CAMINITO RDC | 35202888 |  |  | STS-POLE_BROK_REPL - 411–425 EL CAMINITO | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.4954 | -121.7165 |  | TIER 2 | 1316 | 18237-1112, LAURELES | L0704 | 6899 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 30 | 30 |  |  | 0 | 30 | 30 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103407264 | RELW OH PRI JPOL RESD REMT ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2021-02-05 |  | COMP | 2021-02-05 | [16 empty] | 2019-05-17 | 2020-05-17 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182371112 | 13977.02 | 542.9 | 525.2 | 525.2 | 525.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | CARMEL VALLEY | Monterey |  |  | OPEN | 117343744 | POLE_DECA_REPL - 7W/O 130 CARMEL VLY RD. | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 36.4791 | -121.7013 |  | TIER 2 | 713 | 18237-1111, LAURELES | L08 | 8643 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101777568 | REGW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-05-30 | 2020-05-30 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan |  | UNASSIGNED |  | 182371111 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | CARMEL VALLEY | Monterey |  |  | OPEN | 117689310 | POLE_BROK_REPL - 6/P/N/O FUSE 7601R/O 33 | 35215957 |  |  | STS-POLE_BROK_REPL - 6/P/N/O FUSE 7601R/ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro JointPole |  |  | 36.4523 | -121.6812 |  | TIER 2 | 713 | 18237-1111, LAURELES | L08 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101750553 | RELW OH PRI ESTR GO TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182371111 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | FELTON | Santa Cruz |  |  | OPEN | 116822370 | POLE_BROK_REPL - C/O LAUREL DR/PLATEAU D | 35133996 |  |  | STS-POLE_BROK_REPL - C/O LAUREL DR/PLATE | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 37.0468 | -122.0772 |  | TIER 2 | 25 | 08362-2106, CAMP EVERS | N1204 | 1613 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101673528 | RELW OH PRI JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO | Pole |  | 2019-10-17 | REQD | [17 empty] | 2019-03-24 | 2020-03-24 |  | 2020-03-24 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 083622106 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | CC | FELTON | Santa Cruz |  |  | OPEN | 116826864 | TREE_DECA_INPL - 5795 HILLSIDE DR FELTON | 35135648 |  |  | STS-TREE_DECA_INPL - 5795 HILLSIDE DR FE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0451 | -122.0778 |  | TIER 2 | 25 | 08362-2106, CAMP EVERS | N1203 | 834583 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 2 | 0 | 0 | 0 | 42.4 | 42.4 |  |  | 0 | 42.4 | 42.4 |  |  | EC | F | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 101802981 | RELW OH PRI JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-08-14 | 2021-01-25 | COMP | 2020-08-14 |  |  | 2021-01-25 | 2021-01-25 | [12 empty] | 2019-03-25 | 2020-03-25 | 2024-03-25 | 2024-03-25 | 2021 CBP Plan |  | Bakersfield |  | 083622106 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | FELTON | Santa Cruz |  |  | OPEN | 117184571 | POLE_DECA_REPL - 329 HIHN DRFELTON95018 | 35134240 |  |  | STS-POLE_DECA_REPL - 329 HIHN DRFELTON95 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0489 | -122.0771 |  | TIER 2 | 25 | 08362-2106, CAMP EVERS | M1224 | 1613 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.5 | 38.2 | 1.3 |  | 0 | 39.5 | 38.2 | 1.3 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101671279 | RELW OH SEC JPOL RESD ESTR BTKA FMOB TER2 PRTO | Pole | 2020-01-27 | 2021-01-22 | COMP | 2019-11-15 |  |  | 2021-01-22 | 2021-01-22 | [12 empty] | 2019-05-08 | 2020-05-08 |  | 2020-05-08 | 2021 CBP Plan |  | UNASSIGNED |  | 083622106 | 14389.63 | 183.7 | 27.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | GILROY | Hollister |  |  | OPEN | 117018827 | POLE_BROK_REPL - 2\P\NW 3\P\SO MB 6265 H | 35214910 |  |  | STS-POLE_BROK_REPL - 2\P\NW 3\P\SO MB 62 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 36.9841 | -121.4394 |  | TIER 2 | 543 | 18249-2102, HOLLISTER | A15 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103521878 | RELW OH PRI INSP JPOL ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-12 | 2020-04-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182492102 | 1 | 155 | 128.3 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | GILROY | Hollister |  |  | OPEN | 117017367 | POLE_BROK_REPL - HWY 152 F\O 6350 1\P\N | 35214905 |  |  | STS-POLE_BROK_REPL - HWY 152 F\O 6350 1\ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.9813 | -121.4383 |  | TIER 2 | 543 | 18249-2102, HOLLISTER | A15 |  | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101718109 | RELW PRI OH INSP ESTR BTKA FMOB TER2 FSRP | Pole | 2021-01-28 | 2021-01-28 | COMP | 2021-01-28 | [16 empty] | 2019-04-12 | 2020-04-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182492102 | 7743.09 | 360.2 | 319.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | GONZALES | Salinas |  |  | OPEN | 117088111 | CONN_INCR_REPL - 6W/O 34247 GLORIA RD. G | 35214613 |  |  | STS-CONN_INCR_REPL - 6W/O 34247 GLORIA R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.5171 | -121.3462 |  | TIER 2 | 553 | 18205-2101, SOLEDAD | K17 | 25797 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Connector | Incorrectly Installed | Replace |  | 101752354 | RELW OH PRI NOAC CLR JPOL REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-23 | 2020-04-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182052101 | 1 | 10.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | GREENFIELD | King City |  |  | OPEN | 117107608 | POLE_DECA_REPL - 2NW/O 41879 CARMEL VALL | 35209768 |  |  | STS-POLE_DECA_REPL - 2NW/O 41879 CARMEL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 36.3192 | -121.4889 |  | TIER 2 | 710 | 18208-2103, LOS OSITOS | P13 | 9551 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.3 | 24.3 |  |  | 0 | 24.3 | 24.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101719305 | RELW OH PRI INSP RESD FIRE TRAF ESTR GO BTKA USA FSRP FMOB TER2 | Pole | 2021-02-09 |  | COMP | 2021-02-09 | [16 empty] | 2019-04-26 | 2020-04-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 182082103 | 14154.2 | 577.6 | 568.7 | 1668.7 | 1668.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | GREENFIELD | King City |  |  | OPEN | 117156577 | POLE_BROK_REPL - 7W/O 45133 ELM AVE. GRE | 35209113 |  |  | STS-POLE_BROK_REPL - 7W/O 45133 ELM AVE. | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.2664 | -121.3804 |  | TIER 2 | 710 | 18208-2103, LOS OSITOS | Q16 | 3010 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.7 | 18.7 |  |  | 0 | 18.7 | 18.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101766003 | RELW OH PRI INSP REMT FIRE ESTR BTKA FMOB TER2 FSRP | Pole | 2021-02-22 |  | COMP | 2021-02-22 | [16 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 182082103 | 7935.84 | 55.6 | 46.7 | 1146.7 | 1146.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | GREENFIELD | King City |  |  | OPEN | 117232992 | POLE_DECA_REPL - ENTRANCE TO 30005 ARROY | 35208847 |  |  | STS-POLE_DECA_REPL - ENTRANCE TO 30005 A | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.2457 | -121.4323 |  | TIER 2 | 710 | 18208-2103, LOS OSITOS | Q1420 | 3027 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19 | 19 |  |  | 0 | 19 | 19 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101719397 | PRI RELW OH INSP JPOL REMT FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 182082103 | 8686.97 | 55.6 | 46.7 | 1146.7 | 1146.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | GREENFIELD | King City |  |  | OPEN | 117232993 | POLE_BROK_REPL - 1NW/O 46325 ARROYO SECO | 35202700 |  |  | STS-POLE_BROK_REPL - 1NW/O 46325 ARROYO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 36.2497 | -121.4289 |  | TIER 2 | 710 | 18208-2103, LOS OSITOS | Q1420 | 8839 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101718975 | RELW OH PRI INSP JPOL REMT FIRE ESTR GO BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2020-10-16 | 2020-10-16 | 2021 CBP Plan | 2021-02-28 | EEI |  | 182082103 | 1 | 64.4 | 46.7 | 1146.7 | 1146.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | GREENFIELD | King City |  |  | OPEN | 117234524 | POLE_BROK_REPL - A/F 47407 ARROYO SECO R | 35208862 |  |  | STS-POLE_BROK_REPL - A/F 47407 ARROYO SE | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 36.2365 | -121.4744 |  | TIER 2 | 710 | 18208-2103, LOS OSITOS | Q1324 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 52.3 | 52.3 |  |  | 0 | 52.3 | 52.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101719741 | OH PRI JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP RELW | Pole | 2021-02-19 |  | COMP | 2021-02-19 | [16 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 182082103 | 25071.4 | 233.7 | 233.7 | 233.7 | 233.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | GREENFIELD | King City |  |  | OPEN | 117281577 | CRSS_DECA_REPL - 47463 ARROYO SECO. (1ST | 35209400 |  |  | STS-CRSS_DECA_REPL - 47463 ARROYO SECO. | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.2333 | -121.4681 |  | TIER 2 | 710 | 18208-2103, LOS OSITOS | Q13 | 3027 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Crossarm | Decayed/Rotten | Replace |  | 101719727 | RELW OH PRI INSP JPOL REMT FIRE ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-20 | 2020-05-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 182082103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | GREENFIELD | King City |  |  | OPEN | 117298475 | POLE_BROK_REPL - 2SW/O 47247 ARROYO SECO | 35209533 |  |  | STS-POLE_BROK_REPL - 2SW/O 47247 ARROYO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.236 | -121.45 |  | TIER 2 | 710 | 18208-2103, LOS OSITOS | Q14 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28 | 28 |  |  | 0 | 28 | 28 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101776820 | RELW OH PRI INSP REMT FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2021-02-17 |  | COMP | 2021-02-17 | [16 empty] | 2019-05-21 | 2020-05-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 182082103 | 10508.14 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | GREENFIELD | King City |  |  | OPEN | 117325774 | POLE_BROK_REPL - 1N/O 47177 ARROYO SECO | 35209766 |  |  | STS-POLE_BROK_REPL - 1N/O 47177 ARROYO S | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.2409 | -121.433 |  | TIER 2 | 710 | 18208-2103, LOS OSITOS | Q1425 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101719524 | RELW OH PRI INSP CUST JPOL RESD REMT ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-27 | 2020-05-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 182082103 | 1 | 26.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | GREENFIELD | King City |  |  | OPEN | 117325891 | POLE_DECA_REPL - 3SW/O 47155 ARROYO SECO | 35203037 |  |  | STS-POLE_DECA_REPL - 3SW/O 47155 ARROYO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 36.2399 | -121.4366 |  | TIER 2 | 710 | 18208-2103, LOS OSITOS | Q1424 | 3027 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101719562 | RELW OH PRI INSP CUST CLR JPOL ESTR GO BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-27 | 2020-05-27 | 2020-10-17 | 2020-10-17 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182082103 | 1 | 58 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | GREENFIELD | King City |  |  | OPEN | 117325892 | POLE_BROK_REPL - 1W/O 47155 ARROYO SECO | 35203039 |  |  | STS-POLE_BROK_REPL - 1W/O 47155 ARROYO S | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 36.2406 | -121.4358 |  | TIER 2 | 710 | 18208-2103, LOS OSITOS | Q1424 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 15.4 | 15.4 |  |  | 0 | 15.4 | 15.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101719571 | RELW OH PRI INSP CUST JPOL REMT FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole | 2021-02-22 |  | COMP | 2021-02-22 | [16 empty] | 2019-05-27 | 2020-05-27 | 2020-10-17 | 2020-10-17 | 2021 CBP Plan | 2021-02-28 | EEI |  | 182082103 | 5875.13 | 17.7 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | GREENFIELD | King City |  |  | OPEN | 117326625 | POLE_DECA_REPL - 2SE/O 47385 ARROYO SECO | 35209771 |  |  | STS-POLE_DECA_REPL - 2SE/O 47385 ARROYO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 36.2312 | -121.4677 |  | TIER 2 | 710 | 18208-2103, LOS OSITOS | R13 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101719713 | RELW OH SEC INSP CUST JPOL REMT ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-28 | 2020-05-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 182082103 | 1 | 43.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | GREENFIELD | King City |  |  | OPEN | 117263867 | POLE_DECA_REPL - 1SW/O M/B 44500 CARMEL | 35209135 |  |  | STS-POLE_DECA_REPL - 1SW/O M/B 44500 CAR | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.2713 | -121.4467 |  | TIER 2 | 710 | 18208-2103, LOS OSITOS | Q14 | 9211 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.8 | 44.8 |  |  | 0 | 44.8 | 44.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101719094 | RELW OH ESTR PRI INSP REMT FIRE GO BTKA FMOB TER2 FSRP | Pole | 2021-02-02 | 2021-02-02 | COMP | 2021-02-02 | [16 empty] | 2019-05-17 | 2020-05-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | EEI |  | 182082103 | 19894.7 | 73.3 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | HOLLISTER | Hollister |  |  | OPEN | 116851500 | POLE_BROK_REPL - 38778 HWY 152 HOLLISTER | 35192793 |  |  | STS-POLE_BROK_REPL - 38778 HWY 152 HOLLI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.0603 | -121.2218 |  | TIER 2 | 543 | 18249-2102, HOLLISTER | YY20 | 9765 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101718997 | RELW OH PRI INSP CLR PUBL ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2020-11-14 | 2020-11-14 | 2021 CBP Plan | 2020-12-31 | ENENG |  | 182492102 | 1 | 40.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | HOLLISTER | Hollister |  |  | OPEN | 117034703 | POLE_DECA_REPL - 1P/N/OF 14800 PACHECO P | 35089022 |  |  | STS-POLE_DECA_REPL - 1P/N/OF 14800 PACHE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 37.0351 | -121.309 |  | TIER 2 | 543 | 18249-2102, HOLLISTER | ZZ18 | 9757 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 72.4 | 72.4 |  |  | 0 | 72.4 | 72.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103006366 | RELW OH PRI INSP JPOL FIRE NOAC ESTR BTKA FMOB TER2 FSRP | Pole | 2021-01-29 |  | COMP | 2021-01-29 | [16 empty] | 2019-04-15 | 2019-09-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | San Jose |  | 182492102 | 7851.14 | 211.1 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | HOLLISTER | Hollister |  |  | OPEN | 117225544 | POLE_BROK_REPL - 10900 CIENEGA RDHOLLIST | 35202668 |  |  | STS-POLE_BROK_REPL - 10900 CIENEGA RDHOL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Enviro JointPole |  |  | 36.7429 | -121.373 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | F16 | 4087 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 43.4 | 43.4 |  |  | 0 | 43.4 | 43.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101710978 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-20 |  | COMP | 2021-01-20 | [16 empty] | 2019-05-13 | 2020-05-13 | 2020-08-17 | 2020-08-17 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182492105 | 23197.92 | 8.8 | -1251.3 | -162.8 | -162.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | HOLLISTER | Hollister |  |  | OPEN | 117230570 | POLE_BROK_REPL - NICHOLAS TURK FARM GRAS | 35214917 |  |  | STS-POLE_BROK_REPL - NICHOLAS TURK FARM | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 36.7356 | -121.3926 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | F16 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29 | 29 |  |  | 0 | 29 | 29 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101711699 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-28 | 2021-01-27 | COMP | 2021-01-27 | [16 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182492105 | 12237.85 | 55.6 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | HOLLISTER | Hollister |  |  | OPEN | 117231847 | POLE_DECA_REPL - FROM FUSE 4197GRASS VAL | 35214937 |  |  | STS-POLE_DECA_REPL - FROM FUSE 4197GRASS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.734 | -121.3856 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | F16 | 4197 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101711640 | RELW OH PRI ESTR SCOP SCPA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182492105 | 1 | 26.2 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | HOLLISTER | Hollister |  |  | OPEN | 117320637 | POLE_DECA_REPL - 7P/E/OF ENTRANCE TO 176 | 35203013 |  |  | STS-POLE_DECA_REPL - 7P/E/OF ENTRANCE TO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.0518 | -121.2716 |  | TIER 2 | 543 | 18249-2102, HOLLISTER | YY19 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101719045 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-25 | 2020-05-25 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182492102 | 1 | 242.3 | 61.1 | 61.1 | 61.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | Hollister | Hollister |  |  | OPEN | 118223809 | POLE_BROK_REPL - 3/N/17/E/1/N/O 15666 PA | 35215964 |  |  | STS-POLE_BROK_REPL - 3/N/17/E/1/N/O 1566 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.6462 | -121.0708 |  | TIER 2 | 1060 | 25367-1103, PANOCHE | H24 | 9525 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101772995 | OH PRI REMT JAR CGI PRTO RELW SWRK BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-12-03 | 2020-12-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 253671103 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | Hollister | Hollister |  |  | OPEN | 118239863 | POLE_DECA_REPL - 9/S/15/E/13/S/O 17441 P | 35215793 |  |  | STS-POLE_DECA_REPL - 9/S/15/E/13/S/O 174 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.6288 | -121.0565 |  | TIER 2 | 1060 | 25367-1103, PANOCHE | I24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101689945 | RELW OH PRI REMT NOAC ESTR GO FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-12-05 | 2020-12-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 253671103 | 1 | 26.2 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | HOLLISTER | Hollister |  |  | OPEN | 117217337 | +POLE_DECA_REPL- I/R/O/7722 CIENGA RD HO | 35136941 |  |  | STS-POLE_DECA_REPL - I/R/O/7722 CIENGA R | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.7701 | -121.4136 |  | TIER 2 | 241 | 18249-2106, HOLLISTER | E15 | 9387 | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-04 16:00 | Scheduled | CLICK | [6 empty] | 50.1 | 50.1 |  |  | 0.5 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101769975 | RELW OH PRI GO SCOP SCPA FMOB TER2 PRTO | Pole | 2019-11-27 | 2020-07-09 | COMP | 2019-11-27 | [16 empty] | 2019-05-11 | 2020-05-11 |  | 2020-05-11 | circuit based plan 2.14 | 2019-12-09 | San Jose |  | 182492106 | 15606.95 | 12676.7 | 6340.6 | 30802.5 | 30802.5 | 1467.1 |  | 1467.1 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | CC | HOLLISTER | Hollister |  |  | OPEN | 117217338 | POLE_DECA_REPL - 3/P/SW/O/7800 CIENGA RD | 35214760 |  |  | STS-POLE_DECA_REPL - 3/P/SW/O/7800 CIENG | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 36.7687 | -121.415 |  | TIER 2 | 241 | 18249-2106, HOLLISTER | F15 | 9387 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.4 | 14.4 |  |  | 0 | 14.4 | 14.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101711131 | RELW OH PRI ESTR GO FMOB TER2 FSRP PRTO | Pole | 2021-01-29 | 2021-01-28 | COMP | 2021-01-28 | [16 empty] | 2019-05-11 | 2020-05-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182492106 | 9892.68 | 111.2 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | MONTEREY | Monterey |  |  | OPEN | 117266551 | POLE_BROK_REPL - MAR VISTA/CRESCENT CTMO | 35202890 |  |  | STS-POLE_BROK_REPL - MAR VISTA/CRESCENT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 36.5838 | -121.9117 |  | TIER 2 | 1653 | 18285-2202, VIEJO | I0225 | 8021 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101733889 | RELW OH PRI JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-17 | 2020-05-17 | 2020-10-30 | 2020-10-30 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182852202 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | Monterey | Monterey |  |  | OPEN | 118280577 | POLE_DECA_REPL - 60 SIERRA VISTA DR MONT | 35202709 |  |  | STS-POLE_DECA_REPL - 60 SIERRA VISTA DR | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 36.5826 | -121.9081 |  | TIER 2 | 1757 | 18285-2204, VIEJO | I0225 | 9629 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101783558 | RELW OH PRI INSP JPOL RESD BTKA FMOB TER2 FSRP ESTR | Pole |  |  | REQD | [17 empty] | 2019-12-17 | 2020-12-17 | 2020-09-28 | 2020-09-28 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182852204 | 1 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | MONTEREY | Monterey |  |  | OPEN | 120049211 | TREE_DECA_INPL - 5 LINDA VISTA DR., MONT | 35214216 |  |  | STS-TREE_DECA_INPL - 5 LINDA VISTA DR., | UNSC | UNSC SRDY | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  | "New" A&B Tags additions. Inc | 1 | 2021-01-20 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.5839 | -121.9088 |  | TIER 2 | 1653 | 18285-2202, VIEJO | I0225 | 8021 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 11.2 | 11.2 |  |  | 0 | 11.2 | 11.2 |  |  | EC | B | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 101733898 | RELW OH SERV ESTR TER2 | Pole | 2020-12-10 | 2021-02-02 | COMP | 2020-12-10 |  |  | 2020-12-11 | 2020-12-15 | [12 empty] | 2020-11-17 | 2021-02-17 |  | 2021-02-17 | B tag clean up 11/19/2020 |  | Fresno |  | 182852202 | 13655.7 | 637.5 | 310 | [5 empty] | FRMMA/WMPMA - Electric | N | Pulled from MPP Import File | N |  | Y | 2020-11-19
South | CC | Paicines | Hollister |  |  | OPEN | 114868259 | POLE_DECA_REPL - Limekiln Rd 12 pole S.W | 35080914 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 36.6958 | -121.3339 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | G17 | 50527 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26 | 26 |  |  | 0 | 26 | 26 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101710919 | RELW OH PRI INSP FIRE BTKA SCOP SCPA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2018-08-09 | 2019-09-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | San Jose |  | 182492105 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117138570 | POLE_BROK_REPL - MONTEBENITO RCH LIMEKIL | 35202426 |  |  | STS-POLE_BROK_REPL - MONTEBENITO RCH LIM | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.6765 | -121.3758 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | H160 | 4709 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101711353 | RELW OH PRI PATR CLR FIRE NOAC ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-01 | 2020-05-01 | 2020-10-21 | 2020-10-21 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182492105 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117222472 | POLE_DECA_REPL - 2PE/O 28600 HWY 25PAICI | 35214836 |  |  | STS-POLE_DECA_REPL - 2PE/O 28600 HWY 25P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 36.5452 | -121.1571 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | K22 | 4519 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101690103 | RELW OH PRI CLR RESD FMOB ESTR BTKA USA TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-13 | 2020-05-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182492105 | 1 | 465.2 | 447.6 | 307.8 | 307.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117227303 | POLE_BROK_REPL - 1PS/O 29711 HWY 25 PAIC | 35215902 |  |  | STS-POLE_BROK_REPL - 1PS/O 29711 HWY 25 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 36.5317 | -121.1448 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | K22 | 4519 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101773351 | RELW OH PRI CNCL CLR MINR RESD GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-13 | 2020-05-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182492105 | 1 | 158.8 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117237332 | POLE_DECA_REPL - 3PE/O 1281 OLD HERNANDE | 35214989 |  |  | STS-POLE_DECA_REPL - 3PE/O 1281 OLD HERN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.511 | -121.0627 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | K24 | 4007 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101690298 | OH PRI REMT FIRE SWRK ESTR FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182492105 | 1 | 220.5 | 209.8 | 140.2 | 140.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117268961 | POLE_DECA_REPL - 18018 CIENEGA RD 7/P/W/ | 35202906 |  |  | STS-POLE_DECA_REPL - 18018 CIENEGA RD 7/ | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 36.6768 | -121.2867 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | H18 | 9459 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 59.3 | 58.6 | 0.7 |  | 0 | 59.3 | 58.6 | 0.7 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101701845 | RELW PRI OH CLR RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-11-06 |  | COMP | 2020-11-06 | [16 empty] | 2019-05-18 | 2020-05-18 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182492105 | 29191.97 | 137.5 | 0 | -135.8 | -135.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117284681 | INSU_BROK_REPL - 95043 PAICINES | 35215468 |  |  | STS-INSU_BROK_REPL - 95043 PAICINES | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.6202 | -121.2226 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | I20 | 39363 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Insulator | Broken/Damaged | Replace |  | 103407355 | RELW OH PRI CLR REMT SWRK ESTR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-20 | 2020-05-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182492105 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117435721 | POLE_DECA_REPL - 5W/20620 NEW IDRIA RDPA | 35215978 |  |  | STS-POLE_DECA_REPL - 5W/20620 NEW IDRIA | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.4267 | -120.6685 |  | TIER 2 | 1060 | 25367-1103, PANOCHE | N34 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101693462 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-11 | 2020-06-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 253671103 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | Paicines | Hollister |  |  | OPEN | 117688984 | POLE _ BROK _ REPL_16/S/O 12500 PANOCHE | 35202339 |  |  | STS-POLE _ BROK _ REPL_16/S/O 12500 PANO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land Enviro JointPole |  |  | 36.6302 | -121.1223 |  | TIER 2 |  |  | I23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101689835 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2020-10-27 | 2020-10-27 | 2021 CBP Plan | 2021-01-31 | CALENG |  |  | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | Paicines | Hollister |  |  | OPEN | 117688985 | POLE _ BROK _ REPL_27/S/O 12500 PANOCHE | 35216290 |  |  | STS-POLE _ BROK _ REPL_27/S/O 12500 PANO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 36.6124 | -121.1174 |  | TIER 2 |  |  | I23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101772672 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | Paicines | Hollister |  |  | OPEN | 117688986 | POLE_DECA_REPL - 14/P/NW/O/8130 PANOCHE | 35216294 |  |  | STS-POLE_DECA_REPL - 14/P/NW/O/8130 PANO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.6722 | -121.1969 |  | TIER 2 |  |  | H21 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101689888 | RELW PRI OH ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 1 | 879.3 | 868.7 | 868.7 | 868.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | Paicines | Hollister |  |  | OPEN | 118199787 | POLE_DECA_REPL - 21/S/O 12500 PANOCHE RD | 35215785 |  |  | STS-POLE_DECA_REPL - 21/S/O 12500 PANOCH | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 36.6219 | -121.1214 |  | TIER 2 | 1060 | 25367-1103, PANOCHE | I23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101689840 | RELW OH PRI JPOL ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-11-22 | 2020-11-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 253671103 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117319271 | POLE_BROK_REPL - MONTEBENITO RCH LIMEKIL | 35203005 |  |  | STS-POLE_BROK_REPL - MONTEBENITO RCH LIM | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6648 | -121.3832 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | H160 |  | Y | 311 |  |  | 2021-03-12 07:00 | 2021-03-12 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 27.8 | 27.8 |  |  | 0 | 27.8 | 27.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101711369 | RELW OH PRI ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-29 | 2020-12-29 | COMP | 2020-12-29 | [16 empty] | 2019-05-24 | 2020-05-24 | 2020-10-20 | 2020-10-20 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182492105 | 9706.83 | 938.9 | 930.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 115033385 | POLE_DECA_REPL - 21200 Hwy 25 Paicines C | 35140381 |  |  | STS-POLE_DECA_REPL - 21200 HWY 25 PAICIN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6223 | -121.2248 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | I20 | 39363 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101768310 | OH RELW PRI INSP CLR REMT FIRE SCOP SCPA FMOB TER2 FSRP | Pole | 2020-03-31 | 2020-03-31 | COMP | 2020-03-31 | [16 empty] | 2018-10-08 | 2019-10-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 182492105 | 18180.97 | 1218 | 1173.7 |  |  | 44.3 |  | 44.3 | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 115067265 | POLE_BROK_REPL - 5550 WILLOW CREEK RD PA | 35089037 |  |  | STS-POLE_BROK_REPL - 5550 WILLOW CREEK R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.5723 | -121.1306 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | J22 | 51083 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101773701 | RELW OH PRI INSP REMT FIRE JAR BTKA SCOP SCPA FMOB FSRP TER2 | Pole | 2020-12-18 | 2020-12-18 | COMP | 2020-12-18 | [16 empty] | 2018-10-17 | 2019-10-17 |  | 2019-10-17 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 182492105 | 7672.03 | 1010.4 | 970.1 | 353 | 353 |  |  |  | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117138572 | POLE_DECA_REPL - ATT TOWET MONTEBENITO R | 35202432 |  |  | STS-POLE_DECA_REPL - ATT TOWET MONTEBENI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6623 | -121.4007 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | H15 | 4709 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.6 | 25.6 |  |  | 0 | 25.6 | 25.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101711419 | RELW OH PRI PATR FIRE NOAC ESTR BTKA FMOB TER2 FSRP | Pole | 2021-01-20 | 2021-01-20 | COMP | 2021-01-20 | [16 empty] | 2019-05-01 | 2020-05-01 | 2020-10-20 | 2020-10-20 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 182492105 | 8810.61 | 8.8 | 0 | 851 | 851 |  |  |  | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117138573 | POLE_DECA_REPL - ATT TOWER MONTEBENITO R | 35202437 |  |  | STS-POLE_DECA_REPL - ATT TOWER MONTEBENI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6637 | -121.3925 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | H160 | 4709 | Y | 311 |  |  | 2021-04-15 07:00 | 2021-04-15 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101711376 | RELW OH PRI PATR FIRE NOAC ESTR BTKA FMOB TER2 FSRP | Pole | 2021-01-12 | 2021-01-12 | COMP | 2021-01-12 | [16 empty] | 2019-05-01 | 2020-05-01 | 2020-10-20 | 2020-10-20 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182492105 | 6171.2 | 8.8 | 0 | 529.8 | 529.8 |  |  |  | Electric Distribution | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117228140 | POLE_DECA_REPL - 7PN/O 31000 HWY 25 PAIC | 35214882 |  |  | STS-POLE_DECA_REPL - 7PN/O 31000 HWY 25 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.5275 | -121.1407 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | K22 | 4519 | Y | 311 |  |  | 2021-06-15 07:00 | 2021-06-15 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101690120 | RELW OH PRI REMT FIRE CGI SWRK ESTR GO FSRP FMOB TER2 PRTO | Pole | 2021-02-10 | 2021-02-10 | COMP | 2021-02-09 |  |  | 2021-02-10 | 2021-02-10 | [12 empty] | 2019-05-13 | 2020-05-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182492105 | 11758.75 | 69.5 | 60.6 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117228151 | POLE_DECA_REPL - 9PN/O 31000 HWY 25 PAIC | 35214888 |  |  | STS-POLE_DECA_REPL - 9PN/O 31000 HWY 25 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.5289 | -121.1425 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | K22 | 4519 | Y | 311 |  |  | 2021-06-15 07:00 | 2021-06-15 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101690118 | RELW OH PRI REMT FIRE CGI SWRK ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-10 | 2021-02-10 | COMP | 2021-02-09 | [16 empty] | 2019-05-13 | 2020-05-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182492105 | 11099.41 | 17.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117250278 | POLE_DECA_REPL - F/O 2010 HWY 146PAICINE | 35202869 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 36.4931 | -121.1487 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | L22 | 4257 | Y | 311 |  |  | 2021-06-15 07:00 | 2021-06-15 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101769984 | RELW OH PRI CLR RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-09 | 2021-02-04 | COMP | 2020-12-08 |  |  | 2020-12-03 | 2020-12-03 | [12 empty] | 2019-05-16 | 2020-05-16 | 2020-10-17 | 2020-10-17 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182492105 | 15218.98 | 2335.7 | 693.2 | -3.1 | -3.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117250284 | POLE_DECA_REPL - 1PS/O 2010 HWY 146PAICI | 35202871 |  |  | STS-POLE_DECA_REPL - 1PS/O 2010 HWY 146P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.4912 | -121.1496 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | L22 | 4257 | Y | 311 |  |  | 2021-06-15 07:00 | 2021-06-15 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101690144 | RELW OH PRI CLR RESD NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-12-02 | 2021-02-04 | COMP | 2020-12-02 | [16 empty] | 2019-05-16 | 2020-05-16 | 2020-10-17 | 2020-10-17 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182492105 | 26931.31 | 5032.8 | 4436 | 4101.7 | 4101.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117268792 | CRSS_DECA_REPL - 6/P/NW/O/9331 PANOCHE R | 35215270 |  |  | STS-CRSS_DECA_REPL - 6/P/NW/O/9331 PANOC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6648 | -121.1745 |  | TIER 2 | 1060 | 25367-1103, PANOCHE | H21 |  | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Crossarm | Decayed/Rotten | Replace |  | 101689777 | RELW JPOL OH PRI CLR REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-25 | 2021-01-25 | COMP | 2021-01-25 | [16 empty] | 2019-05-18 | 2020-05-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 253671103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117284705 | POLE_DECA_REPL - 21200 HWY 25 PAICINES | 35215473 |  |  | STS-POLE_DECA_REPL - 21200 HWY 25 PAICIN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 36.6215 | -121.2235 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | I20 |  | Y | 311 |  |  | 2021-06-15 07:00 | 2021-06-15 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101701432 | RELW OH PRI REMT FIRE SWRK ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-20 | 2020-05-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182492105 | 1 | 57.3 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117316475 | POLE_BROK_REPL - ATT TOWER MONTEBENITO R | 35202985 |  |  | STS-POLE_BROK_REPL - ATT TOWER MONTEBENI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6618 | -121.396 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | H160 |  | Y | 311 |  |  | 2021-06-15 07:00 | 2021-06-15 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101711380 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-25 | 2021-01-25 | COMP | 2021-01-25 | [16 empty] | 2019-05-24 | 2020-05-24 | 2020-10-20 | 2020-10-20 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182492105 | 10804.06 | 452.7 | 435 | 435 | 435 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117316517 | POLE_BROK_REPL - ATT TOWER MONTEBENITO R | 35202988 |  |  | STS-POLE_BROK_REPL - ATT TOWER MONTEBENI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6639 | -121.3934 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | H160 |  | Y | 311 |  |  | 2021-04-15 07:00 | 2021-04-15 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101772947 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-06 | 2021-01-06 | COMP | 2021-01-06 | [16 empty] | 2019-05-24 | 2020-05-24 | 2020-09-20 | 2020-09-20 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 182492105 | 7503.25 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117316518 | POLE_BROK_REPL - ATT TOWER MONTEBENITO R | 35202991 |  |  | STS-POLE_BROK_REPL - ATT TOWER MONTEBENI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6613 | -121.3968 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | H160 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101772949 | RELW OH TER2 PRI ESTR FMOB PRTO FSRP | Pole | 2020-12-28 | 2020-12-28 | COMP | 2020-12-28 | [16 empty] | 2019-05-24 | 2020-05-24 | 2020-08-20 | 2020-08-20 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182492105 | 11379.41 | 2158.6 | 1770.1 | 543 | 543 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | PAICINES | Hollister |  |  | OPEN | 117417876 | POLE_DECA_REPL - 1/N/O 5550 WILLOW CRK R | 35215919 |  |  | STS-POLE_DECA_REPL - 1/N/O 5550 WILLOW C | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.5676 | -121.1276 |  | TIER 2 | 220 | 18249-2105, HOLLISTER | J22 |  | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101773700 | PRI OH RELW REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-26 | 2021-01-26 | COMP | 2021-01-26 | [16 empty] | 2019-06-07 | 2020-06-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182492105 | 14456.75 | 111.2 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116682214 | POLE_BROK_REPL - R\O 12 CORRAL DE TIERRA | 35214594 |  |  | STS-POLE_BROK_REPL - R\O 12 CORRAL DE TI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 36.5771 | -121.7279 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | J0703 | 3645 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101785108 | RELW OH SEC JPOL REMT NOAC ESTR GO REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-07 | 2020-03-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 1 | 81.6 | 81.5 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116682542 | POLE_BROK_REPL - 1W/O R/O 53 CORRAL DE T | 35214600 |  |  | STS-POLE_BROK_REPL - 1W/O R/O 53 CORRAL | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 36.5764 | -121.7265 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | J0703 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101746802 | RELW OH PRI CLR JPOL REMT NOAC ESTR GO REAR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-07 | 2020-03-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 1 | 209.9 | 209.8 | 140.2 | 140.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116682709 | POLE_BROK_REPL - R\O 53 CORRAL DE TIERRA | 35214606 |  |  | STS-POLE_BROK_REPL - R\O 53 CORRAL DE TI | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 36.576 | -121.7264 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | J0703 | 3645 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101746807 | RELW OH PRI JPOL REMT NOAC ESTR GO REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-07 | 2020-03-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 1 | 64.4 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116683103 | POLE_BROK_REPL - 53 CORRAL DE TIERRA RD | 35214615 |  |  |  | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.5754 | -121.7268 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | J0703 | 3645 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 55.6 | 54.6 | 1 |  | 0 | 55.6 | 54.6 | 1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101746806 | RELW OH PRI JPOL RESD NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2019-03-07 | 2020-03-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 23288.47 | 35.1 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116683993 | POLE_BURN_REPL - 1W/O 751 HWY 68 SALINAS | 35214619 |  |  | STS-POLE_BURN_REPL - 1W/O 751 HWY 68 SAL | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 36.5755 | -121.7332 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | J0703 | 5835 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 101746786 | RELW OH PRI JPOL RESD ESTR GO BTKA FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-03-07 | 2020-03-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 1 | 342.8 | 325.2 | 307.8 | 307.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116705160 | POLE_BROK_REPL - N/S DRIVE 40 SECA PL. S | 35214642 |  |  | STS-POLE_BROK_REPL - N/S DRIVE 40 SECA P | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.5663 | -121.7522 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | J0610 | 23145 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.9 | 13.9 |  |  | 0 | 13.9 | 13.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101746716 | RELW OH PRI JPOL REMT NOAC ESTR GO REAR FSRP PRTO FMOB TER2 | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2019-03-10 | 2020-03-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 11921.01 | 111.2 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116705221 | POLE_BROK_REPL - ON HILL E/S HOUSE 36 SE | 35214647 |  |  | STS-POLE_BROK_REPL - ON HILL E/S HOUSE 3 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 36.5658 | -121.7521 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | J0610 | 23145 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101746717 | RELW OH PRI JPOL REMT NOAC ESTR GO REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-10 | 2020-03-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116720593 | POLE_DECA_REPL - CORRAL DE TIERRA RD AT | 35202098 |  |  | STS-POLE_DECA_REPL - CORRAL DE TIERRA RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.5386 | -121.6692 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0901 | 4193 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 14.7 | 14.7 |  |  | 0 | 14.7 | 14.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101754173 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-11-20 | 2020-11-19 | COMP | 2020-11-19 | [16 empty] | 2019-03-13 | 2020-03-13 | 2020-11-11 | 2020-11-11 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182222104 | 7042.66 | 53.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116720636 | CRSS_DECA_REPL - A/F 386 CORRAL DE TIERR | 35214714 |  |  | STS-CRSS_DECA_REPL - A/F 386 CORRAL DE T | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 36.5305 | -121.7072 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0806 | 4191 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Crossarm | Decayed/Rotten | Replace |  | 101754237 | RELW OH PRI JPOL TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-13 | 2020-03-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 1 | 17.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116720752 | CRSS_BROK_REPL - CORRAL DE TIERRA RD MB | 35214718 |  |  | STS-CRSS_BROK_REPL - CORRAL DE TIERRA RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 36.5384 | -121.67 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0901 | 4193 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Crossarm | Broken/Damaged | Replace |  | 101754174 | RELW OH PRI JPOL REMT ESTR GO BTKA FSRP PRTO FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-03-13 | 2020-03-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116725107 | POLE_BROK_REPL - 1W/O 545 CORRAL DE TIER | 35202125 |  |  | STS-POLE_BROK_REPL - 1W/O 545 CORRAL DE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 36.5263 | -121.6785 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0809 | 4193 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.6 | 24.6 |  |  | 0 | 24.6 | 24.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101775641 | RELW OH PRI JPOL REMT TRAF FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2020-11-10 |  | COMP | 2020-11-10 | [16 empty] | 2019-03-13 | 2020-03-13 | 2020-10-10 | 2020-10-10 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182222104 | 14784.19 | 235.1 | 0 | -226.3 | -226.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116735545 | POLE_BROK_REPL - R/O 389 CORRAL DE TIERR | 35214767 |  |  | STS-POLE_BROK_REPL - R/O 389 CORRAL DE T | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.5317 | -121.7082 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0801 | 4191 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 16.4 | 16.4 |  |  | 0 | 16.4 | 16.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101754279 | RELW OH PRI JPOL RESD NOAC ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-29 |  | COMP | 2021-01-29 | [16 empty] | 2019-03-14 | 2020-03-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 5754.7 | 17.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116736361 | POLE_BROK_REPL - 1E/O 395 CORRAL DE TIER | 35214779 |  |  | STS-POLE_BROK_REPL - 1E/O 395 CORRAL DE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 36.5297 | -121.7016 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0806 | 4191 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101754229 | RELW OH PRI CLR JPOL PUBL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-14 | 2020-03-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 1 | 148.5 | 130.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116740136 | POLE_DECA_REPL - A/F 392 CORRAL DE TIERR | 35202136 |  |  | STS-POLE_DECA_REPL - A/F 392 CORRAL DE T | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Enviro JointPole |  |  | 36.5289 | -121.7002 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0807 | 4191 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101754217 | RELW OH PRI JPOL TRAF FLAG GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-15 | 2020-03-15 | 2020-10-10 | 2020-10-10 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 182222104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116743408 | CRSS_DECA_REPL - 398 CORRAL DE TIERRA RD | 35214842 |  |  | STS-CRSS_DECA_REPL - 398 CORRAL DE TIERR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 36.5269 | -121.6984 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0807 | 4191 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Crossarm | Decayed/Rotten | Replace |  | 101754215 | RELW OH PRI JPOL RESD TRAF FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-15 | 2020-03-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116745799 | POLE_BROK_REPL - 1W/O 486 CORRAL DE TIER | 35214853 |  |  | STS-POLE_BROK_REPL - 1W/O 486 CORRAL DE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 36.5243 | -121.6887 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0808 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.8 | 13.8 |  |  | 0 | 13.8 | 13.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101775637 | RELW OH PRI JPOL ESTR RESD TRAF FLAG BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-26 |  | COMP | 2021-01-26 | [16 empty] | 2019-03-15 | 2020-03-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 9533.94 | 17.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116750776 | POLE_DECA_REPL - A/F 2S/O 27441 VISTA DE | 35214896 |  |  | STS-POLE_DECA_REPL - A/F 2S/O 27441 VIST | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 36.5232 | -121.6999 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0807 | 5845 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101775629 | RELW OH PRI JPOL RESD TRAF ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 1 | 305.2 | 287.5 | 217.2 | 217.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116751458 | POLE_DECA_REPL - 27445 VISTA DEL TOROSAL | 35202128 |  |  | STS-POLE_DECA_REPL - 27445 VISTA DEL TOR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 36.5217 | -121.7007 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0812 | 4969 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 66.8 | 64.9 | 1.9 |  | 0 | 66.8 | 64.9 | 1.9 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101754161 | RELW OH PRI JPOL RESD TRAF FLAG ESTR BTKA FMOB FSRP TER2 PRTO | Pole | 2020-12-07 |  | COMP | 2020-12-07 | [16 empty] | 2019-03-17 | 2020-03-17 | 2020-10-11 | 2020-10-11 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182222104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116751743 | POLE_BROK_REPL - 27395 VISTA DEL TOROSAL | 35214931 |  |  | STS-POLE_BROK_REPL - 27395 VISTA DEL TOR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 36.5271 | -121.6997 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0807 | 5845 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101754148 | RELW OH PRI JPOL RESD FLAG ESTR BTKA FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 1 | 452 | 434.3 | 434.3 | 434.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116752726 | POLE_BROK_REPL - 388B CORRAL DE TIERRA R | 35202132 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.5244 | -121.7058 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0806 | 5845 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 63.6 | 62.3 | 1.3 |  | 0 | 63.6 | 62.3 | 1.3 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101754284 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-16 | 2021-02-16 | COMP | 2021-02-16 | [16 empty] | 2019-03-17 | 2020-03-17 | 2020-10-09 | 2020-10-09 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182222104 | 24218.87 | 181 | -90.5 | -140.3 | -140.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116755634 | POLE_BROK_REPL - 28900 UNDERWOOD RD SALI | 35202140 |  |  | STS-POLE_BROK_REPL - 28900 UNDERWOOD RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 36.5141 | -121.6894 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K08 | 25297 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 66.3 | 65.2 | 1.1 |  | 0 | 66.3 | 65.2 | 1.1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101776604 | RELW OH PRI CLR JPOL REMT ESTR OTHR USA TER2 FSRP | Pole | 2021-01-11 |  | COMP | 2021-01-11 | [16 empty] | 2019-03-05 | 2020-03-05 | 2020-10-11 | 2020-10-11 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182222104 | 32643.25 | 49.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116788732 | POLE_DECA_REPL - 3S/O 28005 MESA DE TIER | 35215151 |  |  | STS-POLE_DECA_REPL - 3S/O 28005 MESA DE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.5162 | -121.6901 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0813 | 4155 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101776603 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 1 | 226 | 217.2 | 217.2 | 217.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116807754 | POLE_DECA_REPL - R/O 397A CORRAL DEL TIE | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 36.5322 | -121.7028 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0801 | 4191 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101754238 | REGW OH PRI JPOL RESD NOAC ESTR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-03-21 | 2020-03-21 | 2020-10-09 | 2020-10-09 | 2021 CBP Plan |  | UNASSIGNED |  | 182222104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 117052317 | CONN_INCR_REPL - 4E/O 24020 LIMEKILN RD | 35215260 |  |  | STS-CONN_INCR_REPL - 4E/O 24020 LIMEKILN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.5138 | -121.5412 |  | TIER 2 | 585 | 18273-1102, RESERVATION ROAD | K12 | 5567 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Connector | Incorrectly Installed | Replace |  | 101769464 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-17 | 2020-04-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182731102 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | Salinas | Salinas |  |  | OPEN | 117689216 | POLE _ BROK _ REPL_1/P/N/O REAR OF 29095 | 35216298 |  |  | STS-POLE _ BROK _ REPL_1/P/N/O REAR OF 2 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.5929 | -121.4567 |  | TIER 2 |  |  | I1423 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101741954 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  |  | 1 | 10.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | Salinas | Salinas |  |  | OPEN | 117689550 | POLE_BROK_REPL - 2S/O R/O 66 CORRAL DE T | 35202344 |  |  | STS-POLE_BROK_REPL - 2S/O R/O 66 CORRAL | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 36.5714 | -121.7328 |  | TIER 2 |  |  | J0708 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 24.8 | 24.8 |  |  | 0 | 24.8 | 24.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101781476 | OH PRI TRAF FLAG ESTR BTKA USA TER2 PRTO FSRP RELW | Pole | 2020-11-24 |  | COMP | 2020-11-24 | [16 empty] | 2019-07-31 | 2020-07-31 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-01-31 | CALENG | [11 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116751919 | +POLE_BROK_REPL- R/O 430 VISTA DEL TORO | 35178566 |  |  | X STS-POLE_BROK_REPL - R/O 430 VISTA DEL | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.5215 | -121.699 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0812 | 4113 | Y | 311 |  |  | 2021-03-01 07:00 | 2021-03-01 16:00 | Dispatched | CLICK | [6 empty] | 32.1 | 32.1 |  |  | 6.75 | 32 | 32 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101754162 | RELW OH PRI JPOL NOAC ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2020-06-16 | 2020-06-22 | COMP | 2020-06-16 | [16 empty] | 2019-03-17 | 2020-03-17 | 2020-08-11 | 2020-08-11 | Work Plan Reconcilation (B-Tags) |  | Fresno |  | 182222104 | 14933.72 | 15906.8 | -1545 | 23211.2 | 23211.2 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Previous Reason Code Submitted - No Action | Y | 2020-07-21
South | CC | SALINAS | Salinas |  |  | OPEN | 116685799 | POLE_BROK_REPL - 1\P\E 789 HWY 68 SALINA | 35214628 |  |  | STS-POLE_BROK_REPL - 1\P\E 789 HWY 68 SA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.5753 | -121.7335 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | J0703 |  | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101746785 | RELW OH SEC RESD ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2021-01-25 | 2021-01-25 | COMP | 2021-01-25 | [16 empty] | 2019-03-08 | 2020-03-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 182222104 | 5971.89 | 586.4 | 568.7 | 568.7 | 568.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116704847 | POLE_DECA_REPL - 1/P/N/O 109 LAGUNA PL. | 35089768 |  |  | STS-POLE_DECA_REPL - 1/P/N/O 109 LAGUNA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.5677 | -121.7507 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | J0610 | 5753 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101746732 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2019-11-05 | 2019-11-21 | COMP | 2019-11-05 |  |  | 2019-10-29 | 2019-10-29 | [12 empty] | 2019-03-10 | 2020-03-10 | 2020-11-16 | 2020-11-16 | 2021 CBP Plan | 2019-11-11 | CALENG |  | 182222104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SALINAS | Salinas |  |  | OPEN | 116749499 | POLE_DECA_REPL - R/O27400 VISTA DEL TORO | 35202126 |  |  | STS-POLE_DECA_REPL - R/O27400 VISTA DEL | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.5264 | -121.7028 |  | TIER 2 | 964 | 18222-2104, DEL MONTE | K0806 | 5845 | Y | 311 |  |  | 2021-03-01 07:00 | 2021-03-01 16:00 | Dispatched | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 15.25 | 35.55 | 35.55 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101754270 | RELW OH PRI JPOL RESD NOAC ESTR GO BTKA CCNT FMOB TER2 PRTO FSRP | Pole | 2020-10-19 | 2020-12-11 | COMP | 2020-10-19 | [16 empty] | 2019-03-16 | 2020-03-16 | 2020-10-09 | 2020-10-09 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 182222104 | 23608.8 | 2579.8 | 2562.1 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SAN JUAN BAUTISTA | Hollister |  |  | OPEN | 117206627 | POLE_DECA_REPL - 5000 SAN JUAN CYN RD 2S | 35214607 |  |  | STS-POLE_DECA_REPL - 5000 SAN JUAN CYN R | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land Enviro JointPole |  |  | 36.7969 | -121.4735 |  | TIER 2 | 321 | 18318-1101, SAN JUSTO | E14 | 833507 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101771927 | RELW OH PRI JPOL RESD REMT FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 183181101 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SAN JUAN BAUTISTA | Hollister |  |  | OPEN | 117218060 | POLE_BROK_REPL - 4P/S/OF C/O CHITTENDEN | 35214765 |  |  | STS-POLE_BROK_REPL - 4P/S/OF C/O CHITTEN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.8983 | -121.5904 |  | TIER 2 | 321 | 18318-1101, SAN JUSTO | C1102 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101790591 | RELW OH PRI ESTR RTRN FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-12 | 2020-05-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 183181101 | 1 | 19.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SAN JUAN BAUTISTA | Hollister |  |  | OPEN | 117280678 | POLE_DECA_REPL - A/F 5335 SAN JUAN CYN R | 35215427 |  |  | STS-POLE_DECA_REPL - A/F 5335 SAN JUAN C | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7856 | -121.4723 |  | TIER 2 | 321 | 18318-1101, SAN JUSTO | E14 | 4091 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101747109 | RELW OH PRI CLR REMT CGI ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-20 | 2020-05-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 183181101 | 1 | 87.3 | 69.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SAN JUAN BAUTISTA | Hollister |  |  | OPEN | 117239484 | POLE_BROK_REPL - 1281 HWY 129 SAN JUAN B | [6 empty] | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Needs Order, Estimated | Permit FAA |  |  | 36.893 | -121.5766 |  | TIER 2 | 321 | 18318-1101, SAN JUSTO | C1104 | 4099 | Y | 311 | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101792156 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | 2011-08-01 |  | 2010-11-23 | 2018-06-29 | 2018-07-23 | [12 empty] | 2019-05-15 | 2020-05-15 | 2020-10-30 | 2020-10-30 | B-Tag Clean Up 5/14/20 |  | UNASSIGNED |  | 183181101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-05-25
South | CC | SAN JUAN BAUTISTA | Hollister |  |  | OPEN | 117208923 | POLE_DECA_REPL - 3\P\S\O 4401 SAN JAUN C | 35214641 |  |  | STS-POLE_DECA_REPL - 3\P\S\O 4401 SAN JA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.7983 | -121.4886 |  | TIER 2 | 321 | 18318-1101, SAN JUSTO | E13 |  | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101772569 | RELW OH PRI PGEA RESD REMT ESTR GO TER2 BTKA PROG FMOB PRTO FSRP | Pole | 2021-02-01 | 2021-02-01 | COMP | 2021-02-01 | [16 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 183181101 | 5618.46 | 530.8 | 522 | 522 | 522 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | SOQUEL | Santa Cruz |  |  | COMP | 117214458 | +POLE_DECA_REPL- 1PE/O/MB/3411 CUNNISON | 35102728 |  |  | STS-POLE_DECA_REPL - 1PE/O/MB/3411 CUNNI | DOCC | DOCC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 36.9925 | -121.9418 |  | TIER 2 | 526 | 08325-2106, PAUL SWEET | O1606 |  | Y | 311 |  |  | 2021-02-09 07:00 | 2021-02-09 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 31.1 | 31.1 |  |  | 0 | 31 | 31 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101795324 | RELW COMP JPOL OH PRI INSP RESD ESTR BTKA CCNT FMOB TER2 FSRP | Pole | 2020-05-12 | 2020-07-23 | COMP | 2020-05-12 | COMP | 2021-02-09 | 2020-04-08 | 2020-04-08 | [11 empty] | 2021-02-11 | 2021-02-09 | 2019-10-11 | 2024-05-09 | 2024-05-09 | Program Manager | 2020-05-20 | PIKEENG |  | 083252106 | 11821.98 | 9872.9 | 6700.8 | 28365.1 | 28365.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
South | CC | WATSONVILLE | Santa Cruz |  |  | OPEN | 117185886 | POLE_DECA_REPL - 504 DUSTY TRAIL WATSONV | 35202545 |  |  | STS-POLE_DECA_REPL - 504 DUSTY TRAIL WAT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.9586 | -121.8219 |  | TIER 2 | 232 | 08369-2104, ROB ROY | P1901 | 1955 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 38.2 | 38.2 |  |  | 0 | 38.2 | 38.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101796979 | RELW OH PRI JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-23 | 2021-02-18 | COMP | 2020-12-23 |  |  | 2020-12-01 | 2020-12-01 | [12 empty] | 2019-05-08 | 2020-05-08 | 2020-09-03 | 2020-09-03 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 083692104 | 20129.03 | 1621.6 | 1482.9 | 471.7 | 471.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | WATSONVILLE | Santa Cruz |  |  | OPEN | 117208591 | POLE_DECA_REPL - A/F 547 CALABASAS RD 'H | 35158883 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.9531 | -121.8116 |  | TIER 2 | 232 | 08369-2104, ROB ROY | P1902 | 3869 | Y | 311 |  |  | 2021-07-01 07:00 | 2021-07-01 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101694478 | OH RELW PRI INSP ESTR CPGI FMOB TER2 FSRP | Pole | 2020-04-06 | 2021-01-25 | COMP | 2020-04-06 |  |  | 2021-01-25 | 2021-01-25 | [12 empty] | 2019-05-10 | 2019-05-17 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan |  | Fresno |  | 083692104 | 16403.54 | 100 | 55.7 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | WATSONVILLE | Watsonville |  |  | CNCL | 120027000 | POLE_BROK_REPL - BACK OF PROPERTY 490 HA | 35214058 |  |  | *CANC* STS-POLE_BROK_REPL - BACK OF*CANC | CLSD | CLSD CANC HOLD | Poles | MPP |  | 07D | New A&B Tags | New EC B Tags | 1.4 |  |  | 1 | 2020-12-03 | 2021 | 2021 |  |  | Y |  |  | 2021 | Closed | Out of PEND |  | No Action | 36.9929 | -121.8227 |  | TIER 2 | 232 | 08369-2104, ROB ROY | O1906 | 6861 | Y | 311 |  |  |  |  | Cancelled | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 101801590 | RELW OH SEC CNCL ESTR CPGD TER2 | Pole |  |  | REQD | 2021-01-07 | [15 empty] | 2020-12-06 | 2020-12-03 | 2021-02-13 |  | 2021-02-13 | B tag clean up 11/19/2020 |  | UNASSIGNED |  | 083692104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-11-19
South | CC | WATSONVILLE | Watsonville |  |  | OPEN | 117298874 | POLE_DECA_REPL - B\O HOUSE 345 RACE HORS | 35202950 |  |  | STS-POLE_DECA_REPL - B\O HOUSE 345 RACE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.9682 | -121.8603 |  | TIER 2 | 232 | 08369-2104, ROB ROY | O1821 | 3887 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 58.8 | 58.8 |  |  | 0 | 58.8 | 58.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101693733 | RELW OH PRI JPOL REMT ESTR GO BTKA USA PROG FMOB TER2 PRTO FSRP | Pole | 2021-02-03 |  | COMP | 2021-02-03 | [16 empty] | 2019-05-22 | 2020-05-22 | 2020-09-23 | 2020-09-23 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 083692104 | 25712.55 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | Watsonville | Watsonville |  |  | OPEN | 118264781 | POLE_DECA_REPL - 115 APPLE LNWatsonville | 35202703 |  |  | STS-POLE_DECA_REPL - 115 APPLE LNWATSONV | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 36.9893 | -121.859 |  | TIER 2 | 232 | 08369-2104, ROB ROY | O1806 | 1031 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 72.8 | 72.8 |  |  | 0 | 72.8 | 72.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101691296 | RELW PRI OH INSP CLR JPOL ESTR BTKA FMOB TER2 FSRP | Pole | 2021-01-04 |  | COMP | 2021-01-04 | [16 empty] | 2019-12-12 | 2020-12-12 | 2020-10-20 | 2020-10-20 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 083692104 | 33267.9 | 216 | 36.9 | 398.9 | 398.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | CC | WATSONVILLE | Watsonville |  |  | COMP | 117294085 | POLE_DECA_REPL - 1\S OF A\F M\B 40 NUNES | 35154232 |  |  | STS-POLE_DECA_REPL - 1\S OF A\F M\B 40 N | MAPP | MAPP SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 36.9695 | -121.8451 |  | TIER 2 | 232 | 08369-2104, ROB ROY | O1823 | 9569 | Y | 311 |  |  | 2021-02-04 | 2021-02-04 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 53.5 | 53.5 |  |  | 60 | 3.5 | 3.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101693433 | RELW OH PRI COMP JPOL RESD FLAG GO BTKA PROG CPGG FMOB FSRP PRTO TER2 | Pole | 2020-10-27 | 2020-10-28 | COMP | 2020-05-18 | COMP | 2021-02-04 | 2020-10-26 | 2020-10-26 | [11 empty] | 2021-02-10 | 2021-02-04 | 2020-05-21 | 2024-05-19 | 2024-05-19 | 2021 CBP Plan | 2020-05-01 | QUES |  | 083692104 | 30397.43 | 6402.7 | 6175.7 | 37.4 | 37.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | DA |  | Cupertino |  |  | OPEN | 115597232 | R/O 14760 ALOHA AV | 35069420 |  |  | R/O 14760 ALOHA AV | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-11-27 | Renew Permit | 37.2536 | -122.0319 |  | TIER 2 |  |  | I1310 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 54.2 | 54.2 |  |  | 0 | 54.2 | 54.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100514015 | REGW OH TER2 | Pole | 2019-11-08 | 2019-12-02 | COMP | 2019-09-19 |  |  | 2019-11-26 | 2019-12-02 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-19 | EEI |  |  | 36221.17 | 7262.1 | -26971.7 | -26971.7 | -26971.7 | 21102.7 |  | 21102.7 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
South | DA | CUPERTINO | Cupertino |  |  | OPEN | 116829614 | POLE_BROK_REPL - 11825 SKYLINE BL/1PSCUP | 35202492 |  |  | STS-POLE_BROK_REPL - 11825 SKYLINE BL/1P | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land |  |  | 37.2775 | -122.1494 |  | TIER 2 | 228 | 02413-1103, MENLO | H10 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.7 | 14.7 |  |  | 0 | 14.7 | 14.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100265529 | RELW OH PRI CLR JPOL FIRE FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-17 |  | COMP | 2020-12-17 | [16 empty] | 2019-03-25 | 2020-03-25 | 2020-12-31 | 2020-12-31 | 2021 CBP Plan | 2021-01-31 | EEI |  | 024131103 | 15164.89 | 1053.9 | -959.2 | 713.8 | 713.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | DA | LOS GATOS | Cupertino |  |  | OPEN | 116973871 | POLE_DECA_REPL - 80 OAK GROVELOS GATOS95 | 35125778 |  |  | STS-POLE_DECA_REPL - 80 OAK GROVELOS GAT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2166 | -121.9868 |  | TIER 2 | 30 | 08202-1107, LOS GATOS | J1410 |  | Y | 311 |  |  |  |  | Started | Order Operation | [6 empty] | 25.7 | 24.6 | 1.1 |  | 0 | 25.7 | 24.6 | 1.1 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100539960 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO | Pole | 2020-07-09 | 2020-08-31 | COMP | 2020-02-05 |  |  | 2020-06-28 | 2020-07-08 | [12 empty] | 2019-04-07 | 2020-04-07 |  | 2020-04-07 | 2021 CBP Plan |  | UNASSIGNED |  | 082021107 | 11276.51 | 1763.2 | 1279.7 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | DA | Los Gatos | Cupertino |  |  | OPEN | 119792865 | POLE_DECA_REPL - H-17 5 N\O ALMA BRIDGEL | 35203999 |  |  | STS-POLE_DECA_REPL - H-17 5 N\O ALMA BRI | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2001 | -121.9923 |  | TIER 2 | 143 | 08202-1106, LOS GATOS | J1420 | 2981 | Y | 311 |  |  | 2021-03-14 07:00 | 2021-03-14 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 53.1 | 43.1 |  | 10 | 1.5 | 53 | 43 |  | 10 | EC | B | Pole | Decayed/Rotten | Replace |  | 100539856 | RELW OH PRI INSP ESTR FMOB TER2 | Pole | 2020-12-11 | 2020-12-18 | COMP | 2020-11-08 |  |  | 2020-12-09 | 2020-12-09 | [12 empty] | 2020-09-21 | 2020-12-21 |  | 2020-12-21 | B tag clean up 9/26/2020 |  | San Jose |  | 082021106 | 37325.76 | 22813.3 | 21684.4 | 18124.7 | 18124.7 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Previous Reason Code Submitted - No Action | Y | 2020-09-26
South | DA | LOS GATOS | Cupertino |  |  | COMP | 116755953 | POLE_BROK_REPL - 138 WOOD RD/1PN/1PE/2PS | 35203937 |  |  | STS-POLE_BROK_REPL - 138 WOOD RD/1PN/1PE | FICL | FICL SRDY CRDY REDL | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-10-09 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.2206 | -121.9882 |  | TIER 2 | 1110 | 08202-1108, LOS GATOS | J1405 |  | Y | 311 |  |  | 2021-01-05 | 2021-01-05 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 52.7 | 52.7 |  | 0 | 218.75 | 1.7 | 1.7 |  | 0 | EC | B | Pole | Broken/Damaged | Replace |  | 100540029 | OH RELW PRI COMP CLR ESTR GO CPGG FMOB TER2 PRTO | Pole | 2020-10-27 | 2020-11-18 | COMP | 2020-10-27 | COMP | 2021-01-05 | 2020-11-02 | 2020-11-16 | [11 empty] | 2021-01-08 | 2021-01-05 | 2020-03-18 | 2020-11-06 | 2020-11-06 | B tag clean up 9/26/2020 |  | San Jose |  | 082021108 | 15972.58 | 60980.9 | 19183.9 | 19183.9 | 19183.9 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N |  | Y | 2020-09-26
South | DA | LOS GATOS | Cupertino |  |  | OPEN | 116974045 | POLE_DECA_REPL - 20 OAK GROVELOS GATOS95 | 35125779 |  |  | STS-POLE_DECA_REPL - 20 OAK GROVELOS GAT | PEND | PEND | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 37.2175 | -121.9865 |  | TIER 2 | 30 | 08202-1107, LOS GATOS | J1410 | 4403 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.7 | 36.6 | 1.1 |  | 0 | 37.7 | 36.6 | 1.1 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100539963 | RELW OH PRI FMOB RESD FLAG ESTR BTKA TER2 PRTO | Pole | 2021-01-14 | 2020-11-12 | COMP | 2020-02-13 |  |  | 2020-11-12 | 2020-11-12 | [12 empty] | 2019-04-07 | 2020-04-07 |  | 2020-04-07 | 2021 CBP Plan |  | UNASSIGNED |  | 082021107 | 22703.35 | 447.4 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
South | DA | LOS GATOS | Cupertino |  |  | OPEN | 117011249 | POLE_DECA_REPL - F/O 11 EUCLID AV LOS GA | 35125801 |  |  | STS-POLE_DECA_REPL - F/O 11 EUCLID AV LO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-05-21 | Renew Permit | 37.2176 | -121.985 |  | TIER 2 | 30 | 08202-1107, LOS GATOS | J1506 | 4403 | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100525307 | RELW OH PRI INSP JPOL TRAF FLAG ESTR BTKA FMOB TER2 | Pole | 2019-10-12 | 2020-03-02 | COMP | 2019-10-12 |  |  | 2019-11-04 | 2019-11-22 | [12 empty] | 2019-04-11 | 2020-04-11 |  | 2020-04-11 | Q1 Work Plan |  | UNASSIGNED |  | 082021107 | 11010.08 | 1583.4 |  |  |  | 98.4 |  | 98.4 |  | Y | MPP File Only | N |  | Y | 2020-02-18
South | DA | SARATOGA | Cupertino |  |  | OPEN | 116705797 | POLE_DECA_REPL - 22000 MT. EDEN RD. /1/P | 35089776 |  |  | STS-POLE_DECA_REPL - 22000 MT. EDEN RD. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2675 | -122.0745 |  | TIER 2 | 1066 | 08337-1105, SARATOGA | I12 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.6 | 20.6 |  |  | 0 | 20.6 | 20.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100526710 | RELW OH PRI INSP CLR JPOL RESD REMT FIRE NOAC SPCR ESTR GO FMOB TER2 FSRP | Pole | 2020-03-10 | 2020-03-13 | COMP | 2020-01-24 | [16 empty] | 2019-03-10 | 2020-03-10 | 2020-10-03 | 2020-10-03 | 2021 CBP Plan | 2020-01-31 | PIKEENG |  | 083371105 | 11126.54 | 516.2 |  |  |  | 88.7 |  | 88.7 |  | N | MPP File Only | N |  | Y | 2020-08-25
South | DA | SARATOGA | Cupertino |  |  | OPEN | 117261231 | POLE_DECA_REPL - #2 W/O 21250 BLUE HILLS | 35180034 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 1 | 2021-05-03 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.2911 | -122.0473 |  | TIER 2 | 924 | 08337-1115, SARATOGA | H1313 | 845 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 68.6 | 68.6 |  |  | 0 | 68.6 | 68.6 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100532513 | RELW OH PRI ESTR GO FMOB TER2 PRTO FSRP | Pole | 2021-02-19 | 2021-02-19 | COMP | 2020-06-25 |  |  | 2020-10-30 | 2020-11-03 | [12 empty] | 2019-05-17 | 2020-05-17 | 2021-05-31 | 2021-05-31 | B-Tag Addition 06.24.20 |  | San Jose |  | 083371115 | 40110.93 | 3340.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-06-29
South | FR |  | Auberry |  |  | OPEN | 115597382 | POLE_DECA_REPL - R/O 35885 LODGE RD 1/NE | 35070355 |  |  | R/O 35885 LODGE RD 1/NE PVTP | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0123 | -119.4251 |  | TIER 2 |  |  | 0000010235 | R2578 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 51 | 51 |  |  | 0.5 | 50.5 | 50.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100675660 | REGW OH TER2 | Pole | 2019-04-11 | 2019-04-11 | COMP | 2019-04-11 | [16 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-02 | EEI |  |  | 27376.74 | 19438 | 1707.5 | 19.1 | 19.1 |  |  |  | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR |  | Fresno |  |  | OPEN | 115597373 | POLE_DECA_REPL - N/W COR/O FRAZIER RD & | 35069178 |  |  | MB 32442 FRAISER RD 2/W ROAD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND | 2020-09-04 | Renew Permit | 37.0678 | -119.4953 |  | TIER 2 |  |  | 10232C | 687 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 51 | 51 |  |  | 1.5 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100679887 | REGW OH TER2 | Pole | 2019-04-26 | 2019-09-16 | COMP | 2019-04-26 |  |  | 2020-07-08 | 2020-07-08 | [12 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-02 | EEI |  |  | 34302.64 | 13388.7 | 68 | 68 | 68 | 23.8 |  | 23.8 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | AUBERRY | Auberry |  |  | OPEN | 117388312 | POLE_BROK_REPL - SIERRA NATIONAL FORESTA | 35173512 |  |  | STS-POLE_BROK_REPL - SIERRA NATIONAL FOR | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1273 | -119.5241 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009224 | D9445 | Y | 311 |  |  | 2021-03-17 07:00 | 2021-03-17 16:00 | Scheduled | CLICK | [6 empty] | 42.3 | 42.3 |  |  | 1.5 | 41.3 | 41.3 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 103271930 | RELW OH PRI CLR REMT SPCR ESTR WATR FMOB TER2 PRTO FSRP | Pole | 2020-06-01 | 2020-07-17 | COMP | 2020-06-01 | [16 empty] | 2019-06-04 | 2020-06-04 | 2020-07-15 | 2020-07-15 | B-Tag Clean Up 5/14/20 |  | Fresno |  | 252561101 | 31313.79 | 5670.1 | [7 empty] | N | 11/2 in MPP Import File | N | Internal Timeliness - Consturction - Need to coordinate with dam repair | Y | 2020-05-25
South | FR | Auberry | Auberry |  |  | OPEN | 119621986 | POLE_DECA_REPL - Sierra National ForestA | 35193406 |  |  | STS-POLE_DECA_REPL - SIERRA NATIONAL FOR | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1213 | -119.4596 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000009236 | D4495 | Y | 311 |  |  | 2021-03-30 07:00 | 2021-03-31 16:00 | Dispatched | CLICK | [6 empty] | 50 | 50 |  |  | 43 | 7 | 7 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 103267352 | RELW OH PRI INSP CLR REMT SPCR ESTR GO BTKA USA FMOB TER2 | Pole | 2020-11-16 | 2020-11-16 | COMP | 2020-11-16 | [16 empty] | 2020-08-15 | 2020-11-15 |  | 2020-11-15 | B-Tag Clean Up 8/25/20 |  | Fresno |  | 254151101 | 15882.23 | 34377.7 | -1372.7 | -1372.7 | -1372.7 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Not Accessible | Y | 2020-08-27
South | FR | Auberry | Auberry |  |  | OPEN | 119622011 | POLE_DECA_REPL - Sierra National ForestA | 35193407 |  |  | STS-POLE_DECA_REPL - SIERRA NATIONAL FOR | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1221 | -119.4596 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000009236 | D4495 | Y | 311 |  |  | 2021-03-30 07:00 | 2021-03-31 16:00 | Dispatched | CLICK | [6 empty] | 50 | 50 |  |  | 40 | 10 | 10 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 103267355 | RELW OH PRI INSP CLR REMT ESTR BTKA USA FMOB TER2 | Pole | 2020-11-23 | 2020-11-23 | COMP | 2020-11-23 | [16 empty] | 2020-08-15 | 2020-11-15 |  | 2020-11-15 | B-Tag Clean Up 8/25/20 |  | Fresno |  | 254151101 | 10594.07 | 41244.3 | -1419.7 | -1419.7 | -1419.7 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Not Accessible | Y | 2020-08-27
South | FR | Auberry | Auberry |  |  | OPEN | 119622043 | POLE_DECA_REPL - 38993 JOSE BASIN RD 7PS | 35193408 |  |  | STS-POLE_DECA_REPL - 38993 JOSE BASIN RD | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.1223 | -119.4584 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000009235 |  | Y | 311 |  |  | 2021-03-30 07:00 | 2021-03-31 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.9 | 50.9 |  |  | 0 | 50.9 | 50.9 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100677459 | RELW OH PRI INSP REMT ESTR BTKA USA FMOB TER2 | Pole | 2020-11-23 | 2020-11-25 | REQD | 2020-11-21 | [16 empty] | 2020-08-15 | 2020-11-15 |  | 2020-11-15 | B-Tag Clean Up 8/25/20 |  | UNASSIGNED |  | 254151101 | 6423.42 | 13923.7 | -1158.7 | -1158.7 | -1158.7 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Not Accessible | Y | 2020-08-27
South | FR | AUBERRY | Fresno |  |  | OPEN | 117008891 | POLE_DECA_REPL - AT HOUSE 30914 SPEARHEA | 35154376 |  |  | STS-POLE_DECA_REPL - AT HOUSE 30914 SPEA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.0586 | -119.5243 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 10224A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.4 | 15.4 |  |  | 0 | 15.4 | 15.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100680068 | RELW OH PRI CLR SWRK ESTR FMOB TER2 PRTO FSRP | Pole | 2020-08-12 |  | COMP | 2020-08-12 | [16 empty] | 2019-04-11 | 2020-04-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254151102 | 7192.95 |  | -1385 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | AUBERRY | Fresno |  |  | OPEN | 117033900 | POLE_DECA_REPL - R/O WC/O 35136 POWERHOU | 35105451 |  |  | STS-POLE_DECA_REPL - R/O WC/O 35136 POWE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 37.1083 | -119.5026 |  | TIER 2 | 767 | 25256-1101, KERCKHOFF | 0000009236 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.5 | 25.5 |  |  | 0 | 25.5 | 25.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100681977 | RELW OH PRI CLR RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-09-10 |  | COMP | 2020-09-10 | [16 empty] | 2019-04-15 | 2019-10-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 252561101 | 15052.79 | 550.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | AUBERRY | Fresno |  |  | OPEN | 117098024 | POLE_DECA_REPL - N/W C/O FRASIER RD/SPRE | 35154086 |  |  | STS-POLE_DECA_REPL - N/W C/O FRASIER RD/ | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.068 | -119.506 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 10232C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.2 | 25.2 |  |  | 0 | 25.2 | 25.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100679850 | RELW OH PRI CLR RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-07-08 |  | COMP | 2020-07-08 |  |  | 2021-02-05 | 2021-02-08 | [12 empty] | 2019-04-25 | 2020-04-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | TRC |  | 254151102 | 10690.59 | 1220.4 | 87.5 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | AUBERRY | Fresno |  |  | OPEN | 117121806 | POLE_BROK_REPL - R/O 33960 FRAZIER RD 1P | 35154230 |  |  | STS-POLE_BROK_REPL - R/O 33960 FRAZIER R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.0695 | -119.5271 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 0000010221 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100681898 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254151102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | AUBERRY | Fresno |  |  | COMP | 117032944 | POLE_DECA_REPL - 35776 AUNT JULIES LN 1W | 35154634 |  |  | STS-POLE_DECA_REPL - 35776 AUNT JULIES L | FICL | FICL ERDY SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.0578 | -119.4717 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 10233A |  | Y | 311 |  |  | 2021-01-08 | 2021-01-08 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 52.7 | 52.7 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100677156 | RELW OH PRI COMP ESTR CCNT FMOB TER2 PRTO | Pole | 2020-04-20 | 2020-04-20 | COMP | 2020-04-20 | COMP | 2021-01-08 | [13 empty] | 2021-01-13 | 2021-01-08 | 2020-04-15 |  | 2020-04-15 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 9049.51 | 23120.3 | 23120.3 | 33963.1 | 33963.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | AUBERRY | Fresno |  |  | COMP | 117034255 | POLE_BROK_REPL - 38668 AUBERRY RD 6/NWAU | 35154650 |  |  | STS-POLE_BROK_REPL - 38668 AUBERRY RD 6/ | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2021-02-19 | No Action | 37.0783 | -119.4489 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 10231C |  | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 51.8 | 51.8 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100680970 | OH RELW PRI COMP ESTR BTKA RTRN USA CCNT FMOB TER2 PRTO | Pole | 2020-04-27 | 2020-07-09 | COMP | 2020-04-27 | COMP | 2021-01-13 | 2020-06-25 | 2020-06-29 | [11 empty] | 2021-01-19 | 2021-01-13 | 2020-04-15 |  | 2020-04-15 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 9754.26 | 14492.3 | 11722.3 | 17692.5 | 17692.5 | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | AUBERRY | Fresno |  |  | COMP | 117054061 | POLE_BROK_REPL - S/W CO RINGTAIL LN & RA | 35154691 |  |  | STS-POLE_BROK_REPL - S/W CO RINGTAIL LN | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.0774 | -119.4337 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 10231C | D13007 | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 51.8 | 51.8 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100680841 | RELW OH PRI ESTR FMOB TER2 PRTO CCNT COMP | Pole | 2020-05-15 | 2020-08-04 | COMP | 2020-05-07 | COMP | 2021-01-13 | [13 empty] | 2021-01-19 | 2021-01-13 | 2020-04-18 |  | 2020-04-18 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 11050.3 | 13254.1 | 13165.4 | 21508.9 | 21508.9 | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | AUBERRY | Fresno |  |  | COMP | 117068935 | POLE_BROK_REPL - 41990 RADIO LN 2P S/E 2 | 35154746 |  |  |  | MAPP | MAPP SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.0728 | -119.4319 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 10231C | D4502 | Y | 311 |  |  | 2021-01-14 | 2021-01-14 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 3.7 | 3.7 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100680863 | OH RELW PRI COMP ESTR CCNT FMOB TER2 PRTO | Pole | 2020-05-01 | 2020-05-01 | COMP | 2020-04-30 | COMP | 2021-01-14 | [13 empty] | 2021-01-19 | 2021-01-14 | 2020-04-20 |  | 2020-04-20 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 13625.38 | 12637.3 | 12548.7 | 21045.8 | 21045.8 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | AUBERRY | Fresno |  |  | OPEN | 117015386 | POLE_DECA_REPL - 33740 MEDFORD RD W/ TRA | 35154399 |  |  | STS-POLE_DECA_REPL - 33740 MEDFORD RD W/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0662 | -119.5184 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 10224A | D8092 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 53.5 | 53.5 |  |  | 0 | 53.5 | 53.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100680117 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole | 2020-08-24 | 2020-08-24 | COMP | 2020-08-24 | [16 empty] | 2019-04-12 | 2020-04-12 | 2024-04-10 | 2024-04-10 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254151102 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | AUBERRY | Fresno |  |  | OPEN | 117072044 | POLE_BROK_REPL - 42719 PINECONE LNAUBERR | 35154774 |  |  | STS-POLE_BROK_REPL - 42719 PINECONE LNAU | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0857 | -119.4149 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 10231A | D955 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100681654 | OH PRI ESTR FMOB TER2 PRTO RELW | Pole | 2020-05-12 | 2020-06-16 | COMP | 2020-05-12 |  |  | 2020-06-16 | 2020-06-16 | [12 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 16486.21 | 1307.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | AUBERRY | Fresno |  |  | OPEN | 117072243 | POLE_BROK_REPL - 41835 CORLEW DRAUBERRY9 | 35154778 |  |  | STS-POLE_BROK_REPL - 41835 CORLEW DRAUBE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.077 | -119.4303 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0001023114 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.8 | 23.8 |  |  | 0 | 23.8 | 23.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100677587 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-06-25 | 2020-06-25 | COMP | 2020-06-24 |  |  | 2020-03-17 | 2020-03-17 | [12 empty] | 2019-04-21 | 2020-04-21 |  | 2020-04-21 | 2021 CBP Plan | 2020-12-31 | TRC |  | 254151101 | 14503.44 | 2654.5 | 1299.8 | 1299.8 | 1299.8 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | AUBERRY | Fresno |  |  | OPEN | 117092065 | POLE_BROK_REPL - N/W CO CHIPMUNK LN & PO | 35154074 |  |  | STS-POLE_BROK_REPL - N/W CO CHIPMUNK LN | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.0799 | -119.4296 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0001023111 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100675446 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole |  |  | REQD |  |  |  | 2020-03-17 | 2020-03-17 | [12 empty] | 2019-04-24 | 2020-04-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254151101 | 1 | 88.7 | -1141.3 | -49.3 | -49.3 | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | AUBERRY | Fresno |  |  | OPEN | 117114939 | POLE_DECA_REPL - 33756 FRASIER 2N/O AUBE | 35154162 |  |  | STS-POLE_DECA_REPL - 33756 FRASIER 2N/O | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.071 | -119.5179 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 0000010221 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.5 | 17.5 |  |  | 0 | 17.5 | 17.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100681915 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-06-25 |  | COMP | 2020-06-25 | [16 empty] | 2019-04-28 | 2020-04-28 | 2024-04-26 | 2024-04-26 | 2021 CBP Plan | 2020-12-31 | TRC |  | 254151102 | 7828.02 | 1417 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | AUBERRY | Fresno |  |  | OPEN | 117115455 | POLE_BROK_REPL - R/O 33620 FRASIER /1PNA | 35154170 |  |  | STS-POLE_BROK_REPL - R/O 33620 FRASIER / | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.069 | -119.5167 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 0000010221 | 477572 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.4 | 32.4 |  |  | 0 | 32.4 | 32.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100681911 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-07-02 | 2020-11-12 | COMP | 2020-07-02 | [16 empty] | 2019-04-28 | 2020-04-28 | 2024-04-26 | 2024-04-26 | 2021 CBP Plan | 2020-12-31 | TRC |  | 254151102 | 15472.09 | 1130 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | AUBERRY | Fresno |  |  | OPEN | 117125579 | POLE_DECA_REPL - R/O 33316 S.J.AND E.RD | 35097506 |  |  | STS-POLE_DECA_REPL - R/O 33316 S.J.AND E | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0721 | -119.4845 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0001023085 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 12.6 | 12.6 |  |  | 0 | 12.6 | 12.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100679687 | RELW OH PRI CLR RESD REMT NOAC ESTR USA FMOB TER2 PRTO | Pole | 2020-09-10 | 2020-09-10 | COMP | 2020-09-10 | [16 empty] | 2019-04-30 | 2019-10-30 |  | 2019-10-30 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 254151101 | 7236.02 | 353.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Dinuba |  |  | COMP | 117106077 | POLE_DECA_REPL - A/F 49595 HWY245 3N/1E/ | 35178985 |  |  | OCLH PLE_DECA_RPL-A/F 49595 HWY245 3N | FICL | FICL SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-08 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 36.6418 | -119.0128 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015271 | 3748F | Y | 311 |  |  | 2021-01-14 | 2021-01-14 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 61.3 | 37.3 | 24 |  | 42.5 | 24 |  | 24 |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100690297 | PRI OH RELW INSP COMP JPOL REMT FIRE ESTR GO BTKA PROG CPGD FMOB FSRP TER2 | Pole | 2020-10-14 | 2020-10-14 | COMP | 2020-10-14 | COMP | 2021-01-13 | [13 empty] | 2021-01-14 | 2021-01-13 | 2020-04-26 | 2020-08-05 | 2020-08-05 | B-Tag Addition 06.24.20 |  | Fresno |  | 254601103 | 23928.08 | 21702.1 | 11379.5 | 11379.5 | 11379.5 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N |  | Y | 2020-06-29
South | FR | BADGER | Dinuba |  |  | OPEN | 116843672 | POLE_DECA_REPL - CEMETERY 6N OSBORNE BAD | 35214880 |  |  | STS-POLE_DECA_REPL - CEMETERY 6N OSBORNE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.6252 | -118.9647 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015283 | 7955F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 26.1 | 26.1 |  |  | 0 | 26.1 | 26.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100684259 | RELW OH PRI INSP JPOL REMT NOAC ESTR FMOB TER2 FSRP | Pole | 2021-01-28 |  | COMP | 2021-01-28 | [16 empty] | 2019-03-26 | 2020-03-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254601103 | 9388.35 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Dinuba |  |  | OPEN | 116843674 | POLE_BROK_REPL - CEMETERY 9N OSBORNE BAD | 35202514 |  |  | STS-POLE_BROK_REPL - CEMETERY 9N OSBORNE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6276 | -118.9655 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015283 | 7955F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.6 | 19.6 |  |  | 0 | 19.6 | 19.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100684273 | RELW OH PRI INSP JPOL REMT NOAC ESTR FMOB TER2 FSRP | Pole | 2020-12-15 | 2021-01-26 | COMP | 2020-12-15 | [16 empty] | 2019-03-26 | 2020-03-26 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254601103 | 11101.51 |  | -633.6 | -135.8 | -135.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Dinuba |  |  | OPEN | 116843689 | POLE_DECA_REPL - CEMETERY 2N OSBORNE BAD | 35202516 |  |  | STS-POLE_DECA_REPL - CEMETERY 2N OSBORNE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6223 | -118.9639 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015283 | 7955F | Y | 311 |  |  | 2021-05-04 07:00 | 2021-05-04 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100684142 | RELW PRI OH INSP JPOL REMT ESTR FMOB TER2 FSRP | Pole | 2020-11-30 | 2021-01-19 | COMP | 2020-11-30 | [16 empty] | 2019-03-26 | 2020-03-26 | 2020-10-01 | 2020-10-01 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254601103 | 6395.04 |  | -497.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Dinuba |  |  | OPEN | 116852535 | POLE_DECA_REPL - C/O CEMETERY DR / OSBOR | 35214985 |  |  | STS-POLE_DECA_REPL - C/O CEMETERY DR / O | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.6148 | -118.9653 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015283 | 7993F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.9 | 16.9 |  |  | 0 | 16.9 | 16.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100684094 | RELW OH PRI INSP CLR JPOL REMT NOAC ESTR GO FMOB TER2 FSRP | Pole | 2021-01-28 |  | COMP | 2021-01-28 | [16 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254601103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Dinuba |  |  | OPEN | 116852746 | POLE_DECA_REPL - C/O CEMETERY DR / OSBOR | 35202526 |  |  | STS-POLE_DECA_REPL - C/O CEMETERY DR / O | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6164 | -118.9618 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015283 | 7993F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.4 | 15.4 |  |  | 0 | 15.4 | 15.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100684118 | RELW OH PRI INSP JPOL REMT NOAC ESTR FMOB TER2 FSRP | Pole | 2020-12-11 | 2021-01-29 | COMP | 2020-12-11 | [16 empty] | 2019-03-27 | 2020-03-27 | 2020-09-01 | 2020-09-01 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254601103 | 6520.85 | 75.9 | -1267 | -769.2 | -769.2 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Dinuba |  |  | OPEN | 116864966 | POLE_BROK_REPL - R/O 54520 ESHOM VALLEY | 35083073 |  |  | STS-POLE_BROK_REPL - R/O 54520 ESHOM VA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6045 | -118.9432 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015283 | 7339F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22 | 22 |  |  | 0 | 22 | 22 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100684399 | RELW OH PRI INSP REMT NOAC ESTR GO FMOB TER2 FSRP | Pole | 2020-12-07 | 2020-12-07 | COMP | 2020-12-07 | [16 empty] | 2019-03-28 | 2020-03-28 | 2020-11-01 | 2020-11-01 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254601103 | 9146.52 |  | -1230.8 | -687.8 | -687.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Dinuba |  |  | OPEN | 116869488 | POLE_DECA_REPL - END OF CEMETERY DRIVEBA | 35202562 |  |  | STS-POLE_DECA_REPL - END OF CEMETERY DRI | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.6315 | -118.9668 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015282 | 7955F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.1 | 15.1 |  |  | 0 | 15.1 | 15.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100684278 | RELW OH PRI INSP JPOL REMT NOAC SWRK ESTR FMOB TER2 FSRP | Pole | 2021-01-21 |  | COMP | 2021-01-21 | [16 empty] | 2019-03-29 | 2020-03-29 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254601103 | 5987.33 |  | 0 | 785.2 | 785.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Dinuba |  |  | OPEN | 117124042 | POLE_DECA_REPL - 50775 RD469 SPACE 21 1 | 35202358 |  |  | STS-POLE_DECA_REPL - 50775 RD469 SPACE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.638 | -118.9962 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015271 | 3746F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100690233 | RELW OH PRI INSP JPOL REMT FIRE ESTR GO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2020-09-06 | 2020-09-06 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254601103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Fresno |  |  | OPEN | 117145010 | POLE_BROK_REPL - 50970[ENTR]ESHOM VALLEY | 35097563 |  |  | STS-POLE_BROK_REPL - 50970[ENTR]ESHOM VA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 36.6312 | -118.9946 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015271 | 7110 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.9 | 25.9 |  |  | 0 | 25.9 | 25.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100683661 | RELW OH PRI INSP JPOL ESTR GO BTKA USA FMOB TER2 FSRP | Pole | 2021-02-02 |  | COMP | 2021-02-02 | [16 empty] | 2019-05-02 | 2020-05-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254601103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Fresno |  |  | OPEN | 117190068 | POLE_BROK_REPL - 46565 DRY CREEK RD 1/P/ | 35202553 |  |  | STS-POLE_BROK_REPL - 46565 DRY CREEK RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 36.5939 | -119.0142 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015275 | 3206F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 54.4 | 54.2 | 0.2 |  | 0 | 54.4 | 54.2 | 0.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 100683066 | OH PRI INSP RESD FLAG ESTR GO BTKA USA FMOB TER2 FSRP RELW | Pole | 2021-01-22 |  | COMP | 2021-01-22 | [16 empty] | 2019-05-08 | 2020-05-08 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254601103 | 24834.35 | 13.5 | 0 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Fresno |  |  | OPEN | 117192181 | POLE_DECA_REPL - 46216[ENTR]DRY CREEK RD | 35215543 |  |  | STS-POLE_DECA_REPL - 46216[ENTR]DRY CREE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.5915 | -119.0146 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015275 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100683085 | RELW OH PRI INSP REMT ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-09 | 2020-05-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254601103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Fresno |  |  | OPEN | 117192552 | POLE_DECA_REPL - 46216[ENTR]DRY CREEK RD | 35215548 |  |  | STS-POLE_DECA_REPL - 46216[ENTR]DRY CREE | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 36.5877 | -119.0127 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015275 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100683097 | RELW OH PRI INSP CLR RESD ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-09 | 2020-05-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254601103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Fresno |  |  | OPEN | 117192657 | POLE_DECA_REPL - 46216[ENTR]DRY CREEK RD | 35215559 |  |  | STS-POLE_DECA_REPL - 46216[ENTR]DRY CREE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.5877 | -119.0125 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015275 | 3206F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100683099 | RELW OH PRI INSP CLR RESD ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-09 | 2020-05-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254601103 | 1 | 154.1 | 140.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Fresno |  |  | OPEN | 117192724 | POLE_DECA_REPL - 46216[ENTR]DRY CREEK RD | 35215564 |  |  | STS-POLE_DECA_REPL - 46216[ENTR]DRY CREE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 36.5886 | -119.0133 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015275 | 3206F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100683092 | RELW OH PRI INSP REMT FLAG ESTR BTKA USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-09 | 2020-05-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254601103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Fresno |  |  | OPEN | 117370659 | POLE_BROK_REPL - DRY CREEK RD 1EBADGER93 | 35203097 |  |  | STS-POLE_BROK_REPL - DRY CREEK RD 1EBADG | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.5916 | -119.0114 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015275 | 3206F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100683143 | RELW OH PRI CLR RESD REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-01 | 2020-06-01 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254601103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | BADGER | Fresno |  |  | OPEN | 117370723 | POLE_BROK_REPL - DRY CREEK RDBADGER93603 | 35215855 |  |  | STS-POLE_BROK_REPL - DRY CREEK RDBADGER9 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.5916 | -119.012 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015275 | 3206F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100683140 | RELW OH PRI CLR RESD REMT ESTR GO REAR PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-01 | 2020-06-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254601103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | CLOVIS | Auberry |  |  | OPEN | 116928054 | POLE_BROK_REPL - 26597 STONEY HILL RD/1P | 35162210 |  |  | BUNDLE-STS-2POLES_REPL-26597 STONEY HILL | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.9338 | -119.4594 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000011236 | D1876 | Y | 311 |  |  | 2021-03-26 07:00 | 2021-03-26 16:00 | Dispatched | CLICK | [6 empty] | 100 | 100 |  |  | 0 | 100 | 100 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100679405 | RELW OH PRI CLR GO SCOP SCPA FMOB TER2 PRTO | Pole | 2020-03-20 | 2020-05-22 | COMP | 2020-03-20 | [16 empty] | 2019-04-02 | 2020-04-02 |  | 2020-04-02 | Per email from [REDACTED] 5/6 |  | Fresno |  | 254151101 | 34377.35 | 11125.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-05-10
South | FR | CLOVIS | Fresno |  |  | OPEN | 116879469 | POLE_BROK_REPL - 18155 TOLLHOUSE RD/2PNC | 35215579 |  |  | STS-POLE_BROK_REPL - 18155 TOLLHOUSE RD/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.9398 | -119.5043 |  | TIER 2 | 250 | 25241-1104, COPPERMINE | 0000011236 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100675688 | RELW OH PRI ESTR FSRP FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-01 | 2020-04-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252411104 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | CLOVIS | Fresno |  |  | OPEN | 117028179 | POLE_BROK_REPL - RO 27895 CANAL/ CLOVIS | 35215852 |  |  | STS-POLE_BROK_REPL - RO 27895 CANAL/ CLO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.0431 | -119.5515 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 10224C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100680364 | OH PRI MINR JAR FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-04-14 | 2020-04-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254151102 | 1 | 30.9 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | CLOVIS | Fresno |  |  | OPEN | 117021061 | POLE_DECA_REPL - 29702 AUBERRY RD 4P/W 1 | 35154472 |  |  | STS-POLE_DECA_REPL - 29702 AUBERRY RD 4P | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0383 | -119.5131 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 10225A | D334 | Y | 311 |  |  | 2021-03-26 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 52.5 | 52.5 |  |  | 0 | 52.5 | 52.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100678601 | RELW PRI OH COMM ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2020-07-01 | 2020-07-02 | COMP | 2020-05-11 |  |  | 2020-06-16 | 2020-06-16 | [12 empty] | 2019-04-13 | 2020-04-13 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151102 | 39148.78 | 5947.3 | -202.5 | -202.5 | -202.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | CLOVIS | Fresno |  |  | OPEN | 117021956 | POLE_DECA_REPL - 28549 AUBERRY RD 1P/S C | 35154500 |  |  | STS-POLE_DECA_REPL - 28549 AUBERRY RD 1P | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0315 | -119.5285 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 10225A |  | Y | 311 |  |  | 2021-04-21 07:00 | 2021-04-21 16:00 | Reserved | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100678687 | RELW OH PRI RESD REMT TRAF ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-08-31 | 2021-01-20 | COMP | 2020-08-31 |  |  | 2021-01-20 | 2021-01-20 | [12 empty] | 2019-04-13 | 2020-04-13 | 2024-04-11 | 2024-04-11 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254151102 | 12420.69 | 252.9 |  |  |  | 71.9 |  | 71.9 |  | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | CLOVIS | Fresno |  |  | OPEN | 117023178 | POLE_DECA_REPL - 29334 SPEARHEAD RD IN H | 35154507 |  |  | STS-POLE_DECA_REPL - 29334 SPEARHEAD RD | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0408 | -119.5177 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 10224D |  | Y | 311 |  |  | 2021-03-26 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100679934 | RELW PRI OH CLR NOAC SWRK ESTR FMOB TER2 PRTO FSRP | Pole | 2020-05-11 | 2020-05-11 | COMP | 2020-05-11 | [16 empty] | 2019-04-13 | 2020-04-13 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151102 | 8732.21 | 2907.4 | 1203.9 | 1203.9 | 1203.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | CLOVIS | Fresno |  |  | OPEN | 117027750 | POLE_DECA_REPL - 27773 CANAL/2PE 1PN 2PN | 35088577 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0449 | -119.5553 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 10224C |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100680345 | RELW OH SEC CLR REMT NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2021-01-11 | 2021-01-11 | COMP | 2021-01-11 | [16 empty] | 2019-04-14 | 2019-09-14 | 2020-10-18 | 2020-10-18 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254151102 | 11306.66 | 180.5 | 180.5 | 180.5 | 180.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | CLOVIS | Fresno |  |  | OPEN | 118557741 | POLE_BROK_REPL - 26597 STONEY HILL LN CL | 35162210 |  |  | BUNDLE-STS-2POLES_REPL-26597 STONEY HILL | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.9338 | -119.4597 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000011236 | D1876 | Y | 311 |  |  | 2021-03-26 07:00 | 2021-03-26 16:00 | Dispatched | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100679409 | POHW OH ESTR TER2 | Pole | 2020-03-20 | 2020-05-22 | COMP | 2020-03-20 | [16 empty] | 2020-01-02 | 2021-01-02 |  | 2021-01-02 | Per email from [REDACTED] 5/6 |  | Fresno |  | 254151101 | 34377.35 | 11125.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-05-10
South | FR | DINUBA | Dinuba |  |  | OPEN | 117684237 | POLE_DECA_REPL - R/O 15499 SANDY CREEK R | 35216214 |  |  | STS-POLE_DECA_REPL - R/O 15499 SANDY CRE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6281 | -119.2432 |  | TIER 2 | 1429 | 25234-1112, REEDLEY | 0000015254 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.1 | 15.1 |  |  | 0 | 15.1 | 15.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100659213 | RELW PRI OH ESTR TER2 PRTO FSRP | Pole | 2021-02-01 | 2021-02-08 | COMP | 2021-02-01 | [16 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252341112 | 8229.33 | 387.5 | 374 | 374 | 374 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | DUNLAP | Fresno |  |  | OPEN | 116717104 | TREE_DECA_INPL - 36503 KINGS CANYON HWY | 35214704 |  |  | STS-TREE_DECA_INPL - 36503 KINGS CANYON | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7567 | -119.1592 |  | TIER 2 | 504 | 25406-1103, DUNLAP | 0000013266 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100761595 | RELW OH SEC RESD REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-12 | 2020-03-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254061103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | DUNLAP | Fresno |  |  | OPEN | 116791281 | POLE_DECA_REPL - 45432 MILLWOOD RD 1W DU | 35215191 |  |  | STS-POLE_DECA_REPL - 45432 MILLWOOD RD 1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7351 | -119.0518 |  | TIER 2 | 504 | 25406-1103, DUNLAP | 0000014272 | 7166 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100775417 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254061103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | FESNO | Fresno |  |  | OPEN | 116735949 | POLE_DECA_REPL - HSE 36877 DUNLAP RDFESN | 35082685 |  |  | STS-POLE_DECA_REPL - HSE 36877 DUNLAP RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 36.7444 | -119.1591 |  | TIER 2 | 504 | 25406-1103, DUNLAP | 0000014262 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100691772 | RELW OH REMT PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-14 | 2020-03-14 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254061103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | FR | Fresno |  |  | OPEN | 117187065 | POLE_DECA_REPL - A/F 46585[STABLES]DRY C | 35215480 |  |  | STS-POLE_DECA_REPL - A/F 46585[STABLES]D | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.5963 | -119.0115 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015275 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.5 | 20.5 |  |  | 0 | 20.5 | 20.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100683057 | RELW OH PRI INSP CLR REMT ESTR BTKA FMOB TER2 FSRP | Pole | 2021-01-28 | 2021-01-28 | COMP | 2021-01-28 | [16 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254601103 | 7380.7 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | FR | Fresno |  |  | OPEN | 117187132 | POLE_DECA_REPL - A/F 46585[STABLES] 2E F | 35202547 |  |  | STS-POLE_DECA_REPL - A/F 46585[STABLES] | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.5963 | -119.0111 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015275 | 3206F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27 | 27 |  |  | 0 | 27 | 27 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100683054 | RELW OH PRI INSP CLR ESTR GO BTKA FMOB TER2 FSRP | Pole | 2020-12-15 | 2020-12-15 | COMP | 2020-12-15 | [16 empty] | 2019-05-08 | 2020-05-08 | 2020-10-30 | 2020-10-30 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254601103 | 10992.09 | 13.5 | -1013.6 | -561.1 | -561.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | FRESNO | Fresno |  |  | OPEN | 117042072 | POLE_DECA_REPL - MB 28162 AUBERRY RD/1PE | 35215158 |  |  | STS-POLE_DECA_REPL - MB 28162 AUBERRY RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 37.0169 | -119.5494 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 10225C |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100678993 | SEC RELW OH RESD REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-16 | 2020-04-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254151102 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | FRESNO | Fresno |  |  | COMP | 117153828 | POLE_DECA_REPL - 21516 AVE 380/2PEFRESNO | 35097570 |  |  | STS-POLE_DECA_REPL - 21516 AVE 380/2PEFR | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 36.479 | -119.095 |  | TIER 2 | 1355 | 25292-1110, STONE CORRAL | 0000017272 |  | Y | 311 |  |  | 2021-01-15 | 2021-01-15 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 51.1 | 51.1 |  |  | 0 | 51.1 | 51.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100703859 | RELW OH PRI INSP COMP ESTR FMOB TER2 FSRP CCNT | Pole | 2020-03-27 | 2020-06-23 | COMP | 2020-03-27 | COMP | 2021-01-15 | [13 empty] | 2021-01-21 | 2021-01-15 | 2020-05-03 | 2024-05-01 | 2024-05-01 | Program Manager | 2020-06-30 | Fresno |  | 252921110 | 5236.64 | 4125.5 | 4125.5 | 9871.8 | 9871.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
South | FR | FRESNO | Fresno |  |  | OPEN | 116713245 | POLE_DECA_REPL - 34601 HOEWELL RD-1NFRES | 35086561 |  |  | STS-POLE_DECA_REPL - 34601 HOEWELL RD-1N | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.7466 | -119.1669 |  | TIER 2 | 504 | 25406-1103, DUNLAP | 0000013266 | 7945D | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | [6 empty] | 50.1 | 50.1 |  |  | 2 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100761632 | RELW OH PRI JPOL REMT ESTR REAR PROG FMOB TER2 PRTO FSRP | Pole | 2020-03-26 | 2020-05-21 | COMP | 2020-03-26 | [16 empty] | 2019-03-12 | 2020-03-12 | 2024-03-10 | 2024-03-10 | Program Manager | 2020-07-31 | Fresno |  | 254061103 | 17447.48 | 16145.5 | 12743.9 | 31302.6 | 31302.6 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
South | FR | FRESNO | Fresno |  |  | COMP | 116742668 | POLE_DECA_REPL - R/O 37017 BLUE OAKFRES | 35181651 |  |  | OCLH STS-PLE_DECA_RPL - 37017 BLUE OAK | FICL | FICL SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-08-03 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 36.7393 | -119.1542 |  | TIER 2 | 504 | 25406-1103, DUNLAP | 0000014262 | 7943F | Y | 311 |  |  | 2021-01-07 | 2021-01-07 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 43 | 43 |  |  | 35.5 | 0.8 | 0.8 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100691723 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP COMP CPGD | Pole | 2020-07-23 | 2020-08-05 | COMP | 2020-07-22 | COMP | 2021-01-04 | [13 empty] | 2021-01-05 | 2021-01-04 | 2020-03-15 | 2020-08-31 | 2020-08-31 | B-Tag Addition 06.24.20 |  | Santa Rosa |  | 254061103 | 20854.71 | 11887.1 | 9335.7 | 9335.7 | 9335.7 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N |  | Y | 2020-06-29
South | FR | KINGS CANYON N. PARK | Dinuba |  |  | OPEN | 116846697 | POLE_BROK_REPL - 83928–83990 CA-180 KING | 35214890 |  |  | STS-POLE_BROK_REPL - 83928–83990 CA-180 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7386 | -118.9646 |  | TIER 2 | 504 | 25406-1103, DUNLAP | 0001428052 | 3774F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103271864 | RELW OH PRI JPOL RESD FIRE ESTR GO BTKA OTRG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254061103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | KINGS CANYON N. PARK | Dinuba |  |  | OPEN | 117820868 | TREE_DECA_INPL - 83865 SIERRA LANE, WILS | 35117226 |  |  | STS-TREE_DECA_INPL - C/O PALISADE WY/SIE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7315 | -118.9575 |  | TIER 2 | 561 | 25406-1102, DUNLAP | 0001428055 | 7714D | Y | 311 |  |  | 2021-04-14 07:45 | 2021-04-14 16:05 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 608 | 608 |  |  | 0 | 608 | 608 |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 103781988 | POHW OH PRI JPOL RESD FIRE ESTR GO BTKA PROG FMOB PRTO FSRP TER2 | Pole |  |  | REQD | [17 empty] | 2019-08-09 | 2019-12-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 254061102 | 1 | 1097.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | KINGS CANYON N. PARK | Dinuba |  |  | OPEN | 117820869 | TREE_DECA_INPL - C/O PALISADE WY/SIERRA | 35117226 |  |  | STS-TREE_DECA_INPL - C/O PALISADE WY/SIE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7316 | -118.9577 |  | TIER 2 | 561 | 25406-1102, DUNLAP | 0001428055 | 7714D | Y | 311 |  |  | 2021-04-14 07:45 | 2021-04-14 16:05 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100774931 | POHW OH PRI JPOL RESD FIRE ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-08-09 | 2019-12-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 254061102 | 1 | 1097.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | KINGS CANYON N. PARK | Dinuba |  |  | OPEN | 117820926 | TREE_DECA_INPL - C/O PALISADE WY/SIERRA | 35117226 |  |  | STS-TREE_DECA_INPL - C/O PALISADE WY/SIE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7316 | -118.9584 |  | TIER 2 | 561 | 25406-1102, DUNLAP | 0001428055 | 7714D | Y | 311 |  |  | 2021-04-14 07:45 | 2021-04-14 16:05 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100774934 | POHW OH PRI JPOL RESD FIRE ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-08-09 | 2019-12-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 254061102 | 1 | 1097.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | KINGS CANYON N. PARK | Dinuba |  |  | OPEN | 117821013 | TREE_DECA_INPL - C/O PALISADE WY/SIERRA | 35117226 |  |  | STS-TREE_DECA_INPL - C/O PALISADE WY/SIE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7314 | -118.9587 |  | TIER 2 | 561 | 25406-1102, DUNLAP | 0001428055 | 7714D | Y | 311 |  |  | 2021-04-14 07:45 | 2021-04-14 16:05 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100774935 | POHW OH PRI JPOL RESD FIRE ESTR GO BTKA PROG FMOB PRTO TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-08-09 | 2019-12-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 254061102 | 1 | 1097.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | KINGS CANYON N. PARK | Dinuba |  |  | OPEN | 117821017 | TREE_DECA_INPL - C/O PALISADE WY/SIERRA | 35117226 |  |  | STS-TREE_DECA_INPL - C/O PALISADE WY/SIE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7314 | -118.9589 |  | TIER 2 | 561 | 25406-1102, DUNLAP | 0001428056 | 7714D | Y | 311 |  |  | 2021-04-14 07:45 | 2021-04-14 16:05 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100774936 | POHW OH PRI JPOL RESD FIRE ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-08-09 | 2019-12-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 254061102 | 1 | 1097.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | KINGS CANYON N. PARK | Dinuba |  |  | OPEN | 117821019 | TREE_DECA_INPL - C/O PALISADE WY/SIERRA | 35117226 |  |  | STS-TREE_DECA_INPL - C/O PALISADE WY/SIE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7313 | -118.9592 |  | TIER 2 | 561 | 25406-1102, DUNLAP | 0001428056 | 7714D | Y | 311 |  |  | 2021-04-14 07:45 | 2021-04-14 16:05 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100774937 | POHW OH PRI JPOL RESD FIRE ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-08-09 | 2019-12-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 254061102 | 1 | 1097.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | KINGS CANYON N. PARK | Dinuba |  |  | OPEN | 117821232 | TREE_DECA_INPL - C/O PALISADE WY/SIERRA | 35117226 |  |  | STS-TREE_DECA_INPL - C/O PALISADE WY/SIE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7318 | -118.9585 |  | TIER 2 | 561 | 25406-1102, DUNLAP | 0001428055 | 7714D | Y | 311 |  |  | 2021-04-14 07:45 | 2021-04-14 16:05 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100774929 | POHW OH PRI JPOL RESD FIRE ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-08-09 | 2019-12-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 254061102 | 1 | 1097.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | KINGS CANYON N. PARK | Dinuba |  |  | OPEN | 117821235 | TREE_DECA_INPL - C/O PALISADE WY/SIERRA | 35117226 |  |  | STS-TREE_DECA_INPL - C/O PALISADE WY/SIE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7317 | -118.9583 |  | TIER 2 | 561 | 25406-1102, DUNLAP | 0001428055 | 7714D | Y | 311 |  |  | 2021-04-14 07:45 | 2021-04-14 16:05 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100774930 | POHW RESD OH PRI JPOL FIRE ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-08-09 | 2019-12-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 254061102 | 1 | 1097.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | KINGS CANYON N. PARK | Dinuba |  |  | OPEN | 117821436 | TREE_DECA_INPL - C/O PALISADE WY/SIERRA | 35117226 |  |  | STS-TREE_DECA_INPL - C/O PALISADE WY/SIE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7319 | -118.9584 |  | TIER 2 | 561 | 25406-1102, DUNLAP | 0001428055 | 7714D | Y | 311 |  |  | 2021-04-14 07:45 | 2021-04-14 16:05 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100774928 | POHW OH PRI JPOL RESD FIRE ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-08-09 | 2019-12-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 254061102 | 1 | 1097.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | KINGS CANYON N. PARK | Dinuba |  |  | OPEN | 117821437 | TREE_DECA_INPL - C/O PALISADE WY/SIERRA | 35117226 |  |  | STS-TREE_DECA_INPL - C/O PALISADE WY/SIE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.732 | -118.9584 |  | TIER 2 | 561 | 25406-1102, DUNLAP | 0001428055 | 7714D | Y | 311 |  |  | 2021-04-14 07:45 | 2021-04-14 16:05 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100774927 | POHW OH PRI JPOL RESD FIRE ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-08-09 | 2019-12-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 254061102 | 1 | 1097.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | KINGS CANYON N. PARK | Dinuba |  |  | OPEN | 117821591 | TREE_DECA_INPL - C/O PALISADE WY/SIERRA | 35117226 |  |  | STS-TREE_DECA_INPL - C/O PALISADE WY/SIE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7321 | -118.9582 |  | TIER 2 | 561 | 25406-1102, DUNLAP | 0001428055 | 7714D | Y | 311 |  |  | 2021-04-14 07:45 | 2021-04-14 16:05 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100774925 | POHW OH PRI JPOL RESD FIRE ESTR GO BTKA PROG FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-08-09 | 2019-12-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 254061102 | 1 | 1097.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | KINGS CANYON N. PARK | Dinuba |  |  | OPEN | 117821594 | TREE_DECA_INPL - #2 S/O LILAC LN BTWN WI | 35117226 |  |  | STS-TREE_DECA_INPL - C/O PALISADE WY/SIE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7323 | -118.9582 |  | TIER 2 | 561 | 25406-1102, DUNLAP | 0001428055 | 7714D | Y | 311 |  |  | 2021-04-14 07:45 | 2021-04-14 16:05 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Tree/Vine | Decayed/Rotten | Install CL Pole |  | 100774197 | POHW OH PRI JPOL RESD FIRE ESTR GO BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-08-09 | 2019-12-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 254061102 | 1 | 1097.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | KINGS CANYON NATIONAL PK | Fresno |  |  | OPEN | 116720191 | POLE_DECA_REPL - 36309 KINGS CANYON/6PWK | 35080467 |  |  | STS-POLE_DECA_REPL - 36309 KINGS CANYON/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.7557 | -119.1685 |  | TIER 2 | 504 | 25406-1103, DUNLAP | 0001326321 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 22.9 | 22.9 |  |  | 0 | 22.9 | 22.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100761533 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-09-08 | 2020-11-20 | COMP | 2020-09-08 |  |  | 2020-08-27 | 2020-08-27 | [12 empty] | 2019-03-13 | 2020-03-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 254061103 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | MIRAMONTE | Fresno |  |  | OPEN | 116842384 | POLE_DECA_REPL - 1 POLE W/OF 8693-9121/B | 35202509 |  |  | STS-POLE_DECA_REPL - 1 POLE W/OF 8693-91 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.6852 | -119.0458 |  | TIER 2 | 561 | 25406-1102, DUNLAP | 0000014276 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21 | 21 |  |  | 0 | 21 | 21 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100777013 | RELW OH PRI RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-13 | 2021-01-11 | COMP | 2021-01-11 | [16 empty] | 2019-03-26 | 2020-03-26 | 2020-09-27 | 2020-09-27 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254061102 | 6967.97 |  | 0 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | MIRAMONTE | Fresno |  |  | OPEN | 116846778 | POLE_BROK_REPL - F/O/47107 ORCHARD RD. M | 35214895 |  |  | STS-POLE_BROK_REPL - F/O/47107 ORCHARD R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 36.6859 | -119.0417 |  | TIER 2 | 561 | 25406-1102, DUNLAP | 0000014276 | 7060 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100777099 | RELW OH PRI RESD REMT ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-27 | 2020-03-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254061102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | MIRAMONTE | Fresno |  |  | OPEN | 116948398 | POLE_DECA_REPL - 46360 TODD EYMANN RD AT | 35202607 |  |  | STS-POLE_DECA_REPL - 46360 TODD EYMANN R | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.7143 | -119.0316 |  | TIER 2 | 504 | 25406-1103, DUNLAP | 0000014271 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.7 | 15.7 |  |  | 0 | 15.7 | 15.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100775270 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-13 |  | COMP | 2021-01-13 | [16 empty] | 2019-04-03 | 2020-04-03 | 2020-10-11 | 2020-10-11 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254061103 | 5776.33 |  | 0 | 663 | 663 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | OROSI | Dinuba |  |  | COMP | 116805895 | POLE_DECA_REPL - R/O 44954 HWY245 OROSI | 35180138 |  |  | OCLH PLE_DECA_RPL-R/O 44954 HWY245 OR | FICL | FICL SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-07-29 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 36.5814 | -119.1019 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015265 |  | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 42.7 | 42.7 |  |  | 40 | 24 | 24 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 103257164 | RELW OH PRI INSP COMP REMT NOAC ESTR CPGD FMOB TER2 FSRP | Pole | 2020-06-30 | 2020-07-19 | COMP | 2020-06-30 | COMP | 2021-01-14 | [13 empty] | 2021-01-15 | 2021-01-14 | 2020-03-21 | 2020-08-26 | 2020-08-26 | B-Tag Addition 06.24.20 |  | Fresno |  | 254601103 | 7127.71 | 10569.6 | 10524.2 | 10524.2 | 10524.2 |  |  |  | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N |  | Y | 2020-06-29
South | FR | OROSI | Dinuba |  |  | OPEN | 116805124 | POLE_BROK_REPL - 45575[ENTR]HWY245 1/P/N | 35202247 |  |  | STS-POLE_BROK_REPL - 45575[ENTR]HWY245 1 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 36.598 | -119.1066 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015265 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 37.3 | 37.3 |  |  | 0 | 37.3 | 37.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100686562 | RELW OH PRI INSP CLR REMT NOAC ESTR FMOB FSRP TER2 | Pole | 2020-12-29 |  | COMP | 2020-12-29 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-10-26 | 2020-10-26 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254601103 | 28820.58 | 983.5 | 970.1 | 362 | 362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | OROSI | Dinuba |  |  | OPEN | 116805897 | POLE_DECA_REPL - R/O 44954 HWY245 OROSI | 35202255 |  |  | STS-POLE_DECA_REPL - R/O 44954 HWY245 OR | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 36.5811 | -119.1029 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015265 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.4 | 24.4 |  |  | 0 | 24.4 | 24.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100686437 | RELW OH PRI INSP REMT NOAC ESTR FMOB TER2 FSRP | Pole | 2021-02-18 | 2021-02-17 | COMP | 2020-12-16 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-10-26 | 2020-10-26 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254601103 | 15024.12 | 127.5 | -850.7 | -352.9 | -352.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | OROSI | Dinuba |  |  | OPEN | 116805901 | POLE_DECA_REPL - 45452 HWY245 2W/2N/1S/2 | 35202259 |  |  | STS-POLE_DECA_REPL - 45452 HWY245 2W/2N/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.593 | -119.1058 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015265 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.1 | 14.1 |  |  | 0 | 14.1 | 14.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100686474 | RELW OH PRI INSP REMT NOAC ESTR FMOB TER2 FSRP | Pole | 2020-11-19 | 2020-11-19 | COMP | 2020-11-19 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-10-26 | 2020-10-26 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254601103 | 5330.98 | 13.5 | -362 | -362 | -362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | OROSI | Dinuba |  |  | OPEN | 116805902 | POLE_DECA_REPL - MIILLWOOD OROSI | 35202263 |  |  | STS-POLE_DECA_REPL - MIILLWOOD OROSI | APPR | APPR | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 36.5953 | -119.1057 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015265 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100789094 | RELW OH PRI INSP REMT ESTR FMOB TER2 FSRP | Pole |  |  | INPR | [17 empty] | 2019-03-20 | 2020-03-20 | 2020-10-26 | 2020-10-26 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254601103 | 1 | 78.3 | 64.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | OROSI | Dinuba |  |  | OPEN | 117077467 | POLE_DECA_REPL - 49349 RD152 2W/2N/1W OR | 35215573 |  |  | STS-POLE_DECA_REPL - 49349 RD152 2W/2N/1 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.6453 | -119.1718 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015262 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100682448 | RELW PRI OH INSP JPOL REMT FIRE ESTR BTKA PROG FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-22 | 2020-04-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254601103 | 1 | 60.2 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | OROSI | Dinuba |  |  | OPEN | 117087363 | POLE_BROK_REPL - 51161[ENTR]RD152 10W OR | 35214590 |  |  | STS-POLE_BROK_REPL - 51161[ENTR]RD152 10 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.6464 | -119.15 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015262 | 7070SB | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100682425 | RELW OH PRI INSP JPOL REMT FIRE ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-23 | 2020-04-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254601103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | OROSI | Dinuba |  |  | OPEN | 117092544 | POLE_BROK_REPL - 51161[ENTR] RD152 1W OR | 35202188 |  |  | STS-POLE_BROK_REPL - 51161[ENTR] RD152 1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6435 | -119.1336 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015261 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 28.9 | 28.9 |  |  | 0 | 28.9 | 28.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100682412 | RELW OH PRI REMT INSP JPOL RESD FIRE ESTR GO BTKA FMOB TER2 FSRP | Pole | 2020-12-16 | 2020-12-16 | COMP | 2020-12-16 | [16 empty] | 2019-04-24 | 2020-04-24 |  | 2020-04-24 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254601103 | 12637.33 | 94.2 | -760.2 | -307.7 | -307.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | OROSI | Dinuba |  |  | OPEN | 117092558 | POLE_DECA_REPL - 51161 DRIVE 152 OROSI | 35214665 |  |  | STS-POLE_DECA_REPL - 51161 DRIVE 152 ORO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6437 | -119.1331 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015261 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 9.7 | 9.7 |  |  | 0 | 9.7 | 9.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103260329 | RELW OH SERV INSP JPOL REMT FIRE GO NOAC ESTR PROG FMOB TER2 FSRP | Pole | 2021-02-09 | 2021-02-09 | COMP | 2021-02-09 | [16 empty] | 2019-04-24 | 2020-04-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254601103 | 4570.28 | 107 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | OROSI | Dinuba |  |  | OPEN | 117095773 | POLE_DECA_REPA - RD152 SAND CREEK SUBSTA | 35214694 |  |  | STS-POLE_DECA_REPA - RD152 SAND CREEK SU | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.6449 | -119.1596 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015262 | 65869BP | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Repair |  | 100687599 | RELW OH PRI INSP JPOL REMT FIRE ESTR GO BTKA OTRG FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-24 | 2020-04-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254601103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | OROSI AREA | Dinuba |  |  | OPEN | 117071289 | POLE_BROK_REPL - 8401 RD152 2W OROSI ARE | 35202420 |  |  | STS-POLE_BROK_REPL - 8401 RD152 2W OROSI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6363 | -119.1903 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015262 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.2 | 15.2 |  |  | 0 | 15.2 | 15.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100688067 | RELW OH PRI INSP JPOL REMT FIRE ESTR FMOB TER2 FSRP | Pole | 2020-12-14 | 2020-12-14 | COMP | 2020-12-14 | [16 empty] | 2019-04-20 | 2020-04-20 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254601103 | 5833.87 | 13.5 | -760.2 | -488.7 | -488.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | PRATHER | Fresno |  |  | OPEN | 116717255 | POLE_DECA_REPL - 24933 WILD HORSE RD 1PN | 35154058 |  |  | STS-POLE_DECA_REPL - 24933 WILD HORSE RD | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0195 | -119.5775 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 10226D | D4909 | Y | 311 |  |  | 2021-03-26 07:00 | 2021-03-26 16:00 | Dispatched | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100681356 | RELW OH PRI INSP CLR REMT ESTR FMOB TER2 FSRP | Pole | 2020-04-22 | 2020-04-22 | COMP | 2020-04-22 | [16 empty] | 2019-03-12 | 2020-03-12 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151102 | 32579.45 | 4976.2 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | PRATHER | Fresno |  |  | OPEN | 116724333 | POLE_DECA_REPL - 24955 LITTLE WILD HORSE | 35202123 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0177 | -119.5785 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 10226D | D4908 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100681343 | RELW OH PRI INSP RESD ESTR BTKA FMOB TER2 FSRP | Pole | 2021-01-12 | 2021-01-12 | COMP | 2021-01-12 | [16 empty] | 2019-03-13 | 2020-03-13 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254151102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | PRATHER | Fresno |  |  | OPEN | 116741969 | POLE_DECA_REPL - 25037 LITTLE WILD HOARS | 35202142 |  |  | STS-POLE_DECA_REPL - 25037 LITTLE WILD H | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 37.0167 | -119.5774 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 10226D | D4385 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 47.3 | 47.3 |  |  | 0 | 47.3 | 47.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100681339 | RELW OH PRI INSP CLR RESD REMT ESTR BTKA FMOB TER2 FSRP | Pole | 2020-12-07 |  | COMP | 2020-12-07 | [16 empty] | 2019-03-15 | 2020-03-15 | 2020-10-28 | 2020-10-28 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254151102 | 21402.97 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | PRATHER | Fresno |  |  | OPEN | 117019387 | POLE_DECA_REPL - 31983 LOCKWOOD LN 1P/N | 35202210 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0265 | -119.5103 |  | TIER 2 | 390 | 25415-1102, AUBERRY | 10225A |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100678856 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-11 | 2021-01-11 | COMP | 2021-01-11 | [16 empty] | 2019-04-12 | 2020-04-12 | 2020-10-03 | 2020-10-03 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254151102 | 12828.7 | 58.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | REEDLEY | Dinuba |  |  | OPEN | 116691164 | POLE_DECA_REPL - AT 636 WAKEFIELD DR 1PN | 35080256 |  |  | STS-POLE_DECA_REPL - AT 636 WAKEFIELD DR | UNSE | UNSE ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7249 | -119.3487 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000014241 | 7802F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100706206 | RELW OH SEC INSP REMT ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-09 | 2020-03-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | Fresno |  | 252941107 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | SANGER | Dinuba |  |  | OPEN | 116749330 | POLE_BROK_REPL - 6160 LUPINE DRSANGER936 | 35080257 |  |  | STS-POLE_BROK_REPL - 6160 LUPINE DRSANGE | UNSE | UNSE ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 36.7907 | -119.2948 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 13253C | 7791F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103277590 | RELW OH PRI CLR ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-16 | 2020-03-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | Fresno |  | 252941107 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | SANGER | Fresno |  |  | OPEN | 116679466 | POLE_BROK_REPL - 30448 E. TRIMMER SPRING | 35214574 |  |  | STS-POLE_BROK_REPL - 30448 E. TRIMMER SP | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 36.8654 | -119.3485 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000012244 | D9038 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103273248 | RELW OH PRI INSP CLR JPOL RESD NOAC ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-06 | 2020-03-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252941107 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | SANGER | Fresno |  |  | OPEN | 116757490 | POLE_BROK_REPL - MB 7174 ELWOOD RD 2/ESA | 35126805 |  |  | STS-POLE_BROK_REPL - MB 7174 ELWOOD RD 2 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land | 2021-04-01 |  | 36.7955 | -119.314 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 13244A |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.4 | 27.4 |  |  | 0 | 27.4 | 27.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100725582 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-09-01 |  | COMP | 2020-09-01 |  |  | 2021-02-05 | 2021-02-08 | [12 empty] | 2019-03-18 | 2019-11-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 252941107 | 15572.14 | 352.8 | 67.6 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | SANGER | Fresno |  |  | COMP | 119204375 | POLE_DECA_REPL - R/O 34849 MAXOM RD SANG | 35183610 |  |  | STS-POLE_DECA_REPL - R/O 34849 MAXOM RD | MAPP | MAPP SRDY CRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2020-08-22 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 36.9095 | -119.3062 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000012241 | D4387 | Y | 311 |  |  | 2021-01-15 | 2021-01-15 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 77.1 | 77.1 |  |  | 0 | 77 | 77 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 100721424 | OH RELW PRI CREW COMP CLR ESTR BTKA CCNT TER2 | Pole | 2020-08-15 | 2020-08-15 | COMP | 2020-08-15 | COMP | 2021-01-15 | [13 empty] | 2021-01-21 | 2021-01-15 | 2020-09-19 |  | 2020-09-19 | Work Plan Reconcilation (B-Tags) |  | Fresno |  | 254151101 | 24312.6 | 10756.4 | 484.5 | [5 empty] | FRMMA/WMPMA - Electric | N | 11/2 in MPP Import File | N | Tag in Closure Status | Y | 2020-07-21
South | FR | SANGER | Fresno |  |  | COMP | 116842409 | POLE_BROK_REPL - R/O 34849 MAXSON RD/1PS | 35154609 |  |  | STS-POLE_BROK_REPL - R/O 34849 MAXSON RD | MAPP | MAPP SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 36.9093 | -119.3061 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000012241 |  | Y | 311 |  |  | 2021-02-12 07:00 | 2021-02-12 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 50 | 50 |  |  | 70 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100721423 | PRI RELW OH COMP ESTR CPGG FMOB TER2 PRTO | Pole | 2020-05-13 | 2021-01-11 | COMP | 2020-05-11 | COMP | 2021-02-11 | [13 empty] | 2021-02-11 | 2021-02-11 | 2020-03-26 |  | 2020-03-26 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 6985.88 | 6077.2 | 6077.2 | 1312.8 | 1312.8 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | SANGER | Fresno |  |  | OPEN | 117157553 | POLE_DECA_REPL - R/O 32451 TRIMMER SPR R | 35105414 |  |  | STS-POLE_DECA_REPL - R/O 32451 TRIMMER S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.8694 | -119.3107 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000012244 | D9037 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 49.6 | 49.6 |  |  | 0 | 49.6 | 49.6 |  |  | EC | F | Pole | Decayed/Rotten | Replace |  | 100723255 | RELW OH PRI CLR RESD NOAC ESTR USA FMOB TER2 PRTO FSRP | Pole | 2020-09-10 | 2020-09-10 | COMP | 2020-09-10 | [16 empty] | 2019-05-03 | 2019-10-07 | 2024-03-11 | 2024-03-11 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 252941107 | 21814.15 | 135.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | SANGER (PIEDRA) | Fresno |  |  | OPEN | 116812432 | POLE_DECA_REPL - 30432 SUNNYSLOPE 2PNWSA | 35126822 |  |  | STS-POLE_DECA_REPL - 30432 SUNNYSLOPE 2P | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.8612 | -119.3412 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000012245 | D8702 | Y | 311 |  |  | 2021-04-23 07:00 | 2021-04-23 16:00 | Reserved | CLICK | [6 empty] | 52.5 | 52.5 |  |  | 0 | 52.5 | 52.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100721604 | INSP RELW OH PRI CLR JPOL RESD ESTR FMOB TER2 FSRP | Pole | 2020-09-01 | 2021-01-23 | COMP | 2020-08-28 |  |  | 2021-01-20 | 2021-01-20 | [12 empty] | 2019-03-22 | 2019-11-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 252941107 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116714725 | POLE_BROK_REPL - MB 32219 INDIAN GUIDE R | 35080319 |  |  | STS-POLE_BROK_REPL - MB 32219 INDIAN GUI | APPR | APPR ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 36.735 | -119.2335 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000014251 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100705752 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | INPR | [17 empty] | 2019-03-12 | 2020-03-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 252941107 | 1 | 2640.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116720095 | POLE_BROK_REPL - ENT 31390 RUTH HILL RD | 35080466 |  |  | STS-POLE_BROK_REPL - ENT 31390 RUTH HILL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7301 | -119.2468 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000014251 | 7877F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100707247 | RELW OH PRI CLR JPOL ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-13 | 2020-03-13 | 2024-03-11 | 2024-03-11 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 252941107 | 1 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116720252 | POLE_BROK_REPL - 31293 RUTH HILL RDSQUAW | 35080470 |  |  | STS-POLE_BROK_REPL - 31293 RUTH HILL RDS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7254 | -119.2457 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000014251 | 584840 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100707394 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-13 | 2020-03-13 | 2024-03-11 | 2024-03-11 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 252941107 | 1 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116721836 | POLE_DECA_REPL - 31488 RUTH HILL RD 3PE | 35079887 |  |  | STS-POLE_DECA_REPL - 31488 RUTH HILL RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7286 | -119.2408 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000014251 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100707222 | RELW OH SEC CLR ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-13 | 2020-03-13 | 2024-03-11 | 2024-03-11 | 2021 CBP Plan | 2020-10-31 | EEI |  | 252941107 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116761995 | POLE_DECA_REPL - 37332 HWY180 1/S SQUAW | 35215034 |  |  | STS-POLE_DECA_REPL - 37332 HWY180 1/S SQ | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land Enviro JointPole |  |  | 36.7595 | -119.1419 |  | TIER 2 | 504 | 25406-1103, DUNLAP | 0000013265 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.5 | 20.5 |  |  | 0 | 20.5 | 20.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100761649 | RELW OH PRI JPOL RESD REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-01 |  | COMP | 2021-02-01 | [16 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254061103 | 26483.67 | 357.5 | 344.1 | 118.2 | 118.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116713318 | POLE_DECA_REPL - 34601 HOPEWELL RDSQUAW | 35097538 |  |  | STS-POLE_DECA_REPL - 34601 HOPEWELL RDSQ | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.7464 | -119.167 |  | TIER 2 | 504 | 25406-1103, DUNLAP | 0000013266 |  | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | [6 empty] | 50.1 | 50.1 |  |  | 0 | 50.1 | 50.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100761633 | RELW OH PRI JPOL REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2020-05-22 | 2020-06-05 | COMP | 2020-03-26 | [16 empty] | 2019-03-12 | 2020-03-12 | 2024-03-10 | 2024-03-10 | Per email from [REDACTED] 5/6 |  | Fresno |  | 254061103 | 17398.12 | 2099.4 | 542.9 | 342.1 | 342.1 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-05-10
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116725577 | POLE_DECA_REPL - A/F 1725 CRANE LN 1PN | 35079896 |  |  | STS-POLE_DECA_REPL - A/F 1725 CRANE LN | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.766 | -119.234 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000013255 |  | Y | 311 |  |  | 2021-02-20 07:00 | 2021-02-20 16:00 | Completed | CLICK | [6 empty] | 50.1 | 50.1 |  |  | 0 | 50.1 | 50.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100762355 | RELW OH PRI JPOL REMT SWRK ESTR FMOB TER2 PRTO FSRP | Pole | 2020-11-02 | 2020-11-03 | COMP | 2020-04-14 |  |  | 2020-10-27 | 2020-10-27 | [12 empty] | 2019-03-13 | 2020-03-13 | 2021-05-31 | 2021-05-31 | Per email from [REDACTED] 5/6 | 2020-01-31 | EEI |  | 252941107 | 14766.25 | 4304.3 | 480.1 | 279.3 | 279.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-05-10
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116822061 | POLE_BROK_REPL - AT 29415 RUTH HILL RD 1 | 35173219 |  |  | STS-POLE_BROK_REPL - AT 29415 RUTH HILL | CONS | CONS SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.7449 | -119.2808 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000014252 | 7797F | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | [6 empty] | 256.5 | 256.5 |  |  | 0 | 256.5 | 256.5 |  |  | EC | B | Pole | Broken/Damaged | Replace |  | 100708836 | PRI OH RELW CLR ESTR FMOB TER2 PRTO FSRP | Pole | 2020-06-22 | 2020-06-29 | COMP | 2020-06-22 |  |  | 2020-06-23 | 2020-06-23 | [12 empty] | 2019-03-24 | 2020-03-24 | 2020-07-10 | 2020-07-10 | B-Tag Clean Up 5/14/20 |  | Fresno |  | 252941107 | 148379.29 | 7982.2 | [7 empty] | N | 11/2 in MPP Import File | N | Other Process Error | Y | 2020-05-25
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 119166357 | POLE_DECA_REPL - AT 29415 RUTH HILL RD 1 | 35173219 |  |  | STS-POLE_BROK_REPL - AT 29415 RUTH HILL | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.745 | -119.2806 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000014252 | 7797F | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100708838 | POHW OH ESTR TER2 | Pole | 2020-06-22 | 2020-06-29 | COMP | 2020-06-22 |  |  | 2020-06-23 | 2020-06-23 | [12 empty] | 2020-05-26 | 2021-05-26 |  | 2021-05-26 | Per DOT Approved Request 28511 |  | Fresno |  | 252941107 | 148379.29 | 7982.2 | [7 empty] | N | MPP File Only | N |  | Y | 2021-01-14
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 119166424 | POLE_DECA_REPL - AT 29415 RUTH HILL RD 1 | 35173219 |  |  | STS-POLE_BROK_REPL - AT 29415 RUTH HILL | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.7449 | -119.2807 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000014252 | 7797F | Y | 311 |  |  | 2021-03-02 07:00 | 2021-03-02 16:00 | Dispatched | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100708837 | POHW OH ESTR TER2 | Pole | 2020-06-22 | 2020-06-29 | COMP | 2020-06-22 |  |  | 2020-06-23 | 2020-06-23 | [12 empty] | 2020-05-26 | 2021-05-26 |  | 2021-05-26 | Per DOT Approved Request 28512 |  | Fresno |  | 252941107 | 148379.29 | 7982.2 | [7 empty] | N | MPP File Only | N |  | Y | 2021-01-14
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116720937 | POLE_DECA_REPL - 31338 RUTH HLL RDSQUAW | 35079882 |  |  | STS-POLE_DECA_REPL - 31338 RUTH HLL RDSQ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.7289 | -119.2447 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000014251 | 7877F | Y | 311 |  |  | 2021-04-27 07:00 | 2021-04-27 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 51.8 | 51.8 |  |  | 0 | 51.8 | 51.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100707227 | RELW OH PRI CLR JPOL ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-04-08 | 2020-06-11 | COMP | 2020-04-08 | [16 empty] | 2019-03-13 | 2020-03-13 | 2021-05-31 | 2021-05-31 | Per email from [REDACTED] 5/6 | 2020-01-31 | EEI |  | 252941107 | 18413.87 | 1465.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-05-10
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116722732 | POLE_BROK_REPL - HSE 3135 RUTH HILL RD/1 | 35080399 |  |  | STS-POLE_BROK_REPL - HSE 3135 RUTH HILL | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.7243 | -119.2433 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000014251 | 4171F | Y | 311 |  |  | 2021-03-26 07:00 | 2021-03-26 16:00 | Scheduled | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100707169 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-13 | 2020-03-13 | 2021-05-31 | 2021-05-31 | Program Manager | 2020-09-30 | Fresno |  | 252941107 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-02-20
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116722844 | POLE_BROK_REPL - HSE 31315 RUTH HILL RD/ | 35079888 |  |  | STS-POLE_BROK_REPL - HSE 31315 RUTH HILL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.7233 | -119.2436 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000014251 | 4171F | Y | 311 |  |  | 2021-04-13 07:00 | 2021-04-13 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100707175 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-05-18 | 2020-07-16 | COMP | 2020-04-10 | [16 empty] | 2019-03-13 | 2020-03-13 | 2021-05-31 | 2021-05-31 | Per email from [REDACTED] 5/6 | 2020-01-31 | EEI |  | 252941107 | 23443.67 | 11986.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-05-10
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116788599 | POLE_DECA_REPL - 35639 SAND CREEK RD-SER | 35082781 |  |  | STS-POLE_DECA_REPL - 35639 SAND CREEK RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6858 | -119.204 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000014255 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.2 | 22.2 |  |  | 0 | 22.2 | 22.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100722900 | RELW OH PRI REMT CGI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-17 | 2021-01-25 | COMP | 2020-12-16 | [16 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Fresno |  | 254601103 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116825031 | POLE_DECA_REPL - R/O 37542 SQUAW VALLEY | 35126834 |  |  | STS-POLE_DECA_REPL - R/O 37542 SQUAW VAL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6871 | -119.1785 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000014266 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15.8 | 15.8 |  |  | 0 | 15.8 | 15.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100707382 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-10-01 | 2020-10-01 | COMP | 2020-10-01 | [16 empty] | 2019-03-25 | 2019-11-07 | 2024-03-23 | 2024-03-23 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 254601103 | 7803.13 | 1335.6 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116825257 | POLE_DECA_REPL - R/O 41656 SANDCREEK RDS | 35202472 |  |  | STS-POLE_DECA_REPL - R/O 41656 SANDCREEK | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6831 | -119.174 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000014266 | 54211 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.6 | 32.6 |  |  | 0 | 32.6 | 32.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100687496 | RELW OH PRI REMT FIRE ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-21 | 2020-12-21 | COMP | 2020-12-21 | [16 empty] | 2019-03-25 | 2020-03-25 | 2020-09-07 | 2020-09-07 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 254601103 | 17435.11 | 1286.6 | 1273.2 | 271.5 | 271.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116829715 | +POLE_DECA_REPL -38386 DUNLAP RD 2PWSQU | 35083599 |  |  | STS-POLE_DECA_REPL - 38386 DUNLAP RD 2P | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.7426 | -119.135 |  | TIER 2 | 504 | 25406-1103, DUNLAP | 0000014261 | 7040 | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Scheduled | CLICK | [6 empty] | 51.2 | 50 | 1.2 |  | 0 | 51.2 | 50 | 1.2 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100691776 | RELW OH PRI RESD REMT ESTR REAR FMOB TER2 PRTO | Pole | 2019-06-05 | 2019-06-05 | COMP | 2019-06-05 |  |  | 2019-06-05 | 2019-06-05 | [12 empty] | 2019-03-25 | 2019-08-15 |  | 2019-08-15 | Q1 Work Plan |  | UNASSIGNED |  | 254061103 | 11191.61 | 4414.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116863483 | POLE_BROK_REPL - AT 29415 RUTH HILL RD 1 | 35126849 |  |  | STS-POLE_BROK_REPL - AT 29415 RUTH HILL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.7299 | -119.2825 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000014252 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50.1 | 50.1 |  |  | 0 | 50.1 | 50.1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100708558 | RELW OH PRI CLR ESTR GO FMOB TER2 FSRP PRTO | Pole | 2020-10-27 | 2021-02-03 | COMP | 2020-10-26 | [16 empty] | 2019-03-28 | 2019-09-28 | 2024-03-26 | 2024-03-26 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 252941107 | 30567.61 | 1584.1 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 116871947 | POLE_DECA_REPL - 39564 CLOVER LN/1PNSQUA | 35202568 |  |  | STS-POLE_DECA_REPL - 39564 CLOVER LN/1PN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 36.6717 | -119.1536 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000014266 | 3512F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.6 | 36.6 |  |  | 0 | 36.6 | 36.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100685189 | RELW OH PRI JPOL ESTR FMOB TER2 PRTO FSRP | Pole | 2021-02-01 |  | COMP | 2021-02-01 | [16 empty] | 2019-03-30 | 2020-03-30 | 2020-09-14 | 2020-09-14 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254601103 | 18566.83 | 89.4 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 117368012 | POLE_DECA_REPL - R/O 38825 WILLOWOOD LN/ | 35203093 |  |  | STS-POLE_DECA_REPL - R/O 38825 WILLOWOOD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.6592 | -119.1831 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000014266 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.2 | 13.2 |  |  | 0 | 13.2 | 13.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100691222 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-14 | 2020-12-14 | COMP | 2020-12-14 | [16 empty] | 2019-05-31 | 2020-05-31 | 2020-10-29 | 2020-10-29 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 254601103 | 5177.25 | 13.5 | -1303.1 | -624.4 | -624.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | SQUAW VALLEY | Fresno |  |  | OPEN | 117370388 | POLE_DECA_REPL - R/O 38825 WILLOWOOD LN/ | 35215851 |  |  | STS-POLE_DECA_REPL - R/O 38825 WILLOWOOD | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 36.6592 | -119.187 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000014266 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100691202 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-06-01 | 2020-06-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254601103 | 1 | 13.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | TOLLHOUSE | Fresno |  |  | COMP | 116990208 | POLE_BROK_REPL - 28605 BURROUGH NORTH RD | 35154303 |  |  | STS-POLE_BROK_REPL - 28605 BURROUGH NORT | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 36.981 | -119.3803 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000011242 |  | Y | 311 |  |  | 2021-01-12 | 2021-01-12 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100650513 | RELW OH PRI ESTR FMOB TER2 PRTO COMP CCNT | Pole | 2020-04-28 | 2020-04-28 | COMP | 2020-04-28 | COMP | 2021-01-12 | [13 empty] | 2021-01-14 | 2021-01-12 | 2020-04-09 |  | 2020-04-09 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 13160.43 | 13250.9 | 11796.5 | 20222.1 | 20222.1 | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | TOLLHOUSE | Fresno |  |  | COMP | 117016665 | POLE_BROK_REPL - 35735 OAK SPRINGS RDTOL | 35154438 |  |  | STS-POLE_BROK_REPL - 35735 OAK SPRINGS R | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.0282 | -119.4228 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000010235 | D510 | Y | 311 |  |  | 2021-01-05 | 2021-01-05 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 52.7 | 52.7 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100676066 | RELW OH PRI COMP ESTR BTKA CCNT FMOB TER2 PRTO | Pole | 2020-04-29 | 2020-04-29 | COMP | 2020-04-29 | COMP | 2021-01-05 | [13 empty] | 2021-01-07 | 2021-01-05 | 2020-04-12 |  | 2020-04-12 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 16765.46 | 32905.6 | 32905.6 | 32946.4 | 32946.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | TOLLHOUSE | Fresno |  |  | COMP | 117017143 | POLE_BROK_REPL - R/O 35667 LODGE RD 1/E | 35154446 |  |  | STS-POLE_BROK_REPL - R/O 35667 LODGE RD | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.0147 | -119.4259 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000010235 | R2578 | Y | 311 |  |  | 2021-01-12 | 2021-01-12 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 51.8 | 51.8 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100675711 | RELW OH PRI COMP ESTR CCNT FMOB TER2 PRTO | Pole | 2020-05-05 | 2020-05-05 | COMP | 2020-05-05 | COMP | 2021-01-12 | [13 empty] | 2021-01-14 | 2021-01-12 | 2020-04-12 |  | 2020-04-12 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 18135.72 | 9029.4 | 8985.1 | 21879.6 | 21879.6 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | TOLLHOUSE | Fresno |  |  | COMP | 117022186 | POLE_BROK_REPL - 35218 LODGE RD TOLLHOUS | 35154504 |  |  | STS-POLE_BROK_REPL - 35218 LODGE RD TOLL | DOCC | DOCC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND | 2021-02-15 | No Action | 37.0192 | -119.433 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000010235 | R2839 | Y | 311 |  |  | 2021-01-11 | 2021-01-11 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 52.7 | 52.7 |  |  | 0 | 52.7 | 52.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100675748 | RELW OH PRI COMP ESTR CCNT FMOB TER2 PRTO | Pole | 2020-05-05 | 2020-06-30 | COMP | 2020-05-05 | COMP | 2021-01-11 | 2020-06-29 | 2020-06-30 | [11 empty] | 2021-01-14 | 2021-01-11 | 2020-04-13 |  | 2020-04-13 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 18553.29 | 14409.4 | 13825.9 | 23978.5 | 23978.5 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | TOLLHOUSE | Fresno |  |  | COMP | 117023718 | POLE_BROK_REPL - R/O 34661 OAK SPRINGS R | 35154515 |  |  | STS-POLE_BROK_REPL - R/O 34661 OAK SPRIN | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.023 | -119.4308 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000010235 |  | Y | 311 |  |  | 2021-01-10 | 2021-01-10 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 52 | 52 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100679349 | RELW OH COMP CCNT TER2 PRI ESTR FMOB PRTO | Pole | 2020-05-05 | 2020-05-05 | COMP | 2020-05-05 | COMP | 2021-01-10 | [13 empty] | 2021-01-13 | 2021-01-10 | 2020-04-13 |  | 2020-04-13 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 8756.27 | 25435.7 | 25391.4 | 42716.3 | 42716.3 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | TOLLHOUSE | Fresno |  |  | COMP | 117023804 | POLE_BROK_REPL - 35218 LODGE RD 3/NE 2/S | 35154519 |  |  | STS-POLE_BROK_REPL - 35218 LODGE RD 3/NE | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.0187 | -119.4309 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000010235 |  | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 52.7 | 52.7 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100675746 | OH RELW PRI COMP ESTR GO CCNT FMOB TER2 PRTO | Pole | 2020-05-15 | 2020-05-15 | COMP | 2020-05-14 | COMP | 2021-01-06 | [13 empty] | 2021-01-08 | 2021-01-06 | 2020-04-13 |  | 2020-04-13 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 7837.11 | 32809.4 | 32809.4 | 32809.4 | 32809.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | TOLLHOUSE | Fresno |  |  | COMP | 117032003 | POLE_BROK_REPL - 33678 LODGE RD/ AT HOUS | 35154630 |  |  | STS-POLE_BROK_REPL - 33678 LODGE RD/ AT | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 37.0259 | -119.451 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000010235 | D2298 | Y | 311 |  |  | 2021-01-12 | 2021-01-12 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 52.7 | 52.7 |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100675947 | RELW OH PRI COMP ESTR CCNT FMOB TER2 PRTO | Pole | 2020-04-27 | 2020-04-27 | COMP | 2020-04-27 | COMP | 2021-01-12 | [13 empty] | 2021-01-14 | 2021-01-12 | 2020-04-15 |  | 2020-04-15 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 19151.86 | 15440.9 | 15396.6 | 25445 | 25445 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | TOLLHOUSE | Fresno |  |  | OPEN | 116977527 | POLE_DECA_REPL - 33020 WINTERMUTE LN AT | 35154204 |  |  | STS-POLE_DECA_REPL - 33020 WINTERMUTE LN | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0355 | -119.4638 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000010236 | R1013 | Y | 311 |  |  | 2021-02-08 07:00 | 2021-02-08 16:00 | Completed | CLICK | [6 empty] | 50.1 | 50.1 |  |  | 2.75 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100676321 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-05-07 | 2020-05-07 | COMP | 2020-05-07 | [16 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 25153.66 | 9357.5 | 396.3 |  |  | 127.7 |  | 127.7 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | TOLLHOUSE | Fresno |  |  | OPEN | 117005007 | POLE_BROK_REPL - 37332 FOX CREEK LNTOLLH | 35154343 |  |  | STS-POLE_BROK_REPL - 37332 FOX CREEK LNT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0111 | -119.4101 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000010235 | D12538 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100676203 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-05-06 | 2020-05-06 | COMP | 2020-05-06 | [16 empty] | 2019-04-10 | 2020-04-10 |  | 2020-04-10 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | TOLLHOUSE | Fresno |  |  | OPEN | 117016847 | POLE_DECA_REPL - R/O 35667 LODGE RD 1/E | 35154442 |  |  | STS-POLE_DECA_REPL - R/O 35667 LODGE RD | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0133 | -119.4254 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000010235 | R2578 | Y | 311 |  |  | 2021-03-03 07:00 | 2021-03-03 16:00 | Scheduled | CLICK | [6 empty] | 50.1 | 50.1 |  |  | 1.5 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100675663 | RELW OH PRI TER2 ESTR GO FMOB PRTO | Pole | 2020-05-05 | 2020-05-14 | COMP | 2020-05-05 | [16 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 12211.09 | 5564.6 | 2485 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | TOLLHOUSE | Fresno |  |  | OPEN | 117023811 | POLE_DECA_REPL - 33342 LODGE RD 1/N 6/E | 35154544 |  |  | STS-POLE_DECA_REPL - 33342 LODGE RD 1/N | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0329 | -119.4441 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000010235 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50.1 | 50.1 |  |  | 1 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100676206 | RELW OH PRI NOAC ESTR FMOB TER2 PRTO | Pole | 2020-06-01 | 2020-06-01 | COMP | 2020-06-01 | [16 empty] | 2019-04-13 | 2020-04-13 |  | 2020-04-13 | circuit based plan 2.14 | 2020-05-31 | TRC |  | 254151101 | 8979.12 | 3216.6 | 2439.1 | 1203.9 | 1203.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | TOLLHOUSE | Fresno |  |  | COMP | 116966568 | POLE_BROK_REPL - 29448 SEMINOLE-SERVICE | 35154136 |  |  | STS-POLE_BROK_REPL - 29448 SEMINOLE-SERV | FICL | FICL SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-12-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 36.9671 | -119.38 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000011243 |  | Y | 311 |  |  | 2021-01-15 | 2021-01-15 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 50.8 | 50.8 |  |  | 70 | 0.8 | 0.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100651525 | RELW OH PRI COMP ESTR CPGG FMOB TER2 PRTO | Pole | 2020-06-17 | 2020-06-20 | COMP | 2020-04-23 | COMP | 2021-01-15 | 2020-06-16 | 2020-06-16 | [11 empty] | 2021-01-18 | 2021-01-15 | 2020-04-05 |  | 2020-04-05 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 5020.82 | 19721.6 | 18417.4 | 18417.4 | 18417.4 | 44.3 |  | 44.3 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | TOLLHOUSE | Fresno |  |  | OPEN | 116864934 | POLE_DECA_REPL - ENT 30198 WATTS VLY RD | 35126850 |  |  | STS-POLE_DECA_REPL - ENT 30198 WATTS VLY | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.9338 | -119.3663 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000011246 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.2 | 18.2 |  |  | 0 | 18.2 | 18.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100652659 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2020-09-16 | 2020-10-20 | COMP | 2020-09-15 | [16 empty] | 2019-03-28 | 2019-11-07 |  | 2019-11-07 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 254151101 | 7658.51 | 43.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | TOLLHOUSE | Fresno |  |  | OPEN | 116966566 | POLE_BROK_REPL - 29615 SEMINOLE RD 2/STO | 35126876 |  |  | STS-POLE_BROK_REPL - 29615 SEMINOLE RD 2 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-04-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.9662 | -119.3833 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000011243 | D2170 | Y | 311 |  |  | 2021-04-22 07:00 | 2021-04-22 16:00 | Reserved | CLICK | [6 empty] | 38.1 | 38.1 |  |  | 0.75 | 37.35 | 37.35 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100651533 | OH RELW PRI ESTR FMOB TER2 PRTO | Pole | 2020-09-01 | 2021-01-20 | COMP | 2020-08-31 |  |  | 2021-01-20 | 2021-01-20 | [12 empty] | 2019-04-05 | 2019-10-15 |  | 2019-10-15 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 254151101 | 22594.83 | 497.6 | 244.4 | 244.4 | 244.4 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | TOLLHOUSE | Fresno |  |  | OPEN | 116977679 | POLE_DECA_REPL - 33166 WINTERMUTE LNTOLL | 35085686 |  |  | STS-POLE_DECA_REPL - 33166 WINTERMUTE LN | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0344 | -119.4635 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000010236 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 15 | 15 |  |  | 0 | 15 | 15 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100676325 | RELW FMOB OH PRI ESTR TER2 PRTO | Pole | 2021-01-21 | 2021-01-25 | COMP | 2020-09-08 |  |  | 2021-01-20 | 2021-01-20 | [12 empty] | 2019-04-08 | 2019-09-27 | 2020-11-15 | 2020-11-15 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 254151101 | 6859.63 | 43.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | TOLLHOUSE | Fresno |  |  | OPEN | 116977854 | POLE_DECA_REPL - 29455 FALLEN OAK RDTOLL | 35154209 |  |  | STS-POLE_DECA_REPL - 29455 FALLEN OAK RD | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.9597 | -119.38 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000011243 | D8164 | Y | 311 |  |  | 2021-03-26 07:00 | 2021-03-26 16:00 | Dispatched | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100651471 | RELW OH PRI CLR ESTR FMOB TER2 PRTO | Pole | 2020-05-11 | 2020-05-11 | COMP | 2020-05-11 | [16 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 12666.9 | 2775.7 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | TOLLHOUSE | Fresno |  |  | OPEN | 116979958 | POLE_DECA_REPL - 31879 REBEL HILL LN 1PS | 35154225 |  |  | STS-POLE_DECA_REPL - 31879 REBEL HILL LN | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-01-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.9799 | -119.3507 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000011243 |  | Y | 311 |  |  | 2021-03-26 07:00 | 2021-03-26 16:00 | Dispatched | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100652224 | RELW OH PRI REMT FIRE SWRK ESTR FMOB TER2 PRTO | Pole | 2020-05-11 | 2020-05-11 | COMP | 2020-05-11 | [16 empty] | 2019-04-08 | 2020-04-08 |  | 2020-04-08 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 254151101 | 10261.24 | 819.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
South | FR | TOLLHOUSE | Fresno |  |  | OPEN | 117015534 | POLE_BROK_REPL - R/O 35885 LOGE RD 1/NE | 35154422 |  |  | STS-POLE_BROK_REPL - R/O 35885 LOGE RD 1 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0115 | -119.4199 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000010235 | R2578 | Y | 311 |  |  | 2021-04-20 07:00 | 2021-04-20 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 51.8 | 51.8 |  |  | 0 | 51.8 | 51.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100675640 | RELW OH PRI ESTR FMOB TER2 PRTO | Pole | 2021-01-21 | 2021-01-21 | COMP | 2021-01-21 | [16 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254151101 | 18532.06 |  | 0 | 1092 | 1092 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | TOLLHOUSE | Fresno |  |  | OPEN | 117016508 | POLE_BROK_REPL - R/O 35885 LODGE RDTOLLH | 35154434 |  |  | STS-POLE_BROK_REPL - R/O 35885 LODGE RDT | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.012 | -119.4255 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0000010235 | D12536 | Y | 311 |  |  | 2021-04-16 07:00 | 2021-04-16 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100675661 | RELW PRI OH ESTR USA FMOB TER2 PRTO | Pole | 2021-01-21 | 2021-01-21 | COMP | 2021-01-21 | [16 empty] | 2019-04-12 | 2020-04-12 |  | 2020-04-12 | 2021 CBP Plan | 2020-10-31 | TRC |  | 254151101 | 14467.69 |  | 0 | 1092 | 1092 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | TOLLHOUSE | Fresno |  |  | OPEN | 117042636 | POLE_BROK_REPL - 28691 TOLLHOUSE RD 1PE | 35088629 |  |  | STS-POLE_BROK_REPL - 28691 TOLLHOUSE RD | UNSC | UNSC srdy | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 37.0179 | -119.3991 |  | TIER 2 | 207 | 25415-1101, AUBERRY | 0001024312 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 14.3 | 14.3 |  |  | 0 | 14.3 | 14.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100680950 | RELW OH SERV ESTR FMOB TER2 PRTO | Pole | 2020-09-28 | 2020-09-28 | COMP | 2020-09-28 | [16 empty] | 2019-04-16 | 2019-09-30 |  | 2019-09-30 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 254151101 | 11993.81 | 1454.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | WOODLAKE | Dinuba |  |  | OPEN | 117134905 | POLE_DECA_REPL - 10 POLES SE OF SW 7185 | 35117228 |  |  | STS-POLE_DECA_REPL - 10 POLES SE OF SW | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 36.5049 | -119.1218 |  | TIER 2 | 1355 | 25292-1110, STONE CORRAL | 16265B | 657333 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 27.1 | 27.1 |  |  | 0 | 27.1 | 27.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103259469 | RELW OH PRI INSP JPOL REMT FIRE ESTR BTKA FMOB TER2 FSRP | Pole | 2020-11-17 | 2021-01-04 | COMP | 2020-11-17 | [16 empty] | 2019-05-01 | 2019-10-15 | 2024-04-29 | 2024-04-29 | 2021 CBP Plan | 2020-10-31 | ENENG |  | 252921110 | 10822.86 | 1415 | 1053 | 1053 | 1053 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | FR | WOODLAKE | Dinuba |  |  | OPEN | 116954432 | POLE_LEAN_ADJU - ESHOM CAMP 1N WOODLAKE | 35214657 |  |  | STS-POLE_LEAN_ADJU - ESHOM CAMP 1N WOODL | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 36.643 | -118.9535 |  | TIER 2 | 756 | 25460-1103, SAND CREEK | 0000015282 | 7982F | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Leaning | Adjust |  | 100685300 | RELW OH PRI INSP CLR REMT ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-04 | 2020-04-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 254601103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | FR | WSIP | Fresno |  |  | OPEN | 116717119 | POLE_BROK_REPL - HOUSE 1270 LELYER LN 1 | 35126596 |  |  | STS-POLE_BROK_REPL - HOUSE 1270 LELYER | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 36.7612 | -119.2267 |  | TIER 2 | 873 | 25294-1107, TIVY VALLEY | 0000013255 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 25.6 | 25.6 |  |  | 0 | 25.6 | 25.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100762294 | ESTR RELW OH PRI FMOB TER2 PRTO FSRP | Pole | 2021-01-27 |  | COMP | 2021-01-27 |  |  | 2021-01-26 | 2021-01-26 | [12 empty] | 2019-03-12 | 2019-10-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | CALENG |  | 252941107 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | KE | BAKERSFIELD | Bakersfield |  |  | OPEN | 117113432 | POLE_DECA_REPL - T/L PARDEE-PASTORIA-WAR | 35154150 |  |  | STS-POLE_DECA_REPL - T/L PARDEE-PASTORIA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 34.8473 | -118.7931 |  | TIER 2 | 349 | 25293-1102, TEJON | 0000009186 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 21 | 21 |  |  | 0 | 21 | 21 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100200630 | RELW OH PRI ESTR FMOB TER2 PRTO FSRP | Pole | 2020-04-29 | 2020-07-10 | COMP | 2020-04-28 | [16 empty] | 2019-04-27 | 2020-04-27 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-05-01 | TRC |  | 252931102 | 9889.48 | 88.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | KE | BAKERSFIELD | Bakersfield |  |  | OPEN | 116790159 | POLE_DECA_REPL - 11322 RND MTN RD 1PNE/4 | 35154242 |  |  | STS-POLE_DECA_REPL - 11322 RND MTN RD 1P | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4994 | -118.8682 |  | TIER 2 | 353 | 25364-2104, POSO MOUNTAIN | 0000028293 |  | Y | 311 |  |  | 2021-05-25 07:00 | 2021-05-27 16:00 | Dispatched | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100117665 | RELW OH PRI INSP REMT FIRE NOAC ESTR GO FMOB TER2 FSRP | Pole | 2020-05-04 | 2020-05-04 | COMP | 2020-05-04 | [16 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 253642104 | 12739.08 | 2392.7 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-02-18
South | KE | BAKERSFIELD | Bakersfield |  |  | OPEN | 116813492 | POLE_DECA_REPL - 11322 RND MTN RD 1PNE/4 | 35154377 |  |  | STS-POLE_DECA_REPL - 11322 RND MTN RD 1P | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.498 | -118.8612 |  | TIER 2 | 353 | 25364-2104, POSO MOUNTAIN | 0000028293 |  | Y | 311 |  |  | 2021-05-25 07:00 | 2021-05-27 16:00 | Dispatched | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100117680 | RELW OH PRI INSP REMT FIRE NOAC ESTR FMOB TER2 FSRP | Pole | 2020-05-14 | 2020-05-14 | COMP | 2020-05-14 | [16 empty] | 2019-03-22 | 2020-03-22 | 2024-03-20 | 2024-03-20 | circuit based plan 2.14 | 2020-05-01 | TRC |  | 253642104 | 12542.68 | 3566.5 | 1203.9 | 1203.9 | 1203.9 | 83.4 |  | 83.4 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | KE | BAKERSFIELD | Bakersfield |  |  | OPEN | 117113433 | POLE_DECA_REPL - T/L PARDEE-PASTORIA-WAR | 35121775 |  |  | STS-POLE_DECA_REPL - T/L PARDEE-PASTORIA | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 34.8477 | -118.7939 |  | TIER 2 | 349 | 25293-1102, TEJON | 0000009186 |  | Y | 311 |  |  | 2021-06-01 07:00 | 2021-06-04 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 0.5 | 49.5 | 49.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100225103 | RELW OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2019-11-21 | 2019-12-03 | COMP | 2019-11-21 | [16 empty] | 2019-04-27 | 2019-11-15 | 2021-05-31 | 2021-05-31 | Per email from [REDACTED] 5/6 |  | UNASSIGNED |  | 252931102 | 8953.95 | 2146.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-05-10
South | KE | BAKERSFIELD | Bakersfield |  |  | OPEN | 117119249 | POLE_DECA_REPL - MB 301 GRANITE ROCK RD | 35121776 |  |  | STS-POLE_DECA_REPL - MB 301 GRANITE ROCK | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.643 | -118.8144 |  | TIER 2 | 833 | 25364-2101, POSO MOUNTAIN | 0000026295 |  | Y | 311 |  |  | 2021-05-18 07:00 | 2021-05-20 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100214714 | RELW OH PRI NOAC INSP REMT FIRE ESTR GO FMOB TER2 FSRP | Pole | 2019-11-21 | 2019-11-21 | COMP | 2019-11-21 | [16 empty] | 2019-04-29 | 2019-11-15 | 2021-05-31 | 2021-05-31 | Per email from [REDACTED] 5/6 |  | UNASSIGNED |  | 253642101 | 27326.25 | 1889.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-05-10
South | KE | BAKERSFIELD | Bakersfield |  |  | OPEN | 117120129 | POLE_BROK_REPL - MB 301 GRANITE ROCK 12N | 35121778 |  |  | STS-POLE_BROK_REPL - MB 301 GRANITE ROCK | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.6426 | -118.8247 |  | TIER 2 | 833 | 25364-2101, POSO MOUNTAIN | 0000026295 |  | Y | 311 |  |  | 2021-05-18 07:00 | 2021-05-20 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 2 | 48 | 48 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100214690 | INSP RELW OH PRI REMT FIRE NOAC ESTR GO FMOB TER2 FSRP | Pole | 2019-12-10 | 2020-02-07 | COMP | 2019-12-04 | [16 empty] | 2019-04-29 | 2019-11-30 | 2021-05-31 | 2021-05-31 | Per email from [REDACTED] 5/6 |  | Bakersfield |  | 253642101 | 8542.23 | 2312.1 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-05-10
South | KE | LEBEC | Bakersfield |  |  | OPEN | 117104096 | POLE_BROK_REPL - 1E/1S 660LEBEC DRLEBEC9 | 35154121 |  |  | STS-POLE_BROK_REPL - 1E/1S 660LEBEC DRLE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 34.8412 | -118.8686 |  | TIER 2 | 349 | 25293-1102, TEJON | 0000919262 |  | Y | 311 |  |  | 2021-06-09 07:00 | 2021-06-09 16:00 | Reserved | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100198643 | RELW OH PRI CLR ESTR FMOB TER2 PRTO FSRP | Pole | 2020-05-08 | 2021-01-22 | COMP | 2020-05-04 |  |  | 2021-01-22 | 2021-01-22 | [12 empty] | 2019-04-26 | 2020-04-26 | 2024-04-24 | 2024-04-24 | 2021 CBP Plan | 2020-05-01 | TRC |  | 252931102 | 24183.17 | 1475 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
South | KE | LEBEC | Bakersfield |  |  | OPEN | 117104719 | POLE_DECA_REPL - I-5~FT TEJON/6PE[SOUTH] | 35121549 |  |  | STS-POLE_DECA_REPL - I-5~FT TEJON/6PE[SO | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 34.8493 | -118.8634 |  | TIER 2 | 349 | 25293-1102, TEJON | 0000009194 |  | Y | 311 |  |  | 2021-06-01 07:00 | 2021-06-04 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 1 | 49 | 49 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100201087 | RELW OH PRI FMOB ESTR PROG TER2 PRTO FSRP | Pole | 2019-11-19 | 2019-11-19 | COMP | 2019-11-19 | [16 empty] | 2019-04-26 | 2019-10-30 | 2021-05-31 | 2021-05-31 | Per email from [REDACTED] 5/6 |  | UNASSIGNED |  | 252931102 | 26437.63 | 3031.9 | [7 empty] | N | MPP File Only | N |  | Y | 2020-05-10
South | KE | LEBEC | Bakersfield |  |  | OPEN | 117280805 | POLE_BROK_REPL - R/O 2817 HIGHLAND DR. L | 35154198 |  |  | STS-POLE_BROK_REPL - R/O 2817 HIGHLAND D | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 34.8523 | -118.8968 |  | TIER 2 | 349 | 25293-1102, TEJON | 0000919214 | 14966 | Y | 311 |  |  | 2021-06-10 07:00 | 2021-06-10 16:00 | Reserved | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 100222847 | PRI OH RELW TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-08-24 | 2021-01-22 | COMP | 2020-08-24 |  |  | 2021-01-22 | 2021-01-22 | [12 empty] | 2019-05-20 | 2020-05-20 | 2024-05-18 | 2024-05-18 | 2021 CBP Plan | 2020-10-31 | TRC |  | 252931102 | 17005.66 | 362 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | KE | WOODY | Bakersfield |  |  | OPEN | 117093141 | POLE_DECA_REPL - 2400 PINE MTN/1PE/13PS | 35123796 |  |  | STS-POLE_DECA_REPL - 2400 PINE MTN/1PE/1 | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.5824 | -118.8233 |  | TIER 2 | 734 | 25364-2103, POSO MOUNTAIN | 0000027294 | 8663 | Y | 311 |  |  | 2021-05-21 07:00 | 2021-05-21 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 50.9 | 50.9 |  |  | 1.5 | 49.4 | 49.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 100203338 | RELW OH PRI INSP REMT FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2019-12-05 | 2019-12-13 | COMP | 2019-12-04 | [16 empty] | 2019-04-24 | 2019-11-21 | 2021-05-31 | 2021-05-31 | Per email from [REDACTED] 5/6 |  | Bakersfield |  | 253642103 | 23370.3 | 4234.2 | [7 empty] | N | MPP File Only | N |  | Y | 2020-05-10
South | LP |  | Santa Maria |  |  | OPEN | 115597418 | +1 POLE SO OF HWY 246 AND 1 POLE E/OF EC | 35069260 |  |  | +1 POLE SO OF HWY 246 & 1 POLE E/OF E.C | CONS | CONS CONT SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 34.6503 | -120.3139 |  | TIER 2 |  |  | BB42 |  | Y | 311 |  |  | 2021-02-06 | 2021-02-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 52.7 | 52.7 |  |  | 9 | 43.7 | 43.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101913467 | REGW OH TER2 | Pole | 2019-06-04 | 2019-06-04 | COMP | 2019-06-04 | [16 empty] | 2018-12-26 | 2019-12-31 |  | 2019-12-31 | Q1 Work Plan | 2019-09-02 | EEI |  |  | 17227.98 | 36690.4 | 7518.5 | 6588.8 | 6588.8 | 7196 |  | 7196 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
South | LP |  | Templeton |  |  | OPEN | 115597333 | SE/CORNER MERCEDES AVE/ SERENA AVE 1/P/S | 35070259 |  |  | +SE/CORNER MERCEDES AVE/SERENA AVE 1/P/S | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4916 | -120.6617 |  | TIER 2 |  |  | II3304 |  | Y | 311 |  |  | 2021-07-30 07:00 | 2021-07-30 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 50.1 | 50.1 |  |  | 20.5 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101935112 | REGW OH TER2 | Pole | 2019-06-11 | 2019-08-30 | COMP | 2019-06-10 |  |  | 2019-07-31 | 2019-07-31 | [12 empty] | 2018-12-26 | 2019-12-31 | 2021-05-31 | 2021-05-31 | Q1 Work Plan | 2019-09-02 | SLO |  |  | 19898.61 | 28570.3 | 43.5 | 43.5 | 43.5 | 19863.8 |  | 19863.8 | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-02-18
South | LP |  | Templeton |  |  | OPEN | 115597364 | 5900 TEMPLETON RD PVTP | 35069216 |  |  | 5900 TEMPLETON RD PVTP | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.495 | -120.6441 |  | TIER 2 |  |  | HH3422 |  | Y | 311 |  |  | 2021-07-15 07:00 | 2021-07-15 16:00 | Reserved | CLICK | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101887267 | REGW FSRP OH TER2 | Pole | 2020-01-22 | 2021-01-20 | COMP | 2020-01-13 |  |  | 2019-03-20 | 2019-03-20 | [12 empty] | 2018-12-26 | 2019-12-31 | 2023-12-25 | 2023-12-25 | 2021 CBP Plan | 2020-01-13 | EEI |  |  | 11564.59 | 544.8 | 55.7 | [5 empty] | Electric Distribution | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116750910 | POLE_BROK_REPL - 1S/O R/O 1534 NOYES RD. | 35081731 |  |  | STS-POLE_BROK_REPL - 1S/O R/O 1534 NOYES | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1615 | -120.5822 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3513 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101910861 | RELW OH PRI CLR JPOL REMT NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116751421 | POLE_BROK_REPL - R/O 1578 NOYES RD.ARROY | 35081732 |  |  | STS-POLE_BROK_REPL - R/O 1578 NOYES RD.A | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1626 | -120.5855 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3513 | 10769 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101910874 | RELW OH PRI CLR JPOL REMT NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116751658 | POLE_DECA_REPL - R/O 1642 NOYES RD.ARROY | 35081733 |  |  | STS-POLE_DECA_REPL - R/O 1642 NOYES RD.A | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1645 | -120.5844 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3513 | 10769 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101910868 | RELW OH PRI ESTR CLR JPOL REMT GO REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116753874 | POLE_DECA_REPL - 2P W/O PRINTZ RD ON ALT | 35081736 |  |  | STS-POLE_DECA_REPL - 2P W/O PRINTZ RD ON | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 35.1386 | -120.5751 |  | TIER 2 | 766 | 18260-1104, OCEANO | QQ3504 | 9311 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 58.2 | 57.2 | 1 |  | 0 | 58.2 | 57.2 | 1 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101927252 | RELW OH PRI JPOL RESD ESTR BTKA FMOB FSRP PRTO TER2 | Pole | 2020-12-21 |  | COMP | 2020-12-21 |  |  | 2020-12-11 | 2020-12-11 | [12 empty] | 2019-03-18 | 2020-03-18 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 182601104 | 24203.6 | 1335 | 1294.7 | 454 | 454 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116754389 | POLE_DECA_REPL - 488 PRINTZ RD 2P E/0 RO | 35081737 |  |  | STS-POLE_DECA_REPL - 488 PRINTZ RD 2P E/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 35.1386 | -120.574 |  | TIER 2 | 766 | 18260-1104, OCEANO | QQ3504 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101884054 | RELW OH PRI JPOL RESD ESTR GO PRTO BTKA FMOB TER2 FSRP | Pole |  |  | REQD |  |  |  | 2020-12-11 | 2020-12-11 | [12 empty] | 2019-03-18 | 2020-03-18 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 182601104 | 1 | 80.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116754744 | POLE_DECA_REPL - F/O 157 CLARENCE AVE AR | 35081739 |  |  | STS-POLE_DECA_REPL - F/O 157 CLARENCE AV | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 35.126 | -120.5685 |  | TIER 2 | 766 | 18260-1104, OCEANO | QQ3510 | 64573 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101846533 | RELW OH PRI JPOL RESD ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116757679 | POLE_DECA_REPL - 573 ERHART RD.ARROYO GR | 35081762 |  |  | STS-POLE_DECA_REPL - 573 ERHART RD.ARROY | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.153 | -120.6046 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3420 | 3211 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101881885 | RELW OH PRI CLR RESD REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-18 | 2020-03-18 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116762087 | POLE_BROK_REPL - 1SE/O 1385 BADGER CYN. | 35081768 |  |  | STS-POLE_BROK_REPL - 1SE/O 1385 BADGER C | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 35.1554 | -120.5678 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3520 | 14013 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101852229 | RELW OH PRI CLR JPOL RESD REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | 1 | 494.1 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116762736 | POLE_BROK_REPL - 2S/O 1299 CORBEROSA DRA | 35215044 |  |  | STS-POLE_BROK_REPL - 2S/O 1299 CORBEROSA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 35.1513 | -120.566 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3616 | 5389 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101932902 | RELW OH PRI CLR RESD REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116763875 | POLE_BROK_REPL - 1SW/O R/O 1297 CORBEROS | 35081774 |  |  | STS-POLE_BROK_REPL - 1SW/O R/O 1297 CORB | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1513 | -120.5676 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3520 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101932903 | RELW OH PRI CLR REMT NOAC ESTR REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116764204 | POLE_BROK_REPL - R/O 1283 CORBEROSA DR.A | 35081775 |  |  | STS-POLE_BROK_REPL - R/O 1283 CORBEROSA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.151 | -120.5674 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3520 | 5389 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101852217 | RELW OH PRI CLR REMT FMOB NOAC ESTR USA TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116767183 | POLE_BROK_REPL - 1136 PHILLIPS RD. ARROY | 35081780 |  |  | STS-POLE_BROK_REPL - 1136 PHILLIPS RD. A | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1486 | -120.5713 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3520 | 5389 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101932913 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116767230 | POLE_DECA_REPL - 1N/O 1SW/O 1175B LA VID | 35081781 |  |  | STS-POLE_DECA_REPL - 1N/O 1SW/O 1175B LA | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1496 | -120.5709 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3520 | 5389 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101852207 | RELW OH SEC REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-19 | 2020-03-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116790349 | POLE_BROK_REPL - A/F 1575 VERDE CYN RD A | 35215155 |  |  | STS-POLE_BROK_REPL - A/F 1575 VERDE CYN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 35.1707 | -120.5645 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3606 | 4903 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101844658 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | 1 | 34.8 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116790354 | POLE_DECA_REPL - HOUSE 1575 VERDE CYN RD | 35215160 |  |  | STS-POLE_DECA_REPL - HOUSE 1575 VERDE CY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land JointPole |  |  | 35.171 | -120.5642 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3606 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101931477 | RELW OH SEC JPOL REMT ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116790494 | POLE_DECA_REPL - 1666 VERDE CYN RD-AT MB | 35215165 |  |  | STS-POLE_DECA_REPL - 1666 VERDE CYN RD-A | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.1708 | -120.5638 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3606 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101844652 | RELW OH PRI CLR JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116790665 | POLE_DECA_REPL - 1S/O 1666 VERDE CYN RDA | 35215175 |  |  | STS-POLE_DECA_REPL - 1S/O 1666 VERDE CYN | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1705 | -120.5639 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3606 | 4903 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101844653 | RELW OH PRI CLR JPOL ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116792691 | POLE_DECA_REPL - A/F C/O HWY 227/LONGHOR | 35202208 |  |  | STS-POLE_DECA_REPL - A/F C/O HWY 227/LON | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Enviro |  |  | 35.1443 | -120.5716 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3525 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 20.6 | 20.6 |  |  | 0 | 20.6 | 20.6 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101878899 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-22 |  | COMP | 2021-01-22 | [16 empty] | 2019-03-20 | 2020-03-20 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182601104 | 14566.42 | 8.8 | 0 | 326 | 326 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116794284 | POLE_BROK_REPL - CORBETT CYN RD C/O EAST | 35081784 |  |  | STS-POLE_BROK_REPL - CORBETT CYN RD C/O | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.1605 | -120.5578 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3612 | 9065 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101844713 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-20 | 2020-03-20 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 182601104 | 1 | 432.9 | 0 | 434.5 | 434.5 | 140.2 |  | 140.2 | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116802608 | POLE_DECA_REPL - 1W/O 1577 DALE AVEARROY | 35215244 |  |  | STS-POLE_DECA_REPL - 1W/O 1577 DALE AVEA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.0722 | -120.5349 |  | TIER 2 | 1090 | 18282-1101, MESA | RR3614 | 13041 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101888429 | RELW OH PRI CLR RESD REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182821101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116802821 | POLE_DECA_REPL - 1NE/O AF 312 APPLEGATE | 35215248 |  |  | STS-POLE_DECA_REPL - 1NE/O AF 312 APPLEG | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 35.0704 | -120.5364 |  | TIER 2 | 1090 | 18282-1101, MESA | RR3614 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101923832 | RELW OH PRI CLR REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182821101 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116803422 | POLE_DECA_REPL - R/O 272 APPLEGATE RD AR | 35215261 |  |  | STS-POLE_DECA_REPL - R/O 272 APPLEGATE R | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 35.0724 | -120.5364 |  | TIER 2 | 1090 | 18282-1101, MESA | RR3614 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101888428 | RELW OH PRI CLR RESD REMT NOAC ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182821101 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116804433 | POLE_DECA_REPL - 1R/O 1538 EWING RD ARRO | 35215284 |  |  | STS-POLE_DECA_REPL - 1R/O 1538 EWING RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 35.069 | -120.5344 |  | TIER 2 | 1330 | 18282-1103, MESA | RR3614 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101888425 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182821103 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116804713 | POLE_BROK_REPL - GP/O 1NW/O 2021 LOS BER | 35215305 |  |  | STS-POLE_BROK_REPL - GP/O 1NW/O 2021 LOS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land JointPole |  |  | 35.0834 | -120.5543 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3607 | 12033 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101888193 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116807400 | POLE_DECA_REPL - R/O 117 EL CAMPO ARROYO | 35215355 |  |  | STS-POLE_DECA_REPL - R/O 117 EL CAMPO AR | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land Enviro JointPole |  |  | 35.0911 | -120.5619 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3601 | 58417 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101888150 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | 1 | 43.7 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116810925 | POLE_DECA_REPL - 2/P/W/O/INTSCT MESA ALT | 35202290 |  |  | STS-POLE_DECA_REPL - 2/P/W/O/INTSCT MESA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land |  |  | 35.0784 | -120.5892 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3507 | 8611 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 45.3 | 45.3 |  |  | 0 | 45.3 | 45.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101887712 | RELW PRI OH CLR RESD REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-11-16 |  | COMP | 2020-11-16 | [16 empty] | 2019-03-22 | 2020-03-22 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182601102 | 20516.92 | 209.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116810933 | POLE_DECA_REPL - 4/P/S/O/INTST HWY 1 ON | 35215415 |  |  | STS-POLE_DECA_REPL - 4/P/S/O/INTST HWY 1 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land JointPole |  |  | 35.0708 | -120.5905 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3512 | 8047 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101911347 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116811126 | POLE_DECA_REPL - WOODLAND HILLS 3P/SE/O | 35215429 |  |  | STS-POLE_DECA_REPL - WOODLAND HILLS 3P/S | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 35.0709 | -120.5906 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3512 | 8047 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101887855 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116811222 | POLE_BROK_REPL - 1/P/S/O/2138 FERNDALE R | 35202295 |  |  | STS-POLE_BROK_REPL - 1/P/S/O/2138 FERNDA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 35.0746 | -120.5645 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3515 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101887935 | RELW OH PRI CLR JPOL REMT TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2020-11-09 | 2020-11-09 | [12 empty] | 2019-03-22 | 2020-03-22 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182601102 | 1 | 44.5 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116811678 | POLE_DECA_REPL - R/O 362 APACHE TRAIL AR | 35202308 |  |  | STS-POLE_DECA_REPL - R/O 362 APACHE TRAI | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Land |  |  | 35.0639 | -120.5288 |  | TIER 2 | 1330 | 18282-1103, MESA | RR3620 | 15361 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.9 | 36.9 |  |  | 0 | 36.9 | 36.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101888581 | RELW OH PRI JPOL REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-11-24 |  | COMP | 2020-11-24 | [16 empty] | 2019-03-22 | 2020-03-22 | 2020-10-26 | 2020-10-26 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182821103 | 18099.48 | 349.2 | -226.3 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116811879 | POLE_DECA_REPL - 2171 FERNDALE RD. ARROY | 35215459 |  |  | STS-POLE_DECA_REPL - 2171 FERNDALE RD. A | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land JointPole |  |  | 35.0743 | -120.5667 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3515 | 29709 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101887932 | RELW OH PRI JPOL REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116812912 | POLE_DECA_REPL - 3/P/N/O/INTSCT HWY 1/HA | 35215474 |  |  | STS-POLE_DECA_REPL - 3/P/N/O/INTSCT HWY | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.0818 | -120.5859 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3507 | V50 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101923049 | RELW OH PRI CLR PUBL FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116813374 | POLE_DECA_REPL - SP/O 7SW/O 1116 POMEROY | 35081527 |  |  | REPL POLE-1116 POMEROY RD, ARROYO GRANDE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.0545 | -120.5349 |  | TIER 2 | 1330 | 18282-1103, MESA | RR3624 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50.1 | 50.1 |  |  | 0 | 50.1 | 50.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101924974 | RELW ESTR OH SERV REMT BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2019-09-18 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-01-31 | SLO |  | 182821103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116814183 | POLE_BROK_REPL - 1/P/W/O 417 ALOMA WAYAR | 35215499 |  |  | STS-POLE_BROK_REPL - 1/P/W/O 417 ALOMA W | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.0775 | -120.5658 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3510 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101887839 | RELW OH PRI CLR REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116814375 | POLE_DECA_REPL - 1/P/S/O/275 EL CAMPO RD | 35215505 |  |  | STS-POLE_DECA_REPL - 1/P/S/O/275 EL CAMP | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.0812 | -120.5706 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3510 | 3815 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101887808 | RELW OH PRI JPOL PUBL FLAG ESTR PRTO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116814584 | POLE_DECA_REPL - 1/P/S/1/P/E/O/275 EL CA | 35215515 |  |  |  | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 35.0811 | -120.5706 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3510 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101887816 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116814695 | POLE_DECA_REPL - 1/P/E/O 417 ALOMA WAY A | 35215540 |  |  | STS-POLE_DECA_REPL - 1/P/E/O 417 ALOMA W | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 35.0767 | -120.5649 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3510 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101887841 | RELW OH PRI CLR REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116814701 | POLE_DECA_REPL - 1/P/S/2/P/E/O/275 EL CA | 35215546 |  |  | STS-POLE_DECA_REPL - 1/P/S/2/P/E/O/275 E | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land JointPole |  |  | 35.0806 | -120.57 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3510 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101926947 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | 1 | 34.8 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116815643 | POLE_BROK_REPL - 2/P/E/O/C/O/EL CAMPO RD | 35214477 |  |  | STS-POLE_BROK_REPL - 2/P/E/O/C/O/EL CAMP | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 35.083 | -120.5648 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3510 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101887831 | RELW OH PRI CLR REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116815728 | POLE_BROK_REPL - 1/P/S/3/P/E/O/A/F/269 E | 35214561 |  |  | STS-POLE_BROK_REPL - 1/P/S/3/P/E/O/A/F/2 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 35.0851 | -120.5638 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3606 | 3815 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101887834 | OH PRI CLR REMT ESTR GO BTKA USA PROG FMOB FSRP RELW TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-03-22 | 2020-03-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116816421 | POLE_DECA_REPL - 100 S/O 631 ARROYO AVE | 35214563 |  |  | STS-POLE_DECA_REPL - 100 S/O 631 ARROYO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1157 | -120.5738 |  | TIER 2 | 766 | 18260-1104, OCEANO | QQ3514 | 9323 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101847261 | OH RELW PRI REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116817273 | POLE_BROK_REPL - A/F 620 SPRING CANYON L | 35214569 |  |  | STS-POLE_BROK_REPL - A/F 620 SPRING CANY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 35.0954 | -120.5021 |  | TIER 2 | 1090 | 18282-1101, MESA | RR3703 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101910474 | RELW OH PRI CLR RESD REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182821101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116818422 | POLE_DECA_REPL - R/O 550 UPPER LOS BERRO | 35214585 |  |  | STS-POLE_DECA_REPL - R/O 550 UPPER LOS B | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.0899 | -120.5091 |  | TIER 2 | 1090 | 18282-1101, MESA | RR3703 | 1391 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101937967 | OH PRI CLR JPOL REMT FMOB RELW ESTR BTKA TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-23 | 2020-03-23 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182821101 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116820157 | POLE_DECA_REPL - 440 CORBETT CYN RD ARRO | 35214616 |  |  | STS-POLE_DECA_REPL - 440 CORBETT CYN RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 35.1409 | -120.5643 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3621 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101844679 | RELW JPOL OH PRI CLR RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | 1 | 55.6 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116821556 | POLE_DECA_REPL - HOUSE 306 HONDONADA RDA | 35214655 |  |  | STS-POLE_DECA_REPL - HOUSE 306 HONDONADA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 35.1514 | -120.5494 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3618 | 4159 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101844797 | RELW OH PRI CLR JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116821925 | POLE_BROK_REPL - 1E/O 482 CORRALITOS RD | 35214677 |  |  | STS-POLE_BROK_REPL - 1E/O 482 CORRALITOS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 35.1641 | -120.5427 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3613 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101910899 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116822693 | POLE_BROK_REPL - 2E/O 482 CORRALITOS RD | 35214697 |  |  | STS-POLE_BROK_REPL - 2E/O 482 CORRALITOS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 35.1642 | -120.5418 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3614 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101910900 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116822811 | POLE_DECA_REPL - HOUSE 437 CORRALITOS RD | 35214708 |  |  | STS-POLE_DECA_REPL - HOUSE 437 CORRALITO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1608 | -120.543 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3613 | 4545 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101910919 | RELW OH PRI CLR JPOL REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | 1 | 46.7 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116823389 | POLE_DECA_REPL - R/O 468 HANSEN HILL RD | 35214733 |  |  | STS-POLE_DECA_REPL - R/O 468 HANSEN HILL | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.149 | -120.5523 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3617 | 9403 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101931444 | RELW OH PRI CLR JPOL REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-24 | 2020-03-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116824481 | POLE_DECA_REPL - R/O 198 COUNTRY HILLS R | 35214756 |  |  | STS-POLE_DECA_REPL - R/O 198 COUNTRY HIL | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 35.1379 | -120.5544 |  | TIER 2 | 766 | 18260-1104, OCEANO | QQ3602 | 2861 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101853087 | RELW OH PRI JPOL RESD FMOB ESTR REAR PROG TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-25 | 2020-03-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116824602 | POLE_DECA_REPL - 1W/O 270 COUNTRY HILLS | 35214761 |  |  | STS-POLE_DECA_REPL - 1W/O 270 COUNTRY HI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 35.1389 | -120.5551 |  | TIER 2 | 766 | 18260-1104, OCEANO | QQ3602 | 2861 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101931427 | RELW OH PRI RESD ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-25 | 2020-03-25 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117027579 | POLE_DECA_REPL - 11355 BOBCAT-LN 4/P/E/2 | 35093620 |  |  | STS-POLE_DECA_REPL - 11355 BOBCAT-LN 4/P | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1044 | -120.3695 |  | TIER 2 | 625 | 18267-1108, SANTA MARIA | QQ41 | 4931 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101879051 | RELW OH PRI JPOL REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-14 | 2019-10-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | SLO |  | 182671108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117027582 | POLE_DECA_REPL - 11355 BOBCAT-LN 4/P/E/2 | 35093621 |  |  | STS-POLE_DECA_REPL - 11355 BOBCAT-LN 4/P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1045 | -120.3697 |  | TIER 2 | 625 | 18267-1108, SANTA MARIA | QQ41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101934207 | RELW OH SEC REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-14 | 2019-10-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | SLO |  | 182671108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117029944 | POLE_DECA_REPL - 11355 BOBCAT-LN 4/P/E/O | 35087725 |  |  | STS-POLE_DECA_REPL - 11355 BOBCAT-LN 4/P | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1035 | -120.3703 |  | TIER 2 | 625 | 18267-1108, SANTA MARIA | QQ41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101879049 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-14 | 2019-09-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | SLO |  | 182671108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117030472 | POLE_DECA_REPL - PARADISE DR C/O BRANCH | 35215001 |  |  | STS-POLE_DECA_REPL - PARADISE DR C/O BRA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 35.1463 | -120.5296 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3625 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101926186 | RELW OH PRI CLR JPOL REMT TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117030785 | POLE_DECA_REPL - 1NW/O 461 HANSON HILL R | 35215007 |  |  | STS-POLE_DECA_REPL - 1NW/O 461 HANSON HI | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 35.1479 | -120.554 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3622 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101844766 | RELW OH PRI JPOL REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117031231 | POLE_BROK_REPL - 3N/O 461 HANSON HILL RD | 35215016 |  |  | STS-POLE_BROK_REPL - 3N/O 461 HANSON HIL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1484 | -120.5549 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3617 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101844749 | RELW OH PRI JPOL REMT NOAC ESTR GO REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117032797 | POLE_DECA_REPL - R/O 2710 BRANCH MILL RD | 35215022 |  |  | STS-POLE_DECA_REPL - R/O 2710 BRANCH MIL | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.1462 | -120.5289 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3625 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101845008 | RELW OH PRI CLR REMT NOAC PRTO ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | 1 | 73 | 64.1 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117033623 | POLE_DECA_REPL - 3031 LOPEZ DR 4PE\O MB | 35215042 |  |  | STS-POLE_DECA_REPL - 3031 LOPEZ DR 4PE\O | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 35.1785 | -120.5204 |  | TIER 2 | 859 | 18263-1104, SAN LUIS OBISPO | PP3701 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101846618 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD |  |  |  | 2021-02-01 | 2021-02-01 | [12 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182631104 | 1 | 64.4 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117033908 | POLE_BROK_REPL - 3031 LOPEZ DR 1\P\S\3\W | 35215047 |  |  | STS-POLE_BROK_REPL - 3031 LOPEZ DR 1\P\S | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.1754 | -120.526 |  | TIER 2 | 859 | 18263-1104, SAN LUIS OBISPO | PP3706 | 5383 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101846634 | RELW OH PRI REMT TRAF FLAG ESTR BTKA USA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182631104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117035231 | POLE_DECA_REPL - 3685 LOPEZ DR 3/P/W/O M | 35215073 |  |  | STS-POLE_DECA_REPL - 3685 LOPEZ DR 3/P/W | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit Land |  |  | 35.1814 | -120.5145 |  | TIER 2 | 859 | 18263-1104, SAN LUIS OBISPO | PP3702 | 15633 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101925880 | RELW OH PRI JPOL PUBL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182631104 | 1 | 35.2 | 35.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117035299 | POLE_DECA_REPL - 3689 ALISOS RD 1/P/N\O | 35215077 |  |  | STS-POLE_DECA_REPL - 3689 ALISOS RD 1/P/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1446 | -120.5184 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3722 | 9413 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101932931 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | 1 | 34.8 | 34.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117035518 | POLE_DECA_REPL - R/O 12151 HUASNA RD RUS | 35215082 |  |  | STS-POLE_DECA_REPL - R/O 12151 HUASNA RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land JointPole |  |  | 35.0971 | -120.3622 |  | TIER 2 | 625 | 18267-1108, SANTA MARIA | RR41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101924961 | RELW OH PRI PGEA CLR RESD FIRE ESTR BTKA RTRN USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182671108 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117035519 | POLE_DECA_REPL - 2PS/2PE/O 8661 HUASNA R | 35215087 |  |  | STS-POLE_DECA_REPL - 2PS/2PE/O 8661 HUAS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.0943 | -120.3639 |  | TIER 2 | 625 | 18267-1108, SANTA MARIA | RR41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101861304 | RELW OH PRI PGEA CLR RESD FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182671108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117035525 | POLE_BROK_REPL - 1PS/O 12151 HUASNA RD R | 35215092 |  |  | STS-POLE_BROK_REPL - 1PS/O 12151 HUASNA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro JointPole |  |  | 35.0964 | -120.362 |  | TIER 2 | 625 | 18267-1108, SANTA MARIA | RR41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101861311 | RELW OH PRI PGEA CLR RESD FIRE TER2 ESTR BTKA FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182671108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117035532 | POLE_DECA_REPL - 794 MANUELA WAYARROYO G | 35215097 |  |  | STS-POLE_DECA_REPL - 794 MANUELA WAYARRO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land JointPole |  |  | 35.1557 | -120.5215 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3716 | 2229 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101846673 | RELW PRI OH JPOL RESD REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117035550 | POLE_BROK_REPL - 2PS/1PE/O 8661 HUASNA R | 35215102 |  |  | STS-POLE_BROK_REPL - 2PS/1PE/O 8661 HUAS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 35.0942 | -120.3645 |  | TIER 2 | 625 | 18267-1108, SANTA MARIA | RR41 | 10627 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101861303 | RELW OH PRI PGEA CLR RESD FIRE ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-20 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182671108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117035551 | POLE_DECA_REPL - 1PS/1PE/O 6801 HUASNA R | 35215108 |  |  | STS-POLE_DECA_REPL - 1PS/1PE/O 6801 HUAS | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.094 | -120.366 |  | TIER 2 | 625 | 18267-1108, SANTA MARIA | RR41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101861300 | RELW OH PRI PGEA CLR RESD BTKA FIRE ESTR RTRN FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182671108 | 1 | 26.2 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117035566 | POLE_DECA_REPL - 3715 ALISOS RD 7\P\N\1\ | 35215113 |  |  | STS-POLE_DECA_REPL - 3715 ALISOS RD 7\P\ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.151 | -120.5076 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP37 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101846724 | RELW OH PRI CLR REMT FMOB ESTR BTKA USA TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2020-04-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117106444 | POLE_DECA_REPL - A/F 155 MOORE LN. ARROY | 35214829 |  |  | STS-POLE_DECA_REPL - A/F 155 MOORE LN. A | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1531 | -120.5941 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3517 | 9297 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101911363 | RELW OH PRI PGEA CLR REMT FIRE ESTR GO BTKA OTHR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-26 | 2020-04-26 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117219080 | POLE_DECA_REPL - 12701 HUASNA RD 26/P/NW | 35214777 |  |  | STS-POLE_DECA_REPL - 12701 HUASNA RD 26/ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land Enviro |  |  | 35.1714 | -120.3607 |  | TIER 2 | 625 | 18267-1108, SANTA MARIA | PP41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101879169 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-12 | 2020-05-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182671108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117292601 | POLE_DECA_REPL - 2N/O 2009 HUASNA RD ARR | 35215493 |  |  | STS-POLE_DECA_REPL - 2N/O 2009 HUASNA RD | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1413 | -120.5466 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3623 | 5565 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101911241 | RELW OH PRI REMT NOAC SWRK ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-21 | 2020-05-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601104 | 1 | 17.7 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117299281 | POLE_BROK_REPL - 1SW/O A/T HOUSE 2000 CO | 35215578 |  |  | STS-POLE_BROK_REPL - 1SW/O A/T HOUSE 200 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1865 | -120.5756 |  | TIER 2 | 859 | 18263-1104, SAN LUIS OBISPO | OO35 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101846048 | RELW OH PRI REMT NOAC ESTR FMOB PRTO FSRP TER2 | Pole |  |  | REQD | [17 empty] | 2019-05-22 | 2020-05-22 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182631104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117315381 | POLE_DECA_REPL - 93420 ARROYO GRANDE | 35215656 |  |  |  | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 35.2188 | -120.3724 |  | TIER 2 | 859 | 18263-1104, SAN LUIS OBISPO | OO41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103771527 | RELW OH PRI CLR REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-24 | 2020-05-24 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182631104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | Arroyo Grande | San Luis Obispo |  |  | OPEN | 117690197 | POLE _ BROK _ REPL_1NE/O 511 ERHARDT RD. | 35216314 |  |  | STS-POLE _ BROK _ REPL_1NE/O 511 ERHARDT | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1514 | -120.6053 |  | TIER 2 |  |  | PP3420 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101930969 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG | [11 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | Arroyo Grande | San Luis Obispo |  |  | OPEN | 117694011 | POLE_BROK_REPL - 1N/O 2856 BRANCH MILL R | 35216370 |  |  |  | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.1524 | -120.5283 |  | TIER 2 |  |  | PP3620 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101911236 | RELW OH PRI ESTR GO RTRN TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-08-01 | 2020-08-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG | [11 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | Arroyo Grande | San Luis Obispo |  |  | OPEN | 118156168 | POLE_BROK_REPL - 14/P/N/4/P/W/O 1900 WIL | 35215712 |  |  | STS-POLE_BROK_REPL - 14/P/N/4/P/W/O 1900 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 35.0583 | -120.5654 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3525 | 10681 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101888118 | RELW OH PRI ESTR BTKA FSRP PRTO FMOB TER2 | Pole |  |  | REQD | [17 empty] | 2019-11-09 | 2020-11-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | Arroyo Grande | San Luis Obispo |  |  | OPEN | 118156362 | POLE_BROK_REPL - 5975 DEER CRK RD 13/P/S | 35215715 |  |  | STS-POLE_BROK_REPL - 5975 DEER CRK RD 13 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.0998 | -120.363 |  | TIER 2 | 625 | 18267-1108, SANTA MARIA | QQ41 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101934200 | FMOB RELW OH PRI CLR ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-11-09 | 2020-11-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182671108 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | Arroyo Grande | San Luis Obispo |  |  | OPEN | 118164133 | POLE_DECA_REPL - 5975 DEER CRK RD 8/P/S/ | 35215718 |  |  | STS-POLE_DECA_REPL - 5975 DEER CRK RD 8/ | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.103 | -120.3637 |  | TIER 2 | 625 | 18267-1108, SANTA MARIA | QQ41 | 2167 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101934197 | RELW OH PRI CLR ESTR FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-11-12 | 2020-11-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182671108 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116750744 | POLE_BROK_REPL - 1570 OLD OAK PARK RD. A | 35081725 |  |  | STS-POLE_BROK_REPL - 1570 OLD OAK PARK R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.1584 | -120.5968 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3511 | 9247 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.3 | 39.3 |  |  | 0 | 39.3 | 39.3 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101910788 | RELW OH PRI JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-20 | 2021-01-21 | COMP | 2019-12-03 |  |  | 2021-01-20 | 2021-01-20 | [12 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-30 | CALENG |  | 182601104 | 23496.88 | 145.6 | 59.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116750766 | POLE_BROK_REPL - 2E/O 1530 NOYES RD.[MB] | 35081726 |  |  | STS-POLE_BROK_REPL - 2E/O 1530 NOYES RD. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.1608 | -120.5849 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3513 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.6 | 16.6 |  |  | 0 | 16.6 | 16.6 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101929709 | RELW OH PRI CLR JPOL REMT ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2019-12-03 | 2021-01-28 | COMP | 2019-12-03 |  |  | 2021-01-28 | 2021-01-28 | [12 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-30 | CALENG |  | 182601104 | 9955.93 | 41.8 | 41.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116750775 | POLE_BROK_REPL - 285 E. ORMONDE RD. ARRO | 35081727 |  |  | STS-POLE_BROK_REPL - 285 E. ORMONDE RD. | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.1648 | -120.59 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3512 | 9251 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 63.9 | 62.8 | 1.1 |  | 0 | 63.9 | 62.8 | 1.1 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101910840 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2019-12-03 | 2021-01-28 | COMP | 2019-12-03 |  |  | 2021-01-28 | 2021-01-28 | [12 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-30 | CALENG |  | 182601104 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116750785 | POLE_BURN_REPL - 1S/O 358 E. ORMONDE RD. | 35081728 |  |  | STS-POLE_BURN_REPL - 1S/O 358 E. ORMONDE | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.1605 | -120.5887 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3512 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 13.3 | 13.3 |  |  | 0 | 13.3 | 13.3 |  |  | EC | E | Pole | Burnt | Replace |  | 101929697 | RELW OH PRI RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-02-19 | 2021-01-28 | COMP | 2020-02-19 |  |  | 2021-01-28 | 2021-01-28 | [12 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-30 | CALENG |  | 182601104 | 5199.25 | 41.8 | 41.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116752063 | POLE_BROK_REPL - 1S/O 235 PACIFIC PINE D | 35081735 |  |  | STS-POLE_BROK_REPL - 1S/O 235 PACIFIC PI | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.1658 | -120.598 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3506 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 19.2 | 19.2 |  |  | 0 | 19.2 | 19.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101932235 | RELW OH PRI CLR JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2019-12-03 | 2021-01-28 | COMP | 2019-12-03 |  |  | 2021-01-28 | 2021-01-28 | [12 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2019-11-30 | CALENG |  | 182601104 | 11953.27 | 41.8 | 41.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116762014 | POLE_BROK_REPL - R/O 965 NOYES RD. ARROY | 35081767 |  |  |  | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.147 | -120.5919 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3522 | Q08 | Y | 311 |  |  | 2021-03-22 07:00 | 2021-03-22 16:00 | Scheduled | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 25.8 | 25 | 0.8 |  | 0 | 25.8 | 25 | 0.8 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101928252 | RELW OH PRI CLR REMT FMOB ESTR REAR TER2 PRTO FSRP | Pole | 2020-11-16 | 2021-01-04 | COMP | 2020-11-16 | [16 empty] | 2019-03-19 | 2020-03-19 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 182601104 | 22125.42 | 182.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116802654 | POLE_DECA_REPL - 2N/O 2NW/O 110 GUS WAY | 35202217 |  |  | STS-POLE_DECA_REPL - 2N/O 2NW/O 110 GUS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.0844 | -120.5562 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3606 | 9589 | Y | 311 |  |  | 2021-06-15 07:00 | 2021-06-15 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101888176 | RELW REMT OH PRI ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-12 | 2020-12-15 | COMP | 2020-12-04 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-10-18 | 2020-10-18 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182601102 | 27229.06 | 312.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116804506 | POLE_BROK_REPL - 275 PHELAN RANCH RDARRO | 35215289 |  |  | STS-POLE_BROK_REPL - 275 PHELAN RANCH RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 35.0835 | -120.5591 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3606 |  | Y | 311 |  |  | 2021-06-15 07:00 | 2021-06-15 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101888170 | CLR OH PRI RELW REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116804648 | POLE_DECA_REPL - 1SE/O 210 PHELAN RANCH | 35215294 |  |  | STS-POLE_DECA_REPL - 1SE/O 210 PHELAN RA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land Enviro |  |  | 35.0841 | -120.5585 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3606 |  | Y | 311 |  |  | 2021-06-15 07:00 | 2021-06-15 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101941107 | RELW OH PRI CLR REMT NOAC ESTR GO BTKA REAR USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116814056 | POLE_DECA_REPL - 1/P/W/1/P/N/O 2420 GREE | 35202328 |  |  | STS-POLE_DECA_REPL - 1/P/W/1/P/N/O 2420 | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.0832 | -120.5748 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3509 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 17.3 | 17.3 |  |  | 0 | 17.3 | 17.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101926949 | RELW REMT OH PRI CLR ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole | 2021-01-19 | 2021-01-21 | COMP | 2020-12-01 | [16 empty] | 2019-03-22 | 2020-03-22 | 2020-10-15 | 2020-10-15 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 182601102 | 8273.57 | 61.9 | -435.1 | -362 | -362 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117031243 | POLE_DECA_REPL - 191 APPY WAY ARROYO GRA | 35202239 |  |  | STS-POLE_DECA_REPL - 191 APPY WAY ARROYO | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.1403 | -120.5502 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3622 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 16.2 | 16.2 |  |  | 0 | 16.2 | 16.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101844859 | OH PRI JPOL REMT FLAG ESTR FMOB TER2 PRTO FSRP RELW | Pole | 2020-11-30 | 2021-01-22 | COMP | 2020-11-30 |  |  | 2020-11-05 | 2020-11-05 | [12 empty] | 2019-04-15 | 2020-04-15 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182601104 | 7074.81 |  | -633.5 | -90.5 | -90.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | COMP | 116804565 | POLE_BROK_REPL - R/O 300 PHELAN RANCH RD | 35202238 |  |  | +STS-POLE_BROK_REPL- R/O 300 PHELAN RANC | MAPP | MAPP SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 35.0837 | -120.5589 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3606 | 9589 | Y | 311 |  |  |  |  | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 50.8 | 50.8 |  |  | 42 | 0.8 | 0.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101888169 | RELW OH PRI COMP CLR REMT ESTR BTKA REAR CPGG FMOB TER2 PRTO FSRP | Pole | 2020-11-16 | 2020-11-16 | COMP | 2020-11-16 | COMP | 2021-02-15 | [13 empty] | 2021-02-17 | 2021-02-15 | 2020-03-21 | 2020-10-18 | 2020-10-18 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182601102 | 21546.01 | 6349.1 | 5633.8 | 1892.5 | 1892.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | COMP | 116810016 | POLE_DECA_REPL - 1R/O 535 STANTON RDARRO | 35202275 |  |  | +STS-POLE_DECA_REPL - 1R/O 535 STANTON R | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 35.0668 | -120.5549 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3617 |  | Y | 311 |  |  | 2021-01-15 | 2021-01-15 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 50 | 50 |  |  | 30 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101888487 | RELW OH PRI COMP REMT ESTR BTKA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-11-18 | 2020-11-18 | COMP | 2020-11-18 | COMP | 2021-01-15 | [13 empty] | 2021-01-19 | 2021-01-15 | 2020-03-22 | 2020-10-26 | 2020-10-26 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182601102 | 8726.22 | 9225.8 | 9044.9 | 9044.9 | 9044.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116751875 | POLE_BROK_REPL - 1414/PASEO LADERA LN A/ | 35081734 |  |  | +STS-POLE_BROK_REPL- 1414/PASEO LADERA L | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.1545 | -120.6087 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3420 |  | Y | 311 |  |  | 2021-07-30 07:00 | 2021-07-30 16:00 | Dispatched | CLICK | [6 empty] | 51.8 | 51.8 |  |  | 0 | 51.8 | 51.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101927776 | RELW OH PRI PGEA CLR RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2019-12-19 | 2019-12-19 | COMP | 2019-12-18 |  |  | 2019-11-21 | 2019-11-21 | [12 empty] | 2019-03-17 | 2020-03-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | Concord |  | 182601104 | 14455.69 | 1572.6 | 1402.8 | 735.4 | 735.4 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116766786 | POLE_DECA_REPL - 3S/O 562 WINDERMERE LN. | 35081778 |  |  | +STS-POLE_DECA_REPL- 3S/O 562 WINDERMERE | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.142 | -120.5842 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3523 | 13065 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Dispatched | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101878811 | RELW OH PRI CLR JPOL RESD ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-11-10 | 2020-11-10 | COMP | 2020-11-10 | [16 empty] | 2019-03-19 | 2020-03-19 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 182601104 | 21878.16 | 2742.1 | 2697.6 | 2703.9 | 2703.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116767105 | POLE_DECA_REPL - 2S/O 562 WINDERMERE LN. | 35081779 |  |  | +STS-POLE_DECA_REPL- 2S/O 562 WINDERMERE | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.1424 | -120.585 |  | TIER 2 | 766 | 18260-1104, OCEANO | PP3523 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Dispatched | CLICK | [6 empty] | 51.7 | 51.7 |  |  | 0 | 51.7 | 51.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101878810 | RELW OH ESTR PRI JPOL RESD BTKA FMOB TER2 PRTO FSRP | Pole | 2020-11-16 | 2020-11-16 | COMP | 2020-11-16 | [16 empty] | 2019-03-19 | 2020-03-19 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 182601104 | 12645.47 | 1467 | 673.8 | 538 | 538 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116802647 | POLE_BROK_REPL - 1N/O 2NW/O 110 GUS WAY | 35202214 |  |  | +STS-POLE_BROK_REPL- 1N/O 2NW/O 110 GUS | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.0838 | -120.5567 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3606 |  | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Scheduled | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101888175 | PRI RELW OH REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-01 | 2020-12-01 | COMP | 2020-12-01 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-10-18 | 2020-10-18 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182601102 | 7363.76 | 950 | 159.3 | 346.6 | 346.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116803734 | POLE_DECA_REPL - 2NE/O R/O 455 RODS RD A | 35202232 |  |  | STS-POLE_DECA_REPL - 2NE/O R/O 455 RODS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.0735 | -120.5612 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3611 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 22.3 | 22.3 |  |  | 0 | 22.3 | 22.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101888324 | RELW OH PRI ESTR PGEA CLR RESD BTKA OTHR FMOB TER2 FSRP | Pole | 2020-12-07 | 2021-01-28 | COMP | 2020-12-07 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182601102 | 11371.81 | 89.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116804277 | POLE_BROK_REPL - 2SE/O R/O 231 MADERO CT | 35215276 |  |  | STS-POLE_BROK_REPL - 2SE/O R/O 231 MADER | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.0852 | -120.5602 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3601 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101888146 | RELW OH PRI REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-03-21 | 2020-03-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182601102 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116804768 | POLE_DECA_REPL - 1SW/O 275 PHELAN RANCH | 35202241 |  |  | +STS-POLE_DECA_REPL- 1SW/O 275 PHELAN RA | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.0827 | -120.5601 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3606 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Dispatched | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101941106 | RELW OH NOAC PRI CLR REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-03 | 2020-12-03 | COMP | 2020-12-02 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-10-18 | 2020-10-18 | 2021 CBP Plan | 2021-02-28 | CALENG |  | 182601102 | 5733.82 | 950.1 | -220.9 | 328.5 | 328.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 116806965 | POLE_DECA_REPL - 2N/O 2086 HALCYON RDARR | 35202271 |  |  | +STS-POLE_DECA_REPL- 2N/O 2086 HALCYON R | CONS | CONS SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.0701 | -120.5617 |  | TIER 2 |  |  | RR3611 |  | Y | 311 |  |  | 2021-05-31 07:00 | 2021-05-31 16:00 | Dispatched | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101926114 | RELW OH SEC PGEA REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-11-23 | 2020-11-23 | COMP | 2020-11-23 | [16 empty] | 2019-03-21 | 2020-03-21 | 2020-07-25 | 2020-07-25 | 2021 CBP Plan | 2021-01-31 | CALENG |  |  | 12212.66 | 563 | 247 | 250.8 | 250.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ARROYO GRANDE | San Luis Obispo |  |  | OPEN | 117301556 | POLE_BURN_REPL - 2S/O 715 APPLEGATE RDAR | 35202954 |  |  | +STS-POLE_BURN_REPL - 2S/O 715 APPLEGATE | UNSC | UNSC SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.0591 | -120.5419 |  | TIER 2 | 2828 | 18260-1102, OCEANO | RR3618 |  | Y | 311 |  |  | 2021-04-30 07:00 | 2021-04-30 16:00 | Scheduled | CLICK | [6 empty] | 50.8 | 50.8 |  |  | 0 | 50.8 | 50.8 |  |  | EC | E | Pole | Burnt | Replace |  | 101888506 | OH RELW PRI CLR REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2020-11-24 | 2020-11-24 | COMP | 2020-11-24 | [16 empty] | 2019-05-22 | 2019-10-22 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182601102 | 16259.97 | 2397.3 | 1990.6 | 509.5 | 509.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117071955 | POLE_DECA_REPL - 1/P/E/O 3536 BLACKHAWK | 35209625 |  |  |  | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 35.5207 | -120.6516 |  | TIER 2 | 387 | 18305-2113, TEMPLETON | HH3411 | 3933 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101887096 | RELW OH PRI CLR RESD REMT ESTR BTKA REAR PROG FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-21 | 2020-04-21 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052113 | 1 | 10.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117103936 | POLE_BROK_REPL - 13608 PALO VERDE RD 2/P | 35140799 |  |  | STS-POLE_BROK_REPL - 13608 PALO VERDE RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 35.4463 | -120.708 |  | TIER 2 | 449 | 18254-1103, ATASCADERO | JJ3203 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 15.2 | 15.2 |  |  | 0.5 | 14.7 | 14.7 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101848119 | RELW OH PRI PGEA REMT TRAF ESTR BTKA FMOB TER2 PRTO | Pole | 2021-02-05 |  | COMP | 2021-02-05 | [16 empty] | 2019-04-26 | 2020-04-26 |  | 2020-04-26 | 2021 CBP Plan | 2020-10-31 | QUES |  | 182541103 | 7381.65 | 611.3 | 266.5 |  |  | 344.9 |  | 344.9 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117104441 | POLE_DECA_REPL - 9961 SANTA CLARA RD 1/P | 35099992 |  |  | STS-POLE_DECA_REPL - 9961 SANTA CLARA RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.4441 | -120.6071 |  | TIER 2 | 387 | 18305-2113, TEMPLETON | JJ3501 | 4059 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101942106 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-26 | 2019-10-12 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-02-28 | EEI |  | 183052113 | 1 | 80.7 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117104988 | POLE_DECA_REPL - 13503 CHISPA RD 2/P/N A | 35099993 |  |  | STS-POLE_DECA_REPL - 14155 CHISPA ROAD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.4431 | -120.6058 |  | TIER 2 | 387 | 18305-2113, TEMPLETON | JJ3501 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101942096 | RELW OH PRI CLR REMT TER2 ESTR BTKA FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-26 | 2019-10-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052113 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117106258 | POLE_BROK_REPL - 1NE/O 7055 SANTA BARBAR | 35140801 |  |  | STS-POLE_BROK_REPL - 1NE/O 7055 SANTA BA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-08-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.4346 | -120.6461 |  | TIER 2 | 449 | 18254-1103, ATASCADERO | JJ34 |  | Y | 311 |  |  |  |  | Reserved | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101890202 | RELW OH PRI CLR REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-26 | 2020-04-26 | 2024-04-24 | 2024-04-24 | 2021 CBP Plan | 2020-10-31 | QUES |  | 182541103 | 1 | 266.5 | 266.5 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117113624 | POLE_DECA_REPL - N/O 15805 CHISPA RD 3/P | 35208782 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 35.4297 | -120.5999 |  | TIER 2 | 387 | 18305-2113, TEMPLETON | JJ3512 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.9 | 18.9 |  |  | 0 | 18.9 | 18.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101889627 | RELW OH PRI JPOL REMT ESTR GO REAR FMOB TER2 PRTO FSRP | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2019-04-28 | 2020-04-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052113 | 7973.71 | 28 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117114478 | POLE_DECA_REPL - 3650 MARICOPA RD. ATASC | 35098432 |  |  | STS-POLE_DECA_REPL - 3650 MARICOPA RD.AT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.4945 | -120.6899 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3321 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101887474 | RELW OH PRI JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-28 | 2019-10-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117115561 | POLE_DECA_REPL - 2/P/S/E/O/4/P/N/E/O 312 | 35208790 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land Enviro |  |  | 35.5011 | -120.6893 |  | TIER 2 | 874 | 18305-2108, TEMPLETON | HH3321 | 7729 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.2 | 57.2 |  |  | 0 | 57.2 | 57.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101887449 | RELW OH PRI REMT NOAC SWRK ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2019-04-28 | 2020-04-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052108 | 27036.28 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117116322 | POLE_DECA_REPL - 8888 ROCKY CNYN RD 1P/S | 35098433 |  |  | STS-POLE_DECA_REPL - 8888 ROCKY CNYN RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.4778 | -120.6275 |  | TIER 2 | 387 | 18305-2113, TEMPLETON | II3409 | 30661 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101895912 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-28 | 2019-10-05 | 2020-10-15 | 2020-10-15 | 2021 CBP Plan | 2021-02-28 | EEI |  | 183052113 | 1 | 161.4 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117118519 | POLE_DECA_REPL - 1/P/E/O/7644 DEL RIO RD | 35098437 |  |  | STS-POLE_DECA_REPL - 1/P/E/O/7644 DEL RI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.5127 | -120.7147 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3213 | 30563 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891486 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2019-10-29 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | EEI |  | 183052111 | 1 | 40.4 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117119252 | POLE_DECA_REPL - 2/P/S/E/O/6605 SANTA CR | 35140805 |  |  | STS-POLE_DECA_REPL - 2/P/S/E/O/6605 SANT | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.5206 | -120.7099 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3208 | 6023 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891667 | RELW OH PRI INSP CLR JPOL RESD ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2020-10-31 | QUES |  | 183052111 | 1 | 470.3 | 384.9 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117119555 | POLE_DECA_REPL - 7644 DEL RIO RDATASCADE | 35098438 |  |  | STS-POLE_DECA_REPL - 7644 DEL RIO RDATAS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 35.513 | -120.7143 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3213 | 30563 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 43 | 43 |  |  | 0 | 43 | 43 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891484 | RELW OH PRI CLR JPOL RESD FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-19 |  | COMP | 2021-01-19 | [16 empty] | 2019-04-29 | 2019-10-29 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | EEI |  | 183052111 | 24743 | 80.7 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117119759 | POLE_DECA_REPL - 1/P/N/O/7644 DEL RIO RD | 35208807 |  |  | STS-POLE_DECA_REPL - 1/P/N/O/7644 DEL RI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 35.5132 | -120.7145 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3213 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891485 | RELW OH SEC JPOL RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 | 17.4 | 17.4 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117120247 | POLE_DECA_REPL - 7620 DEL RIO RD ATASCAD | 35208810 |  |  | STS-POLE_DECA_REPL - 7620 DEL RIO RD ATA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.5129 | -120.7135 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3213 | 30563 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891483 | RELW OH PRI CLR RESD FLAG ESTR GO BTKA PRTO USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 | 46.7 | 46.7 | 256.7 | 256.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117121497 | POLE_DECA_REPL - 7155 SAN GREGORIO RD W/ | 35202325 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 35.5152 | -120.7092 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3213 | 2659 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 31.1 | 29.8 | 1.3 |  | 0 | 31.1 | 29.8 | 1.3 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891471 | RELW OH PRI JPOL RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-18 |  | COMP | 2021-02-18 | [16 empty] | 2019-04-29 | 2020-04-29 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-01-31 | EEI |  | 183052111 | 18302.69 | 1.8 | 0 | 1222.3 | 1222.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117121531 | POLE_DECA_REPL - 1/P/S/O/8130 SAN GREGOR | 35098440 |  |  | STS-POLE_DECA_REPL - 1/P/S/O/8130 SAN GR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.5133 | -120.7225 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3212 | 3665 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891439 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2019-10-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117122735 | POLE_BROK_REPL - 1/P/E/O/7313 GREGORIO R | 35098441 |  |  | STS-POLE_BROK_REPL - 1/P/E/O/7313 GREGOR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.5149 | -120.7122 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3213 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101939846 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2019-10-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117122745 | POLE_BROK_REPL - 2/P/E/O/740 GARCIA ATAS | 35208825 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.5244 | -120.7093 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3208 | 30273 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101932093 | RELW CLR OH PRI REMT TRAF ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 | 1.8 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117122846 | POLE_BROK_REPL - 605 GARCIA RD ATASCADER | 35202343 |  |  | STS-POLE_BROK_REPL - 605 GARCIA RD ATASC | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.5248 | -120.7085 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3209 | 30273 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101932105 | RELW OH PRI INSP CLR RESD TRAF SPCR ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 |  | 2020-04-29 | 2021 CBP Plan | 2021-02-28 | EEI |  | 183052111 | 1 | 1.8 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117123294 | POLE_DECA_REPL - 7400 SAN GREGORIO RDATA | 35202348 |  |  | STS-POLE_DECA_REPL - 7400 SAN GREGORIO R | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 35.5155 | -120.7138 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3213 | 2659 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 61.5 | 57.2 | 4.3 |  | 0 | 61.5 | 57.2 | 4.3 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891459 | RELW OH PRI CLR JPOL RESD FLAG ESTR GO BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-27 |  | COMP | 2021-01-27 | [16 empty] | 2019-04-29 | 2020-04-29 | 2020-10-04 | 2020-10-04 | 2021 CBP Plan | 2021-01-31 | EEI |  | 183052111 | 29081.14 | 1364.2 | 1364.2 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117123337 | POLE_DECA_REPL - 7505 SAN GREGORIO RD AT | 35208830 |  |  | STS-POLE_DECA_REPL - 7505 SAN GREGORIO R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.5155 | -120.7143 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3213 | 2659 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891458 | RELW OH PRI JPOL REMT FLAG ESTR BTKA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117123437 | POLE_BROK_REPL - 7600 SAN GREGORIO RD AT | 35208835 |  |  | STS-POLE_BROK_REPL - 7600 SAN GREGORIO R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.5155 | -120.7151 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3213 | 2659 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101891457 | RELW OH PRI CLR JPOL RESD FLAG ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-29 | 2020-04-29 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117125686 | POLE_DECA_REPL - C/O/MONTEREY/CAMPO RD A | 35208840 |  |  | STS-POLE_DECA_REPL - C/O/MONTEREY/CAMPO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 35.5051 | -120.6988 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3220 | 2533 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891297 | RELW OH PRI CLR JPOL RESD ESTR BTKA FSRP FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 | 1.8 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117125752 | POLE_DECA_REPL - F/O 9205 CORONA RDATASC | 35208846 |  |  | STS-POLE_DECA_REPL - F/O 9205 CORONA RDA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 35.5016 | -120.7241 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3221 | 30173 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 57.4 | 57.4 |  |  | 0 | 57.4 | 57.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101939882 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-20 | 2021-02-18 | COMP | 2021-02-18 | [16 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 26722.93 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117125793 | POLE_BROK_REPL - 7777 SAN GREGORIO RDATA | 35099996 |  |  | STS-POLE_BROK_REPL - 7777 SAN GREGORIO R | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 35.5147 | -120.7165 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3213 | 2659 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48.7 | 41.5 | 7.2 |  | 0 | 48.7 | 41.5 | 7.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101933927 | RELW OH PRI JPOL RESD USA FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-09 |  | COMP | 2021-02-09 | [16 empty] | 2019-04-30 | 2019-10-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 22528.78 | 108.6 | 108.6 | 318.6 | 318.6 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117126162 | POLE_DECA_REPL - GUY POLE/C/O/ALTURAS/DE | 35208851 |  |  | STS-POLE_DECA_REPL - GUY POLE/C/O/ALTURA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 35.513 | -120.7106 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3213 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 33.7 | 33.7 |  |  | 0 | 33.7 | 33.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891473 | RELW OH PRI RESD FLAG ESTR BTKA PRTO USA FMOB TER2 FSRP | Pole | 2021-02-12 |  | COMP | 2021-02-12 | [16 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 15177.98 | 46.7 | 46.7 | 256.7 | 256.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117126555 | POLE_DECA_REPL - 1/P/S/O/925 ROPA CT. AT | 35208856 |  |  | STS-POLE_DECA_REPL - 1/P/S/O/925 ROPA CT | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 35.5177 | -120.7142 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3213 | 2523 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 58.2 | 58.2 |  |  | 0 | 58.2 | 58.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891464 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-18 | 2021-02-17 | COMP | 2021-02-17 | [16 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 25339.24 | 1.8 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117126616 | POLE_DECA_REPL - 2857 MONTEREY RD ATASCA | 35208861 |  |  | STS-POLE_DECA_REPL - 2857 MONTEREY RD AT | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 35.503 | -120.6958 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3220 | 2533 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 73.4 | 73.4 |  |  | 0 | 73.4 | 73.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891303 | RELW JPOL OH PRI CLR PUBL TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-16 |  | COMP | 2021-02-16 | [16 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 30687.62 | 1.8 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117127109 | POLE_DECA_REPL - F/O 2377 MONTEREY RD AT | 35208866 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 35.5058 | -120.6999 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3220 | 2527 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 39.2 | 39.2 |  |  | 0 | 39.2 | 39.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101935275 | RELW OH PRI CLR JPOL RESD ESTR BTKA PROG FMOB TER2 PRTO FSRP | Pole | 2021-02-19 | 2021-02-17 | COMP | 2021-02-17 | [16 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 17935.04 | 1.8 | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117127319 | POLE_BROK_REPL - 6205 CONEJO RD ATASCADE | 35202383 |  |  | STS-POLE_BROK_REPL - 6205 CONEJO RD ATAS | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land JointPole |  |  | 35.5085 | -120.6999 |  | TIER 2 | 874 | 18305-2108, TEMPLETON | HH3220 | 6457 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.9 | 40.9 |  |  | 0 | 40.9 | 40.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103391070 | RELW OH PRI RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-10 |  | COMP | 2021-02-10 | [16 empty] | 2019-04-30 | 2020-04-30 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-01-31 | EEI |  | 183052108 | 17950.73 | 231 | 188.9 | 1688.5 | 1688.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117127383 | POLE_BROK_REPL - 2150 SAN FERNANDO RD AT | 35208871 |  |  | STS-POLE_BROK_REPL - 2150 SAN FERNANDO R | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.5096 | -120.7111 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3218 | 2111 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101891254 | RELW OH PRI JPOL TRAF TER2 FLAG BTKA FMOB PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117127448 | POLE_DECA_REPL - 2035 ALTURAS RDATASCADE | 35099997 |  |  | STS-POLE_DECA_REPL - 2035 ALTURAS RDATAS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.5124 | -120.7111 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3213 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101933922 | RELW OH PRI RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2019-10-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117128159 | POLE_DECA_REPL - A/F7900 BALBOA RDATASCA | 35208876 |  |  | STS-POLE_DECA_REPL - A/F7900 BALBOA RDAT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.5047 | -120.7117 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3218 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101936978 | RELW OH SERV PGEA RESD BTKA TRAF FLAG ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117129236 | POLE_DECA_REPL - 2025 ALTRES RD ATASCADE | 35099998 |  |  | STS-POLE_DECA_REPL - 2025 ALTRES RD ATAS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.5113 | -120.7114 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3213 | 4443 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891477 | RELW OH PRI RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2019-09-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117129705 | POLE_DECA_REPL - 1/P/W/O/2120 ALTURAS RD | 35099999 |  |  | STS-POLE_DECA_REPL - 1/P/W/O/2120 ALTURA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.5111 | -120.7129 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3213 | 4443 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101933921 | RELW OH PRI RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2019-09-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117129958 | POLE_DECA_REPL - 1/P/E/O/2100 ALTURAS RD | 35208891 |  |  | STS-POLE_DECA_REPL - 1/P/E/O/2100 ALTURA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.5104 | -120.7149 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3218 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891226 | RELW OH PRI PGEA CLR RESD TRAF ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117133030 | POLE_DECA_REPL - F/O 7500 GRAVES CREEK R | 35100104 |  |  | STS-POLE_DECA_REPL - F/O 7500 GRAVES CRE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 35.495 | -120.6971 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3225 | 31015 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29 | 29 |  |  | 0 | 29 | 29 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101936989 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-11 |  | COMP | 2021-01-11 | [16 empty] | 2019-05-01 | 2019-10-15 | 2020-10-08 | 2020-10-08 | 2021 CBP Plan | 2021-02-28 | EEI |  | 183052111 | 18450.26 |  | 0 | 1660.3 | 1660.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117133376 | POLE_BROK_REPL - 2/P/W/O/6700 GRAVES CRE | 35208896 |  |  | STS-POLE_BROK_REPL - 2/P/W/O/6700 GRAVES | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.5005 | -120.6968 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3225 | 953423 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101936993 | RELW OH PRI CLR REMT ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-01 | 2020-05-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117133568 | POLE_BROK_REPL - 1PN/O 6900 GRAVES CREEK | 35208901 |  |  | STS-POLE_BROK_REPL - 1PN/O 6900 GRAVES C | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.4994 | -120.6971 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3225 | 6031 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101891374 | RELW OH PRI CLR JPOL REMT TRAF FMOB FLAG ESTR BTKA TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-01 | 2020-05-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117133901 | POLE_BURN_REPL - R/O/3105 ARDILLA RD ATA | 35208906 |  |  | STS-POLE_BURN_REPL - R/O/3105 ARDILLA RD | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.4974 | -120.6996 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3225 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 101891380 | RELW OH PRI CLR REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-01 | 2020-05-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117134550 | POLE_DECA_REPL - 1PE/O R/O 6750 GRAVES C | 35208911 |  |  | STS-POLE_DECA_REPL - 1PE/O R/O 6750 GRAV | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.5016 | -120.6982 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3225 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891372 | RELW OH PRI CLR JPOL REMT ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-01 | 2020-05-01 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117144104 | POLE_DECA_REPL - 7355 BALBOA RD ATASCADE | 35208957 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.4991 | -120.7025 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3224 | 7581 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891089 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-02 | 2020-05-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 | 35.2 | 35.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117152784 | POLE_BROK_REPL - 8120 LOS OSOS RD R/O 1S | 35140830 |  |  | STS-POLE_BROK_REPL - 8120 LOS OSOS RD R/ | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 35.4564 | -120.681 |  | TIER 2 | 449 | 18254-1103, ATASCADERO | II3322 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 11 | 11 |  |  | 0 | 11 | 11 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101931297 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-07-07 |  | COMP | 2020-07-07 | [16 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | QUES |  | 182541103 | 5668.02 | 167.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117153894 | POLE_DECA_REPL - 6400 ROCKY CNYN RD 1P/N | 35209068 |  |  | STS-POLE_DECA_REPL - 6400 ROCKY CNYN RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4921 | -120.6422 |  | TIER 2 | 387 | 18305-2113, TEMPLETON | II3402 | 5879 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 47.9 | 47.9 |  |  | 0 | 47.9 | 47.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101942229 | OH PRI REMT RELW PGEA CLR ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-12 | 2021-02-12 | COMP | 2021-02-12 | [16 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052113 | 22475.59 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117156466 | POLE_DECA_REPL - 8193 SAN DIMAS LN 1WO A | 35140842 |  |  | STS-POLE_DECA_REPL - 8193 SAN DIMAS LN 1 | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 35.4553 | -120.6771 |  | TIER 2 | 449 | 18254-1103, ATASCADERO | II3322 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 25.8 | 25.8 |  |  | 0 | 25.8 | 25.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891997 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-09 |  | COMP | 2021-02-09 | [16 empty] | 2019-05-03 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 182541103 | 12580.41 | 250.2 |  |  |  | 250.2 |  | 250.2 |  | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117160981 | POLE_DECA_REPL - 1W/O 8370 LOS OSOS RD A | 35100156 |  |  | STS-POLE_DECA_REPL - 1W/O 8370 LOS OSOS | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.452 | -120.6739 |  | TIER 2 | 449 | 18254-1103, ATASCADERO | II3323 | 3997 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101931314 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-04 | 2019-10-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 182541103 | 1 | 2259.7 |  |  |  | 125.1 |  | 125.1 |  | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117162916 | POLE_DECA_REPL - 5940 VIOLETA ATASCADERO | 35123124 |  |  | STS-POLE_DECA_REPL - 5940 VIOLETA ATASCA | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 35.4854 | -120.6747 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3303 | 4475 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 44.1 | 44.1 |  |  | 0 | 44.1 | 44.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101896589 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-08 |  | COMP | 2021-01-08 | [16 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 182541101 | 19580.69 | 70.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117163046 | POLE_DECA_REPL - 6765 ARDILLA RD ATASCAD | 35209244 |  |  | STS-POLE_DECA_REPL - 6765 ARDILLA RD ATA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.4891 | -120.6732 |  | TIER 2 | 874 | 18305-2108, TEMPLETON | II3303 | 2559 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101929457 | RELW OH PRI CLR JPOL RESD BTKA TRAF FLAG ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052108 | 1 | 48.5 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117163173 | POLE_DECA_REPL - 5605 ARDILLA AVE 2/P/N | 35209254 |  |  | STS-POLE_DECA_REPL - 5605 ARDILLA AVE 2/ | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.4903 | -120.6754 |  | TIER 2 | 874 | 18305-2108, TEMPLETON | II3303 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101896485 | RELW OH SEC CLR REMT NOAC ESTR GO FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052108 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117164180 | POLE_DECA_REPL - 1N/W 7595 PORTOLA RD AT | 35123301 |  |  | STS-POLE_DECA_REPL - 1N/W 7595 PORTOLA R | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 35.4718 | -120.6751 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3313 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 32.1 | 32.1 |  |  | 0 | 32.1 | 32.1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101897290 | RELW OH PRI CLR RESD TRAF ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-06-22 |  | COMP | 2020-06-22 |  |  | 2021-01-21 | 2021-01-21 | [12 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-07-31 | Bakersfield |  | 182541101 | 11227.93 | 27.8 | 27.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117165391 | POLE_DECA_REPL - 5955 CHAUPLIN AVE ATASC | 35123219 |  |  | STS-TRAN_CORR_REPL - 5955 CHAUPLIN AVE A | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 35.4842 | -120.6781 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3307 | 12107 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 41.3 | 41.3 |  |  | 0 | 41.3 | 41.3 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101896915 | RELW OH PRI JPOL RESD ESTR GO BTKA OTRG PROG FMOB TER2 PRTO FSRP | Pole | 2021-01-07 | 2021-01-06 | COMP | 2021-01-06 | [16 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-01-31 | Bakersfield |  | 182541101 | 20481.32 | 76.4 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117166534 | POLE_BROK_REPL - N/O 8109 LARGA AVE ATAS | 35209295 |  |  | STS-POLE_BROK_REPL - N/O 8109 LARGA AVE | ADER | ADER | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.4807 | -120.6725 |  | TIER 2 | 874 | 18305-2108, TEMPLETON | II3308 | 429865 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101896877 | RELW OH PRI JPOL RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-06 | 2020-05-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052108 | 1 | 83.7 | 81.9 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117166686 | POLE_DECA_REPL - N/O SAN ANDRES AVE/CARM | 35209300 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 35.481 | -120.6706 |  | TIER 2 | 874 | 18305-2108, TEMPLETON | II3308 | 429865 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 52 | 52 |  |  | 0 | 52 | 52 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101896839 | RELW OH PRI JPOL RESD TRAF FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-18 |  | COMP | 2021-02-18 |  |  | 2021-02-21 | 2021-02-21 | [12 empty] | 2019-05-06 | 2020-05-06 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052108 | 26357.73 | 298.5 | 296.7 | 318.2 | 318.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117174990 | POLE_DECA_REPL - 2/P/W/O 5200 PORTOLA RD | 35209376 |  |  | STS-POLE_DECA_REPL - 2/P/W/O 5200 PORTOL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.4854 | -120.6862 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3301 | 2607 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101896396 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117175130 | POLE_DECA_REPL - 7680 GRAVES CREEK RDATA | 35100178 |  |  | STS-POLE_DECA_REPL - 7680 GRAVES CREEK R | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.4935 | -120.697 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3205 | 31015 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908209 | RELW OH PRI JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2019-11-07 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-02-28 | EEI |  | 183052111 | 1 | 40.4 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117175379 | POLE_DECA_REPL - 2R/O 7740 GRAVES CREEK | 35100179 |  |  | STS-POLE_DECA_REPL - 2R/O 7740 GRAVES CR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.493 | -120.698 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3205 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908210 | RELW OH SEC JPOL RESD NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2019-10-07 | 2020-10-07 | 2020-10-07 | 2021 CBP Plan | 2021-02-28 | EEI |  | 183052111 | 1 |  | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117175652 | POLE_DECA_REPL - 2/P/W/O 4700 PORTOLA RD | 35209381 |  |  | STS-POLE_DECA_REPL - 2/P/W/O 4700 PORTOL | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.4875 | -120.6872 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3301 | 2605 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101896388 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117175675 | POLE_DECA_REPL - 6650 SAN ANSELMO RD ATA | 35100180 |  |  | STS-POLE_DECA_REPL - 6650 SAN ANSELMO RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.4918 | -120.6842 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3302 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101896427 | RELW OH SEC JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2019-10-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117175679 | POLE_DECA_REPL - 1/P/S/O INT SAN PALO RD | 35209390 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.492 | -120.6818 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3302 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101911304 | RELW OH SEC RESD ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117175680 | POLE_DECA_REPL - 5225 ARDILLA AVE ATASCA | 35202515 |  |  | STS-POLE_DECA_REPL - 5225 ARDILLA AVE AT | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land |  |  | 35.4918 | -120.6788 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3302 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 53.2 | 52.6 | 0.6 |  | 0 | 53.2 | 52.6 | 0.6 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101896471 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-15 |  | COMP | 2021-01-15 | [16 empty] | 2019-05-07 | 2020-05-07 | 2020-10-13 | 2020-10-13 | 2021 CBP Plan | 2021-01-31 | EEI |  | 183052111 | 22358.55 | 34.2 | 32.4 | 733.5 | 733.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117175684 | POLE_DECA_REPL - INT ARDILLA AVE @ VEGA | 35209395 |  |  | STS-POLE_DECA_REPL - INT ARDILLA AVE @ V | APPR | APPR ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.4919 | -120.68 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3302 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101911301 | OH RELW PRI JPOL RESD REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | INPR | [17 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117175692 | POLE_DECA_REPL - F\O 1OO53 SANTA LUCIA R | 35123163 |  |  | STS-POLE_DECA_REPL - F\O 1OO53 SANTA LUC | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 35.4808 | -120.6982 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3210 | 30759 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 40.4 | 40.4 |  |  | 0 | 40.4 | 40.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908162 | RELW OH PRI CLR JPOL RESD FLAG ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-06 |  | COMP | 2021-01-06 | [16 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | Bakersfield |  | 182541101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117176398 | POLE_BROK_REPL - 1/P/SE/2/P/NE/O 5100 VE | 35209402 |  |  | STS-POLE_BROK_REPL - 1/P/SE/2/P/NE/O 510 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 35.4902 | -120.6802 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3302 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101896448 | RELW OH SEC JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117176403 | POLE_DECA_REPL - AGUILA AVE 1P S/O VENAD | 35209407 |  |  | STS-POLE_DECA_REPL - AGUILA AVE 1P S/O V | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 35.4893 | -120.68 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3302 | 4601 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 40.5 | 40.5 |  |  | 0 | 40.5 | 40.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101896449 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-17 |  | COMP | 2021-02-17 | [16 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 20851.22 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117177102 | POLE_BROK_REPL - 3650 ARDILLA AVE/BY ENT | 35209412 |  |  | STS-POLE_BROK_REPL - 3650 ARDILLA AVE/BY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 35.4902 | -120.6906 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3301 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101896364 | RELW PRI OH JPOL RESD NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117177729 | POLE_DECA_REPL - AF 6150 LLANO RDATASCAD | 35122931 |  |  | BNDL (3)POLE_DECA_REPL - 1N/O 6050 LLANO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.4837 | -120.7142 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3208 | 32031 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908274 | REGW OH PRI RESD FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 182541101 | 1 | 1611.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117179139 | POLE_DECA_REPL - 6\P\S\W\O R\O 5700 LLAN | 35122931 |  |  | BNDL (3)POLE_DECA_REPL - 1N/O 6050 LLANO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.4816 | -120.7136 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3208 | 32031 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101933340 | REGW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 182541101 | 1 | 1611.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117179504 | POLE_DECA_REPL - 1N/O 6050 LLANO RDATASC | 35122931 |  |  | BNDL (3)POLE_DECA_REPL - 1N/O 6050 LLANO | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.4806 | -120.7125 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3208 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101933341 | RELW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-07 | 2020-05-07 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 182541101 | 1 | 1611.3 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117183220 | POLE_DECA_REPL - 1S/W/O/7950 BALBOA RD A | 35209513 |  |  | STS-POLE_DECA_REPL - 1S/W/O/7950 BALBOA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.5041 | -120.7065 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3219 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891260 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117186093 | POLE_DECA_REPL - #1 W/O 10395 SANTA ANA | 35209553 |  |  | STS-POLE_DECA_REPL - #1 W/O 10395 SANTA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.4844 | -120.7027 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3204 | 6909 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101942268 | RELW OH PRI JPOL REMT FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117189535 | POLE_BROK_REPL - 2NW/O 10400 SANTA ANA R | 35202549 |  |  | STS-POLE_BROK_REPL - 2NW/O 10400 SANTA A | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land |  |  | 35.4841 | -120.703 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3209 | 6909 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 64.5 | 59.3 | 5.2 |  | 0 | 64.5 | 59.3 | 5.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101908247 | RELW OH PRI RESD FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-22 |  | COMP | 2020-12-22 | [16 empty] | 2019-05-08 | 2020-05-08 | 2020-10-23 | 2020-10-23 | 2021 CBP Plan | 2021-01-31 | EEI |  | 183052111 | 30416.77 | 64.8 | -1035.2 | -110.1 | -110.1 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117190600 | POLE_DECA_REPL - 2525 MONTEREY RD ATASCA | 35209597 |  |  | STS-POLE_DECA_REPL - 2525 MONTEREY RD AT | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.5082 | -120.7037 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | HH3219 | 47909 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891275 | RELW OH PRI REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-09 | 2020-05-09 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | TRC |  | 183052111 | 1 |  | 0 | 210 | 210 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117214781 | POLE_BROK_REPL - 1SE/O 3370 SAN FERNANDO | 35202596 |  |  | STS-POLE_BROK_REPL - 1SE/O 3370 SAN FERN | PEND | PEND ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land |  |  | 35.4896 | -120.6999 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3204 | 2111 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 52.3 | 47.1 | 5.2 |  | 0 | 52.3 | 47.1 | 5.2 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101931581 | RELW OH PRI PGEA CLR RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-12-22 |  | COMP | 2020-12-22 | [16 empty] | 2019-05-11 | 2020-05-11 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-01-31 | EEI |  | 183052111 | 27383.51 | 76.9 | -1067.6 | 211.3 | 211.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117214783 | POLE_DECA_REPL - 2SE/O 3370 SAN FERNANDO | 35202600 |  |  | STS-POLE_DECA_REPL - 2SE/O 3370 SAN FERN | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 35.4895 | -120.6988 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3205 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.8 | 27.4 | 2.4 |  | 0 | 29.8 | 27.4 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908199 | RELW OH PRI CLR FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-12-29 |  | COMP | 2020-12-29 | [16 empty] | 2019-05-11 | 2020-03-11 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-01-31 | EEI |  | 183052111 | 15032.28 |  | 0 | 1300.9 | 1300.9 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117216026 | POLE_BROK_REPL - 8700 SIERRA VISTA RD AT | 35123129 |  |  | STS-POLE_BROK_REPL - 8700 SIERRA VISTA R | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.4623 | -120.6834 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3317 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 16 | 16 |  |  | 0 | 16 | 16 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103523227 | RELW OH PRI JPOL REMT FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-11 | 2020-05-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | UNASSIGNED |  | 182541101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117216353 | POLE_BROK_REPL - C/O HWY41 OLD MORRO RD | 35140804 |  |  | STS-POLE_BROK_REPL - C/O HWY41 OLD MORRO | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | DMD |  |  | 35.4589 | -120.6813 |  | TIER 2 | 449 | 18254-1103, ATASCADERO | II3317 | A06 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 24.4 | 24.4 |  |  | 0 | 24.4 | 24.4 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101908583 | RELW OH PRI RESD ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-02-10 | 2021-02-09 | COMP | 2021-02-09 | [16 empty] | 2019-05-11 | 2020-05-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 182541103 | 13258.55 | 921.8 | 384.9 |  |  | 536.9 |  | 536.9 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | Atascadero | Templeton |  |  | OPEN | 117690075 | POLE _ BROK _ REPL_1445 SAN RAMON RD ROA | 35209449 |  |  | STS-POLE _ BROK _ REPL_1445 SAN RAMON RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.5164 | -120.7044 |  | TIER 2 |  |  | HH3214 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101891519 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | QUES |  |  | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | Atascadero | Templeton |  |  | OPEN | 117690099 | POLE_DECA_REPL - A/F 5630 AGUILA AVE ROA | 35209459 |  |  | STS-POLE_DECA_REPL - A/F 5630 AGUILA AVE | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit Land |  |  | 35.4866 | -120.6746 |  | TIER 2 |  |  | II3303 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 23.4 | 23.4 |  |  | 0 | 23.4 | 23.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101896500 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole | 2021-02-22 |  | COMP | 2021-02-22 | [16 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | QUES |  |  | 12218.46 | 50.4 | 48.6 | 978 | 978 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | Atascadero | Templeton |  |  | OPEN | 117690100 | POLE_DECA_REPL - 2GP 7399 PORTOLA RD PVT | 35209464 |  |  | STS-POLE_DECA_REPL - 2GP 7399 PORTOLA RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 35.4726 | -120.6754 |  | TIER 2 |  |  | II3313 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101897293 | RELW OH PRI ESTR TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | QUES |  |  | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | Atascadero | Templeton |  |  | OPEN | 117690195 | POLE_BROK_REPL - 7305 SAN GABRIEL RD ROA | 35209467 |  |  | STS-POLE_BROK_REPL - 7305 SAN GABRIEL RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 35.4667 | -120.6808 |  | TIER 2 |  |  | II3317 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101930534 | RELW OH PRI ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | QUES | [11 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 118186533 | POLE_DECA_REPL - 9000 ROCKY CYN RD | 35202658 |  |  | STS-POLE_DECA_REPL - 9000 ROCKY CANYON | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 35.4754 | -120.6227 |  | TIER 2 | 387 | 18305-2113, TEMPLETON | II3414 | 30661 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 36.8 | 36.8 |  |  | 0 | 36.8 | 36.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101895844 | RELW OH PRI FIRE ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2021-01-15 |  | COMP | 2021-01-15 | [16 empty] | 2019-11-19 | 2020-11-19 | 2020-11-19 | 2020-11-19 | 2021 CBP Plan | 2021-01-31 | EEI |  | 183052113 | 16408.02 | 1.8 | 0 | 1100.2 | 1100.2 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | Atascadero | Templeton |  |  | OPEN | 118187236 | POLE_BROK_REPL - 7110 SERENA AVE ATASCAD | 35210084 |  |  | STS-POLE_BROK_REPL - 7110 SERENA AVE ATA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 35.4934 | -120.6591 |  | TIER 2 | 387 | 18305-2113, TEMPLETON | II3305 | 31637 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 103010325 | RELW OH PRI REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-11-19 | 2020-11-19 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-02-28 | QUES |  | 183052113 | 1 | 50.4 | 48.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117175626 | POLE_DECA_REPL - 9335 BARRANCO 1/P/S/O A | 35123305 |  |  | STS-POLE_DECA_REPL - 9335 BARRANCO 1/P/S | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4663 | -120.6921 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3220 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32 | 32 |  |  | 0 | 32 | 32 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908135 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-09-01 | 2020-09-01 | COMP | 2020-09-01 | [16 empty] | 2019-05-07 | 2020-05-07 | 2020-10-23 | 2020-10-23 | Moved to 2020, per [REDACTED], 10.19.20 | 2020-07-31 | Bakersfield |  | 182541101 | 12734.92 | 1575.5 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | COMP | 117100087 | POLE_DECA_REPL - 9075 SANTA BARBARA RD A | 35140794 |  |  | +STS-POLE_DECA_REPL -9075 SANTA BARBARA | FICL | FICL SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2020-08-30 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 35.4417 | -120.6432 |  | TIER 2 | 449 | 18254-1103, ATASCADERO | JJ3402 |  | Y | 311 |  |  | 2021-01-13 | 2021-01-13 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 50.8 | 50.8 |  |  | 70 | 0.8 | 0.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101945097 | RELW OH COMP PUBL PRI CLR JPOL TRAF FLAG ESTR CPGG PRTO BTKA FMOB TER2 | Pole | 2020-02-28 | 2020-05-27 | COMP | 2020-02-28 | COMP | 2021-01-13 | 2020-05-27 | 2020-05-27 | [11 empty] | 2021-01-20 | 2021-01-13 | 2020-04-25 |  | 2020-04-25 | Program Manager | 2020-02-10 | QUES |  | 182541103 | 10346.49 | 22097.9 | 21637.4 | 19148.9 | 19148.9 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
South | LP | ATASCADERO | Templeton |  |  | COMP | 117151330 | POLE_DECA_REPL - 8300 SAN DIMAS 1/P/S/OA | 35140821 |  |  |  | MAPP | MAPP SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 35.4498 | -120.6819 |  | TIER 2 | 449 | 18254-1103, ATASCADERO | II3322 | 6593 | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 50 | 50 |  |  | 38.5 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101891974 | RELW OH PRI COMP JPOL RESD ESTR BTKA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-06-16 | 2020-07-18 | COMP | 2020-03-20 | COMP | 2021-02-11 | 2020-06-03 | 2020-06-03 | [11 empty] | 2021-02-17 | 2021-02-11 | 2020-05-03 | 2021-05-31 | 2021-05-31 | Program Manager | 2020-02-10 | QUES |  | 182541103 | 17184.2 | 5190.9 | 3562.4 | 871.5 | 871.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
South | LP | ATASCADERO | Templeton |  |  | COMP | 117151355 | POLE_BROK_REPL - 8300 SAN DIMASATASCADER | 35140822 |  |  | +STS-POLE_BROK_REPL -8300 SAN DIMASATASC | MAPP | MAPP SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 35.45 | -120.6812 |  | TIER 2 | 449 | 18254-1103, ATASCADERO | II3322 | 6593 | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 51 | 51 |  |  | 35 | 1 | 1 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101931301 | RELW OH PRI COMP JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP CPGG | Pole | 2020-07-02 | 2020-07-06 | COMP | 2020-03-17 | COMP | 2021-02-11 | 2020-06-03 | 2020-06-03 | [11 empty] | 2021-02-17 | 2021-02-11 | 2020-05-03 | 2021-05-31 | 2021-05-31 | Program Manager | 2020-02-10 | QUES |  | 182541103 | 18670.09 | 5243.1 | 3398 | 1013.1 | 1013.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
South | LP | ATASCADERO | Templeton |  |  | COMP | 117152245 | POLE_DECA_REPL - 8200 SAN DIMAS RD ATASC | 35140828 |  |  | +STS-POLE_DECA_REPL -8200 SAN DIMAS RD A | MAPP | MAPP SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 35.4535 | -120.6789 |  | TIER 2 | 449 | 18254-1103, ATASCADERO | II3322 |  | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 50 | 50 |  |  | 53.5 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101892000 | RELW OH PRI COMP JPOL RESD ESTR BTKA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-03-13 | 2020-06-16 | COMP | 2020-03-13 | COMP | 2021-02-11 | 2020-03-12 | 2020-03-12 | [11 empty] | 2021-02-17 | 2021-02-11 | 2020-05-03 | 2021-05-31 | 2021-05-31 | Program Manager | 2020-02-10 | QUES |  | 182541103 | 15348.13 | 6393.2 | 6393.2 | 2763.1 | 2763.1 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
South | LP | ATASCADERO | Templeton |  |  | COMP | 117152871 | POLE_BROK_REPL - 8130 LOS OSOS RD ATASCA | 35140832 |  |  | +STS-POLE_BROK_REPL - 8130 LOS OSOS RD A | MAPP | MAPP SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 35.457 | -120.682 |  | TIER 2 | 449 | 18254-1103, ATASCADERO | II3322 | 3997 | Y | 311 |  |  | 2021-02-11 07:00 | 2021-02-11 16:00 | Completed | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 50.8 | 50.8 |  |  | 60 | 0.8 | 0.8 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101891982 | COMP JPOL RELW OH PRI RESD ESTR BTKA PROG CPGG FMOB TER2 PRTO FSRP | Pole | 2020-08-10 | 2020-10-11 | COMP | 2020-08-10 | COMP | 2021-02-11 | [13 empty] | 2021-02-17 | 2021-02-11 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-10-31 | QUES |  | 182541103 | 16865.32 | 5493.1 | 5099.5 | 1018.5 | 1018.5 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | COMP | 117156465 | POLE_DECA_REPL - 8275 LOS OSOS RD A/F AT | 35140840 |  |  | +STS-POLE_DECA_REPL- 8275 LOS OSOS RD A/ | MAPP | MAPP SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 35.4514 | -120.6759 |  | TIER 2 | 449 | 18254-1103, ATASCADERO | II3322 |  | Y | 311 |  |  |  |  | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 50 | 50 |  |  | 63 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101892011 | RELW OH PRI COMP RESD ESTR GO BTKA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-07-01 | 2020-07-01 | COMP | 2020-07-01 | COMP | 2021-02-11 | [13 empty] | 2021-02-16 | 2021-02-11 | 2020-05-03 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-12-31 | QUES |  | 182541103 | 17488.23 | 6540 | 5147.6 |  |  | 1225 |  | 1225 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | COMP | 117163102 | POLE_BROK_REPL - 7555 CURBARIL AVEATASCA | 35123130 |  |  | +STS-POLE_BROK_REPL-7555 CURBARIL AVEAT | FICL | FICL SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 35.4747 | -120.6715 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3313 | 2761 | Y | 311 |  |  | 2021-01-15 | 2021-01-15 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 42.9 | 42.9 |  |  | 71.5 | 2.5 | 2.5 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101932667 | RELW OH PRI COMP CLR JPOL RESD ESTR GO BTKA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-06-03 | 2020-07-27 | COMP | 2020-06-03 | COMP | 2021-01-15 | 2019-09-06 | 2019-09-06 | [11 empty] | 2021-01-19 | 2021-01-15 | 2020-05-05 | 2021-05-31 | 2021-05-31 | Program Manager | 2020-07-31 | Bakersfield |  | 182541101 | 22532.77 | 22544.3 | 19585.6 | 19585.6 | 19585.6 | 2021 |  | 2021 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
South | LP | ATASCADERO | Templeton |  |  | COMP | 117165617 | POLE_DECA_REPL - 1SE/O 7940 SAN RAFAEL R | 35122299 |  |  | +STS-POLE_DECA_REPL - 1SE/O7940 SAN RAFA | FICL | FICL SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 35.4604 | -120.674 |  | TIER 2 | 449 | 18254-1103, ATASCADERO | II3318 |  | Y | 311 |  |  | 2021-01-15 | 2021-01-15 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 1 | 52 | 52 |  |  | 70 | 1 | 1 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908637 | RELW OH PRI COMP CLR JPOL RESD JAR TRAF FLAG BTKA CPGG FMOB TER2 PRTO | Pole | 2020-02-21 | 2020-07-02 | COMP | 2019-10-11 | COMP | 2021-01-15 | 2020-02-20 | 2020-07-02 | [11 empty] | 2021-01-19 | 2021-01-15 | 2019-11-06 | 2021-05-31 | 2021-05-31 | Program Manager |  | UNASSIGNED |  | 182541103 | 9135.09 | 21687.4 | 21144.5 | 19463.5 | 19463.5 | 215.8 |  | 215.8 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
South | LP | ATASCADERO | Templeton |  |  | COMP | 117166529 | POLE_DECA_REPL - A/F 8230 LARGA AVE ATAS | 35123013 |  |  | +STS-POLE_DECA_REPL - A/F 8230 LARGA AVE | MAPP | MAPP SRDY CRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-02-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 35.4786 | -120.6762 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3308 | 30459 | Y | 311 |  |  | 2021-02-02 | 2021-02-02 | Completed | Order Operation | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 1 | 50.9 | 50.9 |  |  | 41.5 | 0.9 | 0.9 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101936809 | COMP JPOL RELW OH PRI RESD ESTR GO BTKA CPGG FMOB TER2 PRTO | Pole | 2019-10-01 | 2020-05-27 | COMP | 2019-10-01 | COMP | 2021-02-02 | 2020-05-27 | 2020-05-27 | [11 empty] | 2021-02-03 | 2021-02-02 | 2020-05-06 |  | 2020-05-06 | Q1 Work Plan |  | UNASSIGNED |  | 182541101 | 17703.87 | 8032.9 | 6963.4 | 2069.2 | 2069.2 | 922.1 |  | 922.1 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-18
South | LP | ATASCADERO | Templeton |  |  | COMP | 117176562 | POLE_DECA_REPL - 10660 REALITO DR. ATASC | 35123302 |  |  | +STS-POLE_DECA_REPL-10660 REALITO DR. A | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 35.4634 | -120.697 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3220 | 7435 | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 2 | 50.5 | 50.5 |  |  | 51.5 | 0.5 | 0.5 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908029 | RELW OH PRI COMP CLR JPOL RESD TRAF ESTR BTKA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-04-09 | 2020-05-31 | COMP | 2020-04-09 | COMP | 2021-01-15 | 2020-05-31 | 2020-05-31 | [11 empty] | 2021-01-15 | 2021-01-06 | 2020-03-15 | 2021-05-31 | 2021-05-31 | Program Manager | 2020-07-31 | Bakersfield |  | 182541101 | 55949.71 | 29036.2 | 27507.3 | 27507.3 | 27507.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-02-20
South | LP | ATASCADERO | Templeton |  |  | COMP | 117177441 | POLE_DECA_REPL - 10615 REALITO DR. AT HO | 35123302 |  |  | +STS-POLE_DECA_REPL-10660 REALITO DR. A | FICL | FICL SRDY REDL | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Beyond CONS | Out of PEND |  | No Action | 35.4655 | -120.6939 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3220 | 7435 | Y | 311 |  |  | 2021-01-06 | 2021-01-06 | Completed | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 2 | 0 |  |  |  | 51.5 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908035 | REGW OH PRI COMP CLR RESD ESTR BTKA CPGG FMOB TER2 PRTO FSRP | Pole | 2020-04-09 | 2020-05-31 | COMP | 2020-04-09 | COMP | 2021-01-15 | 2020-05-31 | 2020-05-31 | [11 empty] | 2021-01-15 | 2021-01-06 | 2020-05-07 | 2021-05-31 | 2021-05-31 | Pole Notification Clean Up 05.29.20 | 2020-07-31 | Bakersfield |  | 182541101 | 55949.71 | 29036.2 | 27507.3 | 27507.3 | 27507.3 |  |  |  | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-06-02
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117114215 | POLE_DECA_REPL - 9098 SAN GABRIEL RD 1P/ | 35140803 |  |  | +STS-POLE_DECA_REPL - 9098 SAN GABRIEL R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4604 | -120.6498 |  | TIER 2 | 2722 | 18254-1102, ATASCADERO | II3416 | 2907 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101896331 | RELW OH PRI JPOL RESD ESTR PRTO BTKA FMOB TER2 FSRP | Pole | 2020-03-02 | 2020-04-22 | COMP | 2020-03-02 | [16 empty] | 2019-04-28 | 2020-04-28 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-02-10 | QUES |  | 182541102 | 19443.16 | 171.9 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117159029 | POLE_DECA_REPL - OPP 9600 SANTA LUCIA RD | 35123161 |  |  | STS-POLE_DECA_REPL - 9585 SANTA LUCIA RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.481 | -120.6916 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3306 | 6169 | Y | 311 |  |  | 2021-07-15 07:00 | 2021-07-15 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 3 | 0 | 0 | 0 | 152.7 | 152.7 |  |  | 0 | 152.7 | 152.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101897031 | RELW OH PRI CLR REMT ESTR GO BTKA FMOB TER2 PRTO FSRP | Pole | 2019-10-29 | 2021-01-21 | COMP | 2019-10-29 |  |  | 2021-01-21 | 2021-01-21 | [12 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 182541101 | 55434.69 | 39.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117159242 | POLE_DECA_REPL - 9585 SANTA LUCIA RD ATA | 35123161 |  |  | STS-POLE_DECA_REPL - 9585 SANTA LUCIA RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4807 | -120.6908 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3306 | 6169 | Y | 311 |  |  | 2021-07-15 07:00 | 2021-07-15 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 3 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101897029 | RELW OH PRI CLR REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2019-10-29 | 2021-01-21 | COMP | 2019-10-29 |  |  | 2021-01-21 | 2021-01-21 | [12 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 182541101 | 55434.69 | 39.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117159316 | POLE_DECA_REPL - R/O 9585 SANTA LUCIA RD | 35123161 |  |  | STS-POLE_DECA_REPL - 9585 SANTA LUCIA RD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4802 | -120.6911 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3306 | 6169 | Y | 311 |  |  | 2021-07-15 07:00 | 2021-07-15 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 3 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101897030 | RELW OH PRI CLR REMT NOAC ESTR REAR FMOB TER2 PRTO FSRP | Pole | 2019-10-29 | 2021-01-21 | COMP | 2019-10-29 |  |  | 2021-01-21 | 2021-01-21 | [12 empty] | 2019-05-04 | 2020-05-04 | 2020-10-24 | 2020-10-24 | 2021 CBP Plan |  | UNASSIGNED |  | 182541101 | 55434.69 | 39.1 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117159615 | POLE_DECA_REPL - 3/P/W/O 6450 PORTOLA RD | 35123016 |  |  | +STS-POLE_DECA_REPL- 3/P/W/O 6450 PORTOL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4791 | -120.6849 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3306 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101897011 | RELW OH PRI CLR ESTR JPOL RESD REAR FMOB TER2 PRTO FSRP | Pole | 2019-11-12 | 2019-12-19 | COMP | 2019-11-12 | [16 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 182541101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117160466 | POLE_DECA_REPL - 9270 SANTA LUCIA RDATAS | 35123160 |  |  | +STS-POLE_DECA_REPL - 9270 SANTA LUCIA R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4818 | -120.6875 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3306 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101897040 | RELW OH SEC RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2019-11-12 | 2019-11-25 | COMP | 2019-11-12 | [16 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan |  | UNASSIGNED |  | 182541101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117162661 | POLE_BROK_REPL - 8505 CASONVA RD ATASCAD | 35123306 |  |  | +STS-POLE_BROK_REPL - 8505 CASONVA RD AT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4613 | -120.6847 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3316 | 2381 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101908499 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-06-29 | 2020-10-16 | COMP | 2020-06-29 |  |  | 2020-10-15 | 2020-10-15 | [12 empty] | 2019-05-04 | 2020-05-04 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-07-31 | Bakersfield |  | 182541101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117163088 | POLE_DECA_REPL - EAST CORNER OF ATASCADE | 35140848 |  |  | +STS-POLE_DECA_REPL- EAST CORNER OF ATAS | CONS | CONS SRDY CRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4618 | -120.6546 |  | TIER 2 | 2722 | 18254-1102, ATASCADERO | II3320 | 2907 | Y | 311 |  |  | 2021-02-24 07:00 | 2021-02-24 16:00 | Dispatched | CLICK | [6 empty] | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101897693 | RELW OH PRI JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-03-12 | 2020-05-04 | COMP | 2020-03-12 |  |  | 2020-03-19 | 2020-03-19 | [12 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-02-10 | QUES |  | 182541102 | 27675.13 | 1373.4 | 1373.4 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117163449 | POLE_DECA_REPL - 5800 VENADO AVE ATASCAD | 35123122 |  |  | +TS-POLE_DECA_REPL - 5485 VENADO RD ATAS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4873 | -120.674 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3303 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 151.7 | 151.7 |  |  | 0 | 151.7 | 151.7 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103885817 | REGW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-08-07 | 2021-01-21 | COMP | 2020-08-07 |  |  | 2021-01-21 | 2021-01-21 | [12 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | Pole Notification Clean Up 05.29.20 | 2020-07-31 | Bakersfield |  | 182541101 | 60709.55 | 120.3 | 41.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-06-02
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117163473 | POLE_BROK_REPL - 5705 VENADO RD ATASCADE | 35123122 |  |  | +TS-POLE_DECA_REPL - 5485 VENADO RD ATAS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4874 | -120.674 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3303 | 7525 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101929453 | REGW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-08-07 | 2021-01-21 | COMP | 2020-08-07 |  |  | 2021-01-21 | 2021-01-21 | [12 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | Pole Notification Clean Up 05.29.20 | 2020-07-31 | Bakersfield |  | 182541101 | 60709.55 | 120.3 | 41.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-06-02
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117163530 | POLE_DECA_REPL - 5705 VENADO RD 1/P/N AT | 35123122 |  |  | +TS-POLE_DECA_REPL - 5485 VENADO RD ATAS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4879 | -120.6741 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3303 |  | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101896493 | REGW OH SEC JPOL RESD ESTR TER2 GO REAR FMOB PRTO FSRP | Pole | 2020-08-07 | 2021-01-21 | COMP | 2020-08-07 |  |  | 2021-01-21 | 2021-01-21 | [12 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | Pole Notification Clean Up 05.29.20 | 2020-07-31 | Bakersfield |  | 182541101 | 60709.55 | 120.3 | 41.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-06-02
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117163682 | POLE_DECA_REPL - 5485 VENADO RD ATASCADE | 35123122 |  |  | +TS-POLE_DECA_REPL - 5485 VENADO RD ATAS | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4888 | -120.6763 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3303 | 7525 | Y | 311 |  |  | 2021-06-30 07:00 | 2021-06-30 16:00 | Reserved | CLICK | [6 empty] | 0 |  |  |  | 0 | 0 |  |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101896491 | RELW OH PRI CLR JPOL RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-08-07 | 2021-01-21 | COMP | 2020-08-07 |  |  | 2021-01-21 | 2021-01-21 | [12 empty] | 2019-05-05 | 2020-05-05 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-07-31 | Bakersfield |  | 182541101 | 60709.55 | 120.3 | 41.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117175126 | POLE_DECA_REPL - 9253 LUCINDA RD ATASCAD | 35122440 |  |  | +STS-POLE_DECA_REPL -9253 LUCINDA RD ATA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-04-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4619 | -120.6927 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3220 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Scheduled | CLICK | [6 empty] | 77.4 | 77.4 |  |  | 0 | 77.4 | 77.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908145 | RELW OH PRI JPOL RESD JAR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-05-28 | 2020-05-28 | COMP | 2020-05-28 | [16 empty] | 2019-05-07 | 2019-11-07 | 2021-05-31 | 2021-05-31 | Program Manager | 2020-07-31 | Bakersfield |  | 182541101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-02-20
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117178356 | POLE_DECA_REPL - 3350 SAN FERNANDO RD AT | 35100184 |  |  | STS-POLE_DECA_REPL - 3350 SAN FERNANDO R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.49 | -120.7008 |  | TIER 2 | 1559 | 18305-2111, TEMPLETON | II3204 | 2111 | Y | 311 |  |  | 2021-08-17 07:00 | 2021-08-17 16:00 | Reserved | CLICK | [6 empty] | 51.8 | 51.8 |  |  | 0 | 51.8 | 51.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908212 | RELW OH PRI CLR RESD TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-01-22 | 2021-01-25 | COMP | 2020-07-07 |  |  | 2021-01-21 | 2021-01-21 | [12 empty] | 2019-05-07 | 2019-10-09 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2020-12-31 | QUES |  | 183052111 | 22031.46 | 625.2 | 41.8 |  |  | 583.4 |  | 583.4 | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117179556 | POLE_DECA_REPL - 3W/O 5180 CASCABEL RD A | 35123128 |  |  | +STS-POLE_DECA_REPL- 3W/O 5180 CASCABEL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4881 | -120.6969 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3205 | 31433 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | [6 empty] | 51.8 | 51.8 |  |  | 0 | 51.8 | 51.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101929837 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-09-03 | 2020-11-10 | COMP | 2020-09-02 | [16 empty] | 2019-05-07 | 2020-05-07 | 2024-05-05 | 2024-05-05 | 2021 CBP Plan | 2020-07-31 | Bakersfield |  | 182541101 | 17549.7 | 1200.2 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117180070 | POLE_DECA_REPL - 1SE/O 5655 CASCABEL RDA | 35123162 |  |  | STS-POLE_DECA_REPL - 1SE/O 5655 CASCABEL | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4847 | -120.6927 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3210 |  | Y | 311 |  |  | 2021-08-17 07:00 | 2021-08-17 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908154 | RELW OH PRI RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2020-07-09 | 2021-01-21 | COMP | 2020-07-09 |  |  | 2021-01-21 | 2021-01-21 | [12 empty] | 2019-05-07 | 2020-05-07 | 2020-10-23 | 2020-10-23 | 2021 CBP Plan |  | Bakersfield |  | 182541101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117180398 | POLE_DECA_REPL - F\O 10855 SANTA LUCIA R | 35105762 |  |  | STS-POLE_DECA_REPL - F\O 10855 SANTA LUC | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4774 | -120.7029 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3209 | 32031 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 44.4 | 44.4 |  |  | 0 | 44.4 | 44.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908255 | RELW OH PRI JPOL RESD TRAF FLAG ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole | 2019-11-10 | 2021-01-21 | COMP | 2019-11-10 |  |  | 2021-01-21 | 2021-01-21 | [12 empty] | 2019-05-07 | 2019-10-07 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan |  | SLO |  | 182541101 | 21487.06 | 66.9 | 27.8 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117180734 | POLE_DECA_REPL - 5205 TECOLOTE RD ATASCA | 35122935 |  |  | STS-POLE_DECA_REPL - 5205 TECOLOTE RD AT | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-05-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4787 | -120.7066 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3209 | 32031 | Y | 311 |  |  | 2021-09-30 07:00 | 2021-09-30 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 0 | 0 | 0 | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101933348 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO | Pole | 2019-11-30 | 2021-02-09 | COMP | 2019-11-12 |  |  | 2020-05-15 | 2020-05-15 | [12 empty] | 2019-05-07 | 2020-05-07 |  | 2020-05-07 | 2021 CBP Plan |  | UNASSIGNED |  | 182541101 | 15280.48 | 147.3 | [7 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117184307 | POLE_BURN_REPL - C/O LOS GATOS RD/SAN MA | 35123134 |  |  | STS-POLE_BURN_REPL - C/O LOS GATOS RD/SA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4753 | -120.6829 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3312 |  | Y | 311 |  |  | 2021-07-15 07:00 | 2021-07-15 16:00 | Reserved | CLICK | [6 empty] | 52.5 | 52.5 |  |  | 0 | 52.5 | 52.5 |  |  | EC | E | Pole | Burnt | Replace |  | 101897202 | RELW OH PRI RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-06-22 | 2021-01-21 | COMP | 2020-06-22 |  |  | 2021-01-21 | 2021-01-21 | [12 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-07-31 | Bakersfield |  | 182541101 | 18323.61 | 41.8 | 41.8 | [5 empty] | FRMMA/WMPMA - Electric | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117184427 | POLE_DECA_REPL - 9650 CARMELITA RDATASCA | 35123334 |  |  | +STS-POLE_DECA_REPL - 9650 CARMELITA RDA | UNSC | UNSC ERDY SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4625 | -120.6791 |  | TIER 2 | 901 | 18254-1101, ATASCADERO | II3317 | 4663 | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 0 | 0 | 0 | 0 | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908539 | RELW OH PRI CLR JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-09-01 | 2020-09-01 | COMP | 2020-09-01 | [16 empty] | 2019-05-08 | 2020-05-08 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2020-07-31 | Bakersfield |  | 182541101 | [9 empty] | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117190191 | POLE_DECA_REPL - 9750 CARMELITA RD R/O A | 35140869 |  |  | STS-POLE_DECA_REPL - 9750 CARMELITA RD R | UNSC | UNSC SRDY | Poles | MPP |  | 07D | 11/2 A&B Tags | EC B Tags | 1.4 |  |  | 1 | 2021-03-31 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4597 | -120.6816 |  | TIER 2 | 449 | 18254-1103, ATASCADERO | II3317 | 6493 | Y | 311 |  |  | 2021-03-04 07:00 | 2021-03-04 16:00 | Scheduled | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | B | Pole | Decayed/Rotten | Replace |  | 101931266 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2020-06-03 | 2021-02-12 | COMP | 2020-04-13 |  |  | 2020-05-12 | 2020-05-12 | [12 empty] | 2019-05-09 | 2020-05-09 | 2020-07-11 | 2020-07-11 | Program Manager | 2020-02-10 | QUES |  | 182541103 | 25640.1 | 3993.1 | 1173.7 |  |  | 88.7 |  | 88.7 | FRMMA/WMPMA - Electric | Y | 11/2 in MPP Import File | N | Permitting_Delays | Y | 2020-02-20
South | LP | Atascadero | Templeton |  |  | OPEN | 117690127 | POLE _ BROK _ REPL_13555 HWY 41 ROAD | 35140900 |  |  | STS-POLE _ BROK _ REPL_13555 HWY 41 ROAD | UNSC | UNSC SRDY | Poles | MPP |  | 07D | Critical Work | E&F Carry Over |  |  |  | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.4501 | -120.7032 |  | TIER 2 |  |  | II3224 |  | Y | 311 |  |  | 2021-08-17 07:00 | 2021-08-17 16:00 | Reserved | CLICK | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101907971 | RELW OH PRI ESTR TER2 PRTO | Pole | 2021-02-04 | 2021-02-04 | COMP | 2021-02-04 | [16 empty] | 2019-07-31 | 2020-07-31 |  | 2020-07-31 | 2021 CBP Plan | 2020-10-31 | QUES |  |  | 6141.96 | 44.3 |  |  |  | 44.3 |  | 44.3 |  | Y | MPP File Only | N |  | Y | 2020-08-25
South | LP | ATASCADERO | Templeton |  |  | OPEN | 117690262 | POLE_DECA_REPL - 2P/W/O 3310 TEMPLETON R | 35192821 |  |  | +REPL POLE 3310 TEMPLETON RD. ATASCADER | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-03-15 | 2020 | 2020 | 2021 |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.5214 | -120.6597 |  | TIER 2 |  |  | HH3310 |  | Y | 311 |  |  | 2021-03-31 07:00 | 2021-03-31 16:00 | Reserved | CLICK | POLRPL | # of Poles Replaced | 1 | 1 | 0 | 0 | 51 | 51 |  |  | 0 | 51 | 51 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101942963 | RELW OH PRI ESTR TER2 PRTO FSRP ERR | Pole | 2020-10-22 | 2020-10-28 | COMP | 2020-10-22 |  |  | 2020-10-28 | 2020-10-28 | [12 empty] | 2019-07-31 | 2020-07-31 | 2021-05-31 | 2021-05-31 | Work Plan Reconcilation (B-Tags) |  | SLO |  |  | 11182.99 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-07-21
South | LP | BIG SUR | San Luis Obispo |  |  | OPEN | 117037837 | POLE_DECA_REPL - SALMON CRK 6P/N BIG SUR | 35098346 |  |  | STS-POLE_DECA_REPL - SALMON CRK 6P/N BIG | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8137 | -121.3685 |  | TIER 2 | 1693 | 18277-1101, CAMBRIA | AA16 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103012362 | RELW OH PRI INSP JPOL REMT ESTR GO BTKA REAR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-15 | 2019-11-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | SLO |  | 182771101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BIG SUR | San Luis Obispo |  |  | OPEN | 117132086 | POLE_DECA_REPL - #14 ON LINE N/O MB A/F | 35215059 |  |  | STS-POLE_DECA_REPL - #14 ON LINE N/O MB | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8149 | -121.3613 |  | TIER 2 | 1693 | 18277-1101, CAMBRIA | AA16 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908710 | RELW OH PRI INSP CLR REMT FIRE NOAC SPCR SWRK ESTR USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-04-30 | 2020-04-30 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | SLO |  | 182771101 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BIG SUR | San Luis Obispo |  |  | OPEN | 117150083 | POLE_DECA_REPL - A/F 77450 HWY 1 W/TRANS | 35215129 |  |  | STS-POLE_DECA_REPL - A/F 77450 HWY 1 W/T | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8037 | -121.351 |  | TIER 2 | 1693 | 18277-1101, CAMBRIA | AA16 | 14933 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101908720 | RELW PRI OH INSP CLR PUBL REMT NOAC SWRK ESTR GO REAR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-02 | 2020-05-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | SLO |  | 182771101 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BIG SUR | San Luis Obispo |  |  | OPEN | 117150085 | POLE_BROK_REPL - #6N CO#14933 ON LINE N/ | 35098456 |  |  | STS-POLE_BROK_REPL - #6N CO#14933 ON LIN | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.8027 | -121.3492 |  | TIER 2 | 1693 | 18277-1101, CAMBRIA | AA16 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101948016 | RELW OH PRI INSP FIRE CLR PUBL REMT ESTR GO USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-02 | 2019-11-02 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | SLO |  | 182771101 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117209636 | POLE_DECA_REPL - LAKE NACIMIENTO RESORT | 35100212 |  |  | STS-POLE_DECA_REPL - LAKE NACIMIENTO RES | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.7558 | -120.899 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | CC27 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 32.9 | 31.6 | 1.3 |  | 0 | 32.9 | 31.6 | 1.3 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101939374 | RELW OH PRI PGEA INSP REMT NOAC ESTR FMOB TER2 FSRP | Pole | 2021-02-01 | 2021-02-01 | COMP | 2021-02-01 | [16 empty] | 2019-05-10 | 2019-10-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | SLO |  | 182391103 | 19760.29 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117210831 | POLE_DECA_REPL - 93426 BRADLEY | 35214646 |  |  | STS-POLE_DECA_REPL - 93426 BRADLEY | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7921 | -120.8572 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB29 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103522007 | RELW OH PRI PGEA INSP REMT ESTR GO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 48.5 | 46.7 | 46.7 | 46.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117211666 | POLE_BROK_REPL - G19/VISTA DR 15/P/E BRA | 35202584 |  |  | STS-POLE_BROK_REPL - G19/VISTA DR 15/P/E | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7921 | -120.8596 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB28 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101943201 | RELW OH PRI PGEA INSP REMT ESTR BTKA FMOB FSRP TER2 | Pole |  |  | REQD | [17 empty] | 2019-05-10 | 2020-05-10 | 2020-10-19 | 2020-10-19 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | 1 | 448.5 | 446.8 | 299.8 | 299.8 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117211672 | POLE_BURN_REPL - 1/S/61882 VISTA RDBRADL | 35100223 |  |  | STS-POLE_BURN_REPL - 1/S/61882 VISTA RDB | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7929 | -120.8729 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB28 | 3891 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 101943214 | RELW OH PRI INSP CLR JPOL RESD REMT FIRE TRAF FLAG ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-10 | 2019-10-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | SLO |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117211676 | POLE_DECA_REPL - R/O 61446 VISTA RD 2/P/ | 35100225 |  |  | STS-POLE_DECA_REPL - R/O 61446 VISTA RD | ADER | ADER ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7955 | -120.8781 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB28 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101861130 | RELW OH PRI PGEA INSP REMT FIRE TER2 ESTR BTKA FMOB FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-10 | 2019-10-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | SLO |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117211682 | POLE_BROK_REPL - G19/VISTA RD(EAST SIDE) | 35214662 |  |  | STS-POLE_BROK_REPL - G19/VISTA RD(EAST S | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.7932 | -120.8717 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB28 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101861126 | RELW OH PRI PGEA INSP REMT FMOB FIRE ESTR BTKA TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117211683 | POLE_DECA_REPL - 61201 VISTA RD 1/P/N BR | 35214666 |  |  | STS-POLE_DECA_REPL - 61201 VISTA RD 1/P/ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | JointPole |  |  | 35.7974 | -120.8828 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB28 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101943213 | RELW OH PRI INSP JPOL COMM REMT FIRE ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-10 | 2020-05-10 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 19.2 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117214267 | POLE_BROK_REPL - 18/N/11235 SANATONIO LE | 35214700 |  |  | STS-POLE_BROK_REPL - 18/N/11235 SANATONI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.7888 | -120.8782 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB28 | 3891 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101861140 | OH PRI INSP JPOL REMT FIRE TRAF FLAG ESTR BTKA FMOB TER2 FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-05-11 | 2020-05-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 10.6 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117215698 | POLE_DECA_REPL - G19/VISTA DR 14/P/E8BRA | 35214725 |  |  | STS-POLE_DECA_REPL - G19/VISTA DR 14/P/E | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7924 | -120.8615 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB28 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101861118 | RELW OH PRI RESD PGEA INSP CLR REMT FIRE ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-11 | 2020-05-11 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117216769 | POLE_BURN_REPL - 75057 BRYSON-HESPERIA R | 35202611 |  |  | STS-POLE_BURN_REPL - 75057 BRYSON-HESPER | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8353 | -121.0395 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 | 32835 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Burnt | Replace |  | 101877480 | RELW OH PRI INSP CLR RESD REMT ESTR BTKA REAR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-11 | 2020-05-11 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117217677 | POLE_DECA_REPL - 2240 BRYSON-HESPERIA 1P | 35202627 |  |  | STS-POLE_DECA_REPL - 2240 BRYSON-HESPERI | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 35.8354 | -121.0468 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 15 | 15 |  |  | 0 | 15 | 15 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877485 | RELW OH PRI INSP CLR REMT ESTR BTKA FMOB TER2 FSRP | Pole | 2021-01-15 |  | COMP | 2021-01-15 | [16 empty] | 2019-05-12 | 2020-05-12 | 2020-09-26 | 2020-09-26 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | 5393.11 | 46.7 | 46.7 | 1024.7 | 1024.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117218595 | POLE_DECA_REPL - 2239 BRYSON-HESPERIA RD | 35202638 |  |  | STS-POLE_DECA_REPL - 2239 BRYSON-HESPERI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land JointPole |  |  | 35.834 | -121.0488 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 | 6619 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101946719 | RELW OH PRI INSP CLR REMT ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-12 | 2020-05-12 | 2020-09-26 | 2020-09-26 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | 1 | 46.7 | 46.7 | 1146.7 | 1146.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117218596 | POLE_DECA_REPL - 75057 BRYSON-HESPERIA R | 35214768 |  |  | STS-POLE_DECA_REPL - 75057 BRYSON-HESPER | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.836 | -121.043 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101944623 | RELW OH PRI INSP CLR REMT ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-12 | 2020-05-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117218598 | POLE_DECA_REPL - 75057 BRYSON-HESPERIA R | 35214772 |  |  | STS-POLE_DECA_REPL - 75057 BRYSON-HESPER | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8362 | -121.0414 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877483 | RELW OH PRI INSP CLR REMT ESTR GO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-12 | 2020-05-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117218770 | POLE_DECA_REPL - 2230 BRYSON-HESPERIA RD | 35202643 |  |  | STS-POLE_DECA_REPL - 2230 BRYSON-HESPERI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 35.8294 | -121.0495 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 | 32833 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877496 | RELW OH PRI INSP CLR REMT TRAF FLAG ESTR GO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-12 | 2020-05-12 | 2020-09-26 | 2020-09-26 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | 1 | 46.7 | 46.7 | 1146.7 | 1146.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117219326 | POLE_DECA_REPL - 2580 INTERLAKE RD BRADL | 35214804 |  |  | STS-POLE_DECA_REPL - 2580 INTERLAKE RD B | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 35.8359 | -121.0366 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 | 6617 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877451 | RELW OH PRI INSP CLR REMT ESTR GO FSRP TER2 REAR FMOB | Pole |  |  | REQD | [17 empty] | 2019-05-12 | 2020-05-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117219328 | POLE_DECA_REPL - A/F HESPERIA HALLBRADLE | 35202650 |  |  | STS-POLE_DECA_REPL - A/F HESPERIA HALLBR | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 35.8219 | -121.0537 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101945289 | RELW OH PRI INSP CLR RESD REMT ESTR GO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-12 | 2020-05-12 | 2020-09-24 | 2020-09-24 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | 1 |  | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117219330 | POLE_DECA_REPL - 75826 BRYSON HESPERA RD | 35214808 |  |  | STS-POLE_DECA_REPL - 75826 BRYSON HESPER | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit JointPole |  |  | 35.8234 | -121.0523 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877502 | RELW OH PRI INSP CLR JPOL REMT TRAF FLAG ESTR GO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-12 | 2020-05-12 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117219458 | POLE_DECA_REPL - 2445 BRYSON HESPERA RD | 35202653 |  |  |  | UNSC | UNSC | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Out of PEND |  |  | 35.8229 | -121.0566 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 | 6619 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48 | 48 |  |  | 0 | 48 | 48 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877506 | RELW OH PRI INSP CLR JPOL REMT ESTR GO BTKA FMOB TER2 FSRP | Pole | 2020-12-30 | 2021-02-19 | COMP | 2020-12-30 | [16 empty] | 2019-05-12 | 2020-05-12 | 2020-09-24 | 2020-09-24 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | 22850.09 |  | 0 | 1687.3 | 1687.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117222048 | POLE_DECA_REPL - 2210 BRYSON-HESPERIA RD | 35214831 |  |  | STS-POLE_DECA_REPL - 2210 BRYSON-HESPERI | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8343 | -121.0465 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 | 30029 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877487 | RELW OH PRI INSP CLR RESD REMT ESTR REAR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-13 | 2020-05-13 | 2021-05-21 | 2021-05-21 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117225804 | POLE_DECA_REPL - 75854 INTERLAKE RD 1/P/ | 35214859 |  |  | STS-POLE_DECA_REPL - 75854 INTERLAKE RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8234 | -121.0295 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 | 3413 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877847 | RELW OH PRI INSP CLR RESD REMT ESTR BTKA REAR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-13 | 2020-05-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117225973 | POLE_DECA_REPL - 75732 INTERLAKE RD 3/P/ | 35214864 |  |  |  | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Enviro |  |  | 35.8235 | -121.0306 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877848 | RELW OH PRI INSP CLR RESD REMT ESTR GO BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-13 | 2020-05-13 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117229240 | POLE_DECA_REPL - SAN ANTONIO RD-PARK ENT | 35214893 |  |  | STS-POLE_DECA_REPL - SAN ANTONIO RD-PARK | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.8267 | -120.9808 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877205 | RELW OH PRI PGEA CLR FIRE FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117229757 | POLE_DECA_REPL - SAN ANTONIO RD-PARK ENT | 35214902 |  |  | STS-POLE_DECA_REPL - SAN ANTONIO RD-PARK | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.8221 | -120.98 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877210 | RELW OH PRI PGEA INSP REMT FLAG ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117229895 | POLE_DECA_REPL - 2625 INTERLAKE BRADLEY | 35202689 |  |  | STS-POLE_DECA_REPL - 2625 INTERLAKE BRAD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 35.8062 | -120.9762 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA26 | N48 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 64.2 | 61.8 | 2.4 |  | 0 | 64.2 | 61.8 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101946282 | OH RELW PRI PGEA REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole | 2020-12-29 |  | COMP | 2020-12-29 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-09-27 | 2020-09-27 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | 29159.74 | 1.8 | 0 | 1763 | 1763 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117231475 | POLE_DECA_REPL - SAN ANTONIO LAKE/PARK E | 35214927 |  |  | STS-POLE_DECA_REPL - SAN ANTONIO LAKE/PA | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8329 | -120.9702 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA26 | 568013 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101945856 | RELW OH PRI PGEA REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-21 | 2021-05-21 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117232454 | POLE_DECA_REPL - 74743 COPPERHEAD RD 5/P | 35214947 |  |  | STS-POLE_DECA_REPL - 74743 COPPERHEAD RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8371 | -121.0535 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 | 6619 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877490 | RELW OH PRI CLR REMT ESTR FSRP FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 35.2 | 35.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117232455 | POLE_BROK_REPL - 74743 COPPERHEAD RD 4/P | 35214952 |  |  | STS-POLE_BROK_REPL - 74743 COPPERHEAD RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8376 | -121.0545 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101877491 | RELW OH PRI REMT NOAC ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 17.4 | 17.4 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117232456 | POLE_DECA_REPL - 74743 COPPEREAD RD 2/P/ | 35214957 |  |  | STS-POLE_DECA_REPL - 74743 COPPEREAD RD | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8388 | -121.0563 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877474 | RELW OH PRI CLR REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 178.2 | 178.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117232458 | POLE_DECA_REPL - 74743 COPPERHEAD RD 6/P | 35202695 |  |  | STS-POLE_DECA_REPL - 74743 COPPERHEAD RD | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Enviro |  |  | 35.8363 | -121.0517 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 48.1 | 45.7 | 2.4 |  | 0 | 48.1 | 45.7 | 2.4 |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877489 | RELW PRI OH CLR REMT ESTR FMOB TER2 PRTO FSRP | Pole | 2021-01-04 | 2020-12-30 | COMP | 2020-12-30 | [16 empty] | 2019-05-14 | 2020-05-14 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | 34404.17 | 81.6 | 81.5 | 1251.3 | 1251.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117233147 | POLE_DECA_REPL - 76725 BRYSON HESPERIA R | 35214962 |  |  | STS-POLE_DECA_REPL - 76725 BRYSON HESPER | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8169 | -121.0863 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877512 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 FSRP PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117233149 | POLE_DECA_REPL - BRYSON HIGHTS PVRD BRYS | 35214967 |  |  | STS-POLE_DECA_REPL - BRYSON HIGHTS PVRD | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8136 | -121.084 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101945873 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117233159 | POLE_BROK_REPL - 49965 SAPAGUE RD MAIL-B | 35214972 |  |  | STS-POLE_BROK_REPL - 49965 SAPAGUE RD MA | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8115 | -121.0854 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA23 | 4057 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101877518 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 129.6 | 129.6 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117235348 | POLE_DECA_REPL - 2820 NASIMENTO LAKE DR | 35214981 |  |  | STS-POLE_DECA_REPL - 2820 NASIMENTO LAKE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 35.8071 | -120.8515 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA29 | 2251 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101874428 | RELW OH REMT PRI PGEA RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 25 | 16.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117237260 | POLE_DECA_REPL - 2280 SAPAGUE RD 1/P/N/O | 35214986 |  |  | STS-POLE_DECA_REPL - 2280 SAPAGUE RD 1/P | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8099 | -121.1064 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA22 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877856 | RELW OH PRI PGEA REMT ESTR GO REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-14 | 2020-05-14 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117238257 | POLE_DECA_REPL - SAN ANTONIO LAKE/PARK E | 35214995 |  |  | STS-POLE_DECA_REPL - SAN ANTONIO LAKE/PA | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8216 | -120.9685 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA26 | 568013 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877230 | RELW OH PRI PGEA REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117238667 | POLE_DECA_REPL - SAN ANTONIO LAKE/PARK E | 35202831 |  |  | STS-POLE_DECA_REPL - SAN ANTONIO LAKE/PA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8168 | -120.9606 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877234 | RELW OH PRI PGEA REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | 1 | 65.9 | 64.1 | 1146.7 | 1146.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117238851 | POLE_DECA_REPL - SAN ANTONIO LAKE/CABIN | 35202833 |  |  | STS-POLE_DECA_REPL - SAN ANTONIO LAKE/CA | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8369 | -120.9641 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877246 | RELW OH SEC PGEA INSP REMT ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | 1 | 48.5 | 46.7 | 1146.7 | 1146.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117239180 | POLE_DECA_REPL - R/O 9990 LYNCH CANYON R | 35215000 |  |  | STS-POLE_DECA_REPL - R/O 9990 LYNCH CANY | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7962 | -121.0084 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB25 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101946533 | OH RELW PRI PGEA REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117239423 | POLE_DECA_REPL - HARRIS LAUNCH RAMP 1P/N | 35215010 |  |  | STS-POLE_DECA_REPL - HARRIS LAUNCH RAMP | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Land |  |  | 35.8124 | -120.9372 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA27 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877267 | OH PRI PGEA CLR RESD ESTR BTKA RTRN USA FMOB TER2 PRTO FSRP RELW | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | ENENG |  | 182391103 | 1 | 18 | 16.2 | [5 empty] | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117239649 | POLE_DECA_REPL - 2433 BRYSON-HESPERIA RD | 35215020 |  |  | STS-POLE_DECA_REPL - 2433 BRYSON-HESPERI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8245 | -121.0581 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 | 32827 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877744 | RELW OH PRI CLR REMT ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117239700 | POLE_DECA_REPL - HARRIS LANCH RAMPBRADLE | 35202835 |  |  | STS-POLE_DECA_REPL - HARRIS LANCH RAMPBR | APPR | APPR | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.812 | -120.9361 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA27 | 2757 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877268 | RELW OH PRI PGEA CLR RESD ESTR BTKA USA PROG FMOB TER2 PRTO FSRP | Pole |  |  | INPR | [17 empty] | 2019-05-15 | 2020-05-15 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | 1 | 95.3 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117240565 | POLE_BROK_REPL - 2610 SAN ANTONIO RD R/O | 35215030 |  |  | STS-POLE_BROK_REPL - 2610 SAN ANTONIO RD | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8343 | -120.9662 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101877259 | RELW OH SEC PGEA INSP REMT NOAC ESTR USA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117241352 | POLE_DECA_REPL - 49510 SAPAGUE RD 1/P/SE | 35215040 |  |  | STS-POLE_DECA_REPL - 49510 SAPAGUE RD 1/ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8105 | -121.0894 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101945296 | RELW OH PRI JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117241371 | POLE_DECA_REPL - 76473 BRYSON-HESPERIA R | 35105803 |  |  |  | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 35.8183 | -121.0761 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 29.8 | 29.8 |  |  | 0 | 29.8 | 29.8 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877543 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole | 2021-02-19 | 2021-02-18 | COMP | 2021-02-18 | [16 empty] | 2019-05-15 | 2019-10-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | SLO |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117241537 | POLE_DECA_REPL - 10/W/LYNCH CYN 2650BRAD | 35202841 |  |  | STS-POLE_DECA_REPL - 10/W/LYNCH CYN 2650 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.7804 | -120.9916 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB25 | N46 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101941811 | RELW OH PRI PGEA PUBL RESD TRAF ESTR BTKA FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2020-10-27 | 2020-10-27 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117241696 | POLE_DECA_REPL - 49460 SAPAQUEBRADLEY934 | 35215046 |  |  | STS-POLE_DECA_REPL - 49460 SAPAQUEBRADLE | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8126 | -121.0947 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA23 | 4057 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877533 | RELW OH BTKA PRI REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117241885 | POLE_DECA_REPL - 3/S/OAK SHORES DR LYNCH | 35202846 |  |  | STS-POLE_DECA_REPL - 3/S/OAK SHORES DR L | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.7789 | -120.9932 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB25 | 3437 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101941810 | RELW OH PRI PGEA CLR REMT ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2020-10-27 | 2020-10-27 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117242794 | POLE_DECA_REPL - 2225 BEE ROCK RD 1/P/W | 35215051 |  |  | STS-POLE_DECA_REPL - 2225 BEE ROCK RD 1/ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7613 | -120.9417 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB2624 | 5789 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101940516 | OH RELW PRI CLR RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117243031 | POLE_DECA_REPL - SAN ANTONIO RD-PARK ENT | 35215056 |  |  | STS-POLE_DECA_REPL - SAN ANTONIO RD-PARK | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8254 | -120.9747 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA26 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877218 | RELW OH PRI PGEA INSP REMT NOAC ESTR FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | 1 | 1.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117246458 | POLE_DECA_REPL - 2433 BRYSON-HESPERIA RD | 35215060 |  |  | STS-POLE_DECA_REPL - 2433 BRYSON-HESPERI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8226 | -121.0605 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877751 | RELW OH PRI FMOB CLR REMT ESTR TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117246462 | POLE_DECA_REPL - 74435 BRYSON-HESPERIA R | 35202858 |  |  | STS-POLE_DECA_REPL - 74435 BRYSON-HESPER | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8243 | -121.0623 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877757 | RELW OH PRI CLR REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2020-09-25 | 2020-09-25 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117246464 | POLE_DECA_REPL - 2433 BRYSON-HESPERIA RD | 35215064 |  |  | STS-POLE_DECA_REPL - 2433 BRYSON-HESPERI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8226 | -121.0596 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 | 6619 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877750 | RELW OH PRI CLR REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117247339 | POLE_DECA_REPL - 49307 SAPAQUE RD [HOUSE | 35215069 |  |  | STS-POLE_DECA_REPL - 49307 SAPAQUE RD [H | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8179 | -121.0947 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101945885 | RELW OH PRI PGEA JPOL RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-15 | 2020-05-15 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117248649 | POLE_BROK_REPL - R/O 6020 BEE ROCK RDBRA | 35215081 |  |  | STS-POLE_BROK_REPL - R/O 6020 BEE ROCK R | UNSE | UNSE | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.762 | -120.9477 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB2624 | 5789 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101863344 | RELW OH PRI CLR RESD REMT ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117248660 | POLE_BROK_REPL - 1/P/W/O 5900 BEE ROCK R | 35215086 |  |  | STS-POLE_BROK_REPL - 1/P/W/O 5900 BEE RO | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7618 | -120.9444 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB2624 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101940515 | RELW OH PRI CLR RESD REMT ESTR BTKA USA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | 1 | 8.8 | [7 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117249135 | POLE_BROK_REPL - OAK SHORES DR 10/P/S/1/ | 35202862 |  |  | STS-POLE_BROK_REPL - OAK SHORES DR 10/P/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.7649 | -120.9968 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB25 | 3439 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101863392 | RELW OH PRI REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2019-11-16 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-02-28 | EEI |  | 182391103 | 1 | 73.2 | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117249136 | POLE_DECA_REPL - OAK SHORES DR 10/P/S/8/ | 35215091 |  |  | STS-POLE_DECA_REPL - OAK SHORES DR 10/P/ | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7583 | -120.9877 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB2523 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101947802 | RELW OH PRI REMT ESTR GO REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117249162 | POLE_DECA_REPL - 103396007BRADLEY93426 | 35215096 |  |  | STS-POLE_DECA_REPL - 103396007BRADLEY934 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.7591 | -120.9863 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB2524 | 4651 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 103396007 | RELW OH PRI RESD TRAF ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117249210 | POLE_DECA_REPL - 78790 HESPERIA RD 4/P/E | 35215101 |  |  | STS-POLE_DECA_REPL - 78790 HESPERIA RD 4 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7905 | -121.0609 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB23 | 2827 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101944971 | RELW OH RESD PRI PGEA CLR ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117249410 | POLE_DECA_REPL - 78790 HESPERIA RD 4//E/ | 35215106 |  |  | STS-POLE_DECA_REPL - 78790 HESPERIA RD 4 | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7904 | -121.0606 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101863426 | RELW OH PRI PGEA CLR RESD ESTR GO BTKA FMOB FSRP PRTO TER2 | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117249583 | POLE_BROK_REPL - 2357 BRYSON-HESPERIA RD | 35215111 |  |  | STS-POLE_BROK_REPL - 2357 BRYSON-HESPERI | ESTS | ESTS ERDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8223 | -121.0655 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101946730 | RELW OH PRI INSP REMT FIRE NOAC ESTR GO FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117249901 | POLE_DECA_REPL - 78790 HESPERIA RD 4/P/E | 35215121 |  |  | STS-POLE_DECA_REPL - 78790 HESPERIA RD 4 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7875 | -121.0639 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101863415 | RELW OH PRI PGEA RESD ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117249951 | POLE_DECA_REPL - 52543 SMITH RD 1/P/N/OF | 35215126 |  |  | STS-POLE_DECA_REPL - 52543 SMITH RD 1/P/ | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8106 | -121.0382 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877807 | RELW OH PRI CLR RESD REMT ESTR BTKA REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117250316 | POLE_DECA_REPL - ENTERANCE TO 52543 SMIT | 35215131 |  |  | STS-POLE_DECA_REPL - ENTERANCE TO 52543 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8073 | -121.0388 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA24 | 2819 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877815 | RELW OH PRI CLR REMT ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117250323 | POLE_DECA_REPL - 8029 LYNCH CYNBRADLEY93 | 35202872 |  |  | STS-POLE_DECA_REPL - 8029 LYNCH CYNBRADL | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit JointPole |  |  | 35.781 | -120.9819 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB25 | N62 | Y | 311 |  |  |  |  | Initiated | Order Operation | POLRPL | # of Poles Replaced | 0 | 0 | 1 | 0 | 30.2 | 30.2 |  |  | 0 | 30.2 | 30.2 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101863377 | RELW OH PRI JPOL RESD REMT ESTR BTKA FMOB FSRP PRTO TER2 | Pole | 2021-01-06 |  | COMP | 2021-01-06 | [16 empty] | 2019-05-16 | 2020-05-16 | 2020-10-27 | 2020-10-27 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | 11107.11 | 108.6 | 108.5 | 1421.7 | 1421.7 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117250912 | POLE_BROK_REPL - 1/W/LYNCH CYN RD 8025 B | 35215136 |  |  | STS-POLE_BROK_REPL - 1/W/LYNCH CYN RD 80 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7815 | -120.9811 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB25 | N62 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101863376 | RELW OH PRI PGEA FIRE ESTR REAR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117251105 | POLE_DECA_REPL - 4SW/10/W/LYNCH CYN RD 2 | 35215141 |  |  | STS-POLE_DECA_REPL - 4SW/10/W/LYNCH CYN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7811 | -120.9788 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB25 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101863375 | RELW OH PRI JPOL REMT ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117252757 | POLE_DECA_REPL - 76473 BRYSON-HESPERIA R | 35215147 |  |  | STS-POLE_DECA_REPL - 76473 BRYSON-HESPER | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8185 | -121.0768 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA23 | 4057 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101877544 | RELW OH PRI INSP CLR REMT FIRE ESTR GO BTKA USA PROG FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117252758 | POLE_BROK_REPL - 76043 BRYSON-HESPERIA R | 35215152 |  |  | STS-POLE_BROK_REPL - 76043 BRYSON-HESPER | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8222 | -121.0711 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101946333 | RELW OH PRI INSP REMT ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117252796 | POLE_BROK_REPL - 76043 BRYSON-HESPERIA R | 35202880 |  |  | STS-POLE_BROK_REPL - 76043 BRYSON-HESPER | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | Permit |  |  | 35.8222 | -121.0687 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA23 | 4057 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 34.9 | 34.9 |  |  | 0 | 34.9 | 34.9 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101877536 | RELW CLR OH PRI INSP REMT FIRE ESTR USA FMOB TER2 FSRP | Pole | 2020-12-31 |  | COMP | 2020-12-31 | [16 empty] | 2019-05-16 | 2019-10-16 | 2020-09-24 | 2020-09-24 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | 17346.61 |  | 0 | 1636.3 | 1636.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117252798 | POLE_BROK_REPL - 76473 BRYSON-HESPERIABR | 35202882 |  |  | STS-POLE_BROK_REPL - 76473 BRYSON-HESPER | PEND | PEND | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Pending | JointPole |  |  | 35.8183 | -121.0757 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA23 | 4057 | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 47.2 | 44.9 | 2.3 |  | 0 | 47.2 | 44.9 | 2.3 |  | EC | E | Pole | Broken/Damaged | Replace |  | 101877545 | RELW OH PRI INSP CLR COMM REMT FIRE ESTR BTKA USA FMOB TER2 FSRP | Pole | 2021-01-25 |  | COMP | 2021-01-25 | [16 empty] | 2019-05-16 | 2020-05-16 | 2020-09-30 | 2020-09-30 | 2021 CBP Plan | 2021-01-31 | EEI |  | 182391103 | 18011.88 |  | 0 | 1100 | 1100 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117252810 | POLE_BROK_REPL - 2280 SAPAGUE RD [GATE] | 35202885 |  |  | STS-POLE_BROK_REPL - 2280 SAPAGUE RD [GA | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.8128 | -121.1027 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA22 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 18.2 | 18.2 |  |  | 0 | 18.2 | 18.2 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101877850 | OH RELW PRI INSP REMT FIRE NOAC ESTR FMOB TER2 FSRP | Pole | 2021-02-11 | 2021-02-11 | COMP | 2021-02-11 | [16 empty] | 2019-05-16 | 2020-05-16 | 2020-10-06 | 2020-10-06 | 2021 CBP Plan | 2021-02-28 | EEI |  | 182391103 | 7856.16 | 93.5 | 93.5 | 93.5 | 93.5 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117253270 | POLE_BROK_REPL - 2411 BRYSON-HESPERIA RD | 35215157 |  |  | STS-POLE_BROK_REPL - 2411 BRYSON-HESPERI | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.8175 | -121.0758 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | AA23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Broken/Damaged | Replace |  | 101877548 | RELW OH PRI INSP REMT FIRE ESTR BTKA FMOB TER2 FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-16 | 2020-05-16 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117255319 | POLE_DECA_REPL - 1/N/10/W/LYNCH CYN RDBR | 35215187 |  |  | STS-POLE_DECA_REPL - 1/N/10/W/LYNCH CYN | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | Permit |  |  | 35.783 | -120.9756 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB25 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101941821 | RELW OH PRI JPOL REMT TRAF FLAG ESTR BTKA FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-17 | 2020-05-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117256546 | POLE_DECA_REPL - 78790 HESPERIA 4/P/E/8/ | 35202897 |  |  | STS-POLE_DECA_REPL - 78790 HESPERIA 4/P/ | UNSC | UNSC SRDY | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-06-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Ready | Out of PEND |  |  | 35.7949 | -121.0595 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 35.4 | 35.4 |  |  | 0 | 35.4 | 35.4 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101944974 | RELW PRI OH INSP COMP ESTR CPGI FMOB TER2 FSRP | Pole | 2021-02-11 | 2021-02-12 | COMP | 2020-11-23 | [16 empty] | 2019-05-17 | 2019-05-24 | 2020-10-22 | 2020-10-22 | 2021 CBP Plan | 2021-01-31 | CALENG |  | 182391103 | 28177.1 | 34.8 | -553.5 | -588.3 | -588.3 |  |  |  | FRMMA/WMPMA - Electric | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117258372 | POLE_DECA_REPL - 78790 HESPERIA RD 4/P/E | 35215196 |  |  | STS-POLE_DECA_REPL - 78790 HESPERIA RD 4 | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7959 | -121.0576 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB23 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101863430 | RELW OH PRI PGEA REMT NOAC ESTR FMOB TER2 PRTO FSRP | Pole |  |  | REQD | [17 empty] | 2019-05-17 | 2020-05-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25
South | LP | BRADLEY | Templeton |  |  | OPEN | 117260150 | POLE_DECA_REPL - 6125 (GATE) BEE ROCK RD | 35215207 |  |  | STS-POLE_DECA_REPL - 6125 (GATE) BEE ROC | ESTS | ESTS | Poles | MPP |  | 07D | [5 empty] | 6 | 2021-07-15 | 2021 | 2021 |  |  | Y |  |  | 2021 | Estimating | DMD |  |  | 35.7573 | -120.9486 |  | TIER 2 | 1226 | 18239-1103, OILFIELDS | BB2624 |  | Y | 311 |  |  |  |  | Initiated | Order Operation | [6 empty] | 50 | 50 |  |  | 0 | 50 | 50 |  |  | EC | E | Pole | Decayed/Rotten | Replace |  | 101940511 | OH PRI CLR REMT ESTR GO BTKA REAR FSRP RELW FMOB TER2 PRTO | Pole |  |  | REQD | [17 empty] | 2019-05-17 | 2020-05-17 | 2021-05-31 | 2021-05-31 | 2021 CBP Plan | 2021-03-31 | EEI |  | 182391103 | [9 empty] | N | MPP File Only | N |  | Y | 2020-08-25