## Sheet1
[17 empty] | EOD | Basemap Update
Order | Order Desc | MAT | USER Status | Priority | Contractor | ADE | Status | CAT. | Notes | Rejections | Redesign | FC EOD Month | 1st ADE Submittal Forecast | 2nd Submittal (Prelim DWG) | PRELIM DWG Ready [Yes] | EDRS | APPR Approval [EOD] | Base Map Status | Expected Base Map Complete [WHSP] | Manager
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | UNSE | 30d - Mar Fasttrack |  | TBD | Iss_R0.0 - Estimating | Scope Overlap - Need rework; OH - Basemap (May 7) | [Basemap; OH] 03/03 - 2/24: [EOD PUSH] Current scope has some overlap with another PM35212441 - scope needs some rework (maybe more UG); Scope includes work along Highway, will require land basemaps (May 7) |  |  | 2021-06-30 | 2021-06-04 |  |  | 2021-06-16 | 2021-06-18 | In Progress | 2021-05-07
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | UNSE | 30d - Mar Fasttrack |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (May 7) | [Basemap; UG] 03/10- 02/24: [EOD PUSH] UG – pending basemaps (May 7) |  |  | 2021-06-30 | 2021-06-04 |  |  | 2021-06-16 | 2021-06-18 | In Progress | 2021-05-07
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | UNSE | 30d - Mar Fasttrack |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (May 7) | [Basemap; UG] 03/10 - 02/24: [EOD PUSH] UG – pending basemaps (May 7) 02/21: EST started |  |  | 2021-06-30 | 2021-06-04 |  |  | 2021-06-16 | 2021-06-18 | In Progress | 2021-05-07
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1 | 08W | UNSE | 30d - Apr Fasttrack |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (May 14) | [Basemap; UG] 03/01 Work awarded - UG, need basemaps (May 14) |  |  | 2021-06-30 | 2021-06-11 |  |  | 2021-06-23 | 2021-06-25 | In Progress | 2021-05-14
35226627 | CWSP - KESWICK 1101 LR 1586 PH 2 | 08W | UNSE | 30d - Apr Fasttrack |  |  | R0.0 - Estimating | Pre-design Sched 3/15 | [OH] 03/09: Pre-design sched Mon 3/15; Potential weather impacts. PMgr - requesting ADE assignment 03/01 Work awarded; 30day + 1wk Pre |  |  | 2021-04-30 | 2021-03-31 |  |  | 2021-04-17 | 2021-04-19
35226628 | CWSP - KESWICK 1101 LR 1586 PH 3 | 08W | UNSE | 30d - Apr Fasttrack |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (May 14) | [Basemap; UG] 03/01 Work awarded - UG, need basemaps (May 14) |  |  | 2021-06-30 | 2021-06-11 |  |  | 2021-06-23 | 2021-06-25 | In Progress | 2021-05-14
35226629 | CWSP - KESWICK 1101 LR 1586 PH 4 | 08W | UNSE | 30d - Apr Fasttrack |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (May 14) | [Basemap; UG] 03/01 Work awarded - UG, need basemaps (May 14) |  |  | 2021-06-30 | 2021-06-11 |  |  | 2021-06-23 | 2021-06-25 | In Progress | 2021-05-14
35226630 | CWSP - KESWICK 1101 LR 1586 PH 5 | 08W | UNSE | 30d - Apr Fasttrack |  |  | R0.0 - Estimating | Pre-design Sched 3/15 | [OH] 03/09: Pre-design sched Mon 3/15; Potential weather impacts. PMgr - requesting ADE assignment 03/01 Work awarded |  |  | 2021-04-30 | 2021-03-31 |  |  | 2021-04-17 | 2021-04-19
35226631 | CWSP - KESWICK 1101 LR 1586 PH 6 | 08W | UNSE | 30d - Apr Fasttrack |  |  | R0.0 - Estimating | Pre-design Sched 3/15 | [OH] 03/09: Pre-design sched Mon 3/15; Potential weather impacts. PMgr - requesting ADE assignment 03/01 Work awarded |  |  | 2021-04-30 | 2021-03-31 |  |  | 2021-04-17 | 2021-04-19
35217270 | CWSP - Konocti 1102 LR 965078 PH1 | 08W | ESTS | 30d - Mar Fasttrack |  | TBD | Iss_ON HOLD - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH]03/02: Still pending Pre-design mtg; waiting for PMgr [REDACTED]2/24: Authorization to begin project without the pre-design fieldwalk was received on 2/18/2021 from [REDACTED]. Fielding of this project was completed on 2/23/2021. Design started on 2/24/2021. Some poles are in Caltrans ROW, so a base map will be needed for the DSDD program.2/23: Status - Unable to get everybody coordinated for walkdown – EST Fielding for design02/16: EST fielding - General statement, Finding Transmission Poles in scope/design. Communicate to Trans Team; also check Highway Crossover/Caltran impacts, will require basemap/permitting. EST to note in SAP longtext |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | In Progress
35225589 | CWSP - Konocti 1102 LR 965078 PH2 | 08W | UNSE | 30d - Mar Fasttrack |  | TBD | Iss_ON HOLD - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH]03/02: Still pending Pre-design mtg; waiting for PMgr [REDACTED]; Awaiting Transmission - Engr assigned, approx 2wk turnaround.02/24: Authorization to begin project without the pre-design fieldwalk was received on 2/18/2021 from [REDACTED]. Fielding of this project was completed on 03/02: 2/23/2021. Design started on 2/24/2021. One Pole is in the Caltrans ROW, so a base map will be needed for the DSDD program.2/23: Status - Unable to get everybody coordinated for walkdown – EST Fielding for design02/16: EST fielding - General statement, Finding Transmission Poles in scope/design. Communicate to Trans Team; also check Highway Crossover/Caltran impacts, will require basemap/permitting. EST to note in SAP longtext |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | In Progress
35225591 | CWSP - Konocti 1102 LR 965078 PH3 | 08W | ESTS | 30d - Mar Fasttrack |  | TBD | R0.0 - Estimating | 1st subReady- Pending Pre-design mtg | [OH] 03/02: EST to submit (3/05); Still pending Pre-design mtg; waiting for PMgr Patrick Donavan 02/24: Authorization to begin project without the pre-design fieldwalk was received on 2/18/2021 from Brian Kirchner. Fielding of this project was completed on 2/23/2021. Design started on 2/24/2021. With caltrans working on Hwy 29 and a PGE relocation project already complete, verification needed for caltrans ROW. 2/23: Status - Unable to get everybody coordinated for walkdown – EST Fielding for design 02/16: EST fielding - General statement, Finding Transmission Poles in scope/design. Communicate to Trans Team; also check Highway Crossover/Caltran impacts, will require basemap/permitting. EST to note in SAP longtext |  |  | 2021-03-31 | 2021-03-12 |  |  | 2021-03-29 | 2021-03-31
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | 08W | UNSE | 30d - Mar Fasttrack |  | TBD | Iss_R0.0 - Estimating | RISK: Customer Issue (Legal) T-Line (3-pole) | [OH] 03/09 - 03/02: EST target sub 3/11; T-Line Pole impact RISK (3 poles); EST will reachout to Trasmission upon submittal. 02/23: [EOD PUSH] No Cal/No base map required – Customer Conflict, anticipating Legal resistance from customer. Fielding complete, ADE assigned (Eric Lucero), EST sub date TBD, 35219119 incorrect (shows as completed subdivision) 02/18: Attached circulated for a kmz denoting environmental constraints associated with this project (or both projects now that UG and OH have been split into two order numbers); 02/16: PMgr Josh Eagar; 02/17: SCOPE SESSION mtg held, Clarissa to see if sub-order [35219119] for UG was with CO or Internal?; |  |  | 2021-04-30 | 2021-03-11 |  |  | 2021-04-28 | 2021-04-30
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | 08W | UNSE | 30d - Mar Fasttrack |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (Mar 12) | [Basemap; UG] 03/09 - 03/02: EOD date on hold for basemap receipt 02/24: [EOD PUSH] UG – pending basemaps (Mar 12) |  |  | 2021-04-30 | 2021-06-01 |  |  | 2021-04-28 | 2021-04-30 | In Progress | 2021-03-12
35219272 | CWSP - MIDDLETOWN 1101481876 | 08W | ESTS | 30d - Mar Fasttrack |  | TBD | Iss_R0.0 - Estimating | Pending Scoping Mtg | [OH]03/09: Contradicting AA's; EST reached out to PMgr03/02: EST approved to start per [REDACTED]; Still pending scoping meeting02/23: [RISK EOD PUSH] EST request mtg - Waiting for scoping meeting 02/16: PMgr transferred to [REDACTED]; |  |  | 2021-04-30 | 2021-03-31 |  |  | 2021-04-14 | 2021-04-16
35219280 | CWSP - POTTER VALLEY P H 110564118 | 08W | UNSE | 30d - Mar Fasttrack |  | TBD | Iss_R0.0 - Estimating | Awaiting Scope Clarification | [OH]03/10 - 2/24: [EOD PUSH] Awaiting Scope Clarification (preferred scope in SAP has OH & UG) – [REDACTED] to assist in separating PMs |  |  | 2021-04-30 | 2021-03-31 |  |  | 2021-04-28 | 2021-04-30
35226632 | CWSP - POTTER VALLEY P H 110564118 PH 2 | 08W | UNSE | 30d - Mar Fasttrack |  | TBD | Iss_R0.0 - Estimating | Awaiting Scope Clarification | [OH]03/10 - 2/24: [EOD PUSH] Awaiting Scope Clarification (preferred scope in SAP has OH & UG) – [REDACTED] to assist in separating PMs |  |  | 2021-04-30 | 2021-03-31 |  |  | 2021-04-28 | 2021-04-30
35062374 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.1 | 08W | UNSE | 30d - Mar Fasttrack |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (Apr 12) | [Basemap; UG] 02/24: [EOD PUSH] UG – pending basemaps (4/12 bm) |  |  | 2021-05-31 | 2021-05-01 |  |  | 2021-05-29 | 2021-05-31 | In Progress | 2021-04-12
35226846 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.2 | 08W | ESTS | 30d - Mar Fasttrack |  | TBD | R0.0 - Estimating | Prelim ready - Jobwalk resched 3/12 | [OH]03/10: Job walk reschd (3/12); weather03/03 - 02/24: Ph1.2 Scope changed issued 2/24; added protection; [REDACTED]3/9 Walk |  |  | 2021-04-30 | 2021-03-26 |  |  | 2021-04-18 | 2021-04-20
35226847 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.3 | 08W | ESTS | 30d - Mar Fasttrack |  | TBD | R0.0 - Estimating | Prelim ready - Jobwalk resched 3/12 | [OH]03/10: Job walk reschd (3/12); weather03/03 - 02/24: All prelim maps; done; sub 2/25-26; need to upload to EES; [REDACTED] 3/9 Walk |  |  | 2021-04-30 | 2021-03-26 |  |  | 2021-04-18 | 2021-04-20 | N/A
35231607 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.4 | 08W | ESTS | 30d - Mar Fasttrack |  | TBD | R0.0 - Estimating | RISK - Enviro info 3/12; Prelim ready - Job walk 3/16 | [OH] 03/10 - 03/03: Job Walk 03/16; waiting on walk to submit; Enviromental rvwing water way easements (due back 3/12) 02/24:Prelim maps ready by 2/26 |  |  | 2021-04-30 | 2021-03-23 |  |  | 2021-03-31 | 2021-04-02
35231609 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.5 | 08W | ESTS | 30d - Mar Fasttrack |  | TBD | R0.0 - Estimating | Prelim ready - Jobwalk 3/16 | [OH] 03/10 - 03/03: Job Walk 3/16 02/24: Prelim maps ready by 2/26 |  |  | 2021-03-31 | 2021-03-23 |  |  | 2021-03-29 | 2021-03-31
35231608 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.6 | 08W | UNSE | 30d - Mar Fasttrack |  | TBD | R0.0 - Estimating | Repurposing to specific OH Scope | [OH] 03/11: Repurposed order number for Phase 1.6, added scope, remove 856’ of hardening in Phase 1.2. 02/24: Being cancelled ao 02/24; was not commity approved scope |  |  | 2021-04-30 | 2021-03-26 |  |  | 2021-04-18 | 2021-04-20 | In Progress | 2021-04-12
35062375 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.1 | 08W | UNSE | 30d - Mar Fasttrack |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (Apr 12) | [Basemap; UG] 02/24: [EOD PUSH] UG – pending basemaps (4/12 bm) |  |  | 2021-05-31 | 2021-05-01 |  |  | 2021-05-29 | 2021-05-31 | In Progress | 2021-04-12
35226848 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.2 | 08W | ESTS | 30d - Mar Fasttrack |  | TBD | R0.0 - Estimating | Prelims ready - Jobwalk 3/18 | [OH] 03/10: Jobwalk tentative 3/18 03/03- 02/24: (3mile) Targeting prelims ready 2/25-26; Job Walk sched (TBD) |  |  | 2021-03-31 | 2021-03-23 |  |  | 2021-03-24 | 2021-03-26
35226849 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.3 | 08W | UNSE | 30d - Mar Fasttrack |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (Apr 12) | [Basemap; UG] 02/24:[EOD PUSH] UG – pending basemaps (4/12 bm); OH piece separated |  |  | 2021-05-31 | 2021-05-01 |  |  | 2021-05-29 | 2021-05-31 | In Progress | 2021-04-12
35226850 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.4 | 08W | ESTS | 30d - Mar Fasttrack |  |  | R0.0 - Estimating | OH | [OH] 03/10: EST target sub (3/12); applying JW adjustments 03/03 - 02/24: Prelim maps ready by 2/26; Walk next Thurs 3/4 |  |  | 2021-04-30 | 2021-03-12 |  |  | 2021-04-07 | 2021-04-09
35226851 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.5 | 08W | ESTS | 30d - Mar Fasttrack |  | TBD | R0.0 - Estimating | Prelim ready - Jobwalk 3/11 | [OH] 03/10: Job walk (03/11) 03/03: Job walk (TBD) 02/24: Prelim maps ready by 2/26 |  |  | 2021-03-31 | 2021-03-23 |  |  | 2021-03-29 | 2021-03-31
35232280 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.6 | 08W | ESTS | 30d - Mar Fasttrack |  |  | R0.0 - Estimating | OH | [OH] 03/10: EST target sub (3/12); applying JW adjustments and ADE rvw revisions 03/03 - 02/24: [EOD PUSH] Walk next Thurs 3/4 |  |  | 2021-04-30 | 2021-03-12 |  |  | 2021-04-07 | 2021-04-09
35219273 | CWSP - VOLTA 110149742 | 08W | ADER | 30d - Mar Fasttrack |  |  | Iss_R1.2 - ADE Review in Progress | RISK - Transmission Poles - Resource Capped | [OH]03/10: ADE in rvw03/03: CAL submitted for 1st ADE rvw; ADE assigned [REDACTED]03/03: EST sub today; Distribution portion; Trans Portion - 90%, 8-9 Pole adjustments, 2 pole cannot make clearance req; Likely a couple Trans-pole replacement required. Sched impact TBD; Dist est. moving forward.2/24: On Track; 75% EST complete; 94 locs. Distribution portion complete. CAL doing T-pole loading calc scope as well.2/18: [EOD PUSH] Trans-Est down personnel 5 Sr Estimators 7 2 ADEs retiring over next 3-mnths. Resources exhausted/ no capacity to take on work. T-line south group as a possible option?2/17: EST advised 2-Thirds Transmission, will need a plan to drive Transmission response to meet schedule.2/16: Pre engineering fld mtg held – PMgr seeking new EOD |  |  | 2021-03-31 | 2021-03-12 |  |  | 2021-03-29 | 2021-03-31
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | R0.0 - Estimating | OH | [OH] |  |  | 2021-04-30 | 2021-04-09 |  |  | 2021-04-21 | 2021-04-23
35219589 | CWSP - WILDWOOD 11011454 | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | R0.0 - Estimating | OH | [OH] |  |  | 2021-04-30 | 2021-04-09 |  |  | 2021-04-21 | 2021-04-23
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | ESTS | 30d - Apr Fasttrack |  | TBD | R0.0 - Estimating | OH | [OH] 03/10: EST target sub (3/19) 03/03: Fielding completion this week; EST target sub (3/19) |  |  | 2021-03-31 | 2021-03-19 |  |  | 2021-03-31 | 2021-04-02
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | 08W | UNSE | 30d - TBD Fasttrack |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (TBD-May) | [Basemap; UG] Require easment rites 02/24: Not issued to Vendor;[EOD PUSH] UG – pending basemaps (TBD/mid-May bm) |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | In Progress
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | R0.0 - Estimating | OH | [OH] |  |  | 2021-04-30 | 2021-04-09 |  |  | 2021-04-21 | 2021-04-23
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (TBD) | [Basemap; UG] Need Base Map |  |  | 2021-06-30 | 2021-04-09 |  |  |  | NULL | Need
35226900 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | R0.0 - Estimating | OH | [OH] |  |  | 2021-04-30 | 2021-04-09 |  |  | 2021-04-21 | 2021-04-23
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | 08W | ADER | 30d - Mar Fasttrack |  |  | R1.2 - ADE Review in Progress | RISK - PMgr noted issues; follow up with CO | [OH]03/11: EOD needed to push; PM projects 2-3 wks03/10: ADE in rvw03/04: CAL submitted for 1st ADE rvw; ADE assigned ([REDACTED])03/03: EST submitting today2/24: On Track; 75% EST complete; 109 locs. Target submittal early next week. |  |  | 2021-03-31 | 2021-03-02 | 2021-03-04 |  | 2021-04-07 | 2021-04-09
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (TBD) | [Basemap; UG] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (TBD) | [Basemap; UG] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | R0.0 - Estimating | OH | [OH] |  |  | 2021-04-30 | 2021-04-09 |  |  |  | 2021-04-23
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (TBD) | [Basemap; UG] |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (TBD) | [Basemap; UG] |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (TBD) | [Basemap; UG] |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (TBD) | [Basemap; UG] |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (TBD) | [Basemap; UG] |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | R0.0 - Estimating | OH | [OH] |  |  | 2021-04-30 | 2021-04-09 |  |  |  | 2021-04-23
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | R0.0 - Estimating | OH | [OH] |  |  | 2021-04-30 | 2021-04-09 |  |  |  | 2021-04-23
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | R0.0 - Estimating | OH | [OH] |  |  | 2021-04-30 | 2021-04-09 |  |  |  | 2021-04-23
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | R0.0 - Estimating | OH | [OH] |  |  | 2021-04-30 | 2021-04-09 |  |  |  | 2021-04-23
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | R0.0 - Estimating | OH | [OH] |  |  | 2021-04-30 | 2021-04-09 |  |  |  | 2021-04-23
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | R0.0 - Estimating | Hybrid | [Hybrid] |  |  | 2021-04-30 | 2021-04-09 |  |  |  | 2021-04-23
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | R0.0 - Estimating | Hybrid | [Hybrid] |  |  | 2021-04-30 | 2021-04-09 |  |  |  | 2021-04-23
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (TBD) | [Basemap; UG] |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemap (TBD-hwy/Caltrans) | [Basemap; UG] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemap (TBD-hwy/Caltrans) | [Basemap; UG] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35227013 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | R0.0 - Estimating | OH | [OH] |  |  | 2021-04-30 | 2021-04-09 |  |  |  | 2021-04-23
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemap (TBD-hwy/Caltrans) | [Basemap; UG] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | R0.0 - Estimating | OH | [OH] |  |  | 2021-04-30 | 2021-04-09 |  |  |  | 2021-04-23
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH] Need Base Map |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | Hybrid | [Hybrid] Need Base Map |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | In Progress
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | Hybrid | [Hybrid] Need Base Map |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | In Progress
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | 08W | #N/A | 30d - TBD Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | OH - Need Basemap (TBD-hwy/Caltrans) | [Basemap; OH] Cal-trans-Basemap |  |  | 2021-06-30 | 2021-06-01 |  |  |  | NULL | Need
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | R0.0 - Estimating | OH | [OH] |  |  | 2021-04-30 | 2021-04-09 |  |  |  | 2021-04-23
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | #N/A | 30d - Apr Fasttrack [2] |  | TBD | Iss_R0.0 - Estimating | UG - Need Basemaps (TBD) | [Basemap; UG] Need Basemap |  |  | 2021-06-30 | 2021-04-09 |  |  |  | NULL | In Progress