## Sheet1
Order | Parent order | Priority | Link to Materials | Project Manager | Project Reporting Year | Project Name | Caltrans Dist. | Caltrans DSDD? | UG Ft. | OH Ft. | Division | ADE or Estimator | Land Surveyor | Survey Vendor | Basmap Status | ETA Prelim. Basemap COMP | Pothole Needed? | ETA Final Basemap COMP | Land Comments
35094513 |  | 1 | missing |  | 2021 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | 10 | Yes | 428 | 9423 | ST |  |  |  | COMP
35219268 |  | 1 | 35219268 |  | 2021 | CWSP - MARIPOSA 210197142 PH 1 | 10 | TBD | 0 | 8553.6 | YO |  |  |  | INPR | 2021-03-12
35226241 | 35219268 | 1 | 35219268 |  | 2021 | CWSP - MARIPOSA 210197142 PH 2 | 10 | TBD | 0 | 7920 | YO |  |  |  | INPR | 2021-03-12
35219266 |  | 1 | 35219266 |  | 2021 | CWSP - MARIPOSA 2102CB PH 1 | 10 | TBD | 0 | 13713 | YO |  |  |  | INPR | 2021-03-31
35192292 |  | 1 | 35192292 |  | 2021 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | 4 | No | 4224 | 0 | SO |  |  |  | INPR | 2021-03-19
35225594 | 35192292 | 1 | 35192292 |  | 2021 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | 4 | No | 2481.6 | 0 | SO |  |  |  | INPR | 2021-03-19
35223024 | 35192284 | 1 | missing |  | 2021 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | 4 | No | 11827.2 | 0 | NB |  |  |  | INPR | 2021-03-29
35192284 |  | 1 | 35192284 |  | 2021 | ECOP - SILVERADO 2104 - H05-LR726 | 4 | No | 10929.6 | 0 | NB |  |  |  | INPR | 2021-03-29
35223026 | 35192284 | 1 | missing |  | 2021 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | 4 | No | 9504 | 0 | NB |  |  |  | INPR | 2021-03-29
35217273 |  | 1 | 35217273 |  | 2021 | SH - UPPER LAKE 1101 CB | 1 | Yes | 0 | 5702.4 | HB |  |  |  | INPR | 2021-03-15
35217270 |  | 1 | 35217270 |  | 2021 | CWSP - KONOCTI 1102 LR 965078 PH1 | 1 | Yes | 0 | 2904 | HB | [7 empty] | Sent to [REDACTED] waiting to have scope check and approval
35145540 |  | 1 | missing |  | 2021 | PSPS - FROGTOWN 1702 - CB | 10 | Yes | 2846 | 3872 | ST |  |  |  | COMP | 2021-03-15
35217275 |  | 1 | 35217275 |  | 2021 | FRRB - PN DIVISION SANTA CRUZ COUNTY | 4 | No | 0 | 15312 | PN |  |  |  | INPR | 2021-05-15
35217274 |  | 1 | 35217274 |  | 2021 | FRRB - PN DIVISION SAN MATEO COUNTY | 4 | No | 0 | 11774.4 | PN |  |  |  | INPR | 2021-05-15
35223615 | 35191319 | 2 | 35191319 |  | 2021 | ECOP - LAS GALLINAS A 1105 PH 2 | 4 | No | 8606.4 | 0 | NB |  |  |  | INPR
35191319 |  | 2 | 35191319 |  | 2021 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | 4 | No | 6177.6 | 0 | NB |  |  |  | INPR
35219097 |  | 2 | 35219097 |  |  | CWSP - COARSEGOLD 2104CB PH 1.1 | 10 | Yes | 0 | 12473 | YO
35062376 |  | 2 | 35062376 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | 3 | No | 13358.4 | 0 | SI |  |  |  | INPR | 2021-04-19
35062374 |  | 2 | 35062374 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | 3 | No | 8236.8 | 0 | SI |  |  |  | INPR | 2021-04-12
35062375 |  | 2 | 35062375 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | 3 | No | 5860 | 0 | SI |  |  |  | INPR | 2021-04-12
35192291 |  | 2 | 35192291 |  | 2021 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | 3 | No | 2534.4 | 0 | SI |  |  |  | INPR | 2021-04-19 |  |  | ETA changed to 4/19 - county permit for lane closure 2-3 weeks out
35224712 |  | 2 | missing |  | 2021 | CWSP - BUCKS CREEK 1101 CB PH 2 | 2 | Yes | 9134.4 | 0 | NV |  |  |  | INPR | 2021-05-07 |  |  | Coordinate mobile lidar w Caltrans
35224713 |  | 2 | missing |  | 2021 | CWSP - BUCKS CREEK 1101 CB PH 3 | 2 | Yes | 9662.4 | 0 | NV |  |  |  | INPR | 2021-05-07 |  |  | Coordinate mobile lidar w Caltrans
35226849 |  | 2 | missing |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | 3 | No | 9398 | 0 | SI |  |  |  | INPR | 2021-04-12
35226853 |  | 2 | missing |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | 3 | No | 264 | 15153.6 | SI |  |  |  | INPR | 2021-04-19
35192280 |  | 2 | 35192280 |  | 2021 | ECOP - CLAYTON 2212 - H01-LR2951 | 4 | No | 7075.2 | 0 | DI |  |  |  | INPR | 2021-04-11
35226848 |  | 2 | missing |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | 3 | No | 0 | 15153 | SI
35217272 |  | 3 | 35217272 |  | 2023 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 2 | No | 1584 | 0 | NV |  |  |  | INPR
35226628 | 35217272 | 3 | 35217272 |  |  | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 2 | No | 4329.6 | 0 | NV |  |  |  | INPR
35226629 | 35217272 | 3 | 35217272 |  |  | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 2 | No | 23760 | 0 | NV |  |  |  | INPR
35226700 |  | 3 | missing |  |  | CWSP - WYANDOTTE 110932586 PH 1.2 | 3 | No | 3010 | 0 | NV |  |  |  | On hold
35217269 |  | 3 | 35217269 |  | 2023 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | 1 | Yes | 633.6 | 2642 | HB |  |  |  | RFP |  |  |  | Sent out to [REDACTED] for [REDACTED] & [REDACTED] to work togeather on
35217271 |  | 3 | 35217271 |  | 2023 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | 1 | No | 8106 | 0 | HB |  |  |  | RFP |  |  |  | Scope seems to have same area as Middletown 1102
35220895 |  | 3 | 35220895 |  |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | 1 | No | 8000 | 0 | HB |  |  |  | RFP |  |  |  | Sent Proposal to [REDACTED]
35220896 |  | 3 | 35220896 |  |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | 1 | No | 2798 | 0 | HB |  |  |  | RFP |  |  |  | Proposal sent to [REDACTED]
35227030 |  | 3 | missing |  |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | 1 | Yes | 7286 | 1784 | HB |  |  | Confirming scope |  |  |  |  | Question about where the work is located (email to PM [REDACTED]) (03/03/2021) [REDACTED]
35227031 |  | 3 | missing |  |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | 1 | Yes | 8184 | 2546 | HB |  |  | Confirming scope |  |  |  |  | project manager ([REDACTED])to confirm base map request. Email sent 03/03/2021. [REDACTED]
35227160 |  | 3 | missing |  |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | 1 | Yes | 8405 | 0 | HB |  |  | Confirming scope |  |  |  |  | project manager ([REDACTED])to confirm base map request. Email sent 03/03/2021. [REDACTED]
35227162 |  | 3 | missing |  |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | 1 | Yes | 1711 | 0 | HB |  |  | Confirming scope |  |  |  |  | project manager ([REDACTED])to confirm base map request. Email sent 03/03/2021. [REDACTED]
35227165 |  | 3 | missing |  |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | 1 | No | 9662.4 | 0 | HB
35227864 |  | 3 | missing |  |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | 1 | No | 3272 | 0 | HB
35227868 |  | 3 | missing |  |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | 1 | No | 2123 | 0 | HB | [7 empty] | No docs
35228186 |  | 3 | missing |  |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | 1 | No | 7850 | 0 | HB
35229119 |  | 3 | missing |  |  | CWSP - MIDDLETOWN 1101118494 PH 1.2 | 1 | No | 3221 | 0 | HB |  |  |  | INPR | 2021-03-12
35223037 |  | 3 | missing |  |  | PSPS - OAKHURST 1101 - OAKHURST | 10 | No | 105.6 | 0 | YO
35217267 |  |  | 35217267 |  |  | CWSP - MARIPOSA 210197142 PH 2 | 10 | No |  |  | YO
35219587 | 35217267 |  | 35217267 |  |  | CWSP - MARIPOSA 2102440236 PH2 | 10 | No |  |  | YO
35219588 | 35217267 |  | 35217267 |  |  | CWSP - MARIPOSA 2102440236 PH3 | 10 | No |  |  | YO
35219093 | [5 empty] | Not Yet Approved by WFGC | 1
35219096 | [5 empty] | Not Yet Approved by WFGC
35174501 | [5 empty] | Not Yet Approved by WFGC | 2 | [11 empty] | Question about where the work is located
35174478 | [5 empty] | Not Yet Approved by WFGC | [12 empty] | Question about where the work is located
35219098 | [5 empty] | Changed to OH Only | [7 empty] | On hold | on hold | on hold per meeting with [REDACTED] 02/24/2021
35219099 | [5 empty] | Not Yet Approved by WFGC
35222045 | [5 empty] | Changed to OH Only | 1
35192282 | [5 empty] | Changed to OH Only | 1
35192281 | [5 empty] | Changed to OH Only | 1
35174479 | [5 empty] | Not Yet Approved by WFGC
35191937 | [5 empty] | Not Yet Approved by WFGC
35219260 | [5 empty] | Changed to OH Only
35219589 | [5 empty] | Not Yet Approved by WFGC
35224321 | [5 empty] | Not Yet Approved by WFGC | 4
35223039 | [5 empty] | Not Yet Approved by WFGC | 4
35223030 | [5 empty] | Not Yet Approved by WFGC
35219276 | [5 empty] | Not Yet Approved by WFGC
35224378 | [5 empty] | Not Yet Approved by WFGC
35192290 | [5 empty] | Changed to OH Only
35026643 | [5 empty] | Changed to OH Only
35054184 | [5 empty] | Not Yet Approved by WFGC
35219281 | [5 empty] | Not Yet Approved by WFGC
35217267 | [5 empty] | Changed to OH Only
35219093 |  |  |  |  | 2021 | CWSP - TIDEWATER 210614072 PH 1.1 |  | NO | 6019 | [5 empty] | RFP |  |  |  | 3/11/2021 sent RFP to [REDACTED] @ [REDACTED]
35219096 |  |  |  |  | 2021 | CWSP - KIRKER 2104442850 PH 1.1 |  |  | 8818 | [5 empty] | RFP |  |  |  | 3/11/2021 sent RFP to [REDACTED] @ [REDACTED]
35231543 |  |  |  |  | 2021 | CWSP - TIDEWATER 210614072 PH 1.2 |  |  | 6864 | [5 empty] | RFP |  |  |  | 3/11/2021 sent RFP to [REDACTED] @ [REDACTED]
| 35174478 |  |  |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  |  | 5491 | [5 empty] | RFP
| 35174501 |  |  |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  |  | 21597 | [5 empty] | RFP |  |  |  | sent to [REDACTED] & [REDACTED] for proposal
35226857